2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AF030 to AF043
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AF030 to AF043
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AF030 to AF043
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AF030 to AF043
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 059 000 to AA 01 063 000
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 059 000 to AA 01 063 000
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 059 000 to AA 01 063 000
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with location AE 001 to AE 020 type 4 and C using Cycle Count List # 780/782/781
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AE 001 to AE 020 Cycle /Count type 4 and C at the Aguirre warehouse to start the cycle counts.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 783 localization AE 001 to AE 020
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location. localization AE 001 to AE 020 list #780/781/782
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 748 and 749 locations AI023 to AI031
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 |  | 152 | 418 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AI023 to AI031 Cycle Count List # 786.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AI023 to AI031
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #792, 793 and 794 from locations AI023 to AI031 for a total of 223 units.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Coordination & Discussion of Procore Analytics Program with Lauren Wells (DCMC)-Andres Concepcion (DCMC)-Raissa Borges (DCMC)-Rafael Pabon (CDM)-Luis Roman (DCMC)
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Incorporate Observation SOP V.1.0 for all BESS & Peakers Projects/ Costa Sur BESS RFP Data Review & Prepare prior to Uploading/
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review and editing of Power Point Presentation for the upcoming Procore Kick-off Meeting for the Cambalache Project.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review and editing of SOP draft versions for publishing: taking out main core tool's SOPs for internal and external users.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform preliminary review on discusses documents at the Procore Weekly Meeting held earlier at 2:00pm: pending SOPs on corrections and/or review, drawings' meeting coordination with Design Team (S&L) and overall Project Management documentation.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Cambalache Project Procore Kick-off Internal Discussion with Lauren Wells (Lemoine), and the project field team Andres Concepcion, Luis Damudt, Luis Duque, Jorge Mercado and Carlos De Jesus (all DCMC). Reviewing PP presentation with the team for upcoming Procore Kick-off Meeting with contractor for Cambalache Project.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Meeting to discuss the platform execution and users' interaction with the project management tools. Hosted by Franklyn Colmenares (CSA), team staff overview weekly occurrences from the Procore platform.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Q&A Session with Lauren Wells (DCMC): open office hours for users to join a Teams Channel and discuss ongoing issues and inquiries from the Procore Platform.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ PW#9510 - Working on the with Pre-Intervention Review for CDM Smith TO01_293410-13_2025. Continue reviewing narratives for this invoice. The invoice has a total of 325 lines. Review lines and identify missing information or aligned with SOW lines.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 - TESLA_Contract 106761 review contract information regarding schedule that need to be provided by vendor prior to delivery (section 3.11).
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Preparing PowerPoint presentation for today's internal meeting. Update deltas for this week and send document to D'Alexzander González (DCMC) for Genera meeting on Tuesday.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 149 | 37.25 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - PMO Contract - Meeting to discuss updates on Tesla project regarding contractual issues. In this internal DCMC meeting participated Frances Vallejo, Rafael Calderón, Glorimel Torrado, and Sheila Torres.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Continue meeting with Sheila Torres (DCMC) and Rafael Calderón (DCMC) to finish the discussion on Tesla contract. In this contract we agree that a formal request order should be executed to have all the payment changes clear. Also, in this meeting we discuss about Procore change order format.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ PW#9510 - Working on the with Pre-Intervention Review for CDM Smith TO01_293410-13_2025. Continue reviewing narratives for this invoice. The invoice has a total of 325 lines. Review lines and identify missing information or aligned with SOW lines.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.75 |  | 149 | 111.75 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_ PW#9510 - Working on the with Pre-Intervention Review for CDM Smith TO01_293410-13_2025. Continue reviewing narratives for this invoice. Review lines and identify missing information or aligned with SOW lines. Reviewing contract management lines.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA in preparation for today's team meeting.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Tesla PMO meeting to discuss change orders for payments and equipment. In this meeting participants from Tesla Elizabeth Arentsen, Allin Luong and Michael Grabstein. Also participated Franklyn Colmenares (CDM) and Rafael Calderón (DCMC).
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Anneilia Holton, Mark Merritt, Rafael Calderón, Sheila Torres-Sterling, and Eisha Mercader: Marc Maceira (HONRA LLC)and Shellsea Maysonet (SM Consulting); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 139 | 34.75 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Coordinate a meeting with Jorge Bracero from the Genera PR team and Jean Pierre Menay from DCMC to manage any community collaborative agreement with the pharmaceutical companies near the Cambalache site.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Work on the BESS and Peakers newsletter requesting information and editing the content about the progress of the project.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Frances Vallejo from DCMC Partners about the status of Bess and Peakers project.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.75 |  | 139 | 382.25 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting with Jorge Bracero from the Genera team about the outcomes of the community outreach project related to the Bess and Peakers project.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Work on creating a list of entrepreneurs in the Vega Baja area in order to coordinate meetings with them regarding the BESS and Peakers project.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting with Jean Pierre Menay from DCMC Partners to indicate my efforts related to the Local Environmental Emergency Response Committee – Arecibo to support them in managing any community collaborative agreement with the pharmaceutical companies surrounding the Cambalache site.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11 ¦ DR4339 – Weekly Corporate Affairs Meeting with the Genera PR team: Rafael Rodriguez Ema, Jorge Bracero, and Ivan Baez.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued translation of Volume 3, Chapter 5 (Sections 5.11 to 5.13) of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The translation follows the established formatting requirements, maintaining the original structure and style to ensure consistency, technical precision, and alignment with applicable standards. Accurate terminology has been applied, with carefully adapted language to preserve the original intent and all formal elements, including section headings, numbering, and references.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued the translation of Volume 3, Chapter 6 (Sections 6.1 to 6.11) of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The work complies with the established formatting guidelines, maintaining the original structure and style to ensure consistency, technical accuracy, and alignment with applicable standards. Precise terminology was used throughout, and the language was thoughtfully adapted to reflect the original intent while preserving all formal elements, including section titles, numbering, and references.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Ongoing translation of Volume 3, Chapter 5 (Sections 5.1 to 5.10) of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The work adheres to the established formatting guidelines, preserving the original structure and style to ensure consistency, technical accuracy, and compliance with applicable standards. Terminology is used precisely, and the language has been carefully adapted to maintain the original meaning, including all formal elements such as section titles, numbering, and references.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Completed review BESS Pond, Culvert and Pump Inlet plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on resources projections template considering daily hours for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on resources projections template considering daily hours for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on initial pending process considering Procore, guides and contractual file for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on Teams meeting related to Review RGE presentation/training agenda considering PROCORE in charge, authorization and format instructions worked first as intern with Lauren Wells (Lemoine), Luis Roman, Luis Duque and Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project documentation (Genera BESS State of Design and Milestone Schedule). Excavation and fill compacting drawings. Foundations and BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project documentation (Genera BESS State of Design and Milestone Schedule) Demolition and Dewatering system drawings. BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review BESS Pond, Culvert and Pump Inlet plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Review RGE presentation/training agenda meeting with Andres Concepcion (DCMC) and Lauren Well (Procore) for the 4339_9510 BESS_Cambalache project.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Continue review BESS Pond, Culvert and Pump Inlet plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Establishing a new reporting framework to present project status and updates in a more frequent and structured manner, facilitating improved client comprehension of progress.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Procore Weekly Q&A Session meeting with Lauren Wells from Lemoine to help answer any questions regarding Procore software.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 122 | 427 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Creating a new report template to provide project status updates more frequently and in a revised format, enhancing the client's ability to visualize project progress effectively.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Total Distance 64.0 miles
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 114.8 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Travel from Home Office Luquillo to Central Aguirre (17.951690, -66.229675) to Jobos Gas Turbine (17.961105, -66.140130) to Home Office Luquillo. Purpose, Central Aguirre & Jobos Gas Turbine Plant, Topics discussed, walk through Project Site, discussed scope of work, project needs, construction Office Trailers (DCMC) areas & Subcontractor Laydown & Office Trailers Area. Measured areas. Took Pictures and review utilities facilities for the Office Trailer's. Attendees Central Aguirre, Jose M Lopez (DCMC), Abraham Velazquez (DCMC) & Harry Del Valle (DCMC). Attendees Jobos Gas Turbine Plant Francisco Vazquez (Genera), Jose M Lopez (DCMC), Abraham Velazquez (DCMC) & Harry Del Valle (DCMC). TOTAL MILEAGE 164 miles
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.42 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled back home in Guaynabo from Central Palo Seco where I conducted an operational reviewed with Mr. Giovanni Taffanelli from DCMC. The visit focused on providing on-site support for warehouse operations, assessing the effectiveness of inventory control protocols, and identifying inefficiencies in workflow execution. Activities included evaluating compliance with established inventory management standards and aligning operational tasks with project scope.
2025-05-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 7.91 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- traveled directly from Guaynabo to Central Palo Seco to conduct an operational review with Mr. Giovanni Taffanelli from DCMC. The visit focused on providing on-site support for warehouse operations, assessing the effectiveness of inventory control protocols, and identifying inefficiencies in workflow execution. Activities included evaluating compliance with established inventory management standards and aligning operational tasks with project scope.
2025-05-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Project update discussions, status of remaining activities, plan activities for the weekend and Holiday work for next Monday with Jaime Pesquera - DCMC Partners.
2025-05-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 24 Homeca make cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the work performed. Worked on house demolition on site. HOMECA is retrieving concrete to reduce waste.
2025-05-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling areas Day 24. Homeca continued making cuts on the steel chimney to prepare for rigging plan which should ensure the safety and success of the work performed. Continue on house demolition on site and retrieving concrete.
2025-05-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Removed beams and metals on a 80CY open truck towards recycling Facility on Caguas. Continue power wash on G-1 and G1 2 to remove dust and dirt on platform.
2025-05-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Uploading to Procore app documents such as Job hazard analysis crucial for preventing workplace injuries by identifying and mitigating hazards and photos requested from the contractor.
2025-05-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Removed beams and metals on a 80CY open truck towards recycling Facility on Caguas.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 1326 | 1326 | 1326 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Airfare (Basic Economy) for Foster Veazey's trip from Mobile, AL to San Juan, PR.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 273.59 | 273.59 | 273.59 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Hotel Lodging for Foster Veazey for 1 night in San Juan, PR ($234 lodging, $22.59 Taxes, $17 fees).
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 worked on internal workflow reviewing notes and questions from the GC walkthrough.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in PMO report meeting, discussed schedule updates, procurement, and reviewed project statuses. Frances Vallejo Rosich DCMC German Nunez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met new DCMC Team Members Carlos Rodriguez, Rafael Barrero and Gabriel Morales. Provided Project update and status for Costa Sur and Yabucoa respectively for their assignments.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Program Met with Harry del Valle DCMC to review trailer delivery schedule for Costa Sur, Cambalache, Aguirre and Yabucoa. Also discussed QA Program development.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Caught up with e-mails correspondence for BESS Program and prepared daily agenda.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Program updated biweekly PMO Progress Report across all sites.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Review proposal from Homeca Recycling for Phase II demolition and responded to it following the contractual option pricing stipulated in the current contract.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur Continued project update and status for the Demolition & Site Construction with Carlos Rodriguez and Rafael Barrero - DCMC. Discuss Scope of Work, current construction schedule. and Site Temporary Facilitries.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Biweekly Progress Update Meeting across BESS, Peakers, Critical Components, Inventory, Procore, Procurement, Cost and Schedule. Participants from CDM Smith, CSA Group, Genera and DCMC Partners.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Met with Jose Lopez - DCMC to get project update status and remaining demolition activities pending.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Weekly internal meeting with DCMC Construction Team - Review Pre-Construction activities and RFC Contract Status with RGE. Andres Concepcion, Luis Damudt, Luis Duque, Jorge Mercado and Gilberto Sucre (DCMC)
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja RFC meeting with ARG Ceres - Review tracker and main pending items - PreCast Value Engineering, Lifting Plan Sequencing and Crane Location, revised pricing and schedule with VE's approval. Final T & C's meeting. Participants ARG Ceres, Sargent & Lundy, CDM Smith, CSA Group adn DCMC Partners.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Contractors Weekly Site Meeting with Homeca Recyling, CDM Smith and DCMC Partners. Diesel Transfer will have to take place after current completion date of May 31st due to Crane interference at Palo Seco.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Reviewed Genera's response from Francisco Feliu to ARG Ceres Legal Counsel on the contract T & C's for the Project
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre RFC Meeting with RGE. Reviewed tracker with main outstanding items need revised based schedule, accelerated schedule and pricing update. RGE to submit Technical Aplicable Specifications. Also discussed status of Cambalache and the need to submit VE Structural Steel to complete the contractual SOW and provide design detail for Sargent & Lundy to provide IFC Documents. RGE, Sargent & Lundy, CDM Smith, CSA Group and DCMC Partners participated.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore support correspondences for meeting minutes.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training tracker to present during Financial alignment call tomorrow.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordinating meeting for the week for Procore items.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on PMO Reporting for Procore for Raissa Borges (DCMC) to use in her master report.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the EHS documehtation by Vega Baja Genera Site. Meeting by Vega Baja Project Status, Jose Lopez, Jaiame Pesquera, Gilberto Soto by (DCMC), Carirma Sanchez (HOMECA), Enrique Laya (CDMSMITH). Coordinate the trailers offices and toilet facility for Cambalache, Costa Sur, Yabucoa and Aguire Genera Site.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Make a EHS Genera training to employees Esteban Mercado, Leonardo Morales, Jose Abreu, Francisco Camacho, Duenas Trailers employees to Trailers Offices Installers.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the EHS documentation by Vega Baja Genera Site. Review documentation by EHS for Cambalache Site. Coordinate with Rod Rodders toilets for Cambalache site. Training Rafael Barrera, Carlos Rodriguez and Gabriel Morales (DCMC) about Genera EHS.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with new hires for the Costa Sur and Yabucoa sites (Rafael Barrera, Carlos Rodriguez and Gabriel Morales). Offered a presentation to the new employees and explained the peaker and BESS project. Participants: Gilberto Sucre (DCMC).
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Attended meeting to discuss trailer installation at coordination at Costa Sur with Harry del Valle (DCMC) and Gilberto Sucre (DCMC)
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Genera communication team to discuss communication plans for each site. Participants: Jorge Bracero (Genera) and Paola Arroyo (DCMC).
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Reporting meeting with support team to discuss one pager status report per department and next steps regarding monthly report for Genera. Participants: Sheila Torres, Rafael Calderon, Gilberto Sucre, Raissa Borges, Paola Arroyo, Jean Pierre Menay, Abraham Velazquez (DCMC), Rafael Pabon (CDM) and Carlos Palomares (CDM)
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4899 - BESS Civil and Construction at Costa Sur - Began assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 15 supporting documents. Initiated the process of completing the mandatory appendices, beginning with Appendix A. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Marc Maceira (HONRA LLC). Subcontractors: Shellsea Maysonet, Johanna Díaz (SM Consulting), Carlos González and Ginnell Torres (Integrum)
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - PMO meeting preparation - Updated legal and procurement update slides for the weekly PMO reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any legal or compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria -Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. Contributed updates on assigned tasks, reviewed performance metrics, and participated in discussions aimed at streamlining reporting processes and enhancing cross-functional coordination. Collaborated with team members to identify action items and align on priorities for the upcoming reporting cycle. DCMC: Frances Vallejo, Gilberto Sucre, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Browne, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria -Discussed opportunities for improving the procurement process with Franklyn Colmenares (CDM Smith) in preparation for the upcoming FOMB package meeting with the Genera Regulatory, Finance and Procurement teams. Focused on identifying key pain points and potential enhancements to strengthen organization, compliance, and alignment with FOMB submission requirements.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Reviewed V1 PW -11855-FAASt Generation Fleet Project -Peakers Check-In Project Tracker (2025-05-12) as shared by Rafael Pabon (CDM Smith) and provided input.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.75 |  | 184 | 690 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Began reviewing feedback from Alejandro Maymi of Genera regarding the Genera Connect Timesheet, specifically focusing on evaluating the user experience for selecting Projects and Tasks as a prerequisite for submitting time entries. Additionally, continued refining the sourcing integration Scope of Work by detailing the use cases discussed with Ginell Torres and Saul Falcon from DCMC, clearly outlining the objective and expected process flow for each scenario to support comprehensive and actionable scope development.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 |  | 184 | 598 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated the weekly project slide with the latest developments for presentation at the Genera PR update meeting. Met with Eisha Mercader DCMC to discuss next steps for the Genera Connect Timesheets, including planning the import of historical timesheet data to ensure accurate reporting. Distributed a communication to all Genera PR HQ employees announcing the availability of the Genera Connect Timesheet platform for time entry, in line with the established communication plan. Provided project updates during the weekly Genera PR meeting, attended by Maria Sanchez and Alejandro Maymi from Genera PR, and Rafael Calderon, Jose Ralat, Mark Merritt, D'Alexzander Gonzalez, and Eisha Mercader from DCMC. Also held discussions with Ginell Torres and Saul Falcon from DCMC to further refine the sourcing integration Scope of Work, focusing on current procurement processes and associated documentation requirements.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Removed Metal Rods from the concrete covered manhole with concrete.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue learning and corrections at the Safety Manual at Genera for word corrections and a better adaptation to the understanding of word usage in Puerto Rico
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11-Nonbillable ¦ DR 4339 - Hurricane Maria Continue works in the review at the Safety Manual at Genera for word corrections and a better adaptation to the understanding of word usage in Puerto Rico
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS - Dismantling, Decommissioning and demolition works planning for phase II. Homeca Recycling should submit an LED abatement removal certification to ensure they can safely handle and remove lead hazards, protecting workers and staff from lead exposure.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11—Project Management ¦ DR 4339—Hurricane Maria—VEGA BAJA BESS - Weekly look-ahead schedule review and discussion with the DCMC team, Gilberto Soto, Jaime Pesquera, and Gilberto Sucre: Coordination and logistics for Homeca's week work plan to ensure labor is performed in a way that minimizes disruptions, and every aspect of the project is executed efficiently.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination with Costa Sur Plant Manager Miguel Beauchamp (Genera) and with Danny Duenas (Duenas Trailers) the Office Trailer Delivery for tomorrow 5/28/2025 in Costa Sur (BESS Project). Coordinate with Jean Pierre Menay (DCMC) the security plan on the premise.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Genera Safety Training by Jean Pierre Menay (DCMC). Topics: Emergency Plan, PPE, verified work areas before, during and after works, falling protection, storage of welding cylinders, ensure all employees use the protection equipment, Inspections of work tools, cell phones are prohibited during work, and following OSHA rules. Attendees - Duenas Trailer Personnel.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination with Cambalache Plant Manager Herminio Arroyo (Genera) and with Danny Duenas (Duenas Trailers) the Office Trailer Delivery for Thursday 5/29/2025 in Cambalache (BESS Project). Coordinate with Jean Pierre Menay (DCMC) the security plan on the premise.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work continues to create safety guidelines for safety in accordance with OSHA Subpart I, 1926.300 Hand and Power Tools for the BESS CAMBALACHE project.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Weekly Internal Meeting with DCMC Cambalache team, Andres Concepcion, Luis Duque and Luis Damudt to ensure team understand their roles and responsibilities, and are aware of the site-specific conditions, safety protocols, and project schedule.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Work is being done to create safety guidelines and recognize global harmonization systems for risk communication involving chemical agents for the BESS CAMBALACHE project.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Work is being done to create safety guidelines for safety according to OSHA Subpart I, 1926.300 Hand and Power Tools for the BESS CAMBALACHE project.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Attended S & L / CDM Smith Weekly BESS Drawings Meeting with Robert Molner, Enrique Laya, Mike Kuscinski and Franklyn Colmenares to review Bess program Design progress.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Luis Roman (DCMC) to review Procore submittal workflow, RFIs, Meetings and Drawings and process to ensure correct implementation during project.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated and planned Cambalache weekly plan and meeting agenda to be discussed on Cambalache Site Team Weekly meeting. (DCMC: Luis Damudt, Gilberto Sucre, Carlos De Jesus, Jorge Mercado, Luis Duque)
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Luis Duque and Luis Damudt (DCMC) to discuss the project RFI and Submittal tracking and follow up process.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated and, reviewed and generated emails regarding Cambalache action items. Site Readiness coordination with Franklin Colmenares. Sent survey report to RG Engineering (Jose Segarra), Completed Procore coordination meetings with Lauren Wells (DCMC). Office Trailer coordination with Harry Del Valle (DCMC).
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Cambalache site team weekly meeting to discuss weekly plan and action items with DCMC Gilberto Sucre, Luis Damudt, Jorge Mercado, Carlos De Jesus and Luis Duque.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Procore RFIs and Submittals that were responded and sent by contractor RG Engineering and review that all information is accurate.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- participated in a virtual coordination meeting via Microsoft Teams with Ms. Maria Sanchez from Genera PR, and DCMC personnel to review the status of ongoing project deliverables. The discussion focused on evaluating weekly progress, addressing current challenges, and aligning next steps to ensure continuity and adherence to project timelines.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted inventory operations planning and data reviewed to support upcoming cycle count activities at the Aguirre warehouse, in coordination with Mr. Juan Vallejo of DCMC. The scope of work included validating item locations, updating inventory records, and coordinating resource allocation to improve procedural accuracy and ensure operational readiness for schedule counts. Today's efforts were specifically focused on locations UA 001 to UA 022.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Aguirre warehouse, a consolidated inventory report was prepared for Mr. Anthony Vega of Genera PR. integrating data from all warehouse's locations. The report included cataloged item count, unit quantities, cost analysis, and variance summaries. It also featured stock thresholds evaluation and percentage-based performance metrics to provide insight into the operational efficiency of each site. Inventory locations analyzed range from UA 001 to UA 022, AK 002 to AK 006, AG 042 to AG 045, BH 001 to BH 008, BI 001 to BI 008, CT 001, GD 001 to GD 006.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed inventory verification at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. Activities included auditing item locations, validating part numbers and descriptions, addressing stock quantities, and cross-referencing physical count with system records. The initiative focused on enhancing inventory control by reinforcing compliance with asset management protocols and improving the accuracy and transparency of inventory data.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued execution of cycle count activities for designated inventory locations, specifically covering UA 001 through UA 022. The objective was to validate and reconcile physical inventory with system records, ensuring data integrity, operational consistency, and compliance with procedural operational standards.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a a coordination meeting with Juan Vallejo and Giovanni Taffanelli of DCMC, along with key warehouse personnel from DCMC. The meeting primarily focused on evaluating data integrity within the inventory management system, identifying root causes of item misclassifications, and outlining corrective measures to improve tracking accuracy and system synchronization. Additionally, the team reviewed escalation protocols for unresolved variances and discussed enhancements to documentation practices to support audit readiness and operational transparency.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a variance analysis at the Aguirre warehouse, to identify inventory discrepancies and evaluate inconsistencies affecting stock accuracy. The objective was to enhance inventory control by resolving anomalies, ensuring the integrity of inventory data, and reinforcing process efficiency. This effort directly supports the implementation of corrective measures and contributes to the ongoing advancement of asset management practices.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed schedule cycle counts for designated inventory zones as part of the broader effort to improve inventory accuracy control. The task centered on reconciling physical inventory with system data to detect and resolve discrepancies. Inventory locations reviewed during this session range from UA 001 to UA 022.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information on NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status. Batch 1
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Complete the Bi-Weekly Report Template in preparation for the PMO reporting meeting. This task involved compiling updates on key project activities, identifying recent accomplishments and ongoing challenges, and summarizing financial and operational status. The finalized report supports leadership oversight and ensures consistent tracking of project milestones and deliverables.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DCMC- Revision Proyectos Federales Status meeting with participation from DCMC: Pedro Cabrera, D'Alexzander Gonzaléz, and Roberto Bosch; from MSC Shellsea Maysonet;, to discuss priorities and deliverables, status updates, identify next steps for projects under Federal Grant.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with Cynthia Ortiz DCMC to review the status of active RFP of current federal projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC and Lemoine: Abraham Velazquez, Frances Vallejo, Gilberto Sucre, Lauren Wells, Rafael Calderon, Pedro Cabrera, Sheila Torres, Raissa Borges, Paola Arroyo, Paul Browne and (CDM Smith), Carlos Palomares, and Franklyn Colmenares, Meeting with DCMC to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Alejandro Maymi, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Continue to Review and edit Preliminary DCMC Partners Cambalache Power Plant BESS Program Quality Control Plan, Division Concrete. Division 4 – Masonry
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting Cambalache update with, Andres Concepcion, and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache Weekly Internal Meeting discussion Comments at Cambalache updated Schedule in Procurement with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Partners Cambalache Power Plant BESS Program Quality Control Plan, Division Concrete Topic Cast in Place Concrete.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Partners Cambalache Power Plant BESS Program Quality Control Plan, Division Concrete.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Continue to Review and edit Preliminary DCMC Partners Cambalache Power Plant BESS Program Quality Control Plan, Division Concrete Topics Submittals, Material, Requirements for Concrete Strength.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Continued Vega Baja Contractor Homeca Recyclers field supervision with Gilberto Soto (DCMC). Overview to and frequent briefings ensure all project participants have a clear understanding of the expectations and requirements and understand their participation in the project’s execution and with safety in mind.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Safety briefing conducted by Homeca Recyclers and Gilberto Soto (DCMC) was present. Had Meeting with Carirma Sanchez (HOMECA ) to discuss the weekly work schedule.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Continued Vega Baja Contractor Homeca Recyclers for this time, I continued field supervision with Gilberto Soto (DCMC). I kept overviewing and continued the frequent briefings to ensure all project participants had a clear understanding of the expectations and requirements and understood their participation in the project’s execution and with safety in mind.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Removed beams and metals, continue demolition of the concrete curb from the site.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Removed Metal Rods from the concrete covered manhole with concrete. Oil Energy vacuum truck arrived to empty dirty water on containers and clean diesel lines for demolition.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 - Hurricane Maria PMO Reporting Meeting - DCMC PMO staff meeting to be discussed specific need of reporting based on project execution development per area. Working on PPT presentation template and review updates from BESS and Peakers project. DCMC Participants Frances Vallejo, Raissa Borges, Glorimel Torrado, Gilberto Sucre, Sheila Torres, Abraham Velazquez, Eduardo Rivera and Paul Brown.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare folders for Invoice Reconciliation special task, organize folder structure and start working on CDM invoices. For this task I open each invoice folder from 2024-2025, verify the final excel spreadsheet, match it with the excel invoice list and create a copy to the reconciliation folder. I started today working on CDM.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC & Genera- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander Gonzalez, Esther Rohena, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz, Christian Cruz, Carlos Gonzalez) Marc Maceira (HONRA LLC) and SM Consulting Shellsea Maysonet, and from Genera (Alejandro Maymi and Maria Sanchez)
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Continuing the investigation of discrepancies found in Recount Lists #811, 812, 813 and 814 for locations AK002 to AK006 and AG042 to AG045, totaling 1246 pieces.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GD001 to GD006
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GD001 to GD006
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GD001 to GD006
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GD001 to GD006
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GD001 to GD006
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BH 00 001 to BH 00 008 000 ; BI 00 001 000 to BI 00 001 000 to BI 00 008 ; CT 00 001 000
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.75 |  | 152 | 570 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and upload in the Asset Suite system. Today we are working with locations BH 00 001 to BH 00 008 000 ; BI 00 001 000 to BI 00 001 000 to BI 00 008 ; CT 00 001 000
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting recounts in accordance with the Asset Suite system. Today we are working with locations BH 00 001 to BH 00 008 000 ; BI 00 001 000 to BI 00 001 000 to BI 00 008 ; CT 00 001 000
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BH 00 001 to BH 00 008 000 ; BI 00 001 000 to BI 00 001 000 to BI 00 008 ; CT 00 001 000
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AU 001 to AU 022.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria at the Aguirre warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts list # 802/808/809 locations AU 001 to AU 022.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AU 001 to AU 022 at the Aguirre warehouse to start the cycle counts.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AU 001 to AU 022 using Cycle Count List # 799/800
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AU 001 to AU 022 using Cycle Count List # 795/798/799
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #811, 812, 813 and 814 locations AK002 to AK006 and AG042 to AG045.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AK002 to AK006 and AG042 to AG045.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations AK002 to AK006 and AG042 to AG045 using Cycle Count List #807 and 810.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations AK002 to AK006 and AG042 to AG045 to start the cycle counts.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Document Control - Data Management - Coordination with Rafael Pabon (CDM) Siemens Equipment Data Review & Process Data/ Review & Verify all BESS Projects for any updated Data to process /Review & Verify all PEAKERS Projects for any updated Data to process/Costa Sur Peakers Siemens PID Data for Review & Process
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management / Costa Sur Peakers Review_Process_Incorporate Siemens Systems Data Documents
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Catch-up on Procore activity and projections for ongoing week: core tools execution and proper documentation on the Documents Tool. Review Meetings distribution and the Accepted/Rejected Feature for Meeting Minutes commentaries from write-off.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Andres Concepcion and Luis Duque (DCMC) to discuss the internal execution of project team with the Meetings Tool for Follow-Up meetings, converting agenda to minutes, and the inclusion of approval/rejection and commentaries field for Minutes Approval from users.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Manage contractual agreement and documentation to comply with client requirements as for Owner's Representative obligations.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Submittals and RFIs for Aguirre Plant project: QA/QC of information being uploaded or shared through wrong project management channels or tools.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare EHSS packages for CPA. Invoices sent to Manuely Concepción and Franklyn Colmenares (CDM Smith) to create CPA. Pre intervention process is complete for: EHSS_TO6_11826_April2025, EHSS_TO7_11835_April2025 EHSS_TO8_11836_April2025 and EHSS_TO8_11838_April2025.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - PW#9510 - Working on the with Pre-Intervention Review for CDM Smith TO01_293410-13_2025. Continue reviewing narratives for this invoice. Review lines and identify missing information or aligned with SOW lines. Review project management lines.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 149 | 186.25 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - PMO Reporting preparation for meeting. Include Homeca and RGE in the report (PMO presentation) and update risks and change orders by plants for Tesla, Homeca, RGE and Siemens.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.25 |  | 149 | 335.25 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reviewing and editing final invoice for Environmental Health Safety Services Inc. Manuely Concepción from CDM Smith send us the Tax ID, I edited the 4 invoices and include that number. Also, complete the merge of the 4 invoices with schedule of values signed. This final merge was sent to Manuely Concepción (CDM) for review. I prepare final packages for all invoices and send them for Jesús Cintrón (Genera) signature.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review Franklyn Colmenares (CDM) requesting clarification on CPA request for TO9. I review TO6 , TO7, TO8, and TO9 total amount on Pre Intervention tracker and verify with the final documents. Identify mistake on TO9 document saved name (duplicating TO6). Prepare TO9 correction and resend it for signature to Jesús Cintrón (Genera).
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - PMO Reporting meeting - Recurrent meeting to discuss project management for Bess and Peakers. In this meeting participates from DCMC Frances Vallejo, Rafael Calderón, Glorimel Torrado, Paul Browne, Eduardo Rivera Jordán, Raissa Borges, Lauren Wells and others. We discussed information and reviewed the best way to present the dashboard to Genera team showing progress and issue on projects.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.75 |  | 149 | 111.75 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 -Genera and DCMC Weekly Meeting with participation from DCMC: Mark Merritt, José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, and Glorimel Torrado, and Marc Maceira (HONRA LLC). Also, Shellsea Maysonet (SM Consulting); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Reporting Meeting with DCMC Partners Team: Frances Vallejo Rosich, Eduardo Rivera Jordan, Jean Pierre Menay, Lauren Wells, Rafael Calderon, Gilberto Sucre, Paul Browne, Foster Veazey, Sheila Torres Sterling, Raissa Borges Almodovar, Abraham Velazquez, Glorimel Torrado and Pedro Cabrera. In the meeting was the CDM Smith team: Carlos Palomares.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Update the Vega Baja Community Relations of Bees and Peakers with the Genera team, Jorge Bracero
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Prepare a meeting with the mayor of Vega Baja, Marcos Cruz, to discuss matters related to the Bess project in Vega Baja. This preparation included coordinating with Genera printed materials about the Bess project to provide during our meeting.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 meeting with Jean Pierre Menay, from the DCMC Partners team, with the purpose of preparing for the meeting with the mayor of Vega Baja, Marcos Cruz, to discuss issues related to the Bess project in Vega Baja.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Progress continued on the translation of Volume 3, Chapter 7 (Sections 7.1 to 7.9) of the Safety, Health, and Environment (SHE) Manual from English to Spanish. The translation adhered strictly to the established formatting guidelines, preserving the original structure and style to ensure consistency and technical precision. Verified spelling was applied throughout the translated content to maintain linguistic accuracy. Terminology was carefully selected to ensure fidelity to the source material, and the language was thoughtfully adapted to reflect the original intent. All formal elements—including section titles, numbering, and references—were retained to ensure alignment with relevant standards.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued translating Volume 3, Chapter 9 (Sections 9.1–9.6) of the SHE Manual, ensuring consistent formatting, structure, and accurate terminology throughout, while correcting spelling errors.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Began translating Volume 3, Chapter 8 (Sections 8.1–8.5) of the SHE Manual from English to Spanish. The work followed all formatting guidelines, preserved the original structure, and ensured accurate terminology and spelling. Section titles, numbering, and references were retained to align with applicable standards.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 134 | 67 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (Part 2) Continue review New Parking Area Grading and Drainage plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on teams meeting related to a PROCORE was verified project submittals status, coordinations status and project contract sign date with DCMC employees Andres Concepcion, Gilberto Sucre, Luis Roman, Luis Damudt, Luis Duque and Jorge Mercado due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule evaluation considering guide and construction sequencing variations for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule procurement sequencing considering guide and construction critical path variations for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 134 | 67 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on teams meeting related to RFC Meeting Costa Sur BESS was verified status of next submittals, proposal pricing and value engineering schedule with DCMC employees Gilberto Sucre, Luis Damudt, Luis Duque, employees of RGE Jose Robles, employees of Sargent and Lundy Robert D Molner, employee of CDM Smith Franklyn Colmenares, due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project schedule documentation, Identify project logic and time durations. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project schedule documentation, identify critical path and make time running durations. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Aguirre RFC meeting RG Engineering. Address by Franklyn Colmenares. Discussed to do action list and Aguirre BASS project schedule acceleration plan. Attendees: Franklyn Colmenares (CDM), Gilberto Sucre (DCMC) José López (DCMC), Luis M. Reyes (DCMC)
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 134 | 469 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Began reviewing project schedule documentation (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Submittal Procore settings meeting with Andres Concepcion (DCMC) and Luis Roman (DCMC) for the 4339_9510 BESS_Cambalache project.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache Weekly internal meeting with Andres Concepcion (DCMC) and Gilberto Sucre (DCMC) for the 4339_9510 BESS_Cambalache project to discuss weekly plan and action items.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (Part 3) Continue review New Parking Area Grading and Drainage plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review New Parking Area Grading and Drainage plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review New Parking Area Grading and Drainage plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. RFI/Submittal tracking meeting with Andres Concepcion (DCMC) and Luis Damudt (DCMC) for the 4339_9510 BESS_Cambalache project.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Ensuring accurate BESS and Peakers project status updates and progress reports within our monthly reporting system, which will be submitted to the client to provide a comprehensive overview of the project's development.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 122 | 305 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Facilitating the accurate documentation of BESS and Peakers project status and progress within our monthly reporting system, incorporating the project progress data from our PMO meeting to ensure a comprehensive update in the May report to be submitted to the client.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the bi-weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Glorimel Torrado, Paola Arroyo. CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 122 | 305 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with BESS and Peakers project status updates and progress reports within our monthly reporting system to provide a comprehensive overview of the project's development.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from BZN>DEN>SJN for project management purposes. Flight from Denver, CO to San Juan was cancelled.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PerDiem for Foster Veazey in San Juan, PR.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 10.21 | 10.21 | 10.21 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BEES PROJECT, Alkaline Batteries.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 6.16 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Mileage from Home to airport
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.13 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from home in Guaynabo to Aguirre warehouse to conduct an on-site assessment of inventory management performance. The primary objective is to support the execution of corrective actions previously identified during cycle count audits. Activities will include verify implementation of inventory reconciliation procedures, evaluate system data alignment in Asset Suite, assessing location integrity, and validating compliance with inventory governance protocols. This visit also aimed to provide direct operational oversight, ensure continuity in workflow documentation, and support Mr. Juan Vallejo.
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 32.34 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- traveled back home in Guaynabo from Aguirre warehouse. The purpose was to conduct an on-site assessment of inventory management performance. The primary objective was to support the execution of corrective actions previously identified during cycle count audits. Activities included was verifying implementation of inventory reconciliation procedures, evaluated system data alignment in Asset Suite, assessing location integrity, and validating compliance with inventory governance protocols. This visit also provided direct operational oversight, ensured continuity in workflow documentation, and supported Mr. Juan Vallejo
2025-05-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Wells, Lauren | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 6.37 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) milage from airport to home.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in design and drawing review meetings. Reviewed latest models for the Costa Sur underground infrastructure. Chris Mateo -Sargent & Lundy Gino Sambolin-Sargent & Lundy William Crespo-Sargent & Lundy
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 was part of meetings reviewing the budget German Nunez- GENERA Rafael Pabon-CDM Smith Carlos Palomares-CDM Smith Frances Vallejo Rosich-DCMC Harry Del Valle-DCMC Gilberto Sucre-DCMC.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Project update discussion with Jose Lopez DCMC, and Meeting agenda with the Municipality with Jean Pierre Menay -DCMC
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Program Correspondence review, validation and response to e-mails and reports.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Overall Management Supervision of all program activities.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Documentation Alignment Meeting with Lauren Wells, Theresa Perez, Luis Roman, and Gilberto Sucre (DCMC) to establish internal and external uploads in Procore Tools and Document Folders. A list of all submissions was developed and agreed to.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre evaluation of RGE Schedule Submission which execution logic needs to be revised. This update will be required prior to their accelerated schedule submission.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting focusing on Staffing Update, Trailers and Material deliveries to Site, PMO RFP status and the Main Topic being the Procore Financial Toll Implementation. Mike Merritt, Jack Darnall, Frances Vallejo, Lauren Wells, Foster Veazey, Ada Diaz, and Gilberto Sucre - DCMC
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache - Weekly Construction Meeting with RGE Management, Sargent & Lundy, CDM Smith and DCMC Partners. Review Safety, RFI, Submittals and Contract Acceptance Documentation Missing as well as Structural Steel VE alternate.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera/Tesla. Weekly Design Coordination meeting providing updates and action items between Genera, Sargent & Lundy, CSA Group, CDM Smith and DCMC Partners.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Financial Model Lauren Wells DCMC - Provided update on implementation and Mike Merritt - DCMC stressed the importance to launch immediately to start and issuing cost reporting for the PMO. Other Participants - Esther Rohena, Jose Ralat, Johanna Diaz, D'Alexander Gonzalez, Foster Veazey and Gilberto Sucre - DCMC.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Legal review comments to ARG Ceres Contract for Vega Baja with Francisco Feliu - Genera. Cambalache Contract RGE Schedule Review and Approval.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Weekly meeting with Joaquin Quinoy (Genera) and email follow-up. worked to update the Genera's new standard Glossary of Lean terms based on the input and feedback from Joaquin. Discussed plan for next onsite training in June.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Scheduled meeting with Kevin D. Futch Genera) for planning of the P3 Approval process improvement project and lean training to support Lean tool utilization in support of improving outcomes for the grant approval process.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Billable-Project Management ¦ DR 4339 - Meetings with DCMC on-site personnel to review Project Status and Roles and Responsibilities. Attendees were Foster Veazey, Gilberto Sucre, Frances Vallejo, Abraham Velazquez.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Procore Financial Alignment Meeting. Attendees were Lauren Wells (DCMC), Foster Veazey (Lemoine), Franklyn Colmenares (CSA), D'Alexzander Gonzalez (DCMC), Mark Merritt (DCMC).
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences for Submittals and meetings.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of current Procore documents to prepare for next meeting. Making sure the correct permissions are in place for needed actions.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) call with Franklyn Colmenares (CSA) to discuss Procore items
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Mark Merritt, D'Alexzander González, Gilberto Sucre, Esther Rohena, all with DCMC and others to discuss Procore Financials and path forward.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Procore Weekly Q&A with Luis Roman (DCMC), Theresa Perez (DCMC) and Jose Lopez (DCMC).
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on documentation for Procore SOP's.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Powerpoint for Procore kick off meeting for Cambalache Team.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore Financials
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Gilberto Sucre (DCMC), Theresa Perez (DCMC) and Luis Roman (DCMC) to discuss Procore documents and required CDM Smith documents.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Gilberto Sucre (DCMC) to discuss Procore items.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore submittals questions for Franklyn Colmenares (CSA) to assist Sargent and Lundy with questions.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the EHS documentation by Vega Baja Genera Site. Review documentation by EHS for Cambalache Site. Coordinate with Rod Rodders toilets for Cambalache site. Meeting with Municipality Administrator in Vega Baja Rafael Figueroa about parking lot necessary in Vega Baja project.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the EHS documentation by Vega Baja Genera Site. Review documentation by EHS for Cambalache Site. Coordinate with Rod Rodders toilets for Cambalache site. Conference call with Andres Concepcion and Harry del Valle (DCMC) about Cambalache Site. Review the Costa Sur installation offices trailers.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Jesus Cintron (Genera) to discuss staffing update, pending change order approvals and Tesla meeting.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Jean Pierre Menay (DCMC) to discuss PPE purchase that is needed on sites.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Drafted letter to the Municipality of Vega Baja regarding parking usage approval. The draft letter was sent to Ivan Baez (Genera) for his approval.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss trailer installation status at Costa Sur site, equipment that is needed to purchase, Procore meeting, and next steps regarding staffing. Participants: Mike Merritt, Lauren Wells, Foster Veazey, Gilberto Sucre, Barry Scanlon (DCMC).
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Call with Rafael Calderon (DCMC) to discuss change order approval for Tesla contract and follow up with Genera.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Mayor of Vega Baja to discuss parking lot request needed for the Vega Baja BESS project. Participants: Jorge Bracero (Genera) and Paola Arroyo (DCMC)
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Raissa Borges (DCMC) to discuss one pager per site regarding BESS status, discuss participation in procore meeting regarding financials and support with the CDM Smith team.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafa Pabon, Alejandro Laya, Carlos Palomares (CDM Smith) Miguel del Valle (S&L). Discussed feedback and updates received from the Genera procurement team.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Prepared for the weekly BESS and Peakers catch-up call by reviewing and updating the project tracking spreadsheet. Incorporated feedback and updates received on 05/27 from the Genera procurement team, including changes to documentation status, and contractor communications. Ensured the tracker reflected accurate, real-time information to support productive discussion, alignment across teams, and timely follow-up during the coordination meeting.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 220877 Purchase of one Torque Converter for Aguirre Combined Cycle - Began assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Initiated the process of completing the mandatory appendices, beginning with Appendix A. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP No. 220871 - Cooling Tower Motors for Aguirre Power Plant - Continued assembling the FOMB Request for Approval package, with a focus on organizing, gathering, and renaming files to ensure clarity and ease of reference.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP No. 220871 - Cooling Tower Motors for Aguirre Power Plant - Continued assembling the FOMB Request for Approval package. Concentrated on the RFP documentation, downloading, reviewing and formatting 10 of the 23 required documents. Ensured that all supporting materials were accurately compiled and aligned with FOMB’s submission requirements to support a complete, well-structured, and compliant approval package.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued the weekly FortiNAC session with Mario Gomez and Michael Silva from Genera PR, conducting device identification tests on the network to enable enhanced control over access to applications such as Asset Suite, Oracle Fusion, and Genera Connect. Additionally, participated in a discussion with Eisha Mercader from DCMC, and Carlos Gonzalez, Jorge Aponte, and Aldwin Pagan from Integrum to address the requirements and planning for the historical data migration related to the Genera Connect Timesheet system.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordinated reschedule meeting with Eisha Mercader (DCMC), Carlos Gonzalez (Integrum), Jorge Aponte (Integrum), and Aldwin Pagán (Integrum). The purpose of the proposed meeting is to discuss strategy to migrate historical timesheets data used to track allocated time and work to federally funded projects. - Began coordinating user access to the Genera Connect Timesheets application for Genera PR users to report work done on federally funded projects
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Removed beams and metals demolition of the concrete curb from the site.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Review of prints in RFP and drawings specific, specifically initial site development and demolition.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Trailer arrival onsite at Costa Sur, meeting to discuss project status and trailer installation with Plant Director Miguel Beauchamp (Genera) with DCMC team. DCMC team to include Harry Del Valle, Carlos Rodriguez, Rafael Barrera, and Gabriel Morales.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Costa Sur Site Meeting with Miguel Beauchamp (Genera), Carlos Rodriguez, Harry Del Valle, Carlos De Jesus and Rafael Barrera (DCMC). Discuss and review the plan to relocate and energized the new DCMC mobile office in the Costa Sur Site.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 |  | 167 | 292.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Costa Sur Site Receive from Duenas Trailer the new mobile office for the Costa Sur site. The mobile office was set up in the designated area.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria: Yabucoa Conducted a comprehensive evaluation of the preliminary BESS design drawings in Procore for the Yabucoa site. Focused on verifying alignment with the project’s scope of work, site-specific requirements. Documented observations and drafted internal comments to define project scope, provide visual details, outline material requirements, and serve as critical contract documents.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Costa Sur A successful office inspection was completed, confirming that everything was in proper working condition and no damages were observed. The inspection was carried out by DCMC team: Carlos Rodriguez, Rafael Barrera, Harry del Valle, and Gabriel Morales (myself).
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed project drawings and RFP documentation for the Costa Sur BESS (Battery Energy Storage System) project to ensure technical accuracy, compliance with project requirements, and alignment with engineering standards.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: New trailer coordination location and conducted review of project drawings and RFP documentation to ensure compliance with project requirements and documentation standards. Assessed technical specifications, identified discrepancies, and coordinated with team member Miguel Beauchamp (Genera) to address issues and ensure alignment.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Finalizing the review of the Safety Manual Genera PR
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Complete and submit the review of the Genera PR Safety Manual to Jean Pierre Menay (DCMC)
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS - Contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting on the Vega Baja BESS site with the DCMC Team, Jaime Pesquera, to review Homeca's scope of work performance and discuss the recovery plan to avoid delays of the project critical path.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Central Costa Sur Office Trailer Installation. Attendees, Miguel Beauchamp (Genera), Roberto Camacho (Genera), Carlos Rodriguez (DCMC), Rafael Barrera (DCMC), Carlos de Jesus (DCMC), Gabriel Morales (DCMC) & Harry Del Valle (DCMC). Topics discussed, walk through Office Trailer Area, discussed Office trailer Installation by Duenas Trailer, Final Location of Existing Generator to be relocated, discussed Office trailer utility's needs. Introduce to Genera the DCMC BESS Project Management team. Supervise the installation of the office trailer.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Central Costa Sur Office Trailer Power Installation. Attendees, Roberto Camacho (Genera), Genera Electrician & Harry Del Valle (DCMC). Topics discussed, Office trailer Power Installation, location to connect the Office trailer. Continue the installation of the office trailer by Duenas Trailer employees.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Generate PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Work is being done to create fire prevention safety guidelines according to OSHA 1910.39, as well as the use and identification of fire extinguishers for the BESS CAMBALACHE project.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of recommendations for disposal areas, prior to the start of the project
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Generate PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Work is being done to create fire prevention safety guidelines according to OSHA 1910.39 for the BESS CAMBALACHE project.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Document evaluation TECHNICAL SPECIFICATION FOR CAMBALACHE BATTERY ENERGY STORAGE SYSTEM (BESS) GENERAL WORK CONTRACT (GWC)
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - RFC Meeting RGE Cambalache whit contractor RGE and DCMC cambalache team.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted the Cambalache Weekly Meeting with contractor (RG Engineering-Jose Segarra), DCMC site Team (Luis Damudt, Carlos De Jesus, Gilberto Sucre, Luis Duque, Jorge Mercado), Genera PR (Roseanne Perez) and Sargent & Lundy (Gary Jasutis). The team discussed important project action items and follow ups.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed for QA/QC Cambalache updated construction schedule provided by RG Engineering (Jose Robles). Evaluated activities durations and sequences with project scope of work.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated and prepared a pre Request for Information (RFI) to designer (Sargent and Lundy-Mike Kuczynski) regarding a potential issue on a construction activity due missing information in drawings.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met via phone call with GeneraPR-Rosseane Perez to discuss environmental requirements to be met in project. Met with DCMC Partners- Jean Pierre Menay to discuss safety considerations for office trailer sanitary tank coordination.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted the Cambalache Weekly Meeting with contractor (RG Engineering-Jose Segarra), DCMC site Team (Luis Damudt, Carlos De Jesus, Gilberto Sucre, Luis Duque, Jorge Mercado), Genera PR (Roseanne Perez) and Sargent & Lundy (Gary Jasutis). The team discussed important project action items and follow ups.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated and prepared the Cambalache Weekly meeting agenda to follow up and discuss important project pending and action items. This is prepared through the Procore platform.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared Cambalache weekly meeting minutes and documented all discussion and action items to be followed. Generated document and distributed through Procore platform.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed contractor (RG Engineering) proposed mobilization plan to the Cambalache facility. The plan is needed to be evaluated and presented to GeneraPR.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while stationed at the Costa Sur warehouse, compiled and submitted a comprehensive inventory performance report to Mr. Anthony Vega of Genera PR. The report consolidated data from all warehouse sites and included a strategic summary of catalog entries, unit counts, valuation metrics, and system-to-physical stock variances. Additionally, it addressed inventory discrepancies, analyzed cost exposure, and evaluate compliance with establish level thresholds. The report also incorporates key performance indicators to provide a clear operational snapshot of the current inventory status. The locations review was, AB 001 to AB 016, AK 019 to AK 023, AG 046 to AG 050, AE 020 to AE 040, AG 001 to AG 008.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-supported the preparation of cycle count sheets to facilitate scheduled inventory activities at the Costa Sur warehouse, working in coordination with Mr. Hernan Machado from DCMC. The task involved validating item locations, confirming stock accuracy and organizing materials to ensure a structured and efficient inventory process. Today's effort concentrates from AB 001 to AB 016.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a cycle recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC to assess inventory data integrity. The objective was to validate prior count results, reconcile identified discrepancies, and ensure alignment between physical inventory and system records. This task contributed to reinforcing the accuracy, consistency, and reliability of inventory documentation as part of ongoing inventory control and audit preparedness measure.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a detailed variance analysis at the Costa Sur warehouse, focusing on the identification of inventory discrepancies and the assessment of systemic inconsistencies between recorded and actual stock levels. The process involved root causes analysis of variances, evaluation of control gaps, and the formulation of timely corrective actions to mitigate future discrepancies and optimize warehouse reliability.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted physical counts for the designated inventory locations scheduled for the day, specifically covering AB 001 through AB 016. This task formed a critical component of the ongoing data reconciliation initiative designed to enhance inventory accuracy and system reliability. Activities included cross-verification of on-hand stock against system records, identification and documentation of variances, and validation of bin-level item assignments. The process contributes to audit compliance, inventory integrity, and optimization of warehouse data management protocols.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led a coordination meeting with Juan Vallejo, Giovanni Taffanelli and key DCMC warehouse personnel to assess current inventory related challenges and establish corrective strategies. The discussion centered on identifying process bottlenecks, enhancing data accuracy, and reinforcing inventory management protocols. The session highlighted the importance of improved coordination and increased accountability across operational procedures.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information on NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status. Batch 2 Part 1
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with Cynthya Ortiz DCMC to review the status of active RFP of current federal projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information on NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status. Batch 3
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information on NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status. Batch 2 Part 2
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Division Masonry.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Topic: Light Weight Topping/Gypcrete.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Division Masonry.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted the Cambalache Weekly Meeting with contractor (RG Engineering-Jose Segarra), DCMC site Team (Luis Damudt, Carlos De Jesus, Gilberto Sucre, Luis Duque, Jorge Mercado), Genera PR (Roseanne Perez) and Sargent & Lundy (Gary Jasutis). The team discussed important project action items and follow ups.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Topic: Division 4 – Masonry Unit Masonry, Testing and Inspection, Provide the bar anchors in horizontal joints of masonry work
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BESS Supervising work from contractor Homeca Recycling. Contractor keeps dismantling, Decommissioning and demolition works and planning for phase II to ensure environmental protection, regulatory compliance, and worker safety.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform, RFI#23, RFI #41, RFI#49.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Removed beams and metals demolition of the concrete curb from the site. Removed metal beams towards safe area and separated concrete from them.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Continue removed Metal Rods from the concrete covered manhole with concrete.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #293566-12 for TO#2 Jan 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Technical Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla Technical reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda, Carlos Palomares), Sargent & Lundy (Mike Kuczynski), and DCMC (Rafael Calderon, Gilberto Sucre)
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Siemens Energy Contract #00106588. Review deliverable Schedule based on project development and new change order #2 request. Contract review and documentation to identify allowable task, scope and impact to contract schedules. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Genera Amend and Restate Contract) Meeting with project management Team. Contract 106761 - Reviewing current change orders procedures and discussing new Change Order Process non-Traditional to better manage multiple changes and prevent delays on contract execution. Meeting participants TESLA (Michael Grabstein, Allin Luong, Jorge Quintana), CSA (Franklyn Colmenares), Genera (Fernando Ortiz)and DCMC (Rafael Calderon)
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Continue working on Siemens Energy Contract #00106588 Meeting. Review deliverable Schedule based on project development and new change order #2 request. Contract review and documentation to identify allowable task, scope and impact to contract schedules. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount 811, 812, 813 and 814 locations AK019-AK023/AG046-AG050
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AG001 to AG008
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AG001 to AG008
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AG001 to AG008
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AG001 to AG008
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AG001 to AG008
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 00 001 000 to AB 00 016 000
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 00 001 000 to AB 00 016 000
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 00 001 000 to AB 00 016 000
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AE 020 to AE 040 using Cycle Count List # 844/846
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AE 020 to AE 040 at the Aguirre warehouse to start the cycle counts.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AE 020 to AE 040
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AE 020 to AE 040 using Cycle Count List # 842/843/844
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #811, 812, 813 and 814 from locations AK019-AK023/AG046-AG050 for a total of 685 pcs.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AK019-AK023/AG046-AG050 Cycle Count List #820, 821, 841 and 845.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AK019-AK023/AG046-AG050 to begin the cycle counts.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AK019-AK023/AG046-AG050
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management / Vega Baja BESS Incoming Data Review & Process from Homeca (Sub)/ Vega Baja BESS Preparation of List for required documents for team coordination
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 151 | 528.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Vega Baja BESS Review & Process all Incoming Documents / Incorporate Additional New Users in Procore/ Coordination Procore Submittals Weekly Q&A with Lauren Wells (DCMC) & Luis Roman (DCMC) Jose Lopez (DCMC)
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Vega Baja BESS & Cambalache BESS Coordination with Paola Arroyo (DCMC) regarding Community Outreach documentation entries to be reviewed and organized according to correct projects
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Coordination with Lauren Wells (DCMC) & Gilberto Sucre (DCMC) Luis Roman (DCMC) for the Implementation of Documents List Required by all Vendors & Subcontractor for Project Team/Aguirre BESS & /Costa Sur BESS Add Additional Procore Users
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Theresa Perez and Gilberto Sucre (DCMC) and Lauren Wells (Lemoine) to discuss the output of Submittals and other Core Tools into the Documents Tool; closed submittals informations and specs, and other closed or archived information inside the main core tools.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform project management activities such as KPI metrics (cost and time projections), scheduling progress and potential implementation of tool only for internal use.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Cambalache Project Weekly Meeting hosted by Andres Concepcion, Luis Duque and Luis Damudt (DCMC), also joined by Jose Segarra, Jose Robles and Xiomara Perez (RGE), Robert Molner (S&L), Herminio Arroyo and Roseanne Perez (GeneraPR). Discussed construction upcoming kick-off and relevant issues such as mobilization and in-site storage areas (Staging Areas), critical initial submittals and the tracking of Procore use for project activities.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform project management metrics analytics for the construction progress of active projects. Download contractual documentation regarding construction budget and projections related to time of contract and execution.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Email Tool for the inclusion of all Emails sent outside Procore for Construction Projects; inclusion of Project Email Address to different team staffs, creation of a Contact for every project email address and structuring the communication to enforce proper Email tool use.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 149 | 372.5 | 149 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 -PW#9510 - Working on the with Pre-Intervention Review for CDM Smith TO01_293410-13_2025. Finish reviewing narratives for this invoice. Review lines and identify missing information or aligned with SOW lines. I also start and finished compliance review. Prepare email requesting final invoice document to CDM Smith.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Correspondence development related to the contact update with the municipality of Vega Baja to coordinate the next community meeting. Write a summary of the meeting with the municipality of Vega Baja was offered to the Genera PR team, Jorge Bracero.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Call meeting with the Genera PR team Jorge Bracero to discuss the work plan and needs to address with the municipality of Vega Baja.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Coordinate a community meeting in Vega Baja to talk about BESS.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Update Cambalache Community Relations Plan with all the new information about the project.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Meeting at the Vega Baja town hall with municipal administrator Rafael Figueroa and DCMC Partners team Jean Pierre Menay in order to request permission to use the municipality's parking and to address upcoming meetings with the community.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 139 | 347.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued translating Volume 3, Chapter 10 (Sections 10.1–10.4) of the SHE Manual, ensuring consistent formatting, structure, and accurate terminology throughout, while correcting spelling errors.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued translating the SHE Manual Volume 3, finishing Chapter 10 (Sections 10.4), starting with Chapter 11, Sections 11.1 and 11.2, ensuring consistent formatting, structure, and accurate terminology throughout, while correcting spelling errors.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – (Day 2) Finalized technical assessment of the proposed grading and drainage design for the new parking area at the BESS Cambalache site (4339_9510). Evaluated topographic alignment, water runoff strategy, and drainage infrastructure integration. Confirmed alignment with engineering best practices and site plan criteria for FEMA PA project documentation.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on site visit to identified demolition and construction area, site meetings to review the project managements process and receive the temporary office at Costa Sur for BESS project with DCMC employees Harry del Valle, Carlos Rodriguez, Rafael Barrera and Gabriel Morales due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted the Cambalache Weekly Meeting with contractor (RG Engineering-Jose Segarra), DCMC site Team (Luis Damudt, Carlos De Jesus, Gilberto Sucre, Luis Duque, Jorge Mercado), Genera PR (Roseanne Perez) and Sargent & Lundy (Gary Jasutis). The team discussed important project action items and follow ups.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on comments in RFP schedule version 6 sequencing considering guide and construction critical path variations for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on site visit to identified steps before construction start and site meetings to review the project managements process and receive the temporary office at Costa Sur for BESS project with DCMC employees Harry del Valle, Carlos Rodriguez, Rafael Barrera and Gabriel Morales due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project schedule documentation, identify critical path activities and reviewing and change logic. Make recommendations to improve time line . (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project schedule documentation. Sent email with critical activities the need to bed included in schedule and eliminate some critical activities not related to Aguirre project. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue revise project schedule documentation. Sent emails with logic recommendations and eliminate activities not related to Aguirre project (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) (PART 2) Continue review New Parking Area Grading and Drainage plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review New Parking Area Grading and Drainage plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review New Parking Area Grading and Drainage plan for 4339_9510 BESS_Cambalache project.BESS.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Construction Weekly Meeting with contractor (RG Engineering-Jose Segarra), DCMC site Team (Luis Damudt, Carlos De Jesus, Gilberto Sucre, Luis Duque, Jorge Mercado), Genera PR (Roseanne Perez) and Sargent & Lundy (Gary Jasutis). Discussed important project action items and follow ups.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Incorporating BESS and Peakers project progress data from our PMO meeting to ensure a comprehensive update in the May report to be submitted to the client.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Ensuring the ongoing integration of the latest progress data for the BESS and Peakers projects. This will help provide a thorough and well-documented update for submission to the client, reflecting key milestones, developments, and any relevant insights from our discussions.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue incorporating BESS and Peakers project progress data from our PMO meeting to ensure a comprehensive update in the May report to be submitted to the client.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 111 | 111 | 111 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PerDiem for Foster Veazey in San Juan, PR.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 30 | 30 | 30 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits with rental vehicle,
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 26.49 | 26.49 | 26.49 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from airport to hotel for Foster Veazey. $18.26 trip fare, $3.00 tip, $1.48 booking fee, $3.75 airport fee
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 19.2 | 19.2 | 19.2 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from DCMC Office to Airport for Foster Veazey. $16.18 trip fare, $1.00 tip, $2.02 booking fee
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 16.13 | 16.13 | 16.13 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from hotel to DCMC Office for Foster Veazey. $13.65 trip fare, $1.00 tip, $1.48 booking fee
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Metting with Municipality Administrator Rafael Figueroa for lot parking necessary in the project
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 122.5 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Yabucoa Gas Turbine to Costa Sur Power Plant to Yabucoa Gas Turbine. Purpose - Meeting with Miguel Beauchamp (Costa Sur Power Plant Site Manager). Relocation of the DCMC Partners Mobile Office to the Costa Sur Site.
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 153.3 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Costa Sur Power Plant (18.000463, -66.753480) to Home Office Luquillo. Purpose, Trailer Installation. Attendees, Miguel Beauchamp (Genera), Roberto Camacho (Genera), Carlos Rodriguez (DCMC), Rafael Barrera (DCMC), Carlos de Jesus (DCMC), Gabriel Morales (DCMC) & Harry Del Valle (DCMC). Topics discussed, walk through Office Trailer Area, discussed Office trailer Installation by Duenas Trailer, Final Location of Existing Generator to be relocated, discussed Office trailer utility's needs. Introduce to Genera the DCMC BESS Project Management team. Supervise the installation of the office trailer. TOTAL MILEAGE 219 miles
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.23 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled back home in Guaynabo from Costa Sur facility. to provide support to Mr. Hernan Machado from DCMC. The objective of the visit was to provide support to Mr. Hernan Machado and to assist in the verification of physical inventory counts, ensured data accuracy within the system, review procedures and confirm the integrity of ongoing inventory task
2025-05-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 55.3 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-traveled directly from home in Guaynabo to Costa Sur facility to provide support to Mr. Hernan Machado from DCMC. The objective of the visit is to assist in the verification of physical inventory counts and ensure data accuracy within the system. Additionally, we will collaborate with Mr. Hernan Machado and the local team to review procedures and confirm the integrity of ongoing inventory task.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended meeting on contract review and budget review German Nunez-GENERA Rafael Pabon-CDM Smith Carlos Palomares-CDM Smith Frances Vallejo Rosich-DCMC Harry Del Valle-DCMC Gilberto Sucre-DCMC.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal working on demolition plan schedule/ durations organizing, sequencing, and managing tasks to ensure timely completion and provide a structured roadmap that prevents delays, reduces inefficiencies, and keeps the project on course, regardless of unforeseen challenges.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Worked and Coordinated Program Activities: * Luis Reyes Resignation from Aguirre - Scheduler and replacement options. * Tesla Upcoming visit coordination to Sites * Vega Baja Update & Decommissioning Plan Final Inspection Report. * Project Trailers and Supplies coordination. * Vega Baja, Costa Sur & Aguirre RFC Status.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's Project Schedule & Budget Meeting Weekly Update led by Carlos Palomares CDM Smith with Participation from CDM Smith, CSA Group, Genera, & DCMC Partners.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC RGE Cambalache Contractual Package Completion coordinated with Sargent & Lundy, Genera and DCMC to submit all documentation for the package approval to Sheila Torres DCMC.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre - Revised Structural Pad and Layout Model Review. Sargent & Lundy presented review concept to be implemented. Due to the Current Award Negotiations with RGE, DCMC stressed the importance to complete and issued this revision to the contractor prior to continuing with RFC evaluation. Sargent & Lundy, CDM Smith, CSA & DCMC Participated.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Procore Kick-off Meeting for DCMC site team with RG Engineering alignment on construction management process through Procore. Participants Sargent & Lundy, RG Engineering & DCMC Partners
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting RGE Cambalache. Reviewed Main two outstanding items for Contract Agreement - 12-month construction execution schedule and submission of Structural Steel VE Platform. Sargent & Lundy, CDM Smith, RGE and DCMC.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache - Evaluated Proposed Structural Steel VE Platform Submission by RGE.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting ARG Ceres / Vega Baja Update Meeting against tracker to identify actions item and assignment tasks and due dates. Also reviewed closed items and legal review alignment between Genera and ARG Legal Counsel. Sargent & Lundy, CDM Smith, CSA Group, ARG Ceres and DCMC Partners.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Planning meeting Kevin Futch (Genera) to determine who should be on the team that will review the current P3 approval process and develop a new improved Genera standard process that will focus on reducing the approval process time. We also discussed the plan for the next onsite training in June where we will work on the P3 Approval process project as a team.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on meeting coordination for Vega Baja team for Rfi's and Submittals for next week.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Powerpoint for Cambalache kick off call today for last minute updates.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Submittals SOP review.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Andres Concepcion, Luis Roman, Theresa Perez, Luis Duque, Luis Damudt, Gilberto Sucre (all with DCMC), Mike Kuczynski (Sargent & Lundy) Monica Ybarra (Sargent and Lundy), Alberto Jose (RGE) for a Procore Kick off for the Cambalache site project.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Rafael Pabon (CDM Smith), Theresa Perez (DCMC), Franklyn Colmenares (CSA), Luis Roman (DCMC) and others to discuss Procore document control.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences for meetings.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore distribution list settings for Peakers Costa Sur.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial documentation to align Financial processes.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore correspondences for Submittals.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Mark Merritt, Jose Ralat, Esther Rohena, Rafael Calderon, all with DCMC and Shellsea Maysonet SM Consulting to discuss current workflow for Grants Management and Operations in order to capture process to finish build out in Procore.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for tasks tool .
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continue Review Installing the offices trailers by Dueñas Trailers for DCMC in Cambalache Genera Site. Meeting in Vega Baja with Gilberto Soto, Jose Lopez, Gabriel Morales (DCMC) about Vega Baja Project.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2.5 |  | 184 | 460 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting in Vega Baja with Gilberto Soto, Jose Lopez, Gabriel Morales (DCMC) about Vega Baja Project and EHS issues.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the EHS documentation by Cambalache Genera Site. Installing the offices trailers by Dueñas Trailers for DCMC in Cambalache Genera Site.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Costa Sur site for the trailer installation coordination by Duenas Trailer.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers schedule meeting with project management team for the BESS and Peaker project, German Nunez (Genera) and Gabriel Perez (CDM).
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP No. 220871 - Cooling Tower Motors for Aguirre Power Plant - Finalized the assembly of the FOMB Request for Approval package. Completed the review, formatting, and organization of all remaining required documents to ensure accuracy and alignment with FOMB’s submission guidelines. Drafted the remaining appendices B, C, and D ensuring they were complete and compliant with the Contract Review Policy. Submitted the full package to Genera Management for review and approval, and to facilitate distribution to other key stakeholders.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 220877 Purchase of one Torque Converter for Aguirre Combined Cycle - Continued assembling the FOMB Request for Approval package. Concentrated on the RFP documentation, downloading, reviewing and formatting the 22 required documents. Ensured that all supporting materials were accurately compiled and aligned with FOMB’s submission requirements to support a complete, well-structured, and compliant approval package.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Homeca continue to demolished corrugated roof areas to disposed on their Location. Jorge Sanchez from Homeca picked for disposal 20CY Bin towards Homeca location in Caguas.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Onsite meeting with Rafael Barrera (DCMC), continuing installation of Power to trailer, brief chat with Plant Manager Miguel Beauchamp (Genera) informing power may be installed in the afternoon or early Morning.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PREPA-Request for proposal drawings review, reviewing specifics of water drainage.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Cambalache Continue with the Set up of the new mobile office of the Cambalache site from Duenas Trailers. to provide a centralized hub for operations,
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Cambalache A successful inspection of the office was completed, confirming that everything was in good working condition and no damages were observed. The inspection was conducted by DCMC team: Jean Pierre Menay, Andres Concepcion, and Gabriel Morales (myself).
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Cambalache Received the new mobile office for the Cambalache site from Duenas Trailers. Setup location instructions were discussed with the Duenas Trailers team.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Vega Baja site demolition status overview with Jean Pierre Menay and Jose Lopez (DCMC) to ensure worker safety, minimize environmental impact and help with regulatory compliance.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Cambalache Site Discussion and review with Andres Concepcion, Harry del Valle and Jean Pierre Menay (DCMC) regarding the plan to relocate and energize the new DCMC mobile office at the Cambalache site.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Held a coordination meeting with Carlos Rodriguez (DCMC) to plan the installation of trailer office facilities at the Costa Sur project site. Discussed site layout, utility connections, delivery logistics, and timeline requirements to ensure readiness for upcoming project phases. Follow-up actions were outlined to align with construction schedules and operational need.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continuous review of project drawings and RFP documentation for the Costa Sur BESS (Battery Energy Storage System) project to ensure technical accuracy, compliance with project requirements, and alignment with engineering standards.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Product Functional Safety: Review standards UL 1642, UL1973, UL 9540, UL 9540A, UL 1741, UL 1998, UL 991, IEC 62619:2022
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Studied project materials for the BESS Aguirre initiative, focusing on understanding scope, reviewing detailed information, and compiling notes to clarify requirements and support coordination efforts.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed documentation and key requirements of the BESS Project in Aguirre. Took detailed notes and analyzed technical specifications to support task planning and execution.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review and learn Electrical, Fire, and Safety Codes and Standards: NFPA 855: Improving Energy Storage System Safety, and NFPA 70
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS PROJECT: Meeting with Carirma Sanchez (HOMECA ) to discuss the weekend work schedule. Dismantling and Demolition Activities field supervision and coordination.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS - Contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Central Cambalache Office Trailer Installation. Attendees, Jean Pierre Menay (DCMC), Andres Concepcion (DCMC), Gabriel Morales (DCMC) & Harry Del Valle (DCMC). Topics discussed, walk through Office Trailer Area, discussed Office trailer Installation by Duenas Trailer, discussed Office trailer utility's needs. Supervise the installation of the office trailer.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on trailer offices layout for Central Aguirre & Yabucoa Gas Turbine Plan. Desing offices and conference areas Layout. Prepare List & Quoting of materials needed for office in projects. Sent Email to Frances Vallejo (DCMC) and Gilberto Sucre (DCMC) with quotes and Layouts.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Work continues at the Cambalache site to inspect and supervise the installation of temporary offices for DCMC teams to serve as the central hub for project management, communication, and coordination throughout the project duration.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Verification of documents and environmental standards for procedures, Clean Water Act and MPDS regulations
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work continues on site to install the temporary offices for DCMC equipment.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Procore Kick-off meeting with Andres Concepcion DCMC to ensure that all parties involved in the project are aligned with the project objectives, understand their roles and responsibilities, and are aware of the site-specific conditions, safety protocols, and project schedule.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Visit to the Cambalache site for inspection and supervision of the installation of temporary offices for DCMC equipment to serve as the central hub for project management, communication, and coordination and ensure seamless operations throughout the project duration
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared documentation regarding contractor proposed mobilization plan and staging areas and met with Herminio Arroyo and Rosseane Perez (Genera PR) to discuss about mobilization and environmental requirements.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared document with recomendations and guidelines to contractor (RG Engineering) to be applied on the Temporary storage for gas cylinders on site. Emailed information to Jose Segarra. (RG Engineering)
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Site Coordination with Jean Pierre Menay, Harry Del Valle, Jorge Mercado (DCMC) for the delivery and installation of the Office Trailer by Duenas Trailer. Coordination completed with GeneraPR (Herminio Arroyo)
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Attended and presented in the Cambalache Procore Kickoff Meeting to align all project stakeholders on the use and management for the Procore platform during the project. RG Engieering team (Jose Segarra, Xiomara Berrios), Sargent and Lundy Team (Robert Molner, Dean Ennes) and DCMC Site Team (Jorge Mercado, Luis Duque, Carlos De Jesus), DCMC Procore Team (Lauren Wells, Luis Roman)
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Attended Cambalache RFC meeting for the coordination and alignment of pending actions for the construction contract completion and sign. DCMC Partners - Gilberto Sucre. RG Engineering - Jose Segarra and Harry Velazquez, Sargent & Lundy - Robert Molner, Angel Alicea.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed targeted cycle counts for assigned inventory zones, focusing on locations AG 009 to AG 016. The task involved validating physical stock levels, reconciling item quantities with system records, and documenting discrepancies for corrective action. These activities support inventory reliability and facilitate accurate reporting for decision making warehouse operations.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 167 | 125.25 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while station at the San Juan warehouse, compiled a consolidated inventory performance report for Mr. Anthony Vega of Genera PR. The report integrated system-wide data from all warehouse locations, including catalog ID validation, stock balance summaries, cost allocation analysis, and variance detection. It also assessed compliance with define minimum/maximum thresholds. Performance indicators were quantified using percentage-based metrics to evaluate inventory accuracy and operational consistency across all warehouses. Locations reviewed are AG 009 to AG 016, AE 040 to AE 060, AK 007 to AK 015, AB 017 to AB 030.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-Led an early morning briefing with Hernan Machado, Milton Flores, and DCMC warehouse personnel to address inventory discrepancies flagged during the prior day. Empasis was placed on reinforcing execution of standardize data entry protocols and ensuring alignment with daily warehouse operational workflows to improve real time accuracy.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-continued execution of cycle count procedures for designated inventory areas, specifically targeting locations AG 009 through AG 016. Activities focused on validating physical inventory levels, reconciling discrepancies with Asset Suite system records, and ensuring data accuracy. The process also involved systematic documentation of variances and real time updates to count logs to maintain inventory control.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a targeted inventory recount at the San Juan warehouse in coordination with Mr. Milton Flores from DCMC to assess data integrity and validate previous cycle count outcomes. The operation involved reconciling physical inventory with Asset Suite records, addressing transactional discrepancies, and reinforcing reliability, traceability, and consistency across recorded inventory data.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-provided technical support for inventory data verification and the structuring of cycle count documentation in coordination with Mr. Milton Flores of DCMC. Activities included validating storage locations and confirming on-hand stock levels against system records. Efforts also focused on aligning material flow process, refining data capture procedures, and ensuring readiness for daily warehouse operations to improve procedural efficiency and overall inventory integrity.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused inventory integrity audit to identify discrepancies between physical stock counts and digital records across critical storage zones. The assessment included root cause analysis of transactional anomalies, review of item lifecycle and movement history, and verification of system generated balances against actual on-hand quantities.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the weekly meeting with CPM, I focused on reviewing Critical Components priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue updated complete a Dashboard Using the available information on NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Complete QA/QC to DCMC Team- Project Management Tool to ensure team stays organized and improve efficiency, communication, and collaboration to achieve project goals more effectively.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Eduardo Rivera, and Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop High-level Cost Estimate - 816612- FAASt [Continuous Emission Monitoring Systems (CEMS)] PW- 10810
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Topic - Fluid-Applied Waterproofing, Thermoplastic Polyolefin (TPO) Roofing .
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Division 8 – Openings, Hollow Metal Doors and Frames, Door Hardware/Access Control
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Division 07 - Thermal and Moisture Protection, Clay Tile Roofing.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Topic - Penetration Firestopping, Joint Sealants.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BESS Supervising work from contractor Homeca Recycling. Contractor keeps dismantling. Supervising decommissioning and demolition works and planning for phase II to ensure environmental protection, regulatory compliance, and worker safety.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Supervising contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project essential for maintaining a healthy environment, complying with regulations, and promoting sustainability. Went over a schedule report review with pictures of the last month and a half with Manuelli Concepcion, (CDM-SMITH) using my phone pictures for his report.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Homeca demolished corrugated roof areas to disposed on their Location.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Homeca demolished corrugated roof areas to disposed on their Location. Xavier Ortiz from Bess arrived to inspect areas and storm water gutters.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #293566-12 for TO#2 Jan 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 164 | 410 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens / Genera Peakers biweekly meeting with project management Team. Siemens Energy Contract #00106588 and Deliverable Schedule review based contract development. Reviewing status of project execution including upcoming Change Orders and Logistic in preparation for the Delivery Dates. Meeting between Siemens Energy team , CMD Smith PM team (Rafael Pabon, Carlos Palomares), Sargent & Lundy (Miguel del Valle, Mateo Agosto and Gino Sambolin) Genera (German Nunez), and DCMC (Rafael Calderon).
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Pro-Core Meeting: Procore - DCMC Financials Tools - review new ProCore functionalities to process and document invoices, contract balance, PWs and discussed workflow streamline opportunities within DCMC Team. This tool will facilitate invoice review process and accurate contract balance for all Genera projects including BESS and Peakers. Participants from DCMC - (Rafael Calderon, Lauren Wells, Jose Ralat, Esther Rohena, Sheila Torres and Mark Merritt).
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #859 from locations AK007 to AK015 for a total of 171 pcs.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AG009 to AG016
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AG009 to AG016
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AG009 to AG016
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AG009 to AG016
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AG009 to AG016
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 00 017 000 to AB 00 030 000
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 00 017 000 to AB 00 030 000
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 00 017 000 to AB 00 030 000
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AE 040 to AE 060 using Cycle Count List # 857/856
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AE 040 to AE 060 at the Aguirre warehouse to start the cycle counts.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AE 040 to AE 060
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AE 040 to AE 060 using Cycle Count List # 847/848/849
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK007 to AK015.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-At the Palo Seco warehouse, preparing the lists from locations AK007 to AK015 to begin the cycle counts.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 859 locations AK007 to AK015
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AK007 to AK015 Cycle Count List # 851.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management / Coordination of Incoming CDM Documents with Lauren Wells (DCMC)/Manuely Concepcion (CDM)/ Rafael Pabon (CDM) / Coordination of S&L Incoming Documents with Ivette Miranda (S&L)/ Incorporate new users in Procore for Costa Sur BESS/Aguirre/Yabucoa BESS/Review Documentation in 01 Genera Program Management Project Folder
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control - Data Management - Costa Sur Peakers Incoming Documents Review & Process Accordingly/ Setup S&L Dropbox for all Incoming Documents for Review & Process for all Projects/ Cambalache BESS Project Coordination for Kick Off /Procore Project Tools including SOPs
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Submittals settings for Ball in Court, Submittal Workflows and Delivery Settings on the Costa Sur Peakers Project; review submittal workflows for potential changes on Design deliveries.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Documentation Meeting with Rafael Pabon and Manuelly Concepcion (CDM Smith), Lauren Wells (Lemoine) and Theresa Perez (DCMC) to discuss the integration of project documents into the Documents Tool, or the management of documents through main Core Tools.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review and Modify Power Point Presentation for the Cambalache Procore Kick-off Meeting today at 2:00pm; designation of roles and responsibilities within the Procore platform.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Creation of multiple meetings agenda for Procore Catch-up and Weekly Q&A Sessions: formulation of Procore Quick Tips to open Weekly Sessions and the highlight of Procore issues on the ongoing working week.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of final SOP publishings for users to experiment full Procore experience on Core Tools and Project Management; SOPs for Action Plans, Forms, Punch Lists and Schedule Tools.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Cambalache Procore Kick-off Meeting for the designation of roles and responsibilities, presentation of Project Team and the intention of DCMC Partners with the use of Procore for Construction management. RG Engineering team (Jose Segarra, Xiomara Berrios), Sargent and Lundy Team (Robert Molner, Dean Ennes) and DCMC Site Team (Jorge Mercado, Luis Duque, Carlos De Jesus), DCMC Procore Team (Lauren Wells, Luis Roman)
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting with the Genera PR team, led by Jorge Bracero, to coordinate edits to the BESS Fact Sheet in Cambalache using Canva. Additionally, we will review and implement the necessary updates to the Genera website, specifically within the sections related to the BESS and Peakers projects.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 139 | 556 | 139 | Yes |  | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Work in Canva to edit the Newsletter for Bess and Peakers to include update information for all BESS and Peakers sites.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: I reviewed an email from Luis Moctezuma (DCMC) concerning the corrections to the Safety Manual and began editing various writing and clarity issues in the document.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review BESS Erosion and Sediment control plan for 4339_9510 BESS_Cambalache project.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule Procore minute report template considering guide and construction scheduling for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 worked on Teams meetings BESS&Peakers Weekly Schedule Meeting with CDM Smith employee Carlos Palomares and Manuely Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Costa Sur worked on schedule Procore minute report template considering guide and construction critical path scheduling for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | PREPA GENERA PR Deliverable 11 DR4339 work related on site Cambalache worked on schedule Procore minute report template considering construction critical path in scheduling for employee Gilberto Sucre (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project schedule documentation, identify critical path activities and reviewing logic. Make recommendations to improve time line . (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Resumed reviewing project schedule documentation, identify critical path activities and reviewing and change logic. Continued making recommendations to improve time line. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project schedule documentation, identify critical path and make time running durations. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes |  | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – (Day 2) Performed a detailed evaluation of the BESS Cambalache project’s Erosion and Sediment Control Plan (4339_9510). Reviewed site grading, drainage paths, and sediment containment strategies to identify any gaps or potential compliance issues. Cross-referenced the plan with FEMA PA program requirements and environmental permitting conditions. Documented findings to support internal quality control and facilitate project alignment with regulatory expectations
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Cambalache Procore Kick-off meeting with Andres Concepcion (DCMC), Luis Roman (DCMC) and Jose Serrano (RGE) for the 4339_9510 BESS Cambalache project.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (PART 2) Continue review BESS Erosion and Sediment control plan for 4339_9510 BESS_Cambalache project.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting with Shellsea Maysonet from MSC to review grants management processes, ensuring gain a clear understanding to assist with the implementation of procedures in Procore software.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 122 | 244 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Developing an updated reporting structure to provide more frequent project updates in a format that enhances the client's ability to track progress effectively.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 122 | 366 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting "Process Diagram Discussion for Financials" with Esther Rohena, Mark Merrit, D' Alexander Gonzalez, Rafael Calderon and José Ralat from DCMC to review grants management processes, budget, invoicing, procurement processes and the steps to implementing them into the Procore software.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting with Esther Rohena from DCMC to review grants management processes, ensuring I gain a clear understanding to assist with the implementation of procedures in Procore software.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 122 | 366 | 122 | Yes |  | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Evaluating the financial processes of projects to create a flowchart that enhances comprehension and facilitates the implementation of procedures within Procore software.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 74.2 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Hurricane Maria. Travel necessary for project inspection from home offices San Juan to Cambalache and Vega Baja Genera Site (18.47 Purpose Genera PR Installing Trailer Offices in Cambalache Genera site by Dueñas Trailers for DCMC. Meeting in Vega Baja with Jose Lopez, Gilberto Soto and Gabriel Morales (DCMC) IN Vega Baja Genera Site
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 112 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Yabucoa Gas Turbine to Cambalache Power Plant to Yabucoa Gas Turbine. Purpose - Relocation of the DCMC Partners Mobile Office to the Cambalache Site.
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 84.7 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Cambalache Power Plant (18.470985, -66.699693) to CVP Guaynabo. Purpose, Office Trailer Installation. Attendees, Jean Pierre Menay (DCMC), Andres Concepcion (DCMC), Gabriel Morales (DCMC) & Harry Del Valle (DCMC). Topics discussed, walked through Office Trailer Area, discussed Office trailer Installation by Duenas Trailer, discussed Office trailer utility's needs. Supervise the installation of the office trailer. TOTAL MILEAGE 121 miles
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 4.97 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- traveled back to residence in Guaynabo from Central San Juan facility. The objective of the visit was to support inventory audit operations, evaluate the progress of inventory reconciliation procedures and provide operational support to Mr. Milton Flores from DCMC
2025-05-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Browne, Paul | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 5.32 | 0.7 | Yes |  |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- traveled directly from residence in Guaynabo to Central San Juan facility to support inventory audit operations. The objective of the visit is to evaluate the progress of inventory reconciliation procedures and provide operational support to Mr. Milton Flores from DCMC
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 4105.92 | 4105.92 | 4105.92 | Yes |  |  | Duenas - Trailer rental, delivery and set up charges for Cost Sur location relating to the Genera project Deliverable 11
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 3856.32 | 3856.32 | 3856.32 | Yes |  |  | Duenas - Trailer delivery and set up charges for Cambalache location relating to the Genera project Deliverable 11
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 910 | 910 | 910 | Yes |  |  | Duenas - Stair intallation for Camabalche trailer location relating to the Genera project Deliverable 11
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 held a weekly coordination meeting with the team. Items discussed were to SOP and coordinating everyone's role and responsibility German Nunez, GENERA Rafael Pabon, CDM smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC Harry Del Valle DCMC Gilberto Sucre DCMC Foster Veazey Lemoine Jean Pierre Menay DCMC Sheila Torres-Sterling DCMC Francisco Feliu (Genera)
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in the weekly Peaker's project management update, reviewed status of costa sur RFP clarifications from the sub-contractors, discussed alternate plans for the relocation of existing materials and equipment, reviewed timelines. German Nunez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Addressed Peakers' Management Execution Issues between CDM Smith and DCMC Partners - Misalignment between Roles & Responsibilities of the two companies. Feedback provided by Abraham Velazquez - DCMC Partners.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria General Overall Program Update Vega Baja Phase I and Phase II with Jose Lopez & Jaime Pesquera - DCMC, Cambalache with Andres Concepcion DCMC and Costa Sur with Carlos Rodriguez and Harry del Valle DCMC.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Discussed Homeca's response to their contract obligations under their Optional Pricing Scopes of work with Franklin Colmenares - CDM Smith.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluated Procore Draft SOP for Submittals prepared by Lauren Wells - DCMC Partners.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria EHS Program update meeting with Jean Pierre Menay DCMC discuss outstanding decisions pending Genera's input in Cambalache, Draft Manual for Genera and Site-Specific trainings and guidelines for Costa Sur and Aguirre.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluated Supplies, Material and Equipment quotes to support construction site offices with Harry Del Valle (DCMC)
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated MAY PMO Monthly Report for BESS Sites
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review draft Quality Assurance program to be implemented across projects Sites.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Project Punchlist list update, Phase II Proposal and MTP rigging and relocation quote. Diesel Transfer restart on Monday, Temporary Power Line relocation by Luma, Pricing acceptance by Homeca for Phase II, PUI Permit Approval and Modification, Preparatory work prior to MPT relocation. Discussion with Jose Lopez and Jaime Pesquera DCMC.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting ARG Ceres - Vega Baja Update Main two action items pending are Geo Piers design calculations and Pre- Cast Value Engineering Proposal from ARG Ceres. The discussion also got off track with the Structural Steel Platform - VE for Cambalache. CDM Smith, CSA Group, Sargent & Lundy and DCMC Partners.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting Concentrated on Construction Staffing updates with new hires, upcoming, resignations and decline offers. Procore Training Update. Office Trailer Mobiliziations and equipment deliveries, Lean roll-out, PMO RFP status. After the main meeting a second discussion concentrated to the salary justification on one of the schedulers for the program. Michael Merritt, Foster Veazey, Frances Vallejo, Anneilia Holton, Lauren Wells, and Gilberto Sucre DCMC.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Management Project Meeting Weekly Meeting. Main Topics was equipment delivery dates throughout the program, payment milestones, change orders and next week visit to the project sites in PR by Tesla. Tesla, Sargent & Lundy, CDM Smith, CSA Group and DCMC Partners.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Yabucoa Meeting with Gabriel Morales, Abraham Velazquez, and Gilberto Sucre - DCMC Partners. BESS and Peaker's Roles & Responsibilities.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Foster Veazey, Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Lauren Wells, Barry Scanlon, Mark Merritt, and Mike Merritt.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore financials videos from Procore team on setup.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing budget changes in Procore for 11855 to encompass Cost codes based on previous entries.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financials in preparing 11855 for contracts and invoices.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences for adding new users.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Procore Weekly Q&A with Luis Roman (DCMC), Theresa Perez (DCMC), Pedro Cabrera (DCMC).
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Raissa Borges (DCMC) to discuss Procore financials project.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) to discuss open Procore items to tackle as a team.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore training schedule.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on meeting coordination's for next week.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt (DCMC) to discuss program staffing and overall program goals.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up new project in Procore for 11855 for Demo and Installation.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes |  | Remote | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Frances Vallejo, Lauren Wells, Gilberto Sucre, Foster Veazey, Ada Diaz, DCMC. Discussed update on project, job offers, PROCORE training schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the safety and Health Cambalache Site Genera presentation. Review emails for EHS Aguire and Cambalache Genera Site.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the safety manual for Genera.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Time | 3 |  | 184 | 552 | 184 | Yes |  | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting with Harry del Valle and Carolyn Baez (DCMC) about EHS supplies necessary in all Genera projects. Call with David Gilde by Best Fire for fire equipment necessary in all Genera Projects Site. Review the fire equipment necessary for the projects.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Carolyn Baez and Harry del Valle (DCMC) to discuss list of materials needed for the trailers. Evaluate the spreadsheet and compare prices.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended Procore Project weekly discussion for the PMO to discuss Procore next steps. Participants: Franklyn Colmenares (CSA), Rafael Pabon (CDM), Lauren Wells (DCMC)
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes |  | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss staffing update, vacant positions at Costa Sur, Aguirre and Yabucoa, Procore financial candidate needed, trailer installation update and equipment needed coordination. Participants: Michael Merritt, Ada Diaz, Anneilia Holton, Gilberto Sucre, Lauren Wells (DCMC). Also, had a conversation with Gilberto Sucre and Michael Merritt to discuss Scheduler candidate justification needed for Cambalache and Vega Baja.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes |  | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Rafael Calderon and Glorimel Torrado (DCMC) to discuss contract management update for Tesla and Siemens.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued supporting the Regulatory Team in assembling seven additional FOMB Contract Approval Request packages. Assisted in gathering, reviewing, and organizing all required documentation in accordance with FOMB’s Contract Review Policy. Ensured each package included properly formatted appendices, fully executed requisition materials, and clearly labeled supporting documents to facilitate a smooth and compliant approval process. Collaborated closely with the team to maintain consistency, accuracy, and timely submission across all packages.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria - Generation Fleet - Supported the Regulatory Team in assembling eight FOMB Contract Approval Request packages. Assisted in gathering, reviewing, and organizing all required documentation in accordance with FOMB’s Contract Review Policy. Ensured each package included properly formatted appendices, fully executed requisition materials, and clearly labeled supporting documents to facilitate a smooth and compliant approval process. Collaborated closely with the team to maintain consistency, accuracy, and timely submission across all packages.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 184 | 644 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Finalized the development of the sourcing integration Scope of Work by incorporating the most recent use cases, ensuring comprehensive coverage of functional and technical requirements. Conducted a thorough review of the document to confirm its accuracy and completeness, with no errors identified.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 184 | 644 | 184 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Uploaded the latest Financial Tracker data into the Genera Connect Financial Tracker and conducted a review session with Jose Ralat and Esther Rohena from DCMC to verify data accuracy and presentation. Additionally, presented the finalized sourcing integration Scope of Work to Sulinnette Perez from Genera PR to collect feedback. The document will be further reviewed with IT stakeholders from Genera PR to ensure alignment with internal requirements beyond procurement.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Homeca continue to demolished corrugated roof areas to disposed on their Location. Jorge Sanchez from Homeca picked for disposal 20CY Bin towards Homeca location in Caguas, Homeca Continue housekeeping applying pressure wash to areas
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review of Genera Bess state of design power point, specifically demolition plan, existing conditions and foundation plan.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Request for Proposal drawings review of division of responsibilities for future subcontractor.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meetings with Gilberto Sucre, Harry Del Valle, Jean Pierre Menay and Abraham Velazquez (DCMC) to discuss Yabucoa BESS project plan details and preliminary drawings.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluation of the Scope of Service for the YABUCOA BATTERY ENERGY STORAGE SYSTEM (BESS) FACILITY. Meeting with Harry del Valle (DCMC) to discuss the Scope of Service received to ensure all parties understand the project's goals, tasks, responsibilities and deliverables to prevent delays for a more efficient construction process.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria resumed reviewing project drawings and RFP documentation for the Costa Sur BESS (Battery Energy Storage System) project to ensure technical accuracy, compliance with project requirements, and alignment with engineering standards.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued coordination with Carlos Rodriguez (DCMC) to plan the installation of trailer office facilities at the Costa Sur project site. Discussed site layout, utility connections, delivery logistics, and timeline requirements to ensure readiness for upcoming project phases.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue with held a coordination meeting with Carlos Rodriguez (DCMC) to plan the installation of trailer office facilities at the Costa Sur project site. Discussed site layout, utility connections, delivery logistics, and timeline requirements to ensure readiness for upcoming project phases. Follow-up actions were outlined to align with construction schedules and operational need
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading the following topics from the occupational health and safety talk of DCMC: What is Occupational Health and Safety? Main risks in the workplace, Consequences of workplace accidents
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading the next topics for take change if is necessary: Rights and duties of the worker, Role of the employer in safety, Correct use of PPE, Safe work habits
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue with the review at the next topic of the Health and Safety Talk at DCMC: What to do in case of emergency
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Revision of The Occupational Health and Safety talk at DCMC to make changes that adapt to the conditions and particularities of the Bess Aguirre Project
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja BESS job site. Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the Procore platform. Hurricane Maria. MST met with Gilberto Sucre (DCMC) and Jaime Pesquera (DCMC) to discuss the current project Phase situation with the Demo Contractor.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 2 | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS PROJECT. I had several phone calls with the GWC (HOMECA) project manager, Carirma Sanchez, and the company administrator, Eduardo Ramos, to discuss the project contract requirements and contract progress. Participated in Team Meeting with Sargent & Lundy Staff, Robert D. Molner, Gilberto Sucre (DCMC), Enrique Laya, CDM Smith, and Angel Alice Rodríguez Sargent & Lundy to discuss the Phase II Request for Comments to the contract (4339_9510) documents.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on trailer offices spreadsheets with materials & price. Quoting materials in different places for cost control. Discussed Desing offices and conference areas Layout & Price the List of materials needed for office in projects with Frances Vallejo (DCMC) and Gilberto Sucre (DCMC).
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working with the proposals for BESS Yabucoa RFP 231175. Verify that the proposals are complete according to the project documents. Review Proposals to make recommendations. Starting coordination with Danny Duenas (Duenas Trailers) the Delivery of the Office Trailers next Wednesday June 4th in Central Aguirre (BESS Project) and Yabucoa BESS Project on June 5th.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Generate PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Verification of documentation related to the Clean Water Act and MPDS standards.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Work is being done to create safety guidelines for environmental impact mitigation according to the Genera PR contractor manual for the BESS CAMBALACHE project.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Generate PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Work is being done to create safety guidelines and recognize global harmonization systems for risk communication involving chemical agents for the BESS CAMBALACHE project.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed contractor's (RG Engineering) Cambalache Structural preliminary design for Cambalache BESS steel platforms. This set of drawings will be coordinated into the final drawings package for the project.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Compliled this week (May 26-May 30) project pending action items to be adressed for next week. Generated pre-report for next week team coordination.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received and reviewed structural design details from contractor (RG Engineering - Jose Robles). Evaluated and distributed to project designer (Sargent and Lundy - Robert Molner) for coordination and consideration in Issued For Construction drawings.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated a list of pending items from GeneraPR on actions to be completed prior contractor mobilization. Provided list to Jean Pierre Menay (DCMC)
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Researched and reviewed environmental regulations compliance and considerations in the Cambalache project.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a targeted inventory recount at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC. The objective was to validate the accuracy of prior cycle count results, reconcile discrepancies between physical inventory and system records, and confirm transactional consistency. The recount process included cross verifying bin-level item quantities, assessing storage compliance, and ensuring data integrity within the inventory management system. Recount was from locations AK 024 to AK 034.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a focused variance investigation to detect and analyze recurring inconsistencies between physical stock levels and digital inventory records from locations AK 024 through AK 034. The analysis involved tracing data anomalies by reviewing item catalog profiles, transaction logs, and the chronological flow of inventory activity. This initiative aimed to strengthen the fidelity of inventory reporting, increase alignment between warehouse operations and system controls, and reinforce adherence to inventory standards.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a detailed inventory data analysis and generated system-aligned cycle count worksheets to support scheduled reconciliation activities at the Palo Seco warehouse. The engagement was conducted in coordination with Mr. Giovanni Taffanelli from DCMC, focusing on operational compliance and procedural standardization. Key task included validating item master data, cross-referencing physical locations with system records, and ensuring bin-level stock accuracy. Additionally, materials required for the count process were identified and staged to optimize execution flow. These activities were designed to strengthen inventory integrity, reduce system variances, and ensure readiness for full-cycle inventory validation aligned with project deliverables and audit controls.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an early morning job briefing alongside Hernan Machado, Juan Vallejo and key DCMC warehouse personnel to address and review discrepancies identify during the prior day's operations. The objective of the session was to reinforce the importance of accurate data entry, adherence to procedural standards, and maintaining inventory integrity. Additionally, compliance with establish procedure, and the maintenance of inventory integrity. Key topics included the analysis of recurrent issues, the implementation of corrective measures, and identification of opportunities for operational improvement. Discussions also focused on standardizing processes, mitigating risks, and enhancing consistency across warehouse functions to ensure alignment with project goals.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco warehouse structured a comprehensive inventory performance report for Mr. Anthony Vega of Genera PR. The report consolidated data from all active warehouse locations and incorporated critical metrics including catalog ID reconciliation, unit-level stock validation, valuation summaries, and discrepancy analytics. The assessment included analysis of cost variances, system to physical mismatches, and compliance with established maximum and minimum stock thresholds. Visual performance indicators were applied to highlight the operational status of each site. This output supports data driven decision making, identifies systemic gaps, and enhances reporting transparency for executive level review. Locations reviewed range from AK 024 to AK 034, AE 060 to AE 103, AB 031 to AB 033, BF 001 to BF 008, AG 017 to AG 024.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed cycle count procedures for inventory locations assigned for the day, specifically covering zones AK 024 through AK 034. This task supported the initiative to enhance inventory accuracy and ensure alignment between physical stock levels and system balances. Activities involved the verification of item master data, validation of bin level quantities inspection of labeling integrity and environmental storage conditions, and identification of anomalies such as missing, misplaced, or incorrectly classified items. The effort also contributed to maintaining transactional accuracy and improving the overall reliability of inventory management system.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information on NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status. Batch 5
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information on NME and Critical Components based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status. Batch 4
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Division Concrete Metals Topic Structural Steel:.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Division Carpentry Topic Rough Carpentry, Shop Fabricated Wood Trusses, Finish Carpentry/Millwor, Division 7 – Thermal and Moisture Protection Topic Waterproofing.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Division Concrete Masonry Topics, Testing and Inspection, Mortar Joints, Cement for Mortar:.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes |  | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit Preliminary DCMC Cambalache Power Plant BESS Program Quality Control Plan, Division Concrete Metals Topic Structural Steel, Quality Assurance, Submitals, Testing Equipment and Personnel Bolting.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- I Supervised the Contractor Homeca, this week they are removing and cleaning of all scrap metal material from the floors turbine UVB 1-1 and turbine UVB 1-2.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | PREPA Genera PR Deliverable 11- Project Management DR 4339 - Hurricane Maria- I continued throughout the day supervising the contractor Homeca Recyclers, this week and today they kept removing and cleaning of all scrap metal material from the floors from turbine UVB 1-1 and turbine UVB 1-2, with sweepers and the hydraulic scissors.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Homeca continue to demolished corrugated roof areas to disposed on their Location. Jorge Sanchez from Homeca picked for disposal 20CY Bin towards Homeca location in Caguas, Homeca started housekeeping applying pressure wash to areas.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks, and ensure project success. Make sure they comply with the safety while conducted Demolition and clean the areas by Homeca. Homeca continued cleaning the field housekeeping and moving materials to continue dismantling scraps. safety and success of the work performed. Worked on house demolition on site. Retrieving concrete. Homeca continue to demolished corrugated roof areas to disposed on their Location. Jorge Sanchez from Homeca picked for disposal 20CY Bin towards Homeca location in Caguas, Homeca Completed housekeeping applying pressure wash to areas cleaning dirt from wash.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 164 | 82 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 Meeting with Frances Vallejo DCMC and Glorimel Torrado DCMC - Catch Up Meeting Contracts Discussing current status of contract execution, Major Issues and resolutions.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Continue working on Siemens Energy Contract #00106588. Review deliverable Schedule based on project development and new change order #2 request. Contract review and documentation to identify allowable task, scope and impact to contract schedules. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #293566-12 for TO#2 Jan 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, MegaPacks and tariffs for all plants. Meeting participants TESLA (Michael Grabstein, Elizabeth Arentsen, Allin Luong), CSA (Franklyn Colmenares), and DCMC (Rafael Calderon and Glorimel Torrado)
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes |  | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- At the Palo Seco warehouse, preparing the lists from locations AK024 to AK034 to begin the cycle counts.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AG017 to AG024
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AG017 to AG024
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AG017 to AG024
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AG017 to AG024
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AG017 to AG024
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 00 031 to AB 00 033; BF 00 001 to BF 00 008
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 00 031 to AB 00 033; BF 00 001 to BF 00 008
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 00 031 to AB 00 033; BF 00 001 to BF 00 008
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AE 060 to AE 103 using Cycle Count List # 865/869
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AE 060 to AE 103 at the Aguirre warehouse to start the cycle counts.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AE 060 to AE 103
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AE 060 to AE 103 using Cycle Count List # 8858/866/867
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #874 and 875 from locations AK024 to AK034 for a total of 428 pcs.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 |  | 152 | 418 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AK024 to AK034 Cycle Count List # 861.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK024 to AK034.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes |  | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 874 and 875 locations AK024 to AK034
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control - Data Managemen t - Jobos Peakers Setup External S&L Specs (not final)/ Daguao Peakers Setup External S&L Specs (not final) /Coordination w Rafael Pabon (CDM) on S&L Specifications External Dropbox for NON FINAL-WIP only/ Cambalache Coordination with Paola Arroyo (DCMC) on Community Outreach Documents/Coordination of Data Incoming Documents for all projects with Lauren Wells (DCMC) & Luis Roman (DCMC)/Coordination of Incorporating Critical Components Tracking (Financial & Procurement) into Procore with Lauren Wells (DCMC) Luis Roman (DCMC) Pedro Cabrera (DCMC)
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control - Data Management / Vega Baja BESS/Cambalache BESS/Costa Sur BESS Review & process all Community Outreach Documentation
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review potential forms to be included at the Core Tools for multiple projects to track the activity and delivery of critical components inside the projects.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 |  | 151 | 264.25 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Procore Specifications Tool to define upcoming project phases as for naming convention and folder structure per project phase and contractors.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Meeting hosted by Franklyn Colmenares (CSA) to discuss the progress of Procore use and implementation among active projects; tracking of SOPs status for publishing, review of the Financials Tool status (still in final phase); also discussed the implementation of naming convensions inside different core tools.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 151 | 113.25 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Q&A session with Theresa Perez and Pedro Cabrera (DCMC) and Lauren Wells (Lemoine): discussing the instrumentation, control and critical components features inside Procore for users covering the Critical Components Role.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of Aguirre documentation uploading to rectify compliance on project management standards: definition of RFI purpose and use; submittals regarding information with no approval required (permits, others)
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Catch-up Meeting with Lauren Wells (Lemoine) and Theresa Perez (DCMC) discussing issues regarding downloading attachments from submittals tool; exporting submission items to Documents Tool.
2025-05-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes |  | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on potential forms to be included in core tools for the tracking of Critical Components; creation of spreadsheets to track Purchase Order and Delivery activities while maintaining specifications and approvals at the Submittals Tool.
118819.75
118819.75
[13 empty] | construction mgmt= | 116387.25
[13 empty] | Community Engagement | 2432.5
118819.75

## June
Entry Date | Client | Proj level1 | Proj level2 | Proj level3 | Client title | Asset | Task | Task Group | Task Description | Activity Type | Hours | Column1 | Activity Rate | Activity Extended | Billing Rate | Line Billable | Invoice Number | Work Site | Narrative
2025-06-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 873.6 | 873.6 | 873.6 | Yes | 146793 |  | Duenas Trailers - 8'x20' Flex-tainer, Rental, 6/1/25 - 6/30/25 - Vega Baja
2025-06-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 140.4 | 140.4 | 140.4 | Yes | 146793 |  | Duenas Trailers -8'x40' Flex-tainer, Rental, 6/28/25 - 6/30/25 - Cambalache-Arecibo
2025-06-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 30 | 30 | 30 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits and travel from Genera offices to CVP offices
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore financial items.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Peakers check in meeting discussed current status of the Peakers projects and the scheduling of activities to ensure timely project completion, efficient resource allocation, cost control, and risk mitigation. German Nunez, GENERA Rafael Pabon, CDM smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC Harry Del Valle DCMC.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Participated in meeting BESS&PEAKERS project needs. Discussed Peakers needs for Costa Sur site and preparing to receive bids from contractors. German Nunez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC Harry Del Valle DCMC.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- RFC Meeting ARG Ceres / Vega Baja Site reviewed pending items to evaluate mainly Value Engineering calculations for Sargent & Lundy review and approval. Participants: Carlos Hernandez -ARG Ceres, Gabriel Perez - CDM Smith, Mike Kuczynski -Sargent & Lundy and Gilberto Sucre -DCMC Partners.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore - DCMC Financials Tools - Continuation Implementation review led by Lauren Kennedy ( Lemoine) - Procore Invoicing Process and Flow Chart for Approval with DCMC Team Rafael Calderon, Lauren Wells, Glorimel Torrado and Gilberto Sucre
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Reviewed final contract revisions submitted by ARG Ceres Legal Counsel for Installation Phase of Project.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence Catch-up reading and responses
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check-In Weekly Program Status Update led by Gabriel Perez CDM Smith. Update highlights were presented for entire BESS program. Participants from Jesus Cintron -Genera, Gabriel Perez CDM Smith, Franklyn Colmenares - CSA Group, Mike Kuczynski - Sargent & Lundy, Gilberto Sucre - DCMC Partners.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM Weekly coordination. Preparation and later update with Franklyn Colmenares - CSA Group discussed projects updates for Vega Baja, Cambalache, Costa Sur & Aguirre. Project needs were also discussed to be raise to Genera for expediting.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Progress and Status of Vega Baja and Aguirre sites discussion with Jose Lopez - DCMC.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria General Management Tasks : * Procore Submittal Process SOP Procedure approval. * Internal Response to Aguirre RGE Acceleration Proposal * Sargent & Lundy coordination with Mike Kuczynski on Design action Items. * Conversation with Genera Legal * Tesla Site Visit Coordination.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Internal Meeting PM /CM Team meeting concentrated on Design Deliverables Priorities from Sargent & Lundy for Vega Baja, Cambalache, Cost Sur & Aguirre. Meeting with Mike Kuczynski - Sargent & Lundy, Gabriel Perez - CDM Smith, Franklyn Colmenares - CSA Group & Gilberto Sucre DCMC
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Evaluation of original RFP to prepare for Homeca's response to Phase II Demolition included in contract as Optional Pricing.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Ricardo Pallens (Genera), Carlos Palomares (CDM Smith), Joaquin Quinoy (Genera), Gabriel Perez (CDM Smith), Mike Kuczynski, Nelson Rosado (Sargent and Lundy), Franklyn Colmenares (CDM Smith) Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial budget import tools.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences for permissions templates, SOP reviews and updates.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore) and Esther Rohena (DCMC), Glorimel Torrado (DCMC), Gilberto Sucre (DCMC), Rafael Calderon (DCMC) for Procore financial discovery calls.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) for Procore weekly check-in call. Discussed Procore progress, issues and reported observations; the export of submittals attachments for document control purposes, project management implementation through Procore features and the revision of submittals process for contractors and staff response time.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing workshop links and material to send to Vega Baja DCMC team so they can do the online course prior to our discussion call tomorrow.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Observations and RACI chart.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Peakers Check-in.Rafael Pabon (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for Vega Baja for drawings tool.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Validated the upload of reports into the Genera Connect Financial Tracker and identified issues related to data consumption within the application that require resolution. Reviewed outstanding items related to Genera Connect in preparation for the upcoming weekly Genera PR meeting. Additionally, continued the creation of user accounts for Genera Connect Timesheets to support onboarding of Genera HQ employees onto the platform.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review and support the Diesel transfer process from Vega Baja Genera Site to Palo Seco Genera Site verifying the use of the right equipment and proper procedures to ensure safety measures are in place to minimize risks.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the Procore progress by Vega Baja and Cambalache jobs. Modules in EHS Genera presentation to Luis Echevarria (DCMC Costa Sur Genera Site EHS coordinator).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 184 | 414 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Osvaldo de Jesus (GENERA) about all project Genera Status. Conference call with Gilberto Soto (DCMC) by Vega Baja Genera project status. Conference call with Harry del Valle (DCMC) about Cambalache trailers offices status.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Daniel Duenas (Duenas Trailers) and Harry del Valle (DCMC) about the trailers offices needed in Genera Sites. Conference call with Luis Moctezuma (DCMC) about EHS review progress by Aguirre. Conference call with Juan Reyes (ARAMSCO) about Safety Items need in all Genera Projects. Review the catalog for Safety Zone require safety items in Genera Projects. Review the Costa Sur drawing with Luis Echevarria (DCMC).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting with new hire Luis Echevarria (DCMC) to provide him an introduction of the BESS and Peakers project, organization and explain de program.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Call with Jesus Cintron (Genera) to discuss staffing update and other related matters for the PMO.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Cambalache update meeting to discuss site needs and status of the contract with RGE. Participants: Andres Concepcion, Jorge Mercado, Luis Reyes (DCMC).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers Check In meetings with project management teams. The meetings were focused on the RFP process, demolition phase , Tesla contract deliverables and Siemens contract. Participants: Gabriel Perez (CDM), Rafael Pabon (CDM), Jesus Cintron (Genera), Rafael Calderon (DCMC), Sheila Tores (DCMC), German Nunez (Genera), Giberto Sucre, Abraham Velazquez, Raissa Borges (DCMC), Carlos Palomares (CDM).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordinate with Carolyn Baez and Harry del Valle (DCMC) the materials and equipment final list and coordinate with the suppliers the availability of items.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Michael Merritt (DCMC) to discuss PMO hourly staff meeting with site employees to discuss change in category from hourly employees to salary employees.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended BESS and Peakers Project needs meeting with Jesus Cintron (Genera) to discuss needs for the PMO and per site regarding RFP process, demolition phase and other needs at the sites. Participants: Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Gabriel Perez (CDM), Franklyn Colmenares (CDM).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued supporting the Regulatory Team in assembling FOMB Contract Approval Request packages. Reviewed and finalized Appendix A for five requests, ensuring accuracy and compliance with FOMB requirements. Converted and verified consistency across all documents to support a complete and well-organized submission package.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Marc Maceira, Carlos González and Ginnell Torres
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Hurricane Maria - Participated in the weekly BESS and Peakers Project Needs meeting with Jesús Cintrón. Reviewed the current status of key workstreams and discussed high-priority items requiring coordination or follow-up. Contributed updates and aligned on next steps to ensure continued progress across both projects. Genera: Jesús Cintrón, Germán Nuñez. DCMC: Abraham Velazquez, Frances Vallejo. CDMSmith: Franklyn Colmenares & Rafael Pabón
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly DCMC coordination meeting to prepare the client briefing for Genera. The team discussed and aligned on key topics, including grant management, cash flow status, procurement activities, technology initiatives, and other ongoing projects. Contributed updates and insights on ongoing BESS and Peakers projects to support a cohesive and well-informed presentation to the client. DCMC Team: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Marc Maceira, Carlos González and Ginnell Torres
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 184 | 138 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Verified the status of key workstreams and high-priority items to prepare for the weekly BESS and Peakers Project Needs meeting.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued supporting the Regulatory Team in assembling FOMB Contract Approval Request packages. Reviewed and finalized Appendix A for the remaining nine requests, ensuring accuracy and compliance with FOMB requirements. Converted and verified consistency across all documents to support a complete and well-organized submission package.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued supporting the Regulatory Team in assembling two additional FOMB Contract Approval Request packages. Assisted in gathering, reviewing, and organizing all required documentation in accordance with FOMB’s Contract Review Policy. Ensured each package included properly formatted appendices, fully executed requisition materials, and clearly labeled supporting documents to facilitate a smooth and compliant approval process. Collaborated closely with the team to maintain consistency, accuracy, and timely submission across all packages.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 184 | 460 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Drafted cybersecurity requirements for inclusion in the Procurement Automation Scope of Work, focusing on ensuring secure data handling, access controls, and compliance with Genera PR’s internal IT and security standards to support a secure and robust integration framework.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervising contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety measures while transferring Diesel from Vega Baja tank towards truck tankers for transport towards Palo Seco. Trucks number 545,510,507 and 509. Contractor: ADS company.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur-Drawings & RFP review of project details Drawings and RFP review of project details to minimize errors, and reduce modifications.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur- Review of drawings & details of RFP Costa Sur specifics, review of project details and location of intial ground work.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluation of the Scope of Service for the YABUCOA BATTERY ENERGY STORAGE SYSTEM (BESS) FACILITY. Meeting with Harry del Valle (DCMC) to discuss the Scope of Service received to ensure all parties understand the project's goals, tasks, responsibilities and deliverables to prevent delays for a more efficient construction process.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Axel Cruz (Genera) to Discuss and review the plan to relocate and energized the new DCMC mobile office in the Yabucoa Site.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue with the evaluation of the Scope of Service for the YABUCOA BATTERY ENERGY STORAGE SYSTEM (BESS) FACILITY. Meeting with Harry del Valle (DCMC) to discuss the Scope of Service received to ensure all parties understand the project's goals, tasks, responsibilities and deliverables to prevent delays for a more efficient construction process.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Continue reviewing RFP-4898 from RG Engineering document and revised email correspondence project to ensure project needs and scope are defined and mitigate risks.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Verification of drawings in the PROCORE project area in order to study future work to be reviewed. Also do a complete trailer office utilities verification to ensure smooth progress and timely completion of project.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Learning and review Site Level Considerations for the Safety Bess installation at Aguirre Project
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Learning and review Fire Protection Systems for the Bess at Aguirre Project
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue learning and review Fire Protection Systems for Bess at Aguirre Project
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Learning and review Code Requirements for Safety Bess Installation at Aguirre Project
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS - Dismantling, Decommissioning and demolition works planning for phase II. Homeca Recycling should submit an LED abatement removal certification to ensure they can safely handle and remove lead hazards, protecting workers and staff from lead exposure.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS - Weekly look-ahead schedule review and discussion with the DCMC team, Gilberto Soto, Jaime Persquera, and Gilberto Sucre: Coordination and logistics for Coordination and logistics for Homeca's week work plan.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working with the proposals for BESS Yabucoa RFP 231175. Verify that the proposals are complete according to the project documents. Review Proposals to make recommendations. Preparing DCMC Quality Control Plan.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working with the proposals for BESS Yabucoa RFP 231175. Verify that the proposals are complete according to the project documents. Review Proposals to make recommendations. Coordination with Danny Duenas (Duenas Trailers) the Delivery of the Office Trailers next Wednesday June 4th in Central Aguirre (BESS Project) and Yabucoa BESS Project on June 5th.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Work to develop safety guidelines for the safe use and handling of cranes in the workplace, in accordance with OSHA 1926 sub-CC standards to prevent accidents, injuries, and costly damages.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Work continues to develop safety guidelines for the safe use and handling of cranes in the workplace, in accordance with OSHA 1926 sub-CC standards.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Work continues to develop safety guidelines for the safe use and handling of cranes in the workplace, in accordance with OSHA 1926 sub-CC standards. This task also includes developing guidelines for rigging systems according to ASME standards.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Monitored and reviewed project data and pending actions in Procore for follow up. Analyzed the project open RFIs (RFI #19: COMMENTING: Response to RFI #17 (Questions based on answered RFI #17) and Submittal performance to ensure rapid actions.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed latest project milestones (updated on May 30, 2025) and latest construction schedule to evaluate activities and sequences for the construction.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Coordinated Duenas Trailers (vendor) through Harry Del Valle (DCMC Partners) visit to site to continue installation of office trailer in Cambalache. Cabling structural support will be installed on 6/3/2025.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Contacted by phone Jorge Mercado (DCMC) to discuss the progress on the Cambalache site specific Safety Orientation presentation. Contacted Luis Damudt (DCMC) to align on the Site laydown plan review and comments.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued evaluation of contractor (RG Engineering) proposed Laydown or staging plan. This plan is needed to be approved for construction start.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed TECHNICAL SPECIFICATION FOR CAMBALACHE BATTERY ENERGY STORAGE SYSTEM (BESS) GENERAL WORK CONTRACT (GWC) document. Reviewed Submittals section to plan submittal process in project.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 1 | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue supervising the Diesel transfer by ADS contractor (3) Diesel trucks has leave the facilities to Palo Seco. Send an email to Mike Kuczynski of S&L for the verification of a CES Plan for Phase 2 of Vega Baja Project. Send email to Ida Ramirez of ACR/CERES to provide list of contact of ARG/CERES personnel.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with contractor Homeca and ADS that start today the Diesel Transfer from Vega Baja to Palo Seco. Homeca contractors are cleaning at demolition site. Reviewing email related to Vega Baja BESS project.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - Meeting with Ida Ramirez and Carlos Hernandez of ARG; Gilberto Sucre and Eduardo Rivera of DCMC; and Wilfredo Sierra, Gary Jasutis, Margolis Jordan, and Angel Alicea of S&L. Meeting to discuss the RFC generated for ARG in regard of the Vega Baja BESS projects.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue supervising the Diesel transfer by ADS contractor (2) Diesel trucks has leave the facilities to Palo Seco in the afternoon for a total of (5). The last truck arrives at Vega Baja for last fueling and fulling is in process. Reviewing Procore online video in regard of tomorrow discussion in regards of RFI and Submittals. Final truck with Diesel leaves at 4:50pm contractor Homeca and ADS is cleaning area and organizing all hose for tomorrow transfer.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-facilitated a strategic coordination session with Hernan Machado, Juan Vallejo from DCMC in conjunction with key warehouse staff, to evaluate the current status of inventory operations. The session aimed to identify procedural inconsistencies, analyze workflow gaps and promote adherence to standardize inventory control methodologies. The meeting also served to review the effectiveness of ongoing inventory tracking mechanisms, discuss corrective actions for previously moted process inefficiencies, establish a unified approach to documentation, physical counts and locations validation. Focus was placed on improving procedural alignment, enhancing team accountability, and sustaining operational continuity throughout the cycle count process.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled ABC cycle counts across assigned inventory zones as part of the ongoing initiative to enhance inventory accuracy, system integrity, and compliance with operational standards. Activities focused on validating physical stock against system records, detecting and resolving discrepancies in reported quantities, and assessing data integrity across multiple storage areas. Task included verifying proper labeling, storage compliance, and adherence to define inventory protocol. Inventory locations reviewed during this session ranged from AE 104 through AE 144.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-a focused inventory validation was carried out at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. The scope of this operation involved auditing ten specific storage locations to verify part numbers and item descriptions, assess quantity accuracy, and reconcile physical stock against the system inventory records. The effort also included addressing discrepancies, improving data integrity, and reinforcing internal inventory controls by aligning practices with asset management standards. This task was conducted to enhance the reliability, traceability and overall transparency of inventory records. Locations reviewed during this session included AE 104 through AE 144.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Aguirre warehouse, a comprehensive inventory performance report was prepared for Mr. Anthony Vega of Genera PR. The report consolidated data from all warehouse locations and included catalog ID validation, unit count verification, cost analysis, and discrepancy identification. Inventory levels were evaluated against authorized maximum and minimum threshold. Additionally, percentage-based metrics were used to visualized stock accuracy, inventory coverage, and overall inventory condition across all sites. The assessment covered storage locations ranging from AE 104 to AE 144, AG 025 to AG 034, AB 035 to AB 045, AL 016.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- participated in a virtual meeting via Microsoft Teams with Ms. Maria Sanchez from Genera PR, and DCMC staff to review and discuss the weekly progress of ongoing project activities.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed planning and preparatory activities for inventory operations at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. The objective was to review and validate key inventory data in preparation for upcoming cycle count procedures. Core tasks included verifying item placement accuracy, reconciling inventory records, and coordinating personnel and asset allocation to strengthen procedural compliance and enhance overall operational readiness.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane –as part of a variance analysis at the Aguirre warehouse, conducted a detailed diagnostic to detect inventory discrepancies and assess data irregularities impacting stock precision. The evaluation focused on strengthening internal inventory controls by identifying root causes of anomalies, enhancing data integrity, and ensuring alignment with procedural standards. The reviewed covered storage locations ranging from AE 104 through to AE 144.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Follow-up and consolidation of delays in critical equipment deliveries – report preparation for GENERA-PR Components analyzed: Fuel control valve, Demin RO system pump, Breakers 480 & 4160, EDI system, Steam bypass valve, Safety valve, Acid pumps P3 and P4, Fuel Transfer Pump, Generator breaker 13kv, Fuel skid solenoid valves, Recirculating valves &Repair Cooling Tower Unit 5.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review Contract 106280 This task included reviewing Milestone and Deliverers and ensuring compliance with FEMA cost reasonableness guidelines. The objective is to support accurate and justifiable funding requests, contributing to proper documentation and audit readiness as part of the DR 4339 recovery efforts.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of delayed contracts and purchase orders. Preparation of a consolidated list with delivery status by unit, component description, contractor, committed vs. actual delivery dates, and observation of the absence of penalty clauses in certain cases. Preparation of report and communication to GENERA-PR for corresponding action.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Alejandro Maymi, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria.Pre-Meeting with participation from DCMC: Mark Merritt, DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Glorimel Torrado, Christian Cruz, Sheila Torres; from SM Consulting Shellsea Maysonet to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with the client , and as part of the RFR development and submission process.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and add comments to the BESS Swap - Parking Area Laydown submitted by Jose Segarra of RGE Contractor
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Cambalache BESS - Existing Pipeline Relocation Potential RFI created by Andres Concepcion from DCMC.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (continue) Review BESS & Peakers - Master Schedule/ COD Table Update 30-May-25 send by Carlos De Jesus DCMC
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS discussion and evaluation with Andres Concepcion of DCMC of Cambalache BESS - Parking Area Laydown RGE Contractor sent by Jose Segarra of RGE.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review BESS & Peakers - Master Schedule/ COD Table Update 30-May-25 send by Carlos De Jesus DCMC.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and edit the Preliminary Quality Control Plan for the BESS Program of the Cambalache Power Plant DCMC, Division 9 Finishes, Topic All Finishes.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria I continued to supervise and monitor diesel transport fuel being transferred from Vega Baja to Palo Seco. I stayed at Palo Seco Central Station all day long, a total of 6 trucks came in today, from this time I supervised truck tankers #509, #507 & #510 (from each truck, it takes them about close to 2 hours to deliver or transfer the fuel to the main tanks)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria I continued to supervise and monitor diesel transport fuel being transferred from Vega Baja to Palo Seco. I stayed at Palo Seco Central Station all day long. A total of 6 trucks came in today, from this time I supervised truck tankers #246, # 509 (from each truck, it takes them about close to 2 hours to deliver or transfer the fuel to the main tanks)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Supervised and monitored diesel transport fuel being transferred from Vega Baja to Palo Seco. I stayed at Palo Seco Central Station all day long, with a total of 6 trucks came in today, from this time I supervised truck tankers #507 &#510 (from each truck, it takes them about close to 2 hours to deliver or transfer the fuel to the main tanks)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria I continued to supervise and monitored diesel transport fuel being transferred from Vega Baja to Palo Seco. I stayed at Palo Seco Central Station all day long. A total of 6 trucks came in today, but from this time I supervised truck tankers #510 & # 246 (from each truck, it takes them about close to 2 hours to deliver or transfer the fuel to the main tanks)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued Managing Vega Baja Genera Site and supervising contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety measures while transferring Diesel from Vega Baja tank towards truck tankers for transport towards Palo Seco. Trucks number 545,510,507 and 509. Contractor: ADS company. Trips for the day were completed and will resume tomorrow.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety measures while transferring Diesel from Vega Baja tank towards truck tankers for transport towards Palo Seco. Trucks number 545,510,507 and 509. Contractor: ADS company.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Pro-Core Meeting: Procore - DCMC Financials Tools - review new ProCore functionalities to process and document invoices, contract balance, PWs and discussed workflow streamline opportunities within DCMC Team. This tool will facilitate invoice review process and accurate contract balance for all Genera projects including BESS and Peakers. Participants from DCMC - (Rafael Calderon, Lauren Wells, Jose Ralat, Esther Rohena, Sheila Torres and Mark Merritt).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC & Genera- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander Gonzalez, Esther Rohena, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz) , Carlos Gonzalez -Integrum and SMC Shellsea Maysonet; from Genera (Alejandro Maymi and Maria Sanchez)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC Pre-Meeting- Weekly Status Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander Gonzalez, Esther Rohena, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz, Christian Cruz), Integrum (Carlos Gonzalez) and SMC Shellsea Maysonet
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, MegaPacks and tariffs for all plants. Meeting participants TESLA (Michael Grabstein, Elizabeth Arentsen, Allin Luong), CSA (Franklyn Colmenares), and DCMC (Rafael Calderon)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review. Siemens Chek-In Meeting: Peakers Costa Sur project Status follow-up and review of contract schedules. Participants from Genera (Jesus Cintron, German Nunez), CSA (Franklyn Colmenares) CDM PM (Carlos Palomares), Sargent and Lundy - (Mike Kuczynski) and DCMC Contract Manager - (Rafael Calderon, Abraham Velazquez, D'Alexander González and Sheila Torres).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA / BESS Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team, CDM Smith PM team (Gabriel Sepulveda), Sargent & Lundy ( (Mike Kuczynski) Miguel Del Valle, Nelson Rosado), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Gilberto Sucre, Foster Veazey, Paola Arroyo, Raissa Borges, Luis Roman, Frances Vallejo), Lemoine Procore (Lauren Wells).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 894 and 895 location AL16 .
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AG025 to AG034, GD007 to GD008
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AG025 to AG034, GD007 to GD008
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AG025 to AG034, GD007 to GD008
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AG025 to AG034, GD007 to GD008.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AG025 to AG034, GD007 to GD008
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 00 035 000 to AB 00 045 000
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 00 035 000 to AB 00 045 000
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 00 035 000 to AB 00 045 000
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AE 104 TO AE 144 LIST # 878/ 879 AND RECOUNT LIST 886
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations UC 001 TO UC 011 using Cycle Count List # 887/88/89 AND RECOUNT LIST # 890
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AE 104 TO AE 144 AND UC 001 TO UC 011
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AE 104 TO AE 144 AND UC 001 TO UC 011 at the Aguirre warehouse to start the cycle counts.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #894 and 895 from location AL16 for a total of 407 pcs.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 152 | 494 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with location AL16 Cycle Count List # 881.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 152 | 114 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the list from location AL16 to begin the cycle count.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria -at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from location AL16.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Submittals and RFI distributions based on established workflow templates or by the Procore Tools settings: Submittal Manager established and RFI Manager to remain.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control - Data Management/ BESS-Peakers GEN 01 Project - Review and Manage Data into Correct Project Folder - Various BESS & Peakers projects documents involved in transfer/Costa Sur BESS & Peakers Projects Coordination with Luis Echevarria (DCMC) & Jean Pierre (DCMC)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control - Data Management / Vega Baja BESS Homeca Incoming Documents for Review & Process/Daguao Peakers S&L Incoming Documents for Review & Process/ Costa Sur Peakers S&L Incoming Documents for Review & Process/Jobos Peakers S&L Incoming Documents for Review & Process/Cambalache BESS Coordination with Lauren Wells (DCMC) & Luis Roman (DCMC)
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Phone call with Jose Lopez (DCMC) to discuss the reach of permissions on the Drawings Tool as for DCMC to allow multiple users interact on the Drawing Tools; creation of permission templates to allow publishing for existing standard level permission users.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – BESS Weekly Meeting hosted by Gabriel Perez (CDM Smith) including Design Team staff Mike (S&L), Lauren Wells (Lemoine), GIlberto Sucre, Rafael Calderon (DCMC), Rafael Pabon and Gabriel Perez (CDM Smith), Jesus Cintron (Genera); discussing weekly open topics for the BESS Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Peakers Weekly Meeting hosted by Franklyn Colmenares (CSA) including Design Team staff Miguel del Valle (S&L), Lauren Wells (Lemoine), Sheila Torres, Raissa Borgers, Rafael Calderon, Abraham Velazquez (all DCMC), Enrique Laya and Rafael Pabon (CDM Smith), German Nunez (Genera); discussing weekly open topics for the Peakers Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review General Work Contract (GWC) Technical Specification Package from designer Sargent & Lundy; Spec Section 000110 "Table of Contents" to verify specifications scope and reach.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Meeting with Theresa Perez (DCMC) and Lauren Wells (Lemoine) to discuss ongoing Procore progress, issues and reported observations; the export of submittals attachments for document control purposes, project management implementation through Procore features and the revision of Submittals process for contractors and staff response time.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the General Work Contractor (GWC) Technical Specifications Package from designer Sargent & Lundy; review Spec Sect. 014500 Quality Control.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the implementation progress of Submittals and RFI distributions and assignations to users based on established workflow templates: review the need for creating addtional templates, the use of Submittal Manager as distribution person and the configuration of proper distribution and assignees lists.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 149 | 260.75 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Configure Asset Suite at Genera's laptop and review CPA update. I verify all the CPA's pending and approved, this information was updated on Pre Intervention Tracker for Friday meeting.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 149 | 298 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - TESLA_Contract 106761 reviewing Tesla proposed change orders and keypoints for Pre Intervention status meeting with Genera and DCMC team. I prepared my summary, verify excel spreadsheet with Tesla changes, describe Siemens next steps and pending items from genera signature.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 149 | 149 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 ¦ Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado and Marc Maceira (HONRA LLC). Also, Shellsea Maysonet (SM Consulting); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines. For this meeting I went to Genera office to present Pre Intervention status.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 149 | 149 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339- Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Cynthia Ortíz; Marc Maceira (HONRA LLC) and Shellsea Maysonet (SM Consulting); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Progress continued on the translation of Volume 3, Chapter 11 (Sections 11.6 to 11.8) of the SHE Manual, ensuring consistent formatting and structure, accurate use of technical terminology, and correction of spelling errors throughout the document.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams Meeting with DCMC Team: Frances Vallejo Rosich, D'Alexzander Gonzalez and Mark Merritt. In the meeting was the Genera Team: Jesus Cintron, Kevin Futch, Francisco Santos, German Nunez, Alejandro Maymi and Sarahi Medina Nieves. In the meeting was the CDM Smith: Juan Mendoza, Rafael Pabon and Carlos Palomares. The meeting was about Peakers Check In.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Integrate Vega Baja Reders to Canva's Invitation for Second Community Meeting. Search the photo and edit it to include it in the document.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Meeting with the team of Genera Iván Báez, Jorge Bracero and Rafael Rodríguez Ema in the Weekly Corporate Affairs Meeting. During this week’s meeting, the team discussed the upcoming agenda, ensuring all members were aligned on key objectives and deliverables. We reviewed pending tasks to identify any roadblocks and prioritize follow-ups. A significant portion of the meeting focused on the approval of communication materials intended for various community audiences. Feedback was shared to fine-tune messaging, confirm branding guidelines, and ensure timely distribution.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Update the materials (agenda, communication pieces, among others) that will be presented today at the week's Weekly Corporate Affairs meeting.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 139 | 173.75 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Raissa Borges from DCMC and Lauren Wells, Foster Veazey from Lemoine. In the meeting was the Genera PR Team: Jesus Cintron, Joaquin A Quinoy, Ricardo Pallens, Maria Sanchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczinsky and Nelson Rosado. The meeting was about the Bess Project.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Edit the fact sheet to change the photos, add a section on important data of the project in Vega Baja and update the status to inform the community.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 139 | 417 | 139 | Yes | 146793 | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Continued translating Volume 3 Chapter 11 (Section 11.1 to 11.5) of the SHE Manual, ensuring consistent formatting, structure, and accurate terminology throughout, while correcting spelling errors.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review BESS Enlarged Ground floor plans, Interior Elevations and details for 4339_9510 BESS_Cambalache project to ensure compliance with regulatory requirements.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA Genera Deliverable 11 Project Management DR4339. Continued reviewing the Issue for Bid (IFB) drawings to configure submittal settings and familiarize with RFI and scheduling tools within the project management platform. The review focused on QA/QC aspects, specifically verifying concrete strength specifications and rebar spacing details to support future field inspections and documentation. This process aims to compare the IFB set with the forthcoming Issue for Construction (IFC) drawings to identify any changes or discrepancies affecting construction execution.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- work on schedule Procore criteria for evaluation considering PROCORE file of minutes for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- work on schedule Procore criteria for evaluation considering PROCORE file of minutes for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, Section B: Project Experience & Management. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Begin reviewing project documentation, Section B: Project Experience & Management. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review BESS Enlarged Ground floor plans, Interior Elevations and details for 4339_9510 BESS_Cambalache project.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Analyzing and compiling Peakers financial data for the monthly report.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Rafel Pabon (CDM Smith), Luis Roman (DCMC), Paola Arroyo (Genera), Jorge Bracero (Genera), Lauren Wells (Lemoine), Foster Veazey (Lemoine), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Franklyn Colmenares (CDM Smith), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Sheila Torres (DCMC).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Rafael Pabon (CDM Smith), Sheila Torres (DCMC), Paola Arroyo (DCMC), Lauren Wells, (Lemoine).
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Overseeing and organizing BESS financial data for inclusion in the monthly report.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Pesquera, Jaime | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 4.34 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travelled from Palo Seco Power Station in Catano, Palo Seco, Toa Baja Rico to Home in Calle Zuania Guaynabo Purpose was to supervise the diesel transfer from Vega Baja to Palo Seco total mileage 6.2 miles
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site to evaluate diesel transfer from Vega Baja to Palo Seco Genera Site.
2025-06-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Pesquera, Jaime | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 4.62 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travelled from Home in Calle Zuania Guaynabo 00966 18.405417 -66.118583 to Palo Seco Power Station in Catano Purpose to supervise the diesel transfer from Vega Baja to Palo Seco total mileage 6.6
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 2108.52 | 2108.52 | 2108.52 | Yes | 146793 |  | Home Depot - Equipment and supplies for Costa Sur
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 286.67 | 286.67 | 286.67 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Helmet necessary for all employees' entrance to the Genera Sites.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mike Merritt, Mark Merritt, Frances Vallejo, Lauren Wells, Gilberto Sucre, Foster Veazey, and Ada Diaz, DCMC. Discussed update on project, job offers, PROCORE workshop schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Attended and participated in meeting to review the revised schedule and construction activities to anticipate and manage changes during the project lifecycle and enhance efficiency by prioritizing tasks. German Nunez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Attended meeting for review Costa Sur demolition modifications to enhance project safety and efficiency. Discussed issuing an addendum to the RFP answer contractors' questions from previous site walkthrough. German Nunez, GENERA Rafael Pabon, CDM Smith Lemuel Nieves Sargent & Lundy.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Tesla Cash Flow Discussion for reporting Carlos Palomares - CDM Smith, Rafael Calderon and Gilberto Sucre DCMC Partners.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting with RGE for Costa Sur Civil & Structural Phase, reviewed outstanding items to complete cycle and reach contract agreement. Gabriel Perez - CDM Smith, Wilfredo Sierra - Sargent & Lundy, Jose Robles - RG Engineering and Gilberto Sucre - DCMC Partners
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting with ARG Ceres for Vega Baja Installation Phase reviewed outstanding items to complete cycle and reach contract agreement. Gabriel Perez - CDM Smith, Wilfredo Sierra - Sargent & Lundy, Carlos Hernandez - ARG Ceres and Gilberto Sucre - DCMC Partners
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly Construction Site Meeting with Carirma Sanchez - Homeca Recycling, Gilberto Sucre - DCMC Partners, Gabriel Perez - CDM Smith and Franklyn Colmenares - CSA Group Participation. Meeting was led by Jose Lopez - DCMC.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting to discuss project Updates from Vega Baja & Aguirre sites with Jose Lopez - DCMC, and Cambalache with Andres Concepcion - DCMC.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC weekly Internal meeting between Site Team - Andres Concepcion, Luis Damudt, Luis Duque, and Jorge Mercado with Gilberto Sucre. Discussed Pre-Mobilization activities, submittals & RFI's, IFC's Pending decision items from Genera Plant Site.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up. Main topics discussed, Staffing Updates, Project Staffing Strategy for Bess & Peakers, Compensation Changes, Technology and Process Updates, and Equipment & Procurement. DCMC: Mark Merritt, Michael Merritt, Frances Vallejo, Ada Diaz, Foster Veazey, Anneilia Holton & Gilberto Sucre.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria E-mail correspondence review and response of PMO Program related topics and reports.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Alignment Meeting about Submittals & RFI's for Vega Baja Site led by Lauren Wells (Lemoine) and Luis Roman with Jose Lopez, Eduardo Rivera, Jaime Pesquera, Gilberto Soto and Gilberto Sucre all DCMC Partners.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Alignment meeting with Mark Merritt - DCMC. Discussed: * Schedulers/Cost Hiring Options * Procurement Support for Construction Site Needs * CDM Smith & DCMC Partners - Relation to date * Cost Reporting & Staffing Updates
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Latest RGE MSA Documentation & Draft Contract Submission for RFP 4899 Read & Review document, issue verification notes to Sargent & Lundy.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine). Discussed project, job offers, PROCORE modules schedule, interviews, trailer set-up, safety, schedule for locations, LEAN, and program management plan update.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences about Procore with helping users get setup for Procore certifications.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for changing templates for QA/QC roles.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore team task items to ensure we are tracking request and completing them.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financials tool with working on budget imports and contracts for 11855.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Vega Baja Team (Eduardo Jordan, Gilberto Sucre, Jose Lopez, Luis Roman, Jaime Pesquera (all with DCMC) and Nelson Soler (CDM Smith) to discuss RFI's and Submittals for this project team.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOP for Submittals before sending to Franklyn Colmenares (CSA) for his review.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences with users for RFI and Submittal questions.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up more dates/times for Procore weekly Q&A and sending out invites.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool to update budget for 11855.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Raissa Borges from DCMC to discuss effective strategies for sharing PMO KPIs using a business intelligence tool, to ensure accessibility for key stakeholders to support informed decision-making.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Pick up Helmet in ARAMSCO necessary for entrance in Genera Site to provide protection, ensure safety, and comply with legal requirements.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the Vega Baja to Palo Seco Diesel transportation process to ensure safe and efficient fuel storage and refueling on the project site.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 1 | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Metting about Vega Baja project status with Jose Lopez, Jaime Pesquera, Gilberto Soto (DCMC), Carirma Sanchez (HOMECA) and Enrique Laya (CDM SMITH). Metting with Jean Gonzalez (GENERA) about start work in Genera BCP Plan. Pick up Helmet in (Aramsco) necessary for entrance in Genera Site.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 |  | 184 | 322 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the Vega Baja project status in Procore. Conference call with Gilberto Soto (DCMC) about the diesel transfer process from Vega Baja to Palo Seco Genera Sites. Conference call with Jorge Mercado (DCMC) about Cambalache Genera Site. Conference call with Osvaldo de Jesus (GENERA) about Aguirre, Yabucoa and Salinas sites EHS programs.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 184 | 644 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended site visit at Yabucoa site for the Tesla meeting to make an inspection for the battery installation phase. Participants: Jesus Cintron (Genera), Mike Kucksynski (S&L), Gabriel Perez (CDM), Gabriel Morales (DCMC), Harry del Valle (DCMC).
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call with PMO leadership team at DCMC to discuss staffing update, hiring status, Procore financials SOPs status, RFPs, trailer installation, material and equipment for sites purchase and coordination. Participants: Ada Diaz, Mike Merritt, Mark Merritt, Gilberto Sucre (DCMC) Foster Veazey, Lauren Wells (Lemoine)
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Cambalache weekly internal meeting to discuss RGE contract process, trailer installation and project status. Participants: Gilberto Sucre (DCMC).
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4898 BESS Installation at Vega Baja - Finalized assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Finalized completing the mandatory appendices and sent out for review and signature to the Procurement Team. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process. Shared all documentation with Cristina Ribas and Jesus Cintron (Genera)
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4898 BESS Installation at Vega Baja - Began assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Initiated the process of completing the mandatory appendices, beginning with Appendix A. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued yesterday's task of managing Vega Baja Genera Site and supervising contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety measures while transferring Diesel from Vega Baja tank towards truck tankers for transport towards Palo Seco. Trucks number 545,510,507 and 509. Contractor: ADS company.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated the Power Point Presentation of "Charla de Salud y Seguridad" sent by Jean Menay (DCMC) yesterday. Focused the updates on evacuation route and emergency contacts list for Costa Sur site.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with the Tesla team (Michael Grabstein & Josue Melendez) to show the site work area for the logistic of delivery the equipment.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Meet the Costa Sur Team (DCMC: Carlos Rodriguez Bury and Rafael Barrera) they showed me the site of the project and explain the roles.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur- Site visit to Aguirre PREPA Plants and meeting with Tesla team Michael Grabstein & Josue Martinez, DCMC Harry Del Valle, Gabriel Morales, Carlos Rodriguez, Luis Echevarria and CDM Franklyn Colmenares and Gabriel Perez to discuss the on-site energy distribution systems for the projects.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur- Meeting with Tesla team Michael Grabstein & Josue Melendez, DCMC Harry Del Valle, Gabriel Morales, Rafael Barrera and Franklyn Colmenares of CDM Smith. Met at Costa Sur for site visit to discuss construction area.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Meeting at Yabucoa with Michael Grabstein, Carlos Melendez (Tesla), Harry Del Valle, Carlos Rodriguez, Rafael Barrera (DCMC), Gabriel Perez (CDM Smith), Franklyn Colmenares (CSA Group) Vincent Skochdopole, Joshua Montanez, Mike Kuczynski and Abdile Gonzales (Sargent and Lundy) to define the strategy of preparation, delivery and installation for the BESS project.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Aguirre Site Meeting at Aguirre with Michael Grabstein, Carlos Melendez (Tesla), Harry Del Valle, Carlos Rodriguez, Rafael Barrera (DCMC), Gabriel Perez (CDM Smith), Franklyn Colmenares (CSA Group) Vincent Skochdopole, Joshua Montanez, Mike Kuczynski and Abdile Gonzales (Sargent and Lundy) to define the strategy of preparation, delivery and installation for the BESS project.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Costa Sur Site Site Meeting at Costa Sur with Michael Grabstein, Carlos Melendez (Tesla), Harry Del Valle, Carlos Rodriguez, Rafael Barrera (DCMC), Gabriel Perez (CDM Smith), Franklyn Colmenares (CSA Group) Vincent Skochdopole, Joshua Montanez, Mike Kuczynski and Abdile Gonzales (Sargent and Lundy) to define the strategy of preparation, delivery and installation for the BESS project.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Site visit to Aguirre & Yabucoa PREPA Plants and meeting with Tesla team Michael Grabstein & Josue Martinez, DCMC Harry Del Valle, Gabriel Morales, Carlos Rodriguez, Luis Echevarria and CDM Franklyn Colmenares and Gabriel Perez to discuss the on-site energy distribution systems for the projects.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Meeting with Tesla team Michael Grabstein & Josue Martinez, DCMC Harry Del Valle, Gabriel Morales, Carlos Rodriguez, Luis Echevarria and CDM Franklyn Colmenares and Gabriel Perez to discuss the on-site energy distribution systems.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Read and review information for the operation and maintenance at the Bess
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Read and review information about the steps to take to the Bess Installation and commissioning for Aguirre
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Call with Jean Pierre Menay (DCMC) to coordinate a visit to Aguirre for next week.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Read and review the Aguirre Evacuation Plan 12JUN22 to acquire data from the different areas of the site
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review for the Safe Transportation of a Tesla BESS (Battery Energy Storage System) 1. Overview 2. Pre-Transport Preparation: Battery State of Charge (SOC), Regulatory Compliance, Packaging and Labeling 3. Mode of Transportation 4. In-Transit Safety 5. Delivery and Unloading 6. Emergency Preparedness
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS- Prepared the Agenda for the weekly progress meeting for the Vega Baja Site to help discuss project issues and improve communication across the site team. Weekly project meeting with HOMECA representatives Carirma Sanchez and Eduardo Ramos. Project Schedule and progress discussion to mitigate risks, optimize resource allocation, and effectively achieve project objectives.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Drafted, reviewed, and finalized the meeting minutes for the Vega Baja BESS project coordination meeting. The task involved organizing detailed notes, confirming technical content and action items ensuring clarity and accuracy of decisions made during the session. The finalized minutes were formatted according to project standards and distributed to Gilberto Sucre, Jaime Pesquera (DCMC Partners), and Noel Soler (CDM Smith) for record and follow-up.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Purpose, Tesla visit Jobs sites Topics discussed, walked through Project Site, discussed scope of work, project needs, discussed logistic for BESS Installation, measured areas. Took Pictures and review utilities facilities. Attendees – TESLA Team - Allin Luong, Michael Grabstein, Keyur Javiya, Qais Feroz, Carlos Melendez Mendez. CPS Team - Gordon Liles, Jay Garrett. TSEA Team - Augusto Cesar da Silva Junqueira, Felipe Augusto Vilas Boas, Andre Silveira Campos Soares. CDM Smith Team - Gabriel Perez. CSA Team - Franklyn Colmenares. Sargent and Lundy - Vincent Skochdopole, Joshua Montanez Rivera, Mike Kuczynski, Abdiel Gonzalez. DCMC - Gabriel Morales, Harry del Valle.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Purpose, Tesla visit Jobs sites Topics discussed, walked through Project Site, discussed scope of work, project needs, discussed logistic for BESS Installation, measured areas. Took Pictures and review utilities facilities. Attendees – TESLA Team - Allin Luong, Michael Grabstein, Keyur Javiya, Qais Feroz, Carlos Melendez Mendez. CPS Team - Gordon Liles, Jay Garrett. TSEA Team - Augusto Cesar da Silva Junqueira, Felipe Augusto Vilas Boas, Andre Silveira Campos Soares. CDM Smith Team - Gabriel Perez. CSA Team - Franklyn Colmenares. Sargent and Lundy - Vincent Skochdopole, Joshua Montanez Rivera, Mike Kuczynski, Abdiel Gonzalez. DCMC - Gabriel Morales, Harry del Valle.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Purpose, Tesla visit Jobs sites Topics discussed, walked through Project Site, discussed scope of work, project needs, discussed logistic for BESS Installation, measured areas. Took Pictures and review utilities facilities. Attendees – TESLA Team - Allin Luong, Michael Grabstein, Keyur Javiya, Qais Feroz, Carlos Melendez Mendez. CPS Team - Gordon Liles, Jay Garrett. TSEA Team - Augusto Cesar da Silva Junqueira, Felipe Augusto Vilas Boas, Andre Silveira Campos Soares. CDM Smith Team - Gabriel Perez. CSA Team - Franklyn Colmenares. Sargent and Lundy - Vincent Skochdopole, Joshua Montanez Rivera, Mike Kuczynski, Abdiel Gonzalez. DCMC - Gabriel Morales, Frances Vallejo, Harry del Valle. Genera - Jesus Cintron.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Working on creating safety guidelines for preventing environmental impact based on the project's daily work, as well as spill prevention and response teams.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Internal meeting of Cambalache where we discuss contract progress and project coordination for the Cambalache site. Attendees Luis O. Damudt (DCMC Partners), Carlos De Jesus (DCMC Partners), Luis Duque (DCMC Partners),
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work is underway to create safety guidelines for preventing environmental impact based on the project's daily work.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Evaluated contractor's (RG Engineering) proposed site staging area plan with Herminio Arroyo (GeneraPR). Generated and sent a response and RFI to Jose Segarra of RG Engineering to continue evaluation.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Cambalache Site Team. DCMC Partners Team: (Luis Damudt, Luis Duque, Carlos De Jesus, Frances Vallejo, Jorge Mercado) for team weekly discussion and follow up.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated,received and supervised Duenas Trailers (vendor) personnel to complete installation of Office Trailer in Cambalache site.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated Cambalache site meeting agenda with follow ups and action items to provide direction to team.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared the Cambalache Weekly Construction Meeting agenda for topics to be discussed with project stakeholders RG Enginering, Sargent and Lundy and DCMC Partners. Distributed agenda through Procore.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - ADS and Homeca continue to fuel of truck container 3 and arrive of truck container 4 that will set at fueling station.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue supervising the Diesel transfer by ADS contractor (1) Diesel trucks has leave the facilities to Palo Seco. Homeca personnel is working on trafic control when truck leave facilities.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja Demolition Project Meeting - DCMC participant Gilberto Sucre, Jaime Pesquera, Jose Lopez, Lauren Wells, Gilberto Sote, Nelson Soler and Luis Roman - Meeting was to understand how we can separate in Procore two project phase under the same project name.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - ADS and Homeca continue to fuel of truck container #5 that arrive at 3PM the truck #4 has leave the facilities to Palo Seco. Truck #5 leave at 5:25pm to Palo Seco, but they are still remaining approximate 1000 galones a truck #6 was requested to complete work.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja Demolition Project Meeting - Homeca Attendee Carirma Sanchez; CDM Smith Manuely Concepcion, and Enrique Laya: DCMC Partners Jose Lopez, Jaime Pesquera, and Jean Menay - Meeting was in regard of Demolition project status where was discuss all pending items and work to be completed.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - ADS and Homeca continue to fuel of truck container #5 with Diesel they completed the fueling at 5:25pm but they are still remaining approximate 1000 galones a truck #6 was requested to complete work. Truck #6 arrive at 6:30pm and started to transfer the remaining approximate 1000 gallones, the truck transfer pump start giving problem, Homeca and ADS relocate hose to another point of extraction but then remaining Diesel does not look good we stop transfer due to pump not working properly last truck leave at 7:45pm and contractor start cleaning all area up to 8PM.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a detail analysis of inventory discrepancies at the Costa Sur warehouse to strengthen internal controls and verify compliance with established inventory management procedures. The effort concentrated on identifying root causes of persistent variances, validating data accuracy between physical inventory and system records, and assessing procedural adherence. Additional responsibilities included documenting anomalies, evaluating inventory integrity, operational efficiency, and audit readiness. The review specifically covered bin locations ranging from AB 046 through AB 061.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC. The objective was to validate previous cycle count results, confirm data accuracy, and resolve outstanding inventory discrepancies. Key task included cross-verifying item quantities, documenting deviations, and ensuring alignment between physical inventory and system records. The reviewed covered locations ranging from AB 046 to AB 061.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while station at the Costa Sur warehouse, compiled, analyze, and submitted a comprehensive inventory assessment report to Mr. Anthony Vega of Genera PR. The report consolidated key data from multiple warehouse locations and presented a strategic overview of catalog materials, including item quantities, unit costs, discrepancy trends, and stock level thresholds (maximum/minimum). The report also integrated performance metrics to evaluate inventory health and operational readiness. Reviewed locations included AB 046 to AB 061, LL 001 to LL 015, BT 001 to BT 024 AG 035 to AG 044.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled cycle counts across designated inventory locations, specifically on storage areas AB 046 to AB 061. This activity supported broader operational initiatives aimed at strengthening inventory governance and optimizing stock accuracy. Task included validating the consistency between physical inventory and system reported balances, documenting discrepancies, and analyzing root causes of recurring variances.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a comprehensive analysis of inventory records and prepared updated cycle count documentation to support scheduled operational task at the Costa Sur warehouse. The work was coordinated with Mr. Hernan Machado from DCMC to ensure alignment with project objectives and standard practices. Key responsibilities included validating inventory data integrity, producing supporting materials for cycle count execution, and ensuring all activities met defined cycle count requirements. Today locations range from AB 046 through AB 061.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a structured operational briefing with Juan Vallejo, Giopvanni Taffanelli, and key DCMC warehouse personnel to assess the current state of inventory control protocols. The session focused on evaluating the effectiveness of existing warehouse practices and identifying inconsistencies in inventory tracking and data recording. Discussions emphasized the need for procedural standardization across all storage facilities, aligning data entry workflows with system integrity requirements, and mitigating inventory discrepancies.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Independent Cost Estime SOP from GENERA-PR
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Scope of Work Development | Direct-PA | Activities necessary to develop/document project's scope of work (any level) | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Draft Fund Sharing version for project 10608. This task included reviewing scope alignment with eligible damages, refining quantities and unit costs, and ensuring compliance with FEMA cost reasonableness guidelines. The objective is to support accurate and justifiable funding requests, contributing to proper documentation and audit readiness as part of the DR 4339 recovery efforts.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Scope of Work Development | Direct-PA | Activities necessary to develop/document project's scope of work (any level) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review DI 1256016 to identify possibles duplication in other PWs. The task involved cross-referencing component lists with FEMA and insurance documentation to ensure no eligible scope was incorrectly omitted. This review supports the accurate validation of project costs and helps uphold compliance with FEMA PA program requirements, contributing to the integrity of the funding request.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DCMC- Revision Proyectos Federales Status meeting with participation from DCMC: Pedro Cabrera, D'Alexzander Gonzaléz, from SM Consulting Shellsea Maysonet;, to discuss priorities and deliverables, status updates, identify next steps for projects under Federal Grant.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with Cynthia Ortiz DCMC to review the status of active RFP of current federal projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Cambalache Weekly Internal Meeting to discuss project updates with Frances Vallejo, Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review and edit the Preliminary Quality Control Plan for the BESS Program of the Cambalache Power Plant DCMC, Division 9 Finishes, Topic All Finishes, Construction Quality Control, Delivery.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the Jose Segarra RGE comments 20250527 - BESS CAMBALACHE - TO GENERA - LAYOUT DISCUSSED ON LAST SITE MEETING RFI sent by Jose Segarra of RGE.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review and edit the Preliminary Quality Control Plan for the BESS Program of the Cambalache Power Plant DCMC, Division 9 Finishes, Topic All Finishes, Storage and Handling, Acceptable Manufactures and Products.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review and edit the Preliminary Quality Control Plan for the BESS Program of the Cambalache Power Plant DCMC, Division 9 Finishes, Topic All Finishes, Inspection and Testing, Inspection by Contractor, Acceptance.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Supervised and monitored diesel transport fuel being transferred from Vega Baja to Palo Seco. I stayed at Palo Seco Central Station all day long. From this time, I supervised truck tankers #509 & #510 (it would take them about close to 2 hours to deliver or transfer the fuel to the main tanks) these are the total of trucks for today 6 in total.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Supervised and monitored diesel transport fuel being transferred from Vega Baja to Palo Seco. I stayed at Palo Seco Central Station all day long. From this time, I supervised truck tankers #246 & #509 (it would take them about close to 2 hours to deliver or transfer the fuel to the main tanks)
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Supervised and monitored diesel transport fuel being transferred from Vega Baja to Palo Seco. I stayed at Palo Seco Central Station all day long. From this time, I supervised truck tankers #510 & #507 &# 509 (it would take them about close to 2 hours to deliver or transfer the fuel to the main tanks)
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Supervised and monitored diesel transport fuel being transferred from Vega Baja to Palo Seco. I stayed at Palo Seco Central Station all day long . This truck came in leaking through the gate so it took a long while to get it inspected and admitted in by Genera-PR security. From this time I supervised truck tanker #246 only.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued yesterday's task of managing Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety measures while transferring Diesel from Vega Baja tank towards truck tankers for transport towards Palo Seco. Trucks number 545,510,507 and 509. Contractor: ADS company. Completed diesel transport with tanks empty.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Resumed yesterday's task of managing Vega Baja Genera Site and supervising contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety measures while transferring Diesel from Vega Baja tank towards truck tankers for transport towards Palo Seco. Trucks number 545,510,507 and 509. Contractor: ADS company.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#10_Invoice# PRIN0008818_Apr 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 164 | 574 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reviewing RG Engineering_109403 contract (876 pages long) Article 1-5 and start preparing RFI for RGE. working session review the contract terms that affects the invoice. review the invoice and identify missing information and clarification; also, prepare a schedule of value based on the contract for this vendor in preparation for RGE Kick-Off Meeting.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Cash Flow) Meeting with project management Team CDM - Carlos Palomares and Gilberto Sucre DCMC. Contract 106761 - Reviewing current Tesla budget and cash flow in relation to equipment and supply labors and field construction execution, in order to align project actual balance.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Continue working with Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#10_Invoice# PRIN0008818_Apr 2025. RFI related to Federal project Scope. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations BT001 to BT024 to begin the cycle counts.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AG035 to AG044
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AG035 to AG044
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AG035 to AG044
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AG035 to AG044
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AG035 to AG044
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 00 046 000 to AB 00 061 000
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 00 046 000 to AB 00 061 000
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 00 046 000 to AB 00 061 000
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations LL 001 TO LL 015 using RECOUNT LIST 911/914/921
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations LL 001 TO LL 015
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations L L 001 TO L L 015 at the Aguirre warehouse to start the cycle counts.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations LL 001 TO LL 015 # COUNT LIST # 906/907/908/909/910/912
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 |  | 152 | 418 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations BT001 to BT024 Cycle Count List # 897.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 152 | 114 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #918, 919 and 920 from locations BT001 to BT024 for a total of 2,713 pcs.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 918.919 and 920 locations BT001 to BT024.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Lauren Wells (Lemoine) and Vega Baja Field Team Gilberto Sucre, Jose Lopez, Eduardo Rivera, Gilberto Soto and Jaime Pesquera (DCMC). DIscussion for the proper execution of Submittals and RFIs review and distribution; Submittal Manager role and obligations.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/ BESS Projects Add Allin Luong (Tesla) to Procore/BESS Peakers Gen 01 Project Data-Review-Process Accordingly/Coordination with Paola Arroyo (DCMC)
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/ BESS Peakers Gen 01 Project Data- Environmental & Permitting Data Transfer to Aguirre BESS/Cambalache BESS Projects
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review of General Work Contract (GWC) Technical Specifications from designer Sargent & Lundy; review of technical specifications regarding General Conditions documentation.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Determine new workflow templates for active projects to cover all needs of duties for reviewing documentation assigned through Submittals and RFI in Vega Baja, Cambalache and Aguirre Power Plants.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Performing analysis on the use of Schedule Tool for external use; testing out Schedule inputs to overview the feasibility of Contractors uploading and updating schedules.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on RFIs 50, 51, 52, 53 and 54 for the Vega Baja Power Plant project to resolve issues regarding Assignees and distribution list.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Submittals and RFIs distribution in the Vega Baja Project; internal distribution being replaced by the design team workflow for review.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 139 | 417 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Update the Communication Plans for Aguirre and Costa Sur to include data on Project Contacts and organize all the files.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Worked on updating the Yabucoa Community Relations Plan to align it with current communication strategies, updated stakeholder information, and recent community engagement practices, with the purpose of ensuring effective outreach and strengthening ties with the Yabucoa community.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 PREPA Add edits to the newsletter related to the updates by BESS project site.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Organize the documentation in the Genera PR files related to the BESS and Peakers project. Work included: editing all document subjects, archiving new documentation for compliance purposes, and updating the Community Outreach 2025 calendar.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review BESS Enlarged Ground floor plans, Interior Elevations and details Janitors elevation north and vestibule elevations for 4339_9510 BESS_Cambalache project for detailed planning, and to ensure a cohesive and functional design.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 134 | 67 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- work on schedule inspection of document of project considering RFP bid documents for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- work on schedule on site project considering RFP contract sign for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on teams meeting related to verify project submittals status, new coordination status and project contract sign date with DCMC employees Andres Concepcion, Frances Vallejo, Luis Roman, Luis Damudt, Luis Duque and Jorge Mercado due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on schedule inspection of bid documents project considering RFP contract sign projection date for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on site meeting at inspection for rigging plan and specific site area with employees (TESLA) Carlos Melendez, Michael Grabstein, employees (DCMC) Carlos Rodriguez, Gabriel Morales, Harry Velazquez, Rafael Barrera, employees (CDM Smith) Gabriel Perez, Franklyn Colmenares, employees (Sargent and Lundy) Vincent Skochdopole due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, Exhibit E: Mechanical Unit Pricing. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, Exhibit E: Civil/Structural Unit Pricing. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, Exhibit E: Electrical Unit Pricing. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review BESS Enlarged Ground floor plans, Interior Elevations details Restroom elevation west and restroom elevation north for 4339_9510 BESS_Cambalache project which are critical to provide a detailed, orthographic view of a room's interior walls, helping to understand the spatial layout and design features.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache Weekly internal meeting with Andres Concepcion (DCMC) and Gilberto Sucre (DCMC) for the 4339_9510 BESS_Cambalache project to discuss weekly plan and action items.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 122 | 305 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue managing data to produce comprehensive Genera BESS, Peakers, Inventory and Critical Components projects report for May, while also facilitating Genera team access to PBI reports.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting by Teams with Manuelly Concepción from CDM Smith to discuss process diagram for projects financials on Procore.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Handling data to create detailed Genera projects May report. Also worked on Genera team access to PBI reports with Marc Maceira (Honra) and Tyler Chapman from Lemoine.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Marc Maceira (Honra) to discuss Power BI reports access to Genera team.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits and travel from Genera offices and facilities
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Pesquera, Jaime | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 4.34 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travelled from Palo Seco Power Station in Catano Palo Seco, Toa Baja Rico to Home in Calle Zuania Guaynabo Purpose was to supervise the diesel transfer from Vega Baja to Palo Seco total mileage 6.2 miles
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 130.2 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Yabucoa Gas Turbine to Costa Sur site to Aguirre Site and To Yabucoa Site. Purpose - Meetings at Costa Sur site, Aguirre Site and Yabucoa Site with Michael Grabstein, Carlos Melendez (Tesla), Harry Del Valle, Carlos Rodriguez, Rafael Barrera (DCMC), Gabriel Perez and Franklyn Colmenares and Surgent and Lundy of Genera design team to define the strategy of preparation, delivery and installation for the BESS project.
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 130.9 | 0.7 | Yes | 146793 |  | PREPA- Genera- Deliverable 11 Site visit to Aguirre & Yabucoa PREPA Plants and meeting with Tesla team Michael Grabstein & Josue Martinez, DCMC Haryy Delvalle, Gabriel Morales, Carlos Rodriguez, Luis Echeverria and Franklyn Colmenares and Gabriel Perez of Genera design team
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 167.3 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Costa Sur Power Plant (18.000463, -66.753480) to Central Aguirre (17.951690, -66.229675) to Yabucoa Gas Turbine (18.106216, -65.823685) to Home Office Luquillo. Purpose, Tesla visit Jobs sites Topics discussed, walked through Project Site, discussed scope of work, project needs, discussed logistic for BESS Installation, measured areas. Took Pictures and review utilities facilities. Attendees – TESLA Team - Allin Luong, Michael Grabstein, Keyur Javiya, Qais Feroz, Carlos Melendez Mendez. CPS Team - Gordon Liles, Jay Garrett. TSEA Team - Augusto Cesar da Silva Junqueira, Felipe Augusto Vilas Boas, Andre Silveira Campos Soares. CDM Smith Team - Gabriel Perez. CSA Team - Franklyn Colmenares. Sargent and Lundy - Vincent Skochdopole, Joshua Montanez Rivera, Mike Kuczynski, Abdiel Gonzalez. DCMC - Gabriel Morales, Harry del Valle. TOTAL MILEAGE - 239 miles
2025-06-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Pesquera, Jaime | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 4.62 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travelled from Home in Calle Zuania Guaynabo 00966 to Palo Seco Power Station in Catano 18.405417 -66.118583 Purpose was to supervise the diesel transfer from Vega Baja to Palo Seco total mileage 6.6
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 3148.65 | 3148.65 | 3148.65 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 required a vehicle to perform various site visits throughout the island. visited Vieques, costa sur, jobos, Aguirre, Yabucoa sits. Misc charge ($250) deducted.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 873.6 | 873.6 | 873.6 | Yes | 146793 |  | Duenas Trailers - 8'x20' Flex-tainer, Rental, 6/1/25 - 6/30/25 - Cambalache-Arecibo
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOPs for Inspections Tool.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Costa Sur internal work on documents and notes from previous meetings necessary for the project management.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Attended meeting discussions on Peakers procurement status of the projects to ensure services will be according to the project’s priorities and objectives and prevent delays and cost overruns. German Nunez, GENERA Rafael Pabon, CDM smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC Harry Del Valle DCMC Gilberto Sucre DCMC Foster Veazey DCMC Jean Pierre Menay DCMC Sheila Torres-Sterling DCMC Jesus. Cintron Genera Joaquin A Quinoy Genera
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed and distributed Issued for Construction sets for Vega Baja Phase II & Cambalache.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 225 | 675 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Site Visit to evaluate Project Status 7 Remaining Items, Phase II Demolition Execution, Installation Phase Execution with ARG Ceres and Tesla Site Visit. Met with Eduardo Rivera, Jaime Pesquera, and Jean Pierre Menay DCMC, Nelson Soler - CDM Smith, and Carlos Hernandez - ARG Ceres.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Reviewed RFI submissions from ARG Ceres and provided instructions to Eduardo Rivera - DCMC on responses.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Value Engineering Topics Presentation by ARG Ceres Subcontractors for Geopiers and Precast Walls and Upper Deck Slab. Main exchange mostly around information missing for Pre-caster to provide designed solution. Carlos Hernandez - ARG Ceres, Martin Marxuach - Marxuach Pre-Fabricados, Jorge Parra - Geopiers, Mike Kuczynski - Sargent & Lundy, Gabriel Perez - CDM Smith, Gilberto Sucre DCMC
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued evaluation of Cambalache and Vega Baja IFC drawings which contain the relevant information needed for the projects design, construction, and operation.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOP for drawings.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to discuss Procore workshop emails and format.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore tools for documents and financial modules.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for project manager versus site managers role.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of meetings for Procore external and internal calls.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool configurations.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on configurations for Procore tools.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial SOP plans for Lauren Kennedy (Procore).
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review Procore SOP's that are complete for final publish.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Esther Rohena, Rafael Calderon, Cynthia Ortiz, Raissa Borges, Johanna Díaz (SMC) and Manuely Concepcion (CDM Smith) to discuss PW processes.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 187.2 | 187.2 | 187.2 | Yes | 146793 |  | Duenas Trailers -8'x40' Flex-tainer, Rental, 6/27/25 - 6/30/25 - Costa Sur
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Jan Rodríguez and José del Río from Genera PR to review the power production and fuels consumption reports, ensuring accuracy and alignment with reporting expectations. Additionally, resolved issues within the master template file that manages references to individual plant reports for fuel consumption and generation, restoring proper functionality and data linkage.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Supervise the demolition phase. Working session with Tesla employees (Carlos Melendez (TESLA) in EHS Genera.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Carirma Sanchez (HOMECA) about Vega Baja Project tasks. Conference call with Julio Gonzalez (Department of Homeland Security) about Genera BCP.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site to evaluate and identify potential hazards in equipment, or facility to ensure they meet established safety standards. Meeting with Digno Cartagena, Herminio Arroyo (GENERA) Andres Concepcion, Jorge Mercado (DCMC) about Cambalache (GENERA) Site.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.25 |  | 184 | 230 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting in Palo Seco with Irving Babilonia (GENERA) about EHS program to safeguard the well-being of workers, protect the environment and ensure safe operations.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Gilberto Sucre and Carolyn Baez (DCMC) to discuss Costa Sur equipment purchase, printers and Ipad status.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Paola Arroyo (DCMC) to discuss community engagement plan, monthly report data, and Vega Baja community meeting coordination.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting with Raissa Borges (DCMC) to discuss monthly report corresponding to May and discuss site one pagers report.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Vega Baja Demolition - Relayed ongoing issues related to Homeca including contract performance concerns and compliance matters to Jesús Cintrón and Winnie Irizarry (Genera) to ensure alignment and awareness. Additionally, discussed the status of ongoing BESS and Peakers procurements, focusing on next steps, pending actions, and coordination efforts across teams.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Vega Baja Demolition - Reviewed a detailed email thread from Gilberto Sucre (DCMC) regarding Homeca, outlining various ongoing issues. Followed up with Gilberto to further discuss concerns related to contract performance, compliance, and adherence to agreed terms. The conversation focused on identifying potential risks and determining appropriate next steps to address the matters raised.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - RFP 4826 BESS Installation at Cambalache - Reviewed an email from Joel Pantojas (Genera) and discussed its contents with Jesús Cintrón (Genera) to align on key takeaways.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafael Pabon, Alejandro Laya, Carlos Palomares (CDM Smith) Miguel del Valle (S&L). Discussed feedback and updates received from the Genera procurement team.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS (228MW of BESS Installation) - Reviewed RFI Responses from Aireko, ARG, BLDM, Quanta, and RGE.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP220877 - Began assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while demolishing the Deisel container located in Vega Baja site. Luma arrived to install the temporary distribution line towards trailers and guard house.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Mobilization of office equipment with site manager Carlos Rodriguez (DCMC) and construction manager Rafael Barrera (DCMC) to ensure efficiency, and allow compliance with safety standards
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review of drawing of Costa Sur RFP. Review project details and battery's location.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur- Review of drawings & details of RFP Costa Sur specifics, review of project details and location batteries and project geographical limitation locations.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur- instalation of office chairs, tables, microwave, transit and fridge. Acompanied by DCMC Rafael Barrera and DCMC Luis Echevarria.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Palo Seco Site Meeting at Palo Seco with Carlos Melendez (Tesla) Vincent Skochdopole, Joshua Montanez, Mike Kuczynski and Abdile Gonzales (Sargent and Lundy) to define the strategy of preparation, delivery and installation for the BESS project.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Cambalache Site Meeting at Cambalache with Carlos Melendez (Tesla), Andres Concepcion (DCMC), Vincent Skochdopole, Joshua Montanez, Mike Kuczynski and Abdile Gonzales (Sargent and Lundy) to define the strategy of preparation, delivery and installation for the BESS project.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Vega Baja Site Meeting at Vega Baja with Carlos Melendez (Tesla), Jose Lopez, Jean Pierre Menay (DCMC)Vincent Skochdopole, Joshua Montanez, Mike Kuczynski and Abdile Gonzales (Sargent and Lundy) to define the strategy of preparation, delivery and installation for the BESS project.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Installation of Costa Sur Plant office equipment by myself in order to provide work area in our Project office trailer to provide flexible, cost-effective, and efficient workspace solutions and enhance team coordination, productivity, and workflow efficiency.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Continue with equipment installation by myself in Costa Sur Plant office trailer, Review work schedule in PDF done by Carlos De Jesus (DCMC) in order to present a project planification. Also, continue reading RFP documentation in PROCORE and verification of site project review as drawings in Procore.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review information of the power and capacity at the Bess
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Identifying emergency exits, routes, and meeting points in the Evacuation Plan 12JUN22' at Aguirre
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review information for the Operational Mechanism at the Bess Systems
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review to Identification of Zones at the Aguirre Electrical Plant Site: Zone Descriptions: A. Generation Zone (Main Power Block) B. Electrical Substation and Switchyard Zone C. Battery Energy Storage System (BESS) Zone D. Control and Operations Building E. Fuel Handling and Storage Zone F. Cooling Water Intake and Discharge Zone G. Maintenance and Workshop Zone H. Administrative and Support Zone I. Security and Access Control Points
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS - Contractor's (HOMECA) Daily activities overview to report the progress of the tasks, number of hours worked, materials used, and any delays or incidents in the project.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS PROJECT: Dismanteling and Demolition Activities field supervision and coordination. Meeting with Carirma Sanchez (HOMECA ) to discuss the weekend work schedule
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Continue working with the review of the proposals submitted for BESS Yabucoa RFP 231175 to ensure alignment with project requirements and documentation. Continue outlining recommendations based on evaluation findings to support internal decision-making.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Reviewed proposals submitted for BESS Yabucoa RFP 231175 to ensure alignment with project requirements and documentation. Verified the completeness of each proposal package and identified key technical elements. Began outlining recommendations based on evaluation findings to support internal decision-making.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continuation of coordination at the Cambalache site regarding the mobilization of contractors to the site with the DCMC team for the Cambalache BESS project Andres Concepcion, Luis Damudt, and Luis Duque,
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Visit the Cambalache site, where a tour was conducted with Tesla team Michael Grabstein & Josue Martinez. This was to coordinate the movement of equipment and installation. Andres Concepcion, DCMC, Herminio Arroyo, Genera Manager, participated in this meeting.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Construction Weekly meeting for Cambalache BESS project. Meeting covers project status, updates and pending actions for the execution of the construction phase with Luis O. Damudt (DCMC Partners), Carlos De Jesus (DCMC Partners), Luis Duque (DCMC Partners),
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared meeting agenda for Cambalache Weekly Construction Meeting. To follow up on weekly action items with contractor and designer team (RG Engineering, Sargent and Lundy)
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed TESLA and Sargent and Lundy site visit purposes and agenda and coordinated encounter on-site with Carlos Melendez (TESLA) and Vincent Skochpole (Sargent and Lundy)
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted Cambalache weekly meeting with Designer (Sargent & Lundy), Contractor (RG Engineering) and Owner (Genera PR) for weekly action items discussion. Attendees: Herminio Arroyo (Genera), Dean Ennes ( Sargent and Lundy) and Jose Segarra (RG Engineering) and, Luis Damudt, Jean Menay, Jorge Mercado, Luis Duque (DCMC) and Digno Cartagena (Genera)
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Followed up with Cambalache Construction Weekly meting to cover pending actions and doubts. Generated meeting minute and distributed through Procore.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received Issued For Construction (IFC) drawings from Sargent & Lundy (Ivette Miranda). Reviewed drawings to plan distribution and publishing in Procore. The published drawings will enable construction contractors to understand the project’s scope.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met in a site visit with Vincent Skochpole (Sargent and Lundy), Carlos Melendez (TESLA), Herminio Arroyo (Genera PR) and DCMC (Luis Damudt, Carlos De Jesus, Jorge Mercado) for design discussion for electrical transformer installation.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja Demolition Project Meeting - Tesla Andre Soares, Felipe Vilos, Keyver Jariya, Qais Feroz and Carlos Melendez; Nord Engineering Cop. Benjamin Gutierrez; Vincent Shochdopole; CPS Gordon Likes, DCMC Rafael Barrera, Carlos Rodriguez, Gabriel Morales, Jose Lopez, Gilberto Soto, Jean Menay and Eduardo Rivera; CDM Smith Nelson Soler; ARG/CERES Carlos Hernandez. - Meeting was to perform a site visit with Tesla, S&L CPS, DCMC, ARG/CERES and Nord to review site for the second phase Contruction project.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - ADS and Homeca had demolish part of the dike wall and also start with the demolition of the main Diesel tank S-1. Site visit has arrived at project for meeting.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue with the demolition of the main diesel tank, tank has been partially demolished. Walkdown with Asdrubal Morales of BETA for the repair and relocation of the existing MPT of Genera site to be relocated to Luma property.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca contractor start today with the demolition of the Diesel wall containment pit. They still had not completed to drain the remain diesel at tank SLOP-1. Meeting with Gilberto Sucre of DCMC that visit the project site we have discuss son of the RFI send by ARG/CERES contractors. Preparing for site visit of Tesla, S&L, CPS and ARG. Send email to Francis Rios of Luma to inform that on June 9 we are expecting to install a crane at their yard for the rigging of two small diesel tank. Send email to Carirma Sanchez (HOMECA) in request to provide the vacuum truck to remove the remaining diesel at tank Slop-1 and Slop-2.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an early morning coordination session with Hernan Machado, Milton Flores, and DCMC warehouse personnel to address outstanding inventory variances identified during the previous day's audit cycle. Emphasis was placed on aligning daily operational workflows with real time inventory system accuracy and ensuring traceability across all recorded transactions to maintain audit compliance and data integrity.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory integrity audit to detect and analyze variances between physical stock levels and digital inventory records within locations AM 001 to AM 012 and GD 007 to GD008. The evaluation involved root cause analysis of transactional discrepancies. lifecycle tracking of serialized and non-serialized items, and detailed examination of movement logs. Activities also included verifying system generated balances in Asset Suite against actual on hand quantities, assessing potencial data input inconsistencies, and validating historical adjustment.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-collaborated on-site with Mr. Milton Flores from DCMC to lead the preparatory phase for upcoming cycle count operations. Activities focused on validating inventory master data, reviewing and confirming bin locations, and organizing stock for accurate physical verification. The effort also included refining the documentation structure, aligning data capture protocols with established audit requirements, and ensuring that all materials and system records were properly synchronized. Today's review will range from AM 001 to AM 012, GD 007 to GD 008.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted targeted cycle count activities across designated inventory zones, specifically locations AM 001 to AM 012 and GD 007 to GD 008. The effort focused on verifying physical stock levels, reconciling item quantities against system records, and identifying discrepancies requiring corrective actions. All findings were documented to ensure traceability and enable process improvements. These actions contribute directly to strengthening inventory reliability.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while at the San Juan warehouse, comprehensive inventory performance assessment was conducted. A consolidated report was prepared for Mr. Anthony Vega of Genera PR, incorporating system wide inventory data from all warehouse locations. The analysis includes catalog ID, stock balance summaries, cost allocation, detection of inventory discrepancies, and compliance assessment with predefine minimum and maximum threshold. Performance indicators were quantified using percentage base metrics to evaluate inventory accuracy, adherence to operational standards, and procedural consistency across all sites. The reviewed locations included: AM 001 to AM 012, GD 007 to GD 008, AB 062 to AB 095, AK 035 to AK 049, AF 001 to AF 084.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a targeted inventory recount at the San Juan warehouse in coordination with Mr. Milton Flores from DCMC to assess data integrity and validate the accuracy of prior cycle count results. The task involved cross-referencing physical inventory with Asset Suite system records, identifying and documenting variances, and analyzing root causes of transactional discrepancies. The scope of work covered inventory locations AM 001 to AM 012 and GD 007 to GD 008 reinforcing compliance with internal controls and audit preparedness protocols.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review and edit the Preliminary Quality Control Plan for the BESS Program of the Cambalache Power Plant DCMC, Division 9 Finishes, Topic All Finishes, Inspection and Testing, Inspection by Contractor, Acceptance.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, TESLA Visit Cambalache with Andres Concepcion, Jorge A. Mercado, Carlos De Jesus, Luis Duque DCMC, Andres Suarez, Felipe Augusto Velas from TESLA, and Herminio Arroyo Genera PR to verify project batteries.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review and edit the Preliminary Quality Control Plan for the BESS Program of the Cambalache Power Plant DCMC, Division 9 Finishes, Topic All Finishes, Acceptance.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - discussion issue before TESLA representatives Visit to Cambalache with Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Meeting Walk-tour Coordination with RGE Cambalache S & L / CDM Smith Weekly Cambalache BESS - Construction Weekly with Andres Concepcion, Luis O. Damudt, Jorge A. Mercado, Carlos De Jesus, Luis Duque DCMC, Alberto Borelli, Jose Segarra, Angel Cruz, Harry Velazques from RGE, Herminio Arroyo Genera PR.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety received Tesla Visit joint with Carlos Hernandez from ARG.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Procore Working Sections - Procore Working Sections Kickoff. Initiated the upload and logging of supportive project documentation into the Procore system for PWs 10710 and 11855 under DR4339. This effort marks the kickoff of the Procore Working Sections initiative and aims to establish a structured repository of evidence of payment and compliance documentation. The goal is to enhance visibility and understanding of the final product presentation and to ensure proper traceability of reimbursable expenditures through a standardized logging process. Participants DCMC (Rafael Calderon, Esther Rohena, Cynthia Ortiz, Mark Merritt, D'Alexander Gonzalez, Lauren Wells (Lemoine), Johanna Diaz (SMC)
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 164 | 574 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reviewing RG Engineering_109403 contract (876 pages long) Article 6-12 and start preparing RFI for RGE. working session review the contract terms that affects the invoice. review the invoice and identify missing information and clarification; also, prepare a schedule of value based on the contract for this vendor in preparation for RGE Kick-Off Meeting.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Continue working with Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#10_PRIN0008450_Feb 2025. RFI related to Federal project Scope. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 935 locations AK035 to AK049.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AM001 to AM012
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AM001 to AM012
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AM001 to AM012
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AM001 to AM012
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AM001 to AM012
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 00 062 000 to AB 00 095 000
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 00 062 000 to AB 00 095 000
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 00 062 000 to AB 00 095 000
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AF 001 TO AF 084 at the Aguirre warehouse to start the cycle counts.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AF 001 TO AF 084 COUNT LIST # 925/926/9/27/932/933/934
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AF 001 TO AF 084 using the RECOUNT LIST # 939/940
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations AF 001 TO AF 084
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 152 | 114 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #935 from locations AK035 to AK049 for a total of 5,131 pcs.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AK035 to AK049 Cycle Count List # 930.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AK035 to AK049 to begin the cycle counts.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK035 to AK049.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Hurricane Maria Verified the implementation of the Drawing Number editing functionality for multiple-sheet drawings to ensure proper document control and consistency across project files. Performed testing and troubleshooting using comparable project files to validate the correct application of drawing number updates and confirm system functionality. Executed the drawing number editing feature to assess accuracy, identify potential issues, and support standardized document management practices in alignment with project requirements.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 151 | 528.5 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/ Procore New Users Setup and Welcome Process/Vega Baja BESS S&L Submittal Review for Process/Costa Sur BESS & Peakers Coordination regarding Community Plan for each project
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/Process Procore New Users - Various Projects/ Costa Sur Peakers/Aguirre/Costa Sur BESS/Daguao/Cambalache Download_Review of Permitting Environmental Data & Transfer to individual Projects
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Gather contractual agreement and clients requirement for the proper incorporation of Construction Management Process inside the Procore Platform; Uniform General Conditions, contractual obligations and agreement's integrity.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform Procore quality control for uncategorize items such as Submittals and RFIs inside Project Management tools; suggestions to move files from Management Tools to the Document Tool.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Cambalache Weekly Meeting on Microsoft Teams with contractor RGE and his team Jose Segarra, Jose Robles, Xiomara Perez and Vernadee Ortiz. Also, from DCMC Andres Concepcion, Luis Damudt and Luis Duque. From Sargent & Lundy Dean Ennes. Discussion of weekly project topics such as Upcoming construction kickoff, Procore implementation of Connection Manager (transfer of data between Procore portfolios) and Document Quality Assurance.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 149 | 596 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reading RGE contract and identifying important information in preparation to internal meeting and Kick Off meeting. RGE Contract has 876 pages and is important to understand key information regarding invoices and supporting documentation.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 149 | 298 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Continue reading RGE contract and identifying important information in preparation to internal meeting and Kick Off meeting. RGE Contract has 876 pages and is important to understand key information regarding invoices and supporting documentation. This is going to be a recurrent task in preparation for next week meetings.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.75 |  | 149 | 409.75 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Start reviewing Sargent & Lundy Invoice_TO1_February2025. Reviewing employees, rates and classification, preparing excel for pre intervention and start reading narratives (309 lines narratives).
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Held a meeting with the Genera PR team, led by Jorge Bracero, to align on next steps regarding the community engagement strategy. The discussion focused on the development of the fact sheet, including content structure, key messages, and distribution plans. Additionally, we reviewed the logistics and objectives for the upcoming community meeting in Vega Baja. Action items were assigned to ensure timely completion of materials and coordinated outreach efforts ahead of the event.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 139 | 243.25 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Meeting with the Genera PR team Jorge Bracero to schedule 'next steps' of pending projects, update and update the work agenda for the next few days
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Reviewed and refined the copy and data included in the BESS & Peakers newsletter to ensure clarity, accuracy, and alignment with the project's communication goals.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.25 |  | 139 | 173.75 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Reviewed and optimized the aesthetic layout of the BESS & Peakers newsletter. Focused on improving visual appeal, brand consistency, and overall design to enhance audience engagement. Updated templates and graphic elements will be applied to future editions to ensure a more polished and cohesive communication piece.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Held a one-on-one meeting with Frances Vallejo DCMC to discuss updates related to the BESS and Peaker project. The conversation focused on the current status of deliverables, key milestones achieved, pending tasks, and any challenges impacting timelines or resource allocation. Action items were identified to ensure continued progress and alignment with project goals.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Meeting with Enactus to coordinate community effort with the Isla de Cabra Community and community effort with the Coqui community in Salinas. The meeting was attended by the Genera PR team: Iván Báez and Jorge Bracero and the Enactus team: Lymaris Otero, Adeline Pérez and Rudy Rivera
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Completed review BESS Enlarged Ground floor plans, Interior Elevations and details for 4339_9510 BESS_Cambalache project.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on TEAMS meeting related to Cambalache BESS - Construction Weekly with pending steps for sign contract, status of the temporary facilities, special initial permits PWPPP, submittals and status of starting initial construction process with DCMC employees Andres Concepcion, Luis Damudt, Luis Duque, employees of RGE Jose Segarra, Xiomara Pérez Álvarez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 134 | 201 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on program procurement with delivery milestones schedule status report for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on site meeting at inspection for rigging plan and transformer specific site proposed area with employees (TESLA) Carlos Melendez, employees (DCMC) Andres Concepcion, Gabriel Morales, Luis Duque, Luis Damudt, employees (Sargent and Lundy) Vincent Skochdopole, Victor Gonzalez, Abdiel Gozalez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache-worked on program procurement schedule status report for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on project construction site visits and projection of starts with schedule milestones status report for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, RFC: Civil/Structural Proposal Data. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, RFC: Mechanical Proposal Data. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, Payment Schedule Data. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS TESLA Visit Cambalache meeting with Andres Concepcion (DCMC) and Vincent Skochdopole (Sargent and Lundy) for the 4339_9510 BESS_Cambalache project.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Construction Weekly meeting with Andres Concepcion (DCMC), Robert Molner (Sargent and Lundy) and Jose Segarra (RGE) for the 4339_9510 BESS_Cambalache project to ensure that the project stays on track and facilitate collaboration and decision-making among team members and stakeholders.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Overseeing and updating new requests for proposals (RFPs) and their current status to ensure accurate and comprehensive documentation in the May report. This includes tracking submission dates, reviewing proposal progress, incorporating relevant stakeholder feedback, and highlighting key developments to provide a thorough and well-structured report for review and submission.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 122 | 244 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Procore - Working Sections Meeting to discuss financial processes. DCMC Attendees: Rafael Calderon, Esther Rohena, Cynthia Ortiz; Lauren Wells (Lemoine), SMC: Johanna Diaz. CDM Smith: Manuelly Concepcion.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continuously overseeing and incorporating the latest updates and relevant details into the Community Outreach project for inclusion in the May report. This ensures a comprehensive and well-documented submission, reflecting all key activities, progress, stakeholder engagements, and any significant developments that have taken place.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 52 | 52 | 52 | Yes | 146793 |  | Portosan - Vega Baja - 6/4-6/18/25 Containment Tray
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site. Tesla visits to Site. Metting with Jose Ramos about rigging plan.
2025-06-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 116.2 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Yabucoa Site to Cambalache site to Vega Baja Site to Palo Seco Site and To Yabucoa Site. Purpose - Meetings at Cambalache site, Vega Baja Site and Palo Seco Site with Carlos Melendez (Tesla) and Surgent and Lundy of Genera design team to define the strategy of preparation, delivery and installation for the BESS project.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore project 11855 for configurations of tool set.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Yabucoa; Met with site manager to walk the scope of work to verify its budgeting, planning, and execution, and definition of responsibilities and requirements. Harry Del Valle DCMC
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Performed Peakers site evaluation (YABUCOA) for field verification of site layout and trailer placement which impact project efficiency, safety, and cost reduction. Verified the site layout optimizes productivity and aids project timeline and budget.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Contractual Documents review in preparation for meeting with RG Engineering and Genera to discuss draft submission made by Contractor.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procurement Meeting with RGE BESS Install Aguirre & Costa Sur Projects Jose Robles - RGE, Wilfredo Sierra - Sargent & Lundy, Gabriel Perez - CDM Smith and Gilberto Sucre DCMC Partners
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluation of Budget Review for PMO Program for BESS and Peakers.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Morning Update call to DCMC Site managers for progress updates for Vega Baja, Cambalache, Aguirre and Costa Sur to help maintain project timelines, ensure resource efficiency, and ensure high-quality results.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Vega Baja Preparatory Meeting for Legal Meeting with Homeca Recycling with Genera, & CDM Smith. Contractor did not show up to the meeting and had to reschedule same parties fro the following day.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Meeting PM/CM Team alignment for RGE & ARG Ceres final scope, budget & schedules for Aguirre, Costa Sur & Vega Baja. Gabriel Perez CDM Smith, Franklin Colmenares CSA Group & Gilberto Sucre DCMC
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Joel Pantojas (Genera) to confirm award schedule duration by RGE of 260 calendar days and not 10 months per latest schedule submission.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Met with Joaquin Quinoy (Genera) for weekly alignment meeting, this week we worked to identify communication and operational challenges impacting project efficiency, Teams group creation, and scheduling. Discussed improvement strategies for the P3 approval process and KPI metrics. Aligned on planning a two-day process improvement workshop and next steps for stakeholder engagement, including Kevin D. Futch and Jose Molina (Genera)
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Worked to schedule initial meeting with the P3 Approval Process Improvement Team Kevin Futch (Genera), Christian J Torres Pena (Genera), Angelina Minier (Genera), Cristina Ribas Morera (Genera), Joel D Pantojas Caraballo (Genera), Jorge E Sanchez Valle (Genera). Sent the team a find time poll, worked to determine availability and scheduled a meeting. Sent the team an explanation of the goal and explained the the 8 step Toyota problem-solving process that we will be using.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Worked with Kevin D. Futch Genera) to support his role as team lead of the P3 Approval process improvement project, set up and explained the 8 step process with an example A3 template so he can communicate the expectations and plan to the project team. I also outlined a sample time table for each step and we worked to determine when we will be next week and when I should plan to schedule my onsite visit in June to work through steps 2-4 with the team. We worked virtually through an excel document and through Teams Chat.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Coordination call for Procore SOPs dealing with the financial module. Attendees were Foster Veazey, Lauren Wells (Lemoine), and Elizabeth Fronduto (Procore)
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reports for usage of tools.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial information.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating team tasks for Procore items.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of several Procore meetings for next week.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Procore (Lauren Kennedy), Esther Rohena, Glorimel Torrado, Rafael Calderon, and Gilberto Sucre all with DCMC to discuss Procore financials.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore documents tool.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore system configurations.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool configurations.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore financials to prepare for upcoming call and gathering notes to turn over to Lauren Kennedy (Procore) for development of SOP's.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore application installs for Office 365.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Keyla Sierra from Integrum and José Ralat from DCMC to review existing issues affecting KPI calculations in the Genera Connect Financial Tracker and to discuss necessary enhancements. The conversation focused on identifying root causes of discrepancies and outlining required additions to improve data accuracy and reporting capabilities.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Working session Luis Gonzalez, Shane Landon, Michael McPhillips by Morris-Shea about Genera EHS for Cambalache Visit. Metting with Gabriel Perez (CDM SMITH) and Clara Padovani about Emergency Management for all Genera projects. Prepare document information for Osvaldo de Jesus (GENERA). Review the Vega Baja project documentation.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting with Clara Padovani (GENERA) about Cambalache Site Status Maintain to maintain clear communication, discuss expectations, and evaluate project progress. Meeting with Victor Rodriguez (GENERA) about all Genera Projects.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with BESS and Peaker project management team to discuss project schedule and budget. Participants: Gabriel Perez (CDM), German Nunez (Genera), Carlos Palomares (CDM), Gilberto Sucre (DCMC) and Abraham Velazquez (DCMC).
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4898 Vega Baja - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4899 Costa Sur - Supported the Regulatory team by beggining to assemble the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Reviewed, commented on, and edited the FEMA 90-Day Plan, with a focus on updating the procurement section to reflect current activities and priorities. Shared feedback and revisions with D’Alexzander González (DCMC) and Jesús Cintrón (Genera) to ensure alignment and support finalization of the document.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued developing the Procurement Automation Scope of Work by consolidating content to eliminate duplication, proofreading for clarity and accuracy, and ensuring all relevant cybersecurity requirements were included. Requested Power BI access for Jesús Cintrón and María Sánchez of Genera to support the strategy for sharing PMO KPIs through business intelligence tools. Additionally, worked with José Ralat DCMC to validate financial tracker workarounds, confirming accurate expense KPI reporting within the Genera Connect platform.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Tested recent modifications to the financial tracker file by uploading it to the Genera Connect Financial Tracker and verifying that KPI values displayed as expected. Continued development of the Procurement Automation Scope of Work, adding new use cases and contextual details to ensure the proposals are clearly defined and aligned with operational objectives.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while demolishing the Deisel container located in Vega Baja site. Completed with Luma installation for the temporary line and waited for Genesis to verify air conditioning console for guard house.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Site visit with Carlos Rodriguez and Rafael Barrera (DCMC) to view the blueprints of the project. Continue watching the Procore videos recommended by Theresa Perez (DCMC) to understand how to use the platform.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria TECHNICAL SPECIFICATION REVIEW FOR BESS CIVIL WORK CONTRACT (CWC) Spec. No.: G-2900 Revision: A; For Bid Project No. A15240 January 31st, 2025
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review of Good Workplace Practices in an Electrical Plant: Operational Efficiency, Environmental Stewardship and Employee Engagement and Communication
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review Unsafe Practices or Gaps in Safety at an Electrical Plant: Inadequate Lockout/Tagout (LOTO) Procedures, Insufficient Use of Personal Protective Equipment (PPE), Poor Hazard Identification and Risk Assessment, Lack of Emergency Preparedness, Weak Safety Modules and Communication, Poor Housekeeping and Cluttered Work Areas, Overloading Electrical Systems
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Conducted a review of good workplace practices applicable to operations within an electrical plant, with a focus on health and safety management, workforce readiness, and operational controls. The review addressed established safety practices, hazard awareness measures, use of personal protective equipment (PPE), communication protocols, and procedures intended to promote safe work execution and regulatory compliance.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS PROJECT; Meeting at the Genera PR Central Office to meet with Carirma Sanchez, Eduardo Ramos & Carlos Sanchez (HOMECA Recycling), (DCMC), Gabriel Pérez (CDM Smith), and Jesus Cintron (GENERA) to discuss project performance and alternate prices for Phase II.Demolition.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS PROJECT - Continued Vega Baja Bess Project contract and Specs. Overview to ensure all project participants have a clear understanding of the expectations and requirements, and understand their participation in the project’s execution.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued working with the proposals for BESS Yabucoa RFP 231175. Verify that the proposals are complete according to the project documents. Review Proposals to make recommendations. Preparing DCMC Quality Control Plan.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working with the proposals for BESS Yabucoa RFP 231175. Verify that the proposals are complete according to the project documents. Review Proposals to make recommendations. Preparing DCMC Quality Control Plan.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attend the project coordination tour with the contractor's staff (RGE), Jose Sarraga, Herminio Arroyo (GENERA), and Andres Concepcion (DCMC). This will be done prior to the contractors' mobilization.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Visit to the Cambalache site where preparations are made with Andres Concepcion DCMC and coordination prior to the meeting of the contractor and subcontractors.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination work continues prior to the contractors' mobilization to the Cambalache site. Environmental issues are being discussed with Roseanne Perez (GENERA), and possible daily work permit formats are being analyzed.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated with Jean Menay (DCMC) and participated of a subcontractor's safety orientation meeting for purpose of access to the Cambalache Plant. Attendees: ADCO Inc. – Demolition Contractor, José L. Santiago Corp. – Earthwork Contractor, Morris-Shea Bridge Company – Rigid Inclusion Contractor, Grupo Titan – Concrete Contractor.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed documentation regarding Issued for Construction (IFC) drawings set to acknowledge new changes and design details. This will be the drawings used during the construction to outline project specifications, and ensure adherence to building codes and quality standards
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Managed Emails from RG Engineering Jose Segarra and provided requested information regarding existing warehouse gas cylinders storage requirements. Managed emails form Genera PR (Erick Rocher) regarding environmental permitting.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Site Visit Meeting to the Cambalache Plant for subcontractors site inspection planning to ensure works within project go forward as planned and are according to requirements, standards and regulations. Meeting conducted by RG Engineering (Jose Segarra). DCMC Partners (Luis Damudt, Luis Duque, Jorge Mercado) and GeneraPR (Herminio Arroyo) attended with ADCO Inc. – Demolition Contractor, José L. Santiago Corp. – Earthwork Contractor, Morris-Shea Bridge Company – Rigid Inclusion Contractor, Grupo Titan – Concrete Contractor.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja Demolition Project Walkdown Meeting - Homeca Carirma Sanchez; CDM Smith Nelson Soler; DCMC Jaime Pesquera and Eduardo Rivera - Meeting was related to review the remaining demolition work to be done before demolition of Guard House, it was address to Homeca all item that should be remove as soon Luma disconnect power to existing guard house and disposal of hazard material before demolish the guard house.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue with demolition of Diesel tank S-1, the vacuum truck arrives at job site they start removing from tank SLOP-1 and SLOP-2 the remaining diesel with sludge, also the remove water with oil from a pit for properly disposal. Luma start with the relocation of the temporary traffic light and new temporary for the trailer and guard house. Genera arrive at site for the removal of PREPA finger to be taken to Genera warehouse. Temporary work has been completed, and finger was removed from project site.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca is awaiting the arrival of the Vacuum Truck. Homeca subcontractor J.N. Electrical contractor continue at site for the temporary relocation. Luma Alexis Amador of Luma inform that they will arrive at 11:30am for the meter relocation and traffic light relocation.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca contractor continue with the demolition of Diesel tank S-1, Homeca electrician has arrive to project for temporary electrical connection for Guard house, we are also expecting Luma to arrive for the meter installation and relocate power for traffic light. Homeca is pending the arrival of vacuum truck for disposal of final Diesel that is contaminated.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a comprehensive inventory data analysis and developed system aligned cycle count worksheets to facilitate planned reconciliation efforts at the Palo Seco warehouse. The engagement was carried out in coordination with Mr. Giovanni Taffanelli from DCMC, with and emphasis on enforcing operational compliance and standardizing procedures. Core task included validating item master data, cross referencing physical inventory with system records, and verifying bin level stock accuracy. Additionally, required materials and resources for the count process were identified and strategically organized to streamline execution.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a focused variance analysis to identify and evaluate persistent discrepancies between physical stock quantities and digital inventory system records across locations BT 025 through BT 040. The review involved a detailed audit of item catalog data, transaction history, and the chronological sequencing of inventory movements.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco warehouse, conducted the development of a comprehensive inventory performance report for Mr. Anthony Vega of Genera PR. The report consolidated data from all active warehouse zones and integrated key analytical metrics, including catalog ID reconciliation, unit-level stock verification, valuation summaries, and variance analysis. The evaluation covered cost discrepancies, physical inventory mismatches, and compliance with established maximum and minimum stock thresholds. Visual performance indicators were utilized to assess the operational status of each location, identify systemic inefficiencies, and improve transparency in reporting. Locations assessed included BT 025 to BT 040, AF 084 to AF 144, GD 009 to GD 015, AB 096 to AB 107.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory recount at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC. The primary objective was to validate the accuracy of previous cycle count results, reconcile discrepancies between physical inventory and system records, and confirm transactional integrity. The recount process involved cross verifying bin level item quantities, evaluating compliance with storage protocols, and identifying any variances impacting data accuracy. Recount activities covered storage locations BT 025 through BT 040.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an early morning operational briefing alongside Juan Vallejo, Hernan Machado and key DCMC warehouse personnel to address and review discrepancies identify during the prior day's activities. The primary objective was to reinforce the importance of accurate data capture, adherence to established procedures, and preservation of inventory integrity. Emphasis was placed on procedural compliance, implementation of corrective actions, and mitigation of recurring issues. Additional focus areas included process standardization, risk mitigation strategies, and driving operational consistency across warehouse functions to ensure alignment with define project goals and performance target.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed cycle count procedures for designated inventory areas BT 025 through BT 040. This task was part of a broader initiative to improve inventory accuracy and ensure alignment between physical stock quantities and system reported balances. Key activities included validation of item master records, verification on bin level quantities, inspection of labeling accuracy, and evaluation of environmental storage conditions. The process also involved identifying discrepancies such as missing, misplaced, or misclassified items. These actions directly contributed to maintaining data integrity, enhancing transactional accuracy, and improving the overall reliability and performance of the inventory management system.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Preparation of a consolidated list with all critical components information to share with CPM.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Independent Cost Estimate for One New Set of Open and Close Hardware for Palo Seco Power Plant Units 3 & 4 under D'Alexzander González (DCMC) review.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Technical Specifications of One New Set of Open and Close Hardware for Palo Seco Power Plant Units 3 & 4 under to develop Independent Cost Estimate.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS RG Engineering - Subcontractors - Site Visit Cambalache site coordination efforts with Andres Concepcion, Jorge Alexis Mercado DCMC, Herminio Arroyo Genera PR Jose Segarra from RGE.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review Lemoine Policy & Procedure Manual Topic: Policy and Procedure.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria - Review and discussion of the coordination and location of storage cars and other issues of the contractor's mobilization to the site with Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque of DCMC Cambalache Power Plant team before the visit with RGE Contractor.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES Homeca Recycling keeps dismantling, Decommissioning and demolition works and planning for phase II. Luma came in today and connected the temporary power to the site, restored the street connection and now we will proceed with tower demolition
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BEES Homeca Recycling keeps dismantling, Decommissioning and demolition works and planning for phase II. Luma came in and connected the temporary power to the site.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria At the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform. RFi #56, RFi #57, RFi #58, RFi #43, RFi #44, RFi #47, RFi #48, RFi #50, RFi #51, RFi #52, RFi #53, RFi #54, RFi #55, RFi #56.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while demolishing the Deisel container located in Vega Baja site.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while demolishing the Deisel container located in Vega Baja site. Continue Luma temporary installation for distribution line.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Pro-Core Meeting: Procore - DCMC Financials Tools - review new ProCore functionalities to process and document invoices, contract balance, PWs and discussed workflow streamline opportunities within DCMC Team. This tool will facilitate invoice review process and accurate contract balance for all Genera projects including BESS and Peakers. Participants from DCMC - (Rafael Calderon, Glorimel Torrado, Gilberto Sucre, Foster Veazey, (Lauren Wells -Lemoine), Lauren Kennedy-ProCore and others
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 164 | 410 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW#10710 Continue working on Siemens Energy Contract #00106588 Meeting. Review deliverable Schedule based on project development and new change order #2 request. Contract review and documentation to identify allowable task, scope and impact to contract schedules. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status / Payment Milestones Financial Reconciliation) Meeting with project management Team, Genera Legal and Genera Finance. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, MegaPacks and tariffs for all plants. Meeting participants CSA (Franklyn Colmenares), Genera team (Kevin Futch, Maria Sanchez, Fernando Ortiz, Alejandro Maymi), and DCMC (Rafael Calderon, Esther Rohena, Jose Ralat)
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 955 and 956 locations BT025 to BT040.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GD009 to GD015
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GD009 to GD015
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GD009 to GD015
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GD009 to GD015
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GD009 to GD015
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 00 096 000 to AB 01 007 000
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 00 096 000 to AB 01 007 000
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 00 096 000 to AB 01 007 000
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AF 084 TO AF 144
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AF 084 TO AF 144 RECOUNT LIST 900
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. AF 084 TO AF 144 COUNT LIST # 942/943/944
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AF 084 TO AF 144 at the Aguirre warehouse to start the cycle counts.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BT025 to BT040.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations BT025 to BT040 Cycle Count List # 945.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations BT025 to BT040 to begin the cycle counts.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 152 | 114 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #955 and 956 from locations BT025 to BT040 for a total of 2,237 pcs.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Rafael Pabon and Manuelly Concepcion (CDM Smith), Franklyn Colmenares (CSA), Lauren Wells (Lemoine) and Theresa Perez (DCMC) to discuss the progress achieved on document control, pre-bid and pre-construction documentation and documents being developed to be archived.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control/ Gen 01 Project Folder - Environmental - Permitting Data Download for Vega Baja BESS - Review & Process for Transfer-Upload/Provide GENERA New User Access in Procore for BESS & Peakers
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management /Gen 01 BESS Peakers Data Management Review and Process/Coordination regarding Financial Project Folder for Invoices with Rafael Pabon (CDM)_Luis Roman (DCMC)_Franklyn Colmenares (CDM)_Manuely Concepcion (CDM)/Coordination of RG Equipment Data Request with Incorporate Subfolders in Procore 1100 Financials - Accounting Project Folder
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review Procore certification and videos from the Drawings tool in search for routes when drawings have multiple sheets and same numbering.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Analyze and review Cambalache project drawing plans to determine potential drawing areas to be established on the Drawings tool to separate drawings with publishing issues.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform QA/QC for Procore Project Management Tools at the Costa Sur and Cambalache projects; review recently uploaded Submittals and RFI to review proper allocation on subfolders or tools.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform QA/QC for Procore SOPs while continuing with the preparation of SOPs for the Punchlist, Action Plan and Forms Tools.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - Siemens Energy Contract #00106588 and Deliverables submittals review for Milestone #2. Reviewing documents: PO's for work packages 2-7 and all submittals provided on zip packages.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 - Siemens Energy Contract #00106588 and Deliverables submittals review for Milestone #2. Continue reviewing documents: PO's for work packages 2-7 and all submittals provided on zip packages. During this time I review 2 more PO's.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.75 |  | 149 | 260.75 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Continue reviewing Sargent & Lundy Invoice_TO1_February2025 validating narratives (309 lines narratives). This task is completed, pending compliance review for this invoice. Also, during this time I review final invoice signed for EHSS_TO9, prepare final package and send it for CPA.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Financials meeting to discuss pre intervention process in Procore platform. In this meeting participates Lauren Kennedy from Procore and from DCMC Rafael Calderón, Glorimel Torrado, Lauren Wells. Also, subcontractors Ginell Torres, Johanna Díaz and Shellsea Maysonet.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.75 |  | 139 | 521.25 | 139 | Yes | 146793 | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Progress continued on the translation of Volume 3, Chapter 11 (Sections 11.9 to 11.12) of the SHE Manual, ensuring consistent formatting and structure, accurate use of technical terminology, and correction of spelling errors throughout the document.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Edited the data included in the BESS & Peakers newsletter to ensure clarity, accuracy, and alignment on the update in all the site.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Coordinate site visits with Genera PR team Jorge Bracero and DCMC Partners team Raissa Borges.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Reviewed and updated the BESS & Peakers newsletter sites. Optimized layout, refreshed design elements, and aligned graphic templates with brand guidelines to ensure a more cohesive and professional presentation.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Create the itinerary and work plan for the upcoming community educational summer camp event in Toa Baja were developed and optimized, with a special emphasis on teaching and raising awareness about sustainable energy through the BESS project.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Held update meeting with the Genera team Jorge Bracero to align on pending projects and next steps. We discussed the upcoming site visits, confirming priorities and outlining the logistics to ensure alignment with project goals.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Update the Community Outreach plan to include new proposed dates, edited the engagement approach, and began drafting an agenda to guide the session.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management - DR 4339: Worked on updating the Genera project sites in Google Maps. Added the Aguirre, Costa Sur, and Yabucoa sites along with their assigned employees. Sent an email to Gilberto Sucre (DCMC) with the updated map link. Updated the Contact Log Per Site with emails and phone numbers.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 139 | 173.75 | 139 | Yes | 146793 | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Progress continued on the translation of Volume 3, Chapter 12 (Section 12.1) of the SHE Manual, with a focus on maintaining consistent formatting and structure, ensuring the accurate use of technical terminology, and correcting spelling and grammatical errors throughout the document.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS RGE Subcontractors meeting and walkthrough with Andres Concepcion (DCMC) and Jose Serrano (RGE) for the 4339_9510 BESS_Cambalache project.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on project PROCORE settings including Meetings and Schedule for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur-worked on project PROCORE settings including RFI and Submittals for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on Teams meeting related to procurement, contract status and principles of construction in demolition themes typical for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on project PROCORE settings including Specification upload for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 134 | 335 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, Level one Schedule. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 134 | 469 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue reviewing project documentation, Milestones Schedules. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Begin reviewing project documentation, RFP 229760 Battery Storage System. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review BESS Issued for Construction plans, mechanical AGBESS FP Isometrics for 4339_9510 BESS Cambalache project to identify potential issues and streamline workflows.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Initiating the development of the project financial flowchart in the Visio application to provide a visual representation of the process and facilitate the implementation of the financial tool within Procore.
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Abraham Velazquez, Gilberto Sucre, Frances Vallejo CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares, Enrique Laya Genera: German Nunez
2025-06-05 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 122 | 244 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continuing with the development of the project financial flowchart in the Visio app, refining visual elements to enhance clarity and ensure a seamless representation of the financial process. Integrating key components to align with Procore's Financial tool requirements, facilitating a smooth implementation and optimizing workflow efficiency.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 2357.14 | 2357.14 | 2357.14 | Yes | 146793 |  | Home Depot - Equipment and supplies for Aguirre trailer
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146793 | Remote | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mark Merritt, Frances Vallejo, Lauren Wells, and Ada Diaz, DCMC. Discussed update on project, job offers, PROCORE working session schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 worked on internal paperwork and catches up on reports to ensure a smooth project workflow and client satisfaction.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Participated in internal meetings with construction personnel reviewed SOP to maintain uniformity, ensure quality control, and promote project safety. Frances Vallejo Rosich DCMC Harry Del Valle DCMC Gilberto Sucre DCMC Jean Pierre Menay DCMC Paul Browne DCMC Lauren Wells DCMC Paola Arroyo DCMC.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Internal Preparation for upcoming legal meeting with Homeca recycling, CDM Smith, and DCMC Partners.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting AGR Ceres Vega Baja. Provided ARG Ceres instruction to close out proposal with Field demolition and Geopiers to complete the award agreement. PreCast VE can be evaluated later. Jesus Cintron -Genera, Gabriel Perez - CDM Smith, Wilfredo Sierra - Sargent & Lundy, Carlos Hernandez ARG Ceres and Gilberto Sucre - DCMC.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Homeca Recycling Contract Meeting. Meeting with Carirma Sanchez - Homeca Recycling, Jesus Cintron - Genera, Gabriel Perez - CDM Smith and Gilberto Sucre -DCMC Partners, as subcontractor is in breach of contract and the goal was for them to accept their contractual obligations.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Prepare Weekly PMO Summary Update and action items list for next week.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria In Person Mandatory Construction Field Staff meeting for all staff members from Vega Baja, Cambalache, Costa Sur Aguirre, Yabucoa with DCMC Abraham Velazquez & Gilberto Sucre as well as PMO Office Staff Support.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 – Met with Estefania Colon (Genera HR) to introduce Lean management principles and explore integration with Genera’s organizational culture. Discussed continuous improvement strategies to enhance performance, safety, and employee engagement. Reviewed existing peer-to-peer recognition efforts aligned with core values (e.g., teamwork, integrity, excellence) and evaluated options to expand recognition tools through digital platforms. Aligned on using WhatsApp and SharePoint for communication and identified next steps including leader awareness surveys, development of Lean resources, and spotlighting staff already practicing Lean behaviors.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating new Project in Procore for critical components projects that are not BESS and Peakers.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences about Procore SOPs about their status and publishing dates.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP reviews.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Johanna Díaz (SMC) about 11855 PW folder structure in Procore and uploading contracts and invoices.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating company level Procore reports for Franklyn Colmenares (CSA) for all TESLA tracking items.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks updates for team projects to ensure we are tracking requests and support for users in the program.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore SOP reviews.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items to different teams to recap activities from this week and open items.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of current financial workflows and processes for implementation into Procore.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items for development.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 184 | 138 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in the weekly DCMC pre-meeting to provide project updates and align on ongoing initiatives. Attendees included D'Alexander Gonzalez, Esther Rohena, Jose Ralat, Rafael Calderon, Pedro Cabrera, Paul Browne, Saul Falcon, and Roberto Bosch from DCMC, as well as Jorge Aponte from Integrum.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.25 |  | 184 | 414 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site. Evaluate riggings plan for diesel tanks and communication pole to ensure safety during lifting operations and minimize the risk of accidents and injuries.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Meeting in Palo Seco Genera Site with Osvaldo de Jesus and Irving Babilonia (Genera) about Environment, Health and Safety (EHS) topics to examine high-risk activities and implement accident prevention strategies.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.75 |  | 184 | 506 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Internal kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Call with Gilberto Sucre (DCMC) to discuss Procore design submittal and approval process, coordination with Genera and S&L and site coordination needed.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended Procore Project weekly discussion meeting to discuss Procore status, SOP's and financials. Participants: Lauren Wells (DCMC), Franklyn Colmenares (CSA).
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended PMO Catch up meeting to discuss BESS and Peaker status of the entire program. We discussed equipment and material purchase, staffing tracker, lean management, safety plan discussion and trailer installation. Participants: Mike Merritt, Mark Merritt, Gilberto Sucre (DCMC) Lauren Wells, Foster Veazey (Lemoine)
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet ¦ Participated in the weekly PMO catch-up meeting with Frances Vallejo (DCMC) and Jesús Cintrón (Genera). Discussed the current status of the BESS and Peakers projects, including progress updates, pending action items, and upcoming deliverables. The conversation focused on key milestones, procurement timelines, and coordination needs across teams to ensure alignment and continued momentum on both initiatives.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4471 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4656 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Uploaded the latest reports into the Genera Connect Financial Tracker to ensure up-to-date data availability. Prepared an updated slide deck for the weekly DCMC pre-meeting to reflect current progress and priorities. Finalized the development of the Procurement Automation Scope of Work by refining the project phases, removing content not intended for the formal exhibit, conducting a final proofreading, and accepting all tracked changes to complete the document.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 184 | 230 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Keyla Sierra from Integrum, along with José Ralat and Esther Rohena from DCMC, to review pending items related to the Genera Connect Financial Tracker. The discussion focused on resolving issues with existing KPI calculations and identifying additional requirements for the development of new KPIs to enhance the platform’s reporting capabilities.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.25 |  | 184 | 598 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Jan Rodriguez and José del Río from Genera PR to review and discuss the KPIs related to power production and fuels consumption. Verified the reported fuel consumption figures against actual fuel receipts to ensure data accuracy. Finalized the report based on this validation and provided it to Jan Rodríguez for submission to the compliance team.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while demolishing the Deisel container located in Vega Baja site. Disposed by 80CY bin towards Homeca recycling facility metal scraps from diesel tank. Uploaded fotos and notes to pro core app.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Internal DCMC Kick off meeting to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Meeting with Abraham Velazquez (DCMC) discussing the Costa Sur Peaker's project. Explain the site mobilization, demolition and new construction areas.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with DCMC Abraham Velazquez on Costa Sur Peaker's project, discussing specifics on site mobilization, demolition, staging and new construction areas.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Internal kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with Abraham Velazquez (DCMC) on Costa Sur Peaker's project to discuss specific on-site mobilization, demolition, staging and new construction areas.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Internal DCMC Kick off meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay, Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Continuous review in PROCORE of project drawings and RFP documentation for the Costa Sur BESS (Battery Energy Storage System) project to ensure technical accuracy, compliance with project requirements, and alignment with engineering standards.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Meeting with Abraham Velazquez (DCMC) about Peakers project summary and drawing review.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: Internal DCMC Kick off meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading Data for Identifying Hazards in an Electrical Plant: Routine hazard assessments, Electrical hazards, Mechanical hazards, Slip, trip, and fall hazards, Chemical hazards, Human factors, Hazard mapping, Risk matrices, Predictive maintenance data
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue reading and review Unsafe Practices or Gaps in Safety at an Electrical Plant: No Culture of Safety or Accountability, Deferred Maintenance, Non-Compliance with Regulatory Standards
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading about the Correct Use of Personal Protective Equipment (PPE) in an Electrical Plant: arc-rated clothing, NFPA 70E and ASTM F1506 standards, insulated rubber gloves, electrical-rated safety boots, face shields and safety glasses, arc flash hoods with balaclavas, earplugs or earmuffs and hard hats
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Internal kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay, Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding the implementation of Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment requirements, time tracking, and the necessary tools for efficient work execution. The team also discussed the integration and management of Peakers within the energy infrastructure, emphasizing the importance of ensuring that Peakers are correctly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Vega Baja BESS job site. Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the Procore platform.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS PROJECT. I had several phone calls with the General Work Contractor, (HOMECA) project manager, Carirma Sanchez, and the company administrator, Eduardo Ramos, to discuss the project contract requirements and contract progress. Participated in Team Meeting with Sargent & Lundy Staff, Robert D. Molner, Gilberto Sucre (DCMC), Enrique Laya, CDM Smith, and Angel Alice Rodríguez Sargent & Lundy to discuss the Phase II Request for Comments to the contract (4339_9510)documents.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Yabucoa Gas Turbine Plant. Attendees, Carlos Villamil (Villamil Group) & Harry Del Valle (DCMC). Topics discussed, walk through Project Site, discussed clearing and grubbing scope of work. Measured areas.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Yabucoa Gas Turbine Plant. Attendees, Abraham Velazquez (DCMC), Gabriel Morales (DCMC) & Harry Del Valle (DCMC). Topics discussed, Costa Sur Peaker's Project Site, discussed scope of work. Project phases.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: Internal kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of peakers within the energy infrastructure, emphasizing the importance of ensuring that peakers are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination with the contractor RGE (Jose Sarraga) for the submission of safe work analysis documents for next week's work at the Cambalache site. This will also include equipment certifications and other requirements.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated various emails as part of project coordination. (1) correspondence to Sargent and Lundy (Vincent Skochpole) for design coordination follow up. (2) Coordination email with RG Engineering regarding soil studies activities. (3) Coordination with Sargent and Lundy (Ivette Miranda) for Procore drawing tool issues discussion.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Performed Review and Comments for observations on the recent released Drawing Set by Sargent and Lundy (Issued for Construction 6.3.2025). Performed review for field coordination and capture any errors or impacts to be revised and solved.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received contractor access request from RG Engineering Jose Segarra for soil study activities. Coordinated requirements for access.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay, Carolyn Baez-Nieves, Glorimel Torrado (all DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team member
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Preparing for meeting with Frances Vallejo and Gilberto Sucre of DCMC. Send email to Carirma Sanchez of Homeca in regard of documentes related to rigging plan for communication tower and also for the rigging of two diesel tanks at Luma facilities.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Coordinate with Jaime Pesquera and Gabriel Soto the works to be done in preparation for tomorrow demolition work of communication tower.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-DCMC Internal kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane –as part of an inventory variance assessment at the Aguirre warehouse, conducted a detailed diagnostic to identify inventory discrepancies and evaluate data irregularities affecting stock accuracy. The assessment aimed to reinforce internal inventory controls by tracing root causes of anomalies, validating data integrity, and ensuring compliance with procedural inventory standards. The analysis supported improved transparency and reliability of records across reviewed storage locations, which range from UH 001 through to UH 011.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted and inventory performance analysis at the Aguirre warehouse, consolidating key data for Mr. Anthony Vega of Genera PR. The review included catalog ID validation, unit count verification, cost variance analysis, and discrepancy identification. Inventory levels were assessed against authorized threshold using percentage base metrics to evaluate stock accuracy, inventory distribution, and system wide integrity. Assessed locations included UH 001 to UH 011, GD 016 to GD 024, AB 108 to AB 121, CL 001 to CL 032.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted planning and preparatory activities for inventory operations at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. The objective was to ensure infrastructure readiness and resource alignment for accurate execution of upcoming cycle count operations. Key tasks included verifying item placement accuracy and coordinating personnel and asset allocation to support procedural compliance.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused inventory validation at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. The scope of work centered on verifying data integrity across selected storage zones by performing physical to system inventory reconciliation, assessing compliance with labeling and storage protocols, and evaluating the accuracy of cataloging and classification. Core activities included validating part numbers and item descriptions, confirming quantity accuracy, and documenting discrepancies for corrective follow up. Storage locations reviewed during this session range from UH 001 through UH 011.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled ABC cycle counts across designated inventory zones as part of continued initiative to strengthen inventory accuracy, reinforce system integrity, and ensure compliance with operational standards. Key activities included validating physical stock against system data, identifying and resolving variances in recorded quantities, and assessing data reliability across multiple storage areas. Task involved verifying labeling accuracy, ensuring compliance with storage protocols, and enforcing adherence to inventory control procedures. Inventory zones review during this session range from UH 001 through UH 011.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a strategic coordination session with Giovanni Taffanelli, Hernan Machado and key warehouse personnel to assess current inventory operations. The session focused on identifying procedural deviations, analyzing workflow inefficiencies, and reinforcing standardized inventory control practices. Emphasis was placed on improving procedural alignment, team accountability, and ensuring continuity throughout the cycle count process.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Made modification to Independent Cost Estimate for One New Set of Open and Close Hardware for Palo Seco Power Plant Units 3 & 4 after D'Alexzander González (DCMC) review.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop High Level Cost Estimate of FAASt Vieques & Culebrea Microgrid Development.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Independent Cost Estimate for One New Set of Open and Close Hardware for Palo Seco Power Plant Units 3 & 4 under D'Alexzander González (DCMC) review.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria: Internal kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Meeting about Review Lemoine Policy & Procedure Manual in City View Plaza with Harry Del Valle and Luis Duque DCMC .
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review Lemoine Policy & Procedure Manual when the Meeting at City View Plaza with Harry Del Valle and Luis Duque of DCMC about the Lemoine Policy & Procedure Manual finishes.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Safety briefing conducted by Emmanuel Santos (Homeca Recyclers) and Gilberto Soto (DCMC) was present. Had Meeting with Carirma Sanchez (HOMECA ) to discuss the weekend work schedule.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Continued Vega Baja Contractor Homeca Recyclers field supervision with Gilberto Soto DCMC. Overview to and frequent briefings ensure all project participants have a clear understanding of the expectations and requirements and understand their participation in the project’s execution and with safety in mind.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while demolishing the Deisel container located in Vega Baja site.Continue to disposed by 80CY bin towards Homeca recycling facility metal scraps from diesel tank. Uploaded fotos and notes to pro core app.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – DR 4339 A meeting was held with Jose Ralat (DCMC) and Carlos Palomares (CDM) to discuss the reconciliation needs for the Working Capital Advance, Genera's procurement process, and the payment breakdown agreements for the federal projects BESS and Peakers. The discussion covered key aspects related to demolition, construction, and installation budget for works associated with these projects.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 164 | 328 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 Internal mandatory meeting between all DCMC employees working under Genera PMO contract. This introductory meeting served to familiarize all team members with one another, review individual responsibilities, clarify the scope of services assigned to each team member, and identify the specific power plant each person will support. The meeting also covered key construction schedule dates, safety protocols, general site management logistics, stakeholder and subcontractor responsibilities, and administrative requirements. Participants: All DCMC PMO Genera team members, including Gilberto Sucre, Abraham Velazquez, Jean Pierre, Frances Vallejo, and others.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 Internal Meeting work session with Raissa Borges (DCMC) to discussed invoice pre-intervention workflow for Por-Core Integration. Going over contract management, flowcharts, communication protocols to be aligned with new pro-core functionalities and implementation.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, MegaPacks and tariffs for all plants. Meeting participants TESLA (Michael Grabstein, Elizabeth Arentsen, Allin Luong), CSA (Franklyn Colmenares), and DCMC (Rafael Calderon)
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reviewing RG Engineering_109403 contract (876 pages long) Article 13-30 and start preparing RFI for RGE. working session review the contract terms that affects the invoice. review the invoice and identify missing information and clarification; also, prepare a schedule of value based on the contract for this vendor in preparation for RGE Kick-Off Meeting.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC- Weekly Status Pre-Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander Gonzalez, Esther Rohena, Marc Maceira - Honra, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz, Christian Cruz, Carlos Gonzalez - Integrum) and SMC Shellsea Maysonet)
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GD016 to GD024
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GD016 to GD024
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GD016 to GD024
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GD016 to GD024
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GD016 to GD024
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 01 008 000 to AB 01 021 000
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 152 | 494 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 01 008 000 to AB 01 021 000
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 01 008 000 to AB 01 021 000
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 152 | 38 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations UH 001 TO UH 011 at the Aguirre warehouse to start the cycle counts.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AF 084 TO AF 144 RECOUNT LIST # 949/950
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. AG 001 TI AG 040 COUNT LIST # 959/960/965/966/968/969
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location UH 001 TO UH 011
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CL001 to CL032.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CL001 to CL032 to begin the cycle counts.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 152 | 190 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 972 locations CL001 to CL032.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CL001 to CL032 Cycle Count List # 970.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #972 from locations CL001 to CL032 for a total of 141 equipment.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Hurricane Maria Performed troubleshooting and functional validation of drawing number editing features using a test project environment to support the resolution of unpublished drawings associated with the Cambalache Project. Activities included reviewing system behavior, verifying drawing file updates, and assessing the impact of drawing number modifications on document control processes. Coordination with the Design Team was conducted to evaluate potential document control implications when revising drawing files, ensuring consistency, traceability, and alignment with established project documentation standards.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 151 | 453 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/ Coordination Jobos_Daguao_Yabucoa Peakers Projects with Vernadee Ortiz (RG) for all future incoming documents after Project Kick off Mtg Next Week/Incorporate access to QAQC & HSSE project folders_all projects for Clara Padovani (GENERA)/Costa Sur Peakers Check-In Trackers Reports Review & Process/ Vega Baja BESS Permitting & Environmental Data Review & Process/Yabucoa Permitting & Environmental Data Review for Processing
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue with the drawing plans review for the Cambalache project to determine potential drawing areas to be established on the Drawings tool to separate drawings with publishing issues.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform QA/QC for Procore SOPs following internal distribution and commentaries/corrections. Also, continue the preparation of SOPs for the Punchlist, Action Plan and Forms Tools.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Discussion Meeting with Franklyn Colmenares (CSA), Lauren Wells (Lemoine), Rafael Pabon (CDM Smith) and Ivette Miranda (Sargent & Lundy) to discuss the weekly progress on the Procore Platform. Talked about Procore Financials Tool update, Project Management SOPs, upcoming new project's team and implementation of Procore with contractors.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform review on contractual documents for the Cambalache project to identify potential project stages for the RFI management between change of contractors (change in project phases).
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 149 | 298 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339: Internal DCMC kickoff meeting at City View office was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay, Carolyn Baez-Nieves, Glorimel Torrado, and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peakers within the energy infrastructure, emphasizing the importance of ensuring that Peakers are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, CDM Constructors, CPM, B&V, Siemens Energy, Tesla, EHSS and CAPTA. Also prepare Power Point presentation for internal meeting and Genera meeting. During this time I review and compare the progress between last week and this week to present deltas on the report. Also corroborate any discrepancy on the final presentation numbers. Adittional, we add DCMC invoices update for this presentation.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 139 | 312.75 | 139 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of peakers within the energy infrastructure, emphasizing the importance of ensuring that peakers are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Internal DCMC Kick off meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay, Carolyn Baez-Nieves, Glorimel Torrado, and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 139 | 417 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Work on the final round of edits to the Cambalache Fact Sheet focused primarily on refining the written content and enhancing the overall visual presentation of the document. Textual changes included adjustments to tone, clarity, and consistency to ensure the messaging aligned with Cambalache's project. As part of this process, we held a meeting call with Jorge Bracero, from Genera PR
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Write an email addressed to the Genera PR team, Jorge Bracero and Ivan Baez with suggestions to effectively manage the increase in operating hours or activity in Cambalache due to the fact that as of July there will be an increase in the hours of activity in Cambalache. This change directly affects the nearby community, so it is important to propose actions that allow possible concerns to be addressed.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Modify colors, typographies and graphic elements to maintain coherence with the visual identity of the brand (logo, institutional palette, etc.). Insert high-quality images related to the BESS project in Puerto Rico.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 |  | 139 | 34.75 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Update the internal Community Outreach plan with the new efforts that will be worked on in the coming week.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Coordinate with the Genera Corporate Affairs team to obtain permission and a formal release to use the Genera logo in connection with the BESS and Peakers project. This will ensure proper authorization and compliance with brand guidelines. The release will define the approved usage, duration, and distribution channels.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.75 |  | 134 | 234.5 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review BESS Issued for Construction plans, mechanical General info plans for 4339_9510 BESS_Cambalache project to ensure they provide detailed insights into the design, layout, and specifications of each system.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on project PROCORE settings preparatory including schedule and meetings for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 134 | 301.5 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean Pierre Menay, Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 134 | 167.5 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur-worked on project PROCORE settings preparatory including correspondence and photos for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 134 | 67 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on project PROCORE settings preparatory including correspondence for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 134 | 201 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continuing reviewing project documentation, Base Schedule rev1. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Begin reviewing project documentation, Base Schedule rev1. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 134 | 469 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continuing reviewing project documentation, RFP 229760 Battery Storage System. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review BESS Issued for Construction plans, mechanical P & ID Plans for 4339_9510 BESS_Cambalache project to mitigate risks and improve quality and cost efficiency of the project.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 134 | 301.5 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Internal DCMC Kick off meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay, Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue with the Genera projects financial and contract processes workflow development in Visio app for the integration of the financial tool on Procore.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 |  | 122 | 91.5 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Genera projects financial and contract processes workflow development for Procore Integration.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 122 | 244 | 122 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: Internal DCMC Kick off meeting held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 122 | 91.5 | 122 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 Internal Meeting work session with Cynthia Ortiz (DCMC) to discussed Procurement (Power Advocate) workflow for Procore Integration. Going over contract management, flowcharts, communication protocols to be aligned with new Procore functionalities and implementation.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 Internal Meeting work session with Rafael Calderon (DCMC) to discussed invoice pre-intervention workflow for Procore Integration. Going over contract management, flowcharts, communication protocols to be aligned with new Procore functionalities and implementation.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 30 | 30 | 30 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits and travel from city view offices to facilities
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Echevarría Tirado, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 15.4 | 15.4 | 15.4 | Yes | 146793 |  | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Tolls for travel from Home (18.0101039, -66.8010416) to City View Plaza in Guaynabo for in person staff meeting. A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Rodriguez Bury, Carlos | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 12.6 | 12.6 | 12.6 | Yes | 146793 |  | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Tolls for travel from Home (18.0101039, -66.8010416) to City View Plaza in Guaynabo for in person staff meeting. A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 116.2 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. Focus was on integrating and operationalizing energy systems.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Echevarría Tirado, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 121.8 | 0.7 | Yes | 146793 |  | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home (18.0101039, -66.8010416) to City View Plaza in Guaynabo for in person staff meeting. A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Rodriguez Bury, Carlos | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 92.4 | 0.7 | Yes | 146793 |  | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home (18.0101039, -66.8010416) to City View Plaza in Guaynabo for in person staff meeting. A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 25.76 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Return trip from City View Plaza to Yabucoa Gas Turbine. Purpose - A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The trip from Yabucoa Gas Turbine to City View Plaza was billed under entry #6357339.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 25.9 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Yabucoa Gas Turbine to City View Plaza to Yabucoa Gas Turbine. Purpose - A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 115.92 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 46.83 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from CVP to Yabucoa Gas Turbine (18.106216, -65.823685) to Home Office Luquillo. Purpose, walk through Project Site and Trailer Office Area, discuss clearing and grubbing scope of work. Measured areas. Attendees – Carlos Villamil (Villamil Group) & Harry Del Valle (DCMC). TOTAL MILEAGE – 66.9 miles
2025-06-06 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes | 146793 |  | ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site and evaluate riggings plan for diesel tanks and communication pole. .
2025-06-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site and supervise riggings task for diesel tanks and communication pole to ensure the lift is executed with minimal risk to both personnel and equipment.
2025-06-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Continuing Inspection in Vega Baja Site and supervise riggings task for diesel tanks and communication pole to minimize accidents, manage project progress, and maintain quality and safety.
2025-06-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Safety briefing conducted by Homeca and Jean P. Menay was present. Had Meeting with Emmanuel Santos (HOMECA Recyclers) to discuss the daily work schedule & activities to make sure we stress on safety today using the crane.
2025-06-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria - Vega Baja BESS Supervising work from contractor Homeca Recycling. Contractor keeps dismantling. Supervising decommissioning and demolition work and planning for phase II to ensure environmental protection, regulatory compliance, and worker safety.
2025-06-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site and supervise riggings task for diesel tanks and communication pole.
2025-06-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Contine Site Inspection in Vega Baja Site Genera and supervise remove the diesel tanks and communication pole.
2025-06-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site Inspection in Vega Baja Site Genera and supervise remove the diesel tanks and communication pole to help minimize construction accidents, manage project progress and ensure safe fuel handling.
2025-06-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 |  | 167 | 626.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working in coordination with Homeca and safety orientation of work activity for today that will demolish the existing guard house and rigging of small diesel tank SLOP-1. The contractor Homeca start in the morning with the demolition of the guard house.
2025-06-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 |  | 167 | 459.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continues with the demolition of the guard house and start preparation for the rigging of the tank SLOP-1. They start rigging at 10:45pm and tank was installed at the truck platform. Homeca after install tank at platform at 11:25 am they decided without notifying our safety or me that will cut the top nozzle of tank vent with gas and oxygen this create an incident that smoke was observe at nozzle immediately Homeca mitigate the situation and was controlled without mayor incident. Incident report was created in Procore by Jean Menay (DCMC)
2025-06-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site. Remove Diesel Tank and Communication Pole.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | PREPA, Genera, Deliverable 11 DR 4339. DCMC TEAMS meeting with Mark Merritt, Gilberto Sucre, and Frances Vallejo to discuss PMO tracker, status of warehouse sites schedule and number of staff per site.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Reviewed recent submittals and comments from reviewers of the specifications. Submittals reviews are important to ensure that all materials, equipment, and other products used in the project meet the requirements and standards to prevent errors, protect project integrity, and enhance communication across project teams.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Work on internal files and reports, reviewing calendar events including upcoming tasks crucial in construction project management which helps manage time and avoid missing deadlines or events.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Introduction meeting and project updates for Carlos Bayron and Carlos Lopez - DCMC Employees.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Projects Needs Meeting with Jesus Cintron Genera. Rafael Pabon CDM Smith presented Peaker's needs and Gabriel Perez -CDM Smith presented BESS Needs.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS CM/PM Weekly Update meeting with Gabriel Perez - CDM Smith, Franklyn Colmenares CSA Group, Carlos Palomares & Enrique Laya - CDM Smith and Gilberto Sucre DCMC.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check-in Weekly Update across all sites on Program to verify progress on projects, improve performance levels and alignment of goals.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Staffing Tracker Discussion with Mark Merritt, Frances Vallejo, Anneilia Holton & Gilberto Sucre.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Installation Phase - review and discussed DOR Scope of Work alignment with Final Contractual Agreement with Gabriel Perez - CDM Smith and Wilfredo Sierra - Sargent & Lundy to be revised accordingly.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja progress update discussion with Eduardo Rivera - DCMC & Cambalache Pre-Mobilization update with Andres Concepcion.- DCMC
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed IFC's drawings issued for Vega Baja & Cambalache. Requested to Andres Concepcion and Eduardo Rivera - DCMC to issue their team comments to Sargent & Lundy during the week.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Ricardo Pallens (Genera), Carlos Palomares (CDM Smith), Joaquin Quinoy (Genera), Gabriel Perez (CDM Smith), Mike Kuczynski, Nelson Rosado (Sargent and Lundy), Franklyn Colmenares (CDM Smith), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Follow up meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of meetings this week for Procore items.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore users for distribution list and new project setup.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) work on Procore financials tool with working on budget imports and contracts for 11855.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOPs for publishing.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore workflows to review changes to the pre-intervention workflow.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore SOPs.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.25 |  | 184 | 230 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Completed the onboarding of Genera HQ employees to the Genera Connect Timesheets platform, providing them with access credentials and instructions on how to access the application for submitting time entries. This marks a key milestone in the rollout of the platform, supporting improved time reporting and operational tracking.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Offices Trailers installation and site inspection with Clara Padovani (GENERA).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Working session with Duenas Trailers employee, Luis Davila Rodriguez, Joshua Cruz Feliciano and Angel Rivera for Genera EHS topics to mounting offices trailers Aguirre. Conference call with Osvaldo de Jesus (Genera) about Genera project and manuals.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Supervise Offices Trailers installation in Aguirre Site to manage project progress. Meeting with Clara Padovani, Osvaldo de Jesus, Irving Vega (GENERA) about EHS, Emergency Managment topics for the project.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 184 | 138 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Participated in the Cambalache weekly update meeting with the site manager. Discussed project status and next steps. Participants: Gilberto Sucre, Jose Lopez, Luis Damudt (DCMC)
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meet with Carolyn Baez (DCMC) to discuss equipment and materials needed and coordination.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 184 | 230 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review resumes for candidates for Yabucoa site positions (safety officer, inspector QA/QC, project controls).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with DCMC new hires for Costa Sur and Aguirre sites (Inspector QA/QC and construction manager). Participants: Gilberto Sucre (DCMC) to discuss project in all sites.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in BESS Check In call with BESS project management team. Topics: Discuss status of the project per site, contract status, RFP process, community engagement meetings. Participants: Gabriel Perez (CDM), Franklyn Colmenares (CSA), Sheila Torres, Paola Arroyo, Gilberto Sucre, Rafael Calderon, Raissa Borges, Luis Roman (DCMC)
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Mark Merritt, Anneilia Holton and Gilberto Sucre (DCMC), to discuss staffing tracker and budget for the PMO.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Marc Maceira, Carlos González and Ginnell Torres
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4759 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Hurricane Maria - Verifying current project progress, ongoing procurement efforts, and challenges impacting project schedules or deliverables to prepare for the weekly BESS and Peakers Project Needs meeting
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.75 |  | 184 | 322 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated the Genera Connect Financial Tracker with the latest data in preparation for the weekly Genera PR project status meeting to ensure accurate reporting of financial metrics. Additionally, revised the Power Production and Fuels Consumption master report for May 2025, addressing an observation raised by José del Río from Genera PR, and submitted the finalized report to Jan Rodríguez for further review and distribution.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in the weekly Genera PR meeting to provide updates and discuss roadblocks related to ongoing projects. Attendees included Maria Sanchez and Alejandro Maymi from Genera PR; Mark Merritt, D'Alexzander Gonzalez, Esther Rohena, Glorimel Torrado, José Ralat, Paul Browne, Pedro Cabrera, Rafael Calderon, Roberto Bosch, Saul Falcon, Sheila Torres, Ginell Torres, and Victor Maldonado from DCMC; and Jorge Aponte and Keyla Sierra from Integrum.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while demolishing the Deisel container located in Vega Baja site. Disposed by 80CY bin towards Homeca recycling facility metal scraps from diesel tank. Uploaded photos and notes to pro core app.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the RFP-4899 Proposal Civil & Structure Works for 30 MW Battery Energy Storage System at Costa Sur.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Hurricane Maria – Costa Sur Completed Procore platform proficiency activities required to satisfy role-based qualification criteria for the Site Manager position at the Costa Sur project. The work focused on submittal management best practices, including proper workflows, identification of responsibility status (e.g., “ball in court”), and avoidance of common compliance errors. Reviewed and applied available Procore tools to support future project controls, document tracking, and implementation of standardized processes, ensuring consistency with project management requirements and documentation oversight standards.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued Revision of Request for proposal drawing towards understanding details of location and specs of Tesla Batteries.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Aguirre Continue with the Set-up of the new mobile office (Dual Trailer) of the Aguirre site from Duenas Trailers to provide a centralized hub for operations.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Aguirre Received the new mobile office (dual trailer) for the Aguirre site from Duenas Trailers. Setup location instructions were discussed by Gabriel Morales, Jose Lopez, Harry del Valle and Jean Pierre Menay (DCMC) with the Duenas Trailers team.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Aguirre Site Discussion and review with Jose Lopez, Harry del Valle and Jean Pierre Menay (DCMC) regarding the plan to relocate and energize the new DCMC mobile office at the Aguirre site.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Yabucoa Site visit to inspect the work performed by the landscaping company Villamil Group Inc. in the area were the DCMC Partners mobile office will be installed. Also, since the area was cleaned, a more detailed evaluation was performed to energize and connect to the water system to the office.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- A site visit and inspection Costa Sur were conducted to assess the current status and conditions of the project area. Verify that the work aligns with the approved construction drawings, technical specifications, and overall project requirements. Reviewed the layout of the site against the architectural and engineering plans. Key elements such as dimensions, materials, and structural components were inspected to ensure compliance with design intent and applicable standards. The inspection also involved a detailed review of the project specifications to confirm that construction practices, equipment, and materials to used on-site. Also, project schedule reviewed in coordination with the site team. Progress was compared with the baseline timeline to identify any deviations or potential delays. Recommendations were made to address critical path items and improve scheduling efficiency where necessary. Overall, the site visit provided valuable insight into the progress and quality of the project, allowing for proactive adjustments and continued alignment with project objectives.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Continue with Costa Sur inspection site was conducted to assess the current status and conditions of the project area. Verify that the work aligns with the approved construction drawings, technical specifications, and overall project requirements. Also reviewed the layout of the site against the architectural and engineering plans. Key elements such as dimensions, materials, and structural components were inspected to ensure compliance with design intent and applicable standards
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We continue to provide assistance at the DCMC office trailer facilities in Aguirre Bess while they carry out exterior and interior work, supervising that the contractor complies with our company's safety standards and policies
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Support in the delivery and trailer installation for the Aguirre Site Project Bess with Jean Pierre Menay (DCMC), Jose Lopez (DCMC) and other workers at (DCMC)
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS - Mobilization works planning and logistics for the DCMC Management Offices Trailer installation. The DCMC staff, comprising Harry del Valle, Jean Pier Menay, and Luis Monteczuma, and in coordination with Genera's Disaster Specialist, Clara M. Padovani, joined forces to coordinate the installation location of the office trailers assigned to the BESS Management Project Site.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS - Weekly look-ahead schedule review and discussion with the DCMC team, Gilberto Soto, Jaime Pesquera, Eduardo Rivera, and Gilberto Sucre: Coordination and overview for Homeca's week work plan.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Central Aguirre Office Trailer Power Installation. Attendees, Roberto Camacho (Genera), Genera Electrician & Harry Del Valle (DCMC). Topics discussed, Office trailer Power Installation, location to connect the Office trailer. Continue the installation of the office trailer by Duenas Trailer employees.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting & Coordination for Yabucoa Gas Turbine Plant. Attendees, Carlos Villamil (Villamil Group) & Harry Del Valle (DCMC). Topics discussed, Review works and took pictures of clearing and grubbing scope of work.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Central Aguirre Office Trailer Installation. Attendees, Alexis Cruz (Genera), Francisco Mari (Genera), Juan M Lopez (DCMC), Gabriel Morales (DCMC), Jean Pierre Menay (DCMC), (DCMC) & Harry Del Valle (DCMC). Topics discussed, walk through Office Trailer Area, discussed Office trailer Installation by Duenas Trailer, Final Location of Existing Generator to be relocated, discussed Office trailer utility's needs. Introduce to Genera the DCMC BESS Project Management team. Supervise the installation of the office trailer.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Verifying the client's documentation regarding construction permits which is critical for compliance with local building codes and regulations. The general permit for daily work is evaluated.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Worked verifying the client's construction permit documentation. The permit and the hazardous energy control procedure are also evaluated.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Reviewed and verified documentation related to construction permits submitted by the client, ensuring compliance with regulatory and project-specific requirements. Conducted a detailed evaluation of the contractor’s cutting and welding permit, focusing on the implementation of safety procedures. Identified potential hazards associated with work and assessed mitigation measures in place. Recommendations were developed to align contractor practices with site safety protocols and ensure adherence to risk management standards.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - - Reviewed project submittal information(Submittal #RGE-0003 Revision 1: NEW PIPING ROUTE AND SUPPORTS DETAILS AT NEW PARKING AREA) received by (Jose Segarra - RG Engineering) in Procore.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Procore platform to confirm new received submittals from RG Engineering (Jose Segarra). Coordinated with Luis Duque (DCMC) to assign tasks to staff responsible of approval (Sargent and Lundy team).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with DCMC Luis Roman and Luis Duque. Sargent and Lundy Ivette Miranda to discuss Procore Drawings tool and pending drawings to be published on the platform to be available to the team.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed and provided comments to the Issued for Construction Drawing set (Issued for Construction 6.3.2025) provided by project designer (Sargent and Lundy) in order to capture potential errors to avoid delays and safety concerns.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued Review and provided comments to the Issued for Construction Drawing set provided by project designer (Sargent and Lundy) in order to capture potential errors that can lead to rework, additional materials, or safety issues.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with construction management support for Vega Baja BESS project, contractor Homeca provide safety modules for personnel previous to start work, they continue with the demolition of Guard House and rigging of Diesel tank SLOP-2, They also start demolition of the (2) tank concrete pedestal.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue working with demolition at concrete pedestal of tanks. The continue removing debrief from guard house and from antenna foundation. Homeca has brought to project a stone cruncher for concrete debriefs of project. Send email to Franklyn Colmenares of CSA Groups to verify if Genera has established communication related to the existing transformer relocation to Luma facilities.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Had conversation by phone with Cesar Sánchez of Luma PR at 10:35am to discuss the removal of the cable interconnection of the 38kV line connected to Genera existing transformer. Discuss with DCMC Jaime Pesquera to publish the punch list for the project and discussed with Carirma Sanchez of Homeca and Nelson Soler of CDM Smith in a daily basis.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the San Juan warehouse, comprehensive inventory performance evaluation was conducted. A consolidated report was developed for Mr. Anthony Vega of Genera PR, integrating system wide inventory data from all audited warehouse locations. The assessment included analysis of catalog identifiers, stock balance validation, cost distribution metrics, and variance detection. Additionally, compliance was measured against predefined thresholds for acceptable inventory levels. Key performance indicators were quantified using percentage-based metrics to assess inventory accuracy, procedural adherence, and consistency across operational standards. The reviewed focused on inventory zones ranging from AM 013 to AM 030, AG 001 to AG 040, CL 035 to CL 044, BD 001 to BD 007, BE 001 to BE 008.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria- participated in a virtual coordination meeting via Microsoft Teams with Ms. Maria Sanchez from Genera PR, and DCMC personnel to assess the current status of key operational projects. The discussion emphasized adherence to project schedules, evaluation of task completion timelines, and identification of any delays.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory recount at the San Juan warehouse in coordination with Mr. Milton Flores from DCMC. The objective was to verify data integrity and validate the accuracy of previous cycle count outcomes. Activities included cross referencing physical inventory against Asset Suite system records. The review focused on inventory locations AM 013 to AM 030 with emphasis on ensuring compliance with internal controls standards and audit preparedness requirements.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a targeted inventory integrity audit focused on identifying and analyzing variances between physical stock counts and system reported inventory data within locations AM 013 through AM 030. The assessment included root cause analysis of discrepancies, lifecycle tracking, and a detailed review of inventory movement transactions. Additional activities involved validating system generated balances in Asset Suite against actual on hand quantities, identifying data input inconsistencies, and confirming the accuracy of historical adjustments.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed focused cycle count operations within designated inventory sectors, specifically targeting locations AM 013 through AM 030. The scope of work involved validating on hand inventory levels, reconciling items counts with system reported data, and documenting any variances requiring corrective measure. Discrepancy findings were analyzed and logged to support traceability, enhance procedural compliance, and drive continuos improvement in inventory accuracy. All actions taken contribute directly to reinforcing inventory reliability and data integrity across the audited zone.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-collaborated on-site with Mr. Milton Flores from DCMC to initiate preparatory phase for the upcoming inventory cycle count. The session focused on verifying inventory master data integrity, confirming bin assignments, and organizing stock to support accurate physical validation. Additionally, efforts were directed toward optimizing documentation workflows, aligning data capture procedures with audit standards, and ensuring full synchronization between physical inventory and system records. Today's assessment concentrated on inventory segments ranging from AM 013 to AM 030.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-initiated and early coordination meeting with Milton Flores, Hernan Machado and DCMC warehouse personnel to reinforce the importance of punctuality and compliance with established work schedule, especially during active inventory reconciliations periods. Emphasis was placed on the critical nature of our role in identifying, documenting, and resolving variances within the warehouse inventory. The session focused on aligning personnel responsibilities with operational timelines to ensure timely execution of audit tasks, accurate system entries, and traceability of all inventory movements.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Working on modification to Independent Cost Estimate for One New Set of Open and Close Hardware for Palo Seco Power Plant Units 3 & 4 after Saul Falcon DCMC review.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continued working modifying the Independent Cost Estimate for One New Set of Open and Close Hardware for Palo Seco Power Plant Units 3 & 4 after Joaquin Quinoy GENERA-PR review.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Alejandro Maymi, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue made modification to Independent Cost Estimate for One New Set of Open and Close Hardware for Palo Seco Power Plant Units 3 & 4 under D'Alexzander González (DCMC)
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings document discipline: Architectural warehouse,
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings document discipline: Civil.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings document discipline: (Continue) Civil Drawings for comment and note for possible draw issue or missing information..
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the last Preliminary Drawings document discipline: Architectural for comment and note for possible draw issue or missing information.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform. RFi #48,
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Safety briefing conducted by Homeca Recyclers and Gilberto Soto was present. Had Meeting with Carirma Sanchez (HOMECA) to discuss the weekly work schedule and the daily punch list from the missing or delayed items.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Had a walk-through meeting with Eduardo Rivera Jordan (DCMC Site Manager) & later with Nelson Soler (DCMSmith) to discuss the daily punch list items and the safety items we found on the site. We will be doing this walk-through inspection with Homeca Recyclers daily if possible to make sure they know the items we need to complete.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while demolishing the Deisel container located in Vega Baja site. Disposed by 80CY bin towards Homeca recycling facility metal scraps from diesel tank. Uploaded photos and notes to pro core app. remove diesel container to transport towards Homeca recycling Facility. dropped 35ft concrete post for disposal.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 |  | 164 | 410 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#2_Invoice# PRIN0008442_Feb 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA / BESS Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team, CDM Smith PM team (Gabriel Sepulveda), Sargent & Lundy ( (Mike Kuczynski) Miguel Del Valle, Nelson Rosado), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Gilberto Sucre, Foster Veazey, Paola Arroyo, Raissa Borges, Luis Roman, Frances Vallejo), Lemoine Procore (Lauren Wells).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review. Siemens Chek-In Meeting: Peakers Costa Sur project Status follow-up and review of contract schedules. Participants from Genera (Jesus Cintron, German Nunez), CSA (Franklyn Colmenares) CDM PM (Carlos Palomares), Sargent and Lundy - (Mike Kuczynski) and DCMC Contract Manager - (Rafael Calderon, Abraham Velazquez, D'Alexander González and Sheila Torres).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Continue working with Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#2_Invoice# PRIN0008442_Feb 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC & Genera- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander Gonzalez, Esther Rohena, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz,, Carlos Gonzalez Integrum) and SMC Shellsea Maysonet; from Genera (Alejandro Maymi and Maria Sanchez)
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CL035 to CL044 Cycle Count List # 976, 979 and 988.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AM013 to AM030
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AM013 to AM030
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AM013 to AM030
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AM013 to AM030
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AM013 to AM030
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 152 | 494 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BD 00 001 to BD 00 007 and BE 00 001 to BE 00 008
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BD 00 001 to BD 00 007 and BE 00 001 to BE 00 008
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BD 00 001 to BD 00 007 and BE 00 001 to BE 00 008
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 152 | 38 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. UH 001 TO UH 011 COUNT LIST # 899/898
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AG 001 TO AG 040 RECOUNT LIST # 967/971
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AG 001 TO AG 040 at the Aguirre warehouse to start the cycle counts.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AG 001 TO AG 040
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #982, 983, 984 and 985 from locations CL035 to CL044 for a total of 71 equipment.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CL035 to CL044 to begin the cycle counts.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CL035 to CL044.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 982, 983, 984 and 985 locations CL035 to CL044.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Call with Ivette Miranda from Sargent & Lundy, to discuss the strategies being taken into considerations for the uploading the Issued for Construction Drawing Plans for Cambalache, looking to avoide drawings to remain unpublished.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/Gen 01 Download All Projects Documents to be Reviewed & Processed in Specific Project Folders/ GENERA Incorporate New User for Procore
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/ Vega Baja BESS Coordinate Refresh of User Profile -Access to CDM
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Peakers Weekly Meeting hosted by Franklyn Colmenares (CSA) including Design Team staff Ivette Miranda (S&L), Rafael Calderon, DCMC), Rafael Pabon (CDM Smith), German Nunez (Genera); discussing weekly open topics for the Peakers Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – BESS Weekly Meeting hosted by Gabriel Perez (CDM Smith) including Design Team staff Ivette Miranda (S&L), Gilberto Sucre, Rafael Calderon (DCMC), and Franklyn Colmenares (CSA) discussing weekly open topics for the BESS Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the final commentaries on Submittals and RFI SOPs to send them out for publishing.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Companies list for creation of new companies inside projects about to kick-off (Aguirre).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Andres Concepcion and Luis Duque (DCMC), and Ivette Miranda and Monica Ybarra from Sargent & Lundy to discuss the uploading of the Issued for Construction Drawing Plans for Cambalache.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Verify Observations features at the Vega Baja project for the QA/QC of project directory and permissions for users not found on the Assignee dropdown (contractor's personnel).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Hurricane Maria Performed Procore system testing within a controlled project environment to simulate the upload of construction drawing plans. Verified the functionality of the auto-labeling feature and manually adjusted formatting for multiple drawing sheets to confirm proper document organization, version control, and consistency. Activities supported document management controls, system configuration validation, and readiness for implementation on active project files.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Hurricane Maria Conducted Procore system validation activities within a controlled project environment to simulate the upload and management of construction drawing plans. Reviewed the performance of the auto-labeling functionality and performed manual formatting adjustments across multiple drawing sheets to verify document organization, version control, and consistency. These efforts supported document management controls, configuration verification, and operational readiness for implementation on active project files.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Hurricane Maria Performed implementation testing of the Procore Punch List tool within a controlled project environment to validate workflow functionality. Reviewed the process for tracking punch list items through completion, including Final Approver review and closeout actions. Verified reassignment controls by returning items to the responsible assignee when corrective work was incomplete. Activities supported project controls, accountability tracking, and readiness for use on active project sites.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Call with Nelson Soler (CDM Smith) to discuss ongoing project management issues and doubts about different Procore processes.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 ¦Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Eisha Mercader, Esther Rohena, Glorimel Torrado and Honra LLC Marc Maceira. Also, Shellsea Maysonet (SM Consulting); and from Genera: María Sánchez, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 149 | 111.75 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - RGE pre Kick Off Meeting with Rafael Calderón (DCMC), Rafael Pabón (CDM), Francisco Feliú (Genera) and Glorimel Torrado (DCMC). In this meeting we clarify some important aspects of RGE contract, deliverables and milestiones previous to the formal Kick off meeting on wednesday.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 149 | 447 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reading RGE contract and identifying important information in preparation for today's meeting and Wednesday Kick Off meeting. RGE Contract has 876 pages and is important to understand key information regarding invoices and supporting documentation. I continue including keypoints on shared word document with Rafael Calderón (DCMC) and making some notes that needs clarification for meeting.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 149 | 149 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reading RGE contract and identifying important information in preparation for today's meeting and Wednesday Kick Off meeting. RGE Contract has 876 pages and is important to understand key information regarding invoices and supporting documentation. I was including keypoints on shared word document with Rafael Calderón (DCMC).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. New invoice was signed from CDM and updated information on tracker.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 149 | 149 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Reading RGE contract and identifying important information in preparation for today's meeting and Wednesday Kick Off meeting. RGE Contract has 876 pages and is important to understand key information regarding invoices and supporting documentation.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Send the official invitation for the upcoming community meeting to the administrative officials of the Municipality of Vega Baja. This process included drafting and designing the message copy to ensure clear, cordial, and goal-aligned communication.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Coordinated an in-person mockup meeting in Vega Baja to review and align visual and conceptual materials for the upcoming community event. This session ensured all resources were properly adjusted and ready for final use.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Meeting with Genera PR Team, Jose del Rio and Jorge Bracero to review key fuel data for upcoming presentations and analysis sheets. Additionally, validate technical information related to generation operations. These discussions ensured accurate and aligned data for future reporting.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria meeting via Microsoft Teams Meeting with DCMC Team: Frances Vallejo Rosich, D'Alexzander Gonzalez and Mark Merritt. In the meeting was the Genera Team: Jesus Cintron, Kevin Futch, Francisco Santos, German Nunez, Alejandro Maymi and Sarahi Medina Nieves. In the meeting was the CDM Smith: Juan Mendoza, Rafael Pabon and Carlos Palomares. The meeting was about Peakers Check In.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Review and edit Fact Sheet for the BESS project in Arecibo to ensure clarity, consistency, and alignment with current project status. Task include summarizing information, correcting and formatting. Ensuring narrative reflect current progress and objectives.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Weekly Corporate Affairs Meeting with the Genera PR: Jorge Bracero, Ivan Baez Santiago and Rafael Baez Santiago for maintaining clear communication, aligning expectations, and ensure project success.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Send the official invitation for the upcoming community meeting to the community leaders of Vega Baja. This process included drafting and designing the message copy to ensure clear, cordial, and goal-aligned communication.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339-meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Raissa Borges, from DCMC, and Lauren Wells, Foster Veazey from Lemoine. In the meeting was the Genera PR Team: Jesus Cintron, Joaquin A Quinoy, Ricardo Pallens, Maria Sanchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczynski and Nelson Rosado. The meeting was about the Bess Project.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Continue review BESS Issued for Construction plans, Civil (cab-cy-000) for 4339_9510 BESS_Cambalache project.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Genera Safety working session with Jean Menay (DCMC) essential for preventing accidents and injuries on job site. Learn to identify and assess hazards, use protective equipment, and respond to emergency situations to prevent liabilities, and ensure project success.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Meeting with Gilberto Sucre DCMC and Frances Vallejo DCMC about the projects overview.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on comments on issued for construction drawing considering mechanical works report for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on comments on issued for construction drawing report for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Complete reviewing project documentation, Base Schedule rev1. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continuing reviewing project documentation, Base Schedule rev1. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review BESS Issued for Construction plans, mechanical UG FP Isometrics for 4339_9510 BESS_Cambalache project to ensure they offer a detailed and accurate representation of the project.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Rafel Pabon (CDM Smith), Luis Roman (DCMC), Paola Arroyo (Genera), Jorge Bracero (Genera), Lauren Wells (Lemoine), Foster Veazey (Lemoine), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Franklyn Colmenares (CDM Smith), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Sheila Torres (DCMC).
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Proceed with the financial and contract process flowchart for Genera projects, focusing on CPA and Routing List development to integrate the financial tool within Procore.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 Internal Meeting work session with Esther Rohena (DCMC) and Johanna Diaz (SMC) to discussed Grants workflow for Procore Integration. Going over contract management, invoices, communication protocols to be aligned with new Procore functionalities and implementation.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees:Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Sheila Torres (DCMC), Paola Arroyo (DCMC), Lauren Wells, (Lemoine)
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 122 | 183 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Work on refining the financial process flowchart for Genera projects, with an emphasis on invoices and Pre-intervention to support seamless integration of the financial tool in Procore.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 64.47 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from home offices San Juan to Aguirre Site (17.951690, -66.229675) to Home Offices San Juan. Site Inspection in Aguirre Site. Metting with Ramon Quinonez, Clara Padovani Irving Vega and Osvaldo de Jesus (GENERA). Trailer Offices installers in site.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 37.94 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Return trip from Aguirre Power Plant to Yabucoa Gas Turbine. Purpose - Relocation of the DCMC Partners Mobile Office to the Aguirre Site.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 38.43 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Yabucoa Gas Turbine to Aguirre Power Plant to Yabucoa Gas Turbine. Purpose - Relocation of the DCMC Partners Mobile Office to the Aguirre Site.
2025-06-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 112.7 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Central Aguirre (17.951690, -66.229675) to Yabucoa Gas Turbine (18.106216, -65.823685) to Home Office Luquillo. Purpose, Meeting & Coordination for Central Aguirre Office Trailer Installation. Topics discussed, walk through Office Trailer Area, discussed Office trailer Installation by Duenas Trailer, Final Location of Existing Generator to be relocated, discussed Office trailer utility's needs. Introduce to Genera the DCMC BESS Project Management team. Supervise the installation of the office trailer. Yabucoa - Meeting & Coordination for Yabucoa Gas Turbine Plant. Topics discussed, Review works and took pictures of clearing and grubbing scope of work. Attendees – Alexis Cruz (Genera), Francisco Mari (Genera), Juan M Lopez (DCMC), Gabriel Morales (DCMC), Jean Pierre Menay (DCMC), (DCMC) & Harry Del Valle (DCMC). Yabucoa - Carlos Villamil (Villamil Group) & Harry Del Valle (DCMC). TOTAL MILEAGE – 161 miles
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore drawings tool to ensure users can publish.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Worked on site plans, construction access plans and reviewed scopes of work for leveling purposes.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Participated in a review meeting to discuss deliverables and schedules updates for the Peaker projects. German Nunez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catchup meeting - focused on critical staffing updates, with several team members discussed for upcoming positions, including temporary placements and interview schedules for construction and site managers. Key updates included the installation of trailers at Costa Sur/Aguirre, with the Yabucoa trailer project set to tomorrow. The RFP discussions highlighted adjustments to the project approach, pricing reviews, and organizational charts to clearly differentiate Best from Peakers. A key priority was on resume inclusion for essential site and construction managers. Further, the team addressed logistics related to inventory systems and equipment tracking, leading to action items assigned to various members for follow-up on hiring, RFP updates, and equipment procurement. DCMC Frances Vallejo, Michael Merritt, Mark Merritt, Ada Diaz, & Gilberto Sucre and Lemoine Foster Veazey
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Mark Merritt - DCMC to provide BESS & Peakers Staffing Project durations for overall PM Project Budget Update.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One on One meeting with Mike Kuczynski of Sargent and Lundy to provide him feedback from Genera and CDM Smith on their delivery performance and Procore Use for IFC Documents.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Installation Phase - Preparatory Meeting Agenda for RFC ARG Ceres pending actions items to complete the contract documents held with Gabriel Perez CDM Smith and Wilfredo Sierra - Sargent & Lundy.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L / CDM Smith Weekly BESS Drawings Meeting - Requested updates from Sargent & Lundy as drawing development and scheduled dates for Cambalache, Vega Baja, Costa Sur IFC's and IFB for Installation Phase for Costa Sur, Aguirre & Yabucoa. Provided site team comments on IFC's for Cambalache. Gabriel Perez - CDM Smith, Franklyn Colmenares - CSA Group, Robert Molner - Sargent & Lundy and Gilberto Sucre - DCMC Partners.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Eduardo Rivera DCMC provide update of weekly meeting with Homeca as well as site situation of potential oil spreading in soil around Peakers foundations and preventive measures being taken.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussed Project Updates from Jose Lopez and Eduardo Rivera (DCMC) for Aguirre Site Mobilization Activities & New Staff personnel, and for Vega Baja Demolition Status and Punchlist activities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja reviewed Demolition Phase II Scope, did quantity take-offs for upcoming pricing proposal comparison. Evaluated underground existing site utility drawings and best drawing to be used for As-built background of Phase I Demolition to be provided to Homeca for their use.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Weekly Internal Meeting met with site team for Pre-mobilization site activities and review comments on IFC Drawings issued by Sargent & Lundy. Also reviewed draft DCMC EHS Modules Slides. Andres Concepcion, Luis Damudt, Luis Duque, Jorge Mercado, Carlos de Jesus and Gilberto Sucre - DCMC Partners.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting with ARG Ceres - Met with contractor to review outstanding items to complete contract documents and provide scope specifics to follow. Participants Gabriel Perez - CDM Smith, Mike Kuczynski - Sargent & Lundy, Carlos Hernandez -ARG Ceres, & Gilberto Sucre - DCMC Partners.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Reviewed RGE Specification Markups on bid submission documents and forwarded comments to CDM Smith & Sargent & Lundy.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discuss implementation and data collection for Weekly One Pager Report for BESS & Peakers Programs to be issued to Jesus Cintron - Genera on Mondays. Participants Gabriel Perez - CDM Smith, Franklyn Colmenares - CSA Group, & Raissa Borges - DCMC Partners.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine). Discussed project, job offers, PROCORE workshop schedule, interviews, trailer set-up, safety, schedule for locations, LEAN, and program management plan update.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-PMO Reporting call to discuss and review the reports created by the PMO team for Genera. Attendees were Frances Vallejo, Jean Pierre Menay, Rafael Calderon, Gilberto Sucre (DCMC), and Lauren Wells, Foster Veazey (Lemoine)
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore) to discuss SOW for Financial tools and timeline for completion.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore financial tool items.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on DCMC invoice upload for Franklyn Colmenares (CSA) for Esther Rohena (DCMC).
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore invoice management pre-intervention workflows after Lauren Kennedy (Procore) made updates.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore user support.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria -Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. Contributed updates on assigned tasks, reviewed performance metrics, and participated in discussions aimed at streamlining reporting processes and enhancing cross-functional coordination. Collaborated with team members to identify action items and align on priorities for the upcoming reporting cycle. DCMC: Frances Vallejo, Gilberto Sucre, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Browne, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Site inspection with Clara Padovani and Richie Echevaria (GENERA) Cambalache Site to go over project status.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Discuss Cambalache Site inspection for vulnerability assessment with Clara Padovani and Richie Echevarria (Genera) to identify and manage risks and determine security and mitigation measures. PMO meeting reporting with Cambalache DCMC team Harry del Valle and Gabriel Perez to discuss project status to ensure consistent project delivery.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Offices site inspection in Vega Baja Genera Site.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Jesus Cintron (Genera) to discuss BESS project needs.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended in the PMO Catch up call with PMO leadership team to discuss overall project status, staffing update, budget, equipment and material logistics and purchase, and Procore. Participants: Mike Merritt, Annelia Holton, Mark Merritt, Gilberto Sucre (DCMC).
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in the PMO Reporting call to discuss project status by department and discuss monthly report data needed to include in the report that we will send to the client. Participants: Raissa Borges, Sheila Torres, Abraham Velazquez, Paola Arroyo, Rafael Calderon (DCMC)
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Draft email and send to Ada Diaz (DCMC) regarding the material and equipment needed for trailers.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended Cambalache weekly internal meeting with the Costa Sur site manager, Andres Concepcion (DCMC), to discuss project status, trailer needs and licenses that are needed for the project.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended staffing update meeting to discuss interview coordination and new hires for BESS project. Participants: Mike Merritt and Nyah Medina (DCMC)
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - PMO meeting preparation - Updated legal and procurement update slides for the weekly PMO reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any legal or compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Hurricane Maria Generation Fleet RFP 4760 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4760 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Scraps disposed by 20CY bin towards Homeca recycling facility metal scraps from site, shredded concrete for disposal. Uploaded photos and notes to PROCORE app. Day2
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review site drawing Appendix D for contractor RG ENGINEERING, INC. RFP-4899 Proposal. Review applicable safety regulations for the project.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria. Aguirre Site meeting with Harry del Valle DCMC, Jose Lopez DCMC, Luis Moctezuma DCMC, Carlos Lopez DCMC, Rafael Barrera DCMC, Carlos Bayron DCMC and Carlos Rodriguez DCMC, support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur RFP revision of general installation requirements and construction tolerances, in specific design shall include specific plumb and top elevation tolerances.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site meeting with Harry del Valle DCMC, Jose Lopez DCMC, Luis Moctezuma DCMC, Carlos Lopez DCMC, Luis Echevarria DCMC, Rafael Barrera DCMC, Carlos Byron DCMC, Carlos Rodriguez DCMC, support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Aguirre Continue with the Set-up of the interior in the new mobile office (Dual Trailer) of the Aguirre site from Duenas Trailers to provide a centralized hub for operations to manage resources, coordinate tasks, and ensure the smooth operation of the project.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Aguirre Receiving from Rafael Barreras, Carlos Rodriguez and Carlos Bayron (DCMC) the office supplies required for the new DCMC offices. Also, the supplies were organized in the office.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Aguirre Continue with the Set-up of the new mobile office (Dual Trailer) of the Aguirre site from Duenas Trailers to provide a centralized hub for operations to ensure materials, personnel, and equipment are effectively managed throughout the life cycle of the project.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Continue review site drawing Appendix D, contractor RG ENGINEERING, INC. RFP-4899 Proposal and schedule 2030 May 25. Also review new Procore project information.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Aguirre site meeting with DCMC, Harry del Valle, Jose Lopez, Luis Moctezuma, Carlos Lopez, Luis Echevarria, Carlos Bayron, Carlos Rodriguez support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre Site Meeting with Harry Del Valle DCMC, Jose Lopez DCMC, Carlos Lopez DCMC, Luis Echevarria DCMC, Rafael Barrera DCMC, Carlos Bayron DCMC,and Carlos Rodriguez DCMC. Support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We continue to provide assistance at the DCMC office wagon facilities in Aguirre Bess while they carry out exterior and interior work, supervising that the contractor complies with our company's safety standards and policies
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS Project Meeting with S&L, Kuczynski, Mike, Robert Muhler, and (CDM Smith), Gabriel Perez, Franklyn Colmenares, (CDMSmith), Andres Concepcion, Gilberto Sucre from DCMC Partners to discuss the BESS Issue For Construction design drawings delivery status.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site meeting with Harry del Valle, Luis Moctezuma, Carlos Lopez, Luis Echevarria, Rafael Barrera, Carlos Byron, and Carlos Rodriguez (DCMC), to support in trailer installation & office supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT; Supervision and support to the Office Trailer Company (Dueñas Trailer), Installation progresses to enhance workflows and optimizing resources for a smoother building experience.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination with Danny Duenas (Duenas Trailers) the Delivery of the Office Trailer next Wednesday June 11th (Tomorrow) in Yabucoa Gas Turbine Plant - BESS Project.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site meeting with Harry del Valle DCMC, Jose Lopez DCMC, Luis Moctezuma DCMC, Carlos Lopez DCMC, Luis Echevarria DCMC, Rafael Barrera DCMC, Carlos Byron DCMC, Carlos Rodriguez DCMC, support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Worked on the development of safety guidelines for the proper use and handling of cranes at project sites, aligned with OSHA 1926 Subpart CC standards. The task included researching applicable regulatory requirements and outlining responsibilities for contractors and supervisors. Continue structuring the guideline document to be integrated into the site-specific safety plan.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -. Construction Weekly meeting for Cambalache BESS project. Meeting covers project status, updates and pending actions for the execution of the construction phase. Attendees: with Luis O. Damudt (DCMC Partners), Carlos De Jesus (DCMC Partners), Luis Duque (DCMC Partners),
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue Work is being done to create safety guidelines and recognize global harmonization systems (GHS) for risk communication involving chemical agents for the BESS CAMBALACHE project. The GHS enhances safety by ensuring employees are informed about chemical hazards, reducing accidents, improving compliance with regulations, and fostering a culture of awareness and preparedness.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Cambalache Team weekly internal meeting to follow up with action items. Meeting with DCMC - Gilberto Sucre, Luis Damudt, Jorge Mercado, Carlos De Jesus, Luis Duque.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - reviewed Cambalache site Safety Orientation presentation provided by Jorge Mercado- DCMC. Provided comments and distributed to DCMC Partners Jean Menay for review.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Created and updated Cambalache Weekly Construction meeting in Procore for the 6/11/2025 meeting with Project Team (Sargent Lundy, RG Engineering, GeneraPR, DCMC Partners).
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Completed review and observations of Issued for Construction (IFC) drawings to be shared with Project Designer (Robert Molner) for revisions.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Review of Cambalache project proposed Schedule of Values or budget breakdown for payment from RG Engineering general contractor.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project weekly meeting to review project status. Homeca Eduardo Ramos, Carirma Snachez and Carlos Sanchez; DCMC Jaime Pesquera, Gilberto Soto, Jean Menay, and Eduardo Rivera, CDM Smith Nelson Soler and Manuely Concepcion. Several items were discussed and closed from previos meeting new item to include oil observe near the existing GT concrete pads this was mitigate but still under review.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Contractor Homeca continue cleaning at perimeter of project, CES plan was fix in the area that was demolish, contractor continue working with crush stone at site yards, erosion control has been requested to Homeca to control dust.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS Punch List Meeting - Walkdown to project area to review and discuss observation and Puch list items with Homeca supervisor Issac and DCMC Jaime Pesquera.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Homeca BAFO contract agreement to be incorporate on Punch List items, Homeca personnel has leave project. Working with S&L IFC drawing comments for second Phase for Vega Baja Site.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue with removing debrief and scrap material from project site, they continue working with punch list item for project closing. Crush machines start today operation to demolish debrief.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- PMO Meeting - DCMC PMO meeting with Frances Vallejo and DCMC PM teams to discuss project status update for Vega Baja BESS schedule progress and demolition upgrade status project and Peakers.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted scheduled cycle count activities across assigned inventory zones, focusing specifically on storage areas AA 164 through AA 170. These efforts were part of a broader operational strategy to enhance inventory governance, ensure data integrity, and improve stock accuracy. The review involved cross verifying physical inventory against system reported quantities, documenting identified discrepancies, and performing root cause analysis on repeated variances. The outcomes of this task contribute directly to improving control reliability and minimizing systemic errors within the warehouse operations.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an operational coordination session with Juan Vallejo, Giovanni Taffanelli, and key DCMC warehouse personnel to review current performance of inventory control operations. The discussion centered on evaluating the efficiency of warehouse workflows, identifying process breakdowns in inventory tracking, and correcting deficiencies in data recording practices. Emphasis was placed on standardizing operational procedures across facilities, reinforcing consistent execution of cycle count tasks, and aligning data entry protocols.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-Performed a targeted inventory recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC, as part of efforts to revalidate previously recorded cycle count results. The objective was to confirm data accuracy, reassess inventory balances, and address unresolved discrepancies identified during the initial count. Core activities included cross-checking physical quantities against system records, documenting variances, and ensuring proper alignment between actual stock and system reported values. The recount covered storage areas from AA 164 through AA 170.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a focused operational assessment at the Costa Sur warehouse to investigate unresolved inventory discrepancies and reinforce compliance with inventory governance standards. The session involved a detailed review of item level variances, assessment of stock reconciliation gaps, and validation of real time inventory positions against system data. Key objectives included detecting error patterns, verifying procedural execution across affected locations, and ensuring that inventory controls were consistently applied. The evaluation concentrated on bin areas spanning from AA 164 through AA 170.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while station at the Costa Sur warehouse, prepared and delivered a detailed inventory evaluation report for Mr. Anthony Vega of Genera PR. The document synthesized critical inventory data from various warehouse sites and provided a high-level operational summary. It included an analysis of stock quantities, cost variances, historical discrepancy patterns, and inventory levels relative to established thresholds. The report also incorporated performance indicators designed to measure inventory stability and assess overall operational preparedness. The scope of the report included locations AA 164 to AA 170, AG 060 to AG 080, AM 031 to AM 040, AK 016 to AK 018, AK 050 to AK 72.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a comprehensive review of inventory documentation and developed update materials to support the planned operational cycle count at the Costa Sur warehouse. Coordination was carried out with Mr. Hernan Machado from DCMC to ensure procedural alignment with established project objectives and operational standards. Inventory locations scheduled for review during this session range from AA 164 to AA 170.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procurement Review ¦ RFP-221012 – Generator Breaker 13kV (Cambalache) Assessed RFP-221012 and confirmed publication, amendment, and clarification steps. Identified failure to receive proposals and confirmation by end-user that only one OEM (ABB Hitachi) can meet technical requirements. Task involved validating compatibility restrictions and preparing justification outline for Sole Source under 2 CFR § 200.320(c). Supports compliant continuation of the acquisition process.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC Roberto Bosch, and Pedro Cabrera from Genera Joaquin Quinoy to review Federal Projects, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procurement Review ¦ RFP-4523 – Temperature Reduction Station Conducted procedural analysis of RFP-4523 following multiple unsuccessful competitive attempts. Reviewed all documented bidder communications, publication records, and internal justifications. Based on market unresponsiveness and technical constraints, recommended Sole Source pathway. Documentation structured to ensure alignment with GENERA procurement standards and FEMA’s PDAT guidelines for noncompetitive contracting.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procurement Review ¦ RFP-4456 – Generator Hydrogen Coolers (Palo Seco) Reviewed the full procurement lifecycle for RFP-4456 under DR-4339 Critical Components. Evaluated failed competitive bidding attempts and documented supplier outreach. Identified the component’s obsolescence and the absence of viable market alternatives. Recommended transition to noncompetitive procurement (Sole Source), in alignment with GENERA-PR procurement guidelines and 2 CFR § 200.320(c). Task supports compliance with FEMA PA program procurement requirements and sustains project continuity.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Cambalache Weekly Internal Meeting Last Construction Drawings with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Preliminary Drawings document discipline: (Continue) Civil Drawings reviewing before the meeting Cambalache Weekly Internal Meeting.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Discussion and send by email to Luis Duque DCMC the Preliminary Quality Control Plan for Preliminary Review.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Contractor or Vendor Work and Access Documentation requirements checklist send by Andres Concepcion from DCMC.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination, cleaning. Safety briefing conducted by Homeca and Gilberto Soto was present. Had Meeting with Gilberto Soto DCMC, Emanuel Santos (from Homeca Recyclers) to discuss the daily schedule chores.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Had a walk-through meeting with Eduardo Rivera Jordan (DCMC Site Manager) & later with Emmanuel Santos & Issack (from Homeca Recyclers) to discuss the daily punch list items and the safety items we found on the site. We will be doing this walk-through inspection with Homeca Recyclers daily to make sure they know the items we need to complete.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities field supervision and coordination. Walked the site with Gilberto Soto & Eduardo Rivera Jordan (both with DCMC Partners), going over safety debri, smoke debri.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Scraps disposed by 20CY bin towards Homeca recycling facility metal scraps from site, continue to shred concrete for disposal. Uploaded photos and notes to pro core app
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 164 | 656 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 Continue working with RG Engineering Inc. Contract #109403 and Deliverable Schedule review in preparation to Kick-off Meeting for RGE Equipment Supply Contract. Developing PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main RGE Contract 109403, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 164 | 574 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 RG Engineering Inc. Contract #109403 and Deliverable Schedule review in preparation to Kick-off Meeting for RGE Equipment Supply Contract. Developing PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main RGE Contract 109403, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 164 | 656 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 Continue working with RG Engineering Inc. Contract #109403 and Deliverable Schedule review in preparation to Kick-off Meeting for RGE Equipment Supply Contract. Developing PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main RGE Contract 109403, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AK016 - AK018 and AK050 - AK072 Cycle Count List # 1000.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AM031 to AM040
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AM031 to AM040
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AM031 to AM040
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AM031 to AM040
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AM031 to AM040
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 064 to AA 01 070
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 064 to AA 01 070
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 064 to AA 01 070
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. AG 060 TO AG 080 986/987/992/993/994
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AG 060 TO AG 080
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AG 60 TO AG 080 RECOUNT LIST # 967/971
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AG 060 TO AG 80 at the Aguirre warehouse to start the cycle counts.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AK016 - AK018 and AK050 - AK072.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AK016 - AK018 and AK050 - AK072 to begin the cycle counts.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #1016 and 1017 from locations AK016 - AK018 and AK050 - AK072 for a total of 1,931 pcs.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 1016 and 1017 locations AK016 - AK018 and AK050 - AK072.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the performance of Drawings Tool by integrating design team in all activities related to drawings upload and tracking, while ensuring the QA/QC of DCMC and Genera prior to drawings approval and publishing.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/San Juan BESS Gen 01 Environmental & Permitting Download_Review_Process Data / CDM Gen 01 Download Gen 01 Procedures & SOPs Download_Review_Process Data / S&L Gen 01 Download Reports & Various Data
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management /DCMC Submittals SOP -all projects/ Aguirre BESS Mobilization Report with Photos/ Aguirre Setup New Procore User DCMC Carlos López Vallellanes QA/QC/Gen 01 Project Download_Review_Process CDM old SOPs/Costa Sur Setup New User DCMC Carlos Bayron/Vega Baja Review of Downloaded GEN 01 Project Documents
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review contract agreement for the Vega Baja project to review terms and conditions on rejected works, liquid damages, contractor's obligation and demolition phase close out.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the implementation per project of the RFI staging phases and every naming convention for all contractors and vendors inside the platform.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Gather documentation and prepare Power Point for discussion with the team about the inclusion of new potential action plans inside the projects to prepare clear and well documented plans inside the platform.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review project scope of works to relate construction phasings to the available Procore features to provide complete integration of platform with construction management.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare final signed package for CDM Invoice 90235516_Feb2025. I identify a mistake on the dates in the second RFI requesting changes, I contacted Kathleen Anderson (CDM) and clarify, she authorized me to make the correction and proceed with the final stage. I prepare package for CPA (pdf and excel files).
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - PMO Reporting meeting - Recurrent meeting to discuss project management progress for Bess and Peakers and present any important risk or milestone to be completed. In this meeting participates from DCMC Frances Vallejo, Rafael Calderón, Glorimel Torrado, Paul Brown, Eduardo Rivera Jordán, Raissa Borges and others.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 149 | 372.5 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón (DCMC) in teams reviewing Siemens contract and preparing key points for tomorrow Kick Off meeting presentation. We discuss a more than 20 pages word document and the whole contract. Identify specific themes to be discussed tomorrow in the presentation.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Distribute the fact sheets to the community leaders of Arecibo.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Create an outline for the PowerPoint presentation structure, including introduction, project details, benefits, and next steps for the BESS project at the second Vega Baja meeting.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Begin preparing the PowerPoint presentation for the second Vega Baja meeting, including key content on the BESS project, project benefits, implementation timeline, and community impact.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Create a video in Canva to showcase the latest updates at the Vega Baja site. Carefully select photos to highlight key improvements and ongoing developments, ensuring the visuals tell a clear and engaging story.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Reporting Meeting with DCMC Partners Team: Frances Vallejo Rosich, Eduardo Rivera Jordan, Jean Pierre Menay, Rafael Calderon, Gilberto Sucre, Paul Browne, Sheila Torres Sterling, Raissa Borges Almodovar, Abraham Velazquez, Glorimel Torrado and Pedro Cabrera, and Lauren Wells and Foster Veazey from Lemoine. In the meeting was the CDM Smith team: Carlos Palomares.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Continue Review BESS Issued for Construction plans, Electrical plans CAB99-EM-BSS-0004 for 4339_9510 BESS_Cambalache project to ensure compliance with codes and regulations.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site meeting with Harry del Valle, Jose Lopez, Luis Moctezuma, Carlos Lopez, Luis Echevarria, Rafael Barrera, Carlos Byron, and Carlos Rodriguez, all DCMC, support in trailer installation & supplies delivered. As a team, we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site support in trailer installation to provide a stable and organized environment and site familiarization with Jose Lopez DCMC, Luis Moctezuma DCMC, Carlos Lopez DCMC to assess the safety regulations in place and any potential hazards on site.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site meeting with Harry del Valle, Jose Lopez, Luis Moctezuma, Carlos Lopez, Luis Echevarria, Rafael Barrera, Carlos Byron, and Carlos Rodriguez, all DCMC. Provided support in trailer installation & supplies delivered. As a team, we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue review site drawing Appendix D, contractor RG ENGINEERING, INC. RFP-4899 Proposal and schedule 30 MW Energy Storage System at Costa Sur Facilities and review new Procore project information.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on teams meeting related to verify project summary documentation status in submittals pending, project contract sign date and pending actions from designer Sargent and Lundy and contractor RGE with DCMC employees Andres Concepcion, Frances Vallejo, Luis Roman, Luis Damudt, Luis Duque, Gilberto Sucre and Jorge Mercado due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on PROCORE settings in considering submittals and correspondence for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on comments on issued for construction drawing and contractor RGE offer report for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 134 | 469 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Aguirre site meetings with Harry del Valle DCMC, Jose Lopez DCMC, Luis Moctezuma DCMC, Luis Echevarria DCMC, Carlos Lopez; Rafael Barrera DCMC; Carlos Byron DCMC and Carlos Rodriguez DCMC to support in trailer installation & supplies delivered. As a team we met to discuss. site safety and initial works, to be done on ground movement and challenges with surrounding terrain and site utilities
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Aguirre continue site meetings with Harry del Valle DCMC, Jose Lopez DCMC, Luis Moctezuma DCMC, Luis Echevarria DCMC, Carlos Lopez; Rafael Barrera DCMC; Carlos Byron DCMC and Carlos Rodriguez DCMC to support in trailer installation & supplies delivered. As a team we met to discuss. site safety and initial works, to be done on ground movement and challenges with surrounding terrain and site utilities
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Review BESS Issued for Construction plans, Electrical plans GGS99-EA-000-001 for 4339_9510 BESS_Cambalache project.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache Weekly internal meeting with Andres Concepcion (DCMC) and Gilberto Sucre (DCMC) for the 4339_9510 BESS_Cambalache project to discuss weekly plan and action items to improve efficiency and productivity, increase accountability and continuous improvement.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting work session with Manuely Concepcion from CDM Smith to discussed workflow for Procore Integration. Going over contract management, invoices, Grants, procurement process and communication protocols to be aligned with new Procore functionalities and implementation.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended "One Pager Discussion" meeting to discuss a new report to show more frequently status of projects progress against key milestones and address any issues impacting timelines or deliverables. DCMC: Frances Vallejo, Abraham Velazquez, Gilberto Sucre, Paul Brown CDMSmith: Franklyn Colmenares, Carlos Palomares
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 122 | 183 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Enhancing the financial process structure for Genera projects with an emphasis on Grants Management, aimed at effective alignment with Procore's financial tools."
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Working with the financial process diagram for Genera projects, with an emphasis on Grants Management to support integration of the financial tool in Procore.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Bayron Liboy, Carlos | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 4.6 | 4.6 | 4.6 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site meeting with Harry del Valle, Jose Lopez, Luis Moctezuma, Carlos Lopez, Luis Echevarria, Rafael Barrera, Carlos Byron, and Carlos Rodriguez, all DCMC. Provided support in trailer installation & supplies delivered. As a team, we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 154.7 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to The Home Depot, Reyna Del Sur Shopping 3305, 3305 C. Baramaya, Ponce, 00728 to Central Aguirre (17.951690, -66.229675) to CVP Guaynabo to Home Office Luquillo. Purpose, Meeting & Coordination for Central Aguirre Office Trailer Installation. Support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities. Supervise the installation of the office trailer. Attendees – Jose Lopez (DCMC), Luis Moctezuma (DCMC), Carlos Lopez (DCMC), Luis Echevarria (DCMC), Rafael Barrera (DCMC), Carlos Byron (DCMC), Carlos Rodriguez (DCMC), Harry Del Valle (DCMC) CVP – Meeting & Coordination with Danny Duenas (Duenas Trailers) the Delivery of the Office Trailer next Wednesday June 11th (Tomorrow) in Yabucoa Gas Turbine Plant - BESS Project. TOTAL MILEAGE – 221 miles
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Bayron Liboy, Carlos | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 62.44 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre- Roundtrip travel from Guayanilla PR to Salinas PR for a site meeting with Harry del Valle, Jose Lopez, Luis Moctezuma, Carlos Lopez, Luis Echevarria, Rafael Barrera, Carlos Byron, and Carlos Rodriguez, all DCMC. Claiming 89.2 millage round trip.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 76.3 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Yabucoa Gas Turbine to Aguirre Power Plant to Yabucoa Gas Turbine. Purpose - Continue with Relocation of the DCMC Partners Mobile Office to the Aguirre Site.
2025-06-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  |  | 0.7 | 61.74 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre site meeting with DCMC, to support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 384.8 | 384.8 | 384.8 | Yes | 146793 |  | Portosan - Vega Baja - 6/11-7/7/25
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore master SOP document to incorporate updates from each tool SOP that have been developed.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Project # 4339-10710. Reviewed design drawings, plans and specifications Reviewed design drawings, plans, and specifications are important in construction projects to provide a clear blueprint of the design, materials, and measurements and define the scope of work providing a clear and detailed description of expectations for the project.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 Participated in Peaker's meeting to discuss schedule and staffing of projects. Rafael Pabon, CDM Smith Carlos Palomares CDM Smith German Nunez, GENERA Frances Vallejo Rosich DCMC Francisco Feliu Genera Paul Browne DCMC Lauren Wells DCMC Paola Arroyo DCMC Laya, Enrique J. CDM Smith.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Peakers Procurement Status meeting with Cynthia Ortiz - DCMC, Gabriel Perez - CDM Smith & Gilberto Sucre - DCMC to review RFP updates on each site including ones currently being routed for approval.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One Page Update for BESS Program meeting with Raissa Borges DCMC
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Site investigation & evaluation of soil/concrete potential contamination to detect hazards, ensure structural safety and comply with environmental regulations.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed status of uploading and Publishing of IFC drawings for Vega Baja & Cambalache with Procore and Project Site Teams from DCMC.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Meetings with Jesus Cintron - Genera, Gabriel Perez - CDM Smith and Gilberto Sucre - DCMC to discuss site findings done by Gilberto Sucre- DCMC. Evaluated alternate options for mitigation and next steps to consider continuing with site work.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PMO * Update Tools P6 & Bluebeam Roosters for PM Field Employees. * Updated Procore Access to Site Managers for Costa Sur & Yabucoa. * Reviewed and revised PM Project procedures write up for Peakers with Abraham Velazquez (DCMC). * Correspondence Reading.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Met with Joaquin Quinoy (Genera) for weekly alignment meeting, this week we worked to identify communication and operational challenges impacting project efficiency, Teams group creation, and scheduling. Discussed improvement strategies for the P3 approval process and KPI metrics. Aligned on planning a two-day process improvement workshop and next steps for stakeholder engagement, including Kevin D. Futch and Jose Molina (Genera)
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore settings/permissions for editing the home page for team members.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tools items.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore drawings and specs with users.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions to configure/modify settings for drawings.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore financial tools to inform the team about our upcoming meetings with Lauren Kennedy (Procore) to complete our SOP's.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.25 |  | 184 | 46 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Provided the third revision of the Fuels Consumption and Power Production report to Jan Rodríguez from Genera PR, incorporating the latest updates to ensure data accuracy and alignment with reporting requirements.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 184 | 552 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site meeting with Harry del Valle and Gabriel Perez (DCMC) support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 -Conference call with Luis Moctezuma (DCMC) about Yabucoa (GENERA) Site EHS Topic. Conference call with Jose Lopez (DCMC) about Aguirre (GENERA) Site installers and EHS Topics. Workshop by EHS (GENERA) topics to employees by Duenas Trailers supplier. Conversation with Enrique Laya (CDM SMITH) about Vega Baja (GENERA) site environmental situation.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 |  | 184 | 414 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 -Aguirre Site meeting with Harry del Valle and Gabriel Perez (DCMC) support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities. Meeting with Harry del Valle, Gabriel Perez and Frances Vallejo (DCMC) about trailers facilities in Genera Sites Projects.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting with Paola Arroyo (DCMC) to discuss community engagement plan, second meeting with the community at Vega Baja site and discuss BESS newsletter.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Gilberto Sucre (DCMC), to discuss Procore design submittals and approval process, coordination between Genera and S&L and site coordination needed.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 184 | 230 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting with Raissa Borges (DCMC) to discuss one pagers per site, data recompilation and monthly report next steps.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Harry del Valle and Jean Pierre Menay (DCMC) to discuss trailer coordination and needs.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4899 - Supported Genera's Legal team by assembling the Request for Approval package by organizing the documentation required which includes over 35 supporting documents. Ensured all materials were clearly labeled and aligned with the submission requirements to facilitate a thorough and compliant approval process.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure the contractors comply with the safety while cleaning the Vega Baja site. Scraps disposed by 20CY bin towards Homeca recycling facility metal scraps from site, shredded concrete for disposal. Uploaded photos and notes to PROCORE app. Day2
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Site visit to identify potential safety hazards. Review plans, identifying areas to be demolished and areas where batteries will be installed with Rafael Barrera, Carlos De Jesus y Carlos Bayron (DCMC). Meeting with Cambalache site staff team Andres Concepcion, Rafael Barrera, Carlos De Jesus, Carlos Bayron (DCMC) to discuss project status.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Request for Proposal Review specific to RFI and submittal process required by sub-contractor to execute.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review of Request for Proposal Costa Sur site on specifics of concrete flow, slump, density and concrete strength by type.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Inspect the work performed by the landscaping company Villamil Group Inc. in the storage and laydown area near the DCMC Partners mobile office are installed.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 |  | 167 | 626.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue with the Set-up of the new mobile office (Dual Trailer) of the Yabucoa site from Duenas Trailers to provide a centralized hub for project managers and teams to manage daily operations, track progress, and coordinate tasks efficiently.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Discussion and review with Harry del Valle and Jean Pierre Menay (DCMC) regarding the plan to relocate and energize the new DCMC mobile office at the Yabucoa site.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 |  | 167 | 459.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Received the new mobile office (dual trailer) for the Yabucoa site from Duenas Trailers. Setup location instructions were discussed by Gabriel Morales, Harry del Valle and Jean Pierre Menay (DCMC) with the Duenas Trailers team.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Review applicable safety regulations for the Costa Sur project and continue with site project visit in order to obtain drawing data.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review for Rigging Plan to Lifting and Placing Tesla BESS: Overview, Equipment Description, Lifting Equipment. Lift Procedure: Pre-Lift Inspection & Setup, Rigging, Lift Execution and Placement.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue reading and review Rigging Plan for Lifting and Placing Tesla BESS: Safety Measures, Contingency Plans and Documentation: Rigging gear certifications Crane load chart and lift calculations Job Hazard Analysis (JHA) Site-specific lift permit (if required) Manufacturer’s handling instructions for Tesla BESS
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT: On-site inspection and meeting with the electrical contractor, Gerardo Rivera (Independent Contractor), to discuss the scope of work to facilitate power to the office trailer. The existing point of connection and the details regarding distance and available power distribution for the trailer were discussed.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Site Visit to coordinate the temporary electrical power installation in the office trailer. Had a call with Carlos López (DCMC) to coordinate office supplies and electronics status pick up at the City View Plaza Office. Has a call with Basilio Ramos from Sunset Construction to coordinate a site visit to the Vega Baja Job Site.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Harry Del Valle and Jean Pierre Menay (DCMC) to discuss the office trailer contractor punch list items. A punch list with pictures was built using the PROCORE platform and distributed via email to Harry Del Valle, Jean Pierre Menay, and Gilberto Sucre (DCMC).
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT: Meeting with Francisco Marí (Genera PR) to go over the site security specifics and to identify the contractor's employee parking available space that could be used for this purpose.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Yabucoa Gas Turbine Office Trailer Installation. Attendees, Duenas Trailers Installer team, Gabriel Morales (DCMC), Jean Pierre Menay (DCMC), & Harry Del Valle (DCMC). Continue with the supervision of the Office Trailer installation.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination for Yabucoa Gas Turbine Office Trailer Installation. Attendees, Duenas Trailers Installer team, Gabriel Morales (DCMC), Jean Pierre Menay (DCMC), & Harry Del Valle (DCMC). Topics discussed, walk through Office Trailer Area, discussed Office trailer Installation by Duenas Trailer, discussed Office trailer utility's needs. Introduce to Genera the DCMC BESS Project Management team. Supervise the installation of the office trailer.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued at the Cambalache site with RGE personnel, where they visit the storage areas to coordinate the movement of materials belonging to the GENERA company to keep project on track, reduce costs, maintain safety, and optimize the construction process.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Visit to the Cambalache site where the contractor RGE is received for planning the movement of containers. This was done with Luis Damudt and Andrés Concepcion of DCMC.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Discussed action items within Cambalache DCMC team while on-site. Reviewed progress on process for project access and work authorization with DCMC Luis Damudt. Reviewed Safety documentation process and review/approval DCMC - with Jorge Mercado.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Organized, Reviewed and planned project follow ups and actions after the Construction Weekly Meeting discussion with contractor (RG Engineering) and Designer (Sargent and Lundy).
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Site Visit from RG Engineering (Edgardo Sureda, Carlos Rivera), GeneraPR (Kevynne Gonzalez) and DCMC (Luis Damudt, Jorge Mercado) to evaluate Existing Warehouse inventory relocation logistics and plan to ensure flow of normal day-to-day business.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Genera Cambalache Plant Manager (Herminio Arroyo) to discuss coordination items on the plant to be considered for pre-construction planning to ensure a smooth process down the road and help prevent miscommunication, delays, and unexpected issues on the construction site.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received a Mechanical Drawing set (IFC 6.10.25) from Sargent and Lundy (Ivette Miranda). Reviewed the set of drawings to provide observations to team concerning issues and solutions for the various mechanical systems for review of the project designer (Sargent and Lundy).
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted Cambalache Weekly Construction Meeting with project team CDM Smith (Gabriel Perez, Franklyn Colmenares) RG Engineering (Jose Segarra), Sargent Lundy (Dean Ennes) to discuss project status and action items.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca personnel continue working with punch list item. Visit from Manuel Hernandez of Genera Environmental to review the oil leak observed at the project near GT-1 and GT-2 pedestal. Working with IFC comments drawing to provide feedback to Gilberto Sucre of DCMC.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - We are in a mitigation of oil found near GT-1 and GT-1 concrete pad. Homeca continue working in completing punch list items. Julio Perez of JP Transportation arrives at site to quote the relocation of the existing transformer to Luma site. DCMC Gilberto Sucre arrive at project to view the issue with the oil fund near GT pedestal.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue with removing debrief and scrap material from project site, they continue working with punch list item for project closing. Crush machines start today operation to demolish debrief. We are in a mitigation of oil found near GT-1 and GT-1 concrete pad. Homeca continue completing punch list items.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed preparatory activities for the upcoming cycle count at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. The focus was on ensuring all preliminary steps were completed to support a smooth and efficient counting process. Key preparation tasks included identifying and verifying the specific areas scheduled for counting, printing the required inventory sheets, and ensuring physical readiness of the workspace. This involved organizing and cleaning the counting zones, clearing obstructions, and confirming proper item labeling and placement. Additionally, materials necessary for the count such as pencils, clipboards, count folders, and tally sheets were gathered and prepared in advance.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Aguirre warehouse, a full-scale inventory performance report was compiled to provide Mr. Anthony Vega of Genera PR with a consolidated overview of inventory conditions across all warehouses. This report served as a centralized audit tool, integrating findings from multiple locations to assess overall compliance, data integrity, and operational efficiency. The scope of the report included catalog ID validation, unit count verification, inventory cost analysis, and identification of system discrepancies. It also assessed whether inventory levels aligned with authorized minimum and maximum thresholds, allowing for early detection of stock shortages or excesses. To enhance clarity and decision making, percentage-based metrics were applied to evaluate inventory accuracy, stock reliability, and overall condition. The evaluation spanned warehouse zones ranging from AG 080 through AG 128 and AH 001 through AH 070, AA 171 to AA 172, GE 001 to GE 007, AP 001.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-a recount was conducted at the Aguirre warehouse in collaboration with Mr. Juan Vallejo from DCMC, as a follow-up to discrepancies identified during the previous cycle count. The objective of this effort was to revalidate questionable data, confirm physical stock alignment, and reinforce inventory accuracy in the system. The recount process involved revisiting the previously flagged storage locations, physically recounting items, and cross-checking part numbers, descriptions, and units of measure against both manual sheets and system records. Additional steps included verifying labeling clarity, correcting bin misplacements, and ensuring that all recorded quantities reflected the actual on-hand inventory. Areas reassessed during this session included bins AG 080 through AG 128 and AH 001 through AH 070.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-a technical coordination session was held with Hernan Machado and Juan Vallejo from DCMC, alongside key personnel from warehouse team to perform a structured assessment of current inventory operations. The objective was to diagnose systemic inefficiencies, validate process integrity, and ensure alignment with standardized inventory control practices. The discussion focused on identifying root causes of procedural deviations. Pinpointing workflow discontinuities and reinforcing the applications of consistent inventory methodologies. Additionally, the team evaluated the performance of existing tracking tools, reviewed anomalies in past material movements, and proposed corrective frameworks to mitigate recurring errors.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane –as part of a variance investigation at the Aguirre warehouse, a diagnostic assessment was performed to examine inventory discrepancies and determine the underlying causes of data mismatches. This investigation aimed to trace variances back to their source by evaluating system transactions, reviewing physical stock accuracy, and validating historical count data. Key steps included analyzing movement history, reviewing item adjustments and transfer records, and comparing documented quantities against physical inventory. Also labeling consistency was inspected, bin assignments, and recent system updates to identify potential process breakdowns contributing to variance. The variance reviewed covered storage zones ranging from AG 080 through AG 128 and AH 001 through AH 070.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 167 | 542.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted ABC cycle count operations across designated inventory zones as part of the ongoing effort to reinforce data accuracy and procedural compliance within warehouse operations. The session focused specifically on the detailed execution of the cycle counting process. Activities included conducting physical counts of inventoried items, reconciling quantities against system records, and identifying discrepancies for further investigation. The process also required verifying item identification through labeling, ensuring correct bin placement, and reviewing adherence to establish storage protocols. Count sheets were utilized to manually record results, which later compared to digital records for accuracy validation. Inventory areas inspected during this session spanned from AG 080 through AG 128 and AH 001 through AH 070.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procurement Evaluation ¦ RFP-4433 Reviewed procurement records for RFP-4433 including receipt of a BAFO proposal and subsequent process cancellation. Analyzed viability of Sole Source option and determined that justification does not meet FEMA criteria due to presence of a competitive respondent. Task included outlining conditions under which Sole Source may become applicable if OEM exclusivity is proven.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Complete the review of the updated Fuel Efficiency component list in anticipation of an amendment to Project 673691. Ensured alignment with GENERA-PR guidelines and PREB resolutions. Communicated with stakeholders to request input on potential modifications to the list, supporting the development of installation scopes and cost estimates. Task contributes to procurement readiness and compliance with FEMA PA documentation requirements.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procurement Evaluation ¦ RFP-225916 – Boiler Feed Water Pumps Analyzed full cycle of RFP-225916. A proposal was received and evaluated; however, the panel recommended re-launching the RFP due to evolving technical specifications. Concluded that current conditions do not support Sole Source. Provided criteria for future consideration if revised scope demonstrates OEM exclusivity or lack of market competition.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS Site Office Inventory Trailer Office I QA-QC y Trailer Office 2 Site/Construction Management. Call and discussion with Luis Duque from DCMC about the Cambalace Bess Program CON-FM50.1 - Sample Quality Control Plan Division Finishes.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Site walkthrough to containers warehouse coordination efforts with Andres Concepcion, Jorge Alexis Mercado DCMC, Herminio Arroyo, Kevyn Gonzalez from Genera PR
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Cambalache BESS - Construction Weekly status meeting to discuss project updates with Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team, Jose Segarra, Alberto Borely from RGE, Robert Molner from Sargent and Lundy.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails and submittals from the RGE contractor to Sargent and Lundy and Site Office Inventory Trailer Office I QA-QC y Trailer Office 2 Site/Construction Management.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS received COMMENTS from DCMC on April 17, 2025. 8. Appendix D.3 - Demolition Plan Specifications and talk with Andres Concepcion from DCMC and Herminio Arroyo from Genera PR about the gas storage room and warehouse containers site location.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities, field supervision & coordination. Had a walk-through meeting with Eduardo Rivera (DCMC Site Manager) & later with Nelson Soler (CDMSmith) to discuss the daily punch list items and the safety items we found on the site. We will be doing this walk-through inspection with Homeca Recyclers daily, if possible, to make sure they know the items we need to complete.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Cleanup activities field supervision and coordination. Had meeting with Emmanuel Santos (from Homeca Recyclers) to discuss safety items that need to be removed from the site like rods & things and make sure they keep spaying water for dust control. We conducted this walk-through inspection again in the day a few times as well.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Cleanup activities field supervision and coordination. Had a walk-through meeting with Emmanuel Santos (from Homeca Recyclers) to discuss safety items that need to be removed from the site like rods & things and make sure they keep spaying water for dust control. We will be doing this walk-through inspection in the afternoon as well.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety Continue cleaning the Vega Baja site. Scraps disposed by 20CY bin towards Homeca recycling facility metal scraps from site, shredded concrete for disposal. Uploaded photos and notes to PROCORE app.day 2
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 164 | 492 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 Continue with Technical portion of the Kick-Off Meeting RG Engineering Inc. Contract #109403, Deliverable Schedule and Obligations review for RGE Equipment Supply Contract. Conducting PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main RGE Contract 109403, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. kick-Off Participants: Genera (German Nuñez, Francisco Feliu), Sargent & Lundy ( Miguel del Valle, Mike Kuczynski, Christopher Mateo, Angel Alicea, CDM (Carlos Palomares, Rafael Pabon, Enrique Laya), DCMC (Abraham Velazquez, Glorimel Torrado)
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 164 | 656 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 Kick-Off Meeting RG Engineering Inc. Contract #109403, Deliverable Schedule and Obligations review for RGE Equipment Supply Contract. Conducting PPT Presentation Slides with schedule Milestones, Invoice required template and key dates. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters. Reviewing documents: Main RGE Contract 109403, Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. kick-Off Participants: Genera (German Nuñez, Francisco Feliu), Sargent & Lundy ( Miguel del Valle, Mike Kuczynski, Christopher Mateo, Angel Alicea, CDM (Carlos Palomares, Rafael Pabon, Enrique Laya), DCMC (Abraham Velazquez, Glorimel Torrado)
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #1027 and 1028 from location AP001 for a total of 22,737 pcs and lft.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GE001 to GE007
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GE001 to GE007
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GE001 to GE007
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GE001 to GE007
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GE001 to GE007
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 071 000 to AA 01 072 000
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 071 000 to AA 01 072 000
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 071 000 to AA 01 072 000
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations AG 080 TO AG 128 & AH 001 TO AH 70 at the Aguirre warehouse to start the cycle counts.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location AG 080 TO AG 128 AND AH 001 TO AH 70
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. AG 080 TO AG 128 & AH 001 TO AH 070 LIST # 996/997/1006/1007/1008/1013/1014
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations AG 80TO AG 128 AND AH 001 T0 AH 070 RECOUNT LIST # 1004/1009/1010
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with location AP001 Cycle Count List # 1019.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from location AP001 to begin the cycle counts.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 1027 and 1028 location AP001.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 151 | 604 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – (Second Part) Peakers Equipment Supply Kick-off Meeting hosted by Rafael Pabon (CDM Smith), with representation from Genera (with German Nunez), from Sargent & Lundy with Ivette Miranda, Alan Figueroa, Angel Alicea; from General Electric Vernova David Lee, Eduardo Zea, Kin Ho; and contractor RGE with Jose Robles, Alberto Borelli, Xiomara Perez, and consultants present from contractor's main office. Purpose of meeting is to setup the upcoming Peakers Equipment Supply by RGE for Nguabo, Jobos and Daguao Plants. Vendor GE Vernova presented their designs and discussed with the team potential changes due to optional additional scopes.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/Yabucoa_Jobos_Daguao Peakers RG Kick Off_Data_Equipment_Submittal Process Coordination/Cambalache BESS Data Review/S&L Gen 01 Download_Review_Process Decommissioning Plan Dwgs-Various Projects
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management /Yabucoa_Daguao_Jobos Peakers RG Kickoff _ Equipment & Contractual Items
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 151 | 604 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – (First Part) Peakers Equipment Supply Kick-off Meeting hosted by Rafael Pabon (CDM Smith), with representation from Genera (with German Nunez), from Sargent & Lundy with Ivette Miranda, Alan Figueroa, Angel Alicea; from General Electric Vernova: David Lee, Eduardo Zea, Kin Ho; and contractor RGE with Jose Robles, Alberto Borelli, Xiomara Perez, and consultants present from contractor's main office. Purpose of meeting is to setup the upcoming Peakers Equipment Supply by RGE for Naguabo, Jobos and Daguao Plants. Introduction from everybody on the Meeting, overview of project initial scope and contractual clauses discussions for contract execution.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 149 | 596 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - RGE Kick off Meeting, in this meeting Rafael Calderón (DCMC) present our part from Contract Management. Some of the participants were: Germán Nuñez (Genera), Rafael Pabón (CDM Smith), Abraham Velázquez (DCMC), Rafael Calderón (DCMC), Glorimel Torrado (DCMC), Luis Román (DCMC), Miguel Del Valle (S&L), Mike Kuczynski (S&L), José Pagán (S&L), José Robles (RGE),, Harry Velázquez (RGE), David Lee (GE Verona), Roozbeh Eshraghnia (GE Verona), Francisco Feliu (Genera), Enrique Laya (S&L), and others (approx. people participated in this meeting).
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 149 | 149 | 149 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review power point presentation, QA/QC to the information to be presented in RGE Kick off meeting.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: Checking prices on Amazon and Walmart for the OtterBox covers for the six iPads for the PMO and the Apple Pencils. The covers are meant to protect the devices, and the Apple Pencils will allow users to make annotations, sign documents, etc. Sent email to Frances Vallejo (DCMC) with the gathered information for her review.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 139 | 417 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Update the BESS and Peakers webpage with key details relevant to the community to strengthen outreach and transparency. Meeting with CDM Smith Team: Rafael Pabon to ensure the updated site clearly communicates essential information in a user-friendly, accessible format.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Meeting with Frances Vallejo from DCMC to discuss key tasks related to community relations and the strategic work plan. The conversation focused on refining outreach efforts, ensuring clear and effective communication with stakeholders, and strengthening partnerships that support long-term engagement.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Refine and edit the BESS community presentation to ensure clarity, coherence, and alignment with engagement goals. Select and incorporate impactful visuals and photos to enhance storytelling and support key messages.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Provide communication updates with the Genera PR team to share key information on pending projects. Meet with Jorge Bracero from Genera to ensure clear and effective dissemination of essential details related to ongoing initiatives.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Update the BESS and Peakers webpage with key details for the community and enhance outreach efforts. Meet with the Genera PR team, including Jorge Bracero, Rafael Rodríguez Ema, and Alex Valdés, to review and refine the webpage content. Ensure the site effectively communicates essential information, making it more accessible and informative for stakeholders. Incorporate critical updates, clarify messaging, and structure content to align with community engagement goals.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Cambalache Power Plant BESS Program Quality Control Plan Submmitals and Construction Facilities and Temporary Controls for 4339_9510 BESS_Cambalache project.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Pick-up office hotspot hardware for Aguirre Site at DCMC Office at City View Plaza. Review Project drawings (AGB99-CY-000-0100 WEST BESS EROSION AND SEDIMENT CONTROL; AGB99-CY-000-0200 WEST BESS GRADING AND DRAINAGE PLAN; AGB99-CY-000-0201 EAST BESS GRADING AND DRAINAGE PLAN)
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Cambalache staff meeting with Andres Concepcion (DCMC) about different issues in the Energy Storage System Construction, Site visit on Construction area of Costa Sur project and review new Procore project information modules.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on PROCORE drawings considering project layout for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on PROCORE documentation considering existing conditions and preliminary drawings of project for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on TEAMS meeting related to Cambalache BESS - Construction Weekly with pending steps for sign contract, status of the temporary facilities, special instructions before start in site of projects, submittals and status of starting initial construction process with DCMC employees Andres Concepcion, Luis Damudt, Luis Duque, employees of RGE Jose Segarra, Xiomara Pérez Álvarez, CDM Smith employees Franklyn Colmenares, Gabriel Perez, employees of Sargent and Lundy Dean Ennes due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on comments considering drainage and grading plan of preliminary drawings of project for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continuing reviewing project documentation, RFP 229760 Battery Storage System. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Reyes, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Completed reviewing project documentation, RFP 229760 Battery Storage System. (PRF-4900) BESS Genera Aguirre projects to track progress, coordinate with the team, identify risks, and ensure accountability
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Construction Weekly meeting with Andres Concepcion (DCMC), Robert Molner (Sargent and Lundy) and Jose Segarra (RGE) for the 4339_9510 BESS_Cambalache project. Discussed work status and the tasks to be completed.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue review Cambalache Power Plant BESS Program Quality Control Plan, Product Receiving, Storage and Handling Requirements for 4339_9510 BESS_Cambalache project to ensure project meets the required standards and specifications.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 122 | 366 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Analyzing key performance indicators and project outcomes to shape a cohesive weekly reporting format.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Conducting a thorough analysis of collected project data to design and implement a comprehensive weekly report template, ensuring clarity, consistency, and actionable insights for stakeholders.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Internal Teams Meeting with Frances Vallejo, DCMC. The purpose of this meeting is to discuss project reports status and updates. The meeting was organized by Frances Vallejo (DCMC).
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting with Gilberto Sucre (DCMC) to gather and discuss project status and progress for the new weekly report.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 68.56 | 68.56 | 68.56 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Office Trailer Supply. Cleaning material and tools.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits and travel from Genera offices to CVP offices
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Site Inspection | Direct-PA | Activities necessary to perform and complete site inspection (other than travel and SIR development) | Expense |  |  | 0.7 | 45.92 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel necessary for project inspection from home offices San Juan to Yabucoa Genera Site Purpose Genera PR – Installing Trailer Offices in Yaubucoa Genera site by Dueñas Trailers for DCMC. Total Distance 65.6 miles.
2025-06-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 42.07 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel from Home Office Luquillo to Yabucoa Gas Turbine (18.106216, -65.823685) to Home Office Luquillo. Purpose, Meeting & Coordination for Yabucoa Gas Turbine Plant Office Trailer Installation. Support in trailer installation. walk through Office Trailer Area, discussed Office trailer Installation by Duenas Trailer, discussed Office trailer utility's needs. Introduce to Genera the DCMC BESS Project Management team. Supervise the installation of the office trailer. Attendees - Duenas Trailers Installer team, Gabriel Morales (DCMC), Jean Pierre Menay (DCMC), & Harry Del Valle (DCMC). TOTAL MILEAGE – 60.1 miles
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks for Procore team to ensure issues/support are being tracked.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Attended budget and schedule meeting discussed and reviewed budgets and schedule impacts based on design delays. German Nunez, GENERA Rafael Pabon, CDM smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC Laya, Enrique J. CDM Smith Jesus. Cintron Genera
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710. Coordination meeting with Peakers staffing for Costa Sur. Discussed roles and responsibilities, expectations and milestones. German Nunez, GENERA Rafael Pabon, CDM smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Internal Meeting PM / CM Team with Sargent & Lundy. Robert Molner Sargent & Lundy provided update on upcoming IFB and IFC for Installation combined phase for Costa Sur, Aguirre and Yabucoa as well as IFC for Costa Sur - Civil & Structural. Gabriel Perez - CDM Smith, Robert Molner - Sargent & Lundy and Gilberto Sucre - DCMC Partners.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's Project Schedule & Budget Meeting. Carlos Palomares CDM Smith presented the weekly status update for BESS & Peakers Programs. Gabriel Perez - CDM Smith, Franklyn Colmenares - CSA Group, Jesus Cintron - Genera & Gilberto Sucre - DCMC Partners participated.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja discussed next steps to be implemented with Phase II Demolition, Storm Water Disposal and Contractor selection for project completion. Gabriel Perez & Enrique Lara CDM Smith, Mike Kuczynski - Sargent & Lundy, Jesus Cintron - Genera & Gilberto Sucre - DCMC
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Kickoff Meeting with DCMC Project Site Team Carlos Rodriguez, Rafael Barrera, Carlos de Jesus, Carlos Bayron & Luis Echevarria. * Project Status * Contractor Selection * Underground Utilities & Soil Testing * Review & Observations of RFP drawing set * Contractor Staging & Office Area * Expected NTP & Mobilization * Weekly Construction Meeting.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence evaluation and response to multiple subjects: * Final Documentation for Costa Sur & Aguirre Contracts with RGE * Revised concept drawings for Aguirre Concrete Battery Paks * Punchlist items for Vega Baja Demolition, and Aguirre Office trailers installation. * Procore IFC Updates * Soil Borings and material classification for Vega Baja * Contractual Obligations not executed by Homeca at Vega Baja. * Others.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 225 | 675 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Site Meetings for Diesel Containment Options. Met on Site with DCMC Site Team, Gabriel Perez & Enrique Laya - CDM Smith and Erick Rocher - Genera and All Contractor's to evaluate current site conditions, diesel presence on ground, containment improvements and storm water conditions. Requested quotes from All Contractors for containment, Concrete demolition & MTP rigging and relocation.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - kickoff meeting with Kevin D. Futch Genera) Team to introduce the 8-Step Problem Solving process focused on improving stakeholder approvals within P3 and FOMB workflows. Attendees included Joaquin Quinoy (Genera), Christian J Torres Pena (Genera), Joel D Pantojas Caraballo (Genera), Jorge E Sanchez Valle (Genera), and Cristina Ribas Morera (Genera). Presented SIPOC and process mapping tools to support root cause identification. Aligned on meeting cadence and scheduled next session for the week of June 23rd to complete problem definition and begin analysis.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-BESS and Peaker's Project Schedule & Budget Meeting. Attendees were Foster Veazey (Lemoine), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Carlos Palomares (CDM Smith) .
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Franklyn Colmenares (CSA), Manuely Concepcion (CDM Smith), Luis Roman (DCMC), Theresa Perez (DCMC) to discuss document control items.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for Eduardo Rivera (DCMC) for Vega Baja.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool set for Budget items.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) requested technical support to address issues with Procore instructional media that was not functioning correctly. Coordination was conducted with Procore technical support to troubleshoot the issue, including review of browser configuration and system settings. The issue was resolved through browser adjustments, restoring proper platform functionality and ensuring continued access to Procore resources in support of project operations.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for changes with supplier access.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) and Theresa Perez (DCMC) for Procore weekly check-in call.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items for Procore tools.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 104629 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Continuing Offices site inspection in Vega Baja Genera Site. Review the Homeca demobilization process to ensure it was executed accordingly to the project plan and the site stays in proper condition.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Offices site inspection in Vega Baja Genera Site. Review the Homeca demobilization process to supervise the removal of materials and equipment and the site cleaning.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Discussed with Jesus Cintron (Genera) and D Alexander Gonzalez (DCMC) the request to create a presentation with the BESS and Peakers projects highlights. Discussed with Raissa Borges (DCMC) and Paola Arroyo (DCMC) the data and information we will include in the slides.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and made changes in excel to the material and equipment tracker and send to Ada Diaz (DCMC).
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Call with Jesus Cintron (Genera) to discuss information needed from the construction team to provide to the PIA association.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with BESS and Peaker project managers to discuss schedule and budget overview. Participants: Gabriel Perez (CDM), German Nunez (Genera), Carlos Palomares (CDM), Gilberto Sucre (DCMC) and Abraham Velazquez (DCMC).
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4826 - Assisted Genera's Regulatory and Procurement team by verifying the debarment status of six subcontractors on SAM.gov and drafting such response to FOMB’s 06/12 RFI.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 4826 - Supported Genera's Regulatory team by reviewing and drafting a response to FOMB's 06/11 RFI.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in a meeting with Franklyn Colmenares, Enrique Laya, Gabriel Sepulveda (CDM Smith) Mike Kuczynski, Manuely Concepcion, Robert Molner, Wilfredo Sierra (S&L) regarding the BESS Installation RFI to review and discuss the submissions received. Contributed to the alignment on next steps to inform the upcoming procurement strategy.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP 105509 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities, field supervision & coordination. Had a walk-through with Eduardo Rivera (DCMC Site Manager) & later with Emmanuel Santos from Homeca Recyclers to discuss the daily punch list items and the safety items we found on the site. We will be doing this walk-through inspection with Homeca Recyclers daily and in the afternoon to make sure they know the items we need to complete.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated the Power Point Presentation of "Charla de Salud y Seguridad" sent by Jean Menay (DCMC). Focused the updates on the main Health and Safety Risks for Costa Sur site.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Regional DCMC Costa Sur meeting with Gilberto Sucre and Costa Sur to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron and Rafael Barrera (DCMC). Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Internal DCMC Costa Sur meeting with Costa Sur team to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron and Rafael Barrera. Open discussion on project basics on housekeeping, basic safety procedures and culture.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Request for proposal review on specific of BESS site related to turbine control panel layout submittal and generator control panel submittal.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Regional DCMC Costa Sur meeting with Gilberto Sucre and Costa Sur to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Internal DCMC Costa Sur meeting with Costa Sur team to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on project basics on housekeeping, basic safety procedures and culture.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue with the Set-up of the new mobile office (Dual Trailer) of the Yabucoa site from Duenas Trailers to provide a centralized hub for operations to increase productivity and efficiency and enhance safety.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue with the Set-up of the new mobile office (Dual Trailer) of the Yabucoa site from Duenas Trailers to provide a centralized hub to streamline operations, and improve coordination and communication.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Regional Costa Sur meeting with Gilberto Sucre DCMC and Costa Sur to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera DCMC. Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Following the meeting held this morning, Gilberto Sucre (DCMC) requested a thorough review of the RFP document to ensure that all necessary revisions are made in a timely manner and that any questions or concerns are adequately addressed. Coordinate closely with the team to meet upcoming deadlines and maintain the expected quality standards.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria This morning, I was assigned by Jean Pierre Menay (DCMC) to provide support for the installation of the office trailer for the DCMC project in Humacao. We provide assistance at the DCMC office wagon facilities in Humacao Bess while they carry out exterior and interior work, supervising that the contractor complies with our company's safety standards and policies
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review of Cranes and Hoists 1926.1400 Subpart CC
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT; Supervision and support to the Office Trailer Company (Dueñas Trailer), Installation progresses. Review the Punch list with the contractor to ensure corrections are made.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT; Supervision and support to the Office Trailer Company (Dueñas Trailer), Installation progresses.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work continues on the information being shared with the contractor RGE for workplace hazard recognition. This information covers safety topics ranging from environmental requirements to emergency meeting point management. The evaluation of annual OSHA training for RGE contractor personnel has begun.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on the information being shared with the contractor RGE to identify workplace hazards. This information covers safety topics, from environmental requirements to managing meeting points in case of emergency.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Cambalache project RFP and Bids documents to validate scope of work information regarding Temporary Warehouse inventory relocation activity to ensure a clear timeline for the relocation process and improve efficiency.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Designer (Sargent & Lundy) response for Submittal RGE-0003.1 regarding mechanical piping. Followed up with email to Robert Molner (Sargent and Lundy).
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Completed and generated Meeting minute for the Construction Weekly Meeting that happened in 6.11.25. Updated notes for meeting minute in Procore.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Various Phone meetings for project coordination. Met with RG Engineering - Jose Segarra for follow up on pending items. Met Luis Roman - DCMC for Procore coordination and met DCMC Gilberto Sucre to align required project actions.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed IFC 6.03.2025 Complete set of drawings upload in Procore and coordinated with DCMC - Luis Duque for publishing the drawings to ensure they are complete and viewable to all users with access to the project's Drawings tool.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed IFC 6.11.2025 Mechanical drawings and coordinated with DCMC - Luis Duque to publish drawings in Procore for an effective management of project drawings that prevents confusion and streamline the process from upload to revision tracking.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - Meeting with Ida Ramirez and Carlos Hernandez of ARG; Gilberto Sucre and Eduardo Rivera of DCMC; and Wilfredo Sierra, Gary Jasutis, Margolis Jordan, and Angel Alicea of S&L. CDM Smith Gabriel Sepulveda and Enrique Laya - Meeting to discuss the RFC generated for ARG in regard of the Vega Baja BESS projects.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue with removing debrief and scrap material from project site, they continue working with punch list item for project closing. Site walkdown with CDM Smith Enrique Laya, and Gilberto Sepulveda, DCMC Gabriel Sucre and Erike Roche of Genera in regard of oil leak detected near turbine pad.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue with removing debrief and scrap material from project site, they continue working with punch list item for project closing. Working with second phase IFC reviewing drawing to provide comments in regard of drawing. Homeca has clean and identify the sanitary piping of the demolish guard house for future second phase use. They had almost completed the removal a crush stone debriefs from the site. Tomorrow Homeca will complete the substantial completion of Vega Baja Demolition project.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue with removing debrief and scrap material from project site, they continue working with punch list item for project closing. Working with second phase IFC reviewing drawing to provide comments in regard of drawing.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Palo Seco warehouse, Mr. Mark Merritt from DCMC and Ms. Sulinnette Perez from Genera PR conducted an on-site walkthrough to review the facility. During the visit, they were able to assess the overall condition of the warehouse infrastructure as well as inspect the state of stored materials and equipment. This visit provided valuable insight into current operational challenges and reinforced the importance of continued oversight and process improvement initiative.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco warehouse, a summarize inventory performance report was developed for Mr. Anthony Vega of Genera PR. The report compiled key metrics from multiple warehouse zones, including catalog reconciliation, stock verification, and variance analysis. Its purpose was to highlight discrepancies, evaluate inventory accuracy, and support data-driven decission-making across identified storage areas. Locations assessed included GE 008 to GE 012, CB 067 to CB 072, AH 070 to AH 140, BB 001 to BB 040, AA 173 to AA 177.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane Maria-upon returning from transporting Mr. Mark Merrit from DCMC and Ms. Sulinnette Perez from Genera PR back to their corporate offices, efforts resumed on the ongoing cycle count activities. The task continued in coordination with Mr. Giovanni Taffanelli from DCMC, focusing on the validation and reconciliation of physical inventory across designated areas. This phase of the operation reinforced inventory accuracy ensured alignment with system records and supported the broader objective of maintaining consistent and reliable stock management practices. Today locations range from CB 067 through CB 072.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused inventory recount at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC. The primary objective was to reassess and validate the results of previous cycle counts, ensuring alignment between physical inventory and system records. The process included detailed bin-level inspections, cross-verification of quantities, confirmation of transactional accuracy, and identification of any inconsistencies. Recount activities emphasized compliance with storage protocols, proper labeling, and documentation standards. This recount phase specifically covered storage locations CB 067 through CB 072.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted variance investigation to address inconsistencies between physical inventory and system reported data within storage locations CB 067 through CB 072. The activity focused on isolating root causes of persistent quantity mismatches, validating item descriptions, and identifying potential process breakdowns contributing to inventory inaccuracies. The analysis included a comprehensive review of historical transactions, bin-level movements, and catalog entries.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-a workplace safety and operational alignment meeting was conducted with Giovanni Taffanelli, Juan Vallejo from DCMC, and key warehouse personnel. The session emphasized the importance of maintaining a safe and professional work environment. Key safety topics discussed included the mandatory use of personal protective equipment (PPE), punctuality upon arrival, and adherence to proper workplace conduct. Employees were reminded of the critical role that discipline, and safety protocols play in preventing accidents and promoting efficient operations.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Independent Cost Estimate for RFP-4386- Demolition Services for Vega Baja Power Plant to serve as a benchmark for evaluating the reasonableness of the contractor's proposed costs and support decision-making,
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Preparation of a consolidated list with information on all delivered critical components, including description, PO number, estimated and actual costs, procurement type, delivery status, and technical justification for their classification as a “Critical Component”. Purpose: To share with GENERA-PR Regulatory Department as part of compliance monitoring and deliverable documentation under DR 4339.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS Review document, Cambalache BESS - Contractor access and work requirements checklist send by Andres Concepcion from DCMC.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Review the Civil Drawings from contractor Sargent and Lundy.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Warehouse Drawings document discipline Demolition: Architectural.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails and submittals from the RGE contractor to Sargent and Lundy.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform. Draft RFI Closed.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW9510 Pre-Intervention Review - Working with Javier Bidot Invoice #6363GE25 for TO#6 Mar 2024. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7. Preparing Email communications for Franklyn Colmenares POC.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#10_Invoice# PRIN0009113_Apr 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#10_Invoice# PRIN0009111_Mar 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CB067 to CB072 Cycle Count List # 1040.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GE008 to GE012
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GE008 to GE012
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GE008 to GE012
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GE008 to GE012
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GE008 to GE012
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 073 000 to AA 01 077 000
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 152 | 38 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 073 000 to AA 01 077 000
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 |  | 152 | 494 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 073 000 to AA 01 077 000
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BB 001TO BB 040 AND AH 070 TO AH 140
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations BB 001 TO BB 040 AND AH 070 T0 AH 140 RECOUNT LIST # 1029/1044
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations BB 001 TO BB 040 & TO AH 001 TO AH 140 at the Aguirre warehouse to start the cycle counts.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BB 001 TO BB 040 & AH 070 TO AH 140 LIST # 1025/1026/1030/1031/1032/1036/1037
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #1049 and 1050 from locations CB067 to CB072 for a total of 228 pcs.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 1049 and 1050 locations CB067 to CB072.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CB067 to CB072.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CB067 to CB072 to begin the cycle counts.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review project documentation regarding contractors and designer organization charts to determine proper workflows for new incoming issues.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/S&L Palo Seco Data Download for Review & Process/GE Peakers Equipment Presentation Data/Gen 01 S&L Download Data for Review & Process/Costa Sur & Aguirre Duenas Trailer Data for Process
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management /Coordination & Data Management with Lauren Wells DCMC & Luis Roman DCMC/ Coordination of Submittals & RFI Distribution _Permissions with Lauren Wells DCMC/Luis Roman DCMC/ Franklyn Colmenares CDM/Manuely Concepcion CDM/Vega Baja BESS Homeca Incoming Data for Review & Process/
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Evaluate the proper project phasing for the Peakers Equipment Supply on Yabucoa, Jobos and Daguao, to reinforce Procore use of main tools such as for Critical Components Tracking, Financial relations and other.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Document Control Meeting with Lauren Wells (Lemoine) Theresa Perez (DCMC), Rafael Pabon (CDM Smtih) and Franklyn Colmenares (CSA) to discuss ongoing progress for the document control on external dropbox for users.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the implementation of new project and existing projects set up for the tracking of critical components inside BESS, Peakers, and other federally-funded projects on the coverage of DCMC.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review and audit the uploading of non-classified documents in the RFI and Submittal Tools for the Cambalache Projects to identify items to be removed or moved to the Documents Tool.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Check in with Lauren Wells (Lemoine) and Theresa Perez (DCMC) to discuss the ongoing topics in the platform such as naming conventions for different project tools, introduction to the Peakers Supply project for 3 different sites and the inclusion of a new project to track Critical Components out of BESS and Peakers projects.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Travel from Guaynabo to Toa Baja to support Genera in community engagement efforts during an educational talk at a children's summer camp, where we will provide information about the BESS and Peakers projects.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Gather information and data on the BESS project to develop a PowerPoint presentation for the Pharmaceutical Industry Association, which will be shared with Jesús Cintrón from Genera.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 139 | 556 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Worked collaboratively with Raissa Borges from DCMC to develop the BESS project presentation for Jesús Cintrón from Genera. This included gathering and analyzing relevant technical data, drafting key messaging tailored to the Pharmaceutical Industry Association, and designing a clear and engaging PowerPoint deck to effectively communicate the project’s value and impact.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 139 | 173.75 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Support Genera in community engagement efforts during an educational talk at Choo Choo Train Day Care & Learning Center, where we were welcomed by Director Sandra Miranda. During the session, we provided information about the BESS and Peakers projects to the students attending the summer camp.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. DAY 2) Review Cambalache Power Plant BESS Program Quality Control Plan for 4339_9510 BESS_Cambalache project to ensure project safety, functionality, and durability.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site support in trailer installation to provide a stable and organized environment and site familiarization with Jose Lopez DCMC, Carlos Lopez DCMC to assess the safety regulations in place and any potential hazards on site.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Supporting Dueñas Trailer on site trailer installation with Jose Lopez DCMC. Reviewing Lifting Plan for lifting and placing BESS batteries to ensure it contemplates that the container frame, corner castings, and welds can bear the full load without deformation or damage to guarantee reliable energy storage during high demand or power interruptions.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria - Regional DCMC Costa Sur meeting with Gilberto Sucre and Costa Sur to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria - Internal DCMC Costa Sur meeting with Costa Sur team to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on project basics on housekeeping, basic safety procedures and culture.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on comments for preconstruction requirements considering GENERA procurement planning schedule and RFP schedule for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 134 | 402 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on construction DCMC meeting related to site office rules, site of PREPA rules, status in project contract sign date, pending actions from designer Sargent and Lundy and review Procore contract documents with DCMC employees Carlos Rodriguez, Carlos Byron, Rafael Barrera, Luis A. Echevarria due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on staff teams meeting related to status in project contract sign date and pending actions from designer Sargent and Lundy with DCMC employees Carlos Rodriguez, Gabriel Sucre, Carlos Byron, Rafael Barrera, Luis A. Echevarria due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review Cambalache Power Plant BESS Program Quality Control Plan for 4339_9510 BESS_Cambalache project to ensure it meets the required standards and specifications.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Contributing to the financial process mapping of Genera projects to support its implementation in Procore.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Gathering information to develop BESS and Peakers project presentation for Jesus Cintrón (Genera) to present to the Pharmaceutical Industry Association team.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 122 | 488 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Developing BESS and Peakers project description and status presentation for Jesus Cintrón (Genera) to present to the Pharmaceutical Industry Association team.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 Internal Meeting work session with Cynthia Ortiz (DCMC) to continue discussing Procurement process for Procore Integration. Going over documents review, vendor's proposal, funding approvals and communication protocols to be aligned with new Procore functionalities and implementation.
2025-06-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 44.8 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager. Travel from home offices San Juan to Vega Baja Site (18.446230, -66.392561) to Home Offices San Juan. Site Inspection in Vega Baja Site. Start Homeca demobilization process.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 146793 | Remote | PREPA Genera Deliverable 11. DR 4339. PMO call. Teams call with Mark Merritt, Mike Merritt, Gilberto Sucre, Foster Veazey and Ada Diaz, DCMC. Discussed update on project, job offers, PROCORE workshop schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria.-COSTA SUR Reviewed and discussed plans, specs, and overall jobsite safety and protocols for the upcoming demolition portion of the project. Carlos De Jesus DCMC Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC Harry Del Valle DCMC.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project # 4339-10710 At Costa Sur, walk the site and reviewed site plan. Carlos De Jesus DCMC Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC Harry Del Valle DCMC
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre Review and Inquiry of revised Battery Packs Foundation design and electrical duct bank details. Also worked on RFI's for missing information.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja prepared three RFP's for the MTP rigging & movement, spill containment improvements, and Concrete Slabs Phase II Demolition & Removal. Documentation was issued to All Contractors,
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja: Homeca's Change Orders summary review discussion with Jose Lopez (DCMC) for the Demolition Phase I of the project. Aguirre: discussed mobilization activities progress.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - One to one meeting with Carlos Hernandez ARG Ceres to discuss project update & premobilization activities to take place prior to NTP.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Civil Design Review and CEST plan evaluation for Demolition Phase II. Participants at meeting Robert Molner - Sargent & Lundy, Gabriel Perez - CDM Smith, Erick Rocher - Genera, & Gilberto Sucre - DCMC Partners.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up Meeting - Addressed essential staffing updates, open positions and Peaker's need to determine positions required for Costa Sur. Trailer installation updates were provided and PMO RFP status was discussed. Mike Merritt, Mark Merritt, Barry Scanlon, Ada Diaz, Foster Veazey, Anneilia Holton, & Gilberto Sucre DCMC Partners.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Review Site Topographic drawings prepared BESS and Peakers, Underground utilities studied carefully.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Prepare Weekly PMO Summary Update and action items list for next week.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Yabucoa Bess - Civil & Structural RFP. Evaluation Panel Meeting in which Mike Kuczynski -Sargent & Lundy presented the proposal highlights of RGE and ARG Ceres. Gabriel Perez - CDM Smith, Jesus Cintron - Genera and Gilberto Sucre - DCMC
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 - Worked to schedule next meeting for the P3 Approval Process Improvement Team Kevin Futch (Genera), Christian J Torres Pena (Genera), Angelina Minier (Genera), Cristina Ribas Morera (Genera), Joel D Pantojas Caraballo (Genera), Jorge E Sanchez Valle (Genera). Sent the team a find time poll, worked to determine availability, and scheduled a meeting. Sent the team an explanation of the goal and explained the 8-step problem-solving process that we will be using.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Anneilia AJ Holton, Barry Scanlon, Mark Merritt, and Mike Merritt and Foster Veazey, Lauren Wells (Lemoine). Discussed project update, PROCORE workshop, logistics, interviews, trailer set-up, schedule for locations, LEAN, and program management plan.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Peakers Project Management Update meeting. Attendees were Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Carlos Palomares (CDM Smith), and Abraham Velazquez (DCMC)
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore documents tool.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items for Procore tools.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Raissa Borges (DCMC) to discuss and review program Diagram wireframe.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore distribution list assignments.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP review for final publishing.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool for building out scope of work for the next 4 weeks.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet Contract No. 104265 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146793 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Conference call with Gilberto Sucre (DCMC) about Vega Baja Genera projects utilities. Conference call with Gilberto Soto (DCMC) about Vega Baja EHS status. Conference call with Daniel Duenas and Esteban Gonzalez (Duenas Trailers) about Vega Baja and Yabucoa trailers offices in Genera Projects. Meeting in Arecibo Emergency Zone Offices about Cambalache Genera projects.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet Contract No. 104814 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet RFP No. 4759- Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet Contract No. 10435 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Scraps disposed by 20CY bin towards Homeca recycling facility metal scraps from site, shredded concrete for disposal. Uploaded photos and notes to PROCORE app.Day 3
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the RFP-4899 Proposal Civil & Structure Works for 30 MW Battery Energy Storage System at Costa Sur Exhibit J- Non-Disclosure Agreement. Review applicable safety regulations for the project.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Regional DCMC Costa Sur meeting with Abraham Velazquez to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, and Rafael Barrera. Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities of Peaker's construction area.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review of request for proposal demolition and site movement prints of Peaker's Project in Costa Sur site, specific to areas walked in the morning meeting that include transmission towers, tanks, buildings and parking areas.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Regional DCMC Costa Sur meeting with Abraham Velazquez to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities of Peaker's construction area.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue with the Set-up and cleaning of the new mobile office (Dual Trailer) of the Yabucoa site from Duenas Trailers to provide a centralized hub for operations with Luis Moctezuma (DCMC)
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 |  | 167 | 542.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluation of the Scope of Service RFP #231175 for the YABUCOA BATTERY ENERGY STORAGE SYSTEM (BESS) FACILITY.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Jose Lopez (DCMC) and Gerardo Ramos from JN Electrical Contractor to evaluate for quotation the energizing of the DCMC Mobile Office for Yabucoa Site.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Regional DCMC Costa Sur meeting with Abraham Velazquez to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities of Peaker's construction area.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | PREPA- Genera- Deliverable 11 DR 4339 - Hurricane Maria- Internal DCMC Costa Sur meeting with Costa Sur team to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on project basics on housekeeping, basic safety procedures and culture. Also, site visit with project team to discuss possible safety issues and construction planning.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and reviewing to identify requirements and state and federal regulations that apply to our activities using a Crane in Aguirre Bess: Ground conditions 1926.1402, Assembly / Dismantling 1926.1403 to .1406, Aerial lines 1926.1407 to .1411, Inspections 1926.1412, Cable inspection 1926.1413, Safety devices 1926.1415 and Operating aids 1926.1416
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We continue to provide support in the installation of the office trailers for DCMC at the Humacao Project to oversee compliance with occupational safety and health regulations.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue reading and review the next Standards and Requirements applicable of OSHA for Aguirres Bess Installation: Signals 1926.1419, Fall protection 1926.1423, Qualification / Certification 1926.1427, Elevating people 1926.1431
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre BESS Project; Participated in Team Meeting with Sargent & Lundy Staff, Robert D. Molner, and Gilberto Sucre (DCMC), Enrique Laya, CDM Smith, and Angel Rodríguez (Sargent & Lundy) to discuss the Phase II Request for Comments to the contract (4339_9510) documents.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS PROJECT. I had several phone calls with Nelson Soler (CDMSmith) regarding the Vega Baja Substantial completion work and punch list status. It was decided to assign Jaime Pesquera (DCMC) responsibility for implementing and evaluating the punch list.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Site Visit to the Yabucoa Site to meet with Gabriel Morales and Luis Moctezuma (DCMC) to discuss the temporary electrical power installation required for the Job Site Office Trailer. We also inspected the installation work performed by Dueñas trailer and began to create a punch list of pending items.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Submittal evaluation (RGE-0007.0: RGE-0007 RG Engineering Safety Manual) for the start of the Bess Cambalache project.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-The evaluation of Submittal (RGE-0007.0: RGE-0007 RG Engineering Safety Manual) continues for the start of the Bess Cambalache project.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed the received project Submittals (Safety) on 6/12/25 by RG Engineering (Jose Segarra). Coordinated review workflow with Luis Roman and Luis Duque (DCMC) to ensure review and responses are provided on time.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed documentation regarding project submittal (Submittal #RGE-0008 Revision 0: RGE-0008 EMPLOYEES CERTIFICATION) regarding employees safety qualifications to ensure Health and Safety Compliance in the project.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - generated correspondence via email to coordinate a meeting and action items with CW Legal Services which is responsible for project regulatory compliance and inspections. Communicated email to Carlos Lopez - CW Legal.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed recent received documentation for submittal (#RGE-0007 Revision 0: RGE-0007 RG Engineering Safety Manual). Studied documentation provided by RGE (Javier Reyes) and do observations and comments to safety plans to ensure required Health and Safety compliance in the project.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared and coordinated next week project management plan for follow up actions, team coordination and project execution. The plan will serve as a roadmap for project managers and team members, explaining expectations, providing structure, and controlling variables that could impact successful project outcomes.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Created standard project reporting formats in Procore Reporting Tool, to improve project status on submittals and RFIs reporting system. and set up weekly notifications accross the team.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue with removing debrief and scrap material from project site they had completed a substantial completion, they continue working with minor punch list item for project closing. Homeca start today removal of fence near the parking as part of punch list and contractual. Homeca has completed the removal of fence at 9:30am, they continue with minor cleaning and closing punch list items.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS Meeting - Preparation for meeting with S&L. Meeting start at 11AM with DCMC Gilberto Sucre and Eduardo Rivera, S&L Marco Galvan, Mike Kuczynski, Robert Molner, and Aimee Sahlas, Erick Rocher of Genera, Gabriel Sepulveda and Enrique Laya of CDM Smith - Meeting to discuss issue with storm water from Vega Baja Site.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca continue working with minor punch list item for project closing. The continue cleaning all perimeter of project. Working with IFC drawing comments to be send by RFI to S&L. RFI was send to S&L Mike Kuczynski in regard of IFC comments drawing send 6/3/25.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-a comprehensive inventory performance analysis was conducted on-site at the San Juan warehouse to support the development of a consolidated report for Mr. Anthony Vega of Genera PR. The report integrated system-wide inventory data across all audited zones and emphasized analytical rigor in evaluating operational integrity. Key components of the report preparation included catalog data validation, stock balance reconciliation, variance quantification, and the application of cost distribution metrics. System outputs were benchmarked against predefine inventory thresholds. The scope of the review covered inventory zones AM 041 to AM 047, BB 040 to BB 145, AA 178 to AA 179, CF 043 to CF 048, AP 001.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a structured cycle count across designated inventory sectors, specifically focusing on storage locations AM 041 through AM 047. The process involved the physical validation of on hand quantities, comparison of recorded stock against system reported values, and the identification of any discrepancies requiring corrective action. Core activities included verifying item descriptions, part numbers, unit measure, and bin locations. Each discrepancy identified during the count was documented in real time to support traceability and ensure that resolution steps could be executed promptly. Emphasis was placed on data accuracy, procedural compliance, and consistency between physical counts and system records.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-a focused inventory recount was conducted at the San Juan warehouse in coordination with Mr. Milton Flores (DCMC) as part of efforts to validate cycle count results. The activity centered on verifying data accuracy by cross referencing physical inventory with Asset Suite records. The review covered locations AM 041 through AM 047 and prioritized compliance with internal control standards and audit readiness.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-a targeted inventory audit was conducted to identify and analyze variances between physical stock counts and system reported inventory data across locations AM 041 through AM 047. The evaluation incorporated root causes analysis of discrepancies, lifecycle tracking, and transactional review of inventory movement within Asset Suite. Key technical activities included validating system generated balances against actual on-hand quantities, i9dentifying anomalies caused by data input errors, and assessing the accuracy of historical inventory adjustments.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted preparatory activities at the San Juan warehouse in coordination with Mr. Milton Flores from DCMC in advance of the upcoming cycle count. The session was centered on setting the necessary groundwork to ensure an efficient and accurate physical inventory process. Preparation included reviewing and validating the inventory master data, confirming bin assignments, and organizing stock layout to facilitate clear visibility and ease of access during counting. Special attention was given to the accuracy of item descriptions, unit of measure alignment, and ensuring that all storage areas were properly labeled and free from obstruction. Today’s readiness check covered inventory segments ranging from AM 041 through AM 047.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-an early coordination session was conducted with Milton Flores, Hernan Machado, and DCMC warehouse personnel to reinforce the importance of operational discipline and adherence to established procedures. The discussion emphasized the need for strict compliance with scheduled timelines, thorough documentation practices, and attention to detail during all inventory reconciliation activities. The session highlighted the critical role that accurate recordkeeping and timely task execution play in maintaining inventory integrity. Team members were reminded to consistently log all movements, discrepancies, and observations in real time to support traceability and audit readiness. Emphasis was placed on documenting even minor details, as these often provide early indicators of larger systemic issues. Additionally, the importance of respecting the client’s expectations and maintaining professionalism at all times was addressed.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Preparation of a consolidated list with updated information on critical components currently in Pre-Shipping and Shipping stages. The list includes component description, associated location, and estimated delivery dates to support coordination and timely tracking.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue developing an Independent Cost Estimate for RFP-4386- Demolition Services for Vega Baja Power Plant to serve as a benchmark for evaluating the reasonableness of the contractor's proposed costs and support decision-making.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Gas Storage Drawings document discipline Demolition: Architectural and the sketch proposed by the contractor where the containers for the warehouse parts are located.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review Relocation Pipes and New parking area Drawings document.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review Relocation Pipes and New parking area Drawings document.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails and submittals in Procore.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria Demolition Activities, field supervision & coordination. Had a walk-through with Eduardo Rivera (DCMC Site Manager) & later with Emmanuel Santos from Homeca Recyclers to discuss the daily punch list items and the safety items we found on the site. We will be doing this walk-through inspection with Homeca Recyclers daily and in the afternoon to make sure they know the items we need to complete.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria - Conducted on-site supervision of demolition activities at the Vega Baja site. Met with Eduardo Rivera (DCMC Site Manager) and later with Emmanuel Santos (Homeca Recyclers) to review outstanding punch list items and safety issues identified during inspection. Discussed corrective actions and reinforced the plan to carry out afternoon walkthroughs with Homeca Recyclers on a daily basis.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR Deliverable 11 Project Management Dr 4339 Hurricane Maria Demolition-Clean up activities, field supervision & coordination. We walk-through meeting with Eduardo Rivera (DCMC Site Manager) & later with Gilberto Soto (DCMC-Safety) to discuss the daily punch list items and the safety items we found on the site.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Scraps disposed by 20CY bin towards Homeca recycling facility metal scraps from site, shredded concrete for disposal. Uploaded photos and notes to PROCORE app. Completed tasks for Day 3
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, MegaPacks and tariffs for all plants. Pending FOMB review. Meeting participants TESLA (Michael Grabstein, Elizabeth Arentsen, Allin Luong), CSA (Franklyn Colmenares), and DCMC (Rafael Calderon)
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#10_Invoice# PRIN0009113_Apr 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#10_Invoice# PRIN0009111_Mar 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by locations CF043 to CF048 and AP001.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AM041 to AM047
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AM041 to AM047
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AM041 to AM047
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AM041 to AM047
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AM041 to AM047
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 078 000 to AA 01 079 000
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 078 000 to AA 01 079 000
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 078 000 to AA 01 079 000
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations BB 040 TO BB 145 . at the Aguirre warehouse to start the cycle counts.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BB 040 TO BB 145
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations BB 040 TO BB 140 AND AH 070 T0 AH 140 RECOUNT LIST # 1029/1044
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BB 040 TO BB 140 . LIST # 1045/1047/1048/1051
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, working on inventory discrepancies, verifying item costs, and identifying the authorized minimum and maximum stock levels for Recounts #1067 and 1068 locations CF043 to CF048 and AP001,
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations CF043 to CF048 and AP001 using Cycle Count List #1059 and 1060.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Continuing the investigation of discrepancies found in Recount Lists #1067 and 1068 for locations CF043 to CF048 and AP001, totaling 14,028 pieces.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations CF043 to CF048 and AP001 to start the cycle counts.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Hurricane Maria Performed system testing within designated project environments to validate the functionality of the Action Plans and Drawings tools for publishing finalized versions of Standard Operating Procedures (SOPs). Reviewed and verified drawing numbering features and established SOP-compliant file naming conventions to ensure proper document control, consistency, and traceability in accordance with project management and federal compliance requirements.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146793 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria¦ Document Control – Data Management/Aguirre BESS Data Review & Process/Cambalache BESS Data Review & Process/Costa Sur BESS Data Review/Gen 01 Geotech Data Download for Review & Process /Gen 01 Financial Download Data
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review contractual agreement for Vega Baja and upcoming Cambalache signed agreement to determine contractual obligations of contractor and designer directly with the Owner.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the distribution lists process and editing project's global distribution groups to independent projects and tools; working on submittals standard distribution for BESS team staff and workflow templates for the required approval of Genera in different project items (safety, contractual, general conditions, etc)
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams call with Nelson Soler (CDM Smith) to discuss the closing and distribution of submittals in the Vega Baja project after reconfiguring project submittal workflow.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Internal Weekly Check In with Franklyn Colmenares (CSA) and Rafael Pabon (CDM Smith); discussed ongoing Procore topics such as the opening of Financial Tool, SOP and Drawings Status, Distribution lists set-up and the implementation of Genera's policies for contruction and installation stages.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review design presentation for the Peakers Equipment Supply for the Yabucoa, Jobos and Daguao Power Plants; review vendor specs on turbines and lead time of critical components.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Worked on the Vega Baja presentation for the second community meeting, focusing specifically on updating the introductory section with the latest project developments and key information.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 139 | 347.5 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Worked on the Vega Baja presentation for the second community meeting, specifically updating the introductory section with the latest project status and key developments at the Vega Baja site.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146793 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Developed fact sheets summarizing key aspects of the BESS project, including technical specifications, site locations, project timeline, community impact, and federal investment. These materials were designed for clear and accessible communication with external stakeholders and the general public.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Continue review Cambalache Power Plant BESS Program Quality Control Plan for 4339_9510 BESS_Cambalache project to ensure the safety, reliability, and efficiency of construction.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Pick-up DCMC Partners banner for Aguirre Site at DCMC Office at City View Plaza. Review Project drawings (AGB99-CY-000-0203 GRADING SECTIONS AND DETAILS; AGB99-CY-000-0204 GRADING SECTIONS AND DETAILS)
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Review Project drawings (AGB99-DM-000-0001 EXISTING GENERAL ARRANGEMENT DEMOLITION PLAN FOR FIRE PROTECTION LINE; AGB99-GA-FPS-0001 FIRE PROTECTION LOOP GENERAL ARRANGEMENT COMPOSITE; AGB99-PI-FPS-0001 PIPING AND INSTRUMENTATION DIAGRAM). Overview and analyzing Crane safety documents sent by Luis Moctezuma DCMC Partners.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria - Regional DCMC Costa Sur meeting with Abraham Velazquez to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities of Peaker's construction area.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on comments for preconstruction requirements considering GENERA procurement planning schedule and RFP schedule for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 -Costa Sur- Regional DCMC meeting and project planning documents review with Abraham Velazquez to include Carlos Rodriguez, Carlos De Jesus, Carlos Bayron, Luis Echevarria and Rafael Barrera. Open discussion on current issues with site on existing utilities, demolition and discussing of the following weeks onsite meetings and activities of Peaker's construction area.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on comments for preconstruction requirements considering GENERA procurement planning schedule and RFP project schedule for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146793 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on comments for preconstruction requirements considering GENERA procurement planning milestone schedule and RFP Peakers project for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146793 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review Cambalache Power Plant BESS Program Quality Control Plan for 4339_9510 BESS_Cambalache project.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting with Franklyn Colmenas and Carlos Palomares from CDM Smith to gather data from BESS and Peaker program status.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 122 | 427 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue developing a standardized weekly reporting format based on in-depth analysis of current project data trends.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Meeting work session with Lauren Wells from Lemoine to discussed workflow for Procore Integration. Going over contract management, invoices, Grants, procurement process and communication protocols to be aligned with new Procore functionalities and implementation.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Transforming raw project data into a structured weekly reporting framework to support data-driven decision-making.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 122 | 183 | 122 | Yes | 146793 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue in the development of the financial process mapping for Genera projects to support its implementation in Procore.
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel to perform various site visits and Genera offices
2025-06-13 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 0.7 | 73.5 | 0.7 | Yes | 146793 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Managment Arecibo for meeting in Emergency Managment Zone Offices with director Juan Carlos Santos about Cambalache Genera Project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 15465.84 | 15465.84 | 15465.84 | Yes | 146794 |  | Duenas Trailers - 16'X40' Flex-tainer, Rental, 6/11/25 - 7/10/25 including Delivery, Installation, modification, Forklift and Cargo charges
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 2357.14 | 2357.14 | 2357.14 | Yes | 146794 |  | Home Depot - Equipment and supplies for Humacao BESS Site
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review and answering correspondences for Procore items.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in meeting Peaker's check in, Discussed current status of the Peaker projects and procurement of equipment with delivery dates. Attended the meeting: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Miguel Del Valle Frances Vallejo Rosich DCMC
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal paperwork, reviewed notes and comments from meetings, reviewed RFP for the demolition scope at Costa Sur.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in a meeting to discuss scheduling impacts to the Costa Sur site and Jobos site based on additional scope of work added to the projects. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended Bess / Peakers meeting, discussed project needs and coordination between contractor and facility personel. Attended the meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Frances Vallejo Rosich DCMC
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Completed Weekly One Page Tracker Report for BESS Program. with Raissa Borges from DCMC Partners.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS organized work week agenda and prepare action items.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Internal Meeting PM / CM Team and Design Team Discuss IFC Issued upcoming scheduled items, input needs from VE at Cambalache & Vega Baja. Coordination of Site Constructability Sessions with Contractors the following week. Further clarification for Aguirre Structural Design. Sargent & Lundy, CDM Smith and DCMC Partners.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Overall Program Management Oversight of all BESS Projects. Verified status of Procore implementation by project sites and needs. Reviewed RGE Ceres Site Logistics, Potential Credits and remaining RFC's. Reviewed Homeca's Punch list, Change orders and legal draft letter breach of contract. Coordinated Telecom Site visit for Luma and HUB to Costa Sur for 6/17.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Morning calls to Site Managers to obtain progress Updates: * Eduardo Rivera - DCMC for Vega Baja * Andres Concepcion - DCMC for Cambalache * Jose Lopez - DCMC for Aguirre
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check IN Led by Gabriel Perez CDM Smith reviewed Program Needs tracker for aspect of the project development, procurement status, design, pre-constrcution and construction status. Attendees: CDM Smith - Gabriel Perez CSA Group - Franklyn Colmenares Sargent & Lundy - Mike Kuczynski Genera - Jesus Cintron DCMC - Frances Vallejo
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PM/CM Meeting to discuss BESS Program status and Needs from Genera to Support Projects: Main Sites on Agenda Vega Baja Closure of Homeca's Contract, Phase 2 Award, All Construction Pricing for Containment Improvements, Concrete Demolition & MPT Rigging and Cambalache final VE. Also discussed Sargent & Lundy's Design status. Meeting with Gabriel Perez CDM Smith.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 – Discussed rescheduling meeting and set new day/time with Jorge Sanchez (Genera) to introduce Genera’s Continuous Improvement (Lean) initiative and discuss department challenges. Topics to be discussed include standardizing processes, and improving communication.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on outlining Procore financial PWs and DI's to put into Procore.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Franklyn Colmenares (CSA), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) and Luis Roman (DCMC) for Procore weekly check-in to discuss open items as a team.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Rafael Calderon (DCMC), Glorimel Torrado (DCMC), Johanna Diaz (SMC) to discuss Procore Budget SOPs.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Peakers Check-in. Rafael Pabon (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore financial items from Lauren Kennedy (Procore).
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOP's final review for RFI's.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for adding users for projects.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated the Genera Connect Financial Tracker with the latest reports to maintain accurate and current financial data. Discussed the strategy for migrating historical timesheets data with Eisha Mercader from DCMC and Aldwin Pagán from Integrum to ensure a smooth and comprehensive data transfer. Additionally, prepared and sent a request to Jean Gonzalez from Genera PR to enable access to Genera Connect Timesheets at various power plant locations, supporting accurate capture of project-related time entries across all operational sites.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Offices site inspection in Costa Sur Genera Projects. Meeting with Rafael Barrera and Luis Echevarria (DCMC) about topics for these projects and EHS themes.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Offices site inspection in Costa Sur and Meeting with Osvaldo de Jesus, Luis F Torres, Richie Correa, Ramon Quinones (GENERA) and Luis Echevarria and Rafael Barrera (DCMC) about Enviromental, Health, Safety and Security requirements in this Genera Projects.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended weekly Cambalache update meeting with Andres Concepcion, Site Manager (DCMC).
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Jesus Cintron (Genera), and project management team for BESS and Peakers to discuss project needs.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 184 | 460 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS Check in and Peakers Check In meetings to discuss project status, RFP status, contract management deliverables, Procore financials and community engagement outreach. Participants: Gabriel Perez (CDM), Abraham Velazquez (DCMC), Jesus Cintron (Genera), Rafael Pabon (CDM), Rafael Calderon, Glorimel Torrado, Sheila Torres, Gilberto Sucre (DCMC)
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Call with Gilberto Sucre (DCMC) to discuss project overview, one pagers for site and staffing coordination.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and analyze the Procore SOP's for the BESS and Peaker project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet Contracts No. 106588 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet Contracts No. 104413 and No. 105509 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Marc Maceira, Carlos González and Ginnell Torres
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Hurricane Maria - Verifying current project progress, ongoing procurement efforts, and challenges impacting project schedules or deliverables to prepare for the weekly BESS and Peakers Project Needs meeting
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore app.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with Jean Menay (DCMC) to introduce the DCMC team (Carlos Rodriguez, Carlos Bayron, Rafael Barrera and Luis Echevarría) and Genera's EHS staff (Ramon Quiñonez, Osvaldo de Jesus, Magdalena Maldonado, Armando Cervoni). Safety issues were discussed to maintain project execution. The meeting focused on key safety topics to support safe project execution, including contractor onboarding protocols, site access requirements, use of PPE, work permit procedures, and emergency communication protocols. Review of the Costa Sur Plant Emergency Response & Action Plan to ensure alignment and understanding of site-specific emergency procedures among all stakeholders.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with the Genera EHS team (Magdalena Maldonado, Armando Cervoni, Luis Felipe Torres and Richie Correa) to take the Environmental Programs Orientation for Contractor of the Costa Sur site. The orientation covered critical environmental compliance topics such as proper waste segregation and disposal, spill prevention and response procedures, hazardous materials handling, stormwater management, and site-specific environmental reporting requirements. Emphasis was placed on contractor responsibilities, adherence to federal and local environmental regulations, and the importance of maintaining environmental integrity throughout all project phases.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with Jean Menay (DCMC) to meet the DCMC team (Carlos Rodriguez, Carlos Bayron y Luis Echevarría) and Genera's EHS staff (Ramon Quiñonez, Osvaldo de Jesus, Magdalena Maldonado, Armando Cervoni). Safety issues were discussed to maintain project execution. Review of the Costa Sur Plant Emergency Response & Action Plan.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with the Genera EHS team (Magdalena Maldonado, Armando Cervoni, Luis Felipe Torres and Richie Correa) to take the Environmental Programs Orientation for Contractor of the Costa Sur site.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue with the installing and set-up process of the Yabucoa site mobile office bathroom with the team of SA Facias and Duenas Trailer to provide a centralized hub for operations.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Set-up of the Yabucoa site mobile office interior with the team of SA Facias to provide a centralized hub for operations to ensure materials, personnel, and equipment are effectively managed throughout the life cycle of the project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Received the materials for the interior of the new mobile office (dual trailer) for the Yabucoa site from Duenas Trailers. Setup location instructions were discussed by Gabriel Morales, and Jean Pierre Menay (DCMC) with the Duenas Trailers team and Samuel Arroyo from SA Facias.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria Meeting with Jean Menay (DCMC) to introduce the DCMC team (Carlos Rodriguez, Carlos Bayron y Luis Echevarría) and Genera's EHS staff (Ramon Quiñonez, Osvaldo de Jesus, Magdalena Maldonado, Armando Cervoni). Safety issues were discussed to maintain project execution. Review of the Costa Sur Plant Emergency Response & Action Plan.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with the Genera EHS team (Magdalena Maldonado, Armando Cervoni, Luis Felipe Torres and Richie Correa) to take the Environmental Programs Orientation for Contractor of the Costa Sur site
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Providing assistance in the interior work being done on the office Trailer of DCMC in the Humacao project, supervising that the work is carried out safely and complies with our standards and policies. Accordance with the General Requirements (29 CFR §1926.501) and Risk Communication (29 CFR §1910.1200). The employees at Duenas Trailer works on the finishes of the interior flooring, bathroom, walls, ceiling, windows, stairs, safety anchors, indoor and outdoor lights.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue Providing assistance in the interior work being done on the office Trailer of DCMC in the Humacao project, supervising that the work is carried out safely and complies with our standards and policies. Accordance with the General Requirements (29 CFR §1926.501) and Risk Communication (29 CFR §1910.1200). The employees at Duenas Trailer resumed works on the finishes of the interior flooring, bathroom, walls, ceiling, windows, stairs, safety anchors, indoor and outdoor lights.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. AGUIRRE BEST PROJECT. Had a call with Brennan LeBlanc LEMOINE ONE IT Technician, to set up the software (BlueBeam) needed for the project administration.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre BESS Project: Had a call with Carlos Rodríguez - (Costa Sur Site Manager DCMC) to review the current Request For Proposal classifications process.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS - Dismantling, Decommissioning and demolition works planning for phase II. Homeca Recycling should submit an LED abatement removal certification to ensure they can safely handle and remove lead hazards, protecting workers and staff from lead exposure. Had a call with Gilberto Sucre (DCMC) to review and discuss the HOMECA Phase II Change Order.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - VEGA BAJA BESS - Dismantling, Decommissioning and demolition punch list works schedule and overview. Homeca Recycling should submit all the pending manifests for the abatement, dismantling, and demolition materials removal certification to ensure they delivered the material to an authorized recycling and landfill center approved by the Department of Natural Resources.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: Electrical work safety program for implementation in the Cambalache project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: fall protection program for implementation in the Cambalache project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared Cambalache Weekly meeting agenda to lead the discussion with General Contractor (RG Engineering) Designer (Sargent and Lundy) and Owners Representative (DCMC Partners). The meeting cover follow up and action items in the project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Coordinated and attended GeneraPR Safety Meeting for Cambalache scheduled visit on 6/17/2025 for Sargent and Lundy staff (Wilfredo Sierra). Orientation led by Jean Menay (DCMC Partners)
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continuation of Preparing Cambalache Weekly meeting agenda to lead the discussion with General Contractor (RG Engineering) Designer (Sargent and Lundy) and Owners Representative (DCMC Partners). The meeting cover follow up and action items in the project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Project Technical Discussion Meeting regarding Structural Design led by Sargent and Lundy Angel Alicea & Robert Molner. Discussion regarding structural basis of design for the BESS Platform steel structure.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Followed Up, Coordinated and supported DCMC Partners Safety Team (Jorge Mercado and Jean Menay) on received safety submittals in Procore Platform. Supported on review and prioritizing a completion date.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Planned, coordinated and followed up the week action items to follow up. Coordinated with Gilberto Sucre (DCMC partners) project pending items. Reviewed Email from Permitting Consultant (Carlos Lopez - CW Legal Services) and planned a follow up meeting for permitting discussions. Installed BlueBeam software with Lemoine IT staff (Brennan Leblanc) to improve document review and observation tool communication.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Cambalache site existing conditions survey report and created markups in Bluebeam software to coordinate future pre-demolition assessments as part of the Demolition activities supervision.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Jaime Pesquera of DCMC enter all punch list item to Procore.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with Homeca project closing items. Review project site for punch list closing items. Send email to Carlos Hernandez of ARG/CERES for tomorrow construction meeting to discuss project need list. Preparing minutes agenda for tomorrow meeting with Homeca at 9AM. Preparing meeting agenda for tomorrow meeting with ARG/CERES second phase at 11AM.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Project PUI sign has been installed. Send email to Carirma Sanchez of Homeca in regard of project closing.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led preparatory efforts for the upcoming operational cycle count at the Costa Sur warehouse. Activities included validating location assignments, reviewing past discrepancies, and organizing updated documentation to facilitate a streamlined count process. Coordination with Mr. Hernan Machado from DCMC ensured alignment on the execution plan, resource allocation, and count methodology. Special attention was given to verifying system data against physical inventory to prevent inconsistencies during execution. The preparation phase focused on location BV 001 to BV 005, BW 001 to BW 004, BX 001 to BX 003.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out inventory validation procedures across designated zones, concentrating efforts on areas BV 001 to BV 005, BW 001 to BW 004, BX 001 to BX 003. The activity formed part of a continuous improvement initiative aimed at strengthening warehouse accountability and ensuring consistency between physical stock and system records. The process included systematic verification of item counts, logging of irregularities, and assessment of recurring variances. This initiative also supported root cause analysis and contributed to the refinement of operational protocols, reducing inventory-related errors and protocols, reducing inventory-related errors and promoting accurate reporting across storage locations.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an investigative review at the Costa Sur warehouse aimed to identifying root causes behind ongoing inventory discrepancies. The assessment involved a methodical walkthrough of affected storage areas to trace anomalies, verify stock positioning, and evaluate the consistency of applied controls. The session also included a step-by-step verification of historical records, analysis of transactions histories, and validation of real time entries to determine where breakdowns may have occurred. Follow-up actions were outlined to correct variances, reinforce procedural compliance, and strengthen traceability across locations BV 001 to BV 005, BW 001 to BW 004, BX 001 to BX 003.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while stationed at the Costa Sur warehouse, compiled and submitted a comprehensive inventory analysis report to Mr. Anthony Vega of Genera PR. The report integrated key operational metrics gathered from multiple warehouse zones and offered a strategic overview of current inventory conditions. It featured detailed evaluations of stock availability, cost fluctuations, recurring discrepancies, and items levels in relation to defined operational benchmarks. In addition, the report included performance-based metrics intended to assess inventory health and gauge the site’s readiness for future operational demands. The analysis covered storage zones ranging from BV 001 to BV 005, BW 001 to BW 004, BX 001 to BX 003, and AM 048 to AM 052, BB 001 to BB 100, CL 045 to CL 053.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led a Monday morning coordination meeting with Juan Vallejo, Giovanni Taffanelli, and key DCMC warehouse personnel to set operational priorities for the week ahead. The session focused on outlining immediate action items, confirming inventory control checkpoints, and aligning expectations for ongoing cycle counts and reconciliation efforts. Strategic goals were established to improve system synchronization, streamline task execution, and ensure timely reporting. The team also discussed anticipated challenges and designated responsible leads to track progress across critical warehouse fuctions.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-as part of ongoing reconciliation efforts, conducted a detailed inventory recount at the Costa Sur warehouse in collaboration with Mr. Hernan Machado from DCMC. The initiative focused on revalidating physical stock levels and investigating discrepancies found during the original cycle count. Emphasis was placed on verifying actual quantities against system-reported data to identify inconsistencies and confirm stock integrity. The process covered inventory zones BV 001 to BV 005, BW 001 to BW 004, BX 001 to BX 003 contributing to improved traceability, corrective documentation, and enhanced inventory accuracy.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document the Cambalache Power Plant Quality Control Plan Document Preface - Project Quality Program Division 2 - Site Work. This control plan review is to ensure project consistency, safety, compliance and reduce risks.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Phone call with Luis Duque from DCMC about the Preparation of the Divisions of the Cambalache Power Plant Quality Control Plan document.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review the Cambalache Power Plant BESS Program Quality Control Plan Plan Document Preface - Project Quality Program Division 2 - Site Work..
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails BESS_Cambalache: Meeting 5 - Cambalache Construction Weekly Minutes and Submittals RGE-0009.0 QA/QC PLAN on Procore.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform and creating a punch list (created items from 1 to item 12 out of 32 items)
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform and creating a punch list (created items from 12 to item 32 out of 32 items)
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Continued managing Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore app.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review. Siemens Chek-In Meeting: Peakers Costa Sur project Status follow-up and review of contract schedules. Participants from Genera (Jesus Cintron, German Nunez), CSA (Franklyn Colmenares) CDM PM (Carlos Palomares), Sargent and Lundy - (Mike Kuczynski) and DCMC - (Rafael Calderon, Abraham Velazquez, D'Alexzander González and Sheila Torres).
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 _ Internal meeting between Invoice review discussion. Meeting to discussed pre-intervention review process and new compliance review integration for invoice validation. DCMC participants (Glorimel Torrado, Gilberto Sucre).
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA / BESS Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team (Michael Grabstein and others), CDM Smith PM team (Gabriel Sepulveda), Sargent & Lundy ( (Mike Kuczynski) Miguel Del Valle, Nelson Rosado), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Gilberto Sucre, Foster Veazey, Paola Arroyo, Raissa Borges, Luis Roman, Frances Vallejo), Lemoine Procore (Lauren Wells).
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Pre-Intervention Review- Working with Black & Veatch Contract #217733_2024-G00207 and TO#5_Invoice# 00004_May 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Pending Insurance Documentation) Meeting with project management Team. Contract 106761 - The purpose of the meeting is to discuss: -Pending insurance documentation related to Supplier's and Owner's Worker's Compensation Insurance. - Proposed new Exhibit on contract to include specific labor cost. - Present Sample of the insurance documentation for reference. - Provide estimated dates for the insurance documentation to be updated and in place. Meeting participants TESLA (Michael Grabstein, Allin Luong and Jorge Quintana / Others), CSA (Franklyn Colmenares), , Genera (Kevin Futch), and DCMC (Rafael Calderon)
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CL045 to CL053 to begin the cycle counts.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AM048 to AM052
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AM048 to AM052
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AM048 to AM052
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AM048 to AM052
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AM048 to AM052
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BV 00 001 to BV 00 005 ; BW 00 001 to BW 00 004 ; BX 00 001 to BX 00 003 and other alternte locations
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BV 00 001 to BV 00 005 ; BW 00 001 to BW 00 004 ; BX 00 001 to BX 00 003 and other alternte locations
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BV 00 001 to BV 00 005 ; BW 00 001 to BW 00 004 ; BX 00 001 to BX 00 003 and other alternte locations.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Prepare the lists for locations BB 100 TO BB 144 at the Aguirre warehouse to start the cycle counts.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre- During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre- Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BB 100 TO BB 144 LIST # 1062/1061/1070/1071/1072/1077/1078
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre-Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BB 100 TO BB 144
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre- Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations BB 100 TO BB 144 RECOUNT LIST # 1073/1075/1082
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on investigating discrepancies in Recount Lists #1087 and 1088 from locations CL045 to CL053 for a total of 144 pcs.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels for the Recount # 1087 and 1088.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CL045 to CL053 Cycle Count List # 1083 and 1084.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – BESS Weekly Meeting hosted by Gabriel Perez (CDM Smith) including Design Team staff Mike Kuczynski (S&L), Lauren Wells (Lemoine), Gilberto Sucre, Rafael Calderon (DCMC), Rafael Pabon and Gabriel Perez (CDM Smith), German Nunez (Genera); discussing weekly open topics for the BESS Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, financials overview and upcoming constructions kick-off for different power plants.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339- Hurricane Maria Genera PR ¦ Document Control – Data Management /Vega Baja BESS DCMC Data Review & Process/Aguirre BESS Geotech Studies Data for Review & Process/RG Engr Peakers Daguao_Yabucoa_Jobos Kick Off Meeting Data _Summary Presentation for Review & Process/
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera PR ¦ Document Control – Data Management/ GEN 01 Aguirre BESS Continuation of all Geotech Study Data Review & Process/GEN 01 Download Meeting Minutes for Review and Process/GEN 01 Download Procurement Data for Review & Process
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Call for Procore Weekly Check-in with Theresa Perez (DCMC) and Laurel Wells (Lemoine) to get into the weekly progress and pending issues in the Procore Platform. Currently discussing the development of recently created project for Critical Components, and ongoing project management strategies and discussions to be formalized through the Procore platform.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 151 | 113.25 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Call with Carlos De Jesus (DCMC) to discuss the actual progress and status of Financial Tool for Procore, discussion for the integration of new features on scheduling and construction tracking, and the brainstorming for new concepts related to the tracking of lead time and issues of Critical Component on project schedules as stated in baseline schedule.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Peakers Weekly Meeting hosted by Rafael Pabon (CDM Smith), Design Team staff Miguel del Valle, Mike Kuzcinsky (S&L), Lauren Wells (Lemoine), Raissa Borges, Rafael Calderon, Abraham Velazquez (all DCMC), Enrique Laya and Manuelly Concepcion (CDM Smith), German Nunez and Fernando Ortiz (Genera); discussing weekly open topics for the Peakers Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others. Also, contractor's staging area definition for Peakers Equipment Supply in Aguirre.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Reviewed the design team’s Issued for Bid (IFB) Specifications Package and performed validation activities within a controlled project environment to verify the uploading, review, and publication workflow for specification books in the Procore platform. Confirmed document organization, version control, and accessibility to support effective project management and the submittals review process. Verified that the designer is required to upload the Issued for Construction (IFC) specifications package to ensure alignment with approved project documentation, proper coordination, and compliance with established document control procedures.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.25 |  | 151 | 339.75 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Weekly QA/QC on the execution of project management through Procore: track contractor's activities at the Submittals and RFIs tools, measuring contractor's time of response on open items, deliverables of specs and drawings by the design team and the implementation of workflow templates for the Specifications tool having the designer as the uploader, while PMO review and approves (publish).
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. I review pending invoices in the tracker and identified past due to be completed this week.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.75 |  | 149 | 558.75 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Pre-Intervention Review Sargent & Lundy Puerto Rico, LLC., TO#1, Invoice #18343723_Feb2025. Sent RFI requesting deliverables. Start and complete compliance review with link provided by vendor. Prepare final package and invoice for Jesús Cintrón (Genera) signature. Send the invoice for signature and update excel Pre-Intervention tracker.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review schedule of values for CDM with Manuely Concepción (CDM) since there was an error on the TO amount. There was missing the amendment that increase the budget. I update the document in PDF and the excel, prepare the new final package and request CPA for CDM_TO1_Feb2025_90235516.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 ¦ Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Paul Browne, Eisha Mercader, Esther Rohena, Glorimel Torrado and Cynthia Ortíz. Also, Shellsea Maysonet (SM Consulting); and from Genera: María Sánchez (online) and Alejandro Maymí, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines. This meeting was held at Genera Headquarters.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Financials Meeting with Lauren Kennedy from Procore and DCMC participants: Rafael Calderón, Glorimel Torrado and Johanna Díaz (SM Consulting). In this meeting we discuss about the platform views for pre intervention, invoices, PW obligation, and others. We will continue with recurrent meetings to complete this task.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - coordinate and organize information for Genera & DCMC meeting at Genera Office. Today I was presenting Pre Intervention process and contracts update.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Informal discussion with Rafael Calderón (DCMC) about information discussed in previous meeting regarding CERES heads up on tariffs modifications.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey. In the meeting was the Genera PR Team: Jesus Cintron, Joaquin A Quinoy, Ricardo Pallens, Maria Sanchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczinsky and Nelson Rosado. The meeting was about the Bess Project status.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Edit a project timeline in Canva for the BESS works in Vega Baja to outline tasks and guide the project from conception to completion.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Weekly Corporate Affairs Meeting with the Genera PR: Jorge Bracero, Ivan Baez Santiago and Rafael Baez Santiago. During this meeting, we shared and agreed on tasks related to the community meeting in Vega Baja, which will take place on Monday, June 23 at 6:00 PM. We reviewed the presentation and communication materials, discussed the week’s pending matters, and provided an update on our ongoing work.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Kroma and Genera Weekly Meeting in the meeting was the Genera's PR Team: Ivan Baez, Jorge Bracero and Rafael Rodriguez. In the meeting was the Kroma team: Amarilys Torres and Victoria Flores. The meeting was focused on addressing specific updates related to the BESS and Peakers Project, including reviewing the latest developments and pending action items. It also included discussions on Genera PR’s social media monitoring efforts to better understand public engagement and sentiment. In addition, the team reviewed key narratives circulating in the media to assess how ongoing coverage could impact the project’s visibility and stakeholder perception.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Meeting with the Genera PR team and Jorge Bracero, the focus is on collaboratively refining the BESS and Peakers website www.genera-pr.com/bess_peakers This includes editing the written content to ensure it is clear, informative, and aligned with the project's communication goals. Additionally, work on the reviews the site’s design elements to enhance visual appeal and usability, making sure it resonates with the target audience. Content updates—such as project milestones, community engagement information, or event announcements—are discussed and implemented. Throughout the session, there’s an emphasis on aligning the site’s tone, message, and functionality with the broader objectives of Genera PR and the BESS initiative.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Edit a document containing updates and corrections for the Genera PR website sections on BESS and Peakers.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Continue review Cambalache Power Plant BESS Program Quality Control Plan for the creation of the DCMC Quality Control Plan to implement in the 4339_9510 BESS_Cambalache project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Reviewing the Minimum Qualification Requirements BESS Aguirre 4900 RG Engineering documentation which include: Proposal Submission Requirements Checklist; Company Cover Page and Cover Letter; Qualifications and Experience; Authorization for Background and/or Financial Information; Certifications Affidavit; S/M/WB/LS Forms; Buy American Act Certification; Technical Proposal; Price Proposal; Draft Contract; among other documentation.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Review Project drawings (ESK9-0002 PRELIMINARY BESS ARRANGEMENT PLAN; EGP-CSK-017 AGUIRRE LIMITS OF GEOPHYSICAL SURVEY PLAN; EPG-005-8 AGUIRRE SITE GEOTECHNICAL INVESTIGATION TEST LOCATION PLAN; EGP-CSK-014 AGUIRRE LIMITS OF TOPOGRAPHIC SURVEY) Start reviewing MQR BESS Aguirre 4900 RGE documentation.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with the Genera EHS team (Magdalena Maldonado, Armando Cervoni, Luis Felipe Torres and Richie Correa) to take the Environmental Programs Orientation for Contractor of the Costa Sur site.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with Jean P. Menay DCMC Safety Manager to introduce the DCMC team (Carlos Rodriguez, Carlos Bayron y Luis Echevarría) and Genera's EHS staff (Ramon Quiñonez, Osvaldo de Jesus, Magdalena Maldonado, Armando Cervoni). Safety issues were discussed to maintain project execution. Review of the Costa Sur Plant Emergency Response & Action Plan.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on comments for Procore requirements considering procurement, contract, resources with cost load, minutes, schedule for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on comments in drawings of site considering procurement, contract, and schedule for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on Peaker's comment with master schedule for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on comments for Procore requirements considering procurement, contract, scurve graph and schedule columns formats for employee Carlos Rodriguez (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Review Cambalache Power Plant BESS Program Quality Control Plan for the creation of the DCMC Quality Control Plan to implement in the 4339_9510 BESS_Cambalache project.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Rafel Pabon (CDM Smith), Luis Roman (DCMC), Paola Arroyo (Genera), Jorge Bracero (Genera), Lauren Wells (Lemoine), Foster Veazey (Lemoine), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Franklyn Colmenares (CDM Smith), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Sheila Torres (DCMC).
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing and addressing BESS and Peakers projects weekly report comments from Frances Vallejo (DCMC) to deliver a more completed and clear information.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Sheila Torres (DCMC), Paola Arroyo (DCMC), Lauren Wells, (Lemoine)
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Collecting and structuring BESS and Peakers projects updates data on Power Bi for the One Pager weekly report to be send to Genera which is essential for tracking project progress and make informed decisions by providing a summarized account of project's activities, progress, challenges, and financial report details.
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits and travel from Genera offices and facilities in the south part of the island
2025-06-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 111.3 | 0.7 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Traveled to Guayanilla P.R. from cll Hidalgo San Juan P.R. for meeting with Osvaldo de Jesus, Richie Cintron, Ramon Quinones, Luis F Torres (GENERA) and Luis Echevaria, Rafael Berrera (DCMC) about Costa Sur Genera Project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 1150 | 1150 | 1150 | Yes | 146794 |  | J Arroyo Enterprise - Installation of electrical power for trailers - Humacao
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 1150 | 1150 | 1150 | Yes | 146794 |  | J Arroyo Enterprise - Installation of electrical power for trailers - Yabucoa
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Mark Merritt, Mike Merritt, Gilberto Sucre, Jack Darnall, Lauren Wells and Ada Diaz, DCMC. Discussed update on project, job offers, PROCORE workshop schedule, logistics, other interviews, trailer set-up, safety, schedule for locations, LEAN, program management plan update.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal discussions with counterparts on how to best set up individual project staffing and priorities. Attended meeting Gilberto Sucre DCMC Frances Vallejo Rosich DCMC
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 225 | 787.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended meetings for the Peaker project. Reviewed contractors RFI and notes for response to the RFP for the COSTA SUR Peaker project. Attendees: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Reviewed internal correspondence, caught up on and responded to comments and inquiries for the Peaker projects. made notes and preparation for the week's meetings.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria E-mail correspondence review and responses for BESS Program.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Organized and schedule recurring Project Management weekly reporting & Coordination of Site Managers Update Meeting on Friday in coordination with Raissa Borges DCMC.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RFC Meeting Costa Sur with RGE. Reviewed pending items to complete contract package; Geo-piers final design, Legal items including tariffs issues $ 100k for rebar, demolition Phase II execution not by Homeca. Meeting with Gabriel Perez CDM Smith, Carlos Hernandez - ARG Ceres and Eduardo Rivera & Gilberto Sucre - DCMC
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Weekly Construction Meeting. Led by Andres Concepcion reviewed and updated on construction project progress and design including Structural steel VE design concept by RGE pending resubmission. RFI's and Submittals were discussed. Attendees: Gilberto Sucre - DCMC Gabriel Perez - CDM Smith Robert Molner - Sargent & Lundy Jose Segarra - RG Engineering.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting main topics covered: Staffing Update and New Hires, Project Timeline & Procurement, Financial Controls & Procore Integration, Construction Progress, System Usage and Documentation. DCMC Participation: Mark Merritt, Mike Merritt, Barry Scanlon, Gilberto Sucre, Lauren Wells, Jack Darnell, Ada Diaz, and Anneilia Holton.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria VEGA BAJA Weekly Construction Meeting - Phase II Installation Eduardo Rivera DCMC led the meeting to update Construction Project Status including: Contract Agreement date, Notice to Proceed date, Site logistics, Demo Phase, Use of Procore, RFI's, Submittals, Schedule of values, safety workshop and site visits. Gabriel Perez - CDM Smith Franklyn Colmenares - CSA Group Carlos Hernandez - ARG Ceres Wilfredo Sierra - Sargent & Lundy Erik Rocher - Genera Gilberto Sucre - DCMC
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS DESIGN Drawings - Meeting with Sargent & Lundy to discussed design status by Sites, Specific needs per project as well as scheduling Vega Baja Civil & Site Meeting with priorities on Tuesday June 24 and for Aguirre Revised Battery Pack Foundation Platform Design for Thursday June 26. Both meetings to be at Sargent & Lundy's office in Santurce with the respective construction Contractors. Gabriel Perez & Enrique Laya - CDM Smith Mike Kuczynski & Robert Molner - Sargent & Lundy Gilberto Sucre - DCMC
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 – Met with Jose Molina Torres (Genera) to introduce Genera’s Continuous Improvement (Lean) initiative and discuss maintenance department challenges across two plants. Topics included standardizing processes, improving communication, and morale. Identified opportunity to use Failure Modes and Effects Analysis (FMEA) for risk assessment and team problem-solving. Aligned on next steps: share FMEA resources and schedule a facilitated session to address equipment downtime and active service projects to Unit 4 and Unit 7 at the two northern region facilities.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review and respondence of correspondences for Procore items.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Procore Weekly Q&A with Luis Roman (DCMC), Theresa Perez (DCMC), Paola Arroyo (DCMC), Johanna Diaz (SMC), Rafael Pabon (CDM Smith).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on preparing for the weekly Procore Q&A session for today.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore distribution lists per project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financial settings for Budgets and permissions.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items requested by Lauren Kennedy (Procore).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Permission profiles for Procore for Financial tools for review with Lauren Kennedy (Procore).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on more correspondence items with Procore for reviewing items sent in by Lauren Kennedy (Procore) for financials.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore permissions matrix for financials.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Johanna Diaz (SMC) to discuss PW folder structure and processes around formulation, procurement and Grants Management.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt (DCMC) to discuss program staffing and overall program goals.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed pending items for the Genera Connect Financial Tracker and Timesheets platforms in preparation for a discussion with José Ralat and Esther Rohena from DCMC, aiming to ensure alignment on upcoming improvements. During the discussion, clarified requirements for enhancements to the Genera Connect platform focused on capturing additional KPIs to improve transparency, reporting accuracy, and decision-making capabilities. Additionally, uploaded Genera PR HQ employee profile data to the Genera Connect system to support accurate tracking and reporting of work hours associated with federally funded projects.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Yabucoa Site working Session with Gabriel Morales (DCMC) support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities. Review the Genera Safety Manual for contractors.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Provided EHS program orientation and safety compliance briefing to Dueñas Trailers staff member Carlos Manuel Montañez, covering Genera’s environmental, health, and safety requirements applicable to project operations. The activity supported contractor awareness, compliance with site safety protocols, and alignment with Genera’s EHS standards for work performed under the Costa Sur project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continuing support installation trailers offices on sit, review safety rules in this process and review the Genera Safety Manual for contractors this action requested by Victor Rodriguez (Genera).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 6300 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Weekly Contract discussions with Rafael Calderón and Glorimel Torrado (DCMC) on Generation Fleet (BESS & Peaker projects) contracts. Discussed ongoing change orders, task orders, and contract amendments, and aligned on key issues related to scope, invoicing, and compliance. These meetings serve to ensure consistent coordination between legal, procurement, and project management teams and to support the timely and efficient execution of all contractual obligations tied to the generation portfolio.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 6299 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Contracts No. 108808 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4634 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore app meeting with Homeca punch list and closing.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with Luma Energy team (Reniel Quiles and Eliezer Medina), Hub Advance team (Abraham Rios and Erica G. Colon), Genera (Kelvin Vega) and DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron and Luis Echevarría) for removal or relocation of telecom lines in the construction area, control room visit for identification of future telecom connections to main hub at Costa Sur.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Conducted a detailed review of Attachment J – Health, Safety, and Environmental (HSE) Policies to ensure contractor compliance with all applicable regulations and internal safety protocols. Assessed alignment with project-specific safety requirements, environmental guidelines, and regulatory obligations. Recommendations were noted for improvement where necessary to reinforce safe work practices and adherence to standards.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with Luma Energy team (Reniel Quiles and Eliezer Medina), Hub Advance team (Abraham Rios and Erica G. Colon), Genera (Kelvin Vega) and DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron and Luis Echevarría) for removal or relocation of telecom lines in the construction area, control room visit for identification of future telecom connections to main hub at COSTA SUR.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Reviewing Costa Sur Drawings on demolition Appendix D comparing existing utilities and RFP proposal for subcontractor works. Works on identifying utilities will be responsibility of the subcontractor to be hired for removal and foundation construction.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue supervising the installation of the Fiberglass Ceiling and all the lamps (interior and exterior) of the Yabucoa site mobile office interior by the team of SA Facias and Duenas Trailer to provide a centralized hub for operations to ensure materials, personnel, and equipment are effectively managed throughout the life cycle of the project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Install the fiberglass ceiling of the 16' x 40' office at the Yabucoa site with the team of SA Facias and Duenas Trailer to provide a centralized hub for operations to ensure materials, personnel, and equipment are effectively managed throughout the life cycle of the project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review the Attachment J - HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES to ensure that the contractor complies with the regulations and policies. Also continue review with RFP-4899 Minimum Qualification Requirements by RG Engineering document
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with Luma Energy team (Reniel Quiles and Eliezer Medina), Hub Advance team (Abraham Rios and Erica G. Colon), Genera (Kelvin Vega) and DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron and Luis Echevarría) for removal or relocation of telecom lines in the construction area, control room visit for identification of future telecom connections to main hub at Costa Sur.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with José M. López, Harry Del Valle and Jean Pierre Menay (DCMC) to discuss the office trailer contractor punch list items. A punch list with pictures was built using the PROCORE platform and distributed via email to Harry Del Valle, Jean Pierre Menay, and Gilberto Sucre (DCMC).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A Walk through was done with José M. López, and Carlos López (DCMC) to identify existing fire protection lines rout and possible issues during the construction process. It was decided to submit and RFI to Sargent & Lundy for these effects.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Reading and review the Checklist for Critical Movements Topics: The ground must be firm and stable. Unless the crane is on concrete, wedges should be used under the jacks and the tracks must be on mats. The chassis of the crane or the base of the strut must be completely level. The weight of the load must be determined accurately. The center of gravity of the load must be located and the crane hook must be placed directly over it. The radius must be measured accurately. The length of the strut must be determined accurately. The angle of the strut, if necessary to determine the crane's capacity, must be determined accurately; do not rely on the reading of the strut angle indicator. The effect of the wind must be taken into account and consider postponing the movement if its speed reaches 20 MPH. And definitely postpone the movement if the speed is 30 MPH or more. The rigging must be balanced. All movements should be made as smoothly as possible.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Harry Del Valle and Jean Pierre Menay (DCMC) to discuss the office trailer contractor punch list items. A punch list with pictures was built using the PROCORE platform and distributed via email to Carlos López, Harry Del Valle, Jean Pierre Menay, and Gilberto Sucre (DCMC).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Gilberto Sucre and Jean-Pierre Menay (DCMC) to discuss the office trailer contractor's punch list items and pending office supplies.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Carlos López and Luis Moctezuma (DCMC) to identify existing fire protection line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, and Luis Moctezuma(DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on the Review and make corrections on Quality Assurance & Control provided by Email by Luis Duque (DCMC) to ensure that all aspects of the project are executed correctly, safely, and within set guidelines.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and make corrections on Quality Assurance & Control provided by Email by Luis Duque (DCMC).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordinate with Gabriel Morales (DCMC), Jean Pierre Menay (DCMC) Office trailers interior finish by Duenas Trailer.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on the Review and make corrections on Quality Assurance & Control provided by Email by Luis Duque (DCMC) to ensure the project meet safety standards, regulatory compliance, and quality benchmarks.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Discussed with Gilberto Sucre (DCMC) status of Office Trailers in project sites, materials missing, connection of utilities proposals
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Trailers update Meeting with Jean Pierre Menay (DCMC). Discussed status of Office trailer in Yabucoa Gas Turbine Plant.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: Electrical work safety program to identify potential hazards, enforce safe practices, and reduce the risk of accidents for implementation in the Cambalache project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: fall protection program to reduce the risk of falls and creating a safer work environment for implementation in the Cambalache project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Completed Cambalache Construction weekly meeting agenda and prepared action items to follow up on meeting with Contractor (RG Engineering) and Designr (Sargent and Lundy)
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project submittal RGE-00009 QA/QC Plan. Reviewed documentation and planned a review process with Luis Duque and Luis Damudt (DCMC Partners).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared Scope of Work alternatives for the Cambalache Gas Storage enclosure, evaluated a Value Engineering proposal and shared with designer (Sargent & Lundy - Mike Kuczynski).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted and led Cambalache Construction Weekly meeting to follow up on weekly project status and coordination on action items with the contractor (RG Engineering - Jose Segarra), Designer (Sargent and Lundy - Robert Molner) and Owner ( GeneraPR - Herminio Arroyo) and DCMC Team (Gilberto Sucre, Luis Damudt, Luis Duque, Jorge Mercado)
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met on the S & L / CDM Smith Weekly BESS Drawings Meeting with Mike Kuczynski, Robert Molner (Sargent and Lundy), Gabriel Perez, Enrique Laya (CDM Smith), Gilberto Sucre (DCMC) for design updates and progress review.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received Sargent and Lundy design team on site (Beverlyn Barreto). a Walkthrough was conducted to validate mechanical piping connection points and complete the Design Drawings.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project construction weekly meeting Phase II. ARFG/CERES Carlos Hernandez, and Ida Ramirez; DCMC Jaime Pesquera, Gilberto Soto, Gilberto Sucre and Eduardo Rivera, CDM Smith Nelson Soler, and Gabriel Perez Sepulveda, CSA Franklyn Colmenares, S&L Robert Molner - Meeting to start construction meeting for second phase of Vega Baja BESS project and coordinate documents to be submitted for new contractor.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Preparing agenda for 11am meeting with ARG/CERES contractor.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project weekly meeting to review project status. Homeca Eduardo Ramos, and Carirma Sanchez; DCMC Jaime Pesquera, Gilberto Soto, and Eduardo Rivera, CDM Smith Nelson Soler, Enrique Laya and Manuely Concepcion. Meeting to discuss punch list items and project closing.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Preparing minutes meeting for Homeca construction meeting and ARG/CERES construction meeting. Reviewing Homeca change order request for Vega Baja project and certification #3.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Preparing agenda for 9am meeting with Homeca contractor.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a focused inventory recount at the Palo Seco warehouse in coordination with Mr. Giovani Taffanelli from DCMC. The primary objective was to reverify inventory data by conducting a detailed recount of previously reviewed areas to confirm physical stock accuracy and identify any remaining discrepancies. The effort concentrated on bin-level validation, item classification accuracy, and storage compliance across designated locations. Specific zones included in the recount were CL 054 through CL 060 and AJ 056 through AJ 060. All findings were documented to support inventory integrity and provide a clear baseline for subsequent reconciliation phases.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed operational planning to support upcoming cycle count activities at the Palo Seco warehouse, with targeted focus on locations CL 054 through CL 060 and AJ 056 through AJ 060. Preparatory efforts included validating inventory records within zones, confirming item placement consistency, and reviewing recent transactions for potential discrepancies. Coordination with Mr. Giovanni Taffanelli from DCMC was conducted to establish the sequencing of count phases, assign zone, and ensure that all related worksheets were aligned with the system master data. Additional steps included physical layout verification, correction of mapping irregularities, and staging of materials to facilitate efficient access during execution.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out cycle count preparation and execution efforts within designated inventory zones CL 054 through CL 060 and AJ 056 through AJ 060 as part of a targeted initiative to validate physical inventory conditions. The process was structure to enhance the accuracy of on-hand balances and ensure consistency between system data and warehouse reality. Activities included confirming item master alignment, reviewing bi-level stock integrity, and assessing labeling compliance. Attention was placed on identifying irregularities such as misplaced or misclassified items and validating stock movement history. These efforts played a key role in supporting data accuracy, optimizing warehouse visibility, and reinforcing the operational reliability of the inventory management system.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted variance investigation at the Palo Seco warehouse to analyze recurring discrepancies between physical inventory counts and system reported quantities. The objective was to identify root causes impacting data accuracy by examining item movement history, stock adjustment, and catalog inconsistencies across locations CL 054 through CL 060 and AJ 056 through AJ 060. The review included a detailed trace of item transactions, verification of audit trails, and analysis of system records to detect potential failures or data entry errors contributing to the variances observed.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a morning briefing with warehouse leads Juan Vallejo, Hernan Machado, Giovanni Taffanelli and Milton Flores from DCMC, to coordinate upcoming cycle count activities across all storage locations. The session emphasized the importance of pre-count preparation, including location validation, bin consolidation, and clearance of obsolete or misplaced inventory. Key priorities discussed included ensuring data accuracy and verifying that all count sheets reflect current physical layouts. The meeting concluded with a review of expected timelines and reinforcement of compliance with standard counting protocols to maintain inventory integrity and audit readiness.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco warehouse, led the preparation of a detailed inventory performance report for Mr. Anthony Vega of Genera PR. The report compiled critical operational data from active warehouse zones, focusing on key inventory control metrics such as catalog ID accuracy, stock valuation discrepancies, and trend-based variance analysis. Specific attention was given to documenting physical mismatches, verifying compliance with defined stock level policies, and verifying systemic inefficiencies impacting warehouse performance. Visual dashboard and summary insights were incorporated to enhance data transparency and support informed decission-making. The assessment included inventory zones CL 054 to CL 060, AJ 056 to AJ 060, AN 001 to AN 013, CA 001 to CA 006, CB 001 to CB 006, CC 001 to CC 006, CD 001 to CD 003, CE 001 to CE 005, CF 001 to CF 004, BB 100 to BB 144, BD 001 to BD 045.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Based on the develop list of critical components, verified the status of items currently in Pre-Shipping and Shipping stages. Confirmed component descriptions, delivery locations, and estimated dates directly with vendors to ensure up-to-date tracking and support coordination efforts aligned with project needs.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Site walkthrough to assess potential site coordination efforts with Andres Concepcion, Jorge Alexis Mercado DCMC, Herminio Arroyo Genera PR and Carlos A Nieves, Bevelyn Barreto from Sargent and Lundy.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 – Hurricane Maria. 4339_9510 Review and BESS document and compare with the Sargent & Lundy Technical Specification Quality Control Manual and that of RG Engineering Inc. submitted by José Segarra of RGE.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Construction Weekly update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Phone call with Harry Del Valle and Luis Duque (DCMC) about the Cambalache Power Plant Quality Control Plan document about the Preparation of the Divisions and other details of the Cambalache Power Plant Quality Control Plan document.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a PHASE II meeting with ARG Ceres with Carlos Hernandez , Ida Ramirez, Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith), Gilberto Soto (DCMC) to address project issues, improve communication across the site team and discussed project timeline.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly construction meeting with Carirma Sanchez, Eduardo Ramos (Homeca Recyclers ) Nelson Soler (CDM-Smith), and Gilberto Soto and Eduardo Rivera(DCMC) and went over Project Documents Overview and analyzing documents status in the Procore platform and all the punch list items created yesterday, the closed items and the open items like (item #30, item #31, item #32) that needed their attention.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 2 | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore app. Meeting with ARG Carlos Hernandez’s, and Nelson Soler (CDM Smith) documents and safety plan.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Cash Flow) Meeting with project management Team CDM - Carlos Palomares and DCMC Gilberto Sucre. Contract 106761 - Reviewing current Tesla budget and cash flow in relation to equipment and supply labors and field construction execution, in order to align project actual balance.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 PMO Contract Management catchup meeting - Meeting to discussed contract management status base on project execution. Reviewing change orders status and issues on construction tasks. Participants Frances Vallejo DCMC and Rafael Calderon DCMC
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Review CDM Smith Invoice #90236431 for TO#11 March 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#1_Invoice# PRIN0007609_Oct 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1108, 1109, 1110, 1111 and 1112 from locations CL054 to CL060 and AJ056 to AJ060 for a total of 264 pcs.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AN001 to AN013
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AN001 to AN013
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AN001 to AN013
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AN001 to AN013
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations An001 to AN013
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations CA 00 001 al CA 00 006; CB 00 001 al CB 00 006; CC 00 001 al CC 00 006; CD 00 001 al CD 00 003; CE 00 001 al CE 00 005 y CF 00 001 al CF 00 004 .
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CA 00 001 al CA 00 006; CB 00 001 al CB 00 006; CC 00 001 al CC 00 006; CD 00 001 al CD 00 003; CE 00 001 al CE 00 005 y CF 00 001 al CF 00 004
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations CA 00 001 al CA 00 006; CB 00 001 al CB 00 006; CC 00 001 al CC 00 006; CD 00 001 al CD 00 003; CE 00 001 al CE 00 005 y CF 00 001 al CF 00 004 .
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BB 100 TO BB 144 AND BD 001 TO BD 025
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BB 100 TO BB 144 & BD 001 TO BD 025 LIST # 1085/1093/1094
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria-Aguirre- Prepare the lists for locations BB 100 TO BB 144 & BD 001 TO BD 025 at the Aguirre warehouse to start the cycle counts.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre- During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations BB 100 TO BB 144 & BD 001 TO BD 025 RECOUNT LIST # 1089/1098
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CL054 to CL060 and AJ056 to AJ060 Cycle Count List #1099, 1104, 1105 and 1103.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CL054 to CL060 and AJ056 to AJ060 to begin the cycle counts.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Cambalache Power Plant Weekly Meeting hosted by Andres Concepcion (DCMC) with representation from the Contractor RGE with Jose Robles, Jose Segarra, Vernadee Ortiz and Xiomara Perez, from the Design Team (S&L) Mike Kuczynski, Ivette Miranda, Wilfredo Sierra and Alan Figueroa, and from DCMC Gilberto Sucre, Luis Duque, Luis Damudt, and Jean Menay. Meeting to continue the discussion of open and pending items for the beginning of construction course: submittals and RFIs, contractor's current responsibilities prior to NTP and Design Team feedback and commentaries on the upcoming constructions starting tasks.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/ Costa Sur Peakers Data Revie w & Process/GEN 01 BESS & Peakers Interconnection Studies MM Data for Review & Process/BESS & Peakers Community Outreach Folder Verification of Permissions/GEN 01 BESS & Peakers Permitting Weekly MM Review & Process/ Coordination with Lauren Wells DCMC_Rafael Pabon CDM_Paola Arroyo DCMC_Luis Roman DCMC for Incoming Data
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/GEN 01 Technical Data Download for Review & Process/GEN 01 Download Teams Weekly Meeting Minutes for Review & Process/Costa Sur Peakers Date Review & Process
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – QA/QC on the current delivery of pending items in the Vega Baja Power Plant project prior to the implementation of project management strategies to comply with the response time of tems involving technical analysis and deep review.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Call with Rafael Pabon (CDM Smith) to discuss the agenda and purpose of Peakers Equipment Supply Meeting with Sargent & Lundy and awarded contractor RGE.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Specification available for Quality Control inside the projects to determine proper review requirements for contractor's submissions related to Quality Control Plan.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Call with the Vega Baja team staff Nelson Soler (CDM Smith) and Jaime Pesquera (DCMC) to track the activity of Contractor inside the Project Management Tools such as document uploading, proper items classification and overseeing the site progress inside the platform.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Q&A session hosted by Lauren Wells (Lemoine), and joined by Theresa Perez (DCMC) and Johanna Diaz (SMC) to discuss in a weekly basis Procore hot topics and pending issues: Discussed the implementation of Financial Tool related to the budgeting, tracking, invoicing and document control inside the Financial Tool.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting for the Peakers Equipment Supply with awarded contractor RGE and its representatives Jose Robles, Jose Segarra and Xiomara Perez. Also, from CDM Smith Rafael Pabon as the host, and included part of the Design Team representatives with Ivette Miranda, and German Nunez from Genera. Purpose of meeting was to discuss with contractor and owner the proper execution of document control and project communications through the established channels and the course of items for review and distribution. Also, discussing the option to manage the Equipment Distribution for the 3 sites (Yabucoa, Jobos, Daguao) using only one Procore project database.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform QA/QC for multiple Project Management Tools for the Vega Baja Power Plant project inside the Procore Platform: review current Drawing Plans Sets, creation and tracking of Punchlist and Punchlist items, and the review of contractual requirements for the timing of response based on user's responsibilities.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 4 |  | 149 | 596 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 - Pre-Intervention Review for CPM- PRNI007372_TO1_Sept2024. Review RFI responses and Deliverables to complete the compliance tool. Also segregate CC in lines that were pending to divide. Prepare final package and PDF sent requesting Jesús Cintrón (Genera) signature.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Internal DCMC Contract management weekly meeting with Rafael Calderón and Sheila Torres to discuss advances and pending action items on change orders and contracts.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Manage updates to the BESS and Peakers sections of the Genera website, including editing content and materials. Coordinate with the Genera team, Jorge Bracero, and Alex Valdés Díaz to refine visual design and layout
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Practice and finalize the editing of the PowerPoint presentation for the BESS community meeting in Vega Baja, scheduled for June 23.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Prepare a document summarizing the current status of the BESS project in Vega Baja. The report includes the progress made, upcoming steps, and relevant data related to the work carried out on site. The report was sent to the Genera team and Rafael Rodríguez Ema, who will be using the information to create posts targeted at the Vega Baja communities through Genera’s social media channels.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Work in the upcoming community meeting in Vega Baja by reviewing all the materials that will be used that day to ensure they are accurate, up to date, and sufficient in quantity. Complete the final edits on the presentation, including correcting grammar, refining formatting, adding visuals to enhance clarity, saving final versions in both editable and PDF formats and confirm the venue.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Reach out to other key members of the Vega Baja community who have not yet been contacted, with the goal of expanding participation in the community meeting scheduled for Monday, June 23rd, as part of the BESS project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Meeting with Genera PR representatives Jorge Bracero and Iván Báez Santiago to align efforts on developing collaborative agreements with nonprofit organizations operating in areas where BESS and peaker units are located.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Cambalache Power Plant BESS RGE Quality Control Plan, Division 2 - Site Work, Concrete Curing , Excavation and Fills Preparation of Ground for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Reviewing the Project Request For Information (RFI) about: Rule 141Information fir Aguirre; Updated Aguirre Boring Map; Site Plan-Aguirre; Priority Zones - Topographic and Geophysical Surveys; Rock Coring Requirement; Additional Boring at Aguirre Site (Possible Debris); Battery Slab Separation; Battery Slabs Section, Drainage Detail.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with José M López, Harry Del Valle and Jean Pierre Menay (DCMC) to discuss the office trailer contractor punch list items. A punch list with pictures was built using the PROCORE platform and distributed via email to Harry Del Valle, Jean Pierre Menay, and Gilberto Sucre (DCMC).
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 134 | 201 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A Walk through was done with José M. López, and Luis Moctezuma (DCMC) to identify existing fire protection lines route and possible issues during the construction process. It was decided to submit and RFI to Sargent & Lundy for these effects.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with Luma Energy team (Reniel Quiles and Eliezer Medina), Hub Advance team (Abraham Rios and Erica G. Colon), Genera (Kelvin Vega) and DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron and Luis Echevarría) for removal or relocation of telecom lines in the construction area, control room visit for identification of future telecom connections to main hub at Costa Sur.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria Continue review site drawing Appendix D, contractor RG ENGINEERING, INC. RFP-4899 Proposal and schedule concrete specification information about at Costa Sur Facilities and review new Procore project information.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked with employee (CDM Smith) Carlos Palomares on preliminary planning schedule in demolition and mechanical works to ensure safety, efficiency, and compliance with regulations for Genera considering preliminary planning process for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked with employee (CDM Smith) Carlos Palomares on preliminary schedule for Genera. Schedule will consider the construction issues by reviewing updated drawings with street details, underground utilities and planning process for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache-TEAMS meeting related to Cambalache BESS - Construction Weekly with pending steps for sign contract, status of the temporary facilities, special instructions before start in site of projects, pending submittals and status of starting initial construction process with DCMC employees Andres Concepcion, Luis Damudt, Luis Duque, employees of RGE Jose Segarra, Xiomara Pérez Álvarez, CDM Smith employee Gabriel Perez, employees of Sargent and Lundy Dean Ennes due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on TEAMS meeting related to Costa Sur RFC BESS - Construction Weekly with pending steps for finish design and negotiation and proponent company team with DCMC employees Gilberto Sucre (DCMC), employees of RGE Jose Segarra, Xiomara Pérez Álvarez, CDM Smith employee Gabriel Perez, employees of Sargent and Lundy Dean Ennes due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on teams meeting related to verify project submittals in ball in court pending, pending actions from designer Sargent and Lundy and contractor RGE with DCMC employees Andres Concepcion, Luis Roman, Luis Damudt, Luis Duque and Jorge Mercado due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Cambalache Power Plant BESS RGE Quality Control Plan, Division 2 - Site Work, Fill material, Slope, Drainage and Terracing for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 122 | 366 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue collecting and gathering information from Procurement, Grants, Invoicing and other areas for the development of the financial process diagram to ensure efficient resource allocation, cost control, project profitability assessment, risk mitigation, and strategic decision-making.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting "Process Diagram for Projects Financials" with Manuelly Concepción (CDM Smith) and Cynthia Ortiz (DCMC) to continue discussing and developing financial flowchart to be implemented in Procore.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue developing the financial process structure as a flowchart using the Visio tool for the Genera Projects BESS & Peakers. Task requested by Mark Merritt (DCMC) and Lauren Wells (Lemoine) to ensure effective alignment with Procore's financial tools.
2025-06-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 46.69 | 0.7 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continuing support installation trailers offices in site and review the Genera Safety Manual for contractors.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on troubleshooting distribution list errors where users were showing up with out being added.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended Bess and Peakers procurement meeting. Discussed the status of all the equipment that has been ordered, to be ordered and delivery dates for each project meeting participants Gilberto Sucre DCMC Frances Vallejo Rosich DCMC German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended meeting on Genera PR/RGE PKR Commercial/Schedule Discussion discussed the coordination of the turbines and all ancillary associated equipment and deliverables Attendees: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Zea, Eduardo GE Vernova Chapman, David GE Vernova.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal review of days meeting notes and comments, updated my notes and agenda for the weeks upcoming meetings
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Reviewed email correspondence from Genera and Sargent and Lundy engineering, updated my calendar for upcoming events and meetings for the Peaker projects. Internal paperwork, reviewed notes and comments from meetings.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluation of Engineering Invoices approval process and coordination with Jesus Cintron - Genera, Rafael Pabon - CDM Smith and Rafael Calderon - DCMC
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Quality Program Implementation and Review of RGE Quality Program meeting with Harry Del Valle, Andres Concepcion and Luis Duque - DCMC Employees.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Legal Review with Genera Legal Counsel and Management to discuss: * Tariffs Clause to ARG Ceres Contract for Vega Baja Installation Project. * Termination Letter to Homeca Recycling, Final Completion date, Punchlist and final contract pricing.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria ARG Ceres RFI Response to Sitework & Demolition for Phase II, and coordination with Eduardo Rivera - DCMC
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 225 | 393.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Final Contract Documents Review with Jose Robles - RG Engineering, Francisco Feliu - Genera, Gabriel Perez - CDM Smith, Sheila Torres - DCMC for Cambalache, Costa Sur and Aguirre.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Project Updates Discussions with Site Managers - DCMC Aguirre - Jose Lopez Weekly Construction Meeting, Mobilization, Access, Road Improvements Design Status. Vega Baja - Eduardo Rivera - Demobilization Letter, Punch List Status, MPT Rigging, Power Outage and IFC Distribution to contractor. Aguirre - Andres Concepcion - Gas Storage Options, Temporary Warehouse, Permitting Coordination and IFC Drawings to contractors. Carlos Rodriguez - Coordination of weekly Construction Drawings & Site Visits
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review Procore Budget Items for SOP's and authorizations. Lauren Wells, Esther Rohena, Johanna Diaz and Gilberto Sucre - DCMC. Need for future alignment meeting on Budget reconciliation was coordinated for next Monday.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.25 |  | 225 | 56.25 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11 ¦ DR4339 – Discussed rescheduling meeting and set new day/time with Jorge Sanchez (Genera) to introduce Genera’s Continuous Improvement (Lean) initiative and discuss department challenges. Topics to be discussed include standardizing processes,and improving communication.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial SOP information.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for Drawings to test user support for publishing.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding users for 01 Genera Program Management project for purpose of shared Financial folder.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP document for Lauren Kennedy (Procore).
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adjusting permissions in Procore to allow for certain contractors to see published IFC drawings.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore PM tool SOP document review.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Johanna Diaz (SMC), Gilberto Sucre (DCMC), Jose Lopez (DCMC) and others to discuss Procore financial SOP questions for workflows.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating meeting minutes agenda to capture and track open items for building Financial SOPs.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permission levels.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 184 | 138 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane MariaDCMC internal meeting with D'Alexzander González, Esther Rohena, Jose Ralat and Roberto Bosch, to discuss the CDBG-DR cost share funds applicable to Genera's eligible María PWs, to be discussed with the PR Housing Department, PREPA and the Czar Office, for the request of these funds.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 184 | 552 | 184 | Yes | 146794 | Site | Genera PR -Deliverable 11- Project Management - DR 4339 - Hurricane Maria: Review the JSH submitted by Homeca for activity in Vega Baja Site. Review the Procore system about Costa Sur and Vega Baja projects documents and activity.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 |  | 184 | 598 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Provided role-based safety orientation and procedural briefing to Dueñas Trailers employee Jesús Emanuel Hernández in support of project readiness requirements. Participated in coordination activities with the Emergency Management Zone in Ponce, which includes the municipalities of Guayanilla and Peñuelas associated with the Costa Sur Project. Activities supported compliance with site access protocols, emergency coordination requirements, and project management oversight.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafael Pabon, Alejandro Laya, Carlos Palomares (CDM Smith) Miguel del Valle (S&L). Discussed feedback and updates received from the Genera procurement team.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.25 |  | 184 | 230 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed the status of all 20 FOMB contract approval packages to ensure they were current and in compliance with submission requirements. Identified outstanding items and proactively followed up with the relevant parties and stakeholders to request the pending information needed to complete and finalize each package for submission.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed prior correspondence related to the ER1 Cost Share Program to ensure continuity and alignment. Held discussions with Winnie Irizarry and Jesús Cintrón (Genera) to clarify outstanding items and confirm next steps. Drafted a formal letter addressed to the Energy Czar and PREPA outlining Genera’s request under the program and seeking guidance on the required submission process. Incorporated feedback received from Jesús Cintrón into the revised draft to support finalization.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment forklifts on site. Uploaded photos and notes to Procore app. Resumed verifying safety plan for tomorrow and JHA Job Hazard analysis for safety purposes, making sure Homeca compliance on site.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continued the review of Attachment J – Health, Safety, and Environmental (HSE) Policies to verify ongoing contractor compliance with applicable safety regulations and environmental standards. Followed up on previous findings and ensured alignment with project-specific HSE requirements.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría) Topic discussed: Organizational Chart and Chain of Command, Procore Platform, Cell Phone Use Policy, Safety and Quality in Demolition Activities, Rigging Plan, Inspection of New Equipment, Weekly and Daily Activity Reporting, Daily Reports in Procore and Team Communication).
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría) Topic discussed: Organizational Chart and Chain of Command, Procore Platform, Cell Phone Use Policy, Safety and Quality in Demolition Activities, Rigging Plan, Inspection of New Equipment, Weekly and Daily Activity Reporting, Daily Reports in Procore and Team Communication).
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Request for proposal Drawings review of Fire protection systems piping and instrumentation diagram specifics that include identification of fire protection route, hose cabinet station, BESS platform and automatic water cannon location.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue supervising the Set-up process of the Yabucoa site mobile office interior installing the rubber tiles of the whole floor (16' x 40') with the team of SA Facias and Duenas Trailer to provide a centralized hub for operations to ensure materials, personnel, and equipment are effectively managed throughout the life cycle of the project.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue supervising the Set-up process of the Yabucoa site mobile office completing the electrical connections between the two trailers including the electrical connection of both air conditioning systems with the team of SA Facias and Duenas Trailer to provide a centralized hub for operations to ensure materials, personnel, and equipment are effectively managed throughout the life cycle of the project.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review the Attachment J - HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES to ensure that the contractor complies with the regulations and policies. Also review Document RFP 4899 RGE Proposal in order to obtain more information about the contractor's scope in the project.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría) Topic discussed: Organizational Chart and Chain of Command, Procore Platform, Cell Phone Use Policy, Safety and Quality in Demolition Activities, Rigging Plan, Inspection of New Equipment, Weekly and Daily Activity Reporting, Daily Reports in Procore and Team Communication).
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue providing assistance in supervising the interior work being done in the DCMC office trailer for the Humacao project, ensuring compliance with the company's safety standards and policies. Accordance with the General Requirements (29 CFR §1926.501) and Risk Communication (29 CFR §1910.1200). The employees at Duenas Trailer resumed works on the finishes of the interior flooring, bathroom, walls, ceiling, windows, stairs, safety anchors, indoor and outdoor lights.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We have been providing assistance in supervising the interior work being done in the DCMC office trailer for the Humacao Project, ensuring compliance with the company's safety standards and policies. Accordance with the General Requirements (29 CFR §1926.501) and Risk Communication (29 CFR §1910.1200). The employees at Duenas Trailer works on the finishes of the interior flooring, bathroom, walls, ceiling, windows, stairs, safety anchors, indoor and outdoor lights.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE JOB SITE. Permitted Quality assurance of the temporary electrical power installation together with Luis A. Moctezuma, Carlos R. López (DCMC). The electrical interior work was inspected to prevent any electrical malfunctions during the temporary power connection. Carlos R. López (DCMC) identified missing wire connectors and exposed junction boxes that could cause a potential short circuit and a possible fire. It was identified and fixed by JN Electrical Contractor.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT. Had a call with Gilberto Sucre, DCMC, to discuss and build the agenda for the kick-off meeting for the next day. Distributed and addressed the meeting agenda with Luis A. Moctezuma and Carlos R López (DCMC) for comments.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE JOB SITE. Supervising JNElectrical Contractor on the installation of the Temporary Electrical Power to the Office Trailers.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT.Performed an inspection with Carlos R. López Vallellanes (DCMC) of the work performed by JN Electrical Contractor with the installation of the temporary electrical power for the DCMC Office Trailers. In general, the installation was performed by the electrical codes.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on the Review and make corrections on Quality Assurance & Control provided by Email by Luis Duque (DCMC) to ensure the project is built according to the required standards and specifications.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on the Review and make corrections on Quality Assurance & Control provided by Email by Luis Duque (DCMC).
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting & Coordination of the QA/QC DCMC Plan. Reviewed and Discussed Quality Assurance Plan Draft. Verified topics missing on the Plan and new comments or ideas to be included. Attendees - Gilberto Sucre (DCMC), Andres Concepcion (DCMC), Luis Duque (DCMC) Harry Del Valle (DCMC)
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Discussed with Gilberto Sucre (DCMC) status of DCMC Quality Control Plan
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on the Review and make corrections on Quality Assurance & Control, adding comments & made corrections discussed in the meeting.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. Permits for hot work and the program for the use and handling of mobile equipment within the Cambalache site are being evaluated.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: Hazard communication program and Hurricane preparedness emergency action plan for implementation in the Cambalache project.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Review of the project General Contractor Quality Control Plan received as submittal by (Jose Segarra - RG Engineering). Observations documented to ensure items are corrected and properly implemented.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated via email a request for a Meeting to CW Legal Services (Carlos Lopez) which is the GeneraPR Permitting consultant. Developed action items and topics for discussion in meeting and requested meeting.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with DCMC Partners Luis Duque, Gilberto Sucre and Harry Del Valle to discuss the DCMC Project quality control plan draft which is being developed to standardized the quality process along the BESS and Peakers program.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated with Jorge Mercado (DCMC Partners) the review and response for the Safety submittals received from Contractor (RG Engineering) to ensure alignment and timeline compliance.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated with Luis Duque (DCMC Partners) Procore submittal management. 3 submittals regarding design where responded and sent to General Contractor (RG Engineering - Jose Segarra).
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 1 | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with ARG RFI #62 and 63, The RFI #62 was redirected to S&L to provide information related to equipment weights. Reviewing information related to MV transformer and switchgear for phase 2. The RFI #63 is related to demolition of concrete slab of Vega Baja and ARG want to know who the contractor for this work will be, this contractor selection will be by Genera and when contractor is selected information will be provided to ARG/CERES.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Reviewing email related to project. Contractor Vivot Eliezer Reyes arrive to project to view existing transformer for rigging quotation to Genera.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on-site at the Aguirre warehouse, a consolidated inventory performance report was compiled and prepared from Mr. Anthony Vega of Genera PR. This report integrated data from multiple warehouse locations, capturing catalog item counts, unit quantities, cost metrics, and existing discrepancies. The analysis also included identification of stock level threshold and variance trends to support strategic decision-making. Percentage based performance indicators were used to present the current operational status of each site. The inventory locations reviewed during this session were, BD 025 to BD 070, AN 014 to AN 024, CG 001 to CG 004, CH 001 to CH 006, CI 001 to CI 006, CJ 001 to CJ 008, CK 001 CK 004.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-participate in a strategic coordination session with Juan Vallejo and Hernan Machado from DCMC, along with essential warehouse staff, to establish a clear operational framework for upcoming inventory activities. The meeting focused on reinforcing roles and responsibilities, standardizing inventory procedures, and addressing any logistical constraints affecting cycle count accuracy. This initiative also aims to ensure full alignment between site operations and project deliverables, while promoting accountability across all teams involved.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted inventory data evaluation and developed cycle count documentation to support scheduled tasks at the Aguirre warehouse, in coordination with Mr. Juan Vallejo from DCMC. Activities focused on verifying item locations, cross-checking quantities against system records, and organizing materials to facilitate an accurate and efficient inventory workflow. Today's locations range from BD 025 through BD 070.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out scheduled cycle count operations for designated inventory zones, as part of the daily agenda. The effort aimed to reinforce data integrity by verifying physical inventory against system records, identifying discrepancies, and documenting variances for corrective actions. Today's verification covered materials located in BD 025 through BD 070.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a variance analysis at the Aguirre warehouse alongside Mr. Juan Vallejo from DCMC, focused on identifying inventory discrepancies and tracking root causes of inconsistencies. The activity included cross-referencing physical stock with system data, validating item classifications, and reviewing prior adjustments to determine their accuracy. This task directly contributes to strengthening inventory control protocols, improving data integrity, and facilitating the implementation of corrective actions to ensure compliance with operational standards and audit requirements. Work was concentrated in locations BD 025 through BD 070.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory recount at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC, with the objective of improving data integrity and operational accuracy. The session emphasized validating previous cycle count results, identifying unresolved discrepancies and ensuring that all inventory records reflect accurate asset locations and quantities, Additional efforts included verifying proper labeling, updating system entries as needed, and reinforcing compliance with established asset management protocols to support audit readiness and project accountability. Locations assessed range from BD 025 through BD 070.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review document, Quality Control Manual RG Engineering, INC. send by Jose Segarra from RGE Division 2 - Site Work and Division 3 - Concrete Comparison with Sargent & Lundy technical specifications.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review document, Quality Control Manual RG Engineering, INC. send by Jose Segarra from RGE Division 2 - Site Work and Division 3 - Concrete Comparison with Sargent & Lundy technical specifications.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails and Submittals in Procore - sent by contractors- confirming that the materials, products, and equipment meet the contract requirements.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore app. Verifying safety plan for tomorrow and job hazard analysis (JHA) for safety purposes, making sure Homeca compliance on site.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Technical Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla Technical reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda, Carlos Palomares), Sargent & Lundy (Mike Kuczynski), and DCMC (Rafael Calderon, Gilberto Sucre)
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens_Contract #00106588 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #2 and #3 based on contract requirements. Reviewing Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Continue working with Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#1_Invoice# PRIN0007609_Oct 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BD 025 TO BD 070
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AN014 to AN024
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AN014 to AN024
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AN014 to AN024
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AN014 to AN024
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AN014 to AN024
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations CG 00 001 al CG 00 004; CH 00 001 al CH 00 006; CI 00 001 al CI 00 006; CJ 00 001 al CJ 00 008; CK 00 001 al CK 00 004
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CG 00 001 al CG 00 004; CH 00 001 al CH 00 006; CI 00 001 al CI 00 006; CJ 00 001 al CJ 00 008; CK 00 001 al CK 00 004
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations CG 00 001 al CG 00 004; CH 00 001 al CH 00 006; CI 00 001 al CI 00 006; CJ 00 001 al CJ 00 008; CK 00 001 al CK 00 004
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations BD 025 TO BD 070 at the Aguirre warehouse to start the cycle counts.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Resumed conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations BD 025 TO BD 070 RECOUNT LIST # 1122/1123
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BD 025 TO BD 070 LIST # 1102/1106/1107/1120
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Go through Owner's General Conditions among contractual agreements to obtain proper interpretation of Contractor's obligation when submitting a Change Order; documentation, timing of elevating the issue and action taken prior to submitting technical and cost proposals.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /Jobos Peakers Incorporate RG Permission in Procore/GEN 01 Data Review & Download for Process/Siemens Costa Peakers Incoming Data to Process/GEN 01 S&L Financial Data Review & Process
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /GEN 01 S&L Financial Data Review & Process/Incorporating Revised S& Task /Orders 1 & 2 /Ensure Documents are Re-created_ Reviewed prior to Uploading and or Archived in an Organized & Controlled Manner
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review contractual documents regarding the delivery of drawings and design workshops (if any) for the design development of construction projects.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Final review and publishing of the Issued for Construction Drawing Plans for the Vega Baja Power Plant project, in order to obtain Genera's final comments and markups prior to sharing drawing plans with Contractor.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the settings and implementation of the Action Plan tool for the convenience of construction logistics and initial works with the purpose to maintain all parts involved in the project inside the Procore Platform; assign tasks and assignees and directions on actions to take.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3.5 |  | 151 | 528.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform QA/QC for the recently received Specifications Book from design team Sargent & Lundy for the Cambalache Power Plant project. Review Table of Contents to contrast with IFC drawings and construction execution.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on Siemens Milestone #2 review. I already reviewed some deliverables, during this time I verify the PO for the U2 Base Frame and U1 Air Intake.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Work on the web page of Genera BESS and Peakers edits to Alex O. Valdés Díaz from the Genera PR team for review and integration into section of the Genera PR website. Ensure that all content updates are clear, accurate, and aligned with the updates of the site.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Work on editing in the presentation about the BESS Project prepared for a community meeting in Vega Baja. Responsibilities included reviewing and editing written content for clarity and tone, updating images to reflect current events and community representation, and making additional visual adjustments to enhance overall presentation quality.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Work on a document Q&A requested by the Genera PR team, compiling potential questions and answers from the community regarding the BESS Project for upcoming public meetings. This task involved researching previous community inquiries, drafting clear and relevant questions, identifying accurate responses based on available project information, and gathering additional data as needed to ensure the document was comprehensive, informative, and aligned with community concerns.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Mockup meeting to prepare for the Vega Baja community meeting on Monday, June 23. Present at the practice session were the team from Genera PR — Ivan Báez Santiago, Jorge Bracero — and from the CDM Smith team, Gabriel Perez.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 134 | 402 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review Cambalache Power Plant BESS RGE Quality Control Plan, Division 2 - Site Work, Setbacks General, Top of cut slope, Top of fill slope and Ground surface preparation for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Inspecting the electrical installation for the office trailer with Jose Lopez (DCMC) and JN Electrical Contractors.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Aguirre Site - Reviewing the Project Submittals: Aguirre GA for Rule 141 Application; Aguirre Rule 141 Form; Jaca & Sierra Job Hazard Analysis; Updated Schedule; Excavation Permit; SPT Hammer Energy Measurements - SN 326745; Topo/GPR; CFSE Aguirre; Final Deliverable; Aguirre - GSU Inspection and Tesla Plan; Aguirre - GSU Inspection and Tesla Plan
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria Continuous review of site drawing Appendix D, contractor RG ENGINEERING, INC. RFP-4899 Proposal and schedule concrete specification information about at Costa Sur Facilities and review new Procore project information.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría) Topic discussed: Organizational Chart and Chain of Command, Procore Platform, Cell Phone Use Policy, Safety and Quality in Demolition Activities, Rigging Plan, Inspection of New Equipment, Weekly and Daily Activity Reporting, Daily Reports in Procore and Team Communication).
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked with employee (CDM Smith) Carlos Palomares on preliminary schedule for Genera considering design updated drawings with mechanical of contractor scope, preliminary utilities for employee Andres Concepcion (DCMC) due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on construction planning with DCMC team related to construction communication line, management tools related to RFI, Procore and specification with DCMC employees Carlos Rodriguez, Carlos Bayron, Rafael Barrera, Luis A. Echevarria due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache Quality Assurance Alignment meeting to stablish and organize the Quality control assurance with Andres Concepcion (DCMC), Gilberto Sucre (DCMC) and Harry del Valle (DCMC) for the 4339_9510 BESS_Cambalache project.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 134 | 268 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Continue review Cambalache Power Plant BESS RGE Quality Control Plan Division 2 - Site Work, Placement and compaction, Grading and Maintenance Protection of graded areas for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 122 | 244 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue reviewing Chapter 7-V5, "Payment & Cash Management," to obtain information, enhance understanding, and successfully complete the grant-related procedures.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing Chapter 7-V5, "Payment & Cash Management," to obtain information, enhance understanding, and successfully complete the grant-related procedures.
2025-06-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 94.5 | 0.7 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Traveled to Ponce for meeting with Osvaldo de Jesus, Richie Cintron, (GENERA), Alcides Rodriguez and Paul Fourquet (Puerto Rico Emergency Managment Agency) about Costa Sur Genera project in Guayanilla.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permission changes to allow for contractors to view IFC drawings.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in weekly Peaker project management update. Discussed weeks events and status of costa sur project and Jobos demolition portion of the projects. Attended the meeting: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 project design review meeting took place to discuss the status of the updated construction drawing for each project meeting participants Chris Mateo, Gino Sambolin, and William Crespo (Sargent & Lundy); German Núñez, GENERA; Rafael Pabon, Carlos Palomares, and Laya, Enrique J. (CDM Smith)
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Meeting review with Costa Sur staff and establishing SOP and project protocols, review construction documents that were available. Attended meeting: Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Responded to emails and inquiries from the weeks email box, reviewed upcoming meetings and updated my notes
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 225 | 787.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Site Visit, Internal Meetings and Weekly Construction Meeting Participation. Kick Off agenda included Project Team Introductions, Contract Status, Scheduling and Coordination Meetings, EHS and Quality Control. Site Access requirements & documentation, and Coordination with Genera on site activities. DCMC - Carlos Rodriguez CSM Smith - Gabriel Perez Sargent & Lundy - Wilfredo Sierra RG Engineering - Jose Segarra
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre - Site Visit, Internal Meetings and Weekly Construction Meeting Participation Site Inspection including temporary offices installation, meeting with DCMC project team members and Led Kick-off construction meeting with Jose Lopez DCMC. Agenda included Project Team Introductions, Contract Status, Scheduling and Coordination Meetings, EHS and Quality Control. Site Access requirements & documentation, and Coordination with Genera on site activities. Participants: Carlos Lopez and Luis Moctezuma - DCMC Jose Robles - RG Engineering Mike Kuczynski- Sargent & Lundy Gabriel Perez - CDM Smith
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Internal Meeting PM / CM and with the presence of Sargent & Lundy reviewed by site project needs and priorities in design items for: Cambalache, Vega Baja, Costa Sur, Aguirre and Yabucoa. Main topic discussion is IFC's with holds and pending drawings to be issued on July 10th. Combined Installation RFP for Costa Sur, Aguirre & Yabucoa to be issued on 6/20. Mike Kuczynski & Robert Molner - Sargent & Lundy Gabriel Perez - CDM Smith Gilberto Sucre - DCMC
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's Permitting. Anna Rausch - Sargent & Lundy provided Permitting update of both programs including a special topic for abandoning and/or removing underground fuel storage tank regulations. PUI closure for Vega Baja require a final inspection. Attendees: Sargent & Lundy - Mike Kuczynski CDM Smith - Gabriel Perez Carlos Lopez - CWL Legal Erick Rocher - Genera Gilberto Sucre - DCMC
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peaker's Project Schedule & Budget Meeting Led by Carlos Palomares CDM Smith update review of BESS and Peakers Programs Schedule Updates and Budgets. Participants: German Nunez - Genera Rafael Pabon & Gabriel Perez - CDM Smith Gilberto Sucre - DCMC
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting for 360 Reporting items.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financial tool information.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Permission matrix for Franklyn Colmenares (CSA) for review.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to discuss Procore reporting for directory items.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool information.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creation of new project in Procore for C-102570 PSSP NEW DEMINERALIZED WATER TANK 2.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financial tool information.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore Budget tool related items to get answers from the team on roles.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on RACI matrix for projects to identify who is doing what in Procore.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on collecting all Financial notes to hand over to Lauren Kennedy (Procore).
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Raissa Borges from DCMC to review the strategy for sharing the PMO Power BI dashboard with María Sánchez and Jesús Cintrón from Genera PR, focusing on access management and sharing.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Yabucoa Site meeting with Gabriel Morales (DCMC) to support in trailer installation & supplies delivered. As a team we met to discuss site safety and initial works to be done on ground movement and challenges with surrounding terrain and site utilities.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Gilberto Sucre, Jose Lopez (DCMC), Jose Segarra (RGE) about Aguire Genera Project and continuing support installation offices trailers process to ensure it provides a convenient and functional space and serves as hub for administration, planning, and meetings.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Budget and Schedule meeting for BESS and Peaker project. Topics discussed: schedule for all the sites and overlay in some of the demolition work. Also discussed RFP status. Participants: Carlos Palomares (CDM), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Rafael Pabon (CDM)
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review correspondence regarding material and equipment needed for trailers logistics for the Aguirre, Yabucoa and Vega Baja sites.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Costa Sur Weekly RGE/DCMC meeting to discuss construction project phase and meet and greet the site team. Participants: Carlos Rodriguez (DCMC), Gilberto Sucre (DCMC), Luis Echevarria (DCMC) Gabriel Perez (CDM), Franklyn Colmenares (CSA).
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 |  | 184 | 552 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4826 -Supported Genera’s Regulatory team in updating the response to FOMB’s 06/11 Request for Information (RFI). The update was necessary due to recent contract amendments that included changes in pricing. As a result, revised FOMB Appendix A to reflect updated contract values and deliverables, and adjusted FOMB Appendix D to ensure consistency with the revised pricing. Coordinated with relevant stakeholders, Jesus Cintron, Fernando Ortiz and Francisco Feliu (Genera) to confirm accuracy and alignment prior to resubmission to FOMB.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4218 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 |  | 184 | 552 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4214 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Reviewed over 50 documents shared by Joel Pantojas (Genera), renamed them and saved them accordingly. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in a meeting to discuss improvement requirements for the Genera Connect Timesheets platform, aimed at ensuring team alignment on upcoming enhancements. The discussion included Eisha Mercader from DCMC and Aldwin Pagán and Keyla Sierra from Integrum, focusing on functionality improvements to support more efficient time tracking, reporting accuracy, and alignment with project needs.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore. JHA for safety purposes, making sure Homeca compliance on site. Continue Present while Javier E Bidot associates mark the field for next phase. Removal of bobcat and forklift.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Reviewed Attachment D – Technical Specifications for the BESS Civil Work Contract (CWC) to ensure understanding of scope and technical requirements. Additionally, reviewed applicable safety regulations relevant to the project to ensure alignment with health and safety standards prior to execution of civil works.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Gilberto Sucre, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), RGE Jose Robles Construction team lead and Sargent and Lundy design team lead Franklyn Colmenares. Topic discussed: Meet all team members, Scope of Work, Schedule, Commercial, Project Communication, General safety and quality control / quality assurance.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Gilberto Sucre, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), RGE Jose Robles Construction team lead and CDM Smith Franklyn Colmenares. Topic discussed: Meet all team members, Scope of Work, Schedule, Commercial, Project Communication, General safety and quality control / quality assurance.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Request for proposal Drawings review of flange, beams and connection typical details. Typical reinforcement details as well as equipment anchor rod sleeve and anchor plate schedule.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Assembly and organize the office supplies (Tables, chairs, Cabinets, etc...) at the Yabucoa Site Mobile office to configure an efficient workspace.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue with the set-up and cleaning process of the Yabucoa site mobile office interior with the team of SA Facias and Duenas Trailer to provide a centralized hub for operations to ensure materials, personnel, and equipment are effectively managed throughout the life cycle of the project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Pick up order #WN22280242 at Home Depot Humacao. Order included equipment (Tables, chairs, Cabinets, etc...) for the Yabucoa Site Mobile office.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria The review of drawings Appendix D.1 continues; in this case, the perimeter of the project is being reviewed and the possible underground utilities that might cross the project are being assessed.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Gilberto Sucre, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), RGE Jose Robles Construction team lead and Sargent and Lundy design team lead Franklyn Colmenares. Topic discussed: Meet all team members, Scope of Work, Schedule, Commercial, Project Communication, General safety and quality control / quality assurance.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review ATTACHMENT J HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES: Health and Safety Provisions, Scaffolds (29 CFR 1926 Subpart L) Confined Spaces (29 CFR 1910.146) Occupational Exposure to Noise (29 CFR 1910.95) Hazardous Materials (29 CFR 1910 Subpart H) Personal Protective Equipment (29 CFR 1910 Subpart I) Hazard Communication (29 CFR 1910.1200) HAZWOPER (29 CFR 1910.120) Fire Protection (29 CFR 1910 Subpart L) Commercial Diving (29 CFR 1910 Subpart T) Respiratory Protection (29 CFR 1910.134) Fall Protection (29 CFR 1926 Subpart M) Electrical (29 CFR 1926 Subpart K) Welding (29 CFR 1926 Subpart J) Excavations (29 CFR 1926 Subpart P) Demolitions (29 CFR 1926 Subpart T) Blasting & Explosives (29 CFR 1926 Subpart U) Ventilation (29 CFR 1926.57) Tools, Hand, and Powered (1926 Subpart I) Electric Industry (29 CFR 1910.269) Lockout/Tagout (29 CFR 1910.147) Asbestos (29 CFR 1910.1001)
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review ATTACHMENT J HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES: Environmental Provisions Clean Water Act (40CFR 112.7 y 122), the Spill Prevention Control and Countermeasure and the EQB’s Water Quality Standards, Environmental Protection Agency (EPA) Spill Prevention and Control and Countermeasure Plan (SPCCP) Hazardous Materials Transportation, 49 CFR 172 Sub. Part H (DOT) Products with ingredients regulated by the EPA’s Toxic Release Inventory (SARA title III, 313)
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Initial Construction coordination meeting with Gilberto Sucre, Jose Lopez (DCMC), and Jose Segarra (RGE) about Aguire Genera Project and continuing support installation offices trailers process.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria; AGUIRRE BESS PROJECT; Organized and participated in the kick-off meeting with the contractor, RG Engineering, with José Segarra, José Robles (RGE), Gilberto Sucre, Carlos R. López, Luis A. Moctezuma (DCMC), Gabriel Pérez, Franklyn Colmenares (CDM Smith), and Theresa Pérez DCMC. It was a Team introduction meeting from the Construction Management Team and the General Contractors, RG Engineering (RGE).
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria; participated in the Request for clarification: Meeting with the Vega Baja contractor ARG Ceres and Gabriel Perez, Franklyn Colmenares, Enrique Laya (CDM Smith); Gilberto Sucre, Eduardo Rivera, (DCMC) and Nelson Soler from CDM Smith. The purpose of the meeting was to follow up on the request for clarification list prepared by Gabriel Perez (CDM Smith)
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria AGUIRRE BESS PROJECT; Held a Site Staff meeting with Luis Moctezuma, Carlos R. López (DCMC) to prepare the Kick-off meeting Agenda
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in the kick-off meeting of the Costa Sur Bess Project with RGE Engineering (Jose Robles and Jose Segarra), Gilberto Sucre, Carlos Rodríguez, Carlos Bayron (DCMC). It was a joint meeting between the contractor (RGE Engineering) and the construction management staff (DCMC), an introductory session, and a discussion of the work plan for the Costa Sur BESS project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: emergency management plan for implementation in the Cambalache project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: accident prevention plan to safeguard workers, mitigate risks, and ensure regulatory compliance for implementation in the Cambalache project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued Review of the project General Contractor Quality Control Plan received as submittal by (Jose Segarra - RG Engineering). Observations documented to ensure items are corrected and properly implemented.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Carlos De Jesus and Luis Damudt (DCMC Partners) to initiate a review process and observations tracking for the Cambalache Construction Schedule. To align and improve the project tracking.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Construction schedule and generated a Observations tracker to identify and track all Construction schedule comments and corrections needed by contractor (RG Engineering).
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Cooridnated various project management tasks including a meeting coordination for technical discussion on 6/26/25 with Sargent and Lundy team (Designer) and RG Engineering (Contractor). Coordinated a meeting with CW Legal Services (Permitting Consultant) for 6/25/2025 to discuss project permitting requirements. Responsed email to Gabriel Perez (CDM Smith) regarding proposed structural study to Cambalache access bridge.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Managed and edited in Procore the RFI # 20 regarding a request for TESLA technical specification by RG Engineering (Contractor) for basis of design reviews.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Luis Roman and Luis Duque - DCMC Partners to upload the Technical Specifications document in Procore Platform.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Homeca today is working with the as built drawing for the Vega Baja site and Javier Vidot surveyor contractor for the land survey of Vega Baja BESS project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - Meeting with Carlos Hernandez of ARG; Eduardo Rivera of DCMC; Wilfredo Sierra, and Angel Alicea Rodriguez of S&L, Gabriel Perez Sepulveda and Enrique Laya of CDM Smith. Meeting to discuss the RFC generated for ARG in regard of the Vega Baja BESS projects.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Homeca today is working with the as built drawing for the Vega Baja site.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 |  | 167 | 542.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue with Vega Baja demolition project closing with Homeca. Homeca and Javier Vidot (surveyor contractor) continue working with the as-built drawing for the Vega Baja site. Reviewing RFI submitted by ARG thru Procore in regard of Vega Baja project. Send email to Mike Kuczynski of S&L to verify open RFI sent by ARG in Procore related to project question.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a virtual meeting via Microsoft Teams with the inventory team Mr. Juan Vallejo, Mr. Giovanni Taffanelli, Mr. Milton Flores and Juan Vallejo from DCMC, to review progress and ensure alignment moving forward. During the meeting, each team member provided a detailed summary of the tasks they completed throughout the day, including updates on discrepancy review, digital file organization, and tracking tool development. This allowed for a productive exchange of observations and helped identify any areas that may require follow-up or additional clarification. In addition, we discussed expectations and preliminary planning for the upcoming cycle count, including target locations, scheduling considerations, and resources needs. The session also served as an opportunity to reinforce accountability, address questions in real time, and foster collaboration despite the remote work environment. Overall, the meeting ensured operational continuity and set the stage for a well-coordinated execution of the next cycle count.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an evaluation of team performance metrics related to recent inventory operations. This included reviewing individual task completion rates, accuracy levels in reported variances, and overall responsiveness to assigned duties. Compiled the data into a performance summary to identify both high performers areas where additional support may be beneficial. This analysis will help guide future resource allocation, enhance accountability, and ensure that performance expectations remain aligned with operational goals. The insights gathered will also serve as a foundation for upcoming one-on-one feedback session and ongoing professional development planning.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- focused auditing and organizing digital inventory records stored across multiple shared drives and internal databases. This task involved verifying file naming consistency, ensuring proper version control key documents such as count sheets, variant reports, and transfer logs, and consolidating outdated or duplicated files. Also created a structured folder system to improve accessibility for the team and reduce the risk of miscommunication or data loss. Additionally, developed a quick reference index to facilitate faster retrieval of frequently used documents, which will support more agile reporting and team coordination moving forward. This initiative enhances data organization standards and reinforces consistency across the inventory documentation process.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-reviewed a selection of critical inventory discrepancies previously reported by the team. This included cross-referencing system data with physical documentation, verifying transaction histories, and identifying recurring patterns that may indicate systemic issue gaps. Documented the root causes of several variances and categorized them based on their nature (data entry errors, undocumented transfers, mislabeling). Parallel, conducted a comparative review of historical variance reports to determine if similar discrepancies had occurred in previous cycles, which provided valuable insight into recurring operational weaknesses.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-I conducted a meeting with the inventory team Mr. Juan Vallejo, Mr. Giovanni Taffanelli, Mr. Milton Flores and Juan Vallejo from DCMC, to outline the tasks to be performed throughout the day while operating remotely. Team members were instructed to review and analyze previously identified discrepancies, verify and organize digital files to ensure alignment with printed records, and develop a tracking tool to monitor the progress of completed work. Additional relevant task may be integrated as necessary. These actions are aimed at reinforcing data accuracy, maintaining operational continuity, and supporting the integrity of our inventory management processes.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Eduardo Rivera, and Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the weekly meeting with CPM, I focused on reviewing Critical Components priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Based on the developed list of critical components, the status of items currently under P3A, Cancelled, or marked for Republishing was verified. Component status was confirmed through data gathered during outreach efforts.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS to Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. Division - Site Work
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Cambalache Construction Schedule Activity Review Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS to Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. Project Quality Program.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. Division - Site Work
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails Cambalache BESS -Schedule Observations, Cambalache - P6 CD Smith Preliminar, and Submittals RGE-0008.0 RGE-0008 EMPLOYEES CERTIFICATION on Procore.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore. JHA for safety purposes, making sure Homeca compliance on site. Present while Javier E Bidot associates mark the field for next phase.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Budget Meeting with project management Team. Contract 106761 - Reviewing budget for all BESS sites including construction, demolition, A&E, Equipment supply, Installation and forecasting based on actual data. Meeting between CMD Smith PM team (Gabriel Sepulveda, Carlos Palomares), CSA (Franklyn Colmenares), and DCMC (Rafael Calderon, Gilberto Sucre)
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 164 | 328 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 164 | 492 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens_Contract #00106588 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #2 and #3 based on contract requirements. Reviewing Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 RG Engineering Inc. & Genera Weekly Meeting_ Contract #109403, Commercial & Schedule Discussion review for RGE Equipment Supply Contract. Reviewing contract requirements, payment milestones, general submittal status and key dates Participants: Genera (German Nuñez), Sargent & Lundy ( Miguel del Valle, Mike Kuczynski), CDM (Carlos Palomares, Rafael Pabon, Enrique Laya), RGE ( Harry Velazquez), Gevernova (David Lee) and DCMC (Rafael Calderon)
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Work resumed with the goal of finalizing the day’s documentation. All verified data was compiled and structured into formal reports, with attention to detail in order to ensure clarity and traceability. Observations and notes from earlier review sessions were incorporated, and draft reports were formatted for presentation. Additionally, support files were prepared, including item logs and exception lists, to back up the day’s findings and recommendations. These materials were organized to facilitate discussion during the closing meeting.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-The workday began with a one-hour virtual kick-off meeting conducted by Paul Browne (DCMC). During this session, the DCMC San Juan warehouse site team discussed the specific objectives and tasks to be completed for the day as part of the ABC Inventory Certification process. Each member received clear guidance regarding their assignments, and tools were reviewed to ensure all participants had access to the necessary digital resources. A Safety Moment was presented, emphasizing the importance of maintaining good posture, taking regular screen breaks, and setting up an ergonomic workstation to prevent strain during extended computer use.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. The focus shifted to analyzing Maximum and Minimum stock level settings for key inventory items. Weekly and monthly summaries were outlined, setting the foundation for a more comprehensive reporting structure to track trends and inform inventory decisions.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria. The day concluded with a one-hour closing meeting held via Microsoft Teams by Paul Browne (DCMC). DCMC Team members of San Juan warehouse shared their progress, findings, and any challenges encountered during the shift. A collective discussion took place, reviewing the effectiveness of current practices and identifying opportunities for process improvement.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – MariaWork resumed with the goal of finalizing the day’s documentation. All verified data was compiled and structured into formal reports, with attention to detail in order to ensure clarity and traceability. Observations and notes from earlier review sessions were incorporated, and draft reports were formatted for presentation. Additionally, support files were prepared, including item logs and exception lists, to back up the day’s findings and recommendations. These materials were organized to facilitate discussion during the closing meeting.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-This work block was dedicated to thoroughly reviewing digital inventory lists that had already been processed and uploaded into the system. The primary goal was to verify the accuracy of the data recorded during previous physical counts. Using spreadsheet tools and inventory management software, each item was cross-checked for consistency with historical entries. Particular attention was given to items in category A due to their higher turnover and impact on inventory valuation. Any irregularities or inconsistencies were flagged and documented for further analysis.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- The day concluded with a one-hour closing meeting held via Microsoft Teams by Mr. Paul Browne from DCMC. DCMC Costa Sur Team members shared their progress, findings, and any challenges encountered during the shift. A collective discussion took place, reviewing the effectiveness of current practices and identifying opportunities for process improvement. The meeting wrapped up with a Round Table segment, where each participant provided input on ways to enhance team collaboration, streamline data verification, and improve report generation going forward.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at remote job in home office - This work block was dedicated to thoroughly reviewing digital inventory lists that had already been processed and uploaded into the system. The primary goal was to verify the accuracy of the data recorded during previous physical counts. Using spreadsheet tools and inventory management software, each item was cross-checked for consistency with historical entries. Particular attention was given to items in category A due to their higher turnover and impact on inventory valuation. Any irregularities or inconsistencies were flagged and documented for further analysis. The focus shifted to analyzing Maximum and Minimum stock level settings for key inventory items. Weekly and monthly summaries were outlined, setting the foundation for a more comprehensive reporting structure to track trends and inform inventory decisions.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-The workday began with a one-hour virtual kick-off meeting conducted by Mr. Paul Browne from DCMC. During this session, the DCMC Costa Sur team discussed the specific objectives and tasks to be completed for the day as part of the ABC Inventory Certification process. Each member received clear guidance regarding their assignments, and tools were reviewed to ensure all participants had access to the necessary digital resources. A Safety Moment was presented, emphasizing the importance of maintaining good posture, taking regular screen breaks, and setting up an ergonomic workstation to prevent strain during extended computer use.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at remote job in home office - Work resumed with the goal of finalizing the day’s documentation. All verified data was compiled and structured into formal reports, with attention to detail in order to ensure clarity and traceability. Observations and notes from earlier review sessions were incorporated, and draft reports were formatted for presentation. Additionally, support files were prepared, including item logs and exception lists, to back up the day’s findings and recommendations. These materials were organized to facilitate discussion during the closing meeting.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 –Aguirre.This work block was dedicated to thoroughly reviewing digital inventory lists that had already been processed and uploaded into the system. The primary goal was to verify the accuracy of the data recorded during previous physical counts. Using spreadsheet tools and inventory management software, each item was cross-checked for consistency with historical entries. Particular attention was given to items in category A due to their higher turnover and impact on inventory valuation. Any irregularities or inconsistencies were flagged and documented for further analysis.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 –Aguirre- Work resumed with the goal of finalizing the day’s documentation. All verified data was compiled and structured into formal reports, with attention to detail in order to ensure clarity and traceability. Observations and notes from earlier review sessions were incorporated, and draft reports were formatted for presentation. Additionally, support files were prepared, including item logs and exception lists, to back up the day’s findings and recommendations. These materials were organized to facilitate discussion during the closing meeting.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 –Aguirre.The day concluded with a one-hour closing meeting held via Microsoft Teams. Team members (Paul Browne, Giovanni Tafanelli, Hernan Machado). The DCMC warehouse supervisors shared their progress, findings, and any challenges encountered during the shift. A collective discussion took place, reviewing the effectiveness of current practices and identifying opportunities for process improvement. The meeting concluded with a Round Table segment, during which each participant shared input on ways to enhance team collaboration, streamline data verification, and improve report generation moving forward.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 –Aguirre. The workday began with a one-hour virtual kick-off meeting with Paul Browne (DCMC warehouse manager). During this session, the DCMC Aguirre team discussed the specific objectives and tasks to be completed for the day as part of the ABC Inventory Certification process. Each member received clear guidance regarding their assignments, and tools were reviewed to ensure all participants had access to the necessary digital resources. A Safety Moment was presented, emphasizing the importance of maintaining good posture, taking regular screen breaks, and setting up an ergonomic workstation to prevent strain during extended computer use.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 –Aguirre.The focus shifted to analyzing Maximum and Minimum stock level settings for key inventory items. Weekly and monthly summaries were outlined, setting the foundation for a more comprehensive reporting structure to track trends and inform inventory decisions.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – dedicated to thoroughly reviewing digital inventory lists that had already been processed and uploaded into the system. The primary goal was to verify the accuracy of the data recorded during previous physical counts. Using spreadsheet tools and inventory management software, each item was cross-checked for consistency with historical entries. Particular attention was given to items in category A due to their higher turnover and impact on inventory valuation. Any irregularities or inconsistencies were flagged and documented for further analysis.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane –The workday began with a one-hour virtual kick-off meeting lead by DCMC Paul Browne and Inventory Team from DCMC, Milton flores, Juan Vallejo and Hernan Machado. During this session, the team discussed the specific objectives and tasks to be completed for the day as part of the ABC Inventory Certification process. Each member received clear guidance regarding their assignments, and tools were reviewed to ensure all participants had access to the necessary digital resources. A Safety Moment was presented, emphasizing the importance of maintaining good posture, taking regular screen breaks, and setting up an ergonomic workstation to prevent strain during extended computer use.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – The day concluded with a one-hour closing meeting held via Microsoft Teams with DCMC Paul Browne. DCMC Team members Milton flores, Juan Vallejo and Hernan Machado shared their progress, findings, and any challenges encountered during the shift. A collective discussion took place, reviewing the effectiveness of current practices and identifying opportunities for process improvement. The meeting wrapped up with a Round Table segment, where each participant provided input on ways to enhance team collaboration, streamline data verification, and improve report generation going forward.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane –The focus shifted to analyzing Maximum and Minimum stock level settings for key inventory items. Weekly and monthly summaries were outlined, setting the foundation for a more comprehensive reporting structure to track trends and inform inventory decisions.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform QA/QC for fine tunning on the Distribution Groups for Management Groups as for Peakers and BESS staff to ease the inclusion of people in the distribution of items through Procore.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /GEN 01 RG Engr Procore Certificates Review & Process/ Aguirre BESS Coordination of Kickoff Meeting - Review & Process Meeting Minutes/ Follow up on Contractor -Vendors Procore Request for Certifications and Email Request/RG Engr set-up of Procore Profiles (no Access) yet/ Costa Sur Peakers Incoming Meetings Data Review & Process
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /Siemens Costa Sur Peakers Incoming Data Review & Process/Procore User Permissions List Preparation/Coordination of Specific Project Reporting with Lauren Wells DCMC
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work with documentation regarding Genera's Critical Components installation around the power plants; review submittal logs from active projects to identify potential critical components per site and start tracking Delivery Dates and Lead Times across the Submittals Tool for each project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the opening of multiple tools for Pedro Cabrera (DCMC) facilitating the work method for Critical Components in Non-BESS or Peakers projects; identify equipment already purchased with established lead times and the coordination for equipment already handled to Genera on a specified facility or plant.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 151 | 37.75 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Call with Carlos Rodriguez (DCMC), Site Manager for BESS Costa Sur, to schedule a site visit for friday, June 20, 2025, to go over the Procore Platform and the main Project Management Tools with the team specially on the approval and distribution of items through standard operating procedures (SOPs).
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Aguire Kick-off Meeting via Microsoft Teams hosted by Jose Lopez (DCMC), and including also from DCMC Gilberto Sucre, Theresa Perez, Gabriel Perez, Carlos De Jesus. Also Franklyn Colmenares (CSA), from design team S&L Harry Velazquez, Mike Kuzcynski, Ivette Miranda, and from contractor RGE Jose Robles, Jose Segarra, Xiomara Perez, Vernadee Ortiz. This meeting had the purpose to set the tone with all parts being represented in a single forum and provide contractor initial guidance before the final signature on contractual agreement. DIscussion of potential design implications and the increase of scope of works.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 151 | 188.75 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Teams Meeting with Andres Concepcion and Luis Duque (DCMC) from the Cambalache field staff to go over the process of uploading specifications to the system, publishing and creating Spec Books with breakups between sections. IFC Specs for Cambalache have been uploaded and published.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the Meetings Tool settings for the Aguirre Power Plant project to provide selected users the space to approve and/or comment on meeting minutes inside the Procore platform. This is the actual approval evidence being worked.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Conduct research and draft a comprehensive Q&A document to address potential questions and concerns for the upcoming community meeting in Vega Baja in the BESS project. Identifying key topics based on previous meetings and community feedback.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Conduct a thorough review of the BESS and Peakers pages on the Genera PR website to confirm that both the text (copy) and images are up to date and aligned with the most recent information.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Gathering accurate and updated information such as project communications and technical, to ensure that all responses included in the Q&A document for the BESS project reflect the latest developments and official positions of the organization. The task also includes writing and drafting the Q&A document
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Send reminders to all community members invited to the meeting on Monday, June 23 in Vega Baja, where the BESS Project will be discussed. The goal is to ensure broad and well-informed participation.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review Cambalache Power Plant BESS RGE Quality Control Plan in Concrete preparations and forms, Placing Reinforcement, and Installation of Embedded Items for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 134 | 469 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria AGUIRRE BESS PROJECT; Held a Site Staff meeting with Luis Moctezuma, Jose M. Lopez (DCMC) to prepare the Kick-off meeting Agenda. Some of the topics were, Quality, Safety and General Requirements for the Contractors.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 134 | 469 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing Project Issued for Bid (IFB) drawings to verify they meets the required specifications of the projects. Reviewed 10 pages.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria AGUIRRE BESS PROJECT; Project kick-off meeting with Luis Moctezuma, Jose M. Lopez, Gilberto Sucre, Jean Pierre Menay (DCMC); Franklyn Colmenares, Gabriel Perez (CDM Smith); Jose Robles, Jose Segarra (RG Engineering) It was a joint meeting between the contractor (RGE Engineering) and the construction management staff (DCMC), an introductory session, and a discussion of the work plan for the Aguirre BESS project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Gilberto Sucre, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), RGE Jose Robles Construction team lead and Sargent and Lundy design team lead Franklyn Colmenares. Topic discussed: Meet all team members, Scope of Work, Schedule, Commercial, Project Communication, General safety and quality control / quality assurance.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review the attachment D technical specification for BESS Civil Work Contract (CWC). Review applicable QAQC regulations for the project, included designer proposal documents for prepared presentation about concrete specification in the project construction requested by DCMC site manager of Costa Sur facilities site.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 134 | 268 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Gilberto Sucre, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), RGE Jose Robles Construction team lead, design team employee (Sargent and Lundy) Dean Ennes and employee (CD Smith) Franklyn Colmenares. Topic discussed: Meet all team members, Scope of Work, Schedule, Commercial, Project Communication, General safety and quality control / quality assurance.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on construction planning considering duration days in general guides for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on construction planning preliminary schedule for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on comments in contractor RGE preliminary construction schedule considering possibles corrections, expand work activities and adding activities in scope for employee (DCMC) Andres Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on teams meeting related to comments in contractor of RGE preliminary construction schedule considering possibles corrections, expand work activities and adding activities in scope for employee (DCMC) Andres Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Continue review Cambalache Power Plant BESS RGE Quality Control Plan, Concrete preparations and Installation of Embedded Items, Preparation of Form Surfaces, Placing, Slabs and Order of Placing for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended Costa Sur BESS Kickoff Meeting RGE Contractor to discuss contractor responsibilities and project scope. Attendees: DCMC: Gilberto Sucre, Carlos Bayron and other DCMC staff. RGE: Jose Segarra. S&L: Kuczynski, Mike.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Formulating a project-specific weekly template based on comprehensive metric insights to help project managers evaluate performance, reduce risk, and make better decisions for BESS, Peakers and Microgrid project progress.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue formulating a project-specific weekly template based for BESS, Peakers and Microgrid project progress.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 122 | 366 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Designing a customized weekly report template through comprehensive evaluation of collected project metrics to provide a snapshot of project health, allowing early identification of issues and implementation of corrective measures.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Marc Maceira (Honra) to discuss Genera team projects report access.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Abraham Velazquez, Gilberto Sucre. CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares, Enrique Laya. Genera: German Nunez.
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Fuel for site visits and travel from Genera offices to CVP , facilities throughout the southern portion of the island
2025-06-19 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 46.69 | 0.7 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Traveled to Yabocoa Gas Turbine for site inspection and offices trailers installed.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Mike Merritt, Gilberto Sucre, Frances Vallejo, Lauren Wells and Ada Diaz, DCMC. Discussed update on project, job offers, PROCORE workshop schedule, logistics, other interviews, trailer set-up, safety, schedule for locations.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 reviewed notes from days meetings about Peaker's project and comments responded to email inquiries for the Peaker projects
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated weekly discussion for the Peaker project management team. Reviewed current status on contractors' proposals, drawing updates, specifications recently submitted for review. Attended by: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 225 | 675 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal paperwork, reviewed notes and comments from Costa Sur meetings, reviewed emails for each Peaker project and responded accordingly for weeks of comments.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Meeting to discuss possible additional scope of work to Costa Sur and Yabucoa projects adding temp. generators. Attendees: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Morning Call with Site PM's to get project updates Jose Lopez - Aguirre Carlos Rodriguez - Costa Sur Eduardo Rivera - Vega Baja All DCMC
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Review legal correspondence to Homeca Recycling, and got final word form Jesus Cintron - Genera their disqualification for the next phase due to their EHS Incidents on Phase I. Memo Issued to ARG Ceres on qualified contractor selection for the demolition phase.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly Procore Projects Implementation and use by site teams review with Franklyn Colmenares - CSA Group and Lauen Wells DCMC. Other participants: Luis Roman and Gilberto Sucre - DCMC
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Management Project Meeting. Weekly Progress meeting to update Contract Status & Change order, Tariffs, Payment Milestones, Shipment & deliveries Logistic, NDA's for Installation Contractors and Long-Term Service Agreements. CDM Smith - Gabriel Perez CSA Group - Franklyn Colmenares DCMC - Rafael Calderon & Gilberto Sucre Tesla Energy -Michael Grabstein & Allin Luong
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reporting alignment meeting with DCMC Site Managers and Raissa Borgess DCMC. One Pager Template to be updated and presented each Friday to discuss main weekly activities and risk items. Jose Lopez, Carlos Rodriguez, Eduardo Rivera, Andres Concepcion, Gabriel Morales, Raissa Borges and Gilberto Sucre - All DCMC
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting _ Main Topics covered Recruitment Status, Procore Implementation, Trailers & Facilities, Safety, SOP's and Infrastructure. DCMC Present: Frances Vallejo. Mike Merritt, Lauren Wells, Anneilia Holton, Ada Diaz, and Gilberto Sucre.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.25 |  | 225 | 281.25 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore - DCMC Financials SOP's continued development of procedures and administration rights for the different budget scopes. DCMC and Procore Team work together. Lauren Kennedy - Procore Lauren Wells, Rafael Calderon & Gilberto Sucre - DCMC
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence Update and preparation of action items for following week.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Budget tool items from follow up of SOP's call.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Abraham Velazquez (DCMC) to discuss Procore items for Peakers Projects.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Procore Weekly Q&A with Luis Roman (DCMC), Theresa Perez (DCMC), Paola Arroyo (DCMC), Johanna Diaz (SMC), Rafael Pabon (CDM Smith).
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items for Procore questions in emails from users.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on more correspondence items for Procore users.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on more Procore permissions for distribution lists.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore weekly tasks items in tracker.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Jack Darnall (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt (DCMC) to discuss program staffing and overall program goals.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Glorimel Torrado (DCMC), Gilberto Sucre (DCMC) to discuss Procore Budget SOPs.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in the DCMC pre-meeting to align on project updates and coordinate next steps across ongoing initiatives in preparation for Monday client meeting. Attendees included José Ralat, Esther Rohena, Eisha Mercader, D'Alexzander Gonzalez, Anneilia Holton, Glorimel Torrado, and Cynthia Ortiz from DCMC and Shellsea Maysonet (SMC) The meeting facilitated cross-functional collaboration and reinforced alignment on priorities.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continuing Review the documentation about EHS in Cambalache site project. Working session of Genera EHS for Luis Vega (Rullan Ruiz Group) to Vega Baja site visit. Review the Vega Baja documents in Procore. Review document about Cambalache Genera project about security bridge.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review the documentation about EHS in Cambalache Genera Project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordinate workshop @ ARG personal Ing. Pedro Suarez about EGH Genera modules. Conference call with Gilberto Soto (DCMC) about Vega Baja Genera Projects. Conference call with Jose Lopez (DCMC) about electrical installation in Yabucoa Turbine Gas site. Conference call Gilberto Sucre (DCMC) about status the offices trailers office. Conference call with Andres Concepcion (DCMC) about Cambalache Genera Projects. Conference with Franklyn Colmenares (CDM SMITH) about bridge status in Cambalache Genera projects. Review the documentation about Cambalache and Aguire Genera projects.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and analyze the SOP's for the Procore implementation for BESS and Peaker projects.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Weekly Procore meeting to discuss Procore financials, Procore SOPs and pending matters for BESS and Peaker project. Participants: Lauren Wells (Lemoine) and Franklyn Colmenares (CSA).
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Meeting with site managers for the BESS project (Vega Baja, Cambalache, Yabucoa, Aguirre). We discussed pending status, needs, RFPs, contracts approval and next steps. Participants: Gilberto Sucre (DCMC), Andres Concepcion, Gabriel Morales, Jose Lopez and Eduardo Rivera (DCMC).
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet Participated in discussions with Winnie Irizarry, Jesus Cintron and Ricardo Pallens (Genera) regarding two letters received from PREPA. The first letter addressed the ER1 Cost Share Program and its potential implications for all FEMA-funded projects, prompting a detailed conversation on funding strategy, program eligibility, and the anticipated impact on project execution. The second letter focused on the operational status and planning considerations for specific units at the San Juan and Palo Seco Power Plants. Discussions centered around how these communications affect Genera’s ongoing project planning, regulatory compliance, and coordination with both federal and local stakeholders.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4826 -Supported Genera’s Regulatory team in drafting a formal explanation outlining the various modifications made to the contract over time (bonding requirement, price, etc). The objective was to provide FOMB with a clear, comprehensive record of the contract’s evolution to support ongoing compliance and approval processes. Shared the initial draft with Ricardo Pallens and Jesús Cintrón (Genera) for review, incorporated their feedback, and finalized the document for internal review and sign-off.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet ¦ Participated in the PMO catch-up meeting with Ricardo Pallens and Jesús Cintrón (Genera). Discussed the current status of the BESS and Peakers projects, with a focus on pending FOMB approvals and outstanding RFIs. The conversation centered on aligning next steps, identifying critical path items, and ensuring timely resolution of outstanding documentation to keep both projects on track.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 187525 - Supported Genera’s Regulatory team in updating the response to FOMB’s RFI. Drafted the written response, gathered all required attachments, and organized the materials into a complete and well-structured submission package. Ensured the information provided was accurate, aligned with the contract amendments, and responsive to FOMB’s specific inquiries.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Updated the ER1 Cost Share Program letter based on converstion with Winnie Irizarry and Jesus Cintron (Genera).
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Performed additional testing on the Genera Connect Financial Tracker platform and validation of the Financial Tracker report following confirmation from Keyla Sierra at Integrum that the uploaded report file values were correct. Despite the validation, discrepancies in KPI reporting persisted during testing. These issues will be escalated for further troubleshooting to ensure accurate data processing and display within the platform.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 |  | 184 | 46 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Sent an email to Jean Gonzalez from Genera PR requesting the expansion of access to the Genera Connect Timesheets platform across the power plant networks. This expansion is intended to enable additional Genera PR personnel to accurately report hours worked on federally funded projects, supporting compliance and comprehensive time tracking.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Began reviewing the questions for RFP 235021 provided by Cynthia Ortiz from DCMC to support the proposal process. Conducted testing on the recent update to the Genera Connect Financial Tracker related to expense tracking and identified a discrepancy in the KPI reporting. Communicated the issue to Keyla Sierra from Integrum, including reproducible steps, to facilitate timely troubleshooting and resolution.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore. JHA for safety purposes, making sure Homeca compliance on site. Present while Javier E Bidot associates mark the field for next phase. Day 2
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continued the review of Attachment D – Technical Specifications for the Battery Energy Storage System (BESS) Civil Work Contract (CWC). Focused on validating compliance with applicable construction safety regulations and confirming that all civil work specifications meet the established safety and quality standards for the project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Luis Roman, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), Meeting to review project controls on Procore specific to creating, sending, reviewing, receiving submittals and RFI. Specific modules to Procore file location and nomenclature for proper classification and organization of project controls and files.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Request for proposal details on surface removal general requirements, protection systems, unsutable trench bottom soils, excavation width, stock piling and dewatering. Review of specifics of bedding and backfill and steps associated to this process that include compacting, placing and testing.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Luis Roman, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), Meeting to review project controls on Procore specific to creating, sending, reviewing, receiving submittals and RFI. Specific modules to Procore file location and nomenclature for proper classification and organization of project controls and files.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Meeting with Javier Arroyo from J Arroyo Enterprise Inc. (Electric Contactor) to discuss the proposal, materials and quotation to energize the Yabucoa Site Mobile office.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue with the Set-up process of the Yabucoa site mobile office installing the stairs of the rear door of the office. Also, the door closers and bug guards were installed to enhance safety, security, energy efficiency, and accessibility.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa A meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Carlos Rodriguez, Jose Lopez (DCMC), and other project team members to discuss key aspects of the ongoing project activities and Reporting Alignment with the different Site Managers.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Inspection to the work performed by SA Facias and Duenas Trailers to the interiors of the Yabucoa Site Mobile office.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review the attachment D technical specification for BESS Civil Work Contract (CWC). Review applicable safety regulations for the project and review Proposal for Genera’s RFP-4899 30 MW Battery Energy Storage System Installation at Costa Sur Minimum Qualification Requirements
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Luis Roman, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), Meeting to review project controls on Procore specific to creating, sending, reviewing, receiving submittals and RFI. Specific workshop to Procore file location and nomenclature for proper classification and organization of project controls and files.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading, review and response emails of BESS_Aguirre: Meeting 1 - Contractor Kick -Off Meeting Minutes and "Attachment J" "Health, Safety and Environmental". Review the Safety General Contractor Items, Safety Protection for an Excavation: 1. Pre-Excavation Planning, 2. Excavation Support and Shoring, 3. Access and Egress, 4. Edge Protection and Barricading, 5. Hazardous Atmosphere Monitoring, 6. Water Control, 7. Equipment and Material Management, 8. Worker Modules and Communication, 9. Emergency Preparedness, 10. Ongoing Monitoring and Supervision
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review of Good Practices for a Hydration Plan in Construction Works: 1. Purpose and Importance, 2. Key Elements of the Hydration Plan: Availability of Drinking Water, Encouraging Frequent Water Intake, Monitoring and Scheduling Breaks, Education and Modules, Alternative Hydration Options, 3. Seasonal and Weather Considerations 4. Monitoring and Supervision 5. Worker Feedback and Continuous Improvement
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS job site. Daily project coordination and project management. Project Documents Overview: Analyzing the documents' status in the Procore platform, loading preliminary drawings into the PROCORE platform, working and reviewing the Kick-Off meeting minutes, and preparing a draft for distribution.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - had a meeting with DCMC Site Managers Staff with Gilberto Sucre DCMC in regards to discussing the Reporting Alignment with DCMC Site Managers from Central Costa Sur (Carlos Rodriguez), Yabucoa, Gabriel Morales, Cambalache, Andres Concepción, and Vega Baja (Eduardo Rivera).
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane MariaGenera PR ¦ AGUIRRE BESS PROJECT, Daily project coordination and project management. Project Documents Overview and analyzing the documents' status in the Procore platform. Had a Call with Basilio Ramos from Sunset Contractor to follow up on the Demolition Phase II proposal for the VEGA Baja BESS Jobsite.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria AGUIRRE BESS PROJECT; Participated in Team Meeting with Sargent & Lundy Staff, Robert D. Molner; Gilberto Sucre (DCMC), Enrique Laya, Gabriel Pérez, Franklyn Colmenares, (CDM Smith), and Angel Alicea Rodríguez (Sargent & Lundy) to discuss the Phase II Request for Clarifications to the contract (4339_9510) documents.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria Documents submitted under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual are evaluated, where the content is analyzed and notes are made for general client evaluation and changes by the contractor.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The documents evaluated were the following: Confined space permits and confined space program to ensure it contains essential guidelines for safely managing confined spaces and addressing regulatory frameworks for implementation in the Cambalache project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Jorge Mercado - DCMC Partners to discuss the Safety Submittals process review and next steps to complete a response and request additional information to complete the safety procedures review.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued Review of the project General Contractor Quality Control Plan received as submittal (RGE-0009) by (Jose Segarra - RG Engineering). Observations documented to ensure items are corrected and properly implemented.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued review of the Quality Control Plan by RG Engineering submittal evaluation. Compared with project technical specifications and elaborated a review plan for the team.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Managed various project items for the construction management (1) Coordinated and distributed to Contractor (RG Engineering) the set of design drawings via Procore. (2) Coordinated with Jean Menay - DCMC Partners the potential solution to review the structural capacity of the access bridge in Camabalache. (3) The review of technical specifications and request of pending specifications to designer (Mike Kuscynski- Sargent and Lundy) and the request to Gilberto Sucre - DCMC Partners the latest contract documents of the project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Cambalache's site team (Luis Duque and Luis Damudt - DCMC Partners) to discuss a plan for the review of the RG Engineering Quality Control Plan submittal.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with BESS program Site Managers and Gilberto Sucre, Raissa Borges, Frances Vallejo - DCMC Partners to align general program action items and reporting systems to be executed.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with punch list item and project closing. Javier Vidot (surveyor contractor) personnel continue working with survey for as-built drawing. Continue reviewing the schedule of valance versus proposed cost estimate. Javier Vidot personnel have completed the survey of the area for VB.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Vega Baja punch list. Javier Vidot (surveyor contractor) personnel continue with the land survey for generating final as built drawing. Send email to Cesar Sanchez of Luma in request to disconnect the feeder cable to the MPT of Genera. Reviewing ARG schedule of value with the proposal cost estimate for second phase of Vega Baja project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Vega Baja demolition project closing with Homeca. Review project site for punch list closing items. Homeca continue with survey of Vega Baja with Javier Vidot (surveyor contractor). CES inspector Carlos Oquendo arrive to project to collect data for final inspection report for Vega Baja BESS projects.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Meeting Vega Baja BESS - Organizer Raissa Borges and Gilberto Sucre of DCMC for the Reporting Alignment with Site Managers of each project site.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a structured cycle count across inventory zones CL 001 to CL 009, CM 001 to CM 008 focusing on the accurate reconciliation of physical stock with system-recorded data. The process involved validating count sheets, confirming item location accuracy, and reviewing unit-of-measure details to ensure consistency across all entries. Warehouse staff were engaged in bin verifications, proper tagging checks, and count variance resolution. Emphasis was placed on maintaining audit trail documentation and ensuring that any discrepancies identified were properly documented for follow up. This cycle count served to support ongoing efforts to strengthen inventory visibility and control within the Costa Sur warehouse.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Costa Sur warehouse, developed a consolidated inventory performance report for Mr. Anthony Vega of Genera PR. The report integrated data from BD 070 to BD100, CL 001 to CL 009, CM 001 to CM 008, AN 025 to AN 043, AJ 049 to AJ 055, focusing on catalog ID reconciliation, stock variance analysis, and compliance with inventory thresholds. The assessment highlighted cost discrepancies, physical mismatches, and operational inefficiencies to support transparency and corrective planning.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a variance-focused inventory recount at Costa Sur warehouse alongside Mr. Hernan Machado from DCMC. The effort concentrated on identifying deviations between physical stock and system-reported quantities across locations CL 001 to CL 009, CM 001 to CM 008. Key activities included isolating root causes of bin level discrepancies, evaluating potential data entry errors, and assessing procedural breakdowns impacting stock accuracy. Findings were documented to support corrective actions and enhance alignment between operational execution and inventory records.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC. The recount focused on validating current stock levels by physically confirming item quantities, assessing bin utilization, and verifying label accuracy. Special attention was given to identifying mismatches between actual inventory and system entries, ensuring corrections were properly documented. The effort supported data integrity across storage zones CL 001 to CL 009, CM 001 to CM 008 and reinforced compliance with warehouse tracking standards.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-prepared for upcoming cycle count operations at Costa Sur warehouse by conducting a detailed inventory data review and developing system-aligned count worksheets. Activities were coordinated with Mr. Hernan Machado from DCMC, with a focus on procedural readiness and compliance. Key preparations included validating item master data, identifying required materials such as count sheets, and bin labels, and organizing these resources to ensure an efficient and structured execution of the cycle count process.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted and early morning safety-focused operational briefing with Juan Vallejo, Hernan Machado, and key DCMC warehouse personnel. The session reinforces adherence to safety protocols during inventory handling, proper use of PPE, and hazard identification within active storage zones. Staff were reminded to maintain clear walkways, secure materials properly, and report unsafe conditions immediately. Emphasis was placed on fostering a safety-first culture while maintaining compliance with operational standards.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails Weekly BESS update based on administrative projected data provided by CDM Smith/Genera as of June 20, 2025 and Submittals Cambalache: Submittal Distributed: (#RGE-0006.0: BESS CAMBALACHE CONCEPTUAL STRUCTURAL STEEL DRAWINGS) on Procore
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) to Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Discussion Quality Control Plan with Andres Concepcion and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents reviewed CERTIFICATION 3 REV for Homeca Recyclers to pass up to management to ensure compliance and mitigate risks.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly construction meeting with Eduardo Ramos (Homeca Recyclers), Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith), Gilberto Soto (DCMC) and went over Project Documents Overview and analyzing documents status in the Procore platform and all the punch list items created Today Item #33. Reviewed CERTIFICATION 3 REV for Homeca Recyclers to pass up to management.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety while cleaning the Vega Baja site. Removal of equipment on site. Uploaded photos and notes to Procore. JHA for safety purposes, making sure Homeca compliance on site. Present while Javier E Bidot associates mark the field for next phase. Day 2 completed
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AJ049 to AJ055 to begin the cycle counts.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AN025 to AN037
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AN025 to AN037
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AN025 to AN037
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AN025 to AN037
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AN025 to AN037
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CL 00 001 to CL 00 009 and CM 00 001 to CM 00 008
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations CL 00 001 to CL 00 009 and CM 00 001 to CM 00 008
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations CL 00 001 to CL 00 009 and CM 00 001 to CM 00 008
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations BD 070 TO BD 100 at the Aguirre warehouse to start the cycle counts.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BD 070 TO BD 100, RECOUNT LIST # 1131/1149
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BD 070 TO BD 100 LIST # 1125/1126
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BD 070 TO BD 100
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1141, 1142 and 1148 from locations AJ049-AJ055 for a total of 263 pcs.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AJ049-AJ055 Cycle Count List # 1136, 1143 and 1144.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 151 | 604 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Meeting on site with the DCMC Costa Sur Peakers team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), Meeting to review project controls on Procore specific to creating, sending, reviewing, receiving submittals and RFI. Specific modules to Procore file location and nomenclature for proper classification and organization of project controls and files.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/GEN 01 Financial Data Management Review & Process (S&L) Documents
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management / Create Procore Report by Company/User/Permission Assigned/Coordination of Documentation Process with Lauren Wells DCMC_Luis Ramon DCMC_Johanna Diaz DCMC/ Costa Sur Peakers Data Review & Process/Daguao Data Review & Process
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the contractual requirement for the three power plants that will be covered on the Peakers Equipment Supply Kick-off Meeting (Yabucoa, Jobos, and Daguao) to analyze the feasibility of joining power plants in a singular Procore project. Currently, not feasible due to funding requirements per project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Call Meeting with Abraham Velazquez (DCMC) to discuss the inclusion of 3 projects in one Procore database for the Peakers Equipment Supply, while pointing out pros and cos of having only one project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Interact at the Company Level with the Distribution Groups that are going to be used inside every project and its management tools; review current organigram and main players to be specified between Peakers and BESS management groups.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Internal Meeting hosted by Franklyn Colmenares (CSA), joined by Lauren Wells (Lemoine), Mike Kuzcynski and Ivette Miranda (S&L), Gilberto Sucre (DCMC) and Rafael Pabon (CDM Smith). Discussed the current open topics on the Procore Platform such as pending Issued for Construction drawings and specifications to be uploaded, current SOP status, upcoming tasks and challenges due to work load, and the potential opening of Financials Tool.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Discuss with Abraham Velazquez (DCMC) the possibility or to discard the idea of joining 3 projects in only one Procore project (Yabucoa, Jobos, and Daguao): review contractual and funding requirements to develop proper document data base for every project with its respective PW number and scope.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.75 |  | 149 | 260.75 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, Tesla, Siemens, Javier Bidot, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. This allows a better preview for pending invoices to be worked on next week and organize week plan.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Financials Meeting with Lauren Kennedy from Procore and DCMC participants: Glorimel Torrado, Lauren Wells and Gilberto Sucre, also participates our subcontractor Ginnell Torres (MZLS). This meeting was to discuss about the budget tool.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Genera & Tesla Management Meeting. This is a recurrent meeting, I participate in substitution of Rafael Calderon (DCMC) that was sick today. In this meeting the team discuss important action items regarding Tesla project like Insurance, Amend and Restate, Missing transformer weight and weel spacing, and other. Participants: Gabriel Sepúlveda (CDM), Mike Kuczynski (S&L), Franklyn Colmenares (CDM), Gilberto Sucre (DCMC), Glorimel Torrado (DCMC), and from Tesla team: Elizabeth Arentsen, Allin Luong and Michael Gabsten.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Eisha Mercader, Anneilia Holton and Cynthia Ortíz. Also, Marc Maceira from Honra, and Shellsea Maysonet (SMC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Continue sending reminders to the Vega Baja communities to keep them informed about the upcoming community meeting in Vega Baja, ensuring the message includes the date, time, and location.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Begin the research process to identify nonprofit organizations that could be positively impacted by the BESS and Peakers project has been completed. The effort focused on organizations aligned with areas such as energy resilience, environmental sustainability, and community development. A structured template was selected to organize the findings, including fields like mission, location, relevance to the project, and potential for collaboration.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Write a formal email to Jorge Bracero, from Genera PR, summarizing recent updates. Inform them that the updated presentation with the requested changes has been completed and is attached to the email. Let them know that the printed project information sheet now includes an extra page for notes or questions, and pens will be available for attendees.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Ensure the final version of the BESS Project fact sheet is ready for printing and prepare a folder with all communication materials to be distributed to the Vega Baja community, including the informational sheet, visual materials, attendance sheet, and any other relevant resources; verify that all content is up to date, in printable format, and ready for distribution on the day of the event.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Completed revisions and edits for the informational page on the BESS and Peaker Units projects. Write a formal email to the Genera team on behalf of Jorge Bracero to announce the completion of revisions and edits to the BESS and Peaker Units informational page.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Review Cambalache RGE Submittal Quality Control Plan, Mansory plan, Mortar, Protection During Construction and Cold Weather Protection preparations and forms for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Continue reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 22 pages.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Start reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 27 pages.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria –Review applicable QAQC regulations for the project, included designer proposal documents for prepared presentation about concrete specification in the project construction requested by DCMC site manager of Costa Sur facilities site. Review the attachment D technical specification for BESS Civil Work Contract (CWC).
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Luis Roman, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), Meeting to review project controls on Procore specific to creating, sending, reviewing, receiving submittals and RFI. Specific modules to Procore file location and nomenclature for proper classification and organization of project controls and files.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on comments in contractor RGE preliminary construction schedule in activities considering updated issue for construction drawings structural, concrete drawings of new wharehouse, BESS site area for create a report of missing activities for employee (DCMC) Andres Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with DCMC team (Luis Roman, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), Meeting to review project Procore controls, submittals acceptance or closed settings and email link with management tools applying considering Genera RFI, submittal and specification due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Review Cambalache RGE Submittal Quality Control Plan, Mansory plan, Clay Masonry and Concrete Masonry preparations and forms for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 122 | 244 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Supporting the development of the financial process diagram to ensure efficient resource allocation, and strategic decision-making for Genera projects, emphasizing on Procurement processes to streamline integration with Procore.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 122 | 244 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Supporting the development of a comprehensive financial process model to estimate costs, track project expenses, and allocate resources effectively for Genera projects BESS & Peakers. Placing targeted emphasis on optimizing Procurement workflows to facilitate integration on Procore platform.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 122 | 427 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Finalizing collecting projects information and status for the weekly report with comprehensive updates on the Genera projects: Battery Energy Storage Systems (BESS), Peaker Units, and Microgrid projects.
2025-06-20 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting "Reporting Alignment with Site Managers" with DCMC BESS team: Gilberto Sucre, Andres Concepcion, Carlos Rodriguez, Eduardo Rivera, Jose Lopez and Gabriel Morales to discuss and schedule upcoming sessions to present project updates and outline how the reporting analyst will gather the project updates from site managers.
2025-06-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 992.72 | 992.72 | 992.72 | Yes | 146794 |  | T-Mobile for Business. June charges for hotspots and cellphones for Genera Deliverable 11 project.
2025-06-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 |  | 167 | 626.25 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Supervise the electrical work performed by Eric Arroyo, Angel Amaro and Javier Arroyo from J Arroyo Enterprise to connect and energize the DCMC Mobile Office.
2025-06-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 895 | 895 | 895 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel expenses to meet with Genera team onsite to support Grant Management process improvement. American Airlines airfare from Oklahoma City OK to San Juan PR for $895.00
2025-06-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 217.81 | 217.81 | 217.81 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I stayed at Airbnb at 7 Calle Cervantes, San Juan, PR 00907-1315, US while visiting the Genera team. The nightly cost was $217.81 per night.
2025-06-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 111 | 111 | 111 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Travel from home of record to Puerto Rico
2025-06-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 fuel to go to JOBOS site and Yabucoa sites to start site layout
2025-06-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 8.05 | 0.7 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Mileage to drive from office to airport for an onsite meeting with Genera team.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items, returning email and answering questions about Procore.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended meetings of constructability of the latest design. Items discussed what to VE of not and what we can retro fit versus demo and new tank. Attended by Carlos De Jesus DCMC Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC Harry Del Valle DCMC
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in meeting BESS & Peaker's Project Needs Discussed each projects immediate needs and concerns with ownership. Attended the meeting: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gilberto Sucre DCMC Frances Vallejo Rosich DCMC Carlos De Jesus DCMC Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC Harry Del Valle DCMC Foster Veazey DCMC Jean Pierre Menay DCMC
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in meeting; Peakers Check In. Discussed latest updates from design and when equipment can be delivered worse case and best-case scenario's. Attendees: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gilberto Sucre DCMC Frances Vallejo Rosich DCMC Carlos De Jesus DCMC Harry Del Valle DCMC
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal paperwork, reviewed notes and comments from BESS & Peaker's Project meetings. Reviewed correspondence and inquiries for the Peaker projects.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Peakers Needs meeting with Genera. Jesus Cintron was not able to attend but German Nunez Genera took the lead. Main topics * Sargent & Lundy's design status * Design Approval Process by Genera to be implemented * A/E Detailed list of deliverables with budget/spent to date/ % complete/forest cost& Schedule to complete. * Information on Temporary Gen-Sets by Prepa and their potential interference with Costa Peakers & Aguirre BESS. * Lack of Contractor Quoting Projects. Attendees: Genera - German Nunez CDM Smith - Gabriel Perez & Rafael Pabon DCMC - Abraham Velazquez & Gilberto Sucre
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PM/CM Weekly Update meeting with Gabriel Perez - CDM Smith & Franklyn Colmenares - CSA Group
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Invoice Approval Process Implementation by DCMC as requested by Jesus Cintron -Genera, with Rafael Calderon & Glorimel Torrado - DCMC.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria FASSt Generation Fleet Allocation meeting with D'Alexander Gonzalez, Jose Ralat, Rafael Calderon and Esther Rohena - DCMC and Carlos Palomares CDM Smith. Reviewed Cost reporting and forecast for the Program.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Site Visit and Civil Scope Review with Carlos Hernandez ARG Ceres and Eduardo Rivera DCMC in preparation for meeting with Sargent & Lundy.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check-in Weekly Update Meeting to update: * BESS RFP/RFC/Contracts * Site Update on Cambalache & Vega Baja * Palo Seco Pre-Demolition Activities * Costa Sur Permits * Global Design Drawings/Procore/Procurement/Permit * Global Unit Retirement List & Interconnection Studies, Tesla Participants: Gabriel Perez - CDM Smith Franklyn Colmenares - CSA Group German Nunez- Genera Gilberto Sucre - DCMC Mike Kuczynski - Sargent & Lundy
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache - FBO Contract Package review with Sheila Torres DCMC, Franklyn Colmenares - CSA Group and Francisco Feliu - Genera prior to re-submission.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence update and responses for Cambalache, Vega Baja, Aguirre, Yabucoa, Costa Sur and Palo Seco Bess program.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Project Updates calls with Carlos Rodriguez - Costa Sur, Andres Concepcion - Cambalache and Eduardo Rivera - Vega Baja all DCMC.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One to one Meeting with Sylvia Franco - DCMC to provide Schedule & Cost role & responsibilities for Vega Baja & Cambalache,
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Prepared for in-person P3 Approval Process Improvement session by finalizing the PowerPoint presentation and ensuring all meeting materials were organized and ready. Coordinated on-site logistics, including setup of the physical meeting space and lunch arrangements, to support a productive and well-structured session.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Facilitated Day 1 of the P3 Approval Process Improvement workshop with Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Focused on Step 1 of the 8-Step Problem Solving process: Clarify the Problem. Defined the standard for the P3 approval process, identified the current state, and established the gap between the two. Discussed key issues including inconsistent packaging, incomplete information, lack of clarity on program decisions, inaccurate data, unclear need dates, and delays in PFO approvals.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Met with Estefania Colon (Genera HR) to continue planning Lean coaching support for HR initiatives, including integration of Genera corporate values and meeting effectiveness efforts. Aligned on next steps and scheduled a follow-up meeting for Tuesday to discuss actionable implementation strategies.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Facilitated Day 1 of the P3 Approval Process Improvement workshop with Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Completed Step 1 of the 8-Step Problem Solving process: Clarify the Problem. Defined the standard, identified the current state, and assessed the gap in the RG-Peaker approval process. Key issues discussed included inconsistent packaging, lack of clear program communication, incorrect data, and delays in PFO approvals. Following the session, captured team action items, organized notes, and updated the Miro board. Cleaned up meeting conference room and prepared materials to support Day 2 continuity.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Met with Vladimir Scott (Genera) and Jorge Sanchez (Genera) to discuss LEADER program tools and best practices for employee engagement and conducting effective annual reviews. Shared examples, demonstrated resources, and compiled a follow-up list of practical tips and tools. Distributed materials to Vladimir Scott, Jorge Sanchez, and Joaquin Quinoy (Genera) to support implementation.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Ricardo Pallens (Genera), Carlos Palomares (CDM Smith), Joaquin Quinoy (Genera), Gabriel Perez (CDM Smith), Mike Kuczynski, Nelson Rosado (Sargent and Lundy), Franklyn Colmenares (CDM Smith), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Follow up meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for users questions.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore project permissions to troubleshoot why users were missing.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Peakers Check-in. Rafael Pabon (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Rafael Calderon (DCMC), Glorimel Torrado (DCMC), Johanna Diaz (SMC) to discuss Procore Funding SOPs.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool information based on previous meeting.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool information.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on PMO reporting information for Procore items for Raissa Borges (DCMC).
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financial tool information.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Franklyn Colmenares (CSA), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 217.81 | 217.81 | 217.81 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I stayed at Airbnb at 7 Calle Cervantes, San Juan, PR 00907-1315, US while visiting the Genera team. The nightly cost was $217.81 per night.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in the weekly Genera PR client meeting to deliver updates on ongoing projects and address key developments. Attendees included Alejandro Maymi from Genera PR, and D'Alexzander Gonzalez, Mark Merritt, Roberto Bosch, José Ralat, Esther Rohena, Cynthia Ortiz, and Eisha Mercader (DCMC) and Shellsea Maysonet (SMC). The meeting served to align stakeholders on current progress and next steps.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Conference call with Osvaldo de Jesus (GENERA) about Cambalache Genera Project. Review documentation in Procore about Vega Baja (GENERA PROJECTS). Workshop in Genera EHS given to Sylvia Franco (DCMC) and Carlos Villamil (Villamil Group). Prepare documents about Cambalache site to RGE Contractor.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review documentation submitted by RGE about Cambalache Genera Project. Conference call with Gabriel Morales (DCMC) about Yabucoa (GENERA) installation. Meeting with Andres Concepcion and Jorge Mercado (DCMC) about Cambalache (GENERA PROJECTS) documentation submitted by RGE.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended the second community engagement meeting at Vega Baja site to discuss BESS project with the community. Participants: Gabriel Perez (CDM), Jorge Bracero (Genera) and Paola Arroyo (DCMC)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers project needs meeting with Jesus Cintron (Genera) and the project management team to discuss project needs, status and updated regarding the projects.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Jorge Bracero (Genera) and Paola Arroyo (DCMC) to discuss meeting preparation, prepare power point and discuss pending matters.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peakers Check In meetings with project management teams. We discussed overall project status, RFP process, contract status and next steps. Participants: Gilberto Sucre, Abraham Velazquez (DCMC). Gabriel Perez (CDM), Franklyn Colmenares (CSA), Rafael Pabon (CDM), Sheila Torres (DCMC) and Rafael Calderon (DCMC)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Marc Maceira, Carlos González and Ginnell Torres
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Participated in an in-depth discussion on the BESS and Peakers projects in the context of the Temporary Generation Project with Gabriel Sepulveda, Rafael Pabon, Franklyn Colmenares and Carlos Palomares (CDMSmith). The conversation focused on how the deployment of Temporary Generation is impacting the scope, cost structure, timelines, and overall efficiency of both BESS and Peakers initiatives. We also addressed the operational and logistical challenges caused by the disorganized rollout of the Temporary Generation effort, which has created uncertainty around planning and execution. As a result, we began strategizing a coordinated path forward to mitigate risks, adapt project timelines, and maintain alignment with regulatory and funding requirements.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Supported the Regulatory team by meeting with María Latoni (Genera) to review and discuss pending FOMB Appendix A and Appendix D submissions for RFP 4826. Provided clarification on recent changes and their implications. Also discussed several other FOMB packages currently on hold due to missing appendices, and explored ways to improve coordination and streamline the process between Procurement, Finance, and Regulatory teams to avoid future delays.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Hurricane Maria - Participated in the weekly BESS and Peakers Project Needs meeting with Jesús Cintrón (Genera). Reviewed the current status of key workstreams and discussed high-priority items requiring coordination or follow-up. Contributed updates and aligned on next steps to ensure continued progress across both projects. Genera: Jesús Cintrón, Germán Nuñez. DCMC: Abraham Velazquez, Frances Vallejo. CDM Smith: Franklyn Colmenares Gabriel Sepulveda Carlos Palomares & Rafael Pabón.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 4473 - Reviewed the cost estimate prepared by Pedro Cabrera (DCMC) for accuracy and completeness. Reformatted the document using Genera’s approved template to ensure consistency with internal standards. Sent the finalized version to Jesús Cintrón (Genera) for review and sign-off.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet ¦ Sargent & Lundy Amendment - Reviewed the cost estimate and cost analysis prepared by Rick Patterson (DCMC). Identified missing information and followed up to request the outstanding details. To support this effort, prepared a clear and organized Excel tracker outlining the specific items pending submission, helping streamline communication and ensure timely completion of the documentation.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - RFP 4826 - Held a meeting with Gilberto Sucre (DCMC) and Franklyn Colmenares (CDM Smith) to review and finalize the RFI response, ensuring the information provided was accurate, complete, and aligned with project and regulatory requirements. Additionally, discussed the revised FOMB contract submission with Francisco Feliu and Fernando Ortiz (Genera) to confirm that all necessary updates had been incorporated and that the package was ready for final review and approval.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Verified the status of key workstreams and high-priority items related to procurement activities and contract submittals requiring approval from FOMB and P3A. This review was conducted in preparation for the weekly BESS and Peakers Project Needs meeting, ensuring up-to-date information was available to support informed decision-making and effective project coordination.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussed the approach for addressing questions related to RFP 235021 with Cynthia Ortiz from DCMC to ensure internal alignment and consistency with the client’s expectations. Additionally, reviewed the latest Financial Tracker report prior to uploading it to the Genera Connect Financial Tracker, verifying accuracy and completeness in preparation for the weekly Genera PR meeting.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Meeting with Gilberto Sucre(DCMC) Carlos Hernandez from ARG Carirma Sánchez Homeca and Nelson Soler(CDMSmith) to verify next steps for the second phase. Completed meeting.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Reviewed the design and installation manual for the Tesla Megapack battery systems to ensure proper understanding of manufacturer specifications, installation requirements, and operational guidelines. Additionally, reviewed applicable safety regulations related to battery energy storage systems to verify compliance and mitigate potential risks during implementation.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Reviewed Appendix D.1 – Design Drawings for Civil & Structure Works related to the 30 MW Battery Energy Storage System (BESS) project at Costa Sur, as included in RFP 4899. The review focused on understanding structural layout, foundation requirements, and civil interfaces critical to project execution. Additionally, reviewed applicable safety regulations for battery energy storage to ensure design considerations align with established safety standards and minimize risks during construction and operation.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Request for proposal review of details on coating systems CS-3116 specifics. Application of 3 Coat Polyamine epoxy system for concrete slabs, that includes description, use, criteria, surface preparation and approved suppliers.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Request for proposal details on conduits to be installed and supports related said conduits. Compliance and review of ASTM standard specifications; additional compliance to Institue of Electrical and Electronic Engineers (IEEE) & National Electronic Safety Code. (C2)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Review the General Information and part of the Division of Responsibility (DOR) of the in the Technical Specification Number G-3300 Scope of Services for BESS General Work Contract (GWC) that will be issued for bid.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Verify with the Duenas Trailer team the installation of the A/C units to the DCMC mobile offices because they were not working properly. It was found that the circuit braker was not working.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Supervise installation of the stairs in the main entrance of the DCMC Partners mobile office with Eric Calo from Duenas Trailers Stairs to provide safe access to the staff.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review the Appendix D.1 - Design Drawings for Civil & Structure Works for 30 MW Battery Energy Storage System at Costa Sur on the RFP 4899. Review safety regulations for battery storage.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continue with review the design and installation manual for the Tesla Megapack batteries. Review safety regulations for battery storage.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue reading and review the ATTACHMENT J HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES for Contractor, and review the Job Hazard Analysis (JHA) – General Cleaning Services Aguirre BESS – Parking Area. Supervising the works of cleaning ground areas parking carried out by Contractor Villamil Group to ensure it is done safely, complying with DCMC safety standards and policies
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre A Visual Inspection of the parking lot and the surrounding office area was conducted. Cleaning work was then carried out to improve the work area's conditions.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review Good Practices for a Hydration Plan in Construction Works for Bess_Aguirre: 1. Purpose and Importance 2. Key Elements of the Hydration Plan 3. Seasonal and Weather Considerations 4. Monitoring and Supervision 5. Worker Feedback and Continuous Improvement
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT - Continued Aguirre Bess Project contract and Specs. Overview to ensure all project participants have a clear understanding of the expectations and requirements, and understand their participation in the project’s execution.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Luis Moctezuma (DCMC) to identify existing trip hazards surrounding the Office Trailer Compound and potential issues that may arise during the construction process. Held a meeting with the contractor from Villamil Cleaning to go over the areas to be clean, and clear of debris. The Job Hazard Analysis was discussed with the contractor representative labor Saúl Santiago, prior to beginning the cleaning works.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Aguirre BESS job site. Daily project coordination and project management. Project Documents Overview and Analyzing the Issue for Bid, TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC), Spec. No.: G-3400, Revision: A; For Bid, Project No. A15240, dated June 20th, 2025, Documents' Status in Procore. Loading
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on the Review and make corrections on Quality Assurance & Control guidelines to ensure the project meet safety standards, regulatory compliance, and quality benchmarks. Prepare Spreadsheet list with status of equipment's & Material for Office Trailers, in Cambalache, Costa Sur, Aguirre & Yabucoa projects.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Duenas Trailers A/C technician to verify new A/C units installed in trailer office in Yabucoa Gas turbine. Mr. Eric Calo (Duenas Trailers), Gabriel Morales (DCMC) & Harry Del Valle (DCMC). Discussed that the HVAC system is installed correctly, in compliance with local building codes and installation will maintain units efficiency.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of the licenses and certifications issued by the contractor RGE continues. These competencies apply to the personnel assigned to the Cambalache site, who will be responsible for the use and handling of heavy equipment. This includes personnel in charge of lifting materials with cranes. Notes are being compiled for discussion with the contractor RGE.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria -An evaluation of the licenses and certifications issued by the contractor RGE is being conducted. These competencies apply to the personnel assigned to the Cambalache site, who will be responsible for the use and handling of heavy equipment. This includes personnel assigned to lifting materials using cranes.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria, Meeting through the Teams platform with Jean Pierre (DCMC) and Andres Concepcion (DCMC) where the results of the evaluation of safety documents sent by RGE as part of the requirements prior to starting activities on site were discussed.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria An evaluation of the occupational health and safety program submitted by the contractor, RGE, is conducted. This evaluation is specified in the section on storage and handling of chemical materials. Notes are made regarding points for improvement to be discussed with the contractor, RGE.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued evaluation of project construction schedule to make observations and comments to advance activity review for future Construction Schedule to be submitted by contractor (RG Engineering)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Phone call meeting with Jose Segarra (RG Engineering) to follow up on important project items regarding pending RFIs responses and a Value Engineering proposal.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Jean Pierre Menay and Jorge Mercado (DCMC) to discuss the Submittal #RGE-0009 regarding Safety Plan for project. Went trough observations and planned the review and response process prior sending to GeneraPR for approval.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Managed the Request for Information (RFI # 20) regarding TESLA Megapacks 2 XL drawings. Organized files and coordinated the response via Procore to contractor (RG Engineering). Reviewed drawings and documented in project folder.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed and prepared the Construction Weekly meeting agenda and discussion topics to be covered. Planned and included project action items for follow up with project team (RG Engineering, Sargent and Lundy, GeneraPR and DCMC Partners)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Performed multiple project management tasks: (1) Organized the project action items and provided to Gilberto Sucre (DCMC) (2) Escalated pending and overdue submittals/RFIs to Gilberto Sucre (DCMC). (3) Managed several submittals workflows to complete responses in Procore with Luis Duque (DCMC).
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - DCMC Frances Vallejo and Eduardo Rivera, CDM Smith Gabriel Perez Sepulveda - Meeting with Vega Baja community to provide information related to BESS project.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Site construction meeting with ARG Carlos Hernandez, Homeca Carirma and Eduardo Ramos, DCMC Jaime Pesquera, Gilberto Soto, Gilberto Sucre and Eduardo Rivera and CDM Smith Nelson Soler. Meeting to review construction work at project site area and discuss RFP issue and concern.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Homeca agenda meeting for tomorrow construction meeting. Working with ARG/CERES agenda meeting for tomorrow construction meeting. Preparing for ARG site visit to project to discuss project areas of construction.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue reviewing construction drawing IFC for second phase. Reviewing the SOV versus RFP proposal. Reviewing specification for construction second phase. Send email to ARG Carlos Hernandez to see if they can provide schedule for the project. Receive at site Frances Vallejo of DCMC for meeting with Vega Baja Major to provide feedback of project status.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing email and reports on Procore and preparing for meeting with Vega Baja Major to provide project status.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed schedule cycle count procedures for inventory zones CA 060 through CA 072, with a focus on validating physical inventory against system-reported quantities. The count process included verification of item master records, bin-level quantity checks, and inspection of label accuracy and environmental storage conditions. Anomalies such as missing, mislocated, or misclassified materials were flagged for immediate review. This activity directly supported data integrity, enhanced reconciliation accuracy, and reinforced control mechanisms within the inventory management system.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a variance investigation for zones CA 060 through CA 072 to identify recurring mismatches between physical counts and system records. The review focused on tracing transaction history, catalog accuracy, and system entry timing to determine root causes and reinforce inventory control compliance.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco warehouse, prepared a consolidated inventory performance report for Mr. Anthony Vega from Genera PR. The report integrated key metrics such as catalog reconciliation, stock validation, and discrepancy analysis across multiple warehouse zones. The assessment provided visibility into cost variances, stock compliance, and operational status, supporting data-driven decision-making and executive-level transparency. Locations reviewed range from BD 100 to BD 150, CA 060 to CA 072, AH 001 to AH 005, AH 029 to AH 036, CN 001 to CN 008, CO 001 to CO 007.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a bin-level inventory recount across zones CA 060 through CA 072 to address discrepancies flagged during prior validations. Focus was placed on verifying physical quantities, confirming correct item placement, and updating records to ensure inventory accuracy within the system.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a morning job briefing with Hernan Machado, Juan Vallejo, and key DCMC warehouse personnel to outline work priorities for the current week. The session emphasized adherence to inventory procedures, safe operational practices, and accountability in daily tasks. Staff were reminded of the importance of accurate data entry, timely execution of assigned duties, and strict compliance with safety protocols. Discussion included expected deliverables, schedule coordination, and maintaining alignment with project goals while minimizing risk and ensuring operational continuity.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-prepared cycle count documentation at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC. Activities focused on validating system data, aligning physical storage locations with system mappings, and staging materials required for the upcoming count. Special attention was given to organizing worksheets by zone, confirming bin-level readiness, and standardizing procedural steps to ensure controlled and efficient execution of the full inventory.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review completeness of documentation for packages ), 221117 (Demin Water Resin), 221853 (Switch Gears 4 kV), 225589 (Spill Over, Cold Reheat & Superheater Turbine Steam Seal Valves) and 225916 (Boiler Feed Water Pumps) as released by the evaluation panels; upon issuance of their determination, proceed with the subsequent procurement process.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review completeness of documentation for packages 4454 (Starting Frequency Converter Transformer), 220871 (Cooling Tower Motors), 220919 (Bunker-C Fuel Oil Pump) as released by the evaluation panels; upon issuance of their determination, proceed with the subsequent procurement process.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC: DAlexzander Gonzalez, Jose Ralat, Rafael Calderon, Eisha Mercader, Roberto Bosch, Victor Maldonado, Pedro Cabrera, Christian Cruz, Sheila Torres, and Glorimel Torrado; from Genera Alejandro Maymi, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 3 - Concrete and DIVISION 4 - Masonry
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 2 - Site Work and DIVISION 2 - Concrete
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 2 - Site Work and DIVISION 2 - Concrete
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 1 - Project Quality Program and DIVISION 2 - Site Work
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents reviewed punch list. Had technical issues with the site/trailer internet. The internet was up and down, and we could not get it back up for a while. Called Aeronet to get some commercial quotes in order to find alternatives to the connection issues.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents reviewed punch list (added 2 more items to the list item # 34 iron rods sticking out & item #35 main diesel tank area membrane disposal).
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we will hold a meeting with Gilberto Sucre(DCMC) Carlos Hernandez from ARG Carirma Sánchez Homeca and Nelson Soler (CDMSmith) to verify next steps for the second phase.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 - Pro-Core Meeting: Procore - DCMC Financials Tools - review new ProCore functionalities to process and document invoices, contract balance, PWs and discussed workflow streamline opportunities within DCMC Team. This tool will facilitate invoice review process and accurate contract balance for all Genera projects including BESS and Peakers. Participants from DCMC - (Rafael Calderon) and from Lemoine Lauren Wells.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA / BESS Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between Tesla team, CDM Smith PM team (Gabriel Sepulveda), Sargent & Lundy ( (Mike Kuczynski) Miguel Del Valle, Nelson Rosado), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Gilberto Sucre, Foster Veazey, Paola Arroyo, Raissa Borges, Luis Roman, Frances Vallejo), Lemoine Procore (Lauren Wells).
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Siemens Energy Contract #00106588 and Deliverable Schedule review. Siemens Chek-In Meeting: Peakers Costa Sur project Status follow-up and review of contract schedules. Participants from Genera (Jesus Cintron, German Nunez), CSA (Franklyn Colmenares) CDM PM (Carlos Palomares), Sargent and Lundy - (Mike Kuczynski) and DCMC - (Rafael Calderon, Abraham Velazquez, D'Alexander González and Sheila Torres).
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC & Genera- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander Gonzalez, Esther Rohena, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz); Carlos Gonzalez (Integrum) and SMC Shellsea Maysonet; from Genera (Alejandro Maymi)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 _PW 11855 meeting between DCMC and CDM_FASSt Generation Fleet Allocation. Meeting to discussed budget status for the project in reference and the specific allocations based on original FEMA obligation. Reviewing budget allocation based on construction manager input. DCMC participants (D'Alexander Gonzalez, Esther Rohena, Jose Ralat, Gilberto Sucre ) From CDM (Carlos Palomares)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CA060-CA072 to begin the cycle counts.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AH29 to AH36 and AD30 to AD40
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AH 29 to AH36 and AD30 to AD40
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AH29 to AH36 and AD30 to AD40
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AH29 to AH36 and AD30 to AD40
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AH29 to AH36 and AD30 to AD40
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CN 00 001 to CN 00 008 and CO 00 001 to CO 00 007
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations CN 00 001 to CN 00 008 and CO 00 001 to CO 00 007
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations CN 00 001 to CN 00 008 and CO 00 001 to CO 00 007
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BD 100 TO BD 150 RECOUNT LIST # 1147/1152
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BD 100 TO BD 150
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BD 100 TO BD 150 LIST # 1145/1146/1147
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Prepare the lists for locations BD 100 TO BD 150 at the Aguirre warehouse to start the cycle counts.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CA060-CA072 for Cycle Count List # 1157.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1174 and 1175 from locations CA060 - CA072 for a total of 278 pcs.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Call with Theresa Perez (DCMC) to discuss the options for new user's when replacing existing users on active workflows inside the Procore Platform.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 151 | 604 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Completion Costa Sur Peakers Siemens New User Procore Access (DCMC)/ Procore Company User Permissions Template Report Completed/Costa Sur Peakers Coordination of New Users with Luis Roman (DCMC)/Completion Cambalache GENERA New User Procore Access
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /RG Cambalache Refresh Procore Profiles/ Vega Baja BESS Procore Addl User Implentation/GEN 01 Financial Data Review & Process/Siemens_S&L_CDM User List w Request Procore Certifications via Email
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Peakers Weekly Meeting hosted by Franklyn Colmenares (CSA) including Design Team staff Miguel del Valle (S&L), Lauren Wells (Lemoine), Abraham Velazquez (DCMC), Enrique Laya and Rafael Pabon (CDM Smith), German Nunez (Genera); discussing weekly open topics for the Peakers Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Weekly startup for Cambalache, Vega Baja, Aguirre and Costa Sur projects: review submittals, rfi's, ongoing issues with Procore execution and review the Documents Tool for new uploaded contractual agreements and/or amendments.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – BESS Weekly Meeting hosted by Gabriel Perez (CDM Smith) including Design Team staff Mike Kuczynski (S&L), Lauren Wells (Lemoine), Gilberto Sucre (DCMC), Rafael Pabon and Gabriel Perez (CDM Smith), Jesus Cintron (Genera); discussing weekly open topics for the BESS Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review documentation from the Vega Baja to reduce and avoid the duplication of items and documents between Project Management Tools and the Documents tool: Submittals uploaded which are common documentation and Drawings out of the typical tool arrangement.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review current execution for the response and approval of submittals; troubleshoot on freeze submittals due to change in status instead of editing the response fields.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Prepare Procore Modules Metrics Report based on users execution and progress based on time required to get users familiar with the Procore Platform: update site's field staff according to Procore execution and proper domain of Project Management tools.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review presentation for Genera/DCMC meeting and verify if information needs to be updated for this meeting. I also discussed with Rafael Calderón (DCMC) about pending invoices for signature and the new process to work that invoices with PMO approval.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Eisha Mercader, Esther Rohena, Glorimel Torrado and others. Also, Shellsea Maysonet (SMC); and from Genera: Alejandro Maymí, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Financials Meeting with Lauren Kennedy from Procore and DCMC participants: Rafael Calderón, Glorimel Torrado and Esther Rohena. In this meeting we discuss about Finance process in Procore tool. We will continue with recurrent meetings to complete this task.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Identify 10 invoices requested by Victor Maldonado (DCMC) to request RFR. I prepare a file and share this excel invoices: 90226153, 90224258, 90227815, 90231395, 90231861, 90231898, 90232782, 90232903 and 18322772.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Internal DCMC Meeting with Gilberto Sucre and Rafael Calderón to discuss Pre Intervention process and how PMO is going to integrate on the SOP. This implementation will give more compliance to the invoice since is going to have a certification that the work was completed correctly prior to our review for reimbursement and contractual compliance. Tomorrow we will have another meeting on this matter.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Siemens Milestone #2 review. I continue verifying the PO for the U2 Base Frame and U1 Air Intake. This item from milestone #2 needs an RFI to request clarification since they are not specified and has a different work package number on the PO. I made the notes in our working spreadsheet to prepare email.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 148 | 148 | 148 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Full day PerDiem
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339-meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander Gonzalez, Rafael Calderon, Gilberto Sucre, Mark Merritt, Raissa Borges, from DCMC, and Lauren Wells, Foster Veazey from Lemoine. In the meeting was the Genera PR Team: Jesus Cintron, Joaquin A Quinoy, Ricardo Pallens, Maria Sanchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczynski and Nelson Rosado. The meeting was about the Bess Project.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Travel from the Vega Baja site to Teatro América venue in Vega Baja for second BESS community meeting.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Travel from Genera's offices in Hato Rey to the Vega Baja site for community meeting-related activities of BESS project. During the trip, a stop was made to purchase a snack that would later be offered to the participants of the community meeting.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Travel back from the Teatro América venue in Vega Baja to Guaynabo after the conclusion of the second community meeting for the BESS. Present at the community meeting were: Genera Team: Jorge Bracero, Community. DCMC Partners Team: Paola Arroyo Guzman, Community Outreach Liaison; Frances Vallejo, Deputy Program Coordinator at DCMC Partners. CDM Smith: Gabriel Perez Sepulveda, BESS Manager.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 - Preparations were made at the Teatro America venue in Vega Baja for the presentation during the second BESS community meeting. These tasks included setting up the space, getting the presentation ready, and organizing the communication materials to be distributed to attendees.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- meeting via Microsoft Teams Meeting with DCMC Team: Frances Vallejo Rosich, D'Alexzander Gonzalez and Mark Merritt. In the meeting was the Genera Team: Jesus Cintron, Kevin Futch, Francisco Santos, German Nunez, Alejandro Maymi and Sarahi Medina Nieves. In the meeting was the CDM Smith: Juan Mendoza, Rafael Pabon and Carlos Palomares. The meeting was about Peakers Check In.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Presented to the Vega Baja community during the second community meeting about the BESS project. The session included a Q&A segment, a presentation of the project's benefits, its timeline, and a video showcasing the ongoing work.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Coordinate confirmation efforts to remind community members about the event of the BESS project. This includes: monitoring the municipality’s social media channels to confirm the reminder was posted, ensuring timely communication and follow-up and notifying Genera PR and address issues identified in the municipality's communication channel regarding community outreach.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.25 |  | 139 | 173.75 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Develop a yearly calendar that for BESS project integrates all community engagement efforts. This includes: researching community organizations; resigning a Canva template to present to Genera PR; organizing key information and data
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 5) Review Cambalache RGE Submittal Quality Control Plan, Thermal and Moisture Protection plan, Joint Sealants for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing Project Issued for Bid (IFB) drawings to verify they meets the required specifications of the projects. Reviewed 13 pages.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 26 pages.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review the Appendix D.1 - Design Drawings for Civil & Structure Works for 30 MW Battery Energy Storage System at Costa Sur on the RFP 4899. Review safety regulations for battery storage. Review the design and installation manual for the Tesla Megapack batteries. Review safety regulations for battery storage.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review the attachment D technical specification for BESS Civil Work Contract (CWC) - RFP. Review applicable QAQC regulations for the project, included designer proposal documents for prepared presentation about concrete specification in the project construction requested by DCMC site manager of Costa Sur facilities site.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on requirements comments for schedule for contractor RGE considering preliminary construction schedule related to BESS building and site construction activities for employee (DCMC) Andres Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on extract data from contractual guides and specifications requirements for schedule for baseline submittal list evaluation of contractor RGE considering preliminary construction process related to BESS construction activities for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 5) Review Cambalache RGE Submittal Quality Control Plan, Thermal and Moisture Protection plan, Fluid Applied Membrane Roofing and Flashing and Sheet Metal for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams meeting with Pedro Cabrera from DCMC to discuss Critical Components project tracker status and updates.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Sheila Torres (DCMC), Paola Arroyo (DCMC), Lauren Wells, (Lemoine)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Adding a risk visualization section on Inventory Management project report to better understand impact and mitigation measure to implement.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees:Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Sheila Torres (DCMC), Paola Arroyo (DCMC), Lauren Wells, (Lemoine)
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Systematically compiling and assessing Inventory Management project updates to enhance data visualization, improve accessibility, and facilitate clearer interpretation of progress and risks.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue incorporating a risk visualization section into the Inventory Management project report to enhance clarity on potential impacts and guide the implementation of mitigation measures.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 17.69 | 17.69 | 17.69 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from airport to the hotel.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 10.42 | 10.42 | 10.42 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Genera's office to Airbnb. 250 Av Luis Munoz Rivera, San Juan, PR 00918, US to 7 Calle Cervantes, San Juan, PR 00907-1315, US.
2025-06-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 7.95 | 7.95 | 7.95 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Airbnb to Genera's office. 7 Calle Cervantes, San Juan, PR 00907-1315, US to 250 Av Luis Munoz Rivera, San Juan, PR 00918, US
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Mark Merritt, Mike Merritt, Gilberto Sucre, Frances Vallejo, Lauren Wells, Ada Diaz, and Barry Scanlon, DCMC. Discussed update on project, job offers, PROCORE, logistics, other interviews, trailer set-up, safety, and schedule for locations.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Worked on internal document control of all the days meetings and calls related to the projects to enable faster decisions, keep track of work done, and improve productivity.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Looked at and responded to emails and correspondence for the peaker project Reviewed correspondence and inquiries for the peaker projects
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 225 | 562.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Meeting to discuss the constructability of the Peaker project at Costa Sur. Attendees: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Carlos De Jesus DCMC Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC Harry Del Valle DCMC.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended PMO meeting , we reviewed the project timelines and the pmo traker for the high level review afterwards attend by Carlos De Jesus DCMC Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC Harry Del Valle DCMC
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Installation Construction Weekly Installation with ARG Ceres. Led by Eduardo Rivera weekly summary update was discussed. * Homeca Demobilization by 6/27 * NTP expected in 3 - 4 weeks * After Monday's site inspection by ARG Ceres & DCMC there will be a Civil & Site meeting in the afternoon at the A/E office. * RFI's Update * Submittals Update. * Pre-Cast VE also to be evaluated in the afternoon meeting. * Schedule of Values review in process. Attendees: Carlos Hernandez - ARG Ceres Gabriel Perez - CDM Smith Wilfredo Sierra - Sargent & Lundy Gilberto Sucre - DCMC Partners
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Weekly Construction Meeting with RGE Led by Andres Concepcion - DCMC reviewed and updated on construction project progress and design issues. Main Topics: RGE and Genera platforms are now aligned to review construction drawings. Jose Segarra's team is working on synchronizing databases and separating disciplines for review. Tesla Megapack drawings have been shared and are under review. GSU transformer will be in the original location pending Geotech review. Next IFC package is expected to be issued on July 10th. RFI 19 regarding electrical components is still open and needs follow-up. Safety submittals 7 and 8 were sent back for revisions. Pending submittals include control room layout and connection to existing transformer. Construction schedule review is ongoing with more detailed tracking needed. Procurement schedule should be included in the construction schedule. Participants DCMC - Gilberto Sucre CDM Smith - Gabriel Perez CSA Group - Franklyn Colmenares Sargent & Lundy - Wilfredo Sierra RGE - Jose Segarra.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Multiple Coordination Tasks & Deliverables prepared. * Vega Baja & Cambalache - RFP documentation, approved schedule, scope of works, final contractor proposals for Sylvia Franco DCMC new Scheduler/Cost person. * Review final soil testing soil testing report for Costa Sur and distribution to site team. * Prepared Vega Baja Permits package to share with ARG Ceres. * Review & provided final comments to PMO Reporting.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up Meeting covering the main topics: * Project Timeline and Coordination Issues * Staffing Confirmations for warehouses * Pro-Core Implementation Challenges * Invoice Processing and Audit concerns for Battery * Vendor Management and Contract Compliance * Technology and Communication Infrastructure DCMC Participants: Mark Merritt, Michael Merritt, Frances Vallejo, Lauren Wells, Ada Diaz, Anneilia Holton & Gilberto Sucre
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 225 | 787.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Site & Underground Utilities Design Review and Pre-Cast VE Conceptual Design Presentation by ARG Ceres Team. Martin Marxauch Presented the latest Pre- Cast VE solution for the platform walls and upper slab, after an exchange of questions the following action items was identified; Sargent & Lundy to prepare a list of RFI's by tomorrow. Marxuach to resubmit revised concept drawings addressing the main questions by A/E. 2nd part of the meeting main discussion was the Site and underground IFC drawings identifying all the missing information + comments provided on behalf of Genera by the DCMC team. Stressed the importance to re-issue IFC for Site asap and not wait until July 10th for the next issue. Participants: Martin Marxuach - Prefabricados Marxuach Gilberto Sucre - DCMC Partners Gabriel Perez - CDM Smith Carlos Hernandez - RGE Ceres Mike Kuczynski - Sargent & Lundy
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Completed follow-up from Day 2 of the P3 Approval Process Improvement workshop. Updated the Miro board with finalized SIPOC elements developed by the team, including process steps, inputs, outputs, suppliers, and customers. Documented key decisions and clarified scope boundaries around the RG-Peaker approval process. Captured action items and prepared summary materials to support continuity into Day 3. Shared updates with Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Added Axel to the teams group and invited the entire team to the Miro board and walked them through how to use the tool.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Met with Esther Rohena (DCMC), D’Alexzander Gonzalez (DCMC), Christian Cruz (DCMC), and Shellsea Maysonet (DCMC) to coordinate upcoming Lean implementation modules for the DCMC team. Discussed current initiatives and priorities to ensure alignment and mutual support. Shared plans to distribute the Lean Glossary and Meeting Ground Rules to support consistent understanding and application of Lean principles across teams.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Met with Estefania Gonzalez (Genera HR) to review and align Lean meeting ground rules with Genera cultural values. Discussed ways to highlight real examples of behaviors aligned with those values. Introduced CliftonStrengthsFinder and Genius Spark tools; reviewed sample team summaries and discussed pricing options for a leadership team rollout of Genisus spark assessments. Identified seven executive team members for initial assessments. Outlined next steps for delivering individual coaching and summaries. Action item: send pricing and rollout recommendation to Estefania and Jennifer Witeczek (Genera)
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Prepared materials and digital workspace for Day 2 of the P3 Approval Process Improvement workshop with team members Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Reviewed notes from Day 1, finalized discussion points on problem clarification, and developed workshop content for introducing the SIPOC tool. Updated Miro board and ensured readiness for team onboarding and activity facilitation.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Met with Shellsea Maysonet (SMC) to discuss the Procurement Department Process Tracker she is developing to monitor the progress of procurement proposals. Reviewed tracker functionality and alignment with process improvement efforts. Received a copy of the tracker to incorporate into the Day 2 discussion with the P3 Approval Process Improvement team for review and integration.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Prepared for Day 3 of the P3 Approval Process Improvement working session by inputting SIPOC data and outputs from previous sessions into the Miro board and setting up materials for the team. Participants include Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Focus of prep included finalizing the SIPOC and initiating the Process Map development.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Facilitated Day 2 of the P3 Approval Process Improvement workshop with Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), Kevin Futch (Genera), and Axel Velez (Genera). Continued Step 1 of the 8-Step Problem Solving process by further defining the problem. Identified that the standard approval time is 5 days, while the Peaker project required 23 days, revealing an 18-day gap. Also identified a goal of zero RFIs, compared to 10 RFIs submitted during the process. Clarified project boundaries, narrowing scope from all approvals to RG-Peaker P3/FOMB external approvals. Delivered SIPOC modules and led the team in developing the SIPOC diagram with 6 defined process steps, including inputs, outputs, suppliers, and customers. Onboarded Axel and aligned the team after late arrivals on Day 1.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-PMO Reporting call to discuss and review the reports created by the PMO team for Genera. Attendees were Frances Vallejo, Jean Pierre Menay, Rafael Calderon, Gilberto Sucre (DCMC), and Lauren Wells, Foster Veazey (Lemoine)
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine). Discussed project, job offers, PROCORE workshop schedule, interviews, trailer set-up, safety, schedule for locations, LEAN, and program management plan update.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for punch list.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt (DCMC) to discuss program staffing and overall program goals.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on wireframe review for financial process flow.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool items.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) to discuss Procore SOPs.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks items
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOP's.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on drawings settings for notifications.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for drawings.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items such as adding users, permissions.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) and Luis Roman (DCMC) for Procore weekly check-in to discuss open items as a team.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 217.81 | 217.81 | 217.81 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I stayed at Airbnb at 7 Calle Cervantes, San Juan, PR 00907-1315, US while visiting the Genera team. The nightly cost was $217.81 per night.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Continued supporting Genera’s Regulatory Team in responding to over 10 inquiries from PREB. Drafted and refined formal responses addressing key aspects of the BESS and Peakers project, including scope, timeline feasibility, system dispatch, and augmentation planning. Ensured the responses maintained a professional, fact-based tone aligned with federal compliance standards. Integrated input from D'Alexzander Gonzalez and Pedro Cabrera (DCMC) into a cohesive document and shared with Jesús Cintrón (Genera) for review and approval.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project construction weekly meeting Phase II. ARFG/CERES Carlos Hernandez; DCMC Jaime Pesquera, Jean Menay, Gilberto Sucre and Eduardo Rivera, CDM Smith Nelson Soler, and Gabriel Perez Sepulveda, CSA Franklyn Colmenares, S&L Robert Molner - Meeting to provide status for future construction of second phase of Vega Baja BESS project and coordinate with ARG documents to be submitted as part for the new construction. Working session given to Jaime Umpierre and Luis Santiago (ARG) about Genera Safety Program. Coordinate Visit to Costa Sur Genera Plant.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Site inspection. Meeting with Homeca (Carirma Sanchez, Eduardo Ramos) Eduardo Rivera, Jaime Pesquera (DCMC) about Vega Baja project, Meeting topics included safety, construction status, demobilization and date the end project, Meeting topics included safety, construction status, demobilization and date the end projects. Meeting with Nelson Soler (CDM SMITH) about Vega Baja projects.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss staffing update, Procore financials, trailer equipment needed and other project needs. Participants: Gilberto Sucre, Lauren Wells, Mark Merritt, Anneilia Holton (DCMC)
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Abraham Velazquez (DCMC) to discuss Peaker's project status and schedule.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in the Cambalache weekly internal meeting to discuss project site status and discuss pending matters with the site staff. Participants: Andres Concepcion, Jorge Mercado, Luis Damudt and Luis Duque (DCMC)
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Harry del Valle (DCMC) to discuss trailer update list and new items to add.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Meeting with Rafael Calderon and Sheila Torres (DCMC) to discuss contract status for Siemens and Tesla.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Supported Genera’s Regulatory Team in responding to over 10 PREB inquiries by reviewing LUMA’s Resource Adequacy Analysis. Extracted insights on generation capacity, BESS integration, and system constraints. Began drafting technical responses addressing degradation, charging cycles, integration timelines, and vendor coordination, ensuring alignment with FEMA PA requirements and Genera’s regulatory strategy. Discussed content and approach with Jesús Cintrón (Genera).
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - PMO meeting preparation - Updated procurement tracker for weekly RFP reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting. Discussed the tracker with Franklyn Colmenares, Rafael Pabon and Gabriel Sepulveda (CDM Smith).
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria ¦ Supported Genera’s Regulatory team in reviewing and updating Appendix D for BESS RFPs 4826, 4898, 4899, and 4900 in coordination with Genera’s Finance team. This task involved refining language within the financial certification sections to ensure accuracy and alignment with FOMB requirements. The updates aimed to more clearly reflect the financial structure and obligations associated with each proposed contract, supporting overall grant documentation and compliance.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. We held a weekly meeting with Carirma Sánchez Homeca and Nelson Soler (CDMSmith) and Jaime Pesquera (DCMC) to verify next steps for the punch list completion. Equipment, excavators were removed from site.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 - Reading RG Engineering Contractor project documentation about revised scope, pricing and schedule of 18 pages.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache & Vega Baja ¦ DR4339 - Organized documents received of the Cambalache and Vega Baja Projects. Some of the documents are Offer and Optional Prices, Schedule of Value, and others.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Theresa Perez (DCMC) to discuss about which modules I have to take, and Miss Perez showed me the different modules in PROCORE.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 - Continue reading RG Enginering contractor documentation of Value Engineering Revised Scope Evaluation which evaluate if the prices and time change.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 - Construction Weekly Meeting which the host was Andres Concepcion (DCMC). Also, other participants were Franklyn Colmenares (CDM Smith), Wilfredo Sierra (Sargent & Lundy), and others. The items discussed were safety, Communication & Documentation Protocol, and others.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 - Construction Weekly Meeting which the host was Andres Concepcion (DCMC). Also others participants were Luis Duque,(DCMC) Gabriel Perez (CDM). Among the topics discussed were -Wherehouse Temporary Storage, Gas Storage Enclosure, Permitting, Submittal & RFI Log, and other topics.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continued the review of the Tesla Megapack design and installation manual, focusing on system integration details, safety features, and emergency procedures. Also continued evaluating applicable safety regulations for battery energy storage to ensure full regulatory compliance and safe implementation practices.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with RGE team (Jose Auli) to visit the construction site and coordinate office trailer mobilization. Metting with DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron and Luis Echevarría) to discuss QA/QC Concrete presentation on specific strength and rebar spacing for construction by Carlos Bayron in order to compare issue for bid and issue for construction.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Reviewing soil findings of Genera site Costa Sur as per Soil testing done by Jaca & Sierra and interpreted finding and samples by environmental quality laboratories. Reviewing initial drawings from Sargent and Lundy for comments and feedback on missing details.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with RGE team (Jose Auli) to visit the construction site and coordinate office trailer mobilization. Meeting with DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron and Luis Echevarría) to discuss QA/QC Concrete presentation on specific strength and rebar spacing for construction by Carlos Bayron in order to compare issue for bid and issue for construction.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Held a meeting at the Yabucoa site with Genera Supervisor Axel Rivera to discuss the requirements for construction signage and to identify, by walking and inspecting the site, an appropriate area for installation that does not interfere with existing operations at the Genera site. Also, a call was held with Henry Diaz (Supervisor from LUMA) to discuss the same theme but in the area that LUMA is in charge. A meeting with Henry Diaz is schedule for next Monday 30JUN25.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing the SECTION 011100 "Summary of work" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing section 011100 summary of work "Advance Fiel Engineerin", "Intent of Documents", "Performance of the Work", "Regulatory Requirements" and "Protection of Property and Personal safety" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid. Also, start to review Appendix #1 Design Drawing.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with RGE team (Jose Auli) to visit the construction site and coordinate office trailer mobilization. Meeting with DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron and Luis Echevarría) to discuss QA/QC Concrete presentation on specific strength and rebar spacing for construction by Carlos Bayron in order to compare issue for bid and issue for construction
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review issue with Carlos Bayron (DCMC) a bid (Drawings) to Configure Submittals Settings, Intro RFIs Tool Permissions, Schedule Tools, included in QA/QC Concrete presentation on specific strength and rebar spacing for construction to compare issue for bid and issue for construction.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Reading and review Safety Process for Entrance and Exit of Trucks at an Energy Plant: This process aligns with general industrial safety standards (e.g., OSHA, NFPA) and local regulations 1. Pre-Arrival Coordination 2. Arrival at Security Checkpoint 3. Safety Induction and Access Authorization 4. Controlled Entry 5. On-Site Movement and Unloading 6. Exit Procedures 7. Incident Reporting and Emergency Protocol
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Reading and review Emergency Hurricane Plan for an Energy Plant: Align with best practices in emergency management (FEMA, OSHA, NFPA 1600) 1. Planning and Preparedness (Year-Round) 2. Phase I: Watch Status (72 to 48 Hours Before Impact) 3. Phase II: Warning Status (48 to 24 Hours Before Impact) 4. Phase III: Impact and Shelter-in-Place 5. Phase IV: Damage Assessment and Initial Recovery 6. Phase V: Full Recovery and Reentry
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS SITE; Received Via PROCORE Platform the Issue for Bid Drawings for the Control House sent by Sargent & Lundy. Working with the QA/QC of the Drawings loaded to PROCORE, and reviewing and evaluating Design Notes and possible design drawing gaps. Coordinate with Frances Vallejo (DCMC) and Gilberto Sucre(DCMC) to seek approval for a general cleaning service for the Aguirre Office Trailer Site Surrounding.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the Issue bid drawings documents to identify potential and possible change orders, as well as potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects to be integrated into the PROCORE platform. A call was held with Javier Aviles from Portosan to coordinate equipment delivery to the Aguirre Site.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Discuss and Coordinate by phone with Javier Aviles (Portosan), the quotes and the delivery dates for the Septic Tank for the following projects, Central Aguirre, Central Costa Sur & Central Cambalache.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on the Review and make corrections on Quality Assurance & Control, adding comments & made corrections discussed previously.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review quotes received from Javier Aviles (Portosan), for the Septic Tank for the following projects, Central Aguirre, Central Costa Sur & Central Cambalache. Discuss quotes to Gilberto Sucre (DCMC) for his approval. After Gilberto Sucre (DCMC) approved, quotes were sent out to Javier Aviles (Portosan) by email.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - An evaluation of the occupational health and safety program submitted by the contractor, RGE, is being conducted. This evaluation is detailed in the section on crystalline silica exposure in construction, 29 CFR 1926.1153. This evaluation includes comments that will be discussed with the contractor, RGE.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - An evaluation of the occupational health and safety program submitted by the contractor, RGE, is being conducted. This evaluation is detailed in the respiratory protection section according to the requirements of OSHA 1910 sub134. This evaluation includes comments that will be discussed with the contractor, RGE.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Followed up with action items related to the Construction Weekly meeting. Coordinated with CW Legal Services - Carlos Lopez for the 6/25/25 Permitting meeting. Prepared Cambalache entrance plan for a GeneraPR project banner and shared with Gabriel Perez - CDM Smith. Phone call with Herminio Arroyo - GeneraPR to discuss regarding the access bridge authority or owner to define responsible in structural studies.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared and completed the Construction Weekly Meeting agenda with follow up and action items. Prepared Submittal and RFI logs reports for discussion on overdue items.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed the construction schedule and compared with latest construction drawings to identify missing activities to be covered in project and improve project management tracking.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued Review of project Quality Control plan (submittal) to provide comments and observations to be addressed by RG Engineering (Contractor - Jose Segarra).
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with DCMC Partners - Luis Duque and Luis Damudt for project quality control plan review and discussion of obervations. Prepared a review to start procurement support for a Prefabricated Gas Storage enclosure required by GeneraPR.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted the Construction Weekly meeting to discuss ongoing project status and action items with project team (RG Engineering - Jose Segarra) (Sargent and Lundy - Robert Molner) (DCMC Partners - Gilberto Sucre) (CDMSmith - Gabriel Perez) and (GeneraPR - Herminio Arroyo)
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met via Teams meeting with Luis Roman - DCMC Partners to review submittals and apply corrective measures in the Procore workflow to ensure information is documented and communicated properly.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca personnel is at project to complete final punch list item pending, also de will demobilize all mayor equipment from site. Working with ARG agenda to include additional documents to be distributed for meeting.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project construction weekly meeting Phase II. ARFG/CERES Carlos Hernandez; DCMC Jaime Pesquera, Jean Menay, Gilberto Sucre and Eduardo Rivera, CDM Smith Nelson Soler, and Gabriel Perez Sepulveda, CSA Franklyn Colmenares, S&L Robert Molner - Meeting to provide status for future construction of second phase of Vega Baja BESS project and coordinate with ARG documents to be submitted as part for the new construction.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Design meeting with S&L - Organizer DCMC Gilberto Sucre and Eduardo Rivera, ARFG/CERES Carlos Hernandez, CDM Gabriel Perez Sepulveda, S&L Mike Kuczynski - Meeting to discuss Vega Baja IFC drawing related to project and identify some deficiency on drawing related to CES Plan, precast discussion and underground piping, also to review electrical drawing related to project.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with preparation for meeting with S&L to discuss drawing IFC and coordinating with Jaime Pesquera (DCMC) the activity work of Homeca to remove transformer scaffold and project closing.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project weekly meeting to review project status. Homeca Eduardo Ramos, and Carirma Snachez; DCMC Jaime Pesquera, Jean Menay, and Eduardo Rivera, CDM Smith Nelson Soler, Enrique Laya, Gabriel Perez and Manuely Concepcion. Meeting to discuss punch list items, demobilization and project closing.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca personnel continue working in project to complete final punch list item pending, also de will demobilize all mayor equipment from site. ARG Ludgardo Gonzalez arrive to project to review field for concrete slab demolition.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held an operational sync meeting with Hernan Machado, Giovanni Taffanelli from DCMC, and warehouse personnel to reinforce alignment on standardized inventory procedures. The session focused on ensuring all team members follow the same operational methods, maintaining consistency across tasks, and prioritizing safety in every phase of execution. Emphasis was placed on proper material handling, clear communication during task assignments, and immediate reporting of any unsafe conditions or procedural deviations.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle count preparation at the Aguirre warehouse alongside Mr. Juan Vallejo from DCMC. Activities focused on validating item locations, updating inventory records, and organizing resource allocation to ensure system alignment and readiness for accurate execution.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a targeted inventory recount at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. The session focused on verifying storage bin assignments, validating part numbers and item descriptions, and reconciling physical inventory with system records. Discrepancies were documented for resolution, and emphasis was placed on maintaining traceability, data integrity, and compliance with asset control standards. Inventory locations reviewed range from BE 001 through BE 100.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-prepared a consolidated inventory performance report at the Aguirre warehouse for Anthony Vega from Genera PR. The report included catalog validation, unit count analysis, and discrepancy metrics across locations BE 001 to BE 100, CP 001 to CP 007, CQ 001 to CQ 009, CR 001, AH 006 to AH 020, CA 020 to CA 031, with a focus on stock accuracy, coverage, and overall inventory conditions.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed scheduled cycle count across inventory zones BE 001 through BE 100 as part of ongoing control measures. The process involved verifying bin-level quantities, reconciling system discrepancies, and inspecting labeling and item placement accuracy. Additional tasks included documenting variances, assessing data integrity, and ensuring compliance with established inventory procedures.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused variance investigation at the Aguirre warehouse to validate inventory discrepancies flagged during previous counts. The review involved tracing system entries, verifying bin assignments, and physically inspecting storage locations to determine whether missing or mismatched parts were present. The objective was to confirm stock availability, identify root causes of inconsistencies, and document findings for corrective action. Inventory zones evaluated ranged from BE 001 trough BE 100.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Drafting audit-style responses to PREB Item 90 on critical component replacement—covering reliability analysis, full component listing, FY2026 timeline feasibility, progress metrics, and alignment of short-term repairs.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Complete the Bi-Weekly Report Template in preparation for the PMO reporting meeting. This task involved compiling updates on key project activities, identifying recent accomplishments and ongoing challenges, and summarizing financial and operational status. The finalized report supports leadership oversight and ensures consistent tracking of project milestones and deliverables.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Modify after review of D'Alexzander Gonzalez DCMC, audit-style responses to PREB Item 90 on critical component replacement—covering reliability analysis, full component listing, FY2026 timeline feasibility, progress metrics, and alignment of short-term repairs.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 4 - Masonry and DIVISION 5 - Structural Steel.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - QA-QC Plan review update with, Andres Concepcion, and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 4 - Masonry
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 4 - Masonry and DIVISION 5 - Structural Steel.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc DIVISION 5 - Structural Steel.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 3 - Concrete and DIVISION 4 - Masonry
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Construction Weekly update with Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team Weekly Meeting. Discussed project progress, identify issues, and completed tasks, and upcoming activities.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Generates PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - RGE Cambalache Meeting discussed the rotation of the contractor's mobilization date, the designer's plans that are still to be submitted by the designer and the signing of the contract with the contractor with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado, Andrés Concepción, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Central Team José Segarra, Ángel Cruz, Harry Velázquez from RGE, Herminio Arroyo Generates PR.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly construction meeting with Carirma Sanchez, Eduardo Ramos (Homeca Recyclers), Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith), and went over Project Documents Overview and analyzing documents status in the Procore platform. Verified all the punch list items that are open and the demobilization status.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria- at the Vega Baja job site. Cleanup activities field supervision and coordination. Had a walk-through meeting with Emmanuel Santos from Homeca Recyclers to discuss safety items that need to be removed from the site like iron rods & things left from the punch list items. We will be doing this walk-through inspection in the afternoon as well.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we will hold a weekly meeting with Carirma Sánchez Homeca and Nelson Soler (CDM Smith) and Jaime Pesquera (DCMC) to verify next steps for the punch list completion.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 PMO Contract Management catchup meeting - Meeting to discuss contract management status base on project execution. Reviewing change orders status and issues on construction tasks. Participants Frances Vallejo DCMC and Rafael Calderon DCMC
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 164 | 492 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens_Contract #00106588 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #2 and #3 based on contract requirements. Reviewing Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 164 | 410 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CA020 to CA031 Cycle Count List # 1182.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AH006 to AH020
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AH006 to AH020
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AH006 to AH020
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AH006 to AH020
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AH006 to AH020
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations CP 00 001 to CP 00 007 ; CQ 00 001 to CQ 00 009 and CR 00 001
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations CP 00 001 to CP 00 007 ; CQ 00 001 to CQ 00 009 and CR 00 001
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CP 00 001 to CP 00 007 ; CQ 00 001 to CQ 00 009 and CR 00 001
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre.Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BE 001 to BE 090
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Aguirre. Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BE 001 to BE 090 LIST # 1158/1159/1160/1172/1173
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BE 001 to BE 090 RECOUNT LIST # 11667/1170/1171/1181
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre.Prepare the lists for locations BE 001 to BE 090 at the Aguirre warehouse to initiate the cycle counts.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1188, 1189 and 1190 from locations CA020 to CA031 for a total of 285 pcs.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CA020 to CA031 to begin the cycle counts.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review and provide final updates to the Meetings tool SOP for both internal and external users; working on agenda and minutes mode; to get sure selected users can comment or accept/deny the meeting minutes.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /GEN 01 Project Data Review & Process/Coordination of Request for Procore Certificates/Siemens Review Procore Access/
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Coordination with Sylvia Franco (DCMC) Procore Data/GEN 01 S&L Financial Data _Task Orders Review & Process
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 151 | 113.25 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Cambalache Project Weekly Meeting hosted by Andres Concepcion (DCMC) and joined by representation from S&L with Mike Kuczynski and Ivette Miranda, also from contractor RGE Jose Robles, Jose Segarra and Vernadee Ortiz, and from DCMC field staff Luis Duque, among others. Discussed the current project status prior to final contractual agreements signing, administrative activities being started or in progress, and typical construction preparedness activities in coordination with the Plant Staff from Genera.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the equipment and locations list for the Aguirre Power Plant to ensure proper Procore kick-off with contractor and design team.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Internal Catchup with Lauren Wells (Lemoine) and Theresa Perez (DCMC). Discusses new inclusions and features for the RFI and Submittals tools such as project staging naming conventions and the review of response options inside the submittals tool. Also went over recently documentation being worked at the Documents tool.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 151 | 37.75 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Call with Andres Concepcion (DCMC) to discuss the proper steps on responding to a submittal: users have being changing submittals status instead of responding on its corresponding screen.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Working on the development of workshop sessions for new and existing users working directly with the uploading of input and documentation.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform review for the inclusion of the Transmittal from for specified documents and its route of distribution among project management tools, typical email or with transmittal signed sheets.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the Submittals SOP for inernal users to specify all instructions on tracking open items, responding on its proper screen and selecting the proper templates for different scenarios.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Verify how users interact with open items and items with Ball in Court of the internal team to comply with response timing and information distribution.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Call Meeting with Lauren Wells (Lemoine) to discuss the current progress and stats of Procore SOPs for Project Management Tools: 12 out of 17 Project Management Tools have an SOP published inside active project's Document Tool.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 148 | 148 | 148 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Full day PerDiem
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: Updating the expense tracker, focusing on updating invoices and entering vendor names to ensure accurate documentation and financial tracking across the project.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache Weekly internal meeting with Andres Concepcion (DCMC) and Gilberto Sucre (DCMC) for the 4339_9510 BESS_Cambalache project to discuss weekly plan and action items to improve efficiency and productivity, increase accountability and continuous improvement.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing Project Issued for Bid (IFB) drawings to verify they meets the required specifications of the projects. Reviewed 22 pages.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing Project Issued for Bid (IFB) drawings to verify they meets the required specifications of the projects. Reviewed 16 pages.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Review Issue for Bid (Drawings) to Configure Submittals Settings, Intro RFIs Tool Permissions, Schedule Tools, included in QA/QC Concrete presentation on specific strength and rebar spacing for construction by Carlos Bayron in order to compare issue for bid and issue for construction.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Meeting with RGE team (Jose Auli) to visit the construction site and coordinate office trailer mobilization. Meeting with DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron and Luis Echevarría) to discuss QA/QC Concrete presentation on specific strength and rebar spacing for construction by Carlos Bayron in order to compare issue for bid and issue for construction.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on TEAMS meeting related to Cambalache BESS - Construction Weekly with pending pending submittals and design process status with DCMC employees Andres Concepcion, Luis Damudt, Luis Duque, employees of RGE Jose Segarra, Xiomara Pérez Álvarez, CDM Smith employee Gabriel Perez, employees of Sargent and Lundy Dean Ennes due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on drawing inspection for comments for schedule for contractor RGE considering BESS building windows, doors, paint, surface and underground utilities of relocation pipping in site activities for employee (DCMC) Andres Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on teams meeting related to verify project submittals, pending actions from designer Sargent and Lundy and contractor RGE with DCMC employees Andres Concepcion, Luis Roman, Luis Damudt, Luis Duque and Jorge Mercado due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on requirements comments for schedule for contractor RGE considering preliminary construction schedule related to BESS building, levee ramp and mechanical pipping's activities for employee (DCMC) Andres Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on requirements comments for schedule for contractor RGE considering preliminary construction schedule related to BESS building, isometric relocation and mechanical pipping's activities for employee (DCMC) Andres Concepcion due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 6) Review Cambalache RGE Submittal Quality Control Plan, Openings plan, Rolling Steel Doors for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Construction Weekly meeting with Andres Concepcion (DCMC), Robert Molner (Sargent and Lundy) and Jose Segarra (RGE) for the 4339_9510 BESS_Cambalache project. Discussed work status and the tasks to be completed.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 6) Review Cambalache RGE Submittal Quality Control Plan, Openings plan, Hollow Metal Doors and Frames,for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 6) Review Cambalache RGE Submittal Quality Control Plan, Openings plan, Aluminum Windows, Tubular Daylight Devices and Door Hardware for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Designing a standardized reporting format for project managers to report project progress in a weekly meeting.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 122 | 488 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Systematically compiling and assessing Critical Components project updates to enhance data visualization, improve accessibility, and facilitate clearer interpretation of progress and risks.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 122 | 366 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing and analyzing BESS project timelines for June and converting the data into a Gantt chart within Power BI for streamlined reporting and visualization so stakeholders can instantly understand project phases, track progress, identify overlaps, and spot potential delays at a glance.
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 11.44 | 11.44 | 11.44 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride fromRide from Airbnb to Genera's office. 7 Calle Cervantes, San Juan, PR 00907-1315, US to 250 Av Luis Munoz Rivera, San Juan, PR 00918, US
2025-06-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 0.7 | 41.51 | 0.7 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Traveled to Vega Baja Genera Site to site inspection.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items for implementation for SOPs.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in design review meeting. Discussed the DOR for Costa Sur and comments. Participants in the meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Reinaldo Romero Sargent & Lundy Miguel Del Valle Sargent & Lundy
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Internal Financial Toll Follow Up to answer any open questions from the call with Procore on 6/23 and in preparation for the meeting on 6/26. Lauren Wells, Rafael Calderon, Esther Rohena, & Gilberto Sucre - All DCMC
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RGE Contrato BESS - Aguirre & Costa reviewed with Francisco Feliu - Genera Final Contract Documentation for both sides. Aguirre was okay, Costa Sur was missing Emergency Generator SOW and Cost.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Installation reviewed Site Demolition DOR and AGR Ceres Cost breakdown to compare vs. IFC documentations Issued by Sargent & Lundy.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria P & P Bond quote clarification confirmations for RGE bid submission for Cambalache, Costa Sur, Aguirre.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Met with Kevin Futch (Genera) to debrief outcomes from the three-day P3 Approval Process Improvement session. Aligned on next steps, clarified expectations and timeline for advancing through the 8-Step Problem Solving process. Reviewed action items; Kevin will follow up with the team to encourage more frequent working sessions. I will summarize the team's progress and provide a communication tool to help Kevin and Joaquin Quinoy (Genera) present deliverables and outcomes to leadership.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Prepared for Day 3 of the P3 Approval Process Improvement working session by inputting SIPOC data and outputs from previous sessions into the Miro board and setting up materials for the team. Participants include Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Focus of prep included finalizing the SIPOC and initiating the Process Map development.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Completed post-meeting follow-up and documentation after P3 Approval Process Improvement Meeting 3. Organized meeting outputs, updated the Miro board with process map progress, captured key decisions, and documented action items for team members: Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Prepared summary and materials for next session to ensure continuity and alignment.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 2.25 |  | 225 | 506.25 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Facilitated Day 3 of the P3 Approval Process Improvement session with the full project team: Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Reviewed the SIPOC developed on Day 2 and progressed to Step 2B of the 8-Step Problem Solving process by beginning the development of the process map. Conducted a working lunch to align on next steps, scheduled the next meeting, and mapped actions for two of the five approval stages.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Held weekly one-on-one with Joaquin Quinoy (Genera) to review outcomes from recent onsite sessions and align on next steps for the P3 Approval Process Improvement initiative. Discussed priority areas for continued Lean coaching support and preparation for the upcoming CliftonStrengthsFinder initiative in collaboration with HR.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore financial items for implementation for SOPs.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore items for weekly call with Franklyn Colmenares (CSA) and others.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on distribution lists for Procore for Rafael Pabon (CDM Smith)
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Gilberto Sucre (DCMC), Johanna Diaz (SMC) for Procore financials.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore budget draft SOP and sent out to the group for review.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Franklyn Colmenares (CSA) to troubleshoot user permissions for submittal workflows for Tesla.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore Financials.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on testing submittal tool in Procore for options on adding an user to a workflow as another vendor.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks items to keep projects on track for Procore team.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for directory and other tools.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Expense |  |  | 223 | 223 | 223 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Toilet Tank for second offices trailer in Vega Baja Genera projects.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet – RFP 231175 (BESS Installation at Yabucoa) - Began preparing the Procurement Memorandum. Collected and consolidated evaluator comments (Over 20 individual comments) and drafted the Executive Summary and Minimum Qualifications Matrix (over 15 items) to document the panel’s findings and support the final recommendation.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review Health and Safety documents submit by RGE (CONTRACTOR).
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordinate equipment necessary in all Genera Projects in P.R. Review Health and Safety documents about Vega Baja, Cambalache and Costa Sur Genera Projects.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Raissa Borges (DCMC) to discuss budget management tracker and reporting for the BESS and Peaker project.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Abraham Velazquez, Gilberto Sucre and Sheila Torres (DCMC) to discuss trailer installation at Costa Sur for peaker project, temporary generation project and next steps.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we removed the second excavator with Emmanuel Santos and Izac Morales from Homeca.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I met with Gilberto Sucre (DCMC), where he clarified my doubts about the project and informed me about the status of the contract with the contractor and the negotiations.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA ¦ GENERA ¦ DELIVERABLE 11 ¦ CAMBALACHE - Review RG Engineering Contractor Schedule which analyze the structure of development of the project, evaluate the critical path and to be sure that all activities are separated per responsible company. The number of pages in the document is 3 and the number of activities evaluated in total was 101.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - Reviewed project-related emails and organized the daily work plan, prioritizing safety documentation, and coordination items related to the BESS civil works at Costa Sur.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Reviewed the Operation and Maintenance Manual for the Tesla Megapack battery systems to understand procedures for routine inspections, preventive maintenance, and emergency response. Additionally, reviewed safety regulations related to battery energy storage to ensure operational practices align with industry standards and regulatory requirements.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of Genera issue for Bid Scope of services Specification G-3200 providing feedback on missing information specific to owner and or subcontractor execution of onsite works in COSTA SUR, to provide a better-defined Scope. Specifically pages 1 through 100.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Received and supervise installation of the portable toilet assigned to the Yabucoa site by Rene Munoz from Portosan.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing section 011900 "Site Design Data" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid. Also, review Appendix #1 Design Drawing.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewing all the emails related to the project. I went through each message carefully to ensure I was up to date on the latest developments, decisions, and any outstanding action items. I paid special attention to updates any flagged issues that might require follow-up. This review helped me clarify the current status of the project and identify the next steps moving forward
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continue reviewing Issue for Bid (Drawings) to configure submittals settings, Intro RFIs tools permissions, schedule tools, included in QA/QC concrete information on specific strength and rebar spacing for construction in order to compare issue for bid and issue for construction.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Finishing Reading and review ATTACHMENT J HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES Section of Enviromental Provision. Reading the process and practices of a Safety Demolition Plan for a Metal Structure: 1. Project Scope and Pre-Demolition Assessment, 2. Site Preparation and Safety Zoning, 3. Equipment and PPE Requirements, 4. Demolition Execution (Step-by-Step), 5. Dust, Noise, and Environmental Controls, 6. Emergency Preparedness and Incident Response, 7. Final Clearance and Demobilization
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017 for the Installation of the Tesla batteries phase, submitted by Sargent & Lundy at the Aguirre Site. Included in the Specifications G-3400, review the issue for the bid Design Drawings included in Appendix 1. Review the Architectural drawings for the Control Room, where comments were made on the door jam detail and drawing identification. It was also commented that the drawing list on the G-3400 specification list did not match the issue for the bid design drawing list. These comments were forwarded to GilbertoSucre (DCMC) via e-mail.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents from Sargent & Lundy, package identified as GENERA-15240-061-0017, for the Installation phase at the Aguirre Site, 17º57'10"N, 66º13'49"W. Review items one to 163 and send comments with findings to Gilberto Sucre (DCMC) to evaluate and discuss with the client Genera PR.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017 for the Installation of the Tesla batteries phase, submitted by Sargent & Lundy at the Aguirre Site. Included in the Specifications G-3400, review the Scope of Services as described in the Issue for Bid Documents on table 103-1 Distribution of Responsibilities items 163 to 250.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Harry Del Valle (DCMC) to discuss the status of the office supply for the job site office trailer. The order for the supplies is still pending completion. The site manager will follow up during the week.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination by phone the septic tanks for office trailers deliveries today with Javier Aviles (Portosan). Deliveries will be in Central Cambalache Arecibo, Central Costa Sur Guayanilla y Central Aguirre Salinas.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on the Review and make corrections on Quality Assurance & Control. Prepare Spreadsheet list with status of equipment's & Material for Office Trailers, in Camabalache, Costa Sur, Aguirre & Yabucoa projects.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria- A site visit was conducted at Cambalache, where I supervised the delivery of the double-containment for the sanitary system provided by PORTOSAN, for the installation of the temporary DCMC offices. This was done in coordination with Andrés Concepción (DCMC) and Jean Menay (DCMC).
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria An evaluation of the documents issued by the contractor Submittal RGE-0007 RG Engineering Safety Manual RGE is performed. This evaluation is required as part of compliance with OSHA 1926 standards.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met and cunducted meeting with CW Legal Services (Carlos Lopez) CDM Smith (Gabriel Perez) and RG Engineering (Jose Segarra) Sargent and Lundy (Anna Raush) ane GeneraPR (Roseanne Perez) to go through the required permitting process for Cambalache project and align expectations and responsibilities.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Created a meeting agenda in preparation for the Cambalache project Permitting meeting to discuss regarding the project permits and regulatory requirements. Organized discussion topics and questions.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Procore to identify responded RFI and Submittals from Sargent and Lundy (Ivette Miranda) and managed the data to ensure are delivered and documented properly.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Shared documentation via email regarding the project permitting list required to GeneraPR (Roseanne Perez). Received from Carlos Lopez (CW Legal Services) and Dept. Economic Development notice that exempts project for a construction permit requirement and reviewed document to align with project.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued to evaluate construction schedule (Mechanical and Electrical Activities) to document observations and comments to coordinate a review with contractor RG Engineering (Jose Segarra) to make corrections.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working at Vega Baja site for equipment demobilization by Homeca they are removing (2) excavator and (1) concrete stone crusher. Working with email send by Eduardo Ramos from Homeca to provide information regard of substantial completion. Homeca brought an articulated boom lifter to remove the scaffold around the main power transformer (MPT). Reviewing Homeca contract 2025-G00272 project # 107011 for substantial completion requirements. Send email to Eduardo Ramos of Homeca in response to email related to substantial completion and inform him that Genera does not have a guidance for substantial completion, but they should work for the notice and requirement for a final completion of the project as per contract article 9.1.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Send email to Jaime Pesquera of DCMC and Nelson Soler of CDM Smith to provide a list of completed work done by Homeca for project closing and provide status of what is pending to be completed by Homeca contractor. Reviewing email related to Vega Baja demolition project closing. Preparing for DCMC meeting for time and expense entries.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-prepared a detailed inventory performance report while at City View Plaza DCMC office for submission to Mr. Anthony Vega from Genera PR. The report summarized key findings from inventory zones AH 039 to AH 50, CA 000 to CA 008, AA 180, BE 090 to BE 145, including item-level accuracy, stock balance validation, and documentation of discrepancies. It also outlined compliance with inventory thresholds, noted recurring issues, and assessed procedural consistency across warehouse operations. The final delivery provides actionable insight to support ongoing audit readiness and strategic decision-making.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue modiffy after review of Joaquin Quinoy GENERA-PR, audit-style responses to PREB Item 90 on critical component replacement—covering reliability analysis, full component listing, FY2026 timeline feasibility, progress metrics, and alignment of short-term repairs.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Based on the developed list of critical components, the status of items that did not receive competitive bids (RFP-4456, RFP-4523, RFP-221012, RFP-4433, RFP-225916) was verified through documented outreach and event reviews. Component status was confirmed against GENERA-PR’s Purchasing Manual, 2 CFR § 200.320(c), and the PDAT Field Manual to determine if can moving to Sole Source Process.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Modiffy after review of Joaquin Quinoy GENERA-PR, audit-style responses to PREB Item 90 on critical component replacement—covering reliability analysis, full component listing, FY2026 timeline feasibility, progress metrics, and alignment of short-term repairs.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting with Cynthia Ortiz (DCMC). A discussion of the competitive bid outcomes for RFP-4456, RFP-4523, RFP-221012, RFP-4433 and RFP-225916 was conducted discussed in detail with Cynthia Ortiz to determine the appropriate course of action.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 5 - Structural Steel.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 4 - Masonry and DIVISION 5 - Structural Steel.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria. at the Vega Baja job site. Cleanup activities field supervision and coordination. Had a walk-through meeting with Emmanuel Santos from Homeca Recyclers to discuss items that need to be removed from the site like iron rods & things left from the punch list items to ensure compliance with regulations.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Cleanup activities field supervision and coordination. Had a walk-through meeting with Emmanuel Santos from Homeca Recyclers to identify and address potential hazards and discuss items that need to be removed from the site like iron rods & things left from the punch list items to prevent accidents among project staff.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA & Genera weekly Technical Meeting with project management Team. Contract 106761 - Reviewing submittals, RFI's, progress based on S&L and Tesla Technical reports. Discussing possible impact on cost, schedule or delivery dates based on technical changes. Meeting between Tesla team (Michael Grabstein, Laura Miglietti), CMD Smith PM team (Gabriel Sepulveda, Carlos Palomares), Sargent & Lundy (Mike Kuczynski), and DCMC (Rafael Calderon, Gilberto Sucre)
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#1_Invoice# PRIN0007609_Oct 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339 _PW#9510 Pre-Intervention Review - Working with CPM Contract #2024-G00142 and TO#1_Invoice# PRIN0007372_Sep 2025. Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AH037 to AH050
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AH037 to AH050
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AH037 to AH050
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AH037 to AH050
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 |  | 152 | 342 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from location AA 01 080 000
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with location AA 01 080 000
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 |  | 152 | 114 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from location AA 01 080 000
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BE 090 to BE 145 at the Aguirre warehouse to initiate the cycle counts.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Aguirre. Hurricane Maria Conducting cycle counts at the Aguirre warehouse by the Asset Suite system. Today, we worked with locations. BE 090 TO BE 145 LIST # 1183/1184
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BE 090 to BE 145
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Aguiirre.Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1208 and 1209 from locations CA000 to CA008 for a total of 35 units.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CA000 - CA008 to begin the cycle counts in accordance with the Asset Suite system. Today we are working Cycle Count List # 1195.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 – Review available information for the Schedule Tool in Procore as how to link Resources Management for Work Crews as DCMC tries to comprehend all construction aspects through Procore; this could provide real wage management and measurement for federal compliances and contractual clauses.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /GEN 01 S&L Financials Data Review & Process (Task Order 02_03 Review & Process
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the recently received Specification Package for Fire Suppresion and Installation works for the BESS Cambalache project.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 148 | 148 | 148 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Full day PerDiem Arrived home after midnite on Thursday 6/26/25.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Work with, Jorge Bracero from Genera PR, in a communications plan coordinating communication with the Mayor’s Office of Vega Baja regarding the second community meeting about the BESS project. We agreed that, as part of the plan, Jorge Bracero will draft and send a communication to the municipality sharing the relevant materials and proposing coordination efforts to support transparency and continued engagement with the Vega Baja community.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Support Genera PR with key questions for the Hispanic Federation ahead of Genera Jorge Bracero’s participation in the panel discussion to which they were invited. The panel will be held on Friday, June 27, from 8:00 AM to 12:00 PM in Arecibo, and we will be sharing details about the BESS Project and its benefits for Puerto Rico. These tasks also included advising the client on stage materials and key points about the BESS project. An email was drafted to Jorge Bracero from the Genera PR Team, which included all the details he should take into account prior to his participation."
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Write draft a concise meeting summary for the second Vega Baja community meeting about the BESS project as part of our community engagement efforts in the BESS project. This summary includes key discussion points, the list of participants, identified challenges, suggestions shared during the session, and the agreed-upon next steps. Write a follow-up email that highlights the most important points from the summary, which can be shared internally or with relevant stakeholders to ensure continued alignment and transparency.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 6) Review Cambalache RGE Submittal Quality Control Plan, Finishes plan, Portland Cement Plastering and Thin Set Ceramic Tiling for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 134 | 201 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing Project Issued for Bid (IFB) drawings to verify they meets the required specifications of the projects. Reviewed 5 pages.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 134 | 402 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing Project Issued for Bid (IFB) drawings to verify they meets the required specifications of the projects. Reviewed 11 pages.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continue reviewing Issue for Bid (Drawings) to configure submittals settings, Intro RFIs tools permissions, schedule tools, included in QA/QC concrete information on specific strength and rebar spacing for construction in order to compare issue for bid and issue for construction.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on requirements comments for schedule for contractor RGE considering preliminary construction schedule considering cost and resources guides of specification on activities for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on create report of requirements comments for create resources cost load notes format and minute report update format with list requirements considering guides of specification and rules on activities for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 134 | 67 | 134 | Yes | 146794 | Site | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 6) Review Cambalache RGE Submittal Quality Control Plan, Finishes plan, Vinyl Composition Resilient Tile Flooring for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 122 | 183 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing and analyzing Peakers project milestone and converting the data within Power BI for streamlined reporting and visualization so stakeholders can better understand project progress and identify potential risks.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 122 | 91.5 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. In person meeting at DCMC office with Gilberto Sucre (DCMC) to discuss Genera project financial process. I also meet with Frances Vallejo (DCMC) to discuss June report status and updates.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing and analyzing Peakers project timelines for June and converting the data into a Gantt chart within Power BI for streamlined reporting and visualization so stakeholders can instantly understand project phases, track progress, identify overlaps, and potential risks.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 60 | 60 | 60 | Yes | 146794 |  | "Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Airport Parking"
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 25 | 25 | 25 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 gas for vehicle visiting genera facility sites for peakers project
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 19.8 | 19.8 | 19.8 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Genera office to Terminal C Airport SJU.
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 8.47 | 8.47 | 8.47 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Ride from Airbnb to Genera's office. 7 Calle Cervantes, San Juan, PR 00907-1315, US to 250 Av Luis Munoz Rivera, San Juan, PR 00918, US
2025-06-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ormonde, Heather | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  |  | 0.7 | 8.05 | 0.7 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Mileage to drive from airport to home from an onsite meeting with Genera team.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 2213.19 | 2213.19 | 2213.19 | Yes | 146794 |  | Office Depot - 3 Epson EcoTank ET-15000 printers, 5 Epson Ink Cartridge packs
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 2036.78 | 2036.78 | 2036.78 | Yes | 146794 |  | Home Depot - Supplies for the Cambalache trailer
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 1226.48 | 1226.48 | 1226.48 | Yes | 146794 |  | Office Depot - 2 Epson EcoTank ET-15000 printers
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 873.6 | 873.6 | 873.6 | Yes | 146794 |  | Duenas Trailers -8'x20' Flex-tainer, Rental, 6/25/25 - 7/24/25- Vega Baja
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | de Jesus, Carlos | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Expense |  |  | 504.88 | 504.88 | 504.88 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Costa Sur site - trailer clean supplies tools for maintenance and health safety. For trailer floor clean and water LOBBY BROOM AND DUSTPAN, SPIN MOP, CEDAR EASY WRING SPIN MOP W/BUCKET, 6-OUTLET SURGE WALL TAP WHT x2 8 OTLT SURGE, 6 OUTLET SURGE PROTECTOR 8' WHITE, HDX 8 GAL FLAP TIE, 50CT MEDIUM BAGS, CHARMIN STRONG, 18 MEGA ROLL PLUS, PURIFIED WTR, MED WASTEBKT RECYCLE BIN 7 GAL, BOUNTY, 14 OZ. ODOMA ODOR ABSORBER LVNDR CRYSTAL AIR 8.8 OZ. FEBREZE AIR ASSORT 3PK, LAVENDER 128OZ, HUSKY 50CT, 10 GAL VAC RIDGID 10 GAL, UMBRELLA- ALL BLACK
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  |  | 479.72 | 479.72 | 479.72 | Yes | 146794 |  | Home Depot - PPE Equipment
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Rafael Calderon (DCMC), Glorimel Torrado (DCMC), Johanna Diaz (SMC) to discuss Procore Financial SOPs.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended meeting Genera PR/RGE PKR Commercial/Schedule Discussion reviewed the equipment specs and delivery times with coordination from the contractor means and methods for final installation and connections. Participants in the meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Chris Mateo Sargent & Lundy Gino Sambolin Sargent & Lundy William Crespo Sargent & Lundy Name Attendance Response Chapman, David GE Vernova Dearing, Jason GE Vernova Mihalyi, Barbara GE Vernova
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 site visit to meet with S&L and site staff to review underground as-built utility lines and connections participated Carlos De Jesus DCMC Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC Lemuel Nieves Sargent & Lundy Reinaldo Romero Sargent & Lundy
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore DCMC Financials SOP's Led by Lauren Kennedy - Procore & Lauren Wells - DCMC continued developing Procore Financial SOP's to be implemented. Covered Categories: * Pre-Publishing * Procurement * Pre-Intervention * CPA & Routing List * Grants Participants Lauren Kennedy - Procore, Lauren Wells, Rafael Calderon, Esther Rohena, Glorimel Torrado & Gilberto Sucre DCMC.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 225 | 675 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Coordination between RG Engineering, DCMC and Sargent & Lundy. Agenda covered: Tesla documents and NDA: Tesla documents were provided to RGE under a separate NDA in mid-February. RGE signed the NDA and received the documents through Power Advocate or SharePoint. Additional documents like the frame drawing were sent out last week. RGE needs to confirm receipt of all necessary documents. Medium voltage cable specifications New specification was not attached to the Tesla RFI response. Low voltage cable specification was updated to copper cabling. RGE needs drawings showing cable entries to the cabinets from Tesla. Chris Niersbach to check if the customer interface section covers cable entries. Temporary road proposals: Proposal to eliminate the second road and modify the existing one. Concerns about maintaining access to the dike and proper slope for trucks. Need to provide sketches of temporary roads for approval. Retaining walls and slope modifications to be considered. Water line and power line relocation Existing water line and power line feeding the warehouse need relocation. Hydro-vac services recommended for locating the water line. Relocation to avoid damage during rigid inclusion installation. Control room building size and layout Control room building size needs to be at least 15 feet wide. Current proposed size of 7 feet is insufficient. Server rack and other equipment need to be accommodated. RGE to provide updated building dimensions and layout. Temporary warehousing plan: Temporary warehousing plan needs approval to proceed with material transfer. Material transfer is critical for starting demolition of the existing warehouse. Work plan to be submitted for evaluation and approval. Coordination of submittals across projects: Common submittals for multiple projects to be identified and streamlined. Approved submittals for one project can be used for others. Submittal schedule with dates to be provided by RGE. Transformer location and foundation modifications: Existing transformer to be temporarily moved for foundation modifications. Transformer study to ensure no issues when batteries are connected. Separate meeting with plant and RGE to finalize scope and sequence. Aguirre - New concept design of 53 independent Battery Foundation Slabs vs two Massive Mat foundations, RGE/DCMC requested additional information as well earth movement profiles. Construction Team expressed the need to improve IFC deliveries CDM Smith - Gabriel Perez: DCMC - Andres Concepcion, Jose Lopez & Gilberto Sucre: RGE - Jose Segarra: Sargent & Lundy - Mike Kuczynski & Wilfredo Sierra:
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Review AGR Ceres Schedule of Values and Potential Deductive Scope Deletions in the Neighborhood of $ 850k + $ 369k in contingency to provide funding for potential tariffs. Met with Gabriel Perez CDM Smith to discuss above subject.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Weekly Construction Meeting with RGE. Led by Gilberto Sucre and Carlos Rodriguez - DCMC Contract Status: Agreement has been reached awaiting now FOB approval, NTP expected next 30 days. Trailer relocation to take place next week. Reviewed outstanding RFI's and Submittal. Current A/E walk thru with Plant evaluating current tower water recirculation on drainage ditches and potential conflict with demolition sequencing. IFC's still schedule for 7/10. Discussed Safety requirements. Stressed importance to start meeting contractor & DCMC these 30 days prior to NTP, for premobilization and coordination. Schedules of Values was requested from RGE. Reminder to have Genera plant staff in meetings. DCMC - Carlos Rodriguez Sargent & Lundy - Wilfredo Sierra RGE - Jose Segarra CDM - Smith - Gabriel Perez CSA Group - Franklyn Perez
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-BESS and Peaker's Project Schedule & Budget Meeting. Attendees were Foster Veazey (Lemoine), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Carlos Palomares (CDM Smith) .
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-PMO Procore Financial SOPs meeting. Individuals in the meeting were Foster Veazey (Lemoine), Elizabeth Fronduto (Procore), and Lauren Wells ( Lemoine)
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information for gathering information from users on current processes.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on closing out helpdesk tickets with Gabriel Perez Quiles (Genera) for Procore support items.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore financials.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial information for implementation workflows.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reviewing support articles for Docusign integration for Procore for invoicing.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for the schedule tool module.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Rafael Calderon (DCMC) and Glorimel Torrado (DCMC) to discuss Docusign + Procore integration and uses.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for adding companies to new project setups.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Addressed a request from Jean Gonzalez of Genera PR to identify and remove all Genera Connect environments not hosted within the official Genera PR infrastructure. Coordinated with Aldwin Pagan from Integrum to successfully locate and decommission legacy environments, ensuring alignment with Genera PR's IT and security standards.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordinate site visit to Costa Sur Genera Power Plant with Carlos Rodriguez (DCMC), S&L and Bidot y Asociados about review and surview regarding the drainage system. Review the documentation about this project. Conference call with Portosan contractors (Javier Aviles) about toilets tanks in Genera Projects.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Communication with Eduardo Rivera (DCMC) about Vega Baja Project. Meeting with Carlos Rodriguez, Gilberto Sucre (DCMC) and Jose Robles, Jose Segarra (RGE Contractors) and Others about Costa Sur Genera project include mobilization, contraction, safety and security plan. Review the emails about all project includes invoice. Conference call Osvaldo de Jesus (GENERA) about all status projects.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Drafted an email to Jesus Cintron (Genera) regarding Peakers delays and hurdles in the project.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review correspondence regarding material and equipment's for trailer supplies and discuss with Carolyn Baez (DCMC) invoices and purchases pending.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended the Budget and scheduling BESS and peakers meeting to discuss project status, RFIs and budget control for each site. Participants: Gilberto Sucre and other DCMC participants and Carlos Palomares (CDM) and other CDM participants.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Discuss one pager summary for BESS and Peaker projects with Raissa Borges (DCMC) and review updates.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Discuss peaker project and pendings with Abraham Velazquez (DCMC).
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended the Costa Sur weekly RGE/DCMC meeting to discuss contract deliverables and BESS project in Costa Sur site. Participants: Gilberto Sucre, Carlos Rodriguez and other DCMC participants.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Sent email to Ada Diaz (DCMC) regarding JL Contractors invoice for the Aguirre trailer service.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Management and Submission of FOMB Contract Approval Packages - Supported the Regulatory Team - Coordinated with internal stakeholders to finalize contract approval packages (Contract No. 102206, 102073, and RFP 221016, 4826, 231175) for submission to FOMB. Reviewed, organized, and ensured completeness of supporting documentation in accordance with FOMB’s Contract Review Policy.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Exchanged multiple emails with Rick Patterson (DCMC) regarding a requested A&E RFP related task. Created an Excel template to facilitate the input of the additional information requested and formally submitted the request to Genera.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Supported Genera’s Procurement Team by responding to RFIs for RFPs 4898, 4899, and 4826. Addressed all questions within our scope, identified and requested outstanding information, compiled the complete set of responses, and shared the draft with Genera's Legal Team (Angelina Minier) for review.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 184 | 460 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet – RFP 231175 (BESS Installation at Yabucoa) - Continued drafting the Procurement Memorandum. Consolidated all evaluator scores into a single Excel sheet, organized and tabulated the data, and calculated average scores to support the evaluation summary.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed the feature and estimation planning submitted by Keyla Sierra from Integrum for upcoming phases of the Genera Connect Financial Tracker and Genera Connect Timesheets platforms. The review focused on ensuring alignment with the long-term roadmap and Genera PR's evolving needs, confirming that proposed enhancements support sustained platform functionality and user adoption.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Collaborated with Shellsea Maysonet (SMC) to resolve data synchronization issues originating from Genera PR Procurement that were impacting KPI visualization in Power BI.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed and responded to the RFP 235021 questions shared by Cynthia Ortiz from DCMC, ensuring that the answers aligned with project objectives and addressed the client’s requirements clearly and accurately.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we removed the manlift with Emmanuel Santos and Izac Morales from Homeca and started dismantling wood panel protection for the transformer.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache and Vega Baja ¦ DR4339 - Meeting with Luis Roman (DCMC) to discuss about Schedule Tool Check-In. Luis explained how to handle some project files.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache and Vega Baja ¦ DR4339 - Meeting by Teams with Theresa Perez (DCMC) to solve an issue with the access documentation on Procore for Cambalache and Vega Baja.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 - Reading Cambalache Request for Proposal which consist of all requirements to be contractor on the project (34 pages).
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache and Vega Baja ¦ DR4339 Identified and reviewed for the Procore system, professional development materials, and system-guidance resources relevant to my responsibilities as Scheduler to enhance proficiency in project coordination processes, planning methodologies, and documentation standards necessary for effective project execution.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of Genera issue for Bid Scope of services Specification G-3200 providing feedback on missing information specific to owner and or subcontractor execution of onsite works in COSTA SUR, to provide a better-defined Scope. Specifically pages 100 through 245.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - DCMC Site team lead by DCMC Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety workshop, submittals and RFI's.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 013216 Project Schedule and Section 013300 Submittals Procedures of the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid. Also, review Appendix #1 Design Drawing.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Meeting with Jose Lopez (DCMC) to discuss the review results and findings of the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing sections 013119 "Project Meeting" and Section 013216 "Project Schedule" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid. Also, review Appendix #1 Design Drawing.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria- DCMC Site team lead by Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety workshop, submittals and RFI's.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continue reviewing Issue for Bid (Drawings) to configure submittals settings, Intro RFIs tools permissions, schedule tools, included in QA/QC concrete information on specific strength and rebar spacing for construction in order to compare issue for bid and issue for construction.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Reading and review Safety Control and Prevention for Earth Movement in a Construction Site: 1. Risk Assessment and Planning 2. Protective Measures and Controls: Shoring and Trench Support, Benching and Sloping, Erosion and Sediment Control, Equipment Safety, Utility Detection, Monitoring Ground Stability. 3. Worker Protection and Site Access Control: Hazard Zones, PPE Requirements, Emergency Planning. 4. Continuous Monitoring and Communication
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Project Create a note on Procore to explain the Delay in Delivery – Sanitary Tank for DCMC Office Trailer Bathroom: We were awaiting the scheduled delivery of the sanitary tank intended for the bathroom at the DCMC office, part of the Bess_Aguirre Project. However, the delivery did not occur as planned. As of today, the sanitary tank has not been received on-site. This delay may impact the installation schedule for the bathroom. We are currently following up with the supplier for an updated delivery timeline. Coordination of Meeting with Plant Manager – Aguirre: Had a conversation with Jose Lopez (DCMC) to coordinate a meeting with the Plant Manager at the Aguirre site before 1:00 pm. Coordination for Safety Equipment Purchase – DCMC Office Trailer: Coordinated with Jean Pierre Menay (DCMC) regarding the purchase of a fire extinguisher and a first aid kit for the DCMC Office Trailer at the Bess_Aguirre Project site. These items are being procured to ensure basic safety measures are in place. Jean Pierre Menay (DCMC) will proceed with the purchase and update once the items are delivered and installed.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We conducted a visual inspection of the parking area and the surroundings of the DCMC offices in the Bess_Aguirre Project to observe order and cleanliness and how we can improve our work area. We suggest painting the parking spaces and marking them. In summary, the parking lot and the surroundings of the office are clean.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Yabucoa BESS PROJECT. Meeting with Gabriel T. Morales, (DCMC) site manager at the Yabucoa Bess project to review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy for the Yabucoa Job Site Included in the Specifications G-3400, review the Division of Responsibilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD), and the Owner Genera PR. Joint efforts with Gabriel T. Morales (DCMC) to identify mismatch information provided by Sargent & Lundy within the provided specifications, designed drawings for the installation phase, the Scope of Work description, and the Directive of Responsibilities from one to 249 line items.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting in person at Sargent and Lundy Central Offices at Santurce PR to go over the Design Drawings and Project Pending missing items to complete the Issue for Construction Drawings. At the conference table were present Gabriel Pérez (CDM Smith), Gilberto Sucre, and Andres Concepción (DCMC). On the Teams were Mike Kuczynski, Robert Molner, and the Civil Design Staff from the Sargent and Lundy office. Review the bid documents package identified as GENERA-15240-061-0017 for the Installation of the Tesla batteries phase, submitted by Sargent & Lundy at the Aguirre Site. It was also present the selected contractor, RG Engineering, represented by Ing. Jose Auli and José Segarra. Sargent and Lundy rejected the proposed control room designed by RG Engineering in response to the lack of space for all the proposed equipment. RG Engineering will revise its proposal to incorporate all the required equipment as specified in the arrangement shown in the design.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue working on the Review and make corrections on Quality Assurance & Control, adding comments & made corrections discussed previously in testing responsible. and third-party inspector qualifications. Made agendas for preparatory meetings for Gilberto Sucre (DCMC) Approval. Follow-up with Carlos Villamil (Villamil group) the status of the quotes and invoices discussed in the morning.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Working on the Review and make corrections on Quality Assurance & Control, adding comments & made corrections discussed previously in testing responsible. and third-party inspector qualifications. Made agendas for preparatory meetings for Gilberto Sucre (DCMC) Approval.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call Meeting with Carlos Villamil (Villamil Group) to discussed quotes prices and invoices for works performed (Clearing & Grubbing) in Yabucoa Gas Turbine.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - An evaluation of the occupational health and safety program submitted by the contractor, RGE, is being conducted. This evaluation is detailed in Section 8 of the document, "Use and Fall Protection Systems." This evaluation includes comments that will be discussed with the contractor, RGE.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - An evaluation of the occupational health and safety program submitted by the contractor, RGE, is being conducted. This evaluation is detailed in section 10 of the Lockout/Tagout Program. This evaluation includes comments that will be discussed with the contractor, RGE.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria- A visit is made to the Cambalache site where the measurements and dimensions of the entrance to the project were taken. This is done with the purpose of knowing the spaces available for the installation of the project's signage.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated several tasks for project management follow up with DCMC internal team. Phone call with Gilberto Sucre DCMC to discuss outstanding open items to follow up on Technical Design Meeting. Phone call with Jorge Mercado DCMC to check on progress of Safety Plan and Municipality coordination regarding access bridge. Phone call with Luis Duque DCMC to follow up on Procore submittal correspondence closing and distribution.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared agenda for the 6/26/25 Design technical meeting with the project team (Sargent Lundy, RG Engineering and CDM Smith). Documented items for discussion and attention.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued review of submittal RGE-0009 Quality Plan (500 pgs) and project technical specifications to markup observations to be corrected by contractor (RG Engineering).
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Technical meeting at Sargent and Lundy offices in San Juan, PR. Meeting with Sargent and Lundy (Mike Kuszynski, Robert Molner, Angel Alicea), CDM Smith (Gabriel Perez), RG Engineering (Jose Segarra) and DCMC (Gilberto Sucre) to discuss open design items and progress for the Cambalache project construction drawings completion.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Managed information and organized communication in Procore. Uploaded documents regarding permitting. Closed and distributed RFI and submittals to the general contractor (RG Engineering). Checked the Procore specifications tool to confirm all information is uploaded.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Homeca contractor at Vega Baja site had completed the removal of scaffold and wood from the Main Power Transformer (MPT) at site. The are now waiting to remove the articulated lift from the project site. Send response to RFI at Procore to Eduardo Ramos of Homeca in regard of substantial completion for VB BESS project it was mentioned in RFI that Genera does not have a guidance for Substantial Completion but in their contract, they need to complete the final project closing as per article 9.1 of their contract the following RFI was closed. Send an RFI email to Mike Kucynski of S&L in regard of new transformer concrete pad versus existing transformer pad dimension.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with Homeca contractor at Vega Baja site, they continue working with the removal of scaffold and wood from the Main Power Transformer (MPT) at site. Provide picture of Homeca office trailer they will be use by DCMC, picture was sent to Jean Menay of DCMC.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with contractor Homeca at Vega Baja site, today they are working with the removal of Main Power Transformer (MPT) scaffold at site. Reviewing email related to Procore in regard of pending RFI, these RFI should be answer by S&L. Send email to Mike Kuczynski of S&L related to open RFI pending respond by S&L. Send email to Carlos Oquendo of Sphera Group requesting to provide the final PUI report for project closing.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-Performed a recount verification process for previously audited inventory areas at the Costa Sur warehouse. The effort focused on revalidating physical quantities, ensuring consistency with prior cycle count results, and investigating any unresolved discrepancies. The review included validating bin assignment, confirming labeling accuracy, and ensuring that recorded adjustment reflects actual inventory status. Observations were documented to reinforce traceability and confirm alignment with established reconciliation protocols. Locations range from AA 181 through AA 183.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-initiates a targeted variance preview to investigate discrepancies found during previous inventory validations. The process includes auditing transactional records, analyzing movement history, and comparing part number references to validate consistency. Special attention is given to items with repeated deviations to determine root causes and implement corrective measures aimed at stabilizing data accuracy and preventing future inconsistencies. Locations range from AA 181 through AA 183.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducting a brief morning meeting with Milton Flores, Giovanni Taffanelli from DCMC and key warehouse personnel to review the day’s operational priorities, reinforce safety protocols, and ensure alignment with established cycle count procedures. The session focuses on assigning task responsibilities, clarifying expected outcomes, and addressing any outstanding inventory discrepancies requiring immediate attention. This coordination is essential to maintain accuracy and continuity in daily inventory operations.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Costa Sur facility, initiates the development of a detailed inventory assessment report to be submitted to Mr. Anthony Vega of Genera PR. The report is structured to consolidate operational findings across multiple warehouse zones, incorporating variance insights, item classification issues, and inventory health indicators. It outlines key deficiencies, highlights stock inconsistencies, and includes actionable recommendations to enhance systemic accuracy and ensure alignment with organizational standards. Locations reviewed included AA 181 through AA 183, HO 021 to H 027, GE 013 to GE 018, CA 032 to CA 059.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed cycle count operations for assigned inventory zones by conducting physical item verification, confirming bin-level assignments, and documenting count results in accordance with established protocols. The process included comparing physical quantities against system-reported balances, flagging discrepancies for immediate review, and ensuring traceability through accurate recording of findings. All activities were performed following cycle count procedures to maintain inventory integrity and support audit compliance. Inventory areas inspected during this session spanned from AA 181 through AA 183.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-initiating the preparatory phase for the upcoming cycle count at the Costa Sur warehouse alongside Mr. Hernan Machado from DCMC, by reviewing system inventory reports, validating item master records, and confirming assigned bin locations. Task includes staging physical areas for count readiness, ensuring that labeling and storage conditions meet audit requirements, and briefing warehouse personnel on count protocols and documentation standards. These steps are essential to establish a controlled environment and reduce the risk of discrepancies during the execution phase.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the weekly meeting with CPM, I focused on reviewing Critical Components priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez DCMC Eduardo Rivera, and Pedro Cabrera. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 5 - Structural Steel and DIVISION 6 - Rough Carpentry.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 6 - Rough Carpentry and DIVISION 7 - Waterptoofing and Dampproofing.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 6 - Rough Carpentry and DIVISION 7 - Waterptoofing and Dampproofing.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria- at the Vega Baja job site. Demolition Activities field supervision and coordination. Safety briefing conducted by Homeca Eduardo Ramos and Gilberto Soto DCMC was present this morning. Been working with Manueli Concepcion from (CDM-Smith) to discuss the Certification for payment #3 from Homeca Recyclers. Later received a phone call from Carlos Oquendo (independent contractor), regarding the erosion and sediment control (CES) plan. We planned to go over tomorrow to review it and see if its finalized.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a phone call with Homeca Recyclers Carirma Sanchez, to go over the portable bathrooms. I also told Eduardo Rivera Jordan (DCMC) via phone about the portable latrines. Went over Project Documents Overview and analyzed documents status in the Procore platform. Verified all the punch list items that are open and the demobilization Punch list items #36 was closed, Homeca Recyclers was working on Item #37 removing the scaffolding from the transformer.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we removed the manlift with Emmanuel Santos and Izac Morales from Homeca and Continued dismantling wood panel protection for the transformer.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Continue working with Pre-Intervention Review - Working with Jaca & Sierra Contract #105165_2025-G00054 and TO#3_Invoice# 0054668_ Dec 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 164 | 492 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens_Contract #00106588 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #2 and #3 based on contract requirements. Reviewing Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 164 | 410 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AH021 to AH027 and GE013 to GE018
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AH021 to AH027 and GE013 to GE018
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AH021 to AH027 and GE013 to GE018
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AH021 to AH027 and GE013 to GE018
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AH021 to AH027 and GE013 to GE018
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AA 01 081 000 to AA 01 083 000.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AA 01 081 000 to AA 01 083 000
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AA 01 081 000 to AA 01 083 000
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BF 001 to BF 025 at the Aguirre warehouse to initiate the cycle counts.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BF 025 to BF 050
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BF 001 TO BF 025 RECOUNT LIST # 1201
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Aguirre. Hurricane Maria: Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BF 001 TO BF 025 LIST # 1200/1201
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount List #1227 from locations CA032 to CA059 for a total of 1,524 pcs.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CA032 to CA059 to begin the cycle counts.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CA032 to CA059 in Cycle Count List # 1211.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Verify among Costa Sur BESS and Peakers projects for files uploaded at the wrong Costa Sur Project. Also, working on the directory of BESS Costa Sur to replace users inside response workflows, gather vendor information on potential submittal packages and QA/QC of the Documents Tool in terms of contractual agreements.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 151 | 453 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Camablache Incoming Data Review & Process/ RG Peakers Incoming Data Review & Process/Vega Baja & Cambalache Review of Permissions/
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/GEN 01 Procurement Data_RFP/RFQ Data Review & Process
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 Hurricane Maria - Reviewed documentation structure across Costa Sur BESS and Peakers projects to identify and correct misfiled documents. Updated the BESS Costa Sur directory by replacing users in response workflows and gathering vendor details related to upcoming submittal packages. Performed quality checks in the Documents Tool to ensure alignment with contractual documentation requirements.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the publishing for the Submittals Internal and the Meetings SOP for users to recognize responsibilities based on roles and permissions; also to provide users with workshop and hands-on tools for direct execution on tools and procedures inside the Procore platform.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 151 | 377.5 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work with the Critical Components projects to determine equipments currently being delivered or already with Purshase Orders to provide real lead times for equipment at the weekly projects progress meetings.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  |  | 150.53 | 150.53 | 150.53 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Safety Shoes required at Genera sites.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 - Review and analyze options on the Pre pre-intervention SOP and how to incorporate correctly the compliance validation for the vendor's invoices. Also, review the Tracker to verify what invoices are pending to start reviewing.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1.5 |  | 149 | 223.5 | 149 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Financials SOP recurrent meeting with Lauren Wells (DCMC), Lauren Kennedy (Procore), Esther Rohena (DCMC) and Rafael Calderón (DCMC). In this meeting we go over some questions for the finance team and the SOP for procore, also about pre intervention or invoice review.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 |  | 149 | 149 | 149 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 - DocuSign + Procore discussion with DCMC Lauren Wells and Rafael Calderón. In this meeting, Lauren Wells gave us a brief presentation on how DocuSign can be integrated with Procore for invoice signature and approvals.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 149 | 298 | 149 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 - PW9510 - Start pre-intervention Review on Sargent & Lundy Invoice from TO5_Feb_1843726 and update tracker. After completing the review, this invoice was sent to CDM for compliance validation.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 139 | 486.5 | 139 | Yes | 146794 | Site | Genera PR – Deliverable 11 – Project Management – DR4339: Progress continued on the translation of Volume 3, Chapter 12 (Section 13.1) of the SHE Manual. This phase focused on maintaining consistent formatting and structure, ensuring the accurate use of technical terminology, and performing a thorough review and correction of spelling errors throughout the document. Special attention was given to correcting and formatting the tables included in Section 13.1 to ensure clarity and alignment with project standards.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 |  | 139 | 34.75 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Meeting with Jackeline Rodríguez, Secretary of the Board of Directors of the Association of Centers for the Care and Development of Children, to whom we presented the BESS and Peakers project with the purpose of scheduling an upcoming visit to school and presenting Genaro's project, which summarizes the generation process as well as bringing information to the child community about the benefits of the BESS and Peakers project. These tasks also included writing an email with more information about the project.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Work on the development of a creative draft for clear and accessible communication to inform the Costa Sur community about the upcoming impact phase of the BESS and Peakers project. As part of this task, begin identifying key information and create a draft in Canva that should include the project's benefits, estimated dates, safety measures, processes involved, and points of contact for the public. Ensure that the selected content is easy to understand. The tasks involved in creating the draft in Canva include selecting graphics, identifying the brand colors, choosing the photos that will be used, and adjusting them to fit the document. It also involves other content editing tasks aimed at generating interest and engagement within the community.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.75 |  | 139 | 243.25 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Update the internal files in SharePoint—Genera PR's collaboration platform—related to the Community Relations Program for the BESS Project in Vega Baja. This includes organizing and archiving photos, meeting minutes and other relevant materials to ensure clear, accessible documentation that supports community engagement efforts and reinforces the project's accountability.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.25 |  | 139 | 173.75 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Prepare some talking points and materials related to the project in order to summarize the benefits of the BESS and Peakers project that includes an overview of the project and its positive impact for the community of Arecibo to present it at the Cross-Sector Dialogue on Location of Large-Scale Energy Projects, event promoted by Hispanic Federation, Fundación Agenda Ciudadana and National Renewable Energy Laboratory (NREL).
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 An email was written to Ms. Jackeline Rodríguez, Secretary of the Board of Directors of the Association of Centers for the Care and Development of Children-including a clear description of the proposed educational activity. The message explained that the BESS & Peakers project would be presented to the children's community in a fun and accessible way through "Genaro," an educational activity that uses a coloring book as a teaching resource. This tool allows children to learn about the energy generation and storage process in Puerto Rico. During the writing process, it was emphasized that the activity is designed to foster knowledge on key topics such as sustainability, energy resilience, and clean technologies. This explanation was essential to contextualize the purpose of the proposed visit and reinforce the educational value of the initiative to the Association.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 139 | 278 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Check the latest details before the launch of the BESS and Peakers www.genera-pr.com/bess_peakers website. These tasks included ensuring that the editing of the written content is clear, informative and consistent with the communication objectives of the project, taking care of the tone, technical precision and consistency of the language in both languages. Likewise, ensure that visual design and navigation elements are optimal to ensure an accessible and engaging experience across all devices, including an effective visual hierarchy, clear iconography, and strategic calls to action. Review that the content has all the milestones of the project by site and that the entire narrative carefully aligns the institutional narrative and functionality of the site with the values of energy transformation, resilience and innovation promoted by Genera PR and its strategic allies.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Meeting with Jorge Bracero, from the Genera PR team, to outline an action plan for the BESS and Peakers website, get project updates, and organize additional details regarding the energy meeting that will be held on Friday, June 27 in Arecibo, where we will be discussing the BESS Project.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: Updating the expense tracker, focusing on updating invoices #250258 and entering vendor names (Duenas Trailer) to ensure accurate documentation and financial tracking across the project.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 7) Review Cambalache RGE Submittal Quality Control Plan, Finishes plan, Coating Systems, Specialties plan, Toilet and Washroom Accessories and for Furnishings, Manufactured Casework for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing Project Issued for Bid (IFB) drawings to verify they meets the required specifications of the projects. Reviewed 17 pages.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing Project Issued for Bid (IFB) drawings to verify they meets the required specifications of the projects. Reviewed 20 pages.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria - DCMC Site team Carlos Rodriguez, Rafael Barrera, and Luis Echevarría lead by DCMC site Manager Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety workshop, submittals and RFI's.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continue reviewing Issue for Bid (Drawings) to configure submittals settings, Intro RFIs tools permissions, schedule tools, included in QA/QC concrete information on specific strength and rebar spacing for construction in order to compare issue for bid and issue for construction.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on Project Schedule inspection in RFP schedule considering requirements considering specification section 013216 for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 134 | 67 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on Project Schedule general requirements considering specification section 013216 for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on Project Schedule inspection in work break down structure (WBS) RFP schedule considering requirements considering specification section 013216 for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - DCMC Site team lead by site Manager Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically to permits, safety workshop, submittals and RFI's.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 7) Review Cambalache RGE Submittal Quality Control Plan, Plumbing plan, Plumbing Requirements, Heating, Ventilating, and Air Conditioning (HVAC) plan, General Requirements for HVAC Systems and for Electrical plan, Electrical Devices by Contractor for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 122 | 244 | 122 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing and analyzing BESS project milestone and converting the data within Power BI for streamlined reporting and visualization so stakeholders can better understand project progress and identify potential risks.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 122 | 183 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Zoom meeting with Lauren Wells (Lemoine), Lauren Kennedy (Procore), and DCMC personnel as Rafael Calderon and Gilberto Sucre to discuss Procore Financials Standard Operating Procedures (SOPs) and workflows.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting with the Costa Sur construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as Safety Plan, mobilization plan, list of personnel amount other documentation needed. Attendees: Gilberto Sucre (DCMC), Carlos De Jesus (DCMC), Jose Segarra (RGE) and others.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 122 | 305 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Updating Community Outreach information, Safety and Request for Proposal data for BESS and Peakers projects on Power BI for June monthly report.
2025-06-26 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Abraham Velazquez, Gilberto Sucre CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares, Enrique Laya
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Mark Merritt, Mike Merritt, Gilberto Sucre, Frances Vallejo, Lauren Wells, Ada Diaz, Foster Veazey, Jack Darnall, and Barry Scanlon, DCMC. Discussed update on project, job offers, PROCORE, logistics, other interviews, trailer set-up, construction update and safety.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 225 | 675 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal paperwork, reviewed notes and comments from meetings Reviewed correspondence and inquiries for the Peaker projects.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 225 | 900 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Costa Sur site visit to review site plans and layouts. Attendees: Carlos De Jesus DCMC Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC Lemuel Nieves Sargent & Lundy Reinaldo Romero Sargent & Lundy.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in meeting to review weeks updates and status of Costa Sur and other peaker projects Participants in the meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Management Project Meeting - Weekly Update covering: * Cambalache A + R Draft Contract * Construction Status * Equipment Delivery * Delivery Slip Impacts * Change Order # 1 * Payment Milestone # 3 * Delivery Logistics * Long Term Service Agreement * NDA's for Subcontractors Participants: Franklyn Colmenares CSA Group, Gabriel Perez CDM Smith, Rafael Calderon, Gilberto Sucre & Glorimel Torrado DCMC Partners, Mike Kuczynski Sargent & Lundy, Michael Grabstein & Allin Luong Tesla Energy
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up among DCMC Partners Management: Mark Merritt, Mike Merritt, Barry Scanlon, Frances Vallejo, Ameilia Holton, Jack Darnell, Foster Veazey, Lauren Wells and Gilberto Sucre. Main topics covered: * Hiring Updates & Recruitment Status * Geographic & Travel Compensation Challenges * Procore Implementation Progress & Challenges * Construction Progress Updates. * Procurement & Administrative Updates. * Safety Program Integration & Implementation. * Leadership Expectations & Performance
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Homeca Recycling Performance review discussion at Vega Baja with Mike Kuczynski - Sargent & Lundy to be used for their bid evaluation process and recommendation for the Peakers Costa Sur Demolition Package.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Sargent & Lundy Invoice Revision Process discussion of implementation stages and time allowed to endorsed invoices for payment. Gabriel Perez - CDM Smith, Franklyn Colmenares - CSA Group, Rafael Calderon and Gilberto Sucre - DCMC Partners.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Update discussion of Gensets Projects for Costa Sur & Aguirre to evaluate potential conflicts with Costa Sur Peakers Layout and BESS Aguirre. Due to current project development agreed to proceed with construction asap. Mike Kuczynski - Sargent & Lundy, Gabriel Perez - CDM Smith and Gilberto Sucre - DCMC.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Harry Del Valle DCMC to get de-briefing prior to his departure for the Quality Assurance Procedure Implementation, Office Trailers Installations and Supplies status across the five project sites.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One Pager Weekly Update. Gilberto Sucre DCMC met with Raissa Borges DCMC to summarize the weekly reports presented by the Site PM's in the morning to finalize and issue the weekly report.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja call with Jaime Pesquera DCMC requesting to double check the yellow paint on the south wall curbs did have not lead paint. After review of the Asbestos & Lead Study it was confirmed as lead free paint.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Sites' Status & Weekly Updates. Site PM's provided their weekly progress update, risfrks and needs for their projects: Vega Baja - Eduardo Rivera: * Demolition & Abatement & * Installation Phase Cambalache _ Andres Concepcion: * Installation Phase Costa Sur - Carlos Rodriguez: * Civil & Structural Aguirre - Jose Lopez: * Civil & Structural Yabucoa - Andres Morales: * Civil & Structural Raissa Borges updated the One Page tracker for each site to later meet in the afternoon with Gilberto Sucre to finaliza the BESS Summary One Page Update Report. All members of DCMC Partners.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine). Discussed project, job offers, PROCORE workshop schedule, interviews, trailer set-up, safety, schedule for locations, LEAN, and program management plan update.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Peakers Project Management Update meeting. Attendees were Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Carlos Palomares (CDM Smith), and Abraham Velazquez (DCMC)
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting for filters for different suppliers.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Financial Process wireframe that Raissa Borges (DCMC) is putting together.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence to Mark Merritt (DCMC) to update him on status of Procore financial user participation.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks with Luis Roman (DCMC) for progress of SOP's for PM tools.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on closing out helpdesk tickets with Gabriel Perez Quiles (Genera) for Procore support items.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore specification and drawings configurations.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 184 | 552 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet – RFP 231175 (BESS Installation at Yabucoa) - Finalized the drafting of the Procurement Memorandum. Completed the conclusion and recommendations section, conducted a thorough review for clarity and accuracy, and circulated the document to Jesús Cintrón (Genera) for feedback and final approval.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 |  | 184 | 598 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review the document submit in Procore by RGE about Cambalache Genera Project. Review and send OSHA topics for Safety Officers in Genera Site. Review the Luis Duque (DCMC) movement in Procore.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Conference call with Portosan contractors (Javier Aviles) about toilets tanks in Genera Projects. Meeting with Harry del Valle and Frances Vallejo (DCMC) about necessary equipment in Genera Site. Review the documents in Procore about Cambalache, Vega Baja and Costa Sur Genera project.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Gilberto Sucre (DCMC) to discuss staffing update and coordination.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS Sites status and update meeting via Teams with site managers for Yabucoa, Costa Sur, Aguirre, Vega Baja and Cambalache. Participants: Gilberto Sucre, Raissa Borges and other DCMC participants.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended PMO Catch up call via Teams to discuss BESS and Peaker updates, Procore status, project status per site, RFP process and Tempest Time update meeting. Participants: Mark Merritt and other DCMC participants.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and analyze material and equipment list tracker and send email to site managers to request monthly updates and quantities.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Discuss communication outreach plan and meetings with Paola Arroyo (DCMC) for the BESS project
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet – RFP 231175 (BESS Installation at Yabucoa) - Continued drafting the Procurement Memorandum. Developed detailed narrative assessments for each of the seven evaluation criteria based on the Evaluation Panel's assessment of the RGE proposal, ensuring alignment with the scoring rationale and evaluation framework.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 184 | 368 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet – RFP 231175 (BESS Installation at Yabucoa) - Continued drafting the Procurement Memorandum. Developed detailed narrative assessments for each of the seven evaluation criteria based on the Evaluation Panel's assessment of the ARG proposal, ensuring alignment with the scoring rationale and evaluation framework.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I prepared a list on excel from materials required for both trailers and took measurements from areas on the field and the transformer base for ARG company requested by Carlos Hernandez.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Reading the scope of work of the project (15 pages). Continue with a schedule missing activities report and visualizing in the schedule. There were 55 points to correct.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Start to read the project specifications. Among the topics read were according to the work to be done who is responsible, and detailed installation and baseline schedule requirements (45 pages).
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continued the review of the Operation and Maintenance Manual for the Tesla Megapack battery systems, focusing on detailed procedures for fault detection, troubleshooting, and system shutdown protocols. Also continued evaluating safety regulations to ensure that all operational procedures support compliance with best practices and minimize potential risks associated with battery storage.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria- Participated in a coordination meeting with the S&L team (Abdiel Gonzalez), Javier E. Bidot & Associates team (Luis Rivera, Hector Luis Diaz), and the DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus, and Luis Echevarría) to discuss and support the survey activities related to the site’s drainage system. Personnel who had not yet completed the required safety workshop received it prior to entering the site. Topics included site access, scope of the survey, safety considerations, and alignment on next steps.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in a coordination meeting with the S&L team (Abdiel Gonzalez), Javier E. Bidot & Associates team (Luis Rivera, Hector Luis Diaz), and the DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus, and Luis Echevarría) to discuss and support the survey activities related to the site’s drainage system. Personnel who had not yet completed the required safety workshop received it prior to entering the site. Topics included site access, scope of the survey, safety considerations, and alignment on next steps. Site Managers meeting was held during the same time were all site managers presented their issues by site lead by Gilberto Sucre [DCMC] these issues are then presented to GENERA for further development and/or solving.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Reviewing Submittals specific to underground utilities and topography of Costa Sur BESS and Peaker's Site. Additional reviewing of RFP specific of coating materials that include epoxy polyamine and others. Coating Application types and process were reviewed to also include requirements, test and repair of damaged coatings, Field meeting on BESS site with Plant Manager Miguel Beauchamp (Genera) to validate underground water findings and movement of miscellaneous metal sheets on construction site to find underground pipes.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 |  | 167 | 375.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 014500 "Quality Control" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid. Also, review Appendix #1 Design Drawing.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 |  | 167 | 292.25 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa A meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Carlos Rodriguez, Jose Lopez (DCMC), and other project team members to discuss key aspects of the ongoing project activities and Reporting from each site with the different Site Managers.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 015250 "Construction Facilities and Temporary Controls", Section 016130 "Nameplates and Tags" and Section 016600 "Product Receiving, Storage and Handling Requirements" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid. Also, review Appendix #1 Design Drawing.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue with coordination meeting with the S&L team (Abdiel Gonzalez), Javier E. Bidot & Associates team (Luis Rivera, Hector Luis Diaz), and the DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus, and Luis Echevarría) to discuss and support the survey activities related to the site’s drainage system to avoid water flow that can erode topsoil and undermine structures. Topics included site access, scope of the survey, safety considerations, and alignment on next steps to ensure the safety of foundations.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in a coordination meeting with the S&L team (Abdiel Gonzalez), Javier E. Bidot & Associates team (Luis Rivera, Hector Luis Diaz), and the DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus, and Luis Echevarría) to discuss and support the survey activities related to the site’s drainage system to ensure machinery and workers can move safely. Personnel who had not yet completed the required safety workshop received it prior to entering the site. Topics included site access, scope of the survey, safety considerations, and alignment on next steps.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Coordination Meeting on Safety and Construction Works Location: Genera PR – Aguirre Power Plant, Puerto Rico A coordination meeting was held with Jose Lopez and Jean Pierre Menay (DCMC) to review and align ongoing and upcoming construction activities with site safety protocols and operational priorities. The purpose of the meeting was to ensure that all construction work is executed efficiently, without compromising the safety of personnel or the reliability of plant operations.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Meeting. Topics Discussed with the Jose Lopez and Jean Pierre Menay (DCMC) at DCMC Bess_Aguirre: Safety Integration, Construction Schedule Coordination, Permit-to-Work System, Logistics and Material Management, Daily Coordination and Communication.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirres I was supervising the contractor Villamil Group while they were installing PVC and CPVC pipes for the connection of the toilet Trailer Office to the sanitary tank. We were attentive to the work so that the contractor complied with the policies and standards of DCMC partners and Genera PR.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Reading and review information about Material Recycling Program at Aguirre Plant, Puerto Rico as standards, good practices and norms: The program focuses on the systematic segregation, collection, and processing of recyclable materials generated during plant operations. Key materials include: Copper, aluminum, and steel from retired electrical equipment and infrastructure Used oils and lubricants recovered from machinery maintenance Electronic waste (e-waste) from obsolete control systems and communication devices Cardboard and packaging materials from incoming spare parts and equipment Plastic containers and bottles used by staff and contractors Recyclables are sorted at designated collection points across the facility and temporarily stored in compliance with OSHA and EPA guidelines. Partnering with certified recycling vendors in Puerto Rico ensures materials are processed responsibly, either through reuse, material recovery, or energy-from-waste solutions. The program has yielded measurable benefits: A reduction in landfill waste by 35% over the past year Revenue recovery through scrap metal sales Enhanced awareness among employees through ongoing workshop and signage Support for Puerto Rico’s circular economy and environmental protection initiatives.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with all site managers from DCMC: Andres Concepcion, Gabriel T. Morales, Carlos Rodríguez, Eduardo Rivera, Gilberto Sucre, and Raissa Borges (DCMC). A very brief description of the project's main activities, risks, and project needs was discussed for each project. From the Aguirre BESS site, the main activities are the RG Engineering notice to proceed expected date, the Sargent and Lundy Issue For Constructions Drawings deliverables date, the contractor entrance roads existing conditions, and who will be responsible for the maintenance and initial improvements. It was discussed that the new Genera Plan, which aims to accommodate temporary power equipment near the BESS project, could potentially conflict with the storm sewer discharge line as designed by Sargent and Lundy. A meeting will be coordinated with the plan manager to confirm this information.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (RG Engineering) and the Owner Genera PR. There are drawing pages included on the list of drawings, but the drawing was not included in Appendix 1, "Design Drawings".The Scope of the Specification includes site grading, drainage, surfacing, foundations, underground utilities, including embedded electrical conduits and duct banks, fire protection systems, a stormwater sewer system, as well as all substructure foundations and Pads for the Project.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a meeting with Alexis Cruz, the Genera PR Plant Manager for the Aguirre complex, to make a brief Team Introduction. It was attended by Carlos R. López Vallellanes and Luis Moctezuma (DCMC). The meeting consisted of a short project description of activities, to confirm with the plant manager the DCMC Trailer Office Location as per Mr. Cruz's instructions, and to discuss some details of the next steps for the project, including the bid award and construction schedule dates. Regarding the Safety topics, it was brought to Mr. Cruz's attention that the current evacuation plan should be combined with project-specific activities for implementation. This subject will be discussed in detail in a later meeting with Plan EHS, Rafael Ramos (Genera PR), and the plant's First Safety Officer (FSO), Mr. Francisco Mari from Genera PR. Mr. Cruz confirmed in this meeting the Temporary Power installation Location
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Carlos López and Luis Moctezuma (DCMC) to identify existing site conditions for the potential temporary power equipment location, which could conflict with the current BESS project storm sewer discharge line design route and potentially raise issues during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 167 | 125.25 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the AGUIRRE BESS job site. Load the descriptions on the weekly Report link for the Aguirre BESS site, including current main activities, risks, needs, and distribution of responsibilities. Also, View Situations with issues, deliverables status, internal DCMC needs, and comments. Had a brief meeting with Carlos R. López Vallellanes and Luis Moctezuma (DCMC) to review the current project's main activities and follow up with the issue for construction design status. It was discussed that the new Genera Plan, which aims to accommodate temporary power equipment near the BESS project, could potentially conflict with the storm sewer discharge line as designed by Sargent and Lundy.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Gilberto Sucre (DCMC), discussed the status of the Quality Control Plan where we are at the moment, what missing and who working to finish, also we discussed the equipment's and materials missing for office trailers, explain to him the spread sheets list for each project and create another spread sheet for inventory.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordinate with Jean Pierre Menay (DCMC), the equipment's and materials missing for office trailers, explain to him the spread sheets list for each project. prices, serial number suppliers and quantities.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - working of new forms to keep the inventory on office trailers material, and checklist to order monthly office supplies. Sent an email to all Site Managers of each project requesting return those forms filled for Monday.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Travel from Home Office Luquillo to Home Depot San Juan to Pick up office trailers printers then to Office Depot San Patricio Guaynabo for pick up the rest of the order them to CVP Guaynabo. The materials are for the Cambalache, Vega Baja, Costa Sur, Aguirre and Yabucoa Projects.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Del Valle, Harry | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Preparing all documentations for transition. Documents included, Quality Control Program, Sites materials inventory, equipment and materials needed, genera documents for Yabucoa Gas Turbine BESS Project.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - An evaluation is being conducted of the documents submitted by RGE detailing the work for the installation of the contractor's temporary offices. This evaluation includes a work safety analysis and plans for erecting the temporary offices.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - An evaluation of the occupational health and safety program submitted by the contractor, RGE, is being conducted. This evaluation is detailed in the Emergency Action Plan (Section 12). This evaluation includes comments that will be discussed with the contractor, RGE.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Review and coordination of project General Contractors request for TESLA design files, coordinated with RG Engineering (Jose Segarra) and CSA (Franklyn Colmenares) to identify and distribute files. Reviewed project existing site condition report and prepared communication to RG Engineering (Jose Segarra) to discuss and plan undergrounfd piping or lines removal and relocation.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Managed and documented Cambalache office and operational inventory to plan pending purchase for the trailer supplies.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received via Procore from general contractor (RG Engineering - Jose Segarra) and reviewed the submittal RGE-0010 regarding Temporary Warehouse storage plan to be implemented in the facility.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Internal Meeting with DCMC Partners Site Managers team to discuss project weekly status report and action items to solve in the project. Meeting with Gilberto Sucre, Raissa Borges (DCMC) and DCMC project Site Managers.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared drawing markups and action items regarding the underground lines plan to be requested to general contractor (RG Engineering). Drafted communication to be sent via email to Jose Segarra (RG Engineering)
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared and generated Cambalache weekly status report for discussion with DCMC internal team and Gilberto Sucre & Raissa Borges. This report is for team alignment actions and generate one pager report to GeneraPR.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with email send by Nelson Soler of CDM Smith related to documents turnover by Homeca. Reviewing Manifest send by Carirma Sanchez of Homeca related to project closing documentation.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Direct request for inventory of office equipment to Jaime Pesquera and Gilberto Soto (DCMC) for the Vega Baja site. Also request to Gilberto Soto an inventory for office supply, safety and cleaning. Carlos Hernandez of ARG has a concern in regard of the transformer relocation to new concrete pad and mention that this has to be informed to Gilberto Sucre of DCMC and he will have a meeting today with S&L in regard of this topic. Also have conversation with Raissa Borges of DCMC to discuss the item to be include in PMO presentation to Genera for Vega Baja Site.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with reviewing Schedule of Value (SOV) of ARG contractor. Received call from Eduardo Ramos of Homeca in regard of substantial completion list by Genera and I inform that on their contract the only have a Final Completion that should be completed for project closing.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing ARG/CERES addendum for the phase 2 project. Send email to Carlos Hernandez of ARG to redirect design RFI to Wilfredo Sierra of S&L and for submittal Ivette Miranda of S&L. Call Gilberto Sucre of DCMC to inform that yesterday was sent a RFI to Robert Molner S&L in regard of new transformer concrete pad that does not have the dimension to install the existing transformer that will be installed temporary into new transformer arrive. Reviewing site condition for Homeca project closing.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting organizer Raissa Borges and Gilberto Sucre of DCMC and all site manager of BESS projects - Construction status update for demolition and new construction of second phase. Meeting was provided an update status of Vega Baja Site regard of project closing and status of phase 2 with ARG/CERES.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled cycle count procedures for designated inventory zones, focusing on bin locations CA 009 through CA 019. The task involved verifying physical stock quantities, reconciling discrepancies against system data, and documenting any deviations for further analysis. This activity supports the broader operational objective of improving data synchronization, strengthening inventory reliability, and maintaining accurate real-time records within the warehouse management system.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led a closing-week briefing alongside Juan Vallejo, Milton Flores, and key DCMC warehouse personnel to review accomplishments and finalize reporting. The session highlighted the successful completion of all scheduled inventory activities, adherence to procedural standards, and the absence of incidents or safety concerns throughout the week. The team emphasized the importance of maintaining this level of operational discipline and reinforced positive practices that contributed to the efficient and compliant execution of warehouse tasks.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an inventory recount at the Palo Seco warehouse in collaboration with Mr. Giovanni Taffanelli from DCMC. The effort focused on confirming the accuracy of prior cycle count entries, specifically CA 009 through CA 019, identifying unresolved discrepancies, and reinforcing the consistency of recorded inventory data. This process was instrumental in validating system figures, supporting audit readiness, and ensuring dependable inventory records aligned with operational standards.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while working from the Palo Seco warehouse, developed a comprehensive inventory summary report to Mr. Anthony Vega of Genera PR, consolidating cross-site data from multiple warehouse facilities. The report provided an analytical breakdown of stock availability by item code, unit volume, catalog accuracy, and cost metrics. It also included a variance assessment, identified stock level alerts against defined minimum and maximum thresholds, and incorporated performance indicators to evaluate the overall inventory condition. Locations assessed included GA 001 t GA 005, BF 025 to BF 050, CA 009 to CA 019BY 001 to BY 005, BZ 001 to BZ 004, AB 122 to AB 131 and MZ 001.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a targeted variance analysis to investigate inventory deviations and assess irregular stock movements. The activity involved a comparison between physical inventory counts and system data to pinpoint root causes of discrepancies and flag systemic inaccuracies. Key actions included documenting mismatches by location, evaluating transaction logs for potential input errors, and recommending corrective adjustment to improve inventory reconciliation practices. The locations impacted were CA 009 through CA 019.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at the Palo Seco warehouse, collaborating with Mr. Giovanni Taffanelli from DCMC to conduct inventory review preparations and cycle count documentation for upcoming activities. The efforts include confirming the accuracy of item bin locations, analyzing stock levels, and compiling necessary resources to facilitate a smooth and organized counting process. These actions were intended to support operational readiness and ensure that all materials and data were properly aligned for the scheduled inventory procedures.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Cost Estimation | Direct-PA | Activities necessary to develop/document project's cost estimate (any level) | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop a CE related to Fuel Efficiency Components under the FEMA Public Assistance (PA) Program. This task included reviewing scope alignment with eligible damages, refining quantities and unit costs, and ensuring compliance with FEMA cost reasonableness guidelines. The objective is to support accurate and justifiable funding requests, contributing to proper documentation and audit readiness as part of the DR 4339 recovery efforts.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Gathering information to complete the ER-1 Cost Share Program requirements and Federal Register guidelines, the plant-specific forms. Assistance is requested from GENERA-PR Operations to populate each form—including the long-term O&M plan for CDBG-DR-funded electrical improvements—using the ER1 Compliance Requirements, Program Overview, and online guides as reference.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Worked jointly with D’Alexzander González (DCMC Partners) on a PREPA-requested response to an RFI (Request for Information) from FEMA regarding FAASt funds allocation under Hurricane María. The session focused on preparing a financial forecast of the additional FAASt Award funds that Genera will require to complete all current and future projects under Disaster 4339 (parent PW 6099, project 136271). The analysis considered amendments already submitted through Grants Portal, amendments currently in development, procurement data (awarded and pending), information provided by Genera’s PMO team, and projections for upcoming initiatives.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails send by Carlos de Jesus from DCMC BESS Costa Sur - Template comments for Cambalache and Submittals RGE-0007.1 RGE-0007 RG Engineering Safety Manual, Request for Clarification and Confirmation of Revised Top Platform Dimensions on Procore.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS (Continue) Review and Comparison Sargent & Lundy Specification No.: G-2600 Section 014500 and Quality Control Quality Control Manual RG Engineering, Inc. DIVISION 15 - Mechanical and DIVISION 16 - Electrical.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails send by Carlos de Jesus from DCMC BESS Costa Sur - Template comments for Cambalache and Submittals RGE-0008.1 RGE-0008 EMPLOYEES CERTIFICATION on Procore.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Went over project documents overview and analyzing documents status in the Procore platform and all the punch list items that were closed today, were these items #37, Item #36, Item #35, Item #33, Item #31 were closed.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria -at the Vega Baja job site. Demolition Activities field supervision and coordination. Had a meeting with Gilberto Soto DCMC and Nelson Soler from (CDM-Smith) to discuss the Certification for payment #3 from Homeca Recyclers and punch list item #30 that still open from Homeca recyclers. Received follow up call from Carlos Oquendo (independent contractor) regarding the erosion and sediment control (CES) plan. Once it is finalized, we planned to review it.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I prepared a list on excel from materials required for both trailers and took measurements from areas on the field and the transformer base for ARG Carlos Hernandez. Excel list completed and forwarded, information requested analyzed and send to ARG for discussion.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates for MVT, GSU, MegaPacks and tariffs for all plants. Pending FOMB review. Meeting participants TESLA (Michael Grabstein, Elizabeth Arentsen, Allin Luong), CSA (Franklyn Colmenares), and DCMC (Rafael Calderon)
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 |  | 164 | 492 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Continue working with Pre-Intervention Review - Working with Jaca & Sierra Contract #105165_2025-G00054 and TO#3_Invoice# 0055188_ Feb 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Working with Pre-Intervention Review - Working with Jaca & Sierra Contract #105165_2025-G00054 and TO#3_Invoice# 0055188_ Feb 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 _meeting between DCMC and CDM. Meeting to discussed Invoice Pre-Intervention process and new compliance review integration. Reviewing general invoices from S&L and CDM and look for solutions to streamline the review process and tasks confirmation. DCMC participants (Gilberto Sucre, Glorimel Torrado ) From CDM (Franklyn Colmenares, Gabriel Sepulveda)
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 |  | 152 | 266 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations CA009-CA019 to start the cycle counts.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GA001 to GA005
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GA001 to GA005
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GA001 to GA005
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GA001 to GA005
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GA001 to GA005
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations: BY 00 001 @ BY 00 005 ; BZ 00 001 @ BZ 00 004; AB 01 022 @ AB 01 031 and MZ 00 001
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BY 00 001 @ BY 00 005 ; BZ 00 001 @ BZ 00 004; AB 01 022 @ AB 01 031 and MZ 00 001
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BY 00 001 @ BY 00 005 ; BZ 00 001 @ BZ 00 004; AB 01 022 @ AB 01 031 and MZ 00 001
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BF 001 to BF 025
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BF 025 to BF 050 RECOUNT LIST #1223
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria; Aguirre-Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BF 025 TO BF 050 LIST # 1206/1207
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BF 025 to BF 050 at the Aguirre warehouse to initiate the cycle counts.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1238, 1239 and 1240 from locations CA009-CA019 for a total of 315 units.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 |  | 152 | 418 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CA009-CA019 in Cycle Count List # 1230.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Procore Weekly Meeting hosted by Franklyn Colmenares (CSA) and joined by Rafael Pabon (CDM Smith), Lauren Wells (Lemoine), Ivette Miranda (S&L) and myself. Discussed the status of the Financials Tool and its features, talked about the current process for approvals on vendor's submittals.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /Procore Peakers Projects Incorporate S&L New Users/ GEN 01 Data Management Review & Process -Various Projects/GEN 01 Procurement RFPs Data Review & Process/Procore GEN 01 BESS & Peakers Folder incorporate TESLA New User
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /GEN 01 Data Management Review & Process -Various Projects/GEN 01 Procurement RFPs Data Review & Process
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the organization charts update per site to edit Project Teams main staff in the Home Page. Also, editing distribution lists at the company level to start creating distribution groups per project.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Perform projections between Procore and Primavera Scheduling software to report on the full extents of Procore Scheduling tool as to measuring contractor's manpower and scheduled resources. Working to relate project resources with certified employee wages for federal funds compliance.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 - Review and complete the Meetings SOP for internal users; establish controls for approval collection, steps to convert agenda into minutes, minutes distribution, and follow-up meeting for meetings with repeated occurrence.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – Work on the spreadsheets and modules prepared for users to examine the execution of platform while enhancing features for the automation of workflows and documentation routing.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Configure the Fire Suppression Technical Specifications to publish Specs Book under the Master format for USA and Canada construction regions. Editing Pagebreaks to break Spec into Parts as stated in the Table of Contents.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - pw#9510 Complete Pre Intervention Review Jaca & Sierra Engineering Inv#54667 Aguirre for Geotechnical Work review the invoice schedule of values. Also verify the change order request and the Exhibit G . This invoice was sent to RFI for missing Change order signature. Update the tracker.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - pw#9510 Start Pre Intervention Review Jaca & Sierra Engineering Inv#54667 Aguirre for Geotechnical Work review the invoice schedule of values.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 149 | 149 | 149 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR 4339 - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA. Preparing the Power Point presentation for Monday recurrent meeting with Client (Genera). The report was updated with the work completed during the week.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 149 | 149 | 149 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 - Genera & Tesla Management Project Meeting to discuss tariffs, change orders, payment milestone #3, amend and restate follow up and project management overall. In this meeting participates from Tesla: Allin Luong, Michael Grabstein and Elizabeth Arentsen; from DCMC: Gilberto Sucre, Glorimel Torrado, Rafael Calderón and from CDM: Franklyn Colmenares and Gabriel Sepúlveda; Sargent and Lundy: Mike Kuczynski.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Travel from Hato Rey, Genera PR headquarters, to Arecibo to participate in the Cross-Sector Dialogue on Location of Large-Scale Energy Projects event promoted by Hispanic Federation, Fundación Agenda Ciudadana and National Renewable Energy Laboratory (NREL). In this regional event, the BESS project will be presented, its benefits and guide the community on its implementation in Puerto Rico, as well as questions on the subject will be addressed in order to guide citizens. This participation will allow us to strengthen our relationships with the community.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Write an email to Melanie Ramos from the National Renewable Energy Laboratory (NREL) to send her the materials related to the BESS Project in Puerto Rico, following our participation together in the community meeting Trans-sectoral Dialogue on the Location of Large-Scale Energy Projects convened by Hispanic Federation, Fundación Agenda Ciudadana, and the National Renewable Energy Laboratory (NREL for its acronym in English). This task included gathering the project materials, introducing myself, and then contacting her to let her know that I had sent the materials.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Meeting with the Genera PR team, Jorge Bracero and Iván Báez and the Red Cross team, Karem Pérez and Zenobia Donato with whom we talked about the continuity of the Genera PR community agreements, specifically in those municipalities in which we have the BESS project. We also talked about the possibility of coordinating new collaboration strategies during the rest of the year in order to involve the community. Finally, we talked about the next steps we will be implementing as part of the collaboration agreement.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Travel from Arecibo to Hato Rey, Genera PR headquarters, after the event Cross-Sector Dialogue on Location of Large-Scale Energy Projects event promoted by Hispanic Federation, Fundación Agenda Ciudadana and National Renewable Energy Laboratory (NREL).
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 139 | 556 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Participate in the Cross-Sector Dialogue on the Location of Large-Scale Energy Projects in Arecibo promoted by the Hispanic Federation, Fundación Agenda Ciudadana and the National Renewable Energy Laboratory (NREL). Provide an overview of the BESS project and project objectives. We facilitate the connection between all sectors with a particular interest in the members of the community. We started a transparent dialogue to identify the priorities for the community and technicians. We explore the factors influencing regional leaders' perspectives on large-scale energy infrastructure projects, particularly on the BESS project and Peakers. The event was attended by: Marian A Pérez Martínez, from the Abra San Francisco Community; Desirre Pastrana Otero, from the Municipality of Vega Baja, Jenith Rivera Rivera, Sailboat Action; Fello Pérez; of the RAFI organization; William Torres Longo; Caribbean University; María Mercado Arroyo; Woman you are Special; Andre Sanfiorenzo from the University of Puerto Rico; Javier Vélez; Fundación Borincana and Jorge Bracero; of the Genera PR team.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339 Create a report with all the details related to the participation of Genera PR and DCMC Partners in the Cross-Sector Dialogue on the Location of Large-Scale Energy Projects in Arecibo promoted by the Hispanic Federation, Fundación Agenda Ciudadana and the National Renewable Energy Laboratory (NREL). This report included details related to the efforts that were made to document participation, in which we were able to provide details about the goals of the BESS and Peakers project, community outreach, and the people and communities impacted as part of the project
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 7) Review Cambalache RGE Submittal Quality Control Plan, Electrical plan, Control and Instrument Cable, Grounding and Bonding for Electrical Systems and Conduit, Pull Boxes, Junction Boxes, and Support Installation for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Supporting the installation of the water and septic piping for the office trailer with Villamil Group Personnel to ensure a clean water supply and effective wastewater management.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 134 | 268 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Walkdown thru the site with Jose Lopez and Luis Moctezuma (DCMC) to identify areas that might be impacted with other projects. Also look for possible rally point for the contractor's temporary parking.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 6 pages.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 134 | 134 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting with Alexis Cruz (Genera), Jose Lopez and Luis Moctezuma (DCMC) to introduce DCMC on-site Team. The topics of the meeting were safety; evacuation plan and other projects close our project area.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Participated in a coordination meeting with the S&L team (Abdiel Gonzalez), Javier E. Bidot & Associates team (Luis Rivera, Hector Luis Diaz), and the DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus, and Luis Echevarría) to discuss and support the survey activities related to the site’s drainage system. Personnel who had not yet completed the required safety workshop received it prior to entering the site. Topics included site access, scope of the survey, safety considerations, and alignment on next steps.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria-Continue with coordination meeting with the S&L team (Abdiel Gonzalez), Javier E. Bidot & Associates team (Luis Rivera, Hector Luis Diaz), and the DCMC team (Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus, and Luis Echevarría) to discuss and support the survey activities related to the site’s drainage system. Topics included site access, scope of the survey, safety considerations, and alignment on next steps.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on meeting minute for considering requirements specification section 013216 for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on meeting minute for considering requirements specification section 013216 in logical construction for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 7) Review Cambalache RGE Submittal Quality Control Plan, Electrical plan, Site Security, Medium-Voltage Power Cable and Low-Voltage Power Cable for the submittal approval of the 4339_9510 BESS_Cambalache project.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Reviewing correspondence concerning Genera projects report comments from CDM Smith and the DCMC PMO team.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 122 | 366 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue incorporating data collected from BESS sites updates into Power BI and generating a weekly report.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Microsoft Teams meeting with Gilberto Sucre (DCMC) to review the One-Pager report information and make any necessary updates.
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 122 | 183 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting to review site managers' updates for the BESS and Peakers projects. Attendees DCMC: Gilberto Sucre, Andres Concepción, Eduardo Rivera and others
2025-06-27 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 122 | 244 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Analyzing and organizing data collected from the Site Managers meeting and incorporating it into the weekly One Pager report.
2025-06-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Velazquez, Abraham | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  |  | 30 | 30 | 30 | Yes | 146794 |  | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 gas for vehicle weekly site visits and office visits for the peakers projects
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information for SOP completion.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in meetings, costa sur construction and sequencing plan and schedule draw down discussed the revised schedule, procurement impacts to master schedule and sequencing the demolition and construction activities. Participants in the meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal review of meeting notes and communications from the project (emails/texts)
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in BESS/PEAKERS project needs meeting items discussed where the removal of existing materials and clearing an area that can be used for future laydown space during demolition phase at costa sur. attended the meeting; German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gilberto Sucre DCMC Frances Vallejo Rosich DCMC Jesus. Cintron Genera
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 225 | 450 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended meeting, PEAKERS CHECK IN, discussed status update for the costa sur project, Jobos project, and Yabucoa project Attended the meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peakers Needs from Genera. Rafael Pabon, Gabriel Perez CDM Smith, German Nunez - Genera, Abraham Velazquez & Gilberto Sucre - DCMC. and Franklyn Colmenares CSA Group. Discuss needs to support both programs. Sargent & Lundy -Design Progress, Budget & Schedules, Invoice Approvals Reviewed Vea Baja & Cambalache, Palo Seco Needs Amendment required for Beta Engineering to complete Transformer Studies GE Visit to PR on 7/9 & 7/10 AM at Genera and visits to Yabucoa, Daguao & Jobos.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 225 | 337.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check-in Weekly Meeting Led by Gabriel Perez CDM Smith. General Status Update was provided for Cambalache, Veag Baja - Installation, Aguirre, Costa Sur, Yabucoa, Vega Baja Demolition, Palo Seco Pre-Demolition, and Aguirre - Phase Approach. Global Status was also discussed for Design Drawings, Procore, Unit Retirement List, Interconnection Studies, Next Round of Installation RFP, Tesla, Land Use, Transformer Studies, Project Cash Flow Analysis, Internet Provider CM Trailers and Community Engagement for all Sites. Mike Kuczinski Sargent & Lundy, Enrique Laya CDM Smith, Franklyn Colmenares - CSA Group Lauren Wells, Sheila Torres - DCMC
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM Weekly Meeting with Franklyn Colmenares CSA Group in preparation for Genera's Needs. Vega Baja: * Soil Classification Study * Tariffs Clause ARG Ceres Contract * Transformer Relocation Luma or Alternate Site * Disconnect 38KV to transformer. Cambalache: * Site Entry Security Definition Meeting with Digno - Genera * Temporary Warehouse Submittal * Bridge Load Study * Costa Sur/Aguirre/Yabucoa: * Gather all RFP's comments and share with TRC to have alignment meeting on Sargent & Lundy Performance Audit. Request weekly Time Sheets * Procore Get with Lauren Wells for old information transfer.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 |  | 225 | 168.75 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Peakers - Construction Sequencing Study meeting with German Nunez - Genera and DCMC Peakers Team Abraham Velazquez, Carlos Rodriguez, Carlos De Jesus, Rafael Barrero and Gilberto Sucre. Genera walked us thru the 3D model and provided input on previous projects activities durations to contribute to Construction Sequencing Presentation due the following day, in consideration of having three contractors, demolition, civil & structural and Installation all concurrently.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Contract Discussion with Francisco Feliu - Genera & Gabriel Perez - CDM Smith. Remaining topic - Tariffs escalation & Cost Sharing 50/50. Discussed strategy - path-forward discussion with Carlos Hernandez ARG Ceres.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Meeting PM/ CM Team. Meeting with Enrique Laya - CDM Smith and Robert Molner - Sargent & Lundy who provided an IFC Drawings issue by Site, Costa Sur 7/10, Vega Baja 7/17, Aguirre 7/24 & Cambalache issue pending RGE structural drawings. A complete disappointment as design continues to slip nothing the cost & schedule risks to all projects.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Ricardo Pallens (Genera), Carlos Palomares (CDM Smith), Joaquin Quinoy (Genera), Gabriel Perez (CDM Smith), Mike Kuczynski, Nelson Rosado (Sargent and Lundy), Franklyn Colmenares (CDM Smith), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Follow up meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in. Franklyn Colmenares (CSA), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 225 | 225 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) and Luis Roman (DCMC) for Procore weekly check-in to discuss open items as a team.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting to show number of RFI/Submittals.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore directory items for home page listing.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on pending Procore financial items.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore workflows.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore financial items.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 225 | 112.5 | 225 | Yes | 146794 | Remote | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items for adding users to Procore directory.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 |  | 184 | 598 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussed with Vladimir Scutt from Genera PR the reporting needs for power plant KPIs and the upcoming compliance report on Power Generation and Fuels Consumption. Also discussed reporting requirements with Victor Torres from Genera PR to ensure alignment for integration with their internal Power BI dashboards. Updated the Genera Connect Financial Tracker with the latest data and reviewed access to necessary resources to facilitate the evaluation of reporting KPIs.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with portosan contractors (Javier Aviles) about toilets tanks in Genera Projects. Review the documents submits by RGE in Procore about Cambalache, Review the documents submits by Dueñas Trailers about all Genera projects.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 184 | 736 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continue review the Safety documents in Procore about Cambalache Genera Site. Meeting call with Luis Moctezuma about the Health and Safety topics in Aguirre Genera Site. Conference call with Frances Vallejo, Gilberto Sucre and Jose Lopez (DCMC) about Aguirre Genera project. Instructing Sunem Martinez (DCMC) in Genera Safety program. Conference call with Carlos Villamil (Villamil group) about Cambalache Site septic tank installation.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 184 | 230 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended meeting with Sunem Martinez (DCMC), Gilberto Sucre and Jean Menay (DCMC), to discuss onboarding and PMO overview regarding BESS project at Aguirre.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Update PMO organization chart with names, emails and site positions.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 184 | 276 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Costa Sur construction sequencing plan and schedule drawdown meeting via Teams with Abraham Velazquez (DCMC) and other DCMC participants and German Nunez (Genera). We discussed Peaker project at Costa Sur site and next steps.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with BESS project management team and Peakers team to discuss project needs. Participants: Gabriel Perez (CDM), German Nunez (Genera), Abraham Velazquez, Gilberto Sucre and Sheila Torres (DCMC)
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Jean Pierre Menay (DCMC) to discuss materials needed and PPE purchases at Yabucoa, Aguirre, Costa Sur.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended BESS check in meeting with project management team to discuss BESS project overview, pending issues, RFPs, Procore financials and next steps. Participants: Jesus Cintron (Genera), Gabriel Perez (CDM), Sheila Torres (DCMC), Paola Arroyo, Raissa Borges, Gilberto Sucre (DCMC).
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339- Hurricane Maria - Participated in the weekly BESS and Peakers Project Needs meeting with Jesús Cintrón. Reviewed the current status of key workstreams and discussed high-priority items requiring coordination or follow-up. Contributed updates and aligned on next steps to ensure continued progress across both projects. Genera: Jesús Cintrón, Germán Nuñez. DCMC: Abraham Velazquez, Frances Vallejo. CDMSmith: Franklyn Colmenares Gabriel Sepulveda Carlos Palomares & Rafael Pabón
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet ¦ Sargent & Lundy Amendment - Had a call with Rick Patterson (DCMC). Reviewed the updated cost analysis prepared by Rick Patterson (DCMC). Uploaded the document to Genera's procurement file and sent to Jesús Cintron (Genera) for sign off.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 184 | 230 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 184 | 644 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Began reviewing the RFP package for the 234MW BESS Installation at Yabucoa, Aguirre, and Costa Sur. Completed a detailed review of the 40-page solicitation document to assess compliance requirements, scope alignment, and overall procurement structure.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Verified the status of key workstreams and high-priority items related to procurement activities and contract submittals requiring approval from FOMB and P3A. This review was conducted in preparation for the weekly BESS and Peakers Project Needs meeting, ensuring up-to-date information was available to support informed decision-making and effective project coordination.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Marc Maceira, Carlos González and Ginnell Torres
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 |  | 184 | 184 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Management and Submission of FOMB Contract Approval Packages - Supported the Regulatory Team - Coordinated with internal stakeholders to finalize contract approval packages (Contract No. 107962, 108808 and RFP 4211) for submission to FOMB. Reviewed, organized, and ensured completeness of supporting documentation in accordance with FOMB’s Contract Review Policy.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 184 | 46 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Held a meeting with Victor Torres, Josué Sanchez, and Jan Rodríguez from Genera PR to establish action items in preparation for the July 7, 2025, deadline for submitting the Power Production and Fuels Consumption reports.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 184 | 92 | 184 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Held a meeting with Victor Torres from Genera PR to initiate planning for the development of reporting dashboards, focusing on prioritizing key metrics and deliverables. The discussion aimed to establish a structured approach for report creation aligned with operational needs and stakeholder expectations.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 2 | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Porto San arrived to clean the restrooms, after LUMA arrived to start transformer line disconnection.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | PREPA Genera Deliverable 11 DR 4339. Meeting conducted by Gilberto Sucre, Jose Lopez, Frances Vallejo and Jan Pierre Mena. Provided Safety workshop, guidance on the overall project of Aguirre,
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading the project specifications. The total number of pages were 139 to 173. The following was covered in the reading: selective demolition and alternations, details of existing conditions, hazardous materials and waste, disposal, cleanup, required concrete mix design data, all related at concrete masonry unit about quality, control joints, expansion joints, reinforcing and cleaning.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading the project specifications. The total pages were 46 to 87. The following was covered in the reading: Submittal procedure and time, how to present and what information should it contain the shop drawings, the instrument and equipment database requirement.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading the project specifications. The total pages were 88 to 138. The following was covered in the reading: earthwork testing (inspection, subgrade, embankment fill, backfill), inspection and testing concrete, materials and execution.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Attended a virtual meeting Teams with German Núñez (GENERA) to discuss the sequencing and phasing of the BESS project at Costa Sur. Representing DCMC were Abraham Velázquez, Carlos Rodriguez, Rafael Barrera, Carlos De Jesus, Carlos Bayron, and Luis Echevarría. The purpose of the meeting was to review the demolition, civil works, construction activities, and equipment installation phases to develop a detailed and realistic project sequence. Discussions focused on identifying potential overlaps between phases to optimize the schedule and prepare a comprehensive plan that will guide the GC in executing the work efficiently.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Reviewed the Job Safety Analysis (JSA) for the trailer removal activity at Costa Sur, prepared by RG Engineering. The review focused on verifying that all identified risks, including heavy equipment use, electrical disconnection, fall protection, and environmental hazards, were properly addressed. Evaluated the proposed control measures, required PPE, and prerequisites to ensure alignment with site-specific safety regulations and Genera’s HSE policies.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continued the review of the Job Safety Analysis (JSA) for the trailer removal at Costa Sur, with emphasis on validating the adequacy of the proposed control measures and the clarity of hazard communication. Assessed the implementation feasibility of the safety procedures on site, including coordination requirements with Genera personnel. Observations and recommendations were noted to enhance compliance with established HSE protocols and promote safer execution of the task.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Attended a virtual meeting Teams with German Núñez (GENERA) to discuss the sequencing and phasing of the BESS project at Costa Sur. Representing DCMC were Abraham Velázquez, Carlos Rodriguez, Rafael Barrera, Carlos De Jesus, Carlos Bayron, and Luis Echevarría. The purpose of the meeting was to review the demolition, civil works, construction activities, and equipment installation phases to develop a detailed and realistic project sequence. Discussions focused on identifying potential overlaps between phases to optimize the schedule and prepare a comprehensive plan that will guide the GC in executing the work efficiently. After Meeting was completed a detailed planned for scheduling was discussed with DCMC team member scheduler Carlos De Jesus, in order to formalize a preliminary plan to include all details of activities related to initial demolition, underground piping, fittings, connections to exiting system, civil work, staging, and sequencing of events leading to partial completion of Peaker's project.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Continued verification of Fridays Survey markings and site visit findings found by the S&L team (Abdiel Gonzalez), Javier E. Bidot & Associates team (Luis Rivera, Hector Luis Diaz), and from the DCMC team (Rafael Barrera) Verification of field findings related to the survey activities of the site’s underground drainage system and electrical utilities.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Held a meeting at the Yabucoa site with LUMA Inventory Supervisor Henry Diaz to discuss the requirements for construction signage and to identify, by walking and inspecting the site, an appropriate area for installation that does not interfere with existing operations at the LUMA. Also, in the meeting was discuss the LUMA plan to remove the spare parts and debris that currently is located in the project area.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 0119110 "Startup, Testing and Commissioning" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 050530 "Anchor Rods", Section 050538 "Post Installed Concrete Anchors" and Section 055842 "MISCELLANEOUS METAL & EMBEDDED WORK" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review the demolition, civil works, construction activities, and equipment installation phases to develop a detailed and realistic project sequence as discuss in the meeting. Also, verify the potential overlaps between phases to optimize the schedule and working on a comprehensive plan that will guide the General Contractor execute the work efficiently.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue in-site with the survey activities the site’s drainage system to avoid water flow that can erode topsoil and undermine structures, included site access, scope of the survey, safety considerations, and alignment on next steps to ensure the safety of foundations.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Attended a virtual meeting Teams with German Núñez (GENERA) to discuss the sequencing and phasing of the BESS project at Costa Sur. Representing DCMC were Abraham Velázquez, Carlos Rodriguez, Rafael Barrera, Carlos De Jesus, Carlos Bayron, and Luis Echevarría. The purpose of the meeting was to review the demolition, civil works, construction activities, and equipment installation phases to develop a detailed and realistic project sequence. Discussions focused on identifying potential overlaps between phases to optimize the schedule and prepare a comprehensive plan that will guide the GC in executing the work efficiently.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre We were working on creating an Inspection Preparation Checklist Form that adapts to the Bess_Aguirre Project using Attachment J and we are review the next standards they are applicate to the project: Part Number:1926 Part Number Title:Safety and Health Regulations for Construction Subpart:1926 Subpart C Subpart Title:General Safety and Health Provisions Standard Number: 1926.20 Title: General safety and health provisions. GPO Source: e-CFR
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewing and reading some of the standards that may apply to the Bess_Aguirre Project according to the activities to be carried out. Stairs (29 CFR §1926.1053), Motor Industrial Truck (29 CFR §1910.178), Lockout and Tagout (29 CFR §1910.147), Machine Guarding (29 CFR §1910.212)
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Team Meeting with Sargent and Lundy (S&L) to review the Design Drawings Issue for Construction Status and Provide Clarifications for the Cambalache and Aguirre BESS Project. The main discussion was to review all pending project items to complete the Issue for Construction Drawings. Attendees for this meeting were Gabriel Pérez (CDM Smith), Gilberto Sucre, and Andres Concepción (DCMC). Franklyn Colmenares (CDM Smith), Enrique Laya (CDM Smith). On the S&L team were Mike Kuczynski, Robert Molner, and the Civil Design Staff from the Sargent and Lundy office. Review the bid documents package identified as GENERA-15240-061-0017 for the Installation of the Tesla batteries phase, submitted by Sargent & Lundy at the Aguirre Site. The Cambalache Site has a potential conflict with an existing water distribution line in the same path as the proposed BESS site, which will be discussed in detail during a site visit from S&L scheduled for tomorrow. Additionally, JACA and Sierra, a Geotechnical company, will perform a Radar Penetration test, and RG Engineering representative José Segarra will also be present to explore options for identifying the line route in the field and the means and methods of the test.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the Issue bid drawings documents to identify potential and possible change orders, as well as potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects to be integrated into the PROCORE platform, and a call was held with Javier Ignacio from Portosan to coordinate equipment delivery to the Aguirre Site.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 |  | 167 | 41.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Call with Carlos Bayron- QA/QC- (DCMC) at Costa Sur, to discuss the QA/QC plan submitted by the Contractor RG Engineering for the Costa Sur Project. The main subject of the call was to discuss the possibility of having a QA/QC plan completed by DCMC Partners to review and evaluate the applicable conditions for the Costa Sur Project. At this moment, a follow-up meeting should be held with Gilberto Sucre (DCMC) to verify the Document Status for evaluation. It was also agreed to perform a weekly meeting with all QA/QCs to discuss the need for the QA/QC plan.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 167 | 417.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Yabucoa BESS PROJECT. Meeting with Gabriel T. Morales, site Manager (DCMC) at the Yabucoa Bess project to review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy for the Yabucoa Job Site Included in the Specifications G-3400, review the Division of Responsibilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD), and the Owner Genera PR. Joint efforts with Gabriel T. Morales (DCMC) to identify mismatch information provided by Sargent & Lundy within the provided specifications, designed drawings for the installation phase, the Scope of Work description, and the Directive of Responsibilities from one to 249 line items.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 |  | 167 | 208.75 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. New Hires Meeting with Gilberto Sucre, Jean Pierre Menay, Frances Vallejo (DCMC), and the new hire, Sunem Martínez, who will be the latest team member for the Aguirre Site, working with project controls and schedules. A brief project description was presented to Sunem Martínez, and also a general arrangement drawing was shown during the meeting. We schedule the job site start date for July 7, 2025. In the meantime, the Aguirre DCMC site Manager (José M. López-Linares) will send all the project information by email.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Created inventory list for operational assets needed and available in the office trailer on site. This will ensure team operational needs for construction management.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Reviewed submittal # RGE-0011 regarding the levee access road modification design proposal by RG Engineering (Jose Segarra), consolidated observations and comments to be included in submittal's response.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Organized and generated correspondence (emails) with pending action items related to required work plans and submittals approvals from GeneraPR plant manager. All emails communicated to GeneraPR (Herminio Arroyo).
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Drafted response and comments for the Quality Control Plan submittal for the project. Consolidated team comments and continued to include important details to consider in the quality plan.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated email correspondence to request to General Contractor (RG Engineering - Jose Segarra) to provide a plan for the site underground infrastructure pre-demolition plan to ensure activities are performed satisfactorily.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 |  | 167 | 83.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project RFI#22 response regarding BESS Platform dimensions. Ensured that it was documented properly and all information was included. Followed up with Jose Segarra (RG Engineering) via phone and with Mike Kucsynski (Sargent & Lundy) via email on pending information.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 167 | 250.5 | 167 | Yes | 146794 | Site | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Submittal RGE-0001 response regarding the design for the control room. Verified technical comments and worked on the correspondence via Procore to RG Engineering (Jose Segarra)
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Luma personnel that are working with the disconnect of the TL 0010 of 38kV from the existing MPT work was completed by Luma. Continue working with the review of Vega Baja As-Built drawing and generating comments in regard of the As-Built. Send response to Carirma Sanchez of Homeca in Procore regard of submittal for As-Built drawing was sent back with review and comments.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Homeca project closing for Vega Baja Site. Send email to Harry Del Valle of DCMC for equipment inventory. Send email to Gilberto Sucre of DCMC in regard of pending item by Homeca, Sphere Group, Luma and Genera for Vega Baja site.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 |  | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Luma that arrive to project for the disconnect of the TL 0010 of 38kV from the existing MPT. Working with review of Vega Baja As-Built drawing.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 |  | 167 | 501 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Modify audit-style responses to PREB Item 88 on PEAKERS Installation—covering reliability analysis, full component listing, timeline feasibility, progress metrics, and alignment of short-term repairs.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 2 | 167 | 334 | 167 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Porto San arrived to clean the restrooms, after luma arrived to start transformer line disconnection. Luma completed transformer distribution line disconnection including concrete pole.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Kept reviewing Certificate of payment #3 from Homeca Recyclers with Manueli Concepcion from CDM-Smith. Also supervised a LUMA team that came into the site to finally disconnect the old transformer to prevent accidents and mitigate environmental risks,
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 167 | 668 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents reviewed punch list reviewed all the items, make sure all were closed except for item #30 & item #32. Made an internal inventory of trailer equipment. Reviewed Certificate of Payment #3 from Carirma Sanchez (from Homeca Recyclers), had various phone conversations with Emanueli Concepcion from CDM-Smith about the certificate of payment also reviewed it.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Email and call an Interport Trading Corporation supplier for a quote on a gas cylinder storage cabinet for the temporary relocation of the Cambalache gas room.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 |  | 167 | 584.5 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails: Cambalache BESS - Levee access road RGE proposal., field visit to the Cambalache Power Plant on Tuesday, July 1st, 2025, and Submittals: RGE-0008.1 RGE-0008 EMPLOYEES CERTIFICATION, Cambalache Temporary Warehouse RFP SOW, RGE-0007.1 RGE-0007 RG Engineering Safety Manual, RGE-0001.0 BESS Cambalache control room layout and views on Procore
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 167 | 167 | 167 | Yes | 146794 | Site | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Coordinate via phone the visit of designer Sargent & Lundy tomorrow, July 1st, to the Cambalache site with Andres Concepcion of DCMC to take measurements of the pipes for the new parking lot.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 164 | 82 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339 - New- DCMC & Genera- Weekly Status Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexander Gonzalez, Esther Rohena, Eisha Mercader, Glorimel Torrado, Cynthia Ortiz, Christian Cruz), from MSC ( Shellsea Maysonet), from HONRA LLC (Marc Maceira), From Genera (Alejandro Maymi)
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 |  | 164 | 164 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 |  | 164 | 328 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 164 | 246 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA / BESS Check-In meeting with project management Team. Contract 106761 and Deliverable Schedule review based contract development. Meeting between CDM Smith PM team (Gabriel Sepulveda, Carlos Palomares), Sargent & Lundy ( (Mike Kuczynski, Miguel Del Valle, Nelson Rosado), Genera (Jesus Cintron) and DCMC (Rafael Calderon, Gilberto Sucre, Foster Veazey, Paola Arroyo, Raissa Borges, Luis Roman, Frances Vallejo), Lemoine Procore (Lauren Wells).
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 |  | 164 | 574 | 164 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #293410-16 for TO#1 May 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB011 to AB019
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AB011 to AB019
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 |  | 152 | 304 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AB011 to AB019
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB011 to AB019
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB011 to AB019
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 01 032 000 to AB 01 049 000
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 01 032 000 to AB 01 049 000
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 01 032 000 to AB 01 049 000
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 |  | 152 | 532 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BF 050 to BF 075 LIST #1224/1225/1226 AND RECOUNT LIST # 1235/1236
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BF 050 to BF 075 at the Aguirre warehouse to initiate the cycle counts.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 |  | 152 | 608 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Aguirre. Hurricane Maria: Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BF 050 TO BF 075 LIST # 1224/1225/1226
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 |  | 152 | 152 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BF 050 TO BF 075
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 |  | 152 | 76 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 |  | 152 | 456 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CB016 to CB026, Cycle Count List # 1243.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 |  | 152 | 228 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CB016 to CB026 to begin the cycle counts.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 |  | 152 | 380 | 152 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount List #1251 from locations CB016 to CB026 for a total of 2650 pcs.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the Cambalache project specifically with the recently received Demolitions Specification Book Issued for Construction and the execution of submittals response provided by the Design Team which is not currently matching Procore response options and final actions.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the setup to implement Genera's Warehouses Inventory to be executed through Procore, from data uploading and sharing, and the tracking and execution of Warehouse inventories through Genera's main plants and warehouses.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call Meeting with Raissa Borges (DCMC) to discuss the ongoing activities and implementations for the tracking of inventory in Genera's warehouses across the plants; information gathering to provide the proper tools to automate this process into the Procore Platform.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 |  | 151 | 226.5 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the contractual agreement for the Vega Baja demolition phase to verify compliance with federal funding clauses involving minimum wages, equipment and construction materials source of origin, owners responsibility and other project management information analysis.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 |  | 151 | 75.5 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Edit the naming convention for the Submittal Workflow Templates established for all projects to maintain consistency in the templates title and contents.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Teams Call with Lauren Wells (Lemoine) and Theresa Perez (DCMC) to perform the weekly Procore internal check-in on ongoing tasks and issues. Discussed the current activities in Peakers Equipment Supply for Yabucoa, Jobos and Daguao, and also the potential implementation of tracking warehouse inventories inside Procore Documents Tool.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 |  | 151 | 302 | 151 | Yes | 146794 | Site | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the implementation for the Critical Components tracking and current update for Purchased or Acquired Items by Genera to be installed between BESS, Peakers, and other internal projects.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 151 | 151 | 151 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 ¦ DR4339 – BESS Weekly Meeting hosted by Gabriel Perez (CDM Smith) including Design Team staff Mike Kuzcynski (S&L), GIlberto Sucre (DCMC), Rafael Pabon (CDM Smith), and Jesus Cintron (Genera) among others; discussing weekly open topics for the BESS Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR 4339 ¦Genera and DCMC Weekly Meeting with participation from DCMC: José Ralat, Roberto Bosch, Rafael Calderón, Pedro Cabrera, Sheila Torres-Sterling, Eisha Mercader, Esther Rohena, Glorimel Torrado and others. Also, Shellsea Maysonet (SMC); and from Genera: Alejandro Maymí, to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 |  | 149 | 74.5 | 149 | Yes | 146794 | Site | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 - Verify CPM Excel invoice requested by José Ralat (DCMC) and make research about the RFI sent to the vendor. Also discuss with Rafael Calderón (DCMC) on critical component management invoices.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Correspondence development to Desiree Pastrana Otero, Executive Director of the Secretariat for Planning and Land Use Management in Vega Baja to shared project materials with stakeholder. Sent an email including BESS-related documents, specifically the fact sheet used during the recent community meeting held in Vega Baja. Offered support in case additional materials or assistance are needed.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Work with the update of the BESS and Peakers page. These works included receiving the updated material to send it to the Genera PR team, Alex Valdés. A document was created to convey the necessary changes to the project and the changes were managed. After submitting the changes, the information was verified.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Meeting with the non-profit organization Enactus with the Genera PR team, Jorge Bracero, and Adaline Pérez, from Enactus. The meeting discussed the details of the pending events corresponding to the community impact that we will be carrying out on the sites related to the community outreach of the BESS and Peakers project. The timeline corresponding to these efforts was evaluated, as well as pending tasks.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- Kroma and Genera Weekly Meeting in the meeting was the Genera's PR Team: Ivan Baez and Jorge Bracero. In the meeting was the Kroma team: Amarilys Torres and Victoria Flores. The meeting focused on recent issues related to Genera PR. Similarly, we elaborate on the information of the advertising campaign that Genera PR will be activating to inform about the integration of more electricity generation capacity. Likewise, we evaluate the pending issues of the project as well as its timeline.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 139 | 208.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ DR 4339- meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander González, Rafael Calderón, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey. In the meeting was the Genera PR Team: Jesús Cintron, Joaquín A Quinoy, Ricardo Pallens, María Sánchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczinsky and Nelson Rosado. At the meeting, the BESS project and the stages in which each site is located were discussed. Key information on the updates to the genera-pr.com/bess_peaker's website was discussed and recommendations for necessary changes to the website were offered.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 |  | 139 | 104.25 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Correspondence development to Sol Molina, from the organization Agenda Ciudadana, to shared project materials with stakeholder. Sent an email including BESS-related documents, specifically the fact sheet used during the recent community meeting held in Vega Baja. Offered support in case additional materials or assistance are needed.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 |  | 139 | 173.75 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Coordinate efforts to hold a weekly meeting with Franklyn Colmenares; CSA Group and the CDM Smith team: Rafael O Pabón and Carlos A. Palomares for the purpose of updating information related to the BESS and Peakers https://genera-pr.com/bess_peakers website. These tasks included providing the team with the worksheet we will be working with, coordinating a date for weekly meetings, and explaining the reasons why we will be coordinating these efforts.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Weekly Corporate Affairs Meeting with the Genera PR: Jorge Bracero and Ivan Baez Santiago. During this meeting, topics were discussed about pending projects, learnings from the last community meeting, the possibility of holding community webinars, the need to integrate a community calendar, summer camp follow-up and the details related to summer camp visits to educate about the BESS project and Peakers in schools.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 |  | 139 | 139 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Meeting for Community Pending Items with the Genera PR team, Jorge Bracero and Estefanía González González. In this meeting, details related to the pending community activities of Genera PR were discussed, as well as future opportunities. Materials that would be shared as part of the initiatives were evaluated.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 |  | 139 | 69.5 | 139 | Yes | 146794 | Site | PREPA Genera ¦ Deliverable 11- Project Management ¦ Correspondence development Maria L. Lara Hernandez, Executive Director of Agenda Ciudadana, to shared project materials with stakeholder. Sent an email including BESS-related documents, specifically the fact sheet used during the recent community meeting held in Vega Baja and Camalache's Fact Sheet. Offered support in case additional materials or assistance are needed.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Cambalache DCMC Quality Control Plan Sample, Construction Policy & Procedures, Schedule Plan, Purpose, responsibility and general plan to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 31 pages.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Continue reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 34 pages.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Attended a virtual meeting Teams with German Nunez (GENERA) to discuss the sequencing and phasing of the BESS project at Costa Sur. Representing DCMC were Abraham Velázquez, Carlos Rodriguez, Rafael Barrera, Carlos De Jesus, Carlos Bayron, and Luis Echevarria. The purpose of the meeting was to review the demolition, civil works, construction activities, and equipment installation phases to develop a detailed and realistic project sequence. Discussions focused on identifying potential overlaps between phases to optimize the schedule and prepare a comprehensive plan that will guide the GC in executing the work efficiently.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Reviewing Issue for Bid (Drawings) to configure submittals settings, Intro RFIs tools permissions, schedule tools, included in QA/QC concrete information on specific strength and rebar spacing for construction in order to compare issue for bid and issue for construction.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 134 | 335 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria Analyzed Issue for Bid drawings to verify QA/QC on concrete strength requirements and rebar spacing. Reviewed submittal settings, RFI permissions, and scheduling tools to ensure alignment between the Issue for Bid and final construction documentation.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 |  | 134 | 335 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur - worked on draft procurement schedule considering procurement equipments of Peakers and logical construction for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 134 | 201 | 134 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Attended a virtual meeting Teams with German Núñez (GENERA) to discuss the sequencing and phasing of the BESS project at Costa Sur. Representing DCMC were Abraham Velázquez, Carlos Rodriguez, Rafael Barrera, Carlos De Jesus, Carlos Bayron, and Luis Echevarría. The purpose of the meeting was to review the demolition, civil works, construction activities, and equipment installation phases to develop a detailed and realistic project sequence. Discussions focused on identifying potential overlaps between phases to optimize the schedule and prepare a comprehensive plan that will guide the GC in executing the work efficiently.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur - worked on draft procurement schedule considering Turbine equipment installation of equipments of Peakers and logical construction for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 134 | 536 | 134 | Yes | 146794 | Site | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Cambalache DCMC Quality Control Plan Sample, Construction Policy & Procedures , Storm Water Pollution Prevention Maintenance and Dimensional Control, Property Lines, Building Corners to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 |  | 122 | 305 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue developing the financial process structure as a flowchart using the Visio tool for the Genera Projects BESS & Peakers. Task requested by Mark Merrit and Lauren Wells to ensure effective alignment with Procore's financial tools.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 |  | 122 | 183 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Rafael Pabon (CDM Smith), Luis Roman (DCMC), Paola Arroyo (Genera), Jorge Bracero (Genera), Lauren Wells (Lemoine), Foster Veazey (Lemoine), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Franklyn Colmenares (CDM Smith), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Sheila Torres (DCMC).
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 |  | 122 | 122 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Developing the pre-publishing process flowchart for the Genera projects.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 |  | 122 | 488 | 122 | Yes | 146794 | Site | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Continue developing the financial process flowchart in Visio for the Genera Projects BESS & Peakers.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams meeting with Luis Román from DCMC to discuss Procore Analytics, reporting processes and how we can integrate reporting using Procore.
2025-06-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 |  | 122 | 61 | 122 | Yes | 146794 | Site | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams working section meeting with Johanna Diaz from (SMC) to discuss Grant Management processes.
97702.5
[13 empty] | Construction mgmt= | 91378
[13 empty] | Community engagement | 6324.5
97702.5

## July
Entry Date | Client | Proj level1 | Proj level2 | Proj level3 | Client title | Asset | Task | Task Group | Task Description | Activity Type | Hours | Activity Rate | Activity Extended | Billing Rate | Line Billable | Invoice Number | Narrative
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 2653.7 | 2653.7 | 2653.7 | Yes | 146795 | Villamil - Grass cutting, debris removal, and debris disposal. Digging up cyclone fences in the area to cut the grass. Remove fence pipes Remove stones and cement within the lawn to be able to cut the grass
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 1450.8 | 1450.8 | 1450.8 | Yes | 146795 | Duenas Trailer Rental - Costa Sur
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 1450.8 | 1450.8 | 1450.8 | Yes | 146795 | Duenas Trailer Rental - Cambalache-Arecibo
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 1435.2 | 1435.2 | 1435.2 | Yes | 146795 | Duenas Trailer Rental - Salinas
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 1310.4 | 1310.4 | 1310.4 | Yes | 146795 | Duenas Trailer Rental - Yabucoa
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 1106.56 | 1106.56 | 1106.56 | Yes | 146795 | Duenas Trailer Rental - Vega Baja
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 902.72 | 902.72 | 902.72 | Yes | 146795 | Duenas Trailer Rental - Cambalache-Arecibo
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 479.72 | 479.72 | 479.72 | Yes | 146795 | Home Depot - PPE Equipment for PMO project
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 369.2 | 369.2 | 369.2 | Yes | 146795 | Portosan - Portable Toilet Rental - Humacao Yabucoa
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 323.35 | 323.35 | 323.35 | Yes | 146795 | Villamil - Collection and disposal of garbage in the trailer area
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Mark Merritt, Mike Merritt, Foster Veazey, Gilberto Sucre, Frances Vallejo, Lauren Wells, Ada Diaz, and Barry Scanlon, DCMC. Discussed update on project, job offers, PROCORE, logistics, other interviews, trailer set-up, safety, and schedule for locations.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal review of previous day notes and comments. setting the day's events to come
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 225 | 675 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal review of meeting notes and calendar events for the upcoming week reviewed my peakers emails, reviewed notes from the weeks meeting, followed up with task list.,
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 1. Staffing for Future Sites: Resource Allocation: When exactly will resources be needed on-site for the new projects? Staffing Levels: Are there any gaps in staffing that need to be addressed? Hiring Plan: Was there any talk about hiring new staff for specific roles? 2. Demolition and Project Schedule: Demolition Timeline: Any changes to the timeline or progress updates on demolition? Overall Project Schedule: Are there any upcoming milestones or deadlines that need closer attention? Any potential delays Participants in the meeting Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 225 | 675 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Held a meeting for the pre-evaluation of RFP demolition at costa sur Reviewed the RFP and discussed adding additional scopes of work to capture all phases of work to be completed. Participants in the meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache BESS Construction Weekly led by Andres Concepcion DCMC. Update provided on Contract status, safety, RFI's, Submittal, temporary parking, warehouse, VE Structural Steel, access road. attendees DCMC Luis Duque CDM Smith - Gabriel Perez Sargent & Lundy - Robert Molner RGE - Jose Segarra Genera- Herminio Arroyo
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria VB Phase II - Weekly Construction Meeting led by Eduardo Rivera. Contract Status RFI's & Submitalls Pre-Cast Evaluation Site Demolition and pending scope items CDM Smith Gabriel Perez DCMC - Gilberto Sucre Sargent & Lundy - Wilfredo Sierra. ARG Ceres - Carlos Hernandez
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One to one meeting with Carlos Hernandez ARG Ceres to discuss one outstanding contractual item, and other outstanding items mainly the Pre-Cast Submittal.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Update correspondence reading, evaluation & response.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Reporting Update Bi-weekly Meeting for BESS & Peakers Program: DCMC _ Jean Peirre Menay, Rafael Calderon, Raissa Borges, Frances Vallejo, Abraham Velazquez, Gilberto Sucre, Paola Arroyo, Sheila Torres, Paul Browne. CDM Smith Carlos Palomares, Rafael Pabon
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting main topics: * Staffing Updates * ProCore Financial Management * Leadership & Team Dynamics * Technical Infrastructure * Quality Control & PM * Administrative & Equipment Management. Attendees: Frances Vallejo, Mark Merritt, Mike Merritt, Lauren Wells, Foster Veazey, Anneilia Holton, Ada Diaz, Barry Scanlon, Gilberto Sucre - All DCMC
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Trailer & Material Update with Frances Vallejo & Jean Peirre Menay DCMC need to complete bathrooms facilities from tanks and containment base.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L CDM Smith Review of latest IFC's Updates that continue to slip. New Strategy is required to force designer to catch up. CDM Smith - Gabriel Peres, Enrique Laya Sargent & Lundy - Robert Molner DCMC Gilberto Sucre
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP tracker updates and reviews.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Foster Veazey (Lemoine), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore review of Submittal configurations.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore financial items to outline our gaps and unanswered questions to send to the group.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore workflows, permission templates, and other directory items.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of PO Order flow from Raissa Borges (DCMC).
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items to outline our gaps and unanswered questions to send to the group
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on correspondences for Procore items to different users.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on reporting update for Raissa Borges (DCMC) monthly updates.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore items answering questions for directory.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Collaborated with Victor Torres from Genera PR to develop a plan for completing the Power Production and Fuels Consumption report, along with the power plant KPI reports covering fiscal years 2023 to 2025. Held a discussion with Eisha Mercader from DCMC to explore potential enhancements to the Genera Connect Timesheets platform aimed at increasing data capture for improved transparency. Additionally, participated in a meeting with Eisha Mercader (DCMC), Carlos Gonzalez, Keyla Sierra, and Pedro Procopio from Integrum to review and refine system requirements based on prior discussions, ensuring alignment with reporting and operational needs.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pickup and delivery Health, Safety and Offices equipment for Cambalache Site. Site inspection with Andres Concepcion (DCMC) about Health, Safety, Enviromental topics review.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continuing review the site condition includes the health, safety and environmental topics. Workshop to (ARG) employees (Sulayka Reyes, Ricardo Lopez and others) necessary to visit the Vega Baja Site.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Conference call with Ramon Reyes (GENERA) about Health and Safety Presentation. Conference with Javier Aviles (Portosan) Septic's Services. Conference call with Andres Concepcion (DCMC) about Health and Safety Topics send by Procore for RGE (Contractors).
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11 ¦ DR 4339 - Hurricane Maria - Attended PMO Coordination call via Teams to discuss project status, staffing update and Procore financial next steps. Participants: Gilberto Sucre and other DCMC participants.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended PMO Reporting call via Teams to discuss the June monthly report to Genera. The topics discussed were critical components, procurement, contract management, BESS, Peakers and Procore. Participants: Raissa Borges and other DCMC participants.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed the grant update email and accompanying documentation (Project Narrative and Statement of Project Objectives) shared by Jesús Cintrón (Genera). Assessed the materials for alignment with project scope, funding objectives, and federal compliance requirements.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. Contributed updates on assigned tasks, reviewed performance metrics, and participated in discussions aimed at streamlining reporting processes and enhancing cross-functional coordination. Collaborated with team members to identify action items and align on priorities for the upcoming reporting cycle. DCMC: Frances Vallejo, Gilberto Sucre, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Browne, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - Supported Genera’s Procurement Team in responding to additional RFIs related to RFPs 4899, 4898, and 4826. Coordinated with Jesús Cintrón, Fernando Ortiz (Genera) and Franklyn Colmenares (CDM Smith) to develop comprehensive responses, requested necessary supporting documentation, and consolidated all materials into a complete response package. Submitted the draft responses to the Procurement Team (Angelina Minier and Joel Pantojas Genera) for final review and approval.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Weekly Contract discussions with Rafael Calderón and Glorimel Torrado (DCMC) on Generation Fleet (BESS & Peaker projects) contracts. Discussed ongoing change orders, task orders, and contract amendments, and aligned on key issues related to scope, invoicing, and compliance. These meetings serve to ensure consistent coordination between legal, procurement, and project management teams and to support the timely and efficient execution of all contractual obligations tied to the generation portfolio.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet – RFP 231175 (BESS Installation at Yabucoa) - Reviewed and revised the Procurement Memorandum for the BESS Installation RFP. Incorporated feedback from the Evaluation Panel to ensure the narrative accurately reflected the evaluation process and scoring methodology. Conducted a final quality review to confirm completeness and compliance with documentation standards. Submitted the updated memorandum to Jesús Cintrón (Genera) for final approval as part of the procurement file supporting federal reimbursement.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - PMO meeting preparation - Updated legal and procurement update slides for the weekly PMO reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any legal or compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed and verified the completeness of the Scope of Work (Attachment B) for Generation Fleet RFPs 4899 and 4900. Coordinated with Mike Kuczynski (S&L), Gabriel Sepúlveda, and Franklyn Colmenares (CDM Smith) to confirm technical content accuracy. Ensured all required documentation was compiled and organized in accordance with approval requirements.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Assisted ARG meeting RFI list with Carlos Hernandez from ARG and DCMC participants Jean Menay, Eduardo Rivera and Jaime Pesquera and Gilberto Sucre. Prepared safety meeting for ARG staff.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Three-hour technical session reviewing the PREPA project presentation materials and Procore access process, as provided by Theresa Perez (DCMC). This workshop ensured proper implementation of Procore workflows to support project management and FEMA compliance requirements for DR4339 projects.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ Learning the proposal from Genera PR RFP No. 4900 Civil & Structure Works for 158 MW Battery Energy Storage System at Aguirre that Gilberto Sucre (DCMC) sent me.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 174 to 211. Among the topics read were bolting (installation, inspection, examination, among other topics), structural welding (requirements, procedures, quality assurance, execution, inspection and acceptance), anchor rod (materials, quality control, protection), shear studs connectors (welding procedure, storage and handling, method and examination, acceptance), post installed anchor concrete (delivery, storage, handling, adhesive anchors, concrete and masonry anchor, undercut, repair of failure)
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 212 to 219. Among the topics read were inspection of structural steel (testing, material examination, reports, certifications, welding examination).
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Assisted to Construction Weekly Meeting with some participants that are Franklyn Colmenares (CDM Smith), Jose Segarra (RG Engineering), Dean Ennes (Sargent & Lundy), and others. Among the topics discussed where the project is visited to locate the water pipes, it must be coordinated to identify the raw water lines and water pipes, RG Engineering, RG submittal #11 on the location of storage trailers, doubts regarding permits were clarified and documentation will be submitted.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Assisted to Construction Weekly Meeting with some participants that are from DCMC Eduardo Rivera, Gilberto Sucre, from CDM Smith Franklyn Colmenares, Gabriel Perez, and others. Among the topics discussed are the list of personnel will be provided today in the afternoon 7/1, deliver the schedule of value and project schedule, request for information for total of equipment and prices, demolition and other topics.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Site visit to the Peakers area with Rafael Barrera (Construction Manager, DCMC) Luis Echevarría (Safety, DCMC) and Carlos Bayron (QA/QC, DCMC) to review the demolition sequence and logistics plan presented by Abraham Velázquez (DCMC). The team also evaluated potential improvements in safety measures to ensure compliance with site standards and enhance worker protection. Additionally, the contractor’s office trailer was inspected and verified for removal, which is scheduled for next Thursday.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continued the site visit efforts at the Peakers area with Rafael Barrera (Construction Manager, DCMC), Luis Echevarría (Safety, DCMC), and Carlos Bayron (QA/QC, DCMC), focusing on the review of available documentation and site diagrams related to the demolition scope. The team evaluated layout drawings, utility disconnection plans, and access routes to validate alignment with the proposed demolition sequence. This review helped identify coordination points and reinforced planning efforts to ensure a safe and organized execution of upcoming activities.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Internal meeting with Carlos Dejesus discussing project Schedule for both Costa Sur BESS and Peaker's project. Continued with Carlos to a meeting with RGE Subcontractor Lead Project Manager Jose Segarra to discuss requirements of schedule for BESS project Costa Sur.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Internal meeting with DCMC Team Abraham Velazquez and Carlos Dejesus preparing Preliminary Schedule for demolition, construction and installation for Costa Sur Peaker's, preliminary run through of all project staging and sequencing to be provided to German Nunez (GENERA).
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 0119110 "Startup, Testing and Commissioning" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 075600 "FLUID-APPLIED MEMBRANE ROOFING, CONCRETE DECK" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Costa Sur Meeting to discuss the Construction Strategy for the Peakers project in the Costa Sur Site. In this meeting participate from DCMC Carlos Rodriguez, Abraham Velazquez, Rafael Barreras and Carlos De Jesus; From CDM Smith Carlos Palomares, Rafael Pabon and other team members. Also, In the meeting was discuss the demolition strategy and 3D drawings.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Visit the Peakers site with Safety (Luis Echevarria DCMC) and Carlos Byron QA/QC DCMC to discuss the demolition sequence and logistics presented by Abraham Velazquez DCMC. Possible areas for improvement in the safety area are also analyzed. Also, we verify the contractor's office trailer, which will be taken out of the site next Thursday.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued the site visit efforts at the Peakers area with Rafael Barrera (Construction Manager, DCMC), Luis Echevarría (Safety, DCMC), and Carlos Bayron (QA/QC, DCMC), focusing on the review of available documentation and site diagrams related to the demolition scope. The team evaluated layout drawings, utility disconnection plans, and access routes to validate alignment with the proposed demolition sequence. This review helped identify coordination points and reinforced planning efforts to ensure a safe and organized execution of upcoming activities.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos R. López Valle Llanes, and Luis A. Moctezuma (DCMC) to discuss project two week look ahead schedule and improve communication across the site team. Introduction call with new Aguirre Team Member Sunem Martinez (DCMC) who will be working with the Project Controls and Schedule.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 | 167 | 459.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre We are work in Development of a Safety Inspection Form for a Construction Project: To enhance workplace safety and ensure compliance with industry standards and regulatory requirements, a dedicated safety inspection form was developed for use across all phases of the construction project. The goal was to create a comprehensive yet user-friendly tool to systematically identify, document, and mitigate potential hazards on-site.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We are work in a Development of a Safety Toolbox Meeting Form for the BESS_Aguirre Project: As part of the BESS_Aguirre Project’s commitment to safety excellence and proactive hazard communication, a tailored Safety Toolbox Meeting Form was developed to standardize daily and weekly safety briefings across the site. Given the complexity and dynamic nature of battery energy storage system (BESS) construction, the toolbox meetings serve as a critical platform for reinforcing site-specific risks, procedures, and lessons learned. 1. Project-Specific Requirements 2. Objective and Scope 3. Form Structure and Content 4. Format and Accessibility 5. Review and Validation 6. Implementation
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the Issue bid drawings documents, TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC) Spec. No.: G-3400 Revision: A; For Bid Project No. A15240, June 20th, 2025to identify potential and possible change orders, as well as potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects to be integrated into the PROCORE platform. A call was held with Javier Ignacio from Portosan to coordinate equipment delivery to the Aguirre Site.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting Coordination and Agenda preparation work with the Construction Weekly Progress Meeting with RG Engineering, the General Work Contractor, José Segarra (RGE), José Robles (RGE), Xiomara Pérez (RGE), Vernaded Ortíz (RGE), Gilberto Sucre, Carlos R. López Vallellanes, Luis Moctezuma, Jean Pier Menay (DCMC), Gabriel Pérez (CDM Smith, Frankling Colmenares(CSA). Categories of the Agenda are as follows: DCMC Construction Management Team Introduction, RG Engineering Construction Team Introduction, Scope of Work Clarifications, Directory of Responsibilities Clarifications, Safety Topics and Plan from RG Engineering, Master Project Schedule, Schedule of Values, RG Engineering Point of Contact during the construction process, Schedule a Initial Genera PR Safety Workshop, and Open Items Discussion. The meeting is scheduled for July 3, 2025, at 11:00 am.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Gilberto Sucre and Jean-Pierre Menay (DCMC) to discuss the office trailer consumables and office equipment supplies pending order and delivery to the DCMC's Aguirre Office Trailer Compound. A list will be shared by Frances Vallejo (DCMC) to follow up on the procurement process and delivery.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Aguirre BESS Project - Attended coordination session with Carlos López and Luis Moctezuma (DCMC) to review the two-week look-ahead schedule for ongoing and upcoming activities. Discussion also addressed strategies to streamline communication and task tracking among the site management team.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Created an agenda to discuss actions items related to the Cambalache Facility and GeneraPR responsibilities, Met with Herminio Arroyo (GeneraPR) to discuss regarding Warehouse activitiesm submittals and pending actions in the project that needed his feedback.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated on-site to receive from Jean Pierre Menay (DCMC) the delivery for office trailers supply that was recently purchased by Ada Diaz (DCMC). Received materials and organized them in the office trailer.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated and followed up with several Cambalache pre-construction items. (1) Email to Gabriel Perez (CDM Smith) escalating pending activities from GeneraPR. (2) Developed correspondence and provided field data to designer (Mike Kuczynski - Sargent and Lundy) to incorporate it to design.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated and completed the Construction weekly meeting report or meeting minutes to officially document the discussion in Procore platform to capture all covered topics in the meeting.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting for (Sargent & Lundy / CDM Smith Weekly BESS Drawings Meeting) with Gabriel Perez (CDM Smith), Gilberto Sucre and Jose Lopez (DCMC), Mike Kuczynski (Sargent and Lundy) to discuss design development progress for the BESS program.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted the Construction Weekly meeting #7 to discuss ongoing project status and action items with project team (RG Engineering - Jose Segarra) (Sargent and Lundy - Robert Molner, Dean Ennes) (DCMC Partners - Gilberto Sucre, Luis Damudt) (CDMSmith - Gabriel Perez) and (GeneraPR - Herminio Arroyo)
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Completed and generated Construction Weekly Meeting agenda document in Procore to capture the outstanding discussion and acction items to be covered with the project team.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Carirma of Homeca send email with the final change order for Vega Baja site. Reviewing the change order send by Homeca and also enter the minutes notes taken for ARG/CERES construction meeting.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting for PMO Reporting - Organizer Frances Vallejo of DCMC - Meeting was provide status report for BESS, Peakers, Critical Components, Procurement Status, Procore status, Budget & Scheduling, and Community Outreach Liaison.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project weekly meeting to review project status. Homeca Carirma Sanchez; DCMC Jaime Pesquera, Gilberto Soto, and Eduardo Rivera, CDM Smith Nelson Soler, Enrique Laya, Gabriel Perez, and Manuely Concepcion. Meeting to discuss final remaining 2 items of punch list, As-Built drawing was review and sent back to be resubmit, Homeca to provide final change order and project closing.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing the Change Orders sent by Carirma Sanchez of Homeca, the following CO has been reviewed and sent to Jose Lopez of DCMC my comments because he was the Site Manager of Vega Baja during period of April-May 2025.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working in reviewing comments of change order send by Jose Lopez of DCMC in regard of Homeca. Reviewing specification send to ARG related to Notification of Award and what are the requirements that they can provide during this notification.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project construction weekly meeting Phase II. ARFG/CERES Carlos Hernandez and Ida Ramirez; DCMC Jaime Pesquera, Gilberto Soto, Gilberto Sucre, Silvia Franco, Raissa Borges and Eduardo Rivera, CDM Smith Nelson Soler, and Gabriel Perez Sepulveda, CSA Franklyn Colmenares, S&L Robert Molner - Meeting to provide status for second phase construction of Vega Baja BESS project, coordinate with ARG documents to be submitted as part for the new construction and ARG provide status of RFI's.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Homeca project closing for Vega Baja Site. Preparing agenda for Homeca construction meeting. Preparing agenda for ARG/CERES construction meeting. Reviewing email in regard of Homeca project closing.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting for Vega Baja Final Specification - Meeting organizer Nelson Soler of CDM Smith, S&L Mike Kucynski and Wilfredo Sierra, and DCMC Eduardo Rivera - Meeting to discuss with S&L to provide the updated project specification for Vega Baja site, S&L will send the specification to be incorporated in Procore.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting for review and analysis of specific cases related to Sole Source procurement processes with DCMC Cynthia Ortiz, and D'Alexzander Gonzalez and GENERA-PR Sullinette Perez Development of a technical note and evaluation of justifications for identified Sole Source cases, including supporting documentation, compliance with regulatory criteria, and recommendations for each case. Related to PW-10710 Equipment & Material
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Complete the Bi-Weekly Report Template in preparation for the PMO reporting meeting. This task involved compiling updates on key project activities, identifying recent accomplishments and ongoing challenges, and summarizing financial and operational status. The finalized report supports leadership oversight and ensures consistent tracking of project milestones and deliverables. Related to PW-10710 Material & Equipment
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC and Lemoine: Abraham Velazquez, Frances Vallejo, Gilberto Sucre, Lauren Wells, Rafael Calderon, Pedro Cabrera, Sheila Torres, Raissa Borges, Paola Arroyo, Paul Browne and (CDM Smith), Carlos Palomares, and Franklyn Colmenares, Meeting with DCMC to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. Related to PW-10710 Equipment & Material
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - ending Invoice Verification – Contract 104413 (Cortes Industrial Organization Inc.) A pending invoice related to the supplier Cortes Industrial Organization Inc. under Contract 104413. However, upon reviewing the Asset Suite system, I did not find any record of this invoice being entered. Related to PW-10710 Material & Equipment
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Compiled and validated the equipment inventory for trailers 1 and 2 at the Cambalache BESS site (PW9510). The task involved reviewing field data, organizing item descriptions, quantities, and serial numbers in an Excel format, and ensuring data consistency with project documentation. Final inventory was submitted to Jean Pierre Menay (DCMC) for internal tracking and coordination. The resulting file will support future equipment verification and asset control for site operations.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails and submittals RGE-0002.0 Temporary Mechanical Connection to Existing Transformer T1from the RGE to Sargent and Lundy.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Site walkthrough to corroborate measurements of raw water pipes with Carlos A. Nieves and Miguel A. Mendez (Sargent & Lundy)
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS - RFC Meeting RGE Cambalache RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Discussion Drawings Issues Meeting with Andres Concepcion, Luis O. Damudt, Jorge A. Mercado, Carlos De Jesus, Luis Duque DCMC, Alberto Borelli, Jose Segarra, Angel Cruz, Harry Velazques from RGE, Herminio Arroyo Genera PR.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly Vega Baja BESS Phase II - Construction Meeting with Carlos Hernandez from (ARG/CERES,) Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith), and went over Project Documents Overview and analyzing documents status in the Procore platform and all the punch list items that are open and the demobilization an the items that we need to close from them in order to close their paper work and punch list.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly construction meeting with Homeca Recyclers Carirma Sanchez, Eduardo Ramos, Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith), and went over Project Documents Overview and analyzing documents status in the Procore platform and all the punch list items that are open and the demobilization an the items that we need to close from them in order to close their paper work and punch list.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Assisted weekly meeting punch list with Homeca Carirma Sanchez and DCMC participants Jean Menay, Eduardo Rivera and Jaime Pesquera.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 | 164 | 164 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Beta Electric, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 | 164 | 164 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW9510 Pre-Intervention Review RFI - Working with Black & Veatch Contract #217733_2024-G00207 and TO#7_Invoice# 000004_ May 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 164 | 164 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- DR 4339 PMO Reporting Meeting - DCMC PMO staff meeting to discuss specific need of reporting based on project execution development per area. Working on live tracker presentation template and review updated status from BESS and Peakers projects. Participants Frances Vallejo, Raissa Borges, Glorimel Torrado, Gilberto Sucre, Sheila Torres, Abraham Velazquez, Eduardo Rivera and Paul Browne.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3.5 | 164 | 574 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Compliance Review CDM Smith Invoice #293410-16 for TO#1 May 2025. Preparing email communication for Genera and CDM about invoice evaluation on system. Also identifying common mistakes that led to Invoice rejections. Reviewing each invoice line item and requesting information based on allowed SOW under contract that include but are not limited to: Plant name, Project Name, PW#, Specific A&E service, component name, meeting purpose & participants and requesting links to supporting documentation for compliance validation. Reviewing documents: Invoice Essentials One Pager to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 | 164 | 246 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- DR 4339_PW11855 Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-03 May 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria Conducting cycle counts at the Palo Seco warehouse in accordance with the Asset Suite system. Today we worked with locations CB027-CB036 using Cycle Count List #1260.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AB021 to AB026 and GA006
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB021 to AB026 and GA006
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AB021 to AB026 and GA006
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB021 to AB026 and GA006
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB021 to AB026 and GA006
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AB 01 050 000 to AB 01 082 000.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AB 01 050 000 to AB 01 082 000.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AB 01 050 000 to AB 01 082 000.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BF 075 to BF 100 at the Aguirre warehouse to initiate the cycle counts.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BF 075 to BF 100 LIST #1249, AND RECOUNT LIST # 1250
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Aguirre. Hurricane Maria: Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BF 075 TO BF 100 LIST # 1249
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BF 075 TO BF 100
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria At the Palo Seco warehouse, preparing the lists for locations CB027-CB036 to start the cycle counts.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1274 from locations CB027-CB036 for a total of 787 units.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the recently issued Specifications Book for Costa Sur BESS project; reviewed and overview the contents and extent of the specifications for project works.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /Aguire BESS Incorporate New Users/GEN 01 BESS & Peakers Project S&L Data Review for processing_stored & archived in an organized & controlled manner/Review of daily incoming documents for processing
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 151 | 302 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Cambalache Weekly Project Meeting hosted by Andres Concepcion (DCMC) and joined by the contractor's team (RGE) with Jose Segarra and Xiomara Robles, also from the design team Deanne Ennes (S&L), Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Roseanne Perez (Genera) and other project staff members. Discussed the current status of main submittals and plans from contractors such as permiting open items, safety related plans, mobilization execution, design inquiries and more.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Paul Browne (DCMC) to discuss the current efforts on managing Genera's Warehouses Inventory on San Juan, Palo Seco, Costa Sur and Aguire Power Plants. Looking to implement the tracking, working efforts and documentation regarding Genera's In-Site Inventories through the Procore Platform.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the implementation of Genera's Warehouse Inventories inside Power Plants to provide the proper tools and features of the Procore platform to track, upload and update information regarding the inventories and reporting for warehouses at Palo Seco, San Juan and Costa Sur.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Continuation for the full setup of Critical Components Tracking and Working process to be incorporated into the Critical Components project in Procore. Setup of power plants locations and the contrast with current construction projects submittal logs to identify potential critical components to be tracked inside project modules.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Issued for Bid Specifications Book for the Costa Sur Power Plant for BESS works; review engineering structure of suggest methods and the review of administrative specifications for contractor obligations on documentation and regulations compliance.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 | 149 | 74.5 | 149 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 - Working session with Rafael Calderón DCMC to review pending items from Siemens to submit RFI and actions pending on RGE meeting. I prepared the RFI email with clarification needed for deliverables workpackages.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 149 | 74.5 | 149 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 - PMO Reporting meeting - Recurrent meeting to discuss project management for Bess and Peakers. In this meeting participates from DCMC Frances Vallejo, Rafael Calderón, Glorimel Torrado, Paul Brown, Eduardo Rivera Jordán, Raissa Borges, and others. In this meeting we discuss information and review updates for both projects, identify risks and red flags.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 149 | 74.5 | 149 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with Sheila Torres (DCMC) and Rafael Calderón (DCMC) to discuss pending action items on Tesla contract and RGE contract. We also provide updates on change orders from Siemens, Tesla, and RGE, and request updates on FOMB process and on the amend and restate.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 PMO Reporting meeting. The DCMC team was present at this meeting: Rafael Calderon, Raissa Borges Almodóvar, Sheila Torres-Sterling, Rafael Calderon and Frances Vallejo. At the meeting, details related to the updates of the project were discussed, new information was offered, and doubts were answered.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Create a report that includes the community engagement efforts with the information of the initiating early outreach with the municipalities of Costa Sur, Aguirre, and Yabucoa by sharing project information in advance. The report explains the collaboration with the Association of Centers for the Care and Development of Children to repeat summer camp activities in Vega Baja and Arecibo and the project website genera-pr.com/BESS_Peakers updates and corrections were completed. The report includes the ongoing neighborhood meetings are being maintained, and there are plans to resume direct engagement with municipalities to strengthen relationships and enhance communication.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Coordinate with the Genera PR team, Jorge Bracero, the new community meetings in Arecibo, Aguirre, Costa Sur and Yabucoa. These tasks included coordinating the logistics of the dates on which we should be impacting the community as well as reviewing the steps to follow for this type of event.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339¦ Work on the designing the operational plan for implementing community webinars, with the goal of expanding public participation and making community meetings more accessible to a broader audience. These tasks included researching the topic, creating a work plan, coordinating with the Genera team—specifically Jorge Bracero—for credentials, integrating a timeline, conducting a webinar test to understand its functionality, among other activities.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Update information related to PMO Reporting. Some project-related data was revised to improve the clarity and understanding of the information provided.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Edit with the Genera PR team, Jorge Bracero, the report includes a summary of the community meetings are still being held, and there are plans to resume direct engagement with municipalities in order to strengthen relationships and improve communication. Additionally, this task includes the updates and corrections to the project website—genera-pr.com/BESS_Peakers—have been completed.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with the Genera PR Jorge Bracero team to update and work on the Community Outreach Program with the purpose of organizing all activities and community meetings related to the efforts of the BESS and Peakers project through other sectors of the island.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 134 | 134 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures ,Schedule Plan, Project Schedule Development to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 134 | 167.5 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting between Jose M. Lopez, Luis A. Moctezuma (DCMC) and myself to discuss project two week look ahead schedule and improve communication across the site team. Introduction call with new Aguirre Team Member Sunem Martinez (DCMC) who will be working with the Project Controls and Schedule.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 | 134 | 368.5 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 25 pages.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 38 pages.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria Continued the site visit efforts at the Peaker's area with Rafael Barrera (Construction Manager, DCMC), Luis Echevarría (Safety, DCMC), and Carlos Bayron (QA/QC, DCMC), focusing on the review of available documentation and site diagrams related to the demolition scope. The team evaluated layout drawings, utility disconnection plans, and access routes to validate alignment with the proposed demolition sequence. This review helped identify coordination points and reinforced planning efforts to ensure a safe and organized execution of upcoming activities.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continue reviewing Issue for Bid (Drawings) to configure submittals settings, Intro RFIs tools permissions, schedule tools, included in QA/QC concrete information on specific strength and rebar spacing for construction in order to compare issue for bid and issue for construction. Site visit to the Peakers area with Rafael Barrera (Construction Manager, DCMC) Luis Echevarría (Safety, DCMC) and Carlos Bayron (QA/QC, DCMC) to review the demolition sequence and logistics plan presented by Abraham Velázquez (DCMC). The team also evaluated potential improvements in safety measures to ensure compliance with site standards and enhance worker protection. Additionally, the contractor’s office trailer was inspected and verified for removal, which is scheduled for next Thursday.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 134 | 201 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on Teams meeting considering minute report activities format for schedule submittal, specification section 013216 list related to construction guides and resources data formats, schedule of values of schedule for employee (DCMC) Carlos Rodriguez, Rafael Barrera, (RG Engineering) employee Jose Segarra, (CDM Smith) employee Carlos Palomares, (Sargent and Lundy) employee Dean Ennes.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- worked on TEAMS meeting related to Cambalache BESS - Construction Weekly with pending submittals and news on items out of scope of works with DCMC employees Andres Concepcion, Luis Damudt, Luis Duque, employees of RGE Jose Segarra, Xiomara Pérez Álvarez, CDM Smith employee Gabriel Perez, employees of Sargent and Lundy Dean Ennes due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 134 | 201 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur - worked on teams meeting considering specific strategy of master schedule, simulation of turbine project, presentation of 3D schematic project, strategy communications of Peakers and logical construction for employee (DCMC) Carlos Rodriguez, Rafael Barrera, Genera employee Rafael Pabon, German Nuñez, CDM Smith employee Carlos Palomares.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 134 | 469 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur - worked on project manager master schedule considering turbine number one and two distributed into a list of activities for create a mechanical duration of time work, create impact on site utilities of construction pipping, electrical works of Peakers and logical construction for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 134 | 67 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur - worked on draft procurement schedule considering demolitions works considering master schedule, simulation of Siemens Turbine equipment of Peakers and logical construction for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 134 | 268 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures ,Schedule Plan, Sequencing Plan and Preliminary Schedule and Baseline Schedule to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures ,Schedule Plan, SOrganization and Formatting of Lemoine’s Schedules, Milestones and Base lining the Schedule plan to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 134 | 134 | 134 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Construction Weekly meeting with Andres Concepcion (DCMC), Robert Molner (Sargent and Lundy) and Jose Segarra (RGE) for the 4339_9510 BESS_Cambalache project. Discussed work status and the tasks to be completed.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 122 | 91.5 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Gilberto Sucre, Paul Brown, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado, Lauren Wells. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams weekly meeting to discuss Vega Baja BESS Phase II project construction activities updates. Attendees DCMC: Eduardo Rivera, Sylvia Franco, Gilberto Sucre, others RGE: Carlos Hernandez, others
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 122 | 152.5 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Compiling and analizing BESS & Peakers projects updates to enhance data visualization, improve accessibility, and facilitate clearer interpretation of progress and risks in the monthly report.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 122 | 427 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Incorporating BESS and Peakers updates from the last PMO meeting to sharpen data visuals and reporting clarity and to provide a more transparent view of project progress and risks.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams weekly meeting to discuss Cambalache BESS project construction activities updates. Attendees DCMC: Andres Concepcion, Luis Damudt, Gilberto Sucre, others S&L: Dean Ennes RGE: Jose Segarra, Xiomara Perez, others
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams workshop section with Cynthia Ortiz (DCMC) to continue developing Procurement process flowchart.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue compiling BESS & Peakers projects updates to enhance data visualization, improve accessibility, and facilitate clearer interpretation of progress and risks in the monthly report.
2025-07-01 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 83.3 | 0.7 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pickup and delivery Health, Safety and Offices equipment for Cambalache Site.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks for showing missing documents and ability for system to send reminder emails/alerts.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 held an internal team meeting to discuss strategy and project managers roles and responsibilities. Gilberto Sucre DCMC Frances Vallejo Rosich DCMC
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 held a meeting to discuss further the RFP demolition for costa sur. reviewed the scope of work discussed impact if temp. generator is installed. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 team meeting to review sequencing plan for costa sur demolition thru civil work. Attended the meeting Rafael Barrera DCMC Carlos Bayron DCMC Luis Echevarria DCMC
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Bess Peaker meeting discussed procurement status of equipment for all sites. attended meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Gilberto Sucre DCMC
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Worked on * Vega Baja - Homeca Change Final Change Order evaluation for Genera Execution. * Review of DCMC Quality Assurance Plan * Abraham Velazquez Performance
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Procurement Status Meeting led by Cynthia Ortiz - Genera Main Topic - FOMB Package preparation for Vega Baja, Costa Sur & Aguirre, Pending Tariffs clause for Vega Baja, and Contract Template used for the last two. Franklyn Colmenares - CSA Group & Sheila Torres - DCMC coordinating these efforts
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Weekly Project Meeting Update & Coordination Design Meeting mainly reviewing extensive RFI's from Tesla. Participants: CDM Smith Gabriel Perez CSA Group Franklyn Colmenares Sargent & Lundy - Mike Kuczynski DCMC - Gilberto Sucre.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Internal meeting with Abraham Velazquez, Frances Vallejo & Gilberto Sucre -DCMC to discuss upcoming management change in Peakers Leadership and Genera's expectations for the Sr. Construction Manager to lead.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.25 | 225 | 281.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Quality Assurance Internal Policy Development SOP, worked with Andres Concepcion and Luis Duque DCMC Reviewed draft plan vs. Lemoine's Manual and provided recommendations to complete manual. Reviewed RGE Quality Plan Submission and response " Revise & Resubmit"
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Peakers Budget Monthly Review Discussion with Carlos Palomares - CDM Smith, highlighted DCMC transfer to PMO Cost.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore + Old Documents update with Lauren Wells - DCMC
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Peakers Correspondence review and response of daily e-mails. Update Agenda for following day.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Prepared for virtual P3 Approval Process Improvement session by updating the Miro board with current process mapping elements and reviewing prior meeting outputs. Developed meeting agenda and talking points to guide the team through Step 2 of the 8-Step Problem Solving process. Verified participant availability and ensured technical materials were in place for smooth facilitation.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Completed follow-up from virtual P3 Approval team meeting. Documented updated process steps on the Miro board and captured team feedback and action items. Initiated Plus/Delta feedback request in Teams and coordinated scheduling for the next session based on team availability. Noted recommendation to include Joel and Romano (Genera) in future sessions for process accuracy and alignment.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Training Specialist | Ormonde, Heather | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Facilitated a virtual session with the P3 Approval Process Improvement team to continue Step 2 of the 8-Step Problem Solving process. Assisted team members with navigating the Miro board and guided discussion through the steps involved in identifying the contract winner, including proposal review, scoring, technical evaluation, and contract negotiations. Clarified sequence and ownership of tasks such as the Notice of Intent and Award Memo, and the role of procurement in submitting documents to legal and regulatory. Identified gaps in documentation and recommended including Joel and Romano (Genera) in future sessions. Scheduled follow-up meeting and gathered feedback on meeting effectiveness. Participants include Axel Velez (Genera), Christian Torres (Genera), Christina Morera (Genera), Joaquin Quinoy (Genera), Jorge Sanchez (Genera), and Kevin Futch (Genera). Focus of prep included finalizing the SIPOC and initiating the Process Map development.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore financial items.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for permissions.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore task tool for tracking documents.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting for users volume and tools being utilized.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for Permissions.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for 360 reporting.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore SOP's for final markups before publishing.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore settings for Specification tool.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting for Siemens RFI and Submittals ensuring accurate tracking, and documentation for project stakeholders.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial task items.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC)meeting with Gilberto Sucre (DCMC) to discuss Procore topics.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore questions.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - In response to a request from Jan Rodriguez of Genera PR, prepared the master Power Production and Fuels Consumption report along with placeholders for the individual power plant reports to support the upcoming submission deadline of July 7, 2025. Initiated review of preliminary data submissions from the power plants to verify consistency in measurement standards and unit alignment, ensuring data integrity across all reporting components.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review the emails about Genera projects. Review the inventory of all Genera sites offices trailers. Review the purchasing process about materials needs in offices trailers.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Conference call with Javier Avilés (Portosan) regarding the septic tank installation for Aguirre. Provided EHS workshop to Edgar Rodriguez (Portosan) focused on Genera’s Environmental, Health, and Safety standards. Held a meeting with Francisco Mari (Genera) to discuss security topics related to the Aguirre Genera project.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Ramon Quiñones (GENERA) to discuss Health and Safety rules for the Aguirre Genera projects. Phone call with Gabriel Morales (DCMC) to address issues related to office trailers in Yabucoa. Meeting with Luis Moctezuma (DCMC) focusing on Health and Safety rules for the Aguirre Genera projects.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Abraham Velazquez (DCMC) to discuss Peaker's project overview and delays.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with client, Jesus Cintron (Genera PR) via call to discuss Peaker's role issue and leadership change.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting with Raissa Borges (DCMC) to discuss monthly report for Genera and one pager status per site.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 184 | 230 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Paola Arroyo (DCMC) to discuss webinars for community engagement, Check in BESS meeting feedback from Genera management and next steps regarding site visits.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Peakers - Diesel Generator DS - Reviewed and reformatted Attachment B – Proposal Data Form to ensure consistency with the RFP's SOW and accuracy of all referenced items. Verified alignment with the overall solicitation package and submitted the revised document to Rafa Pabón (CDM Smith) for review and confirmation.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Held a post-RFP meeting with Franklyn Colmenares (CDM Smith) to discuss the Generation Fleet 234MW BESS Installation RFP. Reviewed required revisions to the RFP and its accompanying attachments. Uploaded all relevant documents to a shared folder to facilitate collaborative editing and ensure timely updates.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafael Pabon, Alejandro Laya, Carlos Palomares (CDM Smith) Axel Velez (Genera). Discussed feedback and updates received from the Genera procurement team.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Peakers - Diesel Generator DS - Reviewed and reformatted Attachment A – Proposal Data Sheet to ensure consistency with the RFP requirements and accuracy of all referenced items. Verified alignment with the overall solicitation package and submitted the revised document to Rafa Pabón (CDM Smith) for review and confirmation.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Peakers - Diesel Generator DS - Reviewed and reformatted Attachment C – Proposal Pricing Sheet to ensure consistency with the RFP's SOW and accuracy of all referenced items. Verified alignment with the overall solicitation package and submitted the revised document to Rafa Pabón (CDM Smith) for review and confirmation.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Met with Victor Torres and Josue Sánchez from Genera PR to assess the current status of reporting efforts and to outline a plan for developing the KPI reports. The discussion focused on identifying required data backfilling activities to ensure completeness and accuracy of the reports prior to their submission to Vladimir Scutt from Genera PR.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Provided safety workshop to ARG visit Andres Ortiz Rodríguez, Ricardo López and prepared meeting for tomorrow’s visit. Had a conversation with Carlos Hernandez from ARG requesting safety plan for next phase will provide and reviewed during the day.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ reviewing documents dated June 22, 2025 at 4:57 pm with a content of 17 pages, called, Generation Fleet Storage Projects BESS Facility GWC Specification Appendix 2 – Reference Drawings
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/Aguirre - Revised GAs, Megapack Foundation Detail, Duct Bank Detail/reviewing documents dated June 22, 2025 with a content of 106 pages, called, Generation Fleet Storage Projects BESS Facility GWC Specification Appendix 1 – Design Drawings
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ reviewing documents dated June 22, 2025 at 9:03 PM with a content of 81 pages, called, Generation Fleet Storage Projects BESS Facility GWC Specification Appendix 4 – Fire Protection Specification.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ I was responding to and sending emails to Carolyn Baez (DCMC), Jose Lopez (DCMC), and Frances Vallejo (DCMC). Reviewing documents dated June 22, 2025 at 9:43 PM call. Genera PR LLC Generation Fleet Storage Projects BESS Facility GWC Specification Proposal Pricing Pages
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 252 to 292. In the reading we read about steel floor decking (design specifications, shop detail drawings, fabrication, delivery, handling, storage, installation) metal grading stairs (coordination, pre-installation conference, quality, project/site conditions, performance requirements, acceptable manufacturers, fabrication, finishes, protection), fluid-applied membrane roof (roofing preinstallation, certifications, inspections, quality, delivery, storage, handling, warranty, manufacturers, base sheet materials, auxiliary roofing materials, concrete deck preparation), flashing and sheet metal (acceptable materials, low slope roof) , joint sealant (exterior and interior).
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 220 to 251. Among the topics read were gallery work fabrication (inspection, test,3D models files, measurement, material requirements, shop drawings), gallery work erection (unloading, handling, storage, preparation prior start, tolerances, supports and bracings, painting).
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Call meeting with Andres Concepción (DCMC) to clarify doubts about the project and important points of it. We talked about the personal protect equipment, safety shoe specifications, Genera ID, I should request Twic Card, and others topics.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Conducted a safety-focused review of the Transportation and Storage Guidelines for the Tesla Megapack batteries, with emphasis on identifying potential hazards during handling, transit, and on-site storage. The evaluation included safety requirements related to temperature control, battery module stability, packaging integrity, and procedures to prevent tipping, short circuits, or fire risks. The objective was to ensure that all transportation and staging activities align with Genera's HSE protocols and regulatory safety standards for lithium-ion battery systems.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Coordination efforts were carried out with Costa Sur plant personnel (Luis Millan, Ramon Quiñones, Osvaldo De Jesus and Luis F. Torres) to support the scheduled removal of the RG Engineering office trailer. Discussions included site access, required safety measures, equipment mobilization, and verification of removal logistics. Ensured alignment with Genera’s protocols and plant operations to avoid disruptions and maintain safety compliance during the activity.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal; reviewing Request for proposal examining requirements for column stiffener plates, trolley beams, and the girt system. Stiffener plates are shipped loose and require field welding, which will require further coordination. Precision alignment requirements for trolley beam flanges to ensure smooth trolley travel at splices. Describes attention to corner squareness and dimensional tolerances around entrances.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal; conducted a detailed examination of Section 3 of the Costa Sur project specifications, with a particular focus on caulking materials. I carefully reviewed the stipulation that no coating should be applied over Thiokol or silicone-based sealants and confirmed that other caulking types must be coated using materials consistent with adjacent surfaces. Coating requirements, specifically reviewing the structure and purpose of Table 304-1. Cross-referenced chart to help align field elements with their appropriate coating systems and reviewed accompanying notes to understand intended applications. Required coating system data sheets referenced in Section 304.2, will be reviewed once field work has commenced.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 081113 "Door Requirements" and section 085113 "Aluminum Windows" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 076000 "FLASHING AND SHEET METAL" and section 079200 "JOINT SEALANTS" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Site visit to the Peakers area with Rafael Barrera (Construction Manager, DCMC) Luis Echevarría (Safety, DCMC) and Carlos Bayron (QA/QC, DCMC) to review the demolition sequence and logistics plan presented by Abraham Velázquez (DCMC). The team also evaluated potential improvements in safety measures to ensure compliance with site standards and enhance worker protection. Additionally, the contractor’s office trailer was inspected and verified for removal, which is scheduled for next Thursday.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- Worked on data report considering quality specifications, testing procedure and safety preliminary requirements documents related to a preconstruction list for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I am currently working on creating and facilitating various safety toolbox meetings to support and guide the contractors operating at the Aguirre Power Plant. These meetings are designed to address specific safety topics relevant to ongoing site activities, reinforce best practices, and ensure compliance with established safety protocols. The goal is to enhance awareness, reduce risks, and promote a culture of safety among all personnel on site. This is the Safety Toolbox Meeting I am currently working: 1. Unsafe Acts and Conditions. 2. The Importance of Defining the Work Area. 3. Prevention of Unsafe Acts.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria on this day, we arrived at the Aguirre Power Plant to receive and inspect the delivery of the sanitary tank designated for the bathroom facilities at the trailer office. The tank was delivered as scheduled and brought to the designated location near the trailer. Upon arrival, the unit was checked for any visible damage and to ensure it met the specifications outlined in the project requirements. Coordination was carried out with the site personnel to confirm the correct placement and installation timeline. The delivery and initial inspection were completed without incident.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT - Participated in a phone call with Basilio Ramos (Sunset Contractors) to discuss the possibility of performed a Job site visit to the Vega Baja Site to Go over any question and or scope of work clarifications for the demolition phase II. The meeting should include an Overview of the Scope of work to ensure that all project participants have a clear understanding of the expectations and requirements, as well as their role in the project’s execution. The Attendees scheduled for this meeting are Gilberto Sucre, Eduardo Rivera, Gilberto Soto (DCMC), and Nelson Soler (CDM Smith).
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Aguirre BESS Project - Engaged in follow-up calls with RG Engineering’s Project Manager, José Segarra, to clarify specific contract deliverables and evaluate current performance against schedule. Joined joint session with Sargent & Lundy, DCMC, and CDM Smith to discuss the Phase II comment log and identify missing structural specifications in the current design set.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Walk through the Aguirre Complex to identify possible locations for the project sign installation. The information was requested by Gabriel Pérez (CDM Smith) and Gilberto Sucre (DCMC). Various pictures were taken and should be discussed with the Genera-PR Plan Manager, Alexis Cruz.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Gilberto Sucre and Luis Duque (DCMC) to discuss (1) The DCMC Quality Assurance plan standard draft and (2) the Cambalache project quality control plan to be evaluated and responded to contractor (RG Engineering)
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued Quality Control submittal documents review and generated observations and comments to be provided to the general contractor (RG Engineering) for resubmission of the plan.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Evaluated and tracked Procore pending submittals and RFI and followed up with pending actions to complete its review and response. Reviewed submittal content to ensure al responsible have necessary information.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Sylvia Franco (DCMC) for Cambalache project alignment and onboarding. Discussed project history, documents and action items moving forward.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated various management tasks of the project. (1) Coordinated Quality Plan review meeting with Gilberto Sucre and Luis Duque (DCMC). (2) Generated correspondence and email to (Gilberto Sucre) on items to be clarified regarding submittal process and responses from designer. (3) Phone call with Jose Segarra (RG Engineering) to catch-up on pending project actions to be solved during the day.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Contact Jose Lopez and Jean Menay of Homeca to coordinate the demolition phase 2 contractor to provide the names of the attendee for the site visit and provide the safety workshop. Reviewing the comments provide to As Built drawing still pending Homeca respond. Working with the site manager weekly report to provide status of Vega Baja site project. Send email to Jean Menay and Gilberto Soto of DCMC to review and provide comments for ARG Contractor Safety Plan and Safety Credential of Maria Reyes of ARG. Reviewing updated specification sent by Wilfredo Sierra of S&L related to Vega Baja site.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing email related to Vega Baja site. Call Jose Lopez of DCMC to discuss on site meeting in person for 7/7 to discuss the Phase II Demolition scope of work to clarify any doubts regarding the task. Send email to Gilberto Sucre of DCMC to confirm the Tesla estimated equipment cost for DCMC to provide information of RFI ARG-R005. Phone call with Gilberto Sucre of DCMC - we discuss that CO of Homeca will be provide a CO evaluation and recomendación to Genera for them to decide in regard of CO evaluation, also discuss to hold by tomorrow the response to RFI ARG-R005 to see if Tesla provide an equipment breakdown, discuss also the site visit of a contractor to review site for proposal of Phase 2 demolition and to coordinate with Jaime Pesquera to take measure of existing MPT temporary relocation.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing the specification send by Wilfredo Sierra of S&L as part of yesterday meeting they a total 79 specification to be review. Send by email to Jaime Pesquera and Luis Roman of DCMC - Jaime Pesquera was requested to review the specification and Luis Roman to see if he can upload on Procore all specification documents file. Send an email to Nelson Soler of CDM Smith with the most updated CES plan drawing IFC sent by Robert Molner of S&L.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Package Preparation – ER-1 Cost Share Program The required package was prepared for submission as part of the ER-1 Cost Share Program (CDBG-DR – Housing), including the completion of plant-specific forms in accordance with the guidelines established in the Federal Register. The package includes the requested documentation and a description of the long-term operation and maintenance (O&M) plan for the improvements funded with CDBG-DR resources.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Continue Package Preparation – ER-1 Cost Share Program The required package was prepared for submission as part of the ER-1 Cost Share Program (CDBG-DR – Housing), including the completion of plant-specific forms in accordance with the guidelines established in the Federal Register. The package includes the requested documentation and a description of the long-term operation and maintenance (O&M) plan for the improvements funded with CDBG-DR resources.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed inventory discrepancies related to equipment counts for Office Trailers 1 and 2 at the Cambalache BESS site (PW9510). Cross-checked on-site logs, previous submittals, and inventory spreadsheets to identify and reconcile inconsistencies in quantities and item descriptions. Updated master inventory records and documented revisions for internal use and submission to DCMC for validation and tracking.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS - Site walkthrough with Jose Segarra from Sargent & Lundy to corroborate measurements of the main raw water pipe that supplies the entire Cambalache plant.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails and Submittals TSL-S019.0 Cambalache Sheltered Aisle Drawings on KORD-02391-ELECTRICAL CONTROLS Procore.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Reviewed & signed certificate of payment #3 went over the schedule, we went over the dates and also covered the contractors (Homeca Recyclers) milestones to make sure we were on the same page, this tasks took us over 2 hours easily with Manueli Concepcion from CDM-Smith.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents reviewed punch list reviewed all the items, make sure all were closed except for item #30 & item #32. Reviewed all punch list items and looked over all the items that we needed from Homeca Recyclers for the completion of the project phase I.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Provided safety workshop to ARG visit Andres Ortiz Rodríguez, Ricardo López and prepared meeting for tomorrows visit.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 | 164 | 246 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- DR 4339_PW11855 Continue working with Pre-Intervention Review for HOMECA Recycling Center_Contract# 107011_2025-G00272 Invoice #HRC-VB-03 May 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 3 | 164 | 492 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Pre-Intervention Review - Workning with Jaca & Sierra Contract #105165_2025-G00054d TO#6_Invoice# 0055188_ Feb 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 | 164 | 246 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339_PW9510 Pre-Intervention Review - Workning with Jaca & Sierra Contract #105165_2025-G00054d TO#2_Invoice# 0054667_ Dec 2024 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 | 164 | 164 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Beta Electric, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 | 164 | 246 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW9510 Continue working with Pre-Intervention Review RFI - Working with Black & Veatch Contract #217733_2024-G00207 and TO#7_Invoice# 000004_ May 2025 Contract documentation to identify allowable task and scope. Adding comments based on site allocations provided by Genera. Also identifying common mistakes that led to Invoice rejections. Reviewing documents: Invoice Essentials One Pager and DCMC Invoice Template to consolidate best practice procedures and documentation based on Federal Requirements 2 CFR 200 and Chapter 7.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AI001 to AI024
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AI001 to AI024
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AI001 to AI024
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AI001 to AI024
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AI001 to AI024
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations DA 00 001 to DA 00 007; DB 00 001 to DB 00 008 and DC 00 001 to DC 00 007.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations DA 00 001 to DA 00 007; DB 00 001 to DB 00 008 and DC 00 001 to DC 00 007.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.75 | 152 | 570 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations DA 00 001 to DA 00 007; DB 00 001 to DB 00 008 and DC 00 001 to DC 00 007.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.25 | 152 | 38 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BF 100 TO BF 140 LIST # 1252/1253/1254, AND RECOUNT LIST # 1256
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BF 100 TO BF 140
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Aguirre. Hurricane Maria: Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BF 100 TO BF 140 LIST # 1252/1253/1254
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BF 100 to BF 140 at the Aguirre warehouse to initiate the cycle counts.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount List #1301 from locations CB001 - CB015 for a total of 809 pcs.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 -Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CB001 to CB015 to begin the cycle counts.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CB001 to CB015, Cycle Count List # 1282.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 151 | 453 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare agenda with topics to be discussed in an upcoming internal meeting to define the projection of DCMC as a PMO inside the Procore Platform: user's responsibilities, project management execution and decision-making on current procedures.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review for publishing the Technical Specfiications for BESS Projects specifically for Cambalache and Vega Baja.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 | 151 | 604 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Technical Specifications submitted by the Design Team S&L for the Costa Sur, Aguirre and Yabucoa Power Plants, for the QA/QC process before uploading and publishing. Making sure Spec Books meet the Master Formart requirements and other engineering evaluations on the proposed methods for works.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 | 149 | 372.5 | 149 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Pre Intervention process start with CDM_293566-14_TO2_Feb2025. Start reviewing employee rates, prepare pivot table and review narratives.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2.5 | 149 | 372.5 | 149 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Pre Intervention process for Jaca & Sierra invoice 54627 Costa Sur and 54668 Palo Seco, invoices were signed, prepare final package and send them to CPA. Also, update pre intervention tracker for tomorrow's meeting. Review Sargent and Lundy_TO2_Feb2025_18343726 invoice that was under Gabriel Pérez (CDM) compliance review. Complete the process with his approval and send invoice for Jesús Cintrón (Genera) signature.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 149 | 37.25 | 149 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Prepare email with Siemens observations for RFI, I include the PO's and an explanation of missing items in a new format sent by Rafael Calderón (DCMC) and share it with him to prepare final email.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.25 | 149 | 186.25 | 149 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Continue Pre-Intervention process for CDM_293566-14_TO2_Feb2025. Reviewing narratives and identifying administrative tasks and tasks aligned to the Scope of Work. Also verify Javier Vidot Task Orders 1-6 and share them by email with Victor Maldonado (DCMC).
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 | 149 | 149 | 149 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Pre Intervention process for Jaca & Sierra invoice 54627 Costa Sur and 54668 Palo Seco. Review RFI response with Change Order signed, compliance review and prepare invoice for signature. Send both invoices for Jesús Cintrón (Genera) signature and update tracker.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 ¦ As part of the ongoing development of the project's annual calendar of community events, progress was made in identifying and adjusting key dates throughout the year. This task included specific coordination with the Red Cross, reviewing their scheduled activities in order to strategically integrate them into the overall calendar. The main goal was to consolidate a comprehensive document that reflects collaborative efforts and serves as input for the presentation to the Genera PR team, led by Jorge Bracero, next Monday. These tasks also included working with the calendar template, organizing the materials, and identifying the data that would be included.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 139 | 347.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339¦ Design a clear, accessible, and visually appealing presentation in Canva to explain to the Genera team the creation and implementation of the BESS and Peakers Project community webinars, fostering understanding, transparency, and citizen participation. As part of these tasks, I researched and documented the optimal length preferences for community webinars, identified important data that needed to be integrated into the presentation, selected the right photos for the presentation, and integrated information on how to create these types of events in Microsoft Teams, benefits, and a timeline on what should happen after each webinar
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 ¦ Evaluate a series of proposals from Community Affairs Sponsorship Opportunities with the purpose of making an official recommendation to Genera PR. These efforts include researching the organization that is seeking sponsorship, emailing the team to provide details, evaluating the scope of this sponsorship agreement in our community relations efforts in the BESS project, and making recommendations on the topic. These tasks also included gathering the necessary information to present this project to the GENERA team led by Jorge Bracero on Monday.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with Frances Vallejo and the DCMC Partners team to discuss the pending projects with Genera PR, details of the BESS and Peakers Projects. We discussed the pilot project for community webinars, the project timeline, and addressed questions related to the schedule.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 ¦ Conducted a detailed evaluation of a social media report corresponding to our client’s account, in order to identify patterns of interaction, reach, and public perception. Obtain key data on the performance of published content, as well as identify strategic opportunities to improve digital communication that can help us with the BESS project. The findings will be essential for making informed decisions and aligning our actions with the project’s objectives. This analysis will be presented to the GENERA team, led by Jorge Bracero.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 134 | 335 | 134 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Quality Control Plan review meeting with Andres Concepcion (DCMC) and Gilberto Sucre (DCMC) for the 4339_9510 BESS_Cambalache project to discuss plan and action items for the creation of a DCMC Quality Assurance Control plan.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 30 pages.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 27 pages.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria –Continued reviewing the Issue for Bid (IFB) drawings to configure submittal settings and familiarize with RFI and scheduling tools within the project management platform. The review focused on QA/QC aspects, specifically verifying concrete strength specifications and rebar spacing details to support future field inspections and documentation. This process aims to compare the IFB set with the forthcoming Issue for Construction (IFC) drawings to identify any changes or discrepancies affecting construction execution.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Conducted a safety-focused review of the Transportation and Storage Guidelines for the Tesla Megapack batteries, with emphasis on identifying potential hazards during handling, transit, and on-site storage. The evaluation included safety requirements related to temperature control, battery module stability, packaging integrity, and procedures to prevent tipping, short circuits, or fire risks. The objective was to ensure that all transportation and staging activities align with Genera's HSE protocols and regulatory safety standards for lithium-ion battery systems.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on report agenda considering report of (RG Engineering) employee Jose Segarra about meeting related of items including activities format for schedule submittal, specification section 013216 list related to construction guides and resources data formats, schedule of values of schedule for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur - worked on report of considering inclusions and foundations with specific durations, demolition works in 3 phases and presented in duration, all deafferented parts installation method of start Peaker equipment, dampert supports, Inlet manifold with field welds, siemens SGT6-8000H gas turbine, siemens fully pre-fabricated and modular air-cooled generator, turbine exhaust manifold and pre-fabricated lube oil module, siemens SGT6-8000H gas turbine base, supports and alignment, support structure for generator housing, prefabricated power control centers and electrical packages, installation of main piping and equipment inside gas turbine enclosure, installation of secondary air system pipping continues, and lube oil pipping, fire protection system with prefabricated cabinets, erection of service-friendly gas turbine enclosure, auxiliary pipping distribution and equipment, intermediate shaft structure, generator coolers and exhaust diffusor, fuel gas manifolds, fuel pipping distribution and interconnection, oil pipping distribution and interconnection, water injection pipping distribution, optional dual fuel equipment, gas turbine enclosure, exhaust diffuser section welded on site, gas air pipping, inlet filter house and fuel gas pipping inside gas turbine, instrument air pipping, air intake duct erection, optional service platforms, air intake, compressor wash skid, fuel gas flex hoses, mechanical assembly and final alignment to the gas turbine generator, testing and commissioning of master schedule, simulation of turbine project, presentation of 3D schematic project, strategy communications of Peakers and logical construction for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 134 | 201 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures ,Schedule Plan, Legal Implications and Summary of the Scheduling Cycle (Steps) to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures ,Schedule Plan, Schedule Updating and Reporting, Distribution, Trend Analysis for Monitoring the Schedule and Corrective Action to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Incorporating BESS and Peakers Community Outreach updates into the Power BI dashboard for the June monthly report.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Incorporating to June monthly report BESS and Peakers Request for Proposal (RFPs) updates and data visuals to provide a more transparent view of project progress and risks.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146795 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Internal MS Teams Meeting with Frances Vallejo, DCMC. The purpose of this meeting is to discuss project reports status and updates. The meeting was organized by Frances Vallejo (DCMC).
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Incorporating BESS and Peakers safety incidents and associated risks for each site into the Power BI dashboard for the June monthly report to enhance transparency regarding project status.
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 52 | 52 | 52 | Yes | 146795 | Portosan - Portable Toilet Rental - Vega Baja
2025-07-02 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 65.03 | 0.7 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. - Metting with Ramon Quinones, Francisco Mari (GENERA) and Luis Moctezuma, Jose Lopez (DCMC) about the Aguirre Genera Project include topics about Safety, Health, Security and Managment.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 520 | 520 | 520 | Yes | 146795 | Portosan - Portable Toilet Rental - Arecibo
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 442 | 442 | 442 | Yes | 146795 | Portosan - Portable Toilet Rental - Salinas
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations and reporting.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 225 | 675 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal reviewed submittals, specifications for the equipment designated to be installed at costa sur
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Peaker project manager update meeting, items discussed were the impacts of lates changes to the project and schedule, discussed the lack of qualified general contractor. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 225 | 675 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal Document Review – Costa Sur Project Conducted an internal review of technical and contractual documents related to the Costa Sur project. The review focused primarily on specifications and technical details of new equipment proposed for implementation. Verified compliance with project requirements, assessed alignment with operational standards, and identified any discrepancies requiring further clarification.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur BESS and Pearkers Update discussion with Carlos Rodriguez - DCMC. Emphasized the importance on comment on the IFB documents and site conditions prior to the Notice to Proceed and IFC drawings. Highlighted the main item topics for the weekly construction meeting to follow.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 225 | 562.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC Meeting at Sargent & Lundy Offices in Santurce to discuss Site Specifics topics with Aguirre - Design documents require more definition on new 53 individual slabs battery foundations slabs and civil earth works. Improvements to site entrance road from highway # 3 was also discussed. Cambalache - RGE proposal for access to road inside pond was presented. Sargent & Lundy to evaluate and provide feedback on next weeks' construction meeting. Vega Baja - Main discussion Site Underground Utilities. Sargent & Lundy - Mike Kuczynski & William Sierra CDM Smith - Enrique Laya & Gabriel Perez DCMC - Jose Lopez, Eduardo Rivera, Andres Concepcion & Gabriel Morales RGE - Jose Segarra.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peakers Project Schedule & Budget presented by Carlos Palomares for weekly update including RFP's Updates and strategy. Present: Gabriel Perez & Rafael Pabon - CDM Smith, DCMC Abraham & Gilberto Sucre, Franklyn Colemares _ CSA Group.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Evaluated the final change order submission by Homeca Recycling for the Demolition Phase, Recommendation was issued to Genera in consideration of Changes in scope, BOFA activities not performed and LD's applicable in compliance with the contract terms.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Weekly Construction Meeting with RG Engineering led by Carlos Rodriguez DCMC. Main Topics Covered: Project Opening & Language Confirmation: Contract Status and NTP were provided, Meeting began with language preference confirmation. Initial project coordination and document control discussions occurred. Underground Utilities Discussion: Robert Molner - Sargent Lundy raised concerns about existing underground utilities, specifically a water line issue discovered during recent site work Water line conflict identified on the north side of the site - demineralized water pipe runs directly through the middle of the demolition area. Carlos Rodriguez SDCMC conducted site walk with Miguel Beauchamp - Genera the previous Friday to assess the water line situation. Gilberto Sucre DCMC requested documentation from Sargent Lundy for evaluation and noted they need to coordinate with RGE for temporary relocation options. July 10th IFC deadline confirmed for site and underground utilities documentation. Water Line Rerouting Strategy: Mike Kuczynski - Sargent & Lundy clarified that they're looking at a temporary reroute solution rather than permanent drawings. Temporary reroute would allow flexibility during construction for demolition rigs and rigid inclusions work. Permanent solution would restore the water line to original route after foundation work is complete. In-person meeting scheduled for 11:00 AM to 1:00 PM in the afternoon at the A/E office to further discuss water line issues with RGE team present. Jose Robles from RGE confirmed to attend the in-person meeting Carlos Rodriguez - DCMC committed to preparing photos and preliminary sketches for the meeting
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Program Started weekly update, review of all bidding and design documentation, correspondence and reports.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on researching how we would use Procore for inventory management.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financials.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for financial tool in gathering information from users.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial information for implementation.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Docusign information for integration with Procore.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Ada Diaz (DCMC) and Frances Vallejo (DCMC) to discuss Inventory Invoices and Procore.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) to discuss documents process for older documents from CDM Smith.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore transmittals and incident tool configurations.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for Warehouse Inventory.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued reviewing submitted performance data related to power generation and fuels consumption for the power plants to ensure accuracy and consistency. - Informed Victor Torres and Josue Sanchez from Genera PR of observed delays in the delivery of power plant performance data, emphasizing the potential impact on reporting timelines. - Additionally, engaged in a discussion with Johanna Diaz, Esther Rohena, and Eisha Mercader from DCMC regarding their request to identify overlapping time entries within existing Excel-based timesheets submitted by Genera PR employees, with the objective of supporting data integrity and audit readiness.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 184 | 644 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria: Request call requests the quote to J Arroyo Enterprise for repairs electrical system in offices trailer on Yabucoa Genera Site. Call with Jose Lopez (DCMC) about Aguirre materials cleaning request. Call with Gilberto Sucre (DCMC) about status all Genera Projects. Meetings about status Costa Sur Genera Projects, include the RGE, CDM SMITH, DCMC and GENERA staffing. Gilberto Sucre (DCMC), Franklyn Colmenares (CDSMITH), Miguel Beauchamp (GENERA) and others. Call with Gabriel Morales (DCMC) to coordinate delivery personal equipment protection to Yabucoa Genera Site.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 184 | 460 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria: Review the document submit by ARG (Contractor) about safety in Vega Baja Project. Review the invoice submitted by Dueñas Trailers about Offices trailer in all Genera Sites.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 00-Nonbillable ¦ DR 4339 - Hurricane Maria: MS Teams with Frances Vallejo, Carolyn Báez-Nieves, and Jean P. Menay (DCMC) to coordinate the procurement of cleaning supplies needed for maintenance operations at the Yabucoa, Costa Sur, and Aguirre sites. Specific materials, estimated quantities, and logistics for delivery and pickup were discussed. It was agreed that Jean P. Menay (DCMC) would be responsible for preparing the order and sending it to Ada Díaz (DCMC) for processing. These supplies are essential to ensure proper sanitation and compliance with safety standards at the designated work locations. Follow-up tasks were assigned to confirm supplier availability, finalize the purchase list, and coordinate product distribution with site personnel. Make process to buy in Home Depot.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria: MS Teams with Frances Vallejo, Carolyn Báez-Nieves, and Jean P. Menay to coordinate the procurement of cleaning supplies needed for maintenance operations at the Yabucoa, Costa Sur, and Aguirre sites. Specific materials, estimated quantities, and logistics for delivery and pickup were discussed. It was agreed that Jean P. Menay (DCMC) would be responsible for preparing the order and sending it to Ada Díaz (DCMC) for processing. These supplies are essential to ensure proper sanitation and compliance with safety standards at the designated work locations. Follow-up tasks were assigned to confirm supplier availability, finalize the purchase list, and coordinate product distribution with site personnel.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended call with Rafael Calderon (DCMC) to discuss contract management and federal project management between legal and federal project teams.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Procore weekly meeting to discuss Procore SOPs and Procore financials status for BESS and Peaker's project. Attendees: Lauren Wells (DCMC) and Franklyn Colmenares (CSA)
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in meeting via Teams regarding procore and invoice management for the PMO program. Participants: Lauren Wells and Ada Diaz (DCMC)
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended call with Carlos Rodriguez, DCMC site manager of Costa Sur, to discuss issues related to the design contractor
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Drafted email to Jesus Cintrón (Genera) regarding recommendation for site managers meetings with design contractor and coordination moving forward with site plans.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Costa Sur weekly meeting with Jose Robles (RGE), Xiomara Perez (RGE) and DCMC to review contract management and deliverables. Participants: Carlos Rodriguez (DCMC), Gilberto Sucre (DCMC).
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS and Peaker budget and schedule meeting with project management team. Participants: Carlos Palomares (CDM), German Nunez (Genera), Gilberto Sucre and Abraham Velazquez (DCMC)
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - Reviewed the email thread concerning the RGE Peakers payment schedule and identified key issues impacting timely disbursement. Also reviewed the GE payment schedule to evaluate consistency and potential cross-cutting concerns. Discussed the matter in detail with José Ralat (DCMC) to assess implications and clarify outstanding concerns. Subsequently, held a follow-up discussion with Jesús Cintrón (Genera) to evaluate potential solutions and ensure alignment with contract terms and funding protocols. Collaboratively strategized a path forward to resolve the issue and maintain project momentum.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 -739681 Power Generation (Generation) Participated in a strategic advisory meeting with Jesús Cintrón, Iván Báez, and Ricardo Pallens (Genera) focused on the Temporary Generation Project. The discussion centered on Puerto Rico’s potential generation shortfall and explored viable mitigation strategies to maintain system reliability. Evaluated multiple scenarios to ensure continuity of service and alignment with regulatory and operational goals. Additionally, reviewed the FOMB Request for Information (RFI) in detail and collaboratively developed thoughtful, data-driven responses to address the inquiries.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - Reviewed PREPA’s email regarding the ER1 Cost Share Program and assessed its implications for ongoing FEMA-funded projects. Held follow-up discussions with D'Alexzander Gonzalez and José Ralat (DCMC) to align on key points and clarify the concerns raised. Collaboratively strategized an appropriate response approach and identified the documentation and supporting materials needed to substantiate Genera’s position. Began compiling the necessary information to draft a formal reply that addresses PREPA’s inquiries while reinforcing compliance with funding and program requirements.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 184 | 644 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Investigated an issue in the Genera Connect Financial Tracker where total expenses were not accurately summing all entries within the uploaded report. Communicated the findings to Keyla Sierra from Integrum and shared an export of the platform’s data model along with sample entries to illustrate the discrepancy. - Delivered an updated KPI report to Victor Torres from Genera PR to support the development of a Power BI dashboard for visualizing power plant performance.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started verifying annex J to compare to safety documentation provided by ARG. ARG provided Safety plan that include 200 pages started to verify page 1-35 comparing to Annex J that is genera’s requirements for safety procedures.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ reviewing documents dated June 21, 2025 at 2:49 AM with a content of 518 pages called, CONTRACTOR, RG Engineering, TO PROVIDE RESPONSES TO PROPOSAL DATA AND PRICING SHEETS AS PART OF BID PROPOSAL.I stayed on page 266.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ Reviewing documents dated June 23, 2025 at 3:26 AM with a content of 518 pages, called, GENERA PR LLC GENERATION FLEET STORAGE PROJECTS AGUIRRE BATTERY ENERGY STORAGE SYSTEM (BESS) FACILITY TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC) I stayed on page 184.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS PROJECT. Meeting in person at Sargent and Lundy Central Offices at Santurce PR to go over the Design Drawings and Project Pending missing items to complete the Issue for Construction Drawings. At the conference table were present Gabriel Pérez (CDM Smith), Gilberto Sucre, and Andres Concepción (DCMC). On the Teams were Mike Kuczynski, Robert Molner, and the Civil Design Staff from the Sargent and Lundy office. Review the bid documents package identified as GENERA-15240-061-0017 for the Installation of the Tesla batteries phase, submitted by Sargent & Lundy at the Aguirre Site. It was also present the selected contractor, RG Engineering, represented by Eng. José Auli and Eng. José Segarra. Sargent and Lundy rejected the proposed control room designed by RG Engineering in response to the lack of space for all the proposed equipment. RG Engineering will revise its proposal to incorporate all the required equipment as specified in the arrangement shown in the design.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ reviewing documents dated June 21, 2025 at 2:49 AM called, CONTRACTOR RG Engineering, represented by Ing. José Auli, TO PROVIDE RESPONSES TO PROPOSAL DATA AND PRICING SHEETS AS PART OF BID PROPOSAL. AGUIRRE BESS.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 340 to 393. Among the topics read were glass and glazing (construction quality control), Portland cement plastering (portion and mixing), ceramic tile and wall tile, vinyl composition resilient tile flooring, coating system (different types and conditions), hot dip galvanized.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 294 to 339. Among the topics read were hollow metal doors and frames (design and performance requirements, different of doors type and material, installation), doors and frames hardware preparation, finishes, rolling steel door, aluminum windows (structural design, warranty, acceptable products), tubular daylight devices, door hardware (individual components)
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Supervised (DCMC - Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría) the trailer removal work performed by RG Engineering (Mickel Lopez, Juan Vega, Juan Gautier and Emmanuelle Hernandez) at the Costa Sur site. The team reviewed and discussed the Job Safety Analysis (JSA) for the tasks involved, emphasizing key safety protocols and risk controls. Additional coordination was held regarding the planned removal route through the Punta Este gate, ensuring all logistical and operational aspects were aligned with plant requirements. On-site supervision focused on verifying the safe execution of the work and ensuring compliance with Genera’s safety standards. Meeting with DCMC team (Gilberto Sucre, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), RGE Jose Robles Construction team lead and Sargent and Lundy design team lead Franklyn Colmenares. Topic discussed: Scope of Work, Schedule, Commercial, Project Communication, General safety and quality control / quality assurance.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Continued the safety assessment of the Tesla Megapack Transportation and Storage Guidelines by cross-referencing manufacturer protocols with on-site logistical conditions. Focused on evaluating the feasibility of implementing required safety measures at the Costa Sur site, including designated storage zones, material handling equipment, and environmental controls. Recommendations were noted to strengthen alignment with lithium-ion battery safety standards and to mitigate potential risks during mobilization and temporary storage.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal review of Section 310.4, which details procedures for setting and grouting column baseplates. Detail emphasizes on field conditions, such as removing anchor rod sleeve tops and cleaning concrete surfaces before grouting. Includes exclusion of leveling nuts and the requirement to remove and refill shim voids. These specific will require close inspection coordination during baseplate installation and curing to ensure conformity.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur DCMC Site team meeting lead by site Manager Carlos Rodriguez weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to continue discussions on initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically to permits, safety modules, submittals and RFI's.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Travel time from Sargent & Lundy Office to Yabucoa site after assist the kickoff meeting with RG Engineering, DCMC Partners, Sargent & Lundy and CDM Smith team.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Travel time from Yabucoa site to Sargent & Lundy Office to assist the kickoff meeting with RG Engineering, DCMC Partners, Sargent & Lundy and CDM Smith team.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Meeting with Javier Arroyo from J Arroyo Enterprise Inc. (Electric Contactor) to assess an unexpected electrical failure, affecting lighting, A/C units, and all power outlets in the DCMC Partners office at the Yabucoa Site.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: A kickoff meeting was held with Jose Segarra from RG Engineering, Wilfredo Sierra, Vincent Skochdopole and the rest of the team of Sargent and Lundy team and with Gilberto Sucre, Andres Concepcion, Jose Lopez, Carlos Lopez from DCMC Partners to discuss key aspects of the ongoing BESS project.A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project Costa Sur, Cambalache and Aguirre sites. Additional topics included equipment needs, drawings details, and the tools necessary for efficient work execution. The team also discussed the integration and management within the civil infrastructure, emphasizing the importance of ensuring that are properly aligned for optimal efficiency and reliability of the project.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR-4339 – Hurricane Maria Continued site visit efforts at the Peakers area alongside Rafael Barrera (Construction Manager, DCMC), Luis Echevarría (Safety, DCMC), and Carlos Bayron (QA/QC, DCMC). The team reviewed available documentation and site diagrams related to the demolition scope, including layout drawings, utility disconnection plans, and access routes. This review supported validation of the proposed demolition sequence, identified key coordination points, and reinforced planning efforts to ensure the safe and organized execution of upcoming field activities.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Supervised (DCMC - Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría) the trailer removal work performed by RG Engineering (Mickel Lopez, Juan Vega, Juan Gautier and Emmanuelle Hernandez) at the Costa Sur site. The team reviewed and discussed the Job Safety Analysis (JSA) for the tasks involved, emphasizing key safety protocols and risk controls. Additional coordination was held regarding the planned removal route through the Punta Este gate, ensuring all logistical and operational aspects were aligned with plant requirements. On-site supervision focused on verifying the safe execution of the work and ensuring compliance with Genera’s safety standards. Meeting with DCMC team (Gilberto Sucre, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), RGE Jose Robles Construction team lead and Sargent and Lundy design team lead Franklyn Colmenares. Topic discussed: Scope of Work, Schedule, Commercial, Project Communication, General safety and quality control / quality assurance.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We work in the specific standards for access to Aguirre Power Plant this in order to guide our contractors: Access to the Aguirre Power Plant requires strict adherence to specific safety standards established to protect personnel and maintain operational integrity. Before entry, all individuals must complete a mandatory safety orientation covering site-specific hazards, emergency procedures, and PPE (Personal Protective Equipment) requirements. Standard PPE includes a hard hat, safety glasses, flame-resistant clothing, high-visibility vest, gloves, and steel-toe boots. Additionally, all personnel must carry valid site access credentials and complete any required permits or documentation for the scope of work to be performed. Contractors are subject to random safety audits and must participate in daily toolbox talks to remain informed on current safety concerns and operational updates. Compliance with LOTO (Lockout/Tagout) procedures, confined space entry protocols, and hot work permits is strictly enforced. These measures ensure that everyone working within the plant maintains a high level of situational awareness and contributes to a safe and efficient work environment.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and review the 29 CFR 1926 OSHA updated Thru January 2024 for Construction Industry Regulations. Include I am reading and review The OSHA's most frequently cited serious violations in Construction Industry. To apply every good practice and standards in Bess_Aguirre
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, and Luis Moctezuma(DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team. The task assigned to the team this week is to complete the DCMC Office Trailer Mobilization and Office Supplies Delivery.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting in person at Sargent and Lundy Central Offices at Santurce PR to go over the Design Drawings and Project Pending missing items to complete the Issue for Construction Drawings. At the conference table were present Gabriel Pérez (CDM Smith), Gilberto Sucre, and Andres Concepción (DCMC). On the team were Mike Kuczynski, Robert Molner, and the Civil Design Staff from the Sargent and Lundy office. Review the bid documents package identified as GENERA-15240-061-0017 for the Installation of the Tesla batteries phase, submitted by Sargent & Lundy at the Aguirre Site. It was also present the selected contractor, RG Engineering, represented by Ing. Joé Auli and Ingenieer José Segrera. Sargent and Lundy rejected the proposed control room designed by RG Engineering in response to the lack of space for all the proposed equipment. RG Engineering will revise its proposal to incorporate all the required equipment as specified in the arrangement shown in the design.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed and evaluated project design drawings latest revision to identify pending design details and specfications that are still pending to ensure construction alignment.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting on Sargent and Lundy's offices in Santurce PR. Met with Sargent & Lundy (Wilfredo Sierra, Angel Alicea, Mike Kuczynski) DCMC (Gilberto Sucre, Jose Lopez) and RG Engineering (Jose Segarra, Alberto Borreli) to discuss design technical items for Costa Sur, Aguirre and Cambalache BESS projects.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared and generated a meeting minute agenda regarding the Technical Design items discusses for Cambalache in the design meeting with RG Engineering (general contractor) and Sargent and Lundy (designer).
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued drafting Submittal RGE-0009 Quality Control Plan observations and responses to be shared with general contractor (RG Engineering) via Procore.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 | 167 | 626.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with ARG specification review send by S&L. Contact Carlos Hernandez of ARG/CERES to inform that submittal ARG-S008 was sent to S&L for review but this submittal does not have any attachment for precast calculation it was rejected and requested to Carlos to resubmit with supporting data. Have a communication meeting with Jaime Pesquera of DCMC to understand the needs for the preparation of the second phase construction.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Site visit with ARG/CERES - Ricardo Lopez, Maria Reyes and Carlos Hernandez, DCMC Jaime Pesquera and Eduardo Rivera and CDM Smith Nelson Soler - Meeting was to walk down the field construction site and to meet with Safety Maria Reyes and Project Engineer Ricardo Lopez of ARG/CERES.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Send email to Gabriel Perez of CDM Smith in regard of proposal of ALL Contractor & Service for repairing the oil pipeline from the GT demolish dikes. Continue working with specification review and also the IFC which send an email to Mike Kucynski in regard of drawing with a revision and not been identify the revision number in the drawing release information. Reviewing ARG/CERES Submittal ARG-S008.1 in regard of load calculation for precast slab to be consider for project, S&L must review also and approve this precast slab.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Review the Drawing document Discipline Architectural on Procore and generate comment for designer Sargent and Lundy.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the Submittal #: RGE-0008.2 RGE-0008 EMPLOYEES CERTIFICATION.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Review the Drawing document Discipline Civil on Procore and generate comment for designer Sargent and Lundy.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Went over construction drawings. All drawings issued from construction against issued for bid according to what we have right now and what we needed updated.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Went over construction drawings. Grading & drainage plan, grading sections & details.Tower section detail drawing, thermal camera & flame detector tower. New transformer lifting points drawings.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started verifying annex J to compare to safety documentation provided by ARG. ARG provided Safety plan that include 200 pages Continue to verify page 1-35 -45comparing to Annex J that is genera’s requirements for safety procedures.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 | 164 | 164 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Beta Electric, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 164 | 82 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11¦ DR 4339 Contract Management Meeting- DCMC and Genera. Go over contract communication protocols, reviewing assigned POC from Genera Legal for each contract and Pending action items review based contracts development. Meeting between Genera (Jesus Cintron) and DCMC (Rafael Calderon, Frances Vallejo).
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 164 | 82 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA Contract meeting (Change Orders Status) Meeting with project management Team. Contract 106761 - Reviewing current change orders status on delivery dates, payment milestones for MVT, GSU, MegaPacks and tariffs for all plants. Meeting participants TESLA (Michael Grabstein, Allin Luong), CSA (Franklyn Colmenares), CDM Smith PM team (Gabriel Sepulveda), Genera (Jesus Cintron), Sargent & Lundy (Mike Kuczynsky, Vincent Skochdopole), and DCMC (Rafael Calderon)
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 164 | 164 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- RG Engineering Inc. Contract #109403 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #2 based on contract requirements. Reviewing Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 164 | 82 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339_PW#10710 RG Engineering Inc. & Genera Weekly Meeting_ Contract #109403, Commercial & Schedule Discussion review for RGE Equipment Supply Contract. Reviewing contract requirements, payment milestones, general submittal status and key dates Participants: Genera (German Nuñez), Sargent & Lundy ( Miguel del Valle, Mike Kuczynski, CDM (Carlos Palomares, Rafael Pabon, Enrique Laya), RGE ( Harry Velazquez), Gevernova (David Lee) and DCMC (Rafael Calderon)
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 | 164 | 82 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- DR 4339 Continue working with Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, EHSS, RGE, Jaca & Sierra, Beta Electric, Javier Bidot, TESLA and CAPTA. In preparation for Genera and DCMC Weekly meeting.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 | 164 | 164 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria New- DCMC- Weekly Status Pre-Meeting Updates on operation Status from all departments at Genera. DCMC participants (Mark Merritt, D'Alexzander Gonzalez, Jose Ralat, Esther Rohena, Eisha Mercader, Glorimel Torrado, Roberto Bosch, Cynthia Ortiz, Christian Cruz), Carlos Gonzalez - Integrum, Marc Maceira - Honra and Shellsea Maysonet - SMC
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 164 | 246 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- TESLA_Contract 106761 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #3 based on contract requirements. Reviewing section 3.11 Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 | 164 | 164 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11- DR 4339 Pre-Intervention Tracker Payment Update - Populating Tracker information and status comments with information related to the Invoiced submitted by Genera from Contractors - Sargent & Lundy, CDM Constructors, CPM, B&V, Homeca, Siemens Energy, Jaca & Sierra, Javier Bidot, TESLA, RGE, EHSS and CAPTA. In preparation for Genera and DCMC Weekly meeting. Reviewing all pending payment status in Asset Suite based on new invoice approval list. Preparing email communication to CPA creator POC from CSA - Franklyn Colmenares and Manuely Concepcion and from Genera Frances Adames based on Asset Suite findings for payment follow-up.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Recovery Manager | Calderon, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 164 | 82 | 164 | Yes | 146795 | Genera PR ¦ Deliverable 11¦ DR 4339_PW#10710 Contract Management Activities- Siemens_Contract #00106588 and Deliverable Schedule review based contract development. Working on Deliverables for Payment Milestone #2 and #3 based on contract requirements. Reviewing Shipping, Delivery and Storage requirements and Liquidated damages. Also reviewing Change Order development status for Genera final approval. Contract documentation to identify allowable task and scope. Identify and mitigate contractual risks. Develop and implement contract management processes and systems. Provide guidance and support to project managers and other stakeholders on contractual matters.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 152 | 190 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AI025 to AI049
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AI025 to AI049
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AI025 to AI049
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AI025 to AI049
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AI025 to AI049
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations DD 00 001 to DD 00 007; DE 00 001 to DE 00 004; DF 00 001 to DF 00 005 and DG 00 001 to DG 00 005
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations DD 00 001 to DD 00 007; DE 00 001 to DE 00 004; DF 00 001 to DF 00 005 and DG 00 001 to DG 00 005
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations DD 00 001 to DD 00 007; DE 00 001 to DE 00 004; DF 00 001 to DF 00 005 and DG 00 001 to DG 00 005
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations in secondary warehouse in the plant, requesting an inventory list and printing it to begin accounting
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BG 001 TO BG 040
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BG 001 TO BG 040 LIST # 1268/1269/1270
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BG 001 TO BG 040 LIST # 1268/1269/1270, AND RECOUNT LIST # 1271/1272
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Prepare the lists for locations BG 001 TO BG 040 at the Aguirre warehouse to initiate the cycle counts.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 | 152 | 266 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 -Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CB037 to CB044 to begin the cycle counts.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 152 | 114 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 152 | 190 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1313 and 1314 from locations CB037 to CB044 for a total of 252 pcs.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CB037 to CB044 Cycle Count List # 1309.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Go over the general contractual agreements and current Submittal Logs on active projects to determine items that needs to be worked through the Transmittals Tool in Procore.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Ensure Documents are created, reviewed, distributed, stored & archived in an organized & controlled manner/ensure information is organized accurately transmitted & readily accessible for the project team/Palo Seco BESS review TESLA date for processing/Review & process daily incoming documents
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Ensure Documents are created, reviewed, distributed, stored & archived in an organized & controlled manner/ensure information is organized accurately transmitted & readily accessible for the project team/provide accurate & Timely information, leading to better execution of project plans and specifications/Vega Baja Data Review/Costa Sur Siemens Data for Review & Upload/Palo Seco BESS Tesla incorporate new users/GEN 01 Procurement Data Review & Process
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Master Format for USA/Canada that applies to Construction Technical Specifications and its contents, to determine flaws in the Specifications Books submitted by the Designer S&L, in order to be able to work with the Submittal Builder feature from the Specifications Tool: deisgner needs to revise document formatting and reorganize the Submittals section from each spec.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Technical Specifications for BESS works at the Costa Sur Power Plant; QA/QC on the proposed methodolody for performing concrete, metal and electrical works. Also, review of Excavation specification to review the dewatering systems specs.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Technical Specifications for BESS works at the Yabucoa Power Plant; QA/QC on the document format to meet Procore requirements for the Submittal Builder feature.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Nelson Soler (CDM Smith) to discuss the permissions extent for QA/QC Manager at the Transmittal and Specifications Tools in Procore; review the project management standards as an input to Procore for the evaluation on correct responding and directing issues as the Owner's Representative.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Weekly Meeting hosted by Franklyn Colmenares (CSA) and joined by Lauren Wells (Lemoine), Ivette Miranda (S&L) and Rafael Pabon (CDM Smith). Discussed the current Procore open topics such as the Procore Financials Tool, SOP publishings, Drawings and Specs upload/publishing, and others.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA – Genera PR ¦ Deliverable 11 ¦ DR 4339 – Hurricane Maria Reviewed the Transmittal tool and performed functional validation activities within a controlled project environment to evaluate available features for the distribution and tracking of project-specific documents and information. Assessed the tool’s capability to support proper document sharing, recipient tracking, and recordkeeping in alignment with established document control procedures.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review and edit the current Distribution Lists and Groups inside the BESS Project Management Main Staff in order to provide easier distribution on items such as Submittals, RFI, correspondence and any project-related information being distributed through Procore.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 | 149 | 74.5 | 149 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Review and discuss with Rafael Calderón (DCMC) pending important action items on contract management and Invoices. Siemens pending Change order and Tesla amend and restate. We update and recap for next week.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1 | 149 | 149 | 149 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Pre-Intervention Tracker Update - Populating Tracker information and status comments with information related to the invoices submitted by Contractors - Sargent & Lundy, Tesla, Homeca, CDM Constructors, CPM, B&V, Siemens Energy and CAPTA.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Grants Manager | Torrado, Glorimel | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 1 | 149 | 149 | 149 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339- Genera Pre-Meeting with participation from DCMC: José Ralat, D'Alexzander González, Roberto Bosch, Rafael Calderón, Eisha Mercader and Cynthia Ortíz. Also, Marc Maceira from Honra, and Shellsea Maysonet (SMC); to discuss priorities and deliverables, status updates, identify next steps, metrics, challenges, and deadlines as preparation for the meeting with client next week.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 139 | 486.5 | 139 | Yes | 146795 | Genera PR – Deliverable 11 – Project Management – DR4339: Progress continued on the translation of Volume 3, Chapter 13, and Chapter 14 (Sections 14.1 to 14.5) of the SHE Manual. This phase focused on maintaining consistent formatting and structure, ensuring the accurate use of technical terminology, and conducting a thorough review to correct spelling and grammatical errors throughout the document. Special attention was given to refining and formatting the chapters to enhance clarity and ensure alignment with project standards.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339¦ Meeting call with the Genera PR team, including Jorge Bracero, to discuss the educational project aimed at impacting summer camps in the municipality of Vega Baja. This project seeks to raise awareness about Puerto Rico's energy issues by providing educational materials through schools located at Genera PR operational sites. During the call, an action plan was outlined to approach the municipality of Vega Baja with a targeted proposal for the BESS project, with the aim of strengthening community outreach in that area.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339¦ Meeting call with the Genera PR team, Jorge Bracero, and the communications team from the municipality of Vega Baja, Gil Rivera, to discuss the educational project aimed at impacting the summer camps in Vega Baja. During the call, the educational project was presented to the Director of Communications of Vega Baja. A work plan was defined to request authorization to visit the schools, and a general action plan was also outlined.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Started creating the Costa Sur fact sheet in Canva. This task included integrating information about the Peakers, BESS, and site details, as well as adjusting photos of the BESS, Peakers, and the render. It also incorporated information about the BESS fire mitigation plan. Additionally, questions regarding the Peakers were clarified, and a section with frequently asked questions was included.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.75 | 139 | 243.25 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Write a formal and professional letter to the municipality of Vega Baja to present the educational project aimed at impacting summer camps in the municipality. The purpose is to request authorization to strengthen community ties with this area and to deliver educational materials related to the BESS Project. This task includes drafting the letter, locating Genera PR’s official format, editing the text, incorporating information about the project, and providing a summary of the schools we have previously impacted.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Call meeting with Jorge Bracero from the Genera PR team to discuss pending tasks, provide a project update, follow up on ongoing items, and align on next steps related to the community meetings in Costa Sur, Aguirre, Jobos, and Yabucoa.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 | 139 | 34.75 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Update the community engagement report status update to be shared during our Monday check-in meetings moving forward, including the community outreach efforts carried out in connection with the initiatives to impact schools and summer camps in the municipality of Vega Baja.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Update the weekly information on Genera PR’s website: genera-pr.com/BEESS / Peakers. This task involved gathering and editing the content so that the Genera PR team—specifically Jorge Bracero and Alex O. Valdés Díaz—could update all the site-specific information related to the BESS and Peakers Project. The tasks also included editing the entire report to ensure it was sufficiently understandable for the Genera PR team.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Write community engagement report status update to be shared during our Monday check-in meetings moving forward. The report includes information about the preparations related to the community webinars for the BESS Project and information about the preparations related to the community webinars. These tasks included drafting communication materials, verifying project information, organizing relevant data, and coordinating internally to ensure accurate and consistent messaging across all efforts. This email was sent to the Genera team, Jorge Bracero.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures ,Schedule Plan, Weather Delays and Time Extensions, from the Subcontractors Plan, Subcontractor Execution and Subcontractor Requisition for Payment to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 134 | 402 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 19 pages.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 134 | 402 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 20 pages.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 134 | 268 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Technical Discussion Meeting about the Aguirre Site design with Gilberto Sucre, Jose Lopez, Sunem Martinez (DCMC); Enrique Laya, Gabriel Perez (CDM Smith); Wilfredo Sierra, Marco Galvan, Angel Alicea and other Sargent & Lundy members.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Supervised (DCMC - Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría) the trailer removal work performed by RG Engineering (Mickel Lopez, Juan Vega, Juan Gautier and Emmanuelle Hernandez) at the Costa Sur site. The team reviewed and discussed the Job Safety Analysis (JSA) for the tasks involved, emphasizing key safety protocols and risk controls. Additional coordination was held regarding the planned removal route through the Punta Este gate, ensuring all logistical and operational aspects were aligned with plant requirements. On-site supervision focused on verifying the safe execution of the work and ensuring compliance with Genera’s safety standards. Meeting with DCMC team (Gilberto Sucre, Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría), RGE Jose Robles Construction team lead and Sargent and Lundy design team lead Franklyn Colmenares. Topic discussed: Scope of Work, Schedule, Commercial, Project Communication, General safety and quality control / quality assurance.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Conducted a safety-focused review of the Transportation and Storage Guidelines for the Tesla Megapack batteries, with emphasis on identifying potential hazards during handling, transit, and on-site storage. The evaluation included safety requirements related to temperature control, battery module stability, packaging integrity, and procedures to prevent tipping, short circuits, or fire risks. The objective was to ensure that all transportation and staging activities align with Genera's HSE protocols and regulatory safety standards for lithium-ion battery systems.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 134 | 67 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on report considering division 1 section 013216, specification format for schedule on specific rule item 103.8 of resources variables employee considering start dates, finish dates and remaining resource loading for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on report considering division 1 section 013216, specification format for schedule on specific rule item 103.8 of equipment considering start dates, finish dates and remaining resource loading for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - DCMC Site team lead by site Manager Carlos Rodriguez internal meeting on deliverables for site that include location of status of sign of contract, access to site parking, site layout, status of design drawings, existing utilities, safety documents updates, construction news and schedule news of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically to permits, safety workshop, submittals and RFI's.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on report considering division 1 section 013216, specification format for schedule submittal, worked on specific rule item 103.8 of resource loading for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures, Subcontractors Plan, Subcontractor Lien Releases, Subcontractor Joint Payment Agreements, Subcontractor Payments and Subcontractor Back Charges to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Abraham Velazquez, Gilberto Sucre CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares, Enrique LayaGenera: German Nunez
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Commenced updating the BESS financial status in Power BI as part of the June monthly report, aiming to improve the clarity and precision of visualized data regarding budget modifications, actual expenditures, and projected remaining costs.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updating the Power BI dashboard for June incorporating updates on Contract Payment Milestones associated to BESS and Peaker sites and a risk assessment for greater project insight.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue updating the BESS financial status in Power BI as part of the June monthly report, aiming to improve the clarity and precision of visualized data regarding budget modifications, actual expenditures, and projected remaining costs.
2025-07-03 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  | 0.7 | 50.96 | 0.7 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Claiming Mileage for this route - Yabucoa Gas Turbine to Sargent and Lundy office to Yabucoa Gas Turbine. Purpose - A kickoff meeting was held to discuss details about the Aguirre, Yabucoa and Costa Sur BESS project number 10710 with SarSmith and the rest of the team of DCMC Partners.
2025-07-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Program Continued weekly update, review of all bidding and design documentation, correspondence and reports. Also started working of performance appraisals of Site Managers. Prepared Needs List from Genera to be discussed with PM group prior to Genera Meeting scheduled for Monday at 9:30 am
2025-07-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with specification division 1 section 013216 using format in columns cost for monthly update, unit percent for monthly update with invoice requirements or periods progress (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-04 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on report considering division 1 section 013216, specification format for schedule on specific rule item 103.8 of resources employees labor, welder and equipment variables considering this period unit, this period cost and remaining unit resource loading for employee (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting setup with Sargent and Lundy for this week to discuss submittal responses in Procore vs what they have on their transmittals.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 bess/peakers project needs meeting discussed items that we need to coordinate with Genera and facility personal for the removal of existing equipment. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group Gilberto Sucre DCMC
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in conference calls with the field team at costa sur discussed the weeks follow up and scheduling. Carlos Rodriguez DCMC Carlos De Jesus DCMC Rafael Barrera DCMC
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Internal review of upcoming weeks meetings, agendas and notes for comment. Reviewed recent submittals for the costa sur equipment procurement
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Tariffs clause continued discussion with Francisco Feliu Genera Legal. Reviewed latest documentation of material pricing submitted by ARG Ceres and evaluated the potential exposure to Genera depending on cost sharing between contractor & owner.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 | 225 | 393.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM Weekly Update meeting with Gabriel Perez CDM Smith, Franklyn Colmenares - CSA Group and Gilberto Sucre-DCMC reviewed and update Program Status as well as each individual project in preparation of BESS & Peaker's Project Needs meeting with Jesus Cintron - Genera. Main Topics: FOMB submissions for Vega Baja, Cost Sur, P3 RFI Response. Sargent & Lundy Performance and design delays. TRC A/E SME incorporation to the team. Homeca's Contract Closure Yabucoa RFC's Vega Baja - Drainage Repair, MPT Rigging & Repair, Soil's evaluation. Tariffs clause for ARG Ceres Contract
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence reading and response to e-mails for BESS Program.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Construction Technical Internal PM/CM Team to review Sargent & Lundy's deliverables and expected issue dates for IFC's across the different projects. Team advised the combined installation BESS for Aguirre, Costa Sur & Yabucoa RFP to be rescheduled due to current Civil & Structural Commencement delays. Present Gabriel Perez, Enrique Laya - CDM Smith, Kime Kuczynski, Robert Molner - Sargent & Lundy. Gilberto Sucre - CDMC
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Follow up call with Gabriel Perez CDM Smith getting feedback from discussions from Jesus Cintron - GENERA form morning's Needs meeting which took place but not at the scheduled time. Main items were Vega Baja to proceed with drainage and MPT relocation and repair, soil sampling confirmed already taken and not required. Follow up status with Finance and Procurement on FOMB submittals, impase with ARG Ceres tariffs.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated PMO Reporting for BESS Program.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Morning Update calls with Site Managers to review day's agenda & needs with Carlos Rodriguez Costa Sur Jose Lopez - Aguirre Eduardo Rivera - Vega Baja Andres Concepcion - Cambalache all DCMC.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed and approval CDM Smith April Invoice identifying not applicable charges as some entries were from unauthorized employees as determined by GENERA
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Meeting with Basilio Ramos - Sunset Contractors to walk thru their demolition phase II quote and introduce him to Carlos Hernandez - ARG Ceres for their potential agreement under the Installation Phase. Present: Jose Lopez, Eduardo Rivera & Gilberto Sucre - DCMC Carlos Hernandez - ARG Ceres Basilio Ramos - Sunset Contractors
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore workshop items for tracking of which users have had experience and which tools have been trained on.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore analytics tool.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating reporting items for Procore for Raissa Borges (DCMC).
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configuration items and policy items.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore distribution list for Peakers projects.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore weekly tasks.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items for implementation.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items for financial information and meetings.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Peakers Check-in.Rafael Pabon (CDM Smith), Frances Vallejo (DCMC), Franklyn Colmenares (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore items for distribution lists and financial items.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.75 | 184 | 690 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated the Genera Connect Timesheets project worksheet records to include the corresponding PW codes, ensuring alignment with project documentation requirements. Continued refining the Power Production and Fuels Consumption master report in preparation for validation. Conducted a review session with José del Rio and Jan Rodriguez from Genera PR to verify the accuracy of the fuels consumption and distribution data, confirming the report’s readiness for submission.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Peakers check in meeting with project management team. The topics discussed were Procore documentation submission, RFP's and site status. Participants: Rafael Pabon (DCMC), Carlos Palomares (CDM Smith), Abraham Velazquez (DCMC), and other DCMC participants.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with client (Jesus Cintron, Genera) to discuss Peaker's project leadership changes and next steps.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Luz Ramirez (DCMC), new employee, safety officer at Yabucoa. Discussed PMO organizational chart, tasks, RFP and contract with supplier, and reporting requirements.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams meeting regarding Cambalache update to discuss project status and reporting. Participants: Andres Concepcion (DCMC) and other DCMC participants.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review and analyze the June monthly report for BESS and Peakers project to send to client.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - 234MW of BESS Installation - Continued formatting the RFP attachments to ensure consistency with procurement standards and ease of use for prospective proponents. Focused on Attachment D (Technical Specifications) and Attachment E (Federal Clauses), verifying that all sections were clearly structured, aligned with the main RFP document. Adjusted formatting for clarity, readability, and compliance, and prepared the documents for internal review and feedback.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - 234MW of BESS Installation - Began formatting the RFP Exhibits to ensure consistency with procurement standards and ease of use for prospective proponents. Focused on Exhibit A (Checklist), verifying that all sections were clearly structured, aligned with the main RFP document. Adjusted formatting for clarity, readability, and compliance, and prepared the documents for internal review and feedback.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - 234MW of BESS Installation - Began formatting the RFP attachments to ensure consistency with procurement standards and ease of use for prospective proponents. Focused on Attachment A (Administrative Requirements) and Attachment B (ITB & Q&A Form), verifying that all sections were clearly structured, aligned with the main RFP document.Adjusted formatting for clarity, readability, and compliance, and prepared the documents for internal review and feedback.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. Subcontractors: Shellsea Maysonet, Johanna Díaz, Marc Maceira, Carlos González and Ginnell Torres
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated the Genera Connect Financial Tracker with the latest data in preparation for the weekly Genera PR meeting. Continued reviewing power production and fuels consumption data submitted by the power plants, with particular focus Trailer Mounted (TMs). Additionally, examined data specific to the Costa Sur and San Juan power plants provided by Jan Rodriguez from Genera PR to verify completeness and accuracy for reporting purposes.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started site visit with Sunset contractor Basilio Ramos for estimate on the demolition site. Continue site visit with Carlos Hernandez, Maria Ramos from ARG and DCMC team Gilberto Sucre, Jose Linares, and Jaime Pesquera including Nelson Soler from CDM Smith.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ G-3400 – Technical Specification for BESS (GWC) Issued for Bid / AGUIRRE BESS; Potential Lay Down Area for Pickers Units.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ GENERA PR 30 MW BESS at Costa Sur DCMC comments on resources duration specification July 03 2025. This document has the main purpose of detailed definition rule considering the Resources from the Specification of Technical Service illustration considering division 1 section 013216 specific rule item 103.8.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ reviewing documents dated June 21, 2025 at 2:49 AM with a content of 518 pages called, CONTRACTOR TO PROVIDE RESPONSES TO PROPOSAL DATA AND PRICING SHEETS AS PART OF BID PROPOSAL.I stayed on page 266 to 518.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 394 to 414. Among the topics read were Toilet and Wash Washroom (construction quality control, delivery, storage, handling, grab bars, soap dispenser, paper towel dispensers or hand dryers, waste receptacles, mirrors, sanitary accessories), plumbing requirements (design requirements, reference documentation, preparation)
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 415 to 441. Among the topics read were general requirements for HVAC Systems (design conditions, calculations, airflow diagram, piping and instrumentation, preparation, installation, protection, record documentation), site security (closed circuit television, card readers, door hardware, access control board), medium voltage power cable (detailed design and construction requirements, cable test and test report), low voltage power cable (detailed design and construction requirements, cable test and test report).
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 442 to 470. Among the topics read were control and instrumentation cable (cable design and construction requirements, cable test and reports, installation), grounding (technical requirements), conduits and supports (junction boxes, pulled boxes, conduit bodies, installation), cable try and support (identification, cable try support installation), testing and checking electrical equipment (testing conditions and parameters), metal clad medium voltage switchgear.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Conducted a review of Appendix D.1 – Design Drawings for Civil & Structural Works related to the 30 MW BESS at Costa Sur. Focused on identifying potential safety considerations in design elements such as access routes, equipment layout, and structural clearances. These early assessments are part of the pre-construction phase to proactively address HSE risks through design. Cross-checked drawings with applicable OSHA and NFPA design-related safety standards.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Reviewed the Tesla Megapack Transportation and Storage Guidelines to verify compliance with safety protocols for battery handling and staging. Focus was placed on temperature control, packaging integrity, and secure storage layout. Verified alignment with Genera’s HSE procedures for lithium-ion systems.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal review of Section 311.2 through 311.4, covers welding, high-strength bolting, and grating installation. Grating section includes comprehensive requirements on fastener locations, removable section treatments, and stop-bar field welding. Summarizing section includes acceptable hold-down clip materials, details for cantilevered panels, tolerances for gaps and edge fit-ups.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal review of Section 311.1, details specifics of anchor rod tightening procedures and overall erection requirements. Snug-tight plus one-quarter turn method for anchor nut installation specified as a critical torque requirement. Details mentioned referring to AISC 303 for erection methodology, indicating that the overall process must align with industry-standard practices and this specification. Specific linkage to external standards will require cross-referencing. Coordination calls were made with Costa Sur BESS Lead Gilberto Sucre (DCMC) & Peaker's lead Abraham Velazquez, on basic necessities for site development that include movement of existing materials and laydown area.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 0119110 "Startup, Testing and Commissioning" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 260512 "Site Security" in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Phone Call with Carlos Rodriguez and Jose Lopez from DCMC Partners to discuss the reported findings of the Scope of Services for Technical Specification Number G-3300 for Aguirre Site and Costa Sur Site BESS General Work Contract (GWC) that will be issued for bid.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 167 | 41.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Phone Call with Gilberto Sucre from DCMC Partners to discuss the reported findings of the Scope of Services for Technical Specification Number G-3300 for Yabucoa Site BESS General Work Contract (GWC) that will be issued for bid.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur BESS Site visit to assess the current site conditions and determine the necessary preliminary actions required before the commencement of construction activities. Performed a thorough walkthrough of the site, documenting observations related to accessibility, safety, and environmental factors. It was noted that the area contained residual debris, overgrown vegetation, and scattered construction materials from previous operations. These conditions pose potential safety hazards and could hinder the efficient mobilization of equipment and personnel. The contractor needs to complete the cleanup activities. A follow-up inspection will be scheduled to verify that the site meets the required standards before construction begins.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur BESS- Review of Specification No. G-3200 was initiated to ensure alignment with current industry standards, project-specific requirements, and regulatory compliance. The focus was on Divisions 00 (General Project Requirement) through 05 (Metals), encompassing general administrative protocols, product requirements, and material specifications related to metals.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Safety Inspection Report: Facility: Aguirre Power Plant Location: Salinas, Puerto Rico Date of Inspection: 7/7/2025 Inspection Conducted By: Luis Moctezuma Accompanied By: [N/A] Purpose of Inspection: The scheduled safety inspection aimed to assess compliance with OSHA standards, identify potential safety hazards, and verify the implementation of the facility’s safety protocols. The inspection focused on operational areas, emergency response systems, PPE usage, and employee safety practices.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Supervision of contractor Villamil Group while they were installing sanitary and potable water piping to the DCMC trailer in the Bess_Aguirre Project. Supervision of the staff to ensure compliance with DCMC Partners, Genera PR, and OSHA standards and policies. We carried out a visual inspection of the sanitary piping and potable water installations. We also tested the sink in the bathroom, the toilet, and the handwashing station to ensure that they were functioning properly.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -VEGA BAJA BESS JOB SITE VISIT. Meeting on Site with Basilio Ramos ( Sunset Contractors), Carlos Hernandez (ARG/Ceres), Gilberto Sucre, Eduardo Rivera (DCMC), and Nelson Soler (CDM Smith) to go over the Phase II demolition works scope of work and answer any doubts or questions regarding the task. It was discussed what the limit of the work is, and the means and methods will be coordinated with ARG/Ceres, as well as the starting date. Basilio Ramos suggested that the crushed concrete could be used as a construction surface to benefit the project. Basilio Ramos (Sunset Contractors) will revise the proposal and resend it to Carlos Hernandez (ARG/CERES). A walkthrough was performed withBasilio Ramos (Sunset Contractors and Eduardo Ramos (DCMC).
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the Issue bid drawings documents, TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC) Spec. No.: G-3400 Revision: A; For Bid Project No. A15240, June 20th, 2025to identify potential and possible change orders, as well as potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects to be integrated into the PROCORE platform. A call was held with Javier Ignacio from Portosan to coordinate equipment delivery to the Aguirre Site.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: fall protection program to reduce the risk of falls and creating a safer work environment for implementation in the Cambalache project.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - The evaluation of documents under Submittal #RGE-0007 Revision RGE-0007 RG Engineering Safety Manual continues, where the content is analyzed and notes are taken for the client's overall evaluation and changes by the contractor. The following documents were evaluated: Electrical work safety program to identify potential hazards, enforce safe practices, and reduce the risk of accidents for implementation in the Cambalache project.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Drafted a consultation email and diagram to receive feedback from Genera PR (Erick Rocher) regarding the use of a lot for a temporary parking and the environmental implications.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Cambalache project Request for Proposal (RFP) addendums 01,02 & 03 documents to clarify scope of work services and conditions to be implemented in the project.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Procore open submittals status and compared with received information by email form GeneraPR (Herminio Arroyo) and forwarded to Sargent and Lundy (Mike Kucsynski) to complete response for submittal RGE-0002.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed a response for a submittal (RGE-0009) for Quality Control Plan review and comments. Sent comments to Gilberto Sucre (DCMC) for concurrence and implementation.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed potential drawings information discrepancies that may impact pending design activities from general contractor (RG Engineering). This is part of a potential RFI review.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated Cambalache Construction Weekly meeting agenda to capture this week discussion and pending actions to be covered with the project team (Sargent and Lundy, RG Engineering, GeneraPR and DCMC)
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met via phone with Jose Segarra (RG Engineering) to discuss rregarding pending coordination items and RFIs in the project. Met via Phone with Jorge Mercado (DCMC Partners) to touchbase on Safety actions and coordination.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with agenda preparation of Homeca construction meeting and ARG/CERES construction meeting. Working in review of IFC drawing to identify posible change order for Vega Baja site must of drawing has Hold areas that may be impacted in a CO.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management - Meeting and Coordination ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting at Site Vega Baja - Organizer Jose Lopez of DCMC, attendee Carlos Hernandez, Maria Reyes, and Ricardo Lopez of ARG/CERES, Basilio Ramos of Sunset, Jaime Pesquera, Gilberto Soto and Eduardo Rivera of DCMC and Nelson Soler of CDM Smith; meeting to discuss second phase demolition scope of work for Sunset to provide cost estimate to ARG in regard of project activity.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working in reviewing the list of drawing sent by the IFB in the specification versus the IFC drawing sent by S&L, notice that are several drawings are missing from the IFB vs IFC. Send email to Gilberto Sucre of DCMC in regard of email send by Homeca requesting DCMC to confirm the Final Project Closing date certify for the Vega Baja site. Preparing for site visit with contractor Sunset to review demolition site area for second phase.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-initiating the preparatory phase for the upcoming cycle count at the Palo Seco warehouse by reviewing system inventory reports, validating item master records, and confirming assigned bin locations. Task includes staging physical areas for count readiness, ensuring that labeling and storage conditions meet audit requirements, and briefing warehouse personnel on count protocols and documentation standards. These steps are essential to establish a controlled environment and reduce the risk of discrepancies during the execution phase.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco facility, initiates the development of a detailed inventory assessment report to be submitted to Mr. Anthony Vega of Genera PR. The report is structured to consolidate operational findings across multiple warehouse zones, incorporating variance insights, item classification issues, and inventory health indicators. It outlines key deficiencies, highlights stock inconsistencies, and includes actionable recommendations to enhance systemic accuracy and ensure alignment with organizational standards. Locations reviewed included CB 045 through CB 054, BG 040 to BG 080, DH 001 to DH 004, DI 001 to DI 004, DJ 001 to DJ 006, DK 001 to DK 003, DL 001 to DL 006, DM 001 to DM 005, DN 001 to DN 005, DO 001 to DO 006, DQ 01 013, AI 050 to AI 060.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducting a brief morning meeting with Milton Flores, Juan Vallejo from DCMC and key warehouse personnel to review the day’s operational priorities, reinforce safety protocols, and ensure alignment with established cycle count procedures. The session focuses on assigning task responsibilities, clarifying expected outcomes, and addressing any outstanding inventory discrepancies requiring immediate attention. This coordination is essential to maintain accuracy and continuity in daily inventory operations.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11-RFR/RFA Prep & Submission ¦ DR 4339 - Hurricane Maria-Genera Weekly Meeting to brief client on updates and weekly progress with participation from Genera PR: María Sánchez Brás and José Roque; DCMC: Mark Merritt, Esther Rohena, Sheila Torres, Pedro Cabrera, Eisha Mercader, Glorimel Torrado, Rafael Calderón, Saúl Falcón, and Cynthia Ortiz; Honra LLC: Marc Maceira; SM Consulting: Shellsea Maysonet; Integrum: Carlos González and Keylamerari Sierra; Driven: Wallace Rodríguez and Juan Calderón; and from Strider Consulting: Néstor Ortiz, David Candelario and Carlos Iglesias. Meeting was held at Genera's Headquarters, Costa Sur Conference Room.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed cycle count operations for assigned inventory zones by conducting physical item verification, confirming bin-level assignments, and documenting count results in accordance with established protocols. The process included comparing physical quantities against system-reported balances, flagging discrepancies for immediate review, and ensuring traceability through accurate recording of findings. All activities were performed following cycle count procedures to maintain inventory integrity and support audit compliance. Inventory areas inspected during this session spanned from CB 045 through CB 054.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-Performed a recount verification process for previously audited inventory areas at the Palo Seco warehouse. The effort focused on revalidating physical quantities, ensuring consistency with prior cycle count results, and investigating any unresolved discrepancies. The review included validating bin assignment, confirming labeling accuracy, and ensuring that recorded adjustment reflects actual inventory status. Observations were documented to reinforce traceability and confirm alignment with established reconciliation protocols. Locations range from CB 045 through CB 054.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-initiates a targeted variance preview to investigate discrepancies found during previous inventory validations. The process includes auditing transactional records, analyzing movement history, and comparing part number references to validate consistency. Special attention is given to items with repeated deviations to determine root causes and implement corrective measures aimed at stabilizing data accuracy and preventing future inconsistencies. Locations range from CB 045 through CB 054.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Verify that the services billed on invoice PRIN0008436 were indeed requested by Genera and delivered as specified. CPM Invoice 7609, and 91000. PW-9815 FAASt A&E
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Review the Drawing document Discipline Architectural Warehouse on Procore.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Reviewed contractor submittals RGE-0008 and RGE-0008.2 related to employee certifications for the BESS project (PW9510) in Procore. Evaluated documentation for completeness and compliance with project requirements. Drafted internal comments and prepared follow-up correspondence to address missing information and request clarification from RGE.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Reviewed contractor submittals RGE-0009 for the BESS project (PW9510) in Procore. Evaluated documentation for completeness and compliance with project requirements. Drafted internal comments and prepared follow-up correspondence to address missing information and request clarification from RGE.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- 4339_9510 BESS Review emails regarding RGE's Quality Control Plan and Andrés Concepción DCMC's comments on the Quality Control Plan submitted by RGE.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents reviewed all submittals opened and sent emails (#004 & #006) to see if they could be closed.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Reviewed all RFi's opened and found 3 open ( Rfi # 004, Rfi # 006 & Rfi 007). Also revised punch list all items opened and found only 2 items opened. Item # 34 item #32 remained open, so sent emails to touch base with Homeca Recyclers.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractor ARG for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started site visit with Sunset contractor Basilio Ramos for estimate on the demolition site.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AI050 to AI060
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AI050 to AI060
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AI050 to AI060
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AI050 to AI060
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AI050 to AI060
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 | 152 | 418 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BC 00 001 to BC 00 007; BD 00 001 to BD 00 007 and CS 00 001 to CS 00 009.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BC 00 001 to BC 00 007; BD 00 001 to BD 00 007 and CS 00 001 to CS 00 009.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 | 152 | 114 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BC 00 001 to BC 00 007; BD 00 001 to BD 00 007 and CS 00 001 to CS 00 009.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BG 040 to BG 080
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BG 040 to BG 080 RECOUNT LIST #1277/1290/1291
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria; Aguirre-Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BG040 TO BG 080 LIST # 1275/1276/1277/1278/1279/86/1287/1288/1289
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BG 040 to BG 080 at the Aguirre warehouse to initiate the cycle counts.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Provide assistance to the Vega Baja project team for the uploading and publishing of Technical Specifications from the Issued for Construction Package. Begin initial QA/QC on the received documents.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/GEN 01 Procurement (RFPs - RFQs) Ensure existing documents are reviewed_ stored_archived in an organized & controlled manner/ensure information is titled correctly & readily accessible for the project team/Aguirre BESS Project review all RFP & RFQ Data for accuracy
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/GEN 01 Procurement (RFPs) Cambalache BESS/Vega Baja BESS Ensure Documents are created, reviewed, distributed, stored & archived in an organized & controlled manner/ensure information is organized & readily accessible for the project team
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review contractual agreements for the Vega Baja demolition phase awarded to HOMECA to verify contractor's certifications for payment documentation compared to requirements in the General Conditions for contractor's invoicing.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Peakers Weekly Meeting hosted by Rafael Pabon (CDM Smith) including Design Team staff Mike Kuzcynski (S&L), Lauren Wells (Lemoine), Rafael Calderon, Abraham Velazquez (all DCMC), Enrique Laya (CDM Smith), German Nunez (Genera); discussing weekly open topics for the Peakers Projects: Status for ongoing RFPs, tracking Procore SOPs publishing, execution on field procedures discussed with the design team, and financials overview among others.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue with the QA/QC process for the Vega Baja Technical Specifications package; reviewing documents formatting and sections inside the specs.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the weekly reports from the Warehouse Inventories to understand the potential implementation on Procore.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Write and create an email with the letter for the signature of the Genera PR team, Jorge Bracero, whose purpose is to formalize the process to request authorization from the municipality of Vega Baja in order to impact the municipality's summer camps to bring them the Genera educational project and educate these school populations with information from the BESS
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.25 | 139 | 34.75 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Make edits to the BESS and Peakers https://genera-pr.com/bess_peakers website. These tasks include correcting spelling of the website and sending them to the Genera PR team, Alex Valdés. A screenshot of the repairs that needed to be made was included, along with instructions on the arrangements that needed to be made.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Continue to edit the Costa Sur fact sheet with information related to the BESS project and include the information from Peakers. These tasks included organizing the information, adjusting it so that it is understood according to the narrative we have implemented, including the graphs in the document as well as integrating data specifically related to the Peakers, researching the subject to be able to answer the questions that the communities might have, including the number of megawatts that would be integrated into this site
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.75 | 139 | 243.25 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Follow-up to the labeling of the sites. These tasks included searching the emails for the status of the email chain related to this management, confirming which of the site managers has sent the measurements of their site to complete the labeling task and being able to send the information to the Genera PR team, Rafael Rodríguez Emma, who must formally make the request with the KROMA agency. Similarly, these tasks included writing an email to the DCMC Partners team, Frances Vallejo and Gilberto Sucre to know the update of this project and, likewise, writing an email to the Genera PR team, Rafael Rodríguez Emma, who should have all the information on his side on Monday. Eventually, verify the information received to follow up on it during the Corporate Affairs Team Catch up meeting, which is held with the Genera PR team: Ivan Baez, Jorge Bracero and Rafael Rodriguez Emma.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Coordinate and schedule a meeting with the CDM Smith team Rafael Pabon and Manuely Concepción together with the Genera PR team, Jorge Bracero to discuss doubts, recent information, logistics. As part of this task, I contacted the Genera team and CDM Smith to explain the reasons why we wanted to meet, agree on a date and time and schedule the meeting. Also, in preparation for this meeting, I wrote down the doubts that I needed to answer and wrote them down to have them as a reference.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- PREPA Genera ¦ Meeting about the Peakers update with DCMC Partners Team: Frances Vallejo Rosich, Luis Roman, D'Alexzander González, Rafael Calderón, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey and Abraham Velazquez. In the meeting was the Genera PR Team: German Nuñez, Joaquín A Quinoy, Ricardo Pallens, Fernando Ortiz Meléndez, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczynski, Miguel del Valle and Nelson Rosado. In this meeting we discussed issues related to the update of the Peaker's project. The team offered input on the steps they have taken regarding the project and the pending visits they have at sites such as Jobos, which will be visiting on Wednesday to learn in depth about the details of the project. Likewise, the meeting discussed the works in progress and the details related to Vieques and Culebra in relation to the installation, design and equipment.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Continue to update the Community Engagement Work Plan with the latest details related to task-related data to facilitate its execution. This task was based on validating the information in the document. This task included updating the information in the Support Community Manager with meetings with Stakeholders from community leaders to government officials' section.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 | 139 | 104.25 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Update the internal community relations report to include community engagement efforts related to the BESS project in Vega Baja and Arecibo, with the purpose of connecting with the community and strengthening relationships with external audiences. The tasks included updating the strategies that will be implemented in accordance with the Vega Baja and Arecibo Community Relations Plan developed by Genera PR. Similarly, actions to promote their active participation throughout the dismantling process were included.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 139 | 34.75 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Coordinate visits to the next sites that we will be doing this Friday. These tasks included communicating with Raissa Borges Almodovar, from the DCMC Partners team, and with Jorge Bracero from the Genera team to visit the sites that we are missing: Yabucoa and Daguao. Similarly, the visit was scheduled in the calendar
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Begin updating my weekly community relations plan. These tasks included editing my calendar with the pending tasks and tactics that should be included in the calendar, identifying tasks that should be included in the calendar, and integrating a brief description to organize the content.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line of equipment planning, mechanical and commissioning planning (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 134 | 268 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 17 pages.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 134 | 402 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 30 pages.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Conducted a safety-focused review of the Transportation and Storage Guidelines for the Tesla Megapack batteries, with emphasis on identifying potential hazards during handling, transit, and on-site storage. The evaluation included safety requirements related to temperature control, battery module stability, packaging integrity, and procedures to prevent tipping, short circuits, or fire risks. Purpose of the review is to ensure compliance with Genera's HSE protocols and regulatory safety standards for lithium-ion battery systems during transport and storage.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Take and completed Cyber Security Assignment 2025 Lemoine Company New Hire Workshop, given the Lemoine IT Security team. Start Evaluation contractor QC manual (RG Engineering.) included Site Work requirements, regulatory safety standards for construction process used in the project.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project logic sequence of equipment planning, mechanical, electrical works and commissioning planning (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Commenced updating the Peakers financial status in Power BI as part of the June monthly report, aiming to improve the clarity and precision of visualized data regarding budget modifications, actual expenditures, and projected remaining costs.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue updating BESS & Peakers Payment Milestones in Power BI as part of the June monthly report, to improve the clarity and precision of visualized data regarding budget modifications, actual expenditures, and projected remaining costs and risks.
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Nelson Rosado (S&L), D'Alexander Gonzalez (DCMC), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Enrique Laya (CDM Smith), Abraham Velazquez (DCMC), Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Sheila Torres (DCMC), Paola Arroyo (DCMC), Lauren Wells, (Lemoine)
2025-07-07 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 122 | 244 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue updating the Peakers financial status in Power BI as part of the June monthly report, aiming to improve the clarity and precision of visualized data regarding budget modifications, actual expenditures, and projected remaining costs.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 1626 | 1626 | 1626 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Airfare (Basic Economy) for Foster Veazey's trip from Mobile, AL to San Juan, PR. Trip was following the 4th of July travel weekend, which likely increased the cost from the usual rate.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondence items for user support.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 security projects meeting, discussed protocols for all vendors and workers that will be working at the Peaker sites German Núñez, GENERA Jean Pierre Menay DCMC Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 PMO meeting discussed and reviewed each project status and concerns. participated in the meeting Gilberto Sucre DCMC Frances Vallejo Rosich DCMC Rafael Pabon, CDM Smith Carlos Palomares CDM Smith
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 reviewed submittals and specifications for the new equipment due to be released this year documents to be captured and organized in procore
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre - Jose Lopez - DCMC reported a PREPA IT project had started on site inside the BESS footprint. A foundation form work for the communication building had already been placed, with a porto- john and future 150 ft high tower to be installed. A location map was requested and pictures to provide to CDM Smith, Sargent & Lundy and Genera Management. Conversation between Jose Lopez & Gilberto Sucre - DCMC, Gabriel Perez - CDM Smith, & Jesus Cintron - Genera.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Security Projects Meeting led by Digno Cartagena - Genera presented Security Measures at Plant Sites identifying restricted areas and special requirement to work at the sites. FSO role was highlighted at each facility. Genera: Digno Cartagena, Nelson Median, Francsico Mari, Luis Torres CSA Group: Franklyn Colmenares DCMC: Jose Lopez, Eduardo Rivera, Andres Concepcion, Gabriel Morales, Carlos Rodriguez & Gilberto Sucre.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 225 | 281.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO BESS & Picker's Update meeting with Frances Vallejo and Foster Veasey - DCMC, Program Update was discussed focused on Procurement & Legal Roles on contract and funding restrictions due to IFB documentation. Client's operations and financial challenges were highlighted. Gilberto Sucre DCMC was the third person in the meeting.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 225 | 281.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Weekly Construction Meeting led by Andres Concepcion - DCMC. Participants: Herminio Arroyo - Genera Wilfredo Sierra- Sargent & Lundy Gilberto Sucre, Luis Duque, Raissa Borgess - DCMC Jose Segarra, Harry Velazquez - RG Engineering Gabriel Perez - DCMC Franklyn Colmenares - CSA Group
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Frances Vallejo - DCMC to discuss PMO performance mainly only the Procurement Support effort to Genera and required next steps to improve performance. Project Status, Genera's needs and DCMC support were discussed. France Vallejo -and Gilberto Sucre - DCMC
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria LT Automation Coordination with BESS. Last minute meeting was scheduled to discuss what had happened in the morning at Aguirre with the construction start of the telecommunications facility. Led by Mike Kuczynski of Sargent & Lundy and Gabriel Perez - CDM, design coordination and coordinates had been presented to PREPA but they did not share the information with the contractor LT Automation Inc. It was agreed to exchange plans from both sides to identify other potential interferences at other Genera Sites. Present; Mike Kuczynski, Wilfredo Sierra - Sargent & Lundy, Gabriel Perez - CDM Smith, Jose Lopez & Gilberto Sucre - DCMC, Hector Vazquez, Carlos Irizarry - LT Automation Inc.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One on one meeting Gabriel Perez - CDM Smith and Gilberto Sucre DCMC to discuss: ARG Ceres -Tariffs Clause Sargent & Lundy - Performance Invoice Audit roles requested by Genera Aguirre and Costa Sur Contract Stall holding submission for approval. Genera's Needs.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO met with Cynthia Ortiz DCMC and Franklyn Colmenares to evaluate Genera's and DCMC Roles in the current Federal Funded Projects Execution to date for all awarded and in process RFP's for the BESS and Peaker's Programs.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Program Jesus Cintron request our presence to provide us with an update of the current project status and requested from us to deal with a main challenge with Sargent & Lundy Design Status and Budget. A follow up meeting was set to meet with TRC firm who will be helping with monitoring & auditing the design firm. Present: Gabriel Perez - CDM Smith, Jesus Cintron - Genera & Gilberto Sucre - DCMC
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up Meeting - Led by Frances Vallejo to review updates of Staffing Plan & New Hires, Procore Financial Implementation, Construction Project Status, PMO award, Procurement Process to support Site Office Facilities. Mike Merritt, Mark Merritt, Frances Vallejo, Anneilia Holton, Lauren Wells, Ada Diaz, Barry Scanlon & Gilberto Sucre - All DCMC.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Billable-Project Management ¦ DR 4339 - Meetings with DCMC on-site personnel to review Project Status and Roles and Responsibilities. Attendees were Foster Veazey, Gilberto Sucre, Frances Vallejo.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Docusign information for Procore.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on researching ideas for supply tracking in Procore.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore analytics dashboards for RFI and Submittals.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Frances Vallejo (DCMC), Carolyn Baez (DCMC), Jean Menay (DCMC) to discuss Materials and Supply Trailers.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on research for Procore Action Plans and how we might can utilize them for documents and other items.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence items for Procore for dashboards.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore items for documents tool.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore SOP document for Lauren Kennedy (Procore).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore forms with comments from users for modifications.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 222.19 | 222.19 | 222.19 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Hotel Lodging for Foster Veazey for 1 night in San Juan, PR ($158.84 lodging, $14.30 Government Tax - Rooms, $45.00 Destination Fee, $4.05 Government Tax Destination Fee).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Finalized updates to the Power Production and Fuels Consumption master report and provided the completed version to Jan Rodriguez from Genera PR for distribution, ensuring alignment with previously validated data and reporting requirements.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Hurricane Maria: Meeting with Osvaldo de Jesus (GENERA) about Genera projects Status and EHS topics in the projects. Review the EHS documentation submit for RGE by Procore about Cambalache project. Review in Procore documentation submit by ARG about EHS. Meeting about Vega Baja project Status with Eduardo Rivera, Jaime Pesquera (DCMC), Carirma Sanchez, Eduardo Ramos (HOMECA). Meeting with Andres Concepcion, Luis Duque (DCMC) and RGE contractor's co-workers about Cambalache Genera Site.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 184 | 138 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR4339 Held a follow-up meeting with Frances Vallejo, Jean P. Menay, and Carolyn Báez-Nieves (DCMC) to discuss the structure and organization of the Excel-based tracker for managing material and supply needs under the Genera PR project. It was agreed that the tracker will be organized using separate tabs for each supplier, enabling more precise tracking and control of purchases, deliveries, and inventory levels. This structure is intended to enhance clarity, streamline data entry, and support accurate expense monitoring across all vendor-related transactions.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR4339Review and verify the adequacy and compliance of the Health and Safety documentation for Cambalache Genera Site in relation to DR4339 FEMA requirements and Genera PR protocols. Activities Completed: Evaluated current Job Hazard Analysis (JHA), Emergency Response Plan (ERP), and Lockout/Tagout (LOTO) procedures. Cross-checked documents with OSHA 29 CFR 1910 standards and local Puerto Rico regulations. Health and Safety Modules– Luz Ramirez (DCMC Yabucoa Genera Site) Objective: Deliver comprehensive modules on updated Health and Safety protocols, ensuring standardization across all Genera PR locations. and facilitate the visit of Beta Electric representatives for site assessment and project alignment. Visitors: Eng. Asdrubal Morales and Alberto (Asere) need to verify the power transformer. Delivered to Gabriel Morales (DCMC) the PPE necessary for visitors in Yabucoa Genera Site Projects.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Hurricane Maria: Security meeting with Digno Cartagena Security Manager (Genera) and Nelson Medina (Genera), Gilberto Sucre, Andres Concepcion (DCMC) about Security Genera all Sites Topics.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 184 | 46 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Held a coordination meeting via MS Teams with Lauren Wells, Jean P. Menay, Frances Vallejo, and Carolyn Báez-Nieves (DCMC) to discuss the management and tracking of material and supply needs across sites under the Genera PR project. Key discussion points included the development and maintenance of a centralized tracker to monitor supply requirements, reviewing and organizing the current supplier list, and validating related invoices. It was agreed that a dedicated tab would be added to the tracker for materials and office equipment, serving as a running inventory of items requiring monthly replenishment. Additionally, the team discussed the possibility of creating and managing the tracker within the Procore platform to enhance accessibility, enable real-time updates, and integrate with project documentation. The tracker will be maintained regularly to ensure proper expense allocation to Genera and to support accurate reporting and budget compliance.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review June monthly report for BESS and Peaker projects to send to client.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Internal in person meeting with Foster Veazey (Lemoine) and Gilberto Sucre (DCMC) to discuss BESS and Procurement status, procurement and legal contract issues.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended in person meeting with Gilberto Sucre (DCMC) to catch up on organization for the PMO, S&L meeting, coordination with procurement and safety meeting coordination.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Held a coordination meeting via MS Teams with Lauren Wells, Jean P. Menay, Frances Vallejo, and Carolyn Báez-Nieves (DCMC) to discuss the management and tracking of material and supply needs across sites under the Genera PR project. Key discussion points included the development and maintenance of a centralized tracker to monitor supply requirements, reviewing and organizing the current supplier list, and validating related invoices. It was agreed that a dedicated tab would be added to the tracker for materials and office equipment, serving as a running inventory of items requiring monthly replenishment. Additionally, the team discussed the possibility of creating and managing the tracker within the Procore platform to enhance accessibility, enable real-time updates, and integrate with project documentation. The tracker will be maintained regularly to ensure proper expense allocation to Genera and to support accurate reporting and budget compliance.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended internal Teams PMO catch up call with PMO leadership to discuss staffing update, Procore financial status, material purchasing status, and BESS project status. Participants: Gilberto Sucre (DCMC) and other DCMC participants.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and edit the material and supply equipment tracker to include all items related to cleaning supplies and office supplies for trailer sites.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 234319 - Began reviewing the Procurement Memorandum for the Legal Services RFP. Focused on editing and refining Sections I through IV, including the Background, RFP Publication, Proponent Overview, and Evaluation Committee descriptions. Verified accuracy, improved clarity and alignment with procurement documentation standards. This activity supports grant oversight and documentation as part of the broader effort to maintain a compliant and audit-ready procurement record.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 221016 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - RFP 234319 - Finalized reviewing and editing the Procurement Memorandum for the Legal Services RFP, focusing on Sections V through VII, which include the Proposal Evaluation, Conclusion, and Final Recommendations. Verified factual accuracy, refined narrative structure, and ensured clarity and consistency throughout the document. Aligned content with procurement documentation standards and FEMA Public Assistance (PA) grant management requirements. This effort forms part of the broader administrative activities necessary for grant oversight and compliance, contributing to a complete, defensible, and audit-ready procurement record.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started site visit Luma Cesar Sanchez to verify underground utilities. Took photos of the field and uploaded to Procore requested by Jean Menay from DCMC. Assisted meeting with Homeca Carirma Sánchez and DCMC team Eduardo Rivera, Jaime Pesquera. Assisted meeting with Carlos Hernandez (ARG).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Workshop was provided via Teams with Jean P. Menay (Risk and Safety Manager) on Genera General Health and Safety Policy. This policy focuses on the fundamental concepts of the following programs: Fall Prevention, Lockout/Tagout (LOTO), Safety Data Sheets (SDS), Confined Spaces, Electrical Safety, and the Contractor Safety Program.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 | 167 | 542.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Kick off site meeting with the Yabucoa site with Site Manager Gabriel Morales (DCMC) to discuss the scope of service for the Battery Energy Storage System (BESS). The objective was to ensure that all parties clearly understood the project objectives, task, responsibilities, and deliverables to facilitate an efficient construction process.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I began the Procore module program for the following modules: -Action Plan: Create an Action Plan, Perform an Action Plan, and Sign an Action Plan -Admin: Add trades to the Company Level Admin tool, Company Level Action Plan Configurations, configure tasks setting in the Company Level Admin tool, Configure Project Level Work Break Town Structure, create a form template in the Company Level Admin tool, Create Company Level, Create meeting template in the Company Level Admin tool, Create new configurate field sets in the Company Level Admin tool, Create observation template in the Company Level Admin tool, Create Punch item template in the Company Level Admin tool, and Edit and Manage configurable field sets in the Company Level Admin tool.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting with Francisco Mari (Genera PR) First Security Officer, and José M López-Linares (DCMC) to go over the Central Aguirre Complex evacuation Plan and to Coordinate the activation of the Contractor ID electronic Access.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -AGUIRRE BESS PROJECT. A walk-through was conducted with Carlos López, Luis Moctezuma, and Sunem Martinez (DCMC) to identify existing project general arrangement line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects. We discovered that another contractor is building a structure for the IT department, which will create a clash with the proposed BESS layout. It was immediately informed to Gilberto Sucre (DCMC)
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane María - AGUIRRE BESS PROJECT. I was an observer as part of the internal workshop at the meeting chaired by Carlos de Jesus (DCMC) Costa Sur, with Carlos Palomares CDM Smith, Jose Segarra RG Engineering, Mike Kuczynski Sargent & Lundy, and others. Regarding the Construction Schedule Meeting.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane María - AGUIRRE BESS PROJECT. Meeting with Carlos de Jesus (DCMC) Construction Schedule Costa Sur, regarding the work we are going to carry out, Priority updates, Process improvement, Internal workshop.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -AGUIRRE BESS PROJECT. I had a meeting with José Colón (DCMC) and Carlos López (DCMC) to discuss the status of the office supply for the job site office.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 471 to 495. Among the topics read were power distribution panel (technical requirements, panelboards details, circuit breakers details, fusible switches, corrosion protection), facility lightning protection (installation), lighting (system description, design requirements, illumination levels)
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 496 to 530. Among the topics read were lighting (temporary system, wiring, for emergency), site clearing and grubbing (construction survey, disposal of material, fire responsibility, stream pollution), non-woven geotextiles (anchoring pin, packaging and documentation requirements, acceptance and storage at project site, different ways for installation, earthwork (survey, fill material, topsoil, demolition, excavation, disposal excess material, compaction).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Assisted to Construction Weekly Meeting with some participants that are Ida Ramirez (ARG/CERES JV), Herminio Arroyo (Genera), Gabriel Perez (CDM Smith), and others. Among the topics discussed were the general contractor have to submit some documentation, discuss some RFI and submittals pending and open.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Assisted to Construction Weekly Meeting with some participants that are Jose Segarra (RG Engineering), Herminio Arroyo (Genera), Gabriel Perez (CDM Smith), and others. Among the topics discussed were coordinate a meeting to discuss the storage and moving, follow up the status of the permits and periodic inspections, discussed some things of design like fire protection.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Costa Sur - BESS - Hurricane Maria - Conducted a safety management review of the civil and structural technical specifications, focusing on how design requirements may influence future construction risk. Assessed specifications related to excavation, concrete work, and material staging from a planning and safety coordination perspective. Documented recommendations for pre-task risk identification and control measures in line with ANSI and OSHA guidelines.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Costa Sur - BESS - Hurricane Maria - Reviewed Appendix J – Health, Safety, and Environmental Policies to verify alignment with corporate safety expectations. The analysis emphasized risk management procedures, safety leadership structure, emergency planning, and environmental stewardship. This review is critical during the documentation phase to confirm that all safety management systems meet OSHA, EPA, and Puerto Rico regulatory requirements before mobilization.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal review of Sections 310.1 to 310.3, focusing on column stiffener plate installation, trolley beam alignment, and the girt system. The stiffeners, being shipped loose, will require field welding at beam and girder joints, demanding coordination of materials and skilled labor. Trolley beam splices must be aligned with high precision to ensure seamless trolley travel, calling for both pre-erection measurements and verification post-installation. The girt system was thoroughly reviewed, particularly the erection sequence from ground to roof, ensuring siding can proceed without interruption. Framing tolerances around doors, windows, and louvers—ranging from ±1/16 inch to ±1/4 inch—highlight the need for accurate field layouts and tightly controlled structural alignment. Weekly Schedule meeting Costa Sur lead by Carlos Dejesus DCMC, on updates to construction scheduling changes.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal review of Section 310.4, which details the setting and grouting procedures for column baseplates. Each step—from removing sleeve tops and cleaning concrete surfaces to aligning plates with paraffin-coated shims—is precisely defined. The exclusion of leveling nuts and the emphasis on using leveling bolts, screws, or plates reinforces a strict control of elevation and surface finish. After grout has cured, all temporary supports must be removed and voids filled with matching grout, adding complexity to post-placement inspections. This section will require coordination between structural teams, concrete crews, and quality control personnel to ensure specifications from Section 036241 are fully met.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with the Yabucoa site new Safety Officer Luz Ramirez and Jean Pierre Menay (DCMC) to discuss the GENERA safety workshop to comply with the site requirements.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue reviewing Section 260520 "Control and Instrumentation Cable" and Section 260526 "Grounding and Bonding for Electrical Systems"in the Scope of Services for Technical Specification Number G-3300 for BESS General Work Contract (GWC) that will be issued for bid.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Kick Off site meeting with the Yabucoa site new Safety Officer Luz Ramirez (DCMC) to discuss the Scope of Service of the BATTERY ENERGY STORAGE SYSTEM (BESS) to ensure all parties understand the project's goals, tasks, responsibilities and deliverables to assure efficient construction process.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Luz Ramirez, the new safety officer for the Yabucoa Site BESS project fpr DCMC partners, to introduce her to Procore system and company requirements.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur BESS Continue review of Specification No. G-3200 was initiated to ensure alignment with current industry standards, project-specific requirements, and regulatory compliance. The focus was on Divisions 07 (Thermal & Moisture Protection) through 22 (Plumbing), encompassing general administrative protocols, product requirements, and material specifications related.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur BESS Continue review of Specification No. G-3200 was initiated to ensure alignment with current industry standards, project-specific requirements, and regulatory compliance. The focus was on Divisions 23 (Heating Ventilating) through 33 (Utilities), encompassing general administrative protocols, product requirements, and material specifications related.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre Finishing Reading and review ATTACHMENT J HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES Section of Enviromental Provision. Reading the process and practices of a Safety Demolition Plan for a Metal Structure: 1. Project Scope and Pre-Demolition Assessment, 2. Site Preparation and Safety Zoning, 3. Equipment and PPE Requirements, 4. Demolition Execution (Step-by-Step), 5. Dust, Noise, and Environmental Controls, 6. Emergency Preparedness and Incident Response, 7. Final Clearance and Demobilization.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We work in the specific standards for access to Aguirre Power Plant this in order to guide our contractors: Access to the Aguirre Power Plant requires strict adherence to specific safety standards established to protect personnel and maintain operational integrity. Before entry, all individuals must complete a mandatory safety orientation covering site-specific hazards, emergency procedures, and PPE (Personal Protective Equipment) requirements. Standard PPE includes a hard hat, safety glasses, flame-resistant clothing, high-visibility vest, gloves, and steel-toe boots. Additionally, all personnel must carry valid site access credentials and complete any required permits or documentation for the scope of work to be performed. Contractors are subject to random safety audits and must participate in daily toolbox talks to remain informed on current safety concerns and operational updates. Compliance with LOTO (Lockout/Tagout) procedures, confined space entry protocols, and hot work permits is strictly enforced. These measures ensure that everyone working within the plant maintains a high level of situational awareness and contributes to a safe and efficient work environment.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS Project Meeting with S&L, Kuczynski, Mike, Robert Muhler, and (CDM Smith), Gabriel Perez, Franklyn Colmenares, (CDMSmith), Andres Concepcion, Gilberto Sucre from DCMC Partners to discuss the BESS Issue For Construction design drawings delivery status. The Aguirre BESS project's bid drawings delivery date has been delayed by one week to the first week of August.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Carlos López, Luis Moctezuma, and Sunem Martinez (DCMC) to identify existing project general arrangement line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects. We discovered that another contractor is building a structure for the IT department, which will create a clash with the proposed BESS layout. It was immediately informed to Gilberto Sucre (DCMC)
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria, Meeting with Digno Cartagena, Security Manager from Genera PR and All DCMC Site Managers, Carlos Rodríguez, Andres Concepcion, and Gabriel T. Morales, also Jean Pier Menay, Gilberto Sucre, and Aguirre First Security Officer Francisco Marí. The meeting was held via Team, and the presentation explained all the Safety and Security requirements for the Cambalache Job Site and the Mayaguez site, along with a brief description of the restricted and safety areas of the plant that required the TWIC Card. It was also discussed that the general laborers' entrance logistics involved in the project start, and also explained that the Security Staff from General PR will implement a random check for non-authorized personnel in search of any illegal drugs, firearms, and unauthorized possession of tools.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Aguirre BESS Project - Joined coordination meeting with Carlos López, Luis Moctezuma, and Sunem Martínez (DCMC) to review the two-week look-ahead schedule, confirm sequencing of critical path activities, and address any inter-team communication gaps impacting execution timelines.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Aguirre BESS job site. Daily project coordination and project management. Project Documents Overview and Analyzing the Issue for Bid, TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC), Spec. No.: G-3400, Revision: A; For Bid, Project No. A15240, dated June 20th, 2025, Documents' Status in Procore. Loading
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of RFP 4826 Annex K Civil and Structural. The specifications of the stormwater pond areas are verified for the knowledge and development of environmental protection at the beginning of the project.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Weekly meeting of the BESS Cambalache project with the team working for the Cambalache site, Andres Concepción (DCMC), Luis Damudt (DCMC)
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of RFP 4826 Exhibit L (Pipe Relocation) and exhibit M (Electrical Engineering & Design)
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review of existing contractual documentation for the Cambalache project. An evaluation of the points described in Attachment J is carried out as a compliance guide.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated meeting agenda and reviewed RFI and submittal status to present on the Cambalache Weekly Meeting to discuss project actions and pending items.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Digno Cartagena, Nelson Rivera (GeneraPR), Jean Pierre Menay (DCMC Partners) to discuss GeneraPR security policies and process. Discussed regarding security requirements, rules and access controls for the construction contractors.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Robert Molner (Sargent and Lundy) and CSAGroup (Franklyn Colmenares) to discuss regarding the weekly design updates meeting to review pending design activities to finish the BESS project design.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project design drawings to identify pending and missing details to be developed and provided by project designer (Sargent and Lundy).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Prepared correspondence and narrative for a environmental consultation to GeneraPR regarding sensitive areas to be used as a Parking for the construction contractor. Sent to Erick Rocher (Genera PR).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Followed up with meeting minutes for the Cambalache Weekly Meeting and followed up with actions items discussed in the meeting ti ensure all pending task keep progress.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted meeting with project team: RG Engineering (Jose Segarra), Sargent and Lundy (Robert Molner), CDM Smith (Gabriel Perez), CSA Group (Franklyn Colmenares) to follow up on weekly updates and project pending actions. Technical Discussion occurred as well regarding a design proposal for an Levee access road.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with minutes notes of ARG/CERES construction meeting. Reviewing the draft project schedule send by Ida Ramirez of ARG for Vega Baja site. Review the attachment I-1 related to Final Completion send by Eduardo Ramos of Homeca for review, documents were requested to be forward to Gabriel Perez of CDM Smith and Franklyn Colmenares of CSA. Continue reviewing the IFC drawing versus IFB for identify posible change orders.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Homeca project closing for Vega Baja Site. Preparing agenda for Homeca construction meeting. Preparing agenda for ARG/CERES construction meeting. Reviewing email in regard of Homeca project closing.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project construction weekly meeting Phase II. ARFG/CERES Carlos Hernandez, Ricardo Lopez and Ida Ramirez; DCMC Jaime Pesquera, Gilberto Soto, Silvia Franco, Raissa Borges and Eduardo Rivera, CDM Smith Nelson Soler, CSA Franklyn Colmenares, S&L Wilfredo Sierra - Meeting to provide status for second phase construction of Vega Baja BESS project, coordinate with ARG documents to be submitted as part for the new construction and ARG provide status of RFI's. It was discussed with S&L the urgent need to close all RFI's.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with minutes notes taken form ARG/CERES construction meeting.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with minutes notes of Homeca meeting. Add an attachment J file for HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES to ARG/CERES agenda meeting. Reviewing electrical IFC drawing of second phase to identify posible change orders.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting with Genera Digno Cartagena as organizer meeting is addressed to all site manager of DCMC to discuss Facility Security of Genera Installation of all plant site must be incompliance with security requirement for Genera safety department and FSO (Facility Security Officer.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project weekly meeting to review project status. Homeca Carirma Sanchez and Eduardo Ramos; DCMC Eduardo Rivera, Enrique Laya of CDM Smith, and Manuely Concepcion. Meeting to discuss final deliver of pending items for project closing, Homeca has provided de certification #3 and will provide a draft and schedule for certification #4, they also have submitted the as built drawing with comments for DCMC to review, they will send today the Final Completion documents for the VB project. Site visit of Cesar Sanchez of Luma to verify underground utilities at site Nelson Soler of CDM Smith, Jaime Pesquera and Gilberto Soto of DCMC was attendee the visit.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused variance analysis to investigate discrepancies identified during previous inventory validation efforts at Palo Seco warehouse. The review involved auditing transactional data, evaluating part movement logs, and cross-referencing part numbers to ensure alignment and consistency. These efforts support long term data integrity and aim to minimize future inconsistencies. The scope of this activity covered inventory locations from CB 055 through CB 066.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a meeting with my warehouse team Mr. Juan Vallejo, Mr. Hernan Machado and Mr. Milton Flores from DCMC, to emphasize the importance of maintaining a safe work environment and the consistent use of appropiate personal protective equipment (PPE). During the discussion, we also reviewed key operational processes and reinforced the requirement for all personnel to accurately log their daily work hours in the system, as part of our commitment to accountability and procedural compliance.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a recount verification process for previously audited inventory areas at the Palo Seco warehouse. The review focused on revalidating physical quantities, ensuring alignment with prior cycle count results, and addressing any outstanding discrepancies. Key task included confirming bin assignments, verifying labeling accuracy, and ensuring recorded adjustments accurately reflect the current inventory status. All observations were documented to support traceability and compliance with establish reconciliation protocols. The scope of this activity covered inventory locations from CB 055 through CB 066.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco facility, began drafting a comprehensive inventory evaluation report intended for submission to Mr. Anthony Vega of Genera PR. The report consolidates key operational observations across various warehouse zones, with a focus on variance trends, item categorization challenges, and inventory reliability metrics. It identifies critical gaps, highlights inventory discrepancies, and provides targeted recommendations aimed at improving systemic accuracy and ensuring alignment with organizational expectations. The reviewed included inventory locations CB 055 to CB 066, BG 080 to BG 136, GA 007 to GA 009, BC 001 to BC 007, BD 001 to BD 007, CS 001 to CS 009.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle count operations for designated inventory zones at the Palo Seco warehouse, focusing on physical item verification, bin location validation, and accurate documentation of count results in accordance with established protocolos. The process involved comparing physical stock quantities with system reported balances, identifying discrepancies for prompt resolution, and ensuring traceability through detailed recording of all findings. Activities were executed in alignment with cycle count procedures to uphold inventory accuracy and support audit compliance. The scope of this session included inventory locations ranging from CB 055 through CB 066.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-commenced the preparatory phase for the upcoming cycle count at the Palo Seco warehouse. Activities included reviewing system generated inventory reports, validating item master data, and confirming bin location assignments, specifically covering locations CB 055 through CB 066. Preparations also involved staging physical areas for count readiness, verifying labeling accuracy, and ensuring storage conditions complied with audit standards.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails Cambalache BESS - Temp Parking for Contractors Environmental Approval.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, Review the Drawing document BESS Platform Civil Drawing on Procore.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed architectural drawing sets uploaded to Procore for the Cambalache BESS project (PW9510), focusing on the proposed new parking lot layout and underground distribution piping. Evaluated design elements in the context of applicable local construction codes, site development guidelines, and federal environmental policies. Identified potential permitting considerations and compliance issues, and prepared internal notes to support discussion with regulatory and design teams.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Construction Weekly Discussion on fire protection design and Levy Access Road proposal update with Gilberto Sucre, Frances Vallejo, Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly Vega Baja BESS Phase II - Construction Meeting with Carlos Hernandez from (ARG/CERES,) Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith) and went over Project Documents Overview and analyzing documents status in the Procore platform and all the punch list items that are closed.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly construction meeting with Homeca Recyclers Carirma Sanchez & Eduardo Vera, also Eduardo Ramos, Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith) and went over project closing documents overview. Analyzing documents status in the Procore platform and all the punch list items that are now closed.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started site visit Luma Cesar Sanchez to verify underground utilities. Took photos of the field and uploaded to Procore requested by Jean Menay from DCMC.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria; Aguirre-Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BG 080 TO BG 136 LIST # 1292/1293/1297/1298/1299
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GA007 to GA009
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GA007 to GA009
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GA007 to GA009
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GA007 to GA009
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GA007 to GA009
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BC 00 001 to BC 00 007 ; BD 00 001 to BD 00 007 and CS 00 001 to CS 00 009.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BC 00 001 to BC 00 007 ; BD 00 001 to BD 00 007 and CS 00 001 to CS 00 009.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BC 00 001 to BC 00 007 ; BD 00 001 to BD 00 007 and CS 00 001 to CS 00 009.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BG 080 to BG 136 at the Aguirre warehouse to initiate the cycle counts.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BG 080 to BG 136
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BG 080 to BG 136, list # 1298/1299 RECOUNT LIST #1300
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue with the QA/QC process for the Vega Baja Technical Specifications package. Identifying omissions required by Procore to perform features at its maximum potential, saving administrative time for the project.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/ Continuation of all BESS projects review all RFP & RFQ data for accuracy to make readily accessible and available for project team/RG & GE Data Management for Peakers Jobos_Daguao_Yabucoa review & process
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/ Continuation of Cambalache BESS project review all RFP & RFQ data in project folders for accuracy to make readily accessible and available for project teams
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Cambalache Project Weekly Meeting hosted by Andres Concepcion (DCMC) and joined by Gilberto Sucre and Luis Duque (DCMC), Gabriel Perez (CDM Smith), Franklyn Colmenares (CSA), Robert Molner (S&L), Jose Segarra (RGE), and other team staff. Discussed preliminary design shop drawings for potential changes on contract, discussion of Value Engineering evaluation, initial mobilizations and updates for upcoming contractual agreement signing.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Implementation into Procore of the Warehouse Inventories across the Genera's Power Plants; review current activities to relate the Inventories Weekly Reports with the actual Project Files and Folders.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Jobos Submittal Log for potential items to be reclassified as general documentation and reports. Verify the contractual obligations between Pre-Construction and Construction stages in terms of Submittals and actions taken.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the Critical Components that applies to the Costa Sur Power Plant to link project management development in Procore with the Critical Components efforts.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 139 | 34.75 | 139 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Held a coordination meeting via MS Teams with Lauren Wells, Jean P. Menay, Frances Vallejo, and Carolyn Báez-Nieves (DCMC) to discuss the management and tracking of material and supply needs across sites under the Genera PR project. Key discussion points included the development and maintenance of a centralized tracker to monitor supply requirements, reviewing and organizing the current supplier list, and validating related invoices. It was agreed that a dedicated tab would be added to the tracker for materials and office equipment, serving as a running inventory of items requiring monthly replenishment. Additionally, the team discussed the possibility of creating and managing the tracker within the Procore platform to enhance accessibility, enable real-time updates, and integrate with project documentation. The tracker will be maintained regularly to ensure proper expense allocation to Genera and to support accurate reporting and budget compliance.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Organize all the photos of the sites together with the Genera PR team, Jorge Bracero, with the measurements, megawatts and look and feel of each of the sites in which the signs in which it would be installed will be installed.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Continue working with the Costa Sur fact sheet. These tasks included changing the photo that was being used, integrating additional information about the project, creating a more organized format to integrate both projects into a single document. This task also included communicating with Jean Pierre, from the DCMC Partners team, to clarify some doubts related to the security plan of the sites that have BESS and Peakers.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Work on the creation of a document in Canva that includes the itinerary of community events to be able to make it visible with the Genera PR team: Jorge Bracero, Iván Báez and Rafael Rodríguez Emma. This task included looking for the format, integrating the data and branding the Genera PR brand.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with Jorge Bracero, Genera PR team, with the purpose of discussing the pending issues of the week. Topics were discussed on tactics to impact the communities of Yabucoa, Daguao and Jobos. Follow-up on community impact in the schools of Vega Baja and Arecibo. We also talked about updates to the BESS and Peakers project website, presentation of community webinars and annual calendar of community activities.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 139 | 104.25 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 I Meeting with the Genera PR team, Jorge Rodriguez and Rafael Rodriguez Emma to discuss topics related to this week’s tasks, particularly the BESS and Peakers Project, to go over the activity schedule as well as the community webinars.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Integrate changes to the letter to request authorization from the Vega Baja summer camp. This task included: receiving changes, making edits to the letter, reading the letter again, changing the logo of the letter and copying Jorge Bracero's Genera PR team, for acknowledgment of receipt of the letter, which must be submitted to the municipality of Vega Baja.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Meeting with the CDM Smith team: Rafael Pabón and Manuely Concepción with the Genera PR team: Jorge Bracero. At this meeting, details related to the Peakers project were discussed. The task included talking to them about the information requirement we need to create the communication pieces for the communities because there are currently no Peakers pieces created with information about the project.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 139 | 417 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- I gathered and organized the information needed to develop the fact sheet for the Peakers project. This included identifying start dates, the installation sequence, and the main phases of the project, as well as documenting the current progress by site, highlighting key milestones and ongoing activities. I also summarized the technical and community benefits of the new units, including operational efficiency, contributions to energy resilience, and the generation of economic activity. Additionally, I integrated data on environmental impact, type of fuel, fire safety measures, and noise mitigation strategies. Finally, I drafted a brief scope by site using reference presentations as the foundation for upcoming communication materials.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 139 | 104.25 | 139 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR4339: Held a follow-up meeting with Frances Vallejo, Jean P. Menay, and Carolyn Báez-Nieves (DCMC) to discuss the structure and organization of the Excel-based tracker for managing material and supply needs under the Genera PR project. It was agreed that the tracker would be organized using separate tabs for each supplier, enabling more precise tracking and control of purchases, deliveries, and inventory levels. This structure is intended to enhance clarity, streamline data entry, and support accurate expense monitoring across all vendor-related transactions.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line of existing conditions to demolish, general equipment planning, underground pipping and commissioning planning (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Jose Lopez, Luis Moctezuma, and Sunem Martinez (DCMC) to identify existing project general arrangement line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects. We discovered that another contractor is building a structure for the IT department, which will create a clash with the proposed BESS layout. It was immediately informed to Gilberto Sucre (DCMC)
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 51 pages.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Evaluation contractor QC manual (RG Engineering.) included Site Work requirements, Materials (Concrete, masonry, Structural Steel, work construction process (Rought Carpentry, Waterproofing and Damp proofing, Metal , Door and Frames).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Continue evaluation contractor QC manual (RG Engineering.) included Site Work requirements, work construction process and materials used on various areas of the project (Gypsum Wallboard, lath & Plaster) Equipment used for specific activities (mechanical and Electrical).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line of existing conditions to demolish at base turbine 2 Siemens equipment planning, underground pipping, electrical works and commissioning planning (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 134 | 67 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on Teams meeting considering schedule report activities, format for schedule for submittal, specification section 013216 list related to construction guides and resources data formats, schedule of values of schedule for employee (DCMC) Carlos Rodriguez, Sunem Martinez, Rafael Barrera, (RG Engineering) employee Jose Segarra, (CDM Smith) employee Carlos Palomares, (Sargent and Lundy) employee Dean Ennes.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line of existing conditions to demolish at base turbine 1 Siemens equipment planning, underground pipping and commissioning planning (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 | 122 | 91.5 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewing and updating spreadsheet for today's PMO Reporting meeting.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 122 | 244 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updating Procore Analytics Power Bi dashboard data as requested by Lauren Wells (Lemoine).
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 122 | 152.5 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams weekly meeting to discuss Cambalache BESS project construction activities updates. Attendees DCMC: Andres Concepcion, Sylvia Franco, Gilberto Sucre, others S&L: Dean Ennes RGE: Jose Segarra, Wanda Bonet, others
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams weekly meeting to discuss Vega Baja BESS Phase II project construction activities updates. Attendees DCMC: Eduardo Rivera, Sylvia Franco, Gilberto Sucre, others RGE: Carlos Hernandez, others
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 122 | 366 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procore Analytics Dashboards developing and reviewing data to help construction teams make informed decisions, monitor progress, and identify potential areas for improvement throughout the construction lifecycle.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 111 | 111 | 111 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PerDiem for Foster Veazey in San Juan, PR.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  | 70.91 | 70.91 | 70.91 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- PW# 10710- Job Site office Trailer, office supplies, and cleaning materials. The Food was for the DCMC Morning Staff Meeting with Carlos R. López Vallellanes and Sunem Martínez at the Aguirre BESS Job Site Trailer. The purpose of the meeting was to provide a brief presentation of the project to Sunem Martinez (New Hire), the potential awarded general work contractor (RG Engineering), and to outline a two-week look-ahead plan for the project scope of work assigned.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 31.48 | 31.48 | 31.48 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from airport to office for Foster Veazey. $21.63 trip fare, $4.00 tip, $2.10 booking fee, $3.75 airport fee
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 19.6 | 19.6 | 19.6 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from office to hotel for Foster Veazey. $16.28 trip fare, $2.00 tip, $1.32 booking fee.
2025-07-08 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 18.35 | 18.35 | 18.35 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Job Site Office Trailer Supply and consumables.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on research for inventory/materials tracking for office trailers.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in meetings with GE reps to discuss the schedule of procurement for the Peaker site and coordinate the site visits later that day. participants Gino Sambolin Sargent & Lundy William Crespo Sargent & Lundy Lemuel Nieves Sargent & Lundy Reinaldo Romero Sargent & Lundy Miguel Del Valle Sargent & Lundy German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 GE reps onsite to visit peaker sites for coordination of turbines and ancillary equipment layout and configurations at the JOBOS site
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Aguirre IT/OT Communications after yesterday's coordination meeting with LT Automation, PREPA issued a letter during the night indicating they would proceed with the construction as that project funding approval and started the process over 2 years ago. Instructed Jose Lopez DCMC to prepare daily logs as well as take pictures of the activities related to this work and upload in ProCore.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Exchange of e-mails for: * Approval of expense to the power meter repaired at the Yabucoa Site. * Evaluated DOR for the Installation RFP BESS Costa Sur, Aguirre & Yabucoa with Gabriel Morales - DCMC. * Responded to Sargent & Lundy not to further pursue the Pre-Cast VE fort the shear walls at the Vega Baja Site as this design was further delaying the schedule.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS - Sargent & Lundy Due Dates work with Carlos Palomares - CDM Smith to evaluate and established the new dates for IFC submissions including the daily for the 228 MV Installation of Multiples Sites and the rest of the Packages for the BESS Sites except Palo Seco.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Design Discussion with TRC as A/E SME Each team member presented themselves and their role in the Program. PM/CM Team provided a status of the project BESS & Peakers highlighting the design stage on the project, which is far behind, TRC proceeded to present their capabilities of PMO services, but the highlight was the A/E SME as owner's representative. A follow up meeting with Program Specifics to be coordinated by Franklyn Colmenares - CSA Group. Genera - Jesus Cintron TRC - Eli Diaz, Javier Cuadrado, Andrew Dion, William Labbe CDM Smith - Gabriel Perez & Enrique Laya CSA Group - Franklyn Colmenares DCMC - Frances Vallejo & Gilberto Sucre
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Weekly Project Meeting - Let by Vincent Skochdopole - Sargent & Lundy review the different action items, design progress and outstanding RFI's. Main new topic - Tesla indicated there is a required list of items for Genera or the Contractor to procure. NGR quotes were exchange with the team, estimate cost $ 200k. Participants: CDM Smith - Gabriel Santiago & Enrique Laya CSA Group - Franklyn Colmenares Sargent & Lundy - Mike Kuczynski Tesla - Keyur Javiya, Laura Miglietti DCMC - Gilberto Sucre
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued working on the P3 response to the three RFP's scope and cost comparison with Franklyn Colmenares - CSA Group.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Procurement Status Meeting - Cynthia Ortiz DCMC led the meeting following the procurement tracker. Main topics were FOMB submission status od RFP 4898 Vega Baja, RFP 4899 Costa Sur & RFP 4900 Aguirre awaiting contract resolution and completion of exhibit by Genera Finance. For Cambalache P3 requested clarification for Scope & Pring comparison for the same three RFP's. Yabucoa Civil & Structural to start on 7/10. For Costa Sur RFP 231161 one of bidders requested a 7-day response time for the latest request. Attendees - Cynthia Ortiz & Sheila Torres DCMC, Franklin Colmenares - CSA Group, Cynthia Velazquez-Genera.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS - Vega Baja Installation Contract with ARG Ceres - Met with Francisco Feliu - Genera Legal to calculate the exposure of the material cost increase and tariffs exposure for this project. Worked on response as well, the first 5 % increase would be paid by GWC and Genera would pay the rest. Proposed response was presented to Winnie Irizary - Genera for his approval.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Billable-Project Management ¦ DR 4339 - Meetings with DCMC on-site personnel to review Project Status and Roles and Responsibilities. Attendees were Foster Veazey and Abraham Velazquez.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Billable-Project Management ¦ DR 4339 - Retooling of Forecasting model to ensure accurate cost accounting for the PMO team to be input into the overall Genera cost forecast/budget for the program
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Billable-Project Management ¦ DR 4339 - Report overview for the month of June, and review of the current schedule per site/design status and the current hiring needs.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Tesla and Siemens Change Order forms for use in Procore.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financial items for implementation.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for document permissions.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) and Luis Roman (DCMC) for Procore weekly check-in to discuss open items as a team.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore meetings tool for Beta program.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adding distribution groups to project level from company level in Procore.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on gathering information for use of Docusign for DCMC use case in Procore.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items for implementation.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore for adding new users and their roles.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on setting up meetings for next week for Procore and confirming attendees.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Completed the second half of the KPI report for fiscal year 2023–2024, covering January through June 2024, and filled in the missing entries for fiscal year 2024-2025 spanning July through November 2024. This comprehensive dataset enables performance trend analysis across all power plants and serves as the foundation for establishing performance targets for the upcoming fiscal year. Provided the updated data to Josué Sánchez, Victor Torres, and Jan Rodríguez from Genera PR.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Hurricane Maria: Conference call with Rene Muñoz (Portosan) about delivery porto toilet. Conference call with Carlos Rodriguez (DCMC) about the materials need in Costa Sur Genera project. Site inspections Health and Safety indications need for this job. Review the document submit in Procore by ARG contractor about Health and Safety. Conference call with Jose Lopez (DCMC) about Aguirre Communication Tower installation.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Hurricane Maria: Review the document submit in Procore by ARG contractor about Health and Safety in Vega Baja Genera Site. Inspection jobs Dueñas Trailers in Vega Baja Genera Site. Continuum review documentation document about Health and Safety topics submitted by RGE (Cambalache Contractor) in Procore. Coordinate site visit to Yabucoa and Daguao by Paola Arroyo (DCMC) and Jorge Bracero (GENERA) for make community assessment in (BESS) Genera Project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 184 | 138 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended teams call with TRC Company (Eli Diaz), and Jesus Cintron (Genera), Gilberto Sucre (DCMC) to discuss S&L contract transition and deliverables.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended meeting with Raissa Borges (DCMC) to discuss safety officer kick off meeting template sheet.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended call with client (Jesus Cintron, Genera) to discuss PMO status, staffing and other related matters regarding BESS and Peakerr project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting in person with Paola Arroyo (DCMC) to discuss community engagement plan and podcasts for the client regarding BESS project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly catch-up call with Franklyn Colmenares, Gabriel Perez, Rafael Pabon,Carlos Palomares (CDM Smith) Axel Velez (Genera) Cynthia Ortiz (DCMC). Discussed feedback and updates received from the Genera procurement team.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- ¦ DR 4339 - Hurricane Maria - Generation Fleet - Response to the Energy Zar's BESS RFI - Reviewed the PR Energy Zar's July 3 correspondence.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- ¦ DR 4339 - Hurricane Maria - Generation Fleet - Response to the Energy Zar's BESS RFI - Drafted the initial draft of the response, including the Introduction, Project Schedule, Identified Challenges, Mitigation Measures, and Expenditures. Focused on developing clear, factual narratives that accurately reflect project realities. Ensured each section was audit-ready, grounded in verified data, and framed to support transparency. Shared with Jesus Cintron, Kevin Futch (Genera), D'Alexzander Gonzalez (DCMC), Franklyn Colmenares (CDM Smith) for review and feedback.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- ¦ DR 4339 - Hurricane Maria - Generation Fleet - Response to the Energy Zar's BESS RFI - Coordinated with Jesus Cintron (Genera), D'Alexzander Gonzalez (DCMC), Franklyn Colmenares, Carlos Palomares & Gabriel Sepulveda (CDM SMith) and Mike Kuckzynki (S&L) to gather accurate project updates and cost breakdowns. Drafted initial response outline.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - Supported Genera’s Regulatory Team in responding to FOMB's 07/08 RFI regarding BESS Installation at Cambalache (RFP 4826).
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Initiated preparation of the KPI report by backfilling data for fiscal year 2023-2024, completing the first half of the report covering the period from July to December 2023. This phase included compiling monthly performance data for all power plants to ensure a comprehensive and consistent baseline for subsequent analysis and reporting.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Continue verifying submitals related to safety management plan and risk assessment.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I continued module on the Procore platform. The modules taken were the following modules: -Admin: Edit and manage custom fields in the company level admit tool, manage general setting in company level admin tool, manage project setting, set up configurable budget views in company level admin tool, set up defaults in the company level admin tool, and set up word break structure in the company level admin tool. -Announcements: View Announcements -Bid Board: Bid board overview, bid board templates, convert bid board project to portfolio tool, and create a bid board project. - Inspections: Company level inspection response types, create a company level inspection template, create an inspections report, create an inspections schedule, create project level inspection templates, edit an inspection, manage inspections, and perform an inspection. - Maps: Managing photos on the map - Meeting: Create meeting, overview, and view meeting.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I was reading the attached document J related to the Health, Safety, and Environmental Policies. This attachment contains 8 pages and includes the following steps: -Health and Safety Provisions, including 35 required steps. -Environmental Provisions, including 33 required steps.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 | 167 | 542.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I started documenting the Scope of Work of the Technical Specification for the Yabucoa BESS Civil Work Contract. Complete 110 Pages (033020-10).
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Gilberto Sucre and Jean-Pierre Menay (DCMC) to discuss the office trailer contractor's punch list items and pending office supplies.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane María - AGUIRRE BESS PROJECT. Meeting with Carlos de Jesus (DCMC) Construction Schedule Costa Sur, regarding the work we are going to carry out, Priority updates, Process improvement, Internal workshop.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Carlos López and Luis Moctezuma (DCMC) to identify existing fire protection line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents from Sargent & Lundy, package identified as GENERA-15240-061-0017, for the Installation phase at the Aguirre Site, 17º57'10"N, 66º13'49"W. Review items one to 163 and send comments with findings to Gilberto Sucre (DCMC) to evaluate and discuss with the client Genera PR.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 572 to 596. Among the topics read were drilled displacement rigid inclusions (supply and installation requirements of rigid inclusion cement grout columns installed by the drilled displacement method, environmental conditions, protection of existing structures, contractor qualification, aggregate material, installation, construction records, preproduction test drilling exploration), required grout mix design, asphalt paved road (based and subbase course, proof rolling, geotextile)
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I worked on the evaluation of the project's draft schedule. The evaluation consists of analyzing the duration of the activities and their logical sequence for construction.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 531 to 571. Among the topics read were excavation and backfill for foundations (requirements for concrete foundations, materials for backfill, requirements for excavation, classification, protection, support, disposal material), excavation and backfill for underground utilities (material certificates, bedding material, granular or thermal backfill, process, trench excavation, bedding for pipes, bedding for concrete), flowable backfill (mix design, substitution of materials, sequence of installation, tests required, correction of deficiencies).
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I spoke with Eduardo Rivera (DCMC), Vega Baja's Site Manager, about the project's documentation in Procore, which I don't have access to at the moment. We will also coordinate a meeting to discuss the draft schedule and to visit the project on-site.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Conducted a comprehensive safety review of RFP-4899 for the Costa Sur BESS project. The objective was to analyze how health, safety, and environmental (HSE) requirements are defined and distributed throughout the document, including contractor obligations, compliance checkpoints, and deliverable expectations. Special attention was given to safety-related clauses, references to applicable regulations (OSHA, NFPA, EPA), and procedural expectations for submittals and emergency response planning. This early review supports the development of a robust safety framework before contracting and execution phases begin.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- Reviewed safety protocols and manufacturer guidance for the transportation and storage of Tesla Megapack units. Focused on identifying hazards associated with logistics, including thermal control, stacking limits, and containment requirements. The review was conducted to support the development of a risk-based battery storage safety plan in compliance with NFPA 855, UL 9540, and OSHA standards, prior to any site activity.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal review of Sections 311.2 through 311.4, with a strong focus on welding, bolting, and bar grating installation. Welding must comply with Section 050525, while bolting follows Section 050523—both requiring cross-referenced reviews. Grating details were extensive: each panel must be anchored at four corners and, if removable, fastened with stainless steel clips and hardware that remain fixed to prevent misplacement. Field welding of stop bars is mandatory to prevent overhangs from slipping, and spacing tolerances are tightly controlled at edges and transitions. Pipe penetration holes not fabricated in-shop must be cut and banded in the field per actual pipe layout measurements. This final portion integrates structural, safety, and finish coordination that will directly impact post-erection usability and system integration.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur Request for proposal review of covered anchor rod tightening, Section 310.5, site cleanup responsibilities, and general steel erection protocol under Section 311.1. Anchor rod nuts are to be snug-tightened with a quarter-turn beyond, requiring precise torque control. The specification's definition of "snug-tight" serves as guidance for enforcement during inspections. Site cleanup mandates total removal of equipment and debris after work completion, which should be integrated into final punch lists and site turnover planning. Steel erection must conform to AISC 303 standards, ensuring that all practices adhere to industry norms. These sections emphasize field execution quality, post-activity accountability, and standardization across trades.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Axel Rivera, GENERA PR Yabucoa Site Supervisor to evaluate the condition of the main PREPA connection of the DCMC Partners site office due to unexpected electrical failures in the office affecting lighting, A/C units, and all power outlets. Also, Javier Arroyo from J. Arroyo Enterprise Inc. was contacted to discuss the quotation received to resolve the issue.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Reviewing Scope of Services for Technical Specification Number G-3300 and G-3400 for BESS General Work Contract (GWC) that will be issued for bid and perform a comparison report for Gilberto Sucre from DCMC Partners.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Call meeting with Carlos Villamil from Villamil Group Inc. to discuss the scope of work and the quotation for the landscape monthly maintenance at the DCMC Partners office at the Yabucoa Site.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Reviewed with Safety Officer (Luis Echevarria- DCMC) the safety protocols and manufacturer guidance for the transportation and storage of Tesla Megapack units. Focused on identifying hazards associated with logistics, including thermal control, stacking limits, and containment requirements. The review was conducted to support the development of a risk-based battery storage safety plan in compliance with NFPA 855, UL 9540, and OSHA standards, prior to any site activity. Also, we continue visit site project in order to analyze possible rigging plan risks.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur- Conducted a comprehensive safety review of RFP-4899 for the Costa Sur BESS project. The objective was to analyze how health, safety, and environmental (HSE) requirements are defined and distributed throughout the document, including contractor obligations, compliance checkpoints, and deliverable expectations. Special attention was given to safety-related clauses, references to applicable regulations (OSHA, NFPA, EPA), and procedural expectations for submittals and emergency response planning. This early review supports the development of a robust safety framework before contracting and execution phases begin. Also, verify QA/QC procedure that could be implement in the project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Safety Continue reading Standards for Concrete Deposit Work at Aguirre Power Plant: 4. Work Area Control Barricades and clear signage must be installed around the work zone to restrict unauthorized access. Spill kits and wash stations should be nearby in case of accidental contact with wet cement or admixtures. All work should be supervised by a competent person at all times. 5. Environmental & Fire Safety Concrete washout areas must be contained and located away from drainage or water sources to prevent contamination. No work shall be performed during thunderstorms or when high winds compromise formwork safety. Fire extinguishers should be available, especially near areas where curing compounds or flammable admixtures are stored. 6. Emergency Procedures In the event of a chemical burn (cement contact with skin or eyes), personnel must proceed to the nearest eyewash or shower station and report to the medic immediately. Evacuation routes must be clearly marked, and all personnel should be familiar with muster points. Incident reporting must follow the power plant's HSE protocol and be submitted within 24 hours. 7. Post-Work Procedures Remove and clean all tools and equipment. Properly dispose of concrete waste and washout in accordance with the plant’s environmental compliance standards. Conduct final inspection and housekeeping before demobilization. A safety debrief should be held to discuss lessons learned or incidents.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Safety Standards for Concrete Deposit Work at Aguirre Power Plant: Concrete deposition at the Aguirre Power Plant involves the placement, leveling, curing, and inspection of concrete in designated structural or maintenance areas. Due to the sensitive and high-risk environment of a power generation facility, especially one potentially handling fossil fuels or high-voltage equipment, rigorous safety standards are mandated for all personnel and contractors involved in such activities. 1. Pre-Work Safety Preparations Site Risk Assessment: A job hazard analysis (JHA) must be conducted before any concrete work begins. This includes identifying proximity to electrical systems, hot work areas, confined spaces, and potential chemical exposure. Permit to Work (PTW): All concrete activities require an approved PTW, reviewed by the Plant Safety Officer and signed by relevant supervisors. Toolbox Talk: Daily safety briefings are mandatory before shift start. Topics include task-specific hazards, weather conditions, equipment safety, and emergency procedures. 2. Personal Protective Equipment (PPE) Mandatory PPE includes: Hard hat High-visibility vest Safety goggles or face shield Cut-resistant gloves Steel-toed boots Respiratory protection if dust or fumes are present All PPE must be in good condition and certified according to OSHA or local standards. 3. Equipment and Material Handling All mixing and pouring equipment must be inspected and tagged safe for use before deployment. Concrete mixers and pumps must be grounded and operated by certified personnel only. Rebar, formwork, and lifting devices must be handled using proper rigging techniques and lifting plans.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT - Participated in a phone call with Basilio Ramos (Sunset Contractors) to discuss the possibility of performed a Job site visit to the Vega Baja Site to Go over any question and or scope of work clarifications for the demolition phase II. The meeting should include an Overview of the Scope of work to ensure that all project participants have a clear understanding of the expectations and requirements, as well as their role in the project’s execution. The Attendees scheduled for this meeting are Gilberto Sucre, Eduardo Rivera, Gilberto Soto (DCMC), and Nelson Soler (CDM Smith).
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Walk through the Aguirre Complex to identify possible locations for the project sign installation. The information was requested by Gabriel Pérez (CDM Smith) and Gilberto Sucre (DCMC). Various pictures were taken and should be discussed with the Genera-PR Plan Manager, Alexis Cruz. E-mail sent to Gabriel Pérez (CDM Smith) for site confirmation as requested.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Aguirre BESS Project - Held multiple phone discussions with RG Engineering Project Manager, José Segarra, regarding compliance with contract requirements and current progress. Later joined coordination call with Sargent & Lundy (Mike Kuczynski, Angel Alice Rodríguez), Gilberto Sucre (DCMC), and Enrique Laya (CDM Smith) to address Phase II contract review comments and the absence of structural details in the issued design drawings.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Comments are made on the lifting plans where areas for improvement were identified. Some mathematical results are identified that do not match the comments of the 40-ton crane manufacturer, among others.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of the procedure for lifting containers using a 40-ton crane at the Cambalache site. This lifting plan is included in the risk analysis for the task submitted by the contractor, RGE.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Monitored project correspondence trough Procore. Reviewed RFI, Submittals status to ensure is being worked and entered correctly in the Platform.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated consultation and discussed with Gabriel Perez (CDMSmith) and Permitting consultant (Carlos Lopez - CW Legal) to review NPDES permitting scope of work to be implemented in the project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed the project final agreement and proposal budget of scope of work from the contractor (RG Engineering). Specifically, the scope of work related with Fire Protection design agreed in contract and compared with existing design drawings that depend on the new Design Development by the construction contractor. This study will help to follow up and ensure the design development is performed correctly.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Continued creating a list of observations for the Design Drawings set pending details and plans that are needed to be revised. Reviewed Mechanical and Electrical disciplines.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Site coordination meeting visit with Asdrubal Morales of BETA Contractor that visit Vega Baja for them to provide quotation for the relocation of the existing MPT and to collect all information related to the relay control and communication of the existing transformer. Contact Sylvia Franco of Genera to discuss the project draft schedule send by ARG in regard of the construction phase 2 project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the revision of IFB drawing versus IFC drawing to identify posible impact change orders. Send respond to Carlos Hernandez of ARG/CERES that Genera will not pursue the implementation of PreCast on Vega Baja site. Requested to Jaime Pesquera of DCMC to stop certification #3 of Homeca and to remove some items that was included in certification and to contact Carirma Sanchez of Homeca to make the change and in certification #5 tu submit these items with change order if they will proceed.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue to work with the revision of IFB drawing versus IFC drawing to identify posible impact change orders they are many errors observed in the drawing from IFB vs IFC.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the correction of certification #3 that was cancelled to remove some items. Continue working with drawing revision to identify posible change order. We had received Dueñas Trailer that came on site to fix the floor of trailer, install stair on new trailer and anchor trailer for properness of Hurricane season 2025.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-initiated coordination efforts for the next cycle count at the Palo Seco warehouse by assessing inventory readiness and operational flow. The work included evaluating recent transactional data, identifying location integrity. Additional efforts focused on optimizing material layout in areas CC 001 to CC 009 to support a smooth execution of the count, while also reviewing environmental conditions and labeling consistency to align with compliance requirements.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed inventory count activities for assigned zones within the Palo Seco warehouse, concentrating on the validation of item locations, physical counts, and data integrity. Tasks included reconciling on hand inventory with system records, addressing mismatches, and documenting results in compliance with procedural standards. Efforts also covered traceability assurance and audit readiness through systematic review and verification. This session focused on inventory areas CC 001 through CC 009.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco facility, prepare a comprehensive report to Mr. Anthony Vega from Genera PR. The report compiles key operational observations across various warehouse zones, addressing inventory variances, classification concerns, and overall stock condition. It identifies major discrepancies, highlights recurring issues, and provides recommendations aimed at improving data accuracy and alignment with company standards. Reviewed locations included CC 001 to CC 009, LL 010 to LL 020, AJ 001 to AJ 007.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a morning phone meeting with Mr. Juan Vallejo, Mr. Hernan Machado, and Mr. Milton Flores from DCMC to coordinate priorities for the day and align warehouse operations with current project timelines. The discussion covered material handling logistics, updates on pending tasks, and resource allocation to ensure uninterrupted workflow. Action items were assigned, and expectations were clarified to maintain consistency and productivity throughout the team daily operations.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted discrepancy review at the Palo Seco warehouse to analyze inconsistencies found during prior inventory validation processes. The session focused on evaluating historical inventory transactions, inspecting part movement records, and verifying item numbers to detect potential data mismatches. These efforts were directed at strengthening data reliability, identifying root causes, and reinforcing control measures. The review covered inventory locations from CC 001 through CC 009.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a recount of previously audited inventory zones at the Palo Seco warehouse to confirm accuracy and resolve outstanding discrepancies. This effort included rechecking physical stock levels, validating bin locations, and verifying that all prior adjustment were correctly reflected in the system. The activity ensured consistency between physical inventory and system records while reinforcing traceability standards. Recount operations were conducted across locations CC 001 through CC 009 in accordance with internal reconciliation procedures.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Verify that the services billed on invoice PRIN0008436 were indeed requested by Genera and delivered as specified. CPM Invoice 8436, 8587, 8810. PW-9815 FAASt A&E
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed contractor submittals RGE-0011 and RGE-0011.0 for the BESS project (PW9510), which propose road modifications to access the levee without impacting the dyke’s hydraulic capacity. Evaluated the proposed alignment, construction methods, and supporting design documents to assess constructability and compliance with project constraints. Drafted internal review comments and coordinated with the engineering team to determine whether additional geotechnical input would be required prior to acceptance.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Conducted a detailed review of contractor submittals RGE-0008 and RGE-0008.2 related to employee certifications for the BESS project (PW9510). Verified documentation content, cross-checked with contractual and safety requirements, and confirmed inclusion of required supporting attachments. Drafted internal comments and began preparing formal correspondence to request clarification and updates from the contractor via Procore.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed email communications and documentation related to Cambalache RFI #23 for the BESS project (PW9510), which requested clarification on the resolution of RFI #22. Verified the closure documentation for RFI #22 based on prior meeting outcomes, confirmed consistency across records, and prepared a response draft to address the clarification request. Coordinated with internal team members to validate the closure position before submission.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the Submittal #: RGE-0002.1 RGE-0002.1 - Temporary Mechanical Connection to Existing Transformer T1.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents reviewed and closed submittal #008 per Sucre's direction. Worked on existing dwg from IFB & IFC to identify any possible change orders.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents. Worked on existing dwg from IFB & IFC to identify any possible change orders. Also supervised a visit from Beta Electric, they came in to see where to move the actual transformer to a temporary place and to calculate the distance for the heavy equipment crane needed to lift it.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started verifying submitals related to safety management plan and risk assessment.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations LL 10 to LL 020, list # 1298/1299 RECOUNT 1335
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AJ001 to AJ007
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AJ001 to AJ007
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AJ001 to AJ007
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AJ001 to AJ007
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AJ001 to AJ007
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations LL 010 to LL 020 at the Aguirre warehouse to initiate the cycle counts.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location LL 010 to LL 020
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria; Aguirre-Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. LL 010 TO LL 020 LIST # 1306/1307/1308/1310
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Weekly Catch up meeting with Lauren Wells (Lemoine) and Theresa Perez (DCMC) to go over the weekly progress and execution of the Procore platform. Recently added users, pending documentation and project management tools tracking.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/ Aguirre BESS add new User (GENERA Safety Officer)/Vega Baja BESS Add new user (ARG/CERES Project Engr)/Continuation of Cambalache BESS project review all RFP & RFQ data in project folders for accuracy to make readily accessible and available for project teams/Procore Management Coordination with Lauren Wells (DCMC) & Luis Roman (DCMC)
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/ Continuation of Cambalache BESS project review all RFP & RFQ data in project folders for accuracy to make readily accessible and available for project teams/Vega Baja BESS project review all RFP & RFQ data in project folders for accuracy to make readily accessible and available for project teams
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Review the submittal log for Vega Baja to identify Submittals that did not followed the proper response/close/distribution process for corrections.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR4339 – Continue with the publishing process for the Vega Baja Technical Specifications for BESS works: reviewing documents formatting and pointing out the findings for future reference while publishing specs without errors.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review and publish part of the Technical Specifications for the Vega Baja project. Identifying formatting issues for processing files and publishing final approved versions.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Jean Menay, DCMC to discuss the Submittals Workflow Templates for Safety related submittals to reinforce the QA/QC of site safety officers prior to his final approval.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Corporate Affairs Team Catch-Up meeting with Genera PR team members Jorge Bracero, Ivan Baez, and Rafael Rodriguez. During the meeting, key topics were discussed including the upcoming virtual community meetings, the current community engagement calendar, the return on investment of sponsorships, and the coordination of site visits to Yabucoa and Daguao BESS and Peakers project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Reviewing and refining the Frequently Asked Questions (FAQ) document for the Peaker System. This task served as a foundational step to begin developing outreach materials tailored for the community. The editing process involved integrating essential technical and contextual information about how the system operates, its intended impact, and key mitigation measures. Special attention was given to ensuring clarity, accessibility, and cultural sensitivity, making the content easy to understand for non-technical audiences while addressing community concerns identified during prior engagements.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Developed a structured inventory of all communications materials housed in SharePoint. This included identifying, organizing, and cataloging presentations, visual assets, FAQ documents, community outreach guides, and draft materials created to inform and engage various stakeholders.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Manage and coordinate visits to the Yabucoa and Daguao sites. These tasks directly contacting from the DCMC Partners team, specifically Raissa Burgos and Jean Pierre Menay, to gather the necessary information such as timelines, objectives of the visit, safety protocols, and other relevant details. Once the required data is collected, prepare and send a formal email with the requested information BESS and Peakers project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Reviewing and editing key communication documents intended for community engagement BESS and Peakers project. A major component of the task involved updating the presentation materials used in community meetings, incorporating specific feedback and recommendations provided by the Genera PR team. The editing process included refining language for clarity and impact, strengthening core messages, and integrating visual elements to enhance audience comprehension. Adjustments were also made to ensure that the content aligned with the project’s strategic goals and remained culturally sensitive and accessible to all participants.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Prepare for the Corporate Affairs Team Catch-Up meeting, where we need to provide an update on the weeks we've been working and the pending projects about the BESS and Peakers project. This includes conducting a document inventory to identify what would be presented to the Genera PR team and Jorge Bracero.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures, Subcontractors Plan, Subcontractor Lien Releases, Subcontractor Joint Payment Agreements, Subcontractor Payments and Subcontractor Back Charges Subcontractor Default, Subcontractor Terminations and Subcontractor Daily Reports to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 43 pages.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 47 pages.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Continue evaluation contractor QAQC manual (RG Engineering.) included Site Work requirements, work construction process and materials used on various areas of the project (QAQC Codes and Standards) include specific equipment used for construction.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Continue evaluation contractor QC manual (RG Engineering.) included Site Work requirements, work construction process and materials used on various areas of the project (Gypsum Wallboard, lath & Plaster) Equipment used for specific activities (mechanical and Electrical).
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line of structures to demolish at site, concrete pads construction planning with formworks detailing, underground pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line concrete pads for transformer 1 area, construction pads and wall planning with formworks detailing, underground pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures, Billing PLan, Applications for Payment and Collections to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Internal Teams Meeting with Frances Vallejo, DCMC. The purpose of this meeting is to discuss project reports status and updates. The meeting was organized by Frances Vallejo (DCMC).
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 122 | 305 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue with the development of the Safety Officer report template to document site-specific activities, inspections, and any incidents that have occurred.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 122 | 488 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Designing a standardized Safety Officer report template for use during weekly meetings to document site-specific activities, inspections, and any incidents that have occurred.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Coordinating through calls and emails with DCMC team Paola Arroyo, Jean Pierre and Gabriel Morales site visit to Yabucoa and Daguao sites.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 111 | 111 | 111 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. PerDiem for Foster Veazey in San Juan, PR.
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 26.46 | 26.46 | 26.46 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from office to airport for Foster Veazey. $21.44 trip fare, $3.00 tip, $2.02 booking fee
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 15.06 | 15.06 | 15.06 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Uber from hotel to office for Foster Veazey. $11.67 trip fare, $2.00 tip, $1.39 booking fee
2025-07-09 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 41.44 | 0.7 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Purpose Genera Project Inspection Dueñas Trailers installation and repair offices trailers. Training Asdrubal Morales Beta Electric. Meeting with Eduardo Rivera about Vega Baja Genera Site project. Total Distance 59.2 miles.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items, answering questions for users.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Site visit to Daguao site with GE and S&L to review new proposed layout of new turbines to be installed. Reviewed new current configuration and existing conditions. Gino Sambolin Sargent & Lundy William Crespo Sargent & Lundy Lemuel Nieves Sargent & Lundy Reinaldo Romero Sargent & Lundy Miguel Del Valle Sargent & Lundy
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 site visits to Jobos site with GE and S&L reps. reviewed the current site conditions and current proposed layout of the new equipment to be installed. Davd lee GE power gen, J. kin GE power gen, Gino Sambolin Sargent & Lundy William Crespo Sargent & Lundy Lemuel Nieves Sargent & Lundy Reinaldo Romero Sargent & Lundy Miguel Del Valle Sargent & Lundy
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Sargent & Lundy IFC's due dates reviewed the remaining packages met with Gabriel Perez, Carlos Palomares - CDM Smith and Franklyn Colmenares to reach agreement on the final request to Sargent & Lundy.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procurement Evaluation Process and Challenges with FOMB and P3 submissions. Meeting with D'Alexzander Gonzalez and Frances Vallejo, DCMC has been providing support to Genera's Procurement but is not leading the effort and there is des-endgament with Finance. D'Alexzander Gonzalez -DCMC to bring up to Genera's Management.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - reviewed Homeca's draft Invoice # 4 and outstanding Change Order Approvals. Meeting with Gabriel Perez and Manuely Concepion - CDM Smith.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur BESS Weekly Construction Meeting led by Carlos Rodriguez DCMC - Provided update on contract status and expected NTP date. Review RFI and Submittals, Temporary Construction Fence. IFC scheduled for 7/10 Discussed Fiber Optic pending confirmation from Hector Vazquez - Genera IT/OT Potential Layout Conflict with BESS Battery Layout. Running Demineralize Water in storm sewer system crossing the construction Site. For the last two items a walk thru & site visit was scheduled for 7/15 at 8:30 am. DCMC, Sargent & Lundy, RGE, Genera and Vidot (Surveyor) to attend. Attendees: DCMC Gilberto Sucre, Rafael Barrero CDM Smith - Gabriel Perez Sargent & Lundy - Wilfredo Sierra RGE - Jose Segarra Genera - Jose Beauchamp
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 225 | 393.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence evaluation and responses to: * Cambalache Construction Parking and Permit Impacts * Peakers SME Job Description * Fixed Price Tariffs Agreement with ARG Ceres * BESS Checkin M of M * Costa Sur Site Visit * RFI # 0054 - 38 kV and Feeder Line Costa Sur * RFI # 0055 - Yabucoa BESS Area Land Use * Cambalache VE Lasted Version * RFI # 0056 Yabucoa Peakers/Black Start * Vega Baja - 4" water tie-in
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Update discussion with Carlos Rodriguez DCMC to review weekly meeting agenda prior to the meeting.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Yabucoa RFC meeting with RGE - Kickoff meeting with successful contractor Rg Engineering to execute the BESS - Civil & Structural Package. Led by Gabriel Perez CDM Smith and William Serrano - Sargent & Lundy the RFC Tracker was reviewed and discussed. Gilberto Sucre DCMC requested the latest documentation to be on a common file to be shared by all participants. Gabriel Perez - CDM Smith WIlliam Sierra - Sargent & Lundy Gilberto Sucre - DCMC Jose Robles - RE Engineering
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria At the request of Jesus Cintron Coordinated visit of Paul Browne - DCMC Inventory to site meeting with RGE and Genera to manage the warehouse inventory prior and during the transfer to the temporary warehouse at the Cambalache Site, Visit was coordinated with Andres Concepcion - DCMC
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS/Peakers Project Schedule & Budget Meeting led by Carlos Palomares CDM Smith presented the weekly update on both programs, highlighted need for DCMC to provide CM cost for Vega Baja to complete Decommission Final Report due 7/15. Participants CDM Smith - Gabriel Perez, Rafael Pabon CSA Group - Franklin Colmenares DCMC - Abraham Velazquez, Gilberto Sucre
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review CM Team Staffing durations per site for overall PMO Program Budget with Mark Merritt.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-BESS and Peaker's Project Schedule & Budget Meeting. Attendees were Foster Veazey (Lemoine), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Carlos Palomares (CDM Smith) .
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore permissions on documents and meetings.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks list for open support items.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items for 10710 and 11855 for document structure.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Permissions.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore workflows for Per-Intervention.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Powerpoint presentation details to update leadership on what we are doing with Procore.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financial items for implementation.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of current Financial workflows to evaluate use case in Procore.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore submittal responses.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussed the submitted KPI reports for the power plants with Victor Torres from Genera PR, including a review of the new master KPI report encompassing fiscal years 2023 through 2025. The conversation also initiated planning for the development of Power BI data models to support performance visualization. Additionally, reviewed the master KPI dataset provided by Victor Torres (Genera PR) to begin preparing statistical analyses, including mean, variance, and deviation calculations, to establish maximum and minimum target ranges for key operational metrics such as capacity factor, equivalent forced outage rate, equivalent availability factor, maintenance outage factor, and planned outage factor.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 | 184 | 322 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Andres Concepcion (DCMC) about Cambalache Safety and Security topics. Review the documents submit from RGE. Review the OSHA requirements about crane topics.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Nelson Medina about security topics in Cambalache Genera Site. Call with Portosan contractors (Rene Mercado) about toilets tanks in Genera Projects. Review the documents submitted by RGE in Procore about Cambalache. Meeting about Costa Sur Genera Projects with RGE Contractors (Carlos Rodriguez RGE) Genera Representatives (Ing. Beauchamp) and DCMC representative (Gilberto Sucre).
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Continued reviewing documents submitted by RGE, focusing on compliance with OSHA health and safety requirements. Conducted a review of relevant OSHA regulations and laws, particularly those related to crane operations. Coordinated with Maria Sanchez (Genera) to discuss crane safety topics and ensure alignment with regulatory standards and site-specific protocols.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 | 184 | 414 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continuing review the documents submit from RGE and review the OSHA requirements about Health and Safety topics.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended Teams meeting with project management teams for BESS and Peaker's project to discuss budget and schedule. Attendees: Gilberto Sucre (DCMC), Carlos Palomares (CDM), Gabriel Perez (CDM)
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146795 | Genera PR- Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review and analyze one pagers report foe BESS and peaker project and one pager template for safety.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR- Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Teams call with Costa Sur management team for BESS and Peaker's projects. Attendees: Carlos Rodriguez (DCMC) and other DCMC participants.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Teams meeting with D'Alexzander Gonzalez and Gilberto Sucre (DCMC) to discuss procurement issues regarding BESS and Peaker's project.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- ¦ DR 4339 - Hurricane Maria - Generation Fleet - Collaborated with Jose Ralat to review and clarify the Project Worksheet (PW) and account numbers associated with the Generation Fleet projects. As part of this discussion, we identified the need for a standardized process to avoid budget misalignment in future solicitations. We jointly developed an internal process to ensure that all future RFPs include the correct PW number and corresponding Disaster Incident (DI) number. This measure is intended to improve tracking, alignment with FEMA funding, and overall budget compliance.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- ¦ DR 4339 - Hurricane Maria - Generation Fleet - Response to the Energy Zar's BESS RFI - Incorporated edits and suggestions provided by Jesús Cintrón and Kevin Futch (Genera) into the draft response. Ensured that all revisions aligned with project facts, regulatory requirements, and messaging objectives. Shared the updated draft with Jesús Cintrón, Kevin Futch (Genera), D’Alekzander González (DCMC), and Franklyn Colmenares (CDM Smith) for further review and feedback, facilitating collaborative refinement and cross-functional alignment.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- ¦ DR 4339 - Hurricane Maria - Generation Fleet - Revised the Scope of Work (SOW) and accompanying documents for RFPs 4898, 4899, and 4900 in coordination with Gabriel Pérez (CDM Smith), Gilberto Sucre (DCMC) and Mike Kuczynski (S&L) to ensure that all resulting contracts include the correct SOW and corresponding design documents. Verified alignment across all materials to support consistency and contract accuracy. Organized, identified each document and shared final versions with Genera Regulatory and Legal teams.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started verifying submitals related to safety management plan and risk assessment. Continue Day 2
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I continued reading the Scope of Work outlined in the Technical Specifications for the Yabucoa BESS Civil Work Contract (120 pages completed / Reference: 312333-11), along with relevant standards applicable to the activities to be performed. These include Lockout and Tagout (29 CFR 1910.147), Demolition (29 CFR 1926 Subpart T), Excavation (29 CFR 1926 Subpart P), and Fire Protection (29 CFR 1910 Subpart L).
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I continued with the module on the Procore platform and read the preliminary drawing designs (Specification No.: G-3100 / Project No. A1524). The Procore module covered the following modules: -Daily Log: Daily log tool, add daily log entries (Mobile), view daily log report, and daily log resources & review - Incidents- Incidents tool, create an incident, and incidents resources & review - Puch list- Configure Punch list setting, close a punch list item, create a custom punch list report, create a punch list item, resolve a punch list item, respond to a punch list item, and view a punch list item.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane María - AGUIRRE BESS PROJECT. Meeting with Theresa Perez (DCMC) Document Controller, program, priority updates, process improvement, internal workshop.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT/ Continuing education, Submittal Builder course 45 minutes, Permissions tool course 15 minutes.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT/ Continuing education, Action plans, Analytics, Bid, Board, Bid Managment.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Carlos López and Luis Moctezuma (DCMC) to identify existing fire protection line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I met with Theresa Perez (DCMC) by Teams because I continues to have trouble seeing some project folders in PROCORE. We shared screens to find out what the problem was.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja and Cambalache ¦ DR4339 – I did the Procore Workshop Manager (Project Management) with final exam. The certification sent for my records.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Meeting with Andres Concepcion, Carlos de Jesus and Luis Damudt (DCMC) to discuss the contract schedule.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 597 to 630. Among the topics read installation of underground gravity sewer (requirements, field jointing pipe, trace wire, manholes, catch basin, acceptance testing), erection of piping (design requirements, quality, storage, handling, fabrication requirements, field welding, field quality control, cleaning and painting).
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I read the RFP for the Vega Baja project where it specified where to get the scope of the wok, timeline and procedures, proposal submission instructions, evaluation, process, interview, and other topics.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- DCMC Site team lead by DCMC Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's. Reviewed technical sections of the RFP-4899 proposal with a focus on identifying embedded safety management requirements. Emphasis was placed on contractor responsibilities for HSE compliance, modules documentation, and emergency procedures. Cross-referenced content with OSHA and NFPA standards to ensure alignment with regulatory expectations prior to field mobilization.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- Review of Appendix J – Health, Safety, and Environmental (HSE) Policies included in the RFP-4899 proposal. The evaluation focused on the structure and effectiveness of the contractor’s safety program, including incident investigation protocols, hazard communication, emergency response, and environmental controls. Special attention was given to the integration of workshop requirements, subcontractor oversight, and continuous improvement mechanisms. These elements were cross-referenced with OSHA 1926 standards and Genera’s internal safety framework to assess readiness for execution phase requirements.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur DCMC Site team meeting lead by site Manager Carlos Rodriguez weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to continue discussions on initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically to permits, safety modules, submittals and RFI's.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur - BESS- Request for proposal review of Section 301.1 General Excavation Requirements. Verified that excavation activities include incidental clearing, disposal, dewatering, and bearing area prep. Cross-referenced OSHA CFR Title 29, Part 1926 for slope compliance. Excavation must be performed under dry conditions using conventional equipment. Document highlights the importance of maintaining excavation boundaries and avoiding work outside designated areas.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting at the Yabucoa Gas Turbine site to discuss the Peaker project scope, site environment and current layout, design layout and other important info to assure a successful plan to complete the project. In the meeting participate Axel Rivera from GENERA PR; Jose Pagan, Reynaldo Romero, Miguel Del Valle, Nelson Rosado and Gino Sambolin from Sargent and Lundi; Enrique Laya and Rafael Pabon from CDM Smith; Lee David Christopher, Ho Kin Hei from General Electric; Harry Velazquez from RG Engineering and Abraham Velazquez from DCMC Partners.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Reviewing Scope of Services for Technical Specification Number G-3300 and G-3400 for BESS General Work Contract (GWC) that will be issued for bid and perform a comparison report for Gilberto Sucre from DCMC Partners.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue Reviewing Scope of Services for Technical Specification Number G-3300 and G-3400 for BESS General Work Contract (GWC) that will be issued for bid and perform a comparison report for Gilberto Sucre from DCMC Partners.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Kick Off meeting with the selected General contractor RG Engineering team to discuss the scope and details from the project. In the meeting participate Wilfredo Sierra from Sargent and Lundy; Alberto Borrelli, Jose RObles and Harry Velazquez from RG Engineering; Gabriel Perez and Enrique Laya from CDM Smith; and Gilberto Sucre from DCMC Partners.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting at the Daguao Gas Turbine site to discuss the Peaker project scope, site environment and current layout, design layout and other important info to assure a successful plan to complete the project. In the meeting participate Omar Aponte from GENERA PR; Jose Pagan, Reynaldo Romero, Miguel Del Valle, Nelson Rosado and Gino Sambolin from Sargent and Lundi; Enrique Laya and Rafael Pabon from CDM Smith; Lee David Christopher, Ho Kin Hei from General Electric; Harry Velazquez from RG Engineering and Abraham Velazquez from DCMC Partners.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- DCMC Site team lead by DCMC Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's. Reviewed technical sections of the RFP-4899 proposal with a focus on identifying embedded safety management requirements. Emphasis was placed on contractor responsibilities for HSE compliance, modules documentation, and emergency procedures. Cross-referenced content with OSHA and NFPA standards to ensure alignment with regulatory expectations prior to field mobilization.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 BESS Costa Sur; A kickoff meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Abraham Velazquez, Jean P. Menay (DCMC), Carolyn Baez-Nieves, Glorimel Torrado (DCMC), and other project team members to discuss key aspects of the ongoing project. The focus was on integrating and operationalizing energy systems. A detailed discussion was also held regarding implementing Battery Energy Storage Systems (BESS) at the project sites. Additional topics included safety protocols, equipment needs, time tracking, and the tools necessary for efficient work execution. The team also discussed the integration and management of Peaker's within the energy infrastructure, emphasizing the importance of ensuring that Peaker's are properly aligned with the overall energy system for optimal efficiency and reliability. As part of ongoing efforts to enhance productivity and streamline operations, six iPads were distributed to team members.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, Sunem Martínez, and Luis Moctezuma (DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team. The task assigned to the team this week is to complete the DCMC Office Trailer Mobilization and Office Supplies Delivery. We also performed a site walkthrough to follow up on the PREPA IT/OT Project progress that will clash with the Mega Packs layout. By the time we arrived at the site, the PREPA subcontractor had received a reinforced rebar delivery. And reading about Legal compliance: Following NFPA 10 (standard for fire extinguishers) is crucial to comply with local laws and regulations and avoid penalties.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We were walking in the northern area of the Aguirre Bess Battery project to identify the area where the steel preparation work, wooden mold fabrication, and concrete placement will be carried out and continue reading about the standard 29 CFR 1910.151 requires that eye wash stations or a small eye wash kit be provided, and ANZI Z358.1 also establishes minimum requirements for the installation, maintenance, and workshop of these systems.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting with Sargent and Lundy to go over the Design Drawings and the PREPA IT/OT LT Advance Technologies Project Coordination at All Sites, including Aguirre. Also present at the meeting were Gabriel Pérez (CDM Smith), Gilberto Sucre, Andres Concepción, and Carlos Rodríguez (DCMC). On the team were Mike Kuczynski, Robert Molner, and the Civil Design Staff from the Sargent and Lundy office, Carlos Irizarry, and Hector Vazquez from LT Advance Technologies. The layout of the BESS project was shared with the meeting participants to discuss the proposed location for the IT/OT System project. LT Advance requested a 100-amp feed for their site, and S&L will verify the availability of this request. There will be a follow-up meeting next week to go over all the BESS site coordination that the LT Advance project will impact.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, Sunem Martínez, and Luis Moctezuma(DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team. The task assigned to the team this week is to complete the DCMC Office Trailer Mobilization and Office Supplies Delivery. We also performed a site walkthrough to follow up on the PREPA IT/OT Project progress that will clash with the Mega Packs layout. By the time we arrived at the site, the PREPA subcontractor had received a reinforced rebar delivery.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluation of the documentation received by RGE in submittals 0008 revision 2 where they identify areas for improvement in certifications submitted for people assigned to crane operators.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Comments are provided on submissions 0008 rev 2, which reference OSHA sub-CC standards and regulations, contractor manuals, letters of interpretation, and other applicable standards.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed OSHA regulations to understand applicable requirements for crane and rigging plans & certificate of operator to monitor the validation of project safety submittals.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed design drawings and Prepared correspondence to highlight the designer on design items that are delayed in the project. Identified potential scope of work where designer may have progress. Email to Mike Kuszynski (Sargent and Lundy).
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Jean Pierre Menay (DCMC Partners) to discuss internal coordination regarding project safety processes in Cambalache project.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Attended the Meeting: PREPA / Genera / LT Automation: Coordination with IT/OT Communication Building / Monopole and BESS coordination discussion to align with other projects that may impact the BESS project implementation. Met with Gabriel Perez (CDM Smith), Mike Kuszynski (Sargent and Lundy), Gilberto Sucre (DCMC), Juan Rivera (LT Automation).
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Planned and generated action items list to be discussed in a coordination meeting regarding the Temporary Storage Warehouse to be constructed in Cambalache Plant. Coordination required withing GeneraPR, General Contractor and DCMC Partners team. Meeting will be on 7/11/2025.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting with Luis Duque, Luis Damudt and Sylvia Franco (DCMC Partners) to discuss project schedule review and observations to be considered in future evaluation for the schedule baseline submittal.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the correction of the certification #3 of Homeca. Continue working with the drawing review IFC versus IFB.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting with Gilberto Sucre of DCMC organizer, Manuely Concepcion of CDM Smith, Jaime Pesquera and Eduardo Rivera of DCMC - Meeting was to discuss the certification #3 and #4 of Homeca to respond Carirma Sanchez email of Homeca if both certifications can be at a single one and when change order will be approved. Item was discussed and both certifications can be included in a single but change order should be approved by Genera.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working revieing the IFC drawing set and IFB notice that are drawing new drawing on the IFC set that will be potential change order. Set email to Mike Kuczynski of S&L in regard of Potable Water P&ID that on IFB drawing mention that is a 4" pipe and in the field is a 2" pipe, they mention that will revise the drawing.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continued the review of the Issued for Construction (IFC) drawings for the Vega Baja Site. Additionally, sent an email to Carolyn Báez (DCMC) requesting the printing of both the IFC and Issued for Bid (IFB) drawing sets to support ongoing design and field coordination activities.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out preparatory activities at the San Juan warehouse alongside Mr. Milton Flores from DCMC to ensure all conditions were met for the upcoming cycle count. Task included verifying the physical readiness of inventory zones, confirming correct bin identification and labeling, and validating item groupings against system configurations. The session also ensured that all reference data documentation was in place to support a smooth and complaint counting process.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led a morning operations meeting with Mr. Hernan Machado, Mr. Milton Flores, and DCMC personnel focused on inventory handling procedures and safety compliance. The discussion covered secure material movement, verification of storage conditions, and the proper use of personal protective equipment (PPE) during daily tasks. Emphasis was placed on accurate inventory logging, minimizing errors, and reinforcing safety protocols to ensure a secure and efficient working environment.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled cycle count activities within designated inventory zones ranging from AJ 008 through AJ 020 at the San Juan facility. Efforts focused on verifying physical stock levels, reviewing bin locations for accuracy, and validating labeling information against system data. Any inconsistencies identified during the process were documented for follow-up, and adjustments were coordinated as necessary. All tasks were carried out in adherence to established counting protocols to ensure inventory integrity and alignment with system records.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted inventory recount at the San Juan warehouse in coordination with Mr. Milton Flores from DCMC. The effort prioritized validating physical inventory levels, confirming bin assignments, and ensuring that records reflected actual stock conditions. Emphasis was placed on reinforcing consistency in inventory processes, improving the reliability of count data, and supporting ongoing operational integrity. The review focused on inventory zones AJ 008 through AJ 020, in alignment with audit readiness and quality control standards.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-prepared a detailed inventory performance report for Mr. Anthony Vega from Genera PR. The report included a summary of findings from inventory zones AJ 008 to AJ 020, BH 001 to BH 045, EA 001 to EA 006, EB 001 to EB 003, EC 001 to EC 005, ED 001 to ED 005, EE 001 to EE 005, CC 010 to CC 022, covering item level accuracy, stock balance verification, labeling and bin assignment checks, and documentation of variances. It also addressed recurring discrepancies, compliance with inventory thresholds, and an evaluation of procedural consistency across warehouse operations.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a detailed verification and investigation of inventory variances within zones AJ 008 through AJ 020. The effort centered on analyzing discrepancies between physical counts and system reported balances, reviewing item movement history, and validating data integrity through audit trail checks. Special attention was given to identifying root causes of the variances, evaluating recurring patterns, and assessing the accuracy of previous adjustments. This process supported the refinement of inventory records and the reinforcement of control measures.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Verify that the services billed on invoice PRIN0008436 were indeed requested by Genera and delivered as specified. CPM Invoice 9100. PW-108115 Power Plant Installation
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Grant Management-Procurement & Compliance Review | Direct-PA | Activities necessary for review or procurement or compliance activities or documentation | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11¦ DR 4339 - Hurricane Maria- Develop tracker to tracks all expenses for Critical Components–NME, future Fuel Efficiency components under A&E, E&M PW equipment, and installation activities to flag any potential overruns. PW-108115 Power Plant Installation
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed submittal RGE-0011.0 for the BESS project (PW9510), which proposes road modifications to improve access to the levee while preserving dyke capacity and compliance with site constraints. Assessed the proposed route in the context of applicable design standards, drainage considerations, and site safety policies. Additionally, reviewed related email correspondence with the contractor regarding design intent and permitting implications to support internal evaluation.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS On site- Cambalache - Contract Schedule, Sylvia Franco, Jorge A. Mercado, Andres Concepcion, Luis Duque Silvia Franco, DCMC Partners Cambalache Power Plant team.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the Submittal #: RGE-0012.0 RGE-0012 CONSEPTUAL GAS CYLINDER STORAGE STORAGE, and other emails. Measure the area for installing the banner at the entrance of the project.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents. Worked on all existing dwg from IFB & IFC to identify any possible change orders.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents reviewed all submittals opened and sent emails to Homeca Recyclers regarding Certification #3 & Certification #4. Had short meeting called Homeca Factura y Cambio de Ordenes with Gilberto Sucre, Eduardo Rivera Jordan from DCMC and Manuely Concepcion from CDM-Smith.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started verifying submitals related to safety management plan and risk assessment. Day 2
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CC010-CC022.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AJ008 to AJ020
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AJ008 to AJ020
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AJ008 to AJ020
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AJ008 to AJ020
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AJ008 to AJ020
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations EA 00 001 to EA 00 006 ; EB 00 001 to EB 00 003; EC 00 001 to EC 00 005; ED 00 001 to ED 00 005 and EE 00 001 to EE 00 005.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations EA 00 001 to EA 00 006 ; EB 00 001 to EB 00 003; EC 00 001 to EC 00 005; ED 00 001 to ED 00 005 and EE 00 001 to EE 00 005.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations EA 00 001 to EA 00 006 ; EB 00 001 to EB 00 003; EC 00 001 to EC 00 005; ED 00 001 to ED 00 005 and EE 00 001 to EE 00 005.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BH 001 to BH 045, RECOUNT LIST #1321/1324/1334
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria; Aguirre-Conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations. BH 001 TO BH 045 LIST # 1317/1318/1319/1326/1327
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BH 001 to BH 045 at the Aguirre warehouse to initiate the cycle counts.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location Bh 001 to Bh 045
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CC010 to CC022 to begin the cycle counts.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1410 and 1411 from locations CC010 to CC022 for a total of 326 pcs.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CC010 to CC022 Cycle Count List # 1403.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review and publish part of the Vega Baja Specifications Book: reviewing over 30 different Concrete, Metal, Electrical and Controls specifications to contrast on specifications with missing Submittals Section (required for the Submittal Builder feature).
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Coordination with Sunem Martinez (DCMC) for Contract Info_Schedule Data/Coordination with Sylvia Franco (DCMC) for Contract Info_Schedule Info/Vega Baja BESS project review all Procurement RFP & RFQ data in project folder for review_accuracy to make readily accessible & available for project teams
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Continuation of Vega Baja BESS project review of all Procurement RFP & RFQ data in project folder for review_accuracy to make readily accessible & available for project teams/Coordination w Rafael Pabon (CDM) Siemens Meeting Docs/Review & Process all Daily Incoming Documents - Various BESS & Peakers Locations
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review and publishing part of the Vega Baja Technical Specifications. Specifications are in single files and Procore identifies error in the publishing process; Meeting must be held to discuss issue with designer S&L.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Gather the Costa Sur and Yabucoa Technical Specifications and perform initial QA/QC on files received and their formatting.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review standard general agreement form and the General Conditions of contractual agreements to identify funding requirements such as the Buy American Act, American Iron and Steel and other federal audit requirements on documentation.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 139 | 417 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Create a fact sheet in Canva on Battery Energy Storage Systems (BESS) and Peaker units, which will be used during a meeting in Washington with members of Congress, attended by Iván Báez from the Genera PR team. As part of this effort, I received instructions from Jorge Bracero’s team on the elements that needed to be included. I designed the template, researched and compiled relevant information, selected around ten images to enhance the material, updated all sites and sources, and wrote the content using the appropriate language and tone for a congressional context. I designed a clear, visually appealing layout using Canva, balancing concise technical data with strong visuals. I conducted in-depth research on BESS technology, grid reliability, and peaker plant operations to craft accurate and compelling content. I sourced and selected around ten relevant images—ranging from energy infrastructure visuals to community impact photos—to humanize and enrich the document. Additionally, I updated references and verified all sources, ensuring data integrity and alignment with public-facing reports.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 I followed up on the email received from the Municipality of Vega Baja after the Tran sectorial Dialogue organized by Hispanic Federation and Agenda Ciudadana. The message emphasized the municipality’s willingness to collaborate with Genera PR on strategies to integrate renewable energy sources and strengthen the local electrical system. As part of the follow-up, I called Jorge Bracero from the Genera PR team to inform him about the request and coordinate next steps. I also responded to the municipality to coordinate a potential meeting early next week, as they proposed, to continue the conversation on a more equitable distribution of the project’s benefits.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Follow-up to the labeling of the sites continued with a review of the email chain to confirm the status of this request. As part of this effort, I contacted Andrés Concepción from DCMC Partners directly to request the measurements for the Cambalache site. I also drafted follow-up emails to the Genera Team, Jorge Bracero. The information regarding Cambalache’s measurements was later corrected and updated accordingly.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.75 | 139 | 243.25 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Editing and refining a fact sheet in Canva focused on Battery Energy Storage Systems (BESS) and Peakers units, which would be presented during a congressional meeting in Washington, D.C. attended by Iván Báez from the Genera PR team. After receiving initial content instructions from Genera Jorge Bracero’s team, I concentrated on polishing the document to meet professional and contextual standards. This included revising the structure and layout for clarity and visual impact, updating technical data to ensure accuracy, and adjusting tone and wording to align with the expectations of a legislative audience. I also curated approximately ten relevant images and verified source citations, ensuring that all elements contributed to a cohesive, persuasive final product.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 139 | 34.75 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-A working call was held with the Genera PR team, specifically with Jorge Bracero, to present the progress of the fact sheet being developed in Canva. During the meeting, the content and design of the document were reviewed, and additional adjustments were made based on Jorge Bracero’s recommendations in order to align the final product with the strategic needs of the team.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Complete the coordination efforts for a visit to the Vega Baja camp, with the goal of bringing an educational initiative to the community. As part of the process, I communicated with the municipality and sent an official letter signed by the Genera PR team, including Jorge Bracero, to formalize our commitment and outline the details of the effort.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-Updated the weekly report on community engagement efforts related to the BESS and Peakers project. This report compiles the key tasks and activities carried out as part of the project's outreach strategy. The task involved reviewing pending initiatives, documenting the progress made, and organizing the information to accurately reflect how the project has been managed at the community level.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 5) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures, Document Control Plan, RFI Log, Request for Information (RFI’s) and Change Management to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 40 pages.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Jose Lopez, Sunem Martínez, and Luis Moctezuma(DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team. The task assigned to the team this week is to complete the DCMC Office Trailer Mobilization and Office Supplies Delivery. We also performed a site walkthrough to follow up on the PREPA IT/OT Project progress that will clash with the Mega Packs layout. By the time we arrived at the site, the PREPA subcontractor had received a reinforced rebar delivery.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur facilities -DCMC Site team lead by DCMC Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules submittals and RFI's.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Continue evaluation contractor QAQC manual (RG Engineering.) included Site Work requirements, work construction process and materials used on various areas of the project (QAQC Codes and Standards) include specific equipment used for construction and suggested preparing checklist forms to complete inspections for installing material and constructions process.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line critical path, turbine 2 equipment and commissioning, concrete walls for transformer 2 area, construction of buildings roof in planning with formworks detailing, underground pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 134 | 201 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - DCMC Site in BESS project team lead by DCMC Carlos Rodriguez project meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this project meeting DCMC Costa Sur site team had the weekly meeting with RG Engineering, contractor for the BESS project lead by construction manager Jose Auli (RG Engineering employee), Rafael Barrera (DCMC employee) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line critical path, concrete walls for transformer 1 area, construction of buildings roof in planning with formworks detailing, underground pipping pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 5) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures, Document Control PLan, Submittals and Shop Drawings, Addenda and concrete log to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Integrating the latest Procore workshop metrics into the June monthly reporting dashboard to ensure accurate and up-to-date data tracking.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Revising the ‘One-Pager Report’ for this week to incorporate detailed insights on site-specific activities, alongside a consolidated view of program and project progress.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS / Peakers Schedule & Budget Meeting" The purpose of the meeting is to discuss projects finances and schedule status and updates. The meeting was organized by Gabriel Perez (CDM Smith). Meeting chair: Carlos Palomares (CDM Smith).
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 122 | 366 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue updating the ‘One-Pager Report’ for this week to incorporate detailed insights on site-specific activities, alongside a consolidated view of program and project progress.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting with the Costa Sur construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as Safety Plan, mobilization plan, list of personnel amount other documentation needed. Attendees: Gilberto Sucre (DCMC), Carlos De Jesus (DCMC), Jose Auli (RGE) and others.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Team meeting with CDM Smith team (Carlos Palomares, Franklyn Colmenares, Manuely Concepcion) to discuss program and project status and updates for "One Pager Weekly Report".
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Veazey, Foster | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 20 | 20 | 20 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. -Parking in Mobile, AL for Foster Veazey's travel from Mobile, AL to San Juan, PR
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 8.35 | 8.35 | 8.35 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Plumbing Misc. materials for the Office Trailer Barhroom Service installation.
2025-07-10 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 0.7 | 71.4 | 0.7 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Nelson Medina (GENERA) about the security process on site for construction project.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Mark Merritt, Mike Merritt, Foster Veazey, Gilberto Sucre, Frances Vallejo, Lauren Wells, Ada Diaz, and Barry Scanlon, DCMC. Discussed update on project, job offers, PROCORE, logistics, trailer set-up, safety, and schedule for locations.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended weekend meetings on Peaker's and summery of weeks events discussed schedule impacts and procurement meeting attendees: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended meetings peakers pm meetings discussed status of peakers and GE site visits from previous days German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procurement Update & Awards Meeting with Sheila Torres - DCMC Identified incomplete P3 submissions without complete package documentation. Also responded to P3 RFI with respect of Scope of Work & Pricing Comparison between Cambalache 52 MW, Vega Baja 49 MW & Costa Sur 30 MW.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria DCMC EHS Bi-Weekly Meeting Internal Environmental, Health & Safety Kick-off meeting led by Gilberto Sucre & Jean Pierre Menay. Discuss DCMC role as an extension of Genera's Safety & Environmental Department to oversee and audit subcontractor's performance & compliance to the Genera Safety Manual and Contractual Obligation per Attachment J or I (Depending on the contract.). Each site has the specific conditions and on the owner's side they have an FOS assigned to plant. Submittal approval process was discussed as well as the role of Safety Managers on site. * Jorge Mercado - Cambalache * Gilberto Soto - Vega Baja * Luis Moctezuma - Aguirre * Luz Ramirez - Yabucoa * Luis Echevarria - Costa Sur Frances Vallejo and Raissa Borgess participated as well, all DCMC. This meeting will be held every other Friday. Reporting Template reviewed.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed FOMB packages for RFP 4898 Vega Baja, RFP 4899 Costa Sur & RFP4900 Aguirre: All missing the contract and individual appendixes mainly the Fund Availability Certification and Contractors' Final Pricing document.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS / Peakers Weekly Construction Update Meeting. * Gilberto Sucre DCMC opened the meeting providing an Update across the BESS/Peakers Program. * Each Site Manager present an update of their projects as well as Risk or concerns: - Carlos Rodriguez - Costa Sur - Jose Lopez - Aguirre - Gabriel Morales - Yabucoa - Eduardo Rivera - Vega Baja - Andres Concepcion - Cambalache was excused from the meeting as he had another meeting with Genera & RGE. Frances Vallejo & Raissa Borges also participated of this meeting - All DCMC.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Agenda preparation for Weekly Construction Update Meeting with the DCMC Site Managers * Individual Contract Status & FOMB Approvals * TRC SME's * Drawings Updates & Evaluations * Performance Appraisals * IT/OT Communications at Cambalache, Aguirre & Costa Sur * Implementation of Bi-Weekly Safety Meeting * Site Offices & Materials
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting Update led by Frances Vallejo. Main Topics Covered: Construction Project Status Site Facilities Needs BESS/Peakers Design Status Role of TRC as A/E SME Procurement Update Genera/DCMC ProCore Implementation Staffing Updates & Challenges Replacement PM Search for Peakers Program Budget & Contract Management. Attendees: Mark Merritt, Mike Merritt, Lauren Wells, Foster Veazey, Jack Darnell, Ada Diaz, Anneilia Holton, Gilberto Sucre, Barry Scanlon. All DCMC
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine)
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Peakers Project Management Update meeting. Attendees were Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Carlos Palomares (CDM Smith), and Abraham Velazquez (DCMC)
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Powerpoint presentation details to update leadership on what we are doing with Procore.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on workflows for Procore for QA/QC approvals and how we should work that.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financial items for implementation.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Powerpoint presentation details to update leadership on what we are doing with Procore.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for support for users and setting up meetings for next week.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on a call with Theresa Perez (DCMC) to discuss permissions.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on permissions and adding RGE team to Costa Sur project in Procore.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial information.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore distribution lists for Franklyn Colmenares (CSA).
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions and checking items for Luis Roman (DCMC) for QA/QC users.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Reviewed and updated the Power Production and Fuels Consumption report, preparing Revision 3 to address and correct a 2,000 MW discrepancy in gross production figures. - Prepared a data model for key operational metrics for each power plant using historical data series, and established maximum and minimum performance targets through variance-based calculations. - Collaborated with Victor Torres from Genera PR to review the underlying report data and assess the initial Power BI visualizations to ensure accuracy and alignment with reporting objectives.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 | 184 | 506 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Worked on developing workshop to Portosan teams that need to work in Genera Sites. Javier Aviles (Portosan).
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 184 | 460 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting with Gilberto Sucre, Frances Vallejo and others DCMC Health and Safety teams about all Genera Projects in specific topics and tools request by Genera. Performed administrative tasks concerning the procurement and management of materials required for all office trailers across the Genera project sites.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 184 | 552 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended a meeting with Maria del Carmen Rodriguez at Puerto Rico OSHA to discuss OSHA requirements for crane operations. Participated in a conference call with Ernesto Roche (North Safety Group) regarding crane certifications and compliance. Reviewed the documents submitted in Procore by RGE contractors for the Cambalache and Costa Sur Genera sites, ensuring all safety and compliance records are up to date.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Send emails regarding invoicing for CDM Smith, regarding project management and procore.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Teams meeting with Safety officers and management to discuss bi weekly reports and audits at the site. Participants: Jean Menay (DCMC) and other DCMC participants.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Teams meeting with site managers to discuss site status project, materials needed at site, concerns and pending items with contractors. Attendees: Gilberto Sucre (DCMC) and other DCMC participants.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams call with Luis Roman (DCMC) to discuss Procore processes regarding BESS and Peaker's project, discuss designer roles and next steps.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 -Hurricane Maria - Generation Fleet - Based on the coordination meeting with Jesus Cintron, Rafa Pabón, and D’Alexzander González regarding the requisition strategy for the Black Start Generator at Costa Sur, initiated the development of Request for Quotation (RFQ) packages for Siemens and RG Engineering. This included outlining the technical requirements, procurement terms, and supporting documentation needed to solicit competitive pricing and ensure alignment with project objectives and procurement protocols.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 -Hurricane Maria - Generation Fleet - Initiated development of the requisition package for the procurement of the Black Start Generator for Costa Sur. Conducted a detailed review of the Scope of Work to confirm technical and operational requirements. Drafted the procurement justification memorandum, outlining the critical need for the generator, its role in enhancing system resiliency, and the rationale for proceeding with this acquisition. Ensured alignment with project objectives, regulatory requirements, and procurement protocols.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 -Hurricane Maria - Generation Fleet - Participated in a coordination meeting with Jesus Cintron, Rafa Pabón, and D’Alexzander González to review the requisition strategy for the Black Start Generator at Costa Sur. The discussion focused on validating the technical specifications, procurement schedule, and the documentation required to substantiate the purchase. Following a review of applicable procurement guidelines and project urgency, the team agreed to proceed under an alternative procurement pathway. This strategic adjustment ensures timely acquisition while remaining compliant with relevant procurement standards and funding requirements.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 -739681 Power Generation (Generation) Participated in a strategic advisory meeting with Jesús Cintrón, Winnie Irizarry (Genera) D'Alexzander Gonzalez, DCMC focused on the Generation Fleet Project. The discussion centered on Puerto Rico’s potential generation shortfall and explored viable mitigation strategies to maintain system reliability. Evaluated multiple scenarios to ensure continuity of service while the Generation Fleet project is implemented.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started verifying OSHA documents send by Jean Menay. Entered Weekly meeting for safety officers DCMC team Gilberto Sucre, Frances Vallejo, Jean Menay. Continue verifying OSHA documents.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I was reading and reviewing the following documents: Request for Proposal (RFP No. 231175 -BASS Yabucoa), requirements and evaluation criteria for security guards assigned to genera PR facilities, and Site Photos Specification.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, photos and inspections were uploaded to the Procore program for the BESS project, as a result of the walkthrough conducted by the Community Outreach Team.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, a meeting and walkthrough were conducted at the Peakers and BESS project areas. Representatives from the community outreach teams of DCMC Partners and Genera PR met to review the project scope, assess the design plans, and examine the physical spaces that will be impacted. Participants in the walkthrough included Raisa Borges, Luz Ramírez, Gabriel Morales, and Paola Arroyo from DCMC Partners, along with Axel Rivera and Jorge Bracero from Genera PR.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa A safety update meeting was held to discuss the following key topics: the responsibilities of the Safety Officer, procedures for conducting field inspections, incident management protocols, expectations for contractor performance, the importance of verifying contractor work requirements, and the standardized reporting sheet to be used (Safety Officers Reporting). The meeting was attended by: Jean Pierre Menay, Gilberto Sucre, Luz Ramirez, Jorge Alexis Mercado, Raissa Borges, and Frances Vallejo.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane María - AGUIRRE BESS PROJECT. Meeting with Luis Roman (DCMC) Document Controller, program, priority updates, process improvement, internal workshop.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, Sunem Martínez, and Luis Moctezuma(DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team. The task assigned to the team this week is to complete the DCMC Office Trailer Mobilization and Office Supplies Delivery. We also performed a site walkthrough to follow up on the PREPA IT/OT Project progress that will clash with the Mega Packs layout. By the time we arrived at the site, the PREPA subcontractor had received a reinforced rebar delivery.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Meeting with Carlos López, Sunem Martínez, and Luis Moctezuma(DCMC) to discuss project design status and general work contractor RG Engineering contract signage status. Discuss the proposed project's Look-ahead schedule. It was informed that the Issue for the Installation Bid award date has been delayed and has been moved forward to the end of August. As per the Issue for Construction Drawing, the delivery date has been moved forward to December 31, 2025. The team has been instructed to improve communication with the General Work Contractor, RG Engineering, but without requesting documentation related to the contract requirements until the contract signing is completed. Luis Moctezuma DCMC gave a brief description of the Safety Program Discussed in today's meeting. This meeting will be held every two weeks to set a standard in all the BESS and Pickers projects.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Return travel from Cambalache Power Plant to Vega Baja work base after attending project coordination meeting and field visit for the BESS project. Travel followed completion of on-site activities and team discussions.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Assisted to On site- Cambalache Warehouse Alignment Meeting. Person presents are Jose Segarra (RGE), Herminio Arroyo (Genera), Andres Concepcion (DCMC), others. Topics discussed were about the temporary warehouse.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – revised correspondence on Procore about a Request for Information of road modification.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – A walk was held around the power plant to identify in site water and electrical connection, how to do inventory of all material inside warehouse. The people present were Carlos Negron (RGE), Herminio Arroyo (Genera), Andres Concepcion (DCMC), and others.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Travel time from Vega Baja work base to Cambalache Power Plant to attend project coordination meeting and site visit for the BESS project. Purpose of the visit included review of ongoing field activities and alignment with construction team.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Conducted a safety review of Sections 7.0 and 8.0 of the RFP-4899 proposal, which outline the implementation plan and technical methodology for the Costa Sur BESS project. The review focused on evaluating how safety is integrated into the proposed execution strategy, including sequencing of activities, contractor coordination, hazard anticipation, and reference to permitting requirements. Verified whether the plan includes adequate alignment with regulatory safety guidelines from OSHA, NFPA 855, and relevant Puerto Rico construction codes. Recommendations were noted to strengthen the proactive safety planning prior to mobilization.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued with the review of the Costa Sur BESS RFP-4899 proposal by evaluating the integration of HSE protocols within the project’s quality assurance and control framework. Focused on how safety checkpoints are embedded into the execution methodology and whether sufficient provisions exist for pre-task hazard assessments, safety audits, and contractor accountability. Reviewed documentation for alignment with OSHA 1926 subpart C (General Safety and Health Provisions), as well as NFPA 70E references for electrical hazard control. Observations were documented to support the development of a site-specific safety management plan that meets both Genera’s expectations and regulatory standards prior to contractor mobilization.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Participated in a safety coordination meeting Teams, led by Gilberto Sucre (DCMC) and Jean P. Menay (DCMC). All Safety Officers from each plant site were present. The session covered critical project-wide safety topics, including recent incidents and near-misses, weekly report expectations, required Procore entries, and coordination of joint safety walks with representatives from Genera and Lemoine Company. Additional discussions focused on the standard safety equipment required in office trailers, emergency procedures, and clearly marked evacuation routes. Action items were defined to ensure alignment across all sites and consistent implementation of safety protocols.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur - BESS- Review of latest drawing sent by Franklyn Colmenares (CDM Smith). The drawings sent are to be the issued for bid but are missing key components that were discussed internally by the Costa Sur Team; feedback will be provided to the S&L team next week, on our findings and notes of the drawing reviews
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur BESS Site Managers meeting was held during the morning; all site managers presented their issues by site lead by Gilberto Sucre [DCMC] these issues are then presented to GENERA for further development and/or solving. Coordination with DCMC Costa Sur team lead by Carlos Rodriguez, for advancement of current issues that include internal scheduling, site visits, design needs and drawing specifications.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue Reviewing Scope of Services for Technical Specification Number G-3300 and G-3400 for BESS General Work Contract (GWC) that will be issued for bid and completing the comparison report for Gilberto Sucre from DCMC Partners.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa A site meeting and walkthrough were conducted across both project areas (Peakers and BESS) with the community outreach teams from DCMC Partners and GENERA PR to review the project scopes, design layouts, and the physical areas that will be impacted. In this meeting participate Raisa Borges, Luz Ramirez, Gabriel Morales and Paola Arroyo from DCMC Partners, and Axel Rivera and Jorge Bracero from GENERA PR.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur BESS- Review of Specification No. G-3200 was initiated to ensure alignment with current industry standards, project-specific requirements, and regulatory compliance. The focus was on Divisions 40 (Process Integration) through 48 (Electrical Power), encompassing general administrative protocols, product requirements, and material specifications related to metals.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur -BESS Review of issue for construction drawings in order to scrutinize the layouts, cross-referencing dimensions, materials, and design intentions. Revise drawing note were raised about the placement of structural interfering with water flow drainage. As the review continued, the civil works between the site grading plan and the stormwater drainage details. These inconsistencies, if left unaddressed, could lead to costly rework during the site preparation phase. The issue was marked for immediate revision.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria As part of my responsibilities in enhancing site safety and compliance standards, I led the development of a comprehensive Safety Requirements Checklist Form tailored specifically for our construction site operations. The goal was to streamline daily safety inspections, ensure regulatory compliance, and promote a proactive safety culture among all personnel on-site. The process began with identifying key safety areas based on OSHA standards, project-specific risks, and company safety policies. I collaborated closely with site supervisors, safety officers, and project managers to gather input on high-risk activities, recurring issues, and practical inspection protocols. Using this information, I designed a user-friendly, checklist-based form that covered essential areas such as PPE compliance, machinery operation, scaffolding and ladder safety, electrical hazard controls, housekeeping, emergency access, signage, and fall protection measures. I ensured the form was structured to allow both digital and paper use, with space for inspector notes, non-compliance actions, and follow-up requirements. The checklist has been implemented across all active sites, significantly improving consistency in safety monitoring and documentation. Feedback from site personnel has been positive, citing improved clarity and ease of use. Regular updates are scheduled to keep the form aligned with evolving safety regulations and on-site needs.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria AGUIRRE BESS- Meeting with Carlos López, Sunem Martínez, and Luis Moctezuma (DCMC) to discuss project design status and general work contractor RG Engineering contract signage status. Discuss the proposed project's Look-ahead schedule. It was informed that the Issue for the Installation Bid award date has been delayed and has been moved forward to the end of August. As per the Issue for Construction Drawing, the delivery date has been moved forward to December 31, 2025. The team has been instructed to improve communication with the General Work Contractor, RG Engineering, but without requesting documentation related to the contract requirements until the contract signing is completed. Luis Moctezuma DCMC gave a brief description of the Safety Program Discussed in today's meeting. This meeting will be held every two weeks to set a standard in all the BESS and Pickers projects. And I developed a structured Inappropriate Behavior Reporting Form and Checklist for use on our construction sites. This initiative was driven by the need to establish a clear, consistent process for documenting behavioral incidents, promoting accountability, and supporting HR or management actions when necessary. I began by identifying the most common types of inappropriate behaviors encountered on-site—such as harassment, verbal abuse, insubordination, substance misuse, and unsafe conduct. Working closely with site supervisors, HR representatives, and safety personnel, I ensured that the form addressed both policy violations and safety-related behaviors that could jeopardize team morale or project integrity. The form includes key sections such as: Date, time, and location of the incident Employee(s) involved Detailed incident description Witness statements (if any) Immediate actions taken Checklist of behavior categories (e.g., safety violations, disrespectful conduct, substance-related concerns) Supervisor follow-up and resolution plan This tool was designed to be straightforward and confidential, ensuring supervisors and team leads can report incidents promptly and accurately, while giving HR and leadership teams the documentation needed for consistent disciplinary actions. Since implementation, the reporting form has improved transparency and accountability on-site. It has also reinforced expectations regarding conduct and created a clearer channel for escalating behavioral issues before they impact team performance or safety.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Safety Update Call with Gilberto Sucre, Jean Menay and the Safety employees DCMC at the Projects of Bess and Peaker's working at both the BESS (Battery Energy Storage System) and Peaker plant sites to align on current safety measures, coordinate ongoing work, and address any procedural gaps across the projects. The call began with a review of each site's current operational status, key hazards, and upcoming high-risk activities. I emphasized the importance of maintaining consistent safety practices despite the differing scopes and timelines of the two projects. Team leads from both sites provided updates on their specific workstreams, including electrical commissioning at BESS and mechanical installation at Peaker’s, highlighting any planned changes to site layouts, subcontractor activities, or equipment movement. We discussed coordination strategies to prevent cross-site incidents, particularly regarding contractor access control, communication during simultaneous operations, and alignment on lockout/tagout procedures. I reinforced the expectation that all teams must follow the updated site-specific safety protocols and reporting processes, including the daily JHA (Job Hazard Analysis) and incident escalation paths. In addition, we addressed recent observations and near-miss reports, focusing on lessons learned and corrective actions. This created an opportunity for cross-project learning and ensured that safety leadership remained proactive rather than reactive. The call concluded with an open forum for questions and concerns, allowing team members to raise logistical issues and propose improvements. Action items were assigned with clear deadlines, and a commitment was made to continue these bi-weekly calls to sustain strong communication and oversight.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Meeting with Carlos López, Sunem Martínez, and Luis Moctezuma(DCMC) to discuss project design status and general work contractor RG Engineering contract signage status. Discuss the proposed project's Look-ahead schedule. It was informed that the Issue for the Installation Bid award date has been delayed, and has been moved forward to the end of August. As per the Issue for Construction Drawing, the delivery date has been moved forward to December 31, 2025. The team has been instructed to improve communication with the General Work Contractor, RG Engineering, but without requesting documentation related to the contract requirements until the contract signing is completed. Luis Moctezuma DCMC gave a brief description of the Safety Program Discussed in today's meeting. This meeting will be held every two weeks to set a standard in all the BESS and Pickers projects.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with all site managers from DCMC: Andres Concepcion, Gabriel T. Morales, Carlos Rodríguez, Eduardo Rivera, Gilberto Sucre, and Raissa Borges (DCMC). A very brief description of the project's main activities, risks, and project needs was discussed for each project. From the Aguirre BESS site, the main activities are the RG Engineering notice to proceed expected date, the Sargent and Lundy Issue For Constructions Drawings deliverables date, the contractor entrance roads existing conditions, and who will be responsible for the maintenance and initial improvements. It was discussed that the new Genera Plan, which aims to accommodate temporary power equipment near the BESS project, could potentially conflict with the storm sewer discharge line as designed by Sargent and Lundy. A meeting will be coordinated with the plan manager to confirm this information.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the AGUIRRE BESS job site. Load the descriptions on the weekly Report link for the Aguirre BESS site, including current main activities, risks, needs, and distribution of responsibilities. Also, View Situations with issues, deliverables status, internal DCMC needs, and comments. Had a brief meeting with Carlos R. López Vallellanes and Luis Moctezuma (DCMC) to review the current project's main activities and follow up with the issue for construction design status. It was discussed that the new Genera Plan, which aims to accommodate temporary power equipment near the BESS project, could potentially conflict with the storm sewer discharge line as designed by Sargent and Lundy.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria AGUIRRE BESS PROJECT; Participated in Team Meeting with Sargent & Lundy Staff, Robert D. Molner; Gilberto Sucre (DCMC), Enrique Laya, Gabriel Pérez, Franklyn Colmenares, (CDM Smith), and Angel Alicea Rodríguez (Sargent & Lundy) to discuss the Phase II Request for Clarifications to the contract (4339_9510) documents.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Safety Update Call meeting coordinated by Frances Vallejo (DCMC) where Occupational Health and Safety topics were highlighted in each project and routine inspections.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Continued coordination efforts at the Cambalache site with Andrés Concepción (DCMC), Luis Damudt (DCMC), Jose Segarra (RGE), and Herminio Arroyo (GENERA) for the movement and registration of materials from the warehouse. Activities focus on ensuring proper tracking, documentation, and site readiness for material handling operations.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Visited the Cambalache site to attend a coordination meeting organized by Andrés Concepción (DCMC) with the contractor. The meeting was also attended by Luis Damudt (DCMC), José Segarra (RGE), and Herminio Arroyo (GENERA). Discussion focused on the mobilization and registration of warehouse materials, ensuring alignment between all parties for proper material handling and documentation procedures.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Performed survey on Plant entrabce to take measurements for a future sign or banner install for the project. Documented measurements and shared with Herminio Arroyo (GeneraPR for approval)
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Site visit and meeting with RGE (Jose Segarra), Herminio Arroyo (Genera PR), Paul Brown (DCMC Partners) to discuss regarding the Temporary Warehouse storage plan activities. A site walk through performed to survey existing inventory and to evaluate underground pipe lines to be relocated during demolition activities.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Received via Procore a submittal from Jose Segarra (RG Engineering) for the review and approval of a Gas Enclosure steel structure. Reviewed documents and sent to designer (Sargent and Lundy) Mike Kuscynski and Herminio Arroyo (GeneraPR) for review and comments
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated a plan for the Temporary Warehouse Storage logistics based on the agreement within Genera PR, RG Engineering and DCMC Team. Described all the activities and requirements to be covered on the inventory relocation task.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting organizer Frances Vallejo, Raissa Borges and Gilberto Sucre of DCMC and all site manager of BESS projects Carlos Rodriguez, Jose Lopez, Gabriel Morales, and Eduardo Rivera of DCMC - Construction status update for demolition and new construction of second phase. Meeting was provided an update status of Vega Baja Site regard of project closing, status of phase 2 with ARG/CERES and pending need items to be completed by Genera.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the revision of IFB drawing versus IFC drawing to identify posible impact change orders. Reviewing the capacity of the fire protection tank for Vega Baja site. Preparing site manager weekly report for presenting status of Vega Baja Site project. Reviewing submittal at Procore related to Homeca contractor final completion that was submitted and was forward to Frankly Colmenares of CSA Group.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing in Procore the Vega Baja specification entry in the system was noted that are (6) specification 051223, 081113, 099113, 312335, 400510 and 409513 was missing, send a text message to Luis Roman of DCMC to verify why they was not included and to see if he has the specification so it can be uploaded in Procore.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-oulined a preliminary plan for the Cambalache project, focusing on key logistical and operational elements needed to ensure a successful execution. This included defining the steps required to inventory the materials located in the building scheduled for demolition, identifying the types and quantities of containers that will be needed, evaluating the transportation options, and considering the personnel and equipment necessary for the task. The objective of this planning efforts is to ensure readiness, streamline the process, and anticipate any challenges that may arise once the operation begins.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a meeting with inventory team Mr. Juan Vallejo, Mr. Hernan Machado, Mr. Giovanni Taffanelli and Mr. Milton Flores from DCMC, to provide an early overview of the potential task we may be undertaking next week. During the meeting, I shared details about the recent discussion held in Arecibo with representatives from DCMC, Genera PR and RGE, explained the scope of the project we will be supporting. I also outline the type of work that will be required, along with specific conditions observed at the warehouse, to help the team better understand the environment and prepare accordingly.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a walkthrough of both the project site and the warehouse to assess the area firsthand. This allowed us to better identify key details and gain clearer understanding of the actual needs of the project, enabling us to plan and execute the upcoming tasks more efficiently and effectively.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while station at the San Juan warehouse, prepared and delivered a detailed inventory evaluation report for Mr. Anthony Vega of Genera PR. The document synthesized critical inventory data from various warehouse sites and provided a high-level operational summary. It included an analysis of stock quantities, cost variances, historical discrepancy patterns, and inventory levels relative to established thresholds. The report also incorporated performance indicators designed to measure inventory stability and assess overall operational preparedness. The scope of the report included locations BH 045 to BH 090, AC 001 to AC 016, CC 023 to CC 032, AJ 021 to AJ 023.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-continued working on the preparation of the operational plan for Cambalache project, focusing on refining key logistical components and resource allocation. This included defining personnel roles for both core inventory team and supporting staff, identifying equipment needs such as the label printing machine, and outlining the structure of the spreadsheet that will be used to track each inventoried item. Special attention was given to the process for assigning codes and creating detailed descriptions for undocumented materials, ensuring that all assets are properly cataloged prior to the building demolition. The goal remains to ensure an organized, efficient, and fully traceable inventory process.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-meeting at Cambalache Arecibo facility with Mr. Andres Concepcion from DCMC, Mr. Herminio Arroyo from Genera PR, Mr. Juan Alvarez and Mr. Carlos Negron from RGE. During the meeting, several nkey points were discussed, including the demolition timeline of the building, the number of containers required to store the parts, the logistics for transporting the materials, and the necessary resources to successfully carry out the inventory process.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS On site meeting to discuss Cambalache Schedule Activities, Silvia Franco, Andres Concepcion, Luis Duque, and Sylvia Franco DCMC Partners Cambalache Power Plant team.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Conducted technical review of architectural drawings for the Cambalache BESS project (PW9510) available on Procore, specifically focusing on proposed parking lot expansion and underground utility distribution systems. Interpreted design elements in relation to applicable zoning regulations, ADA access standards, and environmental compliance policies. Documented findings and flagged areas requiring further validation prior to coordination with external regulatory stakeholders.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS On site- Cambalache Warehouse Alignment Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque, Paul Browne, DCMC Partners Cambalache Power Plant team Jose Segarra, Juan Alvarado RGE.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents. Worked on all existing dwg from IFB & IFC to identify any possible change orders. today I finished reviewing all Civil drawings and started with Structural drawings.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents. Worked on all existing dwg from IFB & IFC to identify any possible change orders. today I continued working with structural drawings.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Started verifying OSHA documents send by Jean Menay. Entered Weekly meeting for safety officers DCMC team Gilberto Sucre, Frances Vallejo, Jean Menay.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 152 | 114 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations GA010 and AJ021 to AJ033
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations GA010 and A J021 to AJ033
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations GA010 and AJ021 to AJ033
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations GA010 to AJ021 to AJ033
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report GA010 and AJ021 to AJ033
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC 00 001 000 to AC 00 016 000
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC 00 001 000 to AC 00 016 000
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC 00 001 000 to AC 00 016 000
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BH 045 to BH 090, RECOUNT LIST #1342/1343/1348
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location Bh 045 to Bh 090
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BH 045 to BH 090 at the Aguirre warehouse to initiate the cycle counts.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre – Continued inventory verification at the Aguirre warehouse through the Asset Suite platform. This session focused on validating item counts and updating records for storage locations BH 046 to BH 072, referencing Recount Lists #1335/1338/1340 to ensure data accuracy and alignment with project asset control requirements.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CC023 to CC032
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CC023 to CC032 Cycle Count List # 1422.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1430 and 1431 from locations CC023 to CC032 for a total of 222 units.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 152 | 190 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CC023 to CC032 to begin the cycle counts.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the formulation of execution process for the Critical Components projects inside the Procore Platform: looking at Project's Submittals to identify Critical Components to begin tracking inside BESS and Peakers project's tools.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Continuation of Vega Baja BESS project review of all Procurement RFP & RFQ data in project folder for review_accuracy to make readily accessible & available for project teams/Siemens Costa Sur Peakers incoming documents Review & Process/RG Yabucoa BESS incoming documents review & process/
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 151 | 302 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Yabucoa BESS project review of all Procurement RFP & RFQ data in project folder for review_accuracy to make readily accessible & available for project teams/Peakers various projects-review of daily incoming documents for accuracy prior to processing
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Frances Vallejo (DCMC) to discuss current PMO ongoing procedures for Project Management, obligations from third-parties inside the Procore platform and implementation of new aggressive project management applications.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review for publishing the Vega Baja Technical Specifications: reviewing specs format, technical omissions and suggestions before publishing.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review BESS Technical Specifications to identify current formatting errors and technical omissions to be pointed out and discussed.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Sunem Martinez (DCMC) to provide an introductory workshop on the Procore platform at the Specifications, Submittals and Meetings tools: performed testing to review response procedures and taking action on items.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Weekly Meeting hosted by Franklyn Colmenares (CSA) and joined by Lauren Wells (Lemoine) and Monica Ybarra (S&L). Discussed the weekly progress on Procore open and pending topics: Specifications issues on formatting, update on Procore SOPs and the Financial Tool, and updates on Distribution Groups based on new enrolled staff, among others.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review for publishing the Vega Baja Technical Specifications: publishing final specs from the specifications book; reviewing the Submittals Section from specs to contrast with Procore required format.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Travel from Yabucoa to Daguao site to conduct a community mapping and walk-through of the area in order to organize the community plan according to the area we will be impacting related to the peakers project.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 139 | 347.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-A strategic visit was conducted at the Yabucoa site to assess potential locations for the installation of Peaker units and BESS. This site walk-through allowed for a deeper understanding of the project’s technical and logistical dimensions, including land layout, access to critical infrastructure, and factors that could impact both installation and operations. During the visit, detailed discussions took place regarding the equipment specifications, connectivity requirements, and operational considerations. A community mapping was also carried out to identify nearby communities and gain insight into the local population that may be directly impacted by the development. Participants in the visit included DCMC Partners: Gabriel Morales, Raissa Borges Almodóvar, and Luz Ramírez. Alex Rivera and Jorge Bracero from the Genera PR team were attending the visit
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Implement a series of edits to the factsheet for the BESS and Peakers projects, which we're preparing for an upcoming visit to Congress. Review all proposed modifications and make the necessary updates, especially those related to the project costs by site. Ensure the accuracy and clarity of the economic and financial information included. Coordinate a conversation with Rafael Rodríguez Ema from the Genera PR team to review and confirm the updates. Once finalized, I refine the design and presentation, so the factsheet is ready for use during the Congressional meeting.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Create the weekly report for updating the Genera PR website (https://genera-pr.com/bess_peakers). The task includes compiling and organizing all available project information by site, ensuring it reflects the most up-to-date status of each BESS and Peakers location. Once the data is collected, I write the full report ensuring it adheres to the format and communication style of the Genera PR website and send the completed report to the Genera PR Team, Jorge Bracero and Alex Valdés, for review, approval, and eventual publishing on the website.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Travel to Genera PR office Hato Rey from Daguao after a community mapping and walk-through of the area in order to organize the community plan according to the area we will be impacting related to the Peaker's project.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Travel from Genera PR office Hato Rey to the Yabucoa site to conduct a community mapping and walk-through of the area in order to organize the community plan according to the area we will be impacting related to the Peaker's and BESS project.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- PREPA Genera ¦ A strategic visit was conducted at the Jobos site to assess potential locations for the installation of Peakers units. This site walk-through allowed for a deeper understanding of the project’s technical and logistical dimensions, including land layout, access to critical infrastructure, and factors that could impact both installation and operations. Participants in the visit included Jorge Bracero and Omar Aponte Sosa from the Genera PR team.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 6) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures, Document Control Plan, Change Request (CR), Change Orders (CO) and Commitment Change Orders (CCO) to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 51 pages.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 134 | 268 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 25 pages.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing RG Engineering Quality Control Manual to verify the plan meets the required standards and specification to ensure all aspects of the projects will be executed correctly, safely and within the set guidelines. Reviewed 10 pages.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 134 | 134 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Meeting with Jose Lopez, Sunem Martínez, and Luis Moctezuma (DCMC) to discuss project design status and general work contractor RG Engineering contract signage status. Discuss the proposed project's Look-ahead schedule. It was informed that the Issue for the Installation Bid award date has been delayed and has been moved forward to the end of August. As per the Issue for Construction Drawing, the delivery date has been moved forward to December 31, 2025. The team has been instructed to improve communication with the General Work Contractor, RG Engineering, but without requesting documentation related to the contract requirements until the contract signing is completed. Luis Moctezuma DCMC gave a brief description of the Safety Program Discussed in today's meeting. This meeting will be held every two weeks to set a standard in all the BESS and Packers projects.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Conducted a safety review of Sections 7.0 and 8.0 of the RFP-4899 proposal, which outline the implementation plan and technical methodology for the Costa Sur BESS project. The review focused on evaluating how safety is integrated into the proposed execution strategy, including sequencing of activities, contractor coordination, hazard anticipation, and reference to permitting requirements. Verified whether the plan includes adequate alignment with regulatory safety guidelines from OSHA, NFPA 855, and relevant Puerto Rico construction codes. Recommendations were noted to strengthen the proactive safety planning prior to mobilization.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Continue evaluation contractor QAQC manual (RG Engineering.) included Site Work requirements, work construction process and materials used on various areas of the project (QAQC Codes and Standards) include specific equipment used for construction and suggested preparing checklist forms to complete inspections for installing material and constructions process.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for BESS project considering construction in BESS project time line concrete pads for transformer 1 area, construction pads and wall planning with formworks detailing, underground pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for BESS project considering construction in BESS project time line of structures to demolish at site, concrete pads construction planning with formworks detailing, underground pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. On site- Cambalache Warehouse Alignment meeting with Andres Concepcion (DCMC) and Jose Segarra (RGE) for the 4339_9510 BESS_Cambalache project to discuss warehouse equipment inventory and removal to set the site for demolition work.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 122 | 30.5 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting to review site managers' updates for the BESS and Peakers projects. Attendees DCMC: Gilberto Sucre, Gabriel Morales, Eduardo Rivera and others
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2.5 | 122 | 305 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Site visit to Yabucoa BESS and Peakers project with DCMC team Paola Arroyo, Gabriel Morales and Jorge Bracero from Genera for community outreach and reporting purposes.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 122 | 30.5 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Reviewed an incoming email related to the BESS and Peakers project. Verified alignment with current milestones and prepared a brief response to confirm receipt and ongoing review by the project team.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 122 | 488 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Incorporating Gilberto Sucre’s, DCMC insights and recommendations to enhance the Safety Officer report template, ensuring more effective documentation of site-specific activities, inspections, and incidents.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting to review and discuss Safety Officers activities and updates for BESS and Peakers projects. Attendees DCMC: Gilberto Sucre, Frances Vallejo, Jean Pierre Menay, Luz Ramirez and others
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Franco Malave, Sylvia | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 6.25 | 6.25 | 6.25 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria – travel to Cambalache Power Plant for Meeting and Site Visit with Segarra (RGE), Herminio Arroyo (Genera), Andres Concepcion (DCMC), Carlos Negron (RGE), and others.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Borges, Raissa | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 0.7 | 51.73 | 0.7 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Site visit to Yabucoa BESS and Peakers project 10710 with DCMC team Paola Arroyo, Gabriel Morales and Jorge Bracero from Genera for community outreach and reporting purposes.
2025-07-11 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Franco Malave, Sylvia | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 0.7 | 52.78 | 0.7 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria– Traveled from 1166 C. Finlandia, Toa Alta, 00953 to Cambalache Power Plant and return travel to 1166 C. Finlandia to meeting coordination and site visit with Segarra (RGE), Herminio Arroyo (Genera), Andres Concepcion (DCMC), Carlos Negron (RGE), and others.
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence Review and Filling of emails and attachments related to * IT/OT Communication Location drawings at Cambalache, Costa Sur and Aguirre. * Value Engineering SOW for TRC Services of SME for Design Audit * Palo Seco BESS Layouts, S&L Turnover Package * GENERA NGR Quotes
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continued Review of IFC Drawings Dated 7/10/25 including Action Tracker identifying all disciplines "On Hold". Drawing Sets include Civil, Structural, Fire Protection and Electrical drawings in excess of 110ea.
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur BESS Review of IFC Drawings Dated 7/10/25 including Action Tracker identifying all disciplines "On Hold". Drawing Sets include Civil, Structural, Fire Protection and Electrical drawings in excess of 110ea.
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Review and Approval of CDM Smith Invoices # 293410-12 Jan 2025 & # 293410-16 May 2025 after verification of Maria Sanchez - Genera Authorization Memo dated 2/14/25.
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Supervise with Gabriel Morales (DCMC) the electrical work performed by Eric Arroyo, Ricardo Vega and Javier Arroyo from J Arroyo Enterprise to repair the main electrical connection to energize the DCMC Partners Mobile Office at the Yabucoa site.
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Continuing Yabucoa Supervise with Gabriel Morales (DCMC) the electrical work performed by Eric Arroyo, Ricardo Vega and Javier Arroyo from J Arroyo Enterprise to repair the main electrical connection to energize the DCMC Partners Mobile Office at the Yabucoa site.
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 167.25 | 167.25 | 167.25 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Receipt for the purchase of the safety boots.
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Supervise with Jean Pierre Menay (DCMC) the electrical work performed by Eric Arroyo, Ricardo Vega and Javier Arroyo from J Arroyo Enterprise to repair the main electrical connection to energize the DCMC Partners Mobile Office at the Yabucoa site.
2025-07-12 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 46.69 | 0.7 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Supervise with Gabriel Morales (DCMC) the electrical work performed by Eric Arroyo, Ricardo Vega and Javier Arroyo from J Arroyo Enterprise to repair the main electrical connection to energize the DCMC Partners Mobile Office at the Yabucoa site.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 2450 | 2450 | 2450 | Yes | 146795 | J Arroyo Enterprise - Repair of 100 amp meter base and rewiring of service connection
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Powerpoint for Gilberto Sucre (DCMC) and Frances Vallejo (DCMC) for presentation to Jesus Citron (Genera) for an update on Procore.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR-Deliverable 11 – Project Management- DR 4339 – Hurricane Maria Project #4339-10710 Reviewed project-related email correspondence for the Peakers Project to track updates, clarify outstanding items, and ensure alignment across teams on ongoing tasks and deliverables.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 225 | 562.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 BESS/PEAKER's project needs meeting. weekly catch up meeting with Genera to discuss any open items and status review of the projects German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 225 | 562.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 BESS/ PEAKERS TRC drawing and schedule review participated in meetings with new engineering company to review current status of drawings and schedule review of all the projects. participated in meeting Eliot diazatienza - trc companies German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Gilberto Sucre DCMC
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in meeting for peakers Discussed document controls and procore uses participated in the meeting German Núñez, GENERA Rafael Pabon, CDM Smith
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One pager weekly progress update review with Raissa Borges DCMC.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria RGE Contract verification details discussions with Francsico Feliu - Genera Legal and Jose Robles - RGE on Costa Sur and Aguirre P & P Bond cost and Cambalache Performed Specifications.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check-in Weekly Meeting led by Gabriel Perez CDM Smith provided update of all BESS projects, contract award status, RFP's, Permitting and Project Needs from Genera. Updated Tracker to be issued after meeting. Participants: Carlos Palomares, Enrique Laya - CDM Smith Franklyn Colmenares _ CSA Group Frances Vallejo & Gilberto Sucre - DCMC Mike Kuczynski - Sargent & Lundy
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Call with Carlos Hernandez - ARG Ceres to discuss Demolition Contractors and Fire Protection Evaluation
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache update call with Andres Concepcion, DCMC to discuss temporary construction parking and warehousing inventory.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore General Update discussion with Lauren Wells and Frances Vallejo, DCMC.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM Weekly update meeting with Franklyn Colmenares - CSA Group & Gabriel Perez - CDM Smith.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria GENERA - TRC BESS & Peakers Design SME Discussion: * Preparation time of BESS status Construction. * Franklyn Colmenares CSA Group presented BESS Status Update and Gilberto Sucre, DCMC Presented Construction status and design progress between IFB's and IFC's and priority of TRC SME support on Mechanical & Electrical Trades. * Rafael Pabon - CDM Smith presented Peakers Overall Program
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed the EHS Site Specific workshop provided Jean Pierre Menay - DCMC for Cambalache, Costa Sur, and Vega Baja.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Project Needs meeting with Jesus Cintron - Genera. Gabriel Perez - CDM Smith presented BESS Needs and update to Genera German Nunez - Genera & Rafael Pabon - CDM Smith presented Peaker's Attendence: CSA Group - Franklyn Colmenares DCMC - Abraham Velazquez, Frances Vallejo, & Gilberto Sucre
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore DCMC Financials SOP's Meeting to review and continue development of SOP's led by Lauren Wells DCMC. Other participants Rafael Calderon, Esther Rohena, Jose Ralat & Gilberto Sucre DCMC.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Ricardo Pallens (Genera), Carlos Palomares (CDM Smith), Joaquin Quinoy (Genera), Gabriel Perez (CDM Smith), Mike Kuczynski, Nelson Rosado (Sargent and Lundy), Franklyn Colmenares (CDM Smith), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Follow up meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (Lemoine).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) and Luis Roman (DCMC) for Procore weekly check-in to discuss open items as a team.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Frances Vallejo (DCMC) and Gilberto Sucre (DCMC) to discuss internal Procore items.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations and review of PM SOPs.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore testing of workflows in Sandbox project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for BESS Check-in.Franklyn Colmenares (CSA), Frances Vellajo (DCMC), Franklyn Colmaneras (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reports.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for Peakers Check-in.Rafael Pabon (CDM Smith), Frances Vellajo (DCMC), Franklyn Colmaneras (CSA), Mike Kuczynski (Sargent & Lundy), Rafael Calderon (DCMC), and others attended. I was there to update on Procore items.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Rafael Calderon (DCMC), Glorimel Torrado (DCMC), Johanna Diaz (DCMC), Gilberto Sucre (DCMC) and others to discuss Procore Financial SOPs.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting to show user metrics.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.75 | 184 | 690 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated the Genera Connect Financial Tracker with the most recent financial data in preparation for the upcoming weekly Genera PR update meeting. Addressed server access issues affecting the ability to publish updates to both the Financial Tracker and Timesheets modules within the Genera Connect platform. Additionally, reviewed IT/OT Project Manager candidate resumes shared by Nyah Medina and Michael Merritt from DCMC, and developed a role compatibility matrix to assess candidate suitability for interview consideration in support of federally funded project efforts.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Continuing Review documents about "GENERATION FLEET STORAGE PROJECTS" and Fire System Documents in Cambalache Site.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review documents about Yabucoa activity repairs from JArroyo Enterprise. Review documents about Tesla delivery's Bess to Cambalache. Conference call with Gabriel Morales and Luz Ramirez (DCMC) about Health and Safety Topics about Yabucoa Genera Project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review documents about "GENERATION FLEET STORAGE PROJECTS" in Cambalache Site.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Discussion with Abraham Velazquez (DCMC) via call regarding Peaker's alignment and project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR -Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Discuss with Jean Pierre Menay (DCMC) the logistics for the Aguirre and Yabucoa equipment and materials.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR- Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended meeting with Raissa Borges (DCMC) to discuss project controls opportunity at Yabucoa site.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and analyze Procore presentation in preparation for meeting with client.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 184 | 230 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended internal Teams meeting with Lauren Wells and Gilberto Sucre (DCMC) to discuss Procore status, Procore modules, Procore financials and presentation that will be prepared for the client.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Teams call with TRC and CDM Smith to discuss BESS and Peaker Design discussion with S&L. Attendees: Eli Diaz (TRC), Javier Cuadrado (TRC), Gilberto Sucre (DCMC), Gabriel Perez (CDM) and Franklyn Colmenares (CSA).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended teams meeting with client (Jesus Cintron, Genera) and project management team for PMO, to discuss BESS and Peaker project needs and pending issues. Attendees: Gabriel Perez (CDM), Sheila Torres (DCMC), Abraham Velazquez (DCMC) and Rafael Pabon (CDM).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in BESS and Peakers check in calls to discuss RFP's in process, contracts pending approval, project status, and Procore proccesses. Attendees: Gabriel Perez, Carlos Palomares, Rafael Pabon (CDM), Gilberto Sucre, Sheila Torres, Rafael Calderon, Raissa Borges, Paola Arroyo (DCMC).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - PW11855 - Continued preparing the response to FOMB’s RFI concerning the Second Amendment to Contract No. 102696. Requested and reviewed the full procurement file to confirm the materials previously submitted to FOMB. This review was necessary to ensure accuracy and alignment in drafting the response to RFI No. 1 related to a discrepancy between the awarded amount and the BAFO.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 184 | 644 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - PW11855 - Prepared the revised justification memo for the Second Amendment to Contract No. 102696. Incorporated background on the contract and prior amendment, detailed the need for additional funds to support expanded program management at multiple Generation Fleet sites, and clearly articulated the operational urgency due to the current Project Manager’s underperformance. Developed language explaining the readiness to assume the role, ensuring a smooth transition and continued progress on federally funded projects. Revised content for clarity, tone, and alignment with Genera’s internal and external messaging. Shared with Winnie Irizarry and Jesus Cintron (Genera) for review and feedback.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 184 | 230 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Frances Vallejo, Rafael Calderon. S&L: Mike Kuczynski. Genera: Jesus Cintrón
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Verified the status of key workstreams and high-priority items related to procurement activities and contract submittals requiring approval from FOMB and P3A. This review was conducted in preparation for the weekly BESS and Peakers Project Needs meeting, ensuring up-to-date information was available to support informed decision-making and effective project coordination.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly check-in meeting for the Peakers projects. Reviewed current progress, discussed ongoing procurement efforts, and addressed any challenges impacting project schedules or deliverables. CDM Smith: Rafael Pabón, Franklyn Colmenares, Enrique Laya, Carlos Palomares. S&L: Mike Kuczynski (S&L), DCMC: Rafael Calderon, Frances Vallejo. Genera: Jesus Cintron.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today dumpster truck arrived to empty trash container, the portosan arrived to clean DCMC bathrooms, and Rod Roger’s verified the disposal from dirty water on new trailer.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I continued reading about the Occupational Health and Safety Program concerning the following topics: Hazardous Materials (29 CFR 1910 Subpart H), Personal Protective Equipment (29 CFR 1910 Subpart I), and Hazard Communication (29 CFR 1910.1200).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 167 | 41.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I met with Jean Pierre Menay, DCMC to discuss the documents and inspections that the contractor will be required for the project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I read about the Occupational Health and Safety Program regarding the following topics: Scaffolding (29 CFR 1926 Subpart L), Confined Spaces (29 CFR 1910.146), and Occupational Exposure to Noise (29 CFR 1910.95).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I continued with the module on the Procore platform. The Procore module covered the following modules: - Coordination Issue: Create a coordination Issue, Dashboard and Exports Overview, Designer and Detailer workflows, elevate to an RFI, getting started, import viewpoints save an NWD file, syncing and tracking changes, and view coordinator issues. - Correspondence: Change the status on a correspondence item, create correspondence item, respond to a correspondence item, tool permissions, and view and respond to a correspondence item.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the AGUIRRE BESS job site. Daily project coordination and project management. Project Documents Overview and analyzing documents status in the Procore platform.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (RG Engineering) and the Owner Genera PR. There are drawing pages included on the list of drawings, but the drawing was not included in Appendix 1, "Design Drawings".The Scope of the Specification includes site grading, drainage, surfacing, foundations, underground utilities, including embedded electrical conduits and duct banks, fire protection systems, a stormwater sewer system, as well as all substructure foundations and Pads for the Project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Call with Carlos Lopez- QA/QC- (DCMC) at Aguirre, to discuss the QA/QC plan submitted by the Contractor RG Engineering for the Aguirre Project. The main subject of the call was to discuss the possibility of having a QA/QC plan completed by DCMC Partners to review and evaluate the applicable conditions for the Aguirre Project. At this moment, a follow-up meeting should be held with Gilberto Sucre (DCMC) to verify the Document Status for evaluation. It was also agreed to perform a weekly meeting with all QA/QCs to discuss the need for the QA/QC plan.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 668 to 684. Among the topics read were fiber optic patch panel (nameplate, tags, specific product, prohibited materials, testing), main power transformer (two phases, work by contractor, control devices, small wiring, inspection, tests).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue reading specifications from page 631 to 667. Among the topics read standard pipe supports (finish requirements, erection, installation, fabrication requirements), supervisory data acquisition system (SCADA software, monitored equipment, process logic, scheduling/control, networking, access level, remote access, cyber security, commissioning).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – I read the minute number 8 of the Construction Project which have 9 pages and read to preparation of the agenda for tomorrow meeting morning which have 7 pages.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I read the minute number 4 of the Construction Phase II which have 7 pages and read to preparation of the agenda for tomorrow meeting morning which have 6 pages.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I studied the document of Summary of Work (SOW) of Beta Electric in Vega Baja BESS where see the construction work on site.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Conducted a detailed review of the Costa Sur BESS design drawings to identify any missing items, incomplete details, or open technical comments. The objective was to prepare a comprehensive list of observations to support coordination with the design team and project stakeholders. The review focused on layout consistency, equipment labeling, structural references, and civil interface points. All findings were documented to facilitate resolution prior to final design approval and construction planning.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Participated in two internal coordination meetings related to the Costa Sur BESS project. The first meeting, led by Carlos De Jesus (DCMC), focused on reviewing and aligning the overall project schedule, including key milestones, sequencing of deliverables, and coordination with subcontractors. Emphasis was placed on integrating HSE planning checkpoints into the timeline. The second meeting, led by Rafael Barrera (DCMC), involved a technical review of the Costa Sur BESS design drawings. The discussion covered layout coordination, potential conflicts, and clarification of civil and structural details. Notes were taken to support follow-up evaluations and ensure consistency between the construction plans and project requirements. Team Members participants (DCMC): Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur- BESS DCMC Site Scheduler team meeting lead by site manager Carlos Rodriguez and Scheduler Carlos Dejesus (DCMC) discussion with Rafael Barrera (DCMC PM) to arrive on dates and lengths on contractor activities and scheduling for certification. Additional to these dates the dates of equipment arrival are included in the preliminary schedule.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur - BESS- Request for proposal review of Section 301.2 Classification of Excavation. Categorized excavation types: Earth, Rock, and Hand Excavation. Reviewed hand excavation protocols near sensitive structures. Compared OSHA excavation definitions to ensure alignment with drawing standards.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the BESS Checking Project Needs Tracker received from the CDM Smith Team.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Yabucoa – Conducted an on-site meeting with Luz Ramírez, Safety Officer for the Yabucoa Site (DCMC Partners), to review and discuss site-specific safety documentation, including Job Hazard Analyses (JHAs), Emergency Response Plans (ERPs), and other procedures. Addressed compliance requirements under OSHA and applicable Puerto Rico regulations, ensuring alignment with FEMA DR4339 project safety protocols. Additionally, held a follow-up call with Jean Pierre Menay, Safety Manager (DCMC Partners), to clarify outstanding questions and confirm next steps for updating and finalizing safety documentation for submittal and regulatory review.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Reviewing Scope of Services for Technical Specification Number G-3200 for BESS General Work Contract (GWC) that will be issued for bid and completing the comparison report for Gilberto Sucre from DCMC Partners
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Participated in two internal coordination meetings related to the Costa Sur BESS project. The first meeting, led by Carlos De Jesus (DCMC), focused on reviewing and aligning the overall project schedule, including key milestones, sequencing of deliverables, and coordination with subcontractors. Emphasis was placed on integrating HSE planning checkpoints into the timeline. The second meeting, led by Rafael Barrera (DCMC), involved a technical review of the Costa Sur BESS design drawings. The discussion covered layout coordination, potential conflicts, and clarification of civil and structural details. Notes were taken to support follow-up evaluations and ensure consistency between the construction plans and project requirements. DCMC Team Members participants: Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Conducted a detailed review of the Costa Sur BESS design drawings to identify any missing items, incomplete details, or open technical comments. The objective was to prepare a comprehensive list of observations to support coordination with the design team and project stakeholders. The review focused on layout consistency, equipment labeling, structural references, and civil interface points. All findings were documented to facilitate resolution prior to final design approval and construction planning.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We are working on created different form to conducting themes of Safety, Health and Enviromental to train employees of the Contractors are works on Bess_Aguirre Project in Safety and Occupational Health Talk: Earthworks in Construction Projects, Safety and Occupational Health Talk: Use of Personal Protective Equipment (PPE) in Construction, Safety and Occupational Health Talk: Fire Control in Construction Projects, Safety and Occupational Health Talk: Prevention of Trips, Slips, and Falls in Construction, Occupational Safety and Health Talk: Eye Protection in Construction Projects.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We are continue working on created different form to conducting themes of Safety, Health and Enviromental to train employees of the Contractors are works on Bess_Aguirre Project in Safety and Occupational Health Talk: Ear Protection in Construction, Safety and Occupational Health Talk: Respiratory Protection in Construction, Occupational Safety and Health Talk: Cutting Steel and Wood in Construction, Safety and Occupational Health Talk: Safe Use of Electric and Battery Tools in Construction, Safety and Occupational Health Talk: Safe Use and Handling of Heavy Machinery in Construction, Safety and Occupational Health Talk: Risk Communication in Construction Projects.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the Issue bid drawings documents, TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC) Spec. No.: G-3400 Revision: A; For Bid Project No. A15240, June 20th, 2025to identify potential and possible change orders, as well as potential issues that may arise during the construction process. A call was held with Jean Pierre Menay (DCMC) to go over the pending safety protocols and the General Contract Safety Plan. The official document has not been received pending completion of the contract signing. The contract is still under evaluation by Genera PR.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the Issue bid drawings documents to identify potential and possible change orders, as well as potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects to be integrated into the PROCORE platform, and a call was held with Javier Ignacio from Portosan to coordinate equipment delivery to the Aguirre Site.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Luis Moctezuma (DCMC) to identify existing trip hazards surrounding the Office Trailer Compound and potential issues that may arise during the construction process. We had a brief team meeting with Carlos R. López Vallellanes, Sunem Martíne, and Luis Moctezuma (DCMC) to go over the week's plan and schedule tasks. The team has been instructed to review the Contract Specification. Spec. No.: G-3400 Revision: A; For Bid Project No. A15240 June 20th, 2025. The finding will be tabulated and discussed in a future meeting.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - The Transportation Management PlanTesla Energy Cambalache Project Site submitted by the equipment transporter is verified.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Comments were provided on the Tesla Energy Cambalache Project Site Transportation Management Plan submitted by the equipment transporter. Road transportation procedures were implemented to ensure compliance with local laws.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Monitored and managed pending submittal responses in Procore that were needed to be communicated formally to general contractor and be able to revise a resubmit pending information and documents.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated Cambalache Construction Weekly meeting agenda in Procore to capture this week discussion and pending actions to be covered with the project team (Sargent and Lundy, RG Engineering, GeneraPR and DCMC)
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed correspondence (emails) to follow up with important project action items. (1) Emailed to Gilberto Sucre (DCMC Partners) and Gabriel Perez (CDM Smith) regarding Construction temporary Parking impact and potential budget claims from General Contractor. (2) Email coordination request to Paul Browne (DCMC Partners) to begin the Inventory activity in the existing warehouse that will be demolished in the project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed project Fire Protection drawings and project specifications to compare with scope of work in the agreeement with General Contractor (RG Engineering) to define design requirements. Communicated with Wilfredo Sierra (Sargent and Lundy) to request a technical discussion meeting regarding this matter.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Reviewed TESLA Batteries Transportation plan draft received form Gabriel Perez (CDMSmith) to provide comments and concerns to be implemented in the final transportation plan by TESLA company.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated various project and construction management tasks. (1) Phone Call with Gilberto Sucre (DCMC Partners) to discuss project critical items to be solved during the week. (2) Coordination commencement to receive Jesus Cintron (GeneraPR) on site by July 17, 2025. (3) Distributed Cambalache Meeting agenda via Procore. (4) Reviewed project Division of Responsibility Matrix to identify contractor scope of services regarding pre-construction stage.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with two agenda meeting for tomorrow meeting with Homeca and ARG/CERES. Send email to Carlos Lopez of Sphera Group in regard of Final Report of PUI that must be included with all stamps from DRNA. Send a text message to Gilberto Sucre in regard of Genera decision to not pursue the precast for Vega Baja BESS project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working in review of IFC drawing versus IFB. Contractor Dueñas Trailer arrive to install stair at the second office trailer of Vega Baja site. Send email to Mike Kuczynski of S&L requesting information if guard house and electric gate has backup power and if project was considered safety shower station at site near battery.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with reviewing all project open RFI and Submittal pending to be responded. The As-Built drawing sent by Homeca does not came with a revised drawing and they are requesting additional cost to include the requested survey, email was sent to Carirma Sanchez of Homeca that the As-Buil drawing does not comply with project specification and requirement this drawing has been rejected and to resubmit.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled cycle count activities across inventory zones MM 001 through MM 012 as part of routine inventory governance. The effort included validating bin level inventory counts, reviewing physical versus system records, and verifying the accuracy of item labeling and placement. Supplementary tasks involved documenting any identified variances, evaluating data consistency, and confirming adherence to established inventory protocols and compliance standards.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-supported cycle count preparation at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. Task included verifying physical item locations, updating inventory system entries, and reviewing discrepancies to ensure data accuracy. Additional efforts were directed toward refining resource allocation and confirming system readiness to enable a smooth and consistent execution of upcoming inventory activities. Today efforts will concentrate on locations MM 001 to MM012.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-initiated the workweek with a coordination meeting alongside Hernan Machado, Giovani Taffanelli, Milton Flores and Juan Vallejo from DCMC, to reestablish alignment on inventory management protocols. The session emphasized reinforcing procedural consistency at the start of operations, reviewing material handling standards, and synchronizing team efforts to maintain workflow integrity. Priority was given to safety compliance, clarity in task delegation, and early identification of any process anomalies or risks impacting inventory performance.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a targeted inventory recount at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. The effort focused on verifying storage bin assignments, validating part numbers and item descriptions, and reconciling physical stock against system records. Identified discrepancies were documented for resolution, with emphasis placed on traceability, data integrity, and compliance with asset control standards. Inventory locations reviewed ranged from MM 001 through MM 012.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-prepared a consolidated inventory performance report at the Aguirre warehouse for Anthony Vega from Genera PR. The report included catalog validation, unit count analysis, and discrepancy metrics across locations MM 001 to MM 012, AC 017 to AC 060, AJ 034 to AJ 050, CC 033 to CC 046, with a focus on stock accuracy, coverage, and overall inventory conditions.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a targeted variance analysis at the Aguirre warehouse to investigate inventory discrepancies previously identified during cycle counts. The review included cross checking system entries, validating bin assignments, and conducting physical inspections of storage zones to identify missing, excess, or misallocated items. The primary goal was to confirm stock accuracy, determine root causes of the variances, and document actionable findings for resolution. Inventory zones reviewed range from MM 001 through MM 012.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- 4339_9510 BESS Review emails Transportation plan for TESLA batteries and technical data of batteries and type of transportation sent by Andrés Concepción of DCMC for the Integra meeting and the evaluation, analysis of the Cambalache access bridge.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the Submittal #: RGE-0011 Road modification suggested to reach the levee without affecting dyke capacity and Submittal #: RGE-0007 RG Engineering Safety Manual sent by Andres Concepcion from DCMC and other emails.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the Submittal #: RGE-0002 Temporary Mechanical Connection to Existing Transformer T1 send by Andres Concepcion from DCMC and other emails.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Reviewed all RFi's opened for tomorrow's BESS Phase II - Construction Meeting (Rfi # 003, Rfi # 004, Rfi # 006 & Rfi 007,3Rfi, 009,RFi#10). Closed Rfi#3. Completed Documents Overview and analyzing documents. Also worked on all existing dwg from IFB & IFC to identify any possible change orders.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Answered Submittal #84. Closed RFi #4 (New Concrete Pad Dimensions on S&L court). Worked on all existing dwg from IFB & IFC to identify any possible change orders, today the task was completed.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today dumpster truck arrived to empty trash container, the portosan arrived to clean DCMC bathrooms, and Rod Roger’s verified the disposal from dirty water on new trailer. Duenas trailer arrived at 1:00pm to install stairs for the new trailer.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AJ034 to AJ050
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AJ034 to AJ050
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AJ034 to AJ050
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AJ034 to AJ050
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AJ034 to AJ050
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC 00 017 000 to AC 00 060 000
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC 00 017 000 to AC 00 060 000
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC 00 017 000 to AC 00 060 000
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location MM 001 to MM 012
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations MM 001 to MM 012, RECOUNT LIST #1363 AND LIST #1353
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations MM 001 to MM 012, LIST #1349/1350/1351/1352/1353
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations MM 001 to MM 012 at the Aguirre warehouse to initiate the cycle counts.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CC033 to CC046.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1452, 1453, 1454 and 1455 from locations CC033 to CC046 for a total of 493 pcs.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CC033 to CC046 Cycle Count List # 1449.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CC033 to CC046 to begin the cycle counts.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Verify the information recently uploaded to the Documents Tool to verify environmental compliance on demolition and disposal works from Vega Baja.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Cost Sur Peakers Invoices review & process/Cambalache Invoices review & process/CDM San Juan Invoices review & process/Yabucoa BESS Procurement RFP-RFQ review & process/Coordination regarding hot topics w Lauren Wells (DCMC) & Luis Roman (DCMC)
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Costa Sur Peakers Procurement all RFPs &RFQ ensure documents were created_reviewed_stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team/Cambalache Geotech Testing Logs incoming review and process
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Perform testing of the workshop project to verify Procore reaction to different formatting on documentation and confirm what features are enabled with proper format (Specifications Tool).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Finish the reviewing and publishing process for the uploaded Vega Baja Technical Specifications. Commentaries and omissions found were all addressed on a working spreadsheet for upcoming discussion with management.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the proper alignment for the Warehouse Inventories across the plants to introduce them into the proper filing systems. Inventories are not related to project type (BESS or Peakers); are independent and per plant.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - BESS Weekly Project Catch-up hosted by Gabriel Perez (CDM Smith) and joined by Mike Kuzcynski (S&L), Gilberto Sucre, Frances Vallejo and Paola Arroyo (DCMC), Jesus Cintron (Genera) and other staff members. Discussed the weekly open topics such as open RFP's for construction procurement, issues with the Aguirre site referent to an ongoing project inside the plant, Procore progress and execution, and others.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Weekly Check-in with Lauren Wells (Lemoine) and Theresa Perez (DCMC) to discuss the weekly topics and ongoing procedures of the Procore Platform. Discussed the upcoming meetings with field staff to clarify responses procedures and documentation pending regarding contractor's invoices.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Peakers Weekly Meeting hosted by Rafael Pabon (CDM Smith) and joined by Mike Kuzcynski and Nelson Rosado (S&L), Rafael Calderon, Raissa Borgers, Paola Arroyo and Frances Vallejo (DCMC) and Lauren Wells (Lemoine). Discussed the open RFPs for upcoming procurement decisions, pending change requests to reduce contract costs, other changes for substations, documentation needed and more.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Meetings Tool at the Vega Baja project to make corrections on Meetings #4 and #5 due to missing attendance list and for follow-up meeting.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Continue initial evaluation for the Yabucoa Technical Specifications package; review formatting and contents.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-Create invitation for the third community meeting in Arecibo. This task included working on the design in Canva along with the information that would be used to share the information. In addition to selecting the design, the photos that would be used to illustrate the invitation were searched, which were photos of the site and the render.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander González, Rafael Calderón, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey. In the meeting was the Genera PR Team: Jesús Cintron, Joaquín A Quinoy, Ricardo Pallens, María Sánchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczynski and Nelson Rosado. At the meeting we talked about the signs that must be placed on the sites, the steps that are being taken to move forward with the BESS project, the tests that will be carried out on the Cambalache bridge and the efforts we have made in relations with the community.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-Reviews to the BESS/Peakers page ¦ Genera PR. Send corrections that had to be integrated into the Genera PR team, Alex Valdez and send corrections to the Genera PR team, Jorge Bracero, to the signs that would be placed on all sites. These tasks included reviewing the website as well as the signs sent, confirming the information with the available documents, and sending corrections by email.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146795 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-Update the Community Outreach 2025 work plan document to include the latest details related to this week's pending tasks and edit some details related to the report that must be submitted every Monday for the BESS Check In
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA Genera ¦ Deliverable 11 DR 4339 Hurricane Maria- Project Management Community Engagement Create a report to present the work done by Community Engagement. These tasks included drafting the updated report, validating the efforts we have on the agenda as well as locating the follow-up to the status of the conversations with the municipality for the next community meeting. This calendar will be presented at the BESS Check In meeting and the email was sent to the Genera PR team, Jorge Bracero.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-¦ Edit the fact sheet that includes all the information related to the BESS and Peakers project that would be used to present it to the stakeholders. This task included searching for the photos, creating the draft in Canva, adjusting the text copy to highlight the stages of the project, including the data related to the project, creating three versions to present to the client Genera PR, and organizing the file and organizing the file.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-Update the community calendar with the activities that would be carried out throughout the year. This task included meeting with the Genera PR team, Jorge Bracero, to talk about the events that we have pending on the agenda and support to create these events in a virtual calendar to have greater visibility of each of the events.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339-PREPA Genera ¦ Meeting about the peakers update with DCMC Partners Team: Frances Vallejo Rosich, Luis Roman, D'Alexzander González, Rafael Calderón, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey and Abraham Velazquez. In the meeting was the Genera PR Team: German Nuñez, Joaquín A Quinoy, Ricardo Pallens, Fernando Ortiz Meléndez, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczynski, Miguel del Valle and Nelson Rosado. In this meeting we discussed the spaces in Aguirre that we need for the Peakers project. The timeline of the project and LUMA's process in relation to some projects that must be worked on, pending prices from the contractor to be able to move forward with the demolition, and the changes that may need to be implemented in the project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 7) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures, Document Control Plan, Extra Work Authorizations (EWA’s) and Architect’s Supplemental Instructions (ASI’s) to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Conducting a comprehensive review of the BESS Aguirre Power Plant Procore documentation, encompassing the following folders: 0900_QA/QC-Construction Reports (Vendors-Subcontractors); 0925_Equipment Information; 0950_Commissioning-Decommissioning; 1000_Health-Safety (Vendor-Subcontractor); 1100_Financials-Accounting (Vendor-Subcontractor); 1200_Deliverables-Turnover-Project Closeout 2000_External Drop Box; 3000_SOPs. The objective is to verify compliance with established standards and confirm proper document categorization.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Conducting a comprehensive review of the BESS Aguirre Power Plant Procore documentation, encompassing the following folders: 0100_Project Management; 0200_Administration; 0300_Contracts-Procurement-RFP; 0400_Communications; 0500_Regulatory-Agency-Government; 0600_Environmental-Site Assessments; 0700_Permitting-Applications; 0800_Design-Asbuilts; and 0850_Construction-O&M-Data Books (Vendors-Subcontractors). The objective is to verify compliance with established standards and confirm proper document categorization.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Conducted a detailed review of the Costa Sur BESS design drawings to identify any missing items, incomplete details, or open technical comments. The objective was to prepare a comprehensive list of observations to support coordination with the design team and project stakeholders. The review focused on layout consistency, equipment labeling, structural references, and civil interface points. All findings were documented to facilitate resolution prior to final design approval and construction planning.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Continue evaluation contractor QAQC manual (RG Engineering.) included Site Work requirements, work construction process and materials used on various areas of the project (QAQC Codes and Standards) include specific equipment used for construction and suggested preparing checklist forms to complete inspections for installing material and constructions process. Continue evaluation contractor QAQC manual (RG Engineering.) included Site Work requirements, work construction process and materials used on various areas of the project (QAQC Codes and Standards) include specific equipment used for construction and suggested preparing checklist forms to complete inspections for installing material and constructions process.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line at turbine 1 in concrete inspection for survey works, inspection for concrete works, turbine 1 equipment positioning start date, concrete pad inspection for transformer 2 area, construction of buildings roof in planning with formworks detailing, underground pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line concrete inspection for survey works, inspection for concrete works, turbine 2 equipment positioning start date, concrete pad inspection for transformer 2 area, construction of buildings roof in planning with formworks detailing, underground pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 7) Review Cambalache DCMC Quality Control Sample, Construction Policy & Procedures, Meeting Plan, Meeting Documentation and , Weekly Internal Operations Meetings and Weekly Superintendent Meetings to create a new DCMC Quality Control Pan for 4339_9510 BESS-Cambalache project.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updating this week's report to include sites activities insights, integrated with a comprehensive summary of overall program and BESS and Peakers project progress.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 122 | 244 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue refining this week’s report to incorporate site activity insights, along with a detailed summary of the overall program status and progress across the BESS and Peakers projects.
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Rafael Pabon (CDM Smith), Luis Roman (DCMC), Jorge Bracero (Genera), Lauren Wells (Lemoine), Nelson Rosado (S&L), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Franklyn Colmenares (CDM Smith), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Sheila Torres (DCMC).
2025-07-14 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Teams Meeting "Peakers Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Nelson Rosado (S&L), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Miguel Del Valle (S&L), German Nuñez (Genera), Frances Vallejo (DCMC), Abraham Velazquez (DCMC), Rafael Pabon (CDM Smith), Sheila Torres (DCMC), Paola Arroyo (DCMC), Lauren Wells, (Lemoine)
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146795 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Mark Merritt, Gilberto Sucre, Frances Vallejo, Lauren Wells, Ada Diaz, and Nyah Medina DCMC. Discussed update on project, job offers, PROCORE, logistics, trailer set-up, safety, and schedule for locations.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 225 | 562.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 worked on PROCORE entries for ll the Peaker sites. Reviewed recent specification submittals for review at the costa sur site
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 225 | 562.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Reviewed emails and reports for the Peaker projects
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Civil & Structural IFC drawings review and report issued to Sargent & Lundy requesting TRUE IFC Submission Date.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L /CDM Smith Weekly BESS Drawings Meeting. Led by Gabriel Perez - CDM Smith emphasized the need to complete design packages and to have other IFC's with "hold". Page turn sessions were next for next week at Sargent & Lundy's Office to review Cambalache, Costa Sur, Vega Baja & Aguirre. Attendees: Mike Kuczynski, Wilfredo Sierra - Sargent & Lundy Enrique Laya, Gabriel Perez, - CDM Smith Jose Lopez, Andres Concepcion, Gilberto Sucre - DCMC.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch up Meeting led by Frances Vallejo - DCMC Main Topics: * Staffing Updates & Personal Changes * Site Specific Staffing Decisions * Procore System Updates & Modules * Project Status & Technical Issues * Safety & Compliance Initiatives * Administrative & Procurement Matters * Employee Development & Performance Mark Merritt, Mike Merritt, Jack Darnell, Lauren Wells, Ada Diaz, Frances Vallejo, Anneilia Holton, & Gilberto Sucre - DCMC
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja Site Meeting & Visit with Carlos Rodriguez, Rafael Barrera, Carlos de Jesus, Luis Echevarria - DCMC and Abdiel Gonzalez - Sargent & Lundy Agenda: IFC's Comments Demolition Drawings Underground Utilities IT/OT Tower Fiber Optics Relocation Topo & Survey Update Emergency Diesel Generator Relocation Civil & Structural Phasing Rigging Plan.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine)
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on user login report for Peakers Procore.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procore features to better setup teams for use of Procurement process.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore project tool settings.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on PowerPoint for Gilberto Sucre (DCMC) and Frances Vallejo (DCMC) for presentation to Jesus Citron (Genera) for an update on Procore.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore to answer user questions.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on adjusting Procore permissions for meeting items for Peakers projects.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on items for Procore financial tools for Budgets.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore Budget items.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on user login report for BESS Procore.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Working session with D'Alexzander González and Jose Ralat from DCMC; and Shellsea Maysonet from SM Consulting, to discuss the preparation of a report of all procurement processes carried out with the federal funds approved by FEMA under all PWs for the disaster 4339-Hurricane María.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 | 184 | 598 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Picked up fire extinguishers from Best Fire Store for all DCMC office trailers. Meeting with Raisa Borges (DCMC) to discuss reporting procedures and the Genera reporting form. Reviewed project documentation with Andrés Concepción (GENERA) related to the Cambalache project. Attended a project meeting with RGE (contractor) and Genera, including Alberto Borrelli (RGE), Carlos Negrón (Genera), and their teams, to discuss project progress and coordination.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with ARG teams include Carlos Hernandez and DCMC Eduardo Rivera, Gilberto Soto and Jaime Pesquera about documents and process needed to start the project in Vega Baja Genera Site.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.75 | 184 | 690 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Make a process to delivery tools needed in Yabucoa and Aguirre Genera project offices trailers. Conference call with Luis Moctezuma (DCMC) about Health and Safety programs applied and documents needed in Aguirre Genera project. Conference call with Gilberto Soto (DCMC) about actions needed in Procore about Health and Safety in Vega Baja Genera project. POM Meeting about status of the office's trailers in all Genera Sites.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146795 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended meeting with Jesus Cintron (Genera PR) to discuss Peaker's project position and candidates.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended call with Jean Menay (DCMC) to discuss site trailer coordination, material and equipment logistics for Costa Sur, Aguirre and Yabucoa.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Make arrangements with site managers at Vega Baja and Cambalache sites to prepare for site visit from client and NFE staff.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR- Deliverable11- ¦ DR 4339 - Hurricane Maria - Attended PMO Catch up call to discuss staffing update, Procore update, equipment and material logistics, budget tracker and other related matters to BESS and Peaker projects. Attendees: Michael Merritt (DCMC) and other DCMC participants.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Reviewed email correspondence and supporting documentation shared by José Ralat (DCMC) regarding PREPA’s Request for Information (RFI) on Vivienda’s ER1 Cost Share Program. Assessed the scope of the request, identified the specific information needed to prepare a compliant response, and coordinated with the responsible parties to gather the necessary data.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - Participated in a strategic planning meeting with Genera's CEO Winnie Irizarry and Jesús Cintrón to assess temporary generation requirements and evaluate potential impacts on the implementation of FEMA-funded BESS and Peakers projects. The discussion focused on aligning available generation capacity with project timelines to ensure uninterrupted execution and compliance with Public Assistance objectives. Identified potential constraints and coordinated on mitigation strategies to support effective project formulation and long-term grant management.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - RFP 4898 - Supported the Regulatory team by assembling the FOMB Request for Approval package by organizing the documentation required under the FOMB Contract Policy Review Checklist, which includes over 20 supporting documents. Ensured all materials were clearly labeled and aligned with FOMB’s submission requirements to facilitate a thorough and compliant approval process.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in a procurement coordination meeting with Mark Merritt, D'Alexzander González (DCMC), Sulinnette Pérez, and Axel Vélez (Genera) to evaluate current gaps in the procurement process and their impact on FEMA-funded project administration. Discussed alignment issues between Procurement, Finance, and the PMO, and collaboratively developed a strategy to streamline internal workflows, ensure timely compliance with procurement requirements, and strengthen overall grant management and documentation practices.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - PMO meeting preparation - Updated legal and procurement update slides for the weekly PMO reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any legal or compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we had a meeting with Carirma Sánchez from Homeca with DCMC team Jaime Pesquera Eduardo Rivera and CDMSmith Nelson Soler, after we had a meeting with Carlos Hernández from ARG toward documentation required for next phase Vegas Baja BESS.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I reviewed labeling to identify specific areas within the project wagon and reviewed the structure of OSHA Puerto Rico’s services. These services are organized into the following divisions: Inspection, Consulting, Technical Assistance, Evaluation, Legal Affairs, and specialized programs for Elevators, Boilers, and Cranes. Additionally, I examined the Occupational Safety and Health Act of Puerto Rico, which guarantees safe and healthful working conditions for every employee. To ensure that the BESS project is executed in accordance with what OSHA PR establishes.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I reviewed and read some of the standards that may apply to the¿BESS Project according to the activities to be carried out. Tools, Hand, and Powered (1926 Subpart I), Demolitions (29 CFR 1926 Subpart T), NFPA 70E (article 320), and project technical information.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Jose Lopez, Carlos López, and Luis Moctezuma(DCMC) to discuss project two week look ahead schedule and improve communication across the site team.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS Project Meeting with S&L, Kuczynski, Mike, Robert Muhler, and (CDM Smith), Gabriel Perez, Franklyn Colmenares, (CDMSmith), Andres Concepcion, Gilberto Sucre from DCMC Partners to discuss the BESS IFC design delivery status.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Jose Lopez, Carlos López and Luis Moctezuma (DCMC) to identify existing fire protection line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Jose Colon, Gilberto Sucre and Jean-Pierre Menay (DCMC) to discuss the office trailer contractor's punch list items and pending office supplies.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I read the maintenance transmission transformer proposal (contains prices, protocols, schedule, summary of work, test, reports). Pages 1 to 11.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – meeting to discuss second Phase construction. Among the topics discussed were the ARG team was asked for an organizational chart, the contract has not been signed, and the submittal and RFI logs were discussed. Attended Eduardo Rivera (DCMC), Carlos Hernandez (ARG), Nelson Soler (CDM Smith), Gabriel Perez (CDM Smith), and others.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I read Beta Electric Contract Amendment 01 of Vega Baja BESS Project to familiarize yourself with the scope of the project, special scope of work, deliverables, commissioning, standard procedures, coordination of work, protocols for maintenance of different equipment's. Pages 1 to 30.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I continue reading Beta Electric Contract Amendment 01 of Vega Baja BESS Project to familiarize yourself with the scope of the project, domestic preference procurement, Davis Bacon Act, Section 3. Pages 31 to 37.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I continue reading Beta Electric Contract Amendment 01 of Vega Baja BESS Project to familiarize yourself with the scope of the project, safety standards, fair housing act, energy efficiency, conflict of interest, liquidated damages, subcontracting, non-conflict of interest certifications. Pages 38 to 50.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Meeting- Discussed why the contract is still unsigned, Genera will visit the project on Thursday, an inventory of the warehouse will be conducted, and alternative temporary parking for employees will be sought. Attended Xiomara Perez, Jose Segarra (RGE), and Jean Pierre Menay (DCMC)
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Continued with the internal review of the Costa Sur BESS design drawings. Focus remained on identifying inconsistencies, detailing gaps, and potential coordination issues across civil, structural, and electrical disciplines. Additional technical comments were documented as part of the ongoing review process. At this stage, observations are still being compiled and have not yet been submitted to the designer for response.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Participated in a coordination meeting led by Gilberto Sucre (DCMC) with the presence of the design representative Abdiel Gonzalez, Harry Ramos and Gino Sambolin from Sargent & Lundy and the Genera representative Angel Cintron and Roberto Santana. The purpose of the meeting was to review on-site conditions and assess the potential relocation of underground utilities that were not identified in the current design drawings. The team conducted a walkthrough of the work areas to discuss technical alternatives and evaluate constraints related to constructability, safety, and permitting. Notes were taken to update the design team and initiate revisions to the drawings, ensuring that all existing utilities are properly addressed before finalizing construction documentation. Team Members participants (DCMC): Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur- BESS Site meeting for BESS batteries to include designer team Franklyn Colmenares (S&L), Carlos Rodriguez (DCMC) among others to discuss limiting design situations that may cause delays to BESS battery project. These include but are not limited to underground water from demineralization tanks and Concrete pad design for Generator.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur - BESS- Request for proposal review of Section 301.3 Protection and Support and 301.4 Temporary Cofferdams. Confirmed that temporary sheeting, bracing, and shoring must be removed when no longer needed unless otherwise indicated. Verified that cofferdam design must be certified by a Puerto Rico-licensed Structural or Professional Engineer. Referenced Puerto Rico Building Code Chapter 18 for additional foundation and excavation information. Excavation slopes must be maintained to prevent damage to adjacent structures.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Travel time (both ways) from Yabucoa Site to Caguas and back to meet with Jean Pierre Menay from DCMC Partners to receive safety articles and office supplies such as a First Aid Kit, extinctors, printer and paper for the DCMC Partners office in the Yabucoa Site.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Work with the layout and signage of the DCMC partners office including installing the signs of exit, extinguisher and bathroom to comply with OSHA and security requirements.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Housekeeping including landscaping cleaning activities in the house area owned by PREPA and were the DCMC Partners office are located.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Participated in a coordination meeting led by Gilberto Sucre (DCMC) with the presence of the design representative Abdiel Gonzalez, Harry Ramos and Gino Sambolin from Sargent & Lundy and the Genera representative Angel Cintron and Roberto Santana. The purpose of the meeting was to review on-site conditions and assess the potential relocation of underground utilities that were not identified in the current design drawings. The team conducted a walkthrough of the work areas to discuss technical alternatives and evaluate constraints related to constructability, safety, and permitting. Notes were taken to update the design team and initiate revisions to the drawings, ensuring that all existing utilities are properly addressed before finalizing construction documentation. DCMC Team Members participants: Carlos Rodriguez, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Continued with the internal review of the Costa Sur BESS design drawings. Focus remained on identifying inconsistencies, detailing gaps, and potential coordination issues across civil, structural, and electrical disciplines. Additional technical comments were documented as part of the ongoing review process. At this stage, observations are still being compiled and have not yet been submitted to the designer for response.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Continue work in a Development of a Safety Toolbox Meeting Form for the BESS_Aguirre Project: As part of the BESS_Aguirre Project’s commitment to safety excellence and proactive hazard communication, a tailored Safety Toolbox Meeting Form was developed to standardize daily and weekly safety briefings across the site. Given the complexity and dynamic nature of battery energy storage system (BESS) construction, the toolbox meetings serve as a critical platform for reinforcing site-specific risks, procedures, and lessons learned. 1. Project-Specific Requirements 2. Objective and Scope 3. Form Structure and Content 4. Format and Accessibility 5. Review and Validation
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewing and reading some of the standards that may apply to the Bess_Aguirre Project according to the activities to be carried out. Stairs (29 CFR §1926.1053), Motor Industrial Truck (29 CFR §1910.178), Lockout and Tagout (29 CFR §1910.147), Machine Guarding (29 CFR §1910.212) and we are work in a Development of a Safety Toolbox Meeting Form for the BESS_Aguirre Project: As part of the BESS_Aguirre Project’s commitment to safety excellence and proactive hazard communication, a tailored Safety Toolbox Meeting Form was developed to standardize daily and weekly safety briefings across the site. Given the complexity and dynamic nature of battery energy storage system (BESS) construction, the toolbox meetings serve as a critical platform for reinforcing site-specific risks, procedures, and lessons learned. 1. Project-Specific Requirements 2. Objective and Scope 3. Form Structure and Content 4. Format and Accessibility 5. Review and Validation
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS Project Meeting with S&L, Kuczynski, Mike, Robert Muhler, and (CDM Smith), Gabriel Perez, Franklyn Colmenares, (CDMSmith), Andres Concepcion, Gilberto Sucre from DCMC Partners to discuss the BESS Issue for Construction design drawings delivery status. The Aguirre BESS project's bid drawings delivery date has been delayed by one week to the first week of August. The Following Action Items we discuss as a Team. S & L will create a list per site with all the necessary information to complete the drawings, including who is responsible and when it enters the critical path. S & L will create a list of site findings, which is crucial for mitigating potential project risks. We will hold weekly meetings with the BESS PM/CM & S & L for each site. This is important to discuss project priorities. Tuesday will be Cambalache / Costa Sur, and Thursday, Vega Baja / Aguirre. We will review the project drawings. Need approval in writing from the Genera Management Team for permission to connect to the Cambalache existing waterline. S & L will share the scope so we can get approval from the Plant Manager & Management Team. S & L will share the RFI for LUMA to request foundation drawings and concrete slab in Costa Sur.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - At the Aguirre BESS job site. Daily project coordination and project management. Project Documents Overview and Analyzing the Issue for Bid, TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC), Spec. No.: G-3400, Revision: A; For Bid, Project No. A15240, dated June 20th, 2025, Documents' Status in Procore. Loading
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, Luis Moctezuma, and Sunem Martinez (DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria, Meeting with Digno Cartagena, Security Manager from Genera PR and All DCMC Site Managers, Carlos Rodríguez, Andres Concepcion, and Gabriel T. Morales, also Jean Pierre Menay, Gilberto Sucre, and Aguirre First Security Officer Francisco Marí. The meeting was held via Team, and the presentation explained all the Safety and Security requirements for the Cambalache Job Site and the Mayaguez site, along with a brief description of the restricted and safety areas of the plant that required the TWIC Card. It was also discussed that the general laborers' entrance logistics involved in the project start and also explained that the Security Staff from General PR will implement a random check for non-authorized personnel in search of any illegal drugs, firearms, and unauthorized possession of tools.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Carlos López, Luis Moctezuma, and Sunem Martinez (DCMC) to identify existing project general arrangement line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects. We discovered that another contractor is building a structure for the IT department, which will create a clash with the proposed BESS layout. It was immediately informed to Gilberto Sucre (DCMC)
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Submittal 0010, submitted by the contractor RGE for the lifting of containers and the installation of temporary storage, is being verified. Crane positioning, configuration, work plans, certifications, among other things, are verified.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - A meeting was arranged with Andres Concepcion (DCMC) where the comments established in the RGE work plans were discussed so that they could be discussed with the contractor in coordination meetings before starting the tasks.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued verification of work plans for lifting containers. Standards were implemented in the areas for improvement in each document sent by RGE. An analysis of OSHA standards based on crane operator certifications was conducted due to constant changes.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated several project management tasks with the team (internal - DCMC). Coordinated site visit for New Fortress Energy for July 7/15/2025. Cooridnated a meeting for safety discussion about crane rigging plan with Jorge Mercado (DCMC) and RG Engineering (Jose Segarra). Generated an meeting agenda to meet with team on site and follow up with open tasks.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Robert Molner (Sargent and Lundy) and CSAGroup (Franklyn Colmenares) to discuss regarding the weekly design updates meeting to review pending design activities to finish the BESS project design.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated a plan to mitigate GeneraPR lack of resources required for the relocation of materials and vehicles that are required to be removed from construction site. Requested to General Contractor (RG Engineering - Jose Segarra) to quote the required acivities.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed and completed the Construction Weekly meeting minute and distributed via Procore. Followed up with Jose Segarra (RG Engineering) for new staff Procore access.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted meeting with project team: RG Engineering (Jose Segarra), Sargent and Lundy (Robert Molner), CDM Smith (Gabriel Perez), CSA Group (Franklyn Colmenares) to follow up on weekly updates and project pending actions.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Developed a plan to perform a material inventory for the site warehouse. Planned tasks and required resources to complete the task. Generated email to Gilberto Sucre (DCMC Partners) for approval of supplies related.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Compiled and reviewed the project pending actions and tasks to update meeting agenda for upcoming Weekly Construction meeting. Updated last minute updates and instructions to be followed.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Monitored submittals in Procore. Responded and distributed submittal RGE-0011 to the general contractor (RG Engineering - Jose Segarra).
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Preparing final agenda for meeting with Homeca and ARG/CERES, reviewing email send by Ida Ramirez of ARG that include the revised safety management plan. Start reviewing the safety management plan to provide comments if required.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project weekly meeting to review project status. Homeca Carirma Sanchez, Gilberto Soto, Jaime Pesquera, Jean Menay and Eduardo Rivera of DCMC, Nelson Soler and Manuely Concepcion of CDM Smith - Meeting to discuss final pending items related to project closing, it was mentioned to Carirma Sanchez of Homeca that as built drawing should be included underground survey as per contract, also the PUI is still under review by Orlando Oquendo of Spare Group and certification 4 and 5 still pending to be submitted.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project construction weekly meeting Phase II. ARFG/CERES Carlos Hernandez, Ricardo Lopez and Ida Ramirez; DCMC Jaime Pesquera, Gilberto Soto, Silvia Franco, Raissa Borges and Eduardo Rivera, CDM Smith Nelson Soler and Gabriel Sepulveda, S&L Wilfredo Sierra, Mike Kuczynski, Robert Moler - Meeting to provide status for second phase construction of Vega Baja BESS project, coordinate with ARG documents to be submitted as part for the new construction and ARG provide status of RFI's. It was discussed with S&L the urgent need to close all RFI's and submittal. It was also informed to ARG that Genera will not pursue the VE PreCast for VB.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing email sent by Mike Kucynski of S&L regard the evaluation of the Geopier for Vega Baja site and stone column final coordinates. Send email to Carirma Sanchez of Homeca to inform that the as built as per contract should be consider survey aboveground and underground.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the minute's notes of the construction meeting of ARG/CERES. Received the revised PUI report send by Orlando Oquendo of Sphera Group, this report must be sent in a sing pdf file. Send by Team communication to Luis Roman of DCMC to explain the functionality of a transmittal form in Procore. Send invitation to meeting Carlos Hernandez of ARG to discuss how to canalize or redact submittal and RFI question. Send email to Jean Menay of DCMC to inform a site visit schedule for 7/17 at Vega Baja with Genera Jesus Cintron and New Fortress Energy (NFE).
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-a comprehensive review and analysis of inventory variances was conducted across zones AJ 051 through AJ 054 and AR 003. The scope of work focused on identifying discrepancies between physical inventory and system reported data by auditing item movement history and verifying data integrity through audit trail validation. Emphasis was placed on pinpointing the root causes of these variances, recognizing recurring issues, and evaluating the reliability of past adjustments. This initiative contributed to improving inventory record accuracy and strengthening internal control procedures.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a morning operations briefing alongside Mr. Hernan Machado, Mr. Milton Flores, Mr. Giovanni Taffanelli and Juan Vallejo from DCMC, to address inventory handling practices and reinforce safety protocols. The session emphasized secure material transfer, proper storage conditions, and adherence to PPE (personal protective equipment) guidelines throughout daily activities. Key points included ensuring accurate inventory documentation, reducing procedural errors, and promoting a safe and efficient warehouse environment.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a focused inventory recount at the San Juan warehouse in collaboration with Mr. Milton Flores from DCMC. The primary objectives included verifying actual inventory quantities, checking the accuracy of bin assignments, and validating that system records aligned with on-site stock conditions. Attention was placed on maintaining consistency across inventory processes, enhancing data reliability, and supporting operational integrity. The activity concentrated on inventory zones AJ 051 through AJ 054 and AR 003, ensuring alignment with audit requirements and quality assurance protocols.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-prepared a detailed inventory performance report for Mr. Anthony Vega from Genera PR. The report included a summary of findings from inventory zones NN 001 to NN 008, AC 061 to AC 085, CC 047 to CC 056, AJ 051 through AJ 054 and AR 003, covering item level accuracy, stock balance verification, labeling and bin assignment checks, and documentation of variances. It also addressed recurring discrepancies, compliance with inventory thresholds, and an evaluation of procedural consistency across warehouse operations.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle count operations across assigned inventory zones at the San Juan facility, specifically covering areas from AJ 051 through AJ 054 and AR 003. The focus was validating physical stock quantities, confirming bin accuracy, and cross-referencing labeling data with system records. Any discrepancies observed were logged for further review, and the necessary adjustment was coordinated accordingly. All activities were performed in alignment with established inventory control procedures to maintain data accuracy and system consistency.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted preparatory tasks at the San Juan warehouse in coordination with Mr. Milton Flores from DCMC to validate readiness for the upcoming cycle count. Activities involved confirming that all inventory areas met operational standards, including proper bin identification, item labeling, and alignment of stock groupings with system records. Work was specifically focused on locations AJ 051 through AJ 054 and AR 003. Additionally, the session verified that all supporting reference documentation was available to ensure a consistent and accurate counting process.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Complete the Bi-Weekly Report Template in preparation for the PMO reporting meeting. This task involved compiling updates on key project activities, identifying recent accomplishments and ongoing challenges, and summarizing financial and operational status. The finalized report supports leadership oversight and ensures consistent tracking of project milestones and deliverables. Related to PW-10710 Material & Equipment
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -Develop overall status presentation of Critical Components Status requested from GENERA-PR Joaquin Quinoy. PW-10710 Equipment & Material
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting Cambalache Riggin Plan Clarification with Jose Segarra from RGE and Jorge Mercado and Andres Concepcion from DCMC.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Participated in a Bluebeam software working session focused on reviewing construction drawings and adding technical markups for the Cambalache BESS project (PW9510). The session covered tools relevant to submittal reviews and inter-team coordination.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146795 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS RFC Meeting RGE Cambalache Project status update is an issue of design drawings that remain to be completed RFC Meeting RGE Cambalache S & L / CDM Smith Weekly BESS Cambalache Drawings Meeting with Gilberto Sucre DCMC, Gabriel A. Perez Sepulveda, Enrique J. Laya CDM Smith, Mike J. Kuczynski, Eric G. Rivera Santiago Sargent & Lundy, Franklyn Colmenares CSA Group.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- 4339_9510 BESS Review of the preliminary document was initiated, which includes the general planning drawing SECTIONS CAB00-AA-SSB-3000, DETAILS CAB00-AA-SSB-5000.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- 4339_9510 BESS Review of the preliminary document was initiated, which includes the general planning drawing CODE ANALYSIS, SAFETY REFERENCE PLAN & FIRE BARRIERS CAB00-AA-WHB-1000 warehouse.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly Vega Baja BESS Phase II - Construction Meeting with Carlos Hernandez from (ARG/CERES,) Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith) and went over Project Documents Overview and analyzing documents status in the Procore platform and all the punch list items that are closed for the meeting.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly construction meeting with Homeca Recyclers Carirma Sanchez & Eduardo Vera, also Eduardo Ramos, Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith) and went over project closing documents overview. Analyzing documents status in the Procore platform and all the punch list items that are now closed. Also RFI #ARG-R007 - Differential Settlement & Punch Item #30 have been closed.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we had a meeting with Carirma Sánchez from Homeca with DCMC team Jaime Pesquera Eduardo Rivera and CDMSmith Nelson Soler, after we had a meeting with Carlos Hernández from ARG toward documentation required for next phase Vegas Baja BESS. Verified Submital 006 and find missing documents and parts required for approval.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1485 and 1486 from locations CC047 to CC056 for a total of 1132 pcs.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AJ051 to AJ054 and AR03
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report AJ051 to AJ054 and AR03
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AJ051 to AJ054 and AR03
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations AJ051 to AJ054 and AR03
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AJ051 to AJ 054 and AR03
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC 00 061 000 to AC 00 085 000
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC 00 061 000 to AC 00 085 000
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC 00 061 000 to AC 00 085 000
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations NN 001 to NN 008, LIST #1364/1365/1366/1367/1368
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations NN 001 to NN 008, RECOUNT LIST #1369/1370
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations NN 001 to NN 008 at the Aguirre warehouse to initiate the cycle counts.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location NN 001 to NN 008
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CC047 to CC056 Cycle Count List # 1460.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CC047 to CC056 to begin the cycle counts.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 | 152 | 114 | 152 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CC047 to CC056.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Vega Baja project documentation looking for Pre-Construction and Demolition phase documents that are still not allocated into the Procore Documents folders.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Continuation of GEN 01 Incoming BESS Peakers Project Schedules for review_organize_process accordingly/Costa Sur BESS Procurement RFPs RFQs documents review_organize_process accordingly
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management Costa Sur Peakers continuation Procurement RFP RFQ project document review for processing/GEN 01 Incoming BESS_Peakers_BESS-Peakers project schedules for review_organize_process accordingly
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review for comments the Yabucoa Technical Specifications Package received from designer S&L; looking for formatting errors, missing sections inside the specifications and technical discrepancies on project execution.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review for comments the Costa Sur Technical Specifications Package received from designer S&L; looking for formatting errors, missing sections inside the specifications and technical discrepancies on project execution.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Cambalache Project Weekly Meeting hosted by Andres Concepcion (DCMC) and joined by Jose Segarra and Xiomara Robles from RGE, Mike Kuzcynski and Robert Molner (S&L), Gilberto Sucre and Luis Duque (DCMC) and other project team members. Discussed the project upcoming kick-off for construction, ongoing administrative procedures with submittals and RFIs, contractor’s concern on design changes and more.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146795 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the General Conditions from Genera's Contractual Agreement to verify contractual requirements and funding agency clauses such as the Buy American Act, specific documentations stated as Submittals or Transmittals, and other contractual specifications.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 139 | 417 | 139 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339: Updated the expense tracker with vendor invoice data. Reviewed and entered invoice details for proper tracking and reconciliation. Updates included invoice date, number, and amount for each record. Focused on processing multiple invoices from Dueñas Trailer and Villamil Group to ensure all expenses were accurately reflected in the system. Processed the following Dueñas Trailer invoices: #247782, #247858, # 247859, #247959, #247960, # 249075, # 249076, #249077, #249470, #249469, #249542, #249543, #249542-A, #249543-A, #250150, # 250177, and #250258, also updated Villamil Group Invoice # D-3235. Ensured consistency in formatting, cross-checked for duplicates, and confirmed correct assignment to project codes.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA Genera Deliverable 11- Project Management DR 4339- Validation of site signs with the KROMA agency in order to correct the material that would eventually be ordered to be produced. These tasks included verifying the document sent by the advertising agenda, Victoria Flores, which includes all the mock ups of the banners that would be used for the BESS and Peakrs project
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria- Create the graphics in Canva that will be included in the presentation for the second community meeting in Arecibo. This task involves finding and selecting an appropriate template that aligns with Genera PR’s visual identity, choosing the most relevant photographs that represent the graphics to be create, such as images of the project, community engagement, and documented progress, and designing each visual element to ensure aesthetic consistency, clarity, and harmony throughout the full presentation.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA Genera Deliverable 11- Project Management DR 4339- Begin developing the official presentation that will be used during the upcoming community meeting in Arecibo, with the goal of clearly and visually communicating the project's progress, next steps, and key aspects, all aligned with Genera PR's institutional branding. This task includes gathering up-to-date and relevant information, selecting representative visuals (such as photographs of community activities, equipment, and facilities), reviewing the project timeline to build a clear and accessible chronology, drafting a cohesive and accessible narrative for each slide, and adapting the visual design to match the brand’s style elements.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146795 | PREPA Genera Deliverable 11- Project Management DR 4339- Edit the invitation for the second meeting in Cambalache, finish placing the important information related to the meeting, send it to the Genera PR team, Jorge Bracero, for approval of the communications piece and identify contact to pass on the information related to the community meeting. These tasks included writing an email to the Genera PR team, Jorge Bracero, to pass on the invitation.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146795 | PREPA Genera Deliverable 11- Project Management DR 4339- Write a letter to invite a number of nonprofits to the next community meeting to be held on Monday, August 11 in Arecibo. This task included creating the letter with the header that Genera PR uses, collecting the information that would be integrated into the letter, editing the text and adding details about the event. This task included including edits suggested by the Genera PR team, Jorge Bracero and writing him an email with the corrections. I also had a brief call with Genera PR team, Jorge Bracero to specify details related to the task and the reasons why we would be working on this document.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Lemoine Quality Control/Assurance Plan, Inspections plan, City Inspections, State Inspections, Fire Marshal Inspections and A/E Inspections to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 33 pages were examined.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 31 pages were examined.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Continued with the internal review of the Costa Sur BESS design drawings. Focus remained on identifying inconsistencies, detailing gaps, and potential coordination issues across civil, structural, and electrical disciplines. Additional technical comments were documented as part of the ongoing review process. At this stage, observations are still being compiled and have not yet been submitted to the designer for response.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Participated in a coordination meeting led by Gilberto Sucre (DCMC) with the presence of the design representative Abdiel Gonzalez from Sargent & Lundy. The purpose of the meeting was to review on-site conditions and assess the potential relocation of underground utilities that were not identified in the current design drawings. The team conducted a walkthrough of the work areas to discuss technical alternatives and evaluate constraints related to constructability, safety, and permitting. Notes were taken to update the design team and initiate revisions to the drawings, ensuring that all existing utilities are properly addressed before finalizing construction documentation.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line concrete delivery dates for inspection works, turbine 1 & 2 equipment positioning start date, concrete pad inspection for transformer 2 area, construction of buildings roof in planning with formworks detailing, underground pipping with excavation detailing, electrical works and inspection completion dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with issue for construction drawings of project considering existing conditions of structures to demolish at site, concrete pads construction planning in evaluating the type of crane, excavation detailing, electrical works and construction dates (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146795 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Lemoine Quality Control/Assurance Plan, Inspections plan, Owner Inspections and Testing Lab Inspections to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting with the Cambalache construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as Safety Plan, mobilization plan, inventory and other documentation needed. Attendees: Andres Concepcion (DCMC), Jean Pierre Menay (DCMC), Jose Segarra (RGE) and others.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procore Analytics Dashboards developing and reviewing data to help construction teams make informed decisions, monitor progress, and identify potential areas for improvement throughout the construction lifecycle.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue exploring on access options and sharing methods for Procore Project Management dashboards with Franklyn Colmenares from CDM Smith, to facilitate tracking of key metrics and project member KPIs.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting with the Vega Baja BESS construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as mobilization plan, schedule, quality plan and other documentation needed. Attendees: Eduardo Rivera (DCMC), Jean Pierre Menay (DCMC), Jose Segarra (RGE) and others.
2025-07-15 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 122 | 122 | 122 | Yes | 146795 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Working on access options and sharing methods for Procore Project Management dashboards with Franklyn Colmenares from CDM Smith, to facilitate tracking of key metrics and project member KPIs.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued worked on Procore Financial items.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended on site meeting at costa sur with Siemen logistics team. Discussed methodology of the delivery of equipment to the site Reviewed current site conditions and pathways from the road to the site, identified Connor Mclntire - SIEMENS logistics Ragan Watson- SIEMENS logistics Adrian Reza- SIEMENS logistics Luis Quirós - SIEMENS logistics Raissa Borges Almodovar- DCMC Rafael Barrera- DCMC Carlos DeJesus - DCMC
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 on site costa sur meeting with siemens representatives Reviewed construction schedule for costa sur, discussed delivery time tables and site prep and logistics. Connor Mclntire - SIEMENS logistics Ragan Watson- SIEMENS logistics Adrian Reza- SIEMENS logistics Luis Quirós - SIEMENS logistics Raissa Borges Almodovar- DCMC Rafael Barrera- DCMC Carlos DeJesus - DCMC
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Jesus Cintron-Genera, Jose Robles - RG Engineering, Francisco Feliu - Genera Legal * Genera requested from DCMC to evaluate and provide recommendations to change Peakers' Execution Mode from Design-Bid-Build to Design-Build & identify the essential technical documents requirements for the RFP. This would apply to Costa Sur, Yabucoa, Jobos & Daguao Sites. * Kick-off Contract Review of main changes in Contract Format for Costa Sur & Aguirre.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Procurement Status led by Chynthia Ortiz Genera with participation from: CDM Smith - Rafael Pabon, Gabriel Perez GENERA - German Nunez DCMC - D'Alexzander Gonzalez, Sheila Torres, Gilberto Sucre, Abraham Velazquez Sargent & Lundy - Mike Kuczynski. Meeting Overview: Confirmation of specific package cancellation, impacting overall project logistics and timelines. Reviewed contract template requirements to ensure compliance and clarity throughout the procurement process. Parental support requirements discussed as essential for project readiness and successful implementation. Emphasized need for accurate time estimates due to experience factors affecting project execution. Ongoing negotiations highlighted as critical to maintaining project momentum and securing necessary agreements. Financial model forecast recognized as a key deliverable for upcoming review to assess project viability. Original project budget parameters thoroughly examined to identify potential adjustments and reallocations. Identification of critical components crucial to project success, warranting focused attention and resources. Final commitment discussions facilitated scenario planning for project contingencies and risk management. Participant agreeance on next steps and responsibilities to ensure progress in upcoming phases of the project.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting to discuss invoice approval process of CDM Smith PMO Services taking into consideration Maria Sanchez - Genera authorization letter than RFI's required for the resubmission and re-approval of the same. Recommendation to add another staff as the volume of the invoices is expected to increase in the near future. Rafael Calderon, Frances Vallejo and Gilberto Sucre from DCMC.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Final Contract Negotiations with RG Engineering with Jose Robles and Francisco Feliu - Genera. Review revised contract templates for Costa Sur & Aguirre BESS Civil & Structural Projects. Reviewed and confirmed price increase from 5 % to 100 % in Lieu of Credit Letter. Reviewed and confirmed Builder's Risk requirements for both projects. Verified Final Contract Amount for both Projects.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PM/CM internal alignment meeting with Gabriel Perez - CDM Smith, Franklyn Colmenares - CSA Group and Gilberto Sucre DCMC. Evaluated delay stages of the Program due to late decision/direction making from the owner's side, delays design deliverables and Peaker's status which is forcing the evaluation to change Program Execution Process.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Meeting with Luis Roman, Lauren Wells, Frances Vallejo & Gilberto Sucre - DCMC. Meeting Overview: Emphasized the urgency of workflow clarification, especially with Frances requiring an efficient pace due to a tight schedule. Sargent & Lundy utilizes the Ignite system for specifications upload and lacks integration with Procore, which raises workflow concerns. TRC's role as mechanical and electrical SME for design review was confirmed, with a focus on their oversight responsibilities throughout the project. Gilberto highlighted that Sargent & Lundy is not obligated to use Procore during the internal design phase, affecting approval workflows. QA/QC role defined with a designated person responsible for submittal publishing, DCMC acts as the owner’s representative for Genera's approvals, with Genera personnel receiving notifications from Procore. Technical submittals approved by Sargent & Lundy unless owner involvement is necessary; safety submittals require a dual approval process. TRC's integration timeline set for 1-2 weeks, with ongoing discussions impacting their operational model. Transmittal tools in Procore noted as underutilized; decreasing industry use highlighted by Lauren Wells regarding documentation disputes. Buy American Act compliance is in early stages, with no signed agreements but requirements included in all current contracts.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria E-mail correspondence to all Site Managers in preparation of IFC Drawing-page-turn at Sargent & Lundy's Office next Tuesday to review Cambalache & Costa Sur and Thursday - Aguirre and Vega Baja. Meeting presence of RG Engineering, ARG Ceres, DCMC Site Teams, CDM Smith, Sargent & Lundy and Genera.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- PMO Reporting meeting to discuss the reports that have been compiled for the overall Program. Attendees from DCMC were Frances Vallejo, Rafael Calderon, Gilberto Sucre, Paul Brown, and Abraham Velazquez. Attendees from LEMOINE were Foster Veazey and Lauren Wells.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Frances Vallejo (DCMC), Gilberto Sucre (DCMC), Luis Roman (DCMC) to discuss Procore questions.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore correspondences for Financial information for the implementation.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) PMO Reporting Meeting - DCMC PMO staff meeting to discussed specific need of reporting based on project execution development per area. Working on live tracker presentation template and review updates from BESS and Peakers projects. Participants DCMC (Frances Vallejo, Raissa Borges, Glorimel Torrado, Jean Pierre, Eduardo Rivera, Paola Arroyo and Paul Brown).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for documents.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of meetings for Procore submittal responses.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for RGE company .
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on performance review for DCMC for Luis Roman.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting for user usage for last logins and to show tools being utilized.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOPs review.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financials.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Reviewed and responded to correspondence from Sulinnette Perez, Genera regarding RFP 235021, addressing the automation of procurement processes. - Discussed with Shellsea Maysonet from SMC the need to coordinate with Genera PR IT restrictions on contract requisitions involving federal accounts within the Asset Suite system. - Initiated a subsequent discussion with Hiram Medero from Genera PR to explore potential technical approaches for implementing these restrictions, and formally requested his support in generating a report identifying requisitions linked to federal accounts with fields specified by DCMC. - Discussed with Michael Silva from Genera PR on the deployment status of Genera Connect Timesheets across the powerplant network, emphasizing the importance of accurately capturing labor hours related to federally funded projects. - Reviewed an access control issue reported by Aldwin Pagán from Integrum, which is currently impeding the upload of historical timesheet data into the Genera Connect servers.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 184 | 138 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 - PMO Reporting Meeting - DCMC PMO staff meeting to discussed specific need of reporting based on project execution development per area. Working on live tracker presentation template and review updates from BESS and Peakers projects. Participants DCMC (Frances Vallejo, Raissa Borges, Glorimel Torrado, Jean Pierre Menay, Eduardo Rivera, Paola Arroyo, Paul Browne and Lauren Wells).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Make a process to buy the tools necessary in all Genera projects. Review the document by Vega Baja site preview the meeting with ARG contractor. Meeting with ARG contractor Javier Almodovar, and DCMC Eduardo Rivera about the Procore process and document process in Procore system.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 | 184 | 506 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Visit Central San Juan to make the Health and Safety Modules for Site Visit from Genera Teams (Jesus Cintron). This it's a professional Visit. Conference call with Nieves (Portosan) for delivery tank in Costa Sur. Review the fire suppression system document in Procore by Vega Baja Genera site.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.25 | 184 | 414 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 - PMO Reporting Meeting - DCMC PMO staff meeting to discuss specific needs and status by tools, equipment and furniture in all sites Genera projects with Frances Vallejo and Carolyn Baez (DCMC). Review the document by Safety Zone to created account. Conference call with Eduardo Rivera (DCMC) about Vega Baja Fire System. Conference call with Gabriel Perez (CDMSMITH) about Fire system and Vulnerability plan design for Genera Sites.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 - PMO Reporting Meeting - DCMC PMO staff meeting to discuss specific need of reporting based on project execution development per area. Working on live tracker presentation template and review updates from BESS and Peaker's projects. Participants DCMC (Frances Vallejo, Raissa Borges, Glorimel Torrado, Jean Pierre Menay, Eduardo Rivera, Paola Arroyo, Paul Browne and Lauren Wells).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended call with Abraham Velazquez (DCMC) to discuss Peaker's project transition plan and report to client.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Internal in person meeting with Carolynn Baez (DCMC) to discuss PMO roster excel sheet with contact information and update the document with new employee's information.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams call with Gilberto Sucre and Rafael Calderon (DCMC) to discuss S&L invoices and RFI process. Also sent email to Raissa Borges (DCMC) and Gilberto Sucre regarding RFI.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting via teams call with Paola Arroyo (DCMC) to discuss Community engagement plan, meeting at Toa Baja, second meeting at Cambalache site and webinars for BESS and Peakers.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams meeting with Paul Browne (DCMC) to discuss inventory management and Procore submittals, equipment needed at the warehouses and status.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Teams meeting with Gabriel Perez (CDM), project manager for BESS, to discuss alignment for the BESS project and deliverables.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended teams call with Luis Roman (DCMC), Lauren Wells and Gilberto Sucre (DCMC) to discuss procore processes, next steps and delays.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS & Peakers weekly Procurement catch-up call with Franklyn Colmenares, Gabriel Perez, Rafael Pabon,Carlos Palomares (CDM Smith) Axel Velez (Genera) Gilberto Sucre, Cynthia Ortiz (DCMC). Discussed feedback and updates received from the Genera procurement team.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Reviewed and updated the status of key workstreams and high-priority procurement items in preparation for the BESS & Peakers weekly Procurement catch-up call. This activity ensured that all procurement-related tasks were current, properly tracked, and aligned with project schedules. The updated information supported informed decision-making, interdepartmental coordination, and compliance with FEMA PA construction management and documentation requirements.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Reviewed multiple email chains and supporting documentation related to the Generation Fleet Peakers Project to establish a complete understanding of the project’s history and milestones. This review was conducted to support the development of a formal request to FEMA for the closeout of the associated HMGP project. Began drafting the closeout letter, ensuring alignment with FEMA PA project documentation and closeout requirements.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Finalized the drafting of the HMGP project closeout letter, ensuring alignment with COR3’s requirements and expectations. Shared the completed draft with D’Alexzander Gonzalez (DCMC) and Jesús Cintrón (Genera) for review and further action.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed correspondence related to EPA Catalytics Power Generation Project No. 739681. Summarized key comments and observations provided by Ricardo Pallens (Genera) and shared the summary with Jesús Cintrón (Genera). Held discussions with Ricardo Pallens and Jesus Cintron (Genera) and agreed on a path forward.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we had a meeting with Carirma Sánchez from Homeca with DCMC team Jaime Pesquera Eduardo Rivera and CDMSmith Nelson Soler, after we had a meeting with Carlos Hernández from ARG discussing the submital and RFI meeting, after Annex J was being reviewed to answer questions from ARG. Started to review fire pump and enclosure documentation for new phase.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I continued reading and review the Scope of Work outlined in the Technical Specifications for the Yabucoa BESS Civil Work Contract (59 pages completed / Reference: 312333-12 to 400510-15).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I read about the PR OSHA 300 Employer Responsibilities and courses of action following a PR OSHA Inspection. The program regarding the following topics: Employer action required, posting requirements, abatement certification, penalty payment, informal conference, how to contest, the contest process, petition for modification of abatement period, follow- up inspection and failure to abate, employee course of action, discrimination against employees, types of violations, inspection activity data, and area offices.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) Meeting with the Site Manager Gabriel Morales, to discuss creating an Evacuation Plan for the DCMC office (trailer). The office is located outside the area of the BESS project.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Yabucoa (BESS Project) – Coordinated with Technical Support to verify and update Bluebeam and Microsoft Office applications to ensure full compatibility for reviewing BESS construction drawings, annotating technical documents, and preparing compliance reports required under DR4339 project deliverables.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT - Continued Vega Baja Bess Project contract and Specs. Overview to ensure all project participants have a clear understanding of the expectations and requirements and understand their participation in the project’s execution.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. I had several phone calls with the GWC (RG Engineering) project manager,Jose Segarra to discuss the project contract requirements and contract progress. Participated in Team Meeting with Sargent & Lundy Staff, Robert D. Molner, Gilberto Sucre (DCMC), Enrique Laya, CDM Smith, and Angel Alice Rodríguez Sargent & Lundy to discuss the Phase II Request for Comments to the contract (4339_9510)documents.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting in person at Sargent and Lundy Central Offices at Santurce PR to go over the Design Drawings and Project Pending missing items to complete the Issue for Construction Drawings. At the conference table were present Gabriel Pérez (CDM Smith), Gilberto Sucre, and Andres Concepción (DCMC). On the Teams were Mike Kuczynski, Robert Molner, and the Civil Design Staff from the Sargent and Lundy office. Review the bid documents package identified as GENERA-15240-061-0017 for the Installation of the Tesla batteries phase, submitted by Sargent & Lundy at the Aguirre Site. It was also present the selected contractor, RG Engineering, represented by Eng. Joé Auli and Eng. José Segarra. Sargent and Lundy rejected the proposed control room designed by RG Engineering in response to the lack of space for all the proposed equipment. RG Engineering will revise its proposal to incorporate all the required equipment as specified in the arrangement shown in the design.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with José Colón and Carlos López (DCMC) to discuss the status of the office supply for the job site office trailer.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Continued review of structural drawings for the Cambalache BESS project to ensure all design details and construction elements are properly documented. Focused on sheets numbered 1- through 28, including coordination of comments and clarifications with the design and construction teams through project correspondence.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Site Visit with Herminio Arroyo (Genera), Jesus Cintron (Genera), Samuel Cha (NFE), Andres Concepcion (DCMC).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Return travel from Cambalache site to Vega Baja work base after completing a project meeting and site assessment for the BESS project. Discussions on-site covered construction updates and next steps for field execution.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Continued review of structural drawings for the Cambalache BESS project to ensure all design details and construction elements are properly documented. Focused on sheets numbered 28 through 56, including coordination of comments and clarifications with the design and construction teams through project correspondence.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Assisted meeting with DCMC Cambalache Staff to coordinate different works process and responsibilities of each one.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Traveled from Vega Baja work base to Cambalache Power Plant to participate in a scheduled meeting and conduct an on-site inspection related to the BESS project. The visit aimed to review progress and address coordination items with field personnel.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - Peakers - Attended a project planning meeting with Abraham Velázquez (DCMC) to discuss the overall schedule for the Peakers project. The session focused on identifying key milestones, sequencing critical path activities, and coordination with design and construction teams. Emphasis was placed on aligning permitting, mobilization, and procurement timelines to prevent delays. Several tasks were flagged for follow-up to ensure alignment with project goals and resource availability. Team Members participants (DCMC): Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - Peakers - Attended an on-site coordination meeting with Abraham Velázquez (DCMC), Raissa Borges (DCMC), and the Siemens Energy Logistics Team (Luis Quiros, Connor Mcintire, Ragan Watson, Adrian Reza and Jaime Avila). The purpose of the meeting was to review the delivery schedule of major equipment, assess the conditions and access of the designated entry gate, and explain the planned logistics layout for equipment staging and installation. The team walked the site to verify clearance, routing paths, and unloading areas. Alignment was established between Siemens Energy’s delivery plan and the project schedule to ensure efficient mobilization and minimize disruptions during construction. Team Members participants (DCMC): Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Reviewing Scope of Services for Technical Specification Number G-3200 for BESS General Work Contract (GWC) that will be issued for bid and completing the comparison report for Gilberto Sucre from DCMC Partners
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with the site safety officer to evaluate the emergency response plan for any eventuality considering that the office is outside the PREPA area and project perimeter.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue Reviewing Scope of Services for Technical Specification Number G-3300 Section 312201 "Earthwork" and the revised drawing for the Yabucoa BESS YAB99-GA-BSS-0001 Rev. B.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BEES Costa Sur- Reviewed safety protocols and manufacturer guidance for the transportation and storage of Tesla Megapack units. Focused on identifying hazards associated with logistics, including thermal control, stacking limits, and containment requirements. The review was conducted to support the development of a risk-based battery storage safety plan in compliance with NFPA 855, UL 9540, and OSHA standards, prior to any site activity.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - BESS Costa Sur- Conducted a comprehensive safety review of RFP-4899 for the Costa Sur BESS project. The objective was to analyze how health, safety, and environmental (HSE) requirements are defined and distributed throughout the document, including contractor obligations, compliance checkpoints, and deliverable expectations. Special attention was given to safety-related clauses, references to applicable regulations (OSHA, NFPA, EPA), and procedural expectations for submittals and emergency response planning. This early review supports the development of a robust safety framework before contracting and execution phases begin.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Coordination and Planning Agreement for Employees Working in a Power Electrical Plant in Puerto Rico (Compliant with OSHA and ANSI Standards) 1. Purpose and Objective This Safety Coordination and Planning Agreement is designed to ensure the highest standards of safety and health for all employees working in the power electrical plant in Puerto Rico. It outlines the procedures, roles, responsibilities, and compliance measures to be followed to adhere to the Occupational Safety and Health Administration (OSHA) regulations and American National Standards Institute (ANSI) guidelines, as well as applicable local laws and regulations. The purpose is to prevent accidents, injuries, and illnesses while ensuring a safe and efficient work environment for all personnel involved in operations at the power plant. 2. Scope of the Agreement This agreement covers all employees, contractors, subcontractors, and any other personnel working on or in connection with the electrical plant, both permanent and temporary. The safety measures outlined in this document apply to all phases of operation, from plant construction, maintenance, and upgrades to routine operations and emergency response situations. It is a joint effort between management, safety officers, contractors, and employees to ensure compliance with OSHA and ANSI standards. 3. Safety Coordination and Responsibilities 3.1 Plant Management Overall Accountability: The plant management holds ultimate responsibility for ensuring that all safety procedures are in place and adhered to by all personnel. Coordination of Safety Programs: Management will coordinate with safety officers and external bodies to implement and enforce the safety program. Emergency Response Planning: Management is responsible for ensuring the establishment of emergency procedures, including electrical hazards, fire, and evacuation plans. Regular Safety Audits: Conduct periodic safety audits to ensure compliance with OSHA and ANSI regulations. 3.2 Safety Officers and Coordinators Education and Awareness: Safety officers will ensure that all employees are trained on the plant’s safety standards and have access to continuous safety education. Incident Reporting and Investigation: Safety officers will oversee the reporting, documentation, and investigation of safety incidents, ensuring adherence to OSHA standards for injury and illness reporting. Safety Inspections: Perform daily and weekly inspections to ensure that plant operations comply with all relevant safety standards. Safety Equipment Compliance: Ensure that all employees are provided with necessary personal protective equipment (PPE) as per ANSI Z87.1 (eye and face protection) and other relevant ANSI standards. 3.3 Employees Compliance with Safety Procedures: All employees are required to follow safety protocols and participate in safety programs. Reporting Unsafe Conditions: Employees must report any unsafe conditions or practices immediately to their supervisors. Use of PPE: Employees must properly use personal protective equipment (PPE) provided by the plant, including but not limited to gloves, hard hats, safety goggles, hearing protection, and flame-resistant clothing, in compliance with ANSI and OSHA requirements. Engagement in Safety Drills: Employees must participate in regular safety drills, including fire drills, electrical shock hazard drills, and evacuation exercises. 4. Risk Assessment and Mitigation 4.1 Hazard Identification A comprehensive hazard assessment will be conducted on a biannual basis to identify potential risks in the electrical plant. These hazards include but are not limited to: Electrical shock and arc flash High-voltage equipment Confined space entry Fire and explosion hazards Chemical exposures Mechanical hazards from rotating machinery 4.2 Risk Mitigation Plan Based on the identified hazards, a tailored risk mitigation plan will be devel
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Safety coordination and planification accord with OSHA and ANSI for Employees Working in a Power Electrical Plant in Puerto Rico Creating a comprehensive safety coordination and planning protocol for employees working in a power electrical plant in Puerto Rico, according to OSHA (Occupational Safety and Health Administration) and ANSI (American National Standards Institute) standards, involves integrating safety best practices, regulatory compliance, and environmental considerations specific to the location. Here's a breakdown of the key elements you would need to include in your safety coordination and planning: 1. Compliance with OSHA Regulations Ensure that all operations comply with OSHA standards. For electrical power plants, the relevant OSHA standards primarily fall under: 29 CFR 1910 – General Industry Standards Subpart S – Electrical (1910.302-1910.399) Subpart E – Personal Protective Equipment (1910.132) Subpart K – Electrical Power Generation, Transmission, and Distribution (1910.269) Key OSHA requirements include: Lockout/Tagout Procedures (LOTO) – For the safety of workers performing maintenance or repairs on electrical equipment. Personal Protective Equipment (PPE) – Proper equipment for workers such as insulating gloves, safety helmets, face shields, flame-resistant clothing, and hearing protection. Electrical Hazard Safety Orientation – Provided documented safety guidance on electrical hazards, including proper use of tools, equipment, and required risk-mitigation measures. Permit-Required Confined Spaces – If workers enter confined spaces for maintenance or inspection, they must follow procedures for confined space entry and rescue. Fall Protection – Ensure the use of fall protection when working at heights. 2. ANSI Standards for Electrical Safety ANSI provides additional guidance on electrical safety, including: ANSI Z10 – Occupational Health and Safety Management Systems: This provides a framework for implementing an occupational health and safety (OHS) management system and identifying hazards before they become serious problems. ANSI/IEEE C2 – National Electrical Safety Code (NESC): Specifies standards for the design, construction, and maintenance of electric power facilities to ensure safety. 3. Site-Specific Safety Plan Develop a site-specific safety plan that outlines the hazards particular to the electrical plant. For this, consider the following: Electrical Hazards: Arc flash, shock, and electrocution risks. Fire Hazards: Electrical fires, flammable chemicals, or equipment. Workplace Ergonomics: Preventing injuries from repetitive motion or improper lifting. Chemical Handling: In case of transformer oils or hazardous materials. Natural Disasters: Since Puerto Rico is susceptible to hurricanes and tropical storms, plans should include storm safety protocols (e.g., evacuation plans, temporary shutdown procedures).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. I had several phone calls with the GWC (RG Engineering) project manager, Raul Berrios, to discuss the project contract requirements and contract progress. Participated in Team Meeting with Sargent & Lundy Staff, Mike Kuczysnski, Gilberto Sucre (DCMC), Enrique Laya, CDM Smith, and Angel Alicea Rodríguez Sargent & Lundy to discuss the Phase II Request for Comments to the contract (4339_9510)documents, and the lack of structural details in the design drawings. It was announced that the delivery of the construction drawings for the Aguirre BESS site has been rescheduled for the end of August 2025.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Walk through the Aguirre Complex to identify possible locations for the project sign installation. The information was requested by Gabriel Pérez (CDM Smith) and Gilberto Sucre (DCMC). Various pictures were taken and should be discussed with the Genera-PR Plan Manager, Alexis Cruz.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Submittals 0010 Rev. 1, submitted by RGE, is being verified following comments. Work has been done to validate the comments and safety standards applicable to the program.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Coordination meeting with Jose Segarra (RGE) and Andres Concepcion (DCMC) where the safety issues required for the work of lifting the containers and the notes made from the lifting plan were discussed.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria.4339_9510 BESS, RFC Genera PR/New Fortress Energy site visit and coordination meeting with key project stakeholders to review the new project areas, including LPG Gas and Battery Energy Storage System (BESS) zones. Attendees included: Jorge A. Mercado, Andrés Carrión, Andrés Concepción, Carlos De Jesús, Luis Duque (DCMC), Herminio Arroyo, José M. Cintrón (Genera), Samuel Cha and Sophie Drake (New Fortress Energy - NFA). The visit focused on aligning project scopes and ensuring clear communication between Genera PR and New Fortress Energy teams.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Herminio Arroyo (GeneraPR) to discuss action items corresponding to GeneraPR Cambalache Plant administration. Coordinated activities in field and provided updates of project progress.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Jesus Cintron, Herminio Arroyo (GeneraPR) and Luis Damudt, Luis Duque (DCMC) and did a site walkthrough and tour to discuss the BESS project on site and potential new projects for the future.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Followed up with Gilberto Sucre (DCMC) direction to coordinate and organize design drawings for a page turn meeting with the designer (Sargent and Lundy). Coordinated internal team to create observations to drawings.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -Coordinated with Gilberto Sucre and Paul Browne (DCMC) to obtain approval to purchase equipment for the project warehouse inventory. Generated a list of equipment.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Walkthrough on-site to monitored GeneraPR activities while moving materials off the site to start opening space for the construction.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Jorge Mercardo (DCMC) and Jose Segarra (RG Engineering) to discuss submittal #10 and discuss regarding crane rigging plan and safety measures.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Monitored and reviewed submittals in Procore. Ensure received responses during the week were satisfactory in order to move forward distributing the correspondence. Requested to Theresa Perez (DCMC) to provide access to General Contractor (RG Engineering) new staff.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Comparing IFB drawing with the IFC drawing to identify any changes that can impact the contractor or a posible change order we are reviewing the architecture drawing set.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Submittal and RFI Meeting Organizer Eduardo Rivera of DCMC, with Carlos Hernandez, Maria Reyes, Javier Almodovar, Ricardo Lopez, Suleyka Rege and Ida Ramirez from (ARG/CERES,) Gilberto Soto and Jaime Pesquera of (DCMC), Nelson Soler of (CDM-Smith). Submittal and RFI meeting with ARG/CERES to inform how will be the protocol for submittal and RFI generated by ARG/CERES to Genera in meeting was discuss the difference between a RFI and Corresponds and how should be submitted a submittal and submittal should be included with specification number to understand what the topic is related.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 - PMO Reporting Meeting - DCMC PMO staff meeting to be discussed specific need of reporting based on project execution development per area. Working on live tracker presentation template and review updates from BESS and Peakers projects. Participants DCMC (Frances Vallejo, Raissa Borges, Glorimel Torrado, Jean Pierre, Eduardo Rivera, Paola Arroyo, Paul Brown and Lauren Wells).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with the review of IFB drawing versus IFC the architecture review was completed, and the structural review was completed I am working with the electrical set drawing review.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with the electrical set drawing review a total of 39 drawing has been review for the electrical drawing and was identify a total of 20 drawing that has not been issue for construction. Received a call from Jean Menay of DCMC for advice in regard of the fire protection system of Vega Baja site. Genera and NFE site visit did not arrive to project they were at Cambalache but did not visit Vega Baja site.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing email related to project. Have a meeting with Jaime Pesquera and Gilberto Soto (DCMC) to discuss site viste today by Genera and NFE, we are reviewing all site area to see that CES plan es in place and review all site area in preparation of site visit.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a variance investigation at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC. The focus was on analyzing inconsistencies between physical inventory and system reported quantities across storage locations EF 001 to EF 005, EG 001 to EG 006, EH 001 to EH 004, EI 001 to EI 006. Core activities included identifying the root causes of bin level discrepancies, reviewing data entry practices, and assessing procedural failures affecting inventory accuracy. All findings were documented to support corrective actions and improve alignment between physical stock and inventory records.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 - PMO Reporting Meeting - DCMC PMO staff meeting to discussed specific need of reporting based on project execution development per area. Working on live tracker presentation template and review updates from BESS and Peakers projects. Participants DCMC (Frances Vallejo, Raissa Borges, Glorimel Torrado, Jean Pierre, Eduardo Rivera, Paola Arroyo and Lauren Wells).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an inventory recount at the Costa Sur warehouse in coordination with Mr. Hernan Machado from DCMC. The recount focused on physically verifying item quantities, evaluating bin utilization, and confirming label accuracy. Special attention was given to identifying and correcting discrepancies between actual inventory and system records. All corrections were properly documented, supporting data integrity across zones EF 001 to EF 005, EG 001 to EG 006, EH 001 to EH 004, EI 001 to EI 006, and reinforced compliance with warehouse tracking standards.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a structured operational meeting with Juan Vallejo, Giovanni Taffanelli, and key DCMC warehouse staff to review current inventory workflows and evaluate opportunities for improvement. The discussion centers on identifying potential bottlenecks in material flow, improving documentation accuracy, and reinforcing alignment between physical inventory movement and digital records. The session also explores strategies to enhance response readiness and resilience in warehouse operations under emergency scenarios.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performs a detailed review of inventory data and prepares revised cycle count documentation to support upcoming operational efforts at the Costa Sur warehouse. The activity is coordinated with Mr. Hernan Machado from DCMC to ensure compliance with projects standards and inventory protocols. Focus areas include data validation, generation of tracking materials for cycle count execution, and verification that all procedures align with established quality benchmarks. Today's scope of work covers inventory locations from EF 001 to EF 005, EG 001 to EG 006, EH 001 to EH 004, and EI 001 to EI 006.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Costa Sur warehouse, compiled a comprehensive inventory performance report for Mr. Anthony Vega of Genera PR. The report consolidated data from locations BH 090 to BH 146, EF 001 to EF 005, EG 001 to EG 006, EH 001 to EH 004, EI 001 to EI 006, BA 001 to BA 006, CC 0057 to CC 072. The analysis focused on catalog ID reconciliation, variance detection, and adherence to inventory thresholds. Key findings addressed cost discrepancies, physical mismatches, and operational gaps, providing a foundation for enhanced transparency and informed corrective action planning.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performs scheduled inventory cycle counts within designated storage zones, focusing on areas EF 001 to EF 005, EG 001 to EG 006, EH 001 to EH 004 and EI 001 to EI 006. The effort contributes to ongoing warehouse improvement initiatives by reinforcing inventory governance and enhancing the reliability of system reported data. Key tasks include verifying alignment between physical stock and system records, identifying discrepancies, and conducting preliminary assessments to determine the underlying causes of recurring variances.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 - PMO Reporting Meeting - GENERA-PR PMO staff meeting to discuss project execution development per Power Plant for Critical Components. Working with GENERA-PR Joaquin Quinoy, Jorge Sanchez, Carlos Negron, Jose Molina, Eliseo Arroyo, Rene Rodriguez, and Carlos Menendez & DCMC D'Alexzander Gonzalez. PW-9510 FAASt A&E
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-Project Data Management | Direct-PA | Activities necessary for project data management (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Based on the shared information by GENERA-PR staff, develop a narrative to share with Roberto Bosch, DCMC in accordance with the staff guidance on critical components. PW-9515 FASST A&E.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -Continue overall status presentation of Critical Components Status requested from GENERA-PR Joaquin Quinoy. PW-10710 Equipment & Material
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed submittals RGE-0010 and RGE-0010.1 related to the Work Plan for Trailer Unloading for the BESS project (PW9510). Assessed proposed unloading sequence and equipment use to ensure alignment with site safety protocols and project logistics. Additionally, reviewed related email correspondence with RGE regarding equipment staging and unloading coordination, and flagged pending clarifications for follow-up.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting Cambalache Discussed the Rigging Plan Clarification with Jose Segarra from RGE and Jorge Mercado and Andres Concepcion from DCMC.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Initiated internal review of preliminary structural drawing CAB00-SF-BYS-0006 (Slab Module Sections) for the Cambalache BESS project (PW9510). The review focused on general planning layout and structural arrangement to support upcoming design coordination efforts.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS, RFC Meeting Genera PR/New Fortress Energy Visit Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC, Herminio Arroyo Jose M. Cintron from Genera
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Worked on all existing dwg from IFB & IFC to identify any possible change orders, today we compared all the drawings with Eduardo Rivera Jordan, DCMC.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Walked the site to spot hazards, document them, and initiate the process to resolve or mitigate the situation to address risks before they grow or potentially cause damage or injury. Make sure it was up to par, for we have a visit today from Genera-PR.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a Submittal and RFI Meeting with Carlos Hernandez from (ARG/CERES,) Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith) and went over Project Documents Overview. Also went over RFi #009 Precast Determination documents status in the Procore platform and all the punch list items that are closed for the meeting and referred to upper management.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today we had a meeting with Carirma Sánchez from Homeca with DCMC team Jaime Pesquera Eduardo Rivera and CDMSmith Nelson Soler, after we had a meeting with Carlos Hernández from ARG discussing the submital and RFI meeting, after Annex J was being reviewed to answer questions from ARG.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1503 and 1504 from locations CC057 to CC072 for a total of 318 pcs.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BA001 to BA006
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BA001 to BA006
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations BA001 to BA006
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BA001 to BA006
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BA001 to BA006
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations EF 00 001 to EF 00 005; EG 00 001 to EG 00 006; EH 00 001 to EH 00 004 and EI 00 001 to EI 00 006.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations EF 00 001 to EF 00 005; EG 00 001 to EG 00 006; EH 00 001 to EH 00 004 and EI 00 001 to EI 00 006.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations EF 00 001 to EF 00 005; EG 00 001 to EG 00 006; EH 00 001 to EH 00 004 and EI 00 001 to EI 00 006.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BH 090 to BH 146 at the Aguirre warehouse to initiate the cycle counts.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BH 090 to BH 146
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations bh 090 to bh 146, RECOUNT LIST #1376/1382/1389
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations bh 090 to bh 146, LIST #1371/1372/1373/1377/1386
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CC057 to CC072 Cycle Count List # 1494
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CC057 to CC072 to begin the cycle counts.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CC057 to CC072.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with Lauren Wells (Lemoine), Frances Vallejo and Gilberto Sucre (both DCMC) to talk about some discrepancies in the execution of project management procedures.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 151 | 302 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Continuation Costa Sur BESS Procurement RFP & RFQ ensure documents were created_reviewed_stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team/Download all BESS Project Check-in Tracker Reports
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Bess Projects Incoming documents for review & processing/Costa Sur BESS Procurement RFP & RFQ ensure documents were created_reviewed_stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team/Incorporate Cambalache BESS new RG team members
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Continue with the QA/QC for Costa Sur drawing plans prior to the uploading and review/publishing review; reviewing electrical and mechanical drawings to contrast with Technical Specifications.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the General Requirements to confirm obligations between owner, contractor, and owner representative, to disclose the proper workflow for approvals and roles inside Procore for users that approves of respond to different Procore items and procedures.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work with the SOPs for Forms and Correspondence Tools of the Procore Platform.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Perform QA/QC for Costa Sur drawing plans prior to the uploading and review/publishing review; reviewing drawing numbering, titles, and typical construction notes.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Updating the Genera roster with the names of new employees, including their email addresses, worksite locations, and phone numbers. Sent the updated roster to Frances Vallejo and Gilberto Sucre (DCMC).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 139 | 417 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-¦ I attended the meeting where the Community Resilience Plan approved by the Municipality of Toa Baja was officially presented. As part of this task, I took notes, answered questions and collected key contacts to strengthen community relations with Agenda Ciudadana within the framework of the Comprehensive Program for Community Resilience (WCRP). I actively participated in the Assembly, strengthening community ties and supporting local resilience efforts. The team from Genera PR, Jorge Bracero, was present at the meeting, as well as members of Iniciativa Comunitaria, including María de Lourdes Lara. There were also members of the community of Toa Baja, Levittown.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 PMO - DCMC Meeting to discuss PMO requirements to be in compliance with federal requirements. Working on live tracker presentation template and review updates from BESS and Peakers projects. Also reviewing improvement opportunities based on day to day operation. Participants DCMC (Frances Vallejo, Raissa Borges, Glorimel Torrado, Jean Pierre, Eduardo Rivera, Paola Arroyo and Paul Brown), from Lemoine Pro-Core (Lauren Wells).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA Genera Deliverable 11- Project Management DR 4339- Coordinate a educational outreach visit on Battery Energy Storage Systems (BESS) at the Summer Camp in Vega Baja. Preparation involved conducting strategic phone meetings with Gil Rivera, Communications Coordinator for Vega Baja, to align messaging and community engagement approaches. Collaborations also included Jorge Bracero from the Genera PR team to shape the technical content, educational materials, and ensure consistency with broader outreach goals. Additionally, logistical arrangements such as scheduling, transportation, and onsite requirements were managed. Key data concerning BESS, camp demographics, and the local context were analyzed to tailor the experience effectively. The visit is set for the upcoming Monday, with all efforts aimed at delivering an informative and impactful interaction for the participants.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA Genera Deliverable 11- Project Management DR 4339- Begin coordination for the meeting today at the Toa Baja Community Resilience Plan Presentation Assembly Participation at the Levittown Lions Club, Toa Baja. These tasks included concluding revisions to the letter to be presented at the activity and finalizing edits to the material to be delivered.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-¦ Meeting with the Genera PR team: Jorge Bracero, Mike Albladejo, Joaquín Carrillo Maldonado, Camille Rodríguez. Also present was Enactus Puerto Rico staff, Adeline Perez. During this meeting we discussed all the details related to the community activity in Palo Seco, Toa Baja, in which we will be addressing details about: logistics, details, materials, among others.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria- Travel from City View Guaynabo to Toa Baja to participate in a community meeting with the Genera PR team, Jorge Bracero. The meeting was convened by Agenda Ciudadana. This meeting is called the Assembly to Present the Plan to the community.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-¦ Meeting with Frances Vallejo, DCMC Partners, to discuss the status of my projects such as: status of the visit to the sites, sending presentation of the community meetings, follow-up on pending tasks such as today's meeting with the organization Agenda Ciudadana in which we will be discussing some specific issues about the community projects in the region
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 139 | 34.75 | 139 | Yes | 146796 | PREPA Genera Deliverable 11- Project Management DR 4339- Update meeting with Jorge Bracero, from the Genera PR team, to discuss pending issues related to community meeting projects and meeting today with Agenda Ciudadana. During the meeting, issues related to the printed materials that we are going to deliver today at the meeting as well as the tactics that we will be implementing as part of the BESS and Peakers project were addressed
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. On site- Cambalache Warehouse Alignment meeting with Andres Concepcion (DCMC) Jesus Cintron (GeneraPR) and Herminio Arroyo (GeneraPR) for the 4339_9510 BESS_Cambalache project to discuss warehouse equipment inventory and removal to set the site for demolition work.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 37 pages were examined.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Aguirre BESS Project- Conducted detailed review of the Battery Energy Storage System (BESS) General Work Contract Technical Specifications (Specification No.: G-3400, Revision A). Focused on validating the scope of work, contractor obligations, and technical compliance criteria. The review encompassed 34 specification pages to ensure alignment with project execution requirements.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - Peakers - Attended a project planning meeting with Abraham Velázquez (DCMC) to discuss the overall schedule for the Peakers project. The session focused on identifying key milestones, sequencing critical path activities, and coordination with design and construction teams. Emphasis was placed on aligning permitting, mobilization, and procurement timelines to prevent delays. Several tasks were flagged for follow-up to ensure alignment with project goals and resource availability. Team Members participants (DCMC): Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - Peakers - Attended an on-site coordination meeting with Abraham Velázquez (DCMC), Raissa Borges (DCMC), and the Siemens Energy Logistics Team (Luis Quiros, Connor Mcintire, Ragan Watson, Adrian Reza and Jaime Avila). The purpose of the meeting was to review the delivery schedule of major equipment, assess the conditions and access of the designated entry gate, and explain the planned logistics layout for equipment staging and installation. The team walked the site to verify clearance, routing paths, and unloading areas. Alignment was established between Siemens Energy’s delivery plan and the project schedule to ensure efficient mobilization and minimize disruptions during construction. Team Members participants (DCMC): Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for BESS project considering construction in BESS project time line of demolition of existing concrete foundation for power generator, new cable trays, new pipping supports, delivery dates for fire suppression system on unit 1 and 2 in BESS equipment (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 134 | 402 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked on Meeting in site Costa Sur about Peakers project considering Siemens equipment delivery dates, inspection in site the routes for delivery and area for storage with employee (DCMC) Rafael Barrera, Abraham Velazquez, Raissa Borges, employee Siemens Jaime Avila due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for Peakers project considering construction in Peakers project time line considering Siemens delivery dates, Siemens installation guides in projects turbine 1 & 2, concrete pads adjustments for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Lemoine Quality Control/Assurance Plan, Inspections plan, Subcontractor Participation in Quality Control Plan, Pre-Installation Meetings and Follow Up Inspections to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 - PMO Reporting Meeting - DCMC PMO staff meeting to discuss specific need of reporting based on project execution development per area. Working on live tracker presentation template and review updates from BESS and Peakers projects. Participants DCMC (Frances Vallejo, Rafael Calderon, Glorimel Torrado, Jean Pierre, Eduardo Rivera, Paola Arroyo, Paul Brown and Lauren Wells).
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 122 | 366 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Costa Sur BESS and Peakers walkthrough and meeting with Abraham Velazquez, Carlos De Jesus, Rafael Barrera, Luis Echevarria, Carlos Bayron, DCMC and SIEMENS/BARNHART contractor representatives Luis Quiros, Adrian Reza and Ragan Watson to review and discuss equipment's delivery logistic.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 122 | 427 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Costa Sur site visit to discuss with BESS and Peakers Costa Sur team DCMC: Abraham Velazquez, Carlos De Jesus, Rafael Barrera, Luis Echevarria and Carlos Bayron, Discussed the DCMC project details, status and schedule.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Franco Malave, Sylvia | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 7.2 | 7.2 | 7.2 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Meeting and Site Visit with Herminio Arroyo (Genera), Jesus Cintron (Genera), Samuel Cha (NFE), Andres Concepcion (DCMC)
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Borges, Raissa | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 0.7 | 116.2 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Site visit to Costa Sur BESS and Peakers project 10710 with DCMC team Abraham Velazquez, Carlos De Jesus and others and SIEMENS contractor representatives for reporting purposes.
2025-07-16 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Franco Malave, Sylvia | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 0.7 | 52.78 | 0.7 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Roundtrip Work base to Cambalache Power Plant for a meeting and site visit with Herminio Arroyo (Genera), Jesus Cintron (Genera), Samuel Cha (NFE), Andres Concepcion (DCMC).
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 809.63 | 809.63 | 809.63 | Yes | 146796 | Grainger - Cambalache - Portable Labor Printer
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 243.07 | 243.07 | 243.07 | Yes | 146796 | Home Depot - Storage Totes (25) for Cambalache Equipment.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore submittal responses.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in BESS/PEAKERS page turn meeting discussed risks assessments for each project, reviewed status of each project Attended meeting Raissa Borges Almodovar- DCMC Gilberto Sucre DCMC Frances Vallejo Rosich DCMC Rafael Calderon DCMC
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal review of weeks reports from Peaker projects and reviewed emails
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in meeting Peaker commercial schedule Reviewed current progress of each project compared and reviewed base line schedule to projected start of construction on the Peaker projects. Attended the meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 attended GENERAPR/ RGE Peaker's meeting Discussed schedule of procurement, delivery schedule and open items to be formalized as RFI and submitted for record and response. attended meeting Badger, Keith - SIEMENS-ENERGY Kunjappan, Manoj SIEMENS-ENERGY German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Rafael Calderon DCMC Miguel A Del Valle Sargent & Lundy
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Preakers Program - Execution Change from Design/Bid/Build to Design/Build Met first with Mark Merritt - DCMC to provide update on Jesus Cintron request - Genera to evaluate and provide recommendations of this proposed execution change prompt by the poor and late design execution of S & L. Was guided to meet with Kelly George, Rick Patterson DCMC due to their experience with other Federal Design Built Projects. Once concluded met with Abraham Velazquez - DCMC to discuss the agenda for the meeting to take place with the PM/CM in the afternoon.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Meeting with Raissa Borges - DCMC to review and provide comments to the Procore Financial Process Flow Chart. Action Item to meet with D'Alexzander Gonzalez - DCMC need to include the budget reporting process.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Project Team Notification of Buy American Act as it applies to the BESS and Peaker's Program to be taken into consideration during the submittal approval process. Sent internally to all Site Managers. Luis Roman, Frances Vallejo & D'Alexander Gonzalez - DCMC. Future team meeting to be scheduled as a question and answer section.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Weekly Construction Meeting Led by Rafael Barrera DCMC main topics were addressed: Contractor Submittals for Safety, Quality, EHS workshop, personnel documentation and badging. Mobilization, updated schedule and schedule of values. Gilberto Sucre - DCMC provided contract status, estimated NTP date and IFC drawings comments to be discussed next Tuesday with Sargent & Lundy on the page turn review. Jose Segarra, Xiomara Perez - RGE, Gabriel Perez - CDM Smith, Carlos Bayron, Luis Echevarria, Gilberto Sucre - DCMC
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One Pager BESS Weekly Updated Progress with Raissa Borges - DCMC and Franklyn Colmenares - CSA Group.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Internal DCMC - Peakers Execution Change to Design/Build. Discussed the cons and pros with Kelly George and Rick Patterson - DCMC. Highlighted the challenges of approval with FEMA and Core 3.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS/Peaker's Project Schedule & Budget Carlos Palomares CDM Smith presented the weekly update for both programs. Gabriel Perez, Enrique Laya, Rafael Pabon - CDM Smith Franklyn Colmenares - CSA Group German Nunez - Genera Abraham Velazquez -, Gilberto Sucre - DCMC
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in a strategic planning session with Jesus Cintrón, Germán Nuñez (Genera), Carlos Palomares, Rafael Pabón (CDM Smith) Sheila Torres-Sterling, Abraham Velázquez, Gilberto Sucre and D'Alexzander González (DCMC) for the Generation Fleet Peakers project. The discussion focused on evaluating a potential shift in procurement methodology from the traditional design-bid-build approach to a design-build delivery model. This shift was assessed in light of current project constraints, including timelines, resource allocation, and funding deadlines. We weighed the advantages, such as streamlined procurement, reduced interface risk, and faster implementation, against challenges, including contractor interest and qualifications, design control, and federal compliance considerations. The team also examined how the proposed change could impact FEMA funding eligibility and documentation requirements. The discussion helped frame a path forward that aligns with project goals and regulatory expectations.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera / LUMA Risk Management Meeting BESS chaired by Carlos Palomares and Gabriel Perez - CDM Smith. Reviewed and updated the Risk Register with LUMA for the entire program. LUMA - Zuleika Perez Sargent & Lundy - Mike Kuczynski DCMC - Gilberto Sucre CSA Group - Franklyn Colmenares CDM Smith - Carlos Palomares & Gabriel Perez.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-BESS and Peaker's Project Schedule & Budget Meeting. Attendees were Foster Veazey (Lemoine), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Carlos Palomares (CDM Smith) .
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore Financial items.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items for budget change workflows.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating notes for Procurement meeting to align with Procore tasks.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore distribution lists for Sargent and Lundy users.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore for adding new users and allowing RGE to have access to drawings for Costa Sur.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore task for tracking purposes.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for flowcharts for project financials.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Ivette Miranda Rios, Mike Kuczynski, Miguel Del Valle (Sargent and Lundy), Luis Roman (DCMC) to discuss Submittal response alignment.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procurement processes to incorporate into Procore.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Project Financial Flowchart from Raissa Borges (DCMC).
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore submittal responses to discuss with Sargent and Lundy on alignment with their transmittals.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed Genera’s original funding request submitted to PREPA concerning the allocation of additional FAASt funds. Held a detailed discussion with D’Alexzander González (DCMC) to evaluate the tone, structure, and core messaging of the anticipated response. The objective was to ensure that Genera’s position is communicated clearly and persuasively, while maintaining a constructive, professional, and collaborative tone that supports ongoing coordination with PREPA and reinforces the urgency and justification for the requested funds.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review the site presentation by EHS. Review the Fire System used in Mega Packs by Tesla. Conference call with Andres Concepcion (DCMC) about new task to Cambalache Warehouse, make the inventory and accounting. Coordinate delivery toilet tank with Portosan.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Conference call with Carlos de Jesus (DCMC) about Costa Sur Genera project, include Health and Safety topics, Quality topics, calender topics and others. Conference call with Gabriel Morales (DCMC) about Health and Safety topics included the lettering. Continuing review the Fire system document and requirements to comply with Local and Federal law. Review the FM Global requirements to Fire System of Mega Packs. Review the site presentation by EHS. Review the Fire System used in Mega Packs by Tesla.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Continuing the procurement process for necessary tools across all Genera projects to ensure site readiness. Reviewed documents related to the Costa Sur Genera project in preparation for the pre-construction meeting. Participated in the pre-construction meeting for the Costa Sur project with DCMC teams (Gilberto Sucre, Rafael Barrera, Luis Echevarría), RGE construction contractors (Jose Robles, Jose Segarra), and others. Discussed safety protocols, construction planning, and logistics. Coordinated with Genera Osvaldo de Jesús, regarding the Vulnerability Plans for Genera sites. Continued reviewing fire protection documents for the Vega Baja Genera site and submitted a summary report to Eduardo Rivera (DCMC) for review.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and edit email received from Lauren Wells (DCMC) regarding the use of Procore by all employees in the PMO (BESS and Peakers) and the need to send to Theresa Perez (DCMC) all documents before a site visit.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Budget and Schedule meeting for BESS and Peaker project with Gabriel Perez (CDM), Carlos Palomares (CDM) and Gilberto Sucre (DCMC).
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria n- Visit the Yabucoa site to meet with Gabriel Morales and Luz Ramirez (DCMC) and make inspections on trailer needs.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Andres Concepcion and Carolynn Baez (DCMC) to discuss equipment needed at Cambalache site for the inventory management.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet PW11855 - Participated in a strategic planning session with Jesus Cintrón, Germán Nuñez (Genera), Carlos Palomares, Rafael Pabón (CDM Smith) Sheila Torres-Sterling, Abraham Velázquez, Gilberto Sucre and D'Alexzander González for the Generation Fleet Peakers project. The discussion focused on evaluating a potential shift in procurement methodology from the traditional design-bid-build approach to a design-build delivery model. This shift was assessed in light of current project constraints, including timelines, resource allocation, and funding deadlines. We weighed the advantages, such as streamlined procurement, reduced interface risk, and faster implementation, against challenges, including contractor interest and qualifications, design control, and federal compliance considerations. The team also examined how the proposed change could impact FEMA funding eligibility and documentation requirements. The discussion helped frame a path forward that aligns with project goals and regulatory expectations.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet PW11855 - Began preparing the requisition package for the Jobos Demolition RFP. Conducted a detailed review of the SOW to confirm alignment with the FEMA project version, ensuring consistency with grant requirements and eligibility criteria. Verified that the SOW reflected project objectives, allowable activities, and cost-reasonable language as required under FEMA Public Assistance guidelines. Upon confirming compliance, began drafting the justification memorandum to support the procurement request, outlining the project need, procurement method, and rationale for proceeding.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Compiled the necessary information related to the Generation Fleet v0 project in response to PREPA’s Request for Information (RFI) concerning Vivienda’s ER1 Cost Share Program. Reviewed and organized the data into an Excel sheet to ensure clarity and completeness. Sent the compiled information to José Ralat (DCMC) for review and validation.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today i inspected the field to verify if there were new leaks on the concrete and changed oil pads and absorbent barriers. Discussed with Carlos Hernandez from ARG meeting for tomorrow and started preparation for the items to discussed.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS-Project) During this period, I read and reviewed a presentation on Occupational Health and Safety. The presentation included the following key topic: Confined Spaces, Hot Work, Fall Prevention, Electrical Safety, Evacuation Routes, Inspections, Cranes, and Spill kit. Additionally, I began designing a list for emergency contact numbers.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS- Project) During this period, I carried out the following activities: Designed and installed safety and directional signage (Exit, Bathroom, keep this place clean, Fire Extinguisher, First Aid Kit, and PPE), Set up a printer, installed a fire extinguisher in accordance with safety regulations, identified a potential evacuation area to be used in case of emergency, and organized and adapted a designated space into a functional kitchenette.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents from Sargent & Lundy, package identified as GENERA-15240-061-0017, for the Installation phase at the Aguirre Site, 17º57'10"N, 66º13'49"W. Review items one to 163 and send comments with findings to Gilberto Sucre (DCMC) to evaluate and discuss with the client Genera PR.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in the Weekly Construction Meeting for the Costa Sur BESS project. In this meeting, the main discussion subject was the rigging plan for the Tesla Batteries installations. There were also follow-up items, including the Safety Plan, Work Plan, Quality Plan, and Coordination between the awarded General Civil Contractor, RG Engineering, and the DCMC Construction Team. Representing RG Engineering was José Auli (RGE). It was also pointed out in the meeting that the need for the Surveyor to be on site to conduct an As-Built survey at the proposed location was necessary, as the General-PR Plant management staff had informed them of the presence of concrete piles under the proposed concrete platforms. Additionally, to identify existing utilities and the scope of work required for these utilities to be removed or relocated. The Sargent & Lundy personnel at the meeting, Wilson Alicea, informed the group of the recent site visit by the design team regarding the relocation of the existing utilities, and that the information would be shared later.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified RFP No. 4900 Civil & Structural Works for 158 MW Battery Energy Storage System at Aguirre, Issued by the Puerto Rico Electric Power Authority (“PREPA”), represented by its agent, Genera PR LLC (“Genera”) Date Initial RFP Issued: January 31, 2025 Proposal Submissions Due: March 31, 2025 (GENERA-15240-061-0017). The specific subject reviewed was regarding the "BY American Act" (BAA). Send an email to Gilberto Sucre, DCMC, with the following comments: According to the By American Act (BBA), it has been defined in RFP No. 4900 for the Civil & Structural Works for the 158 MW BESS System at Aguirre, in section 6.4.1.16. Nonetheless, I don't see the Exhibits as part of the RFP documentation. The Owner needs to clarify which definition will be applied, and whoever is evaluating the contracts should have a clear definition of this subject. The definition requires the proponent to declare the percentage of FEP material to be used. What percentage of Foreign End Products (FEP) will be allowed? Genera PR needs to keep in mind that the material market is volatile these days, with the USA's economic war against the World. Even though this is a Federal funding program, what will be the general guidelines for this definition of BAA? These observations will be discussed in a meeting with Genera PR and Sergeant & Lundy.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Continue revising mechanical piping relocation drawings were connecting to existing full oil supply, existing full oil return system, existing boiler feed water system, existing raw water system, existing service air system and utility piping relocation. Number of sheets are 32 to 49.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Reviewed mechanical piping relocation drawings for the Cambalache BESS project, focusing on sheets 1 through 20. Verified accuracy of routing details, equipment connections, and alignment with previously approved layouts. Followed up with the design team to address any missing or unclear elements to ensure readiness for field implementation.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Reviewed architectural drawings for the Control House at the Cambalache BESS project, focusing on sheets 1 through 11. Verified layout details, wall sections, and mechanical/electrical interface points to ensure completeness and consistency. Notes were prepared for coordination with the design team.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Cambalache ¦ DR4339 – Reviewed mechanical piping relocation drawings for the Cambalache BESS project, focusing on sheets 21 through 31. Verified accuracy of routing details, equipment connections, and alignment with previously approved layouts. Followed up with the design team to address any missing or unclear elements to ensure readiness for field implementation.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Meet with Eduardo Rivera Jordan (DCMC) to discuss how to work the schedule construction project and where I can find the project documentation.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the systematic review of the Costa Sur BESS design drawings IFC (7/10/25) with a focused effort on refining the master list of missing items, incomplete details, and open technical comments. The process included cross-referencing drawing sheets to validate consistency, identifying annotation gaps, and confirming alignment between plan views, sections, and details. Emphasis was placed on ensuring critical construction information such as dimensions, elevations, connection points, and material specifications was clearly defined. The objective is to consolidate a robust and actionable comment list to facilitate efficient coordination with the design team once formally submitted.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- DCMC Site team lead by DCMC Rafael Barrera internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety workshop, submittals and RFI's. Continued the internal review process of the Costa Sur BESS design drawings. Focus was placed on cross-checking previously noted comments against adjacent drawing sheets to ensure consistency across plan sets. Comments were refined and categorized by discipline to streamline the coordination process prior to formal submittal to the design team. Team Members participants (DCMC): Gilberto Sucre, Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Start Reading Attachment E: Federal Contracting Clauses that consists of 105 pages.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site meeting and walk with Luz Ramirez (DCMC) to discuss safety plans such as evacuation procedure, meeting point in case of an emergency, personal information sheets ideas to share in case of an emergency, etc. considering that the DCMC Partners office is not in the PREPA plant and it's not covered under any existing procedure. Also, remaining signs needed were created and installed such as the First Aid Kid and PPE's storage.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- DCMC Site team lead by DCMC Rafael Barrera internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety workshop, submittals and RFI's. Continued the internal review process of the Costa Sur BESS design drawings. Focus was placed on cross-checking previously noted comments against adjacent drawing sheets to ensure consistency across plan sets. Comments were refined and categorized by discipline to streamline the coordination process prior to formal submittal to the design team. Team Members participants (DCMC): Rafael Barrera, Carlos Bayron, Carlos De Jesus and Luis Echevarría.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the systematic review of the Costa Sur BESS design drawings IFC (7/10/25) with a focused effort on refining the master list of missing items, incomplete details, and open technical comments. The process included cross-referencing drawing sheets to validate consistency, identifying annotation gaps, and confirming alignment between plan views, sections, and details. Emphasis was placed on ensuring critical construction information such as dimensions, elevations, connection points, and material specifications was clearly defined. The objective is to consolidate a robust and actionable comment list to facilitate efficient coordination with the design team once formally submitted.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Continue creating a Unified Path to Integrate Safety, Health, and Environment (SHE) Step 4: Operational Control and Incident Management To reduce risk and ensure accountability: Implement standard operating procedures (SOPs) and checklists for SHE-critical tasks. Utilize digital systems to report, track, and investigate near misses, incidents, and unsafe conditions. Learn from every event through root cause analysis and continuous improvement. Step 5: Monitoring, Measurement, and Continuous Improvement Performance without feedback is guesswork. We will: Establish key SHE metrics (e.g., TRIR, lost time injury rate, emissions data). Perform regular audits, inspections, and management reviews. Engage third-party experts where necessary for independent evaluations. Step 6: Empowerment and Culture Change True integration happens when SHE becomes everyone's responsibility. We will: Foster a Just Culture—one that encourages reporting without fear. Launch recognition programs for SHE champions. Use storytelling, visual communication, and real-life examples to keep SHE messages alive. Step 7: Environmental Responsibility In response to growing climate and sustainability challenges, we will: Monitor and minimize our carbon footprint, waste generation, and water usage. Explore circular economy initiatives and green technologies. Ensure compliance with environmental regulations and pursue voluntary certifications (e.g., ISO 14001).
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre We are worked to create a Unified Path to Integrate Safety, Health, and Environment (SHE) At the heart of every successful and sustainable organization lies a deep-rooted commitment to the well-being of its people, the integrity of its operations, and the stewardship of the environment. As we move forward in a world that demands accountability, resilience, and responsibility, we recognize the need for a comprehensive and integrated approach to Safety, Health, and Environmental (SHE) management. The Vision: A Culture Where SHE is Second Nature We envision a workplace where safety, health, and environmental consciousness are seamlessly woven into the fabric of our day-to-day operations. A culture where SHE is not just a compliance requirement, but a shared value. One where every individual, from leadership to frontline workers, feels responsible and empowered to act. Step 1: Leadership Commitment and Policy Alignment Our journey begins with leadership. Top management will actively champion SHE by: Establishing a clear SHE policy aligned with our core values. Setting measurable objectives for safety performance, employee well-being, and environmental impact. Allocating necessary resources—time, personnel, and funding—to SHE initiatives. Step 2: Risk-Based Planning and Integration To embed SHE into our strategic and operational planning, we will: Conduct comprehensive risk assessments to identify and evaluate hazards to people, processes, and the planet. Prioritize actions using a risk matrix and align SHE goals with corporate KPIs. Ensure that project planning, procurement, and change management processes include SHE considerations at every stage. Step 3: Capacity Building and Workshops People are our greatest asset. We will invest in: SHE workshops tailored to job roles—from induction to advanced emergency response. Regular drills, workshops, and scenario-based simulations. Promoting mental health awareness and ergonomics alongside physical safety.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a follow-up meeting with Alexis Cruz, the Genera- PR Plant Manager for the Aguirre complex, to make a brief Team Introduction. It was attended by Carlos R. López Vallellanes, Sunem Martínez, and Luis Moctezuma (DCMC). The meeting consisted of an introduction of the new DCMC team member, Sunem Martínez, and to discuss a short project description of activities, to confirm with the plant manager the future TEmporary Power site location that could clash with the BESS layout as designed by S&L., and to discuss some details of the next steps for the project, including the bid award and construction schedule dates. Regarding the Safety topics, it was brought to Mr. Cruz's attention that the current evacuation plan should be combined with project-specific activities for implementation.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Evaluating the Geo-Technical Study Report from Jaca & Sierra for the Aguirre BESS Site.Job No.: 8666 Prepared by: Javier E. Osorio Carrasquillo, PE, MECE.This report contains 574 pages, including the cover. Pages Evaluated from cover page to page 29 out of 574 total pages.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified RFP No. 4900 Civil & Structural Works for 158 MW Battery Energy Storage System at Aguirre, issued by the Puerto Rico Electric Power Authority (“PREPA”), represented by its agent, Genera PR LLC (“Genera”) Date Initial RFP Issued: January 31, 2025 Proposal Submissions Due: March 31, 2025 (GENERA-15240-061-0017). The specific subject reviewed was regarding the "Buy American Act" (BAA). Send an email to Gilberto Sucre, DCMC, with the following comments: According to the Buy American Act (BAA), it has been defined in RFP No. 4900 for the Civil & Structural Works for the 158 MW BESS System at Aguirre, in section 6.4.1.16. Nonetheless, I don't see the Exhibits as part of the RFP documentation. The Owner needs to clarify which definition will be applied, and whoever is evaluating the contracts should have a clear definition of this subject. The definition requires the proponent to declare the percentage of FEP material to be used and percentage of Foreign End Products that will be allowed? Observations will be discussed in a meeting with Genera PR and Sargent & Lundy.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Communication was sent to the GWC (RG Engineering) project manager, Raul Berrios, requesting a document advance, despite the contract not having been signed yet. Eng Raul Berrios stated that the required documents have not been completed, and they will be delivered as they are completed in harmony with the contract requirements.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in the Weekly Construction Meeting for the Costa Sur BESS project. In this meeting, the main discussion subject was the rigging plan for the Tesla Batteries installations. There were also follow-up items, including the Safety Plan, Work Plan, Quality Plan, and Coordination between the awarded General Civil Contractor, RG Engineering, and the DCMC Construction Team. Representing RG Engineering was José Auli (RGE). It was also pointed out in the meeting that the need for the Surveyor to be on site to conduct an As-Built survey at the proposed location was necessary, as the General-PR Plant management staff had informed them of the presence of concrete piles under the proposed concrete platforms. Additionally, to identify existing utilities and the scope of work required for these utilities to be removed or relocated. The Sargent & Lundy personnel at the meeting, Wilson Alicea, informed the group of the recent site visit by the design team regarding the relocation of the existing utilities, and that the information would be shared later.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Certifications for operators of equipment such as forklifts, Digger Signal Person aerial platforms, and others are being reviewed. These were issued by the contractor RGE.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Conducted an in-depth review of the certification documents submitted by RGE for the Cambalache BESS project, focusing on compliance with OSHA 29 CFR 1910 and 1926 standards, as well as applicable Puerto Rico occupational safety regulations. Verified the validity and completeness, scope, and alignment with project-specific safety requirements. Added detailed notes to the documents, outlining certification acceptance criteria and identifying any gaps requiring corrective action. Cross-referenced the submitted materials against Genera PR safety protocols and contractor contractual obligations. Coordinated follow-up with RGE’s to ensure timely submission.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Created and coordinated procurement list and process to purchase assets and equipment to plan the Cambalache Inventory activity. Evaluated items to comply with budget and specification needed. Followed up with Ada Diaz (DCMC) to complete the purchase.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated and prepared a special drawing set to be used as a page turn meeting. Organized pages in order to obtain a quotation to print the documents. Reviewed design to decide what will be included in the discussion.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR -PREPA -Participated in meeting: Genera / LT Automation: Coordination with IT/OT Communication Building / Monopole and BESS with Mike Kuscynski (Sargent and Lundy), Gabriel Perez (CDM Smith) and Hector Vasquez (LT Automation) to coordinate PREPA communication project with BESS project.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Multiple project management activities. Prepared DCMC progress weekly report to document project status to Gilberto Sucre (DCMC). Cooridnated with Paul Browne and Jean Menay (DCMC) about upcoming planning of Inventory activities in Cambalache. Reviewed design drawings to start organizing observations to be presented to the project designer company (Sargent and Lundy). Evaluated demolition scope of work to identify if environmental studies are required.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Reviewed Procore project submittals to ensure there completion with corresponding responses. Met with Wilfredo Sierra (Sargent & Lundy) via phone to coordinate submittal RGE-0002.1 responses. Met with Jorge Mercado (DCMC) to discuss submittal RGE-00010 to discuss response for safety/rigging plan.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working email for Carirma Sanchez of Homeca to respond to submittal related to As-Built drawing that must revise and resubmit. Send email to Ricardo Sanchez of ARG regard of the location of the existing transformer MPT to be relocated temporary at VB parking area and include a layout drawing area where transformer will be installed. Cantan Asdrubal Morales of BETA to understand the scope of time for the relocation and repair of the MPT at Vega Baja. Working with review of ARG draft schedule for tomorrow provide comments related to the draft schedule.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting with Scheduler Sylvia Franco of DCMC to discuss the schedule draft send by Carlos Hernandez of ARG for the Vega Baja site - In meeting was discuss several finding in the schedule that is consider as a Macro schedule due it still does not have its processor attachment also was notice some activity that require de GC to make correction due to Electrical Grounding System Installation has 2 week but is schedule it has 18 weeks.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working in the review of structural drawing to identify posible change order notice that the are several drawings that does not match the drawing number from IFB to the IFC, this must be addressed to S&L to review why the drawing has changed from location drawing number this can create a confusion.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working in the review of structural drawing and finalizing the drawing comments table in excel. Reviewing the draft schedule for properness of schedule meeting with DCMC scheduler Sylvia Franco.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue the review of electrical drawing IFB versus IFC they were noted that on IFC are missing several drawings that was released as IFB during the RFP, also was observed that piping to Tesla equipment is several discrepancies in conduit size and quantity. This task drawing review I am working it with Jaime Pesquera of DCMC to review drawing and populate a excel table. In the instrument drawing they are several drawing missing for the IFC. Start reviewing the structural drawing to identify posible change orders. During the review was observed that S&L included several drawings with structural detail that may not apply to the project construction, all these drawing may not be used for construction and dont understand why was included in a IFB set if they will not apply.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a focused inventory recount at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC. This phase aimed to verify the accuracy of previous cycle count data, resolve discrepancies between physical stock and system records, and ensure transactional accuracy. The process included detailed validation of bin-level quantities, assessment of storage protocol compliance, and identification of any data variances affecting inventory integrity. Recount operations were executed across inventory areas CD 001 through CD 012.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed cycle count activities for inventory zones CD 001 through CD 012. This phase focused strictly on the physical counting and reconciliation of inventory to validate accuracy between on-hand quantities and system records. Task included verifying bin-level stock, confirming item master data, identifying labeling discrepancies, and documenting variances such as missing, mislocated, or misclassified items. All findings were recorded to support follow-up actions and ensure alignment with established inventory control standards.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted preparatory work for upcoming cycle count activities at the Palo Seco warehouse. In coordination with Mr. Giovanni Taffanelli from DCMC, efforts focused on organizing system aligned worksheets, validating item master data, and cross-referencing physical stock with system records. The objective was to ensure all necessary materials, resources, and procedural standards were in place to support an accurate and efficient cycle count process.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a strategic planning session with Giovanni Taffanelli, Hernan Machado and key warehouse personnel from DCMC to evaluate the status of inventory operations. The discussion centered on reviewing procedural inconsistencies, addressing workflow inefficiencies, and reinforcing adherence to established inventory control protocols. The team emphasized the need to strengthen accountability, align operational procedures, and maintain consistency throughout the cycle count process.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Palo Seco warehouse, work on the development of a detailed inventory performance report for Mr. Anthony Vega of Genera PR. The report compiled data from various warehouse zones and incorporated key metrics such as catalog ID reconciliation, unit-level stock verification, valuation reviews, and compliance with established stock thresholds. The objective was to evaluate operational performance, identify inefficiencies, and ensure reporting accuracy. Areas reviewed included CD 001 to CD 012, UB 001 to UB 031, AC 096 to AC 113, BA 007 to BA 012.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a targeted variance investigation to assess ongoing discrepancies between physical inventory counts and system reported data across storage areas CD 001 through CD 012. The effort focused on analyzing item catalog records, reviewing transaction logs, and tracing inventory movement chronologically to identify root causes of inconsistencies.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procurement Data gathering to publish RFP for the following components. Exhaust Duct Aguirre, and Boiler Feed Pumps Aguirre & Costa Sur. PW-9510 ¿FAASt¿A&E.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Procurement Data gathering to publish RFP for the following components. Hydrogen Coolers Palo Seco, Reduction Attempters Palo Seco, and Generator Breaker Cambalache.PW-9510 ¿FAASt¿A&E.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the submittals Submittal #: RGE-0010.1 RGE-0010 WORK PLAN FOR TRAILERS UNLOADING, Cambalache BESS - Parking demolition - lead study, and other emails. Cambalache BESS - Parking demolition - lead study
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- 4339_9510 BESS Review of the preliminary document was initiated, which includes the general planning structural drawing MASONRY DETAILS CAB00-AA-WHB-5000_02.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the 8._Appendix_D.3-_Demolition_Specifications (1) TECHNICAL SPECIFICATION FOR DISMANTLING AND DEMOLITION CAMBALACHE.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Attended a 1.5-hour Bluebeam software working session focused on advanced markup tools, plan set comparison features, and collaborative workflows. The session was tailored to the needs of the Cambalache BESS project (PW9510) and included hands-on practice in reviewing submittals, overlaying revised drawings, and annotating PDF plans to streamline coordination among project stakeholders.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed overviewing and analyzing documents for all existing dwg from IFB & IFC to identify any possible change orders for amendments to construction contract and the contractor's scope of work. Completed the review with Eduardo Rivera Jordan, DCMC.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Worked overviewing and analyzing documents for all existing dwg from IFB & IFC to identify any possible change orders for amendments to construction contract and the contractor's scope of work. We continued the documents review and expect to finish today with Eduardo Rivera Jordan, DCMC.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today i inspected the field to verify if there were new leaks on the concrete and changed oil pads and absorbent barriers. Discussed with Carlos Hernandez from ARG meeting for tomorrow and started preparation for the items to discussed. Continue working on items to discuss on fridays meeting with ARG including the documents required for safety such as fire protection program and mitigation.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CD001 to CD012 to begin the cycle counts.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations BA007 to BA012
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BA007 to BA012
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BA007 to BA012
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BA007 to BA012
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BA007 to BA012
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC 00 096 000 to AC 01 013 000.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC 00 096 000 to AC 01 013 000.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC 00 096 000 to AC 01 013 000.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations UB 001 to UB 035, LIST #1399/1400/1398
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations UB 001 to UB 035, RECOUNT LIST #1407/1409
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations UB 001 to UB035 at the Aguirre warehouse to initiate the cycle counts.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location UB 001 to UB 035
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CD001 to CD012.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1519 and 1520 from locations CD001 to CD012 for a total of 406 units.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CD001 to CD012 Cycle Count List # 1518.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review for upload and publishing the Costa Sur BESS IFC Drawing Plans; review drawings number, title, and correct multiple-sheet drawings numbering.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Yabucoa Peakers Procurement RFP & RFQs ensure documents are created, reviewed, distributed, stored & archived in an organized & controlled manner/Provide RGE access for additional personnel/Process all BESS projects incoming Check-in Project Tracker Reports
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Continuation of Yabucoa Peakers Procurement RFP & RFQs ensure documents are created, reviewed, distributed, stored & archived in an organized & controlled manner/Provide RGE personnel Procore access for several BESS projects completed/Provide Siemens Costa Sur Peakers additional team members
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Prepare SOP for the Forms and Correspondence tools at the Procore Platform.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Breakdown the Vega Baja drawings by discipline while looking to improve Procore upload of drawings process in terms of drawing numbering and naming automation.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the Procore Tracking and workshops are provided to project staff from owner, contractor and PMO; prepare spreadsheet to track and measure users progress and execution working and interacting with Procore.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Meeting with the Design Team represented by Mike Kuzcynski, Miguel Del Valle and Ivette Miranda (S&L), and also joined by Lauren Wells (Lemoine). Discussed the current methodology from S&L to review and respond Submittals to match their evaluations with Procore options for response.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR4339 Meeting via MS Teams with Luz Ramirez (DCMC) to explain the procedures for submitting expense and time reports. Clarification of deadlines and submission timelines for both expenses and time reports. Reports were submitted.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-¦ Work on drafting a document to be submitted on Friday, aimed at gathering essential information from the CDM Smith team specifically Carlos Palomares, Rafael Pabón, and Franklyn Colmenares. This task involved sending a detailed email outlining the requested data, specifying exactly which information was needed, and preparing a draft to guide their input and ensure timely delivery of the required content.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-¦ As part of the strategies to strengthen community relations in Vega Baja within the framework of the BESS Project, close collaboration took place with the Genera PR team, represented by Jorge Bracero, and with the team from the Municipality of Vega Baja, Gil Rivera, in planning our participation in the Vega Baja Summer Camp. The tasks carried out included coordinating the participation schedule, finalizing operational logistics, preparing a brief inventory of the necessary materials, and organizing a short internal rundown to ensure the smooth execution of the activities.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 139 | 417 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria- ¦Read, analyze, and develop a Canva white paper on natural gas, with the goal of creating clear and accessible communication pieces for the community. This work includes handling the existing draft, adjusting the content based on the most relevant information available, and crafting graphic materials (such as infographics or presentations) that highlight essential data about this fuel. The result will be a visual and educational tool that facilitates the understanding of the topic by the public for the community outreach.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-¦ As part of Genera PR’s community volunteer efforts in Toa Baja, a preparatory meeting was held to coordinate participation in an upcoming local event, strengthen ties with Levittown residents, and advance the objectives of the BESS Project through meaningful engagement. Participants included Adeline Pérez from Enactus PR, the team from Genera PR, and Jorge Bracero. The event schedule was reviewed and the volunteer roles were defined; in addition, an inventory of the necessary materials was conducted. The internal rundown was also finalized to support team coordination, and strategies were developed to engage community organizations and local leaders in order to encourage greater civic participation.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA Genera ¦ Deliverable 11- Project Management DR 4339 Hurricane Maria-¦ As part of the strategies to strengthen community relations and promote the development of the BESS Project in Arecibo, specifically in the Cambalache area, formal invitations were extended to key organizations. These nonprofit entities play a vital role in connecting with community leaders and encouraging more active citizen participation. To support these efforts, a series of emails were drafted and sent. This initiative aims to foster closer ties, align efforts, and create collaborative spaces that drive community engagement toward the success of the project.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review Lemoine Quality Control/Assurance Plan, Inspections plan, Progress Photographs, Punch List, Mock Up Inspections and Receiving Materials Inspection to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 134 | 402 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 31 pages were examined.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 40 pages were examined.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Sunem Martínez, Jose Lopez, and Luis Moctezuma (DCMC) to discuss project two week look ahead schedule, general civil contractor contract signage status, expected notice to proceed date and to improve communication across the site team.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur facilities -DCMC Site team lead by DCMC Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the systematic review of the Costa Sur BESS design drawings IFC (7/10/25) with a focused effort on refining the master list of missing items, incomplete details, and open technical comments. The process included cross-referencing drawing sheets to validate consistency, identifying annotation gaps, and confirming alignment between plan views, sections, and details. Emphasis was placed on ensuring critical construction information such as dimensions, elevations, connection points, and material specifications was clearly defined. The objective is to consolidate a robust and actionable comment list to facilitate efficient coordination with the design team once formally submitted.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements plan in schedule inspection considering the BESS project in construction timing phases in acceptable or not acceptable reports template in activities in site cut and fill excavations and formworks for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for BESS project considering construction inspection certificates in undergrounds installations, electrical works underground installations in project timeline, rigging in towering for batteries equipment on unit 1 and 2 in BESS equipment (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 134 | 201 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - DCMC Site in BESS project team lead by DCMC Carlos Rodriguez project meeting on deliverables for site that include location of subcontractor trailer, contract status and issue for constructions drawings of BESS battery project. Additional to this project meeting DCMC Costa Sur site team had the weekly meeting with RG Engineering, contractor for the BESS project lead by construction manager Jose Auli (RG Engineering employee), Rafael Barrera (DCMC employee) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 2) Review Lemoine Quality Control/Assurance Plan, Inspections plan, QCP Deficiency Log and Concealed Work Inspection to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Team meeting with CDM Smith team (Franklyn Colmenares, Manuely Concepcion) and Gilberto Sucre, DCMC to discuss program and project status and updates for "One Pager Weekly Report".
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Gilberto Sucre CDM Smith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares Genera: German Nunez
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. In-person meeting at City View Plaza with Gilberto Sucre, DCMC, to incorporate his feedback into the Procore Financial Flowchart.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 122 | 244 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Revising the ‘One-Pager Report’ for this week to incorporate detailed insights on site-specific activities, alongside a consolidated view of program and project progress.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue incorporating Gilberto Sucre, DCMC, comments into the Procore Financial Flowchart.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 122 | 366 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed and verified incoming correspondence and responded to emails concerning a Request for Information (RFI) Gilberto Sucre, DCMC requested my support. Drafted and distributed the Procore flowchart status report, including a comprehensive list of assigned reviewers. This documentation was submitted to Lauren Wells at Lemoine for reference and approval. Conducted follow-up communication with Gilberto Sucre, DCMC to address and resolve comments and feedback related to the Procore flowchart. Assisted Abraham Velázquez, DCMC in initiating access requests for the new vendor, SIEMENS, within the Procore platform, ensuring proper onboarding procedures were followed.
2025-07-17 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Borges, Raissa | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 7.3 | 7.3 | 7.3 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Tolls for site visit to Costa Sur BESS and Peakers project 10710 with DCMC team Abraham Velazquez, Carlos De Jesus and others and SIEMENS contractor representatives for reporting purposes.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 442 | 442 | 442 | Yes | 146796 | Portosan - Holding Tank Rental - Costa Sur
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Expense |  | 396.48 | 396.48 | 396.48 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Costa Sur BESS PW # 10710, drawing project printing copy
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Gilberto Sucre, Frances Vallejo, Lauren Wells, Ada Diaz, and Mike Merritt, DCMC. Discussed update on project, job offers, PROCORE, logistics, trailer set-up, safety, and schedule for locations.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal review of weeks notes, meeting minutes and reviewing emails for the Peaker projects
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in meeting Bess / peaker project status Discussed current status of procurement, RFP to contractors, and master schedule review participated in meeting. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710attende meeting on peakers project management meeting, Reviewed the weeks activities and open RFI or items to be answered Reviewed phases of construction for costa sure project. Attended meeting German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria E-mail correspondence review and response received during the day of BESS and Peakers' Programs.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS/Peakers Sites Status & Updates. DCMC - Site Managers presented their project status and Updates. Yabucoa - Gabriel Morales waiting contract agreement with RG Engineering and update of Procore launching for his project. Only RFP information is available. Gilberto Sucre & Abraham Velazquez to visit site next week. Cambalache - Andres Concepcion - NTP expected next two weeks, warehouse inventory starting on Monday, RGE submitted structural platform for S & L evaluation, page turn is schedule for next Tuesday, Quality & EHS submittal have been evaluated. Trailers and storage units to be delivered next week. IT/OT site inspection with S & L to be scheduled. Costa Sur - Rafael Barrera - IFC drawings page turn scheduled for Tuesday, main efforts is all underground site work and Emergency Generator Relocation. For Peakers there was a site visit with Siemens. Vega Baja - Eduardo Rivera - IFC drawings Rev. 2 issued, Contractor working on Premobilization activities, EHS alignment meeting ongoing. Schedule one to one meeting Tuesday morning with Carlos Hernandez ARG Ceres for SOW alignment and scheduled of values. Frances Vallejo, Raissa Borges and Gilberto Sucre DCMC participated.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Daily Update calls with: Jose Lopez - Aguirre requested to evaluate VE for Battery Megapacks foundations, CM employee starting on 8/04 and new location for IT/OT structures on site. Jean Pierre Menay - Discussed EHS alignment meeting with ARG Ceres for Vega Baja Installation Project. Rafael Barrera - Costa Sur to prepare for weekly update in substitution of Carlos Rodriguez who is on PTO. Eduardo Rivera - Vega Baja - IFC's Rev. 2 initial review. Andres Concepcion - IT/OT site visit for next week & Inventory status. All DCMC employees
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO - DCMC Financials SOP's led by Lauren Kennedy - Procore and Lauren Wells DCMC continued developing the Financial SOP's with D'Alexander Gonzalez, Rafael Calderon and Gilberto Sucre's Input all DCMC.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Team Catch Up Meeting Overview Urgent need to fill Peakers site manager position due to current project status. Carlos Dorta confirmed as ProCore specialist for Lauren's team, starting August 18th, enhancing project support. Candidates for other open positions were discussed including starting dates of new employees. P6 installation emails not yet received by IT/Lemoine; follow-up needed to ensure scheduler access. ProCore implementation on track with financial progress monitoring and a second weekly call scheduled. Internal planning document for Peakers project requested to align inspections, safety, and procurement efforts. All persons evaluated were DCMC employees expect Mike Frank candidate from outside the company. Attendees: Mike Merritt, Barry Scanlon, Ada Diaz, Lauren Wells, Anneilia Holton, Frances Vallejo, Foster Veazey & Gilberto Sucre - DCMC.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja IFC Rev. 1 continue drawings and "On hold" tracker review.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja IFC Rev. 1 partial drawings review.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Genera & Tesla Management Project Meeting led by Franklyn Colmenares CSA Group & Michael Grabstein - Tesla main items discussed: * Equipment Supply Contract. * Genera A&R Schedule Rev. 2 * Genera & Tesla Connect - Delivery Slip Impacts * Change Order Management * Payment Milestone # 3 * Transportation Management Plan * Long Term Service Agreement * NDR for RGE & ARG Ceres Other attendees: Tesla - Allin Luong, Lindsay Welton Sargent & Lundy - Mike Kuczynski DCMC - Rafael Calderon, Glorimel Torrado, Gilberto Sucre CDM Smith - Gabriel Perez
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Peakers Project Management Update meeting. Attendees were Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Carlos Palomares (CDM Smith), and Abraham Velazquez (DCMC)
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine)
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondence for Procore documents to all users for our SOP.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting to discuss Weekly Procore items with Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Ivette Rios (Sargent & Lundy), Luis Roman (DCMC).
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore quality check of Distribution Groups for each project within the program.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination of meetings for next week for Procore items.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore review of document structure.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on support issues for Procore users.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Rafael Calderon (DCMC), Glorimel Torrado (DCMC), Johanna Diaz (DCMC) to discuss Procore Financial SOPs.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) to discuss program staffing and overall program goals.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore workflow for budget changes.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financials.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 | 184 | 598 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Followed up with Hiram Medero from Genera PR regarding the previously requested report on purchase requisitions and material requests associated with federal accounts in the Asset Suite system. - Reviewed the completed report with Hiram Medero from Genera PR, which included historical data spanning from July 1, 2023, to July 17, 2025, ensuring it aligned with the original data specifications. - Communicated the status report of purchase requisitions and material requests associated with federal accounts to José Ralat, DCMC and Shellsea Maysonet , SMC, providing them with the finalized requested data.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting with France Vallejo about purchase process and status for materials in all trailers offices. Meeting with Carolyn Baez-Nieves (DCMC), working with the Expense Tracker to review Dueñas Trailers invoices #247782, #247858, #247859, #247959, #247960, #249075, #249076, #249077, #249470, #249469, #249542, #249543, #249542-A, #249543-A, #250150, #250177, #250258, and #249471; Villamil Group invoice D3235; and J. Arroyo Enterprise invoices #018 and #019. Verified trailer deployment site, invoice date, and billed amount for each entry. Cross-referenced data with site records and confirmed consistency with project documentation. Review the emails about Genera projects Topics, Battery Transportation, Fire Systems and logistics.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Coordinate with Portosan delivery the tanks to Costa Sur Genera project. Meeting with Maria Reyes (ARG contractors), Gilberto Soto (DCMC), Eduardo Rivera (DCMC) about Procore System, Date to start the project, Health and Safety forms, Security plans, Safety plans and workflow in the project. Meeting with Eduardo Rivera about Vega Baja Fire System submitted by Sargent & Lundy.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Sent meeting invites for execution meetings with BESS and Peaker project management teams.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review Procore Financial SOP flowchart for the PMO approval process.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Procore weekly call to discuss procore financials and SOPs status. Attendees: Lauren Wells (DCMC), Raissa Borges (DCMC) and Franklyn Colmenares (CSA).
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meet in person with Jean Menay (DCMC) to discuss pending purchases for the PMO. Also send email to Ada Diaz (DCMC) regarding the list of purchases for equipment and materials per site and locations.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Hurricane Maria - Attended Internal PMO Catch up call to discuss staffing update, RFP processes status for BESS and Peakers projects, Procore updates and advancements and leadership strategy regarding PMO, DCMC participants Gilberto Sucre, Mark Merritt, Lauren Wells and others.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended Teams call with site managers for Yabucoa, Aguirre, Vega Baja, Costa Sur and Cambalache to discuss site needs, procore status and project status with contractors. Attendees: Gilberto Sucre (DCMC) and other DCMC participants.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Gilberto Sucre (DCMC) to strategize on staffing, project needs and coordination with site managers.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Met with Jesús Cintrón (Genera) to discuss current Generation Fleet project needs and address pressing issues impacting progress. The discussion focused on identifying key priorities, evaluating ongoing challenges across the BESS and Peakers portfolios, and aligning next steps to maintain momentum across procurement, compliance, and construction activities. Action items were outlined to ensure timely resolution of outstanding matters and continued coordination with internal and external stakeholders.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Drafted the formal response letter addressing PREPA’s allocation of additional FAASt funds. Coordinated with José Ralat (DCMC) to verify the accuracy of financial figures and ensure consistency with prior submissions. Reviewed the draft with D'Alexzander González (DCMC) and Jesús Cintrón (Genera) to align the tone, structure, and messaging with Genera’s strategic and regulatory objectives. Incorporated their feedback to ensure the letter clearly communicates Genera’s position, maintains a collaborative tone, and supports continued progress toward securing the necessary funding.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Held a discussion with Jesús Cintrón (Genera) to review the draft HMGP Closeout Letter. Gathered his feedback and incorporated suggested edits and additional project-specific information to ensure the letter accurately reflects the status and rationale for closeout. Updated the narrative to strengthen alignment with FEMA closeout requirements and COR3 expectations. Ensured the final version presents a clear, comprehensive summary of project activities and remaining obligations to support a smooth and timely closeout process.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I prepared morning meeting with ARG and discussed with Carlos Hernandez and Maria Reyes from ARG regarding submittals and RFIs with missing documents, then proceed with safety meeting with Jean Menay from DCMC.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I read and reviewed the contractor’s responsibilities within the project. I also began researching safety standards to include in the contractor’s presentation for the BESS project, focusing on key topics such as: major workplace hazards, the definition of occupational health and safety, and the consequences of workplace accidents.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I reviewed and read several OSHA standards that align with the project's planned activities. The following were identified as relevant: - 29 CFR 1926 Subpart B – General Interpretations (1926.16) - 29 CFR 1926 Subpart C – General Health and Safety Provisions (1926.26) - 29 CFR 1926 Subpart D – Occupational and Environmental Health Controls (1926.51, 1926.52,1926.55,1926.59).
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsibilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Call with Carlos Bayron- QA/QC- (DCMC) at Costa Sur, to discuss the QA/QC plan submitted by the Contractor RG Engineering for the Costa Sur Project. The main subject of the call was to discuss the possibility of having a QA/QC plan completed by DCMC Partners to review and evaluate the applicable conditions for the Costa Sur Project. At this moment, a follow-up meeting should be held with Gilberto Sucre (DCMC) to verify the Document Status for evaluation. It was also agreed to perform a weekly meeting with all QA/QCs to discuss the need for the QA/QC plan.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Yabucoa BESS PROJECT. Meeting with Gabriel T. Morles, site Manager (DCMC) at the Yabucoa Bess project to review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy for the Yabucoa Job Site Included in the Specifications G-3400, review the Division of Responsibilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD), and the Owner Genera PR. Joint efforts with Gabriel T. Morales (DCMC) to identify mismatch information provided by Sargent & Lundy within the provided specifications, designed drawings for the installation phase, the Scope of Work description, and the Directive of Responsibilities from one to 249 line items.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Vega Baja ¦ DR4339 – Developed a simplified schedule structure to track and follow up on project activities for the Vega Baja site. The objective was to improve visibility of upcoming tasks and establish checkpoints for progress monitoring and team coordination.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 – Vega Baja ¦ DR4339 – Participated in an on-site walkthrough and coordination meeting at the Vega Baja project location with Eduardo Rivera (DCMC). Discussed upcoming construction activities, specific work areas, and site readiness to ensure alignment between scope, sequencing, and field conditions.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – Revised architectural warehouse building drawings to be sure all details are in place (site plan, ground floor, roof plan, building sections, walls, masonry details, exterior details. Number of sheets are 1 to 20.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 –I worked a breakdown for payment draft using unit prices from the construction auction to simplify the payment process, making it easier to navigate financial transactions.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Safety meeting. Discussed safety protocols, hazards, to become more aware of potential risks and learn how to mitigate them. This awareness can help prevent incidents before they occur. Attendees: Maria Colon (ARG) and from DCMC were Gilberto Soto, Eduardo Concepcion.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Conducted a focused review of civil and structural drawings for the Costa Sur BESS project to verify interface coordination between equipment foundations and slab layouts. Attention was placed on confirming anchor bolt positions, foundation elevations, and alignment with equipment footprints. Noted discrepancies were documented to be included in the master comment log. This verification ensures that structural elements are fully coordinated before construction begins and comply with safety and design intent.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the internal review of the Costa Sur BESS design drawings with a focus on identifying safety-related elements and verifying their adequacy. Particular attention was given to the location of emergency access routes, fire extinguishing systems, signage placement, ventilation clearances, and separation distances between battery enclosures. The review also evaluated if the drawings referenced applicable safety codes such as NFPA 855 and OSHA 1926. Comments were recorded where safety measures were unclear, missing, or not fully coordinated across disciplines. These observations will support the development of a compliant and risk-mitigated installation layout.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa A meeting was held with Gilberto Sucre, Frances Vallejo, Andres Concepcion, Carlos Rodriguez, Jose Lopez (DCMC), and other project team members to discuss key aspects of the ongoing project activities and Reporting from each site with the different Site Managers.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue Reading the themes of REMEDIES, TERMINATION FOR CONVENIENCE, TERMINATION FOR CAUSE and EQUAL EMPLOYMENT OPPORTUNITY from Attachment E: Federal Contracting Clauses.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting call with Harry Velazquez from RG Engineering to coordinate a site meeting in the Yabucoa Site for the BESS project coordination.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue Reading the themes of Compliance with HUD CDBG Labor Standards Requirements, CONTRACT WORK HOURS AND SAFETY STANDARDS ACT and RIGHTS TO INVENTIONS MADE UNDER A CONTRACT OR AGREEMENT from Attachment E: Federal Contracting Clauses.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Preparation for the upcoming meeting with the design team (S&L), a comprehensive review of the construction plans to identify potential deficiencies and ensure alignment with project requirements. The review process involved a detailed analysis of civil, structural, electrical drawings, as well as cross-referencing these documents with applicable codes, design specifications, and client expectations. Several discrepancies were identified during the review, including inconsistencies between structural elements with architectural features. The purpose of the upcoming meeting is to present these observations to the design team (S&L), seek clarification where necessary, and collaboratively develop solutions to resolve the identified issues. The goal is to ensure that all drawings are fully coordinated and construction-ready, minimizing the risk of delays or costly revisions during the build phase.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – BESS Costa Sur- Review drawing for BESS Civil Work Contract (CWC) - RFP. Review applicable QAQC regulations for the project, included designer proposal documents for prepared presentation about concrete specification in the project construction requested by DCMC site manager of Costa Sur facilities site.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre We working to Building Safety and Excellence – Crafting a Safety Plan for the Aguirre Power Plant Project As we embark on the construction project at the Aguirre Power Electrical Plant in Puerto Rico, we carry not only the responsibility to deliver technical excellence, but also a profound duty to protect every person who steps onto the site. This project presents complex challenges—electrical infrastructure, high-voltage systems, heavy equipment, and environmental sensitivities—and with them, the need for a robust, proactive, and integrated Safety Plan. This narrative outlines our commitment and approach toward establishing a living, working culture of safety and best practice throughout the project lifecycle. 1. Establishing the Foundation – Leadership Commitment and Planning Safety will begin not in the field, but in the planning room. We will convene a cross-functional Safety Planning Team that includes: Project managers Site engineers HSE (Health, Safety, Environment) coordinators Contractor representatives Local authorities and regulatory bodies (e.g., PREPA, OSHA Puerto Rico) Their first task: develop a site-specific Construction Safety Plan anchored in zero harm, regulatory compliance, and continuous improvement. This plan will outline: Roles and responsibilities Risk identification and control strategies Emergency response procedures Safety communication channels 2. Understanding the Risks – Site-Specific Hazards at Aguirre The Aguirre plant presents unique risk factors: Electrical Hazards: Working near or within energized systems (transmission lines, substations). Confined Spaces: Turbine rooms, underground ducts, and maintenance pits. High Temperatures and Humidity: Heat stress risk during summer months in Puerto Rico. Environmental Considerations: Coastal location with potential storm surge and flood risks. Heavy Equipment Operations: Cranes, hoists, excavators in tight operational areas. Our team will perform a Job Hazard Analysis (JHA) for each task category, followed by the development of tailored control measures (e.g., lockout/tagout protocols, PPE requirements, permit-to-work systems). 3. Workshop, Orientation, and Workforce Engagement Before any boots touch the ground, all personnel will undergo: Mandatory Safety Orientation: Site rules, emergency exits, hazard zones, first aid protocols. Task-Specific Workshop: Electrical safety (NFPA 70E), fall protection, confined space entry. Daily Toolbox Talks: Morning safety briefings focused on the day’s activities. Additionally, we will empower every worker through a "Stop Work Authority" policy—if they see something unsafe, they can intervene without fear of retaliation.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_aguirre Continue work to Building Safety and Excellence – Crafting a Safety Plan for the Aguirre Power Plant Project 4. Operational Controls and Best Practices Key controls we will implement: Permit-to-Work System: For high-risk activities like electrical isolation, hot work, confined space entry. Daily Site Inspections: Conducted by safety officers using standardized checklists. Access Control: Only trained, authorized personnel allowed in high-voltage or restricted areas. PPE Enforcement: Helmets, gloves, FR (flame-resistant) clothing, and arc-rated gear where required. We will adopt Lean Construction principles to minimize clutter, streamline workflows, and reduce unnecessary exposure to hazards. 5. Emergency Preparedness and Incident Response Given the critical nature of the site, we will prepare for: Electrical accidents and arc flash events Medical emergencies Fire and chemical spills Extreme weather (hurricanes, flooding) We will develop an Emergency Response Plan (ERP) in coordination with the plant’s existing protocols and local emergency services. Drills will be conducted monthly to ensure readiness. 6. Monitoring, Reporting, and Continuous Improvement To ensure the plan stays relevant: Weekly Safety Walks and Audits by supervisors and HSE staff. Real-time reporting using mobile apps for near misses, hazards, and incidents. Monthly Safety Review Meetings with data-driven performance tracking (e.g., TRIR, corrective action close-out rates). Lessons learned will be documented and applied to future phases. 7. A Culture of Safety: Beyond Compliance Our goal is not just to meet regulatory requirements—it’s to embed a mindset of care, awareness, and accountability. We will celebrate safety successes, recognize worker contributions, and maintain open communication with the local community to ensure transparency. By the time the last tool is packed away, we aim to have delivered not only a completed construction project—but a legacy of safety leadership at the Aguirre Power Plant.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Had a meeting via MS Teams with Carlos M. Paez (PCTM Construction) to discuss a potential civil work at the Aguirre Job Site. The contractor's entrance may require repairs to ensure the road is in acceptable condition for Tesla Delivery logistics and coordination. A site visit will be held today at the job site.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, Sunem Martínez, and Luis Moctezuma(DCMC) to discuss the project two two-week look-ahead schedule and improve communication across the site team.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Job Site Visit to the Aguirre Contractors entrance access road with Carlos M. Paez (PCTM Construction) to discuss a potential civil work scope of work and limits of the work that may be require to performed all the necessary repairs to ensure the road is in acceptable condition for Tesla Delivery logistics and coordination. A site visit will be held today at the job site. Physical measurements were taken of the areas that are in greater need of these potential repairs. Engineer Carlos M. Paez will send a budget proposal for this scope of work by the end of next week.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with all site managers from DCMC: Andres Concepcion, Gabriel T. Morales, Carlos Rodríguez, Eduardo Rivera, Gilberto Sucre, and Raissa Borges (DCMC). A very brief description of the project's main activities, risks, and project needs was discussed for each project. From the Aguirre BESS site, the main activities are the RG Engineering notice to proceed expected date, the Sargent and Lundy Issue For Constructions Drawings deliverables date, the contractor entrance roads existing conditions, and who will be responsible for the maintenance and initial improvements. It was discussed that the new Genera Plan, which aims to accommodate temporary power equipment near the BESS project, could potentially conflict with the storm sewer discharge line as designed by Sargent and Lundy. A meeting will be coordinated with the plan manager to confirm this information.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Developed detailed work plans for the safe and efficient movement of equipment and materials from the designated project area to temporary warehouse facilities. Activities included assessing current site conditions, identifying access routes, determining handling requirements based on equipment size and weight, and sequencing tasks to minimize operational disruptions. Coordinated with contractors to align relocation activities with site safety protocols, including traffic control measures, lifting equipment certifications, and environmental protection requirements. Documented the plan in alignment with Genera PR operational standards and FEMA DR4339 compliance guidelines, ensuring readiness for execution and proper resource allocation.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Continued development of work plans for the movement of equipment and materials from the designated project area to temporary warehouse facilities. Prepared detailed risk analysis forms for each stage of the relocation process, including hazard identification, mitigation measures, and emergency response protocols. Verified technical documentation for the equipment to be moved, ensuring all specifications, load capacities, and handling instructions matched project requirements and manufacturer guidelines.