2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Completed review and observations report to the TESLA transporting plan draft. Shared comments document to Gabriel Perez (CDM Smith)
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Gilberto Sucre and Raissa Borges, Frances Vallejo (DCMC Partners) to go over the BESS/Peaker Sites Status & Updates and recap the week project achievements and action items for next week.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Traveled to Office Depot and Art-Tek shop to coordinate blueprints and drawing printing. The documents are required for a design meeting on July 22, 2025.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Jean Menay, Paul Browne and Jorge Mercado (DCMC) to complete coordination and requirements to perform Cambalache Warehouse inventory tasks by July 21, 2025.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Followed up with the planning of Coordination of Cambalache Inventory to prepare action items agenda. Prepared and finalized project weekly report to be discussed with Site Managers (DCMC) team and Gilberto Sucre (DCMC Partners).
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meet at site with Jean Menay to discuss Fire Protection question that we have in regard of the fire protection design of Vega Baja we discuss several questions that will be sent to Gabriel Perez of DCMC related to fire system of the project. Also was reviewing the Civil drawing new set of IFC sent yesterday at 8PM by S&L.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Site visit with Carlos Hernandez and Ricardo Lopez of ARG/CERES to review site area for temporary transformer location and discuss some strategy for the second phase construction. In meeting site meeting was discuss the concern of the Fire Protection system recommendation of a 2000 GPM pump versus two 1000 GPM pumps, I mention to ARG that if a 2000 GPM pump is consider it must be two pumps not one of same capacity because one is an electrical pump, and the second should be a diesel pump. Also was discuss the need of submittal documents related to project work plan, quality plan, risk assessment plan, safety plan, schedule, breakdown for payment, etc. all documents are essential before they start to work. Also, Jean Menay and Gilberto Soto of DCMC was having a safety meeting with Javier Almodovar and Maria Reyes of DCMC to discuss all safety documents need for the project and discrepancy of documents that are not in Procore as sent by ARG/CERES.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Received at site Sylvia Franco of DCMC that will be our project scheduler we discuss her office area and start reviewing the need in regard of ARG/CERES timeline schedule, I requested Sylvia to provide a draft schedule with activity in a more detail. Also, in preparation of site visit of ARG/CERES at 9am.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Start reviewing IFC drawing set by S&L yesterday at 8PM with revision 1 reviewing electrical drawing set and preparing a single file with all drawing set that has revision 0 and revision 1 to create a folder for printing drawing at half size. Notice that on drawing VBB99-EG-BSS-0005 Rev 1 that there are no grounding pigtails to all medium voltage transformer MVT this should be grounded as per NEC.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led a morning safety briefing with Juan Vallejo, Hernan Machado, Milton Flores and Giovanni Taffanelli from DCMC. The session focused on reinforcing critical safety practices, including correct use of personal protective equipment (PPE), hazard identification within active storage areas, and proper material handling procedures. Personnel were instructed to keep walkways unobstructed, secure items appropriately, and promptly report any safety concerns. The briefing aimed to strengthen a safety-first culture while ensuring alignment with operational compliance standards.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-supported the preparation phase for the upcoming cycle count at Costa Sur warehouse by performing a thorough review of inventory data and creating system compatible count worksheets. In collaboration with Mr. Hernan Machado from DCMC, the effort emphasized procedural alignment and operational compliance. Preparatory tasks included verifying item master records, assembling necessary materials such as bin labels and count sheets, and strategically organizing resources to facilitate a streamlined and well-coordinated cycle count execution. Today scope of work is concentrated on locations zones AC 114 to AC 131.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-lead a variance analysis at the Costa Sur warehouse in collaboration with Mr. Hernan Machado from DCMC. The review targeted discrepancies between physical stock and system reported figures within storage zones AC 114 through AC 131. The investigation aimed to trace the root causes of bin-level variances, examine data entry workflows, and identify procedural gaps impacting inventory accuracy. All findings were thoroughly documented to support follow up actions and drive improved synchronization between physical counts and system data.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a meeting with Andres Concepcion, Jean Pierre, Jorge Mercado, and Luis Damudt from DCMC, to discuss safety matters related to the Cambalache project scheduled to begin nest Monday. The discussion emphasized the proper procedures for handling materials stored above six feet in height, particularly given that ladders available for use are only four feet tall. This meeting was conducted to ensure full alignment with both Genera's safety protocols and OSHA regulations.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Costa Sur warehouse, developed a detailed inventory performance report for Mr. Anthony Vega of Genera PR. The report compiled and analyzed inventory data from multiple zones, including AC 114 to AC 131, BI 001 to BI 035, BA 013 to BA 033, CD 013 to CD 024. The reporting effort centered on catalog ID validation, variance trend analysis, and alignment with inventory threshold standards. Key insights highlighted cost variances, physical inventory mismatches, and systemic process gaps supporting future transparency and data driven corrective actions.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out an inventory recount at the Costa Sur warehouse in collaboration with Mr. Hernan Machado from DCMC. The activity centered on the physical validation of item quantities, bin usage assessment, and verification of label accuracy. Emphasis was placed on detecting and resolving mismatches between actual stock and system reported data. The effort covered inventory zone AC 114 through AC 131.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a structured cycle count across inventory zones AC 114 through AC 131, emphasizing precise reconciliation between physical inventory and system records. The effort included validating count documentation, verifying item location, and reviewing unit-of-measure specifications to ensure data consistency. Additionally conducted bin check and confirm tag accuracy. A strong focus was placed on preserving audit trail integrity and ensuring all discrepancies were properly logged for corrective action. This cycle count contributed to broader initiatives aimed at improving inventory transparency and operational control at the Costa Sur warehouse.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Initiated an in-depth technical review of drawing CAB00-AA-WHB-5000_01 for the Cambalache BESS project (PW9510), which outlines structural planning for the gas storage building and adjacent warehouse.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- 4339_9510 BESS call with Andrés Concepción, DCMC. Discussion about the structural drawing on warehouse building to generate feedback on potential drawing issues for the designer.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails from Andres Concepcion, DCMC about the Cambalache warehouse inventory activities and call with Kevin Gonzalez from Genera PR to coordinate the Cambalache warehouse inventory activities.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- 4339_9510 BESS. Review of the preliminary document was initiated, which includes the general planning of the structure on warehouse building Drawings CAB00-AA-WHB-5002, CAB00-AA-WHB-6000.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents. Kept reviewing the package of revised drawings SNL-GENERA-15240-061-0020 – BESS - G-2700 GWC-that were sent yesterday to us by Sargent & Lundy to ensure an accurate record of design changes and avoid confusion from working with outdated information.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed Documents Overview and analyzing documents. Started reviewing package of revised drawings SNL-GENERA-15240-061-0020 – BESS - G-2700 GWC-that were sent yesterday to us by Sargent & Lundy to ensure that the most up-to-date drawings are used for the project and to provide traceability and maintain an accurate history of changes.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I prepared morning meeting with ARG and discussed with Carlos Hernandez from ARG and Maria Reyes safety regarding submitals and RFIs with missing documents, then proceed with safety meeting with Jean Menay. Did a walkthrough on the field with Carlos Hernandez and Ricardo Lopez from ARG and inspected the next phase parking area located on the municipality library verified areas that could be flood by heavy rains and how could we take measures for this topic.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CD013 to CD024 to begin the cycle counts.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BA013 to BA033
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BA013 to BA033
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BA013 to BA033
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations BA013 to BA033
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BA013 to BA033
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC 01 014 000 to AC 01 031 000
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC 01 014 000 to AC 01 031 000
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC 01 014 000 to AC 01 031 000
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations BI 001 to BI 035 at the Aguirre warehouse to initiate the cycle counts.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BI 001 to BI 035, LIST #131399/1400/1348
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location BI 001 to BI 035
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations BI 001 to bi 035, RECOUNT LIST #1407/1409
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CD013 to CD024.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CD013 to CD024 Cycle Count List # 1522 and 1531.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1529 and 1530 from locations CD013 to CD024 for a total of 168 units.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Vega Baja Drawings Plans to guide Sylvia Franco (DCMC) on how to allocate plans per discipline while working with drawings plans that references other drawings or documents.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/S&L Review of personnel permissions and removal of non active members
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Continuation of Yabucoa Peakers Procurement RFP & RFQs ensure documents are created, reviewed, distributed, stored & archived in an organized & controlled manner/RGE Cambalache BESS personnel changes/Siemens Costa Sur Peakers provide access to additional user/Vega Baja BESS download S&L Transmittal
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review Client's Requirement for the preparation of Change Orders for additional works that change contract's cost and time.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Completion of the Transmittal SOP to be published for users reference.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review contractual funding requirements for compliance referring to the Buy American Act that applies to the furnish of project's materials and equipment.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the potential implementation to prevent sharing of information between parties (different contractors) that are not related; critical compromising information such as design plans and specifications.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Weekly Meeting hosted by Franklyn Colmenares (CSA) and joined by Ivette Miranda (S&L), Rafael Pabon (CDM Smith) and Lauren Wells (Lemoine) to discuss the weekly procore open topics and new issues for discussion: specifications and submittal responses meetings update, financials tools and distribution groups organization.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Go over the Aguirre Project Management Tools with Sunem Martinez (DCMC) to review the project documentation and the type of documents that applies to the folders inside the Documents Tool.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 150 | 150 | 150 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Expense for Cambalache Issued For Construction drawings (131 pages) printing for the used of page turn meeting with project designer. Original Cost $131.00 Plus additional items (Red Pen and Binder Clips) for a total of $134.53 + Tax totaling $150.00 payment.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Meeting with Jean P. Menay (DCMC), working with the Expense Tracker to review Dueñas Trailers invoices #247782, #247858, #247859, #247959, #247960, #249075, #249076, #249077, #249470, #249469, #249542, #249543, #249542-A, #249543-A, #250150, #250177, #250258, and #249471; Villamil Group invoice D3235; and J. Arroyo Enterprise invoices #018 and #019. Verified trailer deployment site, invoice date, and billed amount for each entry. Cross-referenced data with site records and confirmed consistency with project documentation.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 ¦ Perform coordination work related to sending all invitations to community leaders for the community meeting. This task included writing an email and attaching the invitation for about twenty people to participate in the next community meeting on the BESS in Cambalache.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339¦ Meeting with the Genera PR team, Jorge Bracero, to coordinate 'workshop' to work on the 'updates' of Cambalache. This task included scheduling a date to coordinate the logistics of cross-checking information with the CDM Smith team.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 ¦ Coordinate report cross-checking with the CDM Smith team on the most recent updates related to the BESS project in Arecibo. The document was created so that they can provide the information and the team was provided with timely information on the information required to complete the information related to the project in order to communicate the latest information about the BESS project to the community.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339¦ Meeting with CDM Smith team, Manuely Concepción and Genera PR team, Jorge Bracero, in order to obtain the most important information about BESS and Peakers 'update' for the BESS/Peakers website ¦ Genera PR. These works included correcting the inversions of all the sites, creating the copies to publish them on the website and updating the necessary document.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339¦ Organize and set up the educational materials we will be taking to the camp in Vega Baja during the visit to expand our community outreach in that municipality.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 ¦ Update the related 2025 community calendar to include all new community activities that are being coordinated.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 134 | 402 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review Lemoine Quality Control/Assurance Plan, Inspections plan, Start Up Inspections of Equipment, Equipment in Place Inspection and Final Inspection and Acceptance to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 38 pages were examined.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 34 pages were examined.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur facilities - Continue Costa Sur BESS Drawing revision of designers company (S & L) Sargent and Lundy for RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site equipment mobilization, safety, look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Bayron Liboy, Carlos | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11 Project Management ¦ DR 4339 - Hurricane Maria – Costa Sur Facilities- Continue evaluation contractor QAQC manual (RG Engineering.) included Site Work requirements, work construction process and materials used on various areas of the project (QAQC Codes and Standards) include specific equipment used for construction and suggested preparing checklist forms to complete inspections for installing material and constructions process.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance report plan in schedule inspection considering the BESS project in construction specifications in activities in site cut and fill excavations, formworks, structures, electrical works, mechanical works, and commissioning time scheduling for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with draft plan schedule for BESS project considering construction in concrete structures, delivery dates of equipments, rigging of tower, inspection certificates in undergrounds installations, electrical works underground installations in project timeline on unit 1 and 2 in BESS equipment for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 3) Review Lemoine Quality Control/Assurance Plan, Inspections plan, Superintendent Daily Reports and Owner Furnished Equipment Matrix to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Inventory Coordination meeting with Andres Concepcion (DCMC) and Paul Browne (DCMC) for the 4339_9510 BESS_Cambalache project. Discussed inventory coordination and plan process to be completed.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Team meeting with Rafael Pabon from CDM Smith to discuss Peakers project status and updates for One Pager Weekly Report.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 122 | 183 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting to review site managers' updates for the BESS and Peakers projects. Attendees DCMC: Gilberto Sucre, Gabriel Morales, Andres Concepcion, and others. Sending notes gathered from meeting to the attendees.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 122 | 244 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewing the site managers' reporting sheet, sending reminders for our recurring meetings, and verifying that all BESS & Peakers project data and information have been accurately updated.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 122 | 488 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Synthesizing gathered BESS & Peakers project data to craft a clear and informative "One Pager" weekly report for consistent communication incorporating detailed insights on site-specific activities, alongside a consolidated view of program and project progress.
2025-07-18 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 41.51 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Traveled to Vega Baja P.R. from cll Hidalgo San Juan P.R. for meeting with Nelson Santiago (CDSMITH), Jaiem Pesquera (DCMC) and Maria Reyes (ARG contractor)
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 641.04 | 641.04 | 641.04 | Yes | 146796 | T-Mobile for Business. July charges for hotspots and cellphones for Genera Deliverable 11 project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial tool items.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Reviewed and responded to morning emails to stay updated on project developments and stakeholder communications. Organized the day's schedule, confirmed meeting agendas, and ensured all necessary materials and action items were prepared in advance.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 meeting focused on making sure individual project needs were met, and part of the discussion was around ensuring equipment was procured and delivered on time. Was there anything specific about the equipment or delivery schedules that was a challenge or stood out during the meeting. Attendees: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Completed Internal Review of Project Emails and Documents An internal review was conducted on all relevant project emails and documents to ensure consistency, accuracy, and alignment with project objectives. The review focused on communication clarity, documentation of key decisions, and compliance with internal standards. Findings were documented, and necessary follow-up actions have been identified and assigned.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in a strategic project planning session with Jesús Cintrón (Genera), Carlos Palomares, Rafael Pabón (CDM Smith), Sheila Torres-Sterling, Abraham Velázquez, Gilberto Sucre, and D'Alexzander González (DCMC) to address critical path issues related to the Generation Fleet Peakers project. The primary focus of the session was to evaluate the pros & cons of a potential transition in procurement methodology, from the conventional design-bid-build (DBB) model to a design-build (DB) delivery method. This shift is under consideration due to ongoing delays and coordination challenges that have severely impacted project timelines and budget execution under the current structure. As part of this assessment, the team weighed the regulatory, financial, and scheduling implications of such a change, considering how a DB model could potentially streamline delivery and reduce administrative burdens while still maintaining FEMA PA compliance. The discussion also included a candid review of current performance, particularly with regard to ongoing delays across multiple projects. Given the persistent bottlenecks, the group explored contingency planning options, including the feasibility and ramifications of replacing the current engineering contractor to protect schedule integrity and funding timelines. Attended meeting: Gilberto Sucre DCMC Sheila Torres-Sterling DCMC Jesus. Cintron Genera D'Alexzander Gonzalez – DCMC Rafael Pabon, CDM Smith Carlos Palomares CDM Smith.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 225 | 900 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in a strategic project planning session with Jesús Cintrón (Genera), Carlos Palomares, Rafael Pabón (CDM Smith), Sheila Torres-Sterling, Abraham Velázquez, Gilberto Sucre, and D'Alexzander González (DCMC) to address critical path issues related to the Generation Fleet Peakers project. The primary focus of the session was to evaluate the pros & cons of a potential transition in procurement methodology, from the conventional design-bid-build (DBB) model to a design-build (DB) delivery method. This shift is under consideration due to ongoing delays and coordination challenges that have severely impacted project timelines and budget execution under the current structure. As part of this assessment, the team weighed the regulatory, financial, and scheduling implications of such a change, considering how a DB model could potentially streamline delivery and reduce administrative burdens while still maintaining FEMA PA compliance. The discussion also included a candid review of current performance, particularly with regard to ongoing delays across multiple projects. Given the persistent bottlenecks, the group explored contingency planning options, including the feasibility and ramifications of replacing the current engineering contractor to protect schedule integrity and funding timelines. Outputs from this meeting directly inform procurement realignment decisions, upcoming funding requests, and broader coordination across project formulation, design, and execution. After the meeting prepared along Carlos Palomares CDM Smith an agenda for a Design Status Presentation to be requested from Sargent & Lundy. Met also with Francisco Feliu - Genera- to discuss the need to identify and recommend a Design Built contract to be used.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore - DCMC Financials SOP's Led by Lauren Kennedy - Procore & Lauren Wells - DCMC reviewed the process workflows for Change Orders and Commitment Model for the approval and endorsement of D'Alexzander Gonzalez - DCMC Finance. Esther Rohena and Gilberto Sucre - DCMC also participated.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM weekly update meeting with Gabriel Perez - CDM Smith & Franklyn Colmenares- CSA Group discussed project updates and main needs from Genera to moving forward with the Projects. * Homeca - Contractual Resolution * Vega Baja drainage repair, MTP relocation & Oil Separator collection. * Release for to FOMB Approval Vega Baja, Aguirre & Costa Sur * Cambalache - Genera Inventory Support & Cleanup Areas. * TRC SME Support * Sargent & Lundy combined monitoring. * Timely approvals & decision making.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria One to one meeting with Mike Kuczynski - Sargent & Lundy to discuss the upcoming IFC's page turn reviews for Cambalache, Costa Sur and Vega Baja. Pointed out the critically to get the required information to get rid of all the holds on the drawings.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 225 | 281.25 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Morning call with all DCMC Site Managers to exchange Project and Program updates with Jose Lopez - Aguirre, Rafael Barrera - Costa Sur, Gabriel Morales - Yabucoa, Eduardo Rivera - Vega Baja and Andres Concepcion - Cambalache. Highlight for the week is the IFC's Drawing Turn over Vega Baja, Cambalache & Costa Sur.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peaker's Project Needs meeting with Jesus Cintron - Genera. German Nunez - Genera & Rafael Pabon - CDM Smith presented Peaker's Needs, while Gabriel Perez - CDM Smith & Franklin Colmenares presented BESS needs mainly related to Vega Baja and Cambalache.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Ricardo Pallens (Genera), Carlos Palomares (CDM Smith), Joaquin Quinoy (Genera), Gabriel Perez (CDM Smith), Mike Kuczynski, Nelson Rosado (Sargent and Lundy), Franklyn Colmenares (CDM Smith), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Follow up meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (DCMC).
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permission templates to make adjustments for CDM Smith for Meetings.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Rafael Calderon (DCMC), Glorimel Torrado (DCMC), Johanna Diaz (DCMC), Gilberto Sucre (DCMC), Esther Rhonea (DCMC), Jose Ralat (DCMC), D'Alexzander Gonzalex (DCMC) to discuss Procore Financial SOPs.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore distribution list organization.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) and Luis Roman (DCMC) for Procore weekly check-in to discuss open items as a team.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore financial tool items.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore tasks updates in Teams for tracking purposes.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating distribution lists for BESS projects with adjustments from users.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore distribution list organization.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for meeting template for CDM Smith users.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on more Procore correspondences for answering questions and review of documents for Procurement.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 186.77 | 186.77 | 186.77 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - PW 10710 - Sent to print at Professional Printing & Office Supplies a set of 67 IFC drawing for a total of $186.77 for Vega Baja BESS project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Participated in a meeting with Eisha Mercader from DCMC and Carlos Gonzalez, Jorge Aponte, and Keyla Sierra from Integrum to review the current and pending features of the Genera Connect Timesheet's platform. The discussion focused on re-scoping future development efforts, with particular emphasis on enhancing reporting capabilities to better support federally funded project requirements.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Travel from home office to City View Plaza. Picked up Personal Protection Equipment to deliver it to Vega Baja and Cambalache Genera Sites to ensure compliance with health and safety requirements.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Delivery of Personal Protection Equipment to Costa Sur Genera Site Offices. Meeting with Rafael Barrera and Luis Echevarria (DCMC) about the logistics and Health and Safety topics in this project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Delivery of Personal Protection Equipment to Yabucoa Genera Site. Meeting with Jose Lopez and Gabriel Morales (DCMC) about Yabucoa and Aguirre Genera projects. Review the Yabucoa site and inspections.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 184 | 322 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Conference call with Andres Concepcion (DCMC) about RGE activity in Cambalache Genera Site tomorrow. Conference call with Osvaldo de Jesus (GENERA) about vulnerability plans and RGE tasks in Cambalache Genera Site. Topics in both conference call Health and Safety and Emergency Management.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Read and draft correspondance regarding wifi quotes and change from T Mobile to another company.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Attended meeting in person with Jesus Cintron (Genera PR) to discuss Peaker transition meeting with S&L.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review resume for Mariano Perez, for site manager at Jobos site.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Grant Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for grant management activities | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Toa Baja community engagement summer camp to introduce Genaro, the character that Genera created to explain BESS and Peaker project to communities. Attendees: Paola Arroyo (DCMC) and Jorge Bracero (Genera PR).
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting in person with Abraham Velazquez (DCMC) to discuss Peaker project outline. Discussed project's goals, scope, resources, and timeline for clarity and direction to achieve project objectives.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in a strategic project planning session with Jesús Cintrón (Genera), Carlos Palomares, Rafael Pabón (CDM Smith), Abraham Velázquez, Gilberto Sucre, and D'Alexzander González (DCMC) to address critical path issues related to the Generation Fleet Peakers project. The primary focus of the session was to evaluate the pros & cons of a potential transition in procurement methodology, from the conventional design-bid-build (DBB) model to a design-build (DB) delivery method. This shift is under consideration due to ongoing delays and coordination challenges that have severely impacted project timelines and budget execution under the current structure. As part of this assessment, the team weighed the regulatory, financial, and scheduling implications of such a change, considering how a DB model could potentially streamline delivery and reduce administrative burdens while still maintaining FEMA PA compliance. The discussion also included a candid review of current performance, particularly with regard to ongoing delays across multiple projects. Given the persistent bottlenecks, the group explored contingency planning options, including the feasibility and ramifications of replacing the current engineering contractor to protect schedule integrity and funding timelines. Outputs from this meeting directly inform procurement realignment decisions, upcoming funding requests, and broader coordination across project formulation, design, and execution.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Initiated development of the requisition package for the procurement of demolition services at the Jobos site, which is part of the Generation Fleet infrastructure improvement initiative. Identified the need for the ICE to support the procurement and reimbursement process, in accordance with federal procurement standards and FEMA PA guidelines. Coordinated with the CDM Smith team to request the ICE, emphasizing its critical role in establishing cost reasonableness, supporting contract negotiation, and ensuring compliance with 2 CFR § 200.323. Issued a follow-up reminder to underscore the importance of receiving the ICE promptly to avoid delays in requisition processing and project implementation.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí. DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. DCMC Subcontractors: SM Consulting Shellsea Maysonet and, Johanna Díaz, HONRA Marc Maceira and Integrum Carlos González and Ginnell Torres.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Verified the status of key workstreams and high-priority items related to procurement activities and contract submittals requiring approval from FOMB and P3A. This review was conducted in preparation for the weekly BESS and Peakers Project Needs meeting, ensuring up-to-date information was available to support informed decision-making and effective project coordination.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the weekly BESS and Peakers Project Needs meeting with Genera Jesús Cintrón. Reviewed the current status of key workstreams and discussed high-priority items requiring coordination or follow-up. Contributed updates and aligned on next steps to ensure continued progress across both projects. Genera: Jesús Cintrón, Germán Nuñez. DCMC: Abraham Velazquez & Gilberto Sucre. CDM Smith: Franklyn Colmenares Gabriel Sepulveda, Carlos Palomares & Rafael Pabón.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued developing the requisition package for the procurement of demolition services at the Jobos site. As part of this process, drafted a summary of the SOW to be included in the Requisition Justification Memo, ensuring it accurately captured the key technical and operational elements of the project. Shared the draft summary with Abraham Velázquez (DCMC) for verification and technical alignment prior to finalizing the memo.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued development of the requisition package for the procurement of demolition services at the Jobos site. As part of this process, conducted a thorough review of the SOW to verify that all technical and operational requirements were clearly defined, aligned with project objectives, and consistent with approved project descriptions and eligible scope.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.25 | 184 | 598 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Updated the Genera Connect Financial Tracker with the most recent financial data to support preparation efforts for the weekly Genera PR client meeting. Engaged in a discussion with Eisha Mercader from DCMC to address proposed reporting modifications for the Genera Connect Timesheets module. Participated in the weekly client meeting to deliver project updates, with attendees including María Sanchez, Alejandro Maymi, and Jesus Cintron from Genera PR; D'Alexzander Gonzalez, José Ralat, Eisha Mercader, Sheila Torres, and Esther Rohena; Shellsea Maysonet from SMC; and Carlos Gonzalez from Integrum. Additionally, coordinated a follow-up meeting with Eisha Mercader (DCMC), Keyla Sierra (Integrum), and Carlos Gonzalez (Integrum) to define and plan required enhancements to the Genera Connect platform’s reporting functionalities.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety and welfare measures, ensuring that all aspects of safety are being met. Provided proper supervision to create a safer work environment and minimize the risk of accidents. Continued working on a PowerPoint to discuss safety pointers and emergency exits with ARG CERES safety team for Vega Baja BESS phase two project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, Performance evaluation discussion with Gabriel Morales (DCMC).
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I continued reviewing the SOPs in Procore, such as the Procore SOP's: Submittals Tool'. I also, a read a safety topic related to the effects of heat and the corresponding recommendations for construction projects.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, Gabriel Morales (DCMC) and I (Luz Ramirez -DCMC) supervise the electrical work performed by Eric Calo from Duenas Trailers to repair the main electrical power surge protector in the DCMC Office (wagon) at Yabucoa site.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, review the scope of responsibilities of the contractor within the BESS project, including aspects such as: - SWPP Plan - Construction - Temporary building - Project and interface Schedules - Project Control, Resources Management, Reporting - Project labor agreement. In Addition, I read the SOPs in Procore, such as: Procore Documents tool, Procore SOP’s: RFI Tool (Internal Users), Step by Step: Uploading Drawings, Procore SOP’s: Emails Tool, Procore SOP’s: Incidents Tool, Step by Step: Creating an Observation, and Procore SOP’s: Photos Tool
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Vicent Skochdopole, Wilfredo Sierra, Chris Niersbach, Mindy Madry, Robert Molner, and Camillus Pawlica from Sargent & Lundry; Eduardo Rivera, Andres Concepcion, Jose Lopez, Rafael Barrera from DCMC Partners; Gilbert Fireflies, Feroz Qais, Javiya Keyur, Joseph Muniz and Lim Howen from Tesla; and Franklyn Colmenares from CSA Group; Gabriel Perez from CDM Smith. The meeting focused on reviewing the technical aspects of the 3D model, aligning design intent with project requirements, and addressing stakeholder feedback to support project coordination and execution.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Meeting (BESS Project) with the contractor RG Engineering (Harry Velázquez, José Segarra, and Raúl Berrios); Jose Lopez, Gabriel Morales and Luz Ramirez from DCMC Partners to evaluate the actual conditions of the project and planification items for the civil work for the BESS project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/ Bluebeam for Estimators/ Successfully navigate the interface Locate and place commonly utilized markups. Save customized markups in the Tool Chest. Set the scale of a drawing. Take length, area, and count measurements. Overlay drawings to find differences. Arrange and sort pages using the Thumbnails Panel. Utilize the Markups List to create estimate sums.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Create Batch Links on multi-page documents/ Create a form using the Auto-create function/ Create a Studio Project/ Upload and share files from a Project/ Create custom Columns in the Markups List/Successfully navigate the interface/ Locate and place commonly utilized markups/ Save customized markups in the Tool Chest/ Organize pages using the Thumbnails Panel/ Take length, area, and count measurements/ Utilize the Markups List to filter, sort, and export markups data/ Create Page Labels/ Insert replacement pages using Batch Slip Sheet/ Set the scale of a drawing /Take basic measurements using the length, polylength, and area measurement tools/ Organize pages using the Thumbnails Panel/ Use the Overlay Pages feature to compare different PDFs/ Use the Compare Documents feature to compare different PDFs
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Bluebeam Architects/ Successfully navigate the interface/ Locate and place commonly utilized markups/ Save customized markups in the Tool Chest/ Set the scale of a drawing/ Take length, area, and count measurements/ Utilize the Markups List to filter, sort, and export markups data.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Bluebeam for Engineers/ Successfully navigate the interface. Locate and place commonly utilized markups. Save customized markups in the Tool Chest. Set the scale of a drawing. Take length, area, and count measurements. Overlay drawings to find differences. Arrange and sort pages using the Thumbnails Panel. Add slip sheets in a batch. Utilize the Markups List to filter, sort, and export markups data.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Successfully navigate the interface/ Locate and place commonly utilized markups/ Save customized markups in the Tool Chest/ Create a PDF form
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the review of the Costa Sur BESS IFC drawings by cross-referencing the Sargent & Lundy Document Transmittal List against the physical drawing set and the technical comments previously provided by the PM Gilberto Sucre (DCMC). The objective was to verify that all intended drawing packages were received, ensure proper version control, and confirm that comments already issued were addressed or reflected in the most current IFC versions. Any discrepancies in sheet numbering, missing packages, or unincorporated feedback were flagged for clarification. This task supports quality control efforts and helps maintain traceability of design revisions prior to construction execution.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the detailed review of the Costa Sur BESS IFC drawings dated 7/10/25, with the objective of refining and organizing the master list of missing items, incomplete details, and unresolved technical comments. The session focused on validating drawing consistency across disciplines particularly civil, structural, and electrical plans by cross-checking layout references, verifying section callouts, and confirming alignment of critical construction data. Special attention was placed on identifying missing dimensions, elevation markers, incomplete equipment labels, and unclear construction notes. Observations were categorized by priority and trade to facilitate streamlined coordination during the upcoming review cycle with the design team.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued with the verification of IFC drawing packages for the Costa Sur BESS project by further cross-referencing the Sargent & Lundy Document Transmittal List with the physical plan set and the existing log of PM-issued comments. Focused on identifying inconsistencies in sheet naming conventions, revision tags, and the presence of updated details in response to prior technical observations. Additional emphasis was placed on confirming that critical safety-related notes, such as emergency access routes and clearance zones, were properly integrated. Observations were logged for internal coordination prior to compiling the final tracking matrix.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the Attachment D.1, Appendix 1, Design Drawings to clarify doubts that arose from the Site Meeting with Jose Segarra, Harry Velazquez and Raul Berrios from RG Engineering; and Jose Lopez and Luz Ramirez from DCMC Partners.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue Reading and evaluating Attachment E: Federal Contracting Clauses that consists of 105 pages.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Teams meeting with Vincent Skochdopole, Wilfredo Sierra, Mindy Madry, Chris Niersbach, Camillus Pawlica, Robert Molner from Sargent & Lundy; Javiya Keyur, Gilbert Fireflies, Feroz Qais, Joseph Muniz and Lin Howen from TESLA; Eduardo Rivera, Jose Lopez, Andres Concepcion, Rafael Barrera from DCMC Partners; Gabriel Perez from CDM Smith and Franklyn Colmenares from CSA Group to discuss and review the BESS Project 3D model proposed by Sargent & Lundy for the Cambalache site.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Supervise with Luz Ramirez (DCMC) the electrical work performed by Eric Calo from Duenas Trailers to repair the main electrical power surge protector in the DCMC Partners Mobile Office at the Yabucoa site.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Meeting with Jose Segarra, Harry Velazquez and Raul Berrios from RG Engineering; Jose Lopez and Luz Ramirez from DCMC Partners to evaluate the actual conditions of the project area and key planification items of the civil work for the BESS project in the Yabucoa Site.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the review of the Costa Sur BESS IFC drawings by cross-referencing the Sargent & Lundy Document Transmittal List against the physical drawing set and the technical comments previously provided. The objective was to verify that all intended drawing packages were received, ensure proper version control, and confirm that comments already issued were addressed or reflected in the most current IFC versions.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur-Verifying discrepancies in sheet numbering, missing packages, or unincorporated feedback were flagged for clarification. This task supports quality control efforts and helps maintain traceability of design revisions prior to construction execution.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the detailed review of the Costa Sur BESS IFC drawings dated 7/10/25, with the objective of refining and organizing the master list of missing items, incomplete details, and unresolved technical comments and prepare document to designer meeting that will be held tomorrow at designer (Sargent & Lundy) office.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued focused on validating drawing consistency across disciplines particularly civil, structural, and electrical plans by cross-checking layout references, verifying section callouts, and confirming alignment of critical construction data. Special attention was placed on identifying missing dimensions, elevation markers, incomplete equipment labels, and unclear construction notes. Observations were categorized by priority and trade to facilitate streamlined coordination during the upcoming review cycle with the design team.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre 3. Pre-Operation Requirements Before any crane activity begins at the Aguirre Power Plant, the following must be completed: Job Hazard Analysis (JHA): Conducted for each lift to identify and mitigate risks. Lift Plan: Required for critical, non-routine, or heavy lifts. Must be reviewed and signed off by the safety officer and a qualified engineer. Crane Inspection: Daily and periodic inspections must be documented in accordance with ASME and OSHA guidelines. Permit to Work (PTW): Issued by plant operations, including lockout/tagout if necessary near energized equipment. Weather Considerations: Operations must be suspended under high wind or inclement weather conditions per crane specifications.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre , Reading and reviewing: Site Safety Controls, Barricading and Signage, Spotter and Signal Person, Load Path Planning, Communication Protocol Emergency Response Plan, Environmental Considerations, Avoid Fuel and Oil Spills, Limit Ground Impact, Air Quality Control. Documentation and Reporting All crane operations must be supported by: Daily inspection checklists, Lift plans and JHA reports, Operator certifications, PTW forms and safety briefings, and Incident or near-miss reports (if applicable).
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre We are working on the Critical Lift Definition and Requirements: An 84,000-lb lift qualifies as a Critical Lift under most industrial standards, based on the following: Load exceeds 75% of crane's rated capacity at planned configuration. Load is irreplaceable or involves high risk to plant operations. Lift is performed over critical infrastructure. Additional Planning Requirements: Lift Plan Engineer Review, Pre-lift Meeting, Redundant Rigging Systems, Taglines and Spotters. Engineering and Load Calculations For an 84,000-lb load, the following must be addressed: Load Weight Confirmation: Including lifting gear, rigging, and any attachments. Crane Configuration: Verified against manufacturer’s load chart at specified boom angle and radius. Ground Bearing Pressure Analysis: Soil or slab must support outrigger loads. Swing Radius Clearance: Maintain clearance from energized equipment and plant structures.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reading and reviewing the Crane Operation Standards – Aguirre Power Plant, Puerto Rico to prepare a safety plan and coordination for the installation at the Bess. For this we considerate the next types: 1. Introduction The use of cranes at the Aguirre Power Plant in Salinas, Puerto Rico, is governed by strict safety, regulatory, and operational standards. These standards ensure that lifting operations are conducted safely and efficiently while minimizing risks to personnel, infrastructure, and the environment. 2. Applicable Standards and Regulations Crane operations at the Aguirre Power Plant must comply with the following: OSHA Regulations (29 CFR 1926 Subpart CC), ANSI/ASME B30 Series, Puerto Rico OSHA (PROSHA) – Local occupational safety enforcement aligned with federal OSHA. NERC/FERC Reliability Standards – To ensure lifting activities do not impact grid reliability. PREPA Safety Guidelines – Internal policies by the Puerto Rico Electric Power Authority and Manufacturer's Recommendations.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria We continue reading and review the Crane Operation Standards – Aguirre Power Plant, Puerto Rico to prepare a safety plan and coordination for the installation at the BESS. For this we considerate the next types: 4. Operator Qualifications Crane operators must meet the following criteria: NCCCO Certification (or equivalent): For mobile and tower crane operation. Plant-Specific Workshop: Orientation and safety workshop for the Aguirre facility. Medical Clearance: Operators must be physically fit as per OSHA standards. Experience Requirements: Minimum years of experience depending on crane type and load rating.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting with Sargent and Lundy designers, Alling Loung, Howen Lin, Joseph Muñíz, Wilfredo Sierra and the TESLA Team, Keyur Javiya and Madry Mindy, to go over the 3D Design Drawings at the Cambalache BESS Site Design. Also attending to the meeting Gabriel Pérez (CDM Smith), Gilberto Sucre, and Andres Concepción (DCMC). On the Teams were Mike Kuczynski, Robert Molner of Sargent and Lundy. The meeting was to review in details location of the mega packs, spacing available around the mega packs for the mega dolly operation and variations in the structural design.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS- Morning meeting with Carlos López, Sunem Martínez, and Luis Moctezuma (DCMC) to discuss project two-week look-ahead schedule and improve communication across the site team.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Gilberto Sucre and Jean-Pierre Menay (DCMC) to discuss the office trailer contractor's punch list items and pending office supplies. Follow up on the electrical contractor's payment status for the office trailer electrical power connection.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified RFP No. 4900 Civil & Structural Works for 158 MW Battery Energy Storage System at Aguirre, issued by the Puerto Rico Electric Power Authority- Review of the "Buy American Act" (BAA). According to the Buy American Act (BAA), it has been defined in RFP No. 4900 for the Civil & Structural Works for the 158 MW BESS System at Aguirre, in section 6.4.1.16. Nonetheless, I don't see the Exhibits as part of the RFP documentation. The Owner needs to clarify which definition will be applied, and whoever is evaluating the contracts should have a clear definition of this subject. The definition requires the proponent to declare the percentage of FEP material to be used. What percentage of Foreign End Products (FEP) will be allowed? Genera PR needs to keep in mind that the material market is volatile these days, with the USA's economic war against the World. Even though this is a federal funding program, what will be the general guidelines for this definition of BAA? These observations will be discussed in a meeting with Genera PR and Sargent & Lundy.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Yabucoa BESS project. Job site visit with José Segarra, Raul Berrios Harry Velazquez from RG Engineering, and Gabriel T. Morales, and Luz Ramírez from the Yabucoa DCMC. Base on the site walkthrough there was any major observations in general. Regarding to the existing concrete retaining wall José Segarra will submit an RFI to Sargent and Lundy to clarify the intentions with the existing concrete retaining walk and the proposed design.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - The coordination meeting is attended in person at the Cambalache site conference room together with Luis Damudt (DCMC), Luis Duque (DCMC), and Herminio Arroyo (GENERA), where the logistics for the movement of materials to the temporary storage container area are discussed.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache site- Work continues on supervising the work in the warehouse area where materials are moved and the inventory of available parts is made to ensure that the right resources are present and materials and equipment are available when needed,
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Assistance at the Cambalache site where work was carried out to coordinate daily permits for the movement of materials and inventory of the existing warehouse to ensure a steady supply of materials and equipment needed for the project and ensure project stay on track, preventing delays and cost overruns.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Work arrangements are made for the following day regarding the handover of the temporary offices of the contractor RGE. These arrangements are made with the work team for the Cambalache site. Attendees: Andres Concepcion (DCMC), Luis Duque (DCMC), and Luis Damudt (DCMC)
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Meeting on site with Carlos Oquendo (Sphera Group) to discuss inspection process in the project. Scope of work and site conditions were evaluated to start coordinating an inspection plan.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Coordinated general contractor (RG Engineering) access to site for two deliveries On July 22 and July 23, 2025). Phone call with Jose Segarra (RG Engineering) and Jean Menay (DCMC) to review requirements. Phone call with Paul Browne (DCMC) to discuss inventory work summary of the day and review pending actions for next upcoming activities.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Paul Browne (DCMC) on site to evaluate and coordinate the warehouse inventory logistics in order to prepare for warehouse relocation activities.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Virtual meeting with Sargent and Lundy's (Mike Kuczynski, Vincent Skochpodole) and TESLA's (Howen Lin) to discuss design coordination items within infrastructure and TESLA batteries.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Worked on Design Drawings Markup on printed blueprints. Went through 131 pages of blueprints to identify observations and pending information that will be requested to Designer in a meeting on July 22, 2025.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with reviewing IFB and IFC drawing. Carirma Sanchez of Homeca will send tomorrow personnel of Javier Bidot Associate for completing the underground survey as built of Vega Baja site. Gilberto Sucre of DCMC sent invitation for today for Tesla drawing review at 3PM on 7/24/25. Gilberto Sucre of DCMC call this morning to verify if Genera sent a vacuum truck to clean the oil separate dike, I mention that no work was completed. The IFC Drawing was completed its printing and was picked at printing shop.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working in the review of the electrical drawing IFC Rev 1 and compare with the IFC Rev 0, notice that some new drawing was add during this IFC release by 7/17/25. Preparing for Tesla 3D Review meeting at 3PM.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - BESS Genera Meeting to discuss BESS 3D model review, Originator Allin Luong of Tesla - In meeting was presented the 3D model of Cambalache BESS system it was mentioned that all Megapack required a ground, and this will include the Medium Voltage Transformer also was mention that next Monday will be presented the 3D Model of Vega Baja BESS Project by Tesla.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the IFC electrical drawing revision 1 verification received on 7/17/25 at 8PM and compare drawing with the IFC revision 0 to identify possible change orders. Send all IFC drawing to a printing shop so we can have the drawing for Thursday review meeting with S&L. Installed a printer at trailer office area. The printer needs a software installation; this may require a configuration with IT department.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing the Mechanical drawing IFC released on 7/17/25 and compare the drawing with the IFB drawing that only was included these drawing. The mechanical drawing has several additional components and impact in Change Order and also some deduction should also be considered.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-evaluated the condition of shelving units and storage areas, identifying any structural issues or safety concerns that needed to be address prior to the inventory process. Although containers had not yet arrived, drafted a preliminary map of the warehouse layout to support better coordination and ensure all sections would be properly covered once the inventory begins. These actions contributed to building an organized and controlled environment for the work ahead.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-this morning, a meeting was held with the inventory team specifically Mr. Milton Flores, Mr. Giovanni Taffanelli and Mr. Hernan Machado from DCMC, to emphasize the importance of adhering to safety protocols and using the appropriate personal protective equipment during inventory operations at the Cambalache warehouse. The use of gloves, helmets, reflective vests, and safety footwear was reinforced, along with the need to follow established procedures to prevent incidents and ensure a safe and efficient work environment. This briefing is part of the proactive measures implemented to support the success of the project under challenging operational conditions.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-preliminary inventory activities at the Cambalache warehouse, including physical inspection of the storage areas and identification of item groups. Given the absence of system data or historical records, the morning efforts were dedicated to visually locating materials, assessing the conditions strategy to support an organized documentation process.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-efforts continued at the Cambalache warehouse, building upon the groundwork establish in the morning. The team remained focused on identifying and organizing the physical layout of inventory, inspecting each area to better understand the volume and type of materials present. Priority was given to classifying items by category and determining the most effective way to group and label them for future processing.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-proceed with on-site inventory preparation tasks. This included assessing the layout, identifying potential hazards, and organizing the areas to be inventoried. The focus was on ensuring that ball necessary materials and procedures were in place before beginning the detailed documentation process under the challenging conditions present at Cambalache facility.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status. PW-108115
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Inspections Meeting SWPP testing for rain events, NDS permits, and BESS project activity progress documentation. with Andres Concepcion, Luis Duque, Jorge Mercado from DCMC, and Kevyn Gonzalez from Genera PR.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Create Daily Log on Procore for Inventory on Cambalache power plant warehouse activity.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339. 4339_9510 BESS Coordinate with Client Genera PR and Cambalache DCMC staff to continue the parts inventory on Cambalache power plant warehouse on next Wednesday.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339- 4339_9510 BESS Via phone call, I coordinated with Andres Concepcion of DCMC the visit of the structural inspection of the bridge by Integra and the delivery of the RGE office trailer.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS DCMC warehouse management team gives support to the Client Genera PR to coordinate and create parts inventory on Cambalache power plant warehouse.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Answered RFI #ARG-R012 (Plans in AutoCAD from Ida Ramirez from Sargent & Lundy). Completed working all existing dwg from IFB & IFC to identify any possible change orders. Today I resumed working on the new ones received on July 17th (32 of them in total), I continued working on 5 more of the new ones (Grid support units piping & instrumentation diagrams) with Eduardo Rivera Jordan (DCMC-Site Manager).
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Answered RFI #ARG-R012 (Plans in AutoCAD from Ida Ramirez from Sargent & Lundy). Worked on all existing dwg from IFB & IFC to identify any possible change orders, the task was completed. Today I continued working on the new ones received on July 17th (32 of them in total). I revised the Electrical & Mechanical with Eduardo Rivera Jordan (DCMC).
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Answered RFI #ARG-R012 (Plans in AutoCAD from Ida Ramirez from Sargent & Lundy). Worked on all existing dwg from IFB & IFC to identify any possible change orders, the task was completed. Today I began working on the new ones received on July 17th (32 of them in total), I worked on 6 of them with Eduardo Rivera Jordan (DCMC-Site Manager).
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Observed the workplace to identify potential hazards, conducting comprehensive risk assessments, and implementing preventative measures to mitigate risks. Today I was working on a PowerPoint to discuss safety pointers and emergency exits with ARG CERES safety team for Vega Baja BESS phase two project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with health, safety, and welfare regulations, which is essential for legal and ethical compliance.Today verifies submittals for approval for ARG safety Maria Reyes safety Lead.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-Cambalache facility. Proceed with on-site inventory preparation tasks. This included assessing the layout, identifying potential hazards, and organizing the areas to be inventoried. The focus was on ensuring that ball necessary materials and procedures were in place before beginning the detailed documentation process under the challenging conditions present at Cambalache facility.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-preliminary inventory activities at the Cambalache warehouse, including physical inspection of the storage areas and identification of item groups. Given the absence of system data or historical records, the morning efforts were dedicated to visually locating materials, assessing the conditions strategy to support an organized documentation process.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-efforts continued at the Cambalache warehouse, building upon the groundwork establish in the morning. The team remained focused on identifying and organizing the physical layout of inventory, inspecting each area to better understand the volume and type of materials present. Priority was given to classifying items by category and determining the most effective way to group and label them for future processing.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-this morning, a meeting was held with the inventory team specifically Mr. Paul Browne, Mr. Milton Flores, Mr. Giovanni Taffanelli and Mr. Hernan Machado from DCMC, to emphasize the importance of adhering to safety protocols and using the appropriate personal protective equipment during inventory operations at the Cambalache warehouse. The use of gloves, helmets, reflective vests, and safety footwear was reinforced, along with the need to follow established procedures to prevent incidents and ensure a safe and efficient work environment. This briefing is part of the proactive measures implemented to support the success of the project under challenging operational conditions.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Cambalache-proceed with on-site inventory preparation tasks. This included assessing the layout, identifying potential hazards, and organizing the areas to be inventoried. The focus was on ensuring that all necessary materials and procedures were in place before beginning the detailed documentation process under the challenging conditions present at Cambalache facility.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-evaluated the condition of shelving units and storage areas, identifying any structural issues or safety concerns that needed to be address prior to the inventory process. Although containers had not yet arrived, drafted a preliminary map of the warehouse layout to support better coordination and ensure all sections would be properly covered once
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-proceed with on-site inventory preparation tasks. This included assessing the layout, identifying potential hazards, and organizing the areas to be inventoried. The focus was on ensuring that all necessary materials and procedures were in place before beginning the detailed documentation process under the challenging conditions present at Cambalache facility.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-this morning, a meeting was job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the to emphasize the importance of adhering to safety protocols and using the appropriate personal protective equipment during inventory operations at the Cambalache warehouse. The use of gloves, helmets, reflective vests, and safety footwear was reinforced, along with the need to follow established procedures to prevent incidents and ensure a safe and efficient work environment. This briefing is part of the proactive measures implemented to support the success of the project under challenging operational conditions.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-preliminary inventory activities at the Cambalache warehouse, including physical inspection of the storage areas and identification of item groups. Given the absence of system data or historical records, the morning efforts were dedicated to visually locating materials, assessing the conditions strategy to support an organized documentation process.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-efforts continued at the Cambalache warehouse, building upon the groundwork establish in the morning. We remained focused on identifying and organizing the physical layout of inventory, inspecting each area to better understand the volume and type of materials present. Priority was given to classifying items by category and determining the most effective way to group and label them for future processing.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-efforts continued at the Cambalache warehouse, building upon the groundwork establish in the morning. Remained focused on identifying and organizing the physical layout of inventory, inspecting each area to better understand the volume and type of materials present. Priority was given to classifying items by category and determining the most effective way to group and label them for future processing.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Cambalache. This morning, a meeting was held with the inventory team specifically Mr. Paul Browne, Mr. Milton Flores, and Mr. Hernan Machado from DCMC, to emphasize the importance of adhering to safety protocols and using the appropriate personal protective equipment during inventory operations at the Cambalache warehouse. The use of gloves, helmets, reflective vests, and safety footwear was reinforced, along with the need to follow established procedures to prevent incidents and ensure a safe and efficient work environment. This briefing is part of the proactive measures implemented to support the success of the project under challenging operational conditions.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-Cambalache- Evaluated the condition of shelving units and storage areas, identifying any structural issues or safety concerns that needed to be address prior to the inventory process. Although containers had not yet arrived, drafted a preliminary map of the warehouse layout to support better coordination and ensure all sections would be properly covered once the inventory begins. These actions contributed to building an organized and controlled environment for the work ahead.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-preliminary inventory activities at the Cambalache warehouse, including physical inspection of the storage areas and identification of item groups. Given the absence of system data or historical records, the morning efforts were dedicated to visually locating materials, assessing the conditions strategy to support an organized documentation process.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Warehouse Inventory Reports from June to relate the use of parts and equipment from Warehouse out to repairs and other replacement works.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Costa Sur BESS & Peakers Incoming permitting data for review & process/Continuation of S&L incoming transmittals for review -label-process/Daguao Peakers Continuation of Procurement RFP & RFQ ensure documents were created, reviewed, and stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Costa Sur BESS & Peakers Incoming data for review & process/Vega Baja BESS Incoming data for review & process/ARG CERES Vega Baja BESS Add new users/S&L Incoming Transmittals for review -label-process. Coordination with Lauren Wells (DCMC) & Luis Roman (DCMC)
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the latest editions of the following SOPs to include new instructions or contractual agreement clauses to follow: Inspections, Observations, Specifications and Drawings.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Critical Components working sheet looking to identify redundancy in critical equipments and parts to relate delivery times with the potential project schedule of construction and installation of BESS and Peakers.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 151 | 113.25 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Weekly Catch-up Meeting with Lauren Wells (Lemoine) and Theresa Perez (DCMC) to recall our open topics on the Procore Platform and the most recent new topics such as Workflow Templates Configuration with respect to Field Staff comments, Contractual Agreement clauses related to the use and Procore, and more.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Luis Duque (DCMC) to review the workflow templates and the approval steps for the Cambalache Safety Submittals: adding safety manager Jean Menay (DCMC) to an additional separate step for final approval.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Strictly define the Drawings SOP for internal user in terms of Drawing Numbering and Titles, and the coordination with the Design Team in terms of identifying multiple drawing sheets and other scenarios defined in the Uploading process.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Update the SOP tracker to provide with the Management Team the most updated information for the progress on SOPs completion.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work with Procore permission levels for Gabriel Perez and Carlos Palomares (CDM Smith) to allow them on creating, editing and distributing meeting minutes for Staff Meetings and other importante extraordinary meetings.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review RFI #11 (ARG_0011) related to findings and omissions on Specifications Package for BESS Vega Baja.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the latest version of Transmittal SOP to specify documentation that must be worked through the Transmittal Tool, while contrasting with a Submittals Specification to exclude Submittal material from Transmittals Tool.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.75 | 151 | 113.25 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Update and finish the Action Plans Tools SOP after testing for the Plan Approver's actions to take including signatures, and the distribution to Approved Plan Receivers.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Travel from Vega Baja to Genera PR office Hato Rey after participating in a community activity at a summer camp with educational materials to impact the community with key information about power generation including the BESS project and Peakers.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Coordinate a meeting with Desiree Pastrana Otero, PPL, Director of the Secretariat of Planning and Territorial Planning, and the team of Genera Jorge Bracero in order to discuss some doubts related to the BESS project in Vega Baja.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Travel from Genera PR office Hato Rey to Vega Baja to participate in a community activity at a summer camp with educational materials to impact the community with key information about power generation including the BESS project and Peakers.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Organize BESS and Peakers project documents in Sharepoint. The files were updated along with the efforts that have been made, locate document, update the materials of each file.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Project Management Corporate Affairs Team Catch-Up meeting, in which we organized the agenda of the week together with the Genera PR team: Ivan Baez, Jorge Bracero and Rafael Ema Rodríguez. This meeting served to establish a specific work plan on the pending tasks as well as to determine the logistics for the work plan.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.25 | 139 | 173.75 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with the Genera PR team, Jorge Bracero and the Enactus team, Adeline Pérez, with the purpose of outlining the community plans to know what project we can impact for the communities in which the BESS and Peakers project are available.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Community meeting with the team of the municipality of Vega Baja, Desiree Pastrana Otero, and the Genera team of Jorge Bracero, to clarify doubts to the municipal staff, as well as answer the most common questions about the BESS project. During this meeting, in addition to answering questions, we had the opportunity to offer valuable information about the project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Revisions to the https://genera-pr.com/bess_peakers website to verify that all updates that were submitted to update the information were integrated into the website. These tasks included going through all sections of the project's Genera page to verify that they were up-to-date and correct.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Participate in community activity during a summer camp in Vega Baja for the purpose of educating about electric power generation including the BESS project and Peakers. This task included delivering educational material to students and giving a talk. As part of this effort, the Genera team, Jorge Bracero, participated in the activity. During this activity, about 35 students were impacted.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 139 | 173.75 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with the Genera PR team, Jorge Bracero and Rafael Rodríguez Ema, to evaluate the proposal to deliver cellular power bank and evaluate suppliers who can deliver the utilities for the purpose of using them during the BESS and Peakers community meetings. These tasks included organizing suppliers and evaluating the different models available.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Continue to integrate editions to the community presentation of Arecibo, Cambalache. These tasks included coordinating a meeting with Andrés Concepción, from the DCMC Partners team, who will be offering me information about the site. Similarly, edits were integrated into the presentation in relation to the copy used.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS Inventory process meeting with Andres Concepcion (DCMC) and Paul Browne (DCMC) to discuss the 4339_9510 BESS_Cambalache project warehouse relocation. Began working on inventory tag process and classification of items to be relocated in the temporary warehouse to increase traceability and improve efficiency in the stockroom. ensuring everything in the warehouse is exactly where it should be.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 30 pages were examined.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 6 pages were examined.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – AGUIRRE BESS PROJECT - Performed a focused review of selected sections within the Battery Energy Storage System (BESS) General Work Contract documentation (Spec No. G-3400, Rev A). The objective was to validate specific scope elements and confirm that assigned roles and technical criteria were clearly defined. The review covered 8 pages and supported project oversight efforts.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 7 pages were examined.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with drawings issued for construction for BESS project considering new comments for correction in construction in concrete structures, electrical works for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering the BESS project in construction schedule formats for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with drawings issued for construction for BESS project considering underground pipping installation, fire protection pipping drawings, one line diagram drawings, site plan drawings, mechanicals works drawings for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report considering checklist to evaluate concerns in acceptable or not acceptable, comparative in baseline reports, variance data and delays reports for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 134 | 268 | 134 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Cambalache BESS - Inspections Meeting with Andres Concepcion (DCMC) and Carlos Oquendo (SPHERA Group) for the 4339_9510 BESS_Cambalache project. Discussed inspection coordination and plan process to be completed.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue Cambalache BESS Inventory process with Andres Concepcion (DCMC) and Paul Browne (DCMC) for the 4339_9510 BESS_Cambalache project. Resumed working on inventory tag process and classification of items to be relocated in the temporary warehouse.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 134 | 402 | 134 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue (PART 2) Cambalache BESS Inventory process meeting with Andres Concepcion (DCMC) and Paul Browne (DCMC) for the 4339_9510 BESS_Cambalache project. Continued working on inventory tag process and classification of items to be relocated in the temporary warehouse to facilitate tracking and identification which are essential for effective inventory management.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with Frances Vallejo and Gilberto Sucre from DCMC to discuss new role and responsibilities.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewing RG Engineering contractor technical proposal for civil structural installation at Yabucoa BESS project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 122 | 244 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue assessing team feedback on the Procore flowchart and updating it based on their input.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 122 | 366 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Going through the team's comments on this week Power Bi One Pager report and incorporating suggested revisions in preparation for client submission.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 122 | 427 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Assessing team feedback on the Procore flowchart and updating it based on their input.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 16.73 | 16.73 | 16.73 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - PW 10710 - Sent to print at Professional Printing & Office Supplies a set of 6 IFC drawing for a total of $16.73 for Vega Baja BESS project.
2025-07-21 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 162.4 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Delivery offices and personal protective equipment in Vega Baja, Cambalache, Costa Sur and Yabucoa Genera Sites.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 243.07 | 243.07 | 243.07 | Yes | 146796 | Home Depot - Cambalache - Storage containers
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Gilberto Sucre, Frances Vallejo, Lauren Wells, Ada Diaz, and Mike Merritt, DCMC. Discussed update on project, job offers, PROCORE, logistics, trailer set-up, safety, schedule for locations and program goals .
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended Meeting on Peaker Projects – Status and Schedule Impact Participated in a project status meeting focused on the current progress of the Peaker plant projects. Discussions included updates on key milestones, identification of schedule risks, and assessment of potential impacts to overall project timelines. Action items and mitigation strategies were outlined to address any delays or dependencies. Attended: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Design Review Meeting – Project Drawings Purpose: To review the current status of all project-specific design drawings, identify outstanding issues, and align on next steps toward finalization. Meeting Objectives: Assess completeness and accuracy of submitted drawings Review changes, markups, or revisions Confirm design alignment with project requirements and scope Identify any gaps or required follow-ups Assign responsibilities and establish deadlines. Discussed Deliverable Dates for IFC and Bid Set with S&L Engineers Held a discussion with the structural and lighting (S&L) engineering team to confirm and coordinate key deliverable dates for the Issued for Construction (IFC) and bid set packages. The conversation included a review of current progress, outstanding design items, and timelines for submission to ensure alignment with overall project milestones. Attendees: William Crespo Sargent & Lundy Lemuel Nieves Sargent & Lundy Reinaldo Romero Sargent & Lundy Miguel Del Valle Sargent & Lundy German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 A thorough review of project-related emails and documents was conducted to ensure accuracy, alignment, and continuity across communications and deliverables. This included verifying critical information, identifying and resolving inconsistencies, flagging outstanding action items, and preparing detailed notes for upcoming meetings. The time invested supports effective decision-making, risk mitigation, and improved team coordination.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting. Main Topics Discussed: * Staffing Updates and Position Openings Cambalache position remains open with two qualified candidates identified. Costa Sur Sewer project potentially on hold due to FEMA environmental assessment requirements, decision expected by end of week. Interviews for inspectors willing to drive from San Juan to Daguao. Scheduler opportunity being considered to double up as reporting analyst until activity starts. Safety Peakers position has multiple candidates to start immediately. Staff starting on August 4th for class beginning November 1st. Senior project manager search expanded with resumes submitted, ranging from Argentina to Wisconsin with varied construction and nuclear backgrounds. * Project Updates and Technical Issues Financial call progress made yesterday with outstanding questions remaining for IT. Procore procurement PowerPoint in development. Distribution list screenshot for team alignment. FEMA promotional material discussion on eligible expenses. T-Mobile WiFi capacity issues at trailers, exploring alternatives. * Upcoming Events and Administrative Items PMO all-hands meeting on August 20th (Wednesday) City View venue requested. Office Depot purchases information provided to Ada Diaz. * Project Status and Challenges Sargent & Lundy documentation issues. Design-build methodology change being evaluated for three sites while Costa Sur continues as-is despite potential shelf time. Legal involvement required for existing design-build contract integration within organization. Budget presentation expected early next week. A&E firm contracts nearly finalized with Stan's Tech for Palo Seco and TRC down to two remaining items. *Interview Process and Holiday Communications Senior project manager interview protocol established. Puerto Rico holiday Friday communication sent multiple times regarding 4-10 schedule compliance. End of pay period timing creates additional timesheet submission challenges. Attendees: Mark Merritt, Mike Merritt, Ada Diaz, Jack Darnal, Barry Scanlon, Lauren Wells, Anneilia Holton, Frances Vallejo & Gilberto Sucre - DCMC.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Weekly Construction Meeting led by Andres Concepcion - DCMC * Provided feedback on contract status & estimated NTP * Provided current activities scheduled for the week * Provided feedback on the warehouse inventory & Genera required support * Had lengthy discussed on site access and need to a visitors protocol * Update on Permit status, PUI and NPDES. Gabriel Perez - CDM Smith Jose Segarra - RG Engineering Mike Kuczynski - Sargent & Lundy Osvaldo de Jesus - Genera and Jean Pierre Menay - Gilberto Sucre, DCMC.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Agenda Organization for Vega Baja meeting with ARG Ceres - Carlos Hernandez
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Weekly Construction Meeting with ARG Ceres. Main Topics: * NTP estimate in 30 days * Schedule of Values * Site Activities by Genera prior to mobilization, drainage repair, pit cleaning, & MPT works. * ARG requested permit for staging area from Municipality & 24 hr video camara * Demolition Contractor * IFC drawings Rev2 and Page-turn review with A/E * Fire Protection Design Attendees: Carlos Hernandez - ARG Ceres Eduardo Rivera & Gilberto Sucre - DCMC
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur meeting with Rafael Barrera DCMC in preparation of IFC's Page Turn Meeting, reviewed main information needs and drawing markups.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.75 | 225 | 843.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS - Back-to-Back IFC's page turn reviews for Costa Sur - Civil & Structural Contract and Cambalache - Installation Contract. RG Engineering being the General Contractor on both projects. Gilberto Sucre and Rafael Barrera - DCMC led the review for Costa Sur identifying missing information, "On Holds" clarifications, underground utilities and foundation under the demolished boiler building, underground duct banks, rigging restrains of Mega Packs and required date for Sargent & Lundy to provide information. RGE was requested to submit their rigid inclusions design asap. in coordination with S & L review. Andres Concepcion DCMC led the review covering New Parking and Piping Relocation, Site drainage including box culvert, raw water relocation options, New GSU foundation and staging area, RGE's structural design submission and Fire Protection Requirement, Rigid Inclusions, duct bank elevations and others. At the end of the meeting, it was encouraged to continue holding these meeting until design completion. Attendees: Sargent & Lundy - Mike Kuczynski, Robert Molner, & Wilfredo Sierra CDM Smith - Gabriel Perez RG Engineering - Jose Segarra & Alberto Borrelli DCMC - Rafael Barrera, Andres Concepcion, Gabriel Morales & Gilberto Sucre
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine)
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items with Luis Roman (DCMC) and invoice items with Esther Rohena (DCMC).
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reports for user usage.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) and others to discuss program staffing and overall program goals.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for meeting template for CDM Smith users.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore meetings settings/permissions for Peakers projects.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on Procore financial items for follow up and open questions since we don't have a Friday meeting now.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financial SOP document and created new financial roles/permission in Procore.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on collecting information for Procurement to identify how we can incorporate the processes into Procore.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore SOP's QA/QC for all tools.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed the third RFI related to Generation Fleet RFP 4826. Held discussions with Franklyn Colmenares (CDM Smith) and Jesús Cintrón (Genera) to clarify the financial and timeline elements of the inquiry. Drafted the RFI response, incorporating Jesús Cintrón’s feedback to ensure accuracy and consistency with project objectives and procurement guidelines. Submitted the finalized draft to the Procurement Team for review and official submission.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.75 | 184 | 506 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Conference call with Nelson Medina (GENERA) about security incidents with RGE (Contractor) in Cambalache Genera site. The contractor needs with the security protocol and role in accordance with United States Government Police. Conference call with Andres Concepcion (DCMC) about the RGE (contractor) in Cambalache Genera Site in accordance with conversation with Nelson Medina (GENERA). Review the emails about all Genera Sites status included the Health and Safety, Security and purchases.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with Osvaldo de Jesus and Herminio Arroyo (GENERA) about the Cambalache Project. The topics included the Health and Safety procedure, calendar and equipment delivery logistics.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 184 | 230 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Continuing Inspection delivery de offices trailers for RGE in Cambalache Genera project. Meeting with Nelson Medina (GENERA) about logistics and entrance process in Cambalache Genera Site.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Inspection delivery de offices trailers for RGE in Cambalache Genera project. Meeting with Carlos Negron (RGE) (contractor) and team before and after the task. Meeting with RGE (contractor) Jose Segarra (RGE) and team about Cambalache (BESS) Genera Project.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Jesus Cintron (DCMC) to discuss project overview, staffing update and S&L update.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 184 | 230 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Draft and review correspondence regarding Office Max and Office Depot purchases, invoices from suppliers that are pending and contacting suppliers requesting information.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 184 | 138 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Jesus Cintron (Genera PR) to discuss staffing update for sites, one pager for BESS and Peakers, S&L meeting feedback and next steps.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams call with Gabriel Perez (CDM) and Jesus Cintron (Genera) to discuss BESS project execution needs.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams call with Jean Menay (DCMC) to discuss invoices pending payment to suppliers, trailer coordination at Costa Sur and material and equipment purchases.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Jorge Bracero (Genera) and Paola Arroyo (DCMC) to discuss promotional material for community engagement meetings and applicability to the project.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued the development of the requisition package for the procurement of demolition services at the Jobos site, which is part of the Generation Fleet infrastructure improvement initiative. Received and reviewed the ICE for completeness and accuracy, reformatted it to align with Genera’s internal standards and documentation requirements. Held a discussion with Abraham Velázquez (DCMC) to validate the technical details and ensure the cost breakdown reflected the current SOW. Once finalized, submitted the formatted ICE to Jesús Cintrón (Genera) for review and sign-off as part of the overall procurement documentation process.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Reviewed and verified the status of key workstreams and critical-path items associated with Procurements No. 4898, 4899, and 4900 to support timely project execution and compliance with Genera documentation standards. Identified missing or delayed components and discussed these gaps with Gabriel Sepúlveda (CDM Smith). Coordinated with the Procurement Team to expedite resolution and ensure all required documentation is complete and submission-ready. Additionally, participated in a strategic coordination session with Gabriel Sepúlveda and Franklyn Colmenares (CDM Smith) to identify root causes of recurring procurement delays and to develop process improvements aimed at enhancing future workflow efficiency and maintaining procurement schedule integrity.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Participated in a strategic coordination meeting with Winnie Irizarry, Jesus Cintron, Ricardo Pallens, and Cristina Ribas (Genera) to identify opportunities for enhanced support to the Regulatory Team in the management and oversight of Generation Fleet projects. Discussions focused on streamlining internal coordination, improving documentation practices, and ensuring alignment with FEMA PA program requirements. This effort contributes to effective project execution, regulatory compliance, and timely submission of required materials for federally funded infrastructure initiatives.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed and edited the draft response to PREPA’s Request for Information regarding the ER1 Cost Share Program. Conducted a detailed review to ensure technical accuracy, clarity, and alignment with grant management requirements. Confirmed all Generation Fleet-related items and cost implications with Jesús Cintrón (Genera) and incorporated his input to ensure consistency with internal project documentation. Completed a final review of the revised response to verify completeness and regulatory compliance before submitting it to Jesús Cintrón for final approval. This activity supports accurate grant reporting and transparent interagency coordination.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I was working on the as built documents to make sure work will be done properly and findings will be successful on tomorrow’s task with Javier Bidot, Homeca subcontractor. Meeting with Carirma Sanchez from Homeca was conducted for contractor documentation requirements for work to be performed on the as built, requested documentation from company that will be providing service from Genera to clear the oily water separator.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I review some documents on the Procore platform, including: Geotechnical Report (Results and Recommendations), Environmental Document -Rule 141 (Description, Purpose and Project needs), and BESS Emission Permits.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I read about Trenching and Excavation Safety (29 CFR 1926 Subpart P)The standard emphasized the following key points: The difference between an excavation and a trench, What are the dangers of trenching and excavation operations, Soil classification categories, What is a competent person, Why is preplanning important to excavation work, What safety factor should be considered when bidding on job, How can employers avoid hitting underground utility lines and pipes during excavation work, How can employers prevent cave-ins, What types of protective systems can employers use to protect workers from cave-ins, What are the requirements for safely installing and removing protective systems, and What do employers need to do to maintain materials and equipment used for protective systems.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I continued review documents on the Procore platform, including: Fire Suppression and Detection Specification (86 page), and Scope of Services -Specification- G-3300 (Pag. 51-535/ Document Effective Date: June -20- 2025).
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Develop custom punchkeys/ Do a punch walk on mobile devices/ Manage Punch Data/ Create specific reports for addressing issues/ Track issue fixes with custom statuses.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Describe how control panels are effective for distributing and accessing files. Compile a file structure that allows you to effectively use a control panel. Design both simple and more advanced control panel elements using tags. Add actions to the control panel elements to link them to drawings and other files. Organize the control panel elements to create an easy-to-navigate document. Save the control panel to use it as a template for future projects.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Navigating and tailoring the interface/ Manipulating, reordering, splitting, and combining documents/ Implementing industry-standard markup tools/ Creating and saving custom markups/ Sorting, filtering, and sharing markup data/ Calibrating scales and measurements/ Collaborating with Studio Sessions and Projects.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Create spaces to organize punch data. Create templates for field workflow. Distribute files using Revu. Explain the differences between a set and a multi-page PDF document. Share sets with BESS Aguirre team members as published files or with Studio Projects.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued refining the Costa Sur BESS safety signage and emergency planning effort by validating the visibility, spacing, and orientation of proposed sign placements in high-risk areas. Prepared a preliminary list of required labels for electrical cabinets, battery enclosures, and restricted access areas. Drafted initial templates for bilingual safety signs (English/Spanish) to ensure clear communication for all on-site personnel and contractors.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Developed a safety signage and emergency plan for the Costa Sur BESS project, focusing on the identification and placement of critical safety signs, hazard labels, and directional evacuation markers. Reviewed layout plans to determine optimal locations for emergency route maps, muster point signage, and fire hazard warnings, ensuring compliance with OSHA and NFPA standards.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Conducted a detailed review of the Costa Sur BESS layout to identify and verify the adequacy of proposed evacuation routes and emergency access paths. Evaluated the positioning of exit points, clear zones, and emergency signage based on design documents and standard safety codes, including NFPA 855 and OSHA guidelines. Special consideration was given to battery container arrangements, potential obstruction points, and accessibility for first responders in case of fire or electrical incident. Observations and improvement recommendations were documented to support safe egress planning and coordination with Genera’s HSE team during upcoming design reviews.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA -Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Travel time from Yabucoa site to Sargent & Lundy Office to assist the meeting to review the BESS Project Issue for construction drawings for the Cambalache site and the Aguirre site with RG Engineering, DCMC Partners, Sargent & Lundy and CDM Smith team.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with Vincent Skochdopole, Wilfredo Sierra, Mindy Madry, Chris Niersbach, Camillus Pawlica, Robert Molner from Sargent & Lundy; Andres Concepcion, Rafael Barrera, Luis Duque and Gilberto Sucre from DCMC Partners; Gabriel Perez from CDM Smith to discuss and review the BESS Project Issue for contruction drawings for the Cambalache site and the Aguirre site.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria Travel time from Sargent & Lundy Office to Yabucoa site after assist the meeting to review the BESS Project Issue for construction drawings for the Cambalache site and the Aguirre site with RG Engineering, DCMC Partners, Sargent & Lundy and CDM Smith team.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the Value Engineering Study Request for the BESS Foundation Optimization at the Aguirre site. The evaluation time included a call with Jose Lopez, DCMC Site Manager from the Aguirre site.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- The meeting was held at Sargent & Lundy central office in order to focused on the coordination and planning with DCMC Costa Sur Teams (Gilberto Sucre & Rafael Barrera), S&L designer team and RGE Project manager Jose Segarra. Key participants included project managers from DCMC and engineers from S&L and RGE responsible for various aspects of the projects. The main objectives were to discuss the status of the IFC (Issued for Construction) drawings, demolition plans, and the sequencing of construction activities. Challenges included the lack of complete IFC drawings, uncertainties regarding existing underground structures, and the need for coordination with multiple stakeholders. Decisions were made to prioritize the release of certain drawings and to conduct further site investigations. Action items included reviewing the demolition drawings, coordinating with survey teams for GPR (Ground Penetrating Radar) scanning, and finalizing the transformer specifications. The meeting also addressed the need for a lifting plan for the battery installation and discussed potential locations for infrastructure components. Further discussions were planned to resolve outstanding issues and ensure timely progress of the project.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. BESS Costa Sur- A meeting was held at the DCMC office with Gilberto Sucre (DCMC) to review the current set of plans for the BESS Costa Sur project. The primary objective of the meeting was to thoroughly examine the design documents in order to identify any missing details, incomplete information, or areas requiring clarification. The findings from this review will serve as key discussion points for the follow-up meeting scheduled later today with the project designer, Sargent & Lundy (S&L). The goal is to ensure that all outstanding issues are addressed promptly to maintain the project timeline and design integrity.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. BESS Costa Sur Travel time to meet with Gilberto Sucre (DCMC) in DCMC office preparing for the meeting with Sargent & Lundy in their office.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel time from Sargent & Lundy office meeting to Costa Sur plant
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre We are working on the Safety and Emergency Procedures: Stop Work Authority: All team members empowered to stop the lift if unsafe conditions arise. Emergency Communication Plan: Radios, signals, and emergency contacts established before lift begins. Medical and Rescue Plan: Personnel trained in first aid; site access points and medevac procedures identified.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre We continue working on Equipment and Personnel Requirements: Crane Type: Appropriately rated mobile crane (likely 200-ton or larger depending on radius and boom configuration). Operator Certification: NCCCO or equivalent, with proof of recent evaluation per OSHA 1926.1427. Riggers and Signal Persons: Must be qualified under OSHA and ASME standards. Equipment Certification: Cranes and rigging gear must have current inspection tags and load test records. Site-Specific Controls (Aguirre Power Plant): Permit to Work (PTW): Must be obtained from plant operations and coordinated with shift supervisors. Lockout/Tagout (LOTO): If lift is near energized conductors or equipment, isolation and grounding must be in place. Weather Monitoring: Lift postponed if wind speed exceeds crane specs (typically >20 mph for heavy loads). Restricted Zones: Establish exclusion zones beneath and around the lift path with physical barricades and signage.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria . We continue working in the importance of the Documentation and Records Required documentation includes: PE-stamped lift plan and rigging diagram Load calculation worksheets Daily crane inspection checklist Operator and rigger certifications Pre-lift briefing sign-in sheet Incident/near-miss report forms (if applicable)
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the Issue bid drawings documents, TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC) Spec. No.: G-3400 Revision: A; For Bid Project No. A15240, June 20th, 2025to identify potential and possible change orders, as well as potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects to be integrated into the PROCORE platform.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Had a call with Gilberto Sucre and Jean-Pierre Menay (DCMC) to discuss the office trailer consumables and office equipment supplies pending order and delivery to the DCMC's Aguirre Office Trailer Compound. A list will be shared by Frances Vallejo (DCMC) to follow up on the procurement process and delivery.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, Sunem Martínez, and Luis Moctezuma(DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting Coordination and Agenda preparation work with the Construction Weekly Progress Meeting with RG Engineering, the General Work Contractor, José Segarra (RGE), José Robles (RGE), Xiomara Pérez (RGE), Gilberto Sucre, Carlos R. López Vallellanes, Luis Moctezuma, Jean Pierre Menay (DCMC), Gabriel Pérez (CDM Smith), and Franklyn Colmenares (CSA). Categories of the Agenda are as follows: DCMC Construction Management Team Introduction, RG Engineering Construction Team Introduction, Scope of Work Clarifications, Directory of Responsibilities Clarifications, Safety Topics and Plan from RG Engineering, Master Project Schedule, Schedule of Values, RG Engineering Point of Contact during the construction process, Schedule an Initial Genera PR Safety Modules, and Open Items Discussion.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Cambalache site- Verified that the daily work permits used to authorize the installation of temporary offices at the Cambalache site were finalized, and specific activities were coordinated for tomorrow, such as the movement of containers by crane, certifications, work plans, among others.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Cambalache site- Work continues on the supervision of the work generated by the contractor RGE. The work generated by the contractor assigned today is the installation of temporary offices, where heavy equipment is required for movement, as well as specific machinery such as forklifts, moving platforms, among others.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Assistance was provided to the Cambalache site where the installation of RGE's temporary offices was supervised. The safety regulations applicable to the BESS project were also discussed. The electrical connection points for the temporary offices were identified with the contractor.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met in Sargent and Lundy's office in San Juan, PR to perform a design review for Costa Sur & Cambalache sites with open blueprints to discuss each of the design set pages (131 pages for Cambalache) and disciplines to identify and planning for resolution of pending design items. Met with Gilberto Sucre and Luis Duque (DCMC), Gabriel Perez (CDM Smith), Mike Kuczynski, Wilfredo Sierra, Angel Alicea (Sargent and Lundy).
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Managed General Contractor delivery logistics for access to the Cambalache Plant. Reviewed Open Submittals, RFIs and actions in Procore to prepare and complete the Construction Weekly Meeting Agenda.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted meeting with project team: RG Engineering (Jose Segarra), Sargent and Lundy (Robert Molner), CDM Smith (Gabriel Perez), CSA Group (Franklyn Colmenares) to follow up on weekly updates and project pending actions.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Evaluated design trackers and pending design information to prepare agenda document for upcoming Design Review meeting (Page turn) with Designers (Sargent and Lundy) and General Contractor team (RG Engineering)
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Evaluated Project NPDES permitting requirements to generate a follow up consultation to Carlos Lopez (CW Legal) to define scope of work and responsibilities for GeneraPR. Evaluated proposed temporary parking by general contractor (RG Engineering) and comfirm special environmental requirements, created consultation to Carlos Lopez (CW Legal).
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Send email to Jaime Pesquera of DCMC to coordinate Homeca work related to as built for underground lime and to coordinate with Gabriel Perez of CDM Smith the work related to a vacuum truck to remove water at oil separator. Reviewing RFI send by Gabriel Perez of CDM Smith related to Luma if the existing underground tie line will be reconducted. This RFI may be responded by S&L but at the drawing there is no underground tie in for electrical interconnection. Gabriel Perez of CDM Smith will provide information related to the Table A-2 that mention Luma in the RFI as I requested to him by email.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting held between Genera and DCMC regarding the Vega Baja BESS project. Gilberto Sucre of DCMC participated to prepare for the upcoming meeting with ARG General Contractor. The purpose was to align on discussion topics and to incorporate ARG’s proposal into the agenda. A key objective of the meeting is to request the final draft of the Schedule of Values (SOV).
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Installation Meeting organized by Gilberto Sucre of DCMC, Carlos Hernandez of ARG and Eduardo Rivera of DCMC - Meeting was to discuss the schedule of value for the project, was also discuss the design requirement for fire protection system, was discuss the issue related to the fire tank and pumps. It was discussed to create a new meeting for change order discussion for next week with ARG/CERES and DCMC. Also, in meeting was requested to ARC to start providing all project documents before the NTP.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project weekly meeting to review project status. Homeca Carirma Sanchez, Gilberto Soto, Jaime Pesquera, and Eduardo Rivera of DCMC, Enrique Laya and Manuely Concepcion of CDM Smith - Meeting to discuss final pending items related to project closing, Carirma Sanchez of Homeca is requesting status of the payment of certification #3 and also requested in meeting when Genera will review the proposed change order before they submit the draft of certification #4. It was also mentioned that Harold Vidal Survey Contractor will be tomorrow to complete the underground survey. PUI and permit has been submitted for closing. After meeting was completed, I generated the minutes for the meeting and distributed to all attendance.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with review of ARG Exhibit_E.1_Proposal_Data_Contractor_to_Provide_Responses_to_Price_List_20250131 document in preparation for meeting with ARG. Also, review drawing to be discuss in meeting related to fire protection and grounding.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed a focused variance investigation at the Aguirre warehouse aimed at addressing inventory discrepancies detected during prior cycle counts. The analysis involved reviewing system data, verifying bin assignments, and physically inspecting storage locations to detect overages, shortages, or misplaced items. The objective was to validate inventory accuracy, identify contributing factors to variances, and record actionable insights for corrective measures. The scope of the review covered inventory zones BI 060 through BI 100.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused inventory recount at the Aguirre warehouse, targeting locations BI 060 through BI 100. The process involved validating bin assignments, confirming part numbers and item description, and cross-checking physical inventory against system records. Any discrepancies identified were logged for further investigation, with strong emphasis placed on traceability, data consistency and alignment with asset control protocols. All actions were executed in accordance with established inventory governance standards to ensure operational transparency and accountability.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-executed scheduled cycle count operations within inventory zones BI 060 through BI 100 as part of a broader inventory governance initiative. Activities encompassed physical bin verification, alignment of recorded quantities with system data, and identification of labeling or placement inconsistencies. The effort also included documenting notable variances, validating data integrity, and reinforcing adherence to internal inventory control standards. Special attention was given to traceability audit readiness, ensuring all findings were properly logged and available for further analysis or corrective action.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out preparation tasks at the Aguirre warehouse to enable the execution of the cycle count. Work included organizing storage areas, labeling locations, reviewing existing documentation, and verifying physical inventory zones, specifically within locations BI 060 through BI 100. These actions were essential to establish the structure and control needed for a reliable and systematic counting process.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-compiled and submitted a comprehensive inventory performance report from the Aguirre warehouse, addressed to Anthony Vega and Sulinnette Perez from Genera PR. The report encompassed catalog verification, analysis of unit counts, and variance metrics for inventory zones ranging from BI 060 to BI 100, AC 132 to AC 140, BA 034 to BA 060, CD 025 to CD 034. Emphasis was placed on evaluating stock accuracy, inventory coverage, and the general condition of stored materials.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a morning coordination briefing with Mr. Hernan Machado, Milton Flores, and Giovanni Taffanelli from DCMC, to review the day's inventory priorities and operational checkpoints. Discussions included workload distribution, resource availability, and alignment on safety protocols. Key focus was on maintaining workflow efficiency, minimizing interruptions, and ensuring adherence to inventory control standards established.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Contract 105654 Air Heater Basket to determine Units of Aguirre Plant included in contract to ensure our baskets are covered by Federal Grant Project. PW-9015 A&E
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Tech Spec developed by CPM to regarding, to identify potential RFI in the narrative to Recirculating Fan Duct & GRF of San Juan. PW-9510 A&E.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- DR 4339 - Follow up to Power Plant Manager regarding to installation works related to delivered Critical Components. PW 9510 A&E.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -Develop overall status report of Critical Components Status requested from GENERA-PR Francisco Ramos to response a PREB request. PW-9510 A&E
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Memo Contract Requirements for Hydrogen Coolers Palo Seco. PW-9510 A&E
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Project 687480 to determine activity included in contract 106982 are included. PW-9015 A&E
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera Deliverable PR 11 - Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Via phone call, I coordinated with Andres Concepcion of DCMC the visit of the structural inspection of the bridge by Integra and the delivery of the Genera temporary warehouse trailer and Portolet.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Structural Forensic Study - Entrance Bridge Cambalache. The evaluation and information necessary for the reverse engineering analysis of the entrance bridge of the Cambalache Power Plant was coordinated with the Integra company with Herminio Arroyo, Eliseo Martinez from Genera PR and Milton Ballester, Roberto Rivera, Aida Pedroza Martinez from Integra.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS -Supervising the on-site installation of RGE's office trailer with Eliseo Martinez, and Herminio Arroyo from Genera, and Jorge Mercado of DCMC and Jose Segarra of RGE and others.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed contractor submittal RGE-0010.2 for the BESS project (PW9510), outlining the updated Work Plan for Trailer Unloading. Focused on verifying unloading procedures, equipment sequence, traffic flow, and on-site personnel coordination to ensure compliance with safety and logistics protocols. Prepared internal review notes and identified missing elements requiring contractor clarification prior to approval.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Construction Weekly Drawing and trailer office update and some delay issue with Gilberto Sucre, Jorge A. Mercado, Andres Concepcion, Carlos De Jesus and Luis Duque DCMC Partners Cambalache Power Plant team.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Daily project coordination and project management. Had a weekly construction meeting with Homeca Recyclers Carirma Sanchez & Eduardo Vera, also Eduardo Ramos, Eduardo Rivera Jordan (DCMC), Nelson Soler (CDM-Smith) and went over project closing documents overview. Analyzing documents status in the Procore platform and all the punch list items that are now closed.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Reviewed Punch list #32, the crew is coming tomorrow for the as build. Worked on all existing dwg from IFB & IFC to identify any possible change orders for the new drawings that were released on Thursday the 17th.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Reviewed Punch list #32, the crew is coming tomorrow for the as build. Continued working on all existing dwg from IFB & IFC to identify any possible change orders for the new drawings that were released on Thursday the 17th.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I was working on the as built documents to make sure work will be done properly and findings will be successful on tomorrow’s task with Javier Bidot- Homeca subcontractor. Meeting with Carirma Sanchez from Homeca was conducted for contractors workshop and documentation requirements for work to be performed on the as built Requested documentation from company that will be providing service from Genera to clear the oily water separator. Resumed inspecting the field for dirty oil pads to be replace and clearing the old pads to install new ones for environmental measures. Started fixing the fence cover located on the north side of the site for privacy and construction purposes. Had a meeting with Eduardo Rivera (DCMC) for preparation for tomorrow's task and reviewed the as build information.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I was working on the as built documents to make sure work will be done properly and findings will be successful on tomorrow’s task with Javier Bidot- Homeca subcontractor. Meeting with Carirma Sanchez from Homeca was conducted for contractors workshop and documentation requirements for work to be performed on the as built Requested documentation from company that will be providing service from Genera to clear the oily water separator. Began inspecting the field for dirty oil pads to be replace and started to clear the old pads to install new ones for environmental measures. Started fixing the fence cover located on the north side of the site for privacy and construction purposes.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CD025 to CD034 to begin the cycle counts.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BA034 to BA060
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BA034 to BA060
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BA034 to BA060
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations BA034 to BA060
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BA034 to BA060
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC 01 032 000 to AC 01 040 000.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse reviewing physical locations, requesting an inventory list and printing it to begin accounting.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC 01 032 000 to AC 01 040 000.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC 01 032 000 to AC 01 040 000.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Analyzing and developing a draft of an Excel spreadsheet to track the tasks related to the inventory project at the Cambalache warehouse.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CD025 to CD034 Cycle Count List # 1534.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CD025 to CD034.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1542, 1545 and 1546 from locations CD025 to CD034 for a total of 270 pcs.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Cambalache Weekly Project Meeting hosted by Andres Concepcion (DCMC) and joined by the contractor's team (RGE) with Jose Segarra and Xiomara Robles, also from the design team Deanne Ennes (S&L), Franklyn Colmenares (CSA), Gabriel Perez (CDM Smith), Gilberto Sucre, Jean Menay and Jorge Mercado (DCMC) and other project staff members. Discussed the current status of main submittals and plans from contractors such as office trailers and portable sanitary services delivery, safety credentials and receipt of Genera Safety workshop, the potential tasks for this week, and more.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /Daguao Peakers Procurement RFP & RFQ ensure documents were created, reviewed, and stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team/Provide Procore access and review permissions to add Genera personnel/Jobos Peakers Procurement RFP & RFQ ensure documents were created, reviewed, and stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Jobos Peakers Procurement RFP & RFQ ensure documents were created, reviewed, and stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Perform QA/QC on the Cambalache Workflow Templates for Safety and Management Submittals.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review permission levels for Eng. Ricardo Lopez (ARG/CERES) specifically for the Meetings Tool; currently unable to access past meetings notes.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Reach back to Chandan Dash (Siemens) with update from the Procore Live Assistance Team related to the ongoing issues with Submittal Packages.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review active projects submittal logs and packages looking for items described at the Critical Components spreadsheet; looking to begin official tracking of lead times and deliveries inside the Procore Platform.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Complete the onboarding of Luis Cintron (Genera PR) who acts as EHS Coordinator for Genera and get him onboard on all active projects.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review SOPs latest versions for Action Plans, Drawings for Internal Users, Observations for External Users, and review all other versions for updates.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Touch base with Chandan Dash (Siemens) for an ongoing issue related to the Submittals Tool in Procore: user is not able to upload submittal packages for multiple documentation related to the Costa Sur Peakers Project. Documentation submission is usually part of project scope and schedule and can't be affected.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the most recent Warehouse Inventories for the Genera Plants looking to integrate the way information is obtained and shared with the Genera staff across Procore.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Reach to the Procore Live Assistance Team through the 24/7 Chat to project the ongoing issues with users not being able to upload Submittal Packages on the Platform, specifically for the Costa Sur Peakers Project. Reviewed permission levels and granular options for users. Discussed recommendations to be discussed with users.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Costa Sur BESS Drawings to review unpublished drawings in order to make them public to Contractor and Team Staff.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review Costa Sur project recent history for Submittlas and RFI uploaded to the system, looking to identify issues and deficiencies for users to create new items.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 139 | 417 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Continue to work on corroboration with non-profit organizations with which Genera PR can increase its community efforts, particularly at those sites where the BESS and Peakers project are located. These tasks included: corroborating the identified organizations and assigning them a goal with each organization. Likewise, it included contacting the municipality of Vega Baja to request necessary information about the organizations with which they feel comfortable supporting. Also, I had to create a document to support the recommendations
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Coordinate with Jorge Bracero visit to Aguirre's site together with the non-profit organization Enactus. These tasks included: identifying the appropriate time to visit the site, coordinating the logistics of the visit and scheduling the activity on the calendar
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Read and analyze at least six technical and regulatory documents related to preventive measures that Genera PR implements to mitigate fire risks in its energy storage systems (BESS), including Fire Protection Engineering and UL 9540A Interpretation Report, Destructive Fire Test and Fire Modeling Report, Industrial Lithium-Ion Battery Emergency Response Guide, MEGAPACK SAFETY OVERVIEW, MEGAPACK 2 XL DATASHEET, as well as specialized articles on thermal risks, suppression systems and battery management protocols with the aim of extracting best practices, evaluating failure scenarios and adapting these measures to the local context in Puerto Rico, generating as a result a document that serves as a guide for the communication pieces related to the BESS project in the communities.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting between Genera PR and Enactus Puerto Rico, represented by Jorge Bracero and Adeline Pérez respectively, aims to strengthen the partnership between both organizations through a collaborative community project in Aguirre, Salinas. The focus will be on sustainability, energy education, and youth leadership, with the discussion centered around defining responsibilities, available resources, opportunities for university student engagement, and establishing social impact metrics to guide and monitor the initiative.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Evaluate Kroma's quote together with the Genera PR team, Jorge Bracero and Rafael Rodríguez Ema, to corroborate the amounts of the totals and the sum of the entire quote.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Identify non-profit organizations in Puerto Rico aligned with the values and objectives of Genera PR, and define collaborative strategies to promote the social, economic, and energy development of the island. These tasks included the following: creating database with: name, mission, focus, contact, region, prioritizing organizations with a focus on energy, community development, sustainability, health, and education and made direct calls to several nonprofits identified in the directory.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue In - Person Page Turn for Costa Sur and Cambalache at S&L with Andres Concepcion (DCMC), Gilberto Sucre (DCMC), Jose Segarra (RGE) and Wilfredo Sierra (S & L) for the 4339_9510 BESS_Cambalache project. To clarify doubts and missing items on project drawings.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 134 | 268 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 15 pages were examined.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 7 pages were examined.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 8 pages were examined.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 32 pages were examined.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewing the draft project earth movement schedule to verify comprehensive coverage of all tasks associated with this initiative.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report in evaluate formats of baseline schedule at project start, weekly schedule progress QA in track actual vs planned progress, lookahead schedule QA checklist in verify short-term forecast validity for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- Attended TEAMS meeting related to Cambalache BESS - Construction Weekly with pending issues to start project, sign of contract status and permits status with DCMC employees Andres Concepcion, Gilberto Sucre, Luis Damudt, Luis Duque, employees of RGE Jose Segarra, Xiomara Pérez Álvarez, CDM Smith employee Gabriel Perez, employees of Sargent and Lundy Dean Ennes due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering milestones report, variance report, the BESS project in construction schedule formats, concerns in acceptable or not acceptable comparative in baseline reports, delays reports for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 134 | 268 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering data report of milestones logics, variance data in activity details, the BESS project in construction schedule formats, concerns in acceptable or not acceptable comparative in baseline reports, delays reports for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- Attended Teams meeting considering notice to proceed status, construction activities duration, schedule report activities, format for schedule for submittal, specification section 013216 list related to construction guides and resources data formats, schedule of values of schedule for employee (DCMC) Carlos Rodriguez, Sunem Martinez, Rafael Barrera, (RG Engineering) employee Jose Segarra, (CDM Smith) employee Carlos Palomares, (Sargent and Lundy) employee Dean Ennes.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering acceptance or not acceptance evaluations, delays reports, variance baseline reports, delays reports for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Review Lemoine Quality Control/Assurance Plan, Inspections plan, Variance Request Form and Submittal Stamp Sample to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. In - Person Page Turn for Costa Sur and Cambalache at S&L with Andres Concepcion (DCMC), Gilberto Sucre (DCMC), Jose Segarra (RGE) and Wilfredo Sierra (S & L) for the 4339_9510 BESS_Cambalache project. To clarify doubts and missing items on project drawings.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 4) Review Lemoine Quality Control/Assurance Plan, Inspections plan, Subcontractor Daily Reports and Timberline Submittal Process to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Microsoft Teams meeting with Manuely Concepcion from CDM Smith to review the CPA and routing list workflow, focusing on aligning the flowchart effectively with Procore’s financial tools.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting with the Cambalache construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as Safety Plan, mobilization plan, permits and other documentation needed. Attendees: Andres Concepcion (DCMC), Gilberto Sucre (DCMC), Jose Segarra (RGE) and others.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewing and analyzing email correspondence pertaining to the Asset Activity Report in support of Gilberto Sucre, DCMC."
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 122 | 152.5 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Integrating RFPs status updates from BESS & Peakers projects to strengthen the analytical visual representation of ongoing progress and potential risks in the July monthly report.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.75 | 122 | 91.5 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue integrating RFPs status updates from BESS & Peakers projects showing the ongoing progress and potential risks in the July monthly report.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewing team feedback on the Procore flowchart and implementing revisions accordingly.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Compiling and analyzing BESS & Peakers project data, including current status updates, to enhance the visual clarity of progress and risk metrics in the July monthly report, making the information more intuitive and accessible.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Barrera Quinones, Rafael | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 5.5 | 5.5 | 5.5 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Parking at Sargent & Lundy Office
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 72.8 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Delivery offices trailers by RGE (contractor) and make the Safety Training to Carlos Negron (RGE) and teams. Metting with Nelson Medina (GENERA).
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 0.7 | 50.96 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PW10710 - Claiming Mileage for this route - Yabucoa Gas Turbine to Sargent and Lundy office to Yabucoa Gas Turbine. Purpose-Meeting the teams of Sargent & Lundy, DCMC Partners andCDM Smith to discuss and review the BESS Project Issue for construction Cambalache site and the Aguirre site.
2025-07-22 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Barrera Quinones, Rafael | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 0.7 | 118.3 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Travel to meeting in DCMC City View Plaza Main Office and also to Sargent & Lundy designer Costa Sur BESS project. PW #10710
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 312 | 312 | 312 | Yes | 146796 | Portosan - Holding Tank Rental - Cambalache-Arecibo
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 234 | 234 | 234 | Yes | 146796 | Portosan - Holding Tank Rental - Salinas
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on troubleshooting Submittal Package for Siemens on Costa Sur Peakers.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 225 | 787.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Participated in a project review meeting to address ongoing issues related to design and development. The discussion focused on delays caused by the late issuance of critical drawings, and how these delays have impacted individual project timelines and coordination efforts. Mitigation strategies and revised delivery expectations were explored to minimize further schedule impacts. project review meeting on the issues with design and development. Discussed impact delays for not having issued drawings in time for the individual projects. Attendees: Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group German Núñez, GENERA Rafael Pabon, CDM Smith Gilberto Sucre DCMC Carlos Palomares CDM Smith.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 225 | 562.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 review of project-related emails and documents was conducted to ensure accuracy, alignment, and continuity across communications and deliverables. This included verifying critical information, identifying and resolving inconsistencies, flagging outstanding action items, and preparing detailed notes for upcoming meetings. The time invested supports effective decision-making, risk mitigation, and improved team coordination.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended a procurement-focused meeting to review the status of the power plant turbine and associated ancillary equipment. Discussions covered current procurement progress, vendor updates, and confirmation of expected delivery dates. Key risks and potential impacts on the project schedule were also addressed. Attended: Rafael Calderon DCMC German Núñez, GENERA Rafael Pabon, CDM Smith Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group Carlos Palomares CDM Smith.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Procurement Status led by Cynthia Ortiz DCMC reviewed status of all current & future RFP's, also identified gap between NTA to FOMB Submission Package which is much more than the legal review. Gabriel Perez & Rafael Pabon - CDM Smith Franklyn Colmenares - CSA Group Axel Velez - Genera Abraham Velazquez & Gilberto Sucre DCMC
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Contract / Approvals P3 - FOMB Review 49 MW Battery Energy Storage System Installation. Worked on reviewing documents of package in different platforms Procore, Power Advocate and Personal Files to gather the Contract Attachments including using some documents from Cambalache applicable. Met with Sheila Torres DCMC to provide data and input for each attachment.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria E-mail correspondence reading, evaluating and response to BESS & Peakers Programs.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 225 | 562.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Units 1&2 Costa Sur Boilers. Reviewed and evaluated the Genera's archives of the south end of the BESS Platform Location sent by Mike Kuczynski - Sargent & Lundy. Foundation details & Piles will require demolition delaying the project execution & a change order to the project cost, Rigid Inclusions installation will also be affected by the abandoned foundations.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Contract / Approvals P3 - FOMB Review 49 MW Battery Energy Storage System Installation. Led by Cynthia Ortiz DCMC - reviewed documents of package to find out all contract attachments were missing and in different platforms. Would have to recreate all to complete package. Gilberto Sucre - DCMC took the lead to organize this action item. Gabriel Perez - CDM Smith Franklyn Colmenares - CSA Group Francisco Feliu - Genera Sheila Torres & Gilberto Sucre - DCMC
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur - Peakers Demolition - Shared Lessons Learned of Homeca Recycling Performance at Vega Baja to Abraham Velazquez - DCMC in preparation of kick-off on new award.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur studied further the Site Topo and Survey Drawings vs. Demolition Plan identifying additional underground utilities to be relocated in preparation of a new RFI to be submitted to Sargent & Lundy for scope definition. Information was shared with Rafael Barrera DCMC for him to issue formal RFI in Procore.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja evaluation of RFI 004 Existing Underground Tie Line to Luma and response provided by Eduardo Rivera DCMC to Gabriel Perez CDM Smith.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Morning Update calls with Jose Lopez DCMC on Aguirre, and Andres Concepcion DCMC provide feedback on site security measures to be implemented and the page turn performance from the previous date.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences items for Procore submittals for Sargent and Lundy.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on research and support for Procore drawings for Gilberto Sucre (DCMC).
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items to answer users questions.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Financials.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued to work on Procore Financials.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on clearing out budget in Procore for 11855 PW so that I can input the new numbers and cost types.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on research and testing of Action Plans for use of Procurement items for tracking.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of final Procore SOPs before going to publish.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on procurement setup in Procore to test feasibility of housing those activities in the platform.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.75 | 184 | 690 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Discussed with Shellsea Maysonet from SMC a request to generate an inventory report of federally funded RFPs within the Asset Suite system, intended for use by Genera PR’s auditors. Collaborated with Hiram Medero from Genera PR to evaluate and identify the most effective approach for compiling this report, taking into account existing data constraints within the system. Subsequently, submitted a formal request to Hiram detailing the specific fields required to ensure the report meets the audit and compliance needs. Conducted an additional interview with Nyah Medina from DCMC for a candidate for the IT/OT Project Manager role for DCMC aimed at supporting Genera PR’s federally funded initiatives.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Meeting with Carolyn Baez (DCMC) about the purchases and delivery offices materials in the Genera Sites. Review the documentation in Procore about Cambalache, Costa Sur and Vega Baja Site (Health, safety and Security Topics and actions needed. Review the documents received by Paola Arroyo (DCMC) about BESS projects all around. Conference call with Andres Concepcion (DCMC) about Security bridge in Cambalache Genera Site. Make modules about Health and Safety by Genera to ARG (Ida Ramirez) and Teams.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review the Hazwoper materials for next workshop by Nova Southeastern University. Assist to Hazwoper workshop essential for workers involved in hazardous waste operations and emergency response.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.25 | 184 | 414 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria Continued participation in HAZWOPER safety orientation and regulatory compliance coursework provided by Nova Southeastern University, focused on hazardous materials handling requirements to support workplace safety and compliance with applicable federal regulations.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Meeting in person with Paola Arroyo (DCMC) to discuss community engagement meeting at Arecibo, coordination with the invitations, discuss promotional materials, and non profit meetings.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams meeting with Jorge Bracero (Genera PR), D Alexander Gonzalez (DCMC), Paola Arroyo (DCMC) regarding community engagement promotional material and applicability to FEMA funding for the BESS and Peaker project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting in person with Jean Menay (DCMC) to coordinate purchases for BESS and Peaker project site trailers.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Participated in a project coordination meeting with Frances Vallejo (DCMC) and Jesús Cintrón (Genera) to address ongoing procurement challenges affecting the BESS and Peakers projects. The discussion focused on identifying key bottlenecks, including delays in the internal review and approval process, lack of documentation flow between departments, and gaps in supporting materials required for timely procurement execution. Evaluated the impact of these issues on project timelines and compliance with FEMA PA requirements. As part of the discussion, we collaboratively developed a path forward to prevent recurrence of these issues, including establishing clearer internal communication protocols, assigning points of contact for key deliverables, and reinforcing documentation standards across teams. This meeting supported project oversight, enhanced interdepartmental coordination, and reinforced compliance with FEMA-approved scopes and funding requirements.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet -Reviewed the draft contract package for Vega Baja (RFP 4898) to ensure it met applicable grant documentation standards and was complete for submission to P3A and FOMB. Identified missing attachments and project schedules critical to finalizing the contract file. Conducted a detailed review across relevant systems and folders to locate outstanding documents and began compiling them into a single, organized package. Placed particular focus on Attachment A – Scope of Work, verifying that it accurately reflected the mutually agreed to deliverables and performance standards. Confirmed that all content aligned with procurement compliance. This activity supports sound contract administration, enables timely project execution, and contributes to maintaining a complete and audit-ready grant record.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Participated in a coordination call with Axel Vélez and Francisco Feliú (Genera), Gabriel Pérez and Franklyn Colmenares (CDM Smith), and Gilberto Sucre and Cynthia Ortiz (DCMC) to review the draft contract for Vega Baja (RFP 4898). During the discussion, we identified multiple missing attachments and documentation gaps required to complete the contract package. The team reviewed each outstanding item, clarified responsibilities, and assigned follow-up actions to ensure all documents are properly completed, accurate, and consistent with FEMA Public Assistance program requirements. This effort supports timely contract execution, audit readiness, and alignment with procurement and grant compliance standards.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the BESS & Peakers weekly Procurement catch-up call with Franklyn Colmenares, Gabriel Perez, Rafael Pabon, Carlos Palomares (CDM Smith) Axel Velez (Genera) Gilberto Sucre, Abrahan Velazquez, Cynthia Ortiz (DCMC). The purpose of the meeting was to review project-specific procurement timelines, address outstanding issues, and ensure continued alignment between project delivery schedules and procurement milestones. Discussed recent feedback and updates provided by the Procurement Team, including document submission requirements, pending clarifications, and internal review timelines. Collaboratively assessed potential bottlenecks and identified corrective actions to streamline the procurement workflow in support of FEMA-funded construction activities. This coordination supports effective project management, risk mitigation, and ongoing compliance with FEMA grant administration standards.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Reviewed and updated the status of key workstreams and high-priority procurement items in preparation for the BESS & Peakers weekly Procurement catch-up call. This activity ensured that all procurement-related tasks were current, properly tracked, and aligned with project schedules. The updated information supported informed decision-making, interdepartmental coordination, and compliance with FEMA PA construction management and documentation requirements.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued reviewing the draft contract package for Vega Baja (RFP 4898), focusing on verifying Attachment B (Payment Schedule) and Schedule B-1 (Contract Price Breakdown). Confirmed that both documents align with the RFP requirements, the awarded proposal, and any negotiated terms. Ensured consistency across contract documents to support accurate billing, proper cost tracking, and compliance with FEMA Public Assistance grant requirements. This activity contributes to maintaining a complete and audit-ready contract file and facilitates timely project execution.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued reviewing proposals submitted under RFP 235021 for the procurement automation tool to support preparation for the Genera PR evaluation panel meeting. -Conducted an interview with a candidate for the IT/OT Project Manager role for DCMC aimed at supporting Genera PR’s federally funded initiatives. - Participated in the evaluation panel’s introductory meeting alongside María Sanchez, Sulinnette Perez, Axel Velez, and Jesus Cintron from Genera PR, where the group collectively reviewed the submitted proposals and determined coordinating presentations with RFP participants.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I was working on the as built documents to make sure work will be done properly and findings will be successful on tomorrow’s task with Javier Bidot Homeca subcontractor. Meeting with Carirma Sanchez from Homeca for the as built crew arrival verifying documents required and reviewing work to be performed. Made calls to the as built crew arrival but they canceled today’s visit due to an inconvenience. Prepared field for tomorrow’s work. Contacted Generas office to verify with Franklyn Colmenares-CDM Smith for oily water separator drainage but company will arrive tomorrow for the oily water separator clean up. Continue fixing north fence for construction privacy.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) Meeting with Gabriel Morales (DCMC) to clarify the contractor requirements documents and ensure alignment on the scope of work for the project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I reviewed the contractor's responsibilities for the project as outlined in Attachment J. Additionally, I read the following topics: PR OSHA 3030 (PR OSHA Closing Conference Guide), proper use of spill kits, correct handling of construction tools, and functionality of the eye wash station."
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa-BESS Project; During this period, I read various documents on the Procore platform, including: Preliminary Appendix 1-Design Drawing (Genera Yabucoa BESS Control House and Guard Shack Building, Scope of Services-Specification- G-3300 (Pag.113-535/ End section 050538/Document Effective Date: June -20- 2025), and Scope of Work ( Asbestos and Lead testing).
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I continued reading documents on the Procore platform, including: Genera PR Interconnection Application- Yabucoa Power Plant. Additionally, I began updating the Safety presentation for contractors by integrating the requirements outlined in attachment J for Yabucoa BESS Project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Place effective markups on drawings/ Recognize the value of markups as an annotation tool/ Change the visual properties of markups/ Explore stamp workflows/ Create and share a custom tool set and save markups into tool sets.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Navigating and tailoring the interface/ Manipulating, reordering, splitting, and combining documents/ Implementing industry-standard markup tools/ creating and saving custom markups/ Sorting, filtering, and sharing markup data/ Calibrating scales and measurements/ Collaborating with Studio Sessions and Projects.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Create new PDFs/ Combine or split documents/ Reorder, rotate, replace and insert pages within a PDF/ Edit and redact text and content on a PDF/ Format documents for more effective viewing.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria/ AGUIRRE BESS/Create Spaces for organizing punch data/ Build templates for field workflows/ Distribute files to project stakeholders using Revu/ Explain the differences between a Set and a multi-page PDF document/ Share Sets with team members as published files or with Studio Projects.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Reviewed the “Costa Sur Vulnerability Assessment” document with a focus on safety-critical elements related to natural hazards, cybersecurity posture, infrastructure resilience, and emergency response planning. Particular attention was given to Sections on Threat Landscape, Impact Analysis, and Mitigation Strategies, assessing their alignment with OSHA, NFPA, and local Puerto Rico emergency management guidelines. Evaluated how the CARVER methodology was applied to prioritize assets and risks, and cross-checked recommendations for workforce development, interagency coordination, and emergency stockpiling. The goal was to extract actionable insights to reinforce ongoing HSE planning efforts for the Costa Sur BESS project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – Peakers - Supervised the survey and ground-penetrating radar (GPR) activities conducted by Javier E. Bidot & Associates (Luis A. Rivera and Dennis Alicea) and Sargent & Lundy (Abdiel Gonzalez and Gino Sambolin) personnel at the Costa Sur site, as part of the Peakers drainage system review and the foundation design planning for the BESS pipe rack. The site visit included field inspection and coordination to ensure proper adherence to project scope and safety protocols. Verified that all visitors had received the updated 2025 site-specific safety orientation prior to entering the work area.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – Peakers - Continued supervising the survey and ground-penetrating radar (GPR) activities at the Costa Sur site, led by Javier E. Bidot & Associates (Luis A. Rivera and Dennis Alicea) and Sargent & Lundy (Gino Sambolin). Coordination efforts remained focused on ensuring all field operations complied with established safety procedures and project alignment. Field personnel were monitored for adherence to safe equipment handling and communication protocols near energized areas and high-traffic zones. The team continued reviewing underground utility routes and GPR scanning sequences to avoid conflicts with future excavation and construction activities.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the details of Appendix #1 Design Drawing of the demolition to submit comments to Sargent and Lundy and RG Engineering.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the details of Appendix #1 "Design Drawing' to submit comments to Sargent and Lundy and RG Engineering.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the details of Appendix #1 Design Drawing of the control house to submit comments to Sargent and Lundy and RG Engineering.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Luz Ramirez (DCMC) to clarify the contractor requirements documents and ensure alignment on the scope of the project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – Peakers - Supervised the survey and ground-penetrating radar (GPR) activities conducted by Javier E. Bidot & Associates (Luis A. Rivera and Dennis Alicea) and Sargent & Lundy (Abdiel Gonzalez and Gino Sambolin) personnel at the Costa Sur site, as part of the Peakers drainage system review and the foundation design planning for the BESS pipe rack. The site visit included field inspection and coordination to ensure proper adherence to project scope and safety protocols. Verified that all visitors had received the updated 2025 site-specific safety orientation prior to entering the work area.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – Peakers - Continue visit as part of the Peakers drainage system review and the foundation design. The site visit included field inspection and coordination in order to compare with topographic Bidot drawing plan and ensure proper adherence to project scope.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur Review the foundation design planning for the BESS pipe rack. The site visit included field inspection and coordination to ensure proper adherence to project scope and safety protocols.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – Peakers - Continued supervising the survey and ground-penetrating radar (GPR) activities at the Costa Sur site, led by Javier E. Bidot & Associates (Luis A. Rivera and Dennis Alicea) and Sargent & Lundy (Gino Sambolin). Coordination efforts remained focused on ensuring all field operations complied with established safety procedures and project alignment. Field personnel were monitored for adherence to safe equipment handling and communication protocols near energized areas and high-traffic zones. The team continued reviewing underground utility routes and GPR scanning sequences to avoid conflicts with future excavation and construction activities.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre 2. Immediate Spill Response If a spill occurs, the first responder follows these best practices: Alert and secure the area to prevent injury and environmental contamination. Stop the source of the spill, if it can be done safely. Notify the control room and Environmental Health & Safety (EHS) personnel. Retrieve the nearest spill kit and don proper PPE. Contain the spill using absorbent socks or booms to prevent it from spreading, especially toward drains or environmentally sensitive areas (e.g., the nearby Jobos Bay National Estuarine Research Reserve).
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I continued reviewing and developing the following security practices and controls for Spill Kit good practices Bess_Aguirre Project. 3. Clean-Up and Disposal Use absorbent pads, pillows, or granules to clean up the spilled substance. Place all used absorbent materials and contaminated PPE into the labeled disposal bags provided in the kit. Tag and transfer waste to the hazardous waste accumulation area in accordance with EPA and PREQB (Puerto Rico Environmental Quality Board) regulations. 4. Reporting and Restocking Complete a Spill Incident Report with details including the substance spilled, quantity, location, time, and cleanup measures. Submit the report to the EHS department within 24 hours. Ensure the spill kit is restocked immediately after use to maintain readiness. 5. Continuous Improvement Regular spill drills are conducted quarterly to test response times, coordination, and effectiveness. Feedback from these exercises is used to improve response protocols.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I am reading and review Good Practice for Spill Kit Use at Aguirre Power Plant, Puerto Rico. At the Aguirre Power Plant in Puerto Rico, ensuring environmental protection and operational safety is a top priority. As part of our environmental management and emergency response procedures, spill kits are strategically placed throughout the facility, especially near chemical storage areas, fuel handling zones, maintenance shops, and generator areas. We were reviewing and developing the following safety practices and controls. ... 1. Preparedness and Awareness All personnel receive workshop on spill response protocols, including the proper use of spill kits. Each shift has designated personnel trained as spill response leaders, responsible for coordinating response efforts in the event of a chemical or fuel spill. Before any maintenance or fueling operation begins, workers are required to: Inspect the work area for spill kits and verify their contents are complete and accessible. Ensure that PPE (Personal Protective Equipment) is worn, including gloves, goggles, and coveralls. Conduct a pre-task hazard assessment and review the applicable Material Safety Data Sheets (MSDS).
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I was reviewing the Aguirre Laydown Area for TM2500s: The Bess Project Area, The Area A, B, C, and D, and the Green Field. The Area A & B are currently proposed to be utilized for BESS laydown. The Area A have an estimated area (acre) at 5.9, Area B have an estimated area (acre) at 1.6, Area C have an estimated area (acre) at 0.89, The Area D have an estimated area (acre) at 3.7, Estimated Laydown Requirement (6x TM2500s) Area (acre) 1.4 Area A (1&2) appear to be relatively flat according to satellite images and USGS. These areas were previously used for staging areas and contain lumps of concrete and debris. Crushed stone surfacing, 6.0Z/SY Geotextile and Fencing required for site preparation. Area B appears to be remnants of a fuel storage tank and containment area. Overhead distribution lines for Temporary power with pad mounted transformer might be required. Area C contains scattered debris and parts that would have to be cleared if used for laydown. Area D contains scattered debris and parts that would have to be cleared if used for laydown. We have been reviewing all these notes, suggestions, and possible designated areas.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS Project Meeting with S&L, Kuczynski Mike, Robert Muhler, and (CDM Smith), Gabriel Perez, Franklyn Colmenares, (CDMSmith), Andres Concepcion, Gilberto Sucre from DCMC Partners to discuss the BESS IFC design delivery status. Sargent & Lundy does not have a delivery date status for the issue of construction design drawings.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. I had several phone calls with the GWC (RG Engineering) project manager, Jose Segarra, to discuss the project contract requirements and contract progress. Participated in Team Meeting with Sargent & Lundy Staff, Mike Kuczynski, Gilberto Sucre (DCMC), Enrique Laya, CDM Smith, and Angel Alicea Rodríguez Sargent & Lundy to discuss the Phase II Request for Comments to the contract (4339_9510) documents, and the lack of structural details in the design drawings.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRREBESS PROJECT - Participated in a phone call with Basilio Ramos (Sunset Contractors) to discuss the possibility of performed a Job site visit to the Vega Baja Site to Go over any question and or scope of work clarifications for the demolition phase II. The meeting should include an Overview of the Scope of work to ensure that all project participants have a clear understanding of the expectations and requirements, as well as their role in the project’s execution. The Attendees scheduled for this meeting are Gilberto Sucre, Eduardo Rivera, Gilberto Soto (DCMC), and Nelson Soler (CDM Smith).
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE PROJECT. Walk through the Aguirre Complex to identify possible locations for the project sign installation. The information was requested by Gabriel Pérez (CDM Smith) and Gilberto Sucre (DCMC). Various pictures were taken and should be discussed with the Genera-Alexis Cruz.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - We are working on the planning and design of a routine work permit format that can record the risks associated with the tasks, the supervisors in charge of the work, as well as the owners and area managers who authorize tasks that are considered hazardous or non-routine, outlining potential risks and safety precautions. These permits help ensure safety and compliance with regulations.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 - Hurricane Maria - Cambalache Site - The contractual document for the Cambalache project has been reviewed. Annex J (Health, Safety, and Environmental Policies) outlines the safety requirements that must be incorporated into the contractor RGE's safety plan for the Cambalache project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache site- Review of presentations RGE-0002.1 - Temporary mechanical connection to existing transformer T1 and RGE-0013 TEMPORARY POWER CONNECTION FOR CONSTRUCTION OFFICES.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Confirmed on site and developed SOW for upcoming Lead and Asbestos environmental studies for areas in demolition. Provided correspondence to Franklyn Colmenares (CSAGroup)
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Met with Joshua Montanez (Sargent and Lundy) and Luis Damudt (DCMC) to discuss site evaluation and location for the proposed Gas Storage Containers enclosure new structure slab design.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Met with Herminio Arroyo (GeneraPR), Hector Vazquez (LT Automation) and Joshua Montanez (Sargent and Lundy) to discuss PREPA communications project location alternatives to minimize BESS project impact.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Received drawing progress tracker from Designer (Sargent and Lundy) identifying pending information to complete the design. Prepared communication for follow ups.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Managed to consolidate design review meeting notes. Drafted pending actions determined in meeting. Contacted Jean Menay (DCMC) for security access controls protocols in Cambalache plant. Contacted Jose Segarra (RG Engineering) to discuss about containers delivery activity to be suspended. Contacted Luis Duque, DCMC. to discuss Quality Assurance plan draft document.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Prepared a checklist template with Access Control minimum requirements information to manage Plant access and security protocols.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed RGE-00013 submittal regarding temporary power connections plan. Responded via procore and approved plan.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with printed drawing set of 73 drawing to mark all potential change order and potential credit to Genera. The set of 73 drawing include discipline of mechanical, civil, electrical, instrument and structural, several new drawings has been identified in properness of tomorrow meeting with S&L. Provide feedback respond to LUMA RFI 004 related to underground cable from LUMA raise and pole to substation, the cable may be impact if cable size increase and will be required to be change this will depend on a facility study generated by LUMA.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with electrical and instrument drawing to mark all potential change order and credit, notice that instrument drawing number does not match the IFB drawing numbers this issue will be brought to S&L tomorrow meeting. Working with the data entry to the table created with the comments of the IFB versus IFC, making correction on the total of drawing which are 202 drawing released by S&L and which most of drawing are just typical detail drawing. Working with weekly update table in SharePoint folder for project status update with Gilberto Sucre of DCMC. Reviewing submittal send by Howen Lim of Tesla regard of control drawing for Vega Baja site, the submittal was sent back to revise and resubmit due to drawing project number are related to Cambalache project and not Vega Baja site.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working with structural and electrical drawing to mark on printed drawing set of 73 to identify potential change order and potential credit to Genera. Notice on drawing that S&L has change several drawing orders number with new drawing this can create a confusion during the construction project phase. Jaime Pesquera of DCMC was requested to fix the drawing table with comments in comparison of IFB versus IFC drawing.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while station at the Aguirre warehouse prepared a strategic inventory analysis report for Mr. Anthony Vega from Genera PR, consolidating operational data from all warehouse sites. The report examined cross location performance indicators, identified inventory variances, and assessed stock allocation by item types, as well as transaction activity throughout the evaluation period. Special attention was given to identifying accuracy gaps, turnover patterns, and areas of elevated risk that could impact material traceability. Additionally, benchmarking tools were incorporated to assess inventory reliability across locations. The analysis covered inventory areas from BI 101 to BI 145, AC 141 to AC 148, BB 001 to BB 015, CD 035 TO CD 043.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out scheduled ABC cycle count activities across designated inventory zones, with emphasis on verifying item level accuracy. The task involved a structured comparison of physical inventory against system data, with any discrepancies documented and flagged for post count reconciliation. Control sheets were used to capture manual entries, which were later digitized for audit purposes. This process supports consistent inventory accuracy, promotes compliance, and reinforces data integrity. The review during this session covered locations from BI 101 through BI 145.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-held a morning coordination meeting with Mr. Hernan Machado, Milton Flores, and Giovanni Taffanelli from DCMC, to outline the day's operational objectives and inventory related tasks. The conversation focused on progress tracking, documentation procedures, material handling practices, and immediate support needs. The intent was to ensure operational alignment, maintain accountability, and uphold inventory management protocols throughout the day.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane –as part of a variance investigation effort at the Aguirre warehouse, carried out an in-depth review aimed at identifying the root causes behind inventory record inconsistencies. The session focused on tracking the origin of discrepancies by analyzing system activity logs, cross-checking physical stock levels, and comparing them to existing records. Key tasks included the review of material movements, examination of transfer documents, and validation of quantity related adjustments. This assessment covered inventory bins BI 101 through BI 145.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused inventory recount at the Aguirre warehouse to resolve discrepancies identified during the earlier cycle count. The objective was to validate the accuracy of existing inventory records, align physical stock levels with system data, and enhance overall record reliability. The process involved reviewing designated storage zones, manually recounting items, and confirming part numbers, descriptions, and quantities against both printed documentation and digital inventory logs. Additional verification included correcting label placements, addressing bin assignment errors, and ensuring that recorded values reflected actual on hand stock. This session covered inventory bins from BI 101 through BI 145.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a technical staging operation at the Aguirre warehouse to prepare for the upcoming cycle count. The focus was on confirming operational readiness by implementing organized pre-count activities. Key tasks included verifying storage zones according to the system layout, ensuring printed inventory records aligned with documentation, and evaluating environmental conditions that might affect count accuracy. The review encompassed inventory zones BI 101 through BI 145.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Memo Contract Req of Generator Breaker Cambalache.PW-9510 A&E
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updated a Critical Components Tracker using the available information based on the KPI. This KPI will help determine the course of action regarding project amendments with the current status.PW-9510 A&E
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Memo Contract Req of Exhaust Duct Aguirre.PW-9510 A&E
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Memo Contract Requirements of Reduction Attemperators Palo Seco. PW-9510 A&E
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Memo Contract Requirements of Boiler Feed Pumps Aguirre & Costa Sur. PW-9510 A&E
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA Genera Deliverable 11-DR 4339 Preparation for the weekly meeting with CPM, I focused on reviewing Critical Components priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion. PW-9510 A&E.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Meeting and site walkthrough Cambalache - LTA Site Visit coordinate the location of the new communications antenna for Genera PR with Andres Concepcion from DCMC and Herminio Arroyo from Genera PR. Hector Vazquez from LT Automation and Joshua Montañez of Sargent & Lundy.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. 4339_9510 BESS Collaboration with Andres Concepcion (DCMC) for the Cambalache Security Access Minimum Requirements list document for the general contractor RGE.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 – Hurricane Maria. 4339_9510 BESS Coordinate and supervise the relocation activity of the Genera PR office of two trailers.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Create the daily log and record and document the activity on Procore of relocating the Genera PR two trailers office.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Worked on all existing dwg from IFB & IFC to identify any possible change orders for the new drawings that were released on Thursday the 17th and the previous releases for Eduardo Rivera Jordan (DCMC). Today I worked on the Electrical.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Worked on all existing dwg from IFB & IFC to identify any possible change orders for the new drawings that were released on Thursday the 17th and the previous releases for Eduardo Rivera Jordan (DCMC). I kept working on the Electrical & Structural.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Worked on all existing dwg from IFB & IFC to identify any possible change orders for the new drawings that were released on Thursday the 17th and the previous releases for Eduardo Rivera Jordan (DCMC). I kept working on the Structural.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I was working on the as built documents to make sure work will be done properly and findings will be successful on tomorrow’s task with Javier Bidot Homeca subcontractor. Meeting with Carirma Sanchez from Homeca for the as built crew arrival verifying documents required and reviewing work to be performed. Made calls to the as built crew arrival but they canceled today’s visit due to an inconvenience. Prepared field for tomorrow’s work. Contacted Generas office to verify with Gabriel Colmenares-CDM Smith for oily water separator drainage but company will arrive tomorrow for the oily water separator clean up. Continue fixing north fence for construction privacy. Verified blueprints from transformer with Eduardo Rivera (DCMC) verifying the new oily water separator for environmental prevention and were water and oil will be separated.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I was working on the as built documents to make sure work will be done properly and findings will be successful on tomorrow’s task with Javier Bidot Homeca subcontractor. Meeting with Carirma Sanchez from Homeca for the as built crew arrival verifying documents required and reviewing work to be performed. Made calls to the as built crew arrival but they canceled today’s visit due to an inconvenience. Prepared field for tomorrow’s work.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 161.2 | 161.2 | 161.2 | Yes | 146796 | Portosan - Portable Toilet and Containment tray rental - Humacao Yabucoa
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BB001 to BB015
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BB001 to BB015
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BB001 to BB015
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations BB001 to BB015
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BB001 to BB015
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC 01 041 000 to AC 01 058 000.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane – Maria - at Costa Sur conducted review, organization, and filing of operational reports and inventory records to ensure accurate documentation and easy retrieval for internal audits and logistics coordination.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC 01 041 000 to AC 01 058 000.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC 01 041 000 to AC 01 058 000.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1555 and 1556 from locations CD035 to CD043 for a total of 79 units.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CD035 to CD043 to begin the cycle counts.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Continuing efforts in the development of the Excel spreadsheet to track tasks related to the inventory project at the Cambalache warehouse. Key information has been added and updated to more accurately reflect the progress and needs of the project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CD035 to CD043 Cycle Count List # 1553 and 1557.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the internal modules to update the development and inquiries of users in the Procore Platform looking to maintain tracking of performance as Owner's Representative.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Jobos Peakers Procurement RFP & RFQ ensure documents were created, reviewed, and stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team/Various Projects -Incoming Daily Data for review and process.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Review of all Peakers Projects Users Access/Palo Seco BESS Procurement RFP & RFQ ensure documents were created, reviewed, and stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Configure potential new settings in Procore with the onboarding of consulting firm TRC as the QA/QC on Drawings and other technical project documents: work on suggestions for Procore procedures on uploading/approving and sharing with Owner.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Continue research and reviewing the Buy American Act which is contractual and funding requirement for the completion of projects. Review articles and requirements depending on funding types.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the topics discussed on meeting with Design Team about the Submittal Response Status by design team compared with Procore options to respond on submittals. Scheduling meeting for next week with field staff to discuss and compare both responding methods and outputs.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the actual Drawings Uploading procedure to get consultant TRC onboard with the drawings approval current system.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Documents Tool to go over Pre-Construction documents such as Procurement Process and equipment specs and orders.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Chandan Dash (Siemens) to follow up on the ongoing Submittal Packages issue. User is still unable to upload documentation in the form of Packages. Convenient for several related documents and specs at the same time.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review requirements prior to the uploading of technical documentation such as Specifications and Drawings in terms of approval procedures: determining if Submittals Tool would be the best practice to pass over the approval procedures for record.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review troubleshooting on the Submmitals tool for Chandan Dash (Siemens) and other colleagues that are not allowed to submit Submittal Packages (multiple specifications and documentation) to the Costa Sur Peakers Project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Test different permission levels on a "Dummy" user to recreate current issues with external users with uploading and sharing documentation for review. Currently working on Costa Sur Peakers Submittals Issue.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work with the gathering of final versions for SOP to be published and replaced at the SOP Folders across projects, in order to provide users the most recent updated files. 14 out of 16 Project Management Tools have a complete SOP; other 2 are not being used yet.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR4339: Continue updating invoices from vendor Dueñas Trailer in the Excel Expense Tracker and revise the site location information for the trailers. Adding more vendors (Walmart, Home Depot, Office Depot), Scanning the DCMC Equipment Check Out Form completed for the iPad pencils, iPad, printers, and monitors by Andres Concepcion, Abraham Velazquez, Jose Lopez (DCMC).
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting call with Genera PR team, Jorge Bracero, to outline the work plan for the rest of the week. This task includes: setting up the logistics to present the action plan with the nonprofits and going over the to-do list for the rest of this week.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Telephone meeting with Yauco City Assistant Rodney Torres, in charge of establishing community relations in the south with the purpose of beginning work on the possibility of community agreements in the south near the Aguirre plant to educate about the BESS project and Peakers.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Create a record of the upcoming community meeting on the BESS system in Arecibo. These tasks included an account on an event management platform in Forms Office and Google Forms or similar), designing a form with the necessary fields (name, contact, organization, etc.), and titled it "Community Meeting on the BESS Project in Arecibo", adding key event information such as date, time, location, and topics to be discussed, as well as a description inviting the community to participate and learn more about the project, Carry out internal tests by sending the form to members of the organizing team to verify functionality, clarity and registration flow, adjusting according to comments before its official publication.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Workshop meeting with the Genera PR team, Jorge Bracero and Rafael Rodríguez Ema in order to be able to execute communications campaigns aimed at the communities in which we will be inviting them to the community meetings on BESS and Peakers. This task included taking notes and clarifying doubts. The workshop was on the platform go.botmaker.com
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Update meeting between Jorge Bracero and the Genera PR team to define the logistics related to the sending of invitations to communities interested in participating in community meetings about the BESS project in Arecibo. During the meeting, topics such as the methods of distribution of the call (mail, social networks or direct contact), the validation of the regional calendar of meetings, the follow-up of previously assigned pending tasks and the final verification of the list of non-profit organizations linked to the project will be addressed. The objective is to consolidate an operational plan that ensures effective and representative participation in each community served by Genera PR.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. End reading of least six technical and regulatory documents related to preventive measures that Genera PR implements to mitigate fire risks in its energy storage systems (BESS), including Fire Protection Engineering and UL 9540A Interpretation Report, Destructive Fire Test and Fire Modeling Report, Industrial Lithium-Ion Battery Emergency Response Guide, MEGAPACK SAFETY OVERVIEW, MEGAPACK 2 XL DATASHEET, as well as specialized articles on thermal risks, suppression systems and battery management protocols with the aim of extracting best practices, evaluating failure scenarios and adapting these measures to the local context in Puerto Rico, generating as a result a document that serves as a guide for the communication pieces related to the BESS project in the communities
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with the DCMC Partners team Frances Vallejo and D'Alexzander Gonzalez and the Genera PR team, Jorge Bracero, with the purpose of clarifying doubts about the utilities that can be acquired in order to guide the community about the BESS and Peakers project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Evaluate a new quote together with the Genera PR team, Jorge Bracero, to integrate the banners on the sites with the new prices. This task included checking options related to banners, pricing, and verifying that the information was complete.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Evaluate the proposal presented by the March of Dimes with the objective of identifying strategic opportunities for Genera PR to generate a significant impact in vulnerable communities, particularly in those municipalities where Genera has the BESS and Peakers project such as Arecibo and San Juan. The analysis involves thoroughly reviewing the content of the proposal, understanding its objectives, geographical areas of intervention and target population, in order to explore models of community outreach such as corporate volunteering, participation in emblematic events such as the March for Babies, support in educational talks on energy security and child health, and collaboration in awareness campaigns.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Meeting with Frances Vallejo, DCMC Partners, to discuss the status of my projects. As part of this meeting, details were discussed on quotation status for the purchase of portable batteries, logistics of visiting Aguirre, list of non-profit organizations to support the BESS project, status of Kroma banners, notification from the mayor of Vega Baja
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Finalize documentation related to non-profit organizations to present to the Genera team, Jorge Bracero. These tasks included: Including final organizations as well as general recommendations for next steps that we can implement.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Baez-Nieves, Carolyn | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 139 | 69.5 | 139 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR4339: Updated invoices from vendor Dueñas Trailer in the Excel Expense Tracker and revised the site location information for the trailers.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 5) Review Lemoine Quality Control/Assurance Plan, Inspections plan, Submittal Stamp Cover Sheet Form, Checklist for Submittals Review and Concrete Log to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – AGUIRRE BESS PROJECT - Conducted an in-depth review of 31 pages of the Battery Energy Storage System (BESS) General Work Contract (Specification G-3400, Revision A), focusing on scope definition, role assignments, and compliance with technical standards. The extended analysis supported risk mitigation and ensured alignment with project execution strategies
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 33 pages were examined.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 7 pages were examined.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – AGUIRRE BESS PROJECT - Analyzed six pages of the Battery Energy Storage System (BESS) General Work Contract (Specification G-3400, Revision A) to verify alignment between technical requirements and project scope. The review emphasized clarity in task distribution and compliance with contractual standards, contributing to effective project management.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report considering a data in projection schedule using Primavera reports templates in acceptable or not acceptable comparative in baseline schedule of values (SOV) demolition existing mechanical equipment and tanks, Existing Transformer and electrical equipment, Existing foundations, containments, sumps, privacy walls, fences, paving, Demolition and Relocation of Existing of Piping Existing underground utilities and stormwater piping, Incidental items as identified on the design drawings and items conflicting with the proposed work, in BESS area the electrical grounding cables, duct banks to point of interconnection, manholes and system to point of interconnection, the civil and structural work with earthwork, new aggregates to fill material, asphalt for finish surfacing, new guard rail, stormwater underground system, structural concrete works for construction BESS Foundations which include Switchgear, Control House, Grounding Transformer and Ramps, GSU Transformer Foundation, tesla maintenance foundation, GSU transformer framing, stone columns foundation system for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report cost and cost per unit, 2WLA, summary schedule updated, milestone updated, scurve graph, concerns in acceptable or not acceptable comparative in baseline reports, delays reports for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering data report of delay risk, meet regulations, formats of report for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering data report of man hours, resources, planned start dates, planned finish dates for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 5) Review Lemoine Quality Control/Assurance Plan, Inspections plan, Concrete Pre pour checklists to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 134 | 268 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 5) Review Lemoine Quality Control/Assurance Plan, Inspections plan, Sample Commitment Change Order, Extra Work Authorization Master and Weekly Internal Operations Meetings to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 134 | 402 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DAY 5) Review Lemoine Quality Control/Assurance Plan, Inspections plan, RFI Log, Sample Change Request and Sample Change Order to create a new DCMC Quality Control Plan for 4339_9510 BESS-Cambalache project
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewing updates to the BESS and Peakers project schedule and designing a streamlined method for integrating data into Power BI, with the goal of enhancing visual representation of project progress and identifying potential risks.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Conducted a technical assessment of RG Engineering’s contractor proposal for the civil and structural scope at the Yabucoa BESS site. Focus was placed on verifying constructability, compliance with project specifications, and alignment with site-specific constraints.
2025-07-23 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Collecting and evaluating BESS project schedule updates to optimize the visual depiction of progress and potential risks, ensuring data is more accessible and understandable.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 377.95 | 377.95 | 377.95 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Equipment necessary for Meeting and Communication in Costa Sur.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 377.95 | 377.95 | 377.95 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Equipment necessary for Meeting and Communication in Cambalache.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 377.95 | 377.95 | 377.95 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Equipment necessary for Meeting and Communication in Vega Baja.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 377.75 | 377.75 | 377.75 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Equipment necessary for Meeting and Communication in Yabucoa.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 377.75 | 377.75 | 377.75 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Equipment necessary for Meeting and Communication in Aguirre.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Gilberto Sucre, Frances Vallejo, Ada Diaz, Mark Merritt, Jack Darnall, Foster Veazey and Mike Merritt, DCMC. Discussed update on project, job offers, PROCORE, logistics, trailer set-up, safety, schedule for locations and program goals.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Worked on Internal Review Checklist 1. Define the Scope: Review: emails, project proposals, reports, memos, etc. Time frame: Emails/documents between specific dates. 2. Objectives of the Review Ensure accuracy and consistency Identify miscommunication or missing information Detect sensitive or non-compliant language 3. Organize Documents Sort by project, sender/recipient, or topic Use folders or document management tools for categorization Create a document index or audit log. 4. Review Emails Look for Incomplete threads or missed responses Confidentiality and appropriateness of content 5. Review Project Documents Check for: Factual consistency across documents Clarity of deliverables, deadlines, and roles Proper formatting and document standards 6. Flag Issues Highlight discrepancies, unclear communication, or risks Use comments or annotations. 7. Summarize Findings: Create a report or summary including: Major findings or inconsistencies Recommended actions 8. Take Action Share the review summary with relevant stakeholders Schedule a follow-up review if needed.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Conducted an internal review of emails and project documents, for a structured approach that ensures thoroughness, accuracy, and that every aspect of the project aligns with legal and regulatory frameworks.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Bi-Weekly Siemens Electric Status Meeting Participated in the bi-weekly status meeting with Siemens Electric to review the status of equipment procurement, layout coordination, and overall project schedule. Discussions also included preliminary review of contract verbiage and clarification of key terms. The team aligned on upcoming milestones and ongoing action items to ensure progress remains on track. Attended the meeting: Rafael Calderon DCMC Raissa Borges Almodovar- DCMC Rafael Barrera- DCMC Carlos De Jesus - DCMC Gilberto Sucre DCMC Frances Vallejo Rosich DCMC.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence Review, Invites for Meetings scheduled for Friday and Monday, Request for documentation for completion of FOMB Package for Vega Baja.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting led by Frances Vallejo - DCMC * Staffing Update * BESS Update * Performance Appraisals Meeting * Wifi alternates at Project Sites * PMO Peakers Candidates * IFC Page Turns with S & L * FOMB Approval Status Mark Merritt, Mike Merritt, Frances Vallejo, Ada Diaz, Foster Veazey, Jack Darnell & Gilberto Sucre - DCMC.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 225 | 393.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Management Oversights on all subjects: * Email Correspondence * PA's * FOMB Package Preparation * BESS Needs * Homeca Lessons Learned. * Costa Sur - Peakers Drawings Review * Organize Agenda and Action Items
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Executive Meeting with BESS Team with Jesus Cintron - Genera, Gabriel Perez CDM Smith, Franklyn Colmenares, and Gilberto Sucre - DCMC Partners. PM/CM highlighted the needs from GENERA HOMECA Contract / Change Order Resolution to close out Vega Baja. TRC Contract resolution Stantec Contract Resolution Beta Electric - MPT Proposal Approval for Vega Baja Payments to Soil Testing Companies DCMC to be the PMO for TRC role in Program.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore + S&L Submittal Responses alignment meeting with Lauren Wells, Andres Concepcion, Luis Duque and Gilberto Sucre - DCMC. Agreed to the responses to be used in Procore, will review with Ada Diaz - DCMC Legal prior to implementation.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja IFC drawings Page Turn Meeting at Sargent & Lundy's Office with ARG Ceres - GWC for the 49MW BESS Installation Project: * Fire Protection Consultant Presentation - MEGA Packs Specifics * Discussed Tracker listing & responsible party. * Potable Water, Sanitary Sewer & Storm Water * Demolition Drawings * Foundation Design status * New GSU and Fire Protection Tank * Incomplete Electrical Design * Next Steps.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Weekly Construction Meeting led by Rafael Barrera - DCMC. Contract Update was provided. Highlighted Activities for the week IFC Page Turn, Running water resolution and topo activities. Important Submittal from RGE - on Rigid Inclusions - Morris Shea. Foundation Drawing for Boiler Area found. Emergency Generator Cut-Sheet for Rigging Plan. Vulnerability Study to be shared with Project Team. Demolition Markup and RFI to S&L. Jose Segarra - RG Engineering. Gabriel Perez - CDM Smith. Gilberto Sucre & Jean Menay- DCMC . Wilfredo Sierra - Sargent & Lundy.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-BESS and Peaker's Project Schedule & Budget Meeting. Attendees were Foster Veazey (Lemoine), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Carlos Palomares (CDM Smith) .
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine)
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Procurement items.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued review of Project Financial workflow from Raissa Borges (DCMC) and started applying an overlay of where Procore fits in.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore procurement items for researching putting items in the system.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Andres Concepcion (DCMC), Luis Duque (DCMC), Luis Roman (DCMC), Gilberto Sucre (DCMC) to discuss Procore submittal responses.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy and Lauren Jones (Procore) to discuss update of SOW and path forward for working sessions and upcoming workshop to Procore Financials.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of Project Financial workflow from Raissa Borges (DCMC).
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating distribution lists for Franklyn Colmenares (CSA).
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks list for open items for the Procore team.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Admin items for tracking user certification completions and usage in the tools.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on coordination for Procore meetings upcoming next week.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for testing out how to manage drawings in an approval format way.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financials.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items related to meeting coordination and creation of new submittal responses.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Expense |  | 199.58 | 199.58 | 199.58 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Boots receipt, claiming cost of safety boots only ($179 plus tax $20.58) Total $199.58.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued reviewing the draft contract package for Vega Baja (RFP 4898), focusing on verifying Attachments E-M. Confirmed that the documents align with the RFP requirements, the awarded proposal, and any negotiated terms. Ensured consistency across contract documents to support accurate billing, proper cost tracking, and compliance with FEMA Public Assistance grant requirements. This activity contributes to maintaining a complete and audit-ready contract file and facilitates timely project execution.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Continuing the Hazwoper Modules to learn policies, practices, and procedures to ensure safety when handling hazardous substances.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review documents in Procore about Costa Sur Genera Site, topics: Security and Health and Safety. Meeting with RGE (Contractor) Jose Segarra and Team, DCMC Rafael Barrera and teams, about Costa Sur Genera Project Status, when start the projects and all construction topics. Purchase in Best Buy office equipment necessary for trailers in Cambalache, Vega Baja, Costa Sur, Aguirre and Yabucoa Genera Sites.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Participated in Teams meeting for the PMO Catch up call to update on staffing at the sites, progress for candidates regarding Peaker's managers role, BESS project status and material and equipment purchases. Attendees: Michael Merritt (DCMC), Mark Merritt (DCMC) and other DCMC participants.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146796 | Genera PR - Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Create excel sheet with invoices for materials and equipment and its suppliers.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Formulation-Meetings & Coordination | Direct-PA | Meetings/coordination necessary to formulate project | Time | 3.5 | 184 | 644 | 184 | Yes | 146796 | Genera PR- Deliverable 11 ¦ DR 4339 - Hurricane Maria - Attended Aguirre site for the Enacts visit with the community engagement team of Genera PR. Attendees: Paola Arroyo (DCMC) and Jorge Bracero (Genera)
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended the Costa Sur Weekly Meeting with the site manager and site staff to discuss project progress. Attendees: Rafael Barrera (DCMC) and other DCMC participants.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued reviewing the draft contract package for Vega Baja (RFP 4898), focusing on verifying Attachment D (Contractor Unit Pricing). Confirmed that the documents align with the RFP requirements, the awarded proposal, and any negotiated terms. Ensured consistency across contract documents to support accurate billing, proper cost tracking, and compliance with FEMA Public Assistance grant requirements. This activity contributes to maintaining a complete and audit-ready contract file and facilitates timely project execution.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued reviewing the draft contract package for Vega Baja (RFP 4898), focusing on verifying Attachments N-R. Confirmed that the documents align with the RFP requirements, the awarded proposal, and any negotiated terms. Ensured consistency across contract documents to support accurate billing, proper cost tracking, and compliance with FEMA Public Assistance grant requirements. This activity contributes to maintaining a complete and audit-ready contract file and facilitates timely project execution.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I Continue working on the as built supervising Javier Bidot- HOMECA subcontractor on the as built work to be performed verifying all areas were covered to close down the report. Reverified documents making sure the blueprint provided by Eduardo Rivera (DCMC) was covered with all areas to verify.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I reviewed several key topics from OSHA and the EPA, including the following: -Aerial Lifts (29 CFR 1926.453) Types of lifts, care and inspection procedures, and safe operation guidelines. -Respirable Crystalline Silica in Construction Workplaces (29 CFR 1926.1153) Sources of crystalline silica in common construction materials, associated health hazards, protective measures for employees, housekeeping practices, written exposure control plans, the role of the competent person, and medical surveillance requirements. -Asbestos (29 CFR 1926.1101) A guide to hazard awareness and recommended control methods, including worker protection strategies, exposure control procedures, medical monitoring, demolition protocols, and requirements.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I examined several of the most frequently cited OSHA standards in the construction industry, including: Fall Protection (29 CFR 1926.501), Scaffolding (29 CFR 1926.451), and Eye and Face Protection (29 CFR 1926.102).
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) Meeting with Gabriel Morales (DCMC) to discuss and define the requirements for the documents that must be generated daily as part of the project.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa-BESS Project; Throughout this period, continue examining OSHA construction standards to integrate the demolition section into the Contractor Safety presentation for the Yabucoa BESS Project. Additionally, continue reviewing the Scope of Services – Specification G-3300(159-535/ End section 076000-5/Document Effective Date: June -20- 2025).
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS-Upload, view, and mark up Drawings/ Upload, view, manage, and create submittals from Specifications / Create, import, respond to, close, revise, and distribute Submittals/ Create and close RFIs/ View and use Procore Drive to manage the Schedule/ Create, view, and use your mobile device for Meetings / Upload, view, and use your mobile device for Photos/ Add a new type, create, respond to, and change the status of a Correspondence item/Create, respond to, review, and close Punch List items/ Create, request a signature, and sign a T&M Ticket/ Assign permissions for the various roles on the project
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in the Weekly Construction Meeting for the Costa Sur BESS project. In this meeting, the main discussion subject was the rigging plan for the Tesla Batteries installations. There were also follow-up items, including the Safety Plan, Work Plan, Quality Plan, and Coordination between the awarded General Civil Contractor, RG Engineering, and the DCMC Construction Team. Representing RG Engineering was José Auli (RGE). It was also pointed out in the meeting that the need for the Surveyor to be on site to conduct an As-Built survey at the proposed location was necessary, as the General-PR Plant management staff had informed them of the presence of concrete piles under the proposed concrete platforms. Additionally, to identify existing utilities and the scope of work required for these utilities to be removed or relocated. The Sargent & Lundy personnel at the meeting, Wilson Alicea, informed the group of the recent site visit by the design team regarding the relocation of the existing utilities, and that the information would be shared later.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Jose Lopez (DCMC), Carlos López (DCMC), and Luis Moctezuma (DCMC) to discuss project two week look ahead schedule and improve communication across the site team.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS-Review annotation data in the Markups List/ Manage and filter data to show exactly what you need/ Communicate with replies and status fields/ Create custom columns in the Markups List Export markup data to a sharable summary.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS-Setting up a Studio Project/ Document Setup and Processing/ Adding markups in real-time from Bluebeam Studio in Revu/ Collaborating from computer in Aguirre BESS using Bluebeam Cloud/ Accessing and working on Sessions in the field with Bluebeam Cloud
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Focused on reviewing the mitigation strategies outlined in the “Costa Sur Vulnerability Assessment,” with emphasis on interagency coordination, emergency response roles, and risk communication protocols. Assessed whether the proposed actions address cascading failures between utility, communication, and safety systems. Identified key takeaways relevant to the BESS project, particularly related to staging of emergency supplies, staff workshop and coordination with external agencies. Recommendations were flagged for possible inclusion in site-specific safety plans and onboarding materials for contractors.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Conducted an extended analysis of the “Costa Sur Vulnerability Assessment” with a focus on evaluating the site's critical systems and their exposure to potential threats, including hurricanes, seismic events, utility disruptions, and cyber intrusions. Special attention was given to the document's prioritization of physical assets, such as switchgear rooms, energy storage units, and control systems, using the CARVER matrix scoring model. Reviewed recommendations related to redundancy planning, emergency communications, and response drills. Mapped findings to BESS infrastructure to assess the applicability of identified vulnerabilities. Documented suggestions for integrating key elements into the Costa Sur HSE framework and emergency preparedness strategies.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- DCMC Site team lead by DCMC Rafael Barrera internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's. Continued on-site supervision of the survey and ground-penetrating radar (GPR) activities led by Javier E. Bidot & Associates (Luis A. Rivera and Dennis Alicea) at the Costa Sur project. The extended session focused on verifying safe work practices as the team advanced into more congested and sensitive areas near existing underground utilities. Ensured that exclusion zones were properly delineated, and reinforced communication protocols between survey crews and DCMC field coordination staff. Safety checks were conducted to confirm use of PPE, equipment stabilization, and real-time data logging procedures. Close attention was given to scan overlaps and coverage validation to minimize the risk of undetected utility conflicts.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Site Meeting with Jean Pierre Menay (DCMC) to receive and organize office supplies such as Tv's, Tv; mount and cameras necessary for the DCMC Partners office.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Luz Ramirez (DCMC) to discuss and define the required documents that need to be generated daily as part of the project requirements.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.25 | 167 | 542.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting with S&L Organizer Wifredo Sierra and Mike Kuczynski, DCMC Gilberto Sucre and Eduardo Rivera, and Felix Anastacio of Felix Fire Sprinkler Design - Meeting to discuss Vega Baja site drawing review with Fire Protection contractor company to go thru complete design of BESS fire protection system, meeting also was discussing the structural, civil, mechanical and electrical drawing. Also was discuss a design tracker regard of Vega Baja site.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11¦ DR4339 Travel time from Sargent & Lundy Office to Yabucoa site after assist the meeting to review the BESS Project Issue for construction drawings for the Vega Baja site with ARG Engineering, DCMC Partners, Sargent & Lundy and CDM Smith team.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11¦ DR4339 Travel time from Yabucoa site to Sargent & Lundy Office to assist the meeting to review the BESS Project Issue for construction drawings for the Vega Baja site with ARG Engineering, DCMC Partners, Sargent & Lundy and CDM Smith team.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the details of Appendix #1 Design Drawing to submit comments to Sargent and Lundy and RG Engineering.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- Bidot personnel (Luis A. Rivera and Dennis Alicea) continue with the work of detecting and identifying underground utility lines. This effort is essential to ensure that all existing buried infrastructure within the project area is accurately located and documented before further construction activities proceed. Their findings will be compiled and shared with the RGE project contractor to support safe excavation and avoid potential conflicts with existing utilities. This step is critical to minimizing risk, preventing service disruptions, and maintaining compliance with safety regulations. The information gathered by Bidot will be integrated into the project plans and used to guide the next phases of work on site.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- Preparation for the upcoming project meeting, reviewed the agenda in detail to ensure all relevant points are covered. The primary focus will be to follow up on existing action items and to address any new business that may impact the project's timeline or deliverables.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- Review communication between project stakeholders to ensure consistency in reported observations and previously documented conditions. Relevant documents—such as site surveys, inspection reports, and utility maps—were carefully reviewed and compared against the latest available information to identify any discrepancies or areas requiring clarification. The purpose of this process is to maintain accurate and up-to-date records, which are critical for informed decision-making and effective coordination with contractors and other project participants. Any inconsistencies or missing information identified during this verification have been flagged for follow-up to ensure a complete understanding of current site conditions before proceeding with the next steps of the project.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- As part of the ongoing coordination efforts for the RGE project, personnel from Bidot (Luis A. Rivera and Dennis Alicea) visited the project site to continue the work of detecting and identifying underground utility lines. This effort is essential to ensure that all existing buried infrastructure within the project area is accurately located and documented before further construction activities proceed. During the visit, the Bidot team (Luis A. Rivera and Dennis Alicea) utilized specialized equipment to scan and trace underground lines. Their findings will be compiled and shared with the RGE project contractor to support safe excavation and avoid potential conflicts with existing utilities. This step is critical to minimizing risk, preventing service disruptions, and maintaining compliance with safety regulations. The information gathered by Bidot will be integrated into the project plans and used to guide the next phases of work on site.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- To ensure a productive discussion, I have compiled status updates on all assigned tasks, identifying any pending items and outlining progress made since the last meeting. I've also coordinated with team members to gather their input and any concerns they may have regarding current action items. For new items section of the meeting, we discuss a list of potential topics that may require team attention, including any recent developments, risk factors, or changes in project scope. Supporting documentation and data have been organized in advance to facilitate informed decision-making.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Stabilized Construction Entrance: A gravel pad was installed at the site entrance to minimize the tracking of sediment onto public roads. Temporary Sediment Basins and Check Dams: Where applicable, basins were used to capture runoff and allow sediment to settle before discharge. Diversion Berms and Swales: Constructed to direct clean runoff away from disturbed areas and into vegetated buffers or control structures. 3. Ground Cover and Stabilization 4. Inspection and Maintenance Trained personnel conduct weekly inspections and after significant rain events (>0.5 inches). All erosion and sediment controls are checked for integrity and effectiveness. Sediment removal is performed when accumulation exceeds one-third the height of the barrier. A log of inspections and corrective actions is maintained on-site and available for review by regulators. 5. Stormwater Management Integration Permanent stormwater management features are being integrated into the BESS site design to reduce post-construction runoff and promote infiltration.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in the Weekly Construction Meeting for the Costa Sur BESS project. In this meeting, the main discussion subject was the rigging plan for the Tesla Batteries installations. There were also follow-up items, including the Safety Plan, Work Plan, Quality Plan, and Coordination between the awarded General Civil Contractor, RG Eng erring, and the DCMC Construction Team. The meeting was held by Rafael Vernadeen (DCMC). Representing RG Engineering was engineering José Auli (RGE). It was also pointed out in the meeting that the need for the Surveyor to be on site to conduct an As-Built survey at the proposed location was necessary, as the General-PR Plant management staff had informed them of the presence of concrete piles under the proposed concrete platforms. Additionally, to identify existing utilities and the scope of work required for these utilities to be removed or relocated. The Sargent & Lundy personnel at the meeting, Wilson Alicea, informed the group of the recent site visit by the design team regarding the relocation of the existing utilities, and that the information would be shared later.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning staff meeting with Aguirre Construction management staff: Sunem Martínez, Carlos R. López, and Luis A. Moctezuma (DCMC). The agenda items included issues related to construction drawings delivery status, general work contractor signage, and notice to proceed schedule dates, as well as general safety topics.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Reading and review the OSHA 1926.201 For Signaling. § 1926.201 Signaling. (a) Flaggers. Signaling by flaggers and the use of flaggers, including warning garments worn by flaggers, shall conform to Part 6 of the MUTCD (incorporated by reference, see § 1926.6). (b) Crane and hoist signals. Regulations for crane and hoist signaling will be found in applicable American National Standards Institute standards.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria I am reviewing the NFPA National Electrical Code they applicate for safety electricals work in Bess_Aguirre.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Evaluate the Implementation of Sedimentation Control Plan for the BESS Project at Aguirre Power Plant Project Overview The BESS project at the Aguirre Power Plant involves the construction of a Battery Energy Storage System within the existing facility located in Salinas, Puerto Rico. The project's scope includes earthwork activities such as excavation, grading, and the installation of foundations and utility conduits. Objective The purpose of the sedimentation control plan is to prevent soil erosion and the offsite transport of sediment-laden runoff into adjacent water bodies and stormwater systems. Control Plan Implementation 1. Site Assessment and Planning Prior to the start of construction, a comprehensive assessment of the site’s topography, soil type, drainage patterns, and weather conditions was conducted. 2. Installation of Erosion and Sediment Control Measures A combination of best management practices (BMPs) was selected and implemented at the site, including: Silt Fences and Wattles: Installed along the perimeter of the disturbed area and downslope of excavation zones to intercept sediment in runoff.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. I had several phone calls with the GWC (RG Engineering) project manager, Raul Berrios, to follow up on the project contract requirements and the progress of contract signage. The contract has been turned over to Genera PR and so forwarded to P3A (Public-Private Partnership) for evaluation and approval. Participated in a Teams Meeting with Sargent & Lundy Staff, Robert D. Molner, Gilberto Sucre (DCMC), Enrique Laya, CDM Smith, and Angel Alicea Rodríguez -Sargent & Lundy to discuss the Phase II Request for Comments to the contract (4339_9510) documents. Also, a new proposed Value Engineering Design Option was discussed for the Mega Packs' proposed foundation concrete slabs. Sargent and Lundy will evaluate and share their comments at a later meeting.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Meeting with PREPA/Genera-PR regarding the IT/OT projects that have been coordinated by the PREPA Data and communications management team that will have to be coordinated with the BESS projects to avoid a clash with the proposed BESS layout design. The participants of the meeting are Gabriel Perez (CDM Smith), Franklyn Colmenares (CSA), Mike Kuczynski, Vincent Skochdopole (Sargent and Lundy), Hector Vazquez, Carlos Irizarry from LT Advance, and Andres Concepcion, Gilberto Sucre (DCMC). The Aguirre monopole and control room proposed location by LT Advance is still under evaluation by Sargent and Lundy, and the results of the assessment will be shared by Monday. Regarding the Cambalache Site, there are no issues with the new proposed location. Sargent and Lundy presented an option regarding the area for the Costa Sur Site, which will be evaluated in person during a job site visit by LT Advance scheduled for next Tuesday.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in the Weekly Construction Meeting for the Costa Sur BESS project. In this meeting, the main discussion subject was the rigging plan for the Tesla battery installations. There were also follow-up items, including the Safety Plan, Work Plan, Quality Plan, and Coordination between the awarded General Civil Contractor, RG Engineering, and the DCMC Construction Team. Representing RG Engineering was José Auli (RGE). It was also recognized by Gilberto Sucre (DCMC) during the meeting that the Surveyor's presence on site was necessary to conduct an As-Built survey at the proposed location, as the General-PR Plant management staff had informed them of the presence of concrete piles beneath the proposed concrete platforms. Additionally, identify existing utilities and the scope of work required to remove or relocate them. The Sargent & Lundy personnel at the meeting, Wilson Alicea, informed the group of the recent site visit by the design team regarding the relocation of the existing utilities, and that Sargent and Lundy will share the information with the team later.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsabilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning staff meeting with Aguirre Construction management staff: Sunem Martínez, Carlos R. López, and Luis A. Moctezuma (DCMC). The agenda items included issues related to the delivery status of construction drawings, general work contractor signage, and notice to proceed schedule dates, as well as general safety topics.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Documentation requirements for both the project and the contractor regarding water and discharge protection and emergency site management are being coordinated with Roseanne Perez (GENERA). A meeting has been scheduled for early next week.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - We are working on the planning and design of a routine work permit format that can record the risks associated with the tasks, the supervisors in charge of the work, as well as the owners and area managers who authorize said tasks. Permits will ensure that workers are fully aware of the risks involved in their jobs and provide them with the necessary precautions and preparation to minimize them.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Work is ongoing in the planning and design of a routine work permit format. This format aims to systematically record: the risks associated with each task, the supervisors responsible for executing the work, and the owners and area managers who provide authorization for the tasks.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache site- Working conditions were established with Andres Concepcion (DCMC) for the requirements and permits for the entry of contractors to the Cambalache site to ensure safety and compliance with local regulations.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Meeting for the coordination of the PREPA / Genera / LT Automation: Coordination with IT/OT Communication Building / Monopole project with Hector Vazquez (LT Automation), Gabriel Perez (CDM Smith) and Mike Kuczynski (Sargent and Lundy) to coordinate PREPA communication project in Cambalache in relation with BESS project.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - (1) Managed coordination emails for Carlos Lopez (CW Legal) and Gabriel Perez (CDMSmith) to determine environmental SOW services to be contracted for the project. (2) Received Issued for Construction drawings tracker from Sargent and Lundy (Mike Kuscinsky) and evaluated it to share it and forward it to General Contractor (RG Engineering - Jose Segarra).
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed project demolition plan and scope of work to create drawing markups for review of the Designer (Sargent and Lundy) and they can be able to issue a final demolition plan drawing.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Recieved mechanical drawings (60 pages) update from Sargent and Lundy (Ivette Miranda). Reviewed documents and ensured information is not missing.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed the GeneraPR report for Cambalache Vulnerability plan. Studied the plan to incorporate it in the Safety considerations of the project.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Met with Lauren Wells, Luis Roman, Gilberto Sucre, Luis Duque (DCMC Partners) to review the submittal response process. This process will be proposed to GeneraPR to align with the project designer (Sargent and Lundy) submittal review responses and guarantee an alignment.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Continued the review of the project demolition plan and scope of work to create drawing markups for review of the Designer (Sargent and Lundy) and they can be able to issue a final demolition plan drawing. Markups and sketch generation are being tracked in a Bluebeam platform.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Generated design sketches to identify potential communications project location and required modifications on site. This coordination is to reduce the impact to BESS and future projects in the Cambalache Plant.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Meeting with S&L Organizer Wifredo Sierra and Mike Kuczynski, DCMC Gilberto Sucre, Gabriel Morales and Eduardo Rivera; Carlos Hernandez and Ricardo Lopez of ARG/CERES and Felix Anastacio of Felix Fire Sprinkler Design - Meeting to discuss Vega Baja site drawing review with Fire Protection contractor company to go thru complete design of BESS fire protection system, meeting also was discussing the structural, civil, mechanical and electrical drawing. Also was discuss a design tracker regard of Vega Baja site. after meeting discuss with Wilfredo Sierra that S&L must discuss with Puerto Rico fire Marshal how to mitigate if a BESS battery got into fire.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue working in the review of the excel table DCMC-Vega Baja-IFC 6.3.25 reviewed comments to SL 7.23.25. The excel table has a total of 201 drawing submitted by S&L which a 50% of the drawing are typical detail. Javier Bidot & Associate continue working with the underground survey. Genera vacuum truck has not arrive at project to clean the oil separate dike.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Javier Bidot continue working with the as built of underground and preparing for S&L design review meeting regard Vega Baja Site. In meeting will be presented the IFC drawing set to discuss the finding and what need to be completed for the final design.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the excel table DCMC-Vega Baja-IFC 6.3.25 reviewed comments to SL 7.23.25, the following table has been corrected some comments and drawing revision numbers and dates in properness of today's meeting with S&L to discuss IFC drawings. Subcontractor of Homeca arrive at site Javier Bidot & Associate to complete the underground survey for the final as built drawing. Javier Bidot subcontractor did not come with a clear SOW by Homeca we required to provide them the information need to complete the job.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a technical staging review at the Aguirre warehouse in preparation for the upcoming cycle count. The objective was to validate operational readiness by establishing an organized pre count framework. Activities included confirming the accuracy of storage zones based on the layout, verifying that printed inventory records match existing documentation, and reviewing operational conditions such as accessibility, lighting, and layout organization that could impact count reliability. The review covered inventory zones UA 010 through UA 025.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-on the last day of the week, ahead of the warehouse closure due to the holiday, led a technical oversight session with Hernan Machado, Milton Flores and Giovanni Taffanelli from DCMC. The purpose of the session was to evaluate the team’s performance, identify any operational or resource needs, and ensure full compliance with safety protocols. Special attention was given to confirming that all work hours were accurately submitted by the end of the day and that ongoing activities remained aligned with established procedures and operational standards.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed scheduled ABC cycle count across specific inventory areas, concentrating on ensuring precise item validation. The effort consisted of a methodical evaluation of physical stock against system records, documenting any mismatches for further analysis and resolution. Manual counts were initially recorded on control sheets and later digitized to maintain traceability and audit readiness. This methodology contributed to reinforcing inventory accuracy, regulatory compliance, and overall data consistency. The scope of this session included locations from UA 010 through UA 025.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out a targeted inventory recount at the Aguirre warehouse to address discrepancies noted during the earlier cycle count. The primary goal was to confirm the accuracy of inventory records, ensure alignment between physical quantities and system data, and strengthen overall data reliability. Activities included reviewing specific storage zones, recounting items manually, and validating part numbers, descriptions, and quantities against both printed records and digital inventory logs. This session focused on inventory bins ranging from UA 010 through UA 025.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane –as part of a variance investigation at the Aguirre warehouse, conducted a detailed review focused on identifying the root causes of discrepancies found in inventory records. The effort centered on tracing inconsistencies by analyzing system activity logs, verifying physical stock levels, and reconciling them with documented records. Core tasks included reviewing material movement transactions, examining transfer documentation, and validating quantity related corrections. This assessment encompassed inventory bins from UA 010 through UA 025.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while station at the Aguirre warehouse, a strategic inventory analysis report was prepared for Mr. Anthony Vega from Genera PR. This report consolidated operational data from all warehouse locations and evaluated cross-site performance indicators. The analysis focused on identifying inventory variances, assessing stock allocation by item type, and reviewing transaction activity throughout the assessment period. Emphasis was placed on detecting accuracy gaps, turnover trends, and risk areas that could compromise material traceability. Benchmarking tools were also utilized to evaluate inventory reliability across locations. The review encompassed inventory zones from UA 010 to UA 025, AC 159 to AC 174, BB 016 to BB 027, CD 044 to CD 053.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed Contract 106930– Feedwater Heaters 6 *HP Vertical: verified deliverables and assessed impact of pending governmental approvals.PW-9510 A&E
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed Contract 109048–Condensing Circulating Water Pump: verified deliverables and assessed impact of pending governmental approvals.PW-9510 A&E
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed Contract 106758 – Continuous Condenser Wash SJ5: verified deliverables and assessed impact of pending governmental approvals.PW-9510 A&E
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed Contract 104796–Set of open and close hardware - honeycomb seals, etc: verified deliverables and assessed impact of pending governmental approvals.PW-9510 A&E
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed Contract 106277–Torque converter: verified deliverables and assessed impact of pending governmental approvals.PW-9510 A&E
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA Genera Deliverable 11 DR4339 Critical Component Meeting - CPM Jose Prado, Victor Aviles, Diana Rivera, Victor Alvarez and DCMC Pedro Cabrera and Roberto Bosch. Discuss Critical Components focused on tracking the Cost Estimates and Scope of Work, RFP, and reviewing the deliverables. PW-9510 FAASt A&E.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the emails Cambalache BESS - Continued Warehouse Inventory sent by Andres Concepcion, and Paul Browne of DCMC in collaboration with Herminio Arroyo of Genera PR and Cambalache BESS - Entrance Bridge Structural Assessment 7/22/25 Meeting notes.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11¦ DR 4339 – Reviewed multiple email threads from Andrés Concepción (DCMC) related to the Open Status Report for RGE and the submittal package RGE-0013.0 regarding the temporary power connection for construction offices at the BESS site (PW9510). Conducted a detailed evaluation of the proposed electrical connection plan, reviewed site layout implications, and assessed compliance with applicable codes and project-specific electrical requirements. Consolidated comments from internal stakeholders, documented pending information, and coordinated preliminary follow-up to ensure submittal completeness and readiness for approval.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review the ATTACHMENT J HEALTH, SAFETY, AND ENVIRONMENTAL POLICIES to add and place clauses in the Cambalache Security Access Minimum Requirements list.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed submittal RGE-0010 for the BESS project (PW9510), which outlines the Work Plan for Trailer Unloading. Evaluated proposed unloading areas, traffic routes, sequence of trailer arrival, and site safety controls. Verified consistency with the site logistics plan and assessed potential impacts to adjacent work zones. Drafted internal review comments.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Worked on all existing dwg from IFB & IFC to identify any possible change orders. Kept supervising Javier Bidot Surveyors that came in today to finish surveying the as build. Oil Energy truck came in to empty the oil tanks, I supervised the procedure.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Worked on all existing dwg from IFB & IFC to identify any possible change orders for the new drawings that were released on Thursday the 17th and the previous releases for Eduardo Rivera Jordan (DCMC). We revised the chart of 207 drawings, for possible change orders, revisions, missing pages, mixed pages that were found.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Worked on all existing dwg from IFB & IFC to identify any possible change orders. Supervised Javier Bidot Surveyors that came in today to finish surveying the as build to deliver precise and reliable survey data tailored to meet the unique demands of the project and ensure accuracy, efficiency, and compliance with all regulatory standards.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I continue working on the as built supervising Javier Bidot- HOMECA subcontractor on the as built work to be performed verifying all areas were covered to close down the report. Reverified documents making sure the blueprint provided by Eduardo Rivera (DCMC) was covered with all areas to verify. Oil Energy arrived to drain oily water separator started to drain the separator will continue Monday due to the truck being over field.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I was working on the as built supervising Javier Bidot-HOMECA subcontractor on the as built work to be performed verifying all areas were covered to close down the report.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 | 152 | 418 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1565, 1566 and 1567 from locations CD044 to CD053 for a total of 310 pcs.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BB016 to BB027
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BB016 to BB027
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock and creating report for Min/Max from locations BB016 to BB027
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BB016 to BB027
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BB016 to BB027
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AC 01 059 000 to AC 01 074 000
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AC 01 059 000 to AC 01 074 000
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AC 01 059 000 to AC 01 074 000
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CD044 to CD053.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria - Working with Excel spreadsheet to track tasks related to the inventory project at the Cambalache warehouse. Key information has been added and updated to more accurately reflect the progress and needs of the project.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CD044 to CD053 Cycle Count List # 1560 and 1564.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CD044 to CD053 to begin the cycle counts.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 152 | 114 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Update our internal modules with new input of issues addressed and new users' level of domain.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management / Cambalache/Costa Sur BESS/Costa Sur Peakers/Vega Baja BESS/Yabucoa BESS S&L Incoming Transmittals-Submittals-ensure documents were created, reviewed, and archived in an organized & controlled manner/documents to be readily accessible for the project team.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Palo Seco BESS Continuation Procurement RFP & RFQ ensure documents were created, reviewed, and stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review Drawing Plans of Existing Conditions from Costa Sur and prepared a Transmittal with the information directly to contractor: initial QA/QC of drawing plans (3 sheets)
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review timing responses of RFI and Submittals at the Vega Baja and Cambalache projects to track team activity based on contractor or vendor's submissions.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Teams Meeting with Lauren Wells (Lemoine), and Andres Concepcion, Luis Duque and Gilberto Sucre (all DCMC) to go over the discussion held with designer Sargent & Lundy related to their approval status content and the matches made with the Procore options for responses.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Began the preparation of Warehouse Inventory reports divided by facility. Current reports are performed in general of four facilities: Aguire, Palo Seco, San Juan and Costa Sur.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the closed submittals on the Cambalache project to review responses and contrast with status convention used by design team when reviewing.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Vega Baja BESS Works Specification Package, which has been addressed for omissions in RFI 11 (ARG-011). Pending response from design team.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Return trip from Aguirre to Hato Rey after the site inspection in order to channel efforts with the community and observe what community projects can be carried out with the community in order to achieve acceptability of the BESS project in the region.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with the Genera PR team and Jorge Bracero in order to make additional corrections to the visit record and refine the necessary details for the next steps of the project. Subsequently, a meeting was held to review the editions of Kroma's signs, also together with Jorge Bracero, in order to ensure the visual and communicational alignment of the materials.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Travel from Genera PR office Hato Rey to Aguirre to visit the site with the Genera PR team and Jorge Bracero. The objective was to inspect the site and channel the efforts of work with the nearby communities related to the BESS project, evaluating possible improvements and communication strategies in the field.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Begin sending registration so that guests at community meetings can register prior to the community event on August 11 in Arecibo. These tasks also included evaluating the record and editing it.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Create a document to carry out the sending of updates for the BESS and Peakers page of Genera PR https://genera-pr.com/bess_peakers in order to update the digital platform with the latest information. These tasks focused on creating the document, reviewing the information, updating all the information at the island level about the BESS and Peaker project so that all the data demonstrate and evidence the work carried out
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 139 | 208.5 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Site visit with the Genera PR team and Jorge Bracero in Aguirre to inspect the site and channel the efforts of work with the nearby communities related to the BESS project, evaluating possible improvements and communication strategies in the field.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 134 | 268 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Summary of Work, Project Meetings and Project Schedule to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 29 pages were examined.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 134 | 201 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Aguirre Site - Participated in the morning coordination meeting with Aguirre Construction management team (Sunem Martínez, José López, and Luis A. Moctezuma – DCMC). Discussion covered the current status of construction drawing submissions, requirements for contractor signage, planned Notice to Proceed dates, and reinforcement of site safety protocols.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 7 pages were examined.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed the Technical Specifications for the Battery Energy Storage System (BESS) General Work Contract (GWC) (Specification No.: G-3400; Revision: A) to comprehensively assess the defined scope, assigned responsibilities, and detailed requirements. A total of 17 pages were examined.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Perform a comprehensive evaluation of the Aguirre facility to determine the most suitable storage location for all RGE/GE Peaker Equipment.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering schedule of values (SOV) demolition existing mechanical equipment and tanks, existing Transformer and electrical equipment, Existing foundations, containments, sumps, privacy walls, fences, paving, Demolition and Relocation of Existing of Piping Existing underground utilities and stormwater piping, Incidental items as identified on the design drawings and items conflicting with the proposed work, in BESS area the electrical grounding cables, duct banks to point of interconnection, manholes and system to point of interconnection, the civil and structural work with earthwork, new aggregates to fill material, asphalt for finish surfacing, new guard rail, stormwater underground system, structural concrete works for construction BESS Foundations which include Switchgear, Control House, Grounding Transformer and Ramps, GSU Transformer Foundation, tesla maintenance foundation, GSU transformer framing, stone columns foundation considering formats in client schedule review and approval form in client sign-off on schedule deliverables for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering schedule of values (SOV) demolition existing mechanical equipment and tanks, existing Transformer and electrical equipment, Existing foundations, containments, sumps, privacy walls, fences, paving, Demolition and Relocation of Existing of Piping Existing underground utilities and stormwater piping, Incidental items as identified on the design drawings and items conflicting with the proposed work, in BESS area the electrical grounding cables, duct banks to point of interconnection, manholes and system to point of interconnection, the civil and structural work with earthwork, new aggregates to fill material, asphalt for finish surfacing, new guard rail, stormwater underground system, structural concrete works for construction BESS Foundations which include Switchgear, Control House, Grounding Transformer and Ramps, GSU Transformer Foundation, tesla maintenance foundation, GSU transformer framing, stone columns foundation system data critical path change log in record and analyze critical path changes, milestone achievement QA record, validate completion of contractual milestones for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 134 | 67 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report considering resources evaluation on site works, equipments and delays reports for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report checklist considering schedule of values (SOV) demolition existing mechanical equipment and tanks, existing Transformer and electrical equipment, Existing foundations, containments, sumps, privacy walls, fences, paving, Demolition and Relocation of Existing of Piping Existing underground utilities and stormwater piping, Incidental items as identified on the design drawings and items conflicting with the proposed work, in BESS area the electrical grounding cables, duct banks to point of interconnection, manholes and system to point of interconnection, the civil and structural work with earthwork, new aggregates to fill material, asphalt for finish surfacing, new guard rail, stormwater underground system, structural concrete works for construction BESS Foundations which include Switchgear, Control House, Grounding Transformer and Ramps, GSU Transformer Foundation, tesla maintenance foundation, GSU transformer framing, stone columns foundation QA summary in summarize high-level schedule QA issues for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - DCMC Site in BESS project team lead by DCMC Carlos Rodriguez attended Teams project meeting on deliverables for site that include location of subcontractor trailer, contract status and issue for constructions drawings of BESS battery project. Additional to this project meeting DCMC Costa Sur site team had the weekly meeting with RG Engineering, contractor for the BESS project lead by construction manager Jose Auli (RG Engineering employee), Rafael Barrera (DCMC employee) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked with quality assurance requirements report considering resources evaluation on schedule of values (SOV) demolition existing mechanical equipment and tanks, Existing Transformer and electrical equipment, Existing foundations, containments, sumps, privacy walls, fences, paving, Demolition and Relocation of Existing of Piping Existing underground utilities and stormwater piping, Incidental items as identified on the design drawings and items conflicting with the proposed work, in BESS area the electrical grounding cables, duct banks to point of interconnection, manholes and system to point of interconnection, the civil and structural work with earthwork, new aggregates to fill material, asphalt for finish surfacing, new guard rail, stormwater underground system, structural concrete works for construction BESS Foundations which include Switchgear, Control House, Grounding Transformer and Ramps, GSU Transformer Foundation, tesla maintenance foundation, GSU transformer framing, stone columns foundation system and delays reports for (DCMC) Carlos Rodriguez due to management requirements of contract PMO DCMC for Puerto Rico Electric Power Authority.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Earthwork Testing and Rigid Inclusions Quality Control to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Quality Control, Construction Facilities and Temporary Controls to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 134 | 402 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Worked on submittals and Shop Drawings and Product Data to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 122 | 244 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue working through the financial flowchart team’s comments to align on Procore financial tool integration.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Updating One pager report tracker for this week.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Compiled and integrated updated field data into the weekly ‘One-Pager Report’, ensuring alignment with current site activities and project milestones. The revision emphasized key performance indicators and summarized ongoing progress to support decision-making and reporting consistency.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Puerto Rico Electric Power Authority ¦ Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. Attended the weekly BESS/Peakers's meeting to discuss the status and budget of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Abraham Velazquez CDM Smith: Franklyn Colmenares, Carlos Palomares, others Genera: German Nunez
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Team meeting with CDM Smith team (Franklyn Colmenares, Manuely Concepcion, Carlos Palomares, Rafael Pabon) and Gilberto Sucre DCMC to discuss program and project status and updates for "One Pager Weekly Report".
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Team meeting with Franklyn Colmenares from CDM Smith to discuss and clarify financial flowchart team’s comments to align on Procore financial tool integration.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 122 | 183 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Revising the ‘One-Pager Report’ for this week to incorporate detailed insights on site-specific activities, alongside a consolidated view of program and project progress.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 | 122 | 91.5 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Working through the financial flowchart team’s comments to align on Procore financial tool integration.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 122 | 91.5 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339. MS Teams meeting with the Costa Sur construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as Safety Plan, mobilization plan, list of personnel amount other documentation needed. Attendees: Gilberto Sucre (DCMC), Carlos De Jesus (DCMC), Jose Segarra (RGE) and others.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 51.38 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Purchase in Best Buy equipment necessary in Yabucoa, Costa Sur, Vega Baja, Aguirre and Cambalache.
2025-07-24 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Morales Cruz, Gabriel | Project Management-Travel | Direct-PA | Travel necessary for project management | Expense |  | 0.7 | 50.96 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - PW10710 - Claiming Mileage for this route - Yabucoa Gas Turbine to Sargent and Lundy office to Yabucoa Gas Turbine. Purpose-Meeting with the teams of Sargent and Lundy, DCMC and Felix Fire Sprinkler Design to discuss Vega Baja site dcontractor company to go thru complete design of BESS fire protection system, meeting also was discussing the structudrawing. Also was discuss a design tracker regard of Vega Baja site.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on connecting drawings for RGE for Aguirre project.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 225 | 900 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Weekly Review of Meeting Notes, Submittals, and Project Communications Internal review of notes from this week’s meetings to track decisions and follow-up actions. Examined the latest submittals uploaded for review to verify compliance with project requirements. Also reviewed email correspondence to align on upcoming project milestones and deliverables. Materials to Prepare/Bring: Latest drawing set (with version history) Markup log or comment matrix Design notes or change requests. Schedule of deliverables. Status Update on Current Drawings. Review of Key Design Areas and Revisions. Review open Issues, Comments, and Coordination Needs.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 225 | 900 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 worked remote Participated in meetings PEAKERS pm check in. Reviewed weeks events and latest updates on schedule, equipment, potential contractors were all discussed. Attended: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Yabucoa RFC Meeting with RGE to review pending items of tracker with a follow up meeting Wednesday and a target goal to complete of next Friday 8/1/25. RGE - Harry Velazquez, Jose Robles CDM Smith - Gabriel Perez, Enrique Laya Sargent & Lundy - Wilfredo Sierra DCMC - Gilberto Sucre
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria E-mail responses to Sheila Torres's - DCMC request for information and clarifications on RFP 4898 BESS Installation at Vega Baja on Attachments: B, C, L, M, S and Z.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Peakers Project Management Update meeting. Attendees were Foster Veazey (Lemoine), Rafael Pabon (CDM Smith), Carlos Palomares (CDM Smith), and Abraham Velazquez (DCMC)
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review and comments of Project Financial Flowchart built by Raissa Borges (DCMC) so that I can add my comments and process of when items can be incorporated into Procore.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial items for review with Lemoine for next steps and action items to finalize this implementation.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on review and comments of Project Financial Flowchart built by Raissa Borges (DCMC) so that I can add my comments and process of when items can be incorporated into Procore.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on review of drawings to be published for Costa Sur Peakers.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on research and documentation of Procurement process.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lee Farell (Lemoine) to discuss Procore financials consulting to help get the implementation over the line.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financials for SOP development and documentation of processes.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on review and comments of Project Financial Flowchart built by Raissa Borges (DCMC) so that I can add my comments and process of when items can be incorporated into Procore.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore workflow evaluation for documents module and feasibility.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Machado, Hernan | Grant Management-Payment Report for RFR | Direct-PA | Creation/tracking/updating of payment report for reimbursement(s) | Expense |  | 189.55 | 189.55 | 189.55 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Purchase of safety footwear, since I didn't buy any when I started working at DCMC Partners because I had a used pair. This request is because my current footwear is starting to break down, so I need to buy a new pair. An invoice and authorization for the purchase are attached.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Review expenses for Critical Components for invoices PRIN0007609, PRIN0008436, PRIN0008587 to flag any potential overruns per Power Plant. PW-9815 A&E.
2025-07-25 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Grant Management-Invoice Review | Direct-PA | Review or validation of invoices for any grant management or closeout purpose | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 Review expenses for Critical Components for invoices PRIN0008810, PRIN0009100 to flag any potential overruns per Power Plant. PW-9815 A&E.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks items for the week.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Conducted an internal review of project emails and documentation, followed by a detailed examination of the project schedule. Performed analysis on the sequencing and duration of key construction activities to assess alignment with overall project milestones.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in Peaker's update meeting. Discussed latest schedule and procurement. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 pm coordination meeting discussed durations and sequencing for the demolition portion of the costa sur project. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Check-In Meeting Led by Gabriel Perez - CDM Smith provided update and program needs updating the weekly tracker. Topics covered Vega Baja MPT improvement and relocation, FOMB Package Completion and submission to Genera Legal. IT/OT Antennas at Sites, LUMA land use at Yabucoa. BESS Fire Protection and Criteria Alignment with Bomberos and Local Authorities. Franklyn Colmenares - CSA Group Sargent & Lundy - Mike Kuczynski, Nelson Rosado DCMC - Sheila Torres & Gilberto Sucre, Luis Roman Genera - Jesus Cintron & Jorge Bracero.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 225 | 56.25 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore Submittal Language discussion on approval stamp language and comparison vs. Sargent & Lundy's Approval Stamp. "Approved" word meaning and legal language. Ada Diaz, Lauren Wells and Gilberto Sucre - DCMC
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Procore - DCMC Financials SOP's led by Lauren Kennedy - Procore and Lauren Wells - DCMC Work on Equipment Invoice and Contractor Invoice SOP. other attendees Esther Rohena, Rafael Calderon, D'Alexander Gonzalez & Gilberto Sucre - DCMC.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Project Update Calls with DCMC Project Staff: Carlos Lopez - Wifi Update for 8 sites + RFC review MEP for Aguirre, Costa Sur, Yabucoa Jose Lopez - IT/OT Location, access road improvements Aguirre Andres Concepcion - Warehouse Inventory + Security Entry Requirements, Owner Cleanup of areas. Eduardo Rivera - Oil Pit Separator draining status, Homeca As- Build.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 225 | 281.25 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Peakers - Sargent & Lundy Design Status Meeting requested by Jesus Cintron - Genera. Presentation by Mike Kuczynski - Sargent & Lundy. Design Status Schedule and Manhour Spent by the 4 sides provide Costa Sur, Jobos, Yabucoa, and Daguao. Identified Construction Administration is not included in their budget, budget vs. Spent, and schedule comparison requested. Genera informed Sargent & Lundy last three sites to be design-built. Attendees: Genera - German Nunez, Jesus Cintron CDM Smith - Rafael Pabon, Carlos Palomares DCMC - Abraham Velazquez, Sheila Torres, Gilberto Sucre Sargent & Lundy - Mike Kuczinski, Nelson Rosado.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS PM/CM weekly meeting with Gabriel Perez - CDM Smith & Franklyn Colmenares - CSA Group. Progress Update review of Project Status, Pre-Construction Activities, TRC Contract Negotiations, BESS Fire Protection Concerns, Sargent & Lundy Design Status, FOMB Approval and submissions, Costa Sur and Aguirre Contract Status, Yabucoa RFC.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-Weekly BESS Project Coordination meeting. Meeting attendees were Jesus Cintron, Ricardo Pallens (Genera), Carlos Palomares (CDM Smith), Joaquin Quinoy (Genera), Gabriel Perez (CDM Smith), Mike Kuczynski, Nelson Rosado (Sargent and Lundy), Franklyn Colmenares (CDM Smith), Frances Vallejo, D'Alexzander Gonzalez, Rafael Calderon, and Gilberto Sucre (DCMC), Kevin Futch, Alejandro Maymi, Francisco Santos, Maria Sanchez, Fernando Ortiz (Genera), and Lauren Wells, Foster Veazey (Lemoine)
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- Follow up meeting to review the staffing plan for Peakers as it pertains to the program team, design coordination, and construction team. Looked at both the personnel needed and the schedule (need-by date). Attendees were German Nunez (Genera), Rafael Pabon (CDM), Carlos Palomares (CDM), Frances Vallejo (DCMC), Abraham Velazquez (DCMC) and Foster Veazey (Lemoine).
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore items for Financials and Procurement processes and researching Procore configurations for use.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for troubleshooting submittal package creation.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for creating new field set for Contracts.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procurement items for organization for alignment with Procore.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore submittal items to Sargent and Lundy for review.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Theresa Perez (DCMC) and Luis Roman (DCMC) for Procore weekly check-in to discuss open items as a team.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information for implementation.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 225 | 337.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lauren Kennedy (Procore), Rafael Calderon (DCMC), Glorimel Torrado (DCMC), Gilberto Sucre (DCMC), Esther Rohena (DCMC), Jose Ralat (DCMC), D'Alexzander Gonzalez (DCMC) to discuss Procore Financial SOPs.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Ada Diaz (DCMC) and Gilberto Sucre (DCMC) to discuss Procore submittal language and see if we need approval for language to use.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Project financial workflow diagram and put an overlay of how the processes will work in Procore.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for submittals.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Uploaded the latest financial data to the Genera Connect Financial Tracker and updated the weekly client update slide deck in preparation for the Genera PR project update meeting. - Discussed with Eisha Mercader from DCMC potential improvements to the Genera Connect Timesheets platform, focusing on enabling supervisors to enter time on behalf of other users to ensure complete and accurate hour logging. - Collaborated further with Eisha Mercader from DCMC to identify and address duplicate entries in the existing Time Tracker to maintain data integrity for upcoming Requests for Reimbursement (RFRs). - Participated in the weekly project update meeting with attendees including María Sánchez, Alejandro Maymi, and Jesús Cintrón from Genera PR; D’Alexzander González, Esther Rohena, Eisha Mercader, Rafael Calderon, Roberto Bosch, and Cynthia Ortiz from DCMC; Jorge Aponte and Keyla Sierra from Integrum; and Benjamin Lopez from Driven.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Reviewed the Vega Baja Vulnerability Plan to assess site-specific risk considerations and mitigation strategies. Evaluated the contract documents between Homeca Contractor and Genera PR, focusing on compliance with project scope and safety obligations. Conducted a conference call with Nelson Medina (GENERA) to discuss security-related topics at the Cambalache site. Reviewed safety documentation submitted by Homeca for the Costa Sur Genera Project, verifying alignment with project safety standards. Participated in a conference call with Abraham Velázquez (DCMC) to discuss updates and coordination related to the Costa Sur Peakers Project.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria:Cambalache Vulnerability Plan Review. Conduct a detailed review of the Cambalache Vulnerability Plan to identify any gaps in the current risk assessment, mitigation strategies, and emergency response procedures. Provided recommendations for improving overall site resilience and preparedness. Evaluated rain related issues for the Vega Baja Site and assess drainage systems, and any rain-related vulnerabilities. Evaluate the impact of weather conditions on operations, equipment, and personnel safety. Propose corrective actions to mitigate risks. Verified office equipment orders to ensure timely delivery. Confirm that all items are received in good condition and are installed according to site requirements.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Attended Design Status meeting to discuss S&L tasks and deliverables moving forward for BESS and Peaker projects. Attendees: Jesus Cintron (Genera), Gilberto Sucre (DCMC) and other DCMC participants, Mike Kuczynski (S&L).
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended BESS Check In teams call with project management team to discuss RFP and contracting process, Procore financials, 4interconnection studies and communication outreach. Attendees: Gabriel Perez (CDM), Jesus Cintron (Genera), Sheila Torres (DCMC), Rafael Calderon (DCMC), Gilberto Sucre (DCMC).
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Review and read correspondance regarding BESS and Peaker one pager.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Call with Jean Menay and Eduardo Rivera (DCMC) to discuss Wi-Fi access in Vega Baja and the possibility of using Starlink. Drafted email to Lemoine IT support to request support in star link quote and installation.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 184 | 46 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS -Held a coordination meeting with Francisco Feliu (Genera Contractor) and Gilberto Sucre (DCMC) to discuss the current status of the contract packages for BESS Installation at Costa Sur (RFP 4899) and Civil Works at Aguirre (RFP 4900). Reviewed outstanding documentation and identified inconsistencies across packages. Developed a strategy to ensure alignment and uniformity among all contract documents, in particular regarding supporting attachments. This effort supports compliant contract administration, promotes consistency across FEMA-funded projects, and helps maintain an organized and audit-ready grant file
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 184 | 230 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - BESS - Participated in the weekly touchpoint meeting to review the status of all BESS projects. Discussed progress on key milestones, procurement activities, technical developments, and any issues affecting timelines or coordination. CDMSmith: Gabriel Pérez, Franklyn Colmenares, Carlos Palomares, Enrique Laya. DCMC: Gilberto Sucre, Rafael Calderon. S&L: Mike Kuczynski. Genera: Jesus Cintrón
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued reviewing the draft contract package for Vega Baja (RFP 4898), focusing on verifying Attachments S-W. Confirmed that the documents align with the RFP requirements, the awarded proposal, and any negotiated terms. Ensured consistency across contract documents to support accurate billing, proper cost tracking, and compliance with FEMA Public Assistance grant requirements. This activity contributes to maintaining a complete and audit-ready contract file and facilitates timely project execution.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in a Design Status Meeting with Jesús Cintrón (Genera), Carlos Palomares, Rafael Pabón (CDM Smith), Abraham Velázquez, Gilberto Sucre, (DCMC) and Mike Kuczynski and Nelson Rosado (Sargent and Lundy) to review key project planning and design deliverables for the Peaker sites. Discussed the latest budget, actuals, and forecast data; progress for IFB/IFC packages; and a comparison of baseline versus current design schedules, including explanations for any delays. This meeting supported proactive project management, alignment of design milestones with procurement and construction schedules.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Genera Weekly Meeting to brief client on project updates and weekly progress with participation from Genera: María Sánchez Bras & Alejandro Maymí. DCMC: Mark Merritt, D'Alexzander González, Roberto Bosch, Esther Rohena, Jose Ralat, Cristian Cruz, Saúl Falcón, Eisha Mercader, Victor Maldonado, Rafael Calderón, Glorimel Torrado. DCMC Subcontractors: Shellsea Maysonet, Johanna Díaz, Marc Maceira, Carlos González and Ginnell Torres.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued reviewing the draft contract package for Vega Baja (RFP 4898), focusing on verifying Attachment Z. Confirmed that the documents align with the RFP requirements, the awarded proposal, and any negotiated terms. Ensured consistency across contract documents to support accurate billing, proper cost tracking, and compliance with FEMA Public Assistance grant requirements. This activity contributes to maintaining a complete and audit-ready contract file and facilitates timely project execution.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 184 | 644 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Continued supporting Eisha Mercader from DCMC by cross-referencing employee IDs against the existing time tracker to effectively identify duplicate time entries and enhance data accuracy. - Coordinated a meeting with Integrum to discuss design considerations for the platform. - Engaged in a prioritization discussion with Mark Merritt and Eisha Mercader from DCMC to align on outstanding tasks for the Genera Connect Timesheets. - Participated in a presentation of the redesigned Genera Connect Timesheets prototype led by Pedro Procopio from Integrum, which showcased new interface features including an improved dashboard, card-based QA review format, bulk action functionality, and enhanced reporting tools. Attendees included Eisha Mercader from DCMC; Carlos Gonzalez, Pedro Procopio, Jorge Aponte, and Keyla Sierra from Integrum; and Marc Maceira from Honra.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety measures. Inspected the field with Eduardo Rivera (DCMC) were Javier Bidot & Associates performed as built work on Thursday. Received items from Jean Menay (DCMC): TV, Camera and wall mount for trailer. Started unboxing items to mount. Fix the construction site cover on entrance gate. Contacted Gabriel Sepulveda (CDM) for oily water separator work to be performed inspected the separator due to being drained and was full over the weekend. Inspected manholes that required oil energy services to be drained for construction purposes.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I continued reviewing the Scope of Services – Specification G-3300 (225-535 / End Section 099113-17, Document Effective Date: June 20, 2025), as well as the BESS Check-In Project Tracker. Additionally, I continued integrating safety-related information into the Contractor Safety Presentation for the Yabucoa BESS project.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, I reviewed the Lead Standard (29 CFR 1926.62) to ensure compliance at the Yabucoa BESS project. The standard emphasized the following points: 1926.62(a)(1) Demolition or Salvage of structures where lead or materials containing lead are present,1926.62(a)(2) Removal or encapsulation of materials containing lead,1926.62 (a)(3) New construction, alteration, repair, or renovation of structures, substrates, or portions thereof, than contain lead, or materials containing lead, 1926.62 (a)(4) Installation of products containing lead, 1926.62 (a)(5)Lead contamination/emergency cleaup,1926.62 (a)(6) Transportation, disposal, storage, or containment of lead or materials containing lead on the site or location at which construction activities are performed, and 1926.67(a)(7) Maintenance operations associated with the construction activities described in this paragraph.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsibilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (RG Engineering) and the Owner Genera PR. There are drawing pages included on the list of drawings, but the drawing was not included in Appendix 1, "Design Drawings". The Scope of the Specification includes site grading, drainage, surfacing, foundations, underground utilities, including embedded electrical conduits and duct banks, fire protection systems, a stormwater sewer system, as well as all substructure foundations and Pads for the Project.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Yabucoa BESS PROJECT. Meeting with Gabriel T. Morales (DCMC) at the Yabucoa Bess project to review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy for the Yabucoa Job Site Included in the Specifications G-3400, review the Division of Responsibilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD), and the Owner Genera PR. Joint efforts with Gabriel T. Morales (DCMC) to identify mismatch information provided by Sargent & Lundy within the provided specifications, designed drawings for the installation phase, the Scope of Work description, and the Directive of Responsibilities from 1 to 249 line items.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsibilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Call with Carlos Bayron (DCMC) at Costa Sur, to discuss the QA/QC plan submitted by the Contractor RG Engineering for the Costa Sur Project. The main subject of the call was to discuss the possibility of having a QA/QC plan completed by DCMC Partners to review and evaluate the applicable conditions for the Costa Sur Project. At this moment, a follow-up meeting should be held with Gilberto Sucre (DCMC) to verify the Document Status for evaluation. It was also agreed to perform a weekly meeting with all QA/QC staff to discuss the need for the QA/QC plan.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I worked a Work Breakdown Structure (WBS) presentation to simplify contractor project schedule to follow up the activities in the project and ensure everyone knows what needs to be done, when and by whom.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I was reading and responding emails that I received during my vacations regarding second phase construction, the contract and other topics.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache and Vega Baja ¦ DR4339 – I received the Schedule of Value and compare its structure with the draft schedule project. I received a call from Jonathan Moore (Lemoine) and he told me he needed to create a structure for the Genera program. He understood I'd be completing it by Tuesday.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Meeting by phone with Eduardo Rivera (DCMC) to discuss the draft Work Breakdown Structure (WBS) schedule project. Discussed what the project will deliver and how to help teams understand the project full scope of work.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – I was reading and responding emails that I received during my vacations regarding project schedule, pending requests for information and other topics.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Modified the draft of the Work Breakdown Structure (WBS) schedule project with the comments received from Eduardo Rivera (DCMC) by email to bring structure and clarity to the entire project.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS - Coordinated with Costa Sur plant personnel (Luis Millan, Luis Torres, Osvaldo De Jesus and Ramon Quiñones) to facilitate the upcoming mobilization of RG Engineering’s office trailer. Arrangements were made to ensure the Punta Este gate will be opened on Thursday morning to allow trailer access and proper placement at the designated area. Additionally, coordination was completed for the required safety modules for RG personnel, scheduled for Wednesday, to ensure full compliance with Genera’s onboarding protocols. These efforts support a smooth and safe mobilization process aligned with site logistics and HSE requirements.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- DCMC Site team lead by DCMC Rafael Barrera internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Conducted an on-site meeting with the RG Engineering team (Jose Auli and Miguel Rojas) and DCMC (Rafael Barrera, Carlos De Jesus and Luis Echevarría) to verify the proposed area for the installation of their office trailer. The visit included a walkdown of the designated location to evaluate accessibility, surface conditions, and proximity to utilities. Verified that the personnel present had completed the required safety orientation and site-specific workshop. The discussion included reviewing updated drawings to identify existing underground lines and determining whether any need to be relocated or removed. Coordination focused on ensuring that trailer placement does not interfere with future construction activities or active utility corridors. Observations were documented for alignment with site logistics and HSE requirements.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Teams meeting with Vincent Skochdopole, Wilfredo Sierra, Mindy Madry, Chris Niersbach, Camillus Pawlica, Robert Molner from Sargent & Lundy; Javiya Keyur, Gilbert Fireflies, Feroz Qais, Joseph Muniz and Lin Howen from TESLA; Eduardo Rivera, Jose Lopez, Andres Concepcion, Rafael Barrera from DCMC Partners; Gabriel Perez from CDM Smith and Franklyn Colmenares from CSA Group to discuss and review the BESS Project 3D model proposed by Sargent & Lundy for the Cambalache site.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue evaluating the Fire Protection Engineering and UL 9540A Interpretation Report for the TESLA Mega Pack 2 XL.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the Fire Protection Engineering and UL 9540A Interpretation Report for the TESLA Mega Pack 2 XL.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- DCMC Site team lead by DCMC Rafael Barrera internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Conducted an on-site meeting with the RG Engineering team (Jose Auli and Miguel Rojas) and DCMC (Rafael Barrera, Carlos De Jesus and Luis Echevarría) to verify the proposed area for the installation of their office trailer. The visit included a walk down of the designated location to evaluate accessibility, surface conditions, and proximity to utilities. Verified that the personnel present had completed the required safety orientation and site-specific modules. The discussion included reviewing updated drawings to identify existing underground lines and determining whether any need to be relocated or removed. Coordination focused on ensuring that trailer placement does not interfere with future construction activities or active utility corridors. Observations were documented for alignment with site logistics and HSE requirements.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- As part of the ongoing compliance efforts with HOMECA company, a thorough review of the documentation within the Request for Clarification (RFC) for the Disposal and Recycling Procedure was conducted. This initiative aimed to ensure that all procedures align with current environmental regulations, internal corporate policies, and industry best practices. The review process focused on identifying outdated documentation, inconsistencies in procedural steps, and gaps in the documentation trail regarding hazardous material disposal and recyclable asset tracking. Special attention was given to verifying whether the chain of custody for electronic waste (e-waste) was properly documented, and whether recycling vendors had valid environmental certifications. Also, an analysis of the Security Plan associated with the disposal process was performed. The security evaluation focused on physical, operational, and information security measures implemented during the transportation and destruction of sensitive materials.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - BESS- Meeting was held with the IT, Mario Gomez of Genera, to identify an active communication line currently in use. During the session, we discussed various strategies to determine the utilization of the service associated with the line. One of the main options considered was performing a trace on the line. The team agreed that tracing would help pinpoint the exact location and system where the service is being used. It was also proposed to carry out the necessary technical tests to verify and confirm the line's purpose and current connections. Next steps include coordinating access for testing, gathering technical data during the trace, and analyzing the results to determine the appropriate actions moving forward.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Tesla Megapack 2 and 2 XL: Reading and review Destructive Test Test Cabinet, Test Setup and Initiation, Instrumentation, Test Results.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Tesla Megapack 2 and 2 XL: Reading and review the Introduction Destructive Fire Test and Fire Modeling Report, Codes, Standards, Test Methods, Refference Materials, Acronyms and Abbreviations. 1.1 Codes, Standards, and Test Methods The following codes, standards, and test methods have been applied to this analysis: • 2023 NFPA 68, Standard on Explosion Protection by Deflagration Venting (NFPA 68). • 2024 NFPA 69, Standard on Explosion Prevention Systems (NFPA 69). • 2023 NFPA 855, Standard for the Installation of Stationary Energy Storage Systems (NFPA 855). • UL 9540A, Test Method for Evaluating Thermal Runaway Fire Propagation in Battery Energy Storage Systems, Edition 4, November 12, 2019 (UL 9540A). 1.2 Reference Materials In addition to the fire codes, standards, and test methods listed above, the following reference materials were reviewed as part of this analysis: • Megapack 2 FPE Report, Fire & Risk Alliance, LLC., dated April 17, 2024 (MP2 FPE Report). • Megapack 2 XL FPE Report, Fire & Risk Alliance, LLC., dated April 3, 2024 (MP2XL FPE Report). 1.3 Acronyms and Abbreviations Authority Having Jurisdiction Battery Energy Storage System Battery Management System AHJ BESS BMS Megapack 2 Megapack 2XL Megawatt hour MP2 MP2XL MWh PAGE 1 DESTRUCTIVE FIRE TEST AND FIRE MODELING Customer Interface Bay Fire Code Official feet Fire Protection Engineering Fire & Risk Alliance, LLC hour inch kilogram kilowatt hour Megapack 1 PAGE 2 DESTRUCTIVE FIRE TEST AND FIRE MODELING TESLA MEGAPACK 2 AND 2 XL CIB FCO ft FPE FRA hr in kg kWh MP1 Meter Millimeter minute National Fire Protection Association Northern Nevada Research Center second State of Charge Thermal Management System UL, LLC m mm min NFPA NNRC s SOC TMS UL
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting Coordination and Agenda preparation work with the Construction Weekly Progress Meeting with RG Engineering, the General Work Contractor, José Segarra (RGE), José Robles (RGE), Xiomara Pérez (RGE), Vernaded Ortíz (RGE), Gilberto Sucre, Carlos R. López Vallellanes, Luis Moctezuma, Sunem Martínez, Jean Menay (DCMC), Gabriel Pérez (CDM Smith, Franklin Colmenares (CSA). Categories of the Agenda are as follows: DCMC Construction Management Team Introduction, RG Engineering Construction Team Introduction, Scope of Work Clarifications, Directory of Responsibilities Clarifications, Safety Topics and Plan from RG Engineering, Master Project Schedule, Schedule of Values, RG Engineering Point of Contact during the construction process, Schedule an Initial Genera PR Safety Workshop, and Open Items Discussed.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Morning call with Gilberto Sucre(DCMC) to go over the pending items and important task activities for the coming week. On this, an update from Sargent & Lundy regarding the issue with the Construction Drawings delivery date. As of today, the Aguirre project deliverables have been moved forward from the original schedule dates. Gilberto Sucre (DCMC) requested that Carlos R. López Vallellanes (DCMC) and QA/QC from the Aguirre Bess Project review the issue with the bid design drawings, make all necessary comments, and send the list to Gilberto Sucre (DCMC) for action.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. I had several phone calls with the GWC (RG Engineering) project manager, Jose Segarra, to follow up on the project contract requirements and contract progress. Ing Jose Segrarra (RGE) informed that they don't have a contract approval authorization from Gener-PR Still. No further action will be taken into consideration until the Puerto Rico Public–Private Partnerships Authority (P3A) has evaluated and approved the contract terms.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning staff meeting with Sunem Martínez, Carlos R. López, and Luis A. Moctezuma (DCMC). The agenda items included issues related to the delivery status of construction drawings, general work contractor signage, and notice to proceed schedule dates, as well as general safety topics.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria, Aguirre BESS project. Offered a workshop to Sunem Martínez (DCMC) in regard to the correct process of using the Submittal Tool into the PROCORE platform. We run an example of a Submittal workshop with the Step One: Generating a Submittal; Step 2, Identifying the Submittal Manager and Step 3; Assigning the Submittal responsible person and company. As part of the exercise, we also went through the response process and how to keep a record and a submittal log of all submittals registered into the Procore's submittal tool.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria; 4339_9510; VEGA BAJA BESS 3D EXPLANATION MEETING. Allin Luong, Molner, Robert, Niersbach, Chris Pawlica, Camillus J, Skochdopole, Vincent (Sargent & Lundy), Eduardo Rivera. Here are the meeting comments: Move the 3D Model review meeting to next week on Pro Core. ~Franklyn Colmenares (CSA): Take the concern regarding the turning radius and internal measurements to the service team. ~Keyur Javiya (S&L), Verify and validate the dimensions of the telescopic forklift for ground space assessment. ~Vincent Skochdopole (S&L). Follow up on clearance concerns related to the model before going to the power blocks. Make a note of the possibility of extending the platform to the second aisle, where the green panel is located. ~Vincent Skochdopole (S&L).
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Cambalache-An analysis was conducted on the Occupational Health and Safety Plan documentation submitted by RGE contractor. Notes and observations were prepared for discussion during the meeting held at the contractor’s RGE offices.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Reviewed the security plans designed for the environmental protection of the BESS project at the Cambalache site. Notes were taken to incorporate recommendations provided by the environmental department of Genera Cambalache.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Site visit to the Cambalache location for a meeting with Roseanne Pérez (GENERA). Discussions focused on the environmental requirements for the project, including the spill contingency plan and other related topics.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed the designer (Mike Kuczynski - Sargent and Lundy) information regarding: Genera BESS: Preventative Measures to Mitigate Fire Risks to evaluate potential Fire Protection project scope of work to mitigate and coordinate the mentioned emergency risks.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Managed Meeting Agenda in Procore. Organized topics and action items to be followed up in the Construction Weekly meeting.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - (1) requested to general contractor a quote for the furnishing of storage racks for the temporary warehouse activity. (2) Coordinated meeting with Carlos Lopez (CW Legal) to discuss environmental permitting work. (3) Managed submittal status in Procore with Luis Duque (DCMC Partners).
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Organized project milestones information and project history to consolidate a status and progress report to be shared with Public Relations team which is organizing a community event.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR -Generated correspondence by email to Jose Segarra (RG Engineering) to formalize Cambalache plant access and security control requirements. This communication will apply for a process to be performed in the duration of project.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed mechanical drawings sent by designer (Mike Kuczynski) and generated list of pending drawings that were missed in the set.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Virtual meeting with Sargent and Lundy's (Mike Kuczynski, Vincent Skochpodole) and TESLA's (Howen Lin) to discuss design coordination items within infrastructure and TESLA batteries.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - BESS Genera Meeting to discuss BESS 3D model review, Originator Allin Luong and Javiya Keyur of Tesla, Design leader Vincent Skochdopole of S&L - In meeting was presented the 3D model of Vega Baja BESS system it was mentioned that all Megapack required a ground, and this will include the Medium Voltage Transformer. The issue in the meeting was the forklift to be used for removing the battery there is no ramp at this site and the mega dolly required a space for removal of the battery and forklift required an 8 ft clearance between megapack. Issue also with the fire automatic canon Javiya Keyur of Tesla does not recommend the use of automatic water canon due to the concern of a fire in the battery and also mention that the heat detection system he also not consider due to something it can detect false heat and can trigger the water cannon, he recommend a manual system with a lot of fire hydrants and hose station in case of use these are some recommendation of Tesla.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the revised schedule of value (SOV) send by ARG related to Vega Baja site. Working with comments to SOV sent by ARG before approval by DCMC and Genera. Send JHA to Gilberto Soto of DCMC related to ARG survey measurement work at Vega Baja site for marking project boundary and relocation of existing transformer. Send email to Ricardo Lopez of ARG related to As Built drawing send by Homeca of demolition site.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 | 167 | 542.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing new set of drawing sent by S&L on 7/24/25 related to fire protection system, drawing has the isometric of the Vega Baja site project. Send email to Gabriel Perez of CDM Smith in regard of existing MPT relocation that on proposal inform that the transformer will be consider a rigging of the MPT including the oil which this is consider a high-risk critical lifting. Send email to Sylvia Franco of DCMC to know if draft schedule for Vega Baja site was completed for us to discuss the schedule a presented to ARG as a template schedule.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with Sylvia Franco of DCMC in regard of Vega Baja Work Breakdown Schedule (WBS) for development of Vega Baja draft schedule for BESS installation second phase.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted cycle count operations within designated inventory zones at the San Juan facility, focusing specifically on locations BB 028 through BB 040. Efforts centered on validating physical stock quantities, confirming bin accuracy, and cross-referencing data with system records. Any discrepancies identified were documented for further review, and necessary adjustment were coordinated as needed. All activities were executed in accordance with established inventory control protocols to ensure data accuracy and system integrity, and continued progress toward cycle count completion objectives.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out preparatory activities at the San Juan warehouse alongside Mr. Milton Flores from DCMC, focusing on inventory locations BB 028 through BB 040 to ensure all conditions were met for the upcoming cycle count. Task included verifying the physical readiness of inventory zones, confirming accurate bin identification and labeling, and validating item groupings against system configurations. The session also ensured that all reference documentation was in place to support a smooth and complaint counting process.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a detailed review and analysis of inventory variances across zones BB 028 through BB 040. The effort focused on identifying discrepancies between physical inventory and system reported data by reviewing item movement history and validating data integrity through audit trail analysis. Emphasis was placed on determining the root causes of these variances, detecting recurring patterns, and assessing the reliability of previous adjustments. This initiative supported improvements in inventory accuracy and reinforced internal control measures.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-prepared a comprehensive inventory performance report for Mr. Anthony Vega from Genera PR. The report consolidated key findings from inventory zones CE 001 to CE 008, BB 028 to BB 040, AF 001 to AF 009, CD 054 to CD 063. It addresses item level accuracy, stock balance verification, bin assignment validation, and variance documentation. The report also highlighted recurring issues, assessed compliance with inventory thresholds, and evaluated procedural consistency throughout warehouse operations.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-began the workweek with a coordination meeting alongside Hernan Machado, Milton Flores, Giovanni Taffanelli and Juan Vallejo from DCMC to align objectives for the upcoming days. The session focused on setting priorities for inventory audits, verifying current warehouse conditions, and outlining the support structure for ongoing ABC cycle count operations. Emphasis was placed on maintaining inventory accuracy, upholding safety standards, and ensuring operational consistency across all assigned tasks.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.25 | 167 | 375.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a focused inventory recount at the San Juan warehouse in coordination with Mr. Milton Flores from DCMC. The main objectives included confirming actual inventory quantities, verifying the accuracy of bin assignments, and ensuring that system records accurately reflect physical stock conditions. Emphasis was placed on maintaining consistency within inventory processes, improving data reliability, and upholding operational integrity. The effort targeted inventory zones BB 028 through BB 040, ensuring compliance with audit standards and quality assurance protocols.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component Meeting- GENERA-PR Jose Molina, Carlos Menendez, Victor Ortiz, Jose Borges, Jorge Sanchez, Carlos Negron and Joaquin Quinoy DCMC Pedro Cabrera. Discuss Critical Components focused on tracking the components of San Juan and Palo Seco Generations Plants. PW-9515 FAASt A&E.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Develop Attachment 2 NON-COMPETITIVE PROCUREMENT JUSTIFICATION WORKSHEET for the following Critical Components. Hydrogen Coolers Palo Seco Reduction Attemperators Palo Seco Generator Breaker Cambalache Boiler Feed Water Pump Costa Sur & Cambalache PW-9510 FAASt A&E
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Develop overall status presentation of Critical Components Forecast FY2025-2026 requested from GENERA-PR Joaquin Quinoy. PW-9510 FAASt A&E
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed Contract 102928– Safety Valves and Rehabilitation San Juan: verified deliverables and assessed impact of pending governmental approvals.PW-9510 A&E
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed Contract 109357–Traveling Screens San Juan 9: verified deliverables and assessed impact of pending governmental approvals.PW-9510 A&E
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewed Contract 108707 –Circulating Water Pumps San Juan: verified deliverables and assessed impact of pending governmental approvals.PW-9510 A&E
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Preparation for the weekly meeting with GENERA-PR, I focused San Juan and Palo Seco Generation Plant, on reviewing Critical Components priorities, compiling status updates, identifying next steps, metrics, challenges, and deadlines. These efforts aimed to ensure a productive discussion.PW-9510 A&E
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Genera - BESS Meeting with Franklyn Colmenares from CSA Group, Gabriel Perez Sepúlveda from CDM Smith, Mike Kuczynski from Sargent & Lundy, Howen Lim from Tesla 3D Model Review S&L will show 3D modelling to Tesla and discuss.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review First submittals: Submittal: RGE-0010.2 RGE-0010.2 WORK PLAN FOR TRAILERS UNLOADING, Second Submittal #: TSL-S018.0 Title: Cambalache CT Burden Calculation
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – ¦ DR 4339 – Development module in Procore focused on the Preconstruction tools available to project managers representing the Owner. The session included guided instruction on bid management, document tracking, project setup workflows, and configuration of cost-related settings to support preconstruction oversight for the Cambalache BESS project (PW9510). This supported improved alignment between Owner responsibilities and contractor deliverables during early project phases.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS - Call to Andres Concepcion (DCMC) discussion about the detail Meeting Genera - BESS 3D Model Review.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Review EMAILS Cambalache BESS - Temp Warehouse Racks task the preparation of the temporary warehouse sent by Andres Concepcion (DCMC) to RGE submittals: #RGE-0006.1: RGE-0006.1 - BESS CAMBALACHE CONCEPTUAL STRUCTURAL STEEL DRAWINGS.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Continued reviewing and addressing comments received on RFI #ARG-R012 from Sargent & Lundy. Conducted a comprehensive review of all existing drawings (DWGs) from both IFB (Issued for Bid) and IFC (Issued for Construction) packages. Analyzed design documents to identify any discrepancies or potential change orders that may impact project scope, schedule, or budget. Task was completed.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Reviewed and addressed comments received on RFI #ARG-R012 from Sargent & Lundy. Conducted a comprehensive review of all existing drawings (DWGs) from both IFB (Issued for Bid) and IFC (Issued for Construction) packages. Analyzed design documents to identify any discrepancies or potential change orders that may impact project scope, schedule, or budget.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety measures. Today I inspected the field with Eduardo Rivera (DCMC) were Javier Bidot & Associates performed as built work on Thursday. Received items from Jean Menay (DCMC): TV, Camera and wall mount for trailer. Started unboxing items to mount. Fix the construction site cover on entrance gate.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CD054 to CD063 Cycle Count List # 1568 and 1571.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BB028 to BB040
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BB028 to BB040
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BB028 to BB040
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels and creating report for Min/Max from locations BB028 to BB040
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BB028 to BB040
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AF 00 001 000 to AF 00 009 000
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AF 00 001 000 to AF 00 009 000
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AF 00 001 000 to AF 00 009 000.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations CE 001 to CE 008 at the Aguirre warehouse to initiate the cycle counts.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations CE 001 to CE 008 , RECOUNT LIST # 1501/1506/1507
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location CE 001 to CE 008
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations CE 001 to CE 008, LIST #1500/1501/1502
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1570, 1582,1583 and 1584 from locations CD054 to CD063 for a total of 128 units.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CD054 to CD063 to begin the cycle counts.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CD054 to CD063.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Carlos De Jesus and Rafael Barrera (both DCMC) to clarify the uploading process for RFIs in the Costa Sur BESS project: request for information related to underground utilities on Drawing Plans. Overview of filling the required fields for the creation of RFI (assignees, location, and others).
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Cambalache BESS incoming documents for review & process/Vega Baja BESS incoming documents for review & process/Costa Sur BESS incoming documents for review & process/Project Team Coordination with Lauren Wells (DCMC) & Luis Roman (DCMC)
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/Costa Sur BESS continuation of incoming documents review & process/Vega Baja BESS incoming documents for review & process/Homeca_CDM_S&L request current Certifications for our records
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - BESS Weekly Check-in Meeting hosted by Gabriel Perez (CDM Smith) and joined by Franklyn Colmenares (CSA), Gilberto Sucre, Rafael Calderon (DCMC), Mike Kuczynski (S&L), Jesus Cintron (Genera PR), and other project staff. Discussed current status for multiple BESS project issues such as procurement and RFP of upcoming activities, discussion of open items per site (Cambalache, Vega Baja, Costa Sur and Aguirre), and other important notes related to BESS works.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339- Continue with the review of the completion of Homeca Demolition Contract in Vega Baja to continue the audit of documentation from demolition stage.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 151 | 453 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the completion of Homeca Demolition Contract in Vega Baja and perform brief audit of documentation from demolition stage.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Procore Weekly Catch-up Meeting with Lauren Wells (Lemoine) and Theresa Perez (DCMC). Discussed the most recent topics as for Drawings File Naming Convention, responsibilities from the Design Team and potential new process for getting certain uploads into the system.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 139 | 104.25 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Review and update the existing list of nonprofit organizations. These edits may include correcting information, adding or removing entities, verifying contact details, and categorizing them by area of impact or region.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Carry out updates on Genera PR’s website, specifically in the section https://genera-pr.com/bess_peakers. These tasks included providing updated information about the different sites to the Genera team, particularly to Alex Valdés Díaz, with the goal of ensuring that accurate and current data is reflected on the site. Additionally, a document containing the revised content was created, and further information was shared with Rafael Rodríguez Ema for the update of the fact sheet. This included a representative image of the BESS and Peakers project across the island, along with site-specific megawatt information. Lastly, as part of these tasks, a Gmail account was created to gain access to Google Analytics https://genera-pr.com/bess_peakers.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Create an updated contact list of community leaders in the municipality of Arecibo for use on the go.botmaker.com platform to send automated invitations to the community meeting scheduled for August 11. The list includes name, organization (if applicable), community role, and phone number. The document was created in Excel.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 139 | 173.75 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 meeting via Microsoft Teams with DCMC: Frances Vallejo Rosich, D'Alexzander González, Rafael Calderón, Gilberto Sucre, Mark Merritt, Raissa Borges, Lauren Wells, Foster Veazey. In the meeting was de CDM Smith Team: Gabriel Perez Sepulveda; Carlos Palomares. In the meeting was the Genera PR Team: Jesús Cintron, Joaquín A Quinoy, Ricardo Pallens, María Sánchez Bras, Fernando Ortiz, Kevin Futch and Francisco Santos. In the meeting was the Sargent & Lundy Team: Mike Kuczynski and Nelson Rosado. During the corresponding meeting, safety protocols related to BESS batteries were also discussed, specifically in the context of fire prevention, and an update was provided on the status of each site. In addition, we talked about the signs that must be placed on the sites, the steps being taken to move forward with the BESS project, the tests that will be carried out on the Cambalache bridge, and the efforts we have made in community relations. All of this work aims to strengthen transparency, operational safety, and effective communication of the project at both the technical and community levels.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with the Corporate Affairs team of Genera PR, composed of Jorge Bracero, Iván Báez, and Rafael Rodríguez Ema. During the meeting, the key topics to be addressed during the week were discussed, an update on the work completed so far was provided, and specific details related to the work agenda were reviewed. The purpose of this meeting was to ensure alignment of efforts, set priorities, and coordinate upcoming actions effectively.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Practical workshop on the full process of sending messages through the go.botmaker.com platform, conducted with the Genera PR team and Rafael Rodríguez Ema. This task included running message-sending tests on the platform. As part of the workshop, a step-by-step walkthrough was provided on how to use the interface, upload contacts, segment audiences, draft and schedule messages, review delivery metrics, and apply best practices to ensure clear, effective communication aligned with community engagement goals.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Product Receiving, Storage and Handling Requirements to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed drawings AGB99-EB-BSS-0001; AGB99-EB-BSS-0002; AGB99-EB-BSS-0003; AGB99-EB-BSS-0004; AGB99-EB-BSS-0005; AGB99-EB-BSS-0006; AGB99-EB-BSS-0007; AGB99-EB-BSS-0008; AGB99-EB-BSS-0009; AGB99-EB-BSS-0010; AGB99-EB-BSS-0011; AGB99-EB-BSS-0012; AGB99-EB-BSS-0013; AGB99-EB-BSS-0014; AGB99-EB-BSS-0015; AGB99-EB-CHB-0001;AGB99-EI-BSS-0001 to verify they meets the required specifications of the projects.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Continued reviewing drawings AGB99-EI-BSS-0001; AGB99-EI-BSS-0002; AGB99-EI-BSS-0003; AGB99-EI-BSS-0004; AGB99-EI-BSS-0005; AGB99-EI-BSS-0006; AGB99-EI-BSS-0007; AGB99-EI-BSS-0008; AGB99-EI-BSS-0009; AGB99-EI-BSS-0010; AGB99-EI-BSS-0011; AGB99-EI-BSS-0012; AGB99-EI-BSS-0013; AGB99-EI-BSS-0014; AGB99-EI-BSS-0015; AGB99-EI-BSS-0016; AGB99-EI-BSS-0018; AGB99-EI-CHB-0001; AGB99-EL-000-0001; AGB99-EL-BSS-0001 to verify they meets the required specifications of the projects.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at BESS project with document verification of existing condition and photo of survey as-built and create a comment report in missing comments of water piping, fire protection piping, in project site, in perimeter project site, in sidewalk exterior of project and exterior street of project for (DCMC) Carlos Rodriguez.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at PEAKERS project with document verification of existing condition and photo of survey as-built and create a comment report in missing comments of water piping, fire protection piping, in project site, in perimeter project site, in sidewalk exterior of project and exterior street of project for (DCMC) Carlos Rodriguez.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Nameplates and Tags, Demolition, Removals, and Alterations to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 122 | 305 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Integrating milestone updates from BESS projects to strengthen the analytical visual representation of ongoing progress and potential risks in the July monthly report.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Going through the team's comments on this week Power Bi One Pager report and incorporating suggested revisions in preparation for client submission.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 122 | 366 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Integrating milestone updates from Peakers projects to strengthen the analytical visual representation of ongoing progress and potential risks in July monthly report.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Teams Meeting "BESS Check In" The purpose of this meeting is to discuss projects status and updates. The meeting was organized by Jesus Cintrón from Genera. Attendees: Luis Roman (DCMC), Jorge Bracero (Genera), Lauren Wells (Lemoine), Rafael Calderon (DCMC), Mike Kuczynski (S&L), Jesus Cintron (Genera), Frances Vallejo (DCMC), Gabriel Perez (CDM Smith), and others
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Starting systematically compiling and reviewing Critical Components updates to enhance data visualization, improve accessibility, and facilitate clearer interpretation of progress and risks.
2025-07-28 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Menay, Jean Pierre | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 0.7 | 41.44 | 0.7 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Project Manager Travel necessary for Travel from home offices San Juan to Vega Baja Site to Home Offices San Juan. Site Inspection in Vega Baja Site and evaluate rain issues and delivery Offices equipment.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Holton-Williams, Anneilia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | PREPA Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-PMO call. Teams call with Gilberto Sucre, Frances Vallejo, Ada Diaz, Mark Merritt, Jack Darnall, Nyah Medina and Mike Merritt, DCMC. Discussed update on project, job offers, PROCORE, logistics, trailer set-up, safety, schedule for locations and program goals.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in a Peaker's schedule update meeting. Discussed the latest impacts to schedule from procurement, and recent scope changes. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Carlos Rodriguez DCMC Carlos De Jesus DCMC Rafael Barrera DCMC.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710. Internal review of emails, meeting for project schedules, worked on outlines for upcoming demolition portion of Costa Sur project. Attendees: German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group Rafael Calderon DCMC.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Attended BESS Peaker's procurement meeting. Discussed the status of equipment deliverables, payments and delivery to site logistics German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Miscellaneous Follow Up of: * Sargent & Lundy's Peakers Design Cost vs. Funding Budget. * Homeca's Legal Correspondence review of Breach of Contract and LD's. * Procore Drawings Files of IFB, and IFC's * BESS PMO Reporting
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache BESS - Construction Weekly Meeting led by Andres Concepcion - DCMC Topics: Contract Status, Warehouse Inventory, Permitting, Security & Access Procedures, Construction Parking Water Line Relocation, Value Engineering by RGE, Fire Protection, Tracker. RFI's Submittals and SOV. Attendees: Sargent & Lundy - Mike Kuczynski- Wilfredo Sierra CDM Smith - Gabriel Perez CSA Group - Franklyn Colmenares DCMC - Luis Duque, Andres Concepcion, Sylvia Franco, RGE - Jose Segarra, Wanda Bonet
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Cambalache Construction Parking Considerations to determine if permits are required or not. All agreed as long as no improvements are made to the area. Carlos Lopez -CWLegal, Jose Segarra - RGE, Andres Concepcion & Gilberto Sucre - DCMC.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria S & L / CDM Smith /DCMC Weekly BESS Drawings Meeting - Updated review of Design Status IFB, IFC's and Action Items Trackers for Vega Baja, Cambalache, Costa Sur, Aguirre and Yabucoa. Internal need to have Fire Protection Design Criteria of Megapacks agreed by all parties being essential for all sites. Mike Kuczynski, Robert Molner - Sargent & Lundy CDM Smith - Gabriel Perez, Enrique Laya DCMC - Andres Concepcion, Jose Lopez, Gilberto Sucre
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria PMO Catch Up Meeting. Overview Organizational chart reviewed; staff across Cambalache, Aguirre, Costa Sur, and Vega Baja discussed, with a scheduler position open at Cambalache. Mark Merritt requested three budget scenarios: full staffing, total freeze, and hybrid, highlighting the need for strategic planning amid potential hiring freezes. FEMA discussions ongoing regarding Environmental Assessment needs for the Peakers, possibly delaying Costa Sur installations for one year. Design-build strategy for the last three Peaker sites was announced by Genera. Procore implementation SOP development is in progress with bi-weekly meetings. Procurement challenges noted with Office Depot as items frequently go out of stock during purchasing, complicating supply acquisition. Attendees: Michael Merritt, Mark Merritt, Anneilia Holton, Jack Darnall, Frances Vallejo, Ada Diaz, Lauren Wells and Gilberto Sucre - DCMC/ Lemoine
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Weekly Construction Meeting led by Eduardo Rivera - DCMC. Update on Topics; Contract Status, IFC drawings, Fire Protection Criteria, RFI's and Submittals, SOV, Schedule, Safety & Quality Program. Ida Ramirez, Carlos Hernandez - ARG Ceres Eduardo Rivera, Jean Pierre Menay, Gilberto Sucre, Sylvia Franco- DCMC Gabriel Perez - CDM Smith Wilfredo Sierra - Sargent & Lundy
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable- PMO Reporting meeting to discuss the reports that have been compiled for the overall Program. Attendees from DCMC were Frances Vallejo, Rafael Calderon, Gilberto Sucre, Paul Browne, and Abraham Velazquez. Attendees from LEMOINE were Foster Veazey and Lauren Wells.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable - Weekly PMO Call with Program Management team. DCMC attendees were Frances Vallejo, Gilberto Sucre, Barry Scanlon, Mark Merritt, and Mike Merritt and Lauren Wells and Foster Veazey (Lemoine)
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on research for Drawing workflows to be used in Submittal workflows in Procore.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued work on Procore financials.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations to test out functionality in the Sandbox for doing RFI' solo for Pre-Intervention before budget is set up.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procurement details for overlay with Procore usage.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. (DCMC) PMO Reporting Meeting - DCMC PMO staff meeting to discuss specific need of reporting based on project execution development per area. Working on live tracker presentation template and review updates from BESS and Peakers projects. Participants DCMC (Frances Vallejo, Raissa Borges, Glorimel Torrado, Jean Pierre Menay, Eduardo Rivera, Paola Arroyo and Paul Browne) and others.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for CDM Smith for document access.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financials.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting for PMO update. Anneilia Holton Williams (DCMC), Frances Vallejo (DCMC), Mike Merritt (DCMC), Gilberto Sucre (DCMC), Mark Merritt(DCMC) and others to discuss program staffing and overall program goals.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial SOP documentation.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating PMO reporting dashboard information for Raissa Borges (DCMC).
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - PMO meeting preparation - Updated legal and procurement update slides for the weekly PMO reporting meeting. The slides provided a clear summary of key developments, including the status of active solicitations, contract execution updates, and any legal or compliance considerations impacting project timelines. Ensured the content was concise, accurate, and aligned with internal reporting standards to support informed discussion and strategic planning during the meeting.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Coordinated between Genera and RGE (Contractor) for the delivery of office trailers and necessary materials to be inventoried at the Cambalache Genera site. Ensured proper scheduling and documentation to support seamless onsite setup and inventory management.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Status and Construction Meeting held with ARG teams, including Carlos Hernandez, Gilberto Sucre (DCMC), and Gabriel Perez (CDM Smith), focusing on the Vega Baja Genera site. Topics included: Health and Safety protocols, project schedule updates, and logistics coordination. Meeting with the PMO team, including Frances Vallejo (DCMC), to review overall project progress status. Reviewed the invoice for Portosan septic services to verify billing and service details. Participated in a conference call with Andrés Concepción (DCMC) to discuss security topics related to the Cambalache Genera project.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 184 | 276 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Reviewed the internal Health and Safety document for use in Genera Bess projects. Evaluate the Tesla Megapack Fire Protection Engineering Report and the UL 9540A Interpretation Report. Send the Emergency Management information to Osvaldo De Jesús (GENERA)."
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Status and Construction Meeting with RGE teams include Alberto Borrelli, Javier Reyes, Andres Concepcion and Gilberto Sucre (DCMC), and Osvaldo de Jesus (GENERA). Reviewed documents sent by Jaime Pesquera (DCMC) related to Vega Baja inspection procedures used by ARG, to ensure alignment with project requirements and documentation standards.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Took the Procore modules for the project management system.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.25 | 184 | 46 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review correspondence regarding warehouse inventory, internet setup for trailers and purchases for inventory at the sites.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.75 | 184 | 138 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended site trailer update call with Jean Menay (DCMC) to discuss trailer coordination, invoices and pending purchases for equipment and materials.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Participated in Teams call regarding PMO Reporting call to discuss each department update and data in order to update the monthly report for the client. Attendees: Raissa Borges (DCMC), Carlos Palomares (CDM) and other DCMC participants.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Assisted PMO Catch up call to discuss staffing update, Procore, BESS project status and RFPs. Attendees: Mike Merritt, Mark Merritt, Gilberto Sucre, Ada Diaz, Anneilia Holton (DCMC).
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - BESS Installation at Vega Baja RFP 4898 - Reviewed the RFI issued by P3A and discussed its requirements with Gabriel Sepúlveda (CDM Smith) Gilberto Sucre (DCMC) and Francisco Feliu (Genera contractor). Retrieved, reviewed, and organized all relevant documentation necessary to support a comprehensive and accurate response. Drafted the formal reply and provided it to Angelina Minier (Genera) for legal review and integration into the final submission package. Ensured the response aligned with applicable federal grant compliance standards and supported audit readiness.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - BESS Installation at Vega Baja RFP 4898 - Reviewed the RFI issued by FOMB and discussed its requirements with Gabriel Sepúlveda (CDM Smith) and Gilberto Sucre (DCMC). Retrieved, reviewed, and organized all relevant documentation needed to support a comprehensive response. Identified gaps in the supporting materials and formally requested the missing information from the contractor (ARG) to ensure the response package is complete, accurate, and compliant with federal grant documentation standards.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Developed comprehensive checklists for the P3A and FOMB contract approval request packages to support the Procurement Team in assembling complete and compliant submissions. Each checklist outlines the specific documentation and formatting requirements necessary to facilitate regulatory review, improve consistency across packages, and reduce delays caused by incomplete or inaccurate filings. This initiative is intended to streamline the approval process, minimize Requests for Information (RFIs), and strengthen internal quality control. Shared both checklists with the DCMC Procurement Team to support implementation and ensure alignment with current grant administration practices.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. Contributed updates on assigned tasks, reviewed performance metrics, and participated in discussions aimed at streamlining reporting processes and enhancing cross-functional coordination. Collaborated with team members to identify action items and align on priorities for the upcoming reporting cycle. DCMC: Frances Vallejo, Gilberto Sucre, Rafael Calderon, Raissa Borges, Abraham Velazquez, Jean Pierre Menay, Gilberto Sucre, Paul Browne, Eduardo Rivera Jordan, Foster Veazey, Glorimel Torrado. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Reviewed the weekly BESS and Peakers “One-Pager” project summary report to ensure consistency, accuracy, and alignment with current project data. Provided feedback and recommended edits to Raissa Broges (DCMC) to support accurate project reporting and effective communication with stakeholders. This activity supports grant oversight and contributes to maintaining a clear, up-to-date record of project performance for FEMA PA documentation.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Began inspecting the field with Javier Bidot & Associates to verify performed as built work missing components. Verified manholes identify that they were clogged with sediments. Had meeting with Eduardo Rivera, Jaime Pesquera, Gilberto Sucre and Jean Menay from DCMC Partners and Carlos Hernandez from ARG to discuss Vega Baja BESS. Entered meeting with Homeca concluding documents for closing with Eduardo Rivera, and Jaime Pesquera from DCMC and Carirma Sanchez from Homeca.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I reviewed the Destructive Fire Test and Fire Modeling Report for Tesla’s Megapack 2 (MP2) and Megapack 2 XL (MP2XL) lithium-ion battery energy storage systems (BESS). The report covers codes, standards, and testing methods; reference materials; destructive testing procedures; fire propagation modeling; application of the MP2 system; conclusions; limitations; and the revision control sheet. Additionally, I examined the Megapack 2 XL Data Sheet, “Megapack – Safe by Design,” the Megapack Safety Overview, and began the Procore workshop course titled The Cultural Shift Toward Prioritizing Safety.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I read about fire protection engineering (FPE) analysis report of Tesla’s Megapack 2 XL (MP2XL) battery energy storage system (BESS).This analysis includes the following: the codes, standards, and test methods, Reference Materials, MP2XL Design and Fire Safety Features, MP2XL Product Listings, UL 9540A Testing, and Conclusions. Additionally, I’m revisiting the Action Plan (plan your work & work you plan) module in Procore.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa During this period, Meeting with Gabriel Morales (DCMC) to discuss the daily status of the Yabucoa BESS Project, documents updated (Contractor Induction presentation, Toolbox and Evacuation Attendance Record) and verify next steps.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT/Coordination with Carlos Lopez (DCMC) to monitor the quality of the work as indicated in Section 014500 of this Specification, including batteries and all other electrical equipment.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. A walk-through was conducted with Jose Lopez (DCMC), Carlos López (DCMC) and Luis Moctezuma (DCMC) to identify existing fire protection line routes and potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents from Sargent & Lundy, package identified as GENERA-15240-061-0017, for the Installation phase at the Aguirre Site, 17º57'10"N, 66º13'49"W. Review items 1 to 163 and send comments with findings to Gilberto Sucre (DCMC) to evaluate and discuss with the client Genera PR.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Jose Lopez (DCMC), Carlos López (DCMC), and Luis Moctezuma (DCMC) to discuss project two week look ahead schedule and improve communication across the site team.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Meeting. Discussed delivery of ARG/CERES Schedule of Value (SOV) for approval, that is not aligned with the RFP proposal, Management requested the contractor to provide several documents, ARG will submit final schedule draft by end of this week, and others. Attended Ricardo Lopez (ARG/CERES), Gabriel Perez (CDM Smith), Jaime Pesquera (DCMC), Wilfredo Sierra (Sargent & Lundy).
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 – I read the minutes and agenda that will be discussed at today's meeting. Total of minute pages are 8 and for agenda are 2.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I read the minutes and agenda that will be discussed at today's meeting. Total of minute pages are 7 and for agenda are 2.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I started to read the Agreement with Beta Electric Corporation (BEC). Among the topics read were terms and conditions, contractor responsibilities, warranty and correction of work, indemnities, and others. Total of pages were 1 to 30.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Cambalache ¦ DR4339 –Meeting -Project Progress- Discussed about the heavy equipment to rent to move warehouse materials, RGE will provide a submittal with alternatives of piping relocation, and plan for pipping survey, and other topics. Attended Jose Segarra (RGE), Robert Molner (Sargent & Lundy), Gilberto Sucre (DCMC), Gabriel Perez (CDM Smith), and others.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Participated in a site visit related to the IT/OT Communication Building, monopole installation, and overall BESS construction at the Costa Sur site with participants Gino Sambolin (S&L), Hector Vazquez (LTA), to assess the feasibility of the location in relation to the LTA footprint. It was agreed that S&L will confirm with Miguel Beauchamp (Genera) to ensure that Genera has no objections to the proposed area. This coordination is critical to maintain schedule alignment and avoid future construction conflicts. DCMC team participants: Rafael Barrera, Carlos De Jesus and Luis Echevarría.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the review of the “Costa Sur Vulnerability Assessment” with a focus on developing structured comments and recommendations to be discussed with Jean Menay (DCMC). The evaluation emphasized operational gaps and response deficiencies highlighted in Sections 4 through 7, particularly regarding continuity of operations during multi-hazard events. Drafted observations addressed areas such as inadequate backup systems for critical infrastructure, the need for defined communication hierarchies during emergencies, and opportunities for enhancing collaboration with external emergency management entities. Comments were organized by risk category to streamline discussion and support the integration of actionable items into the project’s HSE preparedness strategy.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continued housekeeping including landscaping and cleaning activities in the house area owned by PREPA and were the DCMC Partners office are located.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Landscaping cleaning activities in the house area owned by PREPA and were the DCMC Partners office are located to ensure design, planning, building and outdoor spaces are functional areas around the structure.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Luz Ramirez (DCMC) to discuss the daily assistance documents and the emergency procedure presentation to create a transparent record and ensure everyone is on the same page regarding the project's progress and hurdles.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR4339 – Hurricane Maria: Yabucoa - Completed the Procore Certification: Project Manager (Project Management) offered by Procore Technologies to enhance project management capabilities and ensure effective use of Procore tools in support of federally funded recovery efforts under DR4339.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- Today, a representative from Sargent & Lundy (Gino Sambolin (S&L) & Hector Vazquez (LT Automation) conducted a site visit to the Battery Energy Storage System (BESS) project location. The purpose of the visit was to perform a field verification of both existing and future electrical installations intended to supply the Tesla battery control room (MegaPack). During the walkthrough, the designer reviewed the current site conditions, including installed conduit runs, cable trays, and available space for future expansions. Particular attention was given to the routing and termination points for power and communication cables that will interconnect the control systems with the Tesla MegaPack units. Also, included a detailed inspection of the proposed locations for power panels, transformer tie-ins, and control equipment. The Sargent & Lundy representative verified alignment with the latest design drawings and gathered data to inform any necessary updates to the engineering documentation. Overall, the site conditions were found to be generally consistent with the planned design. Minor adjustments were noted and will be incorporated into the final design package to ensure seamless integration of future equipment.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur After visit of designer Sargent & Lundy (Gino Sambolin (S&L) & Hector Vazquez (LT Automation) to the BESS project site I started to evaluate the designated project area and review both existing and future electrical connections. One of the objectives of the visit was to verify that field conditions align with the drawings submitted as part of the design documentation. I reviewed the on-site conditions with the latest issued drawings to confirm consistency and identify any discrepancies. I started to pay attention to the layout of control panels, cable trays, transformer connections, and proposed power supply points for the Tesla MegaPack system. Any deviations or required adjustments noted during the visit were documented for further engineering review and will be reflected in the final as-built and construction drawings.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Reading and review the MP2 APPLICATION, CONCLUSIONS, LIMITATIONS, AND REVISION CONTROL SHEET
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Reading and review about FIRE PROPAGATION MODELING: Heat Flux Model Basis and Validation – No Wind Heat Flux Model Basis and Validation – With Wind Heat Flux Model Results Thermal Runway Model Basis Fire Propagation Model Results
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, and Luis Moctezuma(DCMC) to discuss the project's two-week look-ahead schedule and improve communication across the site team.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the Issue bid drawings documents, TECHNICAL SPECIFICATION FOR BESS GENERAL WORK CONTRACT (GWC) Spec. No.: G-3400 Revision: A; For Bid Project No. A15240, June 20th, 2025to identify potential and possible change orders, as well as potential issues that may arise during the construction process. It was decided to submit an RFI to Sargent & Lundy for these effects to be integrated into the PROCORE platform. A call was held with Javier Ignacio from Portosan to coordinate equipment delivery to the Aguirre Site.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. It seems that the status of the issue for the bid drawings is still pending. During the call with Gilberto Sucre from DCMC, we discussed the ongoing delays in the delivery of the Issue for Construction Drawings from Sargent and Lundy. They are expected to provide updates soon. For further details or any specific questions regarding the timeline or any other aspects, they will be discussed in the 2:00 pm design status meeting.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS Project Meeting with S&L Mike Kuczynski, Robert Muhler, and (CDM Smith), Gabriel Perez, Franklyn Colmenares, (CDM Smith), Andres Concepcion, Gilberto Sucre from DCMC Partners to discuss the BESS IFC design delivery status. Costa Sur, Cambalache, and Vega Baja are the only BESS projects for which Sargent and Lundy has delivered the Issue for Construction Drawings. Yabucoa and Aguirre BESS Sites have not been delivered yet.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting Coordination and agenda preparation work with the Construction Weekly Progress Meeting with RG Engineering, the General Work Contractor, José Segarra (RGE), José Robles (RGE), Xiomara Pérez (RGE), Vernaded Ortíz (RGE), Gilberto Sucre, Carlos R. López Vallellanes, Luis Moctezuma, Jean Menay (DCMC), Gabriel Pérez (CDM Smith, Franklin Colmenares(CSA). Categories of the Agenda are as follows: DCMC Construction Management Team Introduction, RG Engineering Construction Team Introduction, Scope of Work Clarifications, Directory of Responsibilities Clarifications, Safety Topics and Plan from RG Engineering, Master Project Schedule, Schedule of Values, RG Engineering Point of Contact during the construction process, Schedule an Initial Genera PR Safety Workshop, and Open Items Discussion.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Visited the Cambalache site and attended a physical security briefing led by FSO Nelson Medina (GENERA). The session was also attended by Andrés Concepción and Luis Duque (DCMC). Briefing involved defining primary security objectives and assessing potential threats and vulnerabilities.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Evaluated and approved Submittal 10.3, submitted by Jose Segarra (RGE), regarding the use of crane equipment and the lifting of containers.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Visited the Cambalache site accompanied by Luis Damudt and Andres Concepción (DCMC) to coordinate project activities related to the availability of storage areas within temporary warehouses. Also attended the weekly progress meeting with contractor RGE, represented by Jose Segarra, where discussions focused on contracting matters, project progress, and safety submittals.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Generated list of observations regarding the weekly design meeting discussion regarding updates of pending design activities to finish the BESS project design.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Meeting with Carlos Lopez (CW Legal), Gilberto Sucre (DCMC Partners) and Jose Segarra (RG Engineering) to discuss the evaluation to use a lot as temporary parking for contractor personnel and its environmental implications.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Met with Genera PR - Nelson Medina to discuss Cambalache Plant Access Control and Security requirements to be followed in project. Received Security Orientation.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Coordinated meeting for Safety submittal discussion with General Contractor (RG Engineering). Managed to generate information regarding project milestones to be shared with Public Relations Team. Coordinated meeting with Carlos Lopez (CW Legal) to discuss temporary parking environmental requirements. Met with Cambalache team on site (Luis Damudt, Luis Duque, Jorge Mercado - DCMC) to cover internal site team pending actions.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Met with Mike Kuczynski, Robert Molner (Sargent and Lundy) Gilberto Sucre (DCMC), Gabriel Perez (CDMSmith) and CSAGroup (Franklyn Colmenares) to discuss regarding the weekly design updates meeting to discuss pending design activities to finish the BESS project design.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS - 4339DR - Conducted meeting with project team: RG Engineering (Jose Segarra), Sargent and Lundy (Robert Molner), CDM Smith (Gabriel Perez), CSA Group (Franklyn Colmenares) to follow up on weekly updates and project pending actions.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed Open Submittals, RFIs and actions in Procore to prepare and complete the Construction Weekly Meeting Agenda. Consolidated action items to be discussed in meeting.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with minutes of ARG/CERES meeting; Vega Baja site will not be considering a ramp for forklift. A&L will provide specification for the Mega Dolly for battery removal. ARG to submit RFI for catch basin alternative. Potable water will remain 2" size versus 4" size requested by S&L mention Gilberto Sucre of DCMC. Sanitary lift station will be on hold into ARG to intercept existing sanitary pipeline and review if works. They will not be considered Potable Wate drain at site. Eye wash and safety shower will be included in design tracker if apply ARG will be noticed to submit a change order. Guard house floor and wall thickness will be included in design tracker ARG will be notice if change will apply.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project weekly meeting to review project status. Homeca Carirma Sanchez, Gilberto Soto, Jaime Pesquera, and Eduardo Rivera of DCMC, Enrique Laya of CDM Smith - Meeting to discuss final pending items related to project closing, Carirma Sanchez of Homeca is requesting status of the proposed change order before they submit the draft of certification #4. Certification #4 will be including only contracted work completed all change order will be provided on certification #5 and final certification #6 will be the % retainage.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Send email to Gilberto Sucre of DCMC in regard yesterday meeting with Tesla and S&L. In the meeting was sent some of the notes taken in regard of Vega Baja site. The most relevant issue was the forklift at the platform of the BESS area and the use of automatic water cannon and heat detection system which can trigger a false activation and spread water to the BESS equipment's.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing the documents send by ARG related to project safety such as Fire Extinguisher Plan, Tools Inspection Plan, Spill Management Plan, Stair or working Height plan, Finger Use Plan, Emergency Evacuation Plan, Hurricane Procedure Plan, Equipment Inspection Plan, and Vehicule Inspection Plan. Preparing agenda for ARG/CERES meeting to discuss final project closing items.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with comments in regard ARG payment schedule draft submitted for review all comments was sent to Gilberto Sucre of DCMC for review and comments. Preparing agenda for Homeca meeting to discuss final project closing items.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Project construction weekly meeting Phase II. ARFG/CERES Carlos Hernandez, Ricardo Lopez, Jennifer Vansadani and Ida Ramirez; DCMC Jaime Pesquera, Gilberto Soto, Sylvia Franco, Raissa Borges, Gilberto Sucre and Eduardo Rivera, CDM Smith Gabriel Sepulveda, S&L Wilfredo Sierra - Meeting to provide status for second phase construction of Vega Baja BESS project, coordinate with ARG documents to be submitted as part for the new construction and ARG provide status of RFI's and Submittals. Most relevant issue in meeting are the fire protection system that ARG will need to submit RFI in response of some question.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led a focus variance review to examine discrepancies identified during prior inventory validations at the Costa Sur warehouse. The effort involved auditing transaction logs, reviewing movement history, and cross-referencing part numbers to confirm data consistency. Focus was placed on recurring variances to identify root causes and apply corrective actions designed to improve inventory accuracy and mitigate future inconsistencies. This analysis covered inventory zones from AF 010 through AF 025.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out cycle count operations across designated inventory zones by performing physical item verification, validating bin assignments, and recording results in line with established procedures. The process involved reconciling actual quantities with system reported balances, identifying variances for prompt review, and ensuring traceability through proper documentation of all findings. All activities adhered to the approved cycle count standards to uphold inventory accuracy and audit compliance. This session focused on inventory locations ranging from AF 010 through AF 025.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led a brief coordination session with Juan Vallejo, Giovanni Taffanelli, Milton Flores and Hernan Machado from DCMC, to align on the day’s operational focus. The discussion covered task delegation, reinforcement of safety measures, and verification of adherence to cycle count protocols. Emphasis was placed on clarifying objectives and addressing any unresolved inventory discrepancies requiring immediate resolution. This effort was key to ensuring continuity and accuracy in daily inventory activities.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while on site at the Costa Sur facility, began drafting a comprehensive inventory assessment report intended for submission to Mr. Anthony Vega of Genera PR. The report consolidates detailed information across multiple warehouses zones and includes key data such as catalog ID, maximum and minimum stock levels, total item counts, and the overall inventory value recorded. It also incorporates variance analysis, classification issues, and inventory health indicators. The document highlights operational deficiencies, identifies recurring stock inconsistencies, and presents actionable recommendations to improve data accuracy, inventory control, and alignment with organizational standards. The assessment covered locations were CE 009 to CE 013, AF 010 to AF 025, BB 041 to BB 055, AH 043 to AH 046.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a recount verification of previously audited inventory zones at the Costa Sur warehouse. The objective was to revalidate physical quantities, confirm alignment with prior cycle count outcomes, and investigate any remaining discrepancies. The process involved reviewing bin assignments, verifying labeling accuracy, and ensuring that any adjustments made accurately reflected the true inventory status. All observations were recorded to strengthen traceability and confirm compliance with established reconciliation procedures. The verification covered inventory locations from AF 010 through AF 025.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-began the preparatory phase for the upcoming cycle count at the Costa Sur warehouse, working jointly with Mr. Hernan Machado from DCMC. Efforts focused on reviewing system inventory data, validating item master records, and verifying assigned bin locations specifically covering areas AF 010 through AF 025. Preparations included staging physical zones for count execution, confirming that storage and labeling conditions meet audit requirements, and providing guidance to warehouse personnel on protocol adherence and documentation standards. These actions were critical to establishing a controlled environment and minimizing the risk of discrepancies during the counting phase.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components regarding to Palo Seco Power Plant continue update Critical Components Tracker. Related to PW-9510 FAASt A&E
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components regarding to Palo Seco Power Plant finishing update Critical Components Tracker. Related to PW-9510 FAASt A&E
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components regarding to Palo Seco Power Plant update Critical Components Tracker. Related to PW-9510 FAASt A&E
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Critical Component - Using the available information such as Cost Estimate, Scope of Work, RFP, Contracts and Invoice of NME and Critical Components regarding to San Juan Power Plant update Critical Components Tracker. Related to PW-9510 FAASt A&E
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Weekly Status Meeting - With participation from DCMC and Lemoine: Abraham Velazquez, Frances Vallejo, Gilberto Sucre, Lauren Wells, Rafael Calderon, Pedro Cabrera, Sheila Torres, Raissa Borges, Paola Arroyo, Paul Browne and (CDM Smith), Carlos Palomares, and Franklyn Colmenares, Meeting with DCMC to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. Related to PW-10710 Equipment & Material
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Complete the Bi-Weekly Report Template in preparation for the PMO reporting meeting. This task involved compiling updates on key project activities, identifying recent accomplishments and ongoing challenges, and summarizing financial and operational status. The finalized report supports leadership oversight and ensures consistent tracking of project milestones and deliverables. Related to PW-9510 FAASt A&E
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS I contacted Luis Roman and Andres Concepcion from DCMC to coordinate a meeting to define the information parameters needed for the weekly report of the BESS Cambalache project on the Procore platform.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Prepare an outline of the information parameters needed for the weekly progress report of the Cambalache BESS project in the Procore platform.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS - Course Project Manager: Preconstruction Learn Procore's Preconstruction Tools as a project manager as an Owner.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Genera PR Security Orientation with Genera Nelson Medina, and DCMC Andres Concepcion for the discussion of Entry requirements for all BESS program staff at Genera PR Cambalache Power Plant facilities in Arecibo.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Construction Weekly discussion Safety Plan and Issue drawings with Gilberto Sucre, Andres Concepcion, Jorge Mercado, Luis Duque from DCMC, Jose Segarra, Xiomara Perez, Alberto Borelli from RGE.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS - (Continue) Course Project Manager: Preconstruction Learn Procore's Preconstruction Tools as a project manager.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Began daily project coordination and management activities. Weekly construction meeting with the following project stakeholders: Homeca Recyclers: Carirma Sanchez & Eduardo Vera, DCMC: Eduardo Ramos & Eduardo Rivera Jordan, CDM Smith: Nelson Soler. Discussed the project closing documentation, providing an overview of current status and next steps. Reviewed and analyzed documentation progress and completion status using the Procore platform and verified and confirmed that all punch list items have been completed and officially closed.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Continued daily project coordination and management activities. Weekly Vega Baja BESS Phase II Construction Meeting with: Carlos Hernandez (ARG/CERES), Eduardo Rivera Jordan (DCMC), and Nelson Soler (CDM Smith). Reviewed the Project Documents Overview and conducted a detailed analysis of document status in the Procore platform to ensure compliance and progress tracking.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. I inspected the field with Javier Bidot & Associates performed as built work missing components. Verified manholes identify that they were clogged with sediments. Meeting with Eduardo Rivera, Jaime Pesquera, Gilberto Sucre and Jean Menay from DCMC Partners and Carlos Hernandez from ARG to discuss Vega Baja BESS. Entered meeting with Homeca concluding documents for closing with Eduardo Rivera Jaime Pesquera from DCMC and Carirma Sanchez from Homeca. Continue supervision for Javier Bidot as built process and documentation, supervised oil Energy for the draining for the oily water separator.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BB041 to BB055
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels and creating report for Min/Max from locations BB041 to BB055
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BB041 to BB055
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BB041 to BB055
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BB041 to BB055
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AF 00 010 000 to AF 00 025 000.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AF 00 010 000 to AF 00 025 000.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AF 00 010 000 to AF 00 025 000.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location CE 009 to CE 013
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations CE 009 to CE 013, LIST #1512/1513
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations CE 009 to CE 013 at the Aguirre warehouse to initiate the cycle counts.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations CE 009 to CE 013 , RECOUNT LIST # 1514/1515
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CD064 to CD071 and AH043 to AH046.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.75 | 152 | 418 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1587, 1593 and 1594 from locations CD064 to CD071 and AH043 to AH046 for a total of 47 units.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.25 | 152 | 494 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CD064 to CD071 and AH043 to AH046 Cycle Count List # 1586 ans 1589.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CD064 to CD071 and AH043 to AH046 to begin the cycle counts.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Cambalache Project Weekly Meeting hosted by Andres Concepcion (DCMC) and joined by Gilberto Sucre and Jean Menay (DCMC), Jose Segarra (RGE), Wilfredo Sierra (S&L), Osvaldo De Jesus (Genera), and other project staff members; discussed safety documentation regarding project activities, the use of Procore for project documentation, the use of Connection Manager (feature that allows to share and connect Procore projects from one portfolio to another) and coordinations to be made at the site.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/ Review & process all certifications-various/GEN 01 S&L Financial Task Orders ensure documents were created_reviewed_stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the Costa Sur civil drawings looking to define potential areas of the project site to be included as Locations for Procore purposes; also reviewing the existing site conditions plans.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Gather information to complete a Summary Report for the ongoing efforts at the Genera's Plants Warehouse Inventories.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Perform QA/QC on Vega Baja project documentation that has being uploaded to the Documents Tool; looking for potential missing files, correspondences and any other material shared through conventional email and before the arrival of DCMC to the program.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the implementation of different methods to be included in the approval of drawings inside Procore; uploading as submittals for approval and before being uploaded to the Drawings Tool. Expected to meet Lauren Wells (Lemoine) tomorrow for further discussion.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 139 | 417 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Completing the mass message distribution through the Botmaker for the second meeting of the Cambalache Project in Arecibo. This process involved a series of essential preliminary tasks to ensure effective and organized communication. First, the official contact list was managed by collecting accurate information from key community participants. Then, a thorough validation of the list was carried out. The invitation texts (copies) were also reviewed and approved to ensure clear, accessible language aligned with the project's objectives. As part of the enhancements to the digital communication strategy, internal processes were implemented within the Botmaker platform to create a dedicated communication channel for communities linked to the BESS system.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Accessing the Google Analytics platform with the purpose of monitoring web traffic and user activity on the BESS and Peakers project pages. This action made it possible to observe key metrics such as the number of visits, traffic sources, user behavior, and average time on page. The preliminary analysis helped identify access patterns and evaluate the visibility and reach of both pages within the context of the project's communication initiatives.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Design key communication pieces using the Canva platform to support the community presentation of the Cambalache project. This work included the creation of graphic arts, visual elements, and informational materials aimed at facilitating the community’s understanding of the project. Among the highlighted content were the project timeline and next steps, intended to provide clarity about the ongoing process and upcoming actions. The pieces were designed with an accessible, visually appealing approach aligned with the project’s identity to ensure an effective presentation to the community.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Continue working on pieces in PowerPoint format to support the community presentation of the Cambalache project. This work included creating slides with graphic arts, visual elements, and informational materials aimed at facilitating the community’s understanding of the project. Among the highlighted content were the project timeline and next steps, intended to provide clarity about the ongoing process and upcoming actions. The slides were designed with an accessible, visually appealing approach aligned with the project’s identity to ensure a clear and effective presentation to the community.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Concrete Unit Masonry Unit Construction, Bolting, Structural Welding and Anchor Rods to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed drawings GGS99-EA-000-0001-06; GGS99-EA-000-0001-07; GGS99-EA-000-0001-08; GGS99-EA-000-0003-01; GGS99-EA-000-0003-02; GGS99-EA-000-0004-01; GGS99-EA-000-0004-02; GGS99-EA-000-0004-03 to verify they meets the required specifications of the projects.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Successfully completed the Procore development program for Project Manager Quality/Safety, encompassing modules on Action Plans, Daily Logs, Incident Reporting, Inspection Procedures, Observation Protocols, and Documentation Forms. Additionally, obtained official certification by passing the comprehensive examination.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 134 | 67 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- attended Teams meeting BESS project considering notice to proceed status, construction activities duration guided by specification section 013216 list related to construction guides and resources data formats, schedule of values of schedule for employee (DCMC) Carlos Rodriguez, Sunem Martinez, Rafael Barrera, (RG Engineering) employee Jose Segarra, (CDM Smith) employee Carlos Palomares, (Sargent and Lundy) employee Dean Ennes.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at PEAKERS project with project procurement in pending Tesla, Portosan, employee's certification, QC plan, temporary power connection, work plan for trailers submittal verification for (DCMC) Carlos Rodriguez.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at BESS project with project inspection in survey existing condition underground utilities for (DCMC) Carlos Rodriguez.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 134 | 67 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at BESS project with project procurement in pending RFI or Drawings type Issue for construction (IFC) for (DCMC) Carlos Rodriguez.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at BESS project with project procurement in pending Tesla, Portosan, employee's certification, QC plan, temporary power connection, work plan for trailers submittal verification for (DCMC) Carlos Rodriguez.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 134 | 134 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Cambalache- attended Teams meeting in Cambalache BESS project Construction Weekly with pending issues to start project work plan, sign of contract status and permits status with DCMC employees Andres Concepcion, Gilberto Sucre, Luis Damudt, Luis Duque, employees of RGE Jose Segarra, Xiomara Pérez Álvarez, CDM Smith employee Gabriel Perez, employee of Sargent and Lundy Dean Ennes.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Inspection and Testing of Concrete, Concrete Work and Grout Work to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue integrating Inventory Management updates in July monthly report to strengthen the analytical visual representation of ongoing progress and potential risks.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue integrating updates of Critical Components project into the July monthly report to provide a comprehensive and visually enhanced analysis of operational trends, progress and emerging risks.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Attended the weekly PMO reporting meeting to review the status of active projects, discuss progress against key milestones, and address any issues impacting timelines or deliverables. We identified action items and aligned on priorities. DCMC: Frances Vallejo, Sheila Torres-Sterling, Rafael Calderon, Raissa Borges, Abraham Velazquez, Gilberto Sucre, Paul Browne, Eduardo Rivera Jordan, Lauren Wells. CDMSmith: Franklyn Colmenares, Rafael Pabon, Carlos Palomares
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Integrating detailed updates of Critical Components project into the July monthly report to provide a comprehensive and visually enhanced analysis of operational trends, progress benchmarks, and emerging risks.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams meeting with the Vega Baja BESS construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as mobilization plan, schedule, quality plan and other documentation needed. Attendees: Eduardo Rivera (DCMC), Jean Pierre Menay (DCMC), Jose Segarra (RGE) and others.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams meeting with the Cambalache construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as Safety Plan, mobilization plan, permits and other documentation needed. Attendees: Andres Concepcion (DCMC), Gilberto Sucre (DCMC), Jose Segarra (RGE) and others.
2025-07-29 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Integrating Inventory Management updates in July monthly report to strengthen the analytical visual representation of ongoing progress and potential risks.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  | 416.6 | 416.6 | 416.6 | Yes | 146796 | Home Depot - Supplies for the Costa Sur location
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  | 416.6 | 416.6 | 416.6 | Yes | 146796 | Home Depot - Supplies for the Yabucoa location
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  | 416.6 | 416.6 | 416.6 | Yes | 146796 | Home Depot - Supplies for the Aguirre location
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  | 302.88 | 302.88 | 302.88 | Yes | 146796 | Office Depot - Office supplies for the Vega Baja location
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  | 298.64 | 298.64 | 298.64 | Yes | 146796 | Office Depot - Office supplies for the Aguirre location
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  | 297.3 | 297.3 | 297.3 | Yes | 146796 | Office Depot - Office supplies for the Cambalache location
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  | 297.3 | 297.3 | 297.3 | Yes | 146796 | Office Depot - Office supplies for the Costa Sur location
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Grant Management-Travel | Direct-PA | Travel necessary to support grant management activities | Expense |  | 297.3 | 297.3 | 297.3 | Yes | 146796 | Office Depot - Office supplies for the Yabucoa location
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) continued working on adding Safety Inspection checklist to each project in Procore.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 site visited reviewed information and coordinated with onsite field staff the possible new laydown locations, team will continue to asses' new locations over the next few weeks. Carlos Rodriguez DCMC Carlos De Jesus DCMC Rafael Barrera DCMC.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 225 | 675 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 participated in Bess peakers needs meeting discussed each projects needs and requirements for upcoming scheduled invents and activities. German Núñez, GENERA Rafael Pabon, CDM Smith Carlos Palomares CDM Smith Laya, Enrique J. CDM Smith Gabriel S. Perez CDM Smith Franklyn Colmenares, CSA Group Carlos Rodriguez DCMC Carlos De Jesus DCMC Rafael Barrera DCMC.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 225 | 450 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 internal review of project emails and documentation, followed by a detailed examination of the project schedule. Performed analysis on the sequencing and duration of key construction activities to assess alignment with overall project schedule
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Star Link Internet Discussion for all Genera BESS & Peakers Project Sites. Teams Meeeting with Lemoine IT Support Team to present our needs, project location coordinates for Lemoine to contact their account team and provide options in order to finalize the wifi provider selection process. Dillon Gilger - Lemoine IT Support, Frances Vallejo, Gilberto Sucre, & Carlos Lopez - DCMC
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Execution One on One Meeting with BESS Team, Jesus Cintron - Genera, Gabriel Perez - CDM Smith, Frances Vallejo & Gilberto Sucre - DCMC Main topics discussion: Homeca Financial Resolution Meeting with Genera Legal set for 7/31 @ 10 am BETA Engineering approval to proceed with MPT relocation and repair S & L Engineering Budget & Progress Status TRC Contract and Task Order Performance Guarantee Clause applicable to CWC and GWC. Peakers Sr. Manager Replacement Candidates.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Peaker's Alignment Meeting with Mike Kuczynski and Nelson Rosado - Sargent & Lundy on establishing the minimum technical items required for the Design/Build RFP for the Yabucoa, Jobos and Daguao Sites.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.25 | 225 | 281.25 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria HOMECA Costa Sur Peakers Pre-Negotiation Discussion. The goal of the meeting is to prepare the agenda for the kick-off Final Negotiation Meeting set for the following Thursday 8/7. Giberto Sucre - DCMC presented to the team the Lessons Learned of Homeca's Performance at the Vega Baja Demolition Site Project on Safety, Planning, Communication, Contract Obligation Knowledge, Scheduling, Invoicing & Closed out. Team to request in advance agenda from contractor to present their execution of the above topics in relation to the upcoming Scope of this new project at Cost Sur. Present: Genera - Francisco Feliu, German Nunez CDM Smith - Rafael Pabon & Enrique Laya DCMC - Abraham Velazquez, Giberto Sucre
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Organization Reschedule of meetings and agenda for the remainder of the week.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Correspondence reviewed and responded to BESS and Peakers e-mails and Bid Documents.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS & Peakers Procurement Status Meeting led by Cynthia Ortiz - Genera, Reviewed and Updated all Programs RFP's Status and Action Items. Attendees: CDM Smith - Gabriel Perez, Rafael Pabon CSA Group - Franklin Colmenares DCMC - Sheila Torres, Gilberto Sucre, Abraham Velazquez
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on creating Safety requirement checklist in Procore.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for new users.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore certification tracking details for users.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on more correspondences for Procore items.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial setup for 11855 to prepare for a stress test on the system to test our configurations against reality.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on updating Procore tasks to track items.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Lee Farell (Lemoine) to discuss Procore financials.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Luis Roman (DCMC) to discuss Procore open items and show inspection safety checklist that was created.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial SOP documents items.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore configurations for reporting on analytics.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 184 | 276 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Generation Fleet - Participated in a biweekly strategic planning meeting with Genera's CEO Winnie Irizarry and Jesús Cintrón to assess temporary generation requirements and evaluate potential impacts on the implementation of FEMA-funded BESS and Peakers projects. The discussion focused on aligning available generation capacity with project timelines to ensure uninterrupted execution and compliance with Public Assistance objectives. Identified potential constraints and coordinated on mitigation strategies to support effective project formulation and long-term grant management.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review the documents in Procore related to the Cambalache Genera Project. Coordinate the delivery of equipment to the Cambalache site for RGE (Contractor). Review the equipment delivery process for the Costa Sur Genera Project. Review the offices and equipment purchase for all sites. Additionally, review the Tesla Megapack fire protection system documentation.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Conduct a Health and Safety working session for the RGE (Contractor) team, including Jose Auli and Carlos Negrón. The session should cover all relevant topics related to the Cambalache Genera Project, including construction, logistics, health and safety, security, and environmental considerations. Provide an explanation of both the Health and Safety Manual and the site-specific manual. Additionally, explain the use of the Procore system and the available tools.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 184 | 138 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Continuing Health and Safety working session for the RGE (Contractor) team, including Jose Auli and Carlos Negrón. to cover all relevant topics related to the Cambalache Genera Project, including construction, logistics, health and safety, security, and environmental considerations. An in-depth explanation was provided on the contents and application of the Health and Safety Manual as well as the site-specific manual, emphasizing their importance in daily operations. Additionally, participants were trained on the Procore system, including an overview of its tools and functionalities to facilitate effective project documentation, communication, and compliance monitoring.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Meeting via teams with Jorge Bracero (Genera) and Paola Arroyo (DCMC) to discuss Arecibo meeting with the community and coordination for the Costa Sur engagement meeting.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 184 | 322 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Review and draft correspondence regarding purchasing of material and equipment for Aguirre and Yabucoa sites and also discuss with Gilberto Sucre (DCMC) PMO logistics.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 184 | 138 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended internal meeting with Lemoine IT Support team (Tyler Courville) and Dillon Gilger (Lemoine), Gilberto Sucre (DCMC) to discuss star link connection at the generation sites for the internet access.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams call with Jesus Cintron (Genera), Gilberto Sucre (DCMC) and Gabriel Perez (CDM) to discuss BESS project overview and execution needs.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams call with Anneilia Holton and Gilberto Sucre (DCMC) to review and discuss performance evaluation forms for the PMO employees.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Continued reviewing the draft contract for the BESS Installation at Costa Sur (RFP 4899). Focused on verifying that Attachment A (Scope of Work) accurately reflects all negotiated items while maintaining consistency with the original RFP language and requirements. Ensured that the scope aligns with project objectives, deliverables, and compliance expectations to support a clear, enforceable, and audit-ready contract.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Costa Sur Demolition (RFP 231161) Discussed with Abraham Velazquez (DCMC) multiple safety concerns related to Homeca and explored strategies to address and mitigate these issues through the terms and requirements of the upcoming contract. Focused on incorporating enforceable safety standards, oversight mechanisms, and clear performance expectations to ensure compliance and protect personnel and project integrity.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in the BESS & Peakers weekly Procurement catch-up call with Franklyn Colmenares, Gabriel Perez, Rafael Pabon, Carlos Palomares (CDM Smith) Axel Velez (Genera) Gilberto Sucre, Abraham Velazquez, Cynthia Ortiz (DCMC). The purpose of the meeting was to review project-specific procurement timelines, address outstanding issues, and ensure continued alignment between project delivery schedules and procurement milestones. Discussed recent feedback and updates provided by the Procurement Team, including document submission requirements, pending clarifications, and internal review timelines. Collaboratively assessed potential bottlenecks and identified corrective actions to streamline the procurement workflow in support of FEMA-funded construction activities. This coordination supports effective project management, risk mitigation, and ongoing compliance with FEMA grant administration standards.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in a procurement coordination meeting with Jose Ralat, Sasha Martinez, Saul Falcon (DCMC) Shellsea Maysonnet (DCMC contractor) Sulinnette Pérez, and Axel Vélez (Genera) to evaluate current gaps in the procurement process and their impact on FEMA-funded project administration. Discussed alignment issues between Procurement, Finance, and the PMO, and collaboratively developed a strategy to streamline internal workflows, ensure timely compliance with procurement requirements, and strengthen overall grant management and documentation practices.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Held a strategic discussion with José Ralat (DCMC) and Jesús Cintrón (Genera) regarding the ongoing reevaluation of FAASt fund allocations. The conversation focused on understanding the revised funding landscape, identifying potential impacts on existing and planned projects, and determining how changes in allocations could affect project timelines, scopes, and federal reimbursement strategies. Aligned on next steps to support compliance with FEMA Public Assistance program requirements and to ensure that any necessary revisions to project funding documentation are appropriately supported and submitted for approval.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Began reviewing the draft contract for BESS Installation at Costa Sur (RFP 4899). Identified missing attachments and project schedules critical to finalizing the contract file. Conducted a detailed review across relevant systems and folders to locate outstanding documents and began compiling them into a single, organized package.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Generation Fleet - Reviewed and updated the status of key workstreams and high-priority procurement items in preparation for the BESS & Peakers weekly Procurement catch-up call. This activity ensured that all procurement-related tasks were current, properly tracked, and aligned with project schedules. The updated information supported informed decision-making, interdepartmental coordination, and compliance with FEMA PA construction management and documentation requirements.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I began taking took 2 modules in Procore: 1 project manager and 2 project manager Procore tools. Modules were 2 hours each.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I reviewed some safety topics that may apply to the¿BESS Project according to the activities to be carried out. Aerial lift -1926.453(a)(1)(Important: employees must be trained and authorized), Flag Bearer-1926.201(a) /1926.200(g)(2) (Important: Highly visible clothing, signaling methods with flags and STOP/YIELD paddles), and Housekeeping 1926.25(Important: There shall be no remnants of wood and residual with protruding nails or any other debris in the work areas 1926.25(a), Combustible waste and debris shall be removed at periodic intervals 1926.25(b),and Containers for the collection and separation of all garbage shall be provided. Waste shall be removed at frequent intervals 1926.25(c)).
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I continued taking modules in Procore through a course titled: “The Cultural Shift Toward Prioritizing Safety.” The course covered key topics such as: The current state of safety, understanding and learning from mistakes, delivering effective workshop, combating complacency through incentives, and defining a shared safety value across teams. Additionally, I continued reviewing the Scope of Services – Specification G-3300 (370-535 / End Section 312333-4, Document Effective Date: June 20, 2025).
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT/Apply and customize stamps/ Add media by using Images and Capture tools to boost productivity, standardize document approval processes, and personalize PDF workflows.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT/ Worked with Thumbnails Panel to insert, extract, reorder, combine, and delete pages differentiate between Rotate View and Rotate Pages/Enable, disable, and reposition panels, toolbars, and interface components/ Switch between Profiles to match specific workflows for the project.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. I had several phone calls with RG Engineering project manager, Jose Segarra to discuss the project contract requirements and contract progress. Participated in Team Meeting with Sargent & Lundy Staff, Robert D. Molner, Gilberto Sucre (DCMC), Enrique Laya, CDM Smith, and Angel Alicea Rodríguez (Sargent & Lundy) to discuss the Phase II Request for Comments to the contract (4339_9510) documents.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting in person at Sargent and Lundy Central Offices at Santurce PR to go over the Design Drawings and Project Pending missing items to complete the Issue for Construction Drawings. At the conference table were present Gabriel Pérez (CDM Smith), Gilberto Sucre, and Andres Concepción (DCMC). On the Teams were Mike Kuczynski, Robert Molner, and the Civil Design Staff from the Sargent and Lundy office. Review the bid documents package identified as GENERA-15240-061-0017 for the Installation of the Tesla batteries phase, submitted by Sargent & Lundy at the Aguirre Site. It was also present the selected contractor, RG Engineering, represented by Eng. Jose Auli and Eng. José Segarra. Sargent and Lundy rejected the proposed control room designed by RG Engineering in response to the lack of space for all the proposed equipment. RG Engineering will revise its proposal to incorporate all the required equipment as specified in the arrangement shown in the design.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I continue reading the Agreement with Beta Electric Corporation (BEC). Among the topics read were schedule planned works, labor rates, construction equipment rates, change order and task force forms, and others. Total of pages were 65 to 86.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I continue reading the Agreement with Beta Electric Corporation (BEC). Among the topics read were government contracting requirements, sworn statement, contractor certification requirement, payment bond, performance bond, health, safety, environmental policies, provisions, and others. The total number of pages were 87 to 110.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – I continue reading the Agreement with Beta Electric Corporation (BEC). Among the topics read were representations and conflict of interest, default, termination, suspension, dispute resolution, confidentiality, limitation of liability, anticorruption and human rights, scope of work, protocols and others. Total of pages were 31 to 64.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the technical review of the JSA for the contractor’s office trailer mobilization by refining internal comments and preparing them for discussion with the RG Engineering safety officer (Miguel Rojas). Emphasis was placed on validating the sequencing of tasks, the adequacy of control measures for simultaneous operations, and the clarity of emergency response actions. Additional attention was given to evaluating traffic control near the Punta Este access gate and reviewing the documentation of required permits and certifications. The goal is to ensure the JSA is operationally sound and aligned with site-specific logistics before final approval and mobilization.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Participated in an HSE orientation meeting led by Jean Menay (DCMC), who delivered the General Safety Workshop required by Genera PR for contractor personnel. The session was conducted for members of RG Engineering, specifically Jose Auli and Miguel Rojas. The workshop covered site-specific safety expectations, emergency response procedures, hazard identification, required PPE, and reporting protocols for incidents and near misses. The orientation also emphasized the importance of daily coordination with the DCMC safety team and compliance with Genera’s HSE standards. Conducted a comprehensive review of the Job Safety Analysis (JSA) prepared by RG Engineering for the mobilization and utility connection of the contractor’s office trailer at the Costa Sur BESS project. The evaluation focused on verifying that all high-risk activities such as heavy equipment operation, electrical and plumbing connections, and elevated work during staircase installation were adequately assessed and mitigated. Each task step was reviewed to confirm that control measures align with OSHA standards, NFPA guidelines, and Genera PR’s HSE requirements.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Meeting with Harry Velazquez from RG Engineering, Gabriel Perez from CDM Smith, Franklyn Colmenares from CSA Goup and Wilfredo Rodriguez from Sargent and Lundy to discuss and review the RFC details for the Yabucoa BESS Project.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Continue Evaluating the details of Appendix #1 "Design Drawing' to submit comments to Sargent and Lundy and RG Engineering.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate the details of Appendix #1 "Design Drawing' to submit comments to Sargent and Lundy and RG Engineering.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Participated in an HSE orientation meeting led by Jean Menay (DCMC), who delivered the General Safety Workshop required by Genera PR for contractor personnel. The session was conducted for members of RG Engineering, specifically Jose Auli and Miguel Rojas. The workshop covered site-specific safety expectations, emergency response procedures, hazard identification, required PPE, and reporting protocols for incidents and near misses. The orientation also emphasized the importance of daily coordination with the DCMC safety team and compliance with Genera’s HSE standards. Conducted a comprehensive review of the Job Safety Analysis (JSA) prepared by RG Engineering for the mobilization and utility connection of the contractor’s office trailer at the Costa Sur BESS project. The evaluation focused on verifying that all high-risk activities such as heavy equipment operation, electrical and plumbing connections, and elevated work during staircase installation were adequately assessed and mitigated. Each task step was reviewed to confirm that control measures align with OSHA standards, NFPA guidelines, and Genera PR’s HSE requirements.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the technical review of the JSA for the contractor’s office trailer mobilization by refining internal comments and preparing them for discussion with the RG Engineering safety officer (Miguel Rojas). Emphasis was placed on validating the sequencing of tasks, the adequacy of control measures for simultaneous operations, and the clarity of emergency response actions. Additional attention was given to evaluating traffic control near the Punta Este access gate and reviewing the documentation of required permits and modules certifications. The goal is to ensure the JSA is operationally sound and aligned with site-specific logistics before final approval and mobilization.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Continue Reading and review. MEGAPACK SAFETY OVERVIEW: ENHANCED SAFETY ARCHITECTURE, INDUSTRY-LEADING COMPLIANCE AND THIRD-PARTY VALIDATION, ENHANCED APPROACH TO FIRE SAFETY, 24/7 GLOBAL SUPPORT. Megapack Safe by Design: Low Impact, Built-in Safety, 24/7 Monitoring, Proactive Fire Control, Live Support.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Bess_Aguirre Reading and review. MEGAPACK SAFETY OVERVIEW: ENHANCED SAFETY ARCHITECTURE, INDUSTRY-LEADING COMPLIANCE AND THIRD-PARTY VALIDATION, ENHANCED APPROACH TO FIRE SAFETY, 24/7 GLOBAL SUPPORT. Megapack Safe by Design: Low Impact, Built-in Safety, 24/7 Monitoring, Proactive Fire Control, Live Support.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Walk through the Aguirre Complex to identify possible locations for the project sign installation. The information was requested by Gabriel Pérez (CDM Smith) and Gilberto Sucre (DCMC). Various pictures were taken and should be discussed with the Genera-PR Plan Manager, Alexis Cruz. E-mail sent to Gabriel Pérez (CDM Smith) for site confirmation as requested.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS PROJECT - Participated in a phone call with Basilio Ramos (Sunset Contractors) to discuss coordinating a job site visit to the Vega Baja Site. The purpose of the visit is to address questions and clarify the scope of work related to Demolition Phase II. Meeting will include a comprehensive overview of the scope of work to ensure all stakeholders have a clear understanding of project expectations, requirements, and their individual roles in the successful execution of the demolition phase. Scheduled Attendees for the meeting: Gilberto Sucre, Eduardo Rivera, and Gilberto Soto (DCMC), and Nelson Soler (CDM Smith).
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Review the bid documents package identified as GENERA-15240-061-0017, for the Installation phase submitted by Sargent & Lundy at the Aguirre Site, 17º57'10"N, 66º13'49" W. Included in the Specifications G-3400, review the Division of Responsibilities Table 103-1 to identify the correct distribution of responsibilities between the Designer Sargent & Lundy, the General Work Contractor (TBD) and the Owner Genera PR.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Aguirre BESS Project - Coordinated with RG Engineering Project Manager José Segarra via phone to review contractual obligations and verify progress milestones. Participated in technical meeting with Sargent & Lundy, DCMC, and CDM Smith representatives to review Phase II contract documents and highlight deficiencies in structural detailing within the design package.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 -Project Management ¦ DR 4339 - Hurricane Maria - Returned to the workplace in Arecibo, PR after attending a meeting at the contractor RGE offices in San Juan, PR. The meeting focused on discussing and reviewing the safety plans with the contractor.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Reviewed and approved Submittal 10.04, which covers the procedures and safety measures for load lifting operations using a crane. The submittal includes detailed specifications on crane capacity, rigging methods, lifting plans, and safety protocols to ensure compliance with project requirements and industry standards.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11-Project Management ¦ DR 4339 - Hurricane Maria - Traveled from the workplace in Arecibo, PR to the RGE contractor offices in San Juan, PR to attend a pre-coordinated meeting.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Attended a meeting at the contractor RGE offices to discuss the development and submission of the site-specific manual required for the BESS Cambalache project. Attendees: Jean Menay, Andrés Concepción, Luis Damudt (DCMC), and Jose Segarra (RGE)
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Met in General Contractor (RG Engineering) office in Santurce, San Juan. Met with Jean Menay, Jorge Mercado, Luis Damudt (DCMC) and Jose Segarra, Xiomara Alvarez, Carlos Negron, Wanda Monet (RG Engineering) to discuss Site Safety Plans documents and Security protocols.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Generated correspondence and a list of pending design items to be included in the designers (Sargent and Lundy) drawing tracker. Communicated report to Mike Kuczynski (Sargent and Lundy), Gabriel Perez (CDM Smith). Also sent Demolition drawing markups for review to Sargent and Lundy.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Coordinated with Paola Arroyo (DCMC Partners) to distribute Community Outreach event invitations to Cambalache Plant staff. Coordinated with Jean Menay (DCMC) pending information for personnel access to plant for Friday material delivery activities.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed Procore submittal status updates, organized according to project status. Reviewed Mechanical drawing set in order to publish it in Procore. Coordinated with Luis Duque (DCMC Partners)
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Evaluated submittal RGE-0014 regarding a proposed temporary Parking for contractor personnel. Created a communication with details to request approval from Genera PR (Erick Rocher)
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed Paola Arroyo (DCMC) project presentation that will be used for community outreach in Arecibo Municipality community presentations.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing Procore modules for compliance with Genera. Reviewing RFI answer by Wifredo Sierra of S&L related to specification that may be missing from IFB. Also reviewing the Submittal log of Vega Baja site in Procore.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - The start to pump water out with a vacuum truck of Pull Box Manhole #1 and #2 and also de pump water out of second containment of oil separator for a total of 3,500 gallons of water with oil.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Continue with Procore review for compliance with Genera, this Procore has several video files to review and to understand some of the functionality of how the system works. Ida Ramirez of ARG/CERES sent email related to guard house concern elevation and also requested to upload safety submittal for review in Procore.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with the review of the revised As Built drawing send by Carirma Sanchez of Homeca, after reviewing document was send an email to Carirma Sanchez to clarify an area that Javier Bidot Associate mark a 18" piping going from a Storm Manhole out of Genera property, this made be a mistake or the survey is correct. Carirma Sanchez of Homeca responded to email mention that is correct the survey and drawing reflect the piping route as drawing. IT Dillon Gilger of Lemoine contact me to review an issue with un equipment at Vega Baja site that equipment required configuration.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted scheduled cycle count procedures for assigned inventory zones, with a focus on bin locations AJ 061 through AJ 066. Activities included validating physical stock quantities, reconciling discrepancies against system records, and documenting any variances for further review. This effort supports the broader objective of enhancing data synchronization, improving inventory accuracy, and maintaining reliable, real-time records within the warehouse management system.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted inventory preparations and cycle count documentation activities at the Palo Seco warehouse, in collaboration with Mr. Giovanni Taffanelli from DCMC. The objective was to ensure readiness for upcoming inventory procedures. Tasks included verifying the accuracy of bin locations, analyzing stock levels, and organizing the necessary resources to support an efficient and structured counting process. Mr. Davis Candelario from Strider Consulting participated as an observer to assess and provide feedback on the overall process. These efforts were aligned with operational readiness objectives and aimed to ensure all data and materials were properly prepared in accordance with the scheduled procedures.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted variance analysis to investigate inventory discrepancies and identify irregular stock movements. The review compared physical inventory with system data to determine root causes and detect systemic inaccuracies. Key actions included documenting mismatches by location, reviewing transaction logs for potential data entry errors, and recommending corrective measures to enhance inventory reconciliation practices. The analysis focused on bin locations AJ 061 through AJ 066.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-while working from the Palo Seco warehouse, prepared a consolidated inventory summary report to Mr. Anthony Vega of Genera PR, integrating data from multiple warehouse locations. The report compiled critical metrics such as catalog ID, bin locations, unit counts, unit cost, on-hand balance and cost, variances in quantity and cost, as well as defined minimum and maximum thresholds. This analysis provided a clear overview of inventory health across sites, highlighting discrepancies, stock level deviations, and overall performance. The assessment supported operational planning and decision making by delivering a detailed, cross site evaluation of current inventory conditions and cost exposure. The report covered locations CE 014 to CE 018, AF 026 to AF 043, BC 001 to BC 012, AJ 061 to AJ 066.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted an inventory recount at the Palo Seco warehouse in coordination with Mr. Giovanni Taffanelli from DCMC. The objective was to validate the accuracy of previous cycle count entries, specifically for bin locations AJ 061 through AJ 066, identify any unresolved discrepancies, and ensure alignment between physical inventory and system records. This effort was essential to support audit readiness, reinforce data consistency, and maintain inventory accuracy in accordance with established operational standards.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led a morning job briefing with Hernan Machado, Giovanni Taffanelli, Juan Vallejo and Milton Flores from DCMC. The session focused on reinforcing compliance with inventory procedures, promoting safe operational practices, and ensuring accountability in daily activities. Staff were reminded of the importance of accurate data entry, timely execution of assigned tasks, and strict adherence to safety protocols. The discussion also covered expected deliverables, scheduling coordination, and maintaining alignment with project objectives while minimizing risk and supporting uninterrupted operations.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Grant Management-Procurement & Compliance Review | Direct-PA | Activities necessary for review or procurement or compliance activities or documentation | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. ¿Procurement Package Tracker Update – Using the available information such as Independent Cost Estimate, Scope of Work, RFP, Contracts, Requisitions and Bid Lists forRFP-4456 (Generator Hydrogen Coolers), I reviewed the status of the package, documented missing or pending items (ICE, justification memos, requisitions, scopes of work, RFP schedules, equipment contract confirmations) and flagged the need to confirm evaluation panel members. Related to PW-9510¿FAASt¿A&E.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Grant Management-Procurement & Compliance Review | Direct-PA | Activities necessary for review or procurement or compliance activities or documentation | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. ¿Procurement Package Tracker Update – Using the available information such as Independent Cost Estimate, Scope of Work, RFP, Contracts, Requisitions and Bid Lists for RFP-4523 (Temperature Reduction Station), I reviewed the status of the package, documented missing or pending items (ICE, justification memos, requisitions, scopes of work, RFP schedules, equipment contract confirmations) and flagged the need to confirm evaluation panel members. Related to PW-9510¿FAASt¿A&E.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Called Luis Roman of DCMC to coordinate a meeting to define the reporting parameters for the weekly report format for the BESS Cambalache project on the Procore platform.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Cambalache BESS - Meeting for Safety Plan Discussion Cambalache Bess Program, Jean Pierre Menay, Jorge A. Mercado, Andres Concepcion, Carlos De Jesus from DCMC Partners, Alberto Borelli, Jose Segarra, Wanda Bonet, Javier Reyes from RG Engineering.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS When meeting finish travel back from RG Engineering, 605 Condado Ave, San Juan, 00907 (18.450878, -66.075185) to Calle # 6 B19 Urb. Isabel la Catolica Aguada PR 00602 (18.381939, -67.198501)
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS Travel time from Calle # 6 B19 Urb. Isabel la Catolica Aguada PR 00602 (18.381939, -67.198501) to a meeting on RG Engineering office, 605 Condado Ave, San Juan, 00907 (18.450878, -66.075185)
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria- Review the emails, Recent history (1-2 years) of entry of Cambalache bridge loads send by Clara Padovani Rivera from Genera PR, Cambalache - Design, other emails, Procurement Priorities send by Andres Concepcion (DCMC) and Submittals RGE-0010.3 Title: RGE-0010.3 WORK PLAN FOR TRAILERS UNLOADING on Procore.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Safety Officer | Soto, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria / Managed Vega Baja Genera Site and supervised contractors for their safety to minimize risks and ensure project success. Make sure they comply with the safety. Today I completed 2 modules in Procore: 1 project manager and 2 project manager Procore tools. Modules were 2 hours each. Started reviewing Maria Reyes from ARG certification for approval in Procore and safety Submittal forms for Vega Baja BESS required for safety such as vehicle inspections, ladders inspection and equipment for approval.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels and creating report for Min/Max from locations BC001 to BC012
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BC001 to BC012
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BC001 to BC012
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BC001 to BC012
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BC001 to BC012
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AF 00 026 000 to AF 00 043 000
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AF 00 026 000 to AF 00 043 000.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AF 00 026 000 to AF 00 043 000.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations CE 014 to CE 018 at the Aguirre warehouse to initiate the cycle counts.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location CE 014 to CE 018
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations CE 014 to CE 018, LIST #1573/1574
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations CE 014 to CE 018 , RECOUNT LIST # 1579/1580
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AJ061 to AJ066.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations AJ061 to AJ066 to begin the cycle counts.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1603 and 1604 from locations AJ061 to AJ066 for a total of 81 units.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations AJ061 to AJ066, Cycle Count List # 1601.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Verify compliance for the Buy American Act regarding BESS and Peakers submittals in the Procore platform.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 151 | 604 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/GEN 01 S&L Financial Task Orders & Invoicing ensure documents were created_reviewed_stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team/Various projects incoming documents for review & process/Certification review & process
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management/GEN 01 S&L Financial Task Orders & Invoicing ensure documents were created_reviewed_stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team/Various projects incoming documents for review & process/Certification review & process/S&L Costa Sur incoming documents review & process
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 151 | 302 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the progress of all DCMC team staff in the Procore Platform reaching out to them to update weekly report of Procore Implementation and modules tracker.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Continue the revision of contractual documents regarding federal funding compliance with materials and equipment origin of procedence (Buy American Act).
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 151 | 37.75 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Lauren Wells (Lemoine) to discuss ideas for processing drawing plans in procore for approval prior to being uploaded directly to the Drawings Tool. We suggest to create submittals for drawings plans and run by a predetermined workflow template.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the current status of Financial Tools such as Budgeting and Change Orders to update Carlos De Jesus (DCMC) on upcoming implementation to ease the management of team staff on meetings, entering invoicing data and others.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the contractual clauses regarding the Buy American Act and project equipment and material approvals.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.25 | 151 | 37.75 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Call with Andres Concepcion (DCMC) to discuss ongoing issues while interacting with the Procore platform from the mobile app; filters and categories of submittals.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on suggestion to implement proper tracking of the Buy American Act in terms of specification packages submitted for approval and those that currently are being procured or delivered. This is critical in the continuation of the program and funds provisions from FEMA.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Travel | Direct-PA | Travel necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Travel to Arecibo from Genera PR office Hato Rey with the purpose of distributing in the municipality of Arecibo the invitations for the meeting about the BESS Project in Cambalache.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Review of the Cambalache project PowerPoint presentation. These tasks included verifying the accuracy of all project-related information (dates, names, locations, and figures), cross-checking data with source documents or updates from stakeholders to avoid errors, and replacing outdated content with relevant and current information. These tasks also included correcting the provided information, revising and editing the presentation text for coherence, adjusting and editing images, the timeline in Canva, and the upcoming project milestones.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Deliver and distribute together with municipal employee Rosa Aymat, who coordinates activities in the municipality. The invitations were handed to her, and we held a brief meeting to explain the details of the event.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339- Create a clear and informative email for the Genera PR Team, Jorge Bracero, that outlines all materials to be distributed at the August 11 meeting. This includes Listing and describing each item, clarifying the purpose of each material in the context of the meeting agenda and confirming logistical details: time, location, intended recipients, and format.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Conduct a final review of the Cambalache project PowerPoint presentation, verifying the accuracy of all project-related information during a virtual workshop with Jorge Bracero from the Genera PR team. I edit the text to ensure clarity and coherence, improve sentence structure, eliminate redundancies, and organize the descriptions logically. We refine several images and align the visual elements for consistency. The project timeline is redesigned in Canva, highlighting key phases, deliverables, and dependencies, while also ensuring accessibility. We also update the upcoming project milestones in Canva.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Structural Steel - Fabrication, Structural Steel - Erection and Steel Floor Decking to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed drawings GGS99-EA-000-0004-04; GGS99-EA-000-0004-05; GGS99-EA-000-0004-06; GGS99-EA-000-0005; GGS99-EA-000-0006-01; GGS99-EA-000-0006-02 to verify they meets the required specifications of the projects.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed drawings AGB99-EM-BSS-0001; AGB99-EM-BSS-0002; AGB99-EM-BSS-0004; GGS99-EA-000-001-01; GGS99-EA-000-001-02; GGS99-EA-000-001-03; GGS99-EA-000-002-01; GGS99-EA-000-002-02; GGS99-EA-000-002-03; GGS99-EA-000-002-04; GGS99-EA-000-002-05 to verify they meets the required specifications of the projects.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at BESS project with schedule requirement report guide document considering formats in duration lags, specific calendar user format, logic in fabrication and delivery, updates in resources and man hours, duration and approval as required in the guide for (DCMC) Carlos Rodriguez.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at BESS project with schedule requirement report guide document considering specification document, logic, program, manhours, resources, duration and approval as required in the guide for (DCMC) Carlos Rodriguez.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Shear Stud Connectors, Post-Installed Concrete Anchors and Inspection of Structural Steel to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Conducting a review of BESS project financial data and updating it into the monthly report to refine progress tracking, highlight risks, and improve data accessibility for clearer interpretation.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 122 | 488 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Reviewing the financial data for the Peakers project and incorporating updates into the monthly report to enhance progress tracking, identify potential risks, and improve data clarity for more effective interpretation.
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Direct Project Expenses, | Project Formulation-Travel | Direct-PA | Travel necessary to support project formulation activities | Expense |  | 52 | 52 | 52 | Yes | 146796 | Portosan - Portable Toilet Rental - Vega Baja
2025-07-30 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria |  | Damudt, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Expense |  | 0.7 | 120.4 | 0.7 | Yes | 146796 | Genera PR Deliverable 11-Project Management DR 4339 - Hurricane Maria. 4339_9510 BESS - PW-10710 Meeting Safety Plan Discussion Cambalache Bess Program, Jean Pierre Menay, Jorge A. Mercado, Andres Concepcion, Carlos De Jesus from DCMC Partners, Alberto Borelli, Jose Segarra, Wanda Bonet, Javier Reyes from RG Engineering on RG Engineering Offices.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore Powerpoint for update to Genera.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710. Costa Sur. Performed an on-site assessment to identify and document a new laydown location for incoming equipment deliveries. Activities included a complete walk-through of the designated area, measurement of available space, identification of access limitations, evaluation of required site preparations (clearing, grading, geotextile, crushed stone, fencing), and verification of drainage and safety conditions. Field notes, geotagged photos, and a preliminary layout sketch were prepared and uploaded to the project platform for follow-up.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Velazquez, Abraham | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 225 | 900 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. project # 4339-10710 Costa Sur. Continued conducting an in-depth site walk throughout the facility to assess current construction progress, verify contractor activities against the approved work schedule, and ensure compliance with safety and quality standards. Inspected multiple work zones, and coordinated with to address any deviations or pending issues. Follow-up notes were prepared for integration into the daily site report and shared with the project management team for action tracking.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Costa Sur Weekly Construction Meeting led by Rafael Barrera - DCMC. Provided update on activities during the week. Safety workshop and security requirements for contractor personnel. RFI's and submittal status, IFC continued evaluation, design tracker, additional survey activities, need for rigging study and fiber communications field verification needed. DCMC - Rafael Barrera, Carlos Rodriguez, Raissa Borges & Gilberto Sucre CDM Smith - Gabriel Perez CSA Group - Franklyn Colmenares Sargent & Lundy - Wilfredo Sierra RGE - Jose Segarra
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.75 | 225 | 168.75 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Reviewed Power Point Presentation for Jesus Cintron - Genera Procore's Implementation Status for the PMO Project. Minor changes were done prior to the formal presentation next week. Lauren Wells, Frances Vallejo and Gilberto Sucre - DCMC participated in the meeting.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Vega Baja - Demolition - Homeca Recycling - Change Orders and Liquidated Damages. Gilberto Sucre DCMC provided an analysis of the final Change Orders submitted by the contractor, work not executed from the BOCA activities and Liquidated Damages assessment. Three alternatives were provided to Genera's Legal Team - Kevin Futch, and Francisco Feliu. Jesus Cintron - Genera also was present in the meeting. DCMC received instructions as how to proceed in order to close out the project.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Aguirre and Costa Sur Continued Legal review of pending comments of Project Contract including the Exhibits with Jose Robles - RGE and Francisco Feliu - GENERA for Civil & Structural Packages. Final agreement was reached on both.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Sucre, Gilberto | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Call with Costa Sur Site Manager - Carlos Rodriguez DCMC. Provided Update of activities for the last two weeks and action items from all parties in preparation for the Weekly Construction Meeting.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Veazey, Foster | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Billable-BESS and Peaker's Project Schedule & Budget Meeting. Attendees were Foster Veazey (Lemoine), Gabriel Perez (CDM Smith), Gilberto Sucre (DCMC), Abraham Velazquez (DCMC), Carlos Palomares (CDM Smith) .
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) meeting with Gilberto Sucre (DCMC) and Frances Vallejo (DCMC) to discuss Procore update for Genera.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore financial information.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore submittal configurations for reporting.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore reporting items for RFI and Submittals.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on procurement items for Procore uses.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore response type(s) for Luis Roman (DCMC)
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on safety site inspection for use in Procore inspection tool .
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on more correspondences for Procore for leadership items to be reported to Genera.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on correspondences for Procore items for using the email module for large files.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 225 | 225 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore submittal responses that were approved and getting them updated in the system to reflect the changes.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) worked on Procore permissions for email tool.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Subject Matter Expert | Wells, Lauren | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 225 | 112.5 | 225 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Lauren Wells (DCMC) Meeting with Rafael Calderon (DCMC) to discuss RFIs in Procore for invoicing.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Maceira, Marc | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 184 | 644 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Prepared for the CPM presentation related to RFP 235021. This included a thorough review of the submitted proposal to identify key areas requiring clarification. A detailed list of questions was developed to address these points during the presentation. - Participated in the CPM presentation meeting related to RFP 235021. The purpose of this virtual meeting is for the CPM team to present their offering in more detail for the benefit of the evaluation panel committee of the RFP process #235021 Procurement Integration Automation. Participants from Genera PR: Axel Velez, María Sánchez, Héctor Vázquez, Jean González, Jesús Cintrón; from Acumenian: Emil Urbina, Brenda Lisa, Diana Rodriguez, Gregory Rivera; from CPM: Brenda Torres, Luis Tapia, Emilio Cirino; from Honra: Marc Maceira
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Review of Project Communications and Meetings – Cambalache, Vega Baja, and Costa Sur (GENERA BESS Projects) Reviewed emails received regarding the Cambalache, Vega Baja, and Costa Sur GENERA BESS projects. Participated in a conference call with Andrés Concepción (DCMC) to discuss RGE contractor activities at the Cambalache site. Held a meeting with José Robles and the RGE team, Gilberto Sucre (DCMC), and Gabriel Pérez (CDM Smith) to review the Costa Sur GENERA BESS project. Topics included project status, logistics, safety, security, and construction progress. Attended a conference call with Rosanne Pérez (GENERA) to discuss RGE’s mobilization to the site.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Menay, Jean Pierre | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 184 | 460 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Held a conference call with Andrés Concepción (DCMC) to coordinate RGE activities scheduled at the Cambalache site for the following day. Reviewed Health and Safety documentation submitted in Procore by Ida Ramírez (ARG/CERES) related to the Vega Baja Genera site. Conducted a conference call with Eduardo Rivera (DCMC) to discuss the project documents submitted by ARG (Contractor) for the Vega Baja Genera projects.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Teams call with Gilberto Sucre (DCMC) and Lauren Wells (Lemoine) to discuss Procore presentation which summarizes Procore status, SOPs and Financials.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria-Participated in Teams call with project management teams for BESS and Peaker's project to discuss Budget and schedule. Attendees: Gabriel Perez (CDM), Jesus Cintron (CDM), Franklyn Colmenares (CSA) and Abraham Velazquez (DCMC)
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 2 | 184 | 368 | 184 | Yes | 146796 | Genera PR- Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Attended Costa Sur weekly call with RGE and site management team to discuss design status and project next steps. Attendees: Rafael Barrera (DCMC), Gilberto Sucre (DCMC), Jose Lopez (DCMC) and Jose Robles (RGE).
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Vallejo, Frances | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Call with Jesus Cintron (Genera) to discuss project management role for the BESS and Peaker's project.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed the formal Request for Information (RFI) from FOMB regarding the amendment to Contract No. 102696. Collected all relevant supporting documentation and shared the materials with Mark Merritt and Kelly George (DCMC) to support the development of a comprehensive and timely response.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 184 | 736 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Continued preparing comprehensive response to P3A’s RFI regarding federal funds management and project execution status. Coordinated internal review of all relevant materials and compiled detailed responses to the seven RFI items, including WCA balances, project completion status, FEMA workflow stages, and ER1 cost-share history. Developed a timeline of communications with PREPA and PRDOH, reviewed supporting documentation, and organized corresponding attachments. Drafted and finalized the formal transmittal letter, aligned narrative responses with attachments, and conducted internal quality control prior to submission. Shared with Jesus Cintron, Christian Torres and Kevin Futch (Genera)
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 184 | 552 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Began compiling requested documentation in response to the formal Request for Information (RFI) from the Puerto Rico P3A regarding federal funds management and project execution. Activities included extracting data from internal systems (including FEMA Grants Portal and COR3 records), validating scope descriptions, funding sources, WCA transactions, cost share status, and reconciliation of obligated vs. disbursed funds across all active PWs. Assisted in preparing electronic datasets, verifying project milestones, and annotating FEMA National Workflow (“Snake Diagram”) stages to substantiate progress on recovery efforts under DR-4339.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 184 | 92 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Participated in a strategic project coordination meeting to address the Request for Information (RFI) received from P3A. Collaborated with Esther Rohena, D'Alexzander Gonzalez, Roberto Bosch, Jose Ralat, Pedro Cabrera (DCMC) and DCMC Subcontractors Johanna Diaz and Shellsea Maysonet to review and develop a coordinated response to seven distinct RFI items, including Work Completion Assessment (WCA) balances, project status updates, FEMA workflow stages, and the historical timeline and documentation related to the ER1 cost share program. This activity supports transparent interagency communication and ensures compliance with FEMA Public Assistance grant management and documentation requirements.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Subject Matter Expert | Torres-Sterling, Sheila | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 184 | 184 | 184 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 - Hurricane Maria - Reviewed the formal Request for Information (RFI) from the Puerto Rico P3A regarding federal funds management and project execution.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR Deliverable 11 Project Management DR 4339 Hurricane Maria at the Vega Baja job site. Completed the review and analysis of all existing drawings (DWGs) from Issued for Bid (IFB) and Issued for Construction (IFC) packages. Identified potential change orders related to amendments in the construction contract and the contractor’s scope of work.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I completed reading the 164 pages of the Scope of Services – Specification G-3300 (End Section 409533/ document effective date of June 20, 2025). Additionally, I reviewed several sections of the Construction OSHA Standards that are relevant to the project's scope of work.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I read an article related to Hand and Power Tools, based on OSHA standards (CFR 1926 Subpart I). The purpose of this article is to educate both employers and employees on the proper use of hand and power tools, as well as to identify any associated hazards.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Ramírez Alvarado, Luz | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa (BESS Project) During this period, I continued taking modules in Procore through a course titled: Owner as a Collaborator Certification. The course covered key topics such as: Intro to Owner, Navigating Procore, Intro to Preconstruction, Upload Drawings, Upload Spec Book, Upload Bid Documents, Create a Bid Package, and Create Bid Forms.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Conduct a site inspection with Jose Lopez, and Luis Moctezuma (DCMC) to assess the logistical challenges associated with the delivery of batteries and equipment due to current site conditions.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT/the following project management tasks were completed to enhance tool organization and workflow efficiency: Defined the hierarchy of digital tools: Markups, Tool Sets, Tool Chest, and Profiles/ Added frequently used markups to My Tools and organized them within the Tool Chest/ Identified the benefits of using Custom Tool Sets to streamline repetitive tasks/ Created and organized Custom Tool Sets tailored to project-specific workflows/ Differentiated between Properties Mode and Drawing Mode to apply the appropriate tool behavior during markup and editing tasks.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Martinez Rodriguez, Sunem | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT/ Worked on the review, validation, and implementation of project management processes. Use the zoom, scrolling, mouse wheel, and navigation tools to move through documents. Compare documents using the Split Screen tool. Switch between the Single Page View mode and the Scrolling Pages mode as appropriate. Use bookmarks and page labels to navigate efficiently.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 167 | 334 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Continue reading the project specifications. Among the topics read were site design data, structural design load, project meetings, project schedule, project schedule, submittal procedures, operation & maintenance, earthwork testing, and others. Pages 41 to 81.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 167 | 501 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Start to read the project specifications. Among the topics read were description of the project, definitions, scope of work, division of responsibility, regulatory requirements, existing site conditions, measurements at site, soil data, design drawings, and others. Pages 1 to 40.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Continue reading the project specifications. Among the topics read were inspections & tests, construction facilities, temporary controls, progress cleaning, nameplates & tags, product receiving, storage, handling requirements, startup, testing, commissioning, and others. Pages 87 to 119.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Franco Malave, Sylvia | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 Vega Baja ¦ DR4339 – Continue reading the project specifications. Among the topics read were quality control programs. Pages 82 to 86.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - Continued the safety review of the “Homeca Recycling Demolition” document by analyzing the sequencing of demolition activities and verifying whether critical control points are clearly identified and addressed. Additional focus was placed on verifying compatibility between the demolition timeline and site access controls, including staging areas, perimeter fencing, and signage placement.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Echevarría Tirado, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur – BESS - DCMC Site team lead by DCMC Carlos Rodriguez internal meeting on deliverables for site that include location of subcontractor trailer, access to site parking, site layout, topography drawings and existing utilities of BESS battery project. Additional to this internal meeting DCMC Costa Sur site team had the weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Carlos Rodriguez (DCMC) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's. Conducted a focused safety review of the “Homeca Recycling Demolition” document to evaluate whether the demolition plan addresses critical risk factors and adheres to applicable regulatory standards. The assessment concentrated on identifying potential hazards related to structural collapse, heavy equipment operation, dust generation, hazardous material handling, and fire prevention. Reviewed whether the plan includes proper PPE requirements, clearly defined work zones, and emergency response procedures. Recommendations were documented to align the demolition activities with OSHA standards and Genera’s site-specific HSE protocols. Additional notes were made regarding the need for real-time monitoring during demolition and coordination with adjacent operations to prevent safety conflicts.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur DCMC Site team meeting lead by DCMC Carlos Rodriguez weekly meeting with RGE, contractor for the BESS project lead by construction manager Jose Auli (RGE), Rafael Barrera (DCMC) among others to continue discussions on initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically to permits, safety modules, submittals and RFI's.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rodriguez Bury, Carlos | Project Management-Policy Interpretation | Direct-PA | Interpretation of policies related to client/applicant's recovery, program management, project management, or funding activities | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria- Costa Sur - BESS- Request for proposal review focused on Section 301.5 Earth Excavation and 301.6 Dewatering. Excavation dimensions must allow for formwork, inspection, and installation of waterproofing and utilities. Over-excavation must be corrected with matching concrete at no extra cost. Assessed dewatering responsibilities and equipment requirements to BESS site Costa Sur.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Call with Wilfredo Sierra (Sargent and Lundy) to request a copy of the RFC Tracker for the Yabucoa site. Evaluate the updated RFC tracker activities and status.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Evaluate and create the pipping design and material list to connect the DCMC partners office to the potable water supply.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 – Project Management ¦ DR 4339 – Hurricane Maria – Yabucoa – Started the Procore Workshop module "The Cultural Shift Toward Prioritizing Safety", which focuses on integrating proactive safety practices into daily construction activities. The session covered strategies for embedding safety culture within project teams, aligning site activities with OSHA and local Puerto Rico regulations, and implementing communication protocols that reinforce hazard awareness. Reviewed case studies relevant to BESS site operations and identified potential safety leadership actions applicable to the Yabucoa project. Progress and notes were documented for application in ongoing safety meetings and compliance tracking.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Morales Cruz, Gabriel | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 0.75 | 167 | 125.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria: Yabucoa Start to view the presentation of DCMC Schedule Reference prepared by Carlos de Jesus (DCMC).
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- During the BESS project meeting at the Costa Sur Plant, we reviewed the pending matters from the past two weeks. The discussion covered three main areas of coordination. First, we addressed the arrangements for relocating the contractor’s trailer, ensuring that all logistical requirements and site access considerations are in place. Second, we discussed the scheduling and delivery of safety talks for the contractor’s employees, emphasizing the importance of compliance with site safety protocols. Finally, we followed up with the project designer regarding the updated project drawings, which are scheduled to be completed and delivered by August 15. These discussions allowed us to confirm responsibilities, set clear deadlines, and ensure alignment among all stakeholders to maintain the project’s progress and meet our established milestones.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- Meeting with Site Manager, Carlos Rodrigez DCMC about the status of the past two weeks, where we have continued to track the progress of the BESS project and address key operational matters. During the latest status meeting, we focused on three main areas: Contractor Trailer Relocation – We reviewed the coordination efforts for moving the contractor’s trailer, confirming site access requirements and the necessary logistical arrangements. Contractor Safety Talks – We discussed the scheduling and delivery of safety orientations for the contractor’s personnel, reinforcing our commitment to site safety compliance. Project Drawings Update – We followed up with the project designer regarding the updated project drawings, which remain scheduled for completion and delivery by August 15. The meeting allowed us to clarify responsibilities, confirm deadlines, and ensure all stakeholders remain aligned to maintain the project on track.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur- In preparation for the upcoming BESS project meeting at the Costa Sur Plant, I have been reviewing all relevant documentation and follow-up items from our previous two meetings. My main focus has been to analyze the progress on each action item, identify any pending tasks, and gather the necessary updates from the responsible team members. I revisited the meeting minutes to ensure I fully understood the context and objectives of each pending issue. I also coordinated with the engineering and operations teams to confirm the current status of technical deliverables, and verified that supporting data and reports were up to date. Additionally, I prepared a concise summary of the key points to be discussed, along with any potential challenges that may require decisions during the meeting. This will help maintain focus and ensure we allocate time effectively to the most critical matters. With all materials and updates organized, I am ready to actively contribute to the discussion, provide clarity where needed, and help drive the successful completion of our project milestones.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Barrera Quinones, Rafael | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria BESS Costa Sur As part of the ongoing work for the BESS Project at Costa Sur, I reviewed recent email correspondence to ensure I was fully updated on all project communications and coordination matters. This included verifying updates from various stakeholders, clarifying pending actions, and noting any new requirements or instructions relevant to our next steps. In addition, I examined the topographic plans recently submitted by Javier E. Bidot & Asociados. The review focused on validating the accuracy of the site details, confirming alignment with the project’s design requirements, and identifying any elements that may require clarification or adjustment. These plans will serve as a critical reference for the next phases of project development and coordination with both the engineering and construction teams.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning staff meeting with Aguirre Construction management staff: Sunem Martínez, Jose Lopez, and Luis A. Moctezuma, DCMC. The agenda items included issues related to construction drawings delivery status, general work contractor signage, and notice to proceed schedule dates, as well as general safety topics.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Conduct a site inspection with Sunem Martinez, Jose Lopez, Luis Moctezuma (DCMC) to assess the logistical challenges associated with the delivery of batteries and equipment due to current site conditions.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Moctezuma, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Bess_Aguirre We were working on creating an Inspection Preparation Checklist Form that adapts to the Bess_Aguirre Project using Attachment J and we are review the next standards they are applicate to the project: Part Number:1926 Part Number Title:Safety and Health Regulations for Construction Subpart:1926 Subpart C Subpart Title:General Safety and Health Provisions Standard Number: 1926.20 Title: General safety and health provisions. GPO Source: e-CFR.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Coordination meeting was held between PREPA and Genera PR regarding IT/OT integration projects, which are managed by the PREPA Data and Communications Management Team. The focus was to ensure alignment and avoid conflicts between IT/OT systems and the proposed Battery Energy Storage System (BESS) layout designs. Meeting Attendees: Gabriel Perez (CDM Smith) Franklyn Colmenares (CSA) Mike Kuczynski (CDM Smith) Vincent Skochdopole (Sargent & Lundy) Hector Vazquez (LT Automation) Carlos Irizarry (LT Automation) Andres Concepcion (DCMC) Gilberto Sucre (DCMC) Carlos Rodríguez (DCMC). The revised proposed location for the Aguirre monopole and control room, reviewed by Sargent & Lundy, has been accepted by LT Automation. At the Cambalache Site, there are no issues with the newly proposed location. Sargent & Lundy presented a new option for the Costa Sur Site, which raised concerns from LT Automation. The proposal will be evaluated during a site visit scheduled for next Tuesday by LT Automation. Assessment results will be shared by Monday for further discussion.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - AGUIRRE BESS- Morning meeting with Carlos López, Sunem Martínez, and Luis Moctezuma (DCMC). Discussed the two-week look-ahead schedule to enhance communication and coordination across the site team. Assigned the team to complete the DCMC Office Trailer Mobilization and the Office Supplies Delivery within the week. The team is actively reviewing the bid drawings to provide feedback focused on quality assurance of the design. This proactive review aims to prevent potential change order issues with the upcoming General Work Contractor.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 167 | 417.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Discussion with the Aguirre Team, including Carlos R. López and Sunem Martínez (DCMC), regarding the bid document package GENERA-15240-061-0017 for the Installation phase submitted by Sargent & Lundy. Reviewed Specifications G-3400, focusing on the Division of Responsibilities Table 103-1 to clarify the allocation of duties among the Designer (Sargent & Lundy), the General Work Contractor (TBD), and the Owner (Genera PR). Noted that the bid process has been placed on hold until further notice by the General-PR PMO.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Lopez, Jose | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Meeting was held with Sargent & Lundy to review the Design Drawings and address pending items required to finalize the Issue for Construction (IFC) drawings. Attendees: Gabriel Pérez (CDM Smith), Gilberto Sucre, and Andres Concepción (DCMC) Mike Kuczynski, and Robert Molner (Sargent & Lundy), and representatives from the selected contractor RG Engineering: Ing. Joé Auli and Engineer José Segarra. Reviewed the bid document package RFP-4900, covering Civil & Structural Works for the BESS Phase at the Aguirre Site. Discussed the Value Engineering proposal presented by Enrique Lara (CDM Smith) aimed at reducing the amount of concrete by using individual precast concrete supports. Sargent & Lundy initially rejected this Value Engineering option but agreed to re-evaluate it following a request from the Construction Management Team.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Coordinated with RGE contractor Jose Segarra to complete the access registration process for the Cambalache site. This included compiling documentation with supporting evidence and photo identification, which will be submitted to the client (GENERA) for approval and authorization of site access.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Mercado Torres, Jorge Alexis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Work is underway on the planning and design of a standardized routine work permit format. This permit will be used to document the risks associated with each specific task, the supervisors responsible for the work, and the owners and area managers who authorize the activities to ensure that all personnel are fully informed of the risks involved in their duties and are equipped with the necessary precautions and preparation to perform their tasks safely. This process aims to enhance overall worksite safety and promote accountability across teams.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Received Cambalache construction contract or MSA latest version document. Began to review document and understand the contract conditions.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Met with Gabriel Perez (CDMSmith), Wilfredo Sierra (Sargent and Lundy) and Hector Vasquez (LT Automation) to coordinate PREPA Communication projects.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Managed Procore submittals and RFIs (RFI #24 and Submittal #RGE-0014). Corrected data and distributed to asignees and responsibles to respond. Aligned with Luis Duque (DCMC) the information and maintain consistency.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Reviewed Erick Rocher (GeneraPR) and Carlos Lopez (CW Legal) responses and comments for the temporary parking approval and conditions to be implemented to general contractor (RG Engineering) for planning purposes.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Supported RG Engineering (Carlos Negron) and Jean Menay (DCMC) in the coordination of information to obtain access clearance to personnel from RG Enginering to enter the Cambalache Facility.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Generated project weekly report to be reported to Gilberto Sucre (DCMC) and Genera PR management (Jesus Cintron). Updates project status and pending actions.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Concepcion, Andres | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | PREPA GeneraPR - Deliverable 11 - Cambalache BESS PW#10710 - 4339DR - Met with Genera PR (Roseanne Perez) to discuss regarding the temporary warehouse containers installation methods to be implemented in Cambalache.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1.5 | 167 | 250.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Reviewing in Procore the open RFI's from ARG/CERES. Emmanuel Rosario of Javier Bidot Associate responds to the email sent in regard of the SDMH pipping and he explain that they are two piping entering to the SDMH manhole and one leaving the manhole in direction to Luma that may connect to a catch basin or another manhole and then jumps to the manhole located at the road. Send an RFI to Wifredo Sierra of S&L to confirm if the Vega Baja site will be considering safety shower and eye wash station. Send email to Carirma Sanchez of Homeca for meeting at Genera PR main office to discuss project closing and final change order agreement.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 3.25 | 167 | 542.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Take the Procore quiz exam to be certify as Genera request for all Procore user. Send email to Carlos Lebron of Javier Bidot Associate to see if he can explain a segment at the as built drawing that present the storm water going to a Storm Drain Manhole (SDMH) and to clarify if once enter the SDMH it leaves to an exterior SDMH located at the road out of the boundary of Genera Vega Baja property. Reviewing RFI ARG-R012 that was requested to S&L a drawing in CAD VBB99-CY-000-0200 REV 1, still pending respond by S&L.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Rivera Jordan, Eduardo | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2 | 167 | 334 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. GENERA & DCMC- Vega Baja BESS - Working with new submittal send by Ida Ramirez of ARG/CERES in regard of safety manual, procedure and plans for Vega Baja, all of the submittal required to be redirected to Jean Menay of DCMC for approval. Contact Emmanuel Rosario of Javier Bidot Associate to understand if the drawing was sent on feet scale and they perform the drawing in meters scale. Correction in Procore of submittal send by ARG/CERES due they enter submittal as Tesla and require to be fix in Procore.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.25 | 167 | 208.75 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted a targeted variance investigation at the Aguirre warehouse to address discrepancies identified during previous cycle counts. The review process included analyzing system data, validating bin assignments, and performing physical inspections of storage areas to identify overages, shortages, or misplaced materials. The primary objective was to verify inventory accuracy, determine root causes of variances, and document actionable findings to support corrective actions. This review focused on inventory zones CE 022 through CE 028.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-led an operational sync meeting with Giovanni Taffanelli, Milton Flores, Hernan Machado and Juan Vallejo from DCMC, to reinforce alignment on standardize inventory procedures. The discussion emphasized consistency in task execution, adherence to established operational methods, and the importance of proper material handling and safety protocols. Additionally, due to the high temperatures observed on site, the team was reminded to exercise cautio, remain hydrated throughout the day, and report any signs of heat related discomfort or unsafe conditions immediately.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.75 | 167 | 292.25 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-performed a focused inventory recount at the Aguirre warehouse, specifically covering locations CE 022 through CE 028. The effort is centered on verifying bin assessments, confirming part numbers and item descriptions, and comparing physical stock with system records. Any discrepancies encountered were documented for follow-up investigation, with particular attention given to traceability, data consistency, and alignment with asset control standards. All activities were carried out in compliance with established inventory governance protocols to promote operational transparency and accountability.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-carried out cycle count preparation activities at the Aguirre warehouse in coordination with Mr. Juan Vallejo from DCMC. The effort focused on validating storage locations, updating inventory records, and coordinating resource assignments to maintain system alignment and support accurate execution. Today’s tasks were concentrated in inventory zones CE 022 through CE 028.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-conducted scheduled cycle count operations across inventory zones CE 022 through CE 028, as part of an ongoing inventory governance initiative. The activities included physical bin verification, reconciliation of recorded quantities with system data, and identification of discrepancies related to labeling or item placement. The effort also focused on capturing significant variances, verifying data accuracy, and reinforcing compliance with internal inventory control protocols. Special emphasis was placed on audit readiness by ensuring all findings were accurately recorded and available for subsequent analysis or corrective measures.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Browne, Paul | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-compiled and submitted a comprehensive inventory performance report from the Aguirre warehouse, addressed to Anthony Vega from Genera PR. The report included catalog verification, unit count analysis, maximum & minimum, and variance metrics covering inventory zones CE 022 to CE 028, AF 044 to AF 061, BC 013 to BC 020, CE 001 to CE 006.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-RFI Response | Direct-PA | Development of response to RFI from Recipient and/or FEMA | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Part I Reviewed and compiled requested documentation in response to the formal Request for Information (RFI) from the Puerto Rico P3A regarding federal funds management and project execution. Activities included extracting data from internal systems (including FEMA Grants Portal and COR3 records), validating scope descriptions, funding sources, WCA transactions, cost share status, and reconciliation of obligated vs. disbursed funds across all active PWs. Assisted in preparing electronic datasets, verifying project milestones, and annotating FEMA National Workflow (“Snake Diagram”) stages to substantiate progress on recovery efforts under DR-4339.Related to PW-9510¿FAASt¿A&E.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Cabrera, Pedro | Project Formulation-RFI Response | Direct-PA | Development of response to RFI from Recipient and/or FEMA | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. ¿Part II Reviewed and compiled requested documentation in response to the formal Request for Information (RFI) from the Puerto Rico P3A regarding federal funds management and project execution. Activities included extracting data from internal systems (including FEMA Grants Portal and COR3 records), validating scope descriptions, funding sources, WCA transactions, cost share status, and reconciliation of obligated vs. disbursed funds across all active PWs. Assisted in preparing electronic datasets, verifying project milestones, and annotating FEMA National Workflow (“Snake Diagram”) stages to substantiate progress on recovery efforts under DR-4339. Related to PW-9510¿FAASt¿A&E.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 1 | 167 | 167 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria at the Vega Baja job site. Reviewed all existing drawings (DWGs) from Issued for Bid (IFB) and Issued for Construction (IFC) packages to identify potential change orders. Focused on evaluating the new drawing set released on July 17th, as well as previous drawing releases submitted for Eduardo Rivera Jordan (DCMC).
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Construction Manager | Pesquera, Jaime | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 167 | 668 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria at the Vega Baja job site. Continued review of all existing drawings (DWGs) from IFB and IFC packages to identify potential change orders related to the latest drawing release (July 17th) and previous submissions for Eduardo Rivera Jordan (DCMC). Reviewed and officially closed RFI #6, RFI #12, and Punch List Item #32 in Procore. Revised the newly completed As-Built drawings submitted by Javier Bidot & Associates for accuracy and compliance.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 0.5 | 167 | 83.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed email correspondence related to the proposed temporary parking area for contractors at Cambalache BESS. Focused on environmental approval requirements and potential impacts to the site layout and access routes. Prepared notes for internal discussion regarding next steps.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 167 | 501 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Developed a detailed outline of the data reporting parameters required for the Cambalache BESS project’s weekly progress report form (PW9510). Identified key performance indicators, progress metrics, and site activity categories to be included in the template. Reviewed prior reporting formats, aligned new structure with stakeholder requirements, and coordinated internally to validate data sources and reporting frequencies. This framework will serve as the basis for standardized weekly reporting moving forward.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Senior Technical / Construction Specialist | Damudt, Luis | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3.5 | 167 | 584.5 | 167 | Yes | 146796 | Genera PR ¦ Deliverable 11 ¦ DR 4339 – Reviewed multiple project documents and email threads related to the BESS project at Cambalache (PW9510). This included analyzing the personnel listing for Activity Agreement 1, assessing submittal RGE-0010.3 which details the updated Work Plan for Trailer Unloading, and reviewing RFI #24 regarding storm sewer connections near the cooling towers. Evaluated the proposed unloading procedures, verified personnel allocations against activity scope, and reviewed technical clarifications related to drainage systems. Drafted internal comments, coordinated responses with the engineering team, and flagged pending items for contractor follow-up.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse conducting cycle counts in accordance with the Asset Suite system. Today we are working with locations CE001 to CE006 Cycle Count List # 1606.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Creating the count list report BC013 to BC020
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations BC013 to BC020
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations BC013 to BC020
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2 | 152 | 304 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels and creating report for Min/Max from locations BC013 to BC020
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Flores, Milton | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 152 | 532 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at San Juan warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations BC013 to BC020
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 152 | 456 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, and investigating discrepancies from locations AF 00 044 000 to AF 00 061 000.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-the morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse conducting cycle counts and recounts in accordance with the Asset Suite system. Today we are working with locations AF 00 044 000 to AF 00 061 000.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Machado, Hernan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Costa Sur warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations AF 00 044 000 to AF 00 061 000.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Prepare the lists for locations CE 022 to CE 028 at the Aguirre warehouse to initiate the cycle counts.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria: Aguirre. Preparing the daily report to be submitted to Mr. Paul Browne from DCMC. The report includes daily counts with associated costs, recounts, discrepancies, and inventory maximum and minimum stock levels by location CE 022 to CE 028
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 4 | 152 | 608 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations CE 022 to CE 028, LIST #1590/1591/1592
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 152 | 228 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria. Aguirre. Resumed conducting cycle counts at the Aguirre warehouse using the Asset Suite system. Today, we worked with locations CE 022 to CE 028 , RECOUNT LIST # 1591
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Vallejo, Juan | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria- Aguirre. During the morning briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and set the goals for the day and the week. In addition, any updates or directives from upper management were discussed.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 152 | 152 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – At the Palo Seco warehouse, preparing the lists from locations CE001 to CE006 to begin the cycle counts.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria-at Palo Seco warehouse preparing the report to be submitted to, Mr. Paul Browne from DCMC. This report includes the daily counts with associated costs, recounts, discrepancies, and the inventory maximum and minimum stock levels from locations CE001 to CE006.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 2.5 | 152 | 380 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11 - Project Management ¦ DR 4339 – Hurricane Maria – at the Palo Seco warehouse, working on inventory discrepancies, verifying the cost of each item, identifying the authorized minimum and maximum stock levels, working on investigating discrepancies in Recount Lists #1613 and 1614 from locations CE001 to CE006 for a total of 82 units.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Technical / Construction Specialist EHP | Taffanelli Cuevas, Giovanni | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 152 | 76 | 152 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 – Hurricane – Maria- Set up all the equipment at the workstation to begin the cycle count operations. The morning job briefing with Mr. Paul Browne from DCMC, we reviewed the key points from the previous day and established the goals for the day and week. Additionally, any updates or directives from upper management were discussed.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 151 | 377.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the most recent drawings sets for the Cambalache project prior to publishing them publically to contractor and users.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3.5 | 151 | 528.5 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /S&L GEN 01 Financials Task Order 04 ensure documents were created_reviewed_stored accordingly and archived in an organized & controlled manner/documents to be readily accessible for the project team/Review & process all incoming documents/Review & process all incoming Certifications as requested
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Perez, Theresa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 3 | 151 | 453 | 151 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria Document Control – Data Management /Continue with S&L GEN 01 Financials Task Order 04 Various Projects - ensure documents were created_reviewed_stored accordingly and archived in an organized & controlled manner
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work to provide access to the Email tools to Glorimel Torrado (DCMC) in order to share and exchange project documentation that exceeds typical email attachments capacity.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1.5 | 151 | 226.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Work on the intensive review of the Warehouses Inventory for Palo Seco, San Juan, Costa Sur and Aguirre: incorporating findings and reports to the General BESS-Peakers folders since reports shares data from the 4 warehouses.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review current status and last action taken for Submittals and RFIs in the projects of Vega Baja and Cambalache: RFI ARG-011 in Vega Baja and safety related submittals for Cambalache.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-QA/QC | Direct-PA | QA/QC of project work products (other than grants management or project formulation work products) | Time | 0.5 | 151 | 75.5 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the current settings of the Meetings Tool for VB to verify actual permissions satisfy DCMC staff needs in the platform.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Specialist | Roman Quinones, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 1 | 151 | 151 | 151 | Yes | 146796 | PREPA - Genera PR ¦ Deliverable 11 ¦ DR4339 - Review the specifications for BESS works for the Yabucoa Power Plant prior to begin the uploading and publishing process.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 2 | 139 | 278 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Develop a work continuity plan for the Genera PR team, led by Jorge Bracero, to ensure the group's continuous and efficient operations during the week of August 4th to August 8th. These tasks also included role assignments and alignment with the weekly timeline, taking into account the August 11th meeting in Arecibo. Additionally, follow-up mechanisms were established.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 3 | 139 | 417 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Implement the final revisions to the Cambalache project presentation for printing and delivery to the client in order to receive their final feedback. Additionally, review the record of the community meeting to monitor the number of attendees, and print all the necessary documents that will accompany the presentation. Make additional edits in Canva to the fact sheet document to adjust the size within the available space.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Meeting with the Genera PR team, led by Jorge Bracero, to outline the week's logistics, discuss pending project matters, coordinate next week's work continuity plan, and align the operational timeline.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Recovery Officer | Arroyo, Paola | Project Management-Correspondence | Direct-PA | Development, validation, or review of correspondence related to project management | Time | 1 | 139 | 139 | 139 | Yes | 146796 | PREPA ¦ Genera PR ¦ Deliverable 11 ¦ DR4339 Complete the review and proceed with printing the communication materials intended for the community meeting in Arecibo. These tasks included identifying and applying necessary corrections in content, design, and format to ensure clarity, coherence, and alignment with the event's objectives.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Joint Sealants, Flashing and Sheet Metal to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1 | 134 | 134 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Morning staff meeting with Aguirre Construction management staff: Sunem Martínez, Jose Lopez, and Luis A. Moctezuma, DCMC. The agenda items included issues related to construction drawings delivery status, general work contractor signage, and notice to proceed schedule dates, as well as general safety topics.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -AGUIRRE BESS PROJECT. Reviewed drawings GGS99-EA-000-0006-03; GGS99-EA-000-0006-04; GGS99-EA-000-0006-05; to verify they meets the required specifications of the projects.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Lopez Vallellanes, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 3 | 134 | 402 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria -Conduct a site inspection with Sunem Martinez, Jose Lopez, Luis Moctezuma (DCMC) to assess the logistical challenges associated with the delivery of batteries and equipment due to current site conditions.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at PEAKERS project with schedule requirement report guide document for evaluate contractor documentation considering specification document, logic, program, manhours, resources, duration and approval as required in the guide for (DCMC) Carlos Rodriguez.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Project Management Activities | Direct-PA | Other project management activities not otherwise accounted for | Time | 2.5 | 134 | 335 | 134 | Yes | 146796 | PREPA GENERA PR Deliverable 11 DR4339 Costa Sur- worked at BESS project with schedule requirement report guide document for evaluate contractor documentation considering specification document, logic, program, manhours, resources, duration and approval as required in the guide for (DCMC) Carlos Rodriguez.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | de Jesus, Carlos | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 1.5 | 134 | 201 | 134 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria - Costa Sur - DCMC Site in BESS project team lead by DCMC Carlos Rodriguez attended Teams project meeting on deliverables for site that include pending special plans, IFC drawings, pending survey drawings, tracker file, location of subcontractor trailer, contract status and issue for constructions drawings of BESS battery project. Additional to this project meeting DCMC Costa Sur site team had the weekly meeting with RG Engineering, contractor for the BESS project lead by construction manager Jose Auli (RG Engineering employee), Rafael Barrera (DCMC employee) among others to discuss initial site mobilization, safety, 2 week look ahead deadline, subcontractor responsibilities towards the date of the NTP; specifically, to permits, safety modules, submittals and RFI's.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Cost Analyst / BCA | Duque, Luis | Project Management-Process Implementation | Direct-PA | Review, validation, design, or implementation of processes related to client/applicant's recovery, program management, project management, or funding activities | Time | 4 | 134 | 536 | 134 | Yes | 146796 | PREPA-Genera PR-Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Review Sargent & Lundy Technical Specifications for Cambalache BESS and General Work Contract, Metal Grating Stairs and Fluid Applied Membrane Roofing to verify and ensure environmental inspection works for 4339_9510 BESS-Cambalache project
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue conducting the monthly review and report update of financial data for the BESS projects Cambalache, Palo Seco and Vega Baja. Encompassing budget revisions, actual expenditures, and remaining balances.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue conducting the monthly review and report update of financial data for BESS project Vega Baja, and Costa Sur encompassing budget revisions, actual expenditures, and remaining balances.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Teams meeting with the Costa Sur construction team from DCMC and from RGE contractor to discuss project status and updates and next steps as Safety Plan, mobilization plan, list of personnel amount other documentation needed. Attendees: Gilberto Sucre (DCMC), Carlos De Jesus (DCMC), Jose Segarra (RGE) and others.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Team meeting with Rafael Pabon from CDM Smith to discuss program and project status and updates for "One Pager Weekly Report".
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Meetings & Coordination | Direct-PA | Meetings/coordination necessary for project management | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. MS Team meeting with CDM Smith team Franklyn Colmenares and Manuely Concepcion and Abraham Velazquez DCMC to discuss program and project status and updates for "One Pager Weekly Report.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1.5 | 122 | 183 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Conducting the monthly review and report update of financial data for Peakers project Costa Sur and Yabucoa encompassing budget revisions, actual expenditures, and remaining balances.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 1 | 122 | 122 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Continue conducting the monthly review and report update of financial data for BESS project Costa Sur and Yabucoa encompassing budget revisions, actual expenditures, and remaining balances.
2025-07-31 | Puerto Rico Electric Power Authority | Genera PR | Deliverable 11- Project Management | DR 4339 - Hurricane Maria | Reporting Specialist | Borges, Raissa | Project Management-Data Management | Direct-PA | Management of project data (includes data entry) | Time | 0.5 | 122 | 61 | 122 | Yes | 146796 | Genera PR ¦ Deliverable 11- Project Management ¦ DR 4339 - Hurricane Maria. Conducting the monthly review and report update of financial data for the Cambalache BESS project, encompassing budget revisions, actual expenditures, and remaining balances.
19334.25
[12 empty] | Construction mgmt= | 16172
[12 empty] | Community Engagement | 3162.25
19334.25

## Master CDM FC
Item Date | Employee/Supplier | Quantity | Column1 | Rate | Amount | Project | Plant | Comment | Task PW# | TO/MONTH
2025-01-27 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Multiple | Verify invoices submitted by Jaca and Sierra for Costa Sur. Follow up with SandL Coordinator, miguel, on daguao rfi no 4 to relocate boring 8 due to underground structures. Review email response to rfi4 on daguao and fwd response to Jaca.. Ck with PC about final distribution of pending documents in Procore for CS and Yabucoa geotech reports. | 9510 | TO1 Feb
2025-01-28 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Meeting with samantha and jeff to discuss Peakers Construction Management plan from a cdmsmith stand point. Follow up with Daguao resident inspector for Geotechnical Studies completed work and work to be completed. | 9510 | TO1 Feb
2025-01-29 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers | Multiple | Attended Peakers Construction Mtng - External with CM Team - Genera, CDMC and S&L. | 9510 | TO1 Feb
2025-01-29 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Multiple | Review and close list of Peakers daily logs open on old Procore account per Amol (CDM Smith) worksheet required for migration to new account. Sent email to Amol with findings and comments. | 9510 | TO1 Feb
2025-01-30 | Soler-Lugo, Nelson I | 5 |  | 170 | 850 | Peakers | Daguao | Site Visit to Daguao Ceiba. Oversee works at daguao geotech studies. Luma and Jaca on site. Finishing b8 inside luma subst. | 9510 | TO1 Feb
2025-01-31 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers | Multiple | Review data for Geotechnical reports for Daguao and Jobos. | 9510 | TO1 Feb
2025-01-31 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Communicate with JACA PM to discuss and follow up on missing files for Daguao and Jobos in Procore. Discuss issues found on Geotech Reports and boring logs. | 9510 | TO1 Feb
2025-02-03 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers | Multiple | Internal Peakers Construction Meeting with all CDM Smith PDT. | 9510 | TO1 Feb
2025-02-03 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Daguao | Discuss with Peakers resident inspector works performed today by Jaca and Sierra, Geotechnical and Environmental Studies in Daguao Ceiba. Set up milestones for the week and review daily logs. | 9510 | TO1 Feb
2025-02-04 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers | Multiple | One on One chat with Amol (CDM Smith)to discuss PROCORE requirements for daily logs and Hardware | 9510 | TO1 Feb
2025-02-04 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Multiple | Geotechnical & Env. Studies - Jaca and Sierra - Follow Up Meeting . Discuss current status with Invoices, Change Orders, Pending Weekly Reports for Daguao, Final Reports for Yabucoa, Draft Report for Jobos. | 9510 | TO1 Feb
2025-02-05 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers | Multiple | Peakers Construction Meeting - External with Genera, DCMC and S&L and CDM Smith CM Team. | 9510 | TO1 Feb
2025-02-05 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Daguao | Coordinate and discuss work plan with TOPO / GPR contractor JEBA SOW and entrance to perform works in Daguao. Follow up with SandL Coordinator on Daguao Submittal # 13 Closing and distribution requirements. | 9510 | TO1 Feb
2025-02-06 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Daguao | Site Visit Daguao to ck JACA Geotechnical studies and inspector; Drilling at B4 with One superv. 3 lab. 1 Slrep. Follow up email with SandL on Daguao Submittal #13 Revision 0: Preliminary Logs B-1, B-2, B-5. | 9510 | TO1 Feb
2025-02-07 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Multiple | Discuss work plan for Daguao Topo GPR with JEBA and coordinated field visit start with Genera Operations at Daguao for next 2/10. Verified list of personnel, schedules, drone flight plan for Daaguao works and coordinated with GENERA security. Start review of GENERA - Grid Support Units - DDR-007 - Costa Sur Demolition Specification Issued for Comment - SNL-GENERA-15240-011-0006. | 9510 | TO1 Feb
2025-02-10 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Multiple | Follow up with Security Mngr Digno Cartagena on Daguao Drone Flight Plan requirements and permits for JEBA Topo studies. Worked with JACA PM on revision of Change orders required for Costa Sur Peaker Geotech Studies. | 9510 | TO1 Feb
2025-02-11 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Daguao | Review documentation submitted by JEBA for Daguao Topo Studies; AHA. Discuss with resident inspector required SOW for Topo / GPR . Coordinate drone flight on Daguao property. Review available data from JEBA. Peer review for Peakers resident inspector surveillance report. | 9510 | TO1 Feb
2025-02-12 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Daguao | Attended Genera CM: Draft Responsibility Matrix meeting by Ennes Dean from SandL. Follow up with JEBA; Review documentation gathered today and daily logs for works in Daguao by JEBA. TOPO/GPR and JACA Geotechnical Studies; drilling shelby tubes. Track completed work and discuss milestones with Peakers inspector on site. | 9510 | TO1 Feb
2025-02-13 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Daguao | Follow up with JEBA; Review documentation gathered today and daily logs for works in Daguao by JEBA. TOPO/GPR. Track completed work and discuss milestones with Peakers inspector on site. Coordination with LUMA Corp Security to enter inside Daguao Substation for TOPO/GPR studies. | 9510 | TO1 Feb
2025-02-14 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | Peakers | Daguao | Follow up with JEBA; Review documentation gathered today and daily logs for works in Daguao by JEBA. TOPO/GPR and JACA Geotechnical Studies; drilling shelby tubes. Track completed work and discuss milestones with inspector on site. Sent email to JACA PM in regards to Daguao Submittal #13 Revision 0: Preliminary Logs B-1, B-2, B-5; Submittal #15 Revision 0: Weekly Report No. 4. Follow up email on Procore to PC on Submittal #16 Revision 0: AHA; | 9510 | TO1 Feb
2025-02-17 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Daguao | Site Visit at Ceiba,Daguao. Overview Topographic and GPR works by Javier Bidot Personnel inside LUMA substation. Owner representative on site. | 9510 | TO1 Feb
2025-02-17 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Daguao | Open Work Order with Luma TOC in the morning to continue works inside Daguao Substation yard with JEBA surveyors. Closed Work Order during the afternoon after work completion. Discuss daily work on Daguao with JEBA.ite. | 9510 | TO1 Feb
2025-02-18 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Daguao | Open Work Order with Luma TOC in the morning to continue works inside Daguao Substation yard with JEBA surveyors. Closed Work Order during the afternoon after work completion. Discuss daily work on Daguao with JEBA. | 9510 | TO1 Feb
2025-02-19 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Daguao | Open Work Order with Luma TOC in the morning to continue works inside Daguao Substation yard with JEBA surveyors. Closed Work Order during the afternoon after work completion. Discuss daily work on Daguao with JEBA. | 9510 | TO1 Feb
2025-02-20 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Daguao | Site visit to Ceiba,Daguao. Overview Topographic and GPR works by Javier Bidot Personnel inside LUMA substation. Owner representative on site. | 9510 | TO1 Feb
2025-02-20 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Daguao | Open Work Order with Luma TOC in the morning to continue works inside Daguao Substation yard with JEBA surveyors. Closed Work Order during the afternoon after work completion. Discuss daily work on Daguao with JEBA. | 9510 | TO1 Feb
2025-02-21 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Daguao | Site Visit to Ceiba,Daguao. Overview Topographic and GPR works by Javier Bidot Personnel inside LUMA substation. Owner representative on site. Discuss daily work on Daguao with JEBA.. | 9510 | TO1 Feb
2025-02-21 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Daguao | Open Work Order with Luma TOC in the morning to continue works inside Daguao Substation yard with JEBA surveyors. Closed Work Order during the afternoon after work completion. Follow up with PC and Sand L on Submittal #11 Revision 0: (Draft) Final Report and Drawings for Topographic and Subsurface Utility Survey - Javier E. Bidot | 9510 | TO1 Feb
2025-01-27 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | BESS | Multiple | Coordinate meeting for tomorrow at caribbean office to discuss CM plan with jeffrey mullen. Verify invoices submitted by Jaca and Sierra for Aguirre, Palo Seco. Follow up with Geo Eng. Geologist on soil spreading at vega baja. | 9510 | TO2 Feb
2025-01-27 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | BESS | Multiple | Chat with Genera safety officer to discuss vb demo scope and invited to meeting with Homeca contractor on 1/28. Ck qith PC about final distribution of pending documents in Procore for cambalache, ps and yabucoa geotech reports. Review proposals for transformer studies on VB and Notify by email to BESS PM, gabriel, to ck if contractor was including the listed tasks (ck email) 1/27/25 7:10pm. | 9510 | TO2 Feb
2025-01-28 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Vega Baja | Meeting with Homeca 1 hr Teams to discuss timeline and requirements for pre-start submittals. Eduardo Ramos – Homeca, Priscila Bonet - Homeca, Gustavo Vazquez – Genera, Franklin Colmenares – CDM Smith, Samantha Scarpone - CDM Smith, Manuely Concepción – CDM Smith | 9510 | TO2 Feb
2025-01-28 | Soler-Lugo, Nelson I | 3.5 |  | 170 | 595 | BESS | Multiple | All day Meeting on CDM Caribbean Office with samantha scarpone and jeff mullen to discuss proposed Construction Management plan for Genera from a cdmsmith stand point. | 9510 | TO2 Feb
2025-01-28 | Soler-Lugo, Nelson I | 3.5 |  | 170 | 595 | BESS | Multiple | Continue in all day Meeting on CDM Caribbean Office with samantha scarpone and jeff mullen to discuss proposed Construction Management plan for Genera from a cdmsmith stand point. | 9510 | TO2 Feb
2025-01-29 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Multiple | Teams meeting of 1 hr with S&L and CDM Smith to discuss CM Plan. Construction Meeting disucssing the field processes at BESS sites with Juan Mendoza (CDM), Sam Scarpone (CDM), Bob Ivy (CDM), Rafa Pabon (CDM), S&L team, Enrique Laya (CDM), Gabriel Perez (CDM). | 9510 | TO2 Feb
2025-01-29 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Multiple | Review and close list of daily logs open on old Procore account per Amol worksheet. TEams meeting with Luma SandL Genera and PDT to discuss interconnection packages BESS. Generate and send email to Homeca with inquiries about waste management plan, recycling, and waste reductions. | 9510 | TO2 Feb
2025-01-30 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Started reviewing documentation submitted for safety plan, demolition plan and safety personnel by HOMECA for VB. Chat with Genera safety officer Gustavo on VB BESS requirements. | 9510 | TO2 Feb
2025-01-30 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | BESS | Vega Baja | Back and forward emails with sandl, dean and gene, about submittal register for VB BESS. Review register submitted by (Sargent & Lundy) S&L with DOR comments. | 9510 | TO2 Feb
2025-01-31 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | BESS | Vega Baja | Generated an send email with detailed requirements needed for VB BESS Preparatory Phase Meeting, distributed with assigned CDM Smith resident inspector, Augusto Bobonis. Teams meeting with sandl, gene and deane, about VB submittal register. | 9510 | TO2 Feb
2025-01-31 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Multiple | Teams mtng w genera safety officer,Gustavo Vélez to discuss HOMECA submitted docs for safety plan and safety staff. Discussed and explained PROCORE tools and process, specifications and contract clauses applicable to safety. | 9510 | TO2 Feb
2025-02-03 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Prepared for Situational Awareness meeting for Vega Baja Demo Works. Meeting with SandL,Dean and Eugene, To review CDMSMith initial markups for Homeca submitted Demo Plan VB and to confirm best approach for S&L’s review. | 9510 | TO2 Feb
2025-02-03 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Acted as moderator to discuss with VB BESS Team (Franklyn Colmenares, Richard Charest, Gabriel Perez, Enrique Laya) the following: 1. MPT testing – Contract award, NTP, Duration 2. Diesel Fuel unloading and loading Negotiation, Work Plan, SOP, and Submittal 3. Homeca Changes within their Contract>Additions and Deductions 4. Submittals Review and timing. 5. Homeca Feets on Ground milestone? | 9510 | TO2 Feb
2025-02-04 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Discuss with Project Coordinator and SandL Proposed plan for Protecting transformer at VB BESS project; Submittal #35 . Sent email in Procore. Sent email to Sargent & Lundy (S&L) on "Contractor Parent Guarantee" submittal inquiry. Review insurance documents submitted by Homeca for VB BESS Demo Contract. Review MPT testing Revised Proposal by Beta. Review revised submittal resgister submitted by BESS PC. | 9510 | TO2 Feb
2025-02-04 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Review Homecas submittal #31 rev 1 for VB Demo Contract Permits and recycling methods.Review RFI# 13 for and #14 VB BESS submitted by Homeca. Response provided for RFI#14. Review Diesel quality and Sampling requirements submitted by ELaya for VB BESS. Review HOMECA Payment and Performance Bond. Review BESS Checking Project Needs Tracker 2/3/25 by PM BESS. Conducted VEGA BAJA GT_DEMOLITION CONTRACT_HOMECA_WKLY MEETING_BESS | 9510 | TO2 Feb
2025-02-05 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | BETA Electric Proposal Meeting for MPT testing at VB BESS. Meeting with Pro Energy to discuss VB BESS MPT Testing Proposal. BESS Intercfonnection Meeting with SandL and LUMA. Verified 3D scans for VB BESS site and calculated dimensions for MPT protection; sent to HOMECA PM. | 9510 | TO2 Feb
2025-02-05 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Review comments from SandL to VB DEMO submittal from Homeca for Protection of MPT. Follow up email in Procore to PC for BEss in regards to RFI#14 distribution. Follow up with BESS PC on RFI#13 reviewer requirements. Follow up with Enrique Laya on Possible points of connections at PS tank to dispose diesel fuel from VB BESS Site. | 9510 | TO2 Feb
2025-02-06 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Chat with Project Coordinator (PC) and Genera safety officer to fix submittal stance from Genera for Site Safety Plan submittal for vega baja demolition Contract with HOMECA. Discussion with Enrique Laya to go over photos and possible locations for connections at PS tank for transfering fuel from VB BESS site. | 9510 | TO2 Feb
2025-02-06 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Working with submittal register requirements for VB BESS. Generate and send group email about submittal register practices and requirements for procore. Follow up email on Procore on VEGA Baja BESS Submittal #38 Ck comments from SandL on Homeca. Create and send email to BESS PDT : Project Specifications on Procore_Action Required from S&L_Best Practices: Submittal Builder | 9510 | TO2 Feb
2025-02-07 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Review VB BESS avilable submittals and take notes for discussion. Meet with BESS PC to discuss and review VB BESS submittal and delays. Meeting with Genera Safety Officer and HOMECA PM to discuss issues with HOMECA submittals and Project management. | 9510 | TO2 Feb
2025-02-07 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Review documents provided by BESS PM for General Arrangement Plan for IT/OT ROOMS UPGRADE FEMA PROJECT. Review submittal revised by Sargent & Lundy (S&L) for VB BESS; GENERA - Generation Fleet Storage - BESS - #29.0 Demolition Plan - SNL-HOMECA-15240-061-0001; and GENERA - Generation Fleet Storage - BESS - #35.0 Plan for Protecting Transformer Amended - SNL-HOMECA-15240-061-0002. | 9510 | TO2 Feb
2025-02-07 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Cambalache | Review documents provided by BESS PM "Consideraciones de riesgos Proyecto BESS Camablache - Aon" | 9510 | TO2 Feb
2025-02-10 | Soler-Lugo, Nelson I | 4 | 3 | 170 | 510 | BESS | Vega Baja | Follow up with BETA on Vega Baja MPT testing coordination. Worked with JACA PM on revision of Change orders required for Aguirre and Palo Seco BESS Geotech Studies. Follow up with BESS PM on LUMA Telecom Works for VB BESS. Review and distribute RFI # 13 for Vega Baja BESS. Review BETA Task Order for VB MPT testing; Genera PR 105453 - VB Transformer Assessment. | 9510 | TO2 Feb
2025-02-10 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | BESS | Multiple | Review responsability matrix email sent by Jeff Mullen. Review documents provided for Tesla Operations and Controls Training Demo • Megapack 2 XL - Introduction.mp4 • Megapack 2 XL - Battery Module Bay Deep Dive.mp4 • Megapack 2 XL - Thermal System Deep Dive.mp4 • Megapack 2 XL - Customer Interface Bay Deep Dive.mp4 | 9510 | TO2 Feb
2025-02-11 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Palo Seco | Review Palo Seco Demolition and Decommissioning Plan submitted by SandL PM. | 9510 | TO2 Feb
2025-02-11 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Site Visit to Vega Baja BESS site with Homeca PM to overview and evaluate Abatement Work Zones_Discuss Work Plan Phases. Follow up with BESS PC on Hazmat Plan for VB BESS submittl # 40. Follow up email with Dean Ennes on Vega Baja GT_Demolition Contract_Homeca_OPEN Submittals_2.10.25: S&L Reviews and BESS_Vega Baja: Action Required for Submittal (#35.0: Plan for Protecting Transformer). | 9510 | TO2 Feb
2025-02-11 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Review BESS PM email for Tesla Deliverables_All projects_Update. Review responsibility matrix provided by ELaya for VB BESS site. Follow up with SandL on Vega Baja GT_Demolition Contract_Homeca_OPEN Submittals_2.10.25: S&L Reviews: Noise Monitoring Plan. Conducted VEGA BAJA GT_DEMOLITION CONTRACT_HOMECA_WKLY MEETING_BESS. | 9510 | TO2 Feb
2025-02-12 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Multiple | Interconnection Meeting BESS Genera/LUMA/S & L. Attended Tesla Operations & Controls Training Demo. Sent Procore email to SandL for Submittal #35 Revision 0: Plan for Protecting Transformer. Follow up emails with Homeca PM in regards to pending submittals. | 9510 | TO2 Feb
2025-02-12 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Follow up with SandL on critical submittals review needed to start works in VB DEMO contract. Review Bess checking Project Needs Tracker submitted by BESS PM. Review Genera Safety Officer authorization to start works in VB BESS Demo contract. | 9510 | TO2 Feb
2025-02-13 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | VB Site Visit/ Safety Training: RFP 4898 Civil and Structure Works for BESS at Vega Baja. Juan Mendoza – CDM Smith, Joel Pantojas – Genera, Mike Kuczynski – S&L, Enrique Laya – CDM Smith | 9510 | TO2 Feb
2025-02-13 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | BESS | Vega Baja | Review Tesla partner Portal with provided usernames and password. Coordinate with Geo Engineering work to remove soil cuts from VB BESS site. Coordinate with LUMA Telecom Jose Bonilla entry to VB BESS for required fiber optics cable relocation. | 9510 | TO2 Feb
2025-02-14 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Attended Engineering Presentation RFP 4898 (Event 229767) - 49 MW Battery Energy Storage System Installation at Vega Baja. | 9510 | TO2 Feb
2025-02-14 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Aguirre | Attended Tesla Aguire New Approach Project Meeting. Gabriel Perez Sepulveda – CDM Smith, Jefferson Silver – Tesla, Carlos Melendz – Tesla, Mike Kuczynski – S&L, Vincent Skochdopole – S&L, Reinaldo Romero – S&L, Franklyn Colmenares - CDM Smith | 9510 | TO2 Feb
2025-02-14 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Multiple | Attended Genera's Contract Status by Jose Arsuaga. Review Homeca Insurance Submittal #36. | 9510 | TO2 Feb
2025-02-17 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Worked with review process of Vega Baja Bess Demo Contract Pre-Construction submittals | 9510 | TO2 Feb
2025-02-18 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | On Vega Baja site all day with Geo Engineering to supervise soil cuts sppreading on site and removal of steel drums. Walkdown with All Star Contractor in VB to overview diesel fuel operation sow in VB tanks. Gabriel Martínez – Geo Engineering Geologist / Supervisor, Luis Rojas – Operador Digger GeoEngineering Luis A Rosado – Labor Geo Engineering, Kelwin Maldonado - Labor Geo Engineering, Neil Borrero – All Contractor | 9510 | TO2 Feb
2025-02-18 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | On Vega Baja site all day with Geo Engineering to supervise soil cuts sppreading on site and removal of steel drums. Walkdown with All Star Contractor in VB to overview diesel fuel operation sow in VB tanks. | 9510 | TO2 Feb
2025-02-19 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Second Day; On Vega Baja site all day with Geo Engineering to supervise soil cuts sppreading on site and removal of steel drums. Finished Task. Gabriel Martínez – Geo Engineering Geologist / Supervisor; Luis Rojas – Operador Digger Geo Engineering; Luis A Rosado – Labor Geo Engineering; Kelwin Maldonado - Labor Geo Engineering | 9510 | TO2 Feb
2025-02-19 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Second Day; On Vega Baja site all day with Geo Engineering to supervise soil cuts sppreading on site and removal of steel drums. Finished Task. | 9510 | TO2 Feb
2025-02-20 | Soler-Lugo, Nelson I | 0.5 |  | 170 | 85 | BESS | Yabucoa | Follow up with JACA on Yabucoa BESS Final Geotechnical Report. | 9510 | TO2 Feb
2025-02-20 | Soler-Lugo, Nelson I | 1.5 | 1.5 | 170 | 255 | BESS | Vega Baja | Generate and send email reminder to BESS PM with Pending Actions for VB GT DEMO Contract. Review VB DEMO Contract Insurance Amendment submitted by Homeca Submittal #36 VB BESS. | 9510 | TO2 Feb
2025-03-03 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Communicate with Procore Admin on issues found with Daily Logs Mon 1/13-Tue1/14-Wed1/15_4339_10710_Daguao-4339_1070. Working with gathering data for time comments for Peakers worked hours | 9510 | TO1/March
2025-03-04 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. Follow up with PC on documents available to validate communication for FORMAL NOTICE_GUARANTEED MAXIMUM PRICE CONTRACT_JACA AND SIERRA_GEOTECHNICAL | 9510 | TO1/March
2025-03-05 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-06 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-06 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-10 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-11 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-12 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. Follow up with Genera Procurement manager on issues with Geotechnical Invoicing Studies_Completed Works_Jaca and Sierra_Geo Engineering. Review Yabucoa Submittal #11 Revision 1: Final Report and Drawings for Topographic and Subsurface Utility Survey - Javier E. Bidot. | 9510 | TO1/March
2025-03-14 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-17 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with documentation required for invoicing discussion with Genera lawyers meeting this week. Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-18 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Worked with geotech studies contract requirements to discuss with Genera lawyer advisors on meeting set for tomorrow at 11 am. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-19 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Worked with geotech studies contract requirements to discuss with Genera lawyer advisors on meeting set for tomorrow at 11 am. Gathering data for time comments for Peakers worked hours. Teams meeting with Genera legal Team and external advisors to discuss contract issues within JACA Geotechnical and Environmental Studies contract and invoicing. | 9510 | TO1/March
2025-03-20 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-21 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Sent multiple files to Genera legal advisors in regards to geotech contract and rfp exhibits. Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-03-26 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. Sent email to Genera Legal, Angelina, requesting path to follow with JACA invoices. | 9510 | TO1/March
2025-03-28 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers | Multiple | Working with Geotechnical and environmental studies contracts invoices and change orders. Gathering data for time comments for Peakers worked hours. | 9510 | TO1/March
2025-02-24 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Demo works with Homeca. Office trailer and bathroom mobilization activities. | 9510 | TO2/March
2025-02-24 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Removal of handrails at units 1-1 and 1-2. Battery removal from the battery room. | 9510 | TO2/March
2025-02-25 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Demo works with Homeca. Meeting with BESS PM. Meeting with VB BESS team. Visited VB Site Admin Building with Homeca supervisor to discuss abatement plan for Lead. Witness craft working on parking cutting steel walls from unit 1-2. Witness removal of batteries from battery room. | 9510 | TO2/March
2025-02-25 | Soler-Lugo, Nelson I | 4 | 3 | 170 | 510 | BESS | Vega Baja | Witness dumped handrails on dumpsters for recycling. Witness Stockpiling batteries in pallets. Follow up with DCMC on adding equipment options to the VB daily log module. Follow up with ELaya on Homeca SOV and contract additions and deductions. Follow up with JACA PM on CS, Aguirre and PS invoices with changes requested by GENERA and DCMC. | 9510 | TO2/March
2025-02-25 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Witness laboratory testing for air monitoring. Informed Homeca Safety Officer about requirements for air compressor inspection docs. Working with gathering data for time comments for BESS worked hours. Interconnection Meeting BESS Genera/LUMA/S & L/. | 9510 | TO2/March
2025-02-26 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project.Witness removal stockpille of batteries. Witness cutting steel on parking. Witness installation of water cistern. Witness lead abatement activities with ceramic tiles inside Admin Bldg. Participate on news press site visit with Genera, DCMC,CDMSMith and El Nuevo Dia. Witness lab rep on site and El neuvo dia. | 9510 | TO2/March
2025-02-26 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Lab on site for air monitoring. Informed HOMECA General Manager about acetylene regulators issue.; Not in compliance. Witness Homeca PE attendance on site for site assessment prior to demo per OSHA requirements. Working with gathering data for time comments for BESS worked hours. | 9510 | TO2/March
2025-02-26 | Soler-Lugo, Nelson I | 2 | 1 | 170 | 170 | BESS | Vega Baja | Procore email sent to PC and new CM in regards to Submittal 42 for VB BESS; Project Site Lead Mitigation Stages; Revise and Resubmit. Review documents provided by BESS PM for Weekly Meeting LUMA & Genera Interconnection Studies & RFI Tracker BESS 2/26/25. Review documentation submitted by JEBA for audit on their financial records. | 9510 | TO2/March
2025-02-27 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Overview office trailer electrical connections. Homeca continued works with lead abatement. Witness air monitoring activities by Lab on site. Working with gathering data for time comments for BESS worked hours. | 9510 | TO2/March
2025-02-27 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Continue working with Resident QA Engineer at VB BESS Project. Overview office trailer electrical connections. Homeca continued works with lead abatement. Witness air monitoring activities by Lab on site. Working with gathering data for time comments for BESS worked hours. | 9510 | TO2/March
2025-02-27 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Redacted and sent Procore emails for VB BESS Submittals; #36 Revision 1: Insurance, Submittal #011100-1 Revision 0: Noise Monitoring Plan, Submittal #35 Revision 1: Plan for Protecting Transformer, Submittal #29 Revision 1: Demolition Plan, Submittal #25 Revision 1: Occupational Safety and Health Plan | 9510 | TO2/March
2025-02-27 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Continue working with Redacted and sent Procore emails for VB BESS Submittals; #36 Revision 1: Insurance, Submittal #011100-1 Revision 0: Noise Monitoring Plan, Submittal #35 Revision 1: Plan for Protecting Transformer, Submittal #29 Revision 1: Demolition Plan, Submittal #25 Revision 1: Occupational Safety and Health Plan | 9510 | TO2/March
2025-02-28 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Met new BESS safety director on site. Witness Construction of Office trailer stairs for HOMECA. Meet with BEES PC on site. Followed up with New Safety Director and PC on findings about stairs not in conformance with OSHA reqs. | 9510 | TO2/March
2025-02-28 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Continue working with Resident QA Engineer at VB BESS Project. Met new BESS safety director on site. Witness Construction of Office trailer stairs for HOMECA. Meet with BEES PC on site. Followed up with New Safety Director and PC on findings about stairs not in conformance with OSHA reqs. | 9510 | TO2/March
2025-02-28 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Witness Air Monitoring on site by independent lab. Witness lead Abatement inside guard house bathroom. Followed up with CM on personnel violating safety rules by walking with flip flops inside work zone. Working with gathering data for time comments for BESS worked hours. Follow up with E Laya and Genera legal team on Schedule of values Homeca contract changes. Review HRC Certificate of Liability updated by HOMECA. | 9510 | TO2/March
2025-02-28 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Continue working with Witness Air Monitoring on site by independent lab. Witness lead Abatement inside guard house bathroom. Followed up with CM on personnel violating safety rules by walking with flip flops inside work zone. Working with gathering data for time comments for BESS worked hours. Follow up with E Laya and Genera legal team on Schedule of values Homeca contract changes. Review HRC Certificate of Liability updated by HOMECA. | 9510 | TO2/March
2025-03-03 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Meeting with new CM and E. Laya to discuss current issues with HOMECA SOV submitted. Working with gathering data for time comments for BESS worked hours. Follow up with BESS PM on entrance Sign requirements for VB BESS site. | 9510 | TO2/March
2025-03-03 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Follow up with PC on Submittal # 19 status for PS BESS Geotech Report. Attend Weekly Meeting for VB Bess by CM. Witness lead abatement activities on VB site. GenerATE AND SENT email to CM regarding uncomplete submittals. Follow up with CM on contractor Homeca weekly summary with lack of info. Chat with PC in relation to JACA Geotech invoices. | 9510 | TO2/March
2025-03-04 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. | 9510 | TO2/March
2025-03-04 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Phone call with BESS PM to discuss VB BESS project status. Sent email to CM regarfing Daily Job Report weekly from homeca. Sent email to CM regarding ces plan compliance requirements. Called PE, carlos oquendo, to discuss project status and pui needs. Meet with CM and PUI Inspector on site to chat about permitting requirements and ces plan compliance. | 9510 | TO2/March
2025-03-05 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Follow up with Bess PM and Genera TO PM on CES plan requirements. Meeting with Genera safety manager and officer at the VB BESS site. Meet with BEESS PC and Scheduler to discuss submittals and rfi management. | 9510 | TO2/March
2025-03-05 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Discussed JACA Geotech invoices for BESS sites with PC. Email sent to jaca about invoicing revision. Attended 1.5 hr meeting about all BESS sites with sandl Teams. Attended interconnection meeting with luma. Sent email to PM about sphera group contract needs for vbaja BESS. Witness Homeca fixing stair for trailer, added landing. Work with gathering of data to complete hrs comments for BESS CDM SMith invoicing. | 9510 | TO2/March
2025-03-06 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Cambalache | Meet with Genera legal team to discuss invoicing issues with Geotechnical and Environmental studies by Geo Engineering performed on Cambalache BESS. | 9510 | TO2/March
2025-03-06 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Surveillance over Demolition contract activities by HOMECA Recycling at VB BESS. Meet with Genera legal team to discuss invoicing issues with Geotechnical and Environmental studies by Geo Engineering performed on VB BESS. | 9510 | TO2/March
2025-03-07 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. | 9510 | TO2/March
2025-03-07 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Hauling and dumping srap etals from site into dumpster. Remove dumpsters from site. Housekkeeping and trash collection. Installation of Sediment control devices at storm sewer inlets. | 9510 | TO2/March
2025-03-10 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. | 9510 | TO2/March
2025-03-10 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Overrview works by Genera: Genera personnel on site collecting equipments and materials; removal of bus bars from mpt. Contacted Gnera Procurement Manager for discussin. Sent email to fernando from legal to follow up on invoicing tasks. | 9510 | TO2/March
2025-03-11 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Visited CM at temporary office location located in Atelier Bldg to discuss pending deliverables and contract requirements for Homeca in VB BESS. | 9510 | TO2/March
2025-03-11 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Overview work done by Genera personnel on site, continued removal of bus bars and bus tray parts, electrical fixtures, ss main panel boxes. USrveillance of removal activities; Homeca removed unit 1-1 baffles that were stockpiled at ground level west side of property lot next to property line fence with Luna whse. Witness Homeca working with removal of ss louvers at unit1-2 intake/filter room module plu Hauling and dumping louvers into dumpsters. Worked with time breakdown/description for cdmsmith Eamon and Arsuaga. Sent email to Arsuaga requesting cost codes for charges. Witness Homeca works on collecting scrap material along site and disposing on dumpsters. | 9510 | TO2/March
2025-03-12 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Attended visit from dcmc Program Manager on site. Gave a walk around briefing to all parties. Visited with personnel CM at Atelier Office. | 9510 | TO2/March
2025-03-12 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Met with LUMA Op Supervisor electrical lines issues on VB BESS site. Walkdown facility with luma. Sent procore email to team with steps to follow on LUMA requirements for VB BESS. Witness works of Homeca removing ss louvers from filter intake room at unit 1-1 and collecting removed luminaries from stockpile area and disposal on dumpsters. Witness removal of scrap material from sea container 40ft located at south west of property. Witness housekeeping and collecting miscellaneous scrap material from site. Generated email to CM requesting to log in and log out all trips during the demolition aactivities. Created and forwarded excel form to fill for loging. Reiew manifest reports provided by Homeca. | 9510 | TO2/March
2025-03-13 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project all day. Today Homeca was on site to walkdown and oversee current site issues ith the management team but no work was performed on site. One truck loaded with steel louvers was removed from the site at noon.Walk down on site. | 9510 | TO2/March
2025-03-13 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project all day. Homeca was on site to walkdown and oversee current site issues ith the management team but no work was performed on site. One truck loaded with steel louvers was removed from the site at noon.Walk down on site. | 9510 | TO2/March
2025-03-14 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Homeca did not performed any work on site. Continue working with Procore daily logs for VB Bess. | 9510 | TO2/March
2025-03-14 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Homeca did not performed any work on site. Worked with Procore daily logs for VB Bess. | 9510 | TO2/March
2025-03-14 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Cambalache | Reviewing invoices from Geo Engineering for Geotech studies at VB and Cambalache. | 9510 | TO2/March
2025-03-17 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Homeca did not performed work on site. Walkdown site with Senior CM, sucre; and soto, pesquera, jean, jose, and jesus cintrón. Discussed current issues claimed by Homeca to hold and stop project. Discussed path to follow with Luma for disconnection of secondary luminarie lines and traffic light at pr 2 and temporary connection with meter next to entrance gate. | 9510 | TO2/March
2025-03-17 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Meeting at with sucre jose and frances to discuss contract terms and requirements to use as back up on answering homeca stop of works letter. Witness work for Personnel from Dueñas on site to set up entrance stair with platform and hurricane straps embeded into asphalt. Weekly meeting with dcmc and homeca on vb demo project disussion. | 9510 | TO2/March
2025-03-18 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Meet with Telecomm personnel from Luma on VB site to overview required relocation works. | 9510 | TO2/March
2025-03-18 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Meet with LUMA field personnel jesus romero and cesar sanchez to discuss requirements to shut down secondary power lines connected to luminaries. Discussed requirements for temporary meter. Sit down with CM and provided briefing of assessment done for vb demo site status done back on december 2024. Explained and pointed out points to CM for possible contract amount reductions as a change order | 9510 | TO2/March
2025-03-19 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Walked down site and take multiple pictures of existing units 1-1 and 1-2 to compare with assessment done last december 2024 by me. Discussed findings with new CM, jpesquera. | 9510 | TO2/March
2025-03-19 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Had a teams meeting with Senior CM and CM (sucre and pesquera) to discuss possible contract deductions within the homeca demo contract due to changes within the scope. Attended meeting with Genera legal advisors to discuss issues with Geo Engineering invoices and contract terms. Witness works performed by Luma brigade on site; Removed connection of plant luminaries from secondary overhead lines. Informed PM and sent email with photo links. | 9510 | TO2/March
2025-03-20 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Continue on surveillance over Demolition contract activities by HOMECA Recycling all day. Attended teams meeting with Vega Baja Bess MPT Testing Agency. | 9510 | TO2/March
2025-03-20 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling all day. Attended teams meeting with Vega Baja Bess MPT Testing Agency. | 9510 | TO2/March
2025-03-21 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Witness relocation of oil drums from VB to PS BESS by jean menay. | 9510 | TO2/March
2025-03-21 | Soler-Lugo, Nelson I | 4 | 3 | 170 | 510 | BESS | Vega Baja | Attended Genera safety meeting with osvaldo de jesus. Communicated with PC, franklyn on providing copies of contract documents and specs for transformer testing in VB. Followed up with geo eng admin on invoices status and sent email. Attended Luma staff, visited vb to ck work area for cost estimate to build temporary facilities. | 9510 | TO2/March
2025-03-24 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Working with gathering data for time comments for BESS worked hours. Follow up with geo eng on invoice status for VB BESS. | 9510 | TO2/March
2025-03-24 | Soler-Lugo, Nelson I | 4 | 3 | 170 | 510 | BESS | Vega Baja | Follow up with VB CM pesquera and alexis morales on Luma requirements for temporary meter at VB. Follow up with lauren wells on procore access to photo library edit on VB. Working with daily logs for VB Bess mon 3/17 to Fri 3/21. | 9510 | TO2/March
2025-03-24 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Cambalache | Follow up with geo eng on invoice status for Cambalache BESS. Follow up withEnvironmental Specialist, rosseanne, in camabalache to coordinate soil cuts disposals on site with geo eng. Follow up with Geo Engineering Geologist on cambalache soil cut disposal. | 9510 | TO2/March
2025-03-25 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Working with gathering data for time comments for BESS worked hours. Witness work from Homeca, on site collecting lighting fixtures along project. | 9510 | TO2/March
2025-03-25 | Soler-Lugo, Nelson I | 1 | 1 | 170 | 170 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Continue working ongathering data for time comments for BESS worked hours. Witness work from Homeca, on site collecting lighting fixtures along project. | 9510 | TO2/March
2025-03-25 | Soler-Lugo, Nelson I | 4.5 | 4.5 | 170 | 765 | BESS | Vega Baja | Witness Master electrician work on site; removing secondary low voltage power lines from inside of plant perimeter. Informed homeca to complete ces plan implementation. Beta eng on site with 3 staff and 1 lead to start mpt testing. Installed ground cables and started removal of parts at top of unit. Jha was discussed and signed prior to start. Pointed out the need to add falling and electrocution hazards. Walkdown with Luma Visitors. | 9510 | TO2/March
2025-03-26 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Meet with SandL on site Sand L visited the site to ck available utilities for bess fire protection final design. Beta second day on site 7-4:30 performing mot test. Informed SandL about sanl presence required on site. Homeca on site. Brought excavator with crusher but operator had no certificate. Personell worked with ces plan implementation and leveling off cyclon fence to the ground. . Fill out procore daily log. Prepare spreadsheet with cklist for beta requirements. | 9510 | TO2/March
2025-03-26 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Meet with SandL on site Sand L visited the site to ck available utilities for bess fire protection final design. Continue on Beta second day on site 7-4:30 performing mot test. Informed SandL about sanl presence required on site. Homeca on site. Brought excavator with crusher but operator had no certificate. Personell worked with ces plan implementation and leveling off cyclon fence to the ground. . Fill out procore daily log. Prepare spreadsheet with cklist for beta requirements. | 9510 | TO2/March
2025-03-26 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Cambalache | Coordinate camablache work with geo eng. Soil cut removal. Informed camabalache env lead and safety officer. Sent email to geo eng about invoice status | 9510 | TO2/March
2025-03-27 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. Surveillance over MPT testing by BETA. Stay after work hours with BETA engineer to discuss work completed vs work to be completed. | 9510 | TO2/March
2025-03-27 | Soler-Lugo, Nelson I | 1 | 1 | 170 | 170 | BESS | Vega Baja | Surveillance over Demolition contract activities by HOMECA Recycling. Surveillance over MPT testing by BETA. Stay after work hours with BETA engineer to discuss work completed vs work to be completed. | 9510 | TO2/March
2025-03-27 | Soler-Lugo, Nelson I | 4 | 3 | 170 | 510 | BESS | Vega Baja | Informed about requirements of 480V to complete tests. Witness Sand l on site doing surveillance of MPT Testing. Discuss with PC franklyn path to follow with jaca BESS invoices; Sent email. Fill out ck list for BETA testing. Follow up with CM on temporary power bank meter estimate from luma. | 9510 | TO2/March
2025-03-27 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Cambalache | Reschedule soil cutting disposal at cambalache with geo eng. | 9510 | TO2/March
2025-03-28 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Engineer at VB BESS Project. Surveillance over Demolition contract activities by HOMECA Recycling. All day in vb site. Witness testing of mpt. Fill out daily logs 3/27 and 28. Completed ck lists for beta surveillance and upload into PROCORE. Witness S&L QA activities on site. Witness Genera electrician works on site to provide 480v. Homeca did not worked. Meet with Scheduler and Genera S.O. | 9510 | TO2/March
2025-03-28 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Surveillance over Demolition contract activities by HOMECA Recycling. All day in vb site. Witness testing of mpt. Fill out daily logs 3/27 and 28. Completed ck lists for beta surveillance and upload into PROCORE. Witness S&L QA activities on site. Witness Genera electrician works on site to provide 480v. Homeca did not worked. Meet with Scheduler and Genera S.O. | 9510 | TO2/March
2025-03-31 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers |  | Review of Jaca and Sierra invoices for Geotechnical Studies Costa Sur Peaker project, submitted by Project Coordinator for CM review and signature. |  | TO1 April
2025-04-01 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers |  | Continued review of Jaca and Sierra invoices for Geotechnical Studies Costa Sur Peaker project, submitted by Project Coordinator for CM review and signature. |  | TO1 April
2025-04-02 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | Peakers |  | Meeting with with Peakers Project coordinator to discuss legal terms and Genera steps to follow with Jaca and Sierra invoicing. |  | TO1 April
2025-04-03 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers |  | Reviewing Geotechnical Studies Jaca Invoices for accuracy and comments for Peakers. |  | TO1 April
2025-04-04 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | Peakers |  | Continued reviewing Geotechnical Studies Jaca Invoices for accuracy and comments for Peakers. |  | TO1 April
2025-03-31 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Specialist services @ VB BESS. Meeting in the morning on VB BESS site with New Sr CM; Sucre, Jean, Lopez, Pesquera. Discussed safety issues pointed out by Genera on Gustavo Vazquez email. Sit down in the morning with Homeca PM, Eduardo. Discussed issues with re submittal for transformer protection and demolition plan not available addressing the review comments by S&L. Generated email and distribute in regards to osha and contract requirement for survey required by PE prior to starting demo at VB. | 9510 | TO2 April
2025-03-31 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Aguirre | Reviewed Jaca invoices for the Aguirre project, verifying costs, supporting documentation, and alignment with approved scope and contract requirements to ensure COR3/A&E compliance and eligibility for reimbursement. | 9510 | TO2 April
2025-03-31 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Cambalache | Communicate with cambalache environmental Lead and herminio to set entrance for soil cutings removal with Geo Eng; Review jha and certifications. Coordinate with contractor geologist and dcmc safety manager for security entrance. Work set up for tomorrow 4/1 at 8am. Follow up with geo engineering admin edna collazo on invoicing status. | 9510 | TO2 April
2025-04-01 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Homeca safety Officer came to deliver some wood planks and material for mpt protection. Homeca Supervisor came to receive small forklift. | 9510 | TO2 April
2025-04-01 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Personnel from luma came to overview required materials and equipment to do relocation of telecom on site. Cctv company on site to overview conditions for camera installation proposal. | 9510 | TO2 April
2025-04-01 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Cambalache | Follow up with geo eng supervisor and cambalache env. lead on soil cut spreading works. | 9510 | TO2 April
2025-04-02 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. 4/2. Luma Telecomm crew were on site to start relocation of fiber optics cable entering the old telecomm room located inside the safety guard building. Luma worked from Pull Box/MH located at other side of the road, East of VB GT plant in front of LUMA lot gate. Pulled cable that comes from Vega Alta substation. Luma also installed new run of fiber cable from other side of the road and entering the VB site at South of property line to reach the splice point at mid section of total length. Aerial installation. Technicians spliced cable with existing one to connect with LUMA warehouse. | 9510 | TO2 April
2025-04-02 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Discussed Transformer Protection / Scaffolding work plan with HOMECA SSHO on site and foreman. The material and means and methods observed on the installation does not align with the plan proposed by the contractor and discussed on the site. The contractor is not using correct size of wood timber and type of screws. Not clear on the support member distances and cross members location the contractor is planning to use. As of Today there is no erection drawing showing the specific distances, materials, gauges, etc; as requested by SandL on their Submittal review remarks. The temporary structure must be designed to hold impacts and wind loads. | 9510 | TO2 April
2025-04-02 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Cambalache | Communicate with PC, franklyn and CM,sucre, regarding geo eng invoicing status with genera legal Communicate with Geo engineering to inform about genera legal status with invoicing steps. Communicate with sandl PM on surveillance report for BETA testing done last week by francisco mathews. | 9510 | TO2 April
2025-04-03 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Luma visited project site at VB to finish telecomm utilities and hardware removal. Cut cables comming from antennas located t main pole entering the telecom room. Remove racks and hubs from inside. Work finished Today. | 9510 | TO2 April
2025-04-03 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Homeca continued erection of scaffolding structure at MPT perimeter. Removed wood timber used Yesterday and replaces with 2x4. However, it was observed the screws and methods used by the crew to hold the horizontal main frame made of timber to the vertical steel posts are not acceptable for the loads. It was recommended to install additional attachments at mid sections and timber to attach the wood planks. It was also recommended to use bolts with nuts and washers in lieu of screws. Teams meeting with Genera legal fernando/christian to discuss issues with Geotech contracts invoicing. Genera still indicating contractors must invoice the total LS awarded on each task order without taking in consideration if the testing was or was not done. Genera is supposed to discuss the issue with dcmc on 4/4/25. | 9510 | TO2 April
2025-04-04 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Homeca continued assembly of scaffolding and installation of timber to serve as frame for planks. Mechanic on site to evaluate requirements to fix excavator oil leak. Homeca PM was requested to generate jha for excavator repairs. Work coordinated for Tomorrow , Saturday. | 9510 | TO2 April
2025-04-04 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Meeting with sandl, dean and eugene, to discuss transformer protection requirements and review remarks from DOR that Homeca needs to resubmit. Visited site with Site Manager, jose, and pointed out deficiencies on transformer protection. Homeca did not corrected bolts and nuts. Missing timber for stability. No u bolts as requested. | 9510 | TO2 April
2025-04-07 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. No power on trailer or gate. Main breaker damaged during wknd. Homeca continued closing transformer with wood planks. | 9510 | TO2 April
2025-04-07 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Personnel from homeca on site to weld shear tool attached to the excavator. Personnel from Liferafts on site to pick up ansul co2 cylinders. 72 ea. Removed 2 oxygen and 2 acetylene as well. Removed semi portable extinguisher. Homeca electrician on site to ck main breaker and required parts to fix the power entry. | 9510 | TO2 April
2025-04-07 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Field verify construction of mpt structure. Punchlist items: missing ubolts support at bottom end missing screws. Missing door. Informed homeca superintendent. | 9510 | TO2 April
2025-04-08 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS: tasks include Homeca continued mpt protection, open punch list, and data logging in Procore | 9510 | TO2 April
2025-04-08 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Spent all day at cpm office in Guaynabo. Procore training. Homeca continued mpt protection. | 9510 | TO2 April
2025-04-08 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Multiple | Open punch list. Supervisor informed will be completed by next Friday. Data logging in Procore. | 9510 | TO2 April
2025-04-09 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Homeca started lead abstement phase 2 at unit 1-1. | 9510 | TO2 April
2025-04-09 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Removed one dumpster from site 20 cy. Cutting steel at 1-2 steel frame around intake. | 9510 | TO2 April
2025-04-09 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Kick off mtng conducted before start. Dimensions of 1-1 intake gathered for record. Air monitoring in place. Company. Homeca Recycling Safety Officer, Emanuel Santos; Foreman, Isaac Morales; DCMC Safety Officer, Gilberto Soto. and CDM SMITH QA staff, Nelson Soler | 9510 | TO2 April
2025-04-10 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Homeca continued abatement activities at intake 1-1 zone. | 9510 | TO2 April
2025-04-10 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | 2 dumpsters 20cy out of the site. Meeting with new dcmc Procore lady and site manager to discuss equipment and location addition to procore data base. | 9510 | TO2 April
2025-04-10 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Worked with photo entry and daily log. Procore Daily Log entries for the day shift during Demolition Contract activities with Homeca Recycling. Input of weather data, daily notes, inspections performed, equipments used, waste management data, and photo entries. | 9510 | TO2 April
2025-04-11 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Phone call with carlos lopez during evening to chat about permitting requirements based on federal gov vs executive order from local gov. Visit from Genera Safety Officer and Jean to talked about safety issues with Homeca. Taking photos and working with daily report on Procore. Informed all Team members about requirements to salvage materials including 1-1 turbine. | 9510 | TO2 April
2025-04-11 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Contractor Homeca worked with demo of GT control and battery rooms plus intake filter room. Informed Homeca to be aware of salvage material including pumps and turbine at 1-1. Contractor started demolishing without finishing abatement. Attended call from Homeca PM, eduardo, to chat about project requirements to salvage GT components. | 9510 | TO2 April
2025-04-12 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Saturday. 8 hrs shift at VB. Contractor Homeca started mitigation at 1-2 intake. | 9510 | TO2 April
2025-04-12 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Contractor was advised for not following abatement steps for lead and entering demolition scope without authorization. Meet with field supervisor, Bonet, on site, to discuss work plan for the day. Informed all metals will be considered Pb containing. | 9510 | TO2 April
2025-04-14 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Contractor worked all day collecting metals and debris from site and placing into containers. | 9510 | TO2 April
2025-04-14 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Teams chat with enrique laya to discuss current rfp status for vb and current diesel fuel transfer SOW for VB. Weekly meeting with Homeca, teams. Continued housekeeping at lead abatement zone. | 9510 | TO2 April
2025-04-14 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Started filling log for manifests reports supplied by Homeca. | 9510 | TO2 April
2025-04-15 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Wrote email to BESS PM, gabriel, richard and scott about qa duties. | 9510 | TO2 April
2025-04-15 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continued abatement cleaning activities. Contractor brought skid steer for hauling materials. Altol was on site but unable to do sampling of diesel. Surveillance over HOMECA Recycling crew; continued cleaning and removing the steal from the site to prepare for the Lead clearance. Altol representatives on site (2 ea) Jamie Rodriguez and Jorge Aponte, to perform diesel tank fuel elevation readings and sampling specimens for laboratory results needed before unloading fuel inside Palo Seco Bunker tank B-1. | 9510 | TO2 April
2025-04-15 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Innovative lab on site to test trailer and antenna pole for lead and asbestos. complete daily log on Procore. Filled out and completed log to track manifest reports from Homeca. Innovate Corporation Inspector, Claudio Cabral was on site to perform Asbestos and Lead testing at locations not included on initial studies results submitted by EHSS on July 19,2024. Locations included Telecomm antenna and Storage 40 lf sea container located at South-West of Property. No asbestos/lead found. | 9510 | TO2 April
2025-04-16 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Project scheduler on site to overview and discuss current work status and milestones. | 9510 | TO2 April
2025-04-16 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Today Altol was on site to Take samples of diesel at 3 storage tanks. | 9510 | TO2 April
2025-04-16 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Went to tanks location and field verify with tape tanks dimensions for volume calculations. Homeca continued cleaning of lead abatement phase 2 zone. | 9510 | TO2 April
2025-04-17 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. | 9510 | TO2 April
2025-04-17 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Laboratory on site to collect site samples for lead abatement phase 2 final clearance | 9510 | TO2 April
2025-04-17 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Review Draft report submitted by scheduler, that will be submitted to PREB for VB 1 progress report. Procore daily log input and comments. | 9510 | TO2 April
2025-04-21 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Reviewing definable feature of works and preparatory phase required for Homeca demolition contract tasks. | 9510 | TO2 April
2025-04-21 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Porto San on site to install portable toilet trays, Porto san second crew on site to provide cleaning service to tanks. | 9510 | TO2 April
2025-04-21 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Rod Rodgers came to fix trailer tank. Procore daily logs and photo input. | 9510 | TO2 April
2025-04-22 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Homeca CEO on site to chat abou proposed work plan and projections. | 9510 | TO2 April
2025-04-22 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Cutting 1-1 chimney stack. Dismsantling fuel skid pipes and draining diesel. Demolishing 1-1 motor/ acc. gear enclosure. | 9510 | TO2 April
2025-04-22 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Cutting structural steel at 1-1. 000 Visit today from Genera CEO and FEMA funded projects PM. Phone chat with PUI inspector, carlos oquendo, to discuss ces plan requirements. Fill daily log procore. | 9510 | TO2 April
2025-04-23 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Homeca continue dismantling and cutting structural steel at 1-1. | 9510 | TO2 April
2025-04-23 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Cutting metal at exhaust chimney 1-1 on ground. Draining diesel at skid pump house. Demolish 1-2 engine enclosure. Walkdown site with pui inspector c oquendo. Wkly Meeting with homeca. Generate and send email to PM gabriel about pui inspector. | 9510 | TO2 April
2025-04-23 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Sent email to homeca about uncompliance with lubes and oils removal from units. Procore daily logging. Provide directive to fix ces, fix transformer protection and diesel removal from parts. | 9510 | TO2 April
2025-04-24 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Walkdown site to verify CES plan implementation for compliance. Found deficiencies at CES plan and mpt protection. Informed Homeca. Write notes on procore. Photos. | 9510 | TO2 April
2025-04-24 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Walkdown with GENERA, jaime lopez and omar to overview Turbocompressor 1-1 rigging requirements. Homeca at 1-1 ldismantling and cutting struct. steel frame. Cutting chimney stack 1-1 on ground. Cutting beams and columns. | 9510 | TO2 April
2025-04-24 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Inspected unit 1-1 for oil leaks. Leaks still / observation written on procore. Procore daily input. Requested manifest reports to Homeca. CES plan fabric restored at north gate inlet. | 9510 | TO2 April
2025-04-25 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident QA Inspection services @ VB BESS. Walkdown site with scheduler and BESS PM. Visit from manuel, Genera environmental staff. Walked down site with him and homeca safety officer. Overview oil separator conditions at north west side. Genera provided manifest report to homeca for material with lead landfill disposal. | 9510 | TO2 April
2025-04-25 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Homeca fixing sediment control mesh at water inlets. House keeping scrap metals. Cleaning inside of dike at pump skid station. Installed u bolts at mpt protection. No hot works. No dismantling of structural steel, Man lift damaged. Procore daily input. | 9510 | TO2 April
2025-04-28 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. | 9510 | TO2/May
2025-04-28 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | QA/QC over the following tasks: Dismantling at unit 1-1 acc . compartment area. Dismantling of struct steel at 1-1. Removal of lubricating oil from 1-1. Spoke with homeca ceo about issues with oil and diesel spills within the unit 1-1 dike containment. Requested to improve and install more oil spill control devices. | 9510 | TO2/May
2025-04-28 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Cutting electrical conduits from Unit 1-2. Procore daily log data entry with photos. | 9510 | TO2/May
2025-04-29 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Cutting activities at unit 1-1. Cutting steel structure at 1-1. North side. Issues with oil spill inside dike. Homeca spending time to absorb and contain oil and fuel. Unit 1-1. Instructions provided to hold works until corrective actions taken with spills at 1-1. | 9510 | TO2/May
2025-04-29 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Walkdown site with PUI (Permiso Unico Incidental) inspector visited site. Weekly BESS project status meeting with dcmc and homeca. | 9510 | TO2/May
2025-04-29 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Pumps and plastic tanks used to contain oils and diesel. Contractor brought vac truck at was not authorized due to lack of permits and incorrect eq for fuel. Worked with daily log and photo labeling in procore. | 9510 | TO2/May
2025-04-30 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Draining activities oils and fuel unit 1-1. Bring correct vac truck. Provided genera safety orientation. Suck oils and diesel from unit 1-1. Started vac but did not finished 1-2. Cutting activities unit 1-2.north struct steel. | 9510 | TO2/May
2025-04-30 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Called Genera Environmental, manuel and Yvonne, to drain oilywater pit. Meassure pit volume. Coordinate for next week to bring vac. Called Genera Mngr jaime lopez to authorize demolition of exhaust plenum unit 1-1. Sent email to jose lopez with path to follow. Answer email to PC, fcolmenares about plenum diaposal/recycling task. | 9510 | TO2/May
2025-04-30 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Worked with daily log on procore and photo labeling. Review documentation provided by E laya for diesel fuel tests and change order. | 9510 | TO2/May
2025-05-01 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Perform review and send review remarks to team about homecas diesel fuel operation. Homeca continued cutting s. steel at north of unit 1-2 and metal at south of unit 1-1 acc gear area. | 9510 | TO2/May
2025-05-01 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Worked with photo description and daily log input in Procore. Gathering emails and forms, send email to Site Manager Jose Lopez about trip log and abatement log tracker not followed. | 9510 | TO2/May
2025-05-01 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Followed up with PC, fcolmenares, and homeca on revising DRNA certificate for none asbesto address. Worked with revision of spreadsheet for manifest reports tracking. | 9510 | TO2/May
2025-05-02 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site | 9510 | TO2/May
2025-05-02 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | QA/QC over the following tasks: Continued cutting metal and steel at 1-1 acc gear section south and 1-2 struct steel north. | 9510 | TO2/May
2025-05-02 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Revised manifest report tracker log. Sent emails to Homeca in regards to New requirements for logging truck trips. Provided form. Requested Homeca to provide scale tickets. Review email provided by Safety Manager in regards to diesel operation remarks. Worked with daily log on procore. | 9510 | TO2/May
2025-05-05 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continue working as the Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. | 9510 | TO2/May
2025-05-05 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | QA/QC over the following tasks: Verify materials for Recycling; Two trips to HRC Caguas. Rigger on site to ck rigging task for heavy parts. Homeca cont. cutting at 1-1 north section acc. gear base and struct steel. Cutting struct steel at north side unit 1-2. Cutting struct steel on ground. Dumping steel pieces from 1-2 and 1-1 into containers with skid steer and forklift. | 9510 | TO2/May
2025-05-05 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Walked down site with PUI inspector. Genera on site in the afternoon to monitor removal of oily water with vac truck. Qa on site with genera and homeca safety and supervisor. Procore daily log and photo comments. | 9510 | TO2/May
2025-05-06 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continue working as the Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. | 9510 | TO2/May
2025-05-06 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | QA/QC over the following tasks: Weekly mtng with Homeca teams. Homeca finished fixing pins at excavator. Inspect works. Homeca brought a second offroad fork lift. Inspect equipment. Cont cutting works at Unit 1-1 acc. gear section base. Cont cutting works at struct steel at Unit 1-1 mid section. Cutting 1-2 enclosure side walls and parts at U-1-2 tail section north. | 9510 | TO2/May
2025-05-06 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Procore daily log and photo comments Work with SOP for observations in procore. | 9510 | TO2/May
2025-05-07 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continue working as the Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. | 9510 | TO2/May
2025-05-07 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | QA/QC over the following tasks: Today vac truck was on site to suck oils at 1-2. Arrival and inspection of temporary security shack setup. Rigger from homeca on site to ck rigging. New skid steer today – inspected. Continnue cutting works at U-1-2 gratings and U-1-1 enclosure walls. Cutting pipes and ducts at acc. gear section U-1-2. Cutting side beams at tail section. Removal of ceramics and lighting arrestors, cut cables and ducts and trays at switch gear. | 9510 | TO2/May
2025-05-07 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Started demo at switch gear. Demolition of mech components w excavator at 1-1 mid section behind turbine. Worked with photo comments and daily log input in procore. Generate and send email to safety manager about exclusion zone requirements during rigging. Stayed late to ck demo of switchgear. | 9510 | TO2/May
2025-05-08 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continue working as the Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. | 9510 | TO2/May
2025-05-08 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | QA/QC over the following tasks: Requested new crane operator and foreman from homeca details about exclusion zone during rigging of 1-2 chimney stack. Ck daily log notes and emails on Procore. Continue Demolition and cutting activities at Unit 1-2 North Side, Excitation-Tail Steel base support. Hot Works. Cutting of Generator outside metal enclosure to expose internal components. Unit 1-1. Hot Works. Cutting parts and steel unit 1-2 accessory Gear and Motor Section. | 9510 | TO2/May
2025-05-08 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Continue demolition of switch gear cabinet. Hauling material with excavator and stockpiling at West side of unit 1-1. Cut with acetylene piping, conduits and appurtenances from support Beams South of Unit 1-2 @ acc. Gear/Motor Section Arrival of Homeca 50 ton crane to the site. Inspected. Homeca electricians visited the site to overview work requirements for temporary PREPA Meter and guard house electrical connections. Review Homeca's Job Safety Briefing, Hot Works Permit and Attendance Sheet for Today | 9510 | TO2/May
2025-05-09 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continue working as the Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. | 9510 | TO2/May
2025-05-09 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | QA/QC over the following tasks: Continue hot works at unit 1-1 generator steel cover, 1-2 excitation base frame, 1-2 acc gear / motor components and frame. Replaced man lift to 100 ft model. Inspected. Excavator hauling metals to 80 cy bin container with grapper tool. Pui inspector on site to overview ces compliance Walkdown site. | 9510 | TO2/May
2025-05-09 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | The staff stayed doing housekeeping along the project site and collecting scrap metals from unit 1-1 and 1-2 perimeter. Working with procore photo comments and daily log. Wrote observation #1 in procore. | 9510 | TO2/May
2025-05-12 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continue working as the Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. | 9510 | TO2/May
2025-05-12 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | QA/QC over the following tasks: Meet New site manager. Contractor was working with cutting of chimney stack on ground unit 1-1 west of site. Cutting unit 1-1 exciting frame base. Cutting unit 1-1 generator metal frame to expose internal components. Cutting anchor bolt base plates at excitation section unit 1-2. Cutting steel at unit 1-2 acc gear/engine section south side of unit. Excavator with demo hammer doing demolition of concrete base unit 1-1 intake filters location. Remove sediment and broom at north entrance gate next to storm water inlet. | 9510 | TO2/May
2025-05-12 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Verify and audit available oxygen/ fuel regulators. Personnel were cutting bolts at unit 1-2 exhaust stack flanges prior to rigging. Coordinate with Genera env. lead Manuel removal of sediments from oily water pit at north west of site. Opened observation no 2 due to lack of speed from Homeca on delivery of scale tickets. Issue with dust control during demolition of concrete. Measures taken not acceptable. email to homeca requesting corrective action with dust control. Procore daily logging and photo albums. | 9510 | TO2/May
2025-05-13 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Started rigging of unit 1-2 exhaust stack. Removal of baffles and two sections. Cutting at Unit 1-1 generator encasement, excitation support beams, turbo compressor zone support beams. | 9510 | TO2/May
2025-05-13 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Attended Visit from new GC that will do next phase. Walkdown with site manager. Attended Visit from Genera environmental to clean oily water pit. Attended Visit from pui inspector carlos oquendo. W Weekly BESS VB project meeting with homeca by teams. | 9510 | TO2/May
2025-05-13 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Procore daily log input and photos . Review submittal from Homeca for diesel fuel transfer operation. Submitted review remarks to site manager jose lopez for distribution. Observation was generated on procore due to non conformance with not providing scale tickets. Observ 1 and 2 still open. Inspected dust control fan brought to the site. Requested evidence to validate bolt grade used for rigging lugs attachments. | 9510 | TO2/May
2025-05-14 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Overview work by Genera environmental, cont. cleaning oily water separator. Rigging activities cont. in VB at u 1-2 exhaust stack. 2 additional sections. 4 to date. | 9510 | TO2/May
2025-05-14 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Hot works cont. at generator base support beams. Hot works cont at plenum section base support structure. Hot works at turbo compressor base support beam. All at unit 1-1. Removal of baffles from exhaust stack 1-2 section 1-4. Burning holes at 1-2 struct steel top structure for rigging. Demolished with shears exhaust stack parts at west of project. | 9510 | TO2/May
2025-05-14 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Procore meeting with lauren wells and CDM team. Phone chat with bess Project Coordinator regarding geotech studies invoice. Procore daily log input and photos . | 9510 | TO2/May
2025-05-15 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos . Excavator with grapper was hauling and dumping all metal cuts from Unit 1-1 excitation, Generator and Turbo Compressor Supporting Base Frame; stockpiled West side of unit. Hauling and Dumping metals for recycling inside 80 cy container. To be recycled at HRC Caguas. Excavator with grapper hauled and dumped Rebar stockpiled at South side of unit 1-1. | 9510 | TO2/May
2025-05-15 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Personnel from Homeca spent time doing housekeeping at inside of unit 1-1 containment structure and perimeter Excavator with grapper hauling and dumping crushed metals from unit 1-1 exhaust stack stockpiled at West side of project. Fueling Station Area. Truck with 80 cy container was transported to HRC in Caguas yard. Rigging personnel continued burning holes with oxy-fuel equipment to set up rigging lugs and slings to lift the steel structure located at unit 1-2 exhaust perimeter. Crane lifted top structural steel structure from unit 1-2 exhaust and set module on the ground. To be cut with oxy-fuel equipment for recycling. Tanks inspection for use made by Emmanuel Santos and inspected by safety to continue labor. Used crane to lift and remove exhaust stack Section #5 from Unit 1-2 Used crane to lift and remove exhaust stack Section #6 from Unit 1-2 Removal of Structural Steel members from chimney stack U 1-2 main frame East side top Beams Removal of exhaust pipe Unit 1-2 @ chimney stack location West side. Loading of exhaust stack sections 5 and 6 (last 2 sections) in top of platform. To be recycled at HRC Caguas. | 9510 | TO2/May
2025-05-15 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Project Management Team walked down project site with Homeca Representative to identify work completed vs work to be completed and set milestones and projected completion times. | 9510 | TO2/May
2025-05-16 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos . Excavator with grapper, removed baffles and crushed metal from last exhaust stack unit 1-1 stockpiled on ground level at West side of plant. | 9510 | TO2/May
2025-05-16 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Rigging personnel continued burning / cutting activities with oxy-fuel equipment. Using Man lift and Crane. Set up rigging lugs and chains for lifting and removing steel structure members located along unit 1-2 turbo compressor plenum perimeter. Cutting structural steel members into small pieces, at ground level, for future recycling.1-1 Cutting Base Support Steel frame, Unit 1-1 @ Generator and Load Gear Section Homeca Electrical Subcontractor, JN Elect. were on site, crew of 5 and 2 utility trucks. Installation of temporary wood support with required circuit panel, breakers, conduits, and conductors. Provide wood supports to hold aerial cables needed for the temporary Guard Shack power. | 9510 | TO2/May
2025-05-16 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Homeca Subcontractor,ADL, visited the site and walkdown diesel tank containment area with project QA, Site Manager and Homeca S.O. to identify best point and method for connection required to unload the diesel fuel. Excavator hauled and stockpiled scrap metals from diesel unloading area to North-West corner of unit 1-1. Stockpiled baffles removed from exhaust stack. Housekeeping with skid steer inside Diesel fuel unloading station slab. Placing insulation inside dumpster. Gather information Homeca's Safety Job Briefing, Attendance Sheet and Hot works Permit | 9510 | TO2/May
2025-05-17 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos Rigging personnel continued burning / cutting activities with oxy-fuel equipment. Using Man lift and Crane. Set up rigging lugs and chains for lifting and removing steel structure members located along unit 1-2 turbo compressor plenum perimeter. Cutting structural steel members into small pieces, at ground level, for future recycling. 1-1 Cutting Base Support Steel frame, Unit 1-1 @ Generator and Load Gear Section Removal of Unit 1-1 Plenum and relocate at north side of Unit 1-1 Hauling and dumping Metals from unit 1-1 support base and structural steel from 1-2 exhaust stack structure. | 9510 | TO2/May
2025-05-17 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Homeca's CEO, Carlos Sanchez, was on site. Walked down project with Homeca's SO, Site Mngr and QA to overview remaining tasks and path to move forward with projected milestones to complete the work on or before May 31. Gather information Homeca's Safety Job Briefing, Attendance Sheet and Hot works Permit | 9510 | TO2/May
2025-05-19 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos . | 9510 | TO2/May
2025-05-19 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Charlies crane was brought to the site to do the rigging of turbocompressor unit 1-1 plenum and generator. Personnel continue cutting steel at unit 1-2. Using 50 ton crane for cutting task. Personnel worked at 1-1 cutting activities until rigging of turbo compressor. ADS came to set up fittings and valves at main tank for diesel transfer to start tomorrow. | 9510 | TO2/May
2025-05-19 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Phone call in the afternoon w jaca j osorio PE to chat about invoices. Spent time making spreadsheet to track diesel tankers. Gather information Homeca's Safety Job Briefing, Attendance Sheet and Hot works Permit | 9510 | TO2/May
2025-05-20 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos | 9510 | TO2/May
2025-05-20 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Today we started diesel transfer to PS. Transferred 48,000 gals. 5 trips. Spent must of the shift tracking fuel trips, logs and placing tie wraps with control numbers to be provided at the end to Genera. Filing into procore. Attended Pui indpector, was on site for weekly visit. Cont. cutting structural steel into pieces. Cutting base support at U1-1 turbo compressor and load gear with generator base. | 9510 | TO2/May
2025-05-20 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Hauling activities; scrap metals and stockpiling at north of 1-1. Removal of plenum at U1-2. Cutting base at load gear section U1-2. Cutting supports at turbocompressor U1-2. Lift and remove turbo compressor 1-2. | 9510 | TO2/May
2025-05-21 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos. | 9510 | TO2/May
2025-05-21 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continue diesel fuel transfer operation. Spent must of the shift tracking fuel trips, logs and placing tie wraps with control numbers to be provided at the end to Genera. Filing into procore. One tanker was left full at the end of the day to start tomorrow at 6am Weekly BESS project meeting with CDM and Genera. | 9510 | TO2/May
2025-05-21 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Charlie crane continue on site dismantling crane. 80cy truck on site to pick up metals from unit 1-1 and 1-2. Attended PUI inspector, walkdown storm water inlets. Informed Contrator to fix damages.. Continue cutting activities at unit 1-1 and 1-2. Gather information Homeca's Safety Job Briefing, Attendance Sheet and Hot works Permit | 9510 | TO2/May
2025-05-22 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos | 9510 | TO2/May
2025-05-22 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Continue diesel fuel transfer operation. Spent must of the shift tracking fuel trips, logs and placing tie wraps with control numbers to be provided at the end to Genera. Filing into procore. Started day with Tanker left full Yesterday. Diesel fuel Trasfer was stopped Today due to issues with subcontractor. Walkdown site with PUI inspector. | 9510 | TO2/May
2025-05-22 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Meet with LUMA to coordinate relocation of power meter. Coordinate with homecas electrician. Continue cutting activities at unit 1-2 Started collecting metals with excavator magnet. Started draft of punch list items Gather information Homeca's Safety Job Briefing, Attendance Sheet and Hot works Permit | 9510 | TO2/May
2025-05-23 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos . PUI inspector on site. Demolition of concrete building. | 9510 | TO2/May
2025-05-23 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Spent time taking dimension of inside rooms and bathrooms @ admin house. Walkdown inside Diesel tank dike to identify storm water inlets. Excavator was hauling scrap metals from U1-2 and stockpiling. Moved trailer conex to create space. Demolition of admin building. Provide input to project scheduler, was on site today. | 9510 | TO2/May
2025-05-23 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Excavator with crusher was brought today with new operator. Inspected. Safety training provided. Sent email with punch list items, pending tasks, to team players. Gather information Homeca's Safety Job Briefing, Attendance Sheet and Hot works Permit | 9510 | TO2/May
2025-05-24 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Resident Construction Quality Management Support for Vega Baja BESS.Provide technical support and Surveillance over the contract requirements during the Demolition Contract within the Genera Vega Baja Gas Turbines site. QA/QC over the following tasks: Procore daily log input and photos . Worked on site with DCMC Safety Officer. Gather information Homeca's Safety Job Briefing, Attendance Sheet and Hot works. | 9510 | TO2/May
2025-05-24 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Personnel was power washing unit 1-2 concrete foundation. Removing rebar steel from concrete debris from old admin bldg structure. Demolish old storage conex. Truck with dumpster 80cy on site to pick up and remove metals from conex and axles. Instructed Project foreman and safety officer to dispose ac units following correct protocols. Requested certificate from ac tech certifying ac units free of gas refrigerant. | 9510 | TO2/May
2025-05-24 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Housekeeping along project site. Restoration of filter fabrics and sediment control socks along project site. Cleaning inside of storm water inlets. Spent time reviewing Geo Eng invoices for VB | 9510 | TO2/May
2025-05-28 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Cambalache | Finished reviewing Geo Eng. invoices for Cambalache. Sent signed docs with comments to Project Coordinator. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-05-28 | Soler-Lugo, Nelson I | 1 | 1 | 170 | 170 | BESS | Vega Baja | Finished reviewing Geo Eng. invoices for VB. Sent signed docs with comments to Project Coordinator. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-05-28 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the following tasks: Housekeeping activities along unit 1-1 and 1-2 perimeter. Personnel cutting rebar protruding from concrete foundations. Requested homeca Safety Officer to cover on ground openings at 1-1 and 1-2 pits. Personnel dismantling mechanical components at fueling pump house. Vacuum truck on site to clen inside diesel pipelines and drain from main tank to old units fuel pump skid station. | 9510 | TO2 June
2025-05-28 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Vega Baja | Continue Geotech studies invoice review for jaca and sierra. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-05-28 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Recommended to remove poles and lighting fixtures, cyclone fences at fueling station. Data gathering and photos. Input notes and comments into Procore Daily Log. | 9510 | TO2 June
2025-05-29 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Aguirre | Review of Jaca and Sierra invoice review for Aguirre. Sent signed documents to Project Coordinator. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-05-29 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Cambalache | Review of Jaca and Sierra invoice review for Cambalache. Sent signed documents to Project Coordinator. Invoice review/approval for accuracy and eligibility of the project as part of the compliance review. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-05-29 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the following tasks: Data gathering and photos. Input notes and comments into Procore Daily Log.Sent internal email regarding RFI process for new VB project. Communicate with electrician for load census request by Luma. Received document late during night. Review with comments and received revision. Submitted to Luma | 9510 | TO2 June
2025-05-29 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Surveillance over the following tasks: Dismantling mechanical appurtenances, pumps, valves and fittings at fueling station. Dismantling cyclone fence at fueling station. Demolishion of structural steel and ceiling at fueling station shack. Demolition of oil containment/storage steel shack. Demolition of concrete pit demolition of pump skid foundation. Demolition of one concrete pole at fueling zone. Dismantling lighting fixtures. Cleaning of inside area between units 1-1 and 1-2. | 9510 | TO2 June
2025-05-30 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Palo Seco | Surveillance of Transportation of horizontal pumps to Palo Seco. | 9510 | TO2 June
2025-05-30 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Costa Sur | Worked with Jaca and Sierra invoice review for Costa Sur. Submitted to Project Corrdinator for payment. Invoice review/approval for accuracy and eligibility of the project as part of the compliance review. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-05-30 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Data gathering and photos. Input notes and comments into Procore Daily Log. Surveillance and quality management over the following tasks: Back and fwd communication with luma management in regards to temporary meter connection. Take photos and prepare email for luma. Luma finally accepted to connect. Received Luma staff on site to overview works. Climbed Diesel fuel tank with Altol and Genera reps. To meassure diesel tank volume. | 9510 | TO2 June
2025-05-30 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Surveillance over Homeca cleaning activities over concrete slab at west lane. Demolishion of concrete structure oil lube containment shack. Washing and removal of fueling pump house liner. Cut pipelines. Installed cap on top of pipeline next to old pump house skid. Disposal of 2 loads of metal for recycling. Walked down site with PUI inspector on site to check CES compliance. | 9510 | TO2 June
2025-06-02 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Data gathering and photos. Input notes and comments into Procore Daily Log. Surveillance over diesel fuel transfer operation from Vega Baja to Palo Seco from early am to late pm. 48000 gals moved to PS. | 9510 | TO2 June
2025-06-02 | Soler-Lugo, Nelson I | 1 | 1 | 170 | 170 | BESS | Vega Baja | Prepare and send Send email to project coordinator with invoice comments and path to follow for soil cut removals at all Jaca and Sierra sites. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-06-02 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Follow up with Consultant Carlos Lopez from Sphera Group on CES plan requirements for Vega Baja site. Follow up with Homeca on manifest requirements and logs for diesel fuel operation. Walkdown site with PUI inspector. | 9510 | TO2 June
2025-06-02 | Soler-Lugo, Nelson I | 1 | 1 | 170 | 170 | BESS | Vega Baja | Attended VB Demolition contract weekly meeting. | 9510 | TO2 June
2025-06-02 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Palo Seco | Working with revision of Jaca and Sierra Invoices and Change Order fro Palo Seco Geotechnical and Environmental studies. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-06-03 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the following daily tasks: Data gathering and photos. Input notes and comments into Procore Daily Log. Continue diesel fuel transfer operation from VB to PS. Started early am and fineshed during night. Diesel fuel transfer. Last day. Opened diesel fuel tank man entry cover to ck. 6” were at bottom. Suction hose was used to remove to remove content. Today total: 6 trips. | 9510 | TO2 June
2025-06-03 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the following daily tasks: Homeca removing lighting lamps at south of plant site. PUI inspector walkdown. Safety briefing with Osvaldo and Luis Roman from Genera Safety Dept. | 9510 | TO2 June
2025-06-03 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the following daily tasks: Teams Meeting to discuss rfi and submittals. | 9510 | TO2 June
2025-06-03 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the following daily tasks: Perform field assessment at vertical pump manhole located at south of property next to old fuel pumps skid. | 9510 | TO2 June
2025-06-04 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over daily tasks performed on site. Data gathering and photos. Input notes and comments into Procore Daily Log. Attended visitor Jean Menay on site, Safety Manager for DCMC. Attended visitor Gilberto Sucre on site vist, Senior CM for DCMC. Attended Tesla and SandL representatives to overview site conditions and discuss design inquiries and contractor doubts. | 9510 | TO2 June
2025-06-04 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Field verify; climb Slop-01 tank to ck current level of diesel inside tank. Calculate diesel amount for disposal. Approx 330 gallons. Sorveillance over demolition of diesel tanks dike wall at south side. Using excavador with hudraulic hammer. Using excavator with steel cutter to start demolition of tank s-1. Crushed tank and started cutting in pieces. Followed up with Luma on temporary meter and pr2 cabling works. Coordinate for Tomorrow 6/5/25. | 9510 | TO2 June
2025-06-04 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Review trip log submitted by Homeca for diesel transfer. Sent comments for resubmission. Instructed Homeca to vac remaining diesel sludge from tank s1 and slop 1 and 2 tanks. Waiting all day but truck never arrived. To be done next day. Informed work plan to site Superintendent to be ready with Electricians for Tomorrow works with LUMA. | 9510 | TO2 June
2025-06-05 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Vega Baja | Review and sign Genera Summary documents for Jaca and Sierra Invoices. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-06-05 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the daily tasks performed on site. Data gathering and photos. Input notes and comments into Procore Daily Log. Surveillance over Luma activities. Remove and relocate power lines. Aee Meter and traffic light power. | 9510 | TO2 June
2025-06-05 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Field surveillance over the demolishion activity of diesel tank s-1. Surveillance of demolition of concrete curbs at fueling pump house lane, both sides. Walkdown with contractor inside security building and pointed out required dismantling of elements before structure demolition. | 9510 | TO2 June
2025-06-05 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Surveillance over electrical works at temporary guard shack and construction trailers performed by contractor master electrician. Surveillance over Vac truck on site to remove remaining diesel inside tanks s1 and slop1 and 2. | 9510 | TO2 June
2025-06-06 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the daily tasks performed on site. Data gathering and photos. Input notes and comments into Procore Daily Log. Surveillance of demolition activities at diesel tanks dike walls. Surveillance of cutting tank walls and stockpiling metals. Verify proper disposition of tank metals into containers for recycling. | 9510 | TO2 June
2025-06-06 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Overview Separating steel from demolished concrete. Sirveillance of dismantling activities inside security building structure. Ensure proper disposition of fluoresc lamps, ac units ACT and electrical components. Generate RFI requesting path to follow with Duct bank and risers located in front of security building. Called SandL Francisco Matthew to explain findings. | 9510 | TO2 June
2025-06-06 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Receive visitor from Forteza cranes. Walkdown to MPT area to show location and available spaces. Sit down at trailer to call Mathews from sandl and to gather some dims from the 3D scan. Called Genera Security to follow up on temp safety shack ac unit repairs. Still not working. Attended PUI inspector C. Oquendo from Spehera Group. | 9510 | TO2 June
2025-06-09 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the daily tasks performed on site. Data gathering and photos. Input notes and comments into Procore Daily Log. Attended walkdown with Carlos Oquendo, PUI / CES Plan inspection. QA/QC Surveillance over the following daily activities: Hauling and dumping scrap metals and Rebars into containers for recycling. | 9510 | TO2 June
2025-06-09 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Demolishion activities for concrete light pole adjacent to old security building and parking lot. Rigging and removal of Slop-2 tank. Demolishion of slop-1 and slop-2 foundations. Demolishion of concrete slab / floor at old security building. Demolishion of telecomm antenna pole foundation. Pending to cut and remove anchor bolts. | 9510 | TO2 June
2025-06-09 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Removal of concrete debris from old security building area. Follow up with site manager on Contractor requirement to perform as built dwgs. Received and started review of submittal ARG-S002 Redesign electrical plans. Worked with review and transmittal for ARG-S001 Concrete Mix submittal. Distribute. Follow up with CM Team on MPT weight for rigging operation. | 9510 | TO2 June
2025-06-10 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the daily tasks performed on site. Data gathering and photos. Input notes and comments into Procore Daily Log. Walked down site with PUI inspector, Carlos Oquendo, to overview site conditions and installation of sediment control devices. QA pointed out about deficiencies observed at the old tanks containment area/water inlet protection. | 9510 | TO2 June
2025-06-10 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | QA/QC Surveillance over the following tasks: Personnel from Homeca spent time cutting wires, anchor bolts and Revars protruding from current ground elevation. Excavator was crushing concrete debris and stockpilling inside old diesel tank footprint. 5 Senses Solution Env. Services on site to collect all fluorescent lamp tubes removed from old Security Building ceiling lamps. Contractor started using mobile crusher to reduce concrete debris stockpiled on site. To be Recycled. Manifest Required While doing surveillance over the activities within the VB project site it was observed that fluid similar to oil was present next to the old unit 1-1 and 1-2 concrete foundations North side. The contractor used absorbing material to contain the fluids. After further investigation it seems the issue is comming from below ground. QA informed Genera Envirronmental Lead in the afternoon to perform assessment. Coordinated for 6/11 at 8:00am. | 9510 | TO2 June
2025-06-10 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Back and forward communications by emails and phone with Lauren Wells and Luis Roman from DCMC to clarify Procore rights within the Drawings modules. Uploaded civil drawings into procore but was not able to publish. Project Weekly meeting with Homeca Project and Corporate Manager. Chat with S and L PM, Mike Kuczynsk, to provide project specifications. Phone chat with Enrique Laya from CDM Smith to discuss final status on Diesel fuel transportation summary. | 9510 | TO2 June
2025-06-11 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the daily tasks performed on site. Data gathering and photos. Input notes and comments into Procore Daily Log. | 9510 | TO2 June
2025-06-11 | Soler-Lugo, Nelson I | 4 | 2 | 170 | 340 | BESS | Vega Baja | QA/QC Surveillance over the following tasks: Attended Visitors from Charlie Crane to ck MPT rigging requirements. Gilberto Sucre on site to ck issues with oil found at 1-1 and 1-2 north section. Walkdown and explain old oily water flow route. Provided CAPTA SUE dwgs. For use. Generate and sent email to team in regards to oil issue found on 6/10 at 1-1 and 1-2. | 9510 | TO2 June
2025-06-11 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Generate and sent email in regards to requirements for demolition of concrete footings 1-1 and 1-2. Visited VB landfill with isaac. Homeca continued housekeeping along unit 1/2 perimeter. Cont crushing concrete debris. Hauling crushed concrete to VB sanitary landfill. Visit from Manuel Hndz to overview issues with oils at unit 1-1 foundation mat. | 9510 | TO2 June
2025-06-12 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the daily tasks performed on site. Data gathering and photos. QA/QC Surveillance over the following tasks: Gabriel (BESS PM), Erick (GENERA ENV.) and Sucre (SR. CM DCMC) visited site to overview oil seepage unit 1-1. Walked down site to identify storm water and oily water system. Attended All Star Reps., on site to see MPT mpt area for quoting rigging and relocation. | 9510 | TO2 June
2025-06-12 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Surveillance over Homeca, search and identify sanitary line lost at the old security building during demolition. Surveillance over Hauling operation. Dump truck moved 6 ea 28cy trips to VB landfill. | 9510 | TO2 June
2025-06-12 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Surveillance over Housekeeping along project site. Verify Installation of oil absorber socks at u 1-1. Verify saw cut joints at diesel tanks walls. Input notes and comments into Procore Daily Log. | 9510 | TO2 June
2025-06-13 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Surveillance over the daily tasks performed on site. Data gathering and photos. Input notes, photos and and data into Procore Daily Log. Witness Homeca completed punch list. Removed fence along East side of unit 1-2. Housekeeping. | 9510 | TO2 June
2025-06-13 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Create Pdf Binder for Enrique Laya, Diesel fuel manifests and qa logs. Walked down site with Xavier Ortiz, Sphera rep., PUI/CES inspection. Prepared and sent email to C.Oquendo and Mike from SandL related to CES plan on file plus future CES plan needs. Review. Answer and distribute submittal ARG 003 and 001. | 9510 | TO2 June
2025-06-13 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Called Project Coordinator to discuss issues with ARG submittals procedures. Called manuel hndz to follow up on sucres request for oily water separator status. Sit down with Progress scheduler, Manuelly, to discuss completed works and pending items. Show Procore daily log notes for use on Periodic Report to PREB. | 9510 | TO2 June
2025-06-16 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance over the daily tasks. Data gathering and photos. Input notes, photos and and data into Procore Daily Log. Worked with documentation for closing diesel fuel transfer. Prepared final summaries with copies of daily logs. Distribute with Genera and phone chat with E.Laya. | 9510 | TO2 June
2025-06-16 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Verify instalation and compliance of the PUI sign installed by Homeca at the VB main gate. Surveillance over oil presence at top elevation and perimeter of unit 1-1 and 1-2 mat foundation. | 9510 | TO2 June
2025-06-16 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Witness demobilization from site for off Road Fork Lift JLG 1055; 2017; 10000 lbs; s/n 0160079508, 1250AJP man lift OUT; s/n 0300224919; C957. Prepared summary tables and supporting documentation for diesel fuel transfer task. Distributed with all Team members. Witness Homeca labor and Safety Officer on site doing housekeeping. | 9510 | TO2 June
2025-06-17 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance over the daily tasks. Input notes, photos and and data into Procore Daily Log. | 9510 | TO2 June
2025-06-17 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Attended Homecas weekly meeting Walked down site with Xavier Ortiz, PUI / CES inspection. Attended Genera Environmental Staff staff, brought additional stock for oil absorbing materials, (pads and socks), to have them available on site. To be used at Unit 1-1 and 1-2 Oil seepage zone. | 9510 | TO2 June
2025-06-17 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Attended personnel from Homeca; visited the site to pick up some tools and oxygen tanks and MOT devices. Weekly meeting conducted Today with ARG @ 11:00 am. Refer to Project Minutes. | 9510 | TO2 June
2025-06-18 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance over the daily tasks. Input notes, photos and and data into Procore Daily Log. Attended All Contractor Sub and visited MPT area for lifting quote. Walked area with Site manager. | 9510 | TO2 June
2025-06-18 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Pulled out all vega baja bess submittal requirements and copy into words. Answered email to mike from SandL and gabriel PM for BESS, in regards to uncomplete ces plan drawings. Review submittal ARG S004.1 rigging plan. Prepared transmittal with review remarks and distribute. Phone chat with Project Coordinator for BESS about submittal S004.1 | 9510 | TO2 June
2025-06-18 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Cambalache | Review email from Project Coordinator BESS about Geo Eng. invoice for cambalache. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-06-18 | Soler-Lugo, Nelson I | 1 |  | 170 | 170 | BESS | Vega Baja | Phone Chat with jose lopez, site Manager for Aguire BESS. Brainstorming about project requirements for quality. Phone Chat with eduardo, VB Site Mngr, about AGR not aligned on initial project requirements. | 9510 | TO2 June
2025-06-19 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance over the daily tasks. Input notes, photos and and data into Procore. Surveillance of surveying activities from JEBA Surveyors, on site to gather data for Homeca’s as built drawings. | 9510 | TO2 June
2025-06-19 | Soler-Lugo, Nelson I | 0.5 |  | 170 | 85 | BESS | Vega Baja | Follow up with BESS Project Coordinator on Geo Eng invoice. Invoice review/approval for accuracy and eligibility of the project. The purpose of this activity was to facilitate timely and accurate payment processing in support of ongoing energy storage project management, proper compliance with FEMA approved SOW, aligment with FEMA PA Policy and compliance with COR3 RFR Process for Federal Funds. | 9510 | TO2 June
2025-06-19 | Soler-Lugo, Nelson I | 3.5 | 3.5 | 170 | 595 | BESS | Vega Baja | Worked with Procore AGR submittals. Follow up with BESS Project Coordinators about AGR contract template. Sent email to DCMC Procore Lead, Lauren, regarding Procore certification reqs for AGR contractor. Upload docs into procore CDM smith drop box for tessie, Document Control – DCMC. Attended walkdown with Eduardo Ramos PM from Homeca. | 9510 | TO2 June
2025-06-19 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Review Homeca’s submittals for fluorescent lamps disposal and close. Started review of DRNA final package for lead permit closing. Move forward AGR submittal for VB SOV. | 9510 | TO2 June
2025-06-20 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance over the daily tasks. Input notes, photos and and data into Procore. Continue with surveillance over surveying field works by Javier Bidot crew on VB site for as built drawings by Homeca. | 9510 | TO2 June
2025-06-20 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Walkdown site with Carlos Oquendo to overview existing CES plan implementation and required maintenance. Working with Homecas manifest reports for all project. Working with Homecas weight tickets for all project. | 9510 | TO2 June
2025-06-20 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Review and close Homeca’s submittal 81. Follow up with Site Manager about LuMA assistance to remove cables from MPT per LUMA Lead, Cesar Sanchez, recommendation. | 9510 | TO2 June
2025-06-23 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance over the daily tasks. Input notes, photos and and data into Procore. Met with Gilberto Sucre on site to chat with ARG PM Carlos Hernandez about upcoming works and preparatory requirements | 9510 | TO2 June
2025-06-23 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Site manager and QA chat with Manny Crane representative about future rigging plan requirements when setting the megapacks in top of the platform. Walked down site with personnel from ARG to evaluate existing conditions within the project site. Concrete slab, unit foundations, sound barrier wall, storm water system, oily water system. | 9510 | TO2 June
2025-06-23 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Worked with Procore input and Homeca’s Manifest reports data and filing. Chat with Press staff from Genera and DCMC about meeting to be held during the evening with the Community at the Municipality of VB. Updated and organized project documentation in Procore, including Homeca’s manifest data and related records, to maintain compliance with contract and FEMA documentation standards; coordinated with Genera and DCMC staff regarding logistics for the scheduled Vega Baja community meeting to support stakeholder engagement and project communication requirements. | 9510 | TO2 June
2025-06-24 | Soler-Lugo, Nelson I | 4 | 2 | 170 | 340 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance over the daily tasks. Input notes, photos and and data into Procore. Weekly meeting with proposed BESS construction Contractor, ARG / Ceres, was conducted today by VB site manager, Eduardo Rivera from DCMC. Refer to meeting minutes available in Procore. Weekly meeting for demolition contract phase 1 with Homeca was was held Today with HOMECA PM Carisma Sanchez and DCMC site manager Eduardo Rivera. Refer to meeting minutes available in Procore | 9510 | TO2 June
2025-06-24 | Soler-Lugo, Nelson I | 4 | 2 | 170 | 680 | BESS | Vega Baja | Surveillance over Homeca’s demobilization activities. Removal of desks, chairs and office supplies from inside of Dueñas Trailer. Attended personnel from contractor ARG-Ceres, Ludgardo Gonzalez, and subcontractor Onshore PR, Luis Santiago and Jaime Umpierre, visited the site to overview site conditions and to take dimensions and photos of concrete area. QA personnel overviewed current conditions at oil/diesel seepage in top of units 1-1 and 1-2. Seepage still present but contained. No environmental issues observed. CES inspector, Carlos Oquendo from Sphera Group, on site to check correct device installation at stirm water inlets. Homeca removed the diesel storage tank from site and dust control blower. Homeca removed the concrete crusher equipment from site. | 9510 | TO2 June
2025-06-24 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Personnel from Homeca, Emmanuel Sanchez - Safety Officer, Carima Sanches - PM, Isaac Morales - Superintendent; visited the site to work with pending items from punchlist and demobilization activities. Procore input and continue filing of Waste Manifest reports for Demo contract. | 9510 | TO2 June
2025-06-25 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance over the following daily tasks. Input notes, photos and and data into Procore. Homeca, Emmanuel Sanchez - Safety Officer, Isaac Morales - Superintendent, Labor removed entrance stairs from their construction trailer. Personnel from Luma on site, Abner Marquez - Supervisor, Cesar Sanches - Supervisor, CREW. QA and staff discussed project needs at MPT location to disconnect and remove aerial lines running from the transformer to the existing poles at PR no 2 merge lane. Luma will perform the removal of aerial lines next Saturday. Work will be done from the outside of Genera’s property fence. | 9510 | TO2 June
2025-06-25 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Personnel from S and L visited the site, Engineer Harry Ramos / Nelson Trias. QA and staff walked out the project to overview existing storm water and potable water system. Staff gathered data for potable water entrance/connection pipeline at Sout-East side of project fence. Homeca personnel Emmanuel Sanchez - Safety Officer, Isaac Morales - Superintendent, Labor on site to demobilize backhoe attachment tools used during the demolition. Crusher, Hoe, Hydraulic Hammer. Oil / Fuel bleeding continue at unit 1-1 and 1-2 foundation area. New man lift brought Today by Homeca. Equipment was inspected. Brand new equipment. To be used for MPT protection scaffolds removal. Work will start on 6.26. Homeca portolet provider Rod Rodder on site to remove 2 portolet units. Homeca lifted grates from storm water inlets and removed debris and leaves from filter fabric material. CES compliance. Homeca removed their two Komatsu excavators from site. | 9510 | TO2 June
2025-06-25 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Meeting with S and L, Francisco Mathews, CDM Smith, Gabriel Perez, and BETA Electric, Asdrubal Morales; to discuss work requirements and possible path to move the MPT from actual location and to repair on site. Assited Site manager, Eduardo Rivera and Sr CM, Gilberto Sucre from DCMC on providing information and templates related to Substantial Completion process. Contacted Genera Procurement Manager, Joel Pantojas to find info about substantial completion. Procore input and continue with Demo contract manifest reports review process and filing. Follow up email to Project coordinator and team in regards to MPT disconnection status with Luma. | 9510 | TO2 June
2025-06-26 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Input daily notes, photos and data entry into Procore daily log module. Surveillance over Homeca staff, removing Main Power Transformer protection consisting of tubular scaffold and wood plants. All day task. Visual assessment of Main Power Transformer components that needs to be removed or dismantled before rigging activities | 9510 | TO2 June
2025-06-26 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Review Homecas Submittal for WASTER MANAGEMENT manifest reports. Sent back with comments. Fill Demolition Contract Waste Manifest Log. Provide Submittals response on Procore and distribute | 9510 | TO2 June
2025-06-26 | Soler-Lugo, Nelson I | 2 | 2 | 170 | 340 | BESS | Vega Baja | Reviewing Homecas Submittal for manifest reports. Sent back with comments. Fill Demo Contract Waste Manifest log. Submittals response on Procore and distribution. | 9510 | TO2 June
2025-06-27 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. Input notes, photos and and data into Procore. Review process for final documentation required for demolition contract closing acceptance. | 9510 | TO2 June
2025-06-27 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide technical support and follow up with E. Laya from CDMS and BESS Proj. Coord. on MPT, MAIN POWER TRANSFORMER, relocation SOW requirements. Gathering and share data with VB Superintendent and Site Manager on lead abatement initial assessment an required SOW for Homeca. | 9510 | TO2 June
2025-06-27 | Soler-Lugo, Nelson I | 2 | 1 | 170 | 170 | BESS | Vega Baja | Attended meeting with Jaime Pesquera, Gilberto Soto and Eduardo Rivera from DCMC to discuss current Demo contract punch list items and documentation required for contract closing. Reviewing iFC, ISSUE FOR CONSTRUCTION, drawings and bid specifications for VB BESS. Coordinate meeting with s and l for next tue 7/1 to chat about project specifications. | 9510 | TO2 June
2025-06-30 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. | 9510 | TO2/July
2025-06-30 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Spend time with Site Manager reviewing Homeca’s As Built Drawings submitted as Submittal no. 84. Workwith Construction Management Team with documentation and coordination required for Demolition Contract closing | 9510 | TO2/July
2025-06-30 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Surveillance over LUMA crew. On site with equipment and personnel to remove aerial lines connecting from current MPT to Transmision line. Remove cables from poles. | 9510 | TO2/July
2025-07-01 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. SOV Submittal uploaded through submittal module with reference number ARG-S005 was reviewed by Genera Reps. and returned to contractor. | 9510 | TO2/July
2025-07-01 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Soler QA lead had Teams meeting with DCMC PM specialist, Luis Roman to discuss current Specifications issues and Submittal requirements for VB Bess. QA lead conducted MS Teams meeting with SanL PM, SandL PE, and DCMC Site Mngr to discuss current issues with project specifications not being available in Procore and No Submittal Register. No availability to upload submittals with the Submittal Builder. | 9510 | TO2/July
2025-07-01 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Weekly meeting with new contractor AGR was conducted Today with PDT. Refer to available minutes on Procore module. Last Weekly meeting for Demolition contract was held Today by MS Teams. Contractor Homeca did not attended the meeting. Refer to available meeting minutes on Procore module. CM staff reviewing Homeca’s final documentation, invoice and change orders status for dinal closing. | 9510 | TO2/July
2025-07-02 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. Phone chat with Enrique Laya to discuss and provide input about Homeca's performance and safety incidents at VB Demolition contract. TO be used for final determination over Costa Sur Demo contract. Phone chat with Luis Roman from DCMC to continue discussion about current specs available, requirements and submittal builder. | 9510 | TO2/July
2025-07-02 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Continue reading IFC Specs for VB BESS. Gathering submittal data required for submittal register builder. Contact Genera Procurement Mngr to find out about available RFP docs forVB BESS. Review draft copy of VB BESS Contract template for ARG. | 9510 | TO2/July
2025-07-02 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Yabucoa | Start reviewing Jaca and Sierra revised invoices and change order for Yabucoa BESS. Follow up with BESS PC FCOlmenares on Jaca and Sierra pending invoices for Yabucoa BESS site. | 9510 | TO2/July
2025-07-03 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. Working with submittal management VB BESS and work flow. Submittal arg-s006 007 and 008 | 9510 | TO2/July
2025-07-03 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Pre cast calculations. Safety officer credentials. Safety plan. Send request to s and l regarding stone column plan schedule worksheet. Follow up communication with lauren wells regarding access to use transmittal module. Send email to agr regarding incorrect numbering and uploading of submittals in procore. Safety plan. | 9510 | TO2/July
2025-07-03 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Visit of agr with proj eng, safety officer and PM. Walkdown site. Chat about requirements prior to starting demo works and atone columns installation. Inform about spec requirements and SWPPP requirements. Quality requirements. Proposed work plan with concrete recycling and geopier temp base. | 9510 | TO2/July
2025-07-07 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. | 9510 | TO2/July
2025-07-07 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Visit Today of AGR project Engineer, PM, Safety and DCMC sr CM sucre. Also demolition subcontractor on site. Overview sow required for concrete slab demolition. Identify posible path to follow in regards to soil contamination. Request SandL bess stone columns excel sheet for location coordinates. Sent 2nd email. | 9510 | TO2/July
2025-07-07 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Follow up with construction team on site with RFi 004, 006, and 007 for ARG. Follow up with Super., J Pesquera, on homeca’s punch list item no 32 for as built drawings status. Respond and distribute submittal 81.1 from Homeca for oily water and diesel fuel disposal. Read meeting 15 agenda for Homeca Demo contract. Read meeting agenda 4 for ARG. Prepare for meeting to be held on 7.8.25. Review quarterly Report 2 for Vb Power Plant to be submitted to PREB. | 9510 | TO2/July
2025-07-08 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. | 9510 | TO2/July
2025-07-08 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Weekly meeting with Homeca was held Today. Weekly meeting with ARG was held Today. Pointed out project requirements for submittals and preconstruction plans that should be provided in advance for review and approval. Answered inquiry about Geopiers submittals which contractor PM thought was approved to start and QA informed a lot of info needs to be submitted for final review. TEsting agency, material gradation, testing plan, work plan, etc. LUma lead Cesar Sanchez visited the site. Qa walked down project to overview below ground site conditions at pull boxes located at south of property and south east next to fence. Verified no power on conductors. Used voltage detector. Requested to drain pull boxes for further investigation. | 9510 | TO2/July
2025-07-08 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Review ARG submittal no 007 safety officer. certs. Review and resubmit. Fill out transmittal form and distributed. Review ARG submittal 006 for ARG Safety Plan. Left site late comparing attachment J vs ARG safety plan sections. Highlighted and wrote crossreferences on pdf files. Sent email with path to follow and attachments to Safety Manager, Jmenay and Gsoto. | 9510 | TO2/July
2025-07-10 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. Spend all day on the following tasks: Specification No G-2700 Rev 01 Conformed Dated June 9, 2025 for the "Generation Fleet Storage Projects BESS Facility GWC Specifications" Working with submittal data gathering over the different Divisionjs and Sections (revised specifications) | 9510 | TO2/July
2025-07-10 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Yabucoa | Spend all day on the following tasks: Working with Jaca and Sierra invoice and change order detailed verification to validate amounts for yabucoa bess invoice. | 9510 | TO2/July
2025-07-14 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. | 9510 | TO2/July
2025-07-14 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | COntinue working with submittal data gathering for Project Register. Revise civil and structural drawings. Prepare Breakdown of required Quality Verification documents by trade, to be requested. | 9510 | TO2/July
2025-07-14 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Discussed findings of missing data on drawings with VB Site Manager. Email sent to S and L PM for clarification. Submittal review for ARG safety docs. | 9510 | TO2/July
2025-07-15 | Soler-Lugo, Nelson I | 4 | 4 | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. Attend weekly meeting with Homeca Recycling Attend Weekly meeting with ARG. Discuss with safety officer requirements for reviewing safety Management Plan submittal and risk analysis submittal in procore. # S006 #S009 and S010. Phone chat with safety manager JMenay on current AGR issues with submittals being uploaded into procore with missing info. | 9510 | TO2/July
2025-07-15 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Follow up emails in procore regarding incorrect uploading of submittals rev ARG s-010.1 into Procore. Communicate with s and l in regards of coordinates required for RAP installation. Received from BESS PC Geo Engineering invoice and change order for review for payment. Start review. | 9510 | TO2/July
2025-07-15 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Yabucoa | Go over Jaca and Sierra invoice and CO peer review for yabucoa per BESS PC request. | 9510 | TO2/July
2025-07-16 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. Prepare presentation for Teams meeting with ARG RFI vs submittal. Attend Meeting with ARG to discuss RFI vs Submittal requirements. Chat with BESS PC to discuss Geo Eng revised invoices and CO for vega baja. | 9510 | TO2/July
2025-07-16 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Prepare and sent procore email in relation to ARG proposed Org Chart. Long statement to site manager about difference between project engineering vs quality management. Prepare best practices bess projects org chart on excel format and distribute. Review remarks and distribute in Procore submittals from ARG no s006, s009, s010 and s010.1. Occupational Safety and Health Program, Risk Analysis, Safety Management Plan. | 9510 | TO2/July
2025-07-16 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Cambalache | Review Geo Eng change orders for Cambalache. Compare with original review remarks from May 2025 and send revised docs stamped to BESS PC. Chat with BESS PC to discuss Geo Eng revised invoices and CO for cambalache. | 9510 | TO2/July
2025-07-17 | Soler-Lugo, Nelson I | 3 | 3 | 170 | 510 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. Review documentation and values for VB Geo Eng CO. Approve and send by email documentation 6:18pm Review comments by s and l for PS submittal 1.6.1a4-4.0 PS TOPO and Sue. Follow up with VB site manager on Submittal 84.1 for Homeca Recycling As built dwgs remarks. Review and distribute submittal ARG - s002.0, Proposed redesign for elect dwgs. | 9510 | TO2/July
2025-07-17 | Soler-Lugo, Nelson I | 3 |  | 170 | 510 | BESS | Yabucoa | Review and sign documentation received fro BESS PC to release Jaca and Sierra Yabucoa certificate for payment. Review Yabucoa submittal remarks by s and l. Submittal 11.2. Final TOPO SUE. | 9510 | TO2/July
2025-07-17 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Yabucoa | Spent all morning working with worksheets and verification of values to validate Jaca and Sierra invoice and CO for Yabucoa. Sent email with all files to PC. | 9510 | TO2/July
2025-07-18 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | Provide QA/QC Technical Support at VB BESS Project. QA/QC Surveillance. Input notes, photos and and data into Procore. Review VB BESS IFC revised drawings submitted by s and l. Review available IFC Specs. divisions and sections. Cross reference with CSI Masterformat. Prepare pdf document with remarks / notes. Prepare RFI ARG-R011 and send to S and L. Review accountings for Jaca and Sierra revised invoices and CO. Compare with RFP and Task Order amounts and unit prices. Send email with certified docs to PC. | 9510 | TO2/July
2025-07-18 | Soler-Lugo, Nelson I | 4 |  | 170 | 680 | BESS | Vega Baja | ARG visited site. Attended walkdown with ARG reps to overview SOW requirements with PM and Proj Eng. ARG safety personnel and Generas dcmc safety representatives conducted on site meeting to overview submittal status and safety requirements. Review ARG submittal S-007 rev 1 for safety officer credentials. Move forward to next review steps. Review docs received through docusign from BESS PC, VB BESS Geo Eng invoices summary / application for payment. | 9510 | TO2/July
2025-07-18 | Soler-Lugo, Nelson I | 2 |  | 170 | 340 | BESS | Cambalache | Review docs received through docusign from BESS PC and Cambalache Geo Eng invoices summary / application for payment. | 9510 | TO2/July
|  | 846.5 | 835.5 |  | 142035
|  |  |  | Nelson Soler | 142035