## Monthly - O&M
Line | Asset | Terminal 1 | Terminal 2 | Miles | Month | Status
40100 | 115 kV | Jobos | Aguirre | 0.72 | February | In Progress
40200 | 115 kV | Jobos | Aguirre | 0.72 | February | In Progress
50100 | 230 kV | Cambalache | Manati | 2.95 | February | In Progress
50200 | 230 kV | Manati | Bayamon | 13.1 | February | In Progress
50200 | 230 kV | Costa Sur | Manati | 12.05 | February | In Progress
50800 | 230 kV | Sabana Llana | Yabucoa | 1.72 | February | In Progress
37100 | 115 kV | Acacias | San German | 3.26 | February | In Progress
37400 | 115 kV | Cambalache | Barceloneta | 4.27 | February | In Progress
39800 | 115 kV | Mayaguez TC | Acacias | 3.41 | February | In Progress
100 | 38 kV | Santa Isabel | Guayama | 0.06 | February | Completed
1600 | 38 kV | San German Tc | Yauco 1 Hp | 0.1 | February | Completed
1900 | 38 kV | Dos Bocas Hp | San Sebastian Tc | 5.47 | February | Completed
2000 | 38 kV | Mayaguez Gp | Colegio Sect | 3.79 | February | Completed
2100 | 38 kV | Dos Bocas Hp | Hatillo Tc | 0.25 | February | Completed
2200 | 38 kV | Dos Bocas Hp | Cambalache Tc | 0.02 | February | Completed
2300 | 38 kV | Dos Bocas Hp | Arecibo Sect | 0.29 | February | Completed
2400 | 38 kV | Dos Bocas Hp | Caonillas 2 Hp | 0.71 | February | Completed
2500 | 38 kV | San Sebastian Tc | Victoria Tc | 0.84 | February | Completed
2600 | 38 kV | San Sebastian Tc | Quebradillas Sect | 0.17 | February | Completed
3000 | 38 kV | Bairoa To | Caguas Tc | 0.11 | February | Completed
3100 | 38 kV | Sabana Llana Tc | Carolina | 1.86 | February | Completed
3200 | 38 kV | Viaducto Tc | Martin Peña Tc | 0.22 | February | Completed
3500 | 38 kV | Las Lomas Sect | Cachete Sect | 0.57 | February | Completed
4500 | 38 kV | Canas Tc | La Rambla Sect | 0.15 | February | Completed
4700 | 38 kV | Canas Tc | Adjuntas To | 1.36 | February | Completed
5200 | 38 kV | Caguas Tc | Aguas Buenas Sect | 1.16 | February | Completed
5900 | 38 kV | San Juan Sp | Crematorio To | 0.2 | February | Completed
6800 | 38 kV | San Fernando Sect | Puerto Nuevo To | 0.52 | February | Completed
7500 | 38 kV | Tres Monjitas Sect | Puerto Nuevo To | 0.1 | February | Completed
7700 | 38 kV | Tres Monjitas Sect | Puerto Nuevo To | 0.11 | February | Completed
8100 | 38 kV | Yauco 1 Hp | Adjuntas To | 5.01 | February | Completed
8200 | 38 kV | San Juan Sp | Amelia Sect | 0.36 | February | Completed
8900 | 38 kV | Fonalledas To | Venezuela Sect | 0.05 | February | Completed
13400 | 38 kV | Acacias Tc | San German Sect | 0.31 | February | Completed
15500 | 38 kV | Monacillos Tc | Centro Medico Sect | 0.03 | February | Completed
18400 | 38 kV | Barranquitas Tc | El Abanico | 0.06 | February | Completed
19500 | 38 kV | Palmer Tc | Radial | 0.31 | February | Completed
36100 | 115 kV | Ciales | Pinas | 0.45 | February | Completed
36300 | 115 kV | Rio Blanco | Humacao TC | 0.73 | February | Completed
36400 | 115 kV | Ponce TC | Jayuya | 2.23 | February | Completed
36800 | 115 kV | Fajardo TC | Canovanas TC | 0.77 | February | Completed
36900 | 115 kV | Costa Sur Power Plant | Canas TC | 0.08 | February | Completed
37800 | 115 kV | Monacillos TC | Cayey | 0.32 | February | Completed
38200 | 115 kV | Palo Seco Power Plant | Monacillos TC | 0.13 | February | Completed
38300 | 115 kV | Monacillos TC | San Juan Power Plant | 0.46 | February | Completed
38800 | 115 kV | Viaducto TC | Sabana Lana | 0.09 | February | Completed
38900 | 115 kV | Hato Rey TC | Martin Peña GIS | 0.89 | February | Completed
39000 | 115 kV | Aguas Buenas | Juana Dias | 1.03 | February | Completed
40300 | 115 kV | Ponce TC | Pattern Wind Farm | 1.49 | February | Completed
41000 | 115 kV | Humacao TC | Yabucoa TC | 0.33 | February | Completed
41400 | 115 kV | Juncos TC | Humacao TC | 1.7 | February | Completed
41500 | 115 kV | Barrio Piña GIS | Dorado TC | 0.02 | February | Completed
50300 | 230 kV | Costa Sur | Aquirre | 1.8 | February | Completed
50900 | 230 kV | Aquirre | Aguas Buenas Sect | 0.23 | February | Completed
1335-03 | Distribution | N/A | N/A | 0.03 | February | Completed
1359-07 | Distribution | N/A | N/A | 0.03 | February | Completed
1519-02 | Distribution | N/A | N/A | 0.01 | February | Completed
1525-03 | Distribution | N/A | N/A | 0.06 | February | Completed
1703-02 | Distribution | N/A | N/A | 0.05 | February | Completed
1704-03 | Distribution | N/A | N/A | 0.03 | February | Completed
1707-01 | Distribution | N/A | N/A | 0.08 | February | Completed
1710-01 | Distribution | N/A | N/A | 0.12 | February | Completed
1901-04 | Distribution | N/A | N/A | 0.04 | February | Completed
2301-02 | Distribution | N/A | N/A | 0.1 | February | Completed
2305-01 | Distribution | N/A | N/A | 0.03 | February | Completed
2305-04 | Distribution | N/A | N/A | 0.21 | February | Completed
2306-01 | Distribution | N/A | N/A | 0.15 | February | Completed
3004-01 | Distribution | N/A | N/A | 0.15 | February | Completed
3010-04 | Distribution | N/A | N/A | 0.05 | February | Completed
3103-02 | Distribution | N/A | N/A | 0.38 | February | Completed
3103-04 | Distribution | N/A | N/A | 0.03 | February | Completed
3103-05 | Distribution | N/A | N/A | 0.13 | February | Completed
3401-02 | Distribution | N/A | N/A | 0.12 | February | Completed
3405-01 | Distribution | N/A | N/A | 0.09 | February | Completed
3601-02 | Distribution | N/A | N/A | 0.12 | February | Completed
3604-06 | Distribution | N/A | N/A | 0.04 | February | Completed
3701-03 | Distribution | N/A | N/A | 0.25 | February | Completed
4003-01 | Distribution | N/A | N/A | 0.09 | February | Completed
4003-03 | Distribution | N/A | N/A | 0.03 | February | Completed
4201-03 | Distribution | N/A | N/A | 0.06 | February | Completed
4301-01 | Distribution | N/A | N/A | 0.04 | February | Completed
4603-02 | Distribution | N/A | N/A | 0.26 | February | Completed
5004-07 | Distribution | N/A | N/A | 0.14 | February | Completed
5013-01 | Distribution | N/A | N/A | 0.54 | February | Completed
5303-01 | Distribution | N/A | N/A | 0.19 | February | Completed
5501-02 | Distribution | N/A | N/A | 0.07 | February | Completed
5501-04 | Distribution | N/A | N/A | 0.18 | February | Completed
5808-02 | Distribution | N/A | N/A | 0.05 | February | Completed
5817-02 | Distribution | N/A | N/A | 0.05 | February | Completed
5901-01 | Distribution | N/A | N/A | 0.4 | February | Completed
5901-02 | Distribution | N/A | N/A | 0.29 | February | Completed
6007-02 | Distribution | N/A | N/A | 0.09 | February | Completed
6008-04 | Distribution | N/A | N/A | 0.06 | February | Completed
6014-02 | Distribution | N/A | N/A | 0.16 | February | Completed
6101-01 | Distribution | N/A | N/A | 0.02 | February | Completed
6201-01 | Distribution | N/A | N/A | 0.19 | February | Completed
6305-03 | Distribution | N/A | N/A | 0.07 | February | Completed
6401-02 | Distribution | N/A | N/A | 0.24 | February | Completed
6406-02 | Distribution | N/A | N/A | 2.55 | February | Completed
6501-02 | Distribution | N/A | N/A | 0.05 | February | Completed
6702-02 | Distribution | N/A | N/A | 0.2 | February | Completed
6705-01 | Distribution | N/A | N/A | 0.05 | February | Completed
6801-01 | Distribution | N/A | N/A | 0.03 | February | Completed
6802-02 | Distribution | N/A | N/A | 0.24 | February | Completed
7008-08 | Distribution | N/A | N/A | 0.14 | February | Completed
7403-03 | Distribution | N/A | N/A | 0.06 | February | Completed
7702-02 | Distribution | N/A | N/A | 0.11 | February | Completed
7802-03 | Distribution | N/A | N/A | 0.26 | February | Completed
7805-11 | Distribution | N/A | N/A | 0.06 | February | Completed
7901-01 | Distribution | N/A | N/A | 0.1 | February | Completed
8001-01 | Distribution | N/A | N/A | 0.02 | February | Completed
8007-04 | Distribution | N/A | N/A | 0.12 | February | Completed
8202-03 | Distribution | N/A | N/A | 0.06 | February | Completed
8405-02 | Distribution | N/A | N/A | 0.4 | February | Completed
8701-02 | Distribution | N/A | N/A | 0.13 | February | Completed
9003-06 | Distribution | N/A | N/A | 0.04 | February | Completed
9601-01 | Distribution | N/A | N/A | 0.11 | February | Completed
40100 | 115 kV | Jobos | Aguirre | 4.14 | January | In Progress
40200 | 115 kV | Jobos | Aguirre | 4.14 | January | In Progress
50100 | 230 kV | Cambalache | Manati | 2.4 | January | In Progress
50200 | 230 kV | Manati | Bayamon | 4.76 | January | In Progress
50400 | 230 kV | Costa Sur Power Plant | Mayaguez TC | 13.6 | January | In Progress
50700 | 230 kV | AES | Yabucoa | 1.25 | January | Completed
300 | 38 kV | Juana Diaz TC | Toro Negro | 0.12 | January | In Progress
1300 | 38 kV | Yauco 1 | Yauco 2 | 0.03 | January | In Progress
1400 | 38 kV | Yauco 1 | Yauco 2 | 0.09 | January | In Progress
4700 | 38 kV | Canas TC | Adjuntas | 0.42 | January | In Progress
4800 | 38 kV | Santa Isabel | Aibonito | 0.12 | January | In Progress
4800 | 38 kV | Toro Negro | Villalba | 0.15 | January | In Progress
7900 | 38 kV | Juana Diaz TC | Toro Negro | 0.18 | January | In Progress
36300 | 115 kV | Jobos | Yabucoa | 1.26 | January | In Progress
3700 | 115 kV | Costa Sur | Ponce Hostos | 0.54 | January | In Progress
40300 | 115 kV | Costa Sur | Ponce Hostos | 1.26 | January | In Progress
50200 | 230 kV | Costa Sur | Manati | 0.9 | January | In Progress
51300 | 230 kV | Costa Sur | Ponce Hostos | 1.08 | January | In Progress
8202-01 | Distribution | N/A | N/A | 0.06 | January | In Progress
8404-01 | Distribution | N/A | N/A | 0.17 | January | In Progress
9002-03 | Distribution | N/A | N/A | 0.28 | January | In Progress
7901-01 | Distribution | N/A | N/A | 0.06 | January | In Progress
1343-01 | Distribution | N/A | N/A | 0.09 | January | In Progress
1602-04 | Distribution | N/A | N/A | 0.17 | January | In Progress
1401-07 | Distribution | N/A | N/A | 0.03 | January | In Progress
1520-01 | Distribution | N/A | N/A | 0.03 | January | In Progress
1658-13 | Distribution | N/A | N/A | 0.06 | January | In Progress
1118-10/1110-03 | Distribution | N/A | N/A | 0.03 | January | In Progress

## Monthly - Clearing Program
Line | Asset | Miles | Month | Status
3004-03 | Distribution | 0.04 | February | In Progress
3009-03 | Distribution | 0.3 | February | In Progress
3014-01 | Distribution | 0.58 | February | In Progress
3101-02 | Distribution | 0.04 | February | In Progress
3103-04 | Distribution | 3.39 | February | In Progress
3103-05 | Distribution | 4.52 | February | Completed
3301-03 | Distribution | 0.47 | February | In Progress
3401-01 | Distribution | 0.75 | February | In Progress
3402-06 | Distribution | 0.1 | February | Completed
3405-02 | Distribution | 5.66 | February | In Progress
3601-01 | Distribution | 0.61 | February | In Progress
5008-03 | Distribution | 1.45 | February | In Progress
5008-04 | Distribution | 2.42 | February | In Progress
5802-03 | Distribution | 0.88 | February | In Progress
5805-01 | Distribution | 1 | February | In Progress
7701-02 | Distribution | 5.03 | February | In Progress
7802-04 | Distribution | 0.79 | February | In Progress
8007-03 | Distribution | 0.16 | February | In Progress
8013-02 | Distribution | 6.44 | February | In Progress
8701-03 | Distribution | 0.1 | February | In Progress
9703-02 | Distribution | 0.41 | February | In Progress
9902-03 | Distribution | 0.08 | February | In Progress
36800 | 115 kV Transmission | 0.55 | February | In Progress
3004-03 High | Distribution | 0.4 | January | In Progress
3009-01 High | Distribution | 0.11 | January | In Progress
3009-04 High | Distribution | 0.84 | January | In Progress
3014-01 High | Distribution | 1.28 | January | In Progress
3014-03 High | Distribution | 0.01 | January | Completed
3101-02 High | Distribution | 0.81 | January | In Progress
3301-03 High | Distribution | 0.21 | January | In Progress
3302-01 High | Distribution | 0.02 | January | Completed
3401-01 High | Distribution | 0.09 | January | In Progress
3406-03 High | Distribution | 1.71 | January | Completed
3501-03 High | Distribution | 1 | January | In Progress
3601-01 High | Distribution | 0.04 | January | In Progress
4504-02 High | Distribution | 0.05 | January | Completed
4602-01 High | Distribution | 0.05 | January | Completed
5003-01 High | Distribution | 0.53 | January | In Progress
5008-03 High | Distribution | 0.19 | January | In Progress
5008-04 High | Distribution | 0.48 | January | In Progress
5401-04 High | Distribution | 1.15 | January | Completed
5501-02 High | Distribution | 0.03 | January | In Progress
5901-01 High | Distribution | 0.85 | January | In Progress
6404-02 High | Distribution | 0.78 | January | In Progress
7402-01 High | Distribution | 0.13 | January | In Progress
7505-05 High | Distribution | 1.68 | January | In Progress
7602-05 High | Distribution | 0.05 | January | In Progress
7802-04 High | Distribution | 1.09 | January | In Progress
7805-13 High | Distribution | 1.01 | January | In Progress
7903-06 High | Distribution | 0.4 | January | In Progress
8002-02 High | Distribution | 0.02 | January | Completed
8007-03 High | Distribution | 0.83 | January | In Progress
8011-01 High | Distribution | 0.07 | January | In Progress
8301-01 High | Distribution | 0.11 | January | In Progress
8701-03 High | Distribution | 0.21 | January | In Progress
8801-02 High | Distribution | 0.11 | January | In Progress
9001-01 High | Distribution | 0.01 | January | In Progress
9004-10 High | Distribution | 0.02 | January | In Progress
9703-02 High | Distribution | 0.23 | January | In Progress
9703-03 High | Distribution | 0.05 | January | In Progress
39000 | 115 kV Transmission | 0.48 | January | Completed
36800 | 115 kV Transmission | 0.7 | January | In Progress