## Projects
FEMA ID | Project Name | 428 Cost | 406 MIT Cost | Other Funding | Total Cost | Current Project Status or comments | DSOW Submittal date to FEMA | Anticipated Design Completion Date | Comments
334770 | FAASt - Guajataca Dam - Permanent Repairs (Dams, Hydro, & Irrigation) | 566085576 | 520884424 |  | 1086970000 | Planning & Design-Preliminary Studies- Developing Detailed SOW | TBD | 2028-12-31
334771 | FAASt - Guajataca Reservoir – Dredging (Dams, Hydro, & Irrigation) | 42161570 | 0 |  | 42161570 | DSOW submitted and under FEMA Review- Completion of 60% Design in progress | Submitted | 2028-06-22 | PREPA actively working to identify 406 Hazard Mitigation measures and potential costs to be reallocated under 406
436621 | FAASt - Dams Minor Repairs | 15309227 | 9298063.48 |  | 24607290.48 | DSOW submitted and under FEMA Review | Submitted | 2026-07-25
334811 | FAASt - Dos Bocas Reservoir – Dredging (Dams, Hydro, & Irrigation) | 123379970.5 | 0 |  | 123379970.5 | DSOW submitted and under FEMA Review- Completion of 60%Design in progress | Submitted | 2027-07-01 | PREPA actively working to identify 406 Hazard Mitigation measures and potential costs to be reallocated under 406
178722 | FAASt - Caonillas Reservoir – Dredging (Dams, Hydro, & Irrigation) | 87072982 | 0 |  | 87072982 | DSOW submitted and under FEMA Review- Completion of 60% Design in progress | Submitted | 2027-05-31 | PREPA actively working to identify 406 Hazard Mitigation measures and potential costs to be reallocated under 406
334772 | FAASt - Guayabal Reservoir – Dredging (Dams, Hydro, & Irrigation) | 6452231 | 15540000 |  | 21992231 | Planning & Design- Developing Detailed SOW | 2026-09-30 | 2027-10-01 | *406 Hazard Mitigation measures identified. PREPA actively working with FEMA to identify potential costs to be reallocated under 406
335206 | FAASt - Matrullas Reservoir – Dredging (Dams, Hydro, & Irrigation) | 8055082 | 6190000 |  | 14245082 | Planning & Design- Developing Detailed SOW | 2026-09-30 | 2027-04-01 | *406 Hazard Mitigation measures identified. PREPA actively working with FEMA to identify potential costs to be reallocated under 406
335207 | FAASt - Guineo Reservoir – Dredging (Dams, Hydro, & Irrigation) | 3143743 | 6200000 |  | 9343743 | Planning & Design- Developing Detailed SOW | 2026-09-30 | 2027-02-02 | *406 Hazard Mitigation measures identified. PREPA actively working with FEMA to identify potential costs to be reallocated under 406
334803 | FAASt - Loco Reservoir – Dredging (Dams, Hydro, & Irrigation) | 8080000 | 5750000 |  | 13830000 | Planning & Design- Developing Detailed SOW-Completion of 60% Design in progress | 2026-04-30 | 2026-12-01 | *406 Hazard Mitigation measures identified. PREPA actively working with FEMA to identify potential costs to be reallocated under 406
334813 | FAASt - Guayo Reservoir – Dredging (Dams, Hydro, & Irrigation) | 17260000 | 5800000 |  | 23060000 | Planning & Design- Developing Detailed SOW-Completion of 60% Design in progress | 2026-04-30 | 2027-08-01 | *406 Hazard Mitigation measures identified. PREPA actively working with FEMA to identify potential costs to be reallocated under 406
334773 | FAASt - Lucchetti Reservoir – Dredging (Dams, Hydro, & Irrigation) | 40020000 | 25590000 |  | 65610000 | Planning & Design- Developing Detailed SOW-Completion of 60% Design in progress | 2026-04-30 | 2027-06-01 | *406 Hazard Mitigation measures identified. PREPA actively working with FEMA to identify potential costs to be reallocated under 406
334798 | FAASt - Guerrero Reservoir – Dredging (Dams, Hydro, & Irrigation) | 3918132 | 0 |  | 3918132 | Planning & Design- Developing Detailed SOW | 2026-02-27 | 2027-02-15 | PREPA actively working to identify 406 Hazard Mitigation measures and potential costs to be reallocated under 406
334769 | FAASt - Garzas Reservoir – Dredging (Dams, Hydro, & Irrigation) | 11154286 | 0 |  | 11154286 | Planning & Design- Developing Detailed SOW | 2026-02-27 | 2027-06-10 | PREPA actively working to identify 406 Hazard Mitigation measures and potential costs to be reallocated under 406
435769 | FAASt - South Coast Irrigation District - Canals (Dams, Hydro, & Irrigation) | 89245881.92 | 27093224.61 |  | 116339106.53 | Costs updated and decreased- Completion of Design in progress | 2026-05-31 | 2026-05-01 | *406 Hazard Mitigation measures identified. PREPA actively working with FEMA to identify potential costs to be reallocated under 406
436462 | FAASt - Lajas Irrigation District - Canals (Conveyance and Canals) | 37270276.12 | 5302995.4 |  | 42573271.52 | Planning & Design- Developing Detailed SOW | 2026-07-31 | 2026-07-01 | PREPA actively working to identify 406 Hazard Mitigation measures and potential costs to be reallocated under 406
USDA/436467 | Isabella Irrigation District Canals (Water Assets Conveyance and Canals) | 15000000 | 0 | 17000000 | 15000000 | PREPA seeking USDA/NRCS full project funding - Potential reallocation of funds | TBD | TBD
721184 | Guayabal Dam Seismic Retrofit | 163467420 | 156302821 |  | 319770241 | Planning & Design- Developing Detailed SOW | TBD | 2030-12-01
728260 | FAASt - Caonillas 1 Hydro System (Hydro) | 3611152 | 0 |  | 3611152 | Planning & Design- Developing Detailed SOW | 2026-05-31 | 2027-03-31 | PREPA actively working to identify 406 Hazard Mitigation measures and potential costs to be reallocated under 406
180723 | FAASt - Rio Blanco Hydroelectric System (Dams, Hydro, & Irrigation) | 22911551 | 26094024.55 |  | 49005575.55 | Planning & Design- Developing Detailed SOW | 2026-05-31 | 2026-09-30
436468 | FAASt - Toro Negro Hydroelectric Conveyance Canal and Penstock Repairs | 43483764.17 | 13760297.54 |  | 57244061.71 | Planning & Design- Developing Detailed SOW | 2026-05-31 | 2026-09-30
1307082844.71
Formulas:
Anticipated Design Completion Date = VLOOKUP(Table13[[#This Row],[FEMA ID]],'[1]PREB Report (2)'!$B8:W32,20,FALSE)

## Cost (hidden)
Number | FEMA ID | Project Name | 428 Cost | 406 MIT Cost | Other Funding | Total Cost | Estimate Class | Range | High End of Range | Capped High | Uncapped High | Anticipated Design Completion Date | Anticipated Construction Completion Date | Comments
5 | 334770 | FAASt - Guajataca Dam - Permanent Repairs (Dams, Hydro, & Irrigation) | 566085576 | 520884424 |  | 1086970000 | 5 | -50% to +100% | 2173940000 | 1086970000 | 1041768848 | 2028-12-31 | BERMUDEZ
6 | 436621 | FAASt - Dams Minor Repairs | 15309227 | 9298063.48 |  | 24607290.48 | 5 | -50% to +100% | 49214580.96 | 24607290.48 | 18596126.96 | 2026-07-25 | TBD
12 | 334811 | FAASt - Dos Bocas Reservoir – Dredging (Dams, Hydro, & Irrigation) | 123379970.5 | 0 |  | 123379970.5 | 3 | -15% to +20% | 148055964.6 | 123379970.5 | 0 | 2027-07-01 | BERMUDEZ
13 | 178722 | FAASt - Caonillas Reservoir – Dredging (Dams, Hydro, & Irrigation) | 87072982 | 0 |  | 87072982 | 3 | -15% to +20% | 104487578.4 | 87072982 | 0 | 2027-05-31 | BERMUDEZ
14 | 334772 | FAASt - Guayabal Reservoir – Dredging (Dams, Hydro, & Irrigation) | 20606934 | 15540000 |  | 36146934 | 5 | -50% to +100% | 72293868 | 36146934 | 31080000 | 2027-10-01 | BERMUDEZ
15 | 335206 | FAASt - Matrullas Reservoir – Dredging (Dams, Hydro, & Irrigation) | 8055082 | 6190000 |  | 14245082 | 5 | -50% to +100% | 28490164 | 14245082 | 12380000 | 2027-04-01 | BERMUDEZ
16 | 335207 | FAASt - Guineo Reservoir – Dredging (Dams, Hydro, & Irrigation) | 3143743 | 6200000 |  | 9343743 | 5 | -50% to +100% | 18687486 | 9343743 | 12400000 | 2027-02-02 | BERMUDEZ
17 | 334803 | FAASt - Loco Reservoir – Dredging (Dams, Hydro, & Irrigation) | 8080000 | 5750000 |  | 13830000 | 5 | -50% to +100% | 27660000 | 13830000 | 11500000 | 2026-12-01 | BERMUDEZ
18 | 334813 | FAASt - Guayo Reservoir – Dredging (Dams, Hydro, & Irrigation) | 17260000 | 5800000 |  | 23060000 | 5 | -50% to +100% | 46120000 | 23060000 | 11600000 | 2027-08-01 | BERMUDEZ
19 | 334773 | FAASt - Lucchetti Reservoir – Dredging (Dams, Hydro, & Irrigation) | 40020000 | 25590000 |  | 65610000 | 5 | -50% to +100% | 131220000 | 65610000 | 51180000 | 2027-06-01 | BERMUDEZ
20 | 334771 | FAASt - Guajataca Reservoir – Dredging (Dams, Hydro, & Irrigation) | 42161570 | 0 |  | 42161570 | 3 | -15% to +20% | 50593884 | 42161570 | 0 | 2028-06-22 | BERMUDEZ
21 | 334798 | FAASt - Guerrero Reservoir – Dredging (Dams, Hydro, & Irrigation) | 3966763 | 0 |  | 3966763 | 3 | -15% to +20% | 4760115.6 | 3966763 | 0 | 2027-02-15 | BERMUDEZ
22 | 334769 | FAASt - Garzas Reservoir – Dredging (Dams, Hydro, & Irrigation) | 11154286 | 0 |  | 11154286 | 5 | -50% to +100% | 22308572 | 11154286 | 0 | 2027-06-10 | BERMUDEZ
9 | 435769 | FAASt - South Coast Irrigation District - Canals (Dams, Hydro, & Irrigation) | 89245881.92 | 27093224.61 |  | 116339106.53 | 5 | -50% to +100% | 232678213.06 | 116339106.53 | 54186449.22 | 2026-05-01 | BERMUDEZ | Note: Guamani canal has decreased from $49M to $21M from Class 5 to Class 3
10 | 436462 | FAASt - Lajas Irrigation District - Canals (Conveyance and Canals) | 37270276.12 | 5302995.4 |  | 42573271.52 | 5 | -50% to +100% | 85146543.04 | 42573271.52 | 10605990.8 | 2026-07-01 | BERMUDEZ
11 | USDA/436467 | Isabella Irrigation District Canals (Water Assets Conveyance and Canals) |  | 0 | 17000000 | 17000000 | 5 | -50% to +100% | 34000000 | 17000000 | 34000000 | TBD | FERNANDO OSORIO | Note: USDA Funding - Check with PREPA
7 | 721184 | Guayabal Dam Seismic Retrofit | 163467420 | 156302821 |  | 319770241 | 5 | -50% to +100% | 639540482 | 319770241 | 312605642 | 2030-12-01 | TBD
8 | 728260 | FAASt - Caonillas 1 Hydro System (Hydro) | 3611152 | 0 |  | 3611152 | 5 | -50% to +100% | 7222304 | 3611152 | 0 | 2027-03-31 | BERMUDEZ
3 | 180723 | FAASt - Rio Blanco Hydroelectric System (Dams, Hydro, & Irrigation) | 22911551 | 26094024.55 |  | 49005575.55 | 5 | -50% to +100% | 98011151.1 | 49005575.55 | 52188049.1 | 2026-09-30 | BERMUDEZ
4 | 436468 | FAASt - Toro Negro Hydroelectric Conveyance Canal and Penstock Repairs | 43483764.17 | 13760297.54 |  | 57244061.71 | 5 | -50% to +100% | 114488123.42 | 57244061.71 | 27520595.08 | 2026-09-30 | BERMUDEZ
#REF! | 746897 | FAASt BONUS | 1562350 | 178320.9 |  | 1740670.9 | 1 | -3% to +3% | 1792891.027 | 1740670.9 | 183670.527 | Completed | JOHN ROSADO
#REF! | 725535 | IT/OT | 11423825 | 0 |  | 11423825 | 5 | Bid | 11423825 | 11423825 | 0 | DIANA BERRIOS | DIANA BERRIOS
|  | Total | 753186777.71 | 303099747.48 |  | 1073286525.19 |  |  | 1928195746.207 | 1073286525.19 | 640026523.687
Formulas:
Anticipated Design Completion Date = VLOOKUP(Table1[[#This Row],[FEMA ID]],'[1]PREB Report (2)'!$B8:W32,20,FALSE)