## Summary
LUMA Consolidated List |  | Amount ($M) | Allocation |  | Amount ($M)
428 Cost Allocation |  |  | 428 Cost Allocation
| 428 Allocation (Without the A&E and E&M) | 3134057188.3733 |  | 428 Allocation (Without the A&E and E&M) | 3894802175.3195
| 428 A&E-PW 9510 | 351042612.5512 |  | 428 A&E-PW 9510 | 471515255.3357
| 428 E&M-PW 10710 | 443540365.7918 |  | 428 E&M-PW 10710 | 542053793.3389
406 Cost Allocation |  |  | 406 Cost Allocation
| 406 Allocation (Without the A&E and E&M) | 1914894041.5754 |  | 406 Allocation (Without the A&E and E&M) | 2298728982.6983
| 406 A&E-PW 9510 | 155463965.1751 |  | 406 A&E-PW 9510 | 191927360.0168
| 406 E&M-PW 10710 | 286761423.4572 |  | 406 E&M-PW 10710 | 430916194.2041
Total 428 Expected Cost |  | 3928640166.7163 | Total 428 Expected Cost |  | 4908371223.9941
Total 406 Expected Cost |  | 2357119430.2077 | Total 406 Expected Cost |  | 2921572536.9192
Expected Total Project Cost |  | 6285759596.924 | Expected Total Project Cost |  | 7829943760.9134
Attachment A |  | Amount ($M)
428 Cost Allocation
| 428 Allocation (Without the A&E and E&M) | 635976230.1362
| 428 A&E-PW 9510 | 97835662.6411
| 428 E&M-PW 10710 | 98513427.5471
406 Cost Allocation
| 406 Allocation (Without the A&E and E&M) | 380988372.623
| 406 A&E-PW 9510 | 36321119.6751
| 406 E&M-PW 10710 | 144154770.7469
Total 428 Expected Cost |  | 832325320.3244
Total 406 Expected Cost |  | 561464263.0449
Expected Total Project Cost |  | 1393789583.3694
Attachment B |  | Amount ($M)
428 Cost Allocation
| 428 Allocation (Without the A&E and E&M) | 124768756.81
| 428 A&E-PW 9510 | 22636980.1434
| 428 E&M-PW 10710 | 0
406 Cost Allocation
| 406 Allocation (Without the A&E and E&M) | 2846568.5
| 406 A&E-PW 9510 | 142275.1666
| 406 E&M-PW 10710 | 0
Total 428 Expected Cost |  | 147405736.9534
Total 406 Expected Cost |  | 2988843.6666
Expected Total Project Cost |  | 150394580.62
Summary Expected Project Costs Allocation
Total Project Costs Allocation
Inccluded LUMA Consolidated List, Attachment A and Attachment B

## Consolidated Project List
Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | Process Step | 428 Allocation (Without the A&E and E&M) | 406 Allocation (Without the A&E and E&M) | 428 A&E-PW 9510 | 406 A&E-PW 9510 | 428 E&M-PW 10710 | 406 E&M-PW 10710 | Expected Total Project Cost | Total 428 Expected cost | Total 406 Expected Cost | Obligation Amendment Status | Comments
165209 | FAASt - EPC - Culebra Substation 3801 and New Culebra Substation 3802 (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | 1133466.58 | 58777240.65 | 148303.89 | 84426.97 | 118838.82 | 298749.59 | 60561026.5 | 1400609.29 | 59160417.21 | Submitted to COR3/PREPA | The SOW submitted to COR3/PREPA only includes changes in the scope of the repairs to the existing substation. Currently, the project includes the new substation that will be part of the microgrid (not full Section 406HM). LUMA will request to transfer the scope of the new substation to the microgrid project (full Section 406HM). Cost change is driven by more defined scope and inflation.
165213 | FAASt – Line 5400 – Rio Blanco HP to Daguao TC to Punta Lima TO to Vieques 2501 to Culebra 3801 (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 90286761.91 | 33780983.5629 | 7450643.73 | 2497575.1807 | 14930827.72 | 1685383.8863 | 150632175.99 | 112668233.36 | 37963942.63 | Project in V0 - No amendment required at this time | The DSOW revision will be submitted as part of the pending RFI response. The updated scope and design incorporate an additional segment. The revised estimate includes a budgetary allowance for this added transmission overhead line segment, as well as new underground distribution and transmission components that will likely be Hazard Mitigation.
165225 | FAASt - EPC - Vieques 2501 substation repairs & New Vieques 2502 substation (Substation) | Substation | Vieques and Culebra Projects (6) | Yes | Obligated | 2115845.46 | 61747355.43 | 196682.43 | 74220.68 | 209878.53 | 481486.47 | 64825469 | 2522406.42 | 62303062.58 | Submitted to COR3/PREPA | The SOW submitted to COR3/PREPA only includes changes in the scope of the repairs to the existing substation. Currently, this project includes the new substation that will be part of the microgrid (not full Section 406HM). LUMA will request to transfer the scope of the new substation to the microgrid project (full Section 406HM). Cost change is driven by a more defined scope and inflation.
165226 | FAASt [Feeders Vieques & Culebra] (Distribution) | Distribution | Vieques and Culebra Projects (6) | No | Pending PDMG Scope & Cost Routing | 53655359.67 | 7910341.47 | 6294597.32 | 1006025.84 | 3171076.36 | 1176186.58 | 73213587.24 | 63121033.35 | 10092553.89 | Project in V0 - No amendment required at this time | The project estimate was based on a Class 3. Project is currently under FEMA evaluation.
165268 | FAASt Rio Grande Estate Substation CH-2306 (Su | Substation | Substation Rebuilds | Yes | Obligated | 22290107.58 | 8550353.26 | 1837831.336 | 1216566.725 | 510106.56 | 15489893.44 | 49894858.901 | 24638045.476 | 25256813.425 | Amendment to be submitted to COR3/PREPA | LUMA is finalizing changes in the scope and estimate. The amendment is expected to be submitted by Q1 FY2027.
167446 | FAASt - Line 36100 (115kV) - Bayamon to Monacillos (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 16767135.99 | 10441839.67 | 4907530.43 | 3867090.21 | 2133671.71 | 5779812.06 | 43897080.07 | 23808338.13 | 20088741.94 | Amendment - Pending Development | Information represents the latest LPCE information provided.
168226 | FAASt San Juan 115kV Underground Transmission | Transmission | Transmission Line Rebuild | Yes | Obligated | 14746039.57 | 0 | 2258339.67 | 0 | 0 | 0 | 17004379.24 | 17004379.24 | 0 | Obligated - No amendment need Identified | Data included was not modified, it represents the obligated amounts. The scope is being revised and may impact the estimate.
168483 | FAASt - 115kV Line 36400 - Dos Bocas HP to Ponce TC (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 73843869.7985 | 62335950.1897 | 4386536.3259 | 3697488.9625 | 29668.6935 | 0 | 144293513.97 | 78260074.8179 | 66033439.1521 | Project in V0 - No amendment required at this time | The estimate added in the original (2.28.2026) document only included one of the two segments within the project ($81M) one of the estimates was left out. Adding both segments, totals $144M however, the latest LPCE has not undergone 428/406 split therefore the percentage split used was the same split for the TL36100 project.
169058 | FAASt - Llorens Torres MC 1106 - Equipment Repair & Replacement - (Substations) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | 20962734.639 | 10164051.2316 | 1335184.07 | 721159.747 | 4713846.148 | 3706655.7 | 41603631.5356 | 27011764.857 | 14591866.6786 | New V0 to be submitted to COR3/PREPA | LUMA is finalizing the scope and estimate. Expects to submit it to COR3/PREPA by Q3 FY2027.
169266 | FAASt Centro Medico 1327/1359 (Substattion) Rebuilt | Substation | Substation Rebuilds | Yes | Obligated | 16976611.278 | 6063148.102 | 4484183.594 | 1270820.683 | 11542228.878 | 2457771.126 | 42794763.661 | 33003023.75 | 9791739.911 | Amendment – Amendment Needed/Pending Development | LUMA is finalizing the scope. The amendment is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
169276 | FAASt Substation - Viaducto TC - MC 1100 - Equipment Repair & Replacement (Substation) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | 55931024.5724 | 25736012.7031 | 4317911.5193 | 1570417.2477 | 38843873.86 | 2801096.1 | 129200336.0024 | 99092809.9517 | 30107526.0508 | New V0 to be submitted to COR3/PREPA | LUMA finalizing scope and estimate and will be submitted to COR3/PREPA in Q3 FY2027
169495 | FAASt [Substations - Tapia GIS Rebuilt Equipment Repair &amp;amp; Replacement] (Substations) | Substation | Substation Rebuilds | Yes | Obligated | 8253800.1089 | 1962924.3274 | 1167269.299 | 530329.9907 | 3869859.11 | 3130140.89 | 18914323.7259 | 13290928.5179 | 5623395.208 | Amendment – Amendment Needed/Pending Development | LUMA is finalizing scope. The revised scope is expected to be submitted Q1 FY2027.
169500 | FAASt [Bayamon TC - MC-BKRS-Y1] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 7511561.2795 | 1144238.3003 | 763861.7166 | 260304.4243 | 924443.5657 | 1718189.3207 | 12322598.607 | 9199866.5618 | 3122732.0452 | Amendment – Amendment Needed/Pending Development | Luma is finalizing the scope. The amendment is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
169896 | FAASt - Costa Sur SP TC  Equipment Repair and | Substation | Substation Rebuilds | Yes | Obligated | 31075136.224 | 548761.477 | 3742364.835 | 58919.883 | 0 | 0 | 35425182.419 | 34817501.059 | 607681.36 | Amendment – Submitted to COR3/PREPA | Amendment submitted to COR3/PREPA on March 4, 2026. On April 2026, the estimate was reviewed and a new estimate for $35M will be submitted to COR3/PREPA.
174422 | FAASt - Catano-Rebuild 1801(Substation) | Substation | Substation | Yes | Obligated | 20620556.5073 | 3141135.3313 | 2096934.7257 | 714581.4152 | 4515587.433 | 8392761.2153 | 39481556.6278 | 27233078.666 | 12248477.9618 | Amendment – Scope and Cost development in progress | The scope of the amendment has been finalized. LUMA expects to submit the amendment by Q1 FY2027. Cost change is driven by more defined scope and inflation.
176913 | FAASt [Palo Seco SP to Catano Sect 38kV Line- 9500] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 17467604.15 | 3864276.13 | 2619374.41 | 2157076.76 | 2071399.22 | 66725.58 | 28246456.25 | 22158377.78 | 6088078.47 | Amendment - Pending Development | Information represents the latest LPCE information provided.
176971 | FAASt –38kV Line 8200 - San Juan SP to Catano Sect Line (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 18218875.04 | 4631659.7 | 2848814.49 | 568928.1 | 1080651.07 | 23122.43 | 27372050.83 | 22148340.6 | 5223710.23 | Amendment - Pending Development | Information represents the latest LPCE information provided.
178258 | FAASt - [Taft - MC 1105] (Substations) | Substation | Substation | Yes | Obligated | 11140186.6419 | 1696987.8503 | 1132861.9677 | 386050.2181 | 2678011.84 | 3321988.16 | 20356086.6779 | 14951060.4496 | 5405026.2283 | Amendment – Amendment Needed/Pending Development | LUMA is finalizing the scope. Amendment is expected to be submitted by Q2 FY2027. Cost change is driven by more defined scope and inflation.
178503 | FAASt Aguirre TC - BKRS (Substations) | Substation | Substation Rebuilds | Yes | Obligated | 38456815.04 | 776010.76 | 4013944.7 | 73159.13 | 0 | 0 | 43319929.63 | 42470759.74 | 849169.89 | Amendment to be submitted to COR3/PREPA | LUMA is finalizing the changes in scope and estimate. The amendment is expected to be submitted by Q1 FY2027.
178577 | FAASt [Cachete – MC 1526] (Substations) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 28780859.5334 | 8197490.385 | 3180011.1696 | 1083666.0036 | 39248524.9358 | 7152945.5114 | 87643497.5388 | 71209395.6388 | 16434101.9 | New V0 to be submitted to COR3/PREPA | LUMA finalizing scope and estimate and will be submitted to COR3/PREPA in Q2 FY2027
179558 | FAASt - Manatí TC - BRKS 230 kV - (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 1932688.3493 | 655782.0456 | 175000.6866 | 59635.7325 | 0 | 0 | 2823106.814 | 2107689.036 | 715417.778 | Amendment – Submitted to COR3/PREPA | This project is in closeout. Amendment submitted to COR3/PREPA.
180052 | FAASt Ponce TC to Salinas Urbano TC- 38kV 100 & 200 (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 189214147.25 | 38650198.93 | 18683215.39 | 6899520.54 | 21880052.02 | 41872865.87 | 317200000 | 229777414.66 | 87422585.34 | Amendment - Pending Development | Currently undergoing redesign with updated scope, latest estimate reflects $317M. The scope will be reconfigured to go from a double circuit (100 & 200) to a single circuit with a higher capacity.
334323 | FAASt Distribution Pole and Conductor Repair - Ponce Group 1 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 323692 | 54648 | 26179 | 14482 | 0 | 0 | 419001 | 349871 | 69130 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
334329 | FAASt Distribution Pole and Conductor Repair - Ponce Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 342249.92 | 50699 | 25530 | 13435 | 0 | 0 | 431913.92 | 367779.92 | 64134 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
334468 | FAASt Line 2200 Dos Bocas HP to Dorado TC (T | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 3049725.4 | 33717.27 | 129281.25 | 2827.08 | 9793.65 | 0 | 3225344.65 | 3188800.3 | 36544.35 | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
334470 | FAASt [TL 3100 Monacillos TC to Sabana Llana TC] (Transmission) | Priority Transmission | Transmission Line Rebuild | Yes | Obligated | 27732104.95 | 8785252.58 | 4550630.02 | 2355507.88 | 5594861.69 | 10425727.74 | 59444084.86 | 37877596.66 | 21566488.2 | Amendment - Pending Development | The information reflects the latest LPCE data provided. The cost currently includes the full line rebuild A&E design cost, under 428. This will be corrected through the obligation amendment.
334488 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 142917 | 9779 | 11465 | 1047 | 0 | 0 | 165208 | 154382 | 10826 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
334527 | FAASt [Distribution Pole and Conductor Repair – Caguas Group 8 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 108847 | 12431 | 8540 | 2443 | 0 | 0 | 132261 | 117387 | 14874 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
542517 | FAASt -Luquillo Distribution Streetlighting | Distribution | Distribution Streetlighting | Yes | Obligated | 4946319 | 158253.8999 | 989521 | 36758.1001 | 0 | 0 | 6130852 | 5935840 | 195012 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $4M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 81.19% (1986 locations completed). Estimate ammedment submission Q1 FY2027.
542687 | FAASt Lajas Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10510560 | 793672.8937 | 1674019 | 194038.1063 | 0 | 0 | 13172290 | 12184579 | 987711 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $45K for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 93.87% (3888 locations completed).Estimate ammedment submission Q1 FY2027.
542688 | FAASt Aguada Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 17056591 | 1425202.197 | 2565976 | 329317.803 | 0 | 0 | 21377087 | 19622567 | 1754520 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $1.2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 88.74% (6047 locations completed).
542690 | FAASt Maunabo Streetlighting (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5640236 | 197986.2881 | 984819 | 48872.7119 | 0 | 0 | 6871914 | 6625055 | 246859 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $1M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 95.09% (2306 locations completed).Estimate ammedment submission Q1 FY2027.
542756 | FAASt Streetlighting - Guánica (Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 6817015 | 506125.5667 | 1189325 | 116896.4333 | 0 | 0 | 8629362 | 8006340 | 623022 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $3M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 86.43% (2598 locations completed). Estimate ammedment submission Q1 FY2027.
542758 | FAASt Substation Minor Repairs -Group B (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 8776075.803 | 1217442.578 | 451066.682 | 80034.625 | 0 | 0 | 10524619.688 | 9227142.485 | 1297477.203 | Amendment – Submitted to COR3/PREPA | Amendment submitted to COR3/PREPA on March 2, 2026.
542762 | FAASt Distribution Pole and Conductor Repair – Arecibo Group 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 610448 | 146428 | 50794 | 10992 | 0 | 0 | 818662 | 661242 | 157420 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
546370 | FAASt - Substation Minor Repairs Group A (Subs | Substation | Substation Rebuilds | Yes | Obligated | 4931269.761 | 367083.277 | 1095995.021 | 169939.561 | 0 | 0 | 6564287.62 | 6027264.782 | 537022.838 | Amendment – Amendment Needed/Pending Development | LUMA finalizing scope, amendment to be submitted Q1 FY2026. Cost change is driven by more defined scope and inflation.
546371 | FAASt- Substation Minor Repairs Group C (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2913084.966 | 288261.908 | 711120.476 | 134833.446 | 0 | 0 | 4047300.796 | 3624205.442 | 423095.354 | Amendment – Amendment Needed/Pending Development | LUMA is working on the scope. The amendment is expected to be submitted by Q1 FY2027. Cost change is driven by more defined scope and inflation.
547187 | FAASt [Substation Component Replacement Program] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 8910537.185 | 272764.041 | 2942350.301 | 89054.581 | 2669172.077 | 22183.282 | 14906061.467 | 14522059.563 | 384001.904 | New V0 submitted to COR3/PREPA | LUMA finalizing scope and estimate and addressing comments from COR3.
547251 | FAASt Line 2400 Dos Bocas HP to America Apparel (Transmission) | Transmission | Transmission Line Rebuild | Yes | Obligated | 41036495.65 | 5812385.04 | 3399766.76 | 535704.77 | 7682133.79 | 343803.19 | 58810289.2 | 52118396.2 | 6691893 | Amendment - Pending Development | The information reflects the latest LPCE data provided. The cost currently includes the full line rebuild A&E design cost, under 428. This will be corrected through the obligation amendment.
549715 | FAASt Substation Minor Repairs - Group D (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 2841446.894 | 201293.004 | 638207.559 | 115642.934 | 0 | 0 | 3796590.391 | 3479654.453 | 316935.938 | Amendment – Amendment Needed/Pending Development | LUMA is finalizing scope. The amendment is expected to be submitted by Q2 FY2027. Cost change is driven by more defined scope and inflation.
549725 | FAASt [Substation Minor Repairs - Group E] (Substation) | Substation | Substation | Yes | Obligated | 4316417.259 | 414743.23 | 900049.964 | 223001.042 | 0 | 0 | 5854211.495 | 5216467.223 | 637744.272 | Amendment – Amendment Needed/Pending Development | LUMA is working on the project scope with Genera, amendment to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
549764 | FAASt Physical Security - Group 2 (Substation) | Substation | Substation Security | Yes | Obligated | 2374913.541 | 165562.287 | 582748.639 | 81586.461 | 0 | 0 | 3204810.928 | 2957662.18 | 247148.748 | Amendment – Amendment Needed/Pending Development | LUMA is finalizing the scope. The revised scope is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
550106 | FAASt [Conquistador CH] (Substation) | Substation | Substation Rebuilds | No | Pending Scope & Cost Completion by Applicant | 8360260.4039 | 1994931.4709 | 823453.8066 | 341756.0115 | 4324989.8973 | 4563696.6127 | 20409088.2028 | 13508704.1077 | 6900384.0951 | New V0 to be submitted to COR3/PREPA | LUMA is finalizing the scope and estimate. Amendment to be submitted to COR3/PREPA by Q1 FY2027.
550896 | FAASt Line 6700 Martin Peña TC to Villamar Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1322875.5755 | 5312.0445 | 86031.6501 | 1203.8499 | 159132.66 | 10982.34 | 1585538.12 | 1568039.8856 | 17498.2344 | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
550910 | FAASt Physical Security - Group 1 (Substatio | Substation | Substation Security | Yes | Obligated | 6627797.242 | 509533.277 | 1406160.756 | 223021.579 | 0 | 0 | 8766512.854 | 8033957.998 | 732554.856 | Amendment – Submitted to COR3/PREPA | LUMA is currently discussing the amendment with COR3/PREPA.
550950 | FAASt - EPC - [Monacillo TC] (Substations) | Priority Substation | Substation | Yes | Obligated | 105263051.6657 | 16405165.3271 | 16410099.5355 | 1849115.9258 | 62121740.86 | 11046468.76 | 213095642.0741 | 183794892.0613 | 29300750.0129 | Amendment to be submitted to COR3/PREPA | LUMA finalizing changes in scope and estimate and will submit the amendment Q1 FY2027.
551861 | FAASt [Physical Security - Group 3] (Substation) | Substation | Substation Security | Yes | Obligated | 4066652.26 | 333495.019 | 929320.381 | 146526.534 | 0 | 0 | 5475994.194 | 4995972.641 | 480021.553 | Amendment – Submitted to COR3/PREPA | LUMA is currently discussing the amendment with COR3/PREPA.
551914 | FAASt [Caparra 1912 & 1924] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 7611654.41 | 6435512.38 | 708217.1 | 448433.37 | 5350921.67 | 6374855.95 | 26929594.88 | 13670793.18 | 13258801.7 | New V0 to be submitted to COR3/PREPA | LUMA is finalizing the scope and estimate and expects to submit it COR3/PREPA in Q1 FY2027.
551925 | FAASt [SCADA Remote Access and RTU Replacements Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 7507076.66 | 1853362.06 | 1043403.42 | 266016.14 | 0 | 0 | 10669858.28 | 8550480.08 | 2119378.2 | Amendment submitted to FEMA April 7, 2026 | Split revised 428/406 , 1 additional site was included + Rooftop repairs costs submitted in the amendment to address actual cost. E&M changed to 0.
551926 | FAASt [SCADA Remote Access and RTU Replacements Group 2] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 5664186.55 | 939009.1711 | 800287.41 | 134453.44 | 0 | 0 | 7537936.5711 | 6464473.96 | 1073462.6111 | Amendment - In process | Amendment to be submitted to include the 428/406 split and actual cost.
551963 | FAASt [Transport Network Group 1] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 4489030.64 | 3693295.57 | 671253.14 | 539034.63 | 0 | 0 | 9392613.98 | 5160283.78 | 4232330.2 | Amendment – Submitted to FEMA | Amendment submitted to include the 428/406 split.
657300 | FAASt ENERGY MANAGEMENT SYSTEM (EMS) (Telecom) | Telecommunication | IT/OT | Yes | Obligated | 36900874.92 | 29069659.63 | 2477105.02 | 1951041.22 | 0 | 0 | 70398680.79 | 39377979.94 | 31020700.85 | Amendment submitted to FEMA March 30, 2026 | Amendment included the revision of the 428/406 split and cost update reflecting the current cost. E&M changed to 0.
659623 | FAASt Distribution Streetlighting - Cataño ( | Distribution | Distribution Streetlighting | Yes | Obligated | 7282778 | 499180.1274 | 1345465 | 156938.8726 | 0 | 0 | 9284362 | 8628243 | 656119 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $11M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 55.73% (1299 locations completed).Estimate ammedment submission Q1 FY2027.
659625 | FAASt Distribution Streetlighting - Dorado | Distribution | Distribution Streetlighting | Yes | Obligated | 12068437 | 1385150.1318 | 1911204 | 171057.8682 | 0 | 0 | 15535849 | 13979641 | 1556208 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $11M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 76.39% (3314 locations completed).Estimate ammedment submission Q1 FY2027.
659715 | FAASt Distribution Streetlighting - Aibonito | Distribution | Distribution Streetlighting | Yes | Obligated | 5738710 | 137843.3353 | 1197087 | 52403.6647 | 0 | 0 | 7126044 | 6935797 | 190247 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at: $2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 89.62% (2496 locations completed). Estimate amendment submission Q1 FY2027.
659968 | FAASt [San Germán Streetlighting] (Distributio | Distribution | Distribution Streetlighting | Yes | Obligated | 26194807 | 3105148.8829 | 4178149 | 1064155.1171 | 0 | 0 | 34542260 | 30372956 | 4169304 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $5M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 83.80% (4339 locations completed). Estimate ammedment submission Q1 FY2027.
660227 | FAASt Hatillo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 16131869 | 1430424.6192 | 2596438 | 487221.3808 | 0 | 0 | 20645953 | 18728307 | 1917646 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $4M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 82.67% (4375 locations completed).
660239 | FAASt Streetlighting - Villalba (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12489008.47 | 607135.3755 | 1810409 | 85900.6245 | 0 | 0 | 14992453.47 | 14299417.47 | 693036 | Amendment - Pending Development | This project is currently over budget because the work assigned, based on vendor rates, exceeded the Class 3 estimate. Based on a high‑level evaluation, the work that can be executed within the remaining budget is estimated to be approximately $2,195,079.47 to cover both overruns and pending work (Added to 428 Child for FFO review). This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 90.60% (3065 locations completed).
660422 | FAASt [Physical Security - Group 4] (Substation) | Substation | Substation Security | Yes | Obligated | 3826369.8 | 249315 | 843279.8 | 122789.7 | 0 | 0 | 5041754.3 | 4669649.6 | 372104.7 | Amendment – Amendment Needed/Pending Development | LUMA is finalizing the scope. The amendment to be submitted Q2 FY27. Cost change is driven by more defined scope and inflation.
660437 | FAASt Manati Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 15401358 | 1286291.785 | 2596783 | 411619.215 | 0 | 0 | 19696052 | 17998141 | 1697911 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $14M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 63.98% (3704 locations completed). Estimate ammedment submission Q1 FY2027.
662238 | FAASt [Microwave Point-to-Point Backbone] (Telecommunications) | Telecommunication | IT/OT | No | Pending CRC Review | 28826526.1978 | 5417440.08 | 2708469.2267 | 509009.2933 | 0 | 0 | 37461444.7978 | 31534995.4245 | 5926449.3733 | Project in V0 - No amendment required at this time | Project under CRC review; Pending Obligation.
668583 | FAASt Line 13300 GOAB 13301C to Hato Tejas Se | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 909002.34 | 5807.1 | 55062.25 | 2246.48 | 100526.19 | 18046.81 | 1090691.17 | 1064590.78 | 26100.39 | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
668592 | FAASt Line 9800 Bayamon TC - Guaraguao Sect | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 524429.75 | 8046.34 | 34734.97 | 698.02 | 0 | 0 | 567909.08 | 559164.72 | 8744.36 | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
671502 | FAASt [Distribution Streetlighting - Yabucoa] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14918381.07 | 1418283.01 | 2742910.41 | 547325.25 | 0 | 0 | 19626899.74 | 17661291.48 | 1965608.26 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 63.93%/ (3096 locations completed).
673292 | FAASt Telecom Infrastructure - Cerro Puntas (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 8138862.31 | 34775.61 | 1076416.85 | 3866.5 | 0 | 0 | 9253921.27 | 9215279.16 | 38642.11 | Amendment Expected | Design Package expected June 2026. E&M changed to 0.
673504 | FAASt [Distribution Streetlighting - Gurabo] | Distribution | Distribution Streetlighting | Yes | Obligated | 13326352 | 1163470.3301 | 2498935 | 411543.6699 | 0 | 0 | 17400301 | 15825287 | 1575014 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $6M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 77.57% (2919 locations completed). Estimate ammedment submission Q1 FY2027.
673771 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1894033.53 | 373539 | 370850.25 | 98988 | 0 | 0 | 2737410.78 | 2264883.78 | 472527 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
673772 | FAASt [Distribution Pole and Conductor Repair - Mayagüez Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 3286536 | 660857 | 636837 | 175127 | 0 | 0 | 4759357 | 3923373 | 835984 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
673774 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 3378138.08 | 283336 | 273831 | 75084 | 0 | 0 | 4010389.08 | 3651969.08 | 358420 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
673775 | FAASt [Distribution Pole and Conductor Repair - Mayaguez Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5304271.78 | 777623 | 689888.45 | 79570.1 | 0 | 0 | 6851353.33 | 5994160.23 | 857193.1 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
673795 | FAASt Distribution Pole and Conductor Repair - Mayaguez Group 4 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1615221.64 | 291663 | 278116 | 77291 | 0 | 0 | 2262291.64 | 1893337.64 | 368954 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
673818 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 674464.58 | 151265 | 121044 | 20349 | 0 | 0 | 967122.58 | 795508.58 | 171614 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
673836 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4686914.68 | 841203 | 900014.8 | 222918.8 | 0 | 0 | 6651051.28 | 5586929.48 | 1064121.8 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
673838 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 329669.44 | 57917 | 55025 | 15348 | 0 | 0 | 457959.44 | 384694.44 | 73265 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
673839 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 69706.66 | 4609 | 10152 | 1221 | 0 | 0 | 85688.66 | 79858.66 | 5830 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. The scope was adjusted to address unforeseen site conditions, based on a high‑level assessment. The additional budget of $85,688.66 is to cover both overruns and outstanding activities. Project Class 3 estimate will be revised, any adjustments will be incorporated into the final amendment during closeout.
673843 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 2253235.45 | 179969 | 175796 | 47692 | 0 | 0 | 2656692.45 | 2429031.45 | 227661 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
673844 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1286113.33 | 252343 | 208800.58 | 66870.9 | 0 | 0 | 1814127.81 | 1494913.91 | 319213.9 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
673847 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 924289.93 | 39481 | 37242 | 10462 | 0 | 0 | 1011474.93 | 961531.93 | 49943 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
673848 | FAASt [Distribution Pole and Conductor Repair-Carolina Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 139921 | 4443 | 13281 | 1177 | 0 | 0 | 158822 | 153202 | 5620 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
674072 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 1] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 872891 | 188302.7 | 171585 | 49900.3 | 0 | 0 | 1282679 | 1044476 | 238203 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
674083 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1747929 | 286587 | 335722 | 75946 | 0 | 0 | 2446184 | 2083651 | 362533 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
674088 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1502387.82 | 228975 | 267370 | 60678 | 0 | 0 | 2059410.82 | 1769757.82 | 289653 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
674092 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 939116.74 | 71480 | 82578 | 18942 | 0 | 0 | 1112116.74 | 1021694.74 | 90422 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
674096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1773428 | 252057 | 332705 | 66795 | 0 | 0 | 2424985 | 2106133 | 318852 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
674098 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 84433 | 20556 | 16517 | 2766 | 0 | 0 | 124272 | 100950 | 23322 | Obligated - Final Ammendment Version once closeout stage | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
678789 | FAASt [Distribution Streetlighting - Carolina] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14865613.02 | 845273.47 | 2559492.85 | 313673.09 | 0 | 0 | 18584052.43 | 17425105.87 | 1158946.56 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 69.97% (3032 locations completed).
678793 | FAASt [Streetlighting - Mayagüez] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11019180.1 | 954580.45 | 2291581 | 397623.91 | 0 | 0 | 14662965.46 | 13310761.1 | 1352204.36 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 56.86% (1723 locations completed).
678800 | FAASt [Telecom Infrastructure – Group B] (Telecommunication) | Telecommunication | IT/OT | Yes | Obligated | 13148929.44 | 55895.837 | 2828793.1 | 10487.44 | 0 | 0 | 16044105.817 | 15977722.54 | 66383.277 | Obligated - No amendment need Identified | Design Package is expected by June 2026; but no change in cost expected.
678985 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 735890.97 | 42939 | 66915 | 11378.84 | 0 | 0 | 857123.81 | 802805.97 | 54317.84 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
678988 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 911136.76 | 163360 | 175440.55 | 43290.4 | 0 | 0 | 1293227.71 | 1086577.31 | 206650.4 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
679025 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 402804.8 | 42382 | 46884 | 6588 | 0 | 0 | 498658.8 | 449688.8 | 48970 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
679026 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 784267.71 | 81250 | 93451 | 12630 | 0 | 0 | 971598.71 | 877718.71 | 93880 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
679033 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 729040 | 142215 | 140628 | 37687 | 0 | 0 | 1049570 | 869668 | 179902 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
679039 | FAASt [Distribution Streetlighting - Caguas] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 22960633 | 1507378.5968 | 4065133 | 452047.4032 | 0 | 0 | 28985192 | 27025766 | 1959426 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $55M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 38.19% (2394 locations completed). Estimate ammedment submission Q1 FY2027.
679127 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 171152.23 | 36372 | 33340.3 | 9638.58 | 0 | 0 | 250503.11 | 204492.53 | 46010.58 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
679134 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 452956.93 | 87431 | 86724.25 | 23169.22 | 0 | 0 | 650281.4 | 539681.18 | 110600.22 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
679149 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 5 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 129744 | 21694 | 25191 | 5749 | 0 | 0 | 182378 | 154935 | 27443 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
679153 | FAASt Distribution Pole and Conductor Repair - Mayagüez Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 163846.51 | 40583 | 31068.05 | 10754.5 | 0 | 0 | 246252.06 | 194914.56 | 51337.5 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
679457 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 3] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 589335 | 123232 | 115386 | 33921 | 0 | 0 | 861874 | 704721 | 157153 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
679458 | FAASt [Distribution Pole and Conductor Repair - Ponce Group 4] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 498436 | 75480 | 95421 | 20002 | 0 | 0 | 689339 | 593857 | 95482 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
679780 | FAASt [Distribution Streetlighting - Bayamon] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 20710527 | 871692 | 3212958 | 304684 | 0 | 0 | 25099861 | 23923485 | 1176376 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 76.90% (5076 locations completed).
681672 | FAASt Transmission Priority Pole Replacements 2300 | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 835010.89 | 2243 | 0 | 699 | 0 | 0 | 837952.89 | 835010.89 | 2942 | Obligated - Amendment Pending Final Actual Costs | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
682028 | FAASt [Pole and Conductor Repair - San Juan Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 431381.68 | 83592 | 83822 | 22151.62 | 0 | 0 | 620947.3 | 515203.68 | 105743.62 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682031 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 516951 | 85571 | 94044 | 22676 | 0 | 0 | 719242 | 610995 | 108247 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682121 | FAASt - EPC -Aguirre TC-Phase II (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 83657110.0997 | 3775560.6762 | 8101618.921 | 359601.847 | 36352089.0673 | 1554241.9338 | 133800222.545 | 128110818.088 | 5689404.457 | Amendment – Scope and Cost development in progress | LUMA working on the scope. Amendment to be submitted Q2 FY2027.
682135 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 577000.79 | 92316 | 109858.85 | 24463.74 | 0 | 0 | 803639.38 | 686859.64 | 116779.74 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682136 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 469650.95 | 75853 | 90259.5 | 20101.05 | 0 | 0 | 655864.5 | 559910.45 | 95954.05 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682172 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 362192.7 | 43995.35 | 40930 | 6838 | 0 | 0 | 453956.05 | 403122.7 | 50833.35 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
682178 | FAASt [Pole and Conductor Repair - Arecibo Group 7] (Distribution ) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 208544.25 | 42487 | 40949.45 | 11259.06 | 0 | 0 | 303239.76 | 249493.7 | 53746.06 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682180 | FAASt [Pole and Conductor Repair - Mayagüez Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 120882.62 | 8412 | 8414 | 1308 | 0 | 0 | 139016.62 | 129296.62 | 9720 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
682210 | FAASt [Pole and Conductor Repair - Mayagüez Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 198050.74 | 33041 | 38248.35 | 8755.87 | 0 | 0 | 278095.96 | 236299.09 | 41796.87 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682228 | FAASt [Pole and Conductor Repair - Ponce Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 775779 | 139828 | 150784 | 37054.42 | 0 | 0 | 1103445.42 | 926563 | 176882.42 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682324 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 573047.24 | 107654 | 110616.4 | 28528.31 | 0 | 0 | 819845.95 | 683663.64 | 136182.31 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682328 | FAASt [Bayamón TC - Rebuild] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 87274829.6388 | 13294600.018 | 8875105.814 | 3024407.7676 | 21340863.5442 | 19963184.0398 | 153772990.8224 | 117490798.997 | 36282191.8254 | New V0 to be submitted to COR3/PREPA | LUMA is finalizing the scope and estimate and will be submitted to COR3/PREPA in Q2 FY2027
682373 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 65944 | 9218 | 12740 | 2443 | 0 | 0 | 90345 | 78684 | 11661 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682645 | FAASt [Maunabo TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 64448906.8891 | 9817520.6097 | 6553904.1509 | 2233401.949 | 7931690.2403 | 14741998.2911 | 105727422.13 | 78934501.2803 | 26792920.8497 | Amendment – Pending Design Package for Development | LUMA isworking on the scope. Amendment to be submitted by Q2 FY2027. Cost change is driven by more defined scope and inflation.
682834 | FAASt [EPC - Costa Sur TC - Phase II & III ] (Substation) | Priority Substation | Substation Rebuilds | Yes | Obligated | 53265182.432 | 7858797.408 | 5239198.272 | 1746399.424 | 14525597.69 | 37474402.31 | 120109577.536 | 73029978.394 | 47079599.142 | Amendment – Scope and Cost development in progress | LUMA finalizing scope. The amendment to be submitted Q2 FY2027. Cost change is driven by more defined scope and inflation.
682865 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 152533.26 | 16132 | 13377 | 2508 | 0 | 0 | 184550.26 | 165910.26 | 18640 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
682870 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 115082.99 | 13827 | 16716.65 | 3664 | 0 | 0 | 149290.64 | 131799.64 | 17491 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
682882 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 545661.24 | 89627 | 104353.35 | 23751.16 | 0 | 0 | 763392.75 | 650014.59 | 113378.16 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682890 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 510067.96 | 80878 | 98275.6 | 21432.67 | 0 | 0 | 710654.23 | 608343.56 | 102310.67 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
682898 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 853881.22 | 82921.49 | 120284.25 | 12889.35 | 0 | 0 | 1069976.31 | 974165.47 | 95810.84 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
682910 | FAASt [Distribution Pole and Conductor Repair - Bayamón Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 580036.28 | 82945 | 99229 | 12530 | 0 | 0 | 774740.28 | 679265.28 | 95475 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
684920 | FAASt Substation High Voltage Replacement_Group 1 (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 12563778.153 | 189367.6032 | 5504338.38 | 0 | 0 | 0 | 18257484.1362 | 18068116.533 | 189367.6032 | Amendment – Scope and Cost development in progress | LUMA finalizing the scope. The amendment is expected to be submitted Q2 FY2027. Cost change is driven by more defined scope and inflation.
685263 | FAASt Distribution Pole and Conductor Repair - Ponce Group 6 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 537688 | 106478 | 103281 | 28217 | 0 | 0 | 775664 | 640969 | 134695 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
685370 | FAASt [Pole and Conductor Repair - Mayagüez Group 8] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 68823 | 11847 | 13127 | 3139 | 0 | 0 | 96936 | 81950 | 14986 | Obligated - Final Ammendment Version once closeout stage | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
685477 | FAASt [Pole and Conductor Repair - Arecibo Group 6] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 392742.1 | 47748.1 | 67123 | 6914 | 0 | 0 | 514527.2 | 459865.1 | 54662.1 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
685943 | FAASt Distribution Pole and Conductor Repair Ponce Group 5(Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 254972.22 | 50008 | 49774.2 | 13252 | 0 | 0 | 368006.42 | 304746.42 | 63260 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
686453 | FAASt [Pole and Conductor Repair - Mayagüez Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 39233.59 | 3949 | 4059 | 1046 | 0 | 0 | 48287.59 | 43292.59 | 4995 | Amendment - Pending Development | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
686471 | FAASt [Pole and Conductor Repair - Arecibo Group 5] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 319916.81 | 57115.8 | 49227 | 14392 | 0 | 0 | 440651.61 | 369143.81 | 71507.8 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
686480 | FAASt [Pole and Conductor Repair - Ponce Group 7] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 523404 | 85891 | 101359 | 22761 | 0 | 0 | 733415 | 624763 | 108652 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
688096 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 21408.25 | 4609 | 4169.45 | 1221.39 | 0 | 0 | 31408.09 | 25577.7 | 5830.39 | Obligated - Final Ammendment Version once closeout stage | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
688109 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 448719.06 | 90680 | 87443.55 | 24030.2 | 0 | 0 | 650872.81 | 536162.61 | 114710.2 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
688198 | FAASt [Pole and Conductor Repair - Arecibo Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 60838.48 | 12667 | 12052.8 | 3356.76 | 0 | 0 | 88915.04 | 72891.28 | 16023.76 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
688472 | FAASt [Pole and Conductor Repair - Mayaguez Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 164908.86 | 11846.54 | 29921.55 | 3139.46 | 0 | 0 | 209816.41 | 194830.41 | 14986 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
688625 | FAASt [Pole and Conductor Repair - Ponce Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 710014.69 | 151206 | 139357.85 | 40069.59 | 0 | 0 | 1040648.13 | 849372.54 | 191275.59 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
688627 | FAASt [Distribution Pole and Conductor Repair - Arecibo Group 9] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 303774 | 57066 | 58918 | 15122.49 | 0 | 0 | 434880.49 | 362692 | 72188.49 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
688629 | FAASt [Pole and Conductor Repair - Mayagüez Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 106941.99 | 22045 | 20833.9 | 5841.93 | 0 | 0 | 155662.82 | 127775.89 | 27886.93 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
688630 | FAASt [Pole and Conductor Repair - Mayagüez Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 59446.36 | 7898 | 8327.05 | 2092.97 | 0 | 0 | 77764.38 | 67773.41 | 9990.97 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
688774 | FAASt Distribution Pole and Conductor Repair - Ponce Group 9 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 443331 | 77853 | 86719 | 20631 | 0 | 0 | 628534 | 530050 | 98484 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
689071 | FAASt [Pole and Conductor Repair - Arecibo Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 106997.11 | 13827 | 11878.8 | 3664.16 | 0 | 0 | 136367.07 | 118875.91 | 17491.16 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
690545 | FAASt Aguadilla Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10433035 | 1035906.3077 | 2151690 | 358776.6923 | 0 | 0 | 13979408 | 12584725 | 1394683 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $10M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 46.93% (1148 locations completed). Estimate ammedment submission Q1 FY2027.
691246 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 10] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 374263.26 | 26654 | 41363.6 | 7063.31 | 0 | 0 | 449344.17 | 415626.86 | 33717.31 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and proceed with the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, and any necessary cost adjustments will be incorporated into the final version.
691702 | FAASt Distribution Streetlighting - Trujillo Alto (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9704697 | 860820.467 | 1981105 | 277993.533 | 0 | 0 | 12824616 | 11685802 | 1138814 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $16M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 36.09% (939 locations completed). Estimate ammedment submission Q1 FY2027.
698424 | FAASt Streetlight Florida Distribution | Distribution | Distribution Streetlighting | Yes | Obligated | 7063699 | 741458.8765 | 1487857 | 285427.1235 | 0 | 0 | 9578442 | 8551556 | 1026886 | Amendment - Pending Development | This project was among the first to be developed, originally including the underground work as part of the program's initial scope—estimated at $2M for this portion to be removed. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 85.08% (1454 locations completed).Estimate ammedment submission Q1 FY2027.
698439 | FAASt Streetlight - Las Marías (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7073217 | 888414 | 1653390 | 399291 | 0 | 0 | 10014312 | 8726607 | 1287705 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 51.97% (898 locations completed).
698458 | FAASt [Distribution Streetlighting - Guaynabo] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9762754.59 | 605024.35 | 1979750.26 | 248032.07 | 0 | 0 | 12595561.27 | 11742504.85 | 853056.42 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 77.27% (2237 locations completed).
698511 | FAASt [Culebra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 1155804 | 91406 | 476440 | 62197 | 0 | 0 | 1785847 | 1632244 | 153603 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 78.02% (323 locations completed).
698570 | FAASt [Distribution Streetlighting - Corozal] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13720208.31 | 1608383.29 | 2501126 | 617490.33 | 0 | 0 | 18447207.93 | 16221334.31 | 2225873.62 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 81.41% (3180 locations completed).
698579 | FAASt [Distribution Streetlighting - Orocovis] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9591989.9 | 925633.77 | 1873982.08 | 414167.51 | 0 | 0 | 12805773.26 | 11465971.98 | 1339801.28 | Obligated - Final Ammendment Version once closeout stage | This project is currently over budget because the work assigned, based on vendor rates, exceeded the Class 3 estimate. Based on a high‑level evaluation, the work that can be executed within the remaining budget is estimated to be approximately $1,521,024.94 to cover both overruns and pending work (Added to 428 Child for FFO review). This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 72.60% (1627 locations completed).
701472 | FAASt [Comerio Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 6538769.44 | 585944.46 | 1640383 | 276181.29 | 0 | 0 | 9041278.19 | 8179152.44 | 862125.75 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 82.75% (1382 locations completed).
701495 | FAASt [Pole and Conductor Repair - Mayagüez Group 14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 20549.54 | 4609 | 3959.6 | 1221.39 | 0 | 0 | 30339.53 | 24509.14 | 5830.39 | Amendment - Pending Development | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
701504 | FAASt [Pole and Conductor Repair - Arecibo Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 150345 | 29943 | 29252 | 7935 | 0 | 0 | 217475 | 179597 | 37878 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
701545 | FAASt [Pole and Conductor Repair - Ponce Group 11] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 487190 | 102007 | 95198 | 27032 | 0 | 0 | 711427 | 582388 | 129039 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
701552 | FAASt [Pole and Conductor Repair - Ponce Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 186321 | 40981 | 36670 | 10860 | 0 | 0 | 274832 | 222991 | 51841 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
701555 | FAASt [Pole and Conductor Repair - Ponce Group 13] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 547010 | 80962 | 104535 | 21455 | 0 | 0 | 753962 | 651545 | 102417 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
701679 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 12] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 168343.89 | 12827 | 12535.35 | 3399.16 | 0 | 0 | 197105.4 | 180879.24 | 16226.16 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
703535 | FAASt [Toa Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9529190.37 | 444807.71 | 1814022 | 175326.98 | 0 | 0 | 11963347.06 | 11343212.37 | 620134.69 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 62.61% (1492 locations completed).
704679 | FAASt Coamo Streetlight (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 14311922.45 | 1481726 | 2687463.9 | 579175.35 | 0 | 0 | 19060287.7 | 16999386.35 | 2060901.35 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 64.97% (3177 locations completed).
704750 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 10 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 486385 | 72920 | 92511 | 19324 | 0 | 0 | 671140 | 578896 | 92244 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
704751 | FAASt Distribution Pole and Conductor Repair - Bayamon Group 11 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 338491 | 76424 | 66168 | 20252 | 0 | 0 | 501335 | 404659 | 96676 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
704755 | FAASt [Distribution Pole and Conductor Repair-Bayamon Group 12-13-14] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 725501.08 | 76551.4 | 83450.9 | 18053.92 | 0 | 0 | 903557.3 | 808951.98 | 94605.32 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
704844 | FAASt [Distribution Pole and Conductor Repair - Caguas Group 16-17-18-19-20] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 320740 | 70006 | 62490 | 18552 | 0 | 0 | 471788 | 383230 | 88558 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
704849 | FAASt [Naguabo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11620676.42 | 1182070.57 | 2380242.99 | 487666.4 | 0 | 0 | 15670656.38 | 14000919.41 | 1669736.97 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 72.69%/2661 locations completed.
704868 | FAASt [Ceiba Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5152111.14 | 472131.79 | 1481546.84 | 244786.81 | 0 | 0 | 7350576.58 | 6633657.98 | 716918.6 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 66.77% (1125 locations completed).
704916 | FAASt [Pole and Conductor Repair - Arecibo Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 273996 | 23695 | 49755 | 6279 | 0 | 0 | 353725 | 323751 | 29974 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
704921 | FAASt [Barranquitas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 9430329.22 | 1104151.73 | 2048083.31 | 472894.36 | 0 | 0 | 13055458.62 | 11478412.53 | 1577046.09 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 66.99% (1727 locations completed).
704927 | FAASt [Añasco Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12087876.17 | 1294052.66 | 2420466.41 | 526309.26 | 0 | 0 | 16328704.5 | 14508342.58 | 1820361.92 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 89.01% (3354 locations completed).
704933 | FAASt [Distribution Pole and Conductor Repair - San Juan Group 13-14-15-16] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1201420 | 177653 | 231255 | 47078 | 0 | 0 | 1657406 | 1432675 | 224731 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
704938 | FAASt [Distribution Streetlighting - Las Piedras (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13807923.4 | 1285354.42 | 2760454.04 | 522246.69 | 0 | 0 | 18375978.55 | 16568377.44 | 1807601.11 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 69.50% (3480 locations completed).
704943 | FAASt [Naranjito Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 11644048.42 | 1501948.72 | 2348209.91 | 613589.66 | 0 | 0 | 16107796.71 | 13992258.33 | 2115538.38 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 67.10% (2144 locations completed).
705527 | FAASt [Distribution Pole and Conductor Repair - San Juan 17-18-19-20-21] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 668853.23 | 98919 | 125147 | 26214 | 0 | 0 | 919133.23 | 794000.23 | 125133 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
705584 | FAASt [Distribution Pole and Conductor Repair - Ponce Groups 14 &amp;amp; 15] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1511604.39 | 299196 | 284698 | 79287 | 0 | 0 | 2174785.39 | 1796302.39 | 378483 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
708579 | FAASt [Pole and Conductor Repair - Ponce Group 16, 17, 18 & 19] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1976883.61 | 307856.04 | 343118.15 | 81581.8 | 0 | 0 | 2709439.6 | 2320001.76 | 389437.84 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
708637 | FAASt T-Pole Program Line 3700] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1367810.2561 | 38822.55 | 41458.8653 | 5793.0785 | 35983.6407 | 6521.5294 | 1496389.92 | 1445252.7621 | 51137.1579 | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
709631 | FAASt [Morovis Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 13486398.85 | 1257031.57 | 2499521.06 | 487450.7 | 0 | 0 | 17730402.18 | 15985919.91 | 1744482.27 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 78.98% (2585 locations completed).
710094 | FAASt [Pole and Conductor Repair - Bayamon Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7096249.5 | 165571 | 614123.07 | 29565.32 | 0 | 0 | 7905508.89 | 7710372.57 | 195136.32 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
710099 | FAASt [Pole and Conductor Repair - Arecibo Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 7366388.46 | 153523.07 | 602047.2 | 42926.93 | 0 | 0 | 8164885.66 | 7968435.66 | 196450 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
710110 | FAASt [Distribution Pole and Conductor Repair - Bayamon Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 94998.5 | 2000 | 14756.12 | 478.06 | 0 | 0 | 112232.68 | 109754.62 | 2478.06 | Amendment - Pending Development | Project is 100% executed, and QC has been fully completed. This project was obligated under a 428/406 based on a Class 3 estimate. Reconciliation of actual costs is currently in progress in order to initiate close out according to FEMA Guidelines.
711670 | FAASt [T-Pole Program Line 100] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 441327.62 | 18841.36 | 12340.69 | 4531.35 | 0 | 0 | 477041.02 | 453668.31 | 23372.71 | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
711819 | FAASt [Transmission Priority Pole Replacement Program Line 13400 San German Sect-La Parguera Sect] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 2202286.53 | 160980.0333 | 201035.14 | 15575.52 | 147447.87 | 21069.57 | 2748394.6633 | 2550769.54 | 197625.1233 | Obligated - No amendment need Identified | Information represents the latest LPCE information provided.
711856 | FAASt [Pole and Conductor Repair - Bayamon Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 11304564.29 | 328412 | 891093.89 | 67251.43 | 0 | 0 | 12591321.61 | 12195658.18 | 395663.43 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
711888 | FAASt [Pole and Conductor Repair - Caguas Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5425810.57 | 132877 | 434784.65 | 33026.3 | 0 | 0 | 6026498.52 | 5860595.22 | 165903.3 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
712968 | FAASt [Pole and Conductor Repair - Arecibo Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 6147251.54 | 145147 | 503550 | 35903.97 | 0 | 0 | 6831852.51 | 6650801.54 | 181050.97 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
712980 | FAASt [T-Pole Program Line 3000] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1609934.104 | 43793.7069 | 46767.5976 | 6534.8717 | 40591.2804 | 7356.5994 | 1754978.16 | 1697292.9821 | 57685.1779 | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
714641 | FAASt [Rincón Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10842339.26 | 82026.55 | 1946225.97 | 106422.03 | 750618 | 506022 | 14233653.81 | 13539183.23 | 694470.58 | Obligated - No amendment need Identified | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at: 0.00%/0 locations completed.
714654 | FAASt [Advanced Metering Infrastructure (AMI)] (Telecommunications) | Telecommunication | AMI Implementation Program | Yes | Obligated | 332062581 | 517366615 | 1484008 | 26840980 | 0 | 0 | 877754184 | 333546589 | 544207595 | Obligated - No amendment need Identified | No changes needed.
723002 | FAASt - EPC - Jobos TC (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 51025274.884 | 7772694.8675 | 5188835.2651 | 1768221.5863 | 6279651.4998 | 11671486.0104 | 83706164.113 | 62493761.6489 | 21212402.4641 | New V0 to be submitted to COR3/PREPA | LUMA is finalizing the scope and estimate. Amendment to be submitted to COR3/PREPA by Q3 FY2027.
723077 | FAASt - EPC - [Sabana Llana TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 75932414.213 | 8971281.759 | 7744020.4116 | 1085098.707 | 39651716.253 | 10017910.1187 | 143402441.4624 | 123328150.8777 | 20074290.5847 | Amendment – Pending Design Package for Development | LUMA finalizing the scope. The amendment is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
723078 | FAASt - EPC - [San Juan SP TC] (Substation) | Substation | Substation Rebuilds | Yes | Obligated | 47732082.057 | 7712225.873 | 6479737.176 | 1137410.296 | 54699508.996 | 10188178.968 | 127949143.366 | 108911328.229 | 19037815.137 | Amendment – Scope and Cost development in progress | LUMA is working on the project scope with Genera. Amendment to be submitted Q2 FY2027. Cost change is driven by more defined scope and inflation.
723883 | FAASt [Region 1 -San Juan Group A] (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 66761022.13 | 18368702.69 | 879324.5 | 2687.33 | 0 | 0 | 86011736.65 | 67640346.63 | 18371390.02 | Obligated - Amendment Pending Final Actual Costs | Cost revised to aligned with the FEMA Obligation value from Version2 (Amendment 2 - its last amendment).
724600 | FAASt [Jayuya Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 7277670.2 | 931433.8 | 1704125.72 | 419107.52 | 0 | 0 | 10332337.24 | 8981795.92 | 1350541.32 | Obligated - Final Ammendment Version once closeout stage | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 73.80% (1332 locations completed).
724601 | FAASt [Salinas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12097203.53 | 1141690.52 | 2463885.54 | 469330.38 | 0 | 0 | 16172109.97 | 14561089.07 | 1611020.9 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 79.89% (3225 locations completed).
724698 | FAASt [Adjuntas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 10742462 | 1338877 | 2199843.63 | 552275 | 0 | 0 | 14833457.63 | 12942305.63 | 1891152 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 81.53% (2423 locations completed).
724703 | FAASt [Arroyo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 5314332 | 489465.16 | 1504203.15 | 250928.85 | 0 | 0 | 7558929.16 | 6818535.15 | 740394.01 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 76.83% (1502 locations completed).
724825 | FAASt [Cidra Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12812478.84 | 1311297.11 | 2516455.74 | 526932.49 | 0 | 0 | 17167164.18 | 15328934.58 | 1838229.6 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 69.99% (2551 locations completed).
724938 | FAASt [Vega Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | Yes | Obligated | 12445015.33 | 1331810.63 | 2459742.66 | 537278.89 | 0 | 0 | 16773847.51 | 14904757.99 | 1869089.52 | Amendment - Pending Development | This project is ongoing and currently within budget. This Class 3 estimate any required adjustments will be incorporated into the final amendment version. As of March 2026, the project is at 61.03% (2401 locations completed).
727522 | FAASt [Region 3 Bayamon TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 2653352.966 | 8930252.562 | 79600.589 | 267907.5769 | 0 | 0 | 11931113.6938 | 2732953.555 | 9198160.1389 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
727529 | FAASt [Region 6 Ponce TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 7751854.11 | 26340450.42 | 95803.98 | 245287.236 | 0 | 0 | 34433395.746 | 7847658.09 | 26585737.656 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
727531 | FAASt [Region 6 -Ponce Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 6849050.26 | 15776180 | 110659.38 | 3288703.85 | 0 | 0 | 26024593.49 | 6959709.64 | 19064883.85 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
727572 | FAASt [Region 3 -Bayamon Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 11268772.7 | 30826184.94 | 179741.68 | 491691 | 0 | 0 | 42766390.32 | 11448514.38 | 31317875.94 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
727606 | FAASt [Region 4 Caguas TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 4217039.02 | 14325508.11 | 50985.56 | 133401.828 | 0 | 0 | 18726934.518 | 4268024.58 | 14458909.938 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
727608 | FAASt [Region 1 San Juan TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 3698704.16 | 12571501.92 | 46746.2 | 117068.19 | 0 | 0 | 16434020.47 | 3745450.36 | 12688570.11 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
727657 | FAASt [Region 5 Mayaguez TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 3096774.74 | 10517290.41 | 36660.8 | 97938.99 | 0 | 0 | 13748664.94 | 3133435.54 | 10615229.4 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
727659 | FAASt [Region 2 Arecibo TL - 115kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 2669312.23 | 8989281.612 | 80079.3669 | 269678.4484 | 0 | 0 | 12008351.6573 | 2749391.5969 | 9258960.0604 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
727692 | FAASt [Region 4 -Caguas Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 7414164.75 | 20309782.6 | 119789.88 | 328143.02 | 0 | 0 | 28171880.25 | 7533954.63 | 20637925.62 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
728827 | FAASt [Region 2 -Arecibo Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 4807675.47 | 13169769.88 | 79166.85 | 216863.46 | 0 | 0 | 18273475.66 | 4886842.32 | 13386633.34 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
728832 | FAASt [Region 5 -Mayaguez Group A] High Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 3767690.42 | 8682952.46 | 62820.38 | 1810049.02 | 0 | 0 | 14323512.28 | 3830510.8 | 10493001.48 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
729286 | FAASt HV Equipment Replacement Group 2 (Substation) | Substation | Substation | Yes | Obligated | 17860595.12 | 0 | 5206874.3 | 0 | 0 | 0 | 23067469.42 | 23067469.42 | 0 | Amendment – Scope and Cost development in progress | LUMA finalizing the scope. The amendment is expected to be submitted Q2 FY2027. Cost change is driven by more defined scope and inflation.
735474 | FAASt [Pole and Conductor Repair -Caguas Group 3 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 17211915.22 | 71312.91 | 1524520.51 | 44805.65 | 1144636.03 | 468198.97 | 20465389.29 | 19881071.76 | 584317.53 | Amendment - Pending Development | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate.
738120 | FAASt [Pole and Conductor Repair-Carolina Group 2- Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 11242486.77 | 234531 | 1159111 | 175368.81 | 0 | 0 | 12811497.58 | 12401597.77 | 409899.81 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
738670 | FAASt [Pole and Conductor Repair - Ponce Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 4926640 | 116500.11 | 439974.62 | 31370.9 | 0 | 0 | 5514485.63 | 5366614.62 | 147871.01 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
738672 | FAASt [Pole and Conductor Repair - Mayaguez Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 10313627 | 243129 | 834793 | 63002.37 | 0 | 0 | 11454551.37 | 11148420 | 306131.37 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
738971 | FAASt [Pole and Conductor Repair - Caguas Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 13884126 | 310288 | 1643630 | 66835.67 | 0 | 0 | 15904879.67 | 15527756 | 377123.67 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
741105 | FAASt [All Regions TL - 230kV] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 18022659.27 | 75789392.67 | 204576.49 | 702611.58 | 0 | 0 | 94719240.01 | 18227235.76 | 76492004.25 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. Amendment will be needed after work completion and /or assessment completion.
742026 | FAASt [Pole and Conductor Repair - San Juan Group 2 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 1740768.37 | 68617 | 83942.74 | 15418.96 | 0 | 0 | 1908747.07 | 1824711.11 | 84035.96 | Amendment - Pending Development | The project was obligated under Sections 428/406 using a Class 3 estimate. Additional funding will be required to complete the remaining work and the TPA removal. The final reconciliation of the project’s incremental costs will be conducted during the closeout phase, any necessary cost adjustments will be incorporated into the final version.
742070 | FAASt [Pole and Conductor Repair - San Juan Group 1 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 5461200.05 | 170555 | 491326.68 | 35032.38 | 0 | 0 | 6158114.11 | 5952526.73 | 205587.38 | Obligated - Final Ammendment Version once closeout stage | This project was obligated under a 428/406 split using a Class 3 estimate. The project remains ongoing and currently within budget. Reconciliation of actual costs will be addressed during the closeout phase.
743399 | FAASt [High Voltage Equipment Replacement - Group 3] (Substation) | Substation | Substation | Yes | Obligated | 21038292.91 | 0 | 4509930.04 | 0 | 3457839.23 | 0 | 29006062.18 | 29006062.18 | 0 | Amendment – Scope and Cost development in progress | LUMA is finalizing the scope. The amendment is expected to be submitted Q2 FY2027.
745856 | FAASt [Automation Program Group 14] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1410445.2 | 555441.55 | 112272.97 | 65062.72 | 148295.58 | 442571.92 | 2734089.94 | 1671013.75 | 1063076.19 | Amendment – Submitted to FEMA | 406HM revision currently Pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3.
745859 | FAASt [Automation Program Group 18: DAR – SAN JUAN 2001- FY24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 223935.37 | 120620.22 | 21856.33 | 15504.92 | 33515.73 | 77702.27 | 493134.84 | 279307.43 | 213827.41 | Amendment – Submitted to FEMA | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $15,417.30 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
745861 | FAASt [Automation Program Group 12] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2168647.62 | 784104.06 | 196183.24 | 101775.43 | 228547.36 | 557560.64 | 4036818.35 | 2593378.22 | 1443440.13 | Amendment – Submitted to FEMA | 406HM revision pending Award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $84,795.15 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
746309 | FAASt [Automation Program Group 30] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 327791.49 | 132752.89 | 53695.19 | 28394.95 | 65212.75 | 98251.25 | 706098.52 | 446699.43 | 259399.09 | DSOW – Submitted to FEMA | No amendment needed. In addition to the amendment version, a revised differential estimate of $23,125.95 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
746545 | FAASt [Primary Control Center / Secondary Data Center & Control Room] (Telecommunication) | Building | Building | No | Pending PDMG Scope & Cost Routing | 93654467.72 | 44072690.69 | 12578331.03 | 5919214.6 | 0 | 0 | 156224704.04 | 106232798.75 | 49991905.29 | Project in V0 - No amendment required at this time | The PCC Project is in a Tiered Environmental Assessment process that is being led by FEMA and after the TEA process is completed the DSOW review will continue through to funding obligation. The DSOW is still in Version 0 and will not require an amendment until the TEA process is complete.
746660 | FAASt [Minor Protection, Automation, and Control [PAC] Replacement] (Substation) | Substation | Substation | No | Pending Scope & Cost Completion by Applicant | 12586601.6917 | 4270769.9909 | 1139689.148 | 388376.7455 | 0 | 0 | 18385437.576 | 13726290.8396 | 4659146.7364 | New V0 to be submitted to COR3/PREPA | LUMA is finalizing the scope and estimate. The amendment is expected to be submitted to COR3/PREPA by Q3 FY2027.
749060 | FAASt [Transmission Priority Pole Replacement Program Line 5600 Victoria TC – Añasco TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1077371.11 | 145054.24 | 154904.41 | 21644.91 | 134447.11 | 24366.65 | 1557788.43 | 1366722.63 | 191065.8 | Amendment - Pending Development | Information represents the latest LPCE information provided.
749072 | FAASt [Transmission Priority Pole Replacement Program Line 2700 Aguadilla Hospital Distrito Sect – Mora TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 1002273.48 | 44679.36 | 181551.75 | 2952.97 | 85082.65 | 14236.35 | 1330776.56 | 1268907.88 | 61868.68 | Obligated - Amendment needed | Information represents the latest LPCE information provided.
750063 | FAASt [Region 6 -Ponce Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | No | Pending Applicant Project Review | 16058969.33 | 43985784.19 | 481769.0799 | 1319573.5257 | 0 | 0 | 61846096.1256 | 16540738.4099 | 45305357.7157 | N/A | Cost were changed to aligned to the pending FEMA Obligation values.
750065 | FAASt [Region 3 -Bayamon Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 18569923.87 | 50798780.76 | 294281.61 | 805019.28 | 0 | 0 | 70468005.52 | 18864205.48 | 51603800.04 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
750066 | FAASt [Region 4 -Caguas Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 28466485.03 | 77871225.66 | 448177.27 | 1226007.11 | 0 | 0 | 108011895.07 | 28914662.3 | 79097232.77 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
750067 | FAASt [Region 2 -Arecibo Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 15030146.18 | 41115575.14 | 238185.98 | 651567.42 | 0 | 0 | 57035474.72 | 15268332.16 | 41767142.56 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
750068 | FAASt [Region 5 -Mayaguez Group A] Low Density (Vegetation) | Vegetation | Vegetation-DT | Yes | Obligated | 13840548.75 | 37861383.08 | 219334.17 | 599997.54 | 0 | 0 | 52521263.54 | 14059882.92 | 38461380.62 | Project obligated. No Amendment needed. | Cost aligned to the FEMA Obligation values.
750150 | FAASt [Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Toro Negro 1 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 138347.1 | 5675.78 | 19852.4 | 1075.69 | 5971.66 | 1473.34 | 172395.97 | 164171.16 | 8224.81 | Amendment - Pending Development | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
750151 | FAASt [Transmission Priority Pole Replacement Program Line 700 Costa Sur SP – Yauco 2 HP] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 243268.16 | 9181.75 | 23495.1804 | 1041.06 | 16785.94 | 2341.06 | 296113.1504 | 283549.2804 | 12563.87 | Amendment - Pending Development | Information represents the latest LPCE information provided.
750168 | FAASt [ Transmission Priority Pole Replacement Program Line 4800 Santa Isabel TC – Aibonito TO] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 431757.15 | 28284.79 | 45787.13 | 3335.39 | 36682.34 | 5852.66 | 551699.46 | 514226.62 | 37472.84 | Amendment - Pending Development | Information represents the latest LPCE information provided.
750692 | FAASt [Pole and Conductor Repair - Mayaguez Group 3 - Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 15534571.38 | 65783.22 | 1378411.7 | 41393.16 | 1059507.72 | 432530.28 | 18512197.46 | 17972490.8 | 539706.66 | Amendment - Pending Development | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate.
751655 | FAASt [Vieques Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 671661.536 | 109183728.0243 | 10795126.3543 | 22484740.5443 | 0 | 25228860.2043 | 168364116.6632 | 11466787.8903 | 156897328.7729 | Not obligated - Increase in estimate that will be submitted to FEMA. | The expected total reflects the latest information from the discontinued RFP.
751656 | FAASt [Culebra Microgrid] (Transmission) | Transmission | Vieques and Culebra Projects (6) | No | Pending Scope & Cost Completion by Applicant | 406083.4394 | 62593651.6797 | 51303.2161 | 9109976.8943 | 0 | 9746878.2781 | 81907893.5075 | 457386.6555 | 81450506.852 | Not obligated - Increase in estimate that will be submitted to FEMA. | The expected total reflects the latest information from the discontinued RFP.
752540 | FAASt [Pole and Conductor Repair -Mayaguez Group 4 Phase 2] (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 8685452.68 | 37311.66 | 773151.6 | 23427.4 | 624817.52 | 244800.38 | 10388961.24 | 10083421.8 | 305539.44 | Amendment - Pending Development | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate.
752808 | FAASt [Automation Program Group 19] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1352947.241 | 389336.94 | 119711.919 | 52375.13 | 134857.23 | 320428.9 | 2369657.36 | 1607516.39 | 762140.97 | Amendment – Submitted to FEMA | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $38,543.25 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
752810 | FAASt [Automation Program Group 20] (TL/Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1645985.22 | 492364.67 | 176266.8 | 72284.36 | 202809.71 | 358776.21 | 2948486.97 | 2025061.73 | 923425.24 | Amendment – Submitted to FEMA | 406HM Revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
753782 | FAASt [Transmission Priority Pole Replacement Program Line 3100 Monacillos TC – Sabana Llana TC] (Transmission) | Transmission | Transmission Priority Pole Replacements | Yes | Obligated | 221703.17 | 2218.84 | 20500.96 | 291.07 | 5970.66 | 1473.34 | 252158.04 | 248174.79 | 3983.25 | Obligated - Amendment Pending Final Actual Costs | This information reflects the latest LPCE data provided and includes the actuals delta. The final cost will be taken into consideration during the project reconciliation and close-out.
755211 | FAASt [Automation Program Group 15] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 276277.7686 | 143276.18 | 29684.97 | 18557.49 | 53139.71 | 103164.29 | 624100.4086 | 359102.4486 | 264997.96 | Amendment – Submitted to FEMA | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $15,417.30 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
756997 | FAASt [TL 1900 Caguanas to Lares TO] (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 34621568.58 | 7218553.15 | 2584537.17 | 770659.35 | 1066728.72 | 3635223.17 | 49897270.14 | 38272834.47 | 11624435.67 | Project in V0 - No amendment required at this time | The DSOW revision has been submitted to FEMA.
756999 | FAASt [TL 1900 Lares TO to San Sebastian] (Transmission) | Transmission | Transmission Line Rebuild | No | Pending Scope & Cost Completion by Applicant | 29020727.34 | 6217908.83 | 2251104.25 | 556753.47 | 2446381.79 | 1784156.92 | 42277032.6 | 33718213.38 | 8558819.22 | Project in V0 - No amendment required at this time | The DSOW revision has been submitted to FEMA.
757662 | FAASt [Automation Program Group 21] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1450834.51 | 409419.06 | 316327.09 | 133329.79 | 152199 | 326377 | 2788486.45 | 1919360.6 | 869125.85 | Amendment – Amendment Needed/Pending Development | 406HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
757687 | FAASt [Automation Program Group 22] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1746764.31 | 530280.7 | 364393.9 | 164099.27 | 176671.17 | 397630.03 | 3379839.38 | 2287829.38 | 1092010 | Amendment – Amendment Needed/Pending Development | 406HM revision to be submitted the end of Q4 FY2026 to Grants Portal. Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is a Class 3.
757689 | FAASt [Automation Program Group 24] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1594252.07 | 500159.95 | 141012.25 | 68290.29 | 169799.83 | 399788.17 | 2873302.56 | 1905064.15 | 968238.41 | Amendment – Submitted to FEMA | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
757692 | FAASt [Automation Program Group 26] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 807422.25 | 340229.83 | 69331.28 | 43770.32 | 82692.01 | 259575.99 | 1603021.68 | 959445.54 | 643576.14 | Amendment – Submitted to FEMA | 406HM revision pending award in Grants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $38,543.25 for the communications wireless portion was added to the 406 section (without A&E and E&M).Estimate is an Class 3.
757694 | FAASt [Automation Program Group 27] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1854481.54 | 591389.65 | 381502.7 | 196477.51 | 230481.01 | 495146.19 | 3749478.6 | 2466465.25 | 1283013.35 | Amendment – Amendment Needed/Pending Development | 406HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Waiting for COR3 feedback/ Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
757696 | FAASt [Automation Program Group 31] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 940960.74 | 346598.27 | 87081.37 | 44095.89 | 122168.23 | 240541.77 | 1781446.27 | 1150210.34 | 631235.93 | Amendment – Submitted to FEMA | 406HM revision pending award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
757697 | FAASt [Automation Program Group 32] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2053127.85 | 562049.57 | 317057.24 | 138127.24 | 219381.16 | 471983.84 | 3761726.9 | 2589566.25 | 1172160.65 | Amendment – Amendment Needed/Pending Development | 406HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Waiting for COR3 feedback/ Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $53,960.55 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
757698 | FAASt [Automation Program Group 33] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1435455.15 | 570512.93 | 298284.82 | 143185.1 | 185468.25 | 392343.7 | 3025249.95 | 1919208.22 | 1106041.73 | Amendment – Submitted to FEMA | 406 HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $69,377.85 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
757699 | FAASt [Automation Program Group 34] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 2072695.44 | 606035.3 | 433846.26 | 195477.43 | 209012.07 | 473571.13 | 3990637.63 | 2715553.77 | 1275083.86 | Amendment – Amendment Needed/Pending Development | 406HM revision to be submitted by the end of Q4 FY2026 to Grants Portal. Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
757700 | FAASt [Automation Program Group 35] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1130075.79 | 551850.51 | 147185.05 | 85545.81 | 118838.8 | 298749.6 | 2332245.56 | 1396099.64 | 936145.92 | Amendment – Submitted to FEMA | 406HM revision currently pending award in Grrants Portal / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $61,669.20 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
790443 | FAASt [Pole and Conductor Repair -San Juan Group 3 Phase 2 (Distribution) | Distribution | Distribution Pole and Conductor Repair | Yes | Obligated | 243833.22 | 919.39 | 21435.45 | 574.91 | 14432.64 | 6007.36 | 287202.97 | 279701.31 | 7501.66 | Amendment - Pending Development | Project obligated under based on a Class 3 estimate full 428. The 428/406HM Amendment was submitted with the revised Class 3 estimate.
797148 | FAASt [Feeder Rebuild # 8101-03] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 3243578.94 | 76998.98 | 678369.17 | 29445.05 | 424402 | 41009.75 | 4493803.89 | 4346350.11 | 147453.78 | Ammendment submitted to FEMA needs to be adjusted with new estimate cost | The project obligation was based on a Class 3 estimate. Project will be versioned prior to close out (Final Amendment). Current A/E & Planning costs are higher than the initial estimate ($951.9K). This variance will be mitigated as part of the Final amendment during project versioning prior to closeout.
798275 | FAASt [Feeder Rebuild # 1620-02] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 6267255.15 | 215006.18 | 1289176.91 | 37409.72 | 531498.7 | 78348.17 | 8418694.83 | 8087930.76 | 330764.07 | Ammendment submitted to FEMA needs to be adjusted with new estimate cost | Project was obligated full 428 based on a Class 3 estimate. A versioning was submitted including split 428/406 and is currently under FEMA evaluation.
800286 | FAASt [Automation Program Group 36] (TL / Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1427638.4262 | 582790.347 | 137043.707 | 78366.543 | 175789.83 | 397237.57 | 2798866.4232 | 1740471.9632 | 1058394.46 | Amendment – Submitted to FEMA | 406HM Revision currently Pending to be Award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $63,377.85 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
800361 | FAASt [Automation Program Group 37] (Distribution) | Grid Automation | Grid Automation | Yes | Obligated | 1514451.93 | 369437.55 | 174540.79 | 68764.66 | 164586.33 | 302167.8 | 2593949.06 | 1853579.05 | 740370.01 | Amendment – Submitted to FEMA | 406HM revision pending award in GP / Estimated date Cfci strategy to be defined. In addition to the amendment version, a revised differential estimate of $46,251.90 for the communications wireless portion was added to the 406 section (without A&E and E&M). Estimate is an Class 3.
801166 | FAASt [Feeder Rebuild # 6601-03] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 19979701.47 | 0 | 1724565.72 | 0 | 2135838.13 | 0 | 23840105.32 | 23840105.32 | 0 | Not Submitted | The project was fully obligated under Section 428 using the Class 3 estimate. Versioning was submitted, including the split between 428 and 406, and it is currently under FEMA evaluation. The final DSOW versioning will be submitted, reflecting an additional $152,918 to the approved budget.
801172 | FAASt [Feeder Rebuild # 1529-15] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 2621409.16 | 242729.86 | 538090.23 | 52278.72 | 135020.88 | 39130.64 | 3628659.49 | 3294520.27 | 334139.22 | Ammendment submitted to FEMA needs to be adjusted with new estimate cost | The project was fully obligated under Section 428 using the Class 3 estimate. Versioning was submitted, including the split between 428 and 406, and it is currently under FEMA evaluation. The final DSOW versioning will be submitted, reflecting an additional $835,029 to the approved budget.
812569 | FAASt [Feeder Rebuild 3502-02] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 10019547.43 | 1071193.26 | 1552343.58 | 168085.95 | 399838.42 | 57779.14 | 13268787.78 | 11971729.43 | 1297058.35 | Amendment – Submitted to COR3/PREPA | Project was obligated full 428 based on a Class 3 estimate. A versioning was submitted including split 428/406 and is currently under FEMA evaluation.
817956 | FAASt [Feeder Rebuild # 1303-02] (Distribution) | Distribution | Distribution Feeders | Yes | Obligated | 2783776.04 | 37150.77 | 631442.21 | 8316.85 | 78644.98 | 21278.54 | 3560609.39 | 3493863.23 | 66746.16 | Ammendment submitted to FEMA needs to be adjusted with new estimate cost | Project was obligated full 428 with Class 3 estimate, versioning was submitted including split 428/406, Under FEMA evaluation. Current A/E & Planning costs are higher than the initial estimate ($681.6K). This variance will be mitigated as part of the Final amendment during project versioning prior to closeout.
825843 | FAASt [Guanica TC] (Substation) | Priority Substation | Substation | Yes | Obligated | 2552411.356 | 0 | 909679.243 | 0 | 4620795.872 | 0 | 8082886.471 | 8082886.471 | 0 | Amendment – Amendment Needed/Pending Development | LUMA is finalizing the scope. The amendment is expected to be submitted by Q2 FY2027. Cost change is driven by more defined scope and inflation.
956330 | FAASt [Caguas Region 4 - Feeder 3007-03] (Vegetation) | Vegetation | Vegetation-DT | No | Pending QA Review | 1968823.15 | 5853486.17 | 163550.83 | 448769.62 | 0 | 0 | 8434629.77 | 2132373.98 | 6302255.79 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
956331 | FAASt [Mayaguez Region 5 Feeder 6014-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1977622.66 | 5879647.9 | 164281.79 | 450775.37 | 0 | 0 | 8472327.72 | 2141904.45 | 6330423.27 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
956332 | FAASt [San Juan Region 1 - Feeder 2401-01] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 2787055.9 | 8286164.87 | 231521.7 | 635275.99 | 0 | 0 | 11940018.46 | 3018577.6 | 8921440.86 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
956335 | FAASt [San Juan Region 1 - Feeder 2301-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1849955.27 | 5500081.4 | 153676.43 | 421675.11 | 0 | 0 | 7925388.21 | 2003631.7 | 5921756.51 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
956337 | FAASt [Mayaguez Region 5 Feeder 6012-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1800712.05 | 5353676.79 | 149585.76 | 410450.73 | 0 | 0 | 7714425.33 | 1950297.81 | 5764127.52 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
956339 | FAASt [Caguas Region 4 - Feeder 3301-01] (Vegetation) | Vegetation | Vegetation-DT | No | Pending Insurance Completion | 2959532.24 | 8798952.37 | 245849.34 | 674589.93 | 0 | 0 | 12678923.88 | 3205381.58 | 9473542.3 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
956340 | FAASt [Ponce Region 6 Feeder 5602-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 1624663.76 | 4830269.73 | 134961.38 | 370322.63 | 0 | 0 | 6960217.5 | 1759625.14 | 5200592.36 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
956341 | FAASt [Ponce Region 6 Feeder 5803-02] (Vegetation) | Vegetation | Vegetation-DT | No | Pending EHP Review | 41293.37 | 52055.36 | 3165.6 | 4323.45 | 0 | 0 | 100837.78 | 44458.97 | 56378.81 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to LUMA LPCE values. Amendment will be needed after project obligation.
956342 | FAASt [Arecibo Region 2 Line 36400 – Ponce TC to Dos Bocas HP] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 2786535.15 | 9869424.87 | 83596.05 | 296082.75 | 0 | 0 | 13035638.82 | 2870131.2 | 10165507.62 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
956343 | FAASt [Ponce Region 6 Line 4800 – Toro Negro to Aibonito, Santa Isabel] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 3162797.958 | 8682357.558 | 262734.708 | 720921.912 | 0 | 0 | 12828812.136 | 3425532.666 | 9403279.47 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
956345 | FAASt [Arecibo Region 2 Line 2400 – Dos Bocas HP to Coronillas 2] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 1083485.898 | 2974332.24 | 90005.55 | 246967.614 | 0 | 0 | 4394791.302 | 1173491.448 | 3221299.854 | Obligated -Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
956348 | FAASt [Bayamon Region 3 Line 10000 – Bayamon Pueblo to Magnolia TO] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 176585.496 | 484753.794 | 14669.028 | 40250.52 | 0 | 0 | 716258.838 | 191254.524 | 525004.314 | Obligated -Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. Amendment will be needed after work completion and /or assessment completion.
956349 | FAASt [San Juan Region 1 Transmission Line 36800 – Canovanas TC to Palmer TC] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 812052.35 | 2894107.23 | 24361.5705 | 86823.2169 | 0 | 0 | 3817344.3674 | 836413.9205 | 2980930.4469 | Amendment – Submitted to FEMA | Cost aligned to 80% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 80% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
956353 | FAASt [Arecibo Region 2 Line 36100 – Dos Bocas HP to Barrio Pina] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 3154458.67 | 11080517.97 | 94633.76 | 332415.54 | 0 | 0 | 14662025.94 | 3249092.43 | 11412933.51 | Obligated - Amendment Pending Final Assessment or Actual Costs | Cost aligned to 80% of the LPCE values for this project. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; project obligations are much lower than submitted mileage, far below forecast needs. LUMA estimates 80% of miles require clearing and seeks gap funding for the mileage not covered/approved by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
956356 | FAASt [Ponce Region 6 Transmission Line 39000 – Aguas Buenas Substation to Hacienda San Jose] (Vegetation) | Vegetation | Vegetation-TL | Yes | Obligated | 302418.26 | 690456.65 | 9072.54 | 20713.7 | 0 | 0 | 1022661.15 | 311490.8 | 711170.35 | Obligated - Amendment Pending Final Actual Costs | Cost was changed to 60% of total LPCE values. Amendment will be needed after work completion.
956357 | FAASt [Mayaguez Region 5 Line 1900 – Dos Bocas HP to San Sebastian TC] (Vegetation) | Vegetation | Vegetation-TL | No | Pending Scope & Cost Completion by Applicant | 1879460.01 | 5159401.236 | 156127.392 | 428400.39 | 0 | 0 | 7623389.028 | 2035587.402 | 5587801.626 | Project in V0 -Amendment Pending Final Assessment or Actual Costs | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800. . Amendment will be needed after work completion and /or assessment completion.
956593 | FAASt [Factor Sect 8014 Transformer Replacement] (Substation) | Substation | Substation | Yes | Obligated | 4404224.9449 | 1427070.1716 | 402805.69 | 137265.82 | 0 | 0 | 6371366.6265 | 4807030.6349 | 1564335.9916 | Obligated -No expected changes | No expected changes to this project.
957578 | FAASt [Costa Sur TC Underground Cable Failure Replacement on Transformer Lead Bank #2] (Substation) | Substation | Substation | Yes | Obligated | 1273789.3886 | 432210.5068 | 115338.8324 | 39304.5072 | 0 | 0 | 1860643.235 | 1389128.221 | 471515.014 | Amendment – Amendment Needed/Pending Development | LUMA is working on the project scope with Genera. The amendment is expected to be submitted Q1 FY2027. Cost change is driven by more defined scope and inflation.
[6 empty] | 3134057188.3733 | 1914894041.5754 | 351042612.5512 | 155463965.1751 | 443540365.7918 | 286761423.4572 | 6285759596.924 | 3928640166.7163 | 2357119430.2077
LUMA Consolidated Project List

## Attachment A
Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | 428 Estimate (Without the A&E and E&M) | 406 Estimate (Without the A&E and E&M) | 428 A&E Estimate-PW 9510 | 406 A&E Estimate -PW 9510 | 428 E&M Estimate -PW 10710 | 406 E&M Estimate -PW 10710 | Expected Total Project Cost | Total 428 Estimate Cost | Total 406 Estimate Cost | Comment
754350 | Distribution Underground Circuit Feeders - San Juan Group 1 | Distribution | Underground | No | 4310111.715 | 9577521.9267 | 362956.776 | 812115.7863 | 1512.3199 | 58980.4761 | 15123199 | 4674580.8109 | 10448618.1891 | Pending Operation Assessment, and design work has not yet been finalized. Further evaluation is required before moving forward.
750503 | FAASt [25 MW BESS Installation and Integration - San Juan] (Substation) | Substation | Grid Modernization | No | 0 | 24053536.03 | 0 | 3187811.29 | 0 | 28261718.24 | 55503065.56 | 0 | 55503065.56
750502 | FAASt [25 MW BESS Installation and Integration - Aguadilla] (Substation) | Substation | Grid Modernization | No | 0 | 21118171.64 | 0 | 3340630.47 | 0 | 28261718.24 | 52720520.35 | 0 | 52720520.35
752972 | FAASt [4 x 25 MW BESS Interconnections Manati] (Substation) | Substation | Grid Modernization | No | 0 | 23808829.62 | 0 | 3414922.97 | 0 | 30416253.08 | 57640005.67 | 0 | 57640005.67
738671 | FAASt [25 MW BESS Installation and Integration - Barceloneta] (Substation) | Substation | Grid Modernization | No | 0 | 20318919.35 | 0 | 5211394.35 | 0 | 30411453.8 | 55941767.5 | 0 | 55941767.5
800394 | Automation Program Group 39 (Distribution) | Distribution | Automation | No | 1256040 | 395420 | 116300 | 69780 | 162820 | 325640 | 2326000 | 1535160 | 790840 | This is Class 5 estimated total per project, considering the current identified scope for devices, $165,500 per 3ph reclosers, $25,500 per 1ph reclosers and $4000 per cFCIs. (11) 3PH Reclosers, (17) 1ph reclosers, (18) cFCi. It requires an engineering evaluation due to the amount of time that has passed since the designs were originally completed, in order to verify their validity and ensure they meet current standards and conditions.
790427 (1066737) | Distribution Pole and Conductor Repair - Caguas Group 5 - Phase 2 | Distribution | Distribution Pole and Conductor Repair | No | 7591896.49 | 32126 | 673492.23 | 20229.46 | 515199.89 | 211384.11 | 9044328.18 | 8780588.61 | 263739.57 | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission.
806935 (1066738) | Distribution Pole and Conductor Repair - Caguas Group 6 - Phase 2 | Distribution | Distribution Pole and Conductor Repair | No | 7262006.01 | 330225.13 | 645539.7 | 44770.71 | 509451.1 | 208755.9 | 9000748.55 | 8416996.81 | 583751.74 | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission.
757945 (1066739) | Distribution Pole and Conductor Repair - Arecibo Group 3 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | No | 2039409.93 | 366564.02 | 181779.7 | 35823.76 | 173097.79 | 69460.21 | 2866135.41 | 2394287.42 | 471847.99 | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission.
790446 (1066740) | Distribution Pole and Conductor Repair – Caguas Group 4 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | No | 3867419.78 | 16119.41 | 342713.17 | 10132.71 | 258899.2 | 105879.8 | 4601164.07 | 4469032.15 | 132131.92 | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission.
817249 (1066741) | Distribution Pole and Conductor Repair – Caguas Group 7 – Phase 2 | Distribution | Distribution Pole and Conductor Repair | No | 4608333 | 284709.51 | 409935.75 | 36039.36 | 381146.2 | 153938.8 | 5874102.62 | 5399414.95 | 474687.67 | Class 3 estimate has been submitted to COR3 for validation. WOP design is 100% completed, and the DSOW package has been completed. We are currently pending COR3’s review prior to FEMA submission.
666894 | FAASt [San Juan Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 28178017.76 | 2123472.21 | 6380570.04 | 123157.52 |  |  | 36805217.53 | 34558587.8 | 2246629.73 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
671396 | FAASt [Utuado Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 16760927.205 | 2851675.47 | 3319870.72 | 155072.6 |  |  | 23087545.995 | 20080797.925 | 3006748.07 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
671400 | FAASt [Barceloneta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 7422038.0375 | 477869.14 | 1206563.5 | 50306 |  |  | 9156776.6775 | 8628601.5375 | 528175.14 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
678794 | FAASt [Ponce Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 10968715.275 | 884181.41 | 1713141.92 | 51717 |  |  | 13617755.605 | 12681857.195 | 935898.41 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
678795 | FAASt [Arecibo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 11879105.0925 | 800134.36 | 1902215.74 | 59360 |  |  | 14640815.1925 | 13781320.8325 | 859494.36 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
686482 | FAASt [Isabela Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 6005455.39 | 671912.08 | 1332970.6 | 37797.8 |  |  | 8048135.87 | 7338425.99 | 709709.88 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
690480 | FAASt [Humacao Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 6455271.8825 | 488325.81 | 1006696.36 | 29209 |  |  | 7979503.0525 | 7461968.2425 | 517534.81 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
690483 | FAASt [Cayey Streetlighting] | Distribution | Distribution Streetlighting | No | 10596790.82 | 1275717.24 | 2435204.39 | 95954.76 |  |  | 14403667.21 | 13031995.21 | 1371672 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
690721 | FAASt [Guayama Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 4107291.015 | 305442.59 | 1011463.98 | 25642.92 |  |  | 5449840.505 | 5118754.995 | 331085.51 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
693543 | FAASt [Juncos Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 10994681.6975 | 685135.01 | 1631297.312 | 26436.06 |  |  | 13337550.0795 | 12625979.0095 | 711571.07 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
693615 | [Rio Grande Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 5347407.42 | 397032.05 | 1156399.63 | 21533.62 |  |  | 6922372.72 | 6503807.05 | 418565.67 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
693788 | FAASt [Toa Alta Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 4767387.52 | 197071.81 | 1162797.94 | 17891.57 |  |  | 6145148.84 | 5930185.46 | 214963.38 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
697183 | FAASt [Vega Baja Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 8602549.46 | 1056851.66 | 1621313.74 | 17891.57 |  |  | 11298606.43 | 10223863.2 | 1074743.23 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
698522 | [Vieques Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 3987957.0575 | 454616.91 | 810226.05 | 32120.4 |  |  | 5284920.4175 | 4798183.1075 | 486737.31 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
699814 | FAASt [Juana Diaz Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 14011750.655 | 872747.53 | 2795912.01 | 55146.97 |  |  | 17735557.165 | 16807662.665 | 927894.5 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
701473 | FAASt [Canovanas Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 11994894.83 | 1520521.43 | 2377385.56 | 89359.81 |  |  | 15982161.63 | 14372280.39 | 1609881.24 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
704744 | [San Sebastian Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 21521273.585 | 1542129.95 | 4057973.95 | 94811.81 |  |  | 27216189.295 | 25579247.535 | 1636941.76 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
704793 | [Yauco Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 13232024.93 | 1588137.76 | 2540431.6 | 79529.34 |  |  | 17440123.63 | 15772456.53 | 1667667.1 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
704929 | [San Lorenzo Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 13787578.6125 | 968406.72 | 2944605.83 | 60896.29 |  |  | 17761487.4525 | 16732184.4425 | 1029303.01 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
704931 | FAASt [Camuy Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 14028036.5825 | 867189.9 | 1972441.141 | 107984.699 |  |  | 16975652.3225 | 16000477.7235 | 975174.599 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
724603 | FAASt [Cabo Rojo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | 7308020.08 | 517830.31 | 1689593.17 | 41489.51 |  |  | 9556933.07 | 8997613.25 | 559319.82 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
724828 | [Loiza Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 6213147.88 | 388351.58 | 1248099.37 | 14137.5 |  |  | 7863736.33 | 7461247.25 | 402489.08 | Considering work completed portion and to be completed, formulation will be separately. Class 3 Estimate its based on latest assumtions. Adding work completed portion would take longer for formulation purposes. Lodging and Perdiem arent considered.
724941 | [Aguas Buenas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 12423846.45 | 585725.31 | 1646095.25 | 83021.58 |  |  | 14738688.59 | 14069941.7 | 668746.89 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
704741 | [Moca Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 19741562.46 | 976458.2 | 2533607.94 | 134366.43 |  |  | 23385995.03 | 22275170.4 | 1110824.63 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724605 | [Guayanilla Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 8485594.47 | 412336.03 | 1106363.96 | 57568.51 |  |  | 10061862.97 | 9591958.43 | 469904.54 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724599 | [Sabana Grande Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 11849851.49 | 636889.83 | 1536485.07 | 88808.54 |  |  | 14112034.93 | 13386336.56 | 725698.37 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724669 | [Ciales Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 13170687.29 | 682982.51 | 1629722.94 | 90151.24 |  |  | 15573543.98 | 14800410.23 | 773133.75 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724716 | [Quebradillas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 11505789.6 | 550706.35 | 1511148.92 | 77403.68 |  |  | 13645048.55 | 13016938.52 | 628110.03 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
713795 | [Lares Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 13027118.33 | 631320.8 | 1563494.51 | 80701.22 |  |  | 15302634.86 | 14590612.84 | 712022.02 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724670 | [Patillas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 9123256.82 | 358025.92 | 1167539.54 | 48560.66 |  |  | 10697382.94 | 10290796.36 | 406586.58 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
724781 | [Penuelas Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | 8600953.35 | 357444.72 | 1159987.24 | 51045.69 |  |  | 10169431 | 9760940.59 | 408490.41 | DSOW package complete.Ready to be sumitted, scope consider all construction phases.
753785 | TPole 3300 San Gerardo Sect to Venezuela Sect | Transmission | Transmission Priority Pole Replacements | No | 299085.29 | 81090.53 | 55226.85 | 14556.86 | 12296.95 | 1013.73 | 463270.21 | 366609.09 | 96661.12 | Project Not Obligated
753786 (1066980) | TPole 5900 San Juan SP to Crematorio TO | Transmission | Transmission Priority Pole Replacements | No | 407830.94 | 1921.02 | 77598.93 | 1382.15 | 40781.7 | 6101.3 | 535616.04 | 526211.57 | 9404.47 | Project Not Obligated
753787 | TPole 13700 Mora TC to Isabela TO | Transmission | Transmission Priority Pole Replacements | No | 591148.31 | 7196.15 | 103198.13 | 1529 | 35991.1 | 2143.44 | 741206.13 | 730337.54 | 10868.59 | Project Not Obligated
811923 (1066730) | Transmission Priority Pole Replacement Program Line 16500 Fajardo TC-Dos Marinas | Transmission | Transmission Priority Pole Replacements | No | 212650.88 | 381.28 | 48267.18 | 305.98 | 37102.11 | 1220.26 | 299927.69 | 298020.17 | 1907.52 | Project Not Obligated
1064452 | Transmission Priority Pole Replacement Program Line 800 Comsat Sect –Cidra Sect (Active) | Transmission | Transmission Priority Pole Replacements | No | 609182.23 | 2812.61 | 110189.24 | 1928.4 | 52018.89 | 8792.11 | 784923.48 | 771390.36 | 13533.12 | Project Not Obligated
727691 | FAASt [Region 1 San Juan Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No | 788376.99 | 8663674.704 | 6629.484 | 72765.402 | 0 | 0 | 9531446.58 | 795006.474 | 8736440.106 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
740406 | FAASt[Region 1 San Juan Transmission 38kV - Non-Sensitive (Vegetation)] - Group B | Vegetation | Vegetation-TL | No | 281264.03 | 3116841.11 | 2365.12 | 25959.59 | 0 | 0 | 3426429.85 | 283629.15 | 3142800.7
740410 | FAASt[Region 2 Arecibo Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | No | 21352.15 | 236614.32 | 179.55 | 1970.74 | 0 | 0 | 260116.76 | 21531.7 | 238585.06
740409 | FAASt[Region 4 Caguas Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | No | 715385.11 | 7927576.7 | 6901584.83 | 66028.4 | 0 | 0 | 15610575.04 | 7616969.94 | 7993605.1
740414 | FAASt [Region 6 Ponce Transmission 38kV - Non-Sensitive (Vegetation)- Group B | Vegetation | Vegetation-TL | No | 141749.28 | 1570801.41 | 1191.98 | 13083.11 | 0 | 0 | 1726825.78 | 142941.26 | 1583884.52
727694 | FAASt [Region 4 Caguas Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No | 437628.366 | 4809208.998 | 3680.034 | 40392.096 | 0 | 0 | 5290909.494 | 441308.4 | 4849601.094 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
740411 | FAASt [Region 5 Mayaguez Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | No | 799358.09 | 8858127.48 | 6721.82 | 73778.93 | 0 | 0 | 9737986.32 | 806079.91 | 8931906.41 | No comments. Projects already submitted to PREPA.
727562 | FAASt [Region 5 Mayaguez Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No | 1232141.82 | 13540319.136 | 10361.1 | 113723.898 | 0 | 0 | 14896545.954 | 1242502.92 | 13654043.034 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
727530 | FAASt [Region 6 Ponce Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No | 1367036.856 | 15022714.938 | 11495.436 | 126174.408 | 0 | 0 | 16527421.638 | 1378532.292 | 15148889.346 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
727540 | FAASt [Region 2 Arecibo Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No | 1105536.432 | 12149020.278 | 9296.478 | 102038.502 | 0 | 0 | 13365891.69 | 1114832.91 | 12251058.78 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
740408 | FAASt[Region 3 Bayamon Transmission 38kV - Non-Sensitive (Vegetation)]- Group B | Vegetation | Vegetation-TL | No | 622799.54 | 6901584.83 | 5237.14 | 57482.97 | 0 | 0 | 7587104.48 | 628036.68 | 6959067.8
727558 | FAASt [Region 3 Bayamon Transmission 38kV sensitive areas] (Vegetation) - Group C | Vegetation | Vegetation-TL | No | 793759.878 | 8722828.56 | 6674.742 | 73262.238 | 0 | 0 | 9596525.418 | 800434.62 | 8796090.798 | Cost aligned to 60% of the LPCE values for all transmission projects. Costs are based on expected work miles and cost per clearing mile, which vary by voltage, terrain/access, vegetation density, and other factors. Transmission will not require clearing on all submitted miles; the obligation averages 14%, far below forecast needs. LUMA estimates 60% of miles require clearing and seeks gap funding for the 46% not covered by obligations. After assessment, transmission projects will be versioned to reflect actual work miles, as done for 39000 and 36800.
547344 (1066724)) | Acacias 6801 TC (Relocation) | Substation | Substation Rebuilds | No | 65766025.0617 | 31538831.8413 | 2841208.2382 | 785561.5157 | 12378234.9672 | 3124060.0459 | 116433921.67 | 80985468.2671 | 35448453.4029
547247 | Cambalache TC Rebuild | Substation | Substation Rebuilds | No | 4966986.47 | 62195402.17 | 344907.31 | 9217663.45 | 151612.12 | 13320220.44 | 90196791.96 | 5463505.9 | 84733286.06
550099 (1066979) | Esc Industrial Miguel Such (Metal-Clad) 1423 | Substation | Substation Rebuilds | No | 3301739.68 | 1135704.94 | 1112050.13 | 0 | 6614733.66 | 4603565.8 | 16767794.21 | 11028523.47 | 5739270.74
551260 (1066729) | Guaynabo Pueblo | Substation | Substation Rebuilds | No | 9487047.4 | 4257510.71 | 2263654.35 | 576564.36 | 4962433.97 | 3961056.7649 | 25508267.5549 | 16713135.72 | 8795131.8349
551927 (1066731) | SCADA Remote Access and RTU Replacements Group 3 | Telecommunication | IT/OT | No | 18668671.07 | 3375608.8 | 2470554.28 | 425678.76 | 1293008.64 |  | 26233521.55 | 22432233.99 | 3801287.56
679035 | Telecomm Infrastructure Group A | Telecommunication | IT/OT | No | 6440145.54 | 15927.16 | 1756408.47 | 4175.18 | 2800 |  | 8219456.35 | 8199354.01 | 20102.34
748180 | Transmission Advanced Sensors and Wide-Area Monitoring, Protection, and Control (WAMPAC) System | Telecommunication | IT/OT | No | 0 | 47130973.41 | 0 | 5250645.64 | 0 | 423360 | 52804979.05 | 0 | 52804979.05
Pending FAASt Number | Fleet adquisition | E&M | E&M |  | 0 |  |  |  | 40000000 |  | 40000000 | 40000000 |  | New Project
Pending FAASt Number | Line 8700 – Costa Sur Power Plant to Garzas 2 HP / Garzas 1 HP | Transmission | Line Rebuild | No | 31681262.15 |  | 4873900 |  |  |  | 36555162.15 | 31681262.15 | 0 | As part of recent coordination efforts PREPA requested T-line 1100 be taken into consideration by LUMA for reactivation. After internal discussion and evaluation LUMA presented the repair of T-Line 8700 instead of T-Line 1100 and PREPA concurred. The solution for T-Line 8700 will be submitted to FEMA HM for consideration as Hazard Mitigation to the system for a Black Start inclusion of the hidroelectric plants
Pending FAASt Number | Aguadilla Sect 7003 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | No | 5579634.34 | 311868.76 | 629419.11 | 31110.94 | 1938416.48 | 60347.84 | 8550797.47 | 8147469.93 | 403327.54 | New Project
Pending FAASt Number | Hogar Crea 1717 Transformer 115/13.2 kV, 44.8 MVA | Substation | Substation Component Replacements | No | 6398013.45 | 188830.71 | 904549.27 | 23961.87 | 2064663.44 | 34482 | 9614500.74 | 9367226.16 | 247274.58 | New Project
Pending FAASt Number | Isla Grande TC Bank 2 Transformer 115/40 kV, 112 MVA | Substation | Substation Component Replacements | No | 5001240.02 | 43376.06 | 862846.03 | 5789.88 | 2955632.71 | 9814.28 | 8878698.98 | 8819718.76 | 58980.22 | New Project
Pending FAASt Number | Quebradillas 7402 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | No | 4522746.03 | 111790.07 | 559970.38 | 11194.81 | 1878676.91 | 16521.12 | 7100899.32 | 6961393.32 | 139506 | New Project
Pending FAASt Number | Rincon 7301 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | No | 5756093.73 | 330484.121 | 658093.86 | 30072.85 | 2034277.28 | 25621.12 | 8834642.96 | 8488464.87 | 386178.09 | New Project
Pending FAASt Number | Santa Isabel Sect 4401 Transformer 38/13.2-4.16, 22 MVA | Substation | Substation Component Replacements | No | 7837106.38 | 431467.46 | 774387.34 | 38617.71 | 2241468.32 | 71267.84 | 11394315.05 | 10852962.04 | 541353.01 | New Project
704805 | Telecomm Infrastructure Group D | Telecommunication | IT/OT | No | 5297451.62 | 18959.16 | 683790.17 | 2498.07 |  |  | 6002699.02 | 5981241.79 | 21457.23
Pending FAASt Number | Mobile Substations | Substation | TBD | No |  |  |  |  | 17709050 |  | 17709050 | 17709050 | 0 | New Project
Pending FAAST Number | TAShelix Mobile Platform Implementation | TBD | TBD | No |  | 1957950 |  |  |  |  | 1957950 |  | 1957950 | New Project
Pending FAAST Number | Fiber Optic Replacement Group 1 | Telecommunication | IT/OT | No | 67811581.03 | 9902187.96 | 6835688.41 | 948496.8 | 108101.8 |  | 85606056 | 74755371.24 | 10850684.76 | New Project
[5 empty] | 635976230.1362 | 380988372.623 | 97835662.6411 | 36321119.6751 | 98513427.5471 | 144154770.7469 | 1393789583.3684 | 827491420.3244 | 561464263.0439
LUMA Attachment A

## Attachment B
Project # | Title | Asset | Sub Asset | Obligated (Yes / No) | Project Status | 428 Estimate (Without the A&E and E&M) | 406 Estimate (Without the A&E and E&M) | 428 A&E Estimate-PW 9510 | 406 A&E Estimate -PW 9510 | 428 E&M Estimate -PW 10710 | 406 E&M Estimate -PW 10710 | Expected Total Project Cost | Total 428 Estimate Cost | Total 406 Estimate Cost
735357 | FAASt [Mayaguez Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 2005600 | 0 | 330319.93 | 0 | 0 | 0 | 2335919.93 | 2335919.93 | 0
746108 | FAASt [San Juan Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 7814250 | 0 | 825170.91 | 0 | 0 | 0 | 8639420.91 | 8639420.91 | 0
735131 | FAASt [Arecibo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 3149850 | 0 | 503094.78 | 0 | 0 | 0 | 3652944.78 | 3652944.78 | 0
746111 | FAASt [Caguas Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 3646650 | 0 | 508288.97 | 0 | 0 | 0 | 4154938.97 | 4154938.97 | 0
735665 | FAASt [Carolina Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 4328600 | 0 | 795422.75 | 0 | 0 | 0 | 5124022.75 | 5124022.75 | 0
734728 | FAASt [Ponce Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 3681150 | 0 | 576959.77 | 0 | 0 | 0 | 4258109.77 | 4258109.77 | 0
735954 | FAASt [Trujillo Alto Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1817000 | 0 | 251430.18 | 0 | 0 | 0 | 2068430.18 | 2068430.18 | 0
734859 | FAASt [Aguadilla Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 2010200 | 0 | 299127.03 | 0 | 0 | 0 | 2309327.03 | 2309327.03 | 0
735470 | FAASt [Bayamón Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 5318750 | 0 | 704446.74 | 0 | 0 | 0 | 6023196.74 | 6023196.74 | 0
734791 | FAASt [Guayama Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1756050 | 0 | 444662.71 | 0 | 0 | 0 | 2200712.71 | 2200712.71 | 0
735493 | FAASt [Humacao Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1826200 | 0 | 324830.45 | 0 | 0 | 0 | 2151030.45 | 2151030.45 | 0
734927 | FAASt [Isabela Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1552500 | 0 | 306973.5 | 0 | 0 | 0 | 1859473.5 | 1859473.5 | 0
737804 | FAASt [Rio Grande Streetlighting - Part 2 ] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1788250 | 0 | 279529.57 | 0 | 0 | 0 | 2067779.57 | 2067779.57 | 0
737707 | FAASt [Toa Alta Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 2219500 | 0 | 364572.61 | 0 | 0 | 0 | 2584072.61 | 2584072.61 | 0
734393 | FAASt [Cabo Rojo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 2168900 | 0 | 368432.14 | 0 | 0 | 0 | 2537332.14 | 2537332.14 | 0
735677 | FAASt [Guaynabo Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1935450 | 0 | 384791.84 | 0 | 0 | 0 | 2320241.84 | 2320241.84 | 0
735960 | FAASt [Toa Baja Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1461650 | 0 | 311784.53 | 0 | 0 | 0 | 1773434.53 | 1773434.53 | 0
735940 | FAASt [Vega Baja Streetlighting - Part 2] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1896350 | 0 | 313451.11 | 0 | 0 | 0 | 2209801.11 | 2209801.11 | 0
735360 | FAASt [Mayaguez Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 2967000 | 0 | 934399.04 | 0 | 0 | 0 | 3901399.04 | 3901399.04 | 0
737712 | FAAST [San Juan Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 7826900 | 0 | 1103286.53 | 0 | 0 | 0 | 8930186.53 | 8930186.53 | 0
734853 | FAASt [Arecibo Streetlighting- Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 2778400 | 0 | 570030.05 | 0 | 0 | 0 | 3348430.05 | 3348430.05 | 0
735672 | FAASt [Caguas Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 3448850 | 0 | 752635.32 | 0 | 0 | 0 | 4201485.32 | 4201485.32 | 0
735496 | FAASt [Carolina Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 3936450 | 0 | 684791.58 | 0 | 0 | 0 | 4621241.58 | 4621241.58 | 0
734760 | FAASt [Ponce Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 3221150 | 0 | 700990.05 | 0 | 0 | 0 | 3922140.05 | 3922140.05 | 0
735952 | FAASt [Trujillo Alto Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1597350 | 0 | 369585.51 | 0 | 0 | 0 | 1966935.51 | 1966935.51 | 0
735338 | FAASt [Aguadilla Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1401850 | 0 | 313621.72 | 0 | 0 | 0 | 1715471.72 | 1715471.72 | 0
735472 | FAASt [Bayamon Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 4418300 | 0 | 739172.36 | 0 | 0 | 0 | 5157472.36 | 5157472.36 | 0
734789 | FAASt [Guayama Streetlighting - Part 3 ] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1679000 | 0 | 285214.71 | 0 | 0 | 0 | 1964214.71 | 1964214.71 | 0
735487 | FAASt [Humacao Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1498450 | 0 | 282005.08 | 0 | 0 | 0 | 1780455.08 | 1780455.08 | 0
734928 | FAASt [Isabela Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1163800 | 0 | 325113.23 | 0 | 0 | 0 | 1488913.23 | 1488913.23 | 0
737798 | FAASt [Rio Grande Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1212100 | 0 | 239093.65 | 0 | 0 | 0 | 1451193.65 | 1451193.65 | 0
737699 | FAASt [Toa Alta Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1058000 | 0 | 221137.35 | 0 | 0 | 0 | 1279137.35 | 1279137.35 | 0
734396 | FAASt [Cabo Rojo Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1246600 | 0 | 279407 | 0 | 0 | 0 | 1526007 | 1526007 | 0
735499 | FAASt [Guaynabo Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1838850 | 0 | 375286.43 | 0 | 0 | 0 | 2214136.43 | 2214136.43 | 0
735959 | FAASt [Toa Baja Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1317900 | 0 | 300491.01 | 0 | 0 | 0 | 1618391.01 | 1618391.01 | 0
735483 | FAASt [Vega Baja Streetlighting - Part 3] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 1308700 | 0 | 265069.11 | 0 | 0 | 0 | 1573769.11 | 1573769.11 | 0
698427 | [Maricao Streetlighting] (Distribution | Distribution | Distribution Streetlighting | No | Inactive | 4873133.615 | 921314.71 | 926826.7734 | 43337.3166 | 0 | 0 | 6764612.415 | 5799960.3884 | 964652.0266
698432 | FAASt [Hormigueros Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 5999141.915 | 489811.44 | 1362869.66 | 17724.97 | 0 | 0 | 7869547.985 | 7362011.575 | 507536.41
704757 | FAASt [Santa Isabel Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 8526009.33 | 383038.38 | 1562084.58 | 22536.63 | 0 | 0 | 10493668.92 | 10088093.91 | 405575.01
704862 | FAASt [Fajardo Streetlighting] (Distribution) | Distribution | Distribution Streetlighting | No | Inactive | 11073921.95 | 1052403.97 | 2150579.88 | 58676.25 | 0 | 0 | 14335582.05 | 13224501.83 | 1111080.22
[6 empty] | 124768756.81 | 2846568.5 | 22636980.1434 | 142275.1666 | 0 | 0 | 150394580.62 | 147405736.9534 | 2988843.6666
LUMA Attachment B