## Summary
Summary for Q3 - FY2026 Report:
| FY2026 Q3 Miles |  |  | FY2026 YTD Miles |  |  | FY2026 Q3 Acres* |  |  | FY2026 YTD Acres*
Voltage | Federally Funded Clearing** | OpEx Maintenance | Total Miles | Federally Funded Clearing** | OpEx Maintenance | Total Miles | Federally Funded Clearing** | OpEx Maintenance | Total Acres | Federally Funded Clearing** | OpEx Maintenance | Total Acres
Distribution | 105.6 | 27.54 | 133.14 | 390.2 | 392.827 | 783.027 | 128 | 33.9394 | 161.9394 | 472.9697 | 476.1539 | 949.1236
38 kV | 0 | 19.35 | 19.35 | 0 | 71.67 | 71.67 | 0 | 57.5758 | 57.5758 | 0 | 217.1818 | 217.1818
115 kV | 12.17 | 159.47 | 171.64 | 14 | 384.49 | 398.49 | 153.9394 | 1927.2727 | 2081.2121 | 169.697 | 4660.4848 | 4830.1818
230 kV | 0 | 99.32 | 99.32 | 0 | 237.2 | 237.2 | 0 | 1200 | 1200 | 0 | 2875.1515 | 2875.1515
Total | 118.3 | 305 | 423.3 | 404.2 | 1086.187 | 1490.387 | 281.9394 | 3218.7879 | 3500.7273 | 642.6667 | 8228.9721 | 8871.6388
*To calculate acres from miles, the miles are converted to feet by multiplying by 5,280. Then the width of the right of way is assumed for each voltage level (distribution = 10’, 38 kV = 25’, and 115 & 230 kV = 100’). The miles (in feet) are multiplied by the ROW width (in feet) to determine the square feet completed. Finally, the square feet are converted to acres by dividing by 43,560 sq feet per acre. Note: Figures may not add up due to rounding. **For federally funded miles and acres, the figure includes completed work and, in some circuits, miles assessed as clear spans. All reported circuits had physical clearing work performed on them.
Vegetation Management Progress Report

## Primary Transmission Lines
etro
Primary Transmission Lines
Line Voltage (kV) | Transmission Lines ID # | Impacted Zone1 | Circuit Miles Maintained / Cleared | # of Towers / Poles Impacted | Urban or Rural Site | Right of Way (ROWs) Width | ROW Acres Maintained / Cleared | Name of Contractor | Resources Assigned & Their Clasifications (Luma Employees and Contractors) | Type of Response2 | Type of VM Implemented 3 | Type of VM Disposal Clasification4 | Recommendations for Future VM5 | VM Activity Point of Contact (POC) | Funding Source
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 100 | 2.1818 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire Zone / Border Zone | 0.11 | 0.61111 | Rural | 100 | 1.3333 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6500 | Wire Zone / Border Zone | 0.34 | 1.8889 | Rural | 100 | 4.1212 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 1.14 | 6.3333 | Rural | 100 | 13.8182 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.43 | 2.3889 | Rural | 100 | 5.2121 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.14 | 0.77778 | Rural | 100 | 1.697 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700-38600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200-37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200-37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200-37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 19500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 19500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 19500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 6800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3200-3300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 15500-8900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 17200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37600 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700-38700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 38700-38700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 10000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 100 | 12.1212 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Site |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 12600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 12600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 12600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 12600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7700 | Wire Zone / Border Zone | 0.2 | 1.1111 | Rural | 100 | 2.4242 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.36 | 2 | Rural | 150 | 6.5455 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.36 | 2 | Rural | 150 | 6.5455 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.36 | 2 | Rural | 150 | 6.5455 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 18400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 16500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 16500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 12600 | Wire Zone / Border Zone | 0.14 | 0.77778 | Rural | 100 | 1.697 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 3800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 14400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 41400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 7900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4800 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4700 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50300 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36300 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 100 , 10,900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 4500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36900 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Wright Tree |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39000 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 |  |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 100 | 12.1212 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2300 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 11400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36700 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 8100 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2500 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 13400 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2000 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 9200 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 2600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50500 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 51200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 1900 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39100 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | PIS |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37200 | Wire Zone / Border Zone | 0.18 | 1 | Rural | 150 | 3.2727 | Xperts |  | Corrective | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
38 | 5600 | Wire Zone / Border Zone | 0.03 | 0.16667 | Rural | 100 | 0.36364 | Xperts |  | Reactive | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.78 | 4.3333 | Rural | 150 | 14.1818 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire Zone / Border Zone | 1.1 | 6.1111 | Rural | 150 | 20 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40200 | Wire Zone / Border Zone | 1.89 | 10.5 | Rural | 150 | 34.3636 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.7 | 3.8889 | Rural | 150 | 12.7273 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.7 | 3.8889 | Rural | 150 | 12.7273 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.32 | 1.7778 | Rural | 150 | 5.8182 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire Zone / Border Zone | 0.2 | 1.1111 | Rural | 150 | 3.6364 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40200 | Wire Zone / Border Zone | 0.2 | 1.1111 | Rural | 150 | 3.6364 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.75 | 4.1667 | Rural | 150 | 13.6364 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 0.75 | 4.1667 | Rural | 150 | 13.6364 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.68 | 3.7778 | Rural | 150 | 12.3636 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire Zone / Border Zone | 2 | 11.1111 | Rural | 150 | 36.3636 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40200 | Wire Zone / Border Zone | 2 | 11.1111 | Rural | 150 | 36.3636 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 1.8 | 10 | Rural | 150 | 32.7273 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 1.8 | 10 | Rural | 150 | 32.7273 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 1.3 | 7.2222 | Rural | 150 | 23.6364 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 3.6 | 20 | Rural | 150 | 65.4545 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50400 | Wire Zone / Border Zone | 3.5 | 19.4444 | Rural | 150 | 63.6364 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 1.68 | 9.3333 | Rural | 150 | 30.5455 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire Zone / Border Zone | 1.25 | 6.9444 | Rural | 150 | 22.7273 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 2.4 | 13.3333 | Rural | 150 | 43.6364 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 2.4 | 13.3333 | Rural | 150 | 43.6364 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 1.22 | 6.7778 | Rural | 150 | 22.1818 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire Zone / Border Zone | 1.5 | 8.3333 | Rural | 150 | 27.2727 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40200 | Wire Zone / Border Zone | 1.5 | 8.3333 | Rural | 150 | 27.2727 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 5.61 | 31.1667 | Rural | 150 | 102 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50700 | Wire Zone / Border Zone | 2.8 | 15.5556 | Rural | 150 | 50.9091 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 1.4 | 7.7778 | Rural | 150 | 25.4545 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 1.4 | 7.7778 | Rural | 150 | 25.4545 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 0.7 | 3.8889 | Rural | 150 | 12.7273 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.7 | 3.8889 | Rural | 150 | 12.7273 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 1.49 | 8.2778 | Rural | 150 | 27.0909 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 4.55 | 25.2778 | Rural | 150 | 82.7273 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 4.55 | 25.2778 | Rural | 150 | 82.7273 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40200 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.8 | 4.4444 | Rural | 150 | 14.5455 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 1.2 | 6.6667 | Rural | 150 | 21.8182 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 1.2 | 6.6667 | Rural | 150 | 21.8182 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 1.6 | 8.8889 | Rural | 150 | 29.0909 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 4.74 | 26.3333 | Rural | 150 | 86.1818 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 3.41 | 18.9444 | Rural | 150 | 62 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 1.4 | 7.7778 | Rural | 150 | 25.4545 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 1.4 | 7.7778 | Rural | 150 | 25.4545 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 1.6 | 8.8889 | Rural | 150 | 29.0909 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 1.6 | 8.8889 | Rural | 150 | 29.0909 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 1.25 | 6.9444 | Rural | 150 | 22.7273 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 3.46 | 19.2222 | Rural | 150 | 62.9091 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.5 | 2.7778 | Rural | 150 | 9.0909 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 1.5 | 8.3333 | Rural | 150 | 27.2727 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 0.5 | 2.7778 | Rural | 150 | 9.0909 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 1.5 | 8.3333 | Rural | 150 | 27.2727 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 2.29 | 12.7222 | Rural | 150 | 41.6364 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 0.64 | 3.5556 | Rural | 150 | 11.6364 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.65 | 3.6111 | Rural | 150 | 11.8182 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 0.5 | 2.7778 | Rural | 150 | 9.0909 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.5 | 2.7778 | Rural | 150 | 9.0909 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.48 | 2.6667 | Rural | 150 | 8.7273 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 4.09 | 22.7222 | Rural | 150 | 74.3636 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40100 | Wire Zone / Border Zone | 0.05 | 0.27778 | Rural | 150 | 0.90909 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 40200 | Wire Zone / Border Zone | 1 | 5.5556 | Rural | 150 | 18.1818 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 39800 | Wire Zone / Border Zone | 1.16 | 6.4444 | Rural | 150 | 21.0909 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37100 | Wire Zone / Border Zone | 0.3 | 1.6667 | Rural | 150 | 5.4545 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 0.6 | 3.3333 | Rural | 150 | 10.9091 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.3 | 1.6667 | Rural | 150 | 5.4545 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.74 | 4.1111 | Rural | 150 | 13.4545 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 1.37 | 7.6111 | Rural | 150 | 24.9091 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 0.6 | 3.3333 | Rural | 150 | 10.9091 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 0.5 | 2.7778 | Rural | 150 | 9.0909 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 0.51 | 2.8333 | Rural | 150 | 9.2727 | Xperts |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50200 | Wire Zone / Border Zone | 2.49 | 13.8333 | Rural | 150 | 45.2727 | Wright Tree |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
230 | 50100 | Wire Zone / Border Zone | 1.1 | 6.1111 | Rural | 150 | 20 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 37400 | Wire Zone / Border Zone | 1.2 | 6.6667 | Rural | 150 | 21.8182 | PIS |  | Preventative | Physical | Chip/Haul |  | Daniel Perry | Operation Exp
115 | 36100 | Wire Zone / Border Zone | 2.82 | 15.6667 | Rural | 150 | 51.2727 | Ceres |  | Preventative | Physical | Chip/Haul |  | Lucas Samaras | Federal PA Obligated Funds
115 | 36800 | Wire Zone / Border Zone | 7.25 | 40.2778 | Rural | 150 | 131.8182 | Ceres |  | Preventative | Physical | Chip/Haul |  | Lucas Samaras | Federal PA Obligated Funds
115 | 39000 | Wire Zone / Border Zone | 2.1 | 11.6667 | Rural | 150 | 38.1818 | Ceres |  | Preventative | Physical | Chip/Haul |  | Lucas Samaras | Federal PA Obligated Funds
Vegetation Management Progress Report Q3 FY2026

## Substations
Substations
Substations ID | Primary Voltages | Secondary Voltages | KVA | Maintained Area | Urban or Rural Site | Municipalities Impacted | Name of Contractor | Resources Assigned & Their Classifications (LUMA Employees and Contractors) | Type of Response1 | Type of VM Implemented2 | Type of VM Disposal Clasification3 | Recomendations for Future VM4 | VM Activity Point of Contact (POC) | Funding Source | Photos Before/After
2604 | 38000 | 4800 | 5000/6250 | 2.48 | Urban | Yabucoa | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1206 | 115000 | 13200 | 18/24/30/33.6 MVA | 0.4 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1201 | 38000 | 4160 | 3000/3750 | 0.09 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1205 | 115000 | 4160 | 5000 | 0.29 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1203 | 38000 | 4160 | 5000/7500 | 0.32 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
INTERMEDIA T.O. VILLA DE CANEY | 115000 | 38000 | 30/40/50/56 MVA | 0.06 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2605 | 38000 | 13200 | 7500/9375/10500 KVA | 0.23 | Urban | Humacao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1204 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.74 | Urban | Trujillo Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7103 | 38000 | 13200 | 24/32/40/44.8 MVA | 0.32 | Urban | Moca | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9202/9206 | 38000 | 8320 | 7500/11300 | 0.43 | Urban | Dorado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9203/9207 | 38000 | 4160 | 7500/11300 | 1.25 | Urban | Dorado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7601/7602 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.35 | Urban | Camuy | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7403 | 38000 | 4160 | 5000/7500 | 0.05 | Urban | Quebradillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7525 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.19 | Urban | Quebradillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7402/7404 | 38000 | 4160 | 7500/11300 | 0.23 | Urban | Quebradillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7506 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.36 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3405 | 38000 | 8320 | 7500/10500 | 0.15 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7503 | 38000 | 4160 | 7500/11300 | 0.15 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8005 | 38000 | 4160 | 3200/4000 | 2.27 | Urban | Utuado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8101 | 38000 | 4160 | 7500/11300 | 0.07 | Urban | Utuado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1512 | 38000 | 4160 | 7500/11300 | 0.18 | Urban | San Juan | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7504 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.02 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
ISABELA T.O. | 115000 | 38000 | 30/40/50/56 MVA | 0.28 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3602 | 38000 | 8320 | 7500 | 0.6 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1345 | 38000 | 4160 | 7500/11300 | 0.12 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1910 | 38000 | 4160 | 7500/11300 | 0.08 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1416 | 38000 | 4160 | 7500/11300 | 0.17 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1328/1348 | 115000 | 38000 | 60/80/100/112 MVA | 0.34 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7012 | 38000 | 4160 | 4000/4480/5973 | 0.14 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7003 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.53 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3601 | 38000 | 4800 | 5000/6250 | 0.24 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3603/3604 | 38000 | 8320 | 8.5/11.33/12.67 MVA | 0.33 | Urban | Cidra | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3403 | 38000 | 4800 | 5000/6250 | 0.02 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1327/1359 | 115000 | 38000 | 60/80/100/112 MVA | 0.27 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7502 | 38000 | 4160 | 8.5/11.33/12.67 MVA | 0.29 | Urban | Isabela | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1310 | 38000 | 4160 | 7500/11300 | 0.27 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3406/3402 | 38000 | 8320 | 7500/10500 | 0.44 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1531 | 38000 | 4160 | 7500/11300 | 0.21 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1519/1521 | 38000 | 4160 | 7500/11300 | 0.21 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7902 | 38000 | 4160 | 4/5.32/5.95 MVA | 0.07 | Urban | Lares | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7101 | 38000 | 4160 | 5000/6250/7000 | 0.13 | Urban | Moca | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1418 | 38000 | 4160 | 8.5/11.33/12.67 MVA | 0.24 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1329 | 38000 | 4160 | 7500/11300 | 0.21 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1423 | 38000 | 4160 | 7500/11300 | 0.1 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1338 | 38000 | 4160 | 7500/11300 | 0.19 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7011 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.17 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7901/7903 | 230000 | 13200 | 75/100/125 MVA | 0.36 | Urban | Lares | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1437 | 38000 | 4160 | 7500/11300 | 0.12 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1652 | 38000 | 4160 | 7.5/8.4/10/11.2 MVA | 0.2 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
MOCA GIS | 115000 | 38000 | 30/40/50/56 MVA | 0.48 | Urban | Moca | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7002 | 38000 | 4160 | 7500/11300 | 0.07 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7006 | 38000 | 4160 | 5000/6250 | 0.17 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1414 | 38000 | 4160 | 7500/11300 | 0.17 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1334 | 38000 | 4160 | 7500/10500 | 0.02 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1343 | 38000 | 4160 | 7500/11300 | 0.28 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3870 | 38000 | 8320 | 7500 | 0.05 | Urban | Cayey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1520 | 38000 | 4160 | 7500/11300 | 0.25 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8202 | 38000 | 4160 | 7500/11300 | 0.11 | Urban | Adjuntas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7004 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7005 | 38000 | 4160 | 5000/5600/7500 | 0.14 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1616 | 38000 | 4160 | 7500/10500 | 0.17 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8301/8302 | 115000 | 4160 | 8.5/11.33/12.67 MVA | 0.6 | Urban | Jayuya | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8203 | 38000 | 4160 | 7500/11300 | 0.15 | Urban | Adjuntas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1335 | 38000 | 4160 | 7500/11300 | 0.22 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1602 | 38000 | 4160 | 7500/10500 | 0.37 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2201 | 38000 | 8320 | 7500/11300 | 0.24 | Urban | Luquillo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7008 | 38000 | 13200 | 12/16/20/22.4 MVA | 1.25 | Urban | Aguadilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1620 | 115000 | 13200 | 18/24/30/33.6 MVA | 0.66 | Urban | Rio Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1615 | 38000 | 4160 | 8.5/11.33/12.67 MVA | 0.18 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1607 | 38000 | 4160 | 7500/11300 | 0.31 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2401 | 38000 | 4800 | 5000/6250 | 0.23 | Urban | Canovanas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2001/2005 | 115000 | 38000 | 60/80/100/112 MVA | 0.92 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2003 | 38000 | 4800 | 5000/6250 | 0.13 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2002 | 38000 | 4800 | 5000/6250 | 0.08 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2006 | 38000 | 4800 | 5000/6250 | 0.54 | Urban | Fajardo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5021 | 38000 | 8320 | 7500 | 0.09 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2403 | 38000 | 4800 | 5000/6250 | 0.32 | Urban | Loiza | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3010 | 38000 | 4800 | 5000/6250 | 0.73 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3007/3015 | 230000 | 13200 | 75/100/125 MVA | 0.37 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3013 | 38000 | 4800 | 5000/6250 | 0.55 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3005 | 38000 | 4800 | 5000/6250 | 0.12 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3103 | 38000 | 4800 | 5000/6250 | 0.49 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9002 | 38000 | 4160 | 7500/11300 | 0.27 | Urban | Vega Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
DUPONT SWITCH YARD | 115000 | 38000 | 30/40/50/56 MVA | 0.05 | Urban | Manati | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8405 | 38000 | 13200 | 12/16/20/22.4 MVA | 0.33 | Urban | Manati | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9001/9003/9004 | 230000 | 13200 | 75/100/125 MVA | 1.15 | Urban | Vega Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3202 | 38000 | 4160 | 3200/4000 | 0.14 | Urban | Juncos | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2801 | 38000 | 4160 | 7.5/10/11.2 | 0.24 | Urban | Las Piedras | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2601 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Humacao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8401 | 38000 | 8320 | 10000/14000 | 0.23 | Urban | Manati | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2302 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2305 | 38000 | 4800 | 5000/6250 | 0.89 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3101 | 38000 | 4160 | 7500/10500 | 0.13 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3102 | 38000 | 4800 | 5000/6250 | 0.18 | Urban | Gurabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2301 | 38000 | 4800 | 5000/6250 | 0.17 | Urban | Rio Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1806 | 115000 | 13200 | 24/32/40/44.8 MVA | 2.81 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1903 | 38000 | 4800 | 5000/6250 | 0.22 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1911/1912/1924 | 38000 | 13200 | 9/12/13.4 MVA | 0.46 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
SAN JUAN SP TC/PUERTO NUEVO | 13000 | 480 | 2.5KVA | 1.61 | Urban | Puerto Nuevo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3016 | 115000 | 13200 | 18/24/30/33.6 MVA | 0.74 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3014 | 38000 | 4160 | 7500/10500 | 0.5 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3009 | 38000 | 8320 | 7500/11300 | 0.33 | Urban | Caguas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8501 | 38000 | 4160 | 7.5/8.4/10/11.2 MVA | 0.24 | Urban | Barceloneta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9101/9105 | 38000 | 8320 | 7500/11300 | 0.38 | Urban | Vega Alta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9404 | 38000 | 4160 | 7500/11300 | 0.23 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1803 | 38000 | 4800 | 5000/6250 | 0.44 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1907/1909 | 115000 | 38000 | 60/80/100/112 MVA | 0.58 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1901/1904 | 115000 | 38000 | 60/80/100/112 MVA | 0.26 | Urban | Guaynabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9103 | 38000 | 4160 | 7500/11300 | 0.37 | Urban | Vega Alta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1336/1301 | 115000 | 38000 | 60/80/100/112 MVA | 0.89 | Urban | Carolina | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9201 | 38000 | 4160 | 7500/11300 | 0.15 | Urban | Dorado | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
8504 | 38000 | 4160 | 7500/11300 | 0.27 | Urban | Barceloneta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
BARCELONETA TC | 115000 | 38000 | 30/40/50/56 MVA | 0.91 | Urban | Barceloneta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3502 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Aibonito | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7201 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.21 | Urban | Aguada | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6101 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.67 | Urban | Anasco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3501 | 38000 | 4800 | 5000/6250 | 0.09 | Urban | Aibonito | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7302 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.11 | Urban | Rincon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7303 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.42 | Urban | Rincon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
7301 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Rincon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6010 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.12 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6102 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.19 | Urban | Anasco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1419/1420 | 115000 | 38000 | 60/80/100/112 MVA | 2.62 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1303 | 38000 | 4160 | 7500/11300 | 0.63 | Urban | Cupey Alto | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4301 | 38000 | 4160 | 7500/11300 | 0.15 | Urban | Maunabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6003 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6002 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.11 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9601/9602 | 230000 | 13200 | 75/100/125 MVA | 1.67 | Urban | Barranquitas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
Zona Libre | 13000 | 480 | 2.5KVA | 0.35 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6005 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.03 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6015 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.41 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9605 | 38000 | 4160 | 7500/11300 | 0.11 | Urban | Barranquitas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2402/2404 | 230000 | 13200 | 75/100/125 MVA | 1.2 | Urban | Canovanas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6305 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.17 | Urban | Maricao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1734 | 38000 | 4800 | 5000/6250 | 0.08 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4001 | 38000 | 8320 | 7500 | 0.5 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4006 | 38000 | 8320 | 7500 | 0.74 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1710/1712/1719 | 115000 | 38000 | 60/80/100/112 MVA | 1.14 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6001/6014 | 230000 | 13200 | 75/100/125 MVA | 0.47 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1111/1112/1113 | 38000 | 4160 | 7500/10500 | 1.14 | Urban | Hato Rey | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6012 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.42 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1704 | 38000 | 4160 | 7500/10500 | 0.15 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4101 | 38000 | 8320 | 7500 | 0.22 | Urban | Arroyo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
Horizon SY | 115000 | 38000 | 30/40/50/56 MVA | 0.38 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6306 | 38000 | 4160 | 3072/3840 | 0.06 | Urban | Maricao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1706 | 38000 | 4160 | 7500/10500 | 0.21 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1705 | 38000 | 4160 | 7500/10500 | 0.15 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1707 | 38000 | 4160 | 7500/10500 | 0.24 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6801/6802 | 230000 | 13200 | 75/100/125 MVA | 1.95 | Urban | Hormigueros | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4201 | 38000 | 8320 | 7500 | 0.21 | Urban | Patillas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4503 | 38000 | 8320 | 7500 | 0.09 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4502 | 38000 | 8320 | 7500 | 0.23 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1708 | 38000 | 4160 | 7500/10500 | 0.24 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1709/1720 | 115000 | 38000 | 60/80/100/112 MVA | 0.78 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6004 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.2 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4504 | 38000 | 8320 | 7500 | 0.17 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4002 | 38000 | 8320 | 7500 | 0.18 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4501 | 38000 | 8320 | 7500 | 0.22 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9501 | 38000 | 4160 | 7500/11300 | 0.74 | Urban | Corozal | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9502/9503 | 230000 | 13200 | 75/100/125 MVA | 0.29 | Urban | Corozal | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6301 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.16 | Urban | Maricao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6303 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.03 | Urban | Maricao | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4601 | 38000 | 8320 | 7500 | 0.21 | Urban | Coamo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4602 | 38000 | 8320 | 7500 | 0.25 | Urban | Coamo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4402 | 38000 | 8320 | 7500 | 1.34 | Urban | Santa Isabel | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6008 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.49 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6201 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.18 | Urban | Las Marias | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1802 | 38000 | 4800 | 5000/6250 | 0.16 | Urban | Catano | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6404 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.59 | Urban | San German | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5801 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.29 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6705 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6702 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.28 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6704 | 38000 | 13200 | 12/16/20/22.4 MVA | 0.24 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1703 | 38000 | 4160 | 7500/10500 | 0.22 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9801/9802 | 230000 | 13200 | 75/100/125 MVA | 0.23 | Urban | Naranjito | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4401 | 38000 | 8320 | 7500 | 0.23 | Urban | Santa Isabel | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1713 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.62 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5817 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.27 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5804 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.04 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6006 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.15 | Urban | Mayaguez | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6703 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.24 | Urban | Cabo Rojo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6401 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.39 | Urban | San German | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5304 | 38000 | 8320 | 7500 | 0.44 | Urban | Yauco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6603 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.73 | Urban | Lajas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5803 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.28 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5808 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.26 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1701/1715 | 115000 | 38000 | 60/80/100/112 MVA | 0.81 | Urban | Bayamon | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5601 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.1 | Urban | Guanica | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6501 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.31 | Urban | Sabana Grande | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
1718 | 38000 | 4800 | 5000/6250 | 1.1 | Urban | Toa Baja | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9403/9405 | 230000 | 13200 | 75/100/125 MVA | 0.68 | Urban | Toa Alta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5901 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.14 | Urban | Villalba | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5013 | 38000 | 8320 | 7500 | 0.12 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5008 | 38000 | 8320 | 7500 | 0.14 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9401 | 38000 | 4160 | 7500/11300 | 0.27 | Urban | Toa Alta | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5302 | 38000 | 8320 | 7500 | 0.19 | Urban | Yauco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5602 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.8 | Urban | Guanica | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6601/6602 | 230000 | 13200 | 75/100/125 MVA | 0.32 | Urban | Lajas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
6406 | 115000 | 13200 | 24/32/40/44.8 MVA | 1.36 | Urban | San German | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5805 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.03 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
JUANA DIAZ TC | 115000 | 38000 | 30/40/50/56 MVA | 1.6 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5802 | 38000 | 13200 | 24/32/40/44.8 MVA | 0.39 | Urban | Juana Diaz | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5012 | 38000 | 8320 | 7500 | 0.31 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5007 | 38000 | 8320 | 7500 | 0.38 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5902 | 115000 | 13200 | 24/32/40/44.8 MVA | 0.18 | Urban | Villalba | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5305 | 38000 | 8320 | 7500 | 0.49 | Urban | Yauco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5301 | 38000 | 8320 | 7500 | 0.17 | Urban | Yauco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9901 | 38000 | 4160 | 5000/5600/7500 | 0.06 | Urban | Orocovis | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
AGUIRRE 230kV switchyard | 230000 | 13200 | 75/100/125 MVA | 1.46 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
AGUIRRE 115kV switchyard | 230000 | 13200 | 75/100/125 MVA | 2.71 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5303 | 38000 | 8320 | 7500 | 0.47 | Urban | Yauco | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5401 | 38000 | 8320 | 7500 | 0.26 | Urban | Penuelas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
AQUIRRE CC | 230000 | 13200 | 75/100/125 MVA | 2.44 | Urban | Salinas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5501 | 38000 | 8320 | 7500/10500 | 0.3 | Urban | Guayanilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
9902 | 38000 | 13200 | 12/16/20/22.4 MVA | 0.16 | Urban | Orocovis | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5005 | 38000 | 8320 | 7500 | 0.37 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5403 | 38000 | 8320 | 7500 | 0.15 | Urban | Penuelas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
2803 | 38000 | 4800 | 5000/6250 | 0.25 | Urban | Naguabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
PUNTA LIMA | 13000 | 480 | 2.5KVA | 0.05 | Urban | Naguabo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5019 | 38000 | 8320 | 7500 | 0.15 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5016 | 38000 | 8320 | 7500 | 0.5 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5402 | 38000 | 8320 | 7500 | 0.36 | Urban | Penuelas | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
COSTA SUR 115kV | 115000 | 38000 | 30/40/50/56 MVA | 2.52 | Urban | Guayanilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
COSTA SUR 230kV | 115000 | 38000 | 30/40/50/56 MVA | 2.56 | Urban | Guayanilla | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5001/5011 | 230000 | 13200 | 75/100/125 MVA | 2.23 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
AES Power Plant | 230000 | 13200 | 75/100/125 MVA | 3.3 | Urban | Guayama | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
PATERN | 13000 | 480 | 2.5KVA | 0.41 | Urban | Santa Isabel | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5003/5004 | 230000 | 13200 | 75/100/125 MVA | 0.78 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
5002/5018 | 230000 | 13200 | 75/100/125 MVA | 1.93 | Urban | Ponce | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
4603 | 38000 | 8320 | 7500 | 0.19 | Urban | Coamo | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
3201/3205 | 230000 | 13200 | 75/100/125 MVA | 1.33 | Urban | Juncos | Xperts |  | Preventive | Chemical | N/A - No Debris | Bare ground application/5-6 months after treatment | Daniel Perry | Operation Exp
Vegetation Management Progress Report Q3 FY2026

## Distribution Lines
Distribution Lines
Line Voltage (kV) | Primary Distribution Line ID # | Impacted Zone1 | Circuit Miles Maintained / Cleared | # of Poles Impacted | Urban or Rural Site | Municipalities Impacted | Right of Way (Rows) Width | Name of Contractor | Resources Assigned & Their Clasifications (Luma Employees and Contractors) | Type of Response2 | Type of VM Implemented 3 | Type of VM Disposal Clasification4 | Recommendations for Future VM5 | Luma Labor Required | VM Activity Point of Contact (POC) | Funding Source | Photos Before/After
13.2 | 2603-10 | Wire Zone / Border Zone | 3.35 | 111.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3004-03 | Wire Zone / Border Zone | 1.34 | 44.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3009-01 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3009-03 | Wire Zone / Border Zone | 0.89 | 29.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3009-04 | Wire Zone / Border Zone | 1.91 | 63.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 3014-01 | Wire Zone / Border Zone | 3.42 | 114 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 3014-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 3101-02 | Wire Zone / Border Zone | 3.28 | 109.3333 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
13.2 | 3103-04 | Wire Zone / Border Zone | 4.29 | 143 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
13.2 | 3103-05 | Wire Zone / Border Zone | 4.52 | 150.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3301-03 | Wire Zone / Border Zone | 1.83 | 61 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3302-01 | Wire Zone / Border Zone | 0.16 | 5.3333 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3401-01 | Wire Zone / Border Zone | 1.28 | 42.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
13.2 | 3402-06 | Wire Zone / Border Zone | 0.1 | 3.3333 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3405-02 | Wire Zone / Border Zone | 6.08 | 202.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3406-03 | Wire Zone / Border Zone | 6.56 | 218.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3501-03 | Wire Zone / Border Zone | 2.13 | 71 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 3601-01 | Wire Zone / Border Zone | 0.92 | 30.6667 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 4504-02 | Wire Zone / Border Zone | 0.07 | 2.3333 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 4602-01 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 4602-04 | Wire Zone / Border Zone | 1.08 | 36 | Urban | Ponce | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5003-01 | Wire Zone / Border Zone | 0.99 | 33 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5008-03 | Wire Zone / Border Zone | 2.4 | 80 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5008-04 | Wire Zone / Border Zone | 3.46 | 115.3333 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5019-01 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | Ponce | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5304-01 | Wire Zone / Border Zone | 0.39 | 13 | Urban | Ponce | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5401-04 | Wire Zone / Border Zone | 3.82 | 127.3333 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5501-02 | Wire Zone / Border Zone | 0.07 | 2.3333 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5802-02 | Wire Zone / Border Zone | 0.61 | 20.3333 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5802-03 | Wire Zone / Border Zone | 4.24 | 141.3333 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5805-01 | Wire Zone / Border Zone | 1 | 33.3333 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 5901-01 | Wire Zone / Border Zone | 3.08 | 102.6667 | Urban | Ponce | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 6404-02 | Wire Zone / Border Zone | 4.12 | 137.3333 | Urban | Mayaguez | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 7402-01 | Wire Zone / Border Zone | 0.5 | 16.6667 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
13.2 | 7505-05 | Wire Zone / Border Zone | 7 | 233.3333 | Urban | Mayaguez | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 7602-05 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 7701-02 | Wire Zone / Border Zone | 5.03 | 167.6667 | Urban | Arecibo | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 7802-04 | Wire Zone / Border Zone | 4.51 | 150.3333 | Urban | Mayaguez | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
13.2 | 7805-13 | Wire Zone / Border Zone | 3.25 | 108.3333 | Urban | Mayaguez | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
13.2 | 7903-06 | Wire Zone / Border Zone | 1.17 | 39 | Urban | Mayaguez | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 8002-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Arecibo | 10 | Ceres |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
7.2 | 8007-03 | Wire Zone / Border Zone | 2.71 | 90.3333 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 8011-01 | Wire Zone / Border Zone | 0.45 | 15 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
13.2 | 8013-02 | Wire Zone / Border Zone | 6.44 | 214.6667 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
4.16 | 8301-01 | Wire Zone / Border Zone | 0.34 | 11.3333 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 8701-03 | Wire Zone / Border Zone | 0.99 | 33 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 8801-02 | Wire Zone / Border Zone | 0.47 | 15.6667 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 9001-01 | Wire Zone / Border Zone | 0.46 | 15.3333 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 9002-02 | Wire Zone / Border Zone | 1.75 | 58.3333 | Urban | Arecibo | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
13.2 | 9004-10 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Arecibo | 10 | Asplundh Tree Experts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 9703-02 | Wire Zone / Border Zone | 1.48 | 49.3333 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 9703-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 9902-03 | Wire Zone / Border Zone | 0.19 | 6.3333 | Urban | Caguas | 10 | Xperts |  | Preventative | Physical | Chip/Haul |  |  | Lucas Samaras | Federal PA Obligated Funds
8.32 | 9101-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Vega Alta | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9001-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Vega Baja | 10 | PIS |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8005-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8202-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8602-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8202-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8404-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Manati | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8011-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9002-03 | Wire Zone / Border Zone | 0.28 | 9.3333 | Urban | Vega Baja | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8602-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | florida | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8202-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8701-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Ciales | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9003-05 / 2200 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Vega Baja | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8405-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Barceloneta | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8405-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Barceloneta | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8203-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8103-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8203-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8203-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8202-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8103-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8004-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Arecibo | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9003-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Vega Baja | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8202-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-05 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8203-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7702-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hatillo | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 8405-02 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Barceloneta | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8007-04 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8001-01 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8701-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Ciales | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8005-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7902-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8203-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7402-05 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Quebradillas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8010-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8104-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8101-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9004-08 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Vega Baja | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7404-06 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Quebradillas | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 8010-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Arecibo | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8005-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8602-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | florida | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8103-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Utuado | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8602-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | florida | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8202-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Adjuntas | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8302-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Jayuya | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8103-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Utuado | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9004-08 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Vega Baja | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8103-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8103-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Utuado | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 8301-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Ciales | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7701-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Hatillo | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1705-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1903-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1343-05 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1708-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1708/03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 9403-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Toa Alta | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1924-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1901-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1704-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1803-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Catano | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1716-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1704-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9801-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Naranjito | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1707-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1710-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1718-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Toa Baja | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9801-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Naranjito | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1713-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Toa Baja | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1713-05 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Toa Baja | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1704-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1714-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1708-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Bayamon | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1706-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1720-07 | Wire Zone / Border Zone | 0.57 | 19 | Urban | Bayamon | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9401-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1710-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1710-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Bayamon | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1343-05 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Guaynabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3501-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Aibonito | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1205-03 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3014-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3301-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3405-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2601-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Las Piedras | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 1201-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2602-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Humacao | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3006-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3004-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3405-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3302-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9602-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Barranquitas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9602-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Barranquitas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9703-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3009-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3004-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3103-05/3015-07/3103-04/3013-03 | Wire Zone / Border Zone | 0.65 | 21.6667 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3010-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3401-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9601-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Orocovis | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2901-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Yabucoa | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3401-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-06 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3601-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Cidra | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-03 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3405-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9902-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Orocovis | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3405-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9601-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Orocovis | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3604-06 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9703-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Comerio | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3401-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2803-01 | Wire Zone / Border Zone | 0.31 | 10.3333 | Urban | Las Piedras | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 3102-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3007-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3101-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3302-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Juncos | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9703-03 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Comerio | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9703-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-04 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 9703-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Comerio | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2803-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Naguabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-04 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3014-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2801-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Las Piedras | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2801-02 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Las Piedras | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3014-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3602-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3701-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3004-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3405-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Cayey | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3101-04 | Wire Zone / Border Zone | 0.37 | 12.3333 | Urban | Gurabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3602-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Cidra | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3005-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3004-01 | Wire Zone / Border Zone | 0.4 | 13.3333 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3014-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Caguas | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3602-01 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Aguas Buenas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Lorenzo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 3101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Lorenzo | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 3013-03 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Caguas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7505-01 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Isabela | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7805-11 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Lares | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6101-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Añasco | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6305-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maricao | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6702-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Cabo Rojo | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6010-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6305-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Maricao | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6401-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6401-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6007-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Hormigueros | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6014-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7802-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6008-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6801-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7902-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6801-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Hormigueros | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.57 | 19 | Urban | San German | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7505-01 | Wire Zone / Border Zone | 0.63 | 21 | Urban | Isabela | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.57 | 19 | Urban | San German | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7805-11 | Wire Zone / Border Zone | 0.71 | 23.6667 | Urban | San Sebastian | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7303-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Rincon | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 6406-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 7805-13 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Sebastian | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6007-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7008-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguada | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6404-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | San German | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7301-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Rincon | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7301-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Rincon | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7901-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6012-02 | Wire Zone / Border Zone | 0.8 | 26.6667 | Urban | Añasco | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6401-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6008-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Mayaguez | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6801-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Hormigueros | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Isabela | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7903-06 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6802-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7902-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7902-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6201-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Las Marias | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7403-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Lares | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6406-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San German | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7103-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Moca | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 7504-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Aguadilla | 10 | Xperts |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5304-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guayanilla | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Patillas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5501-04 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Guayanilla | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4003-01 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Guayama | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4201-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Patillas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5901-02 | Wire Zone / Border Zone | 0.14 | 4.6667 | Urban | Villalba | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-04 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Sabana Grande | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5901-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Villalba | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5901-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Villalba | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5403-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Penuelas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4301-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Patillas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4301-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Maunabo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4003-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guayama | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 6702-02 | Wire Zone / Border Zone | 0.26 | 8.6667 | Urban | Lajas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5303-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Yauco | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5401-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Penuelas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5501-04 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Yauco | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 4003-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Salinas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5004-07 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Sabana Grande | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5901-03 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Villalba | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5817-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Juana Diaz | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Sabana Grande | 10 | PIS |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 6501-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Sabana Grande | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5004-07 | Wire Zone / Border Zone | 0.68 | 22.6667 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4603-02 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Coamo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5501-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Guayanilla | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4603-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Coamo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5013-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4501-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Salinas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5012-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4503-02 | Wire Zone / Border Zone | 0.23 | 7.6667 | Urban | Salinas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5002-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5005-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Ponce | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 4602-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Coamo | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 5018-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Ponce | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 5901-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Villalba | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1343-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1359-07/08 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1421-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1335-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-04 | Wire Zone / Border Zone | 0.17 | 5.6667 | Urban | Carolina | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1401-07 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1520-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1658-13 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Loiza | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1301-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1203-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Trujillo Alto | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1118-10/1110-03 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1342-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1342-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2401-01 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Canovanas | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 1620-04 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Carolina | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1512-04/1512-05 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1205-01 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-05 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Carolina | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2403-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Loiza | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1330-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Carolina | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2301-02 | Wire Zone / Border Zone | 0.09 | 3 | Urban | Rio Grande | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1334-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1334-02 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1345-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1345-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1525-05 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1334-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1525-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1418-02 | Wire Zone / Border Zone | 0.03 | 1 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1602-01 | Wire Zone / Border Zone | 0.03 | 1 | Urban | Carolina | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Carolina | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1607-03 | Wire Zone / Border Zone | 0.06 | 2 | Urban | Trujillo Alto | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
13.2 | 2306-02 | Wire Zone / Border Zone | 0.11 | 3.6667 | Urban | Rio Grande | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1330-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Corrective | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
8.32 | 2202-01 | Wire Zone / Border Zone | 0.2 | 6.6667 | Urban | Fajardo | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
4.16 | 1342-01 | Wire Zone / Border Zone | 0.06 | 2 | Urban | San Juan | 10 | Wright Tree |  | Reactive | Physical | Chip/Haul |  |  | Daniel Perry | Operation Exp
Vegetation Management Progress Report Q3 FY2026