## Report
Inciso C.i.
Casos Nuevos - enero, febrero, marzo 2026
| Tipo de Caso | # | Proporción %
GDL17 | Flujo Expedito | 9397 | 99.44%
GD10K | Flujo Regular | 0 | 0%
GD1M | Mayores de 25 kW | 49 | 0.5185%
Transmission | Transmisión | 4 | 0.04233%
| Total | 9450 | 100%
| Tipo de Cliente | # | Proporción %
| Residencial | 9179 | 97.13%
| Comercial | 262 | 2.772%
| Industrial | 3 | 0.03175%
| Gubernamental | 6 | 0.06349%
| Agricultural | 0 | 0%
| Total | 9450 | 100%
Inciso C.ii, C.iii, C.iv
| Requerimiento | Información*
| Promedio para activación de interconexión de los sistemas menores de 25 kW (expeditos). | 16.0675 | Inciso ii
| Promedio transcurrido que cliente notifica a LUMA la interconexión de su sistema menor de 25 kW y que se refleja el acuerdo en la factura. (Periodo) | 6.5221 | Inciso iii
| Más de treinta (30) días de espera para reflejar el acuerdo en factura, posterior a la notificación de interconexión en el Portal (expeditos). | 9.701% | Inciso iv
| Cantidad de medidores bidireccionales disponibles en los almacenes. | 28804
| Portal Casos Activados | Cantidad | Proporción % | Promedio de activación
| Cantidad de casos con 30 dias o menos | 8871 | 90.3% | 5.7103
| Cantidad de casos con 30 dias o más | 953 | 9.701% | 113.0803
| Total de casos expeditos GDL17 activados | 9824 | 100% | 16.0675
| Casos Pendientes de Activación | Cantidad | Proporción %
| Cantidad de casos con 30 dias o menos | 148 | 10.21%
| Cantidad de casos con 30 dias o más | 1302 | 89.79%
| Total de casos expeditos GDL17 pendientes activación | 1450 | 100%
| Progreso del Periodo | Cantidad
| Total de solicitudes activadas en menos de 30 días. | 8774
| Total de solicitudes recibidas durante el periodo. | 9397
| Porciento de casos activados en menos de 30 días | 93.37%
Inciso C.v
| BACKLOG END OF PERIOD | # | Proporción %
| Casos Pendientes a Acción del Cliente | 604 | 41.66%
| Casos Pendientes a Acción de LUMA | 846 | 58.34%
| Total Cantidad de casos con 30 dias o más | 1450 | 100%
Inciso: i, ii, iii, iv, v | [24 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
| Resumen de Proceso de Casos | Feb | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | Total | Resumen de Proceso de Casos
| Beginning Bal. | 2919 | 1655 | 1823 | 2053 | 2683 | 3130 | 2913 | 3738 | 5033 | 4985 | 4246 | 5498 | 5418 | 4885 | 4653 | 5610 | 5768 | 5602 | 6328 | 5525 | 6177 | 6483 | 5633 | 3550 | 4344 | 5011 | 5028 | 6193 | 5744 | 5510 | 4357 | 5712 | 6106 | 5350 | 5857 | 6760 | 7667 | 5388 | 5297 | 4741 | 4953 | 4921 | 6171 | 6321 | 8199 | 7963 | 9059 | 8224 | 8562 | 8630 | 8277 |  | Beginning Bal.
| New Cases | 1486 | 2116 | 1681 | 2766 | 2633 | 3003 | 4153 | 3285 | 2866 | 3367 | 3537 | 3233 | 2854 | 3390 | 3009 | 3161 | 2943 | 4255 | 4149 | 4896 | 4848 | 4127 | 1994 | 2947 | 3318 | 3052 | 3038 | 3384 | 3263 | 2611 | 3804 | 3951 | 3507 | 3825 | 4263 | 4245 | 4576 | 3788 | 3077 | 3662 | 3399 | 4390 | 4471 | 6869 | 4675 | 3634 | 4183 | 3143 | 3499 | 2808 | 0 | 9450 | New Cases
| Subtotal Pending Cases | 4405 | 3771 | 3504 | 4819 | 5316 | 6133 | 7066 | 7023 | 7899 | 8352 | 7783 | 8731 | 8272 | 8275 | 7662 | 8771 | 8711 | 9857 | 10477 | 10421 | 11025 | 10610 | 7627 | 6497 | 7662 | 8063 | 8066 | 9577 | 9007 | 8121 | 8161 | 9663 | 9613 | 9175 | 10120 | 11005 | 12243 | 9176 | 8374 | 8403 | 8352 | 9311 | 10642 | 13190 | 12874 | 11597 | 13242 | 11367 | 12061 | 11438 | 8277 |  | Subtotal Pending Cases
| CC&B - Activated - Period | 339 | 1639 | 1447 | 862 | 1971 | 1264 | 2925 | 1876 | 464 | 2967 | 2063 | 812 | 2490 | 3208 | 534 | 2165 | 2491 | 1005 | 3634 | 3793 | 1349 | 4040 | 3723 | 766 | 2410 | 2722 | 1172 | 3540 | 3322 | 2652 | 2220 | 3456 | 1882 | 3134 | 3145 | 885 | 5991 | 3789 | 2217 | 3158 | 3193 | 2863 | 4242 | 4903 | 3300 | 2383 | 4741 | 2282 | 3234 | 3024 | 433 | 8973 | CC&B - Activated - Period
| CC&B - Activated - Backlog | 2411 | 309 | 4 | 1274 | 215 | 1958 | 403 | 114 | 2450 | 1139 | 222 | 2501 | 897 | 414 | 1518 | 838 | 618 | 2524 | 1318 | 451 | 3193 | 937 | 354 | 1387 | 241 | 313 | 701 | 293 | 175 | 1112 | 229 | 101 | 2381 | 184 | 215 | 2453 | 864 | 90 | 1416 | 292 | 238 | 277 | 79 | 88 | 1611 | 155 | 277 | 523 | 197 | 137 | 0 | 857 | CC&B - Activated - Backlog
| Subtotal Activated Cases | 2750 | 1948 | 1451 | 2136 | 2186 | 3222 | 3328 | 1990 | 2914 | 4106 | 2285 | 3313 | 3387 | 3622 | 2052 | 3003 | 3109 | 3529 | 4952 | 4244 | 4542 | 4977 | 4077 | 2153 | 2651 | 3035 | 1873 | 3833 | 3497 | 3764 | 2449 | 3557 | 4263 | 3318 | 3360 | 3338 | 6855 | 3879 | 3633 | 3450 | 3431 | 3140 | 4321 | 4991 | 4911 | 2538 | 5018 | 2805 | 3431 | 3161 | 433 | 9830 | Subtotal Activated Cases
| Total Open Cases | 1655 | 1823 | 2053 | 2683 | 3130 | 2913 | 3738 | 5033 | 4985 | 4246 | 5498 | 5418 | 4885 | 4653 | 5610 | 5768 | 5602 | 6328 | 5525 | 6177 | 6483 | 5633 | 3550 | 4344 | 5011 | 5028 | 6193 | 5744 | 5510 | 4357 | 5712 | 6106 | 5350 | 5857 | 6760 | 7667 | 5388 | 5297 | 4741 | 4953 | 4921 | 6171 | 6321 | 8199 | 7963 | 9059 | 8224 | 8562 | 8630 | 8277 | 7844 |  | Total Open Cases
Número de Clientes con Medición Neta por Período
| MES | Periodo Anterior | Periodo Actual | Total
| Mayo - Julio 2021 | 2844 | 536 | 3380
| Agosto - Octubre 2021 | 3543 | 3032 | 6575
| Novi. 2021 - Enero 2022 | 3697 | 2755 | 6452
| Febrero - Abril 2022 | 2724 | 3425 | 6149
| May - July 2022 | 1626 | 5815 | 7441
| July - September 2022 | 2475 | 6065 | 8540
| Octubre - Diciembre 2022 | 3811 | 5494 | 9305
| Enero - Marzo 2023 | 3812 | 6510 | 10322
| Abril - Junio 2023 | 2974 | 5190 | 8164
| Julio - Septiembre 2023 | 4293 | 8432 | 12725
| Octubre - Diciembre 2023 | 4484 | 9112 | 13596
| Enero - Marzo 2024 | 1941 | 5898 | 7839
| Abril - Junio 2024 | 1169 | 8034 | 9203
| Julio - Septiembre 2024 | 1442 | 8328 | 9770
| Octubre - Diciembre 2024 | 2780 | 8161 | 10941
| Enero - Marzo 2025 | 3407 | 10665 | 14072
| Abril - Junio 2025 | 1946 | 8568 | 10514
| Julio - Septiembre 2025 | 444 | 13445 | 13889
| Octubre - Diciembre 2025 | 2043 | 11639 | 13682
| Enero - Marzo 2026 | 857 | 8973 | 9830
Número de Solicitudes Pendientes de Medición Neta
| MES | Periodo Anterior | Periodo Actual | Total
| Mayo - Julio 2021 | 6313 | 661 | 6974
| Agosto - Octubre 2021 | 3431 | 1516 | 4947
| Novi. 2021 - Enero 2022 | 918 | 2563 | 3481
| Febrero - Abril 2022 | 195 | 1858 | 2053
| Mayo - Julio 2022 | 427 | 2587 | 3014
| Julio - Septiembre 2022 | 657 | 4376 | 5033
| Octubre - Diciembre 2022 | 1222 | 4276 | 5498
| Enero - Marzo 2023 | 1683 | 2968 | 4651
| Abril - Junio 2023 | 1677 | 3923 | 5600
| Julio - Septiembre 2023 | 1307 | 4868 | 6175
| Octubre - Diciembre 2023 | 1691 | 1857 | 3548
| Enero - Marzo 2024 | 1560 | 3419 | 4979
| Abril - Junio 2024 | 1153 | 1614 | 2767
| Julio - Septiembre 2024 | 963 | 2930 | 3893
| Octubre - Diciembre 2024 | 1120 | 3394 | 4514
| Enero - Marzo 2025 | 1075 | 1874 | 2949
| Abril - Junio 2025 | 902 | 541 | 1443
| Julio - Septiembre 2025 | 1004 | 2227 | 3231
| Octubre - Diciembre 2025 | 1140 | 797 | 1937
| Enero - Marzo 2026 | 1026 | 424 | 1450
Clientes y capacidad
MEDICION NETA - AÑO 2021 - 2026
| Date | Clients | Capacity (MW)
| January '21 | 22588 | 207.17
| February | 23712 | 213.66
| March | 24712 | 219.34
| April | 25476 | 224.03
| May | 25823 | 226.25
| June | 26079 | 227.67
| July | 33323 | 247.4892
| August | 35007 | 257.7058
| September | 36308 | 265.6535
| October | 37787 | 274.9847
| November | 39223 | 283.6996
| December | 40492 | 291.2843
| January '22 | 42094 | 301.3658
| February | 43968 | 313.0279
| March | 45729 | 323.2069
| April | 47863 | 336.6098
| May | 49702 | 347.3968
| June | 52390 | 363.4161
| July | 55155 | 380.0682
| August | 57885 | 396.7998
| September | 61582 | 419.0081
| October | 64533 | 437.9309
| November | 67535 | 456.3361
| December | 70910 | 477.3589
| January '23 | 73941 | 496.0153
| February | 77058 | 516.5961
| March | 79825 | 534.233
| April | 82957 | 556.9863
| May | 86109 | 578.42
| June | 89082 | 600.6962
| July | 92015 | 622.4427
| August | 96339 | 653.7813
| September | 100384 | 682.3782
| October | 104684 | 712.4454
| November | 108952 | 742.212
| December | 111988 | 764.1173
| January '24 | 113651 | 776.4201
| February | 115990 | 792.7754
| March | 118834 | 813.2757
| April | 121370 | 831.526
| May | 124557 | 854.3244
| June | 127557 | 878.8589
| July | 129962 | 901.9768
| August | 132254 | 919.4864
| September | 135681 | 947.9065
| October | 139468 | 978.2227
| November | 142626 | 1003.4979
| December | 145715 | 1027.205
| January ' 25 | 149400 | 1054.7733
| February | 154395 | 1095.88
| March | 158684 | 1144.0793
| April | 162096 | 1163.599
| May | 164982 | 1190.586
| June | 167986 | 1217.805
| July | 171584 | 1246.0076
| August | 175481 | 1282.6144
| September | 179947 | 1335.0409
| October | 184369 | 1377.5475
| November | 187908 | 1414.0179
| December | 191929 | 1455.5846
| January ' 26 | 195195 | 1489.5657
| February | 198268 | 1527.9589
| March | 201125 | 1560.669

## Data
Number | Form type | Customer Rate Class | Total Capacity AC (kW) | Case Period | Filling date | Filing Month | Filing Year | Date Activated (NEM Tracker) | Time to activate | Activity | Etapa | Case connected Status | New Definitions | Applicant Registration | Application Completed | Backlog | Backlog Status | Region | Case Connected Month | Returned for corrections (Validation) | LUMA (Activation and Validation) Time per case | Proponents time (Validation) | End of Period 04/1/2026 | Days
2022-GD-24275 | GD1M | Comercial | 28.8 | Out of period | 2022-10-12 | October | 2022 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1267
2025-GD-00063 | TRANSMISSION | Comercial | 0 | Out of period | 2025-03-18 | March | 2025 |  |  | approveTransmissionEnd | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 379
2022-GD-21098 | GD1M | Residencial | 38.4 | Out of period | 2022-09-09 | September | 2022 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 1300
2022-GD-16263 | GD1M | Comercial | 49.27 | Out of period | 2022-07-22 | July | 2022 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1349
2022-GD-09193 | GD1M | Comercial | 133.2 | Out of period | 2022-05-20 | May | 2022 |  |  | Anejar Certificacion e Instalacion | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1412
2022-GD-09188 | GD1M | Comercial | 133.3 | Out of period | 2022-05-20 | May | 2022 |  |  | Anejar Certificacion e Instalacion | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1412
2023-GD-15503 | GD1M | Comercial | 45 | Out of period | 2023-04-17 | April | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 1080
2023-GD-12421 | GD1M | Comercial | 55.5 | Out of period | 2023-04-12 | April | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1085
2023-GD-14728 | TRANSMISSION | Industrial | 1056 | Out of period | 2023-05-23 | May | 2023 |  |  | approveTransmissionEnd | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 1044
2023-GD-12092 | GD1M | Comercial | 31.86 | Out of period | 2023-04-17 | April | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1080
2023-GD-10704 | GD1M | Comercial | 60 | Out of period | 2023-04-17 | April | 2023 |  |  | Anejar Certificacion e Instalacion | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1080
2023-GD-10846 | GD1M | Comercial | 81 | Out of period | 2023-09-14 | September | 2023 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 930
2023-GD-14351 | GD1M | Comercial | 66.965 | Out of period | 2023-04-06 | April | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1091
2023-GD-12231 | GD1M | Comercial | 191.4 | Out of period | 2023-08-23 | August | 2023 |  |  | Anejar Certificacion e Instalacion | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 952
2023-GD-13731 | GD1M | Residencial | 40 | Out of period | 2023-05-22 | May | 2023 |  |  | Anejar Certificacion e Instalacion | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 1045
2023-GD-13846 | GD1M | Comercial | 48 | Out of period | 2023-05-23 | May | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1044
2023-GD-16766 | GD1M | Residencial | 86.4 | Out of period | 2023-06-08 | June | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1028
2023-GD-19982 | GD1M | Comercial | 720 | Out of period | 2023-07-12 | July | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 994
2023-GD-22432 | GD1M | Comercial | 112 | Out of period | 2023-07-31 | July | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 975
2023-GD-22734 | GD1M | Comercial | 132 | Out of period | 2023-07-12 | July | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 994
2023-GD-25009 | GD1M | Comercial | 450 | Out of period | 2023-08-15 | August | 2023 |  |  | Anejar Documentos | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 960
2023-GD-26563 | GD1M | Comercial | 393.6 | Out of period | 2023-07-28 | July | 2023 |  |  | Anejar Certificacion e Instalacion | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 978
2023-GD-28508 | GD1M | Comercial | 36.58 | Out of period | 2023-06-01 | June | 2023 |  |  | Anejar Certificacion e Instalacion | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1035
2023-GD-30187 | GD1M | Comercial | 26.72 | Out of period | 2023-09-19 | September | 2023 |  |  | Anejar Documentos, Asignar Inspector | Aprobación Comercial (A) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 925
2023-GD-05502 | GD1M | Comercial | 50 | Out of period | 2023-02-22 | February | 2023 | 2026-01-26 | 1069 | endevent3 | Aprobados Portal | Activated | [5 empty] | ARECIBO | January |  | 183 | 886 | 2026-04-01 | 1134
2022-GD-10340 | GD1M | Comercial | 27.7 | Out of period | 2022-06-02 | June | 2022 | 2026-01-22 | 1330 | endevent3 | Aprobados Portal | Activated | [5 empty] | SAN JUAN | January |  | 268 | 1062 | 2026-04-01 | 1399
2023-GD-34279 | GD1M | Residencial | 30 | Out of period | 2022-08-08 | August | 2023 | 2026-02-16 | 1288 | endevent3 | Aprobados Portal | Activated | [5 empty] | ARECIBO | February |  | 771 | 517 | 2026-04-01 | 1332
2023-GD-39199 | GD1M | Comercial | 26.72 | Out of period | 2024-01-24 | January | 2023 | 2026-02-16 | 754 | endevent3 | Aprobados Portal | Activated | [5 empty] | SAN JUAN | February |  | 120 | 634 | 2026-04-01 | 798
2025-GD-00045 | GD1M | Comercial | 189 | Out of period | 2025-02-24 | February | 2025 | 2026-01-20 | 330 | endevent3 | Aprobados Portal | Activated | [5 empty] | SAN JUAN | January |  | 169 | 161 | 2026-04-01 | 401
2025-GD-00055 | GD1M | Comercial | 46 | Out of period | 2025-03-04 | March | 2025 | 2026-01-22 | 324 | endevent3 | Aprobados Portal | Activated | [5 empty] | CAROLINA | January |  | 169 | 155 | 2026-04-01 | 393
2017-GD-02929 | GDL17 | Residencial | 3.225 | Out of period | 2023-05-16 | May | 2023 |  |  | approvedDistributionEndEvent | Validación (V) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1051
2017-GD-03620 | GDL17 | Residencial | 4.085 | Out of period | 2017-07-28 | July | 2017 |  |  | approvedDistributionEndEvent | Validación (V) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 3169
2017-GD-03887 | GDL17 | Residencial | 3.225 | Out of period | 2017-08-31 | August | 2017 |  |  | approvedDistributionEndEvent | Validación (V) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 3135
2021-GD-05583 | GDL17 | Residencial | 9.6 | Out of period | 2021-04-19 | April | 2021 |  |  | Completar Información Adicional | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1808
2022-GD-03238 | GDL17 | Residencial | 5 | Out of period | 2023-08-14 | August | 2023 |  |  | Completar Información Adicional, Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 961
2022-GD-03500 | GDL17 | Residencial | 5 | Out of period | 2022-02-28 | February | 2022 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1493
2022-GD-11695 | GDL17 | Residencial | 9.15 | Out of period | 2022-06-15 | June | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 1386
2022-GD-11824 | GDL17 | Residencial | 5 | Out of period | 2022-06-21 | June | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1380
2022-GD-13151 | GDL17 | Residencial | 24.89 | Out of period | 2022-06-30 | June | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 1371
2022-GD-13688 | GDL17 | Residencial | 8.42 | Out of period | 2022-07-12 | July | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1359
2022-GD-14851 | GDL17 | Residencial | 4.03 | Out of period | 2022-07-21 | July | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1350
2022-GD-16788 | GDL17 | Residencial | 5.49 | Out of period | 2023-10-07 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 907
2022-GD-17304 | GDL17 | Residencial | 4.39 | Out of period | 2022-08-15 | August | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 1325
2022-GD-20570 | GDL17 | Residencial | 5.12 | Out of period | 2022-09-06 | September | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1303
2022-GD-21209 | GDL17 | Residencial | 6.95 | Out of period | 2022-09-09 | September | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1300
2022-GD-21425 | GDL17 | Comercial | 3.2 | Out of period | 2022-09-14 | September | 2022 |  |  | Completar Información Adicional, Validación | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1295
2022-GD-23783 | GDL17 | Residencial | 3.29 | Out of period | 2022-10-06 | October | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1273
2022-GD-24162 | GDL17 | Comercial | 5.12 | Out of period | 2022-10-12 | October | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1267
2022-GD-24725 | GDL17 | Comercial | 9.88 | Out of period | 2022-10-14 | October | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 1265
2022-GD-25626 | GDL17 | Comercial | 8.85 | Out of period | 2022-10-24 | October | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1255
2022-GD-27223 | GDL17 | Residencial | 6 | Out of period | 2022-11-10 | November | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1238
2022-GD-27562 | GDL17 | Residencial | 4.15 | Out of period | 2022-11-11 | November | 2022 |  |  | Validación | Validación (V) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1237
2022-GD-27941 | GDL17 | Residencial | 9.6 | Out of period | 2023-09-06 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 938
2022-GD-29026 | GDL17 | Residencial | 13.91 | Out of period | 2023-10-27 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 887
2022-GD-29541 | GDL17 | Residencial | 6.8 | Out of period | 2023-10-17 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 897
2022-GD-30764 | GDL17 | Residencial | 4.03 | Out of period | 2022-12-09 | December | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1209
2022-GD-31226 | GDL17 | Residencial | 5.9 | Out of period | 2022-12-14 | December | 2022 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1204
2022-GD-32004 | GDL17 | Residencial | 4.03 | Out of period | 2022-12-21 | December | 2022 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 1197
202311-NM25-00543 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-16 11:38 | November | 2023 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 867
2025-GD-00042 | GD10K | Residencial | 21.54 | Out of period | 2025-02-19 | February | 2025 |  |  | Cancelled | Cancelled | Cancelled | [5 empty] | ARECIBO |  |  |  |  | 2026-04-01 | 406
202312-NM25-00186 | GDL17 | Residencial | 2.36 | Out of period | 2024-01-16 07:29 | January | 2024 |  |  | Create NEM Agreement | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 806
202312-NM25-00695 | GDL17 | Residencial | 7.6 | Out of period | 2024-02-20 11:58 | February | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 771
202312-NM25-00996 | GDL17 | Residencial | 7.6 | Out of period | 2024-05-01 11:15 | May | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 700
202312-NM25-01565 | GDL17 | Residencial | 4.758 | Out of period | 2023-12-14 10:57 | December | 2023 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 839
202312-NM25-01575 | GDL17 | Residencial | 2.36 | Out of period | 2024-01-25 11:53 | January | 2024 |  |  | Document Submission | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 797
202312-NM25-02124 | GDL17 | Residencial | 3.3 | Out of period | 2024-01-18 11:10 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 804
2025-GD-00086 | TRANSMISSION | Industrial | 0 | Out of period | 2025-05-14 | May | 2025 |  |  | Cancelled | Cancelled | Cancelled | [5 empty] | Bayamon |  |  |  |  | 2026-04-01 | 322
202312-NM25-02570 | GDL17 | Residencial | 6 | Out of period | 2025-01-07 16:21 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 448
202312-NM25-02844 | GDL17 | Residencial | 8 | Out of period | 2024-06-06 06:56 | June | 2024 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 664
202312-NM25-02908 | GDL17 | Residencial | 4.8 | Out of period | 2024-02-20 11:03 | February | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 771
202312-NM25-03346 | GDL17 | Residencial | 2.36 | Out of period | 2024-01-09 08:29 | January | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 813
202312-NM25-03409 | GDL17 | Residencial | 7.6 | Out of period | 2023-12-26 19:39 | December | 2023 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 826
2023-GD-00090 | GDL17 | Residencial | 4.03 | Out of period | 2022-12-30 | December | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1188
2023-GD-03528 | GDL17 | Residencial | 6.95 | Out of period | 2023-11-27 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 856
2023-GD-04435 | GDL17 | Residencial | 9.6 | Out of period | 2023-02-09 | February | 2023 |  |  | Completar Información Adicional | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAROLINA |  |  |  |  | 2026-04-01 | 1147
2023-GD-05898 | GDL17 | Residencial | 5.12 | Out of period | 2023-02-27 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1129
2023-GD-07077 | GDL17 | Comercial | 9.22 | Out of period | 2023-03-10 | March | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 1118
2023-GD-07368 | GDL17 | Residencial | 2.93 | Out of period | 2023-03-14 | March | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1114
2023-GD-09455 | GDL17 | Comercial | 5.76 | Out of period | 2023-03-31 | March | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1097
2023-GD-09705 | GDL17 | Residencial | 11.14 | Out of period | 2023-05-19 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1048
2023-GD-10011 | GDL17 | Residencial | 3.8 | Out of period | 2023-04-21 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1076
2023-GD-10059 | GDL17 | Residencial | 5 | Out of period | 2023-05-12 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1055
2023-GD-10113 | GDL17 | Residencial | 5 | Out of period | 2023-04-21 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1076
2023-GD-10760 | GDL17 | Residencial | 4.03 | Out of period | 2023-05-08 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1059
2023-GD-10822 | GDL17 | Residencial | 7.6 | Out of period | 2023-05-19 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1048
2023-GD-11222 | GDL17 | Residencial | 5 | Out of period | 2023-10-20 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 894
2023-GD-11223 | GDL17 | Residencial | 4.5 | Out of period | 2023-04-14 | April | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1083
2023-GD-11389 | GDL17 | Residencial | 3.63 | Out of period | 2023-05-26 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1041
2023-GD-11522 | GDL17 | Residencial | 5 | Out of period | 2023-05-17 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1050
2023-GD-11536 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-28 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 916
2023-GD-11951 | GDL17 | Residencial | 3 | Out of period | 2023-04-25 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1072
2023-GD-12366 | GDL17 | Residencial | 3.84 | Out of period | 2023-04-17 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1080
2023-GD-08827 | GD1M | Comercial | 99.9 | Out of period | 2023-03-27 | March | 2023 |  |  | approvedDistributionEndEvent | Endoso | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1101
2025-GD-00039 | GD1M | Comercial | 103.3 | Out of period | 2025-02-05 | February | 2025 |  |  | Referido a Proteccion | Endoso | Backlog |  |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 420
2024-GD-00293 | TRANSMISSION | Comercial | 0 | Out of period | 2024-12-10 | December | 2024 |  |  | approveTransmissionEnd | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 477
2023-GD-12622 | GDL17 | Residencial | 7.6 | Out of period | 2023-04-25 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1072
2023-GD-12789 | GDL17 | Residencial | 5 | Out of period | 2023-04-28 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1069
2023-GD-12960 | GDL17 | Residencial | 5 | Out of period | 2023-08-01 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 974
2023-GD-13088 | GDL17 | Residencial | 5 | Out of period | 2023-04-24 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1073
2023-GD-13144 | GDL17 | Residencial | 5 | Out of period | 2023-04-14 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1083
2023-GD-13635 | GDL17 | Residencial | 5 | Out of period | 2023-04-04 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1093
2023-GD-13655 | GDL17 | Residencial | 8 | Out of period | 2023-05-22 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1045
2023-GD-13759 | GDL17 | Residencial | 5 | Out of period | 2023-04-20 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 1077
2023-GD-13776 | GDL17 | Residencial | 5 | Out of period | 2023-05-03 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1064
2023-GD-14082 | GDL17 | Residencial | 5 | Out of period | 2023-05-03 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1064
2023-GD-14164 | GDL17 | Residencial | 7.6 | Out of period | 2023-04-04 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1093
2023-GD-05761 | GD1M | Comercial | 64.85 | Out of period | 2023-02-24 | February | 2023 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1132
2022-GD-10922 | GD1M | Comercial | 110.3 | Out of period | 2022-06-06 | June | 2022 |  |  | Asignar Inspector | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1395
2023-GD-10874 | GD1M | Comercial | 53 | Out of period | 2023-04-20 | April | 2023 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1077
2023-GD-14241 | GDL17 | Residencial | 7.6 | Out of period | 2023-05-26 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1041
2023-GD-14270 | GDL17 | Residencial | 5 | Out of period | 2023-04-26 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1071
2023-GD-13148 | TRANSMISSION | Comercial | 858 | Out of period | 2023-08-01 | August | 2023 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 974
2023-GD-16803 | TRANSMISSION | Comercial | 225 | Out of period | 2023-09-19 | September | 2023 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 925
2023-GD-17075 | TRANSMISSION | Industrial | 0 | Out of period | 2023-09-01 | September | 2023 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 943
2023-GD-26331 | GD1M | Residencial | 38 | Out of period | 2023-07-25 | July | 2023 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 981
2024-GD-00050 | GD1M | Comercial | 462 | Out of period | 2024-01-27 | January | 2024 |  |  | Estudio | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 795
2024-GD-00136 | GD1M | Comercial | 26.72 | Out of period | 2024-03-11 | March | 2024 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 751
2023-GD-14292 | GDL17 | Residencial | 5 | Out of period | 2023-05-09 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 1058
2023-GD-14718 | GDL17 | Residencial | 15.2 | Out of period | 2023-10-20 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 894
2023-GD-14745 | GDL17 | Residencial | 5 | Out of period | 2023-04-28 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1069
2023-GD-14785 | GDL17 | Residencial | 7.6 | Out of period | 2023-05-10 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 1057
2024-GD-00173 | GD1M | Comercial | 27.45 | Out of period | 2024-04-17 | April | 2024 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 714
2024-GD-00197 | GD1M | Residencial | 36.6 | Out of period | 2024-05-27 | May | 2024 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 674
2023-GD-14861 | GDL17 | Residencial | 5 | Out of period | 2023-05-17 | May | 2023 |  |  | Cambio de Cliente | Cancelled | Cancelled | Cancelled |  |  |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 1050
2023-GD-15232 | GDL17 | Residencial | 5 | Out of period | 2023-04-28 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1069
2023-GD-15382 | GDL17 | Residencial | 7.6 | Out of period | 2023-05-17 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1050
2023-GD-15786 | GDL17 | Residencial | 5 | Out of period | 2023-06-02 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1034
2023-GD-15862 | GDL17 | Residencial | 5 | Out of period | 2023-06-13 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1023
2023-GD-16153 | GDL17 | Residencial | 7.6 | Out of period | 2023-06-09 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1027
2023-GD-16247 | GDL17 | Residencial | 5 | Out of period | 2023-06-19 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1017
2023-GD-16393 | GDL17 | Residencial | 5 | Out of period | 2023-06-16 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1020
2023-GD-16411 | GDL17 | Residencial | 5 | Out of period | 2023-06-15 | June | 2023 |  |  | Completar Información Adicional, Validación | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1021
2023-GD-16624 | GDL17 | Residencial | 15.2 | Out of period | 2023-06-14 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 1022
2023-GD-16922 | GDL17 | Residencial | 7.6 | Out of period | 2023-06-12 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1024
2023-GD-16987 | GDL17 | Residencial | 11.4 | Out of period | 2023-09-01 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 943
2023-GD-17115 | GDL17 | Residencial | 7.6 | Out of period | 2023-06-30 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1006
2023-GD-17153 | GDL17 | Residencial | 8 | Out of period | 2023-07-27 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 979
2023-GD-17237 | GDL17 | Residencial | 4.03 | Out of period | 2023-06-15 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 1021
2023-GD-17263 | GDL17 | Residencial | 8 | Out of period | 2023-07-25 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 981
2023-GD-17289 | GDL17 | Residencial | 8 | Out of period | 2023-09-01 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 943
2023-GD-17317 | GDL17 | Residencial | 7.6 | Out of period | 2023-06-19 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 1017
2023-GD-17491 | GDL17 | Residencial | 8 | Out of period | 2023-06-28 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1008
2023-GD-17515 | GDL17 | Residencial | 8 | Out of period | 2023-06-26 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1010
2023-GD-17596 | GDL17 | Residencial | 5 | Out of period | 2023-06-06 | June | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1030
2023-GD-17826 | GDL17 | Residencial | 7.6 | Out of period | 2023-06-11 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1025
2023-GD-18164 | GDL17 | Residencial | 8.78 | Out of period | 2023-09-14 | September | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 930
2023-GD-18592 | GDL17 | Residencial | 6 | Out of period | 2023-06-20 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1016
2023-GD-18698 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-03 | July | 2023 |  |  | Cambio de Cliente | Cancelled | Cancelled | Cancelled |  |  |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 1003
2023-GD-18938 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-05 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1001
2023-GD-18957 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-05 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1001
2023-GD-19209 | GDL17 | Residencial | 3 | Out of period | 2023-09-11 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 933
2023-GD-19389 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-12 | September | 2023 |  |  | Completar Información Adicional, Validación | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 932
2023-GD-19785 | GDL17 | Residencial | 8 | Out of period | 2023-07-11 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 995
2023-GD-19963 | GDL17 | Residencial | 8 | Out of period | 2023-08-03 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 972
2023-GD-19989 | GDL17 | Residencial | 8 | Out of period | 2023-07-12 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 994
2022-GD-04339 | GD1M | Residencial | 45.6 | Out of period | 2022-03-07 | March | 2022 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 1486
2023-GD-37692 | TRANSMISSION | Industrial | 2875 | Out of period | 2023-12-11 | December | 2023 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 842
2024-GD-00207 | TRANSMISSION | Comercial | 437 | Out of period | 2024-06-03 | June | 2024 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 667
2024-GD-00211 | TRANSMISSION | Comercial | 482.3 | Out of period | 2024-06-08 | June | 2024 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 662
2023-GD-20031 | GDL17 | Residencial | 3.66 | Out of period | 2023-07-12 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 994
2023-GD-20196 | GDL17 | Residencial | 5 | Out of period | 2023-07-13 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 993
2023-GD-20276 | GDL17 | Residencial | 8 | Out of period | 2023-08-02 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 973
2023-GD-20387 | GDL17 | Residencial | 5 | Out of period | 2023-07-17 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 989
2023-GD-20472 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-29 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 915
2023-GD-20486 | GDL17 | Residencial | 5 | Out of period | 2023-07-26 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 980
2023-GD-20530 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-14 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 961
2023-GD-20606 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-13 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 993
2023-GD-20671 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-17 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 989
2024-GD-00295 | GD1M | Residencial | 45 | Out of period | 2024-12-17 | December | 2024 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Bayamon |  |  |  |  | 2026-04-01 | 470
2023-GD-20795 | GDL17 | Residencial | 8 | Out of period | 2023-07-18 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 988
2023-GD-21064 | GDL17 | Residencial | 8 | Out of period | 2023-07-20 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 986
2023-GD-21230 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-20 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 986
2023-GD-21251 | GDL17 | Residencial | 5 | Out of period | 2023-09-19 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 925
2023-GD-21314 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-21 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 985
2023-GD-21928 | GDL17 | Residencial | 5 | Out of period | 2023-07-14 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-22011 | GDL17 | Residencial | 3.66 | Out of period | 2023-07-14 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-22093 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-26 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 980
2023-GD-22099 | GDL17 | Residencial | 6.95 | Out of period | 2023-07-14 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-22148 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-27 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 979
2023-GD-22157 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-14 | July | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-22273 | GDL17 | Residencial | 4.03 | Out of period | 2023-07-27 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 979
2023-GD-22363 | GDL17 | Residencial | 3.84 | Out of period | 2023-07-28 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 978
2023-GD-22603 | GDL17 | Residencial | 5 | Out of period | 2023-08-03 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 972
2023-GD-22664 | GDL17 | Residencial | 4.39 | Out of period | 2023-08-03 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 972
2023-GD-22862 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-31 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 975
2023-GD-22874 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-01 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 974
2023-GD-22890 | GDL17 | Residencial | 5 | Out of period | 2023-08-01 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 974
2023-GD-22893 | GDL17 | Residencial | 8 | Out of period | 2023-08-15 | August | 2023 |  |  | Completar Información Adicional | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 960
2023-GD-23020 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-12 | September | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 932
2023-GD-23264 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-02 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 973
2022-GD-20943 | GD10K | Residencial | 4.43 | Out of period | 2022-09-08 | September | 2022 |  |  | Estudio | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1301
2023-GD-23348 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-02 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 973
2023-GD-23425 | GDL17 | Residencial | 7.6 | Out of period | 2023-06-20 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1016
2023-GD-23432 | GDL17 | Residencial | 8 | Out of period | 2023-06-20 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1016
2023-GD-23434 | GDL17 | Residencial | 7.6 | Out of period | 2023-06-20 | June | 2023 |  |  | Completar Información Adicional, Validación | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1016
2023-GD-23535 | GDL17 | Residencial | 19 | Out of period | 2023-08-03 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 972
2023-GD-23562 | GDL17 | Comercial | 23.6 | Out of period | 2023-08-03 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 972
2023-GD-23604 | GDL17 | Residencial | 8 | Out of period | 2023-08-04 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 971
2023-GD-23657 | GDL17 | Residencial | 4.39 | Out of period | 2023-06-19 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1017
2023-GD-23746 | GDL17 | Residencial | 5 | Out of period | 2023-08-07 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 968
2023-GD-24028 | GDL17 | Residencial | 8 | Out of period | 2023-08-08 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 967
2023-GD-24175 | GDL17 | Residencial | 8 | Out of period | 2023-08-16 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 959
2023-GD-24364 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-16 | August | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 959
2023-GD-24484 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-10 | August | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 965
2023-GD-24491 | GDL17 | Residencial | 7.68 | Out of period | 2023-08-11 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 964
2023-GD-24567 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-14 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-25038 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-15 | August | 2023 |  |  | Validación, Validación Técnica | Validación (V) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 960
2023-GD-25191 | GDL17 | Residencial | 8 | Out of period | 2023-08-16 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 959
2023-GD-25273 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-03 | August | 2023 |  |  | Completar Información Adicional, Validación | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 972
2023-GD-25348 | GDL17 | Residencial | 8 | Out of period | 2023-08-16 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 959
2023-GD-25379 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-31 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 975
2023-GD-25445 | GDL17 | Residencial | 8 | Out of period | 2023-06-12 | June | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1024
2023-GD-25567 | GDL17 | Residencial | 3.8 | Out of period | 2023-08-18 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 957
2023-GD-25688 | GDL17 | Residencial | 5 | Out of period | 2023-07-16 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 990
2023-GD-25725 | GDL17 | Residencial | 4.39 | Out of period | 2023-08-18 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 957
2023-GD-25737 | GDL17 | Comercial | 24.78 | Out of period | 2023-08-18 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 957
2023-GD-25894 | GDL17 | Residencial | 7.6 | Out of period | 2023-08-21 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 954
2023-GD-25980 | GDL17 | Residencial | 2.66 | Out of period | 2023-08-21 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 954
2023-GD-26228 | GDL17 | Residencial | 8 | Out of period | 2023-08-22 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 953
2023-GD-26321 | GDL17 | Residencial | 8 | Out of period | 2023-08-23 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 952
2023-GD-26937 | GDL17 | Residencial | 3.8 | Out of period | 2023-08-30 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 945
2023-GD-26990 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-07 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 999
2023-GD-27250 | GDL17 | Residencial | 5 | Out of period | 2023-09-01 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 943
2023-GD-27304 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-01 | September | 2023 |  |  | Completar Información Adicional, Validación | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 943
2023-GD-27441 | GDL17 | Comercial | 15.2 | Out of period | 2023-09-01 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 943
2023-GD-27503 | GDL17 | Residencial | 11.35 | Out of period | 2023-07-25 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 981
2023-GD-27912 | GDL17 | Residencial | 8 | Out of period | 2023-07-17 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 989
2023-GD-27952 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-14 | July | 2023 |  |  | Completar Información Adicional, Validación Técnica | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-27973 | GDL17 | Residencial | 12 | Out of period | 2023-09-05 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 939
2023-GD-28024 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-14 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-28163 | GDL17 | Residencial | 7.6 | Out of period | 2023-07-14 | July | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-28186 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-06 | September | 2023 |  |  | Completar Información Adicional, Validación | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 938
2023-GD-28194 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-06 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 938
2023-GD-28200 | GDL17 | Residencial | 7.6 | Out of period | 2023-04-21 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1076
2023-GD-28680 | GDL17 | Residencial | 6 | Out of period | 2023-09-08 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 936
2023-GD-28691 | GDL17 | Comercial | 20 | Out of period | 2023-05-26 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1041
2023-GD-28893 | GDL17 | Residencial | 7.6 | Out of period | 2023-05-11 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1056
2023-GD-29068 | GDL17 | Residencial | 8 | Out of period | 2023-05-31 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1036
2023-GD-29086 | GDL17 | Residencial | 7.6 | Out of period | 2023-05-04 | May | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1063
2023-GD-29176 | GDL17 | Residencial | 6 | Out of period | 2023-09-12 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 932
2023-GD-29208 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-13 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 931
2023-GD-29252 | GDL17 | Residencial | 8 | Out of period | 2023-09-13 | September | 2023 |  |  | Validación, Validación Técnica | Validación (V) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 931
2023-GD-29256 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-13 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 931
2023-GD-29295 | GDL17 | Residencial | 8 | Out of period | 2023-09-13 | September | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 931
2023-GD-29667 | GDL17 | Residencial | 7.6 | Out of period | 2023-04-14 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1083
2023-GD-29695 | GDL17 | Residencial | 5.5 | Out of period | 2023-04-12 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1085
2023-GD-29781 | GDL17 | Residencial | 15.2 | Out of period | 2023-09-15 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 929
2023-GD-29786 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-15 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 929
2023-GD-29858 | GDL17 | Residencial | 7.6 | Out of period | 2023-04-07 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1090
2023-GD-29963 | GDL17 | Residencial | 7.6 | Out of period | 2023-04-06 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1091
2023-GD-30010 | GDL17 | Residencial | 7.6 | Out of period | 2023-05-01 | May | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1066
2023-GD-30210 | GDL17 | Residencial | 10 | Out of period | 2023-03-30 | March | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1098
2023-GD-30266 | GDL17 | Residencial | 7.6 | Out of period | 2023-01-25 | January | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1162
2023-GD-30403 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-20 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 924
2023-GD-30443 | GDL17 | Residencial | 22.66 | Out of period | 2023-09-20 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 924
2023-GD-30585 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-21 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 923
2023-GD-30610 | GDL17 | Comercial | 20.4 | Out of period | 2023-09-21 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 923
2023-GD-30739 | GDL17 | Residencial | 4.03 | Out of period | 2023-09-21 | September | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 923
2023-GD-30744 | GDL17 | Residencial | 7.6 | Out of period | 2023-03-17 | March | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1111
2023-GD-30839 | GDL17 | Residencial | 7.6 | Out of period | 2023-02-28 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1128
2023-GD-30861 | GDL17 | Residencial | 6 | Out of period | 2023-09-26 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 918
2023-GD-30864 | GDL17 | Residencial | 3.66 | Out of period | 2023-09-26 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 918
2023-GD-30949 | GDL17 | Residencial | 13.91 | Out of period | 2023-09-26 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 918
2023-GD-31002 | GDL17 | Residencial | 11.35 | Out of period | 2023-09-26 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 918
2023-GD-31028 | GDL17 | Comercial | 7.6 | Out of period | 2023-09-26 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 918
2023-GD-31057 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-27 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 917
2023-GD-31063 | GDL17 | Residencial | 8 | Out of period | 2023-02-16 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1140
2023-GD-31095 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-27 | September | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 917
2023-GD-31184 | GDL17 | Residencial | 8 | Out of period | 2023-09-27 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 917
2023-GD-31215 | GDL17 | Residencial | 7.6 | Out of period | 2023-09-27 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 917
2023-GD-31622 | GDL17 | Residencial | 9 | Out of period | 2023-02-02 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1154
2022-GD-05734 | GD10K | Residencial | 6.8 | Out of period | 2022-03-30 | March | 2022 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1463
2023-GD-31725 | GDL17 | Residencial | 8 | Out of period | 2023-10-23 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 891
2023-GD-31942 | GDL17 | Residencial | 7.6 | Out of period | 2022-11-23 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1225
2023-GD-32142 | GDL17 | Residencial | 18 | Out of period | 2023-10-24 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 890
2023-GD-32249 | GDL17 | Comercial | 5.61 | Out of period | 2023-10-25 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 889
2023-GD-32265 | GDL17 | Residencial | 6 | Out of period | 2023-10-25 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 889
2023-GD-32336 | GDL17 | Residencial | 8 | Out of period | 2023-10-26 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 888
2023-GD-32389 | GDL17 | Residencial | 7.6 | Out of period | 2023-10-26 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 888
2023-GD-32415 | GDL17 | Residencial | 8 | Out of period | 2023-10-26 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 888
2023-GD-32482 | GDL17 | Residencial | 6 | Out of period | 2022-11-16 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1232
2023-GD-32557 | GDL17 | Residencial | 7.6 | Out of period | 2023-10-27 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 887
2023-GD-32975 | GDL17 | Residencial | 8.26 | Out of period | 2023-10-30 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 884
2023-GD-33115 | GDL17 | Residencial | 7.6 | Out of period | 2023-10-30 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 884
2023-GD-33198 | GDL17 | Residencial | 8 | Out of period | 2023-10-31 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 883
2023-GD-33228 | GDL17 | Residencial | 7.6 | Out of period | 2023-10-31 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 883
2023-GD-33433 | GDL17 | Residencial | 3.66 | Out of period | 2022-09-01 | September | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1308
2023-GD-33555 | GDL17 | Residencial | 8 | Out of period | 2023-11-02 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 881
2023-GD-33987 | GDL17 | Residencial | 8.35 | Out of period | 2022-08-22 | August | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 1318
2023-GD-34270 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-03 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 880
2023-GD-34441 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-06 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 877
2023-GD-34494 | GDL17 | Residencial | 3.8 | Out of period | 2023-11-07 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 876
2023-GD-34580 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-07 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 876
2023-GD-34631 | GDL17 | Residencial | 8.05 | Out of period | 2023-11-07 | November | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 876
2023-GD-34818 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-09 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 874
2023-GD-34909 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-09 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 874
2023-GD-35001 | GDL17 | Residencial | 4.03 | Out of period | 2023-11-09 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 874
2023-GD-35143 | GDL17 | Residencial | 9 | Out of period | 2023-11-10 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 873
2023-GD-35224 | GDL17 | Residencial | 3.8 | Out of period | 2023-11-13 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 870
2023-GD-35241 | GDL17 | Comercial | 7.6 | Out of period | 2023-11-13 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 870
2023-GD-35426 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-14 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 869
2023-GD-35482 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-15 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 868
2023-GD-35573 | GDL17 | Residencial | 8 | Out of period | 2023-11-15 | November | 2023 |  |  | Validación, Validación Técnica | Validación (V) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 868
2023-GD-35591 | GDL17 | Residencial | 8 | Out of period | 2023-11-15 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 868
2023-GD-35595 | GDL17 | Residencial | 10.98 | Out of period | 2023-11-15 | November | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 868
2023-GD-35607 | GDL17 | Residencial | 3.66 | Out of period | 2023-11-15 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 868
2023-GD-35826 | GDL17 | Residencial | 8 | Out of period | 2023-11-17 | November | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 866
2023-GD-35828 | GDL17 | Residencial | 6 | Out of period | 2023-11-17 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 866
2023-GD-35831 | GDL17 | Residencial | 8 | Out of period | 2023-11-17 | November | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 866
2023-GD-35960 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-20 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 863
2023-GD-35963 | GDL17 | Residencial | 8 | Out of period | 2023-11-20 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 863
2023-GD-36145 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-21 | November | 2023 |  |  | Cambio de Cliente | Cancelled | Cancelled | Cancelled |  |  |  |  | PONCE |  |  |  |  | 2026-04-01 | 862
2023-GD-36233 | GDL17 | Residencial | 3.66 | Out of period | 2023-11-21 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 862
2023-GD-36258 | GDL17 | Residencial | 6 | Out of period | 2023-11-21 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 862
2023-GD-36450 | GDL17 | Residencial | 3.66 | Out of period | 2023-11-24 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 859
2023-GD-36574 | GDL17 | Residencial | 7.6 | Out of period | 2022-01-14 | January | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 1538
2023-GD-36576 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-25 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 858
2023-GD-36776 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-28 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 855
2023-GD-36884 | GDL17 | Residencial | 10.61 | Out of period | 2023-11-28 | November | 2023 |  |  | Cambio de Cliente | Cancelled | Cancelled | Cancelled |  |  |  |  | CAROLINA |  |  |  |  | 2026-04-01 | 855
2023-GD-36920 | GDL17 | Residencial | 5.28 | Out of period | 2023-11-28 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 855
2023-GD-37122 | GDL17 | Residencial | 8 | Out of period | 2023-11-29 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 854
2023-GD-37185 | GDL17 | Residencial | 4.03 | Out of period | 2023-11-30 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 853
2023-GD-37433 | GDL17 | Residencial | 7.6 | Out of period | 2023-11-30 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 853
2023-GD-37532 | GDL17 | Residencial | 7.6 | Out of period | 2020-10-09 | October | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 2000
2023-GD-37548 | GDL17 | Residencial | 8 | Out of period | 2023-11-30 | November | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 853
2023-GD-37619 | GDL17 | Comercial | 7.6 | Out of period | 2023-12-01 | December | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 852
2023-GD-37688 | GDL17 | Residencial | 7.6 | Out of period | 2023-12-11 | December | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 842
2023-GD-37800 | GDL17 | Residencial | 3.66 | Out of period | 2023-12-12 | December | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 841
2023-GD-37843 | GDL17 | Residencial | 7.6 | Out of period | 2023-12-18 | December | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 835
2023-GD-37906 | GDL17 | Residencial | 7.6 | Out of period | 2023-12-28 | December | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 825
2023-GD-38032 | GDL17 | Residencial | 7.6 | Out of period | 2024-03-11 | March | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 751
2023-GD-38079 | GDL17 | Residencial | 7.6 | Out of period | 2024-02-23 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 768
2023-GD-38087 | GDL17 | Residencial | 4.39 | Out of period | 2024-01-27 | January | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 795
2023-GD-38091 | GDL17 | Residencial | 8 | Out of period | 2024-03-25 | March | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 737
2023-GD-38147 | GDL17 | Residencial | 9.52 | Out of period | 2024-02-19 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 772
2023-GD-38202 | GDL17 | Comercial | 15 | Out of period | 2024-01-23 | January | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 799
2023-GD-38237 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-16 | January | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 806
2023-GD-38400 | GDL17 | Residencial | 8.05 | Out of period | 2024-02-21 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 770
2023-GD-38450 | GDL17 | Residencial | 3.8 | Out of period | 2024-02-27 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 764
2023-GD-38503 | GDL17 | Residencial | 8 | Out of period | 2024-01-17 | January | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 805
2023-GD-38588 | GDL17 | Residencial | 6.8 | Out of period | 2024-02-05 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 786
2023-GD-38841 | GDL17 | Residencial | 4.95 | Out of period | 2024-01-17 | January | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 805
2023-GD-38975 | GDL17 | Residencial | 10.98 | Out of period | 2024-01-27 | January | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 795
2023-GD-39099 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-27 | January | 2023 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 795
2023-GD-39135 | GDL17 | Residencial | 2.95 | Out of period | 2024-01-27 | January | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 795
2023-GD-39146 | GDL17 | Residencial | 4.5 | Out of period | 2024-02-12 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 779
2023-GD-39171 | GDL17 | Residencial | 4.39 | Out of period | 2024-02-05 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 786
2023-GD-39299 | GDL17 | Residencial | 7.6 | Out of period | 2024-02-23 | February | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 768
2023-GD-39407 | GDL17 | Residencial | 8 | Out of period | 2023-12-18 | December | 2023 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 835
202401-NM25-00064 | GDL17 | Residencial | 6.8 | Out of period | 2024-06-21 11:03 | June | 2024 |  |  | NM Enter Technical Info | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 649
202401-NM25-00104 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-03 08:17 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 819
202401-NM25-00153 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-23 14:00 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 798
202401-NM25-00373 | GDL17 | Residencial | 8.7 | Out of period | 2024-07-03 19:09 | July | 2024 | 2026-02-18 10:13 | 595 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | February |  | 595 | 57 | 2026-04-01 | 636
202401-NM25-00396 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-05 05:04 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 817
202401-NM25-00421 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-05 11:35 | January | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 817
202401-NM25-00428 | GDL17 | Residencial | 12.9 | Out of period | 2024-04-30 07:37 | April | 2024 |  |  | NM Abandoned Renewable Task | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 701
202401-NM25-00431 | GDL17 | Comercial | 11.712 | Out of period | 2024-01-05 07:03 | January | 2024 |  |  | Document Submission | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 817
202401-NM25-00464 | GDL17 | Residencial | 19.8 | Out of period | 2024-02-20 10:55 | February | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 771
202401-NM25-00667 | GDL17 | Comercial | 7.6 | Out of period | 2024-01-29 09:26 | January | 2024 | 2026-03-25 12:45 | 786 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | March | 2 | 45 | 741 | 2026-04-01 | 793
202401-NM25-01069 | GDL17 | Residencial | 7.6 | Out of period | 2024-02-06 19:08 | February | 2024 |  |  | NM Abandoned Renewable Task | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 784
202401-NM25-01288 | GDL17 | Residencial | 7.69 | Out of period | 2024-01-10 10:54 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 812
202401-NM25-01438 | GDL17 | Residencial | 8 | Out of period | 2024-02-13 06:45 | February | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 778
202401-NM25-01637 | GDL17 | Residencial | 8 | Out of period | 2024-07-01 11:06 | July | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 639
202401-NM25-02315 | GDL17 | Residencial | 11.4 | Period | 2026-01-20 19:21 | January | 2026 | 2026-01-29 15:24 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 9 | 0 | 2026-04-01 | 70
202401-NM25-02430 | GDL17 | Residencial | 8 | Out of period | 2024-01-18 05:37 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 804
202401-NM25-02499 | GDL17 | Residencial | 8.052 | Out of period | 2024-01-17 13:55 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 804
202401-NM25-02640 | GDL17 | Residencial | 7.32 | Out of period | 2024-01-18 07:48 | January | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 804
202401-NM25-02721 | GDL17 | Residencial | 7.6 | Out of period | 2024-06-07 17:01 | June | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 662
202401-NM25-02830 | GDL17 | Comercial | 17.28 | Out of period | 2024-01-18 10:56 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 804
202401-NM25-02992 | GDL17 | Residencial | 10 | Period | 2026-02-09 21:04 | February | 2026 | 2026-02-11 13:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 50
202401-NM25-03380 | GDL17 | Residencial | 6.8 | Out of period | 2024-04-11 13:51 | April | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 719
202401-NM25-03412 | GDL17 | Residencial | 8 | Out of period | 2024-02-13 07:37 | February | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 778
202401-NM25-03924 | GDL17 | Residencial | 7.6 | Out of period | 2024-02-02 09:34 | February | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 789
202401-NM25-03932 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-25 07:25 | January | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 797
202401-NM25-04223 | GDL17 | Residencial | 6 | Out of period | 2024-01-30 15:51 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 791
202401-NM25-04617 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-31 11:02 | January | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 791
202402-NM25-00438 | GDL17 | Residencial | 3.8 | Out of period | 2024-02-14 17:07 | February | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 776
202402-NM25-00841 | GDL17 | Residencial | 18 | Out of period | 2024-05-23 13:26 | May | 2024 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 677
202402-NM25-00879 | GDL17 | Residencial | 7.6 | Out of period | 2024-06-25 08:27 | June | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 645
202402-NM25-01199 | GDL17 | Residencial | 7.6 | Out of period | 2024-06-24 05:12 | June | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 646
202402-NM25-01486 | GDL17 | Residencial | 7.6 | Out of period | 2024-04-18 11:09 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 713
202402-NM25-03057 | GDL17 | Comercial | 14.64 | Out of period | 2024-02-20 13:07 | February | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 770
202402-NM25-03519 | GDL17 | Residencial | 7.6 | Out of period | 2024-05-15 05:26 | May | 2024 |  |  | NM Abandoned Renewable Task | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 686
202402-NM25-03839 | GDL17 | Residencial | 9.15 | Out of period | 2024-05-28 05:59 | May | 2024 |  |  | NM Abandoned Renewable Task | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 673
2024-GD-00275 | GD10K | Residencial | 7.6 | Out of period | 2024-10-17 | October | 2024 |  |  | Estudio | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Bayamon |  |  |  |  | 2026-04-01 | 531
202402-NM25-03903 | GDL17 | Residencial | 4.2 | Out of period | 2024-04-21 09:27 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 710
202402-NM25-03906 | GDL17 | Residencial | 10 | Out of period | 2025-11-07 10:04 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 145
202402-NM25-04193 | GDL17 | Residencial | 21.228 | Out of period | 2024-02-28 09:32 | February | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 763
202402-NM25-04265 | GDL17 | Residencial | 7.6 | Out of period | 2024-02-28 19:29 | February | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 762
202403-NM25-00556 | GDL17 | Residencial | 7.6 | Out of period | 2024-04-06 07:31 | April | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 725
202403-NM25-01873 | GDL17 | Residencial | 8 | Out of period | 2024-04-10 08:38 | April | 2024 |  |  | Document Submission | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 721
202403-NM25-01886 | GDL17 | Residencial | 7.6 | Out of period | 2024-04-25 12:15 | April | 2024 |  |  | Document Submission | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 705
202403-NM25-02389 | GDL17 | Residencial | 3.8 | Out of period | 2024-04-15 19:42 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 715
202403-NM25-02820 | GDL17 | Residencial | 8 | Out of period | 2024-06-26 10:35 | June | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 644
202403-NM25-03231 | GDL17 | Residencial | 7.6 | Out of period | 2024-04-04 17:53 | April | 2024 |  |  | Create NEM Agreement | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 726
202403-NM25-03386 | GDL17 | Residencial | 6.8 | Out of period | 2024-09-17 14:09 | September | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 560
202403-NM25-03739 | GDL17 | Residencial | 3.8 | Out of period | 2024-04-12 06:04 | April | 2024 |  |  | Create NEM Agreement | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 719
202404-NM25-00308 | GDL17 | Residencial | 6 | Period | 2026-01-30 09:30 | January | 2026 | 2026-02-10 09:25 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 61
202404-NM25-00349 | GDL17 | Residencial | 3.66 | Out of period | 2024-04-03 08:26 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 728
202404-NM25-01121 | GDL17 | Comercial | 23.424 | Out of period | 2024-05-01 11:46 | May | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 700
202404-NM25-01133 | GDL17 | Comercial | 3.54 | Out of period | 2024-04-10 04:50 | April | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 721
202404-NM25-01311 | GDL17 | Residencial | 5.49 | Out of period | 2024-04-10 08:35 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 721
202404-NM25-01645 | GDL17 | Residencial | 2.36 | Out of period | 2025-01-10 10:38 | January | 2025 |  |  | Customer Orientation Acknowledgement | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 446
202404-NM25-01754 | GDL17 | Residencial | 11.4 | Out of period | 2024-11-21 09:48 | November | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 511 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 496
202404-NM25-01764 | GDL17 | Residencial | 8 | Out of period | 2024-04-15 11:42 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 716
202404-NM25-02068 | GDL17 | Residencial | 15.2 | Out of period | 2024-08-29 07:06 | August | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 580
202404-NM25-02195 | GDL17 | Residencial | 5 | Out of period | 2024-04-29 11:34 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 702
2025-GD-00034 | TRANSMISSION | Comercial | 2044.3 | Out of period | 2025-01-23 | January | 2025 |  |  | approveTransmissionEnd | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 433
2025-GD-00032 | TRANSMISSION | Comercial | 780 | Out of period | 2025-01-15 | January | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 441
2025-GD-00037 | GD1M | Comercial | 132 | Out of period | 2025-01-30 | January | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 426
2025-GD-00030 | GD1M | Comercial | 31 | Out of period | 2025-01-09 | January | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 447
2025-GD-00031 | GD1M | Residencial | 45 | Out of period | 2025-01-14 | January | 2025 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 442
2025-GD-00035 | GD1M | Residencial | 30 | Out of period | 2025-01-23 | January | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 433
2025-GD-00036 | GD1M | Comercial | 63 | Out of period | 2025-01-24 | January | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 432
202404-NM25-02207 | GDL17 | Comercial | 16.104 | Out of period | 2024-04-16 07:01 | April | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 715
202404-NM25-02414 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-06 10:06 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 481
202404-NM25-02593 | GDL17 | Residencial | 8 | Out of period | 2024-04-18 05:51 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 713
202404-NM25-02731 | GDL17 | Residencial | 15.2 | Out of period | 2024-04-19 06:47 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 712
202404-NM25-03121 | GDL17 | Residencial | 3.8 | Out of period | 2024-05-30 04:03 | May | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 671
202404-NM25-03124 | GDL17 | Comercial | 14.52 | Out of period | 2024-04-22 13:15 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 708
202404-NM25-03635 | GDL17 | Residencial | 7.6 | Out of period | 2024-04-24 05:56 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 707
202404-NM25-03662 | GDL17 | Residencial | 8.418 | Out of period | 2024-04-24 07:02 | April | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 712 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 707
202404-NM25-03663 | GDL17 | Residencial | 3.8 | Out of period | 2024-10-09 11:08 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 539
202404-NM25-03696 | GDL17 | Comercial | 19.8 | Out of period | 2024-05-21 08:55 | May | 2024 | 2026-01-15 08:33 | 604 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 3 | 380 | 224 | 2026-04-01 | 680
202404-NM25-03884 | GDL17 | Residencial | 4.758 | Out of period | 2024-04-25 08:11 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 706
202404-NM25-04458 | GDL17 | Residencial | 7.6 | Out of period | 2024-05-02 21:00 | May | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 698
202404-NM25-04510 | GDL17 | Residencial | 4.392 | Out of period | 2024-04-30 07:22 | April | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 701
202405-NM25-00151 | GDL17 | Residencial | 3.66 | Out of period | 2024-05-01 13:21 | May | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 699
202405-NM25-00340 | GDL17 | Residencial | 3.63 | Out of period | 2024-05-09 14:30 | May | 2024 |  |  | NM Enter Technical Info | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 691
202405-NM25-00466 | GDL17 | Residencial | 8 | Out of period | 2024-05-03 11:07 | May | 2024 |  |  | NM Enter Technical Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 698
202405-NM25-00529 | GDL17 | Comercial | 14.64 | Out of period | 2024-05-17 12:59 | May | 2024 |  |  | NM Enter Technical Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 683
202405-NM25-00816 | GDL17 | Residencial | 7.26 | Out of period | 2024-05-07 10:25 | May | 2024 |  |  | Customer Orientation | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 694
202405-NM25-00837 | GDL17 | Residencial | 6.588 | Period | 2026-01-07 11:05 | January | 2026 | 2026-02-11 14:34 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 35 | 0 | 2026-04-01 | 84
202405-NM25-00845 | GDL17 | Residencial | 7.68 | Out of period | 2025-01-17 14:37 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 438
202405-NM25-00882 | GDL17 | Comercial | 12.444 | Out of period | 2024-05-28 11:31 | May | 2024 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 673
202405-NM25-00897 | GDL17 | Residencial | 3.8 | Out of period | 2024-09-15 18:11 | September | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 562
202405-NM25-01127 | GDL17 | Residencial | 7.6 | Out of period | 2024-05-23 09:16 | May | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 678
202405-NM25-01314 | GDL17 | Residencial | 7.6 | Out of period | 2024-05-17 12:25 | May | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 683
202405-NM25-01493 | GDL17 | Residencial | 4.606 | Out of period | 2024-05-11 10:16 | May | 2024 |  |  | NM Enter Technical Info | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 690
202405-NM25-01518 | GDL17 | Residencial | 7.6 | Out of period | 2024-07-24 08:47 | July | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 616
202405-NM25-01597 | GDL17 | Residencial | 6 | Period | 2026-02-24 14:38 | February | 2026 | 2026-02-27 09:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 35
202405-NM25-01877 | GDL17 | Comercial | 15.2 | Out of period | 2024-05-15 08:12 | May | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 686
2025-GD-00052 | GD1M | Comercial | 36 | Out of period | 2025-02-28 | February | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 397
2025-GD-00049 | GD1M | Comercial | 40 | Out of period | 2025-02-25 | February | 2025 |  |  | Pago Aportacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 400
2025-GD-00051 | GD1M | Comercial | 55 | Out of period | 2025-02-25 | February | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 400
2025-GD-00048 | GD1M | Comercial | 38 | Out of period | 2025-02-24 | February | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 401
2025-GD-00040 | GD1M | Comercial | 180 | Out of period | 2025-02-13 | February | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 412
2025-GD-00046 | GD1M | Comercial | 34 | Out of period | 2025-02-24 | February | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 401
2025-GD-00047 | GD1M | Comercial | 35 | Out of period | 2025-02-24 | February | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 401
2025-GD-00043 | GD1M | Comercial | 54 | Out of period | 2025-02-19 | February | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 406
2025-GD-00041 | GD1M | Comercial | 100 | Out of period | 2025-02-14 | February | 2025 |  |  | endevent2 | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 411
2025-GD-00050 | GD1M | Comercial | 28 | Out of period | 2025-02-25 | February | 2025 |  |  | Pago Aportacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 400
202405-NM25-02053 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:49 | March | 2026 | 2026-03-30 11:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 7
202405-NM25-02444 | GDL17 | Residencial | 3.8 | Period | 2026-02-06 09:56 | February | 2026 | 2026-02-17 10:05 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 54
202405-NM25-02574 | GDL17 | Residencial | 8 | Out of period | 2024-06-10 07:34 | June | 2024 |  |  | NM Enter Technical Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 660
202405-NM25-02636 | GDL17 | Residencial | 15 | Out of period | 2024-05-24 13:29 | May | 2024 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 676
202405-NM25-02753 | GDL17 | Residencial | 6.8 | Out of period | 2024-07-18 05:23 | July | 2024 |  |  | Create NEM Agreement | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 622
2025-GD-00038 | GD10K | Comercial | 7.69 | Out of period | 2025-02-03 | February | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 422
202405-NM25-02797 | GDL17 | Residencial | 3.8 | Out of period | 2025-03-06 20:41 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 390
202405-NM25-02921 | GDL17 | Residencial | 2.304 | Out of period | 2024-06-05 13:29 | June | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 664
202405-NM25-02975 | GDL17 | Residencial | 9.516 | Out of period | 2024-05-23 05:58 | May | 2024 | 2026-03-25 15:49 | 671 | Study | Estudio (E) | Activated | Backlog |  | No | 671 |  | ARECIBO | March |  | 671 | 0 | 2026-04-01 | 678
202405-NM25-03071 | GDL17 | Residencial | 7.6 | Out of period | 2024-05-23 12:04 | May | 2024 |  |  | NM Enter Technical Info | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 677
202405-NM25-03169 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-17 09:50 | September | 2025 | 2026-03-19 08:20 | 183 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March | 1 | 4 | 179 | 2026-04-01 | 196
202405-NM25-03447 | GDL17 | Residencial | 7.6 | Out of period | 2024-05-29 13:12 | May | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 671
202405-NM25-03584 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 13:11 | March | 2026 | 2026-04-07 14:20 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 8 | 0 | 2026-04-01 | 1
202405-NM25-03598 | GDL17 | Residencial | 8 | Out of period | 2024-07-01 12:41 | July | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 638
202405-NM25-03754 | GDL17 | Residencial | 8 | Out of period | 2024-07-01 09:33 | July | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 639
202405-NM25-03890 | GDL17 | Residencial | 13.542 | Out of period | 2025-06-27 07:49 | June | 2025 | 2026-01-29 16:23 | 216 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 3 | 4 | 212 | 2026-04-01 | 278
202405-NM25-04140 | GDL17 | Residencial | 7.6 | Out of period | 2024-05-31 11:10 | May | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 670
202405-NM25-04171 | GDL17 | Residencial | 3.8 | Out of period | 2024-09-19 14:30 | September | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 558
202406-NM25-00007 | GDL17 | Residencial | 11.4 | Out of period | 2024-06-15 06:03 | June | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 655
202406-NM25-00068 | GDL17 | Comercial | 22.8 | Out of period | 2024-09-03 06:54 | September | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 575
202406-NM25-00089 | GDL17 | Residencial | 5 | Period | 2026-02-16 08:48 | February | 2026 | 2026-02-25 15:36 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 4 | 5 | 2026-04-01 | 44
202406-NM25-00205 | GDL17 | Residencial | 8 | Out of period | 2024-06-04 06:16 | June | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 666
202406-NM25-00374 | GDL17 | Residencial | 10 | Out of period | 2024-10-30 09:09 | October | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 524 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 518
202406-NM25-00479 | GDL17 | Residencial | 8 | Out of period | 2024-07-19 13:40 | July | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 620
202406-NM25-00513 | GDL17 | Residencial | 8 | Out of period | 2024-07-17 05:57 | July | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 623
202406-NM25-00519 | GDL17 | Residencial | 8 | Out of period | 2024-07-17 13:27 | July | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 622
202406-NM25-00557 | GDL17 | Residencial | 3.8 | Period | 2026-02-09 14:27 | February | 2026 | 2026-02-11 13:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 50
202406-NM25-00764 | GDL17 | Residencial | 23 | Period | 2026-03-11 10:39 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 21
202406-NM25-01040 | GDL17 | Residencial | 3.8 | Period | 2026-03-13 10:00 | March | 2026 | 2026-03-17 08:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 19
202406-NM25-01079 | GDL17 | Residencial | 8 | Out of period | 2024-07-16 11:09 | July | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 624
202406-NM25-01278 | GDL17 | Residencial | 2.36 | Out of period | 2024-08-01 08:25 | August | 2024 |  |  | Create NEM Agreement | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 608
202406-NM25-01381 | GDL17 | Residencial | 8 | Out of period | 2024-06-11 12:55 | June | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 658
202406-NM25-01518 | GDL17 | Residencial | 9.15 | Out of period | 2025-08-13 | August | 2025 | 2026-02-20 14:48 | 192 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | February | 1 | 19 | 172 | 2026-04-01 | 231
202406-NM25-01893 | GDL17 | Residencial | 7.6 | Out of period | 2024-06-14 12:18 | June | 2024 | 2026-01-29 14:19 | 594 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 5 | 589 | 2026-04-01 | 655
202406-NM25-02003 | GDL17 | Residencial | 8 | Out of period | 2024-06-26 11:28 | June | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 644
202406-NM25-02164 | GDL17 | Residencial | 22.8 | Out of period | 2025-01-31 16:02 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 424
202406-NM25-02247 | GDL17 | Residencial | 8 | Out of period | 2024-10-04 14:56 | October | 2024 |  |  | NM Enter Technical Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 543
202406-NM25-02409 | GDL17 | Residencial | 15.2 | Out of period | 2024-08-26 05:01 | August | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 583
202406-NM25-02884 | GDL17 | Comercial | 9 | Out of period | 2024-06-22 14:14 | June | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 647
202406-NM25-02996 | GDL17 | Comercial | 20.736 | Out of period | 2024-09-19 13:10 | September | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 558
202406-NM25-03054 | GDL17 | Residencial | 15.2 | Out of period | 2024-07-15 07:39 | July | 2024 | 2026-03-03 11:28 | 596 | Study | Estudio (E) | Activated | Backlog |  | No | 596 |  | SAN JUAN | March |  | 596 | 0 | 2026-04-01 | 625
202406-NM25-03300 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-25 13:37 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 491
202406-NM25-03318 | GDL17 | Residencial | 7.6 | Out of period | 2024-08-01 07:26 | August | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 608
202406-NM25-03345 | GDL17 | Residencial | 22.125 | Out of period | 2024-08-23 12:14 | August | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 585
202406-NM25-03508 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-05 07:39 | March | 2025 | 2026-01-23 14:45 | 324 | Study | Estudio (E) | Activated | Backlog |  | No | 324 |  | SAN JUAN | January |  | 324 | 0 | 2026-04-01 | 392
202406-NM25-03699 | GDL17 | Residencial | 15.2 | Out of period | 2024-07-15 12:35 | July | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 624
202407-NM25-00410 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 08:07 | December | 2025 | 2026-01-05 09:17 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 91
202407-NM25-00865 | GDL17 | Residencial | 8.784 | Out of period | 2024-08-16 08:05 | August | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 593
202407-NM25-00941 | GDL17 | Residencial | 3 | Out of period | 2024-07-09 11:49 | July | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 631
202407-NM25-01014 | GDL17 | Residencial | 7.6 | Out of period | 2024-07-09 15:09 | July | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 630
202407-NM25-01518 | GDL17 | Residencial | 8 | Out of period | 2024-08-08 09:45 | August | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 601
202407-NM25-01892 | GDL17 | Residencial | 6.8 | Out of period | 2024-09-18 06:39 | September | 2024 |  |  | Create NEM Agreement | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 560
202407-NM25-01928 | GDL17 | Agricultural | 24.84 | Out of period | 2024-08-12 08:44 | August | 2024 |  |  | Customer Orientation | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 597
202407-NM25-01947 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 09:30 | January | 2026 | 2026-03-31 15:00 | 68 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 68 | 0 | 2026-04-01 | 69
202407-NM25-01999 | GDL17 | Residencial | 3.8 | Out of period | 2025-02-24 12:35 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 400
202407-NM25-02297 | GDL17 | Residencial | 7.6 | Out of period | 2024-08-29 10:44 | August | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | MAYAGUEZ |  |  |  |  | 2026-04-01 | 580
202407-NM25-02490 | GDL17 | Residencial | 6 | Out of period | 2024-10-10 15:15 | October | 2024 | 2026-01-21 07:59 | 468 | Study | Estudio (E) | Activated | Backlog |  | No | 468 |  | PONCE | January |  | 468 | 0 | 2026-04-01 | 537
202407-NM25-02677 | GDL17 | Residencial | 7.6 | Out of period | 2024-07-24 06:00 | July | 2024 |  |  | NM Enter Technical Info | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 616
202407-NM25-02784 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 17:13 | February | 2026 | 2026-02-12 14:41 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 54
202407-NM25-03082 | GDL17 | Residencial | 7.6 | Out of period | 2024-08-23 12:04 | August | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 585
202407-NM25-03200 | GDL17 | Residencial | 10 | Out of period | 2024-09-25 03:23 | September | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 553
202407-NM25-03623 | GDL17 | Residencial | 7.6 | Out of period | 2024-07-25 13:04 | July | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 614
202407-NM25-03886 | GDL17 | Residencial | 5.49 | Out of period | 2024-07-01 07:57 | July | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 639
202407-NM25-04142 | GDL17 | Residencial | 23.79 | Out of period | 2024-07-30 07:18 | July | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 610
202408-NM25-00078 | GDL17 | Residencial | 8 | Out of period | 2024-12-16 14:08 | December | 2024 |  |  | Customer Orientation | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 470
202408-NM25-00346 | GDL17 | Residencial | 3.8 | Out of period | 2025-01-06 13:08 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 449
202408-NM25-00359 | GDL17 | Residencial | 8 | Out of period | 2024-08-16 07:47 | August | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 593
202408-NM25-00399 | GDL17 | Residencial | 8 | Out of period | 2024-08-22 07:44 | August | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 587
202408-NM25-00577 | GDL17 | Residencial | 10 | Out of period | 2025-01-27 16:35 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 428
202408-NM25-00738 | GDL17 | Residencial | 6.588 | Out of period | 2024-09-20 08:26 | September | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 558
202408-NM25-00867 | GDL17 | Residencial | 3.8 | Out of period | 2024-12-07 15:17 | December | 2024 |  |  | Create NEM Agreement | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 479
202408-NM25-01009 | GDL17 | Residencial | 6 | Out of period | 2025-03-30 18:03 | March | 2025 | 2026-01-30 15:20 | 306 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 4 | 302 | 2026-04-01 | 366
202408-NM25-01242 | GDL17 | Residencial | 7.6 | Out of period | 2024-08-29 05:57 | August | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 580
202408-NM25-01269 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 09:05 | February | 2026 | 2026-02-12 15:28 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 3 | 5 | 2026-04-01 | 56
202408-NM25-01653 | GDL17 | Residencial | 8 | Out of period | 2024-08-26 10:41 | August | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 583
202408-NM25-02119 | GDL17 | Residencial | 15.2 | Period | 2026-01-22 09:45 | January | 2026 | 2026-01-26 16:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 69
202408-NM25-02244 | GDL17 | Residencial | 5.124 | Out of period | 2024-08-14 09:09 | August | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 595
202408-NM25-02304 | GDL17 | Residencial | 4.392 | Out of period | 2025-01-20 10:32 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 436
202408-NM25-02491 | GDL17 | Residencial | 3.66 | Out of period | 2024-08-16 08:04 | August | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 593
202408-NM25-02960 | GDL17 | Residencial | 3.8 | Out of period | 2024-12-04 09:20 | December | 2024 | 2026-03-25 10:47 | 476 | Study | Estudio (E) | Activated | Backlog |  | No | 476 |  | MAYAGUEZ | March |  | 476 | 0 | 2026-04-01 | 483
202408-NM25-03015 | GDL17 | Residencial | 7.6 | Out of period | 2024-09-12 10:15 | September | 2024 | 2026-02-18 14:07 | 524 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 7 | 517 | 2026-04-01 | 566
202408-NM25-03086 | GDL17 | Residencial | 7.6 | Out of period | 2024-10-08 13:56 | October | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | PONCE |  |  |  |  | 2026-04-01 | 539
202408-NM25-03197 | GDL17 | Residencial | 5.49 | Out of period | 2024-08-20 14:19 | August | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 588
202408-NM25-03456 | GDL17 | Residencial | 3.84 | Out of period | 2024-08-21 13:59 | August | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 593 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 587
202408-NM25-03725 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-26 21:03 | May | 2025 | 2026-01-16 14:19 | 235 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 1 | 157 | 78 | 2026-04-01 | 309
202408-NM25-03974 | GDL17 | Residencial | 8 | Out of period | 2024-08-26 12:31 | August | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 582
202408-NM25-04092 | GDL17 | Residencial | 8 | Out of period | 2024-09-10 04:45 | September | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 568
202408-NM25-04252 | GDL17 | Residencial | 8 | Out of period | 2024-10-02 13:42 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 545
202408-NM25-04318 | GDL17 | Residencial | 7.6 | Out of period | 2024-08-27 11:58 | August | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 582
202408-NM25-04440 | GDL17 | Residencial | 3.8 | Out of period | 2025-03-27 14:18 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 375 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 369
202408-NM25-04519 | GDL17 | Residencial | 7.6 | Out of period | 2024-08-28 12:10 | August | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 580
202408-NM25-04596 | GDL17 | Residencial | 2.196 | Out of period | 2024-08-28 14:21 | August | 2024 | 2026-01-15 13:04 | 505 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 3 | 205 | 300 | 2026-04-01 | 580
202408-NM25-04605 | GDL17 | Residencial | 8 | Out of period | 2024-09-19 05:17 | September | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | PONCE |  |  |  |  | 2026-04-01 | 559
202408-NM25-04740 | GDL17 | Residencial | 6 | Out of period | 2024-10-11 14:44 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 536
202409-NM25-00039 | GDL17 | Residencial | 3.8 | Out of period | 2025-05-13 17:31 | May | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 322
202409-NM25-00105 | GDL17 | Residencial | 7.29 | Out of period | 2024-10-04 11:31 | October | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 544
202409-NM25-00154 | GDL17 | Residencial | 15 | Period | 2026-03-05 17:18 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 26
202409-NM25-00166 | GDL17 | Residencial | 8 | Out of period | 2024-09-16 07:18 | September | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 562
202409-NM25-00170 | GDL17 | Residencial | 10.98 | Out of period | 2024-12-17 07:40 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 470
202409-NM25-00649 | GDL17 | Residencial | 7.6 | Out of period | 2024-09-13 08:31 | September | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 565
202409-NM25-00720 | GDL17 | Residencial | 5.856 | Period | 2026-03-18 07:54 | March | 2026 | 2026-03-23 08:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 14
202409-NM25-00804 | GDL17 | Residencial | 9.15 | Period | 2026-02-02 14:37 | February | 2026 | 2026-02-13 15:27 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 57
202409-NM25-00955 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-11 15:52 | December | 2024 | 2026-02-11 10:11 | 427 | Study | Estudio (E) | Activated | Backlog |  | No | 427 |  | CAGUAS | February |  | 427 | 0 | 2026-04-01 | 475
202409-NM25-01309 | GDL17 | Residencial | 8.784 | Out of period | 2024-09-10 06:34 | September | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 568
202409-NM25-01530 | GDL17 | Residencial | 8 | Out of period | 2024-09-17 08:57 | September | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 561
202409-NM25-01658 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 07:51 | January | 2026 | 2026-01-20 10:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 77
202409-NM25-01707 | GDL17 | Residencial | 5 | Out of period | 2024-09-18 11:07 | September | 2024 |  |  | NM Enter Technical Info | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 560
2024-GD-00112 | GD10K | Residencial | 9 | Out of period | 2024-02-23 | February | 2024 |  |  | Estudio | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 768
202409-NM25-01882 | GDL17 | Residencial | 8 | Out of period | 2024-09-12 12:20 | September | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 565
202409-NM25-01888 | GDL17 | Residencial | 8 | Out of period | 2024-12-02 10:06 | December | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 485
202409-NM25-01957 | GDL17 | Residencial | 8 | Out of period | 2025-07-13 14:33 | July | 2025 | 2026-01-27 09:38 | 198 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | January | 1 | 5 | 193 | 2026-04-01 | 261
202409-NM25-02222 | GDL17 | Residencial | 6.588 | Out of period | 2024-09-27 13:07 | September | 2024 |  |  | Create NEM Agreement | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 550
2023-GD-39408 | GD10K | Comercial | 9.15 | Out of period | 2024-04-15 | April | 2023 |  |  | Estudio | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 716
202409-NM25-02617 | GDL17 | Residencial | 5 | Out of period | 2024-09-18 11:31 | September | 2024 |  |  | Document Submission | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 560
202409-NM25-02854 | GDL17 | Residencial | 5 | Out of period | 2024-09-20 06:09 | September | 2024 |  |  | Customer Orientation | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 558
202409-NM25-03051 | GDL17 | Residencial | 8 | Out of period | 2024-09-20 12:14 | September | 2024 | 2026-03-23 12:36 | 549 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 8 | 541 | 2026-04-01 | 557
202409-NM25-03354 | GDL17 | Residencial | 20.13 | Out of period | 2024-10-02 16:05 | October | 2024 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 545
202409-NM25-03535 | GDL17 | Residencial | 8.052 | Out of period | 2024-10-30 08:25 | October | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 518
202409-NM25-03916 | GDL17 | Residencial | 6 | Out of period | 2024-12-23 15:37 | December | 2024 | 2026-03-05 10:17 | 437 | Study | Estudio (E) | Activated | Backlog |  | No | 437 |  | CAGUAS | March |  | 436 | 0 | 2026-04-01 | 463
202409-NM25-03949 | GDL17 | Residencial | 7.6 | Out of period | 2024-09-26 07:41 | September | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 552
202409-NM25-04015 | GDL17 | Residencial | 3.8 | Period | 2026-03-11 09:31 | March | 2026 | 2026-03-30 13:01 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 4 | 15 | 2026-04-01 | 21
202409-NM25-04196 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 15:22 | January | 2026 | 2026-01-19 15:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202410-NM25-00004 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-13 12:39 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 503
202410-NM25-00238 | GDL17 | Residencial | 7.6 | Out of period | 2024-10-08 11:10 | October | 2024 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 540
202410-NM25-00627 | GDL17 | Residencial | 15.2 | Out of period | 2025-03-06 10:44 | March | 2025 | 2026-02-27 10:31 | 358 | Study | Estudio (E) | Activated | Backlog |  | No | 358 |  | PONCE | February |  | 358 | 0 | 2026-04-01 | 391
202410-NM25-00723 | GDL17 | Comercial | 24 | Out of period | 2025-10-17 08:40 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 166
202410-NM25-00752 | GDL17 | Residencial | 9 | Out of period | 2024-11-04 22:56 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 512
202410-NM25-01134 | GDL17 | Residencial | 8 | Out of period | 2024-10-09 17:04 | October | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 538
2024-GD-00260 | GD10K | Residencial | 10 | Out of period | 2024-09-13 | September | 2024 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 565
202410-NM25-01138 | GDL17 | Residencial | 20 | Out of period | 2024-12-06 17:17 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 480
202410-NM25-01553 | GDL17 | Residencial | 14.52 | Out of period | 2025-04-25 13:43 | April | 2025 | 2026-01-13 15:33 | 263 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 2 | 240 | 23 | 2026-04-01 | 340
202410-NM25-01693 | GDL17 | Residencial | 10 | Out of period | 2025-03-07 17:34 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 389
202410-NM25-01926 | GDL17 | Residencial | 6 | Period | 2026-03-17 14:28 | March | 2026 | 2026-03-19 09:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 14
2024-GD-00301 | GD10K | Residencial | 10.47 | Out of period | 2024-12-31 | December | 2024 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 456
202410-NM25-02341 | GDL17 | Residencial | 3 | Out of period | 2024-10-14 14:11 | October | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 533
202410-NM25-02355 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-05 11:42 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 331
202410-NM25-02399 | GDL17 | Residencial | 6 | Out of period | 2024-12-20 09:38 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 467
202410-NM25-02503 | GDL17 | Residencial | 13.6 | Out of period | 2025-04-17 11:10 | April | 2025 |  |  | Document Submission | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 349
202410-NM25-02654 | GDL17 | Residencial | 2.7 | Out of period | 2025-01-20 15:59 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 435
2022-GD-04493 | GD1M | Residencial | 11 | Out of period | 2022-03-12 | March | 2022 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 1481
202410-NM25-02714 | GDL17 | Residencial | 6.222 | Out of period | 2024-10-16 12:43 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 531
202410-NM25-02925 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-27 09:43 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 429
202410-NM25-03061 | GDL17 | Residencial | 10.614 | Out of period | 2024-10-18 15:38 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 529
202410-NM25-03165 | GDL17 | Residencial | 3.8 | Out of period | 2024-11-08 11:19 | November | 2024 | 2026-03-12 13:58 | 489 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 486 | 3 | 2026-04-01 | 509
202410-NM25-03322 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-21 14:09 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 434
202410-NM25-03415 | GDL17 | Residencial | 18 | Out of period | 2024-12-09 14:42 | December | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 477
202410-NM25-03650 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-27 14:20 | June | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 283 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 277
202410-NM25-03942 | GDL17 | Residencial | 2.36 | Out of period | 2024-10-31 09:58 | October | 2024 |  |  | NM Representative Review General Info | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 517
202410-NM25-03961 | GDL17 | Residencial | 7.6 | Out of period | 2024-10-24 17:05 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 523
202410-NM25-04138 | GDL17 | Residencial | 10.752 | Out of period | 2024-10-28 16:51 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 519
2025-GD-00058 | GD1M | Comercial | 129.96 | Out of period | 2025-03-12 | March | 2025 |  |  | Anejar Certificacion e Instalacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 385
2025-GD-00060 | GD1M | Comercial | 36.48 | Out of period | 2025-03-13 | March | 2025 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 384
2025-GD-00065 | GD1M | Comercial | 38 | Out of period | 2025-03-25 | March | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 372
2025-GD-00067 | GD1M | Comercial | 30 | Out of period | 2025-03-28 | March | 2025 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 369
2025-GD-00062 | GD1M | Comercial | 26 | Out of period | 2025-03-17 | March | 2025 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 380
2025-GD-00068 | GD1M | Comercial | 26.72 | Out of period | 2025-03-31 | March | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 366
2025-GD-00064 | GD1M | Gubernamental | 150 | Out of period | 2025-03-19 | March | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 378
2025-GD-00059 | GD1M | Comercial | 26.72 | Out of period | 2025-03-13 | March | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 384
2025-GD-00061 | GD1M | Comercial | 41 | Out of period | 2025-03-17 | March | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 380
2025-GD-00057 | GD1M | Comercial | 84.48 | Out of period | 2025-03-11 | March | 2025 |  |  | Firmar Acuerdo | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAROLINA |  |  |  |  | 2026-04-01 | 386
2025-GD-00066 | GD1M | Comercial | 28 | Out of period | 2025-03-28 | March | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 369
2025-GD-00056 | GD1M | Comercial | 30.4 | Out of period | 2025-03-06 | March | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 391
202410-NM25-04142 | GDL17 | Residencial | 5.76 | Out of period | 2024-10-28 17:07 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 519
202410-NM25-04143 | GDL17 | Residencial | 15.2 | Out of period | 2024-10-25 17:27 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 522
202410-NM25-04196 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-22 09:48 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 434
202410-NM25-04243 | GDL17 | Residencial | 6 | Out of period | 2024-11-26 11:02 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 491
202410-NM25-04249 | GDL17 | Residencial | 14.64 | Out of period | 2024-10-28 12:04 | October | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 519
202410-NM25-04795 | GDL17 | Residencial | 7.6 | Out of period | 2024-10-31 10:24 | October | 2024 | 2026-03-27 08:55 | 512 | Study | Estudio (E) | Activated | Backlog |  | No | 512 |  | CAGUAS | March |  | 512 | 0 | 2026-04-01 | 517
202410-NM25-04938 | GDL17 | Residencial | 6.3 | Out of period | 2025-01-04 10:52 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 452
202411-NM25-00060 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-20 09:11 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 497
202411-NM25-00235 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-10 11:01 | February | 2025 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 415
202411-NM25-01137 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-09 16:45 | November | 2024 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 507
202411-NM25-01204 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-05 09:22 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 482
202411-NM25-01218 | GDL17 | Residencial | 15.2 | Out of period | 2024-11-11 11:03 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 506
202411-NM25-01773 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-14 07:37 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 503
202411-NM25-01892 | GDL17 | Residencial | 6.588 | Period | 2026-01-02 11:25 | January | 2026 | 2026-01-14 16:05 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 1 | 9 | 3 | 2026-04-01 | 89
202411-NM25-02157 | GDL17 | Residencial | 8.784 | Out of period | 2024-11-18 09:32 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 499
202411-NM25-02237 | GDL17 | Residencial | 8 | Out of period | 2025-03-18 15:43 | March | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 378
202411-NM25-02465 | GDL17 | Residencial | 15.2 | Out of period | 2024-11-25 11:03 | November | 2024 |  |  | Document Submission | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 492
202411-NM25-02517 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-20 09:54 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 497
202411-NM25-02777 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-21 16:29 | November | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 509 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 495
202411-NM25-02823 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-22 09:22 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 495
202411-NM25-02885 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-22 11:23 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 495
202411-NM25-03370 | GDL17 | Residencial | 7.6 | Out of period | 2024-11-26 13:52 | November | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 490
202412-NM25-00330 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-03 17:27 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 483
202412-NM25-00409 | GDL17 | Residencial | 9.882 | Out of period | 2024-12-05 09:07 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 482
202412-NM25-00573 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-11 14:11 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 475
202412-NM25-00759 | GDL17 | Residencial | 10 | Out of period | 2024-12-10 18:13 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 476
202412-NM25-01043 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-09 11:11 | December | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 484 | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 478
202412-NM25-01124 | GDL17 | Residencial | 2.928 | Out of period | 2024-12-09 13:30 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 477
202412-NM25-01172 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-12 15:15 | November | 2025 | 2026-01-02 12:54 | 51 | Study | Estudio (E) | Activated | Backlog |  | No | 51 |  | MAYAGUEZ | January |  | 51 | 0 | 2026-04-01 | 139
202412-NM25-01761 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-12 08:32 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 475
202412-NM25-01836 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-17 10:15 | December | 2024 | 2026-03-06 10:18 | 444 | Study | Estudio (E) | Activated | Backlog |  | No | 444 |  | CAGUAS | March |  | 444 | 0 | 2026-04-01 | 470
202412-NM25-02139 | GDL17 | Residencial | 4.992 | Out of period | 2024-12-16 09:17 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 471
202412-NM25-02318 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-17 09:50 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 470
202412-NM25-02465 | GDL17 | Residencial | 15.2 | Period | 2026-02-20 09:20 | February | 2026 | 2026-03-02 09:22 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 10 | 0 | 2026-04-01 | 40
202412-NM25-02498 | GDL17 | Residencial | 9.52 | Out of period | 2024-12-18 08:58 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 469
202412-NM25-02756 | GDL17 | Residencial | 2.928 | Out of period | 2024-12-19 09:32 | December | 2024 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 473 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 468
202412-NM25-02800 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-21 10:20 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 404
202412-NM25-03400 | GDL17 | Residencial | 9 | Period | 2026-01-16 09:09 | January | 2026 | 2026-01-19 13:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202412-NM25-03403 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-02 12:02 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 180
202412-NM25-03571 | GDL17 | Residencial | 2.928 | Out of period | 2024-12-24 08:54 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 463
202412-NM25-03821 | GDL17 | Residencial | 7.6 | Out of period | 2024-12-27 09:39 | December | 2024 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 460
202412-NM25-03943 | GDL17 | Residencial | 3.8 | Out of period | 2025-01-30 09:37 | January | 2025 | 2026-01-21 08:57 | 356 | Study | Estudio (E) | Activated | Backlog |  | No | 356 |  | BAYAMON | January |  | 356 | 0 | 2026-04-01 | 426
202412-NM25-04211 | GDL17 | Residencial | 5.76 | Out of period | 2025-02-18 19:09 | February | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | MAYAGUEZ |  |  |  |  | 2026-04-01 | 406
2025-GD-00053 | GD10K | Residencial | 21.54 | Out of period | 2025-02-28 | February | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 397
2024-GD-00039 | GDL17 | Comercial | 6.8 | Out of period | 2024-01-24 | January | 2024 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 798
2024-GD-00069 | GDL17 | Residencial | 7.6 | Out of period | 2024-01-29 | January | 2024 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 793
2024-GD-00165 | GDL17 | Residencial | 8 | Out of period | 2024-04-10 | April | 2024 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 721
2024-GD-00183 | GDL17 | Residencial | 4.03 | Out of period | 2024-05-06 | May | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog | Applicant Registration |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 695
2024-GD-00185 | GDL17 | Residencial | 3.66 | Out of period | 2024-05-07 | May | 2024 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 694
2024-GD-00214 | GDL17 | Residencial | 7.69 | Out of period | 2024-06-17 | June | 2024 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 653
2024-GD-00241 | GDL17 | Comercial | 9.74 | Out of period | 2024-08-09 | August | 2024 |  |  | Completar Información Adicional, Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 600
2023-GD-17135 | GD10K | Comercial | 23.99 | Out of period | 2023-06-12 | June | 2023 |  |  | Completar Información Adicional, Validación | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAROLINA |  |  |  |  | 2026-04-01 | 1024
2024-GD-00263 | GDL17 | Residencial | 7.69 | Out of period | 2024-09-30 | September | 2024 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 548
2024-GD-00269 | GDL17 | Comercial | 23.99 | Out of period | 2024-10-08 | October | 2024 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | Caguas |  |  |  |  | 2026-04-01 | 540
202501-NM25-00102 | GDL17 | Residencial | 15.2 | Out of period | 2025-01-03 20:26 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 452
202501-NM25-00283 | GDL17 | Residencial | 8.784 | Out of period | 2025-01-10 17:00 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 445
202501-NM25-00431 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-09 11:26 | May | 2025 | 2026-01-26 09:35 | 262 | Study | Estudio (E) | Activated | Backlog |  | No | 262 |  | SAN JUAN | January |  | 262 | 0 | 2026-04-01 | 327
2025-GD-00054 | GD1M | Comercial | 25.08 | Out of period | 2025-02-28 | February | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 397
2023-GD-37682 | GD1M | Residencial | 25.34 | Out of period | 2023-12-08 | December | 2023 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 845
2023-GD-32344 | GD1M | Residencial | 25.37 | Out of period | 2023-10-26 | October | 2023 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 888
2024-GD-00149 | GD1M | Comercial | 25.37 | Out of period | 2024-03-21 | March | 2024 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 741
2024-GD-00148 | GD1M | Comercial | 25.37 | Out of period | 2024-03-21 | March | 2024 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 741
2023-GD-20815 | GD1M | Comercial | 25.5 | Out of period | 2023-07-18 | July | 2023 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 988
2024-GD-00116 | GD1M | Comercial | 25.5 | Out of period | 2024-02-27 | February | 2024 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 764
2023-GD-01704 | GD1M | Comercial | 25.62 | Out of period | 2023-01-18 | January | 2023 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1169
2023-GD-22872 | GD1M | Residencial | 25.73 | Out of period | 2023-08-01 | August | 2023 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 974
2024-GD-00248 | GD1M | Residencial | 25.82 | Out of period | 2024-08-26 | August | 2024 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 583
2023-GD-18746 | GD1M | Residencial | 25.99 | Out of period | 2023-07-03 | July | 2023 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1003
2023-GD-32534 | GD1M | Residencial | 25.99 | Out of period | 2023-10-27 | October | 2023 |  |  | Pago Aportacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 887
2023-GD-39379 | GD1M | Comercial | 25.99 | Out of period | 2024-06-19 | June | 2023 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 651
202501-NM25-00562 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-11 11:45 | February | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | MAYAGUEZ |  |  |  |  | 2026-04-01 | 414
202501-NM25-00913 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-08 09:33 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 448
202501-NM25-01167 | GDL17 | Residencial | 4.992 | Out of period | 2025-01-09 10:13 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 447
202501-NM25-01318 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-14 13:01 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 410
202501-NM25-01544 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-11 13:03 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 444
202501-NM25-01633 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-28 16:57 | May | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 307
202501-NM25-01648 | GDL17 | Residencial | 3.6 | Out of period | 2025-01-16 08:08 | January | 2025 | 2026-02-11 08:48 | 391 | Study | Estudio (E) | Activated | Backlog |  | No | 391 |  | CAGUAS | February |  | 391 | 0 | 2026-04-01 | 440
202501-NM25-01853 | GDL17 | Residencial | 3.8 | Out of period | 2025-02-03 10:49 | February | 2025 | 2026-01-13 11:12 | 344 | Study | Estudio (E) | Activated | Backlog |  | No | 344 |  | CAGUAS | January |  | 344 | 0 | 2026-04-01 | 422
202501-NM25-01920 | GDL17 | Residencial | 5.76 | Out of period | 2025-03-06 14:49 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 396 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 390
202501-NM25-02328 | GDL17 | Residencial | 15 | Out of period | 2025-02-20 06:40 | February | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 405
202501-NM25-02358 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-16 11:09 | January | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 445 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 440
202501-NM25-02404 | GDL17 | Comercial | 10 | Period | 2026-03-06 12:01 | March | 2026 | 2026-03-25 13:03 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 19 | 0 | 2026-04-01 | 25
202501-NM25-02459 | GDL17 | Residencial | 5.49 | Out of period | 2025-02-11 13:18 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 413
202501-NM25-02785 | GDL17 | Residencial | 3.8 | Out of period | 2025-02-18 11:51 | February | 2025 | 2026-01-07 13:39 | 323 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 13 | 310 | 2026-04-01 | 407
202501-NM25-02810 | GDL17 | Residencial | 8.4 | Out of period | 2025-03-10 09:10 | March | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 387
202501-NM25-02941 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-20 18:56 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 435
202501-NM25-02944 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-15 16:19 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 350
202501-NM25-02969 | GDL17 | Residencial | 15 | Out of period | 2025-06-03 16:48 | June | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 301
202501-NM25-03145 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-28 13:28 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 368
202501-NM25-03347 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 10:25 | January | 2026 | 2026-01-28 15:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 69
202501-NM25-03691 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-24 11:13 | January | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 432
202501-NM25-03745 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-24 14:34 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 431
202501-NM25-03844 | GDL17 | Residencial | 10 | Out of period | 2025-07-22 11:42 | July | 2025 | 2026-01-23 10:52 | 185 | Study | Estudio (E) | Activated | Backlog |  | No | 185 |  | CAGUAS | January |  | 184 | 0 | 2026-04-01 | 253
202501-NM25-04078 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-27 21:27 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 428
202501-NM25-04103 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-28 09:52 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 428
202501-NM25-04127 | GDL17 | Residencial | 8 | Out of period | 2025-03-18 10:03 | March | 2025 | 2026-03-31 12:39 | 378 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 6 | 372 | 2026-04-01 | 379
202501-NM25-04193 | GDL17 | Residencial | 15 | Out of period | 2025-02-24 11:10 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 401
202501-NM25-04211 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-04 09:10 | February | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 421
202501-NM25-04397 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 14:58 | January | 2026 | 2026-01-29 09:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 68
202501-NM25-04550 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-16 15:07 | June | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 297 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 288
202501-NM25-04571 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-31 11:12 | January | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 425
202501-NM25-04731 | GDL17 | Residencial | 5.124 | Out of period | 2025-02-10 09:29 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 415
202501-NM25-04993 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-04 06:20 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 421
202501-NM25-04999 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-26 15:09 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 398
202501-NM25-05051 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 10:23 | January | 2026 | 2026-01-21 08:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 72
202501-NM25-05065 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-15 10:59 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 351
202501-NM25-05082 | GDL17 | Residencial | 7.6 | Out of period | 2025-01-31 10:17 | January | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 425
202501-NM25-05231 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-10 09:24 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 295
2025-GD-00073 | GD1M | Residencial | 30 | Out of period | 2025-04-16 | April | 2025 |  |  | Anejar Certificacion e Instalacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 350
2025-GD-00071 | GD1M | Industrial | 747 | Out of period | 2025-04-08 | April | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 358
2025-GD-00075 | GD1M | Comercial | 30 | Out of period | 2025-04-21 | April | 2025 |  |  | endevent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Caguas |  |  |  |  | 2026-04-01 | 345
2025-GD-00070 | GD1M | Comercial | 38 | Out of period | 2025-04-01 | April | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 365
2025-GD-00078 | GD1M | Comercial | 83 | Out of period | 2025-04-28 | April | 2025 |  |  | Inspeccion Documentos | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Ponce |  |  |  |  | 2026-04-01 | 338
2025-GD-00079 | GD1M | Gubernamental | 30 | Out of period | 2025-04-30 | April | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 336
2025-GD-00077 | GD1M | Gubernamental | 30 | Out of period | 2025-04-24 | April | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 342
2025-GD-00076 | GD1M | Gubernamental | 30 | Out of period | 2025-04-24 | April | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 342
2025-GD-00072 | GD1M | Comercial | 38 | Out of period | 2025-04-15 | April | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 351
2025-GD-00069 | GD1M | Comercial | 80 | Out of period | 2025-04-01 | April | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 365
202501-NM25-05372 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-03 08:55 | February | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 428 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 422
202502-NM25-00012 | GDL17 | Residencial | 8 | Out of period | 2025-03-05 09:04 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 392
202502-NM25-00149 | GDL17 | Residencial | 10.248 | Out of period | 2025-06-10 10:18 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 295
202502-NM25-00151 | GDL17 | Residencial | 15.84 | Out of period | 2025-07-29 07:57 | July | 2025 | 2026-03-30 16:16 | 244 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 4 | 27 | 217 | 2026-04-01 | 246
202502-NM25-00291 | GDL17 | Residencial | 8 | Out of period | 2025-03-11 09:51 | March | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 386
202502-NM25-00634 | GDL17 | Residencial | 6 | Out of period | 2025-02-26 12:15 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 398
202502-NM25-00696 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-07 14:48 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 417
202502-NM25-00815 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-07 11:12 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 390
202502-NM25-00823 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-14 09:50 | May | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 322
202502-NM25-00851 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-11 16:48 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 413
202502-NM25-00967 | GDL17 | Comercial | 6.3 | Out of period | 2025-07-10 11:11 | July | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 265
202502-NM25-00977 | GDL17 | Residencial | 8 | Out of period | 2025-03-11 09:55 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 386
202502-NM25-01053 | GDL17 | Residencial | 7.5 | Out of period | 2025-12-11 11:01 | December | 2025 |  |  | NM Enter Technical Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 111
202502-NM25-01135 | GDL17 | Residencial | 3.8 | Out of period | 2025-03-03 18:40 | March | 2025 | 2026-01-22 09:03 | 325 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 12 | 313 | 2026-04-01 | 393
202502-NM25-01387 | GDL17 | Residencial | 5.76 | Period | 2026-01-27 13:27 | January | 2026 | 2026-02-17 09:16 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 21 | 0 | 2026-04-01 | 63
202502-NM25-01586 | GDL17 | Residencial | 4.224 | Out of period | 2025-02-08 13:16 | February | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 424 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 416
202502-NM25-01691 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-14 10:11 | May | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 322
202502-NM25-02016 | GDL17 | Residencial | 3.8 | Out of period | 2025-05-12 13:04 | May | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 343 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 323
202502-NM25-02040 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-11 15:52 | February | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 413
202502-NM25-02104 | GDL17 | Residencial | 8 | Out of period | 2025-04-02 14:54 | April | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 363
202502-NM25-02114 | GDL17 | Residencial | 8 | Out of period | 2025-02-21 08:42 | February | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 404
202502-NM25-02137 | GDL17 | Residencial | 8 | Out of period | 2025-04-09 11:58 | April | 2025 | 2026-03-25 14:44 | 350 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 5 | 345 | 2026-04-01 | 357
202502-NM25-02404 | GDL17 | Residencial | 7.6 | Period | 2026-03-02 08:12 | March | 2026 | 2026-03-18 13:01 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 17 | 0 | 2026-04-01 | 30
202502-NM25-02450 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 13:55 | February | 2026 | 2026-03-02 09:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202502-NM25-02523 | GDL17 | Residencial | 5.76 | Out of period | 2025-02-18 13:11 | February | 2025 | 2026-01-14 10:42 | 330 | Study | Estudio (E) | Activated | Backlog |  | No | 330 |  | ARECIBO | January |  | 330 | 0 | 2026-04-01 | 406
202502-NM25-02536 | GDL17 | Comercial | 22.326 | Out of period | 2025-09-18 15:53 | September | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 194
202502-NM25-02543 | GDL17 | Residencial | 9.516 | Out of period | 2025-02-15 16:15 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 409
202502-NM25-02575 | GDL17 | Residencial | 7.6 | Period | 2026-02-16 11:23 | February | 2026 | 2026-02-19 15:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202502-NM25-02647 | GDL17 | Residencial | 15.6 | Out of period | 2025-05-21 14:05 | May | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 314
202502-NM25-02675 | GDL17 | Residencial | 12.078 | Out of period | 2025-04-04 14:28 | April | 2025 | 2026-03-23 16:20 | 353 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | March | 2 | 324 | 10 | 2026-04-01 | 361
202502-NM25-02929 | GDL17 | Residencial | 10 | Out of period | 2025-03-26 10:48 | March | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 371
202502-NM25-03144 | GDL17 | Residencial | 6.528 | Out of period | 2025-02-21 09:49 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 404
202502-NM25-03173 | GDL17 | Comercial | 5 | Out of period | 2025-02-18 14:25 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 406
202502-NM25-03334 | GDL17 | Residencial | 7.6 | Period | 2026-02-02 10:07 | February | 2026 | 2026-02-04 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 58
202502-NM25-03648 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-14 10:54 | May | 2025 | 2026-03-12 11:18 | 302 | Study | Estudio (E) | Activated | Backlog |  | No | 302 |  | PONCE | March |  | 302 | 0 | 2026-04-01 | 322
202502-NM25-03918 | GDL17 | Residencial | 5.124 | Out of period | 2025-08-22 | August | 2025 | 2026-01-28 16:31 | 160 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 2 | 13 | 146 | 2026-04-01 | 222
202502-NM25-04218 | GDL17 | Residencial | 15.2 | Out of period | 2025-04-09 09:22 | April | 2025 | 2026-01-14 14:17 | 280 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | January | 2 | 5 | 275 | 2026-04-01 | 357
202502-NM25-04258 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-12 08:46 | June | 2025 | 2026-01-15 10:26 | 217 | Study | Estudio (E) | Activated | Backlog |  | No | 217 |  | MAYAGUEZ | January |  | 217 | 0 | 2026-04-01 | 293
202502-NM25-04431 | GDL17 | Residencial | 5.31 | Out of period | 2025-02-25 10:47 | February | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 400
202502-NM25-04575 | GDL17 | Residencial | 7.6 | Period | 2026-02-20 09:00 | February | 2026 | 2026-02-26 16:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 40
202502-NM25-04618 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-22 12:06 | April | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 343
202502-NM25-04791 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-21 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 223
202502-NM25-04792 | GDL17 | Residencial | 5.76 | Out of period | 2025-10-29 11:12 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 154
202502-NM25-05046 | GDL17 | Residencial | 8 | Out of period | 2025-04-03 13:34 | April | 2025 | 2026-02-13 11:29 | 316 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February | 6 | 12 | 304 | 2026-04-01 | 362
202502-NM25-05065 | GDL17 | Residencial | 11.5 | Out of period | 2025-02-20 10:35 | February | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 431 | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 405
202502-NM25-05137 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-15 11:17 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 321
2025-GD-00090 | GD1M | Comercial | 32 | Out of period | 2025-05-21 | May | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 315
2025-GD-00089 | GD1M | Comercial | 720 | Out of period | 2025-05-15 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 321
2025-GD-00097 | GD1M | Comercial | 106 | Out of period | 2025-05-31 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 305
2025-GD-00096 | GD1M | Comercial | 383 | Out of period | 2025-05-30 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 306
2025-GD-00095 | GD1M | Comercial | 86.3 | Out of period | 2025-05-30 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 306
2025-GD-00094 | GD1M | Comercial | 66 | Out of period | 2025-05-30 | May | 2025 |  |  | Inspeccion Documentos | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Bayamon |  |  |  |  | 2026-04-01 | 306
2025-GD-00080 | GD1M | Comercial | 83.78 | Out of period | 2025-05-02 | May | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 334
2025-GD-00092 | GD1M | Gubernamental | 31.2 | Out of period | 2025-05-28 | May | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Mayaguez |  |  |  |  | 2026-04-01 | 308
2025-GD-00082 | GD1M | Gubernamental | 384 | Out of period | 2025-05-06 | May | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 330
2025-GD-00091 | GD1M | Comercial | 48 | Out of period | 2025-05-21 | May | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Ponce |  |  |  |  | 2026-04-01 | 315
2025-GD-00088 | GD1M | Comercial | 1000 | Out of period | 2025-05-15 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 321
2025-GD-00087 | GD1M | Comercial | 50 | Out of period | 2025-05-14 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 322
2025-GD-00093 | GD1M | Comercial | 132 | Out of period | 2025-05-29 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 307
2025-GD-00085 | GD1M | Comercial | 65.25 | Out of period | 2025-05-06 | May | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 330
2025-GD-00084 | GD1M | Gubernamental | 90 | Out of period | 2025-05-06 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 330
2025-GD-00083 | GD1M | Gubernamental | 60 | Out of period | 2025-05-06 | May | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 330
2025-GD-00081 | GD1M | Comercial | 45 | Out of period | 2025-05-02 | May | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 334
202502-NM25-05172 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-19 13:22 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 377
202502-NM25-05343 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-16 08:23 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 204 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 197
202502-NM25-05814 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-14 | August | 2025 | 2026-02-13 09:39 | 183 | Study | Estudio (E) | Activated | Backlog |  | No | 183 |  | MAYAGUEZ | February |  | 183 | 0 | 2026-04-01 | 230
202502-NM25-05986 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-06 16:55 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 390
202502-NM25-06008 | GDL17 | Residencial | 5 | Out of period | 2025-03-26 09:01 | March | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 371
202502-NM25-06104 | GDL17 | Residencial | 6 | Out of period | 2025-03-19 13:11 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 399 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 377
202502-NM25-06112 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-12 | August | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 245 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 232
202502-NM25-06162 | GDL17 | Residencial | 11.5 | Out of period | 2025-02-25 12:11 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 399
202502-NM25-06167 | GDL17 | Residencial | 8 | Out of period | 2025-04-03 16:24 | April | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 362
202502-NM25-06678 | GDL17 | Residencial | 6.954 | Out of period | 2025-09-16 09:23 | September | 2025 | 2026-01-05 11:26 | 111 | Study | Estudio (E) | Activated | Backlog |  | No | 111 |  | MAYAGUEZ | January |  | 111 | 0 | 2026-04-01 | 197
202502-NM25-06725 | GDL17 | Residencial | 24.576 | Out of period | 2025-02-28 15:44 | February | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 396
202502-NM25-06788 | GDL17 | Residencial | 7.6 | Out of period | 2025-02-27 21:22 | February | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 397
202502-NM25-06890 | GDL17 | Residencial | 6.528 | Out of period | 2025-08-29 | August | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | MAYAGUEZ |  |  |  |  | 2026-04-01 | 215
202503-NM25-00046 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-02 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 242
202503-NM25-00068 | GDL17 | Residencial | 8 | Out of period | 2025-03-13 15:49 | March | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 383
202503-NM25-00218 | GDL17 | Residencial | 3.8 | Out of period | 2025-03-04 19:57 | March | 2025 | 2026-01-13 13:18 | 315 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 313 | 2 | 2026-04-01 | 392
202503-NM25-00478 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 07:29 | March | 2026 | 2026-03-31 13:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 5
202503-NM25-00484 | GDL17 | Residencial | 3.84 | Out of period | 2025-03-04 15:48 | March | 2025 | 2026-03-02 16:07 | 363 | Study | Estudio (E) | Activated | Backlog |  | No | 363 |  | CAGUAS | March |  | 363 | 0 | 2026-04-01 | 392
202503-NM25-00789 | GDL17 | Residencial | 11.5 | Out of period | 2025-03-06 08:58 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 417 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 391
202503-NM25-00956 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-06 17:22 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 397 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 390
202503-NM25-01500 | GDL17 | Residencial | 8.418 | Out of period | 2025-03-10 19:02 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 386
202503-NM25-01606 | GDL17 | Residencial | 11.5 | Out of period | 2025-03-11 13:05 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 385
202503-NM25-01617 | GDL17 | Residencial | 8 | Out of period | 2025-03-11 15:45 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 385
202503-NM25-01816 | GDL17 | Residencial | 3.8 | Out of period | 2025-03-26 14:50 | March | 2025 |  |  | Customer Orientation | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 370
202503-NM25-01819 | GDL17 | Residencial | 3.66 | Out of period | 2025-03-12 14:38 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 393 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 384
202503-NM25-01922 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-13 09:56 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 384
202503-NM25-02116 | GDL17 | Residencial | 8 | Out of period | 2025-03-19 10:13 | March | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 378
202503-NM25-02138 | GDL17 | Residencial | 8 | Out of period | 2025-04-03 14:00 | April | 2025 | 2026-03-25 14:39 | 356 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March | 2 | 7 | 349 | 2026-04-01 | 362
202503-NM25-02166 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-24 17:46 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 280
202503-NM25-02170 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-01 18:10 | July | 2025 | 2026-01-19 13:23 | 202 | Study | Estudio (E) | Activated | Backlog |  | No | 202 |  | CAGUAS | January |  | 202 | 0 | 2026-04-01 | 273
202503-NM25-02182 | GDL17 | Residencial | 10 | Out of period | 2025-06-30 22:48 | June | 2025 | 2026-01-05 14:55 | 189 | Study | Estudio (E) | Activated | Backlog |  | No | 189 |  | BAYAMON | January |  | 189 | 0 | 2026-04-01 | 274
202503-NM25-02282 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-19 10:10 | May | 2025 | 2026-03-13 13:57 | 298 | Study | Estudio (E) | Activated | Backlog |  | No | 298 |  | BAYAMON | March |  | 298 | 0 | 2026-04-01 | 317
202503-NM25-02298 | GDL17 | Residencial | 8 | Out of period | 2025-03-17 12:02 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 379
202503-NM25-02308 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-30 11:56 | June | 2025 | 2026-01-15 10:23 | 199 | Study | Estudio (E) | Activated | Backlog |  | No | 199 |  | PONCE | January |  | 199 | 0 | 2026-04-01 | 275
202503-NM25-02309 | GDL17 | Residencial | 8 | Period | 2026-01-16 18:42 | January | 2026 | 2026-01-28 15:41 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | January | 1 | 12 | 0 | 2026-04-01 | 74
202503-NM25-02321 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-17 11:50 | March | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 380
202503-NM25-02416 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-27 10:08 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 370
202503-NM25-02417 | GDL17 | Residencial | 15 | Out of period | 2025-06-20 11:54 | June | 2025 | 2026-02-11 07:47 | 236 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 99 | 126 | 2026-04-01 | 285
202503-NM25-02548 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-01 10:16 | July | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | MAYAGUEZ |  |  |  |  | 2026-04-01 | 274
202503-NM25-02620 | GDL17 | Residencial | 6.588 | Out of period | 2025-07-07 13:32 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 267
202503-NM25-02706 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-07 14:57 | November | 2025 | 2026-02-25 10:55 | 110 | Study | Estudio (E) | Activated | Backlog |  | No | 110 |  | SAN JUAN | February |  | 110 | 0 | 2026-04-01 | 144
202503-NM25-02732 | GDL17 | Residencial | 8 | Out of period | 2025-05-13 12:55 | May | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 322
202503-NM25-02834 | GDL17 | Residencial | 8 | Out of period | 2025-05-05 13:58 | May | 2025 | 2026-03-27 15:57 | 326 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 2 | 11 | 315 | 2026-04-01 | 330
202503-NM25-02893 | GDL17 | Residencial | 13.056 | Out of period | 2025-07-16 09:24 | July | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 259
202503-NM25-02951 | GDL17 | Residencial | 8 | Out of period | 2025-05-13 13:02 | May | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 322
202503-NM25-02964 | GDL17 | Residencial | 3.456 | Period | 2026-03-31 16:54 | March | 2026 | 2026-04-07 07:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | April |  | 7 | 1 | 2026-04-01 | 0
202503-NM25-03012 | GDL17 | Residencial | 3.456 | Out of period | 2025-09-01 11:41 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 212
202503-NM25-03101 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-06 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 238
202503-NM25-03110 | GDL17 | Residencial | 3.8 | Out of period | 2025-06-27 11:05 | June | 2025 | 2026-01-20 16:26 | 207 | Study | Estudio (E) | Activated | Backlog |  | No | 207 |  | MAYAGUEZ | January |  | 207 | 0 | 2026-04-01 | 278
202503-NM25-03111 | GDL17 | Residencial | 3.072 | Out of period | 2025-06-12 10:44 | June | 2025 | 2026-01-28 15:57 | 230 | Study | Estudio (E) | Activated | Backlog |  | No | 230 |  | CAGUAS | January |  | 230 | 0 | 2026-04-01 | 293
202503-NM25-03207 | GDL17 | Residencial | 11.5 | Out of period | 2025-06-05 11:49 | June | 2025 | 2026-01-19 10:36 | 228 | Study | Estudio (E) | Activated | Backlog |  | No | 228 |  | CAGUAS | January |  | 228 | 0 | 2026-04-01 | 300
202503-NM25-03234 | GDL17 | Residencial | 6.912 | Out of period | 2025-09-01 10:32 | September | 2025 | 2026-01-08 13:33 | 129 | Study | Estudio (E) | Activated | Backlog |  | No | 129 |  | MAYAGUEZ | January |  | 129 | 0 | 2026-04-01 | 212
202503-NM25-03523 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-09 19:49 | June | 2025 | 2026-03-03 09:36 | 267 | Study | Estudio (E) | Activated | Backlog |  | No | 267 |  | CAGUAS | March |  | 266 | 0 | 2026-04-01 | 295
202503-NM25-03581 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-18 15:28 | July | 2025 | 2026-02-16 14:12 | 213 | Study | Estudio (E) | Activated | Backlog |  | No | 213 |  | BAYAMON | February |  | 213 | 0 | 2026-04-01 | 256
202503-NM25-03622 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 10:27 | January | 2026 | 2026-01-14 07:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 84
202503-NM25-03646 | GDL17 | Residencial | 6.222 | Out of period | 2025-03-25 07:35 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 372
202503-NM25-03677 | GDL17 | Residencial | 15.2 | Out of period | 2025-12-24 10:02 | December | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 98
202503-NM25-03714 | GDL17 | Residencial | 3.8 | Out of period | 2025-07-01 14:50 | July | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 273
202503-NM25-03725 | GDL17 | Residencial | 3.84 | Out of period | 2025-03-24 17:44 | March | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 380 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 372
202503-NM25-03984 | GDL17 | Residencial | 11.5 | Out of period | 2025-03-25 12:26 | March | 2025 | 2026-01-15 09:35 | 296 | Study | Estudio (E) | Activated | Backlog |  | No | 296 |  | CAGUAS | January |  | 296 | 0 | 2026-04-01 | 371
202503-NM25-04067 | GDL17 | Residencial | 5.856 | Out of period | 2025-04-21 12:09 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 344
202503-NM25-04070 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-26 09:00 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 126
202503-NM25-04199 | GDL17 | Residencial | 11.5 | Out of period | 2025-03-25 15:51 | March | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 371
202503-NM25-04702 | GDL17 | Residencial | 7.6 | Out of period | 2025-03-26 16:15 | March | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 370
202503-NM25-04705 | GDL17 | Residencial | 8 | Out of period | 2025-03-31 11:33 | March | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 366
202503-NM25-04723 | GDL17 | Residencial | 3.8 | Out of period | 2025-06-30 11:52 | June | 2025 | 2026-02-10 15:37 | 225 | Study | Estudio (E) | Activated | Backlog |  | No | 225 |  | SAN JUAN | February |  | 225 | 0 | 2026-04-01 | 275
202503-NM25-04811 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 13:29 | February | 2026 | 2026-02-10 14:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 53
2025-GD-00108 | GD1M | Comercial | 86.3 | Out of period | 2025-06-25 | June | 2025 |  |  | approvedDistributionEndEvent | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Bayamon |  |  |  |  | 2026-04-01 | 280
2025-GD-00101 | GD1M | Comercial | 396 | Out of period | 2025-06-01 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 304
2025-GD-00110 | GD1M | Comercial | 998 | Out of period | 2025-06-25 | June | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 280
2025-GD-00104 | GD1M | Comercial | 375 | Out of period | 2025-06-06 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 299
2025-GD-00103 | GD1M | Comercial | 90 | Out of period | 2025-06-06 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 299
2025-GD-00112 | GD1M | Comercial | 53 | Out of period | 2025-06-27 | June | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 278
2025-GD-00109 | GD1M | Comercial | 60 | Out of period | 2025-06-25 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 280
2025-GD-00106 | GD1M | Residencial | 30 | Out of period | 2025-06-21 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 284
2025-GD-00105 | GD1M | Gubernamental | 68 | Out of period | 2025-06-17 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 288
2025-GD-00102 | GD1M | Comercial | 159 | Out of period | 2025-06-03 | June | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 302
2025-GD-00100 | GD1M | Comercial | 139.3 | Out of period | 2025-06-01 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 304
2025-GD-00099 | GD1M | Comercial | 106 | Out of period | 2025-06-01 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 304
2025-GD-00098 | GD1M | Comercial | 264 | Out of period | 2025-06-01 | June | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 304
2025-GD-00107 | GD10K | Residencial | 15 | Out of period | 2025-06-22 | June | 2025 |  |  | Estudio | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Arecibo |  |  |  |  | 2026-04-01 | 283
2025-GD-00111 | GD10K | Residencial | 2.95 | Out of period | 2025-06-25 | June | 2025 |  |  | Validación | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | Caguas |  |  |  |  | 2026-04-01 | 280
202503-NM25-04904 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 07:34 | January | 2026 | 2026-02-03 12:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202503-NM25-04909 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-29 06:26 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 154
202503-NM25-05122 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-24 08:04 | July | 2025 | 2026-01-15 11:16 | 175 | Study | Estudio (E) | Activated | Backlog |  | No | 175 |  | BAYAMON | January |  | 175 | 0 | 2026-04-01 | 251
202503-NM25-05446 | GDL17 | Residencial | 11.5 | Out of period | 2025-06-13 16:21 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 291
202503-NM25-05573 | GDL17 | Residencial | 14.592 | Out of period | 2025-06-27 16:35 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 277
202503-NM25-05574 | GDL17 | Residencial | 21.96 | Out of period | 2025-06-11 14:29 | June | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 293
202503-NM25-05673 | GDL17 | Residencial | 8 | Out of period | 2025-05-05 13:53 | May | 2025 | 2026-03-31 14:34 | 330 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 13 | 317 | 2026-04-01 | 330
202503-NM25-05724 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-16 13:39 | July | 2025 | 2026-01-08 11:11 | 176 | Study | Estudio (E) | Activated | Backlog |  | No | 176 |  | BAYAMON | January |  | 176 | 0 | 2026-04-01 | 258
202503-NM25-05819 | GDL17 | Residencial | 10 | Out of period | 2025-12-10 16:50 | December | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | PONCE |  |  |  |  | 2026-04-01 | 111
202504-NM25-00066 | GDL17 | Residencial | 8 | Out of period | 2025-07-29 14:11 | July | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 245
202504-NM25-00142 | GDL17 | Residencial | 4.392 | Out of period | 2025-09-04 08:46 | September | 2025 | 2026-01-08 15:25 | 126 | Study | Estudio (E) | Activated | Backlog |  | No | 126 |  | ARECIBO | January |  | 126 | 0 | 2026-04-01 | 209
202504-NM25-00149 | GDL17 | Residencial | 8 | Out of period | 2025-05-20 08:05 | May | 2025 |  |  | Customer Orientation | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 316
202504-NM25-00254 | GDL17 | Residencial | 8.448 | Period | 2026-02-03 15:41 | February | 2026 | 2026-02-17 13:45 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 56
202504-NM25-00407 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-02 12:30 | July | 2025 | 2026-01-16 15:50 | 198 | Study | Estudio (E) | Activated | Backlog |  | No | 198 |  | ARECIBO | January |  | 198 | 0 | 2026-04-01 | 272
202504-NM25-00482 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-03 12:34 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 362
202504-NM25-00522 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-02 12:58 | October | 2025 | 2026-01-28 11:25 | 118 | Study | Estudio (E) | Activated | Backlog |  | No | 118 |  | ARECIBO | January |  | 118 | 0 | 2026-04-01 | 180
202504-NM25-00662 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 12:59 | March | 2026 | 2026-03-16 13:25 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 11 | 0 | 2026-04-01 | 26
202504-NM25-00772 | GDL17 | Residencial | 3.072 | Out of period | 2025-06-27 15:33 | June | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 277
202504-NM25-00805 | GDL17 | Comercial | 3.8 | Out of period | 2025-09-24 11:31 | September | 2025 | 2026-02-11 07:56 | 140 | Study | Estudio (E) | Activated | Backlog |  | No | 140 |  | CAGUAS | February |  | 140 | 0 | 2026-04-01 | 189
202504-NM25-00853 | GDL17 | Residencial | 8 | Out of period | 2025-04-10 09:10 | April | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 356
202504-NM25-01129 | GDL17 | Residencial | 14.92 | Out of period | 2025-05-05 16:12 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 330
202504-NM25-01241 | GDL17 | Residencial | 3.8 | Out of period | 2025-05-21 14:36 | May | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 314
202504-NM25-01260 | GDL17 | Residencial | 3.8 | Out of period | 2025-06-16 12:57 | June | 2025 | 2026-01-16 16:25 | 214 | Study | Estudio (E) | Activated | Backlog |  | No | 214 |  | PONCE | January |  | 214 | 0 | 2026-04-01 | 288
202504-NM25-01297 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-10 10:10 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 356
202504-NM25-01404 | GDL17 | Residencial | 15.2 | Out of period | 2025-06-17 11:38 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 288
202504-NM25-01416 | GDL17 | Residencial | 8 | Out of period | 2025-06-20 14:31 | June | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 284
202504-NM25-01630 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-20 | August | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 231 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 224
202504-NM25-01666 | GDL17 | Residencial | 3.8 | Out of period | 2025-09-09 11:39 | September | 2025 | 2026-01-08 13:49 | 121 | Study | Estudio (E) | Activated | Backlog |  | No | 121 |  | MAYAGUEZ | January |  | 121 | 0 | 2026-04-01 | 204
202504-NM25-01693 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-08 14:48 | April | 2025 | 2026-03-03 13:18 | 329 | Study | Estudio (E) | Activated | Backlog |  | No | 329 |  | SAN JUAN | March |  | 329 | 0 | 2026-04-01 | 357
202504-NM25-01743 | GDL17 | Residencial | 8 | Out of period | 2025-04-29 08:32 | April | 2025 | 2026-01-05 09:14 | 251 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 2 | 15 | 236 | 2026-04-01 | 337
202504-NM25-01804 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-17 10:53 | September | 2025 | 2026-03-03 09:45 | 167 | Study | Estudio (E) | Activated | Backlog |  | No | 167 |  | MAYAGUEZ | March |  | 167 | 0 | 2026-04-01 | 196
202504-NM25-01852 | GDL17 | Residencial | 15.2 | Out of period | 2025-05-05 12:56 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 330
202504-NM25-01861 | GDL17 | Residencial | 11.9 | Out of period | 2025-04-10 13:02 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 355
202504-NM25-01872 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-23 11:53 | September | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | MAYAGUEZ |  |  |  |  | 2026-04-01 | 190
202504-NM25-01905 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-10 09:42 | April | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 356
202504-NM25-01971 | GDL17 | Residencial | 11.5 | Out of period | 2025-04-09 15:08 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 356
202504-NM25-02000 | GDL17 | Comercial | 5.76 | Out of period | 2025-04-13 11:37 | April | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 353
202504-NM25-02098 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-13 14:00 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 291
202504-NM25-02181 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-09 11:00 | September | 2025 | 2026-01-07 15:21 | 120 | Study | Estudio (E) | Activated | Backlog |  | No | 120 |  | PONCE | January |  | 120 | 0 | 2026-04-01 | 204
202504-NM25-02238 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 16:28 | March | 2026 | 2026-03-30 12:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202504-NM25-02260 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-07 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 237
202504-NM25-02262 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-22 07:57 | July | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 253 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 253
202504-NM25-02296 | GDL17 | Residencial | 8 | Out of period | 2025-06-24 07:40 | June | 2025 | 2026-03-25 13:19 | 274 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | March | 1 | 5 | 269 | 2026-04-01 | 281
202504-NM25-02375 | GDL17 | Residencial | 16 | Out of period | 2025-04-15 12:00 | April | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 350
202504-NM25-02443 | GDL17 | Residencial | 8 | Out of period | 2025-04-11 13:00 | April | 2025 | 2026-01-19 09:32 | 283 | Study | Estudio (E) | Activated | Backlog |  | No | 283 |  | CAGUAS | January |  | 283 | 0 | 2026-04-01 | 354
202504-NM25-02518 | GDL17 | Residencial | 8.418 | Out of period | 2025-04-11 15:49 | April | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 354
202504-NM25-02527 | GDL17 | Residencial | 13.48 | Out of period | 2025-09-19 09:00 | September | 2025 | 2026-01-29 10:18 | 132 | Study | Estudio (E) | Activated | Backlog |  | No | 132 |  | BAYAMON | January |  | 132 | 0 | 2026-04-01 | 194
202504-NM25-02539 | GDL17 | Residencial | 9.91 | Out of period | 2025-06-23 07:50 | June | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 282
202504-NM25-02550 | GDL17 | Residencial | 2.4 | Out of period | 2025-04-28 15:28 | April | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 357 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 337
202504-NM25-02617 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:57 | January | 2026 | 2026-01-12 11:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202504-NM25-02631 | GDL17 | Residencial | 3.8 | Out of period | 2025-06-09 19:36 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 295
202504-NM25-02736 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-13 | August | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 231
202504-NM25-02889 | GDL17 | Residencial | 12.81 | Out of period | 2025-04-15 13:22 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 350
202504-NM25-02898 | GDL17 | Residencial | 8 | Out of period | 2025-04-23 16:03 | April | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 342
202504-NM25-02899 | GDL17 | Residencial | 8 | Out of period | 2025-06-20 09:33 | June | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 285
202504-NM25-02913 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-07 13:31 | November | 2025 | 2026-01-12 11:27 | 66 | Study | Estudio (E) | Activated | Backlog |  | No | 66 |  | BAYAMON | January |  | 66 | 0 | 2026-04-01 | 144
202504-NM25-02920 | GDL17 | Residencial | 15.2 | Period | 2026-02-09 08:18 | February | 2026 | 2026-02-12 13:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 51
202504-NM25-02937 | GDL17 | Residencial | 11.5 | Out of period | 2025-04-30 19:32 | April | 2025 | 2026-02-18 08:23 | 294 | Study | Estudio (E) | Activated | Backlog |  | No | 294 |  | CAGUAS | February |  | 294 | 0 | 2026-04-01 | 335
202504-NM25-02947 | GDL17 | Residencial | 8 | Out of period | 2025-06-20 09:41 | June | 2025 | 2026-03-31 09:50 | 284 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 2 | 12 | 272 | 2026-04-01 | 285
202504-NM25-02963 | GDL17 | Residencial | 11.5 | Out of period | 2025-04-15 11:40 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 351
202504-NM25-03105 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-13 21:22 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 322
202504-NM25-03121 | GDL17 | Residencial | 11.5 | Out of period | 2025-04-16 01:13 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 350
202504-NM25-03139 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-05 08:54 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 331
202504-NM25-03241 | GDL17 | Residencial | 11.5 | Out of period | 2025-06-30 08:22 | June | 2025 | 2026-02-25 10:47 | 240 | Study | Estudio (E) | Activated | Backlog |  | No | 240 |  | PONCE | February |  | 241 | 0 | 2026-04-01 | 275
202504-NM25-03351 | GDL17 | Comercial | 23 | Period | 2026-01-27 11:24 | January | 2026 | 2026-01-29 13:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202504-NM25-03414 | GDL17 | Residencial | 21.594 | Out of period | 2025-11-26 10:07 | November | 2025 | 2026-01-05 08:25 | 40 | Study | Estudio (E) | Activated | Backlog |  | No | 40 |  | MAYAGUEZ | January |  | 40 | 0 | 2026-04-01 | 126
202504-NM25-03444 | GDL17 | Residencial | 7.686 | Out of period | 2025-09-09 13:16 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 203
202504-NM25-03719 | GDL17 | Residencial | 5.76 | Out of period | 2025-08-26 | August | 2025 | 2026-01-05 16:00 | 133 | Study | Estudio (E) | Activated | Backlog |  | No | 132 |  | MAYAGUEZ | January |  | 132 | 0 | 2026-04-01 | 218
202504-NM25-03737 | GDL17 | Residencial | 8 | Out of period | 2025-04-29 09:21 | April | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 337
202504-NM25-03774 | GDL17 | Residencial | 11.5 | Out of period | 2025-04-21 15:39 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 344
202504-NM25-03814 | GDL17 | Residencial | 8 | Out of period | 2025-07-16 13:22 | July | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 266 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 258
202504-NM25-03845 | GDL17 | Residencial | 8 | Out of period | 2025-06-06 11:41 | June | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 299
202504-NM25-03862 | GDL17 | Residencial | 11.5 | Out of period | 2025-04-22 09:34 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 344
202504-NM25-03875 | GDL17 | Residencial | 3.8 | Out of period | 2025-06-16 07:17 | June | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 294 | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 289
202504-NM25-03901 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 07:08 | January | 2026 | 2026-01-19 14:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 77
202504-NM25-03920 | GDL17 | Residencial | 7.296 | Out of period | 2025-11-05 12:54 | November | 2025 | 2026-03-26 15:30 | 141 | Study | Estudio (E) | Activated | Backlog |  | No | 141 |  | CAGUAS | March |  | 141 | 0 | 2026-04-01 | 146
202504-NM25-03940 | GDL17 | Residencial | 8 | Out of period | 2025-05-05 09:47 | May | 2025 | 2026-02-17 13:00 | 288 | Study | Estudio (E) | Activated | Backlog |  | No | 288 |  | CAGUAS | February |  | 288 | 0 | 2026-04-01 | 331
202504-NM25-03959 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 11:46 | February | 2026 | 2026-02-20 14:30 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 48
202504-NM25-03985 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-22 13:43 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 343
202504-NM25-04006 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-30 10:54 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 153
202504-NM25-04107 | GDL17 | Residencial | 10.248 | Out of period | 2025-04-28 11:36 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 338
202504-NM25-04239 | GDL17 | Residencial | 6.912 | Period | 2026-03-30 11:28 | March | 2026 | 2026-04-07 13:44 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 8 | 0 | 2026-04-01 | 2
202504-NM25-04299 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-16 14:51 | October | 2025 | 2026-02-10 08:58 | 117 | Study | Estudio (E) | Activated | Backlog |  | No | 117 |  | ARECIBO | February |  | 117 | 0 | 2026-04-01 | 166
202504-NM25-04398 | GDL17 | Residencial | 11.5 | Out of period | 2025-04-23 17:03 | April | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 355 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 342
202504-NM25-04496 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-16 13:33 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 319
202504-NM25-04498 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-02 16:26 | October | 2025 | 2026-01-16 10:40 | 106 | Study | Estudio (E) | Activated | Backlog |  | No | 106 |  | MAYAGUEZ | January |  | 106 | 0 | 2026-04-01 | 180
202504-NM25-04647 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-10 13:57 | September | 2025 | 2026-02-02 08:50 | 145 | Study | Estudio (E) | Activated | Backlog |  | No | 145 |  | SAN JUAN | February |  | 145 | 0 | 2026-04-01 | 202
202504-NM25-04699 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-21 | August | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 223
202504-NM25-04832 | GDL17 | Residencial | 11.5 | Out of period | 2025-04-25 09:18 | April | 2025 | 2026-01-14 11:05 | 264 | Study | Estudio (E) | Activated | Backlog |  | No | 264 |  | ARECIBO | January |  | 264 | 0 | 2026-04-01 | 341
202504-NM25-04860 | GDL17 | Residencial | 8 | Out of period | 2025-05-13 12:35 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 322
202504-NM25-04898 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-23 12:16 | July | 2025 | 2026-03-10 08:31 | 230 | Study | Estudio (E) | Activated | Backlog |  | No | 230 |  | BAYAMON | March |  | 229 | 0 | 2026-04-01 | 251
202504-NM25-04905 | GDL17 | Residencial | 8 | Out of period | 2025-05-07 10:56 | May | 2025 |  |  | Customer Orientation | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 329
202504-NM25-04940 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-16 12:07 | July | 2025 | 2026-01-15 11:13 | 183 | Study | Estudio (E) | Activated | Backlog |  | No | 183 |  | BAYAMON | January |  | 183 | 0 | 2026-04-01 | 258
202504-NM25-04964 | GDL17 | Residencial | 8 | Out of period | 2025-05-13 14:55 | May | 2025 | 2026-03-04 09:47 | 295 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | March | 1 | 2 | 293 | 2026-04-01 | 322
202504-NM25-04980 | GDL17 | Residencial | 8 | Out of period | 2025-05-13 12:58 | May | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 322
202504-NM25-05023 | GDL17 | Residencial | 3.8 | Out of period | 2025-06-30 17:19 | June | 2025 | 2026-02-18 09:41 | 233 | Study | Estudio (E) | Activated | Backlog |  | No | 233 |  | MAYAGUEZ | February |  | 233 | 0 | 2026-04-01 | 274
202504-NM25-05132 | GDL17 | Residencial | 8 | Out of period | 2025-06-24 07:46 | June | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 281
202504-NM25-05143 | GDL17 | Residencial | 11.4 | Out of period | 2025-05-21 14:56 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 314
202504-NM25-05159 | GDL17 | Residencial | 8 | Out of period | 2025-05-14 10:20 | May | 2025 | 2026-03-05 13:33 | 295 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March | 1 | 2 | 293 | 2026-04-01 | 322
202504-NM25-05169 | GDL17 | Residencial | 5.76 | Out of period | 2025-07-11 14:20 | July | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 269 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 263
202504-NM25-05178 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-01 10:06 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 274
202504-NM25-05205 | GDL17 | Residencial | 8 | Out of period | 2025-06-24 07:43 | June | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 281
202504-NM25-05391 | GDL17 | Residencial | 3.8 | Out of period | 2025-08-13 | August | 2025 | 2026-01-26 10:32 | 166 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 160 | 6 | 2026-04-01 | 231
202504-NM25-05441 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-25 | August | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 219
202504-NM25-05490 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 08:45 | February | 2026 | 2026-02-06 15:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202504-NM25-05505 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-27 08:13 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 186
202504-NM25-05514 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 07:03 | January | 2026 | 2026-01-19 08:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 77
202504-NM25-05672 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-15 09:57 | May | 2025 | 2026-02-06 14:03 | 267 | Study | Estudio (E) | Activated | Backlog |  | No | 267 |  | CAGUAS | February |  | 267 | 0 | 2026-04-01 | 321
202504-NM25-05694 | GDL17 | Residencial | 7.6 | Out of period | 2025-04-29 14:34 | April | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 336
202504-NM25-05768 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-16 09:46 | July | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 259
202504-NM25-05846 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 07:50 | January | 2026 | 2026-02-03 12:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202504-NM25-05885 | GDL17 | Comercial | 10 | Out of period | 2025-04-30 11:38 | April | 2025 | 2026-01-08 08:13 | 253 | Study | Estudio (E) | Activated | Backlog |  | No | 253 |  | SAN JUAN | January |  | 252 | 0 | 2026-04-01 | 336
202504-NM25-05920 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-05 | August | 2025 | 2026-02-12 12:39 | 192 | Study | Estudio (E) | Activated | Backlog |  | No | 191 |  | SAN JUAN | February |  | 191 | 0 | 2026-04-01 | 239
202504-NM25-05924 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-24 09:10 | July | 2025 | 2026-01-14 10:00 | 174 | Study | Estudio (E) | Activated | Backlog |  | No | 174 |  | SAN JUAN | January |  | 174 | 0 | 2026-04-01 | 251
202504-NM25-05936 | GDL17 | Residencial | 7.68 | Period | 2026-02-20 14:29 | February | 2026 | 2026-02-26 14:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202505-NM25-00016 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-11 11:34 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 264
202505-NM25-00041 | GDL17 | Residencial | 8 | Out of period | 2025-06-03 13:46 | June | 2025 |  |  | Customer Orientation | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 301
202505-NM25-00078 | GDL17 | Comercial | 3.8 | Out of period | 2025-07-07 16:20 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 267
202505-NM25-00116 | GDL17 | Residencial | 8 | Out of period | 2025-06-24 08:53 | June | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 281
202505-NM25-00322 | GDL17 | Residencial | 23 | Out of period | 2025-08-08 | August | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 236
202505-NM25-00401 | GDL17 | Residencial | 8 | Out of period | 2025-06-17 12:15 | June | 2025 | 2026-02-10 14:03 | 238 | Study | Estudio (E) | Activated | Backlog |  | No | 238 |  | CAGUAS | February |  | 238 | 0 | 2026-04-01 | 287
202505-NM25-00423 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-13 10:32 | September | 2025 | 2026-02-24 11:04 | 164 | Study | Estudio (E) | Activated | Backlog |  | No | 164 |  | BAYAMON | February |  | 164 | 0 | 2026-04-01 | 200
202505-NM25-00444 | GDL17 | Residencial | 3.8 | Out of period | 2025-05-08 14:50 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 327
202505-NM25-00459 | GDL17 | Residencial | 5.76 | Out of period | 2025-07-02 13:51 | July | 2025 | 2026-02-10 15:06 | 223 | Study | Estudio (E) | Activated | Backlog |  | No | 223 |  | SAN JUAN | February |  | 223 | 0 | 2026-04-01 | 272
202505-NM25-00497 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-03 15:29 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 332
202505-NM25-00529 | GDL17 | Residencial | 6.6 | Out of period | 2025-05-05 09:56 | May | 2025 | 2026-02-24 12:52 | 295 | Study | Estudio (E) | Activated | Backlog |  | No | 295 |  | SAN JUAN | February |  | 295 | 0 | 2026-04-01 | 331
202505-NM25-00693 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-18 15:55 | September | 2025 | 2026-02-17 13:34 | 152 | Study | Estudio (E) | Activated | Backlog |  | No | 152 |  | CAGUAS | February |  | 152 | 0 | 2026-04-01 | 194
202505-NM25-00826 | GDL17 | Residencial | 7.6 | Out of period | 2025-05-14 21:56 | May | 2025 | 2026-03-02 13:17 | 292 | Study | Estudio (E) | Activated | Backlog |  | No | 292 |  | BAYAMON | March |  | 292 | 0 | 2026-04-01 | 321
202505-NM25-00889 | GDL17 | Residencial | 17.5 | Out of period | 2025-09-11 14:30 | September | 2025 | 2026-02-25 13:16 | 167 | Study | Estudio (E) | Activated | Backlog |  | No | 167 |  | BAYAMON | February |  | 167 | 0 | 2026-04-01 | 201
202505-NM25-00919 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-14 08:46 | May | 2025 | 2026-03-10 10:09 | 300 | Study | Estudio (E) | Activated | Backlog |  | No | 300 |  | SAN JUAN | March |  | 300 | 0 | 2026-04-01 | 322
202505-NM25-00958 | GDL17 | Comercial | 13.056 | Out of period | 2025-07-10 14:00 | July | 2025 | 2026-02-27 15:01 | 232 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February | 2 | 56 | 176 | 2026-04-01 | 264
202505-NM25-00993 | GDL17 | Comercial | 10.368 | Period | 2026-02-26 14:23 | February | 2026 | 2026-03-23 10:59 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 25 | 0 | 2026-04-01 | 33
202505-NM25-01118 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-30 18:10 | June | 2025 | 2026-01-20 11:28 | 204 | Study | Estudio (E) | Activated | Backlog |  | No | 204 |  | CAGUAS | January |  | 204 | 0 | 2026-04-01 | 274
202505-NM25-01123 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-19 13:20 | May | 2025 | 2026-03-04 08:26 | 289 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March | 1 | 286 | 3 | 2026-04-01 | 316
202505-NM25-01137 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-01 11:07 | September | 2025 | 2026-03-11 08:10 | 191 | Study | Estudio (E) | Activated | Backlog |  | No | 191 |  | ARECIBO | March |  | 191 | 0 | 2026-04-01 | 212
202505-NM25-01146 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:10 | March | 2026 | 2026-03-05 16:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 29
202505-NM25-01179 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-04 10:23 | September | 2025 | 2026-02-12 13:16 | 161 | Study | Estudio (E) | Activated | Backlog |  | No | 161 |  | CAGUAS | February |  | 161 | 0 | 2026-04-01 | 209
202505-NM25-01182 | GDL17 | Residencial | 7.32 | Out of period | 2025-05-07 11:37 | May | 2025 | 2026-01-15 14:52 | 253 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 2 | 57 | 196 | 2026-04-01 | 329
202505-NM25-01196 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 12:35 | March | 2026 | 2026-03-19 08:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 15
202505-NM25-01216 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-07 13:08 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 328
202505-NM25-01382 | GDL17 | Residencial | 8 | Out of period | 2025-08-01 | August | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 243
202505-NM25-01389 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-24 15:02 | July | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 250
202505-NM25-01396 | GDL17 | Residencial | 23 | Period | 2026-02-11 14:08 | February | 2026 | 2026-02-12 13:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202505-NM25-01508 | GDL17 | Residencial | 3.8 | Period | 2026-03-12 12:32 | March | 2026 | 2026-03-23 10:37 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 10 | 1 | 2026-04-01 | 19
202505-NM25-01588 | GDL17 | Residencial | 7.7 | Out of period | 2025-09-02 16:32 | September | 2025 | 2026-03-18 07:56 | 197 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | March | 1 | 26 | 171 | 2026-04-01 | 210
202505-NM25-01655 | GDL17 | Residencial | 8 | Out of period | 2025-05-19 14:00 | May | 2025 | 2026-03-05 11:11 | 290 | Study | Estudio (E) | Activated | Backlog |  | No | 290 |  | PONCE | March |  | 290 | 0 | 2026-04-01 | 316
202505-NM25-01744 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:19 | February | 2026 | 2026-02-05 13:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202505-NM25-01747 | GDL17 | Residencial | 14.592 | Out of period | 2025-05-27 11:02 | May | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 318 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 309
202505-NM25-01749 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-16 12:57 | May | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 332 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 319
202505-NM25-01768 | GDL17 | Residencial | 6.912 | Out of period | 2025-09-29 10:27 | September | 2025 | 2026-03-02 14:50 | 154 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | March | 2 | 37 | 117 | 2026-04-01 | 184
202505-NM25-01835 | GDL17 | Comercial | 6.8 | Out of period | 2025-09-02 20:37 | September | 2025 |  |  | NM Enter Technical Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 210
202505-NM25-01851 | GDL17 | Comercial | 6.8 | Out of period | 2025-09-02 20:35 | September | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 210
202505-NM25-01879 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-10 14:11 | June | 2025 | 2026-03-03 10:31 | 266 | Study | Estudio (E) | Activated | Backlog |  | No | 266 |  | SAN JUAN | March |  | 266 | 0 | 2026-04-01 | 294
202505-NM25-01987 | GDL17 | Residencial | 3.84 | Out of period | 2025-09-09 13:29 | September | 2025 | 2026-03-17 10:41 | 189 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | March |  | 189 | 23 | 2026-04-01 | 203
202505-NM25-02114 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-14 09:37 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 322
202505-NM25-02263 | GDL17 | Comercial | 6 | Out of period | 2025-12-18 21:25 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 103
202505-NM25-02390 | GDL17 | Residencial | 3.072 | Out of period | 2025-05-15 10:47 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 321
202505-NM25-02506 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-15 15:27 | May | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 326 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 320
202505-NM25-02824 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 08:47 | February | 2026 | 2026-02-06 15:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202505-NM25-03012 | GDL17 | Residencial | 3.8 | Out of period | 2025-07-21 10:02 | July | 2025 | 2026-01-23 08:36 | 186 | Study | Estudio (E) | Activated | Backlog |  | No | 186 |  | SAN JUAN | January |  | 185 | 0 | 2026-04-01 | 254
202505-NM25-03086 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-19 15:55 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 316
202505-NM25-03198 | GDL17 | Residencial | 3.8 | Period | 2026-03-04 15:20 | March | 2026 | 2026-03-06 16:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202505-NM25-03261 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-07 17:37 | June | 2025 | 2026-01-05 13:48 | 212 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 2 | 209 | 3 | 2026-04-01 | 297
202505-NM25-03678 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-19 13:26 | September | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 193
202505-NM25-03701 | GDL17 | Residencial | 7.6 | Period | 2026-03-02 09:35 | March | 2026 | 2026-03-12 08:42 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 30
202505-NM25-03847 | GDL17 | Residencial | 8 | Out of period | 2025-06-20 09:44 | June | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 285
202505-NM25-03855 | GDL17 | Residencial | 8 | Out of period | 2025-05-21 14:32 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 314
202505-NM25-03879 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-21 13:17 | May | 2025 | 2026-02-27 08:28 | 282 | Study | Estudio (E) | Activated | Backlog |  | No | 282 |  | ARECIBO | February |  | 282 | 0 | 2026-04-01 | 314
202505-NM25-03923 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 08:59 | February | 2026 | 2026-02-24 14:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202505-NM25-04048 | GDL17 | Residencial | 3.8 | Period | 2026-01-23 10:38 | January | 2026 | 2026-02-11 09:33 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 19 | 0 | 2026-04-01 | 68
202505-NM25-04117 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 14:01 | January | 2026 | 2026-01-20 13:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202505-NM25-04126 | GDL17 | Residencial | 11.5 | Out of period | 2025-05-22 12:36 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 313
202505-NM25-04166 | GDL17 | Residencial | 15 | Out of period | 2025-05-30 19:02 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 305
202505-NM25-04196 | GDL17 | Residencial | 4.224 | Out of period | 2025-08-12 | August | 2025 | 2026-01-08 10:16 | 149 | Study | Estudio (E) | Activated | Backlog |  | No | 149 |  | SAN JUAN | January |  | 149 | 0 | 2026-04-01 | 232
202505-NM25-04271 | GDL17 | Residencial | 8 | Out of period | 2025-05-23 10:09 | May | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 313
202505-NM25-04402 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-19 16:59 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 138 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 132
202505-NM25-04441 | GDL17 | Residencial | 7.75 | Out of period | 2025-07-31 11:47 | July | 2025 | 2026-01-05 10:37 | 158 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 150 | 8 | 2026-04-01 | 244
202505-NM25-04450 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-23 07:21 | June | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 287 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 282
202505-NM25-04490 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-28 08:49 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 247
202505-NM25-04498 | GDL17 | Residencial | 7.7 | Out of period | 2025-07-27 18:24 | July | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 247
202505-NM25-04619 | GDL17 | Residencial | 8 | Out of period | 2025-06-20 09:29 | June | 2025 | 2026-03-12 10:24 | 265 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | March | 1 | 9 | 256 | 2026-04-01 | 285
202505-NM25-04683 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-23 08:07 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 198 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 190
202505-NM25-04766 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-10 19:24 | November | 2025 | 2026-01-12 14:02 | 63 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 2 | 17 | 46 | 2026-04-01 | 141
202505-NM25-04806 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 08:46 | February | 2026 | 2026-02-05 11:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202505-NM25-04848 | GDL17 | Residencial | 9.6 | Period | 2026-01-08 10:40 | January | 2026 | 2026-01-12 15:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 83
202505-NM25-04850 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-28 13:40 | July | 2025 | 2026-01-02 15:25 | 158 | Study | Estudio (E) | Activated | Backlog |  | No | 158 |  | MAYAGUEZ | January |  | 158 | 0 | 2026-04-01 | 246
202505-NM25-05105 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-07 | August | 2025 | 2026-02-12 12:56 | 190 | Study | Estudio (E) | Activated | Backlog |  | No | 189 |  | ARECIBO | February |  | 189 | 0 | 2026-04-01 | 237
202505-NM25-05124 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-13 10:42 | June | 2025 | 2026-03-23 13:42 | 283 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 2 | 12 | 271 | 2026-04-01 | 292
202505-NM25-05203 | GDL17 | Residencial | 10.248 | Out of period | 2025-05-29 15:32 | May | 2025 | 2026-03-13 11:12 | 288 | Study | Estudio (E) | Activated | Backlog |  | No | 288 |  | SAN JUAN | March |  | 288 | 0 | 2026-04-01 | 306
202505-NM25-05251 | GDL17 | Residencial | 7.6 | Period | 2026-03-13 10:23 | March | 2026 | 2026-04-08 08:34 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 26 | 0 | 2026-04-01 | 19
202505-NM25-05414 | GDL17 | Residencial | 11.346 | Out of period | 2025-11-12 11:04 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 140
202505-NM25-05447 | GDL17 | Residencial | 8 | Out of period | 2025-11-17 14:24 | November | 2025 | 2026-01-14 08:41 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | MAYAGUEZ | January |  | 57 | 0 | 2026-04-01 | 134
202506-NM25-00006 | GDL17 | Residencial | 3.8 | Out of period | 2025-08-11 | August | 2025 | 2026-01-28 14:49 | 171 | Study | Estudio (E) | Activated | Backlog |  | No | 170 |  | MAYAGUEZ | January |  | 170 | 0 | 2026-04-01 | 233
202506-NM25-00043 | GDL17 | Residencial | 3.84 | Out of period | 2025-06-27 08:15 | June | 2025 | 2026-02-04 10:35 | 222 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 1 | 211 | 10 | 2026-04-01 | 278
202506-NM25-00231 | GDL17 | Residencial | 3.8 | Period | 2026-01-21 15:51 | January | 2026 | 2026-01-23 15:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202506-NM25-00260 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-11 11:15 | June | 2025 | 2026-01-02 08:54 | 205 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 177 | 2 | 2026-04-01 | 294
202506-NM25-00290 | GDL17 | Residencial | 8 | Out of period | 2025-06-05 11:35 | June | 2025 | 2026-01-02 10:49 | 211 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 11 | 200 | 2026-04-01 | 300
202506-NM25-00350 | GDL17 | Residencial | 11.5 | Out of period | 2025-06-30 11:45 | June | 2025 | 2026-01-15 09:51 | 199 | Study | Estudio (E) | Activated | Backlog |  | No | 199 |  | ARECIBO | January |  | 199 | 0 | 2026-04-01 | 275
202506-NM25-00378 | GDL17 | Residencial | 11.5 | Out of period | 2025-06-03 13:35 | June | 2025 | 2026-03-02 14:08 | 272 | Study | Estudio (E) | Activated | Backlog |  | No | 272 |  | PONCE | March |  | 272 | 0 | 2026-04-01 | 301
202506-NM25-00417 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-24 09:37 | September | 2025 | 2026-01-05 15:53 | 103 | Study | Estudio (E) | Activated | Backlog |  | No | 103 |  | MAYAGUEZ | January |  | 103 | 0 | 2026-04-01 | 189
202506-NM25-00430 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-31 11:31 | July | 2025 | 2026-01-16 07:48 | 169 | Study | Estudio (E) | Activated | Backlog |  | No | 169 |  | SAN JUAN | January |  | 168 | 0 | 2026-04-01 | 244
202506-NM25-00531 | GDL17 | Residencial | 8 | Out of period | 2025-06-24 07:58 | June | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 281
202506-NM25-00728 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 07:27 | March | 2026 | 2026-03-18 08:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 20
202506-NM25-00751 | GDL17 | Comercial | 23 | Out of period | 2025-06-10 08:32 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 295
202506-NM25-00759 | GDL17 | Residencial | 10 | Out of period | 2025-08-18 | August | 2025 | 2026-01-21 15:32 | 157 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 6 | 51 | 105 | 2026-04-01 | 226
202506-NM25-00763 | GDL17 | Comercial | 23 | Period | 2026-01-21 15:16 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 69
202506-NM25-00783 | GDL17 | Residencial | 8 | Out of period | 2025-09-15 12:25 | September | 2025 | 2026-01-13 13:40 | 120 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 16 | 104 | 2026-04-01 | 197
202506-NM25-00790 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 11:10 | March | 2026 | 2026-03-24 16:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 15
202506-NM25-00793 | GDL17 | Residencial | 3.8 | Period | 2026-02-18 09:23 | February | 2026 | 2026-02-25 08:41 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 42
202506-NM25-00798 | GDL17 | Residencial | 3.84 | Period | 2026-03-26 10:17 | March | 2026 | 2026-03-31 13:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202506-NM25-00919 | GDL17 | Residencial | 8.052 | Out of period | 2025-06-19 07:39 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 286
202506-NM25-01031 | GDL17 | Residencial | 3.8 | Out of period | 2025-07-31 18:14 | July | 2025 | 2026-03-04 11:19 | 216 | Study | Estudio (E) | Activated | Backlog |  | No | 216 |  | PONCE | March |  | 216 | 0 | 2026-04-01 | 243
202506-NM25-01073 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-09 09:57 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 296
202506-NM25-01081 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:20 | January | 2026 | 2026-01-12 13:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 84
202506-NM25-01086 | GDL17 | Residencial | 3.66 | Out of period | 2025-06-09 10:21 | June | 2025 | 2026-01-20 15:00 | 225 | Study | Estudio (E) | Activated | Backlog |  | No | 225 |  | SAN JUAN | January |  | 225 | 0 | 2026-04-01 | 296
202506-NM25-01119 | GDL17 | Residencial | 7.7 | Period | 2026-02-17 15:42 | February | 2026 | 2026-02-23 09:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202506-NM25-01173 | GDL17 | Residencial | 8 | Out of period | 2025-06-23 08:47 | June | 2025 | 2026-01-14 12:59 | 205 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 6 | 199 | 2026-04-01 | 282
202506-NM25-01190 | GDL17 | Residencial | 8 | Out of period | 2025-08-15 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 229
202506-NM25-01236 | GDL17 | Residencial | 7.68 | Out of period | 2025-08-19 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 225
202506-NM25-01376 | GDL17 | Residencial | 5.376 | Out of period | 2025-09-17 09:14 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 196
202506-NM25-01461 | GDL17 | Residencial | 10.614 | Out of period | 2025-06-16 10:08 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 289
202506-NM25-01546 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:54 | February | 2026 | 2026-02-05 15:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202506-NM25-01670 | GDL17 | Residencial | 3.8 | Out of period | 2025-08-09 | August | 2025 | 2026-01-05 09:56 | 149 | Study | Estudio (E) | Activated | Backlog |  | No | 149 |  | MAYAGUEZ | January |  | 149 | 0 | 2026-04-01 | 235
202506-NM25-01730 | GDL17 | Residencial | 3.8 | Out of period | 2025-12-18 19:54 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 103
202506-NM25-01756 | GDL17 | Residencial | 3.8 | Out of period | 2025-08-08 | August | 2025 | 2026-01-27 07:56 | 172 | Study | Estudio (E) | Activated | Backlog |  | No | 172 |  | MAYAGUEZ | January |  | 172 | 0 | 2026-04-01 | 236
202506-NM25-01909 | GDL17 | Residencial | 3.8 | Out of period | 2025-08-05 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 239
202506-NM25-01978 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-10 10:27 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 265
202506-NM25-01997 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-31 14:11 | October | 2025 | 2026-01-05 16:15 | 66 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 21 | 45 | 2026-04-01 | 151
202506-NM25-02052 | GDL17 | Residencial | 11.5 | Out of period | 2025-06-12 08:33 | June | 2025 | 2026-01-15 10:22 | 217 | Study | Estudio (E) | Activated | Backlog |  | No | 217 |  | ARECIBO | January |  | 217 | 0 | 2026-04-01 | 293
202506-NM25-02154 | GDL17 | Residencial | 5.76 | Out of period | 2025-09-22 13:57 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 204 | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 190
202506-NM25-02201 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 15:04 | February | 2026 | 2026-02-09 10:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202506-NM25-02226 | GDL17 | Residencial | 13 | Period | 2026-02-03 20:51 | February | 2026 | 2026-03-02 15:17 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 3 | 13 | 14 | 2026-04-01 | 56
202506-NM25-02323 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:49 | March | 2026 | 2026-04-08 07:47 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 19 | 0 | 2026-04-01 | 11
202506-NM25-02329 | GDL17 | Comercial | 4.758 | Out of period | 2025-06-13 11:12 | June | 2025 | 2026-02-04 10:24 | 236 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February | 1 | 5 | 231 | 2026-04-01 | 292
202506-NM25-02330 | GDL17 | Residencial | 2.562 | Out of period | 2025-06-13 11:11 | June | 2025 | 2026-02-10 08:28 | 242 | Study | Estudio (E) | Activated | Backlog |  | No | 242 |  | CAGUAS | February |  | 241 | 0 | 2026-04-01 | 292
202506-NM25-02399 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-31 09:10 | July | 2025 | 2026-01-08 14:50 | 161 | Study | Estudio (E) | Activated | Backlog |  | No | 161 |  | CAGUAS | January |  | 161 | 0 | 2026-04-01 | 244
202506-NM25-02511 | GDL17 | Residencial | 10.98 | Out of period | 2025-06-16 10:18 | June | 2025 | 2026-02-05 17:29 | 234 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | February | 3 | 77 | 157 | 2026-04-01 | 289
202506-NM25-02571 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-19 15:22 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 285
202506-NM25-02607 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-02 11:10 | July | 2025 | 2026-01-07 13:23 | 189 | Study | Estudio (E) | Activated | Backlog |  | No | 189 |  | CAGUAS | January |  | 189 | 0 | 2026-04-01 | 273
202506-NM25-02615 | GDL17 | Residencial | 3.8 | Period | 2026-02-05 12:58 | February | 2026 | 2026-02-10 11:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 54
202506-NM25-02672 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-25 13:43 | June | 2025 | 2026-01-07 14:28 | 196 | Study | Estudio (E) | Activated | Backlog |  | No | 196 |  | MAYAGUEZ | January |  | 196 | 0 | 2026-04-01 | 279
202506-NM25-02673 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-07 | August | 2025 | 2026-01-02 12:39 | 149 | Study | Estudio (E) | Activated | Backlog |  | No | 148 |  | MAYAGUEZ | January |  | 148 | 0 | 2026-04-01 | 237
202506-NM25-02704 | GDL17 | Residencial | 9.6 | Out of period | 2025-11-17 13:48 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 140 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 134
202506-NM25-02727 | GDL17 | Residencial | 3.8 | Period | 2026-02-11 11:44 | February | 2026 | 2026-02-25 14:01 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 49
202506-NM25-02756 | GDL17 | Residencial | 15.738 | Out of period | 2025-09-22 13:19 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 198 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 190
202506-NM25-03013 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:33 | March | 2026 | 2026-03-17 14:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 19
202506-NM25-03069 | GDL17 | Residencial | 18.875 | Out of period | 2025-09-09 09:42 | September | 2025 | 2026-03-10 09:12 | 182 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | March | 7 | 7 | 175 | 2026-04-01 | 204
202506-NM25-03072 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-29 06:46 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 154
202506-NM25-03136 | GDL17 | Residencial | 3.84 | Out of period | 2025-09-10 10:48 | September | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 203
202506-NM25-03145 | GDL17 | Residencial | 8 | Out of period | 2025-06-24 07:54 | June | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 281
202506-NM25-03176 | GDL17 | Residencial | 2.928 | Out of period | 2025-07-02 05:18 | July | 2025 | 2026-01-16 10:56 | 198 | Study | Estudio (E) | Activated | Backlog |  | No | 198 |  | SAN JUAN | January |  | 198 | 0 | 2026-04-01 | 273
202506-NM25-03187 | GDL17 | Residencial | 11.5 | Out of period | 2025-06-19 09:06 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 286
202506-NM25-03214 | GDL17 | Residencial | 10 | Out of period | 2025-06-19 10:35 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 286
202506-NM25-03254 | GDL17 | Residencial | 3.84 | Period | 2026-01-26 14:03 | January | 2026 | 2026-01-28 15:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202506-NM25-03266 | GDL17 | Residencial | 15.2 | Out of period | 2025-10-08 07:46 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 175
202506-NM25-03339 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-06 | August | 2025 | 2026-03-13 13:23 | 220 | Study | Estudio (E) | Activated | Backlog |  | No | 219 |  | ARECIBO | March |  | 219 | 0 | 2026-04-01 | 238
202506-NM25-03457 | GDL17 | Residencial | 12 | Out of period | 2025-07-29 14:29 | July | 2025 | 2026-02-10 10:03 | 196 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February | 1 | 193 | 3 | 2026-04-01 | 245
202506-NM25-03496 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-03 11:35 | October | 2025 | 2026-01-07 08:17 | 96 | Study | Estudio (E) | Activated | Backlog |  | No | 96 |  | BAYAMON | January |  | 96 | 0 | 2026-04-01 | 180
202506-NM25-03607 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 15:23 | January | 2026 | 2026-01-20 16:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 71
202506-NM25-03648 | GDL17 | Residencial | 3.8 | Out of period | 2025-08-07 | August | 2025 | 2026-01-08 13:52 | 155 | Study | Estudio (E) | Activated | Backlog |  | No | 154 |  | MAYAGUEZ | January |  | 154 | 0 | 2026-04-01 | 237
202506-NM25-03780 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-26 | August | 2025 | 2026-03-23 15:17 | 210 | Study | Estudio (E) | Activated | Backlog |  | No | 209 |  | CAGUAS | March |  | 209 | 0 | 2026-04-01 | 218
202506-NM25-03929 | GDL17 | Residencial | 7.6 | Out of period | 2025-06-24 11:48 | June | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 281
202506-NM25-04003 | GDL17 | Residencial | 3.84 | Out of period | 2025-09-23 08:38 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 190
202506-NM25-04041 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-21 | August | 2025 | 2026-02-26 09:39 | 189 | Study | Estudio (E) | Activated | Backlog |  | No | 189 |  | PONCE | February |  | 189 | 0 | 2026-04-01 | 223
202506-NM25-04180 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-10 10:22 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 147 | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 142
202506-NM25-04204 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 08:47 | March | 2026 | 2026-04-02 13:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 1
202506-NM25-04296 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-17 15:22 | September | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 195
202506-NM25-04303 | GDL17 | Residencial | 5 | Period | 2026-02-24 11:42 | February | 2026 | 2026-03-03 14:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 36
202506-NM25-04336 | GDL17 | Residencial | 8 | Out of period | 2025-07-09 07:57 | July | 2025 | 2026-01-02 10:09 | 177 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 13 | 164 | 2026-04-01 | 266
202506-NM25-04378 | GDL17 | Residencial | 3.84 | Period | 2026-01-19 09:55 | January | 2026 | 2026-01-26 14:27 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 72
202506-NM25-04479 | GDL17 | Residencial | 8 | Out of period | 2025-07-03 08:02 | July | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 272
202506-NM25-04483 | GDL17 | Residencial | 8 | Out of period | 2025-06-27 13:56 | June | 2025 | 2026-01-29 12:55 | 216 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 1 | 3 | 213 | 2026-04-01 | 277
202506-NM25-04535 | GDL17 | Residencial | 11.5 | Out of period | 2025-06-30 08:54 | June | 2025 | 2026-01-15 09:46 | 199 | Study | Estudio (E) | Activated | Backlog |  | No | 199 |  | SAN JUAN | January |  | 199 | 0 | 2026-04-01 | 275
202506-NM25-04580 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-18 14:20 | July | 2025 | 2026-02-12 14:52 | 209 | Study | Estudio (E) | Activated | Backlog |  | No | 209 |  | CAGUAS | February |  | 209 | 0 | 2026-04-01 | 256
202506-NM25-04697 | GDL17 | Residencial | 3.84 | Out of period | 2025-06-30 15:50 | June | 2025 | 2026-01-12 12:53 | 196 | Study | Estudio (E) | Activated | Backlog |  | No | 196 |  | MAYAGUEZ | January |  | 196 | 0 | 2026-04-01 | 274
202507-NM25-00013 | GDL17 | Residencial | 4.608 | Out of period | 2025-07-01 09:19 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 274
202507-NM25-00048 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-01 11:42 | July | 2025 | 2026-01-07 08:47 | 190 | Study | Estudio (E) | Activated | Backlog |  | No | 190 |  | MAYAGUEZ | January |  | 190 | 0 | 2026-04-01 | 274
202507-NM25-00057 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-01 11:45 | July | 2025 | 2026-01-15 11:07 | 198 | Study | Estudio (E) | Activated | Backlog |  | No | 198 |  | PONCE | January |  | 198 | 0 | 2026-04-01 | 274
202507-NM25-00065 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-01 13:33 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 273
202507-NM25-00073 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-24 13:53 | July | 2025 | 2026-01-08 14:07 | 168 | Study | Estudio (E) | Activated | Backlog |  | No | 168 |  | ARECIBO | January |  | 168 | 0 | 2026-04-01 | 250
202507-NM25-00085 | GDL17 | Residencial | 7.6 | Period | 2026-02-10 11:23 | February | 2026 | 2026-02-11 14:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 50
202507-NM25-00102 | GDL17 | Residencial | 3.8 | Out of period | 2025-08-03 | August | 2025 | 2026-01-08 11:19 | 158 | Study | Estudio (E) | Activated | Backlog |  | No | 158 |  | MAYAGUEZ | January |  | 158 | 0 | 2026-04-01 | 241
202507-NM25-00104 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:50 | February | 2026 | 2026-02-18 11:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 46
202507-NM25-00155 | GDL17 | Residencial | 8 | Out of period | 2025-07-01 16:00 | July | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 273
202507-NM25-00250 | GDL17 | Residencial | 23 | Period | 2026-02-18 08:59 | February | 2026 | 2026-02-24 14:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202507-NM25-00280 | GDL17 | Residencial | 6 | Period | 2026-02-03 17:50 | February | 2026 | 2026-02-06 15:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202507-NM25-00368 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-09 14:02 | July | 2025 | 2026-01-05 14:42 | 180 | Study | Estudio (E) | Activated | Backlog |  | No | 180 |  | MAYAGUEZ | January |  | 180 | 0 | 2026-04-01 | 265
202507-NM25-00394 | GDL17 | Residencial | 22.8 | Out of period | 2025-08-20 | August | 2025 | 2026-03-31 13:25 | 224 | Study | Estudio (E) | Activated | Backlog |  | No | 223 |  | BAYAMON | March |  | 224 | 0 | 2026-04-01 | 224
202507-NM25-00583 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-05 | August | 2025 | 2026-03-03 10:35 | 210 | Study | Estudio (E) | Activated | Backlog |  | No | 210 |  | PONCE | March |  | 210 | 0 | 2026-04-01 | 239
202507-NM25-00585 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-08 07:21 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 267
202507-NM25-00589 | GDL17 | Residencial | 11.904 | Out of period | 2025-10-16 16:17 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 166
202507-NM25-00645 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-07 13:25 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 267
202507-NM25-00762 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-25 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 219
202507-NM25-00812 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-22 08:43 | July | 2025 | 2026-01-08 08:00 | 170 | Study | Estudio (E) | Activated | Backlog |  | No | 170 |  | ARECIBO | January |  | 170 | 0 | 2026-04-01 | 253
202507-NM25-00832 | GDL17 | Residencial | 4.224 | Out of period | 2025-09-26 09:02 | September | 2025 | 2026-01-07 10:12 | 103 | Study | Estudio (E) | Activated | Backlog |  | No | 103 |  | MAYAGUEZ | January |  | 103 | 0 | 2026-04-01 | 187
202507-NM25-00936 | GDL17 | Residencial | 3.8 | Period | 2026-03-10 12:42 | March | 2026 | 2026-03-25 14:58 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 2 | 13 | 2026-04-01 | 21
202507-NM25-01017 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-06 | August | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | MAYAGUEZ |  |  |  |  | 2026-04-01 | 238
202507-NM25-01185 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-11 11:58 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 264
202507-NM25-01281 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-10 11:00 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 265
202507-NM25-01300 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 20:45 | March | 2026 | 2026-03-17 14:30 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 21
202507-NM25-01310 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-13 16:12 | November | 2025 | 2026-01-05 16:10 | 53 | Study | Estudio (E) | Activated | Backlog |  | No | 53 |  | MAYAGUEZ | January |  | 53 | 0 | 2026-04-01 | 138
202507-NM25-01339 | GDL17 | Residencial | 14.592 | Out of period | 2025-07-11 11:53 | July | 2025 | 2026-01-23 15:19 | 196 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 5 | 191 | 2026-04-01 | 264
202507-NM25-01364 | GDL17 | Residencial | 5.76 | Period | 2026-02-23 13:57 | February | 2026 | 2026-02-27 14:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202507-NM25-01409 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-07 | August | 2025 | 2026-02-17 08:47 | 194 | Study | Estudio (E) | Activated | Backlog |  | No | 194 |  | SAN JUAN | February |  | 194 | 0 | 2026-04-01 | 237
202507-NM25-01489 | GDL17 | Residencial | 3.84 | Out of period | 2025-09-30 10:16 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 183
202507-NM25-01570 | GDL17 | Residencial | 8 | Out of period | 2025-09-02 11:04 | September | 2025 | 2026-03-30 14:10 | 209 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | March | 1 | 8 | 201 | 2026-04-01 | 211
202507-NM25-01617 | GDL17 | Residencial | 5.76 | Out of period | 2025-09-15 16:11 | September | 2025 | 2026-01-07 15:37 | 114 | Study | Estudio (E) | Activated | Backlog |  | No | 114 |  | MAYAGUEZ | January |  | 114 | 0 | 2026-04-01 | 197
202507-NM25-01621 | GDL17 | Residencial | 5.76 | Period | 2026-02-27 16:03 | February | 2026 | 2026-03-25 15:07 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 26 | 0 | 2026-04-01 | 32
202507-NM25-01653 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-26 09:56 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 187
202507-NM25-01663 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-20 | August | 2025 | 2026-02-19 15:54 | 184 | Study | Estudio (E) | Activated | Backlog |  | No | 183 |  | CAGUAS | February |  | 183 | 0 | 2026-04-01 | 224
202507-NM25-01681 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-08 09:51 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 175
202507-NM25-01702 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-14 10:58 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 261
202507-NM25-01712 | GDL17 | Residencial | 8 | Out of period | 2025-07-16 08:07 | July | 2025 | 2026-01-22 12:44 | 190 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 68 | 122 | 2026-04-01 | 259
202507-NM25-01715 | GDL17 | Residencial | 10.368 | Out of period | 2025-09-26 07:57 | September | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 187
202507-NM25-01727 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-30 09:41 | September | 2025 | 2026-01-26 10:50 | 118 | Study | Estudio (E) | Activated | Backlog |  | No | 118 |  | BAYAMON | January |  | 118 | 0 | 2026-04-01 | 183
202507-NM25-01738 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-14 13:22 | July | 2025 | 2026-02-10 13:40 | 211 | Study | Estudio (E) | Activated | Backlog |  | No | 211 |  | MAYAGUEZ | February |  | 211 | 0 | 2026-04-01 | 260
202507-NM25-01781 | GDL17 | Residencial | 9.6 | Out of period | 2025-11-12 09:36 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 140
202507-NM25-01841 | GDL17 | Residencial | 15.2 | Period | 2026-01-26 17:33 | January | 2026 | 2026-01-28 15:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202507-NM25-01895 | GDL17 | Residencial | 8 | Out of period | 2025-08-11 | August | 2025 | 2026-03-11 14:04 | 213 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | March | 1 | 23 | 189 | 2026-04-01 | 233
202507-NM25-01905 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-15 10:23 | July | 2025 | 2026-01-02 07:55 | 171 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 123 | 48 | 2026-04-01 | 260
202507-NM25-01932 | GDL17 | Residencial | 2.36 | Out of period | 2025-07-15 11:49 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 260
202507-NM25-01946 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-11 | August | 2025 | 2026-03-11 13:50 | 213 | Study | Estudio (E) | Activated | Backlog |  | No | 212 |  | CAGUAS | March |  | 212 | 0 | 2026-04-01 | 233
202507-NM25-02078 | GDL17 | Residencial | 11.5 | Period | 2026-02-08 21:10 | February | 2026 | 2026-02-10 16:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 51
202507-NM25-02132 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-03 07:55 | September | 2025 | 2026-01-28 16:25 | 147 | Study | Estudio (E) | Activated | Backlog |  | No | 147 |  | SAN JUAN | January |  | 148 | 0 | 2026-04-01 | 210
202507-NM25-02231 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-26 08:50 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 187
202507-NM25-02270 | GDL17 | Residencial | 8 | Out of period | 2025-08-06 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 238
202507-NM25-02290 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-30 07:48 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 183
202507-NM25-02318 | GDL17 | Residencial | 3.8 | Period | 2026-01-26 17:00 | January | 2026 | 2026-01-28 16:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202507-NM25-02350 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-08 08:22 | September | 2025 | 2026-01-29 07:38 | 143 | Study | Estudio (E) | Activated | Backlog |  | No | 143 |  | ARECIBO | January |  | 143 | 0 | 2026-04-01 | 205
202507-NM25-02386 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-17 10:18 | July | 2025 | 2026-01-29 18:12 | 196 | Study | Estudio (E) | Activated | Backlog |  | No | 196 |  | ARECIBO | January |  | 196 | 0 | 2026-04-01 | 258
202507-NM25-02394 | GDL17 | Residencial | 6.528 | Period | 2026-03-24 14:13 | March | 2026 | 2026-04-01 07:53 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 8 | 0 | 2026-04-01 | 7
202507-NM25-02403 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:31 | January | 2026 | 2026-01-14 10:33 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 82
202507-NM25-02426 | GDL17 | Residencial | 3.84 | Period | 2026-02-25 17:30 | February | 2026 | 2026-03-10 07:56 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 34
202507-NM25-02451 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-17 12:09 | July | 2025 | 2026-01-09 09:33 | 176 | Study | Estudio (E) | Activated | Backlog |  | No | 176 |  | MAYAGUEZ | January |  | 176 | 0 | 2026-04-01 | 257
202507-NM25-02459 | GDL17 | Residencial | 12.288 | Period | 2026-02-16 11:25 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 44
202507-NM25-02460 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:01 | January | 2026 | 2026-01-20 15:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 71
202507-NM25-02530 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-24 15:06 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 250
202507-NM25-02547 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-18 09:08 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 257
2025-GD-00117 | GD1M | Comercial | 66 | Out of period | 2025-07-14 | July | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 261
2025-GD-00113 | GD1M | Comercial | 66 | Out of period | 2025-07-03 | July | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 272
2025-GD-00114 | GD1M | Comercial | 133.2 | Out of period | 2025-07-03 | July | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 272
2025-GD-00124 | GD1M | Comercial | 30 | Out of period | 2025-07-23 | July | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 252
2025-GD-00122 | GD1M | Comercial | 83.3 | Out of period | 2025-07-23 | July | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 252
2025-GD-00119 | GD1M | Comercial | 25.99 | Out of period | 2025-07-15 | July | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 260
2025-GD-00125 | GD1M | Comercial | 42 | Out of period | 2025-07-24 | July | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 251
2025-GD-00126 | GD1M | Comercial | 30 | Out of period | 2025-07-26 | July | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 249
2025-GD-00120 | GD1M | Comercial | 120 | Out of period | 2025-07-16 | July | 2025 |  |  | Anejar Certificacion e Instalacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 259
2025-GD-00121 | GD1M | Comercial | 120 | Out of period | 2025-07-16 | July | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 259
2025-GD-00123 | GD1M | Comercial | 83.3 | Out of period | 2025-07-23 | July | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 252
2025-GD-00118 | GD1M | Comercial | 150 | Out of period | 2025-07-14 | July | 2025 |  |  | Finalizar estudio o indicar pago por mejora | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 261
2025-GD-00115 | GD1M | Comercial | 28 | Out of period | 2025-07-07 | July | 2025 |  |  | Pago Aportacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 268
2025-GD-00116 | GD1M | Comercial | 264 | Out of period | 2025-07-09 | July | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 266
2025-GD-00130 | GD1M | Comercial | 36 | Out of period | 2025-08-12 | August | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 232
2025-GD-00137 | GD1M | Comercial | 29.66 | Out of period | 2025-08-19 | August | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 225
2025-GD-00143 | GD1M | Gubernamental | 31.2 | Out of period | 2025-08-27 | August | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 217
2025-GD-00139 | GD1M | Comercial | 66 | Out of period | 2025-08-20 | August | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 224
2025-GD-00136 | TRANSMISSION | Industrial | 999 | Out of period | 2025-08-15 | August | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 229
2025-GD-00141 | GD1M | Comercial | 42 | Out of period | 2025-08-21 | August | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 223
2025-GD-00128 | GD10K | Residencial | 6.8 | Out of period | 2025-08-07 | August | 2025 |  |  | Validación | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 237
2025-GD-00142 | TRANSMISSION | Industrial | - | Out of period | 2025-08-27 | August | 2025 |  |  | approveTransmissionEnd | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 217
2025-GD-00135 | GD1M | Comercial | 67.5 | Out of period | 2025-08-14 | August | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 230
2025-GD-00133 | GD1M | Comercial | 495.3 | Out of period | 2025-08-13 | August | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 231
2025-GD-00140 | GD1M | Residencial | 240 | Out of period | 2025-08-21 | August | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 223
2025-GD-00127 | GD1M | Gubernamental | 49.92 | Out of period | 2025-08-07 | August | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 237
2025-GD-00129 | GD1M | Comercial | 30 | Out of period | 2025-08-08 | August | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 236
2025-GD-00132 | GD1M | Comercial | 42 | Out of period | 2025-08-12 | August | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 232
2025-GD-00134 | GD1M | Comercial | 37.27 | Out of period | 2025-08-14 | August | 2025 |  |  | Inspeccion de Campo | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 230
2025-GD-00131 | GD1M | Comercial | 37.5 | Out of period | 2025-08-12 | August | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 232
2025-GD-00138 | GD1M | Comercial | 30 | Out of period | 2025-08-20 | August | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAROLINA |  |  |  |  | 2026-04-01 | 224
2025-GD-00145 | GD1M | Comercial | 72 | Out of period | 2025-09-05 | September | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 208
2025-GD-00154 | GD1M | Residencial | 34.5 | Out of period | 2025-09-18 | September | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 195
2025-GD-00148 | GD1M | Industrial | 53 | Out of period | 2025-09-11 | September | 2025 |  |  | Anejar Documentos, Asignar Inspector | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 202
2025-GD-00164 | GD1M | Comercial | 34.5 | Out of period | 2025-09-24 | September | 2025 |  |  | Pago Aportacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 189
2025-GD-00147 | GD1M | Comercial | 46.6 | Out of period | 2025-09-10 | September | 2025 |  |  | Pago Aportacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 203
2025-GD-00156 | GD1M | Comercial | 1625 | Out of period | 2025-09-19 | September | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 194
2025-GD-00167 | GD1M | Comercial | 93.6 | Out of period | 2025-09-30 | September | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 183
2025-GD-00150 | GD1M | Comercial | 36 | Out of period | 2025-09-11 | September | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 202
2025-GD-00161 | GD1M | Residencial | 26.112 | Out of period | 2025-09-22 | September | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 191
2025-GD-00162 | GD1M | Industrial | 30 | Out of period | 2025-09-23 | September | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 190
2025-GD-00159 | GD1M | Residencial | 34.5 | Out of period | 2025-09-19 | September | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 194
2025-GD-00144 | GD1M | Residencial | 66 | Out of period | 2025-09-05 | September | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 208
2025-GD-00155 | GD1M | Comercial | 660 | Out of period | 2025-09-19 | September | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 194
2025-GD-00166 | GD1M | Gubernamental | 36 | Out of period | 2025-09-29 | September | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 184
202507-NM25-02580 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-07 15:13 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 175
2025-GD-00157 | GD1M | Comercial | 30.9 | Out of period | 2025-09-19 | September | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 194
2025-GD-00165 | TRANSMISSION | Comercial | - | Out of period | 2025-09-26 | September | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 187
2025-GD-00153 | GD1M | Comercial | 44 | Out of period | 2025-09-17 | September | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 196
2025-GD-00158 | GD1M | Comercial | 41.2 | Out of period | 2025-09-19 | September | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 194
2025-GD-00152 | GD1M | Gubernamental | 30 | Out of period | 2025-09-17 | September | 2025 |  |  | Anejar Certificacion e Instalacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 196
2025-GD-00160 | GD1M | Residencial | 34.5 | Out of period | 2025-09-22 | September | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 191
2025-GD-00146 | GD1M | Comercial | 75 | Out of period | 2025-09-08 | September | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 205
2025-GD-00149 | GD1M | Comercial | 212 | Out of period | 2025-09-11 | September | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 202
202507-NM25-02582 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-18 12:51 | July | 2025 | 2026-02-10 10:25 | 207 | Study | Estudio (E) | Activated | Backlog |  | No | 207 |  | ARECIBO | February |  | 207 | 0 | 2026-04-01 | 256
202507-NM25-02588 | GDL17 | Residencial | 5.76 | Out of period | 2025-10-07 13:11 | October | 2025 | 2026-02-13 15:57 | 129 | Study | Estudio (E) | Activated | Backlog |  | No | 129 |  | CAGUAS | February |  | 129 | 0 | 2026-04-01 | 175
202507-NM25-02618 | GDL17 | Residencial | 16.512 | Out of period | 2025-11-25 15:32 | November | 2025 | 2026-01-14 12:45 | 50 | Study | Estudio (E) | Activated | Backlog |  | No | 50 |  | CAGUAS | January |  | 50 | 0 | 2026-04-01 | 126
202507-NM25-02621 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-24 13:18 | July | 2025 | 2026-02-10 10:42 | 201 | Study | Estudio (E) | Activated | Backlog |  | No | 201 |  | ARECIBO | February |  | 201 | 0 | 2026-04-01 | 250
202507-NM25-02622 | GDL17 | Residencial | 2.8 | Out of period | 2025-07-22 16:39 | July | 2025 | 2026-01-12 13:13 | 174 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 4 | 83 | 91 | 2026-04-01 | 252
202507-NM25-02651 | GDL17 | Residencial | 12 | Period | 2026-02-02 11:47 | February | 2026 | 2026-02-10 14:47 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 58
202507-NM25-02653 | GDL17 | Residencial | 10 | Out of period | 2025-07-23 10:36 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 252
202507-NM25-02738 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-30 | August | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 222 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 214
202507-NM25-02750 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-24 11:08 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 195 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 189
202507-NM25-02780 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:25 | January | 2026 | 2026-01-13 11:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202507-NM25-02781 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-23 07:53 | September | 2025 | 2026-03-18 08:33 | 176 | Study | Estudio (E) | Activated | Backlog |  | No | 176 |  | PONCE | March |  | 177 | 0 | 2026-04-01 | 190
202507-NM25-02807 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-30 16:55 | July | 2025 | 2026-01-16 12:46 | 170 | Study | Estudio (E) | Activated | Backlog |  | No | 170 |  | ARECIBO | January |  | 170 | 0 | 2026-04-01 | 244
202507-NM25-02808 | GDL17 | Residencial | 6.528 | Period | 2026-01-21 17:34 | January | 2026 | 2026-01-28 14:49 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 69
202507-NM25-02853 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-26 09:53 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 187
202507-NM25-02900 | GDL17 | Residencial | 10 | Out of period | 2025-09-17 15:36 | September | 2025 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 195
202507-NM25-02930 | GDL17 | Residencial | 5 | Out of period | 2025-08-02 | August | 2025 | 2026-01-16 12:55 | 168 | Study | Estudio (E) | Activated | Backlog |  | No | 167 |  | MAYAGUEZ | January |  | 167 | 0 | 2026-04-01 | 242
202507-NM25-03010 | GDL17 | Residencial | 8 | Out of period | 2025-08-20 | August | 2025 | 2026-02-10 11:09 | 174 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 9 | 165 | 2026-04-01 | 224
202507-NM25-03138 | GDL17 | Residencial | 12 | Out of period | 2025-08-08 | August | 2025 | 2026-01-02 10:14 | 147 | Study | Estudio (E) | Activated | Backlog |  | No | 147 |  | MAYAGUEZ | January |  | 147 | 0 | 2026-04-01 | 236
202507-NM25-03170 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-22 12:25 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 252
202507-NM25-03199 | GDL17 | Residencial | 9.984 | Period | 2026-01-26 17:59 | January | 2026 | 2026-01-28 15:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202507-NM25-03290 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-08 13:13 | September | 2025 | 2026-02-16 14:34 | 161 | Study | Estudio (E) | Activated | Backlog |  | No | 161 |  | BAYAMON | February |  | 161 | 0 | 2026-04-01 | 204
202507-NM25-03365 | GDL17 | Residencial | 3.8 | Period | 2026-02-13 16:26 | February | 2026 | 2026-03-20 09:28 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 6 | 29 | 2026-04-01 | 46
202507-NM25-03405 | GDL17 | Residencial | 7.68 | Period | 2026-02-27 09:04 | February | 2026 | 2026-03-05 09:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 33
202507-NM25-03435 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:09 | January | 2026 | 2026-01-14 07:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 83
202507-NM25-03463 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-23 09:35 | July | 2025 | 2026-03-03 10:43 | 223 | Study | Estudio (E) | Activated | Backlog |  | No | 223 |  | SAN JUAN | March |  | 224 | 0 | 2026-04-01 | 252
202507-NM25-03480 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:09 | February | 2026 | 2026-02-09 15:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 55
202507-NM25-03544 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:58 | January | 2026 | 2026-01-09 09:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 84
202507-NM25-03571 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-23 12:57 | July | 2025 | 2026-01-28 14:02 | 189 | Study | Estudio (E) | Activated | Backlog |  | No | 189 |  | MAYAGUEZ | January |  | 189 | 0 | 2026-04-01 | 251
202507-NM25-03600 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-23 14:00 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 251
202507-NM25-03623 | GDL17 | Residencial | 18 | Out of period | 2025-09-25 12:53 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 187
202507-NM25-03684 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-12 10:00 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 148 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 140
202507-NM25-03711 | GDL17 | Residencial | 3.8 | Period | 2026-02-01 14:52 | February | 2026 | 2026-02-04 13:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 58
202507-NM25-03730 | GDL17 | Residencial | 3.84 | Out of period | 2025-08-27 | August | 2025 | 2026-01-08 15:21 | 135 | Study | Estudio (E) | Activated | Backlog |  | No | 134 |  | MAYAGUEZ | January |  | 134 | 0 | 2026-04-01 | 217
202507-NM25-03813 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-31 16:04 | July | 2025 | 2026-01-15 12:46 | 168 | Study | Estudio (E) | Activated | Backlog |  | No | 168 |  | MAYAGUEZ | January |  | 168 | 0 | 2026-04-01 | 243
202507-NM25-03815 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-11 08:39 | September | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 202
202507-NM25-03876 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-18 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 226
202507-NM25-03899 | GDL17 | Residencial | 5.76 | Period | 2026-03-30 10:00 | March | 2026 | 2026-04-21 13:48 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 22 | 0 | 2026-04-01 | 2
202507-NM25-03933 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-25 09:15 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 250
202507-NM25-03949 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:51 | January | 2026 | 2026-01-13 16:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202507-NM25-03952 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-25 10:29 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 250
202507-NM25-03984 | GDL17 | Residencial | 11.5 | Out of period | 2025-07-25 13:26 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 249
202507-NM25-03987 | GDL17 | Residencial | 23 | Period | 2026-02-09 15:46 | February | 2026 | 2026-02-11 13:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 50
202507-NM25-03995 | GDL17 | Comercial | 4.224 | Period | 2026-02-13 12:35 | February | 2026 | 2026-02-18 12:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 46
202507-NM25-04026 | GDL17 | Residencial | 7.7 | Out of period | 2025-12-23 08:04 | December | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 99
202507-NM25-04039 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 12:42 | January | 2026 | 2026-01-12 10:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 83
202507-NM25-04042 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:27 | January | 2026 | 2026-01-28 15:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202507-NM25-04061 | GDL17 | Residencial | 12 | Out of period | 2025-09-29 08:45 | September | 2025 | 2026-01-15 14:16 | 108 | Study | Estudio (E) | Activated | Backlog |  | No | 108 |  | ARECIBO | January |  | 108 | 0 | 2026-04-01 | 184
202507-NM25-04178 | GDL17 | Residencial | 10 | Period | 2026-01-26 18:02 | January | 2026 | 2026-01-28 15:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202507-NM25-04196 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-02 10:17 | September | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 211
202507-NM25-04211 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-06 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 238
202507-NM25-04277 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 09:12 | February | 2026 | 2026-02-06 14:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 56
202507-NM25-04288 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-12 09:51 | November | 2025 | 2026-01-15 10:02 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | MAYAGUEZ | January |  | 64 | 0 | 2026-04-01 | 140
202507-NM25-04386 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-16 13:17 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 205 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 196
202507-NM25-04419 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:56 | February | 2026 | 2026-02-06 13:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202507-NM25-04423 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-01 13:55 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 181
202507-NM25-04426 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:45 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 33
202507-NM25-04527 | GDL17 | Residencial | 11.4 | Out of period | 2025-09-01 16:54 | September | 2025 | 2026-01-08 12:55 | 129 | Study | Estudio (E) | Activated | Backlog |  | No | 129 |  | MAYAGUEZ | January |  | 129 | 0 | 2026-04-01 | 211
202507-NM25-04531 | GDL17 | Residencial | 24 | Period | 2026-02-21 09:26 | February | 2026 | 2026-02-26 08:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 39
202507-NM25-04562 | GDL17 | Residencial | 3.84 | Period | 2026-03-13 07:56 | March | 2026 | 2026-04-22 14:59 | 40 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 40 | 0 | 2026-04-01 | 19
202507-NM25-04683 | GDL17 | Residencial | 5.76 | Period | 2026-02-25 15:23 | February | 2026 | 2026-03-06 07:58 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 34
202507-NM25-04705 | GDL17 | Residencial | 9 | Out of period | 2025-07-29 21:36 | July | 2025 | 2026-03-02 16:19 | 216 | Study | Estudio (E) | Activated | Backlog |  | No | 216 |  | SAN JUAN | March |  | 216 | 0 | 2026-04-01 | 245
202507-NM25-04757 | GDL17 | Comercial | 11.5 | Out of period | 2025-07-30 10:11 | July | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 245
202507-NM25-04760 | GDL17 | Residencial | 5.376 | Out of period | 2025-08-14 | August | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 230
202507-NM25-04806 | GDL17 | Residencial | 4.608 | Out of period | 2025-07-30 11:57 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 245
202507-NM25-04811 | GDL17 | Comercial | 5 | Out of period | 2025-07-30 16:36 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 244
202507-NM25-04921 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 16:27 | January | 2026 | 2026-01-13 10:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202507-NM25-04953 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:02 | February | 2026 | 2026-02-16 08:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 49
202507-NM25-04965 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-31 08:49 | July | 2025 | 2026-01-29 15:26 | 182 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 76 | 106 | 2026-04-01 | 244
202507-NM25-04980 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-17 13:27 | September | 2025 | 2026-01-12 16:05 | 117 | Study | Estudio (E) | Activated | Backlog |  | No | 117 |  | MAYAGUEZ | January |  | 117 | 0 | 2026-04-01 | 195
202507-NM25-04988 | GDL17 | Residencial | 3.8 | Out of period | 2025-08-29 | August | 2025 | 2026-01-02 13:41 | 127 | Study | Estudio (E) | Activated | Backlog |  | No | 126 |  | MAYAGUEZ | January |  | 126 | 0 | 2026-04-01 | 215
202507-NM25-04993 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 17:57 | January | 2026 | 2026-01-14 15:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 82
202507-NM25-05003 | GDL17 | Residencial | 4.608 | Out of period | 2025-07-31 09:45 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 244
202507-NM25-05037 | GDL17 | Residencial | 12 | Out of period | 2025-08-19 | August | 2025 | 2026-01-19 10:56 | 153 | Study | Estudio (E) | Activated | Backlog |  | No | 153 |  | MAYAGUEZ | January |  | 153 | 0 | 2026-04-01 | 225
202507-NM25-05066 | GDL17 | Residencial | 7.6 | Out of period | 2025-07-31 11:48 | July | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 244
202507-NM25-05091 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-25 | August | 2025 | 2026-01-22 12:54 | 151 | Study | Estudio (E) | Activated | Backlog |  | No | 150 |  | BAYAMON | January |  | 150 | 0 | 2026-04-01 | 219
202507-NM25-05122 | GDL17 | Residencial | 8 | Out of period | 2025-08-15 | August | 2025 | 2026-03-12 13:07 | 210 | Study | Estudio (E) | Activated | Backlog |  | No | 209 |  | ARECIBO | March |  | 209 | 0 | 2026-04-01 | 229
202507-NM25-05130 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 16:23 | January | 2026 | 2026-01-26 11:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 69
202507-NM25-05157 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:48 | January | 2026 | 2026-01-12 16:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 82
202507-NM25-05198 | GDL17 | Residencial | 4.224 | Out of period | 2025-11-04 09:41 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 148
202507-NM25-05207 | GDL17 | Residencial | 7.7 | Out of period | 2025-08-04 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 240
202507-NM25-05217 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-24 10:01 | October | 2025 | 2026-01-02 14:49 | 70 | Study | Estudio (E) | Activated | Backlog |  | No | 70 |  | BAYAMON | January |  | 70 | 0 | 2026-04-01 | 159
202508-NM25-00016 | GDL17 | Residencial | 8.448 | Out of period | 2025-08-22 | August | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | PONCE |  |  |  |  | 2026-04-01 | 222
202508-NM25-00037 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-12 13:27 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 200
202508-NM25-00095 | GDL17 | Residencial | 3.84 | Out of period | 2025-11-12 07:30 | November | 2025 | 2026-01-05 15:36 | 54 | Study | Estudio (E) | Activated | Backlog |  | No | 54 |  | MAYAGUEZ | January |  | 55 | 0 | 2026-04-01 | 140
202508-NM25-00100 | GDL17 | Comercial | 13.5 | Out of period | 2025-10-10 10:40 | October | 2025 | 2026-01-16 14:11 | 98 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 2 | 40 | 58 | 2026-04-01 | 173
202508-NM25-00105 | GDL17 | Comercial | 13.5 | Out of period | 2025-10-10 10:37 | October | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 173
202508-NM25-00108 | GDL17 | Residencial | 5.376 | Out of period | 2025-10-07 10:54 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 176
202508-NM25-00118 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-02 08:35 | October | 2025 | 2026-01-13 15:03 | 103 | Study | Estudio (E) | Activated | Backlog |  | No | 103 |  | MAYAGUEZ | January |  | 103 | 0 | 2026-04-01 | 181
202508-NM25-00129 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-23 | August | 2025 | 2026-03-25 11:03 | 214 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 172 | 42 | 2026-04-01 | 221
202508-NM25-00149 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-10 18:52 | November | 2025 | 2026-01-14 08:14 | 65 | Study | Estudio (E) | Activated | Backlog |  | No | 65 |  | CAGUAS | January |  | 65 | 0 | 2026-04-01 | 141
202508-NM25-00191 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:52 | January | 2026 | 2026-01-28 10:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202508-NM25-00205 | GDL17 | Residencial | 4.992 | Out of period | 2025-10-30 10:10 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 153
202508-NM25-00270 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-18 10:40 | September | 2025 | 2026-01-20 08:28 | 124 | Study | Estudio (E) | Activated | Backlog |  | No | 124 |  | ARECIBO | January |  | 124 | 0 | 2026-04-01 | 195
202508-NM25-00416 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-04 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 240
202508-NM25-00429 | GDL17 | Residencial | 24 | Out of period | 2025-08-05 | August | 2025 | 2026-01-08 14:32 | 157 | Study | Estudio (E) | Activated | Backlog |  | No | 156 |  | BAYAMON | January |  | 156 | 0 | 2026-04-01 | 239
202508-NM25-00437 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 12:55 | January | 2026 | 2026-01-16 10:26 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 82
202508-NM25-00456 | GDL17 | Residencial | 8 | Out of period | 2025-08-11 | August | 2025 | 2026-03-02 14:55 | 204 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March | 1 | 8 | 195 | 2026-04-01 | 233
202508-NM25-00468 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:58 | January | 2026 | 2026-01-14 08:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 81
202508-NM25-00500 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-28 | August | 2025 | 2026-01-05 15:18 | 131 | Study | Estudio (E) | Activated | Backlog |  | No | 130 |  | MAYAGUEZ | January |  | 130 | 0 | 2026-04-01 | 216
202508-NM25-00510 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:28 | January | 2026 | 2026-01-22 12:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 69
202508-NM25-00515 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:50 | January | 2026 | 2026-01-13 14:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 83
202508-NM25-00577 | GDL17 | Residencial | 5.76 | Period | 2026-03-03 09:44 | March | 2026 | 2026-03-05 14:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 29
202508-NM25-00612 | GDL17 | Residencial | 3.84 | Period | 2026-01-28 14:21 | January | 2026 | 2026-02-03 11:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 62
202508-NM25-00666 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-06 09:50 | November | 2025 | 2026-01-29 13:44 | 84 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 43 | 41 | 2026-04-01 | 146
202508-NM25-00698 | GDL17 | Residencial | 5.124 | Out of period | 2025-08-10 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 234
202508-NM25-00700 | GDL17 | Residencial | 6.912 | Out of period | 2025-08-14 | August | 2025 | 2026-01-19 13:05 | 159 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 62 | 96 | 2026-04-01 | 230
202508-NM25-00713 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:34 | January | 2026 | 2026-01-19 12:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 76
202508-NM25-00744 | GDL17 | Residencial | 3.84 | Out of period | 2025-10-04 10:49 | October | 2025 | 2026-01-29 08:17 | 117 | Study | Estudio (E) | Activated | Backlog |  | No | 117 |  | SAN JUAN | January |  | 117 | 0 | 2026-04-01 | 179
202508-NM25-00747 | GDL17 | Residencial | 5.76 | Period | 2026-02-27 08:45 | February | 2026 | 2026-03-03 16:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202508-NM25-00786 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-08 16:09 | September | 2025 | 2026-02-10 10:29 | 155 | Study | Estudio (E) | Activated | Backlog |  | No | 155 |  | SAN JUAN | February |  | 155 | 0 | 2026-04-01 | 204
202508-NM25-00875 | GDL17 | Residencial | 8 | Out of period | 2025-08-05 | August | 2025 | 2026-01-20 12:34 | 169 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 167 | 1 | 2026-04-01 | 239
202508-NM25-00935 | GDL17 | Residencial | 9.6 | Period | 2026-03-27 08:07 | March | 2026 | 2026-03-31 14:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 5
202508-NM25-00984 | GDL17 | Residencial | 3.84 | Period | 2026-02-04 08:08 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 56
202508-NM25-01009 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-08 | August | 2025 | 2026-01-13 12:54 | 159 | Study | Estudio (E) | Activated | Backlog |  | No | 158 |  | CAGUAS | January |  | 158 | 0 | 2026-04-01 | 236
202508-NM25-01068 | GDL17 | Residencial | 5.76 | Out of period | 2025-11-05 14:23 | November | 2025 | 2026-02-12 15:59 | 99 | Study | Estudio (E) | Activated | Backlog |  | No | 99 |  | BAYAMON | February |  | 99 | 0 | 2026-04-01 | 146
202508-NM25-01142 | GDL17 | Residencial | 8.832 | Out of period | 2025-08-06 | August | 2025 | 2026-02-19 09:13 | 197 | Study | Estudio (E) | Activated | Backlog |  | No | 197 |  | CAGUAS | February |  | 197 | 0 | 2026-04-01 | 238
202508-NM25-01162 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:40 | January | 2026 | 2026-01-26 08:19 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 75
202508-NM25-01187 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 17:02 | January | 2026 | 2026-01-26 15:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 69
202508-NM25-01223 | GDL17 | Residencial | 10 | Period | 2026-01-29 13:43 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 61
202508-NM25-01298 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 16:34 | January | 2026 | 2026-02-09 16:29 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 33 | 0 | 2026-04-01 | 83
202508-NM25-01333 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-06 | August | 2025 | 2026-01-20 11:01 | 167 | Study | Estudio (E) | Activated | Backlog |  | No | 167 |  | CAGUAS | January |  | 167 | 0 | 2026-04-01 | 238
202508-NM25-01358 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-29 07:13 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 154
202508-NM25-01396 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-14 | August | 2025 | 2026-01-21 12:54 | 161 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 2 | 151 | 6 | 2026-04-01 | 230
202508-NM25-01461 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 12:10 | March | 2026 | 2026-03-25 14:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 1 | 6 | 2026-04-01 | 13
202508-NM25-01474 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-03 14:17 | October | 2025 | 2026-01-22 15:06 | 111 | Study | Estudio (E) | Activated | Backlog |  | No | 111 |  | SAN JUAN | January |  | 111 | 0 | 2026-04-01 | 179
202508-NM25-01512 | GDL17 | Residencial | 5.376 | Out of period | 2025-09-10 14:21 | September | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 202
202508-NM25-01549 | GDL17 | Residencial | 5.76 | Period | 2026-02-11 17:04 | February | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 48
202508-NM25-01553 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-15 13:55 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 167
202508-NM25-01558 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 12:59 | January | 2026 | 2026-03-12 16:23 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March | 1 | 36 | 6 | 2026-04-01 | 61
202508-NM25-01581 | GDL17 | Comercial | 5.3 | Out of period | 2025-09-30 08:38 | September | 2025 | 2026-01-30 08:56 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 68 | 54 | 2026-04-01 | 183
202508-NM25-01583 | GDL17 | Residencial | 3.84 | Period | 2026-01-29 13:05 | January | 2026 | 2026-02-17 13:49 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 19 | 0 | 2026-04-01 | 61
202508-NM25-01586 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:08 | October | 2025 | 2026-02-16 15:48 | 137 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 77 | 60 | 2026-04-01 | 181
202508-NM25-01587 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:12 | October | 2025 | 2026-02-17 16:16 | 138 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 84 | 54 | 2026-04-01 | 181
202508-NM25-01588 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:26 | October | 2025 | 2026-02-17 16:09 | 138 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 84 | 54 | 2026-04-01 | 181
202508-NM25-01589 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 10:57 | January | 2026 | 2026-03-17 10:08 | 62 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 36 | 26 | 2026-04-01 | 77
202508-NM25-01590 | GDL17 | Comercial | 4.5 | Out of period | 2025-10-02 09:24 | October | 2025 | 2026-02-17 16:05 | 138 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 84 | 54 | 2026-04-01 | 181
202508-NM25-01591 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:27 | October | 2025 | 2026-01-22 15:29 | 112 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 58 | 54 | 2026-04-01 | 181
202508-NM25-01592 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:29 | October | 2025 | 2026-01-30 09:02 | 120 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 66 | 54 | 2026-04-01 | 181
202508-NM25-01593 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:30 | October | 2025 | 2026-01-30 08:50 | 120 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 66 | 54 | 2026-04-01 | 181
202508-NM25-01594 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:32 | October | 2025 | 2026-01-30 08:40 | 120 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 66 | 54 | 2026-04-01 | 181
202508-NM25-01595 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:35 | October | 2025 | 2026-02-04 16:25 | 125 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 71 | 54 | 2026-04-01 | 181
202508-NM25-01596 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:44 | October | 2025 | 2026-02-04 16:23 | 125 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 71 | 54 | 2026-04-01 | 181
202508-NM25-01597 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:51 | October | 2025 | 2026-02-17 16:00 | 138 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 84 | 54 | 2026-04-01 | 181
202508-NM25-01598 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-02 09:52 | October | 2025 | 2026-02-17 15:57 | 138 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 84 | 54 | 2026-04-01 | 181
202508-NM25-01623 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-24 10:54 | October | 2025 | 2026-01-12 16:21 | 80 | Study | Estudio (E) | Activated | Backlog |  | No | 80 |  | BAYAMON | January |  | 80 | 0 | 2026-04-01 | 159
202508-NM25-01650 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:59 | January | 2026 | 2026-01-14 14:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202508-NM25-01656 | GDL17 | Gubernamental | 24 | Period | 2026-02-17 08:53 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 43
202508-NM25-01671 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-11 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 233
202508-NM25-01672 | GDL17 | Comercial | 8.5 | Out of period | 2025-12-05 08:43 | December | 2025 |  |  | Customer Orientation | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 117
202508-NM25-01681 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-13 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 231
202508-NM25-01697 | GDL17 | Residencial | 3.8 | Out of period | 2025-09-22 14:30 | September | 2025 | 2026-02-27 09:49 | 158 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 1 | 10 | 148 | 2026-04-01 | 190
202508-NM25-01699 | GDL17 | Residencial | 4.224 | Out of period | 2025-10-20 15:36 | October | 2025 | 2026-03-23 12:36 | 154 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | March | 2 | 6 | 148 | 2026-04-01 | 162
202508-NM25-01728 | GDL17 | Residencial | 5.376 | Period | 2026-01-08 13:20 | January | 2026 | 2026-01-20 16:19 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 12 | 0 | 2026-04-01 | 82
202508-NM25-01750 | GDL17 | Residencial | 5.376 | Out of period | 2025-10-06 11:10 | October | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 177
202508-NM25-01799 | GDL17 | Residencial | 7.68 | Period | 2026-01-09 16:40 | January | 2026 | 2026-01-14 09:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 81
202508-NM25-01827 | GDL17 | Residencial | 5.73 | Out of period | 2025-09-22 09:26 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 191
202508-NM25-01829 | GDL17 | Residencial | 6.8 | Out of period | 2025-08-14 | August | 2025 | 2026-01-19 15:56 | 159 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 3 | 18 | 140 | 2026-04-01 | 230
202508-NM25-01844 | GDL17 | Residencial | 4.992 | Out of period | 2025-08-11 | August | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 233
202508-NM25-01857 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-07 15:18 | November | 2025 | 2026-01-09 15:21 | 63 | Study | Estudio (E) | Activated | Backlog |  | No | 63 |  | MAYAGUEZ | January |  | 63 | 0 | 2026-04-01 | 144
202508-NM25-01859 | GDL17 | Residencial | 6.144 | Out of period | 2025-10-30 08:30 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 153
202508-NM25-01872 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 08:32 | February | 2026 | 2026-02-17 14:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 48
202508-NM25-01914 | GDL17 | Residencial | 3.8 | Period | 2026-01-26 15:08 | January | 2026 | 2026-01-28 08:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202508-NM25-01928 | GDL17 | Residencial | 3.84 | Out of period | 2025-09-03 13:12 | September | 2025 | 2026-02-16 10:03 | 166 | Study | Estudio (E) | Activated | Backlog |  | No | 166 |  | BAYAMON | February |  | 166 | 0 | 2026-04-01 | 209
202508-NM25-01936 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 13:02 | January | 2026 | 2026-03-27 10:34 | 80 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 80 | 0 | 2026-04-01 | 84
202508-NM25-01938 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:00 | January | 2026 | 2026-01-16 14:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 81
202508-NM25-01947 | GDL17 | Residencial | 10 | Period | 2026-02-11 17:26 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 48
202508-NM25-01961 | GDL17 | Residencial | 13.8 | Period | 2026-02-06 16:08 | February | 2026 | 2026-02-12 07:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 53
202508-NM25-01974 | GDL17 | Residencial | 5.76 | Period | 2026-03-06 11:09 | March | 2026 | 2026-03-10 14:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 26
202508-NM25-01989 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-09 21:08 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 216 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 203
202508-NM25-01990 | GDL17 | Residencial | 6.588 | Out of period | 2025-10-27 13:45 | October | 2025 | 2026-01-08 09:58 | 73 | Study | Estudio (E) | Activated | Backlog |  | No | 73 |  | ARECIBO | January |  | 72 | 0 | 2026-04-01 | 155
202508-NM25-01999 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 16:01 | January | 2026 | 2026-01-12 10:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 84
202508-NM25-02026 | GDL17 | Residencial | 3.8 | Out of period | 2025-10-16 19:38 | October | 2025 | 2026-01-08 10:53 | 84 | Study | Estudio (E) | Activated | Backlog |  | No | 84 |  | MAYAGUEZ | January |  | 84 | 0 | 2026-04-01 | 166
202508-NM25-02045 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-27 13:50 | October | 2025 | 2026-01-26 13:57 | 91 | Study | Estudio (E) | Activated | Backlog |  | No | 91 |  | CAGUAS | January |  | 91 | 0 | 2026-04-01 | 155
202508-NM25-02069 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:45 | January | 2026 | 2026-01-20 16:20 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 82
202508-NM25-02079 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 17:29 | February | 2026 | 2026-02-24 10:31 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 47
202508-NM25-02125 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:25 | March | 2026 | 2026-03-05 16:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 27
202508-NM25-02127 | GDL17 | Residencial | 3.8 | Period | 2026-01-16 10:38 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 75
202508-NM25-02131 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:57 | February | 2026 | 2026-02-26 09:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 36
202508-NM25-02133 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 19:14 | February | 2026 | 2026-02-26 10:17 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 41
202508-NM25-02138 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:53 | February | 2026 | 2026-02-12 14:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202508-NM25-02139 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:32 | February | 2026 | 2026-03-04 15:38 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 15 | 0 | 2026-04-01 | 42
202508-NM25-02141 | GDL17 | Residencial | 15 | Out of period | 2025-08-20 | August | 2025 | 2026-01-20 12:58 | 154 | Study | Estudio (E) | Activated | Backlog |  | No | 153 |  | SAN JUAN | January |  | 153 | 0 | 2026-04-01 | 224
202508-NM25-02143 | GDL17 | Residencial | 3.072 | Out of period | 2025-11-10 08:12 | November | 2025 | 2026-01-09 09:54 | 60 | Study | Estudio (E) | Activated | Backlog |  | No | 60 |  | ARECIBO | January |  | 60 | 0 | 2026-04-01 | 142
202508-NM25-02154 | GDL17 | Residencial | 4.224 | Out of period | 2025-10-09 14:19 | October | 2025 | 2026-03-02 08:49 | 144 | Study | Estudio (E) | Activated | Backlog |  | No | 144 |  | CAGUAS | March |  | 144 | 0 | 2026-04-01 | 173
202508-NM25-02173 | GDL17 | Residencial | 19.294 | Period | 2026-02-03 09:44 | February | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 57
202508-NM25-02175 | GDL17 | Residencial | 6.588 | Period | 2026-02-19 08:05 | February | 2026 | 2026-02-25 08:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 5 | 1 | 2026-04-01 | 41
202508-NM25-02182 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-12 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 232
202508-NM25-02191 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 17:17 | March | 2026 | 2026-03-12 13:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202508-NM25-02193 | GDL17 | Residencial | 6.912 | Out of period | 2025-11-12 10:28 | November | 2025 | 2026-03-19 15:36 | 127 | Study | Estudio (E) | Activated | Backlog |  | No | 127 |  | CAGUAS | March |  | 127 | 0 | 2026-04-01 | 140
202508-NM25-02199 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:44 | February | 2026 | 2026-02-25 15:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 39
202508-NM25-02210 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:47 | February | 2026 | 2026-02-16 08:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 48
202508-NM25-02211 | GDL17 | Residencial | 3.456 | Out of period | 2025-11-11 13:40 | November | 2025 | 2026-02-24 10:06 | 105 | Study | Estudio (E) | Activated | Backlog |  | No | 105 |  | CAGUAS | February |  | 105 | 0 | 2026-04-01 | 140
202508-NM25-02217 | GDL17 | Residencial | 3.8 | Period | 2026-01-21 16:07 | January | 2026 | 2026-01-27 12:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 69
202508-NM25-02226 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 19:27 | February | 2026 | 2026-02-18 10:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 46
202508-NM25-02232 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-10 16:50 | November | 2025 | 2026-01-08 15:52 | 59 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 4 | 12 | 47 | 2026-04-01 | 141
202508-NM25-02235 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 21:55 | February | 2026 | 2026-03-05 09:24 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 16 | 0 | 2026-04-01 | 42
202508-NM25-02238 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 13:54 | January | 2026 | 2026-01-14 16:07 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 84
202508-NM25-02240 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 14:29 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 46
202508-NM25-02244 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:50 | February | 2026 | 2026-02-13 14:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 48
202508-NM25-02257 | GDL17 | Residencial | 23 | Out of period | 2025-11-05 16:32 | November | 2025 | 2026-01-16 13:43 | 72 | Study | Estudio (E) | Activated | Backlog |  | No | 72 |  | ARECIBO | January |  | 72 | 0 | 2026-04-01 | 146
202508-NM25-02261 | GDL17 | Residencial | 11.5 | Period | 2026-02-22 17:32 | February | 2026 | 2026-03-05 15:09 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 37
202508-NM25-02284 | GDL17 | Comercial | 11.5 | Period | 2026-02-17 12:15 | February | 2026 | 2026-03-05 08:58 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 16 | 0 | 2026-04-01 | 42
202508-NM25-02295 | GDL17 | Residencial | 5.25 | Out of period | 2025-09-17 16:25 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 195
202508-NM25-02296 | GDL17 | Residencial | 8 | Out of period | 2025-09-08 14:22 | September | 2025 | 2026-01-09 10:31 | 123 | Study | Estudio (E) | Activated | Backlog |  | No | 123 |  | MAYAGUEZ | January |  | 123 | 0 | 2026-04-01 | 204
202508-NM25-02298 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:17 | January | 2026 | 2026-01-15 15:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202508-NM25-02317 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 18:06 | March | 2026 | 2026-04-02 09:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 3 | 0 | 2026-04-01 | 1
202508-NM25-02332 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 18:03 | January | 2026 | 2026-01-16 07:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202508-NM25-02339 | GDL17 | Residencial | 5.76 | Period | 2026-02-02 15:47 | February | 2026 | 2026-02-04 16:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202508-NM25-02340 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 17:22 | January | 2026 | 2026-01-13 13:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202508-NM25-02371 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:13 | January | 2026 | 2026-01-28 11:26 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 21 | 0 | 2026-04-01 | 83
202508-NM25-02383 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:36 | January | 2026 | 2026-01-13 10:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202508-NM25-02384 | GDL17 | Residencial | 4.224 | Out of period | 2025-11-25 15:11 | November | 2025 | 2026-01-09 15:54 | 45 | Study | Estudio (E) | Activated | Backlog |  | No | 45 |  | MAYAGUEZ | January |  | 45 | 0 | 2026-04-01 | 126
202508-NM25-02428 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 15:40 | November | 2025 | 2026-02-05 15:56 | 87 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 3 | 84 | 2026-04-01 | 141
202508-NM25-02430 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 22:16 | February | 2026 | 2026-02-20 16:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 43
202508-NM25-02483 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 16:12 | January | 2026 | 2026-01-14 10:06 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 83
202508-NM25-02590 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-10 14:29 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 141
202508-NM25-02593 | GDL17 | Residencial | 5.376 | Out of period | 2025-08-13 | August | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 252 | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 231
202508-NM25-02648 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:44 | March | 2026 | 2026-04-24 09:50 | 43 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 42 | 34 | 2026-04-01 | 19
202508-NM25-02663 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:02 | February | 2026 | 2026-02-27 08:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202508-NM25-02683 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-22 12:04 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 160
202508-NM25-02712 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-12 18:16 | November | 2025 | 2026-01-13 13:46 | 62 | Study | Estudio (E) | Activated | Backlog |  | No | 62 |  | CAGUAS | January |  | 62 | 0 | 2026-04-01 | 139
202508-NM25-02714 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:46 | January | 2026 | 2026-01-14 07:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202508-NM25-02760 | GDL17 | Comercial | 11.5 | Period | 2026-02-16 10:37 | February | 2026 | 2026-02-19 08:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 44
202508-NM25-02774 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 17:40 | January | 2026 | 2026-01-12 08:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 85
202508-NM25-02781 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-14 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 230
202508-NM25-02787 | GDL17 | Residencial | 8.832 | Period | 2026-01-15 14:48 | January | 2026 | 2026-01-26 10:14 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 11 | 0 | 2026-04-01 | 75
202508-NM25-02793 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:07 | January | 2026 | 2026-02-06 13:23 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 28 | 0 | 2026-04-01 | 81
202508-NM25-02812 | GDL17 | Residencial | 23 | Period | 2026-01-06 12:57 | January | 2026 | 2026-01-14 10:05 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 84
202508-NM25-02820 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-14 | August | 2025 | 2026-01-20 12:59 | 160 | Study | Estudio (E) | Activated | Backlog |  | No | 159 |  | PONCE | January |  | 159 | 0 | 2026-04-01 | 230
202508-NM25-02849 | GDL17 | Residencial | 3.3 | Period | 2026-02-19 17:20 | February | 2026 | 2026-03-04 08:38 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 40
202508-NM25-02878 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-08 09:13 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 175
202508-NM25-02885 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:33 | January | 2026 | 2026-02-02 15:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202508-NM25-02889 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:31 | January | 2026 | 2026-02-02 14:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202508-NM25-02936 | GDL17 | Residencial | 16.5 | Period | 2026-03-02 12:37 | March | 2026 | 2026-03-04 09:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 29
202508-NM25-02959 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:32 | March | 2026 | 2026-03-26 12:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202508-NM25-02962 | GDL17 | Residencial | 3.8 | Out of period | 2025-09-03 19:06 | September | 2025 | 2026-01-29 07:37 | 148 | Study | Estudio (E) | Activated | Backlog |  | No | 148 |  | ARECIBO | January |  | 147 | 0 | 2026-04-01 | 209
202508-NM25-02963 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:15 | January | 2026 | 2026-02-04 10:09 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 69
202508-NM25-02970 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-15 | August | 2025 | 2026-02-12 11:24 | 181 | Study | Estudio (E) | Activated | Backlog |  | No | 181 |  | CAGUAS | February |  | 181 | 0 | 2026-04-01 | 229
202508-NM25-02988 | GDL17 | Residencial | 12 | Out of period | 2025-12-17 10:37 | December | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 105
202508-NM25-02992 | GDL17 | Residencial | 6.912 | Period | 2026-01-09 16:41 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 81
202508-NM25-03043 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:34 | February | 2026 | 2026-02-13 09:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 49
202508-NM25-03066 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:52 | February | 2026 | 2026-02-12 11:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202508-NM25-03073 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:18 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 32
202508-NM25-03077 | GDL17 | Residencial | 3.84 | Out of period | 2025-08-18 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 226
202508-NM25-03078 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-18 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 226
202508-NM25-03082 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:57 | January | 2026 | 2026-01-23 15:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 71
202508-NM25-03152 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:07 | January | 2026 | 2026-01-19 11:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 75
202508-NM25-03223 | GDL17 | Comercial | 16 | Period | 2026-01-21 12:45 | January | 2026 | 2026-02-02 13:13 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 4 | 8 | 2026-04-01 | 69
202508-NM25-03248 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 18:51 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 141
202508-NM25-03254 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 07:47 | February | 2026 | 2026-02-26 08:57 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 42
202508-NM25-03257 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 16:28 | March | 2026 | 2026-03-09 12:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 26
202508-NM25-03258 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:14 | February | 2026 | 2026-02-17 07:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 49
202508-NM25-03261 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:05 | February | 2026 | 2026-02-25 15:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 39
202508-NM25-03262 | GDL17 | Residencial | 10 | Period | 2026-03-14 15:52 | March | 2026 | 2026-03-19 15:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 17
202508-NM25-03270 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 09:39 | March | 2026 | 2026-03-09 15:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 26
202508-NM25-03280 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 17:01 | January | 2026 | 2026-01-13 14:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202508-NM25-03281 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-12 11:42 | November | 2025 | 2026-01-30 09:43 | 79 | Study | Estudio (E) | Activated | Backlog |  | No | 79 |  | ARECIBO | January |  | 78 | 0 | 2026-04-01 | 140
202508-NM25-03286 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:16 | February | 2026 | 2026-02-19 08:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 43
202508-NM25-03291 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-19 | August | 2025 | 2026-01-08 09:45 | 142 | Study | Estudio (E) | Activated | Backlog |  | No | 142 |  | MAYAGUEZ | January |  | 142 | 0 | 2026-04-01 | 225
202508-NM25-03294 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 19:17 | February | 2026 | 2026-02-23 13:12 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 46
202508-NM25-03304 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 22:15 | February | 2026 | 2026-02-24 07:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202508-NM25-03308 | GDL17 | Residencial | 23 | Out of period | 2025-10-20 13:12 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 162
202508-NM25-03320 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:00 | March | 2026 | 2026-03-05 16:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 27
202508-NM25-03322 | GDL17 | Residencial | 11.5 | Period | 2026-03-08 17:43 | March | 2026 | 2026-03-11 08:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 23
202508-NM25-03332 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-19 | August | 2025 | 2026-02-06 14:19 | 172 | Study | Estudio (E) | Activated | Backlog |  | No | 171 |  | MAYAGUEZ | February |  | 171 | 0 | 2026-04-01 | 225
202508-NM25-03335 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 22:32 | February | 2026 | 2026-03-02 09:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 34
202508-NM25-03337 | GDL17 | Residencial | 23 | Period | 2026-02-02 17:01 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 57
202508-NM25-03346 | GDL17 | Residencial | 16 | Period | 2026-02-02 15:47 | February | 2026 | 2026-02-11 15:51 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 9 | 0 | 2026-04-01 | 57
202508-NM25-03350 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 23:39 | January | 2026 | 2026-02-04 09:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 60
202508-NM25-03356 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:37 | March | 2026 | 2026-03-17 11:29 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 15 | 0 | 2026-04-01 | 30
202508-NM25-03357 | GDL17 | Residencial | 3.8 | Period | 2026-02-11 08:12 | February | 2026 | 2026-02-16 08:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 49
202508-NM25-03370 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-08 08:55 | September | 2025 | 2026-01-29 07:42 | 143 | Study | Estudio (E) | Activated | Backlog |  | No | 143 |  | PONCE | January |  | 143 | 0 | 2026-04-01 | 205
202508-NM25-03374 | GDL17 | Residencial | 4.608 | Period | 2026-01-08 16:52 | January | 2026 | 2026-01-13 15:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202508-NM25-03441 | GDL17 | Residencial | 3.8 | Period | 2026-02-11 16:42 | February | 2026 | 2026-03-13 15:10 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 2 | 28 | 2026-04-01 | 48
202508-NM25-03453 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 12:49 | January | 2026 | 2026-01-27 14:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 64
202508-NM25-03473 | GDL17 | Residencial | 3.8 | Out of period | 2025-10-08 08:48 | October | 2025 | 2026-01-08 08:55 | 92 | Study | Estudio (E) | Activated | Backlog |  | No | 92 |  | MAYAGUEZ | January |  | 92 | 0 | 2026-04-01 | 175
202508-NM25-03483 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-01 12:42 | September | 2025 | 2026-01-08 08:27 | 129 | Study | Estudio (E) | Activated | Backlog |  | No | 129 |  | MAYAGUEZ | January |  | 129 | 0 | 2026-04-01 | 211
202508-NM25-03540 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:06 | February | 2026 | 2026-03-04 10:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 36
202508-NM25-03542 | GDL17 | Residencial | 5.76 | Period | 2026-03-10 17:24 | March | 2026 | 2026-03-12 13:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202508-NM25-03543 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 08:45 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 1
202508-NM25-03545 | GDL17 | Residencial | 9.6 | Out of period | 2025-09-11 10:46 | September | 2025 | 2026-01-13 15:01 | 124 | Study | Estudio (E) | Activated | Backlog |  | No | 124 |  | SAN JUAN | January |  | 124 | 0 | 2026-04-01 | 202
202508-NM25-03566 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 16:23 | January | 2026 | 2026-01-13 15:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202508-NM25-03587 | GDL17 | Residencial | 23 | Period | 2026-02-21 18:50 | February | 2026 | 2026-03-03 13:07 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 10 | 0 | 2026-04-01 | 38
202508-NM25-03606 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:24 | February | 2026 | 2026-02-18 13:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 44
202508-NM25-03612 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:21 | February | 2026 | 2026-02-16 12:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 49
202508-NM25-03615 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 12:51 | January | 2026 | 2026-01-13 09:33 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202508-NM25-03618 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 10:04 | February | 2026 | 2026-02-13 08:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 49
202508-NM25-03620 | GDL17 | Residencial | 3.84 | Out of period | 2025-08-20 | August | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 224
202508-NM25-03634 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-23 10:17 | September | 2025 | 2026-01-29 10:23 | 128 | Study | Estudio (E) | Activated | Backlog |  | No | 128 |  | ARECIBO | January |  | 128 | 0 | 2026-04-01 | 190
202508-NM25-03657 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 17:46 | February | 2026 | 2026-03-03 16:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202508-NM25-03660 | GDL17 | Residencial | 6.912 | Period | 2026-01-08 17:48 | January | 2026 | 2026-01-13 12:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202508-NM25-03666 | GDL17 | Residencial | 7.32 | Out of period | 2025-11-21 09:50 | November | 2025 | 2026-01-08 14:50 | 48 | Study | Estudio (E) | Activated | Backlog |  | No | 48 |  | CAGUAS | January |  | 48 | 0 | 2026-04-01 | 131
202508-NM25-03698 | GDL17 | Residencial | 4.224 | Period | 2026-01-27 13:40 | January | 2026 | 2026-03-03 12:34 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 35 | 0 | 2026-04-01 | 63
202508-NM25-03724 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 11:47 | January | 2026 | 2026-01-29 15:45 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 1 | 8 | 15 | 2026-04-01 | 85
202508-NM25-03785 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-21 | August | 2025 | 2026-01-07 09:26 | 139 | Study | Estudio (E) | Activated | Backlog |  | No | 139 |  | MAYAGUEZ | January |  | 139 | 0 | 2026-04-01 | 223
202508-NM25-03803 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:45 | February | 2026 | 2026-03-03 15:57 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 36
202508-NM25-03818 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 17:23 | February | 2026 | 2026-03-04 09:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202508-NM25-03834 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 18:51 | February | 2026 | 2026-02-23 14:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202508-NM25-03837 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 16:06 | February | 2026 | 2026-02-13 15:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 47
202508-NM25-03847 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-21 | August | 2025 | 2026-01-21 10:41 | 153 | Study | Estudio (E) | Activated | Backlog |  | No | 153 |  | MAYAGUEZ | January |  | 153 | 0 | 2026-04-01 | 223
202508-NM25-03860 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:33 | March | 2026 | 2026-03-06 13:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 27
202508-NM25-03912 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:50 | January | 2026 | 2026-01-14 15:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 83
202508-NM25-03913 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 12:59 | January | 2026 | 2026-01-14 09:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 82
202508-NM25-03919 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 15:38 | January | 2026 | 2026-01-12 14:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 85
202508-NM25-03933 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:41 | February | 2026 | 2026-02-25 11:03 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 43
202508-NM25-03966 | GDL17 | Residencial | 23 | Period | 2026-01-08 12:40 | January | 2026 | 2026-01-19 08:12 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 82
202508-NM25-03982 | GDL17 | Residencial | 7.68 | Period | 2026-02-19 10:25 | February | 2026 | 2026-02-24 08:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 41
202508-NM25-03986 | GDL17 | Residencial | 8 | Out of period | 2025-08-22 | August | 2025 | 2026-02-03 13:16 | 166 | Study | Estudio (E) | Activated | Backlog |  | No | 165 |  | BAYAMON | February |  | 165 | 0 | 2026-04-01 | 222
202508-NM25-04010 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 11:56 | February | 2026 | 2026-02-18 10:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 46
202508-NM25-04012 | GDL17 | Residencial | 6.144 | Out of period | 2025-09-11 13:28 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 201
202508-NM25-04015 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:49 | January | 2026 | 2026-02-03 08:52 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 67
202508-NM25-04016 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:58 | February | 2026 | 2026-02-18 08:49 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 48
202508-NM25-04017 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:22 | February | 2026 | 2026-02-25 10:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202508-NM25-04018 | GDL17 | Residencial | 5.76 | Period | 2026-02-11 20:29 | February | 2026 | 2026-02-16 15:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202508-NM25-04019 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:45 | February | 2026 | 2026-02-18 10:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202508-NM25-04020 | GDL17 | Residencial | 3.8 | Period | 2026-02-19 19:53 | February | 2026 | 2026-03-13 10:50 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 22 | 0 | 2026-04-01 | 40
202508-NM25-04029 | GDL17 | Residencial | 5.76 | Out of period | 2025-09-18 14:48 | September | 2025 | 2026-02-19 14:38 | 154 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February | 1 | 6 | 148 | 2026-04-01 | 194
202508-NM25-04034 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-09 08:01 | September | 2025 | 2026-01-05 14:33 | 118 | Study | Estudio (E) | Activated | Backlog |  | No | 118 |  | MAYAGUEZ | January |  | 118 | 0 | 2026-04-01 | 204
202508-NM25-04037 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:05 | February | 2026 | 2026-02-18 11:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 44
202508-NM25-04040 | GDL17 | Residencial | 5.76 | Period | 2026-01-07 11:07 | January | 2026 | 2026-01-12 15:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 84
202508-NM25-04045 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:19 | February | 2026 | 2026-02-23 16:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202508-NM25-04052 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 13:59 | January | 2026 | 2026-01-13 10:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 84
202508-NM25-04060 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:57 | February | 2026 | 2026-02-25 15:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202508-NM25-04062 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 09:22 | February | 2026 | 2026-02-26 08:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202508-NM25-04070 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 12:54 | February | 2026 | 2026-03-06 08:19 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 33
202508-NM25-04083 | GDL17 | Residencial | 6.912 | Period | 2026-02-04 17:50 | February | 2026 | 2026-02-06 09:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 55
202508-NM25-04161 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 08:56 | February | 2026 | 2026-02-24 09:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202508-NM25-04166 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:25 | February | 2026 | 2026-02-26 11:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202508-NM25-04226 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:29 | February | 2026 | 2026-02-13 16:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 47
202508-NM25-04254 | GDL17 | Residencial | 3.84 | Period | 2026-02-11 08:42 | February | 2026 | 2026-02-16 11:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 49
202508-NM25-04259 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:11 | February | 2026 | 2026-03-02 15:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 35
202508-NM25-04261 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-25 | August | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 224 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 219
202508-NM25-04271 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 20:05 | February | 2026 | 2026-02-24 07:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202508-NM25-04284 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 20:10 | February | 2026 | 2026-02-26 16:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 41
202508-NM25-04290 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:56 | February | 2026 | 2026-02-26 08:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 36
202508-NM25-04295 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 09:48 | March | 2026 | 2026-03-06 14:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202508-NM25-04307 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 12:32 | February | 2026 | 2026-03-06 08:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 33
202508-NM25-04313 | GDL17 | Comercial | 11.5 | Period | 2026-02-19 15:35 | February | 2026 | 2026-02-25 08:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202508-NM25-04315 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:27 | January | 2026 | 2026-01-14 08:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 82
202508-NM25-04320 | GDL17 | Residencial | 3.3 | Period | 2026-02-21 11:24 | February | 2026 | 2026-02-26 08:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 39
202508-NM25-04322 | GDL17 | Residencial | 3.8 | Period | 2026-01-08 14:00 | January | 2026 | 2026-01-20 15:05 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 82
202508-NM25-04341 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:09 | February | 2026 | 2026-03-03 15:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 32
202508-NM25-04353 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 18:20 | February | 2026 | 2026-03-09 07:44 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 35
202508-NM25-04391 | GDL17 | Residencial | 11.4 | Period | 2026-01-07 15:15 | January | 2026 | 2026-01-20 15:11 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 13 | 0 | 2026-04-01 | 83
202508-NM25-04408 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-05 14:24 | November | 2025 | 2026-01-12 13:58 | 68 | Study | Estudio (E) | Activated | Backlog |  | No | 68 |  | CAGUAS | January |  | 68 | 0 | 2026-04-01 | 146
202508-NM25-04414 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 19:20 | January | 2026 | 2026-01-14 14:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 81
202508-NM25-04420 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:19 | February | 2026 | 2026-02-23 09:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 42
202508-NM25-04469 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-01 16:02 | October | 2025 | 2026-01-08 13:13 | 99 | Study | Estudio (E) | Activated | Backlog |  | No | 99 |  | MAYAGUEZ | January |  | 99 | 0 | 2026-04-01 | 181
202508-NM25-04470 | GDL17 | Residencial | 3.072 | Period | 2026-03-27 07:49 | March | 2026 | 2026-03-31 08:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 5
202508-NM25-04493 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-04 08:27 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 148
202508-NM25-04497 | GDL17 | Residencial | 5.76 | Period | 2026-02-14 15:17 | February | 2026 | 2026-03-16 07:44 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 24 | 1 | 2026-04-01 | 45
202508-NM25-04526 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-26 | August | 2025 | 2026-01-09 09:38 | 136 | Study | Estudio (E) | Activated | Backlog |  | No | 136 |  | MAYAGUEZ | January |  | 136 | 0 | 2026-04-01 | 218
202508-NM25-04530 | GDL17 | Residencial | 5.76 | Period | 2026-01-29 16:19 | January | 2026 | 2026-02-02 15:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 61
202508-NM25-04542 | GDL17 | Residencial | 23 | Period | 2026-03-06 15:34 | March | 2026 | 2026-03-09 11:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 25
202508-NM25-04582 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-03 08:26 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 210
202508-NM25-04592 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-04 10:37 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 148
202508-NM25-04604 | GDL17 | Residencial | 5.76 | Period | 2026-01-29 16:31 | January | 2026 | 2026-02-03 10:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 61
202508-NM25-04621 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:28 | March | 2026 | 2026-03-11 08:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 27
202508-NM25-04635 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:12 | January | 2026 | 2026-01-19 15:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202508-NM25-04685 | GDL17 | Comercial | 11.5 | Period | 2026-02-11 16:32 | February | 2026 | 2026-02-16 07:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 48
202508-NM25-04748 | GDL17 | Residencial | 3.8 | Out of period | 2025-09-23 12:34 | September | 2025 | 2026-02-17 16:13 | 147 | Study | Estudio (E) | Activated | Backlog |  | No | 147 |  | CAGUAS | February |  | 148 | 0 | 2026-04-01 | 189
202508-NM25-04778 | GDL17 | Residencial | 6.912 | Out of period | 2025-10-09 09:46 | October | 2025 | 2026-01-28 13:27 | 111 | Study | Estudio (E) | Activated | Backlog |  | No | 111 |  | ARECIBO | January |  | 111 | 0 | 2026-04-01 | 174
202508-NM25-04802 | GDL17 | Residencial | 3.84 | Out of period | 2025-10-16 12:16 | October | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 166
202508-NM25-04854 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 19:15 | November | 2025 | 2026-02-18 09:20 | 107 | Study | Estudio (E) | Activated | Backlog |  | No | 107 |  | PONCE | February |  | 106 | 0 | 2026-04-01 | 148
202508-NM25-04857 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-07 13:44 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 175
202508-NM25-04860 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-27 | August | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | SAN JUAN |  |  |  |  | 2026-04-01 | 217
202508-NM25-04872 | GDL17 | Residencial | 8 | Out of period | 2025-09-05 11:22 | September | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 208
202508-NM25-04882 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-10 08:10 | September | 2025 | 2026-02-12 09:21 | 155 | Study | Estudio (E) | Activated | Backlog |  | No | 155 |  | CAGUAS | February |  | 155 | 0 | 2026-04-01 | 203
202508-NM25-04886 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:18 | February | 2026 | 2026-03-02 08:13 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 40
202508-NM25-04888 | GDL17 | Residencial | 5.376 | Out of period | 2025-09-09 13:20 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 203
202508-NM25-04898 | GDL17 | Residencial | 8 | Out of period | 2025-09-02 11:16 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 211
202508-NM25-04899 | GDL17 | Residencial | 4.608 | Period | 2026-01-26 16:22 | January | 2026 | 2026-02-02 10:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 64
202508-NM25-04902 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-27 | August | 2025 | 2026-03-02 14:36 | 188 | Study | Estudio (E) | Activated | Backlog |  | No | 187 |  | ARECIBO | March |  | 187 | 0 | 2026-04-01 | 217
202508-NM25-04922 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-08 14:27 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 201 | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 174
202508-NM25-04935 | GDL17 | Residencial | 23 | Period | 2026-01-05 13:02 | January | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 85
202508-NM25-04938 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:30 | January | 2026 | 2026-03-24 15:29 | 61 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 61 | 0 | 2026-04-01 | 69
202508-NM25-04944 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-03 11:09 | September | 2025 | 2026-02-19 13:36 | 169 | Study | Estudio (E) | Activated | Backlog |  | No | 169 |  | BAYAMON | February |  | 169 | 0 | 2026-04-01 | 210
202508-NM25-04981 | GDL17 | Residencial | 5.376 | Period | 2026-01-09 13:17 | January | 2026 | 2026-01-16 13:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 81
202508-NM25-04990 | GDL17 | Residencial | 7.68 | Out of period | 2025-09-30 08:23 | September | 2025 | 2026-03-26 08:57 | 177 | Study | Estudio (E) | Activated | Backlog |  | No | 177 |  | SAN JUAN | March |  | 177 | 0 | 2026-04-01 | 183
202508-NM25-05010 | GDL17 | Residencial | 7.6 | Period | 2026-03-20 10:52 | March | 2026 | 2026-03-23 15:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 12
202508-NM25-05031 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 08:22 | February | 2026 | 2026-03-04 08:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 34
202508-NM25-05042 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 17:52 | March | 2026 | 2026-03-23 08:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 13
202508-NM25-05070 | GDL17 | Comercial | 11.5 | Out of period | 2025-09-05 14:50 | September | 2025 | 2026-03-20 16:09 | 196 | Study | Estudio (E) | Activated | Backlog |  | No | 196 |  | ARECIBO | March |  | 196 | 0 | 2026-04-01 | 207
202508-NM25-05090 | GDL17 | Residencial | 4.992 | Out of period | 2025-09-25 08:19 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 188
202508-NM25-05106 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:55 | February | 2026 | 2026-02-24 14:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202508-NM25-05112 | GDL17 | Residencial | 6.144 | Out of period | 2025-10-20 07:37 | October | 2025 | 2026-03-04 15:07 | 135 | Study | Estudio (E) | Activated | Backlog |  | No | 135 |  | BAYAMON | March |  | 135 | 0 | 2026-04-01 | 163
202508-NM25-05135 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:01 | February | 2026 | 2026-02-19 10:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 43
202508-NM25-05137 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:54 | February | 2026 | 2026-02-23 09:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202508-NM25-05142 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:23 | February | 2026 | 2026-02-12 13:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202508-NM25-05151 | GDL17 | Residencial | 11.52 | Out of period | 2025-09-18 15:49 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 194
202508-NM25-05154 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 08:37 | February | 2026 | 2026-02-17 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 47
202508-NM25-05161 | GDL17 | Residencial | 10 | Out of period | 2025-09-19 14:52 | September | 2025 | 2026-01-08 14:03 | 111 | Study | Estudio (E) | Activated | Backlog |  | No | 111 |  | CAGUAS | January |  | 111 | 0 | 2026-04-01 | 193
202508-NM25-05162 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:09 | February | 2026 | 2026-02-26 08:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 37
202508-NM25-05163 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:51 | February | 2026 | 2026-02-25 16:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202508-NM25-05165 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:28 | February | 2026 | 2026-03-02 14:20 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 39
202508-NM25-05168 | GDL17 | Residencial | 3.3 | Period | 2026-02-25 09:22 | February | 2026 | 2026-02-27 09:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 35
202508-NM25-05170 | GDL17 | Residencial | 3.8 | Period | 2026-03-12 10:33 | March | 2026 | 2026-03-17 13:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 20
202508-NM25-05172 | GDL17 | Residencial | 7.6 | Out of period | 2025-08-27 | August | 2025 | 2026-03-16 16:26 | 202 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | March | 3 | 37 | 164 | 2026-04-01 | 217
202508-NM25-05173 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:02 | February | 2026 | 2026-02-23 09:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202508-NM25-05175 | GDL17 | Residencial | 12 | Period | 2026-03-07 13:51 | March | 2026 | 2026-03-09 13:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 24
202508-NM25-05181 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:51 | February | 2026 | 2026-02-24 14:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 41
202508-NM25-05201 | GDL17 | Residencial | 4.992 | Out of period | 2025-09-18 14:16 | September | 2025 | 2026-03-19 14:10 | 182 | Study | Estudio (E) | Activated | Backlog |  | No | 182 |  | ARECIBO | March |  | 182 | 0 | 2026-04-01 | 194
202508-NM25-05212 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-28 | August | 2025 | 2026-01-20 13:46 | 146 | Study | Estudio (E) | Activated | Backlog |  | No | 145 |  | PONCE | January |  | 145 | 0 | 2026-04-01 | 216
202508-NM25-05220 | GDL17 | Residencial | 11.5 | Out of period | 2025-08-28 | August | 2025 | 2026-01-05 11:10 | 130 | Study | Estudio (E) | Activated | Backlog |  | No | 130 |  | MAYAGUEZ | January |  | 130 | 0 | 2026-04-01 | 216
202508-NM25-05222 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 08:44 | March | 2026 | 2026-03-09 08:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 30
202508-NM25-05238 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:38 | February | 2026 | 2026-03-04 08:16 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 42
202508-NM25-05280 | GDL17 | Residencial | 8.448 | Out of period | 2025-10-31 11:24 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 152
202508-NM25-05286 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:23 | February | 2026 | 2026-02-25 08:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202508-NM25-05318 | GDL17 | Residencial | 5.76 | Period | 2026-01-07 17:43 | January | 2026 | 2026-01-14 13:41 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 83
202508-NM25-05323 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 18:28 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 148
202508-NM25-05324 | GDL17 | Residencial | 16 | Period | 2026-02-02 16:18 | February | 2026 | 2026-02-04 16:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202508-NM25-05360 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:18 | January | 2026 | 2026-01-14 15:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202508-NM25-05361 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-21 08:53 | October | 2025 | 2026-02-04 16:15 | 106 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 52 | 54 | 2026-04-01 | 162
202508-NM25-05363 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:53 | January | 2026 | 2026-01-14 15:50 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 12 | 0 | 2026-04-01 | 88
202508-NM25-05365 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:06 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 77
202508-NM25-05367 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:08 | January | 2026 | 2026-02-25 10:06 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February | 1 | 39 | 3 | 2026-04-01 | 77
202508-NM25-05369 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:10 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 77
202508-NM25-05371 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-21 08:54 | October | 2025 | 2026-02-18 10:33 | 120 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 54 | 2026-04-01 | 162
202508-NM25-05373 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-21 08:55 | October | 2025 | 2026-02-25 11:20 | 127 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 2 | 70 | 57 | 2026-04-01 | 162
202508-NM25-05375 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-21 09:27 | October | 2025 | 2026-02-16 10:19 | 118 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 64 | 54 | 2026-04-01 | 162
202508-NM25-05377 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:19 | October | 2025 | 2026-02-16 10:22 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 65 | 54 | 2026-04-01 | 162
202508-NM25-05378 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:20 | October | 2025 | 2026-02-16 16:29 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 65 | 54 | 2026-04-01 | 162
202508-NM25-05379 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:24 | October | 2025 | 2026-01-22 14:41 | 94 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 34 | 60 | 2026-04-01 | 162
202508-NM25-05380 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:25 | October | 2025 | 2026-02-16 16:25 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 64 | 55 | 2026-04-01 | 162
202508-NM25-05381 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:33 | October | 2025 | 2026-02-16 16:23 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 64 | 55 | 2026-04-01 | 162
202508-NM25-05382 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:35 | October | 2025 | 2026-02-16 16:20 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 64 | 55 | 2026-04-01 | 162
202508-NM25-05403 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-06 10:51 | November | 2025 | 2026-03-03 15:07 | 117 | Study | Estudio (E) | Activated | Backlog |  | No | 117 |  | ARECIBO | March |  | 117 | 0 | 2026-04-01 | 146
202508-NM25-05408 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 08:58 | October | 2025 | 2026-02-16 16:12 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 56 | 2026-04-01 | 166
202508-NM25-05409 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:02 | October | 2025 | 2026-02-16 16:08 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 56 | 2026-04-01 | 166
202508-NM25-05410 | GDL17 | Residencial | 16.5 | Out of period | 2025-12-02 11:34 | December | 2025 | 2026-03-31 07:33 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March |  | 119 | 7 | 2026-04-01 | 120
202508-NM25-05414 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:05 | October | 2025 | 2026-02-16 16:03 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 56 | 2026-04-01 | 166
202508-NM25-05415 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:06 | October | 2025 | 2026-02-16 16:01 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 56 | 2026-04-01 | 166
202508-NM25-05420 | GDL17 | Residencial | 3.8 | Period | 2026-02-26 11:44 | February | 2026 | 2026-03-05 09:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 34
202508-NM25-05436 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 16:15 | February | 2026 | 2026-02-13 14:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 48
202508-NM25-05443 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 20:09 | February | 2026 | 2026-02-23 08:48 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 47
202508-NM25-05481 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:08 | October | 2025 | 2026-02-16 15:58 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 56 | 2026-04-01 | 166
202508-NM25-05482 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:10 | October | 2025 | 2026-02-16 15:56 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 56 | 2026-04-01 | 166
202508-NM25-05483 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:11 | October | 2025 | 2026-02-16 15:54 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 56 | 2026-04-01 | 166
202508-NM25-05486 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:13 | October | 2025 | 2026-01-22 14:50 | 97 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 37 | 60 | 2026-04-01 | 166
202508-NM25-05487 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:14 | October | 2025 | 2026-02-16 15:51 | 122 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 66 | 56 | 2026-04-01 | 166
202508-NM25-05488 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:16 | October | 2025 | 2026-01-22 14:42 | 97 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 37 | 60 | 2026-04-01 | 166
202508-NM25-05491 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-17 09:17 | October | 2025 | 2026-01-22 14:34 | 97 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 37 | 60 | 2026-04-01 | 166
202508-NM25-05493 | GDL17 | Comercial | 5.3 | Period | 2026-01-20 09:00 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 71
202508-NM25-05496 | GDL17 | Comercial | 5.3 | Period | 2026-01-20 09:10 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 71
202508-NM25-05503 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-10 16:26 | September | 2025 | 2026-01-21 13:35 | 133 | Study | Estudio (E) | Activated | Backlog |  | No | 133 |  | PONCE | January |  | 133 | 0 | 2026-04-01 | 202
202508-NM25-05532 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-10 16:02 | September | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | CAGUAS |  |  |  |  | 2026-04-01 | 202
202508-NM25-05550 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-20 07:50 | October | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | PONCE |  |  |  |  | 2026-04-01 | 163
202508-NM25-05561 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 22:20 | February | 2026 | 2026-02-25 14:52 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 42
202508-NM25-05578 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:15 | February | 2026 | 2026-02-17 10:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 49
202508-NM25-05614 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 20:10 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 148
202508-NM25-05644 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:45 | January | 2026 | 2026-01-14 09:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 83
202508-NM25-05649 | GDL17 | Residencial | 3.8 | Period | 2026-03-04 10:01 | March | 2026 | 2026-03-11 14:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 28
202508-NM25-05658 | GDL17 | Residencial | 23 | Period | 2026-01-06 11:48 | January | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 85
202509-NM25-00006 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:30 | February | 2026 | 2026-02-16 14:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202509-NM25-00017 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:55 | February | 2026 | 2026-02-23 13:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-00018 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:52 | February | 2026 | 2026-02-25 14:30 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 56
202509-NM25-00019 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:41 | January | 2026 | 2026-03-05 15:22 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 49 | 0 | 2026-04-01 | 76
202509-NM25-00022 | GDL17 | Residencial | 9.56 | Period | 2026-02-16 13:46 | February | 2026 | 2026-02-19 10:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 43
202509-NM25-00023 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 10:55 | January | 2026 | 2026-01-12 08:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 85
202509-NM25-00024 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:14 | February | 2026 | 2026-02-18 13:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 46
202509-NM25-00034 | GDL17 | Residencial | 9 | Out of period | 2025-11-28 12:00 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 124
202509-NM25-00036 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:57 | February | 2026 | 2026-03-13 16:24 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 7 | 14 | 2026-04-01 | 42
202509-NM25-00038 | GDL17 | Residencial | 3.8 | Period | 2026-02-19 11:31 | February | 2026 | 2026-03-03 14:56 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 41
202509-NM25-00042 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 13:40 | January | 2026 | 2026-01-14 14:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 84
202509-NM25-00051 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:04 | January | 2026 | 2026-01-13 13:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 83
202509-NM25-00060 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:28 | January | 2026 | 2026-01-23 15:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 69
202509-NM25-00079 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 19:34 | February | 2026 | 2026-02-16 14:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202509-NM25-00083 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:28 | January | 2026 | 2026-01-20 15:10 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 82
202509-NM25-00092 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 16:05 | January | 2026 | 2026-01-13 15:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202509-NM25-00102 | GDL17 | Residencial | 6.144 | Out of period | 2025-09-23 08:12 | September | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 190
202509-NM25-00108 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-14 15:08 | November | 2025 | 2026-01-05 09:20 | 52 | Study | Estudio (E) | Activated | Backlog |  | No | 52 |  | MAYAGUEZ | January |  | 52 | 0 | 2026-04-01 | 137
202509-NM25-00124 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:15 | February | 2026 | 2026-02-12 12:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202509-NM25-00129 | GDL17 | Residencial | 5.76 | Period | 2026-02-12 12:06 | February | 2026 | 2026-02-17 10:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202509-NM25-00134 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:20 | March | 2026 | 2026-03-13 08:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 23
202509-NM25-00138 | GDL17 | Residencial | 3.8 | Period | 2026-01-27 13:45 | January | 2026 | 2026-03-17 08:23 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 49 | 0 | 2026-04-01 | 63
202509-NM25-00141 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-20 12:27 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 162
202509-NM25-00144 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:52 | February | 2026 | 2026-02-26 08:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 39
202509-NM25-00158 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-17 16:07 | October | 2025 | 2026-01-05 10:57 | 80 | Study | Estudio (E) | Activated | Backlog |  | No | 80 |  | MAYAGUEZ | January |  | 80 | 0 | 2026-04-01 | 165
202509-NM25-00162 | GDL17 | Residencial | 23 | Period | 2026-01-27 11:37 | January | 2026 | 2026-02-03 08:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 64
202509-NM25-00171 | GDL17 | Residencial | 5.49 | Out of period | 2025-11-20 15:49 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 131
202509-NM25-00185 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:36 | January | 2026 | 2026-01-12 15:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202509-NM25-00190 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-22 15:25 | September | 2025 | 2026-01-16 10:27 | 116 | Study | Estudio (E) | Activated | Backlog |  | No | 116 |  | MAYAGUEZ | January |  | 116 | 0 | 2026-04-01 | 190
202509-NM25-00194 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 16:22 | February | 2026 | 2026-02-09 13:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202509-NM25-00204 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:41 | January | 2026 | 2026-01-09 09:17 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 88
202509-NM25-00207 | GDL17 | Residencial | 3.456 | Out of period | 2025-10-08 14:12 | October | 2025 | 2026-02-27 13:38 | 142 | Study | Estudio (E) | Activated | Backlog |  | No | 142 |  | CAGUAS | February |  | 142 | 0 | 2026-04-01 | 174
202509-NM25-00212 | GDL17 | Residencial | 3.8 | Period | 2026-01-27 13:15 | January | 2026 | 2026-01-29 16:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202509-NM25-00221 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:30 | January | 2026 | 2026-01-28 10:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202509-NM25-00231 | GDL17 | Residencial | 12.288 | Period | 2026-01-02 13:38 | January | 2026 | 2026-01-14 09:13 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 12 | 0 | 2026-04-01 | 88
202509-NM25-00240 | GDL17 | Residencial | 23 | Period | 2026-03-04 17:06 | March | 2026 | 2026-03-27 13:09 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 23 | 0 | 2026-04-01 | 27
202509-NM25-00274 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 16:14 | January | 2026 | 2026-01-13 14:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 83
202509-NM25-00278 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:34 | January | 2026 | 2026-01-29 08:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 64
202509-NM25-00290 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-02 13:48 | September | 2025 | 2026-02-04 16:04 | 155 | Study | Estudio (E) | Activated | Backlog |  | No | 155 |  | BAYAMON | February |  | 155 | 0 | 2026-04-01 | 210
202509-NM25-00305 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 17:36 | January | 2026 | 2026-01-12 11:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 85
202509-NM25-00336 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 02:08 | February | 2026 | 2026-02-24 10:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202509-NM25-00366 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 09:19 | February | 2026 | 2026-02-11 16:12 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 0 | 0 | 2026-04-01 | 49
202509-NM25-00384 | GDL17 | Residencial | 6.144 | Out of period | 2025-09-03 08:18 | September | 2025 | 2026-01-15 10:27 | 134 | Study | Estudio (E) | Activated | Backlog |  | No | 134 |  | ARECIBO | January |  | 135 | 0 | 2026-04-01 | 210
202509-NM25-00391 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:41 | January | 2026 | 2026-01-29 16:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 63
202509-NM25-00405 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:38 | February | 2026 | 2026-02-12 10:03 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 49
202509-NM25-00417 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-02 16:57 | September | 2025 | 2026-01-05 16:04 | 125 | Study | Estudio (E) | Activated | Backlog |  | No | 125 |  | MAYAGUEZ | January |  | 125 | 0 | 2026-04-01 | 210
202509-NM25-00496 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 18:27 | February | 2026 | 2026-02-26 16:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 38
202509-NM25-00502 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-03 09:32 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 210
202509-NM25-00505 | GDL17 | Comercial | 11.5 | Period | 2026-01-30 16:31 | January | 2026 | 2026-02-03 12:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 60
202509-NM25-00510 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 15:21 | February | 2026 | 2026-02-17 14:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 48
202509-NM25-00528 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:57 | January | 2026 | 2026-01-09 10:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 85
202509-NM25-00530 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-03 09:51 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 215 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 210
202509-NM25-00548 | GDL17 | Residencial | 8 | Out of period | 2025-09-05 10:45 | September | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 208
202509-NM25-00554 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:47 | January | 2026 | 2026-01-12 16:06 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 85
202509-NM25-00566 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 16:23 | January | 2026 | 2026-01-08 12:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 88
202509-NM25-00595 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-03 11:41 | September | 2025 | 2026-01-07 10:29 | 126 | Study | Estudio (E) | Activated | Backlog |  | No | 126 |  | MAYAGUEZ | January |  | 126 | 0 | 2026-04-01 | 210
202509-NM25-00600 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:53 | February | 2026 | 2026-02-05 15:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-00614 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 18:09 | November | 2025 | 2026-01-30 13:23 | 88 | Study | Estudio (E) | Activated | Backlog |  | No | 88 |  | SAN JUAN | January |  | 88 | 0 | 2026-04-01 | 148
202509-NM25-00616 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:01 | February | 2026 | 2026-03-06 13:05 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 18 | 0 | 2026-04-01 | 43
202509-NM25-00630 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:00 | February | 2026 | 2026-02-24 07:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202509-NM25-00636 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:52 | February | 2026 | 2026-02-23 09:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-00638 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-22 16:00 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 190
202509-NM25-00642 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-03 12:58 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 209
202509-NM25-00647 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:27 | January | 2026 | 2026-01-13 15:44 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 11 | 0 | 2026-04-01 | 88
202509-NM25-00657 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:13 | January | 2026 | 2026-01-29 10:35 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 24 | 0 | 2026-04-01 | 85
202509-NM25-00668 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-03 13:47 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 209
202509-NM25-00674 | GDL17 | Residencial | 5.376 | Out of period | 2025-09-23 07:42 | September | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 190
202509-NM25-00702 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 15:44 | January | 2026 | 2026-01-12 14:08 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 85
202509-NM25-00709 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:32 | January | 2026 | 2026-01-13 10:58 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 89
202509-NM25-00711 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 16:03 | January | 2026 | 2026-01-19 11:22 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 13 | 0 | 2026-04-01 | 84
202509-NM25-00738 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-24 10:38 | October | 2025 | 2026-01-20 13:10 | 88 | Study | Estudio (E) | Activated | Backlog |  | No | 88 |  | MAYAGUEZ | January |  | 88 | 0 | 2026-04-01 | 159
202509-NM25-00743 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 16:38 | January | 2026 | 2026-01-26 13:12 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 21 | 0 | 2026-04-01 | 85
202509-NM25-00763 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:57 | January | 2026 | 2026-01-14 14:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 83
202509-NM25-00782 | GDL17 | Residencial | 6 | Out of period | 2025-10-01 14:03 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 181
202509-NM25-00800 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:21 | February | 2026 | 2026-02-19 09:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202509-NM25-00801 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:35 | March | 2026 | 2026-03-16 15:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 18
202509-NM25-00803 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:56 | February | 2026 | 2026-02-26 10:49 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 9 | 0 | 2026-04-01 | 43
202509-NM25-00804 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 09:34 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 36
202509-NM25-00805 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:24 | February | 2026 | 2026-03-04 14:14 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 36
202509-NM25-00882 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:22 | March | 2026 | 2026-03-16 16:01 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 11 | 0 | 2026-04-01 | 26
202509-NM25-00890 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-21 08:02 | October | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  |  |  |  | ARECIBO |  |  |  |  | 2026-04-01 | 162
202509-NM25-00899 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:28 | February | 2026 | 2026-03-03 14:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202509-NM25-00900 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-10 19:23 | November | 2025 | 2026-01-09 09:11 | 60 | Study | Estudio (E) | Activated | Backlog |  | No | 60 |  | MAYAGUEZ | January |  | 60 | 0 | 2026-04-01 | 141
202509-NM25-00933 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:08 | January | 2026 | 2026-02-02 12:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202509-NM25-00947 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:10 | February | 2026 | 2026-02-26 10:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202509-NM25-00954 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 16:30 | February | 2026 | 2026-02-10 15:52 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 56
202509-NM25-01046 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-04 14:20 | September | 2025 | 2026-01-29 07:38 | 147 | Study | Estudio (E) | Activated | Backlog |  | No | 147 |  | SAN JUAN | January |  | 147 | 0 | 2026-04-01 | 208
202509-NM25-01056 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-23 11:48 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 160
202509-NM25-01135 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 17:01 | February | 2026 | 2026-03-02 10:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202509-NM25-01152 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:46 | February | 2026 | 2026-02-27 15:06 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 39
202509-NM25-01154 | GDL17 | Residencial | 5.76 | Out of period | 2025-09-05 09:24 | September | 2025 | 2026-01-07 14:31 | 124 | Study | Estudio (E) | Activated | Backlog |  | No | 124 |  | MAYAGUEZ | January |  | 124 | 0 | 2026-04-01 | 208
202509-NM25-01155 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 08:57 | February | 2026 | 2026-02-16 14:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 48
202509-NM25-01185 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:47 | January | 2026 | 2026-01-23 10:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 71
202509-NM25-01186 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 22:48 | February | 2026 | 2026-02-23 16:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 43
202509-NM25-01191 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:31 | February | 2026 | 2026-02-04 13:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-01206 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:51 | February | 2026 | 2026-02-16 15:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 47
202509-NM25-01224 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 07:44 | February | 2026 | 2026-02-09 09:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202509-NM25-01225 | GDL17 | Residencial | 3.8 | Period | 2026-01-29 15:18 | January | 2026 | 2026-03-04 09:55 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March | 1 | 3 | 31 | 2026-04-01 | 61
202509-NM25-01241 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:26 | February | 2026 | 2026-02-24 07:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202509-NM25-01243 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:45 | January | 2026 | 2026-01-12 13:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 85
202509-NM25-01244 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 16:54 | February | 2026 | 2026-02-13 15:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 48
202509-NM25-01247 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:27 | February | 2026 | 2026-03-03 14:16 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 37
202509-NM25-01249 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:57 | February | 2026 | 2026-02-25 15:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202509-NM25-01253 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:53 | January | 2026 | 2026-02-09 07:32 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 60
202509-NM25-01265 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:26 | February | 2026 | 2026-02-27 15:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 35
202509-NM25-01269 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-05 12:13 | September | 2025 | 2026-03-03 08:47 | 179 | Study | Estudio (E) | Activated | Backlog |  | No | 179 |  | SAN JUAN | March |  | 179 | 0 | 2026-04-01 | 207
202509-NM25-01273 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:20 | February | 2026 | 2026-03-05 11:22 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 36
202509-NM25-01277 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:23 | February | 2026 | 2026-03-05 08:09 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 40
202509-NM25-01279 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 01:28 | February | 2026 | 2026-02-23 09:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 42
202509-NM25-01286 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-05 13:55 | September | 2025 | 2026-01-29 09:01 | 146 | Study | Estudio (E) | Activated | Backlog |  | No | 146 |  | MAYAGUEZ | January |  | 146 | 0 | 2026-04-01 | 207
202509-NM25-01290 | GDL17 | Residencial | 3.8 | Out of period | 2025-10-24 08:30 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 159
202509-NM25-01305 | GDL17 | Residencial | 5.76 | Period | 2026-01-26 18:18 | January | 2026 | 2026-01-30 07:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 64
202509-NM25-01316 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:50 | January | 2026 | 2026-01-28 13:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202509-NM25-01317 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:22 | February | 2026 | 2026-02-27 07:52 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 39
202509-NM25-01323 | GDL17 | Residencial | 12 | Out of period | 2025-09-05 19:52 | September | 2025 | 2026-01-21 13:14 | 138 | Study | Estudio (E) | Activated | Backlog |  | No | 138 |  | MAYAGUEZ | January |  | 138 | 0 | 2026-04-01 | 207
202509-NM25-01326 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:45 | March | 2026 | 2026-03-17 13:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 19
202509-NM25-01339 | GDL17 | Residencial | 6.144 | Period | 2026-02-20 13:33 | February | 2026 | 2026-02-25 15:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202509-NM25-01342 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 10:15 | February | 2026 | 2026-02-20 07:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202509-NM25-01353 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:36 | February | 2026 | 2026-02-05 10:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-01354 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-05 15:34 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 207
202509-NM25-01357 | GDL17 | Residencial | 3.8 | Period | 2026-03-08 14:12 | March | 2026 | 2026-03-09 10:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 23
202509-NM25-01361 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:42 | February | 2026 | 2026-02-12 15:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202509-NM25-01365 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:23 | February | 2026 | 2026-02-16 13:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 48
202509-NM25-01368 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:00 | January | 2026 | 2026-01-27 15:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 64
202509-NM25-01373 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:01 | February | 2026 | 2026-03-10 15:10 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 12 | 0 | 2026-04-01 | 33
202509-NM25-01374 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-05 16:19 | September | 2025 | 2026-01-14 14:03 | 131 | Study | Estudio (E) | Activated | Backlog |  | No | 131 |  | PONCE | January |  | 131 | 0 | 2026-04-01 | 207
202509-NM25-01376 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-05 16:26 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 207
202509-NM25-01387 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:27 | January | 2026 | 2026-02-03 13:47 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 64
202509-NM25-01389 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 18:55 | February | 2026 | 2026-03-17 16:51 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 18 | 0 | 2026-04-01 | 32
202509-NM25-01390 | GDL17 | Residencial | 7.68 | Out of period | 2025-09-18 14:16 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 194
202509-NM25-01397 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:12 | March | 2026 | 2026-03-19 14:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 19
202509-NM25-01398 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:45 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 36
202509-NM25-01410 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 14:22 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 12
202509-NM25-01465 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:12 | January | 2026 | 2026-02-12 15:45 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 2 | 13 | 2026-04-01 | 63
202509-NM25-01471 | GDL17 | Comercial | 11.5 | Out of period | 2025-11-07 08:33 | November | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 145
202509-NM25-01515 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:16 | January | 2026 | 2026-01-16 10:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 76
202509-NM25-01549 | GDL17 | Residencial | 6.528 | Out of period | 2025-11-21 13:38 | November | 2025 | 2026-01-14 08:46 | 54 | Study | Estudio (E) | Activated | Backlog |  | No | 54 |  | PONCE | January |  | 53 | 0 | 2026-04-01 | 130
202509-NM25-01558 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 11:43 | March | 2026 | 2026-03-18 09:24 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 14 | 0 | 2026-04-01 | 28
202509-NM25-01563 | GDL17 | Residencial | 3.8 | Period | 2026-01-14 15:38 | January | 2026 | 2026-01-16 14:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 76
202509-NM25-01595 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 07:58 | February | 2026 | 2026-02-06 08:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 56
202509-NM25-01603 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-16 10:02 | October | 2025 | 2026-01-14 08:55 | 90 | Study | Estudio (E) | Activated | Backlog |  | No | 90 |  | MAYAGUEZ | January |  | 90 | 0 | 2026-04-01 | 167
202509-NM25-01658 | GDL17 | Residencial | 23 | Period | 2026-02-02 16:48 | February | 2026 | 2026-02-04 16:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-01659 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-26 15:36 | September | 2025 | 2026-01-07 11:08 | 103 | Study | Estudio (E) | Activated | Backlog |  | No | 103 |  | MAYAGUEZ | January |  | 103 | 0 | 2026-04-01 | 186
202509-NM25-01682 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-08 11:28 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 221 | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 205
202509-NM25-01685 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 07:37 | February | 2026 | 2026-02-20 13:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 44
202509-NM25-01688 | GDL17 | Residencial | 11.5 | Period | 2026-03-01 09:54 | March | 2026 | 2026-03-05 15:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 31
202509-NM25-01693 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 17:11 | February | 2026 | 2026-03-13 15:19 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 2 | 28 | 2026-04-01 | 48
202509-NM25-01694 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-08 13:06 | September | 2025 | 2026-02-11 14:08 | 156 | Study | Estudio (E) | Activated | Backlog |  | No | 156 |  | SAN JUAN | February |  | 156 | 0 | 2026-04-01 | 204
202509-NM25-01697 | GDL17 | Residencial | 23 | Period | 2026-01-07 13:30 | January | 2026 | 2026-01-12 15:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202509-NM25-01701 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-08 12:10 | September | 2025 | 2026-01-02 12:35 | 116 | Study | Estudio (E) | Activated | Backlog |  | No | 116 |  | MAYAGUEZ | January |  | 116 | 0 | 2026-04-01 | 204
202509-NM25-01702 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-08 12:10 | September | 2025 | 2026-01-12 15:48 | 126 | Study | Estudio (E) | Activated | Backlog |  | No | 126 |  | CAGUAS | January |  | 126 | 0 | 2026-04-01 | 204
202509-NM25-01717 | GDL17 | Residencial | 3.8 | Out of period | 2025-09-17 13:51 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 195
202509-NM25-01721 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:26 | February | 2026 | 2026-02-25 10:23 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 42
202509-NM25-01732 | GDL17 | Residencial | 5.76 | Period | 2026-01-26 18:12 | January | 2026 | 2026-01-28 14:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202509-NM25-01733 | GDL17 | Residencial | 15.3 | Period | 2026-02-13 14:19 | February | 2026 | 2026-02-18 11:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 46
202509-NM25-01745 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:23 | February | 2026 | 2026-03-04 14:37 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 35
202509-NM25-01747 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:26 | February | 2026 | 2026-03-04 07:48 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 9 | 0 | 2026-04-01 | 37
202509-NM25-01749 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:17 | February | 2026 | 2026-03-13 12:52 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 3 | 11 | 6 | 2026-04-01 | 35
202509-NM25-01767 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 19:41 | February | 2026 | 2026-02-20 08:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 43
202509-NM25-01774 | GDL17 | Residencial | 3.84 | Period | 2026-01-08 08:13 | January | 2026 | 2026-01-13 15:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202509-NM25-01776 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 15:45 | February | 2026 | 2026-02-16 16:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202509-NM25-01778 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:11 | January | 2026 | 2026-02-03 12:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 60
202509-NM25-01816 | GDL17 | Residencial | 5.76 | Period | 2026-01-23 11:31 | January | 2026 | 2026-01-26 16:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202509-NM25-01834 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-08 17:00 | September | 2025 | 2026-01-08 10:35 | 122 | Study | Estudio (E) | Activated | Backlog |  | No | 122 |  | MAYAGUEZ | January |  | 122 | 0 | 2026-04-01 | 204
202509-NM25-01837 | GDL17 | Residencial | 7.6 | Period | 2026-01-05 14:05 | January | 2026 | 2026-01-14 14:29 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 9 | 0 | 2026-04-01 | 85
202509-NM25-01843 | GDL17 | Residencial | 5.76 | Period | 2026-02-13 17:39 | February | 2026 | 2026-02-20 10:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 46
202509-NM25-01851 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 03:27 | February | 2026 | 2026-02-26 11:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 41
202509-NM25-01855 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:21 | February | 2026 | 2026-02-13 09:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202509-NM25-01867 | GDL17 | Residencial | 5.1 | Out of period | 2025-09-09 08:51 | September | 2025 | 2026-01-21 13:18 | 134 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | January | 1 | 4 | 130 | 2026-04-01 | 204
202509-NM25-01905 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:50 | January | 2026 | 2026-02-03 13:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 63
202509-NM25-01925 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:07 | February | 2026 | 2026-02-27 15:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 35
202509-NM25-01932 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-09 10:33 | September | 2025 | 2026-03-12 08:19 | 184 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | March | 3 | 115 | 69 | 2026-04-01 | 204
202509-NM25-01935 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 08:32 | January | 2026 | 2026-01-23 07:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 72
202509-NM25-01938 | GDL17 | Residencial | 4.608 | Period | 2026-01-20 14:35 | January | 2026 | 2026-01-22 10:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202509-NM25-01939 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-11 11:24 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 202
202509-NM25-01952 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 19:06 | March | 2026 | 2026-03-09 15:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 25
202509-NM25-01957 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-09 09:39 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 204
202509-NM25-01992 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:28 | January | 2026 | 2026-01-22 10:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202509-NM25-02021 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-09 11:43 | September | 2025 | 2026-01-21 13:29 | 134 | Study | Estudio (E) | Activated | Backlog |  | No | 134 |  | BAYAMON | January |  | 134 | 0 | 2026-04-01 | 204
202509-NM25-02077 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-18 08:28 | October | 2025 | 2026-01-02 15:09 | 76 | Study | Estudio (E) | Activated | Backlog |  | No | 76 |  | BAYAMON | January |  | 76 | 0 | 2026-04-01 | 165
202509-NM25-02098 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-04 09:12 | November | 2025 | 2026-01-16 13:37 | 73 | Study | Estudio (E) | Activated | Backlog |  | No | 73 |  | SAN JUAN | January |  | 74 | 0 | 2026-04-01 | 148
202509-NM25-02111 | GDL17 | Residencial | 4.392 | Period | 2026-03-05 09:29 | March | 2026 | 2026-03-10 13:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 27
202509-NM25-02114 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:20 | February | 2026 | 2026-02-19 13:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 43
202509-NM25-02117 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 12:55 | January | 2026 | 2026-01-27 15:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 64
202509-NM25-02124 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-09 15:41 | September | 2025 | 2026-01-07 14:51 | 120 | Study | Estudio (E) | Activated | Backlog |  | No | 120 |  | MAYAGUEZ | January |  | 120 | 0 | 2026-04-01 | 203
202509-NM25-02158 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 15:58 | March | 2026 | 2026-03-11 14:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 25
202509-NM25-02179 | GDL17 | Residencial | 23 | Period | 2026-01-26 17:13 | January | 2026 | 2026-02-05 16:13 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 10 | 0 | 2026-04-01 | 64
202509-NM25-02208 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-10 08:01 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 203
202509-NM25-02231 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 14:12 | March | 2026 | 2026-03-31 13:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 5
202509-NM25-02233 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:57 | January | 2026 | 2026-01-14 13:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202509-NM25-02238 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:19 | February | 2026 | 2026-03-06 12:51 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 37
202509-NM25-02241 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-10 09:02 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 203
202509-NM25-02248 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:28 | February | 2026 | 2026-03-03 08:17 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 36
202509-NM25-02268 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 12:49 | March | 2026 | 2026-03-13 12:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202509-NM25-02271 | GDL17 | Residencial | 23 | Out of period | 2025-10-17 16:59 | October | 2025 | 2026-01-27 11:25 | 102 | Study | Estudio (E) | Activated | Backlog |  | No | 102 |  | ARECIBO | January |  | 102 | 0 | 2026-04-01 | 165
202509-NM25-02274 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 09:54 | March | 2026 | 2026-04-02 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 1
202509-NM25-02278 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:18 | February | 2026 | 2026-02-12 15:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 48
202509-NM25-02279 | GDL17 | Residencial | 5.76 | Out of period | 2025-10-16 15:20 | October | 2025 | 2026-02-13 12:48 | 120 | Study | Estudio (E) | Activated | Backlog |  | No | 120 |  | CAGUAS | February |  | 120 | 0 | 2026-04-01 | 166
202509-NM25-02306 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:12 | February | 2026 | 2026-02-11 14:27 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 56
202509-NM25-02307 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 08:39 | March | 2026 | 2026-03-19 10:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 14
202509-NM25-02311 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:36 | March | 2026 | 2026-03-31 13:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202509-NM25-02312 | GDL17 | Residencial | 3.8 | Period | 2026-01-30 13:24 | January | 2026 | 2026-02-03 12:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 60
202509-NM25-02318 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 11:03 | January | 2026 | 2026-01-26 09:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 70
202509-NM25-02331 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-10 11:39 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 209 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 203
202509-NM25-02334 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 11:26 | January | 2026 | 2026-01-22 09:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 70
202509-NM25-02350 | GDL17 | Residencial | 23 | Period | 2026-02-16 16:49 | February | 2026 | 2026-03-03 09:29 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 4 | 11 | 2026-04-01 | 43
202509-NM25-02362 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-10 13:50 | September | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | BAYAMON |  |  |  |  | 2026-04-01 | 202
202509-NM25-02378 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 11:49 | February | 2026 | 2026-02-24 14:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 41
202509-NM25-02385 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-10 14:56 | September | 2025 | 2026-01-02 14:28 | 114 | Study | Estudio (E) | Activated | Backlog |  | No | 114 |  | MAYAGUEZ | January |  | 114 | 0 | 2026-04-01 | 202
202509-NM25-02397 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-10 19:46 | September | 2025 | 2026-01-29 09:27 | 141 | Study | Estudio (E) | Activated | Backlog |  | No | 141 |  | ARECIBO | January |  | 141 | 0 | 2026-04-01 | 202
202509-NM25-02421 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:29 | January | 2026 | 2026-02-02 11:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202509-NM25-02467 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 17:39 | January | 2026 | 2026-01-16 13:28 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 82
202509-NM25-02479 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:29 | February | 2026 | 2026-02-06 15:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 57
202509-NM25-02488 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:35 | February | 2026 | 2026-03-03 15:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 34
202509-NM25-02493 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:45 | February | 2026 | 2026-02-24 07:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202509-NM25-02497 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:09 | February | 2026 | 2026-02-18 09:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 48
202509-NM25-02516 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:35 | February | 2026 | 2026-02-24 08:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202509-NM25-02522 | GDL17 | Residencial | 17.5 | Period | 2026-02-23 09:19 | February | 2026 | 2026-03-06 10:45 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 37
202509-NM25-02576 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 09:16 | February | 2026 | 2026-02-11 10:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 51
202509-NM25-02605 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 19:03 | February | 2026 | 2026-03-18 12:41 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 23 | 0 | 2026-04-01 | 36
202509-NM25-02641 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 19:21 | November | 2025 | 2026-01-16 12:43 | 67 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 1 | 56 | 11 | 2026-04-01 | 141
202509-NM25-02680 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 11:45 | January | 2026 | 2026-01-22 13:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202509-NM25-02700 | GDL17 | Residencial | 9 | Out of period | 2025-09-17 13:35 | September | 2025 | 2026-01-02 10:02 | 107 | Study | Estudio (E) | Activated | Backlog |  | No | 107 |  | MAYAGUEZ | January |  | 107 | 0 | 2026-04-01 | 195
202509-NM25-02707 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:53 | January | 2026 | 2026-01-26 10:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 69
202509-NM25-02723 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:32 | January | 2026 | 2026-01-30 08:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 65
202509-NM25-02741 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:39 | January | 2026 | 2026-01-19 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 76
202509-NM25-02743 | GDL17 | Residencial | 8 | Out of period | 2025-09-11 14:13 | September | 2025 | 2026-03-16 12:42 | 186 | Study | Estudio (E) | Activated | Backlog |  | No | 186 |  | BAYAMON | March |  | 186 | 0 | 2026-04-01 | 201
202509-NM25-02748 | GDL17 | Residencial | 0.768 | Out of period | 2025-09-27 09:16 | September | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 186
202509-NM25-02755 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 16:12 | January | 2026 | 2026-01-13 16:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 83
202509-NM25-02760 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-11 14:06 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 201
202509-NM25-02796 | GDL17 | Residencial | 5.76 | Out of period | 2025-10-16 14:00 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 166
202509-NM25-02812 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:21 | January | 2026 | 2026-01-13 09:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202509-NM25-02822 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:38 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 88
202509-NM25-02840 | GDL17 | Residencial | 23 | Period | 2026-03-10 18:27 | March | 2026 | 2026-03-12 16:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 21
202509-NM25-02849 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:22 | January | 2026 | 2026-01-28 09:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202509-NM25-02877 | GDL17 | Residencial | 23 | Period | 2026-03-03 07:37 | March | 2026 | 2026-03-05 14:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202509-NM25-02912 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:26 | February | 2026 | 2026-02-26 13:38 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 42
202509-NM25-02948 | GDL17 | Comercial | 11.4 | Out of period | 2025-10-01 18:27 | October | 2025 | 2026-01-02 13:41 | 93 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 74 | 19 | 2026-04-01 | 181
202509-NM25-02956 | GDL17 | Residencial | 5.376 | Period | 2026-02-17 08:39 | February | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 43
202509-NM25-02972 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 14:15 | March | 2026 | 2026-03-16 15:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202509-NM25-02979 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 14:35 | January | 2026 | 2026-01-14 13:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 81
202509-NM25-02980 | GDL17 | Residencial | 8 | Out of period | 2025-09-23 12:49 | September | 2025 | 2026-01-05 12:59 | 104 | Study | Estudio (E) | Activated | Backlog |  | No | 104 |  | MAYAGUEZ | January |  | 104 | 0 | 2026-04-01 | 189
202509-NM25-02984 | GDL17 | Residencial | 6.912 | Out of period | 2025-09-22 15:41 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 190
202509-NM25-02986 | GDL17 | Residencial | 5.76 | Period | 2026-01-29 17:50 | January | 2026 | 2026-02-02 16:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202509-NM25-02991 | GDL17 | Residencial | 8.448 | Out of period | 2025-09-12 13:01 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 200
202509-NM25-02993 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:01 | February | 2026 | 2026-02-04 11:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-03004 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-12 15:07 | September | 2025 | 2026-02-12 08:03 | 153 | Study | Estudio (E) | Activated | Backlog |  | No | 153 |  | CAGUAS | February |  | 153 | 0 | 2026-04-01 | 200
202509-NM25-03015 | GDL17 | Residencial | 1.152 | Out of period | 2025-09-27 09:40 | September | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 186
202509-NM25-03029 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-18 07:32 | October | 2025 | 2026-01-07 14:42 | 81 | Study | Estudio (E) | Activated | Backlog |  | No | 81 |  | MAYAGUEZ | January |  | 81 | 0 | 2026-04-01 | 165
202509-NM25-03049 | GDL17 | Residencial | 3.8 | Period | 2026-02-16 19:07 | February | 2026 | 2026-02-24 07:56 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 6 | 2 | 2026-04-01 | 43
202509-NM25-03068 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 15:43 | January | 2026 | 2026-01-28 10:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202509-NM25-03074 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:16 | February | 2026 | 2026-03-03 13:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 35
202509-NM25-03085 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 20:39 | February | 2026 | 2026-02-24 10:41 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 46
202509-NM25-03094 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 12:25 | January | 2026 | 2026-01-09 10:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 84
202509-NM25-03106 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:11 | February | 2026 | 2026-02-26 14:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202509-NM25-03109 | GDL17 | Residencial | 3.84 | Out of period | 2025-09-22 13:28 | September | 2025 | 2026-01-08 15:18 | 108 | Study | Estudio (E) | Activated | Backlog |  | No | 108 |  | MAYAGUEZ | January |  | 108 | 0 | 2026-04-01 | 190
202509-NM25-03110 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:52 | February | 2026 | 2026-02-20 16:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 43
202509-NM25-03130 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-12 15:21 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 145 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 139
202509-NM25-03168 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:47 | February | 2026 | 2026-02-24 09:44 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 43
202509-NM25-03194 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 14:03 | January | 2026 | 2026-01-09 10:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 84
202509-NM25-03206 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 14:54 | February | 2026 | 2026-02-19 08:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 46
202509-NM25-03223 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-20 14:47 | October | 2025 | 2026-01-08 14:34 | 80 | Study | Estudio (E) | Activated | Backlog |  | No | 80 |  | MAYAGUEZ | January |  | 80 | 0 | 2026-04-01 | 162
202509-NM25-03240 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:07 | March | 2026 | 2026-04-07 15:18 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 13 | 0 | 2026-04-01 | 7
202509-NM25-03262 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-01 11:08 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 182
202509-NM25-03291 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 17:36 | February | 2026 | 2026-02-26 08:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202509-NM25-03299 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:03 | January | 2026 | 2026-02-09 15:18 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 61
202509-NM25-03316 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-15 13:34 | September | 2025 | 2026-01-22 15:47 | 129 | Study | Estudio (E) | Activated | Backlog |  | No | 129 |  | BAYAMON | January |  | 129 | 0 | 2026-04-01 | 197
202509-NM25-03318 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 18:04 | January | 2026 | 2026-01-13 15:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202509-NM25-03332 | GDL17 | Residencial | 3.8 | Period | 2026-01-26 17:06 | January | 2026 | 2026-01-29 09:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 64
202509-NM25-03338 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 18:33 | February | 2026 | 2026-02-25 07:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 41
202509-NM25-03354 | GDL17 | Residencial | 3.8 | Period | 2026-02-17 15:28 | February | 2026 | 2026-02-23 10:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-03357 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:41 | February | 2026 | 2026-02-27 08:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 36
202509-NM25-03361 | GDL17 | Residencial | 11.5 | Period | 2026-02-28 11:49 | February | 2026 | 2026-03-04 12:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 32
202509-NM25-03366 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 12:59 | February | 2026 | 2026-03-02 15:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 34
202509-NM25-03375 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 17:06 | February | 2026 | 2026-02-12 10:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202509-NM25-03378 | GDL17 | Residencial | 15.3 | Period | 2026-02-24 15:29 | February | 2026 | 2026-03-05 15:49 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 9 | 0 | 2026-04-01 | 35
202509-NM25-03381 | GDL17 | Residencial | 9.216 | Out of period | 2025-10-21 13:12 | October | 2025 | 2026-01-07 14:39 | 78 | Study | Estudio (E) | Activated | Backlog |  | No | 78 |  | BAYAMON | January |  | 78 | 0 | 2026-04-01 | 161
202509-NM25-03385 | GDL17 | Comercial | 11.5 | Period | 2026-02-17 12:08 | February | 2026 | 2026-02-23 09:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-03389 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:09 | February | 2026 | 2026-02-12 13:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 49
202509-NM25-03393 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 17:05 | March | 2026 | 2026-03-17 10:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 18
202509-NM25-03402 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:50 | February | 2026 | 2026-02-18 14:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202509-NM25-03404 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:56 | February | 2026 | 2026-02-23 09:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-03405 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:45 | February | 2026 | 2026-02-20 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 43
202509-NM25-03406 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 13:03 | March | 2026 | 2026-03-11 14:05 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 28
202509-NM25-03407 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 20:10 | March | 2026 | 2026-03-13 12:50 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 26
202509-NM25-03408 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 18:59 | February | 2026 | 2026-02-26 08:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 38
202509-NM25-03409 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:27 | February | 2026 | 2026-03-02 09:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 36
202509-NM25-03410 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:28 | March | 2026 | 2026-03-05 08:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 30
202509-NM25-03481 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-16 09:40 | September | 2025 | 2026-01-02 10:36 | 108 | Study | Estudio (E) | Activated | Backlog |  | No | 108 |  | MAYAGUEZ | January |  | 108 | 0 | 2026-04-01 | 197
202509-NM25-03546 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-16 11:12 | September | 2025 | 2026-01-09 08:44 | 115 | Study | Estudio (E) | Activated | Backlog |  | No | 115 |  | MAYAGUEZ | January |  | 115 | 0 | 2026-04-01 | 197
202509-NM25-03547 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-24 14:16 | September | 2025 | 2026-02-02 12:50 | 131 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | February | 1 | 121 | 10 | 2026-04-01 | 188
202509-NM25-03551 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 08:59 | January | 2026 | 2026-01-26 12:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 72
202509-NM25-03555 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-12 12:09 | November | 2025 | 2026-01-19 14:27 | 68 | Study | Estudio (E) | Activated | Backlog |  | No | 68 |  | MAYAGUEZ | January |  | 68 | 0 | 2026-04-01 | 139
202509-NM25-03594 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-24 16:51 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 127
202509-NM25-03610 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:40 | February | 2026 | 2026-02-26 09:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 36
202509-NM25-03611 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-16 14:07 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 196
202509-NM25-03633 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 20:01 | February | 2026 | 2026-02-27 08:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 40
202509-NM25-03640 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 17:02 | February | 2026 | 2026-02-27 08:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 36
202509-NM25-03641 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:24 | February | 2026 | 2026-03-02 13:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 35
202509-NM25-03648 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 14:31 | February | 2026 | 2026-02-19 15:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202509-NM25-03654 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:44 | March | 2026 | 2026-03-05 13:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 29
202509-NM25-03668 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 14:25 | March | 2026 | 2026-03-23 13:31 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 14 | 0 | 2026-04-01 | 22
202509-NM25-03672 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-15 18:32 | December | 2025 | 2026-03-30 16:22 | 105 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 75 | 30 | 2026-04-01 | 106
202509-NM25-03673 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:52 | February | 2026 | 2026-02-26 11:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202509-NM25-03681 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-16 16:31 | September | 2025 | 2026-01-02 14:00 | 108 | Study | Estudio (E) | Activated | Backlog |  | No | 108 |  | MAYAGUEZ | January |  | 108 | 0 | 2026-04-01 | 196
202509-NM25-03683 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-17 15:38 | October | 2025 | 2026-01-30 08:23 | 105 | Study | Estudio (E) | Activated | Backlog |  | No | 105 |  | ARECIBO | January |  | 105 | 0 | 2026-04-01 | 165
202509-NM25-03685 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 10:42 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 49
202509-NM25-03690 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:44 | February | 2026 | 2026-02-12 13:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202509-NM25-03696 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 14:02 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 131
202509-NM25-03699 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-17 09:10 | September | 2025 | 2026-02-19 14:36 | 155 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 1 | 153 | 2 | 2026-04-01 | 196
202509-NM25-03707 | GDL17 | Residencial | 3.84 | Out of period | 2025-11-04 14:22 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 174 | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 147
202509-NM25-03721 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-17 08:30 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 196
202509-NM25-03776 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:42 | January | 2026 | 2026-02-03 10:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 61
202509-NM25-03790 | GDL17 | Residencial | 8 | Out of period | 2025-11-20 11:03 | November | 2025 | 2026-01-13 13:26 | 54 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 8 | 46 | 2026-04-01 | 132
2025-GD-00201 | GD1M | Comercial | 132 | Out of period | 2025-11-06 | November | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 146
2025-GD-00216 | GD1M | Comercial | 48 | Out of period | 2025-12-12 | December | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAROLINA |  |  |  |  | 2026-04-01 | 110
2025-GD-00207 | GD1M | Residencial | 49.65 | Out of period | 2025-11-24 | November | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 128
2025-GD-00175 | GD1M | Comercial | 31.49 | Out of period | 2025-10-15 | October | 2025 |  |  | Anejar Documentos, Asignar Inspector | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 168
2025-GD-00196 | TRANSMISSION | Comercial | - | Out of period | 2025-11-03 | November | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 149
2025-GD-00199 | GD1M | Comercial | 746.3 | Out of period | 2025-11-06 | November | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 146
2025-GD-00182 | GD1M | Comercial | 1476 | Out of period | 2025-10-21 | October | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 162
2025-GD-00188 | GD1M | Comercial | 46.2 | Out of period | 2025-10-27 | October | 2025 |  |  | Completar Informacion Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 156
2025-GD-00215 | GD1M | Comercial | 25.7 | Out of period | 2025-12-11 | December | 2025 |  |  | Validación | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 111
2025-GD-00203 | GD1M | Comercial | 26.112 | Out of period | 2025-11-12 | November | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 140
2025-GD-00212 | GD1M | Comercial | 120 | Out of period | 2025-12-09 | December | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 113
2025-GD-00195 | GD1M | Comercial | 34.5 | Out of period | 2025-10-29 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 154
2025-GD-00209 | GD1M | Comercial | 51 | Out of period | 2025-12-01 | December | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 121
2025-GD-00211 | GD1M | Comercial | 30 | Out of period | 2025-12-01 | December | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 121
2025-GD-00184 | GD1M | Comercial | 56 | Out of period | 2025-10-21 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 162
2025-GD-00176 | GD1M | Comercial | 34.5 | Out of period | 2025-10-16 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 167
2025-GD-00183 | GD1M | Comercial | 32 | Out of period | 2025-10-21 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 162
2025-GD-00186 | GD1M | Comercial | 50 | Out of period | 2025-10-22 | October | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 161
2025-GD-00180 | GD1M | Comercial | 27 | Out of period | 2025-10-19 | October | 2025 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 164
2025-GD-00185 | GD1M | Comercial | 30 | Out of period | 2025-10-22 | October | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 161
2025-GD-00172 | GD1M | Comercial | 30 | Out of period | 2025-10-14 | October | 2025 |  |  | Inspeccion Documentos | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 169
2025-GD-00170 | TRANSMISSION | Gubernamental | 3750 | Out of period | 2025-10-09 | October | 2025 |  |  | approveTransmissionEnd | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 174
2025-GD-00204 | GD1M | Comercial | 70.96 | Out of period | 2025-11-14 | November | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 138
2025-GD-00210 | GD1M | Industrial | 74.19 | Out of period | 2025-12-01 | December | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 121
2025-GD-00177 | GD1M | Comercial | 30 | Out of period | 2025-10-17 | October | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 166
2025-GD-00220 | GD1M | Comercial | 50 | Out of period | 2025-12-24 | December | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | CAROLINA |  |  |  |  | 2026-04-01 | 98
2025-GD-00217 | GD1M | Comercial | 68 | Out of period | 2025-12-15 | December | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 107
2025-GD-00205 | GD1M | Comercial | 125 | Out of period | 2025-11-22 | November | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 130
2025-GD-00173 | GD1M | Comercial | 45 | Out of period | 2025-10-14 | October | 2025 |  |  | Anejar Certificacion e Instalacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 169
2025-GD-00214 | TRANSMISSION | Comercial | 427.9 | Out of period | 2025-12-10 | December | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 112
2025-GD-00208 | GD1M | Comercial | 298.3 | Out of period | 2025-12-01 | December | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 121
2025-GD-00174 | GD1M | Comercial | 34.5 | Out of period | 2025-10-15 | October | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 168
2025-GD-00181 | GD1M | Agricultural | 47.1 | Out of period | 2025-10-20 | October | 2025 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 163
2025-GD-00171 | GD1M | Comercial | 50 | Out of period | 2025-10-09 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 174
2025-GD-00190 | GD1M | Comercial | 240 | Out of period | 2025-10-29 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 154
2025-GD-00206 | GD1M | Comercial | 375 | Out of period | 2025-11-22 | November | 2025 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 130
2025-GD-00193 | GD1M | Comercial | 33.3 | Out of period | 2025-10-29 | October | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 154
2025-GD-00200 | GD1M | Comercial | 33.3 | Out of period | 2025-11-06 | November | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 146
2025-GD-00191 | GD1M | Comercial | 66.6 | Out of period | 2025-10-29 | October | 2025 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 154
2025-GD-00218 | TRANSMISSION | Gubernamental | 2500 | Out of period | 2025-12-19 | December | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 103
2025-GD-00194 | GD1M | Comercial | 62 | Out of period | 2025-10-29 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 154
2025-GD-00178 | TRANSMISSION | Industrial | 240 | Out of period | 2025-10-17 | October | 2025 |  |  | approveTransmissionEnd | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 166
2025-GD-00202 | GD1M | Comercial | 30 | Out of period | 2025-11-10 | November | 2025 |  |  | Pago Aportacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 142
2025-GD-00169 | GD1M | Comercial | 36 | Out of period | 2025-10-06 | October | 2025 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Estudio (E) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 177
2025-GD-00213 | GD1M | Comercial | 196 | Out of period | 2025-12-09 | December | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 113
2025-GD-00192 | GD1M | Comercial | 225 | Out of period | 2025-10-29 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 154
2025-GD-00187 | GD1M | Residencial | 34.5 | Out of period | 2025-10-23 | October | 2025 |  |  | Pago Aportacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 160
2025-GD-00219 | GD1M | Comercial | 132 | Out of period | 2025-12-23 | December | 2025 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 99
2025-GD-00189 | GD1M | Comercial | 34.5 | Out of period | 2025-10-28 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 155
2025-GD-00179 | GD1M | Comercial | 34.5 | Out of period | 2025-10-17 | October | 2025 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 166
202509-NM25-03801 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-17 11:10 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 196
202509-NM25-03827 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:57 | February | 2026 | 2026-02-06 11:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 57
202509-NM25-03834 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:07 | March | 2026 | 2026-03-13 09:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 21
202509-NM25-03840 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:30 | January | 2026 | 2026-02-02 15:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 64
202509-NM25-03847 | GDL17 | Residencial | 8 | Out of period | 2025-09-30 09:20 | September | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 183
202509-NM25-03853 | GDL17 | Residencial | 6 | Period | 2026-01-21 15:19 | January | 2026 | 2026-01-26 13:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 69
202509-NM25-03871 | GDL17 | Residencial | 4.992 | Out of period | 2025-11-18 07:58 | November | 2025 | 2026-01-16 13:13 | 59 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 55 | 4 | 2026-04-01 | 134
202509-NM25-03872 | GDL17 | Residencial | 15.2 | Out of period | 2025-09-18 18:56 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 194
202509-NM25-03877 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-20 11:56 | September | 2025 | 2026-03-16 11:16 | 177 | Study | Estudio (E) | Activated | Backlog |  | No | 177 |  | BAYAMON | March |  | 177 | 0 | 2026-04-01 | 193
202509-NM25-03883 | GDL17 | Residencial | 11.5 | Period | 2026-01-01 17:10 | January | 2026 | 2026-01-07 10:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 89
202509-NM25-03891 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:50 | January | 2026 | 2026-01-12 11:30 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 85
202509-NM25-03898 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-17 13:52 | September | 2025 | 2026-01-16 09:56 | 121 | Study | Estudio (E) | Activated | Backlog |  | No | 121 |  | CAGUAS | January |  | 121 | 0 | 2026-04-01 | 195
202509-NM25-03900 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:16 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 83
202509-NM25-03916 | GDL17 | Residencial | 3.8 | Out of period | 2025-09-17 15:22 | September | 2025 | 2026-01-26 10:17 | 131 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 9 | 122 | 2026-04-01 | 195
202509-NM25-03923 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:34 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 35
202509-NM25-03928 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:57 | January | 2026 | 2026-02-10 08:36 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 61
202509-NM25-03929 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:03 | February | 2026 | 2026-02-23 09:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-03940 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 19:37 | February | 2026 | 2026-03-03 09:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202509-NM25-03942 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-17 15:33 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 195
202509-NM25-03947 | GDL17 | Residencial | 3.456 | Period | 2026-01-29 16:35 | January | 2026 | 2026-02-09 09:15 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 61
202509-NM25-03949 | GDL17 | Residencial | 5.76 | Period | 2026-02-19 11:46 | February | 2026 | 2026-02-24 14:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202509-NM25-03953 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 18:23 | February | 2026 | 2026-02-23 09:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-03965 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 18:21 | February | 2026 | 2026-03-03 13:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 35
202509-NM25-03966 | GDL17 | Residencial | 8 | Out of period | 2025-10-23 14:39 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 159
202509-NM25-03967 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-18 08:17 | September | 2025 | 2026-01-07 08:52 | 111 | Study | Estudio (E) | Activated | Backlog |  | No | 111 |  | MAYAGUEZ | January |  | 112 | 0 | 2026-04-01 | 195
202509-NM25-03970 | GDL17 | Residencial | 17.26 | Period | 2026-02-17 23:27 | February | 2026 | 2026-02-23 09:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-03971 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:41 | January | 2026 | 2026-01-14 14:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202509-NM25-03974 | GDL17 | Comercial | 11.5 | Period | 2026-02-16 15:04 | February | 2026 | 2026-02-20 14:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 43
202509-NM25-03979 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:46 | March | 2026 | 2026-03-11 07:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 26
202509-NM25-04021 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:53 | February | 2026 | 2026-02-25 12:57 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 48
202509-NM25-04024 | GDL17 | Residencial | 11.5 | Period | 2026-02-28 11:53 | February | 2026 | 2026-03-04 10:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 32
202509-NM25-04027 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:35 | February | 2026 | 2026-02-25 08:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202509-NM25-04052 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-01 11:23 | October | 2025 | 2026-01-05 08:25 | 96 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 93 | 3 | 2026-04-01 | 182
202509-NM25-04055 | GDL17 | Residencial | 12.288 | Out of period | 2025-09-18 10:31 | September | 2025 | 2026-02-25 15:24 | 160 | Study | Estudio (E) | Activated | Backlog |  | No | 160 |  | SAN JUAN | February |  | 160 | 0 | 2026-04-01 | 195
202509-NM25-04070 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-18 10:50 | September | 2025 | 2026-01-12 14:27 | 116 | Study | Estudio (E) | Activated | Backlog |  | No | 116 |  | MAYAGUEZ | January |  | 116 | 0 | 2026-04-01 | 195
202509-NM25-04140 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 19:31 | February | 2026 | 2026-02-25 13:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 41
202509-NM25-04142 | GDL17 | Residencial | 3.8 | Period | 2026-02-18 09:35 | February | 2026 | 2026-03-16 10:00 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 26 | 0 | 2026-04-01 | 42
202509-NM25-04143 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 14:26 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 148 | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 141
202509-NM25-04172 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:22 | January | 2026 | 2026-02-02 15:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202509-NM25-04195 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:24 | February | 2026 | 2026-02-11 10:09 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 57
202509-NM25-04221 | GDL17 | Residencial | 17.2 | Period | 2026-02-19 21:41 | February | 2026 | 2026-02-25 08:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202509-NM25-04231 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-05 14:48 | November | 2025 | 2026-02-04 12:42 | 91 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | February | 1 | 6 | 85 | 2026-04-01 | 146
202509-NM25-04312 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:46 | February | 2026 | 2026-02-04 15:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-04316 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-23 10:44 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 160
202509-NM25-04328 | GDL17 | Residencial | 9.216 | Out of period | 2025-11-06 09:47 | November | 2025 | 2026-01-08 09:29 | 63 | Study | Estudio (E) | Activated | Backlog |  | No | 63 |  | MAYAGUEZ | January |  | 63 | 0 | 2026-04-01 | 146
202509-NM25-04342 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:52 | March | 2026 | 2026-03-11 14:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 22
202509-NM25-04349 | GDL17 | Residencial | 8 | Out of period | 2025-10-07 19:06 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 175
202509-NM25-04352 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:41 | January | 2026 | 2026-02-05 10:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 61
202509-NM25-04354 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 14:46 | March | 2026 | 2026-04-10 07:45 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 11 | 0 | 2026-04-01 | 1
202509-NM25-04359 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:24 | February | 2026 | 2026-02-27 09:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 35
202509-NM25-04365 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:43 | February | 2026 | 2026-02-05 15:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 57
202509-NM25-04385 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 10:30 | February | 2026 | 2026-03-02 10:10 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 39
202509-NM25-04390 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-19 13:13 | September | 2025 | 2026-01-07 08:32 | 110 | Study | Estudio (E) | Activated | Backlog |  | No | 110 |  | MAYAGUEZ | January |  | 110 | 0 | 2026-04-01 | 193
202509-NM25-04404 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:26 | February | 2026 | 2026-02-18 15:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202509-NM25-04409 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-19 13:59 | September | 2025 | 2026-02-04 10:00 | 138 | Study | Estudio (E) | Activated | Backlog |  | No | 138 |  | MAYAGUEZ | February |  | 138 | 0 | 2026-04-01 | 193
202509-NM25-04416 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:13 | February | 2026 | 2026-03-05 11:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 34
202509-NM25-04434 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 09:03 | February | 2026 | 2026-02-25 10:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202509-NM25-04446 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:35 | February | 2026 | 2026-02-24 14:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202509-NM25-04449 | GDL17 | Residencial | 3.84 | Period | 2026-01-06 13:08 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 84
202509-NM25-04453 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 10:28 | February | 2026 | 2026-02-27 13:04 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 11 | 0 | 2026-04-01 | 43
202509-NM25-04459 | GDL17 | Residencial | 10.368 | Out of period | 2025-11-11 15:54 | November | 2025 | 2026-03-05 15:33 | 114 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 2 | 5 | 109 | 2026-04-01 | 140
202509-NM25-04468 | GDL17 | Residencial | 8 | Out of period | 2025-09-23 09:50 | September | 2025 | 2026-02-23 12:44 | 153 | Study | Estudio (E) | Activated | Backlog |  | No | 153 |  | ARECIBO | February |  | 153 | 0 | 2026-04-01 | 190
202509-NM25-04476 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:55 | January | 2026 | 2026-02-02 12:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 61
202509-NM25-04498 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-07 08:59 | November | 2025 | 2026-01-29 08:04 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January |  | 83 | 5 | 2026-04-01 | 145
202509-NM25-04513 | GDL17 | Residencial | 8 | Out of period | 2025-09-22 08:48 | September | 2025 | 2026-01-02 08:39 | 102 | Study | Estudio (E) | Activated | Backlog |  | No | 102 |  | MAYAGUEZ | January |  | 102 | 0 | 2026-04-01 | 191
202509-NM25-04545 | GDL17 | Residencial | 8 | Out of period | 2025-09-30 09:08 | September | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 183
202509-NM25-04554 | GDL17 | Residencial | 8 | Out of period | 2025-09-29 09:19 | September | 2025 | 2026-02-04 11:01 | 128 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 1 | 7 | 121 | 2026-04-01 | 184
202509-NM25-04568 | GDL17 | Residencial | 7.68 | Out of period | 2025-09-22 09:49 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 191
202509-NM25-04576 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 17:48 | January | 2026 | 2026-01-16 14:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 81
202509-NM25-04607 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:31 | March | 2026 | 2026-03-16 17:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 22
202509-NM25-04612 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:07 | February | 2026 | 2026-03-03 16:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 32
202509-NM25-04613 | GDL17 | Residencial | 9 | Period | 2026-03-25 12:14 | March | 2026 | 2026-04-02 13:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | April |  | 8 | 4 | 2026-04-01 | 6
202509-NM25-04629 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 13:10 | March | 2026 | 2026-03-11 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 25
202509-NM25-04631 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:43 | February | 2026 | 2026-02-20 08:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202509-NM25-04632 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-22 11:31 | September | 2025 | 2026-01-29 17:45 | 129 | Study | Estudio (E) | Activated | Backlog |  | No | 129 |  | MAYAGUEZ | January |  | 129 | 0 | 2026-04-01 | 191
202509-NM25-04636 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-05 11:25 | November | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 147
202509-NM25-04640 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 07:54 | February | 2026 | 2026-02-18 10:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 47
202509-NM25-04644 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:01 | February | 2026 | 2026-02-19 10:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 43
202509-NM25-04655 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:10 | February | 2026 | 2026-02-25 16:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202509-NM25-04672 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 16:54 | February | 2026 | 2026-02-10 13:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 56
202509-NM25-04684 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-22 13:16 | September | 2025 | 2026-01-16 10:12 | 116 | Study | Estudio (E) | Activated | Backlog |  | No | 116 |  | CAGUAS | January |  | 116 | 0 | 2026-04-01 | 190
202509-NM25-04690 | GDL17 | Residencial | 9 | Period | 2026-01-15 13:25 | January | 2026 | 2026-01-21 15:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 75
202509-NM25-04727 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:05 | February | 2026 | 2026-02-04 13:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-04731 | GDL17 | Residencial | 15.2 | Out of period | 2025-09-29 11:35 | September | 2025 | 2026-03-10 11:18 | 162 | Study | Estudio (E) | Activated | Backlog |  | No | 162 |  | CAGUAS | March |  | 162 | 0 | 2026-04-01 | 184
202509-NM25-04734 | GDL17 | Residencial | 4.714 | Out of period | 2025-09-22 15:55 | September | 2025 | 2026-01-27 11:19 | 127 | Study | Estudio (E) | Activated | Backlog |  | No | 127 |  | MAYAGUEZ | January |  | 127 | 0 | 2026-04-01 | 190
202509-NM25-04742 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 18:37 | January | 2026 | 2026-02-04 15:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 61
202509-NM25-04743 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 00:03 | February | 2026 | 2026-02-23 09:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-04745 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:09 | February | 2026 | 2026-02-13 09:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202509-NM25-04791 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-24 08:26 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 197 | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 189
202509-NM25-04803 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-23 09:09 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 190
202509-NM25-04809 | GDL17 | Residencial | 0.768 | Out of period | 2025-10-18 12:33 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 164
202509-NM25-04827 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 11:21 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 149
202509-NM25-04845 | GDL17 | Residencial | 23 | Period | 2026-02-02 18:00 | February | 2026 | 2026-02-04 16:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-04869 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-23 12:08 | September | 2025 | 2026-01-28 07:54 | 127 | Study | Estudio (E) | Activated | Backlog |  | No | 127 |  | ARECIBO | January |  | 127 | 0 | 2026-04-01 | 189
202509-NM25-04878 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:17 | January | 2026 | 2026-02-02 13:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202509-NM25-04885 | GDL17 | Residencial | 23 | Out of period | 2025-09-23 14:21 | September | 2025 | 2026-01-08 12:46 | 107 | Study | Estudio (E) | Activated | Backlog |  | No | 107 |  | MAYAGUEZ | January |  | 107 | 0 | 2026-04-01 | 189
202509-NM25-04904 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:01 | February | 2026 | 2026-02-23 09:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202509-NM25-04921 | GDL17 | Residencial | 8 | Out of period | 2025-10-01 08:17 | October | 2025 | 2026-03-13 15:05 | 163 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 4 | 159 | 2026-04-01 | 182
202509-NM25-04926 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-27 15:38 | November | 2025 | 2026-01-05 11:20 | 39 | Study | Estudio (E) | Activated | Backlog |  | No | 39 |  | MAYAGUEZ | January |  | 39 | 0 | 2026-04-01 | 124
202509-NM25-04946 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 14:47 | March | 2026 | 2026-04-02 15:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 5
202509-NM25-04953 | GDL17 | Residencial | 23 | Out of period | 2025-11-10 18:57 | November | 2025 | 2026-01-08 08:13 | 59 | Study | Estudio (E) | Activated | Backlog |  | No | 59 |  | MAYAGUEZ | January |  | 58 | 0 | 2026-04-01 | 141
202509-NM25-04960 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-31 10:10 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 152
202509-NM25-04961 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 12:38 | January | 2026 | 2026-02-04 12:59 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 64
202509-NM25-04968 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 16:08 | January | 2026 | 2026-01-13 15:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202509-NM25-05028 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:26 | February | 2026 | 2026-03-03 13:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202509-NM25-05031 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:24 | February | 2026 | 2026-02-25 10:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 42
202509-NM25-05033 | GDL17 | Residencial | 3.8 | Period | 2026-02-13 08:18 | February | 2026 | 2026-02-23 14:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 47
202509-NM25-05038 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:44 | March | 2026 | 2026-03-04 14:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202509-NM25-05041 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:00 | February | 2026 | 2026-02-16 15:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 47
202509-NM25-05048 | GDL17 | Residencial | 15.36 | Period | 2026-01-06 12:14 | January | 2026 | 2026-01-12 13:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 84
202509-NM25-05061 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:40 | February | 2026 | 2026-02-24 07:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202509-NM25-05068 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-25 19:00 | September | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 187
202509-NM25-05077 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 16:51 | November | 2025 | 2026-01-14 12:37 | 65 | Study | Estudio (E) | Activated | Backlog |  | No | 65 |  | SAN JUAN | January |  | 65 | 0 | 2026-04-01 | 141
202509-NM25-05081 | GDL17 | Residencial | 9 | Out of period | 2025-09-29 08:54 | September | 2025 | 2026-01-15 13:42 | 108 | Study | Estudio (E) | Activated | Backlog |  | No | 108 |  | SAN JUAN | January |  | 108 | 0 | 2026-04-01 | 184
202509-NM25-05094 | GDL17 | Residencial | 8 | Out of period | 2025-10-03 16:23 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 179
202509-NM25-05101 | GDL17 | Residencial | 11.5 | Period | 2026-02-22 20:07 | February | 2026 | 2026-03-06 10:04 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 37
202509-NM25-05103 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-05 20:20 | November | 2025 | 2026-01-05 08:09 | 60 | Study | Estudio (E) | Activated | Backlog |  | No | 60 |  | MAYAGUEZ | January |  | 61 | 0 | 2026-04-01 | 146
202509-NM25-05122 | GDL17 | Residencial | 5.76 | Period | 2026-01-30 09:27 | January | 2026 | 2026-02-04 13:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 61
202509-NM25-05131 | GDL17 | Residencial | 9.216 | Out of period | 2025-09-24 15:25 | September | 2025 | 2026-02-19 15:38 | 148 | Study | Estudio (E) | Activated | Backlog |  | No | 148 |  | BAYAMON | February |  | 148 | 0 | 2026-04-01 | 188
202509-NM25-05158 | GDL17 | Residencial | 23 | Period | 2026-03-31 14:20 | March | 2026 | 2026-04-07 13:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 0
202509-NM25-05160 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 19:54 | February | 2026 | 2026-02-26 13:56 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 41
202509-NM25-05171 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-18 11:45 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 134
202509-NM25-05172 | GDL17 | Residencial | 3.8 | Out of period | 2025-10-20 15:06 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 162
202509-NM25-05177 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 08:08 | March | 2026 | 2026-04-02 12:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 1
202509-NM25-05181 | GDL17 | Comercial | 20.496 | Out of period | 2025-10-07 13:58 | October | 2025 | 2026-01-22 16:00 | 107 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 2 | 14 | 93 | 2026-04-01 | 175
202509-NM25-05219 | GDL17 | Residencial | 10.368 | Period | 2026-02-12 15:12 | February | 2026 | 2026-02-13 15:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 47
202509-NM25-05220 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:31 | February | 2026 | 2026-02-25 07:52 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 43
202509-NM25-05230 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-28 10:28 | October | 2025 | 2026-01-20 10:20 | 84 | Study | Estudio (E) | Activated | Backlog |  | No | 84 |  | SAN JUAN | January |  | 84 | 0 | 2026-04-01 | 155
202509-NM25-05256 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:45 | January | 2026 | 2026-01-14 11:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202509-NM25-05260 | GDL17 | Residencial | 6.144 | Out of period | 2025-09-25 09:16 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 188
202509-NM25-05266 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 12:50 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 1
202509-NM25-05277 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-03 16:06 | October | 2025 | 2026-01-29 13:07 | 118 | Study | Estudio (E) | Activated | Backlog |  | No | 118 |  | SAN JUAN | January |  | 118 | 0 | 2026-04-01 | 179
202509-NM25-05295 | GDL17 | Comercial | 10 | Out of period | 2025-09-25 15:40 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 187
202509-NM25-05302 | GDL17 | Residencial | 23 | Period | 2026-02-24 14:46 | February | 2026 | 2026-03-18 12:39 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 22 | 0 | 2026-04-01 | 35
202509-NM25-05318 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:32 | January | 2026 | 2026-02-03 16:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 60
202509-NM25-05345 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:02 | February | 2026 | 2026-03-03 08:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 34
202509-NM25-05358 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-31 09:20 | October | 2025 | 2026-01-14 14:53 | 75 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 1 | 9 | 66 | 2026-04-01 | 152
202509-NM25-05360 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 11:36 | March | 2026 | 2026-04-01 08:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 6 | 0 | 2026-04-01 | 6
202509-NM25-05364 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 09:04 | March | 2026 | 2026-03-09 15:31 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 23
202509-NM25-05404 | GDL17 | Residencial | 17.28 | Period | 2026-03-06 15:40 | March | 2026 | 2026-03-13 08:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 25
202509-NM25-05424 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:01 | February | 2026 | 2026-02-06 11:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 57
202509-NM25-05455 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:59 | January | 2026 | 2026-01-09 15:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 89
202509-NM25-05460 | GDL17 | Residencial | 14.976 | Period | 2026-02-02 13:29 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 57
202509-NM25-05462 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:57 | February | 2026 | 2026-02-16 15:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 47
202509-NM25-05463 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 18:56 | February | 2026 | 2026-02-25 08:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202509-NM25-05465 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 20:07 | February | 2026 | 2026-02-27 09:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 36
202509-NM25-05467 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 17:56 | January | 2026 | 2026-01-09 08:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 84
202509-NM25-05468 | GDL17 | Residencial | 23 | Period | 2026-02-02 15:58 | February | 2026 | 2026-02-04 16:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-05470 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:19 | February | 2026 | 2026-03-04 09:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 33
202509-NM25-05491 | GDL17 | Residencial | 12.078 | Out of period | 2025-12-08 16:50 | December | 2025 | 2026-02-10 15:59 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | SAN JUAN | February |  | 64 | 0 | 2026-04-01 | 113
202509-NM25-05505 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:31 | March | 2026 | 2026-03-12 08:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 21
202509-NM25-05512 | GDL17 | Residencial | 15.3 | Period | 2026-02-19 20:37 | February | 2026 | 2026-02-25 08:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202509-NM25-05517 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:50 | January | 2026 | 2026-02-06 15:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 60
202509-NM25-05530 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:15 | March | 2026 | 2026-03-30 13:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 6
202509-NM25-05533 | GDL17 | Residencial | 23 | Period | 2026-02-25 12:03 | February | 2026 | 2026-03-06 10:38 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 34
202509-NM25-05550 | GDL17 | Residencial | 5.76 | Out of period | 2025-09-30 09:22 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 183
202509-NM25-05577 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 11:04 | March | 2026 | 2026-03-09 10:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 27
202509-NM25-05591 | GDL17 | Residencial | 7.6 | Out of period | 2025-09-26 15:24 | September | 2025 | 2026-02-13 14:50 | 140 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 2 | 6 | 134 | 2026-04-01 | 186
202509-NM25-05600 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 19:26 | January | 2026 | 2026-01-26 16:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 69
202509-NM25-05611 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 18:03 | January | 2026 | 2026-01-14 10:34 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 85
202509-NM25-05613 | GDL17 | Residencial | 7.68 | Out of period | 2025-10-25 09:50 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 163 | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 158
202509-NM25-05627 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:33 | March | 2026 | 2026-03-09 08:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 27
202509-NM25-05632 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:59 | February | 2026 | 2026-02-24 13:37 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 48
202509-NM25-05667 | GDL17 | Residencial | 11.5 | Out of period | 2025-09-26 16:44 | September | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 186
202509-NM25-05678 | GDL17 | Residencial | 17.5 | Period | 2026-02-25 14:48 | February | 2026 | 2026-03-02 09:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202509-NM25-05679 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 14:23 | March | 2026 | 2026-03-18 10:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 19
202509-NM25-05685 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 18:16 | February | 2026 | 2026-03-02 08:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 36
202509-NM25-05689 | GDL17 | Residencial | 16 | Period | 2026-02-10 11:54 | February | 2026 | 2026-02-13 10:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 50
202509-NM25-05707 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-28 08:44 | October | 2025 | 2026-01-28 09:54 | 92 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 49 | 43 | 2026-04-01 | 155
202509-NM25-05717 | GDL17 | Residencial | 5.76 | Out of period | 2025-10-16 16:16 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 166
202509-NM25-05733 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 15:05 | March | 2026 | 2026-03-18 13:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 15
202509-NM25-05743 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 15:41 | January | 2026 | 2026-02-25 13:07 | 51 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | February |  | 51 | 0 | 2026-04-01 | 85
202509-NM25-05756 | GDL17 | Residencial | 12 | Out of period | 2025-10-02 15:35 | October | 2025 | 2026-01-07 07:43 | 97 | Study | Estudio (E) | Activated | Backlog |  | No | 97 |  | MAYAGUEZ | January |  | 97 | 0 | 2026-04-01 | 180
202509-NM25-05785 | GDL17 | Residencial | 11.5 | Period | 2026-02-28 09:44 | February | 2026 | 2026-03-12 10:20 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 32
202509-NM25-05786 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:43 | February | 2026 | 2026-02-05 16:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202509-NM25-05799 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 12:44 | January | 2026 | 2026-01-27 15:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 64
202509-NM25-05825 | GDL17 | Residencial | 12 | Out of period | 2025-10-03 09:17 | October | 2025 | 2026-01-12 08:20 | 101 | Study | Estudio (E) | Activated | Backlog |  | No | 101 |  | MAYAGUEZ | January |  | 101 | 0 | 2026-04-01 | 180
202509-NM25-05867 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-20 07:24 | October | 2025 | 2026-01-12 14:37 | 84 | Study | Estudio (E) | Activated | Backlog |  | No | 84 |  | MAYAGUEZ | January |  | 84 | 0 | 2026-04-01 | 163
202509-NM25-05876 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 19:53 | February | 2026 | 2026-03-09 14:57 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 35
202509-NM25-05878 | GDL17 | Residencial | 3.8 | Period | 2026-02-21 20:59 | February | 2026 | 2026-03-03 13:16 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 10 | 0 | 2026-04-01 | 38
202509-NM25-05884 | GDL17 | Residencial | 4.608 | Period | 2026-01-07 14:58 | January | 2026 | 2026-01-13 11:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 83
202509-NM25-05892 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:14 | February | 2026 | 2026-02-27 09:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 36
202509-NM25-05896 | GDL17 | Residencial | 17.2 | Period | 2026-03-06 09:30 | March | 2026 | 2026-03-06 16:26 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 0 | 0 | 2026-04-01 | 26
202509-NM25-05899 | GDL17 | Residencial | 15.3 | Period | 2026-02-19 10:18 | February | 2026 | 2026-02-27 13:12 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 41
202509-NM25-05901 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 12:10 | February | 2026 | 2026-03-03 12:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 33
202509-NM25-05902 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:37 | February | 2026 | 2026-02-16 10:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 48
202509-NM25-05913 | GDL17 | Residencial | 7.296 | Out of period | 2025-09-30 08:06 | September | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 199 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 183
202509-NM25-05925 | GDL17 | Residencial | 5.376 | Period | 2026-01-08 10:10 | January | 2026 | 2026-01-28 13:32 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 20 | 0 | 2026-04-01 | 83
202509-NM25-05927 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-03 10:05 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 180
202509-NM25-05959 | GDL17 | Residencial | 0.768 | Out of period | 2025-10-18 09:04 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 165
202509-NM25-05982 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:25 | March | 2026 | 2026-03-25 12:50 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 6 | 2 | 2026-04-01 | 15
202509-NM25-05991 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:51 | February | 2026 | 2026-02-25 08:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202509-NM25-05999 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:27 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 29
202509-NM25-06014 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:13 | March | 2026 | 2026-04-13 08:15 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 14 | 0 | 2026-04-01 | 2
202509-NM25-06027 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:42 | February | 2026 | 2026-02-20 08:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 43
202509-NM25-06032 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 09:10 | March | 2026 | 2026-03-30 10:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 7
202509-NM25-06036 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 10:51 | February | 2026 | 2026-02-19 10:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202509-NM25-06038 | GDL17 | Residencial | 17.5 | Period | 2026-02-16 12:07 | February | 2026 | 2026-02-20 08:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 3 | 1 | 2026-04-01 | 43
202509-NM25-06043 | GDL17 | Residencial | 11.5 | Period | 2026-02-22 15:47 | February | 2026 | 2026-02-26 15:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 37
202509-NM25-06044 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:22 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 63
202509-NM25-06058 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:13 | February | 2026 | 2026-02-26 16:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202509-NM25-06061 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-17 12:24 | October | 2025 | 2026-01-19 16:00 | 94 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January |  | 94 | 1 | 2026-04-01 | 165
202510-NM25-00006 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-01 08:11 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 195 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 182
202510-NM25-00008 | GDL17 | Residencial | 3.8 | Period | 2026-01-19 13:58 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 71
202510-NM25-00010 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-01 08:44 | October | 2025 | 2026-01-05 14:21 | 96 | Study | Estudio (E) | Activated | Backlog |  | No | 96 |  | MAYAGUEZ | January |  | 96 | 0 | 2026-04-01 | 182
202510-NM25-00034 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 17:24 | March | 2026 | 2026-03-13 13:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 25
202510-NM25-00035 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:42 | January | 2026 | 2026-01-30 13:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 63
202510-NM25-00053 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 10:38 | March | 2026 | 2026-04-10 16:22 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 11 | 0 | 2026-04-01 | 2
202510-NM25-00065 | GDL17 | Residencial | 0.768 | Out of period | 2025-10-18 08:37 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 165
202510-NM25-00068 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:58 | January | 2026 | 2026-01-29 10:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 64
202510-NM25-00069 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:08 | March | 2026 | 2026-03-10 14:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 22
202510-NM25-00071 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:30 | February | 2026 | 2026-02-18 11:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 44
202510-NM25-00074 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 14:50 | February | 2026 | 2026-02-16 10:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 47
202510-NM25-00075 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 21:12 | February | 2026 | 2026-02-25 15:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 41
202510-NM25-00080 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:10 | February | 2026 | 2026-02-25 08:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-00085 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 19:55 | February | 2026 | 2026-03-02 08:51 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 40
202510-NM25-00087 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:14 | February | 2026 | 2026-03-03 09:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202510-NM25-00088 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:10 | February | 2026 | 2026-02-20 08:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202510-NM25-00113 | GDL17 | Residencial | 23 | Period | 2026-02-18 13:06 | February | 2026 | 2026-02-23 14:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202510-NM25-00125 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-27 14:31 | October | 2025 | 2026-01-19 10:25 | 84 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 1 | 56 | 28 | 2026-04-01 | 155
202510-NM25-00128 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:03 | February | 2026 | 2026-02-26 08:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202510-NM25-00133 | GDL17 | Residencial | 3.84 | Out of period | 2025-10-22 06:36 | October | 2025 | 2026-01-08 10:14 | 78 | Study | Estudio (E) | Activated | Backlog |  | No | 78 |  | BAYAMON | January |  | 78 | 0 | 2026-04-01 | 161
202510-NM25-00135 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:39 | October | 2025 | 2026-02-16 10:25 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 65 | 54 | 2026-04-01 | 162
202510-NM25-00137 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:31 | March | 2026 | 2026-03-16 09:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 20
202510-NM25-00147 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:42 | February | 2026 | 2026-03-03 16:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 35
202510-NM25-00148 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 13:09 | March | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1
202510-NM25-00149 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-13 14:17 | November | 2025 |  |  | Cancelled | Cancelled | Cancelled | Cancelled |  | No |  |  | PONCE |  |  |  |  | 2026-04-01 | 138
202510-NM25-00151 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 10:24 | March | 2026 | 2026-03-18 17:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 16
202510-NM25-00155 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:48 | January | 2026 | 2026-01-30 09:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 63
202510-NM25-00158 | GDL17 | Residencial | 7.6 | Period | 2026-03-25 10:29 | March | 2026 | 2026-04-10 15:53 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 16 | 0 | 2026-04-01 | 7
202510-NM25-00171 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 16:41 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 1
202510-NM25-00201 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 21:21 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 41
202510-NM25-00202 | GDL17 | Residencial | 15.3 | Period | 2026-02-20 16:33 | February | 2026 | 2026-02-26 08:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202510-NM25-00204 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:48 | February | 2026 | 2026-02-23 14:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202510-NM25-00205 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:10 | February | 2026 | 2026-02-23 09:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-00206 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 19:52 | February | 2026 | 2026-02-18 09:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 46
202510-NM25-00208 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:53 | March | 2026 | 2026-03-23 10:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 15
202510-NM25-00215 | GDL17 | Residencial | 5.376 | Out of period | 2025-10-02 14:26 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 180
202510-NM25-00257 | GDL17 | Comercial | 9 | Period | 2026-02-04 12:36 | February | 2026 | 2026-03-09 16:11 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 33 | 0 | 2026-04-01 | 55
202510-NM25-00282 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 09:35 | March | 2026 | 2026-03-06 11:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 27
202510-NM25-00297 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-24 11:45 | October | 2025 | 2026-01-26 14:39 | 94 | Study | Estudio (E) | Activated | Backlog |  | No | 94 |  | MAYAGUEZ | January |  | 94 | 0 | 2026-04-01 | 159
202510-NM25-00300 | GDL17 | Residencial | 6.144 | Period | 2026-03-17 08:05 | March | 2026 | 2026-03-18 15:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202510-NM25-00302 | GDL17 | Residencial | 8 | Out of period | 2025-10-08 08:11 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 175
202510-NM25-00305 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-02 13:27 | October | 2025 | 2026-03-03 15:00 | 152 | Study | Estudio (E) | Activated | Backlog |  | No | 152 |  | BAYAMON | March |  | 152 | 0 | 2026-04-01 | 180
202510-NM25-00306 | GDL17 | Residencial | 5.76 | Out of period | 2025-11-01 19:31 | November | 2025 | 2026-02-11 09:03 | 102 | Study | Estudio (E) | Activated | Backlog |  | No | 102 |  | CAGUAS | February |  | 102 | 0 | 2026-04-01 | 150
202510-NM25-00307 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 18:51 | February | 2026 | 2026-02-18 10:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 46
202510-NM25-00321 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 10:05 | January | 2026 | 2026-02-25 07:55 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 42 | 0 | 2026-04-01 | 77
202510-NM25-00337 | GDL17 | Residencial | 10.752 | Out of period | 2025-10-21 15:40 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 161
202510-NM25-00339 | GDL17 | Residencial | 7.6 | Period | 2026-02-17 09:19 | February | 2026 | 2026-02-25 14:40 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 43
202510-NM25-00346 | GDL17 | Residencial | 24.61 | Out of period | 2025-11-07 15:55 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 144
202510-NM25-00367 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:06 | January | 2026 | 2026-01-12 12:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202510-NM25-00372 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:49 | January | 2026 | 2026-01-22 14:13 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 15 | 0 | 2026-04-01 | 84
202510-NM25-00388 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:30 | February | 2026 | 2026-02-25 08:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202510-NM25-00397 | GDL17 | Residencial | 6.954 | Out of period | 2025-12-31 08:04 | December | 2025 | 2026-01-15 08:29 | 15 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 15 | 0 | 2026-04-01 | 91
202510-NM25-00414 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-17 13:49 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 165
202510-NM25-00425 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-08 12:21 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 174
202510-NM25-00434 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:11 | February | 2026 | 2026-02-19 14:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202510-NM25-00437 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 06:57 | February | 2026 | 2026-02-13 13:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 48
202510-NM25-00449 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:36 | February | 2026 | 2026-02-23 09:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-00450 | GDL17 | Residencial | 17.2 | Period | 2026-02-12 12:30 | February | 2026 | 2026-02-13 16:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 47
202510-NM25-00468 | GDL17 | Residencial | 3.84 | Period | 2026-02-26 10:10 | February | 2026 | 2026-03-03 13:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202510-NM25-00479 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 14:15 | February | 2026 | 2026-03-03 09:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202510-NM25-00480 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:28 | February | 2026 | 2026-02-25 09:41 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 43
202510-NM25-00501 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-03 16:25 | October | 2025 | 2026-01-13 13:52 | 102 | Study | Estudio (E) | Activated | Backlog |  | No | 102 |  | MAYAGUEZ | January |  | 102 | 0 | 2026-04-01 | 179
202510-NM25-00536 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-07 08:10 | October | 2025 | 2026-01-23 15:56 | 108 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 46 | 62 | 2026-04-01 | 176
202510-NM25-00549 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:04 | February | 2026 | 2026-02-25 08:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-00555 | GDL17 | Residencial | 3.84 | Out of period | 2025-10-31 13:47 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 151
202510-NM25-00584 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:32 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 44
202510-NM25-00636 | GDL17 | Residencial | 12.288 | Out of period | 2025-10-20 11:05 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 163
202510-NM25-00648 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-03 08:34 | November | 2025 | 2026-03-10 09:36 | 127 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March |  | 127 | 65 | 2026-04-01 | 149
202510-NM25-00691 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 07:45 | February | 2026 | 2026-02-18 10:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 44
202510-NM25-00710 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:33 | February | 2026 | 2026-03-03 16:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202510-NM25-00725 | GDL17 | Residencial | 7.68 | Out of period | 2025-11-05 09:58 | November | 2025 | 2026-03-26 15:58 | 141 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | March | 1 | 135 | 6 | 2026-04-01 | 147
202510-NM25-00736 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:48 | February | 2026 | 2026-02-16 14:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202510-NM25-00747 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:25 | February | 2026 | 2026-02-24 14:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-00759 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 17:28 | February | 2026 | 2026-02-23 16:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-00780 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:10 | February | 2026 | 2026-02-19 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 43
202510-NM25-00790 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:21 | February | 2026 | 2026-02-13 16:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 47
202510-NM25-00796 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-06 17:13 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 176
202510-NM25-00800 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 18:41 | February | 2026 | 2026-02-26 12:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202510-NM25-00804 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:47 | February | 2026 | 2026-02-27 09:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202510-NM25-00805 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:21 | February | 2026 | 2026-02-25 11:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-00806 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:41 | February | 2026 | 2026-02-25 07:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-00813 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 21:07 | February | 2026 | 2026-02-26 07:42 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 41
202510-NM25-00814 | GDL17 | Residencial | 11.5 | Period | 2026-02-28 16:19 | February | 2026 | 2026-03-05 11:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 31
202510-NM25-00815 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-23 09:32 | October | 2025 | 2026-01-14 12:43 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 38 | 45 | 2026-04-01 | 160
202510-NM25-00816 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-23 09:34 | October | 2025 | 2026-01-14 13:33 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 38 | 45 | 2026-04-01 | 160
202510-NM25-00817 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-23 09:36 | October | 2025 | 2026-01-14 12:39 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 38 | 45 | 2026-04-01 | 160
202510-NM25-00818 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:55 | March | 2026 | 2026-03-09 10:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 26
202510-NM25-00819 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-23 09:38 | October | 2025 | 2026-01-14 12:33 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 38 | 45 | 2026-04-01 | 160
202510-NM25-00820 | GDL17 | Comercial | 5.3 | Out of period | 2025-11-10 08:58 | November | 2025 | 2026-01-14 11:27 | 65 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 27 | 38 | 2026-04-01 | 142
202510-NM25-00821 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-23 09:40 | October | 2025 | 2026-01-14 12:51 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 38 | 45 | 2026-04-01 | 160
202510-NM25-00823 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:51 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 162
202510-NM25-00824 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:52 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 162
202510-NM25-00826 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:53 | October | 2025 | 2026-02-16 11:11 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 65 | 54 | 2026-04-01 | 162
202510-NM25-00827 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:55 | October | 2025 | 2026-02-16 12:45 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 65 | 54 | 2026-04-01 | 162
202510-NM25-00829 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 12:56 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 162
202510-NM25-00830 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 13:01 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 162
202510-NM25-00833 | GDL17 | Comercial | 5.3 | Period | 2026-01-20 09:13 | January | 2026 | 2026-03-18 08:37 | 57 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 31 | 26 | 2026-04-01 | 71
202510-NM25-00834 | GDL17 | Comercial | 5.3 | Out of period | 2025-12-29 13:33 | December | 2025 | 2026-02-04 17:41 | 37 | Study | Estudio (E) | Activated | Backlog |  | No | 37 |  | PONCE | February |  | 37 | 0 | 2026-04-01 | 92
202510-NM25-00835 | GDL17 | Comercial | 5.3 | Out of period | 2025-12-29 13:35 | December | 2025 | 2026-02-04 17:47 | 37 | Study | Estudio (E) | Activated | Backlog |  | No | 37 |  | PONCE | February |  | 37 | 0 | 2026-04-01 | 92
202510-NM25-00836 | GDL17 | Comercial | 5.3 | Out of period | 2025-12-29 13:36 | December | 2025 | 2026-02-04 17:53 | 37 | Study | Estudio (E) | Activated | Backlog |  | No | 37 |  | PONCE | February |  | 37 | 0 | 2026-04-01 | 92
202510-NM25-00837 | GDL17 | Comercial | 5.3 | Period | 2026-03-13 09:12 | March | 2026 | 2026-04-14 12:43 | 32 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 32 | 15 | 2026-04-01 | 19
202510-NM25-00839 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-23 09:41 | October | 2025 | 2026-03-18 08:01 | 146 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March | 2 | 27 | 119 | 2026-04-01 | 160
202510-NM25-00862 | GDL17 | Residencial | 18 | Out of period | 2025-10-07 21:53 | October | 2025 | 2026-01-13 08:44 | 97 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 48 | 50 | 2026-04-01 | 175
202510-NM25-00863 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:27 | January | 2026 | 2026-02-03 08:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 62
202510-NM25-00865 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 07:48 | March | 2026 | 2026-03-23 10:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 13
202510-NM25-00872 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-14 09:45 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 138
202510-NM25-00875 | GDL17 | Residencial | 7.68 | Period | 2026-03-19 10:13 | March | 2026 | 2026-03-26 09:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 13
202510-NM25-00918 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 16:21 | February | 2026 | 2026-02-17 08:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 47
202510-NM25-00944 | GDL17 | Residencial | 18 | Out of period | 2025-10-07 21:08 | October | 2025 | 2026-01-19 15:33 | 104 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 54 | 50 | 2026-04-01 | 175
202510-NM25-00945 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:53 | January | 2026 | 2026-02-04 08:53 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 64
202510-NM25-00950 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-07 10:43 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 176
202510-NM25-00957 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-22 16:14 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 160
202510-NM25-00960 | GDL17 | Residencial | 3.84 | Out of period | 2025-10-17 12:52 | October | 2025 | 2026-02-11 16:07 | 117 | Study | Estudio (E) | Activated | Backlog |  | No | 117 |  | ARECIBO | February |  | 117 | 0 | 2026-04-01 | 165
202510-NM25-00972 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:53 | February | 2026 | 2026-02-23 14:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202510-NM25-00980 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 09:07 | March | 2026 | 2026-03-13 09:44 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 27
202510-NM25-00988 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-18 15:14 | November | 2025 | 2026-01-07 15:39 | 50 | Study | Estudio (E) | Activated | Backlog |  | No | 50 |  | MAYAGUEZ | January |  | 50 | 0 | 2026-04-01 | 133
202510-NM25-00992 | GDL17 | Comercial | 8 | Out of period | 2025-12-29 11:15 | December | 2025 |  |  | NM Enter Technical Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 93
202510-NM25-00993 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:44 | February | 2026 | 2026-02-27 09:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202510-NM25-00995 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:49 | March | 2026 | 2026-03-16 13:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 22
202510-NM25-01015 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-07 13:25 | October | 2025 | 2026-03-31 15:23 | 175 | Study | Estudio (E) | Activated | Backlog |  | No | 175 |  | BAYAMON | March |  | 175 | 0 | 2026-04-01 | 175
202510-NM25-01028 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-07 14:00 | October | 2025 | 2026-01-29 13:36 | 114 | Study | Estudio (E) | Activated | Backlog |  | No | 114 |  | MAYAGUEZ | January |  | 114 | 0 | 2026-04-01 | 175
202510-NM25-01036 | GDL17 | Residencial | 15.5 | Out of period | 2025-10-07 14:39 | October | 2025 | 2026-01-16 11:10 | 101 | Study | Estudio (E) | Activated | Backlog |  | No | 101 |  | MAYAGUEZ | January |  | 101 | 0 | 2026-04-01 | 175
202510-NM25-01048 | GDL17 | Residencial | 15 | Period | 2026-03-30 16:16 | March | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1
202510-NM25-01074 | GDL17 | Residencial | 6.144 | Out of period | 2025-11-13 18:06 | November | 2025 | 2026-03-03 15:16 | 110 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | March | 1 | 7 | 103 | 2026-04-01 | 138
202510-NM25-01086 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-07 17:30 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 175
202510-NM25-01088 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-27 12:25 | October | 2025 | 2026-02-17 13:59 | 113 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February |  | 113 | 13 | 2026-04-01 | 155
202510-NM25-01117 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 13:52 | January | 2026 | 2026-03-17 10:25 | 62 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 36 | 26 | 2026-04-01 | 76
202510-NM25-01119 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 13:53 | January | 2026 | 2026-03-17 10:38 | 62 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 36 | 26 | 2026-04-01 | 76
202510-NM25-01120 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 13:54 | January | 2026 | 2026-03-17 10:42 | 62 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 36 | 26 | 2026-04-01 | 76
202510-NM25-01122 | GDL17 | Comercial | 5.3 | Out of period | 2025-12-29 09:17 | December | 2025 | 2026-02-04 17:25 | 37 | Study | Estudio (E) | Activated | Backlog |  | No | 37 |  | PONCE | February |  | 37 | 0 | 2026-04-01 | 93
202510-NM25-01123 | GDL17 | Comercial | 21.8 | Out of period | 2025-12-29 09:18 | December | 2025 | 2026-02-04 17:30 | 37 | Study | Estudio (E) | Activated | Backlog |  | No | 37 |  | PONCE | February |  | 37 | 0 | 2026-04-01 | 93
202510-NM25-01125 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-23 09:44 | October | 2025 | 2026-01-14 13:21 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 38 | 45 | 2026-04-01 | 160
202510-NM25-01127 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-23 09:46 | October | 2025 | 2026-01-14 12:47 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 38 | 45 | 2026-04-01 | 160
202510-NM25-01129 | GDL17 | Comercial | 5.3 | Period | 2026-03-13 09:27 | March | 2026 | 2026-04-14 12:35 | 32 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 32 | 15 | 2026-04-01 | 19
202510-NM25-01131 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 13:13 | October | 2025 | 2026-01-22 14:10 | 94 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 34 | 60 | 2026-04-01 | 162
202510-NM25-01132 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 13:15 | October | 2025 | 2026-02-16 12:49 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 65 | 54 | 2026-04-01 | 162
202510-NM25-01133 | GDL17 | Comercial | 5.3 | Period | 2026-01-20 09:17 | January | 2026 | 2026-03-18 08:50 | 57 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 31 | 26 | 2026-04-01 | 71
202510-NM25-01136 | GDL17 | Comercial | 5.3 | Period | 2026-03-11 09:13 | March | 2026 | 2026-04-13 15:54 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 33 | 22 | 2026-04-01 | 21
202510-NM25-01153 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 17:39 | February | 2026 | 2026-02-25 10:51 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 43
202510-NM25-01159 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-28 09:05 | October | 2025 | 2026-03-20 09:32 | 143 | Study | Estudio (E) | Activated | Backlog |  | No | 143 |  | CAGUAS | March |  | 143 | 0 | 2026-04-01 | 155
202510-NM25-01168 | GDL17 | Residencial | 11.4 | Out of period | 2025-11-19 09:57 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 133
202510-NM25-01176 | GDL17 | Residencial | 11.5 | Period | 2026-02-28 09:45 | February | 2026 | 2026-03-04 09:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 32
202510-NM25-01182 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 17:26 | February | 2026 | 2026-02-25 08:53 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 43
202510-NM25-01183 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:08 | February | 2026 | 2026-03-03 07:57 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 41
202510-NM25-01189 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-16 10:23 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 106
202510-NM25-01192 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-08 09:53 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 175
202510-NM25-01202 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:56 | February | 2026 | 2026-02-19 10:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 46
202510-NM25-01203 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 21:55 | February | 2026 | 2026-02-25 15:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-01209 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:23 | January | 2026 | 2026-01-14 15:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 84
202510-NM25-01220 | GDL17 | Residencial | 12.288 | Period | 2026-02-06 08:01 | February | 2026 | 2026-02-10 14:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202510-NM25-01258 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:43 | February | 2026 | 2026-02-12 10:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202510-NM25-01262 | GDL17 | Residencial | 11.4 | Period | 2026-03-04 17:11 | March | 2026 | 2026-03-06 14:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 27
202510-NM25-01263 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 11:18 | January | 2026 | 2026-01-29 13:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202510-NM25-01267 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 22:51 | February | 2026 | 2026-02-24 09:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202510-NM25-01274 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-08 13:04 | October | 2025 | 2026-03-09 09:21 | 152 | Study | Estudio (E) | Activated | Backlog |  | No | 152 |  | BAYAMON | March |  | 152 | 0 | 2026-04-01 | 174
202510-NM25-01289 | GDL17 | Residencial | 7.6 | Period | 2026-02-10 11:06 | February | 2026 | 2026-02-17 08:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 50
202510-NM25-01312 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:00 | January | 2026 | 2026-01-29 10:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202510-NM25-01330 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:40 | January | 2026 | 2026-01-12 11:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 84
202510-NM25-01336 | GDL17 | Residencial | 8 | Out of period | 2025-10-08 16:27 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 174
202510-NM25-01354 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 17:06 | February | 2026 | 2026-02-23 09:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-01359 | GDL17 | Comercial | 5.3 | Out of period | 2025-10-20 13:17 | October | 2025 | 2026-02-16 12:56 | 119 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 65 | 54 | 2026-04-01 | 162
202510-NM25-01361 | GDL17 | Comercial | 15 | Out of period | 2025-10-08 22:03 | October | 2025 |  |  | NM Enter Technical Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 174
202510-NM25-01392 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 12:31 | January | 2026 | 2026-01-30 11:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 64
202510-NM25-01396 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:12 | January | 2026 | 2026-02-02 15:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202510-NM25-01398 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 12:38 | March | 2026 | 2026-03-09 15:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 25
202510-NM25-01413 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:48 | February | 2026 | 2026-02-05 12:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202510-NM25-01416 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 07:55 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 47
202510-NM25-01419 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:05 | January | 2026 | 2026-01-08 13:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 88
202510-NM25-01423 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-01 10:07 | November | 2025 | 2026-02-24 14:25 | 115 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 110 | 0 | 2026-04-01 | 151
202510-NM25-01424 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:32 | February | 2026 | 2026-02-10 13:04 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 57
202510-NM25-01435 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:55 | February | 2026 | 2026-02-24 07:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-01437 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 12:51 | January | 2026 | 2026-02-03 15:46 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 64
202510-NM25-01445 | GDL17 | Comercial | 7.6 | Period | 2026-03-13 10:55 | March | 2026 | 2026-03-16 14:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 19
202510-NM25-01462 | GDL17 | Residencial | 8 | Out of period | 2025-10-16 18:25 | October | 2025 | 2026-01-21 13:09 | 97 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 2 | 4 | 93 | 2026-04-01 | 166
202510-NM25-01485 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:21 | January | 2026 | 2026-01-21 16:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202510-NM25-01499 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:13 | February | 2026 | 2026-02-23 09:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202510-NM25-01506 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-30 11:21 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 158 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 153
202510-NM25-01507 | GDL17 | Residencial | 6.528 | Out of period | 2025-10-09 16:53 | October | 2025 | 2026-01-08 09:51 | 91 | Study | Estudio (E) | Activated | Backlog |  | No | 91 |  | MAYAGUEZ | January |  | 90 | 0 | 2026-04-01 | 173
202510-NM25-01516 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:08 | February | 2026 | 2026-02-24 14:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-01525 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 18:32 | February | 2026 | 2026-02-23 09:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-01558 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:47 | March | 2026 | 2026-03-05 15:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202510-NM25-01574 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 18:30 | January | 2026 | 2026-01-21 14:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202510-NM25-01576 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 18:36 | January | 2026 | 2026-01-21 14:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202510-NM25-01593 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:41 | January | 2026 | 2026-01-29 13:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202510-NM25-01596 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:14 | February | 2026 | 2026-02-10 14:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 55
202510-NM25-01613 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 14:04 | February | 2026 | 2026-02-16 08:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 47
202510-NM25-01618 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:10 | January | 2026 | 2026-01-30 12:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 64
202510-NM25-01622 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:18 | February | 2026 | 2026-02-09 16:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 57
202510-NM25-01627 | GDL17 | Residencial | 22.8 | Out of period | 2025-12-29 15:13 | December | 2025 | 2026-03-25 14:55 | 86 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 6 | 80 | 2026-04-01 | 92
202510-NM25-01639 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:36 | February | 2026 | 2026-02-27 10:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 37
202510-NM25-01643 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 21:41 | February | 2026 | 2026-02-26 08:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 38
202510-NM25-01645 | GDL17 | Residencial | 15 | Out of period | 2025-11-04 10:04 | November | 2025 | 2026-02-19 14:51 | 107 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 3 | 3 | 104 | 2026-04-01 | 148
202510-NM25-01646 | GDL17 | Residencial | 3.84 | Period | 2026-01-27 08:54 | January | 2026 | 2026-02-12 15:28 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 16 | 0 | 2026-04-01 | 64
202510-NM25-01658 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:42 | February | 2026 | 2026-02-17 16:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 47
202510-NM25-01664 | GDL17 | Residencial | 23 | Period | 2026-02-19 15:56 | February | 2026 | 2026-02-25 08:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-01665 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:31 | February | 2026 | 2026-02-25 08:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-01671 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 13:30 | January | 2026 | 2026-02-03 13:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 60
202510-NM25-01672 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:03 | March | 2026 | 2026-03-12 11:30 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 9 | 0 | 2026-04-01 | 28
202510-NM25-01675 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 17:44 | February | 2026 | 2026-02-25 09:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-01679 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-10 16:47 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 172
202510-NM25-01684 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 17:30 | January | 2026 | 2026-02-27 14:54 | 38 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 38 | 0 | 2026-04-01 | 70
202510-NM25-01685 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:00 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 42
202510-NM25-01686 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:13 | February | 2026 | 2026-03-03 08:51 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 41
202510-NM25-01726 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 21:16 | February | 2026 | 2026-02-23 13:28 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 47
202510-NM25-01728 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 21:31 | March | 2026 | 2026-03-12 08:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 21
202510-NM25-01731 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:55 | February | 2026 | 2026-03-23 09:44 | 31 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 31 | 0 | 2026-04-01 | 39
202510-NM25-01732 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-19 14:21 | November | 2025 | 2026-01-05 09:32 | 47 | Study | Estudio (E) | Activated | Backlog |  | No | 47 |  | MAYAGUEZ | January |  | 47 | 0 | 2026-04-01 | 132
202510-NM25-01735 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:13 | February | 2026 | 2026-03-02 10:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 35
202510-NM25-01740 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:12 | February | 2026 | 2026-03-05 07:48 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 35
202510-NM25-01745 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:52 | February | 2026 | 2026-02-26 08:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 36
202510-NM25-01750 | GDL17 | Residencial | 11.5 | Period | 2026-03-01 22:00 | March | 2026 | 2026-03-13 12:41 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 4 | 8 | 2026-04-01 | 30
202510-NM25-01753 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:40 | February | 2026 | 2026-02-24 13:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-01772 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:23 | February | 2026 | 2026-03-05 14:04 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 36
202510-NM25-01776 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 19:38 | February | 2026 | 2026-02-24 07:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-01777 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-17 08:13 | November | 2025 | 2026-01-21 14:47 | 65 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 47 | 18 | 2026-04-01 | 135
202510-NM25-01780 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 08:50 | February | 2026 | 2026-02-17 13:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 48
202510-NM25-01796 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:03 | February | 2026 | 2026-02-25 11:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-01800 | GDL17 | Residencial | 12 | Out of period | 2025-10-23 08:54 | October | 2025 | 2026-02-09 08:39 | 109 | Study | Estudio (E) | Activated | Backlog |  | No | 109 |  | CAGUAS | February |  | 109 | 0 | 2026-04-01 | 160
202510-NM25-01801 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:10 | February | 2026 | 2026-02-27 09:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 36
202510-NM25-01806 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-21 14:38 | October | 2025 | 2026-01-12 16:08 | 83 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 20 | 63 | 2026-04-01 | 161
202510-NM25-01828 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:29 | March | 2026 | 2026-03-06 16:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 26
202510-NM25-01831 | GDL17 | Residencial | 3.8 | Period | 2026-02-21 18:58 | February | 2026 | 2026-02-26 16:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 38
202510-NM25-01845 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 18:19 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 41
202510-NM25-01846 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 08:49 | March | 2026 | 2026-03-09 15:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 28
202510-NM25-01847 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-07 17:33 | November | 2025 | 2026-01-07 08:56 | 61 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 54 | 7 | 2026-04-01 | 144
202510-NM25-01849 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 10:37 | February | 2026 | 2026-02-20 16:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 43
202510-NM25-01860 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-06 13:40 | November | 2025 | 2026-01-02 11:17 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | MAYAGUEZ | January |  | 57 | 0 | 2026-04-01 | 145
202510-NM25-01865 | GDL17 | Residencial | 8 | Out of period | 2025-11-10 10:52 | November | 2025 |  |  | Customer Orientation | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 142
202510-NM25-01935 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:57 | February | 2026 | 2026-02-23 09:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-01936 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:18 | February | 2026 | 2026-02-23 09:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-01942 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:52 | January | 2026 | 2026-01-19 09:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202510-NM25-01944 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:54 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 42
202510-NM25-01950 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:22 | February | 2026 | 2026-02-18 13:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202510-NM25-01961 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 17:54 | January | 2026 | 2026-02-03 08:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 61
202510-NM25-01967 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:34 | February | 2026 | 2026-02-27 14:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202510-NM25-01978 | GDL17 | Residencial | 8 | Period | 2026-01-09 10:34 | January | 2026 | 2026-01-20 13:02 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 11 | 0 | 2026-04-01 | 82
202510-NM25-01985 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:32 | January | 2026 | 2026-01-12 10:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202510-NM25-01994 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:10 | January | 2026 | 2026-01-12 16:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202510-NM25-01998 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-16 12:27 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 166
202510-NM25-02000 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:25 | January | 2026 | 2026-01-14 14:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 84
202510-NM25-02012 | GDL17 | Residencial | 23 | Period | 2026-02-17 17:27 | February | 2026 | 2026-03-17 15:08 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 4 | 24 | 2026-04-01 | 42
202510-NM25-02019 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 21:01 | February | 2026 | 2026-02-24 13:45 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 42
202510-NM25-02020 | GDL17 | Comercial | 11.5 | Period | 2026-02-19 21:19 | February | 2026 | 2026-02-25 08:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 40
202510-NM25-02036 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:36 | January | 2026 | 2026-01-09 10:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 83
202510-NM25-02040 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:49 | January | 2026 | 2026-02-17 08:53 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 41 | 0 | 2026-04-01 | 83
202510-NM25-02046 | GDL17 | Comercial | 20.945 | Out of period | 2025-10-16 14:51 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 166
202510-NM25-02051 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:28 | February | 2026 | 2026-02-23 09:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-02060 | GDL17 | Residencial | 6.912 | Period | 2026-01-20 08:23 | January | 2026 | 2026-01-28 13:43 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 71
202510-NM25-02076 | GDL17 | Comercial | 5.3 | Out of period | 2025-12-29 13:37 | December | 2025 | 2026-02-04 16:02 | 37 | Study | Estudio (E) | Activated | Backlog |  | No | 37 |  | PONCE | February |  | 37 | 0 | 2026-04-01 | 92
202510-NM25-02079 | GDL17 | Comercial | 5.3 | Out of period | 2025-12-29 13:38 | December | 2025 | 2026-02-04 15:41 | 37 | Study | Estudio (E) | Activated | Backlog |  | No | 37 |  | PONCE | February |  | 37 | 0 | 2026-04-01 | 92
202510-NM25-02080 | GDL17 | Comercial | 5.3 | Out of period | 2025-12-29 13:40 | December | 2025 | 2026-02-04 15:35 | 37 | Study | Estudio (E) | Activated | Backlog |  | No | 37 |  | PONCE | February |  | 37 | 0 | 2026-04-01 | 92
202510-NM25-02082 | GDL17 | Comercial | 5.3 | Period | 2026-03-13 09:34 | March | 2026 | 2026-04-13 15:53 | 31 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 31 | 15 | 2026-04-01 | 19
202510-NM25-02084 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:55 | January | 2026 | 2026-01-13 09:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202510-NM25-02086 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 18:40 | February | 2026 | 2026-03-04 08:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202510-NM25-02110 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 21:59 | November | 2025 | 2026-01-09 10:56 | 50 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | January | 1 | 43 | 7 | 2026-04-01 | 131
202510-NM25-02133 | GDL17 | Residencial | 11.5 | Period | 2026-01-13 23:41 | January | 2026 | 2026-01-15 14:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 77
202510-NM25-02143 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 20:02 | February | 2026 | 2026-02-16 14:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202510-NM25-02146 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-23 21:02 | November | 2025 | 2026-02-17 14:04 | 86 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February |  | 86 | 13 | 2026-04-01 | 128
202510-NM25-02149 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 10:32 | February | 2026 | 2026-02-19 11:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 44
202510-NM25-02175 | GDL17 | Residencial | 6 | Period | 2026-02-18 07:52 | February | 2026 | 2026-02-23 09:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202510-NM25-02183 | GDL17 | Residencial | 15.3 | Out of period | 2025-11-13 11:02 | November | 2025 | 2026-01-20 08:17 | 68 | Study | Estudio (E) | Activated | Backlog |  | No | 68 |  | MAYAGUEZ | January |  | 68 | 0 | 2026-04-01 | 139
202510-NM25-02192 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:20 | February | 2026 | 2026-03-02 10:33 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 40
202510-NM25-02198 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-17 13:52 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 165
202510-NM25-02201 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 02:11 | February | 2026 | 2026-02-25 10:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-02203 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-17 14:22 | October | 2025 | 2026-03-18 17:45 | 152 | Study | Estudio (E) | Activated | Backlog |  | No | 152 |  | CAGUAS | March |  | 152 | 0 | 2026-04-01 | 165
202510-NM25-02204 | GDL17 | Residencial | 11.46 | Out of period | 2025-11-06 17:33 | November | 2025 |  |  | Customer Orientation | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 145
202510-NM25-02207 | GDL17 | Residencial | 6.3 | Out of period | 2025-10-20 13:57 | October | 2025 | 2026-01-20 13:37 | 92 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 56 | 36 | 2026-04-01 | 162
202510-NM25-02211 | GDL17 | Residencial | 8 | Period | 2026-01-19 10:20 | January | 2026 | 2026-01-30 15:58 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 11 | 0 | 2026-04-01 | 72
202510-NM25-02233 | GDL17 | Comercial | 7.6 | Out of period | 2025-11-14 15:34 | November | 2025 | 2026-01-13 10:56 | 60 | Study | Estudio (E) | Activated | Backlog |  | No | 60 |  | BAYAMON | January |  | 60 | 0 | 2026-04-01 | 137
202510-NM25-02234 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-17 15:36 | October | 2025 | 2026-01-12 09:31 | 87 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 2 | 11 | 64 | 2026-04-01 | 165
202510-NM25-02265 | GDL17 | Comercial | 12 | Out of period | 2025-10-18 11:26 | October | 2025 | 2026-01-08 14:25 | 82 | Study | Estudio (E) | Activated | Backlog |  | No | 82 |  | CAGUAS | January |  | 82 | 0 | 2026-04-01 | 165
202510-NM25-02295 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-19 09:30 | October | 2025 | 2026-01-02 13:16 | 75 | Study | Estudio (E) | Activated | Backlog |  | No | 75 |  | MAYAGUEZ | January |  | 75 | 0 | 2026-04-01 | 164
202510-NM25-02300 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:36 | February | 2026 | 2026-02-23 09:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-02301 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:30 | February | 2026 | 2026-02-25 09:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-02303 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 07:12 | February | 2026 | 2026-02-16 10:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 48
202510-NM25-02313 | GDL17 | Residencial | 3.8 | Out of period | 2025-10-28 14:57 | October | 2025 | 2026-01-16 14:31 | 80 | Study | Estudio (E) | Activated | Backlog |  | No | 80 |  | BAYAMON | January |  | 80 | 0 | 2026-04-01 | 154
202510-NM25-02316 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 16:59 | February | 2026 | 2026-02-19 11:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 47
202510-NM25-02317 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:22 | February | 2026 | 2026-02-24 07:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-02325 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:37 | February | 2026 | 2026-02-19 10:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 43
202510-NM25-02328 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-20 07:46 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 163
202510-NM25-02345 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-20 10:33 | October | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 163
202510-NM25-02364 | GDL17 | Residencial | 5.76 | Out of period | 2025-10-25 14:05 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 157
202510-NM25-02389 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-04 09:27 | November | 2025 | 2026-01-08 07:50 | 65 | Study | Estudio (E) | Activated | Backlog |  | No | 65 |  | MAYAGUEZ | January |  | 65 | 0 | 2026-04-01 | 148
202510-NM25-02395 | GDL17 | Residencial | 8 | Out of period | 2025-11-06 15:54 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 145
202510-NM25-02404 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:40 | January | 2026 | 2026-02-02 14:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 64
202510-NM25-02406 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 10:41 | March | 2026 | 2026-03-18 14:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 16
202510-NM25-02420 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-25 12:18 | November | 2025 | 2026-01-28 07:43 | 64 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 56 | 3 | 2026-04-01 | 126
202510-NM25-02427 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:42 | February | 2026 | 2026-02-25 09:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-02428 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 14:46 | February | 2026 | 2026-02-16 13:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202510-NM25-02429 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:26 | March | 2026 | 2026-03-09 09:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 27
202510-NM25-02437 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 00:36 | February | 2026 | 2026-02-23 09:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-02446 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 18:07 | February | 2026 | 2026-02-23 16:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 6 | 1 | 2026-04-01 | 43
202510-NM25-02463 | GDL17 | Residencial | 3 | Out of period | 2025-10-20 15:14 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 162
202510-NM25-02472 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 08:03 | March | 2026 | 2026-03-10 16:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 0 | 4 | 2026-04-01 | 26
202510-NM25-02483 | GDL17 | Residencial | 5 | Out of period | 2025-10-30 21:01 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 152
202510-NM25-02488 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-31 08:48 | October | 2025 | 2026-01-28 11:11 | 89 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 49 | 40 | 2026-04-01 | 152
202510-NM25-02529 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-24 14:58 | November | 2025 | 2026-01-07 13:55 | 44 | Study | Estudio (E) | Activated | Backlog |  | No | 44 |  | MAYAGUEZ | January |  | 44 | 0 | 2026-04-01 | 127
202510-NM25-02537 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-11 14:46 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 140
202510-NM25-02603 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-10 16:15 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 141
202510-NM25-02610 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:54 | February | 2026 | 2026-02-20 08:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 47
202510-NM25-02611 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 18:10 | February | 2026 | 2026-02-25 08:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-02614 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 23:15 | March | 2026 | 2026-03-09 15:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 3 | 0 | 2026-04-01 | 25
202510-NM25-02620 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-21 09:44 | October | 2025 | 2026-03-09 13:51 | 139 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | March | 2 | 21 | 118 | 2026-04-01 | 162
202510-NM25-02642 | GDL17 | Residencial | 23 | Period | 2026-01-29 16:00 | January | 2026 | 2026-02-04 17:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 61
202510-NM25-02643 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-25 10:13 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 158
202510-NM25-02646 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:13 | March | 2026 | 2026-03-17 11:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202510-NM25-02656 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 14:25 | March | 2026 | 2026-03-20 16:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 13
202510-NM25-02657 | GDL17 | Residencial | 10 | Out of period | 2025-11-20 08:14 | November | 2025 | 2026-01-07 08:56 | 48 | Study | Estudio (E) | Activated | Backlog |  | No | 48 |  | MAYAGUEZ | January |  | 48 | 0 | 2026-04-01 | 132
202510-NM25-02660 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:38 | January | 2026 | 2026-02-10 15:18 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 12 | 0 | 2026-04-01 | 61
202510-NM25-02714 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-21 12:36 | October | 2025 | 2026-01-15 11:29 | 86 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 1 | 64 | 22 | 2026-04-01 | 161
202510-NM25-02715 | GDL17 | Residencial | 3.3 | Period | 2026-03-04 12:18 | March | 2026 | 2026-03-09 08:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 27
202510-NM25-02726 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:43 | March | 2026 | 2026-03-25 13:02 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 21 | 0 | 2026-04-01 | 28
202510-NM25-02741 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-21 14:26 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 161
202510-NM25-02762 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:55 | February | 2026 | 2026-02-19 08:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 44
202510-NM25-02763 | GDL17 | Residencial | 3.3 | Period | 2026-02-18 22:37 | February | 2026 | 2026-02-24 08:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202510-NM25-02765 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 17:44 | February | 2026 | 2026-03-20 10:27 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 35 | 0 | 2026-04-01 | 46
202510-NM25-02792 | GDL17 | Residencial | 9 | Out of period | 2025-10-23 16:39 | October | 2025 | 2026-01-14 12:46 | 83 | Study | Estudio (E) | Activated | Backlog |  | No | 83 |  | MAYAGUEZ | January |  | 83 | 0 | 2026-04-01 | 159
202510-NM25-02796 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 18:06 | February | 2026 | 2026-02-27 08:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 36
202510-NM25-02855 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:57 | February | 2026 | 2026-02-24 14:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-02871 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 11:39 | March | 2026 | 2026-03-16 07:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 21
202510-NM25-02877 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:08 | February | 2026 | 2026-03-04 10:25 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 39
202510-NM25-02878 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-25 17:05 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 126
202510-NM25-02886 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-22 11:11 | October | 2025 | 2026-01-13 12:44 | 83 | Study | Estudio (E) | Activated | Backlog |  | No | 83 |  | CAGUAS | January |  | 83 | 0 | 2026-04-01 | 161
202510-NM25-02897 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 17:35 | February | 2026 | 2026-02-26 10:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202510-NM25-02902 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 23:20 | February | 2026 | 2026-02-27 13:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 35
202510-NM25-02904 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 21:32 | February | 2026 | 2026-02-26 08:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 38
202510-NM25-02920 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-22 13:19 | October | 2025 | 2026-02-24 07:57 | 125 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February |  | 124 | 12 | 2026-04-01 | 160
202510-NM25-02927 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-23 13:10 | October | 2025 | 2026-03-26 16:04 | 154 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 134 | 3 | 2026-04-01 | 159
202510-NM25-02933 | GDL17 | Residencial | 6.912 | Period | 2026-01-21 08:29 | January | 2026 | 2026-01-29 16:21 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 70
202510-NM25-02948 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-05 11:53 | December | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 117
202510-NM25-02956 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 07:53 | February | 2026 | 2026-02-16 14:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202510-NM25-02963 | GDL17 | Residencial | 15.3 | Period | 2026-02-17 12:09 | February | 2026 | 2026-02-23 09:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-02968 | GDL17 | Residencial | 17.2 | Period | 2026-02-20 15:42 | February | 2026 | 2026-02-26 10:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 39
202510-NM25-02974 | GDL17 | Residencial | 19.1 | Period | 2026-02-17 11:15 | February | 2026 | 2026-02-20 08:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 43
202510-NM25-02993 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 20:52 | February | 2026 | 2026-02-25 08:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202510-NM25-03009 | GDL17 | Residencial | 11.5 | Period | 2026-03-08 20:07 | March | 2026 | 2026-03-09 13:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 23
202510-NM25-03013 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:52 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 48
202510-NM25-03024 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 08:31 | March | 2026 | 2026-03-17 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 20
202510-NM25-03064 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:00 | January | 2026 | 2026-01-26 14:02 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 77
202510-NM25-03066 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-23 10:58 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 168 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 160
202510-NM25-03073 | GDL17 | Residencial | 3.8 | Period | 2026-02-27 10:59 | February | 2026 | 2026-03-05 10:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 33
202510-NM25-03102 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 17:36 | February | 2026 | 2026-02-23 09:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-03124 | GDL17 | Residencial | 6.996 | Out of period | 2025-10-24 11:46 | October | 2025 | 2026-01-08 16:23 | 76 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 3 | 10 | 66 | 2026-04-01 | 159
202510-NM25-03128 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-29 12:32 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 160 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 153
202510-NM25-03135 | GDL17 | Residencial | 3.84 | Period | 2026-01-27 11:09 | January | 2026 | 2026-01-29 11:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202510-NM25-03142 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:48 | February | 2026 | 2026-02-27 10:41 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 43
202510-NM25-03150 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 14:07 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 33
202510-NM25-03151 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:59 | February | 2026 | 2026-02-25 08:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-03155 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-23 18:01 | October | 2025 | 2026-01-19 10:31 | 88 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 76 | 12 | 2026-04-01 | 159
202510-NM25-03172 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-24 09:12 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 159
202510-NM25-03180 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 18:05 | February | 2026 | 2026-02-26 08:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 39
202510-NM25-03202 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-24 10:58 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 159
202510-NM25-03203 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:21 | February | 2026 | 2026-02-13 10:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202510-NM25-03213 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:45 | January | 2026 | 2026-02-03 12:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 60
202510-NM25-03216 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:51 | January | 2026 | 2026-02-04 13:23 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 65
202510-NM25-03223 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:55 | February | 2026 | 2026-02-06 11:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202510-NM25-03226 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-24 12:42 | October | 2025 | 2026-01-08 14:57 | 76 | Study | Estudio (E) | Activated | Backlog |  | No | 76 |  | MAYAGUEZ | January |  | 76 | 0 | 2026-04-01 | 158
202510-NM25-03239 | GDL17 | Residencial | 23 | Period | 2026-01-30 13:14 | January | 2026 | 2026-02-12 09:01 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 13 | 0 | 2026-04-01 | 60
202510-NM25-03248 | GDL17 | Residencial | 6.912 | Period | 2026-03-11 16:05 | March | 2026 | 2026-03-16 08:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 20
202510-NM25-03260 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 17:44 | February | 2026 | 2026-03-05 09:05 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 38
202510-NM25-03262 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 14:56 | February | 2026 | 2026-03-17 15:04 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 24 | 0 | 2026-04-01 | 38
202510-NM25-03267 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:35 | January | 2026 | 2026-02-05 14:20 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 65
202510-NM25-03268 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:09 | February | 2026 | 2026-02-19 10:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202510-NM25-03276 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:18 | February | 2026 | 2026-02-23 09:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-03286 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:11 | January | 2026 | 2026-01-27 10:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 65
202510-NM25-03306 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 18:12 | February | 2026 | 2026-02-04 17:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202510-NM25-03307 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:06 | January | 2026 | 2026-02-04 11:24 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 65
202510-NM25-03308 | GDL17 | Residencial | 23 | Period | 2026-01-14 16:03 | January | 2026 | 2026-02-13 09:43 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 30 | 0 | 2026-04-01 | 76
202510-NM25-03315 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 08:39 | January | 2026 | 2026-01-13 09:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202510-NM25-03325 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:30 | February | 2026 | 2026-02-05 15:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 56
202510-NM25-03326 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:04 | January | 2026 | 2026-01-20 15:33 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 12 | 0 | 2026-04-01 | 83
202510-NM25-03362 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 17:03 | January | 2026 | 2026-03-16 15:37 | 66 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 66 | 0 | 2026-04-01 | 81
202510-NM25-03363 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 13:58 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 131
202510-NM25-03365 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:11 | January | 2026 | 2026-01-29 14:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 64
202510-NM25-03366 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 15:51 | March | 2026 | 2026-03-31 13:32 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 11
202510-NM25-03367 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:03 | January | 2026 | 2026-01-16 14:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 76
202510-NM25-03394 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:22 | January | 2026 | 2026-01-13 09:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202510-NM25-03408 | GDL17 | Comercial | 10.672 | Out of period | 2025-11-04 10:05 | November | 2025 | 2026-01-21 14:12 | 78 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 3 | 15 | 63 | 2026-04-01 | 148
202510-NM25-03411 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-27 11:28 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 156
202510-NM25-03419 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-27 11:47 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 156
202510-NM25-03439 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-27 14:36 | October | 2025 | 2026-01-29 10:06 | 94 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 8 | 86 | 2026-04-01 | 155
202510-NM25-03460 | GDL17 | Residencial | 23 | Out of period | 2025-11-13 10:13 | November | 2025 | 2026-01-08 08:22 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | MAYAGUEZ | January |  | 55 | 0 | 2026-04-01 | 139
202510-NM25-03461 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:27 | February | 2026 | 2026-02-25 08:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202510-NM25-03467 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-24 11:38 | November | 2025 | 2026-03-03 15:05 | 99 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | March | 1 | 3 | 96 | 2026-04-01 | 128
202510-NM25-03471 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 22:17 | February | 2026 | 2026-02-27 10:51 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 42
202510-NM25-03475 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 18:20 | January | 2026 | 2026-01-21 09:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 75
202510-NM25-03476 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:55 | February | 2026 | 2026-02-17 09:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202510-NM25-03486 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-24 09:57 | November | 2025 | 2026-01-20 13:19 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | MAYAGUEZ | January |  | 57 | 0 | 2026-04-01 | 128
202510-NM25-03517 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 08:21 | March | 2026 | 2026-03-04 15:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 30
202510-NM25-03523 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:48 | February | 2026 | 2026-03-03 10:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 36
202510-NM25-03534 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:56 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 48
202510-NM25-03551 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 19:46 | February | 2026 | 2026-02-23 09:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-03582 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-12 14:58 | December | 2025 | 2026-03-10 14:00 | 88 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March | 1 | 69 | 19 | 2026-04-01 | 109
202510-NM25-03600 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:23 | March | 2026 | 2026-03-12 09:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202510-NM25-03603 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-28 10:11 | October | 2025 | 2026-02-09 15:48 | 104 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February | 1 | 4 | 100 | 2026-04-01 | 155
202510-NM25-03615 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:21 | February | 2026 | 2026-02-23 09:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-03626 | GDL17 | Comercial | 17.6 | Out of period | 2025-11-20 23:38 | November | 2025 | 2026-01-19 16:14 | 60 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 13 | 47 | 2026-04-01 | 131
202510-NM25-03627 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:58 | January | 2026 | 2026-01-27 14:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 65
202510-NM25-03646 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:52 | January | 2026 | 2026-02-02 13:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 61
202510-NM25-03647 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:07 | February | 2026 | 2026-03-03 16:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 32
202510-NM25-03652 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 15:22 | January | 2026 | 2026-02-04 13:21 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 13 | 0 | 2026-04-01 | 68
202510-NM25-03654 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:23 | March | 2026 | 2026-03-09 14:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 26
202510-NM25-03659 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:38 | February | 2026 | 2026-02-23 09:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-03667 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 12:45 | January | 2026 | 2026-01-26 16:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 67
202510-NM25-03668 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 18:14 | January | 2026 | 2026-01-28 16:02 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 13 | 0 | 2026-04-01 | 75
202510-NM25-03677 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 08:26 | January | 2026 | 2026-01-13 10:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202510-NM25-03678 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:53 | January | 2026 | 2026-01-14 13:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202510-NM25-03680 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:29 | January | 2026 | 2026-01-12 15:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 83
202510-NM25-03684 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:41 | February | 2026 | 2026-02-10 12:49 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 57
202510-NM25-03691 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:48 | February | 2026 | 2026-02-19 11:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 44
202510-NM25-03695 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 17:27 | February | 2026 | 2026-02-20 07:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 43
202510-NM25-03699 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:22 | January | 2026 | 2026-01-14 13:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 82
202510-NM25-03709 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:55 | March | 2026 | 2026-03-05 13:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202510-NM25-03713 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:03 | February | 2026 | 2026-02-26 08:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 37
202510-NM25-03717 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:21 | February | 2026 | 2026-02-19 08:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 47
202510-NM25-03723 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:55 | January | 2026 | 2026-01-21 08:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 76
202510-NM25-03766 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:32 | February | 2026 | 2026-02-13 15:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202510-NM25-03770 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 11:13 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 13
202510-NM25-03776 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-13 10:32 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 144 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 139
202510-NM25-03810 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:02 | March | 2026 | 2026-03-04 15:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 30
202510-NM25-03815 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 16:11 | March | 2026 | 2026-04-17 16:23 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 18 | 0 | 2026-04-01 | 1
202510-NM25-03837 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:24 | March | 2026 | 2026-03-11 14:29 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 9 | 0 | 2026-04-01 | 29
202510-NM25-03839 | GDL17 | Residencial | 9.15 | Out of period | 2025-12-09 20:39 | December | 2025 | 2026-02-13 15:50 | 66 | Study | Estudio (E) | Activated | Backlog |  | No | 66 |  | SAN JUAN | February |  | 66 | 0 | 2026-04-01 | 112
202510-NM25-03843 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 12:54 | January | 2026 | 2026-02-09 08:52 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 60
202510-NM25-03845 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-05 08:57 | November | 2025 | 2026-03-05 13:17 | 120 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | March | 2 | 4 | 116 | 2026-04-01 | 147
202510-NM25-03851 | GDL17 | Residencial | 3.8 | Period | 2026-01-29 14:46 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 61
202510-NM25-03854 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:30 | February | 2026 | 2026-02-25 09:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 41
202510-NM25-03860 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:07 | January | 2026 | 2026-01-12 16:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202510-NM25-03861 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:24 | January | 2026 | 2026-02-02 15:18 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 11 | 0 | 2026-04-01 | 69
202510-NM25-03864 | GDL17 | Residencial | 7.6 | Out of period | 2025-10-29 15:14 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 153
202510-NM25-03867 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 13:21 | January | 2026 | 2026-02-03 13:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202510-NM25-03868 | GDL17 | Residencial | 12 | Out of period | 2025-10-29 13:24 | October | 2025 | 2026-01-07 10:34 | 70 | Study | Estudio (E) | Activated | Backlog |  | No | 70 |  | MAYAGUEZ | January |  | 70 | 0 | 2026-04-01 | 153
202510-NM25-03874 | GDL17 | Residencial | 11.4 | Out of period | 2025-11-06 16:49 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 145
202510-NM25-03880 | GDL17 | Residencial | 23 | Period | 2026-01-26 18:54 | January | 2026 | 2026-01-28 15:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202510-NM25-03881 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-29 15:15 | October | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 159 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 153
202510-NM25-03887 | GDL17 | Residencial | 3.456 | Period | 2026-02-18 16:12 | February | 2026 | 2026-02-24 07:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-03898 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-18 10:57 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 134
202510-NM25-03902 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:25 | January | 2026 | 2026-02-06 13:39 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 60
202510-NM25-03903 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:23 | January | 2026 | 2026-02-02 10:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202510-NM25-03904 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 18:14 | February | 2026 | 2026-02-27 08:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202510-NM25-03907 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:47 | January | 2026 | 2026-01-29 09:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 64
202510-NM25-03912 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 17:21 | February | 2026 | 2026-02-24 14:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-03915 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 18:00 | February | 2026 | 2026-02-06 14:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 56
202510-NM25-03924 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 18:01 | February | 2026 | 2026-02-09 14:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 56
202510-NM25-03925 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-31 09:32 | October | 2025 | 2026-01-20 11:06 | 81 | Study | Estudio (E) | Activated | Backlog |  | No | 81 |  | MAYAGUEZ | January |  | 82 | 0 | 2026-04-01 | 152
202510-NM25-03926 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:42 | January | 2026 | 2026-01-19 14:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202510-NM25-03927 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 13:24 | February | 2026 | 2026-02-16 14:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202510-NM25-03930 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:13 | February | 2026 | 2026-02-23 08:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-03933 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:59 | January | 2026 | 2026-01-29 12:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 69
202510-NM25-03937 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 17:33 | January | 2026 | 2026-01-16 11:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 81
202510-NM25-03939 | GDL17 | Residencial | 24.5 | Period | 2026-02-09 17:09 | February | 2026 | 2026-02-11 10:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202510-NM25-03940 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-29 15:52 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 153
202510-NM25-03941 | GDL17 | Residencial | 11.5 | Out of period | 2025-10-29 15:48 | October | 2025 | 2026-02-11 10:03 | 105 | Study | Estudio (E) | Activated | Backlog |  | No | 105 |  | MAYAGUEZ | February |  | 104 | 0 | 2026-04-01 | 153
202510-NM25-03942 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:17 | March | 2026 | 2026-03-25 09:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 9
202510-NM25-03945 | GDL17 | Residencial | 18.285 | Period | 2026-02-03 12:20 | February | 2026 | 2026-02-05 12:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 56
202510-NM25-03946 | GDL17 | Residencial | 23 | Period | 2026-01-21 14:49 | January | 2026 | 2026-01-23 14:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202510-NM25-03955 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-05 17:28 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 146
202510-NM25-03957 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-05 11:16 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 122 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 117
202510-NM25-03968 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-04 20:25 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 153 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 147
202510-NM25-03999 | GDL17 | Residencial | 7.68 | Out of period | 2025-10-30 08:55 | October | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 153
202510-NM25-04003 | GDL17 | Residencial | 4.992 | Out of period | 2025-11-06 12:38 | November | 2025 | 2026-03-03 10:05 | 117 | Study | Estudio (E) | Activated | Backlog |  | No | 117 |  | BAYAMON | March |  | 117 | 0 | 2026-04-01 | 145
202510-NM25-04012 | GDL17 | Residencial | 15.2 | Period | 2026-01-15 11:12 | January | 2026 | 2026-01-20 08:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 1 | 4 | 1 | 2026-04-01 | 76
202510-NM25-04015 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:55 | February | 2026 | 2026-02-23 11:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 43
202510-NM25-04017 | GDL17 | Residencial | 3.8 | Period | 2026-02-12 16:40 | February | 2026 | 2026-02-16 15:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202510-NM25-04018 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:25 | February | 2026 | 2026-03-05 10:14 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 19 | 1 | 2026-04-01 | 46
202510-NM25-04019 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:21 | February | 2026 | 2026-02-19 07:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202510-NM25-04020 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:37 | February | 2026 | 2026-03-02 16:07 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 39
202510-NM25-04028 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 11:58 | February | 2026 | 2026-02-23 14:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202510-NM25-04040 | GDL17 | Comercial | 13.824 | Out of period | 2025-12-15 17:20 | December | 2025 | 2026-02-10 14:40 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | BAYAMON | February |  | 57 | 0 | 2026-04-01 | 106
202510-NM25-04051 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 10:03 | February | 2026 | 2026-02-26 08:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202510-NM25-04069 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:41 | January | 2026 | 2026-02-04 11:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 60
202510-NM25-04072 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:43 | February | 2026 | 2026-03-02 08:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 36
202510-NM25-04073 | GDL17 | Residencial | 23 | Period | 2026-02-02 17:52 | February | 2026 | 2026-02-05 10:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202510-NM25-04077 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:46 | January | 2026 | 2026-01-29 10:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 65
202510-NM25-04084 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 16:07 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 48
202510-NM25-04085 | GDL17 | Residencial | 15.892 | Period | 2026-02-02 15:52 | February | 2026 | 2026-02-04 15:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202510-NM25-04091 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 18:05 | January | 2026 | 2026-01-12 10:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 84
202510-NM25-04092 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:42 | February | 2026 | 2026-02-05 15:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 57
202510-NM25-04094 | GDL17 | Residencial | 6 | Period | 2026-01-25 08:17 | January | 2026 | 2026-01-29 10:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 66
202510-NM25-04098 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 11:37 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 58
202510-NM25-04099 | GDL17 | Residencial | 3.8 | Out of period | 2025-12-10 14:09 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 117 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 111
202510-NM25-04100 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-17 11:54 | December | 2025 | 2026-02-04 13:44 | 49 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 1 | 4 | 45 | 2026-04-01 | 105
202510-NM25-04101 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:09 | February | 2026 | 2026-02-23 09:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-04103 | GDL17 | Residencial | 7.6 | Period | 2026-02-18 11:45 | February | 2026 | 2026-02-24 12:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-04111 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 16:49 | January | 2026 | 2026-01-08 13:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 88
202510-NM25-04112 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 12:26 | January | 2026 | 2026-02-02 08:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 61
202510-NM25-04117 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-18 15:14 | November | 2025 | 2026-01-15 14:14 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | MAYAGUEZ | January |  | 58 | 0 | 2026-04-01 | 133
202510-NM25-04118 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:23 | February | 2026 | 2026-03-05 09:43 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 16 | 0 | 2026-04-01 | 42
202510-NM25-04121 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:03 | February | 2026 | 2026-02-11 15:03 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 57
202510-NM25-04123 | GDL17 | Residencial | 8.064 | Period | 2026-03-10 07:38 | March | 2026 | 2026-03-13 11:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 22
202510-NM25-04130 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:05 | January | 2026 | 2026-01-26 15:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 69
202510-NM25-04132 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:17 | January | 2026 | 2026-01-14 10:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 82
202510-NM25-04141 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-05 13:46 | December | 2025 | 2026-02-16 07:40 | 73 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February |  | 73 | 0 | 2026-04-01 | 116
202510-NM25-04186 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:21 | February | 2026 | 2026-02-23 09:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202510-NM25-04188 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:32 | February | 2026 | 2026-02-23 16:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 41
202510-NM25-04189 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:53 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 83
202510-NM25-04203 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 13:54 | November | 2025 | 2026-01-27 15:32 | 85 | Study | Estudio (E) | Activated | Backlog |  | No | 85 |  | ARECIBO | January |  | 85 | 0 | 2026-04-01 | 148
202510-NM25-04212 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 20:56 | February | 2026 | 2026-02-18 10:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 46
202510-NM25-04219 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:49 | February | 2026 | 2026-02-24 14:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202510-NM25-04224 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:46 | February | 2026 | 2026-02-26 15:07 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 9 | 0 | 2026-04-01 | 42
202510-NM25-04239 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:45 | February | 2026 | 2026-02-16 14:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202510-NM25-04260 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:43 | January | 2026 | 2026-01-14 15:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202510-NM25-04265 | GDL17 | Residencial | 10 | Out of period | 2025-11-04 10:05 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 148
202510-NM25-04267 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:25 | January | 2026 | 2026-01-29 14:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 64
202510-NM25-04272 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:24 | February | 2026 | 2026-02-06 15:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 55
202510-NM25-04276 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:28 | February | 2026 | 2026-02-09 15:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 57
202510-NM25-04280 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:32 | February | 2026 | 2026-02-25 08:08 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 42
202510-NM25-04281 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:14 | March | 2026 | 2026-03-05 14:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 28
202510-NM25-04286 | GDL17 | Residencial | 5.76 | Period | 2026-03-24 07:37 | March | 2026 | 2026-03-27 13:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 8
202510-NM25-04294 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:29 | January | 2026 | 2026-01-21 14:39 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 82
202510-NM25-04295 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:55 | January | 2026 | 2026-02-02 14:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 61
202510-NM25-04316 | GDL17 | Residencial | 21.5 | Period | 2026-03-17 10:57 | March | 2026 | 2026-03-18 15:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202510-NM25-04323 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:41 | February | 2026 | 2026-02-23 09:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 42
202510-NM25-04324 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:14 | March | 2026 | 2026-03-04 13:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 29
202510-NM25-04351 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:25 | February | 2026 | 2026-02-16 12:50 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 57
202510-NM25-04358 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:55 | February | 2026 | 2026-03-02 10:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202510-NM25-04363 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 15:12 | February | 2026 | 2026-02-17 09:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 48
202510-NM25-04367 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 12:13 | March | 2026 | 2026-03-09 15:48 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 22
202510-NM25-04376 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:48 | February | 2026 | 2026-02-20 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 43
202511-NM25-00004 | GDL17 | Residencial | 3.84 | Period | 2026-02-16 14:49 | February | 2026 | 2026-02-19 12:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202511-NM25-00012 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:54 | February | 2026 | 2026-02-20 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 43
202511-NM25-00014 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 21:18 | February | 2026 | 2026-02-27 09:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202511-NM25-00018 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-21 16:06 | November | 2025 | 2026-01-05 14:03 | 45 | Study | Estudio (E) | Activated | Backlog |  | No | 45 |  | MAYAGUEZ | January |  | 45 | 0 | 2026-04-01 | 130
202511-NM25-00023 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:37 | January | 2026 | 2026-01-26 15:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 69
202511-NM25-00026 | GDL17 | Residencial | 11.4 | Period | 2026-02-05 18:29 | February | 2026 | 2026-02-11 09:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 54
202511-NM25-00031 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-11 09:49 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 141
202511-NM25-00041 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 05:57 | February | 2026 | 2026-02-27 10:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 35
202511-NM25-00055 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-10 15:20 | November | 2025 | 2026-02-06 11:17 | 88 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | February | 1 | 2 | 86 | 2026-04-01 | 141
202511-NM25-00063 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 10:00 | November | 2025 | 2026-01-05 12:42 | 46 | Study | Estudio (E) | Activated | Backlog |  | No | 46 |  | MAYAGUEZ | January |  | 46 | 0 | 2026-04-01 | 132
202511-NM25-00079 | GDL17 | Residencial | 11.5 | Period | 2026-03-01 15:27 | March | 2026 | 2026-03-04 09:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 30
202511-NM25-00089 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 09:59 | November | 2025 | 2026-01-16 08:24 | 74 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 1 | 65 | 9 | 2026-04-01 | 149
202511-NM25-00099 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:28 | December | 2025 | 2026-01-08 11:09 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 91
202511-NM25-00111 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 09:18 | January | 2026 | 2026-02-03 13:15 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 72
202511-NM25-00114 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-11 09:08 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 141
202511-NM25-00127 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:56 | February | 2026 | 2026-02-27 14:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202511-NM25-00158 | GDL17 | Residencial | 4.392 | Period | 2026-01-14 08:26 | January | 2026 | 2026-01-16 13:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 77
202511-NM25-00172 | GDL17 | Residencial | 3.84 | Out of period | 2025-11-19 10:19 | November | 2025 | 2026-01-07 08:14 | 49 | Study | Estudio (E) | Activated | Backlog |  | No | 49 |  | MAYAGUEZ | January |  | 48 | 0 | 2026-04-01 | 133
202511-NM25-00176 | GDL17 | Residencial | 7.68 | Period | 2026-01-08 13:30 | January | 2026 | 2026-01-14 14:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 82
202511-NM25-00180 | GDL17 | Residencial | 3.072 | Out of period | 2025-11-11 14:41 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 147 | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 140
202511-NM25-00193 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 15:17 | November | 2025 | 2026-02-04 09:25 | 93 | Study | Estudio (E) | Activated | Backlog |  | No | 93 |  | BAYAMON | February |  | 93 | 0 | 2026-04-01 | 148
202511-NM25-00195 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 15:30 | November | 2025 | 2026-01-02 14:35 | 60 | Study | Estudio (E) | Activated | Backlog |  | No | 60 |  | MAYAGUEZ | January |  | 60 | 0 | 2026-04-01 | 148
202511-NM25-00212 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-24 13:46 | December | 2025 | 2026-02-02 09:11 | 40 | Study | Estudio (E) | Activated | Backlog |  | No | 40 |  | BAYAMON | February |  | 40 | 0 | 2026-04-01 | 97
202511-NM25-00217 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 11:21 | February | 2026 | 2026-02-25 09:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-00218 | GDL17 | Residencial | 8.448 | Period | 2026-02-17 18:08 | February | 2026 | 2026-02-23 15:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-00219 | GDL17 | Residencial | 5.76 | Out of period | 2025-11-14 12:23 | November | 2025 | 2026-03-26 16:05 | 132 | Study | Estudio (E) | Activated | Backlog |  | No | 132 |  | PONCE | March |  | 132 | 0 | 2026-04-01 | 137
202511-NM25-00222 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 16:06 | February | 2026 | 2026-02-06 11:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 56
202511-NM25-00227 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-03 16:45 | November | 2025 | 2026-01-16 08:56 | 74 | Study | Estudio (E) | Activated | Backlog |  | No | 74 |  | BAYAMON | January |  | 74 | 0 | 2026-04-01 | 148
202511-NM25-00230 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:23 | March | 2026 | 2026-03-27 15:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 7
202511-NM25-00239 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-08 13:31 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 113
202511-NM25-00240 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-19 15:08 | November | 2025 | 2026-01-23 09:19 | 65 | Study | Estudio (E) | Activated | Backlog |  | No | 65 |  | ARECIBO | January |  | 65 | 0 | 2026-04-01 | 132
202511-NM25-00250 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 02:27 | January | 2026 | 2026-01-20 08:22 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 18 | 0 | 2026-04-01 | 89
202511-NM25-00261 | GDL17 | Comercial | 11.4 | Out of period | 2025-11-18 09:12 | November | 2025 | 2026-01-15 15:37 | 58 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 57 | 1 | 2026-04-01 | 134
202511-NM25-00263 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 08:54 | March | 2026 | 2026-03-09 09:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 3 | 1 | 2026-04-01 | 27
202511-NM25-00283 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:19 | February | 2026 | 2026-02-06 15:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 56
202511-NM25-00285 | GDL17 | Residencial | 3.5 | Out of period | 2025-11-05 20:52 | November | 2025 | 2026-01-02 16:15 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | MAYAGUEZ | January |  | 58 | 0 | 2026-04-01 | 146
202511-NM25-00289 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-04 09:29 | November | 2025 | 2026-01-15 13:41 | 72 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 71 | 1 | 2026-04-01 | 148
202511-NM25-00302 | GDL17 | Residencial | 11.5 | Period | 2026-03-01 19:11 | March | 2026 | 2026-03-13 12:51 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 4 | 8 | 2026-04-01 | 30
202511-NM25-00304 | GDL17 | Residencial | 7.6 | Period | 2026-02-16 12:06 | February | 2026 | 2026-02-23 10:34 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 43
202511-NM25-00324 | GDL17 | Comercial | 11.5 | Period | 2026-03-06 11:00 | March | 2026 | 2026-03-11 08:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 26
202511-NM25-00334 | GDL17 | Residencial | 3.5 | Period | 2026-02-02 08:47 | February | 2026 | 2026-02-16 13:35 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 14 | 0 | 2026-04-01 | 58
202511-NM25-00354 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:11 | February | 2026 | 2026-02-24 07:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-00358 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 14:38 | January | 2026 | 2026-03-02 08:33 | 46 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 46 | 0 | 2026-04-01 | 75
202511-NM25-00359 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:28 | February | 2026 | 2026-02-26 08:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 37
202511-NM25-00360 | GDL17 | Residencial | 23 | Period | 2026-02-20 14:24 | February | 2026 | 2026-02-25 15:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202511-NM25-00383 | GDL17 | Residencial | 23 | Period | 2026-02-18 16:09 | February | 2026 | 2026-02-24 10:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-00393 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:49 | February | 2026 | 2026-02-18 10:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-00396 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:06 | February | 2026 | 2026-02-25 11:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-00401 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 18:21 | February | 2026 | 2026-02-11 14:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202511-NM25-00404 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:57 | February | 2026 | 2026-02-24 14:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 40
202511-NM25-00409 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-04 16:21 | November | 2025 | 2026-02-04 13:40 | 92 | Study | Estudio (E) | Activated | Backlog |  | No | 92 |  | SAN JUAN | February |  | 92 | 0 | 2026-04-01 | 147
202511-NM25-00410 | GDL17 | Residencial | 23 | Period | 2026-02-18 16:14 | February | 2026 | 2026-02-24 07:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-00412 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 23:56 | November | 2025 | 2026-01-05 12:55 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | MAYAGUEZ | January |  | 56 | 0 | 2026-04-01 | 141
202511-NM25-00415 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:13 | February | 2026 | 2026-02-17 15:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 48
202511-NM25-00424 | GDL17 | Residencial | 15 | Out of period | 2025-11-07 06:25 | November | 2025 | 2026-01-14 10:51 | 68 | Study | Estudio (E) | Activated | Backlog |  | No | 68 |  | BAYAMON | January |  | 69 | 0 | 2026-04-01 | 145
202511-NM25-00425 | GDL17 | Residencial | 12 | Out of period | 2025-11-13 13:17 | November | 2025 | 2026-01-16 14:14 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | SAN JUAN | January |  | 64 | 0 | 2026-04-01 | 138
202511-NM25-00426 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:12 | March | 2026 | 2026-03-18 17:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 18
202511-NM25-00428 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 18:09 | February | 2026 | 2026-03-03 11:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 33
202511-NM25-00430 | GDL17 | Comercial | 7.68 | Period | 2026-02-18 02:21 | February | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 42
202511-NM25-00431 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:14 | February | 2026 | 2026-02-09 14:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 57
202511-NM25-00439 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:35 | February | 2026 | 2026-03-03 15:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202511-NM25-00440 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:38 | February | 2026 | 2026-02-27 09:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202511-NM25-00442 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-04 18:18 | November | 2025 | 2026-01-20 16:18 | 77 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 77 | 0 | 2026-04-01 | 147
202511-NM25-00444 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:41 | February | 2026 | 2026-02-24 07:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-00446 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 16:58 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 81
202511-NM25-00449 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-06 11:51 | November | 2025 | 2026-03-09 14:24 | 123 | Study | Estudio (E) | Activated | Backlog |  | No | 123 |  | ARECIBO | March |  | 123 | 0 | 2026-04-01 | 146
202511-NM25-00455 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-05 13:51 | November | 2025 | 2026-01-26 13:43 | 82 | Study | Estudio (E) | Activated | Backlog |  | No | 82 |  | MAYAGUEZ | January |  | 82 | 0 | 2026-04-01 | 146
202511-NM25-00470 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:56 | January | 2026 | 2026-01-30 08:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 63
202511-NM25-00502 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:40 | February | 2026 | 2026-02-23 10:52 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 18 | 0 | 2026-04-01 | 55
202511-NM25-00514 | GDL17 | Residencial | 3.84 | Out of period | 2025-11-13 14:30 | November | 2025 | 2026-01-27 07:53 | 75 | Study | Estudio (E) | Activated | Backlog |  | No | 75 |  | BAYAMON | January |  | 75 | 0 | 2026-04-01 | 138
202511-NM25-00519 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-05 10:55 | November | 2025 | 2026-01-16 13:18 | 72 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 2 | 31 | 41 | 2026-04-01 | 147
202511-NM25-00522 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:31 | February | 2026 | 2026-02-23 14:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 41
202511-NM25-00529 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-05 11:19 | November | 2025 | 2026-01-23 09:04 | 79 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January |  | 79 | 3 | 2026-04-01 | 147
202511-NM25-00530 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:23 | January | 2026 | 2026-02-02 13:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202511-NM25-00534 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:43 | January | 2026 | 2026-01-26 15:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 69
202511-NM25-00539 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:15 | February | 2026 | 2026-02-24 08:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 42
202511-NM25-00542 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 12:51 | November | 2025 | 2026-03-26 15:32 | 136 | Study | Estudio (E) | Activated | Backlog |  | No | 136 |  | CAGUAS | March |  | 136 | 0 | 2026-04-01 | 141
202511-NM25-00550 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 18:24 | March | 2026 | 2026-03-12 15:40 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 9 | 0 | 2026-04-01 | 28
202511-NM25-00551 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:31 | January | 2026 | 2026-01-26 15:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 69
202511-NM25-00555 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 19:05 | February | 2026 | 2026-02-23 15:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-00557 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-05 12:46 | November | 2025 | 2026-01-16 09:15 | 72 | Study | Estudio (E) | Activated | Backlog |  | No | 72 |  | BAYAMON | January |  | 72 | 0 | 2026-04-01 | 146
202511-NM25-00558 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:14 | January | 2026 | 2026-02-03 15:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 61
202511-NM25-00560 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:23 | February | 2026 | 2026-02-20 08:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202511-NM25-00562 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:33 | January | 2026 | 2026-02-02 15:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202511-NM25-00573 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-19 15:06 | November | 2025 | 2026-01-19 13:40 | 61 | Study | Estudio (E) | Activated | Backlog |  | No | 61 |  | ARECIBO | January |  | 61 | 0 | 2026-04-01 | 132
202511-NM25-00579 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 12:57 | January | 2026 | 2026-02-04 08:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 60
202511-NM25-00595 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-05 15:44 | November | 2025 | 2026-01-26 15:59 | 82 | Study | Estudio (E) | Activated | Backlog |  | No | 82 |  | MAYAGUEZ | January |  | 82 | 0 | 2026-04-01 | 146
202511-NM25-00604 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:06 | February | 2026 | 2026-02-23 14:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202511-NM25-00605 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:57 | February | 2026 | 2026-02-24 14:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-00611 | GDL17 | Residencial | 23 | Period | 2026-02-12 13:58 | February | 2026 | 2026-02-16 14:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202511-NM25-00622 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:53 | February | 2026 | 2026-02-25 09:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 40
202511-NM25-00632 | GDL17 | Residencial | 12.288 | Period | 2026-02-20 13:12 | February | 2026 | 2026-02-25 15:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 39
202511-NM25-00633 | GDL17 | Comercial | 3.8 | Out of period | 2025-11-18 14:52 | November | 2025 | 2026-01-15 15:11 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | ARECIBO | January |  | 58 | 0 | 2026-04-01 | 133
202511-NM25-00637 | GDL17 | Comercial | 11.5 | Period | 2026-03-05 12:15 | March | 2026 | 2026-03-06 15:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 26
202511-NM25-00639 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 07:02 | January | 2026 | 2026-01-19 10:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 77
202511-NM25-00640 | GDL17 | Residencial | 3.8 | Period | 2026-02-23 09:34 | February | 2026 | 2026-02-26 08:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 37
202511-NM25-00643 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:35 | February | 2026 | 2026-02-25 09:39 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 42
202511-NM25-00646 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 12:04 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 4
202511-NM25-00647 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:47 | February | 2026 | 2026-02-25 08:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202511-NM25-00661 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:37 | February | 2026 | 2026-03-02 13:00 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 18 | 0 | 2026-04-01 | 48
202511-NM25-00667 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:53 | March | 2026 | 2026-03-25 15:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 9
202511-NM25-00680 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-12 09:51 | November | 2025 | 2026-01-15 12:58 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | SAN JUAN | January |  | 65 | 0 | 2026-04-01 | 140
202511-NM25-00685 | GDL17 | Residencial | 10 | Period | 2026-03-03 15:11 | March | 2026 | 2026-03-05 15:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 28
202511-NM25-00686 | GDL17 | Residencial | 9.984 | Period | 2026-01-15 08:35 | January | 2026 | 2026-01-16 16:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202511-NM25-00689 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:49 | February | 2026 | 2026-02-17 08:09 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 57
202511-NM25-00701 | GDL17 | Residencial | 15.2 | Out of period | 2025-11-13 08:41 | November | 2025 | 2026-01-21 13:57 | 69 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 2 | 3 | 66 | 2026-04-01 | 139
202511-NM25-00710 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-06 13:04 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 166 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 145
202511-NM25-00720 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-18 08:40 | November | 2025 | 2026-01-07 11:13 | 50 | Study | Estudio (E) | Activated | Backlog |  | No | 50 |  | BAYAMON | January |  | 51 | 0 | 2026-04-01 | 134
202511-NM25-00744 | GDL17 | Residencial | 6.144 | Out of period | 2025-11-06 14:33 | November | 2025 | 2026-02-06 11:11 | 92 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 1 | 2 | 90 | 2026-04-01 | 145
202511-NM25-00753 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:02 | January | 2026 | 2026-02-16 13:14 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 65
202511-NM25-00754 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:02 | February | 2026 | 2026-02-13 09:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 48
202511-NM25-00756 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:23 | January | 2026 | 2026-01-14 11:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 83
202511-NM25-00765 | GDL17 | Residencial | 4.992 | Period | 2026-01-30 14:56 | January | 2026 | 2026-02-03 15:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 60
202511-NM25-00780 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:06 | February | 2026 | 2026-02-26 15:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 41
202511-NM25-00784 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-24 12:14 | December | 2025 | 2026-02-24 15:34 | 62 | Study | Estudio (E) | Activated | Backlog |  | No | 62 |  | PONCE | February |  | 62 | 0 | 2026-04-01 | 97
202511-NM25-00788 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 19:10 | January | 2026 | 2026-02-27 14:48 | 43 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | February |  | 43 | 0 | 2026-04-01 | 75
202511-NM25-00789 | GDL17 | Residencial | 3.8 | Period | 2026-01-29 14:29 | January | 2026 | 2026-02-11 13:30 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 13 | 0 | 2026-04-01 | 61
202511-NM25-00791 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 18:57 | February | 2026 | 2026-03-02 10:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202511-NM25-00816 | GDL17 | Residencial | 11.346 | Period | 2026-02-02 11:41 | February | 2026 | 2026-02-09 12:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 58
202511-NM25-00819 | GDL17 | Residencial | 8 | Out of period | 2025-11-17 21:24 | November | 2025 | 2026-01-15 14:36 | 59 | Study | Estudio (E) | Activated | Backlog |  | No | 59 |  | MAYAGUEZ | January |  | 59 | 0 | 2026-04-01 | 134
202511-NM25-00822 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 11:56 | March | 2026 | 2026-03-30 10:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 8
202511-NM25-00825 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:29 | February | 2026 | 2026-02-25 16:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 41
202511-NM25-00827 | GDL17 | Residencial | 15.2 | Period | 2026-02-18 14:44 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 41
202511-NM25-00840 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-07 10:18 | November | 2025 | 2026-02-18 14:30 | 103 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 7 | 96 | 2026-04-01 | 145
202511-NM25-00846 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:32 | February | 2026 | 2026-02-23 14:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202511-NM25-00853 | GDL17 | Residencial | 4.992 | Out of period | 2025-11-26 13:05 | November | 2025 | 2026-01-20 11:05 | 55 | Study | Estudio (E) | Activated | Backlog |  | No | 55 |  | CAGUAS | January |  | 55 | 0 | 2026-04-01 | 125
202511-NM25-00872 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:18 | March | 2026 | 2026-03-06 13:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 27
202511-NM25-00876 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:51 | February | 2026 | 2026-02-25 09:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 41
202511-NM25-00879 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 17:28 | February | 2026 | 2026-02-16 13:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202511-NM25-00882 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:03 | February | 2026 | 2026-02-25 07:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-00884 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:32 | February | 2026 | 2026-02-27 09:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 35
202511-NM25-00886 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 18:14 | February | 2026 | 2026-02-24 07:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-00900 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:17 | February | 2026 | 2026-03-02 08:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 40
202511-NM25-00918 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 17:04 | February | 2026 | 2026-02-24 13:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-00919 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 09:58 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 30
202511-NM25-00920 | GDL17 | Residencial | 8 | Out of period | 2025-11-11 17:22 | November | 2025 | 2026-01-20 15:26 | 70 | Study | Estudio (E) | Activated | Backlog |  | No | 70 |  | MAYAGUEZ | January |  | 70 | 0 | 2026-04-01 | 140
202511-NM25-00924 | GDL17 | Residencial | 11.5 | Period | 2026-01-01 19:26 | January | 2026 | 2026-01-12 10:05 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 11 | 0 | 2026-04-01 | 89
202511-NM25-00928 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-07 14:45 | November | 2025 | 2026-03-19 12:54 | 132 | Study | Estudio (E) | Activated | Backlog |  | No | 132 |  | BAYAMON | March |  | 132 | 0 | 2026-04-01 | 144
202511-NM25-00950 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 07:50 | March | 2026 | 2026-03-23 14:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 15
202511-NM25-00954 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 19:08 | February | 2026 | 2026-02-10 14:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202511-NM25-00966 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:39 | February | 2026 | 2026-03-02 12:41 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 12 | 0 | 2026-04-01 | 41
202511-NM25-00968 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:30 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 36
202511-NM25-00977 | GDL17 | Residencial | 17.2 | Period | 2026-02-27 10:16 | February | 2026 | 2026-03-03 09:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202511-NM25-00980 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-07 17:08 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 144
202511-NM25-00982 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-07 16:11 | November | 2025 | 2026-01-13 09:55 | 67 | Study | Estudio (E) | Activated | Backlog |  | No | 67 |  | MAYAGUEZ | January |  | 67 | 0 | 2026-04-01 | 144
202511-NM25-00983 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-10 08:16 | November | 2025 | 2026-01-02 10:42 | 53 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 10 | 43 | 2026-04-01 | 142
202511-NM25-00991 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 13:14 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 33
202511-NM25-00993 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 17:48 | March | 2026 | 2026-04-07 14:20 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 12 | 0 | 2026-04-01 | 5
202511-NM25-00994 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 10:21 | February | 2026 | 2026-02-20 13:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 43
202511-NM25-00998 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:35 | March | 2026 | 2026-03-11 10:00 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 27
202511-NM25-01007 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 19:17 | February | 2026 | 2026-02-11 14:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 50
202511-NM25-01008 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 21:07 | January | 2026 | 2026-01-13 13:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202511-NM25-01012 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:31 | March | 2026 | 2026-04-01 14:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 2 | 0 | 2026-04-01 | 2
202511-NM25-01019 | GDL17 | Residencial | 9 | Out of period | 2025-11-17 15:51 | November | 2025 | 2026-01-29 15:47 | 73 | Study | Estudio (E) | Activated | Backlog |  | No | 73 |  | ARECIBO | January |  | 73 | 0 | 2026-04-01 | 134
202511-NM25-01025 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-24 10:19 | November | 2025 | 2026-01-19 09:12 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | PONCE | January |  | 56 | 0 | 2026-04-01 | 128
202511-NM25-01035 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-10 08:59 | November | 2025 | 2026-01-15 14:23 | 66 | Study | Estudio (E) | Activated | Backlog |  | No | 66 |  | SAN JUAN | January |  | 66 | 0 | 2026-04-01 | 142
202511-NM25-01045 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 17:04 | February | 2026 | 2026-03-03 16:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202511-NM25-01055 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 09:43 | November | 2025 | 2026-01-05 13:58 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | MAYAGUEZ | January |  | 57 | 0 | 2026-04-01 | 142
202511-NM25-01056 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-26 08:32 | November | 2025 | 2026-01-14 11:08 | 49 | Study | Estudio (E) | Activated | Backlog |  | No | 49 |  | MAYAGUEZ | January |  | 49 | 0 | 2026-04-01 | 126
202511-NM25-01060 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:20 | February | 2026 | 2026-02-06 14:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 57
202511-NM25-01065 | GDL17 | Residencial | 6.144 | Out of period | 2025-11-11 12:59 | November | 2025 | 2026-01-14 08:49 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | MAYAGUEZ | January |  | 64 | 0 | 2026-04-01 | 140
202511-NM25-01069 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:36 | February | 2026 | 2026-03-04 15:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 33
202511-NM25-01071 | GDL17 | Residencial | 13.44 | Period | 2026-02-18 12:13 | February | 2026 | 2026-02-24 12:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-01073 | GDL17 | Residencial | 15 | Out of period | 2025-11-24 09:48 | November | 2025 | 2026-01-19 09:22 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | PONCE | January |  | 56 | 0 | 2026-04-01 | 128
202511-NM25-01084 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:37 | February | 2026 | 2026-02-18 11:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-01089 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 21:30 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 85
202511-NM25-01108 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 11:38 | November | 2025 | 2026-01-20 10:06 | 71 | Study | Estudio (E) | Activated | Backlog |  | No | 71 |  | MAYAGUEZ | January |  | 71 | 0 | 2026-04-01 | 142
202511-NM25-01117 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:32 | February | 2026 | 2026-03-03 15:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 32
202511-NM25-01128 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:18 | January | 2026 | 2026-01-29 13:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 69
202511-NM25-01130 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 22:41 | February | 2026 | 2026-02-23 09:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-01138 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:32 | January | 2026 | 2026-02-02 09:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 64
202511-NM25-01139 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:45 | February | 2026 | 2026-02-24 14:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202511-NM25-01145 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 17:16 | February | 2026 | 2026-02-23 09:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-01148 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 18:09 | February | 2026 | 2026-02-20 14:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 45
202511-NM25-01150 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 16:11 | February | 2026 | 2026-03-02 10:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202511-NM25-01155 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 18:25 | February | 2026 | 2026-02-18 13:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 47
202511-NM25-01156 | GDL17 | Residencial | 15.93 | Period | 2026-02-06 10:08 | February | 2026 | 2026-02-10 16:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 4 | 0 | 2026-04-01 | 54
202511-NM25-01160 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 16:23 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 83
202511-NM25-01171 | GDL17 | Residencial | 8 | Out of period | 2025-11-19 22:01 | November | 2025 | 2026-01-02 09:33 | 43 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 43 | 1 | 2026-04-01 | 132
202511-NM25-01191 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:36 | January | 2026 |  |  | Create NEM Agreement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 71
202511-NM25-01193 | GDL17 | Residencial | 4.425 | Out of period | 2025-11-10 15:57 | November | 2025 | 2026-01-13 14:02 | 64 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 4 | 9 | 55 | 2026-04-01 | 141
202511-NM25-01194 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 14:20 | November | 2025 | 2026-01-29 13:35 | 70 | Study | Estudio (E) | Activated | Backlog |  | No | 70 |  | BAYAMON | January |  | 70 | 0 | 2026-04-01 | 131
202511-NM25-01195 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:08 | March | 2026 | 2026-03-06 13:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 28
202511-NM25-01213 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:38 | February | 2026 | 2026-02-05 14:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 56
202511-NM25-01218 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-10 15:49 | November | 2025 | 2026-01-16 08:40 | 67 | Study | Estudio (E) | Activated | Backlog |  | No | 67 |  | CAGUAS | January |  | 66 | 0 | 2026-04-01 | 141
202511-NM25-01219 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 19:30 | January | 2026 | 2026-01-20 13:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202511-NM25-01231 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-10 16:05 | November | 2025 | 2026-01-29 14:04 | 80 | Study | Estudio (E) | Activated | Backlog |  | No | 80 |  | CAGUAS | January |  | 80 | 0 | 2026-04-01 | 141
202511-NM25-01237 | GDL17 | Residencial | 23 | Period | 2026-03-03 15:38 | March | 2026 | 2026-03-12 10:12 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 9 | 0 | 2026-04-01 | 28
202511-NM25-01238 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-17 12:05 | November | 2025 | 2026-01-26 13:44 | 70 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 5 | 65 | 2026-04-01 | 134
202511-NM25-01249 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-01 10:06 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 134 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 121
202511-NM25-01282 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:30 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 42
202511-NM25-01284 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-24 11:23 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 129 | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 128
202511-NM25-01286 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:53 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 35
202511-NM25-01312 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:05 | March | 2026 | 2026-03-20 16:17 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 19 | 0 | 2026-04-01 | 30
202511-NM25-01348 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:33 | January | 2026 | 2026-02-20 13:20 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 30 | 0 | 2026-04-01 | 69
202511-NM25-01361 | GDL17 | Residencial | 7.6 | Period | 2026-02-02 14:51 | February | 2026 | 2026-02-12 14:42 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 57
202511-NM25-01363 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:16 | January | 2026 | 2026-01-22 15:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 69
202511-NM25-01364 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:39 | March | 2026 | 2026-03-25 16:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 8
202511-NM25-01423 | GDL17 | Residencial | 23 | Period | 2026-02-17 13:32 | February | 2026 | 2026-02-23 08:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202511-NM25-01430 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:15 | February | 2026 | 2026-02-25 08:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-01434 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:33 | February | 2026 | 2026-02-25 14:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 41
202511-NM25-01446 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 07:39 | February | 2026 | 2026-03-02 14:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202511-NM25-01448 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:15 | March | 2026 | 2026-03-19 14:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202511-NM25-01449 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 12:18 | February | 2026 | 2026-02-10 14:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202511-NM25-01454 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:57 | February | 2026 | 2026-02-25 09:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202511-NM25-01458 | GDL17 | Comercial | 23 | Period | 2026-02-13 13:47 | February | 2026 | 2026-02-18 10:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-01464 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:22 | March | 2026 | 2026-03-05 13:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202511-NM25-01465 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:48 | March | 2026 | 2026-04-13 09:46 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 14 | 0 | 2026-04-01 | 2
202511-NM25-01473 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-11 14:49 | November | 2025 | 2026-01-08 14:00 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | SAN JUAN | January |  | 58 | 0 | 2026-04-01 | 140
202511-NM25-01480 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 19:38 | February | 2026 | 2026-02-26 08:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202511-NM25-01481 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:13 | February | 2026 | 2026-02-24 13:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-01489 | GDL17 | Residencial | 23 | Period | 2026-01-08 14:04 | January | 2026 | 2026-01-13 14:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202511-NM25-01493 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:47 | February | 2026 | 2026-02-25 12:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-01496 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:03 | February | 2026 | 2026-02-27 13:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 36
202511-NM25-01512 | GDL17 | Residencial | 11.5 | Period | 2026-03-01 13:59 | March | 2026 | 2026-03-05 13:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 30
202511-NM25-01518 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 11:57 | February | 2026 | 2026-02-25 10:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-01524 | GDL17 | Residencial | 23 | Period | 2026-01-28 12:38 | January | 2026 | 2026-02-04 13:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 62
202511-NM25-01539 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:08 | February | 2026 | 2026-02-24 07:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-01544 | GDL17 | Residencial | 15.3 | Period | 2026-01-20 09:35 | January | 2026 | 2026-01-21 16:21 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202511-NM25-01546 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 14:26 | January | 2026 | 2026-02-03 12:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 60
202511-NM25-01551 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-12 08:05 | November | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 140
202511-NM25-01553 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-21 14:03 | November | 2025 | 2026-01-22 13:03 | 62 | Study | Estudio (E) | Activated | Backlog |  | No | 62 |  | PONCE | January |  | 62 | 0 | 2026-04-01 | 130
202511-NM25-01565 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-19 15:08 | November | 2025 | 2026-01-16 13:50 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | CAGUAS | January |  | 58 | 0 | 2026-04-01 | 132
202511-NM25-01575 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 13:56 | January | 2026 | 2026-02-02 14:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202511-NM25-01583 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-17 22:07 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 134
202511-NM25-01607 | GDL17 | Residencial | 3.84 | Period | 2026-01-27 07:55 | January | 2026 | 2026-02-16 08:11 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 20 | 0 | 2026-04-01 | 64
202511-NM25-01610 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-21 14:01 | November | 2025 | 2026-01-19 13:13 | 59 | Study | Estudio (E) | Activated | Backlog |  | No | 59 |  | BAYAMON | January |  | 59 | 0 | 2026-04-01 | 130
202511-NM25-01611 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 19:02 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 53
202511-NM25-01628 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:35 | January | 2026 | 2026-01-14 10:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 83
202511-NM25-01632 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:39 | January | 2026 | 2026-01-13 15:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202511-NM25-01633 | GDL17 | Residencial | 3.84 | Period | 2026-01-15 11:44 | January | 2026 | 2026-01-20 12:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 76
202511-NM25-01635 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:42 | February | 2026 | 2026-02-26 13:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202511-NM25-01637 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:50 | January | 2026 | 2026-01-13 08:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 83
202511-NM25-01644 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 17:04 | November | 2025 | 2026-01-07 13:56 | 48 | Study | Estudio (E) | Activated | Backlog |  | No | 48 |  | BAYAMON | January |  | 48 | 0 | 2026-04-01 | 131
202511-NM25-01662 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:30 | January | 2026 | 2026-01-26 12:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 70
202511-NM25-01663 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-21 17:02 | November | 2025 | 2026-01-14 14:06 | 54 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 14 | 40 | 2026-04-01 | 130
202511-NM25-01665 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:09 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 70
202511-NM25-01677 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:50 | January | 2026 | 2026-01-29 15:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 63
202511-NM25-01693 | GDL17 | Residencial | 8 | Out of period | 2025-11-17 14:29 | November | 2025 | 2026-01-13 10:23 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | MAYAGUEZ | January |  | 57 | 0 | 2026-04-01 | 134
202511-NM25-01702 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:43 | January | 2026 | 2026-01-22 13:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 70
202511-NM25-01724 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 12:01 | January | 2026 | 2026-01-19 14:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202511-NM25-01726 | GDL17 | Residencial | 7.6 | Period | 2026-02-18 09:26 | February | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 42
202511-NM25-01730 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-12 15:22 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 139
202511-NM25-01735 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 12:22 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 131
202511-NM25-01740 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:25 | March | 2026 | 2026-03-30 14:46 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 25 | 0 | 2026-04-01 | 26
202511-NM25-01742 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:00 | February | 2026 | 2026-02-20 13:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 43
202511-NM25-01743 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:14 | February | 2026 | 2026-02-27 16:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202511-NM25-01752 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-12 18:16 | November | 2025 | 2026-01-20 12:55 | 69 | Study | Estudio (E) | Activated | Backlog |  | No | 69 |  | MAYAGUEZ | January |  | 69 | 0 | 2026-04-01 | 139
202511-NM25-01754 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:30 | February | 2026 | 2026-02-17 09:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202511-NM25-01755 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 17:09 | February | 2026 | 2026-02-27 09:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 35
202511-NM25-01758 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:05 | February | 2026 | 2026-02-24 08:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-01760 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:27 | February | 2026 | 2026-02-18 10:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-01762 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:29 | February | 2026 | 2026-02-18 11:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-01767 | GDL17 | Residencial | 7.6 | Period | 2026-02-18 12:03 | February | 2026 | 2026-02-23 14:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 41
202511-NM25-01770 | GDL17 | Residencial | 3.3 | Period | 2026-02-20 01:08 | February | 2026 | 2026-02-25 09:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202511-NM25-01772 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:03 | February | 2026 | 2026-02-23 12:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 44
202511-NM25-01775 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:23 | February | 2026 | 2026-03-04 10:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 34
202511-NM25-01780 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 17:24 | January | 2026 | 2026-01-16 13:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 81
202511-NM25-01782 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 16:03 | February | 2026 | 2026-02-23 13:49 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 11 | 0 | 2026-04-01 | 47
202511-NM25-01789 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:43 | February | 2026 | 2026-02-23 09:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-01790 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:26 | February | 2026 | 2026-02-18 14:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-01803 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-24 10:21 | November | 2025 | 2026-01-02 13:18 | 39 | Study | Estudio (E) | Activated | Backlog |  | No | 39 |  | MAYAGUEZ | January |  | 39 | 0 | 2026-04-01 | 128
202511-NM25-01822 | GDL17 | Comercial | 12 | Period | 2026-03-03 11:47 | March | 2026 | 2026-03-26 16:24 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 20 | 0 | 2026-04-01 | 29
202511-NM25-01827 | GDL17 | Comercial | 12 | Period | 2026-03-03 12:47 | March | 2026 | 2026-03-05 09:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 28
202511-NM25-01832 | GDL17 | Residencial | 16.492 | Out of period | 2025-11-20 15:51 | November | 2025 | 2026-01-16 16:23 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | CAGUAS | January |  | 57 | 0 | 2026-04-01 | 131
202511-NM25-01839 | GDL17 | Residencial | 15 | Period | 2026-01-23 12:51 | January | 2026 | 2026-01-28 16:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 67
202511-NM25-01841 | GDL17 | Residencial | 10 | Period | 2026-02-23 10:09 | February | 2026 | 2026-03-06 09:09 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 10 | 0 | 2026-04-01 | 37
202511-NM25-01859 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-17 12:49 | November | 2025 | 2026-01-02 14:19 | 46 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | January | 1 | 9 | 37 | 2026-04-01 | 134
202511-NM25-01873 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:37 | February | 2026 | 2026-02-24 15:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-01891 | GDL17 | Residencial | 11.5 | Period | 2026-03-01 16:58 | March | 2026 | 2026-03-12 14:13 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 30
202511-NM25-01894 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-13 12:31 | November | 2025 | 2026-01-02 13:56 | 50 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 1 | 14 | 36 | 2026-04-01 | 138
202511-NM25-01897 | GDL17 | Residencial | 10 | Out of period | 2025-11-14 21:22 | November | 2025 | 2026-03-03 11:15 | 109 | Study | Estudio (E) | Activated | Backlog |  | No | 109 |  | SAN JUAN | March |  | 108 | 0 | 2026-04-01 | 137
202511-NM25-01899 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:06 | February | 2026 | 2026-02-06 10:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202511-NM25-01905 | GDL17 | Residencial | 3.8 | Period | 2026-01-29 14:59 | January | 2026 | 2026-02-04 08:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 61
202511-NM25-01908 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 15:25 | January | 2026 | 2026-01-16 14:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 76
202511-NM25-01909 | GDL17 | Residencial | 11.5 | Period | 2026-02-22 16:25 | February | 2026 | 2026-02-27 13:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 37
202511-NM25-01912 | GDL17 | Residencial | 16.128 | Out of period | 2025-11-13 13:54 | November | 2025 | 2026-01-16 09:20 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | SAN JUAN | January |  | 64 | 0 | 2026-04-01 | 138
202511-NM25-01916 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-26 10:08 | November | 2025 | 2026-01-20 14:13 | 55 | Study | Estudio (E) | Activated | Backlog |  | No | 55 |  | SAN JUAN | January |  | 55 | 0 | 2026-04-01 | 126
202511-NM25-01921 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 08:16 | November | 2025 | 2026-02-10 12:48 | 82 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 17 | 65 | 2026-04-01 | 132
202511-NM25-01922 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:12 | February | 2026 | 2026-02-04 10:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202511-NM25-01927 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:59 | January | 2026 | 2026-01-22 15:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202511-NM25-01929 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:59 | February | 2026 | 2026-02-19 10:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 43
202511-NM25-01935 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:07 | February | 2026 | 2026-02-04 15:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202511-NM25-01936 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:21 | February | 2026 | 2026-02-25 15:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 39
202511-NM25-01938 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 14:28 | February | 2026 | 2026-02-25 15:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-01946 | GDL17 | Residencial | 12 | Period | 2026-01-07 11:32 | January | 2026 | 2026-01-13 08:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 84
202511-NM25-01953 | GDL17 | Residencial | 16.104 | Period | 2026-03-17 17:00 | March | 2026 | 2026-03-18 15:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 14
202511-NM25-01954 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:31 | February | 2026 | 2026-02-25 15:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202511-NM25-01963 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-13 18:05 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 138
202511-NM25-01977 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:09 | February | 2026 | 2026-02-23 10:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 6 | 1 | 2026-04-01 | 44
202511-NM25-01979 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:18 | February | 2026 | 2026-02-13 10:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202511-NM25-01982 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 21:47 | February | 2026 | 2026-02-25 14:39 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 12 | 0 | 2026-04-01 | 46
202511-NM25-01984 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:25 | February | 2026 | 2026-02-24 13:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-01999 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-21 12:41 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 130
202511-NM25-02006 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:07 | January | 2026 | 2026-01-13 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202511-NM25-02021 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-14 10:26 | November | 2025 | 2026-02-23 10:16 | 101 | Study | Estudio (E) | Activated | Backlog |  | No | 101 |  | MAYAGUEZ | February |  | 101 | 0 | 2026-04-01 | 138
202511-NM25-02055 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 18:16 | February | 2026 | 2026-02-25 14:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-02058 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 08:49 | January | 2026 | 2026-01-26 10:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 70
202511-NM25-02066 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:30 | February | 2026 | 2026-02-10 09:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 56
202511-NM25-02068 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:15 | February | 2026 | 2026-02-26 13:46 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 42
202511-NM25-02086 | GDL17 | Comercial | 21.228 | Out of period | 2025-12-03 07:39 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 119
202511-NM25-02093 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-14 16:12 | November | 2025 | 2026-01-21 10:01 | 68 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | January | 2 | 37 | 1 | 2026-04-01 | 137
202511-NM25-02097 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:08 | February | 2026 | 2026-02-27 16:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 40
202511-NM25-02100 | GDL17 | Residencial | 7.6 | Period | 2026-02-17 09:11 | February | 2026 | 2026-02-20 13:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 43
202511-NM25-02102 | GDL17 | Residencial | 3.84 | Period | 2026-02-23 15:40 | February | 2026 | 2026-03-03 09:04 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 36
202511-NM25-02115 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-14 16:02 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 137
202511-NM25-02117 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:32 | February | 2026 | 2026-02-04 16:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202511-NM25-02122 | GDL17 | Residencial | 10.752 | Period | 2026-02-03 11:52 | February | 2026 | 2026-02-05 16:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202511-NM25-02123 | GDL17 | Comercial | 23 | Period | 2026-02-19 11:22 | February | 2026 | 2026-02-24 14:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202511-NM25-02127 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-11 13:00 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 110
202511-NM25-02128 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:21 | February | 2026 | 2026-03-03 15:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 33
202511-NM25-02131 | GDL17 | Residencial | 10 | Out of period | 2025-11-19 20:30 | November | 2025 | 2026-01-02 08:29 | 43 | Study | Estudio (E) | Activated | Backlog |  | No | 43 |  | MAYAGUEZ | January |  | 44 | 0 | 2026-04-01 | 132
202511-NM25-02137 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 18:43 | January | 2026 | 2026-02-03 10:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 61
202511-NM25-02141 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 11:50 | February | 2026 | 2026-02-04 15:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 58
202511-NM25-02149 | GDL17 | Residencial | 6.8 | Period | 2026-02-17 20:29 | February | 2026 | 2026-02-24 14:45 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 42
202511-NM25-02162 | GDL17 | Residencial | 8 | Out of period | 2025-12-01 16:23 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 120
202511-NM25-02165 | GDL17 | Residencial | 13.6 | Period | 2026-02-02 13:11 | February | 2026 | 2026-02-05 10:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 57
202511-NM25-02172 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:10 | February | 2026 | 2026-03-04 15:49 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 39
202511-NM25-02175 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 08:57 | March | 2026 | 2026-03-17 16:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202511-NM25-02190 | GDL17 | Residencial | 5.376 | Out of period | 2025-12-18 12:03 | December | 2025 | 2026-02-02 13:33 | 46 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | February | 1 | 8 | 38 | 2026-04-01 | 103
202511-NM25-02194 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-17 08:53 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 135
202511-NM25-02207 | GDL17 | Residencial | 4.992 | Period | 2026-01-23 09:28 | January | 2026 | 2026-01-26 12:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 68
202511-NM25-02209 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-17 09:33 | November | 2025 | 2026-01-22 15:40 | 66 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 45 | 21 | 2026-04-01 | 135
202511-NM25-02214 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 17:51 | February | 2026 | 2026-02-19 07:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 45
202511-NM25-02220 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:04 | March | 2026 | 2026-03-23 15:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 14
202511-NM25-02234 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 19:21 | January | 2026 | 2026-01-16 14:28 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 82
202511-NM25-02238 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:16 | February | 2026 | 2026-02-20 09:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202511-NM25-02247 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 11:33 | January | 2026 | 2026-01-26 14:00 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 20 | 0 | 2026-04-01 | 85
202511-NM25-02257 | GDL17 | Residencial | 3.8 | Period | 2026-02-19 13:10 | February | 2026 | 2026-02-25 11:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-02258 | GDL17 | Residencial | 5 | Period | 2026-01-09 09:14 | January | 2026 | 2026-01-14 13:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202511-NM25-02263 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-17 13:16 | November | 2025 |  |  | Create NEM Agreement | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 134
202511-NM25-02266 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:46 | February | 2026 | 2026-02-27 10:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202511-NM25-02268 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 19:00 | February | 2026 | 2026-03-03 14:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 35
202511-NM25-02269 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:05 | February | 2026 | 2026-03-02 08:20 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 12 | 0 | 2026-04-01 | 41
202511-NM25-02271 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-17 12:15 | November | 2025 | 2026-01-13 08:47 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | MAYAGUEZ | January |  | 57 | 0 | 2026-04-01 | 134
202511-NM25-02288 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 17:30 | February | 2026 | 2026-02-24 07:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-02298 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:25 | February | 2026 | 2026-03-02 14:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 39
202511-NM25-02301 | GDL17 | Residencial | 3.8 | Period | 2026-02-10 11:26 | February | 2026 | 2026-02-11 11:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 50
202511-NM25-02306 | GDL17 | Residencial | 14.64 | Out of period | 2025-12-05 12:46 | December | 2025 | 2026-02-05 15:25 | 62 | Study | Estudio (E) | Activated | Backlog |  | No | 62 |  | CAGUAS | February |  | 62 | 0 | 2026-04-01 | 116
202511-NM25-02308 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-21 07:38 | November | 2025 | 2026-01-19 10:37 | 59 | Study | Estudio (E) | Activated | Backlog |  | No | 59 |  | CAGUAS | January |  | 60 | 0 | 2026-04-01 | 131
202511-NM25-02316 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-17 14:35 | November | 2025 | 2026-01-02 08:09 | 46 | Study | Estudio (E) | Activated | Backlog |  | No | 46 |  | MAYAGUEZ | January |  | 45 | 0 | 2026-04-01 | 134
202511-NM25-02319 | GDL17 | Residencial | 8 | Out of period | 2025-11-20 08:53 | November | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 132
202511-NM25-02347 | GDL17 | Residencial | 11.5 | Period | 2026-02-22 13:01 | February | 2026 | 2026-02-26 08:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 37
202511-NM25-02360 | GDL17 | Residencial | 11.5 | Period | 2026-02-15 12:53 | February | 2026 | 2026-02-18 14:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 44
202511-NM25-02368 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 19:01 | December | 2025 | 2026-02-04 11:16 | 49 | Study | Estudio (E) | Activated | Backlog |  | No | 49 |  | ARECIBO | February |  | 49 | 0 | 2026-04-01 | 104
202511-NM25-02378 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 11:09 | February | 2026 | 2026-02-23 09:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 42
202511-NM25-02384 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:29 | March | 2026 | 2026-04-06 09:22 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 10 | 0 | 2026-04-01 | 5
202511-NM25-02387 | GDL17 | Residencial | 23 | Period | 2026-01-29 12:59 | January | 2026 | 2026-02-04 09:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 61
202511-NM25-02393 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:58 | February | 2026 | 2026-02-25 14:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-02399 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 21:26 | January | 2026 | 2026-02-04 09:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 60
202511-NM25-02408 | GDL17 | Residencial | 15 | Period | 2026-01-07 15:21 | January | 2026 | 2026-02-10 10:14 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | February | 2 | 7 | 27 | 2026-04-01 | 83
202511-NM25-02418 | GDL17 | Residencial | 3.8 | Period | 2026-03-03 19:13 | March | 2026 | 2026-03-05 09:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 28
202511-NM25-02421 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 20:11 | February | 2026 | 2026-02-23 12:43 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 10 | 0 | 2026-04-01 | 46
202511-NM25-02428 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 11:58 | February | 2026 | 2026-02-10 15:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 54
202511-NM25-02429 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:26 | February | 2026 | 2026-02-05 14:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202511-NM25-02435 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:09 | February | 2026 | 2026-02-27 10:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202511-NM25-02447 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 08:43 | January | 2026 | 2026-01-22 14:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202511-NM25-02460 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-18 08:29 | November | 2025 | 2026-01-21 13:28 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | MAYAGUEZ | January |  | 65 | 0 | 2026-04-01 | 134
202511-NM25-02468 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:55 | February | 2026 | 2026-02-18 08:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 49
202511-NM25-02479 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 08:37 | January | 2026 | 2026-01-26 13:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 69
202511-NM25-02480 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-18 08:36 | November | 2025 | 2026-03-12 11:12 | 114 | Study | Estudio (E) | Activated | Backlog |  | No | 114 |  | MAYAGUEZ | March |  | 115 | 0 | 2026-04-01 | 134
202511-NM25-02481 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-21 15:14 | November | 2025 | 2026-01-08 14:45 | 48 | Study | Estudio (E) | Activated | Backlog |  | No | 48 |  | CAGUAS | January |  | 48 | 0 | 2026-04-01 | 130
202511-NM25-02482 | GDL17 | Residencial | 10 | Out of period | 2025-12-04 12:41 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 117
202511-NM25-02484 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-18 09:08 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 134
202511-NM25-02490 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:47 | February | 2026 | 2026-02-26 08:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 37
202511-NM25-02492 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 09:08 | January | 2026 | 2026-01-26 09:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 70
202511-NM25-02507 | GDL17 | Comercial | 7.6 | Period | 2026-02-18 09:44 | February | 2026 | 2026-02-23 09:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202511-NM25-02522 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:18 | March | 2026 | 2026-03-20 15:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 14
202511-NM25-02528 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-05 13:46 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 116
202511-NM25-02539 | GDL17 | Residencial | 8.418 | Out of period | 2025-11-21 09:39 | November | 2025 | 2026-01-12 14:21 | 52 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 2 | 14 | 38 | 2026-04-01 | 131
202511-NM25-02558 | GDL17 | Residencial | 3.84 | Period | 2026-02-02 16:56 | February | 2026 | 2026-02-04 15:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202511-NM25-02560 | GDL17 | Residencial | 12.288 | Period | 2026-02-20 15:55 | February | 2026 | 2026-03-17 08:07 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 25 | 0 | 2026-04-01 | 39
202511-NM25-02571 | GDL17 | Residencial | 23 | Period | 2026-03-09 17:17 | March | 2026 | 2026-03-10 10:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 22
202511-NM25-02572 | GDL17 | Residencial | 8 | Out of period | 2025-12-01 13:02 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 120
202511-NM25-02573 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:17 | January | 2026 | 2026-01-14 15:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 83
202511-NM25-02584 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:49 | January | 2026 | 2026-01-22 09:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202511-NM25-02587 | GDL17 | Residencial | 14.08 | Period | 2026-01-28 14:05 | January | 2026 | 2026-02-02 16:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 62
202511-NM25-02609 | GDL17 | Residencial | 2.304 | Period | 2026-02-06 15:05 | February | 2026 | 2026-02-10 14:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 53
202511-NM25-02615 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:53 | February | 2026 | 2026-02-26 08:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202511-NM25-02623 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 18:15 | January | 2026 | 2026-02-17 13:41 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 64
202511-NM25-02629 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 00:36 | February | 2026 | 2026-02-23 15:06 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 10 | 0 | 2026-04-01 | 46
202511-NM25-02631 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 23:46 | February | 2026 | 2026-03-09 08:20 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 15 | 0 | 2026-04-01 | 38
202511-NM25-02632 | GDL17 | Residencial | 5.25 | Out of period | 2025-11-24 10:28 | November | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 128
202511-NM25-02637 | GDL17 | Residencial | 19.2 | Period | 2026-01-07 11:11 | January | 2026 | 2026-01-12 16:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 84
202511-NM25-02643 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 17:59 | January | 2026 | 2026-01-16 08:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 81
202511-NM25-02646 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 15:59 | February | 2026 | 2026-02-13 16:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 47
202511-NM25-02648 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:18 | February | 2026 | 2026-02-19 12:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 46
202511-NM25-02653 | GDL17 | Residencial | 6.528 | Out of period | 2025-11-25 09:20 | November | 2025 | 2026-01-16 09:37 | 52 | Study | Estudio (E) | Activated | Backlog |  | No | 52 |  | SAN JUAN | January |  | 52 | 0 | 2026-04-01 | 127
202511-NM25-02656 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:23 | January | 2026 | 2026-01-30 13:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 63
202511-NM25-02657 | GDL17 | Residencial | 0 | Out of period | 2025-12-11 09:34 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 111
202511-NM25-02663 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:23 | January | 2026 | 2026-01-14 12:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202511-NM25-02665 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:49 | February | 2026 | 2026-02-16 14:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202511-NM25-02671 | GDL17 | Residencial | 6.776 | Out of period | 2025-11-18 15:46 | November | 2025 | 2026-01-15 15:15 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | CAGUAS | January |  | 58 | 0 | 2026-04-01 | 133
202511-NM25-02699 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-19 09:21 | November | 2025 | 2026-01-21 09:41 | 63 | Study | Estudio (E) | Activated | Backlog |  | No | 63 |  | MAYAGUEZ | January |  | 64 | 0 | 2026-04-01 | 133
202511-NM25-02704 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 22:20 | January | 2026 | 2026-01-19 13:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202511-NM25-02709 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-19 14:31 | November | 2025 | 2026-01-15 16:11 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | ARECIBO | January |  | 57 | 0 | 2026-04-01 | 132
202511-NM25-02728 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:41 | February | 2026 | 2026-02-05 14:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 56
202511-NM25-02736 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 13:37 | January | 2026 | 2026-01-30 16:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 61
202511-NM25-02744 | GDL17 | Residencial | 4.224 | Period | 2026-01-08 13:26 | January | 2026 | 2026-01-14 09:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 82
202511-NM25-02747 | GDL17 | Residencial | 3.84 | Period | 2026-03-18 09:43 | March | 2026 | 2026-03-24 08:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 14
202511-NM25-02750 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:40 | January | 2026 | 2026-01-16 14:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 77
202511-NM25-02763 | GDL17 | Residencial | 16 | Period | 2026-02-04 12:20 | February | 2026 | 2026-02-13 14:42 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 55
202511-NM25-02770 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-03 09:10 | December | 2025 | 2026-02-12 16:25 | 71 | Study | Estudio (E) | Activated | Backlog |  | No | 71 |  | BAYAMON | February |  | 71 | 0 | 2026-04-01 | 119
202511-NM25-02773 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:59 | March | 2026 | 2026-04-08 14:34 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 9 | 0 | 2026-04-01 | 2
202511-NM25-02783 | GDL17 | Residencial | 15.8 | Period | 2026-01-29 07:22 | January | 2026 | 2026-01-30 13:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 62
202511-NM25-02785 | GDL17 | Residencial | 13.824 | Period | 2026-03-10 13:08 | March | 2026 | 2026-04-02 15:33 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 23 | 0 | 2026-04-01 | 21
202511-NM25-02789 | GDL17 | Residencial | 8 | Out of period | 2025-12-09 10:47 | December | 2025 | 2026-02-04 09:50 | 57 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February | 1 | 4 | 53 | 2026-04-01 | 113
202511-NM25-02803 | GDL17 | Residencial | 10 | Period | 2026-01-15 17:06 | January | 2026 | 2026-01-30 13:16 | 15 | Create NEM Agreement | Validación (V) | Activated | Applicant Registration | Yes | No |  |  | MAYAGUEZ | January | 1 | 12 | 3 | 2026-04-01 | 75
202511-NM25-02804 | GDL17 | Residencial | 10.368 | Period | 2026-01-09 14:02 | January | 2026 | 2026-01-14 16:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 81
202511-NM25-02805 | GDL17 | Residencial | 7.87 | Out of period | 2025-11-19 12:10 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 132
202511-NM25-02811 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 15:46 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 131
202511-NM25-02815 | GDL17 | Residencial | 8 | Out of period | 2025-12-09 10:06 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 113
202511-NM25-02816 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:05 | February | 2026 | 2026-03-02 09:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 35
202511-NM25-02821 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 12:10 | January | 2026 | 2026-02-02 15:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 63
202511-NM25-02829 | GDL17 | Residencial | 14.592 | Period | 2026-03-10 09:48 | March | 2026 | 2026-03-17 14:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 22
202511-NM25-02831 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:52 | February | 2026 | 2026-02-05 13:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202511-NM25-02833 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-19 15:13 | November | 2025 | 2026-01-19 15:25 | 61 | Study | Estudio (E) | Activated | Backlog |  | No | 61 |  | ARECIBO | January |  | 61 | 0 | 2026-04-01 | 132
202511-NM25-02839 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 17:15 | February | 2026 | 2026-02-25 08:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-02841 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 14:11 | January | 2026 | 2026-01-29 13:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 63
202511-NM25-02845 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:59 | March | 2026 | 2026-03-27 10:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 8
202511-NM25-02847 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-19 14:57 | November | 2025 | 2026-01-08 15:20 | 50 | Study | Estudio (E) | Activated | Backlog |  | No | 50 |  | MAYAGUEZ | January |  | 50 | 0 | 2026-04-01 | 132
202511-NM25-02856 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-23 09:48 | December | 2025 | 2026-03-02 09:02 | 69 | Study | Estudio (E) | Activated | Backlog |  | No | 69 |  | MAYAGUEZ | March |  | 68 | 0 | 2026-04-01 | 99
202511-NM25-02857 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:43 | February | 2026 | 2026-02-27 07:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202511-NM25-02858 | GDL17 | Residencial | 3.84 | Out of period | 2025-11-30 07:41 | November | 2025 | 2026-01-26 13:20 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | MAYAGUEZ | January |  | 57 | 0 | 2026-04-01 | 122
202511-NM25-02861 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 10:27 | January | 2026 | 2026-02-02 11:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 63
202511-NM25-02868 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-03 14:13 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 125 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 118
202511-NM25-02875 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:52 | February | 2026 | 2026-02-05 13:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202511-NM25-02882 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:42 | February | 2026 | 2026-02-18 11:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-02884 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:35 | February | 2026 | 2026-02-23 11:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-02885 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:51 | January | 2026 | 2026-01-26 12:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 68
202511-NM25-02888 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:35 | February | 2026 | 2026-02-26 08:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 36
202511-NM25-02896 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 19:55 | February | 2026 | 2026-02-24 07:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202511-NM25-02898 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-19 15:59 | November | 2025 | 2026-01-05 07:54 | 47 | Study | Estudio (E) | Activated | Backlog |  | No | 47 |  | MAYAGUEZ | January |  | 47 | 0 | 2026-04-01 | 132
202511-NM25-02900 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:52 | February | 2026 | 2026-02-25 08:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-02906 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-19 16:14 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 132
202511-NM25-02907 | GDL17 | Residencial | 13.62 | Period | 2026-02-25 15:04 | February | 2026 | 2026-03-02 09:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202511-NM25-02909 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 09:58 | February | 2026 | 2026-02-27 08:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 36
202511-NM25-02914 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:50 | March | 2026 | 2026-03-09 09:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 29
202511-NM25-02916 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:13 | February | 2026 | 2026-03-05 08:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 32
202511-NM25-02922 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:28 | February | 2026 | 2026-02-23 09:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-02924 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:31 | March | 2026 | 2026-03-06 15:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 26
202511-NM25-02931 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:01 | March | 2026 | 2026-03-17 13:09 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 22
202511-NM25-02933 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:03 | February | 2026 | 2026-02-26 08:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 37
202511-NM25-02942 | GDL17 | Residencial | 3.8 | Period | 2026-01-21 15:05 | January | 2026 | 2026-01-29 14:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 69
202511-NM25-02966 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:33 | February | 2026 | 2026-03-12 15:23 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 28 | 0 | 2026-04-01 | 47
202511-NM25-02971 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 11:26 | March | 2026 | 2026-03-18 15:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 16
202511-NM25-02976 | GDL17 | Residencial | 3.8 | Out of period | 2025-11-20 11:29 | November | 2025 | 2026-03-23 14:48 | 123 | Study | Estudio (E) | Activated | Backlog |  | No | 123 |  | SAN JUAN | March |  | 123 | 0 | 2026-04-01 | 132
202511-NM25-02980 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:57 | February | 2026 | 2026-02-24 07:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-02985 | GDL17 | Residencial | 6.588 | Out of period | 2025-11-20 10:31 | November | 2025 | 2026-01-29 13:27 | 70 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | January | 1 | 5 | 65 | 2026-04-01 | 132
202511-NM25-02987 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 14:10 | January | 2026 | 2026-02-12 12:40 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 62
202511-NM25-02988 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:07 | March | 2026 | 2026-03-26 12:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 8
202511-NM25-02993 | GDL17 | Residencial | 23 | Period | 2026-03-23 14:39 | March | 2026 | 2026-03-26 11:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202511-NM25-03016 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:29 | December | 2025 | 2026-01-15 16:03 | 15 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 15 | 0 | 2026-04-01 | 91
202511-NM25-03021 | GDL17 | Residencial | 11.5 | Period | 2026-02-22 14:01 | February | 2026 | 2026-03-16 13:54 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 2 | 8 | 14 | 2026-04-01 | 37
202511-NM25-03025 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:30 | March | 2026 | 2026-03-27 16:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 7
202511-NM25-03029 | GDL17 | Residencial | 8 | Period | 2026-02-18 12:11 | February | 2026 | 2026-02-23 14:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202511-NM25-03031 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 10:09 | November | 2025 | 2026-01-14 15:59 | 55 | Study | Estudio (E) | Activated | Backlog |  | No | 55 |  | MAYAGUEZ | January |  | 55 | 0 | 2026-04-01 | 132
202511-NM25-03046 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 15:34 | February | 2026 | 2026-02-11 09:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 54
202511-NM25-03049 | GDL17 | Residencial | 8 | Period | 2026-01-08 15:22 | January | 2026 | 2026-01-13 09:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202511-NM25-03050 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:13 | March | 2026 | 2026-03-05 13:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 30
202511-NM25-03053 | GDL17 | Residencial | 6.912 | Out of period | 2025-11-20 15:18 | November | 2025 | 2026-01-16 15:08 | 57 | Study | Estudio (E) | Activated | Backlog |  | No | 57 |  | MAYAGUEZ | January |  | 57 | 0 | 2026-04-01 | 131
202511-NM25-03058 | GDL17 | Residencial | 23 | Period | 2026-03-18 09:30 | March | 2026 | 2026-03-25 08:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 14
202511-NM25-03066 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 21:09 | January | 2026 | 2026-02-03 16:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 60
202511-NM25-03069 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:53 | January | 2026 | 2026-02-05 15:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 61
202511-NM25-03070 | GDL17 | Residencial | 13.056 | Period | 2026-02-11 08:51 | February | 2026 | 2026-02-24 16:17 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 12 | 1 | 2026-04-01 | 49
202511-NM25-03075 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 23:45 | February | 2026 | 2026-02-25 15:51 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 42
202511-NM25-03077 | GDL17 | Residencial | 15.3 | Period | 2026-02-24 15:14 | February | 2026 | 2026-03-02 14:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 35
202511-NM25-03079 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 17:32 | January | 2026 | 2026-02-03 10:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 61
202511-NM25-03083 | GDL17 | Residencial | 23 | Period | 2026-02-19 15:48 | February | 2026 | 2026-02-25 08:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03084 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 14:21 | January | 2026 | 2026-01-30 07:41 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | January | 1 | 3 | 5 | 2026-04-01 | 68
202511-NM25-03088 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 08:27 | January | 2026 | 2026-01-22 13:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 70
202511-NM25-03089 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:12 | January | 2026 | 2026-01-30 13:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 63
202511-NM25-03093 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 14:32 | January | 2026 | 2026-01-23 16:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 68
202511-NM25-03094 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 16:56 | February | 2026 | 2026-03-03 10:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 34
202511-NM25-03097 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:29 | March | 2026 | 2026-03-27 07:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202511-NM25-03098 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:44 | January | 2026 | 2026-01-16 12:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 77
202511-NM25-03099 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:34 | February | 2026 | 2026-02-25 08:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03101 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 08:21 | January | 2026 | 2026-01-22 14:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202511-NM25-03110 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:55 | January | 2026 | 2026-01-20 08:25 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 12 | 0 | 2026-04-01 | 82
202511-NM25-03112 | GDL17 | Residencial | 5.76 | Period | 2026-03-25 15:23 | March | 2026 | 2026-03-30 13:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202511-NM25-03118 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-04 14:47 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 117
202511-NM25-03121 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 19:04 | January | 2026 | 2026-01-28 14:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202511-NM25-03132 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 15:08 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 131
202511-NM25-03133 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:29 | March | 2026 | 2026-03-25 15:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 9
202511-NM25-03136 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 15:25 | November | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 131
202511-NM25-03137 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 08:49 | February | 2026 | 2026-02-18 11:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 47
202511-NM25-03139 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 20:14 | February | 2026 | 2026-02-16 13:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 47
202511-NM25-03140 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 15:37 | November | 2025 | 2026-01-21 14:32 | 62 | Study | Estudio (E) | Activated | Backlog |  | No | 62 |  | CAGUAS | January |  | 62 | 0 | 2026-04-01 | 131
202511-NM25-03141 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 15:50 | November | 2025 | 2026-01-23 14:59 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | MAYAGUEZ | January |  | 64 | 0 | 2026-04-01 | 131
202511-NM25-03143 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 15:58 | November | 2025 | 2026-01-23 08:25 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | ARECIBO | January |  | 64 | 0 | 2026-04-01 | 131
202511-NM25-03144 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-20 16:25 | November | 2025 | 2026-01-19 10:04 | 60 | Study | Estudio (E) | Activated | Backlog |  | No | 60 |  | CAGUAS | January |  | 60 | 0 | 2026-04-01 | 131
202511-NM25-03145 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:56 | February | 2026 | 2026-03-02 07:59 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 41
202511-NM25-03152 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 16:43 | November | 2025 | 2026-01-30 09:44 | 71 | Study | Estudio (E) | Activated | Backlog |  | No | 71 |  | ARECIBO | January |  | 71 | 0 | 2026-04-01 | 131
202511-NM25-03153 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:36 | February | 2026 | 2026-03-05 10:49 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 34
202511-NM25-03154 | GDL17 | Residencial | 23 | Period | 2026-02-18 15:47 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 41
202511-NM25-03156 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 21:37 | February | 2026 | 2026-02-18 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 46
202511-NM25-03159 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-20 16:56 | November | 2025 | 2026-02-06 11:23 | 78 | Study | Estudio (E) | Activated | Backlog |  | No | 78 |  | ARECIBO | February |  | 78 | 0 | 2026-04-01 | 131
202511-NM25-03162 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:28 | February | 2026 | 2026-03-05 09:52 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 13 | 0 | 2026-04-01 | 39
202511-NM25-03168 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 18:24 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 61
202511-NM25-03193 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 17:56 | February | 2026 | 2026-02-18 10:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 47
202511-NM25-03201 | GDL17 | Residencial | 8.064 | Period | 2026-01-30 16:47 | January | 2026 | 2026-02-03 16:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 60
202511-NM25-03205 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-21 14:54 | November | 2025 | 2026-01-28 15:14 | 68 | Study | Estudio (E) | Activated | Backlog |  | No | 68 |  | ARECIBO | January |  | 68 | 0 | 2026-04-01 | 130
202511-NM25-03208 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-21 09:58 | November | 2025 | 2026-01-07 09:46 | 47 | Study | Estudio (E) | Activated | Backlog |  | No | 47 |  | MAYAGUEZ | January |  | 47 | 0 | 2026-04-01 | 131
202511-NM25-03210 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 07:19 | February | 2026 | 2026-02-11 11:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 50
202511-NM25-03212 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-03 14:14 | December | 2025 | 2026-02-10 14:41 | 69 | Study | Estudio (E) | Activated | Backlog |  | No | 69 |  | BAYAMON | February |  | 69 | 0 | 2026-04-01 | 118
202511-NM25-03213 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-21 09:54 | November | 2025 | 2026-01-22 16:17 | 62 | Study | Estudio (E) | Activated | Backlog |  | No | 62 |  | CAGUAS | January |  | 62 | 0 | 2026-04-01 | 131
202511-NM25-03214 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-25 14:26 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 126
202511-NM25-03221 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:19 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 33
202511-NM25-03222 | GDL17 | Residencial | 8 | Out of period | 2025-12-09 12:58 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 112
202511-NM25-03227 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:28 | March | 2026 | 2026-03-26 08:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 8
202511-NM25-03232 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 17:48 | January | 2026 | 2026-01-14 13:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 82
202511-NM25-03234 | GDL17 | Residencial | 7.6 | Period | 2026-02-23 17:01 | February | 2026 | 2026-03-02 15:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 36
202511-NM25-03235 | GDL17 | Residencial | 15.2 | Period | 2026-03-16 09:09 | March | 2026 | 2026-03-18 08:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 16
202511-NM25-03243 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:52 | February | 2026 | 2026-03-03 16:08 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 39
202511-NM25-03248 | GDL17 | Residencial | 8 | Out of period | 2025-11-25 11:32 | November | 2025 | 2026-01-05 09:39 | 41 | Study | Estudio (E) | Activated | Backlog |  | No | 41 |  | MAYAGUEZ | January |  | 41 | 0 | 2026-04-01 | 127
202511-NM25-03249 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 07:26 | March | 2026 | 2026-03-18 13:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202511-NM25-03251 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:40 | January | 2026 | 2026-02-03 08:21 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 64
202511-NM25-03257 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:44 | February | 2026 | 2026-02-25 15:16 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 42
202511-NM25-03262 | GDL17 | Residencial | 12.288 | Period | 2026-03-11 14:52 | March | 2026 | 2026-03-13 13:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202511-NM25-03266 | GDL17 | Residencial | 3.8 | Period | 2026-01-29 12:38 | January | 2026 | 2026-02-03 09:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 61
202511-NM25-03267 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 12:45 | February | 2026 | 2026-03-02 11:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 34
202511-NM25-03269 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-21 12:18 | November | 2025 | 2026-01-29 15:01 | 69 | Study | Estudio (E) | Activated | Backlog |  | No | 69 |  | ARECIBO | January |  | 69 | 0 | 2026-04-01 | 130
202511-NM25-03270 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 17:55 | February | 2026 | 2026-02-25 14:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03272 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:57 | February | 2026 | 2026-02-25 08:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03273 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:46 | February | 2026 | 2026-02-10 11:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 55
202511-NM25-03274 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:50 | February | 2026 | 2026-02-27 09:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 36
202511-NM25-03278 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:56 | February | 2026 | 2026-02-26 09:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202511-NM25-03281 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:47 | February | 2026 | 2026-02-27 09:09 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 40
202511-NM25-03282 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-21 13:35 | November | 2025 | 2026-01-23 07:46 | 63 | Study | Estudio (E) | Activated | Backlog |  | No | 63 |  | CAGUAS | January |  | 62 | 0 | 2026-04-01 | 130
202511-NM25-03284 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 08:37 | January | 2026 | 2026-01-21 16:06 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 0 | 0 | 2026-04-01 | 70
202511-NM25-03285 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-21 16:33 | November | 2025 | 2026-01-16 14:07 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | ARECIBO | January |  | 56 | 0 | 2026-04-01 | 130
202511-NM25-03287 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-21 13:52 | November | 2025 | 2026-01-21 15:30 | 61 | Study | Estudio (E) | Activated | Backlog |  | No | 61 |  | ARECIBO | January |  | 61 | 0 | 2026-04-01 | 130
202511-NM25-03289 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 08:59 | January | 2026 | 2026-03-05 11:16 | 43 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 43 | 0 | 2026-04-01 | 70
202511-NM25-03307 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:21 | February | 2026 | 2026-02-25 08:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03308 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-21 15:59 | November | 2025 | 2026-01-14 11:22 | 54 | Study | Estudio (E) | Activated | Backlog |  | No | 54 |  | ARECIBO | January |  | 54 | 0 | 2026-04-01 | 130
202511-NM25-03312 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:57 | February | 2026 | 2026-02-09 10:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 57
202511-NM25-03319 | GDL17 | Residencial | 5.76 | Period | 2026-01-26 17:20 | January | 2026 | 2026-01-28 14:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202511-NM25-03327 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 13:59 | March | 2026 | 2026-04-20 12:38 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 21 | 0 | 2026-04-01 | 1
202511-NM25-03335 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:02 | February | 2026 | 2026-02-25 11:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03343 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:24 | February | 2026 | 2026-02-23 15:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 43
202511-NM25-03354 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 12:36 | March | 2026 | 2026-03-20 08:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 19
202511-NM25-03357 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:17 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 61
202511-NM25-03362 | GDL17 | Residencial | 11.712 | Out of period | 2025-11-26 14:22 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 125
202511-NM25-03368 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:17 | February | 2026 | 2026-03-02 10:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 34
202511-NM25-03369 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-19 22:28 | December | 2025 | 2026-02-19 16:06 | 62 | Study | Estudio (E) | Activated | Backlog |  | No | 62 |  | BAYAMON | February |  | 61 | 0 | 2026-04-01 | 102
202511-NM25-03392 | GDL17 | Residencial | 5.76 | Period | 2026-01-26 16:51 | January | 2026 | 2026-01-29 16:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 64
202511-NM25-03418 | GDL17 | Comercial | 15 | Period | 2026-01-20 15:36 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 70
202511-NM25-03432 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 23:04 | February | 2026 | 2026-03-09 13:28 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 34
202511-NM25-03466 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:27 | February | 2026 | 2026-02-24 10:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 42
202511-NM25-03478 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-24 09:54 | November | 2025 | 2026-01-02 09:38 | 39 | Study | Estudio (E) | Activated | Backlog |  | No | 39 |  | MAYAGUEZ | January |  | 39 | 0 | 2026-04-01 | 128
202511-NM25-03494 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 18:36 | February | 2026 | 2026-03-02 10:03 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 40
202511-NM25-03496 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:13 | February | 2026 | 2026-02-25 09:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202511-NM25-03500 | GDL17 | Residencial | 23 | Period | 2026-02-19 21:16 | February | 2026 | 2026-02-25 08:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202511-NM25-03504 | GDL17 | Residencial | 23 | Period | 2026-01-08 11:47 | January | 2026 | 2026-01-15 15:17 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 83
202511-NM25-03509 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 13:02 | February | 2026 | 2026-02-17 14:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 47
202511-NM25-03514 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-24 11:27 | November | 2025 | 2026-01-19 16:04 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | MAYAGUEZ | January |  | 56 | 0 | 2026-04-01 | 128
202511-NM25-03519 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-24 13:15 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 127
202511-NM25-03526 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 16:02 | January | 2026 | 2026-01-23 15:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202511-NM25-03534 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 07:42 | February | 2026 | 2026-02-11 15:23 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 0 | 0 | 2026-04-01 | 49
202511-NM25-03536 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-25 15:25 | November | 2025 | 2026-01-08 15:47 | 44 | Study | Estudio (E) | Activated | Backlog |  | No | 44 |  | MAYAGUEZ | January |  | 44 | 0 | 2026-04-01 | 126
202511-NM25-03537 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 19:53 | February | 2026 | 2026-02-18 14:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-03538 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 08:33 | January | 2026 | 2026-01-21 16:03 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 0 | 0 | 2026-04-01 | 70
202511-NM25-03543 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 14:29 | January | 2026 | 2026-01-27 16:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | January | 1 | 1 | 4 | 2026-04-01 | 68
202511-NM25-03550 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 19:59 | February | 2026 | 2026-02-26 09:41 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 41
202511-NM25-03570 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:21 | March | 2026 | 2026-03-16 08:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 21
202511-NM25-03571 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 14:29 | January | 2026 | 2026-02-04 09:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 60
202511-NM25-03582 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-27 12:18 | November | 2025 | 2026-01-14 11:13 | 48 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 48 | 0 | 2026-04-01 | 124
202511-NM25-03589 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 17:12 | February | 2026 | 2026-03-02 10:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202511-NM25-03593 | GDL17 | Residencial | 7.6 | Period | 2026-02-17 08:57 | February | 2026 | 2026-03-16 09:50 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 2 | 9 | 18 | 2026-04-01 | 43
202511-NM25-03595 | GDL17 | Comercial | 24 | Out of period | 2025-11-24 21:49 | November | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 127
202511-NM25-03601 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 01:42 | February | 2026 | 2026-02-23 09:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202511-NM25-03603 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 13:23 | March | 2026 | 2026-03-31 15:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 4
202511-NM25-03605 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-24 16:01 | November | 2025 | 2026-01-16 14:26 | 53 | Study | Estudio (E) | Activated | Backlog |  | No | 53 |  | ARECIBO | January |  | 53 | 0 | 2026-04-01 | 127
202511-NM25-03614 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:34 | March | 2026 | 2026-03-06 09:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 28
202511-NM25-03616 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:09 | February | 2026 | 2026-02-25 07:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03617 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:49 | February | 2026 | 2026-03-04 15:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 33
202511-NM25-03620 | GDL17 | Residencial | 23 | Period | 2026-02-02 16:43 | February | 2026 | 2026-02-11 11:13 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 57
202511-NM25-03622 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-24 17:00 | November | 2025 | 2026-01-15 08:06 | 52 | Study | Estudio (E) | Activated | Backlog |  | No | 52 |  | MAYAGUEZ | January |  | 51 | 0 | 2026-04-01 | 127
202511-NM25-03628 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 16:35 | February | 2026 | 2026-02-17 09:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 49
202511-NM25-03631 | GDL17 | Residencial | 11.5 | Period | 2026-01-13 20:09 | January | 2026 | 2026-01-14 16:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 77
202511-NM25-03633 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 17:15 | February | 2026 | 2026-02-24 07:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-03644 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:36 | March | 2026 | 2026-03-27 15:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 9
202511-NM25-03648 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:58 | February | 2026 | 2026-02-09 13:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202511-NM25-03657 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-25 09:42 | November | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 127
202511-NM25-03663 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-25 09:19 | November | 2025 | 2026-01-19 15:37 | 55 | Study | Estudio (E) | Activated | Backlog |  | No | 55 |  | MAYAGUEZ | January |  | 55 | 0 | 2026-04-01 | 127
202511-NM25-03669 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 08:36 | March | 2026 | 2026-03-19 10:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 14
202511-NM25-03671 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-25 09:33 | November | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 127
202511-NM25-03672 | GDL17 | Residencial | 3.84 | Period | 2026-01-15 13:16 | January | 2026 | 2026-01-19 14:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202511-NM25-03674 | GDL17 | Residencial | 3.84 | Period | 2026-01-29 10:51 | January | 2026 | 2026-02-02 13:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 62
202511-NM25-03692 | GDL17 | Residencial | 11.52 | Period | 2026-02-18 16:58 | February | 2026 | 2026-02-24 07:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-03693 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:57 | February | 2026 | 2026-02-18 14:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 48
202511-NM25-03698 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:49 | February | 2026 | 2026-02-16 13:04 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 56
202511-NM25-03710 | GDL17 | Residencial | 16.5 | Period | 2026-01-19 09:39 | January | 2026 | 2026-01-20 15:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 72
202511-NM25-03717 | GDL17 | Residencial | 3.84 | Period | 2026-02-03 14:08 | February | 2026 | 2026-02-25 07:59 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 56
202511-NM25-03725 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:49 | February | 2026 | 2026-02-25 07:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03734 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:09 | February | 2026 | 2026-03-05 08:19 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 40
202511-NM25-03735 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 18:11 | February | 2026 | 2026-02-24 09:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-03738 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 12:07 | January | 2026 | 2026-02-12 08:18 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 28 | 0 | 2026-04-01 | 75
202511-NM25-03740 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:52 | March | 2026 | 2026-03-13 13:24 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 27
202511-NM25-03744 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 17:10 | February | 2026 | 2026-02-16 15:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202511-NM25-03746 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:20 | February | 2026 | 2026-02-19 08:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 44
202511-NM25-03756 | GDL17 | Residencial | 3.84 | Period | 2026-01-23 13:25 | January | 2026 | 2026-02-19 13:11 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 27 | 0 | 2026-04-01 | 67
202511-NM25-03757 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:06 | February | 2026 | 2026-02-27 13:27 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 40
202511-NM25-03761 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 17:35 | February | 2026 | 2026-02-25 14:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03765 | GDL17 | Residencial | 15.2 | Period | 2026-02-13 12:37 | February | 2026 | 2026-02-18 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 46
202511-NM25-03766 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:15 | February | 2026 | 2026-02-23 09:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-03767 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-12 14:28 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 115 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 109
202511-NM25-03772 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:11 | February | 2026 | 2026-02-25 10:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-03774 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:31 | February | 2026 | 2026-03-02 14:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 35
202511-NM25-03776 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 19:02 | March | 2026 | 2026-03-16 14:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202511-NM25-03777 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:43 | February | 2026 | 2026-03-02 15:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 34
202511-NM25-03789 | GDL17 | Residencial | 23 | Period | 2026-03-24 08:17 | March | 2026 | 2026-03-30 08:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 8
202511-NM25-03797 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-02 17:55 | December | 2025 | 2026-02-11 15:39 | 71 | Study | Estudio (E) | Activated | Backlog |  | No | 71 |  | MAYAGUEZ | February |  | 71 | 0 | 2026-04-01 | 119
202511-NM25-03798 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:37 | February | 2026 | 2026-02-23 15:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-03800 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 19:27 | January | 2026 | 2026-01-28 14:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202511-NM25-03812 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:23 | January | 2026 | 2026-01-12 16:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202511-NM25-03814 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:22 | January | 2026 | 2026-01-19 12:54 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 10 | 0 | 2026-04-01 | 82
202511-NM25-03825 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:58 | March | 2026 | 2026-03-19 10:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 14
202511-NM25-03830 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-25 16:12 | November | 2025 | 2026-01-05 13:30 | 41 | Study | Estudio (E) | Activated | Backlog |  | No | 41 |  | MAYAGUEZ | January |  | 41 | 0 | 2026-04-01 | 126
202511-NM25-03831 | GDL17 | Residencial | 17.26 | Period | 2026-01-07 10:39 | January | 2026 | 2026-01-09 10:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 84
202511-NM25-03842 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:42 | February | 2026 | 2026-02-26 10:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202511-NM25-03850 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:18 | February | 2026 | 2026-03-03 15:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202511-NM25-03852 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 20:04 | January | 2026 | 2026-02-04 14:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 60
202511-NM25-03857 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:41 | March | 2026 | 2026-03-10 08:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 29
202511-NM25-03859 | GDL17 | Residencial | 8 | Out of period | 2025-11-26 15:56 | November | 2025 | 2026-01-20 14:59 | 55 | Study | Estudio (E) | Activated | Backlog |  | No | 55 |  | SAN JUAN | January |  | 55 | 0 | 2026-04-01 | 125
202511-NM25-03860 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:43 | February | 2026 | 2026-02-26 08:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202511-NM25-03862 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 19:03 | February | 2026 | 2026-02-26 16:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202511-NM25-03867 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 21:28 | February | 2026 | 2026-02-16 13:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202511-NM25-03869 | GDL17 | Residencial | 4.82 | Period | 2026-01-08 13:32 | January | 2026 | 2026-01-13 14:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202511-NM25-03875 | GDL17 | Comercial | 23 | Out of period | 2025-12-19 13:20 | December | 2025 | 2026-02-19 16:03 | 62 | Study | Estudio (E) | Activated | Backlog |  | No | 62 |  | BAYAMON | February |  | 62 | 0 | 2026-04-01 | 102
202511-NM25-03886 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 08:18 | March | 2026 | 2026-03-09 16:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 30
202511-NM25-03912 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 15:17 | March | 2026 | 2026-03-19 12:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 13
202511-NM25-03914 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:33 | February | 2026 | 2026-02-27 08:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 40
202511-NM25-03938 | GDL17 | Residencial | 15.36 | Period | 2026-03-11 17:56 | March | 2026 | 2026-03-16 14:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 20
202511-NM25-03957 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 23:14 | February | 2026 | 2026-02-16 13:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 47
202511-NM25-03963 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:00 | January | 2026 | 2026-02-04 13:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 61
202511-NM25-03967 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:57 | February | 2026 | 2026-02-26 08:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202511-NM25-03972 | GDL17 | Residencial | 8.448 | Period | 2026-03-10 13:54 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 21
202511-NM25-03996 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:36 | February | 2026 | 2026-02-23 15:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202511-NM25-04004 | GDL17 | Residencial | 5.76 | Period | 2026-03-02 14:58 | March | 2026 | 2026-03-05 14:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202511-NM25-04006 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:51 | January | 2026 | 2026-01-12 09:16 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 10 | 0 | 2026-04-01 | 89
202511-NM25-04012 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:22 | February | 2026 | 2026-02-11 16:16 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 3 | 6 | 2026-04-01 | 57
202511-NM25-04013 | GDL17 | Residencial | 3.8 | Period | 2026-02-17 12:47 | February | 2026 | 2026-02-25 16:20 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 42
202511-NM25-04014 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:01 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 47
202511-NM25-04019 | GDL17 | Residencial | 23 | Period | 2026-02-03 13:24 | February | 2026 | 2026-02-27 11:19 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 24 | 0 | 2026-04-01 | 56
202511-NM25-04046 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 11:39 | January | 2026 | 2026-02-04 13:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 63
202511-NM25-04049 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 09:17 | March | 2026 | 2026-03-17 08:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 19
202511-NM25-04054 | GDL17 | Residencial | 23 | Period | 2026-02-20 15:52 | February | 2026 | 2026-02-26 13:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202511-NM25-04058 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:36 | January | 2026 | 2026-02-02 13:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202511-NM25-04061 | GDL17 | Residencial | 8 | Period | 2026-01-16 14:31 | January | 2026 | 2026-01-20 14:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 74
202511-NM25-04062 | GDL17 | Residencial | 5.566 | Out of period | 2025-11-26 14:28 | November | 2025 | 2026-01-16 11:15 | 51 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | January | 1 | 30 | 21 | 2026-04-01 | 125
202511-NM25-04068 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:26 | February | 2026 | 2026-02-24 15:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202511-NM25-04070 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 20:27 | February | 2026 | 2026-02-24 15:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202511-NM25-04072 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:17 | February | 2026 | 2026-02-27 08:34 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 40
202511-NM25-04074 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:04 | January | 2026 | 2026-01-15 14:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 77
202511-NM25-04077 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:09 | February | 2026 | 2026-02-10 13:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 55
202511-NM25-04078 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 22:02 | February | 2026 | 2026-02-18 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 46
202511-NM25-04081 | GDL17 | Residencial | 15.16 | Out of period | 2025-11-26 15:28 | November | 2025 | 2026-01-15 15:13 | 50 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | January | 2 | 28 | 22 | 2026-04-01 | 125
202511-NM25-04083 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 15:03 | December | 2025 | 2026-03-17 16:00 | 90 | Study | Estudio (E) | Activated | Backlog |  | No | 90 |  | SAN JUAN | March |  | 90 | 0 | 2026-04-01 | 104
202511-NM25-04088 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:17 | February | 2026 | 2026-03-02 10:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 35
202511-NM25-04090 | GDL17 | Residencial | 7.6 | Out of period | 2025-11-26 15:44 | November | 2025 | 2026-01-26 14:59 | 61 | Study | Estudio (E) | Activated | Backlog |  | No | 61 |  | CAGUAS | January |  | 61 | 0 | 2026-04-01 | 125
202511-NM25-04094 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-26 16:01 | November | 2025 | 2026-01-20 15:13 | 55 | Study | Estudio (E) | Activated | Backlog |  | No | 55 |  | ARECIBO | January |  | 55 | 0 | 2026-04-01 | 125
202511-NM25-04095 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:45 | January | 2026 | 2026-01-19 16:16 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 81
202511-NM25-04096 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:30 | February | 2026 | 2026-02-27 14:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 39
202511-NM25-04101 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:01 | February | 2026 | 2026-02-18 15:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 47
202511-NM25-04122 | GDL17 | Residencial | 3.84 | Period | 2026-03-17 12:00 | March | 2026 | 2026-03-23 15:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 5 | 1 | 2026-04-01 | 14
202511-NM25-04130 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 16:09 | January | 2026 | 2026-01-12 15:54 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 85
202511-NM25-04132 | GDL17 | Residencial | 20 | Period | 2026-02-19 20:10 | February | 2026 | 2026-02-26 13:23 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 40
202511-NM25-04133 | GDL17 | Residencial | 12 | Out of period | 2025-11-26 22:17 | November | 2025 | 2026-01-09 08:23 | 43 | Study | Estudio (E) | Activated | Backlog |  | No | 43 |  | MAYAGUEZ | January |  | 44 | 0 | 2026-04-01 | 125
202511-NM25-04154 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-27 09:33 | November | 2025 | 2026-01-14 10:36 | 48 | Study | Estudio (E) | Activated | Backlog |  | No | 48 |  | MAYAGUEZ | January |  | 48 | 0 | 2026-04-01 | 125
202511-NM25-04155 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-27 09:36 | November | 2025 | 2026-01-07 15:28 | 41 | Study | Estudio (E) | Activated | Backlog |  | No | 41 |  | MAYAGUEZ | January |  | 41 | 0 | 2026-04-01 | 125
202511-NM25-04156 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:18 | January | 2026 | 2026-01-30 08:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 63
202511-NM25-04176 | GDL17 | Comercial | 23 | Period | 2026-02-03 11:20 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 57
202511-NM25-04184 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:22 | March | 2026 | 2026-03-11 15:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 21
202511-NM25-04193 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:51 | February | 2026 | 2026-03-03 09:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202511-NM25-04196 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-27 11:26 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 125
202511-NM25-04214 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 07:25 | January | 2026 | 2026-01-28 12:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 68
202511-NM25-04235 | GDL17 | Residencial | 7.686 | Period | 2026-03-09 10:07 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 23
202511-NM25-04239 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:01 | February | 2026 | 2026-02-25 15:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202511-NM25-04245 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-27 14:27 | November | 2025 | 2026-01-02 13:58 | 36 | Study | Estudio (E) | Activated | Backlog |  | No | 36 |  | ARECIBO | January |  | 36 | 0 | 2026-04-01 | 124
202511-NM25-04249 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 07:51 | January | 2026 | 2026-01-30 09:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 68
202511-NM25-04256 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-27 14:23 | November | 2025 | 2026-01-13 09:29 | 47 | Study | Estudio (E) | Activated | Backlog |  | No | 47 |  | MAYAGUEZ | January |  | 47 | 0 | 2026-04-01 | 124
202511-NM25-04274 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-27 15:17 | November | 2025 | 2026-01-21 08:18 | 55 | Study | Estudio (E) | Activated | Backlog |  | No | 55 |  | PONCE | January |  | 55 | 0 | 2026-04-01 | 124
202511-NM25-04278 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 08:38 | February | 2026 | 2026-03-02 15:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202511-NM25-04281 | GDL17 | Residencial | 9.216 | Period | 2026-01-08 12:32 | January | 2026 | 2026-01-13 08:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202511-NM25-04286 | GDL17 | Residencial | 6.3 | Out of period | 2025-11-27 18:44 | November | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 124
202511-NM25-04293 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-28 08:32 | November | 2025 | 2026-02-27 14:09 | 91 | Study | Estudio (E) | Activated | Backlog |  | No | 91 |  | ARECIBO | February |  | 91 | 0 | 2026-04-01 | 124
202511-NM25-04294 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-28 08:39 | November | 2025 | 2026-01-02 14:03 | 35 | Study | Estudio (E) | Activated | Backlog |  | No | 35 |  | MAYAGUEZ | January |  | 35 | 0 | 2026-04-01 | 124
202511-NM25-04301 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-28 09:07 | November | 2025 | 2026-01-05 08:35 | 38 | Study | Estudio (E) | Activated | Backlog |  | No | 38 |  | MAYAGUEZ | January |  | 38 | 0 | 2026-04-01 | 124
202511-NM25-04310 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-04 09:57 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 118
202511-NM25-04313 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-28 09:40 | November | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 132 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 124
202511-NM25-04334 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-28 10:14 | November | 2025 | 2026-01-07 15:14 | 40 | Study | Estudio (E) | Activated | Backlog |  | No | 40 |  | MAYAGUEZ | January |  | 40 | 0 | 2026-04-01 | 124
202511-NM25-04335 | GDL17 | Residencial | 9.216 | Period | 2026-03-12 16:24 | March | 2026 | 2026-03-30 09:29 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 15 | 3 | 2026-04-01 | 19
202511-NM25-04336 | GDL17 | Residencial | 16.87 | Out of period | 2025-11-28 12:32 | November | 2025 | 2026-01-14 14:35 | 47 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | January | 1 | 10 | 37 | 2026-04-01 | 123
202511-NM25-04337 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-05 17:11 | December | 2025 | 2026-02-02 16:18 | 59 | Study | Estudio (E) | Activated | Backlog |  | No | 59 |  | ARECIBO | February |  | 59 | 0 | 2026-04-01 | 116
202511-NM25-04353 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 11:12 | January | 2026 | 2026-03-04 10:12 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 34 | 0 | 2026-04-01 | 62
202511-NM25-04357 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-04 14:20 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 138 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 117
202511-NM25-04382 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 09:33 | March | 2026 | 2026-03-16 11:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 23
202511-NM25-04387 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:25 | February | 2026 | 2026-02-10 10:50 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 57
202511-NM25-04389 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-28 12:10 | November | 2025 | 2026-01-12 11:09 | 45 | Study | Estudio (E) | Activated | Backlog |  | No | 45 |  | ARECIBO | January |  | 45 | 0 | 2026-04-01 | 123
202511-NM25-04401 | GDL17 | Residencial | 3.8 | Out of period | 2025-12-12 18:35 | December | 2025 | 2026-02-13 10:28 | 63 | Study | Estudio (E) | Activated | Backlog |  | No | 63 |  | BAYAMON | February |  | 62 | 0 | 2026-04-01 | 109
202511-NM25-04402 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:06 | February | 2026 | 2026-02-25 09:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 39
202511-NM25-04406 | GDL17 | Residencial | 23 | Period | 2026-03-10 17:49 | March | 2026 | 2026-04-24 14:30 | 45 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 45 | 43 | 2026-04-01 | 21
202511-NM25-04424 | GDL17 | Residencial | 8.448 | Period | 2026-02-25 12:57 | February | 2026 | 2026-02-27 12:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 34
202511-NM25-04425 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 09:34 | January | 2026 | 2026-01-15 14:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 77
202511-NM25-04430 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:52 | February | 2026 | 2026-02-20 14:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202511-NM25-04432 | GDL17 | Residencial | 5.76 | Period | 2026-01-15 18:42 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 75
202511-NM25-04444 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-28 14:47 | November | 2025 | 2026-01-13 09:39 | 46 | Study | Estudio (E) | Activated | Backlog |  | No | 46 |  | SAN JUAN | January |  | 46 | 0 | 2026-04-01 | 123
202511-NM25-04448 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 15:23 | March | 2026 | 2026-03-16 15:45 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 7 | 4 | 2026-04-01 | 26
202511-NM25-04452 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 14:52 | January | 2026 | 2026-01-29 13:01 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 13 | 0 | 2026-04-01 | 74
202511-NM25-04458 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-26 12:18 | December | 2025 | 2026-02-17 13:56 | 53 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February | 1 | 42 | 1 | 2026-04-01 | 95
202511-NM25-04463 | GDL17 | Residencial | 11.5 | Out of period | 2025-11-28 15:28 | November | 2025 | 2026-01-02 11:07 | 35 | Study | Estudio (E) | Activated | Backlog |  | No | 35 |  | SAN JUAN | January |  | 35 | 0 | 2026-04-01 | 123
202512-NM25-00005 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 09:54 | January | 2026 | 2026-01-29 12:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 63
202512-NM25-00011 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:20 | March | 2026 | 2026-03-25 15:05 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 21 | 0 | 2026-04-01 | 28
202512-NM25-00027 | GDL17 | Residencial | 6.8 | Period | 2026-01-19 11:04 | January | 2026 | 2026-01-21 14:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 72
202512-NM25-00040 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 13:43 | January | 2026 | 2026-02-02 14:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-00042 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:25 | February | 2026 | 2026-03-11 09:40 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 35
202512-NM25-00043 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:25 | February | 2026 | 2026-03-04 12:42 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 30 | 0 | 2026-04-01 | 57
202512-NM25-00059 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:10 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 36
202512-NM25-00078 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 13:58 | January | 2026 | 2026-02-02 14:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-00084 | GDL17 | Residencial | 7.6 | Period | 2026-01-05 11:19 | January | 2026 | 2026-01-14 10:37 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 9 | 0 | 2026-04-01 | 86
202512-NM25-00092 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:51 | February | 2026 | 2026-02-25 15:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-00093 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 13:52 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 104
202512-NM25-00095 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 17:36 | January | 2026 | 2026-01-22 13:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 1 | 3 | 4 | 2026-04-01 | 75
202512-NM25-00111 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:39 | February | 2026 | 2026-02-11 14:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 55
202512-NM25-00122 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:20 | March | 2026 | 2026-04-07 14:33 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 12 | 0 | 2026-04-01 | 6
202512-NM25-00123 | GDL17 | Residencial | 7.6 | Period | 2026-03-04 14:05 | March | 2026 | 2026-03-05 16:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 27
202512-NM25-00137 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 14:27 | January | 2026 | 2026-01-23 10:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 68
202512-NM25-00144 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-01 12:47 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 142 | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 120
202512-NM25-00151 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 13:49 | January | 2026 | 2026-02-02 13:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-00153 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:15 | February | 2026 | 2026-02-05 13:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 56
202512-NM25-00165 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-01 13:30 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 129 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 120
202512-NM25-00167 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:18 | February | 2026 | 2026-02-09 15:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202512-NM25-00191 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-09 14:55 | December | 2025 | 2026-02-16 16:15 | 69 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | February |  | 69 | 1 | 2026-04-01 | 112
202512-NM25-00192 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-08 10:55 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 114
202512-NM25-00193 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:16 | February | 2026 | 2026-03-04 08:08 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 12 | 0 | 2026-04-01 | 39
202512-NM25-00196 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:05 | March | 2026 | 2026-04-08 14:52 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 15 | 0 | 2026-04-01 | 7
202512-NM25-00200 | GDL17 | Residencial | 3.84 | Period | 2026-01-22 09:54 | January | 2026 | 2026-01-26 14:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 69
202512-NM25-00213 | GDL17 | Residencial | 10.752 | Period | 2026-02-20 18:16 | February | 2026 | 2026-02-26 08:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-00215 | GDL17 | Residencial | 17.5 | Period | 2026-01-26 13:53 | January | 2026 | 2026-01-28 14:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-00221 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 12:42 | January | 2026 | 2026-01-22 15:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 71
202512-NM25-00222 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 07:28 | February | 2026 | 2026-02-06 14:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 56
202512-NM25-00224 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 07:43 | January | 2026 | 2026-01-30 13:35 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 62
202512-NM25-00233 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 08:50 | March | 2026 | 2026-04-07 11:17 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 12 | 0 | 2026-04-01 | 6
202512-NM25-00242 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 14:01 | February | 2026 | 2026-02-24 14:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202512-NM25-00249 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 17:31 | January | 2026 | 2026-01-21 14:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 75
202512-NM25-00252 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:51 | March | 2026 | 2026-03-11 14:06 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 28
202512-NM25-00261 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 19:31 | February | 2026 | 2026-02-23 09:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202512-NM25-00263 | GDL17 | Residencial | 3.84 | Period | 2026-02-06 07:28 | February | 2026 | 2026-02-10 14:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-00264 | GDL17 | Residencial | 8 | Out of period | 2025-12-03 11:09 | December | 2025 | 2026-03-18 14:34 | 105 | Study | Estudio (E) | Activated | Backlog |  | No | 105 |  | MAYAGUEZ | March |  | 105 | 0 | 2026-04-01 | 119
202512-NM25-00277 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:49 | February | 2026 | 2026-02-18 10:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202512-NM25-00283 | GDL17 | Residencial | 4.608 | Period | 2026-02-18 15:08 | February | 2026 | 2026-02-24 07:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202512-NM25-00285 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:37 | January | 2026 | 2026-01-30 11:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-00293 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-03 11:10 | December | 2025 | 2026-03-06 10:20 | 93 | Study | Estudio (E) | Activated | Backlog |  | No | 93 |  | PONCE | March |  | 93 | 0 | 2026-04-01 | 119
202512-NM25-00295 | GDL17 | Residencial | 13.542 | Period | 2026-01-23 12:33 | January | 2026 | 2026-01-26 11:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-00308 | GDL17 | Residencial | 7.68 | Out of period | 2025-12-02 17:31 | December | 2025 | 2026-02-17 09:19 | 77 | Study | Estudio (E) | Activated | Backlog |  | No | 77 |  | CAGUAS | February |  | 77 | 0 | 2026-04-01 | 119
202512-NM25-00322 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-01 17:47 | December | 2025 | 2026-03-25 12:39 | 114 | Study | Estudio (E) | Activated | Backlog |  | No | 114 |  | MAYAGUEZ | March |  | 114 | 0 | 2026-04-01 | 120
202512-NM25-00323 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:33 | February | 2026 | 2026-02-24 09:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202512-NM25-00331 | GDL17 | Residencial | 11.52 | Period | 2026-02-25 18:32 | February | 2026 | 2026-03-05 16:25 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 34
202512-NM25-00341 | GDL17 | Residencial | 11.52 | Out of period | 2025-12-02 16:35 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 119
202512-NM25-00342 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 14:24 | February | 2026 | 2026-02-16 10:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 50
202512-NM25-00351 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:47 | February | 2026 | 2026-02-27 09:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-00368 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:22 | January | 2026 | 2026-01-30 10:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 63
202512-NM25-00379 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-30 15:21 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No | 121 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 91
202512-NM25-00388 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:38 | February | 2026 | 2026-02-17 14:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 47
202512-NM25-00398 | GDL17 | Residencial | 7.68 | Period | 2026-03-13 14:53 | March | 2026 | 2026-03-16 16:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 18
202512-NM25-00404 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:59 | March | 2026 | 2026-03-30 10:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 8
202512-NM25-00414 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-23 14:28 | December | 2025 | 2026-02-11 14:10 | 50 | Study | Estudio (E) | Activated | Backlog |  | No | 50 |  | BAYAMON | February |  | 50 | 0 | 2026-04-01 | 98
202512-NM25-00424 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:02 | January | 2026 | 2026-01-30 13:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 62
202512-NM25-00445 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 08:06 | January | 2026 | 2026-02-03 13:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-00455 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:29 | January | 2026 | 2026-02-27 10:44 | 44 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 44 | 0 | 2026-04-01 | 77
202512-NM25-00467 | GDL17 | Residencial | 22.8 | Period | 2026-01-15 12:59 | January | 2026 | 2026-02-06 11:05 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 2 | 1 | 21 | 2026-04-01 | 75
202512-NM25-00486 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:18 | January | 2026 | 2026-01-09 09:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 83
202512-NM25-00493 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:55 | February | 2026 | 2026-02-27 09:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-00495 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 08:36 | January | 2026 | 2026-02-09 15:06 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 61
202512-NM25-00504 | GDL17 | Residencial | 9.6 | Period | 2026-02-20 16:57 | February | 2026 | 2026-02-26 08:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-00508 | GDL17 | Residencial | 5.76 | Period | 2026-01-10 15:59 | January | 2026 | 2026-01-14 15:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 80
202512-NM25-00526 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 07:26 | January | 2026 | 2026-02-06 15:44 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 64
202512-NM25-00527 | GDL17 | Residencial | 12 | Period | 2026-01-13 22:14 | January | 2026 | 2026-01-15 09:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-00530 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:54 | February | 2026 | 2026-02-16 11:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 48
202512-NM25-00531 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:12 | March | 2026 | 2026-03-12 15:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202512-NM25-00538 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:18 | March | 2026 | 2026-03-16 08:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 22
202512-NM25-00544 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 11:10 | February | 2026 | 2026-02-23 11:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 42
202512-NM25-00554 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:16 | February | 2026 | 2026-02-13 15:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 47
202512-NM25-00566 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:11 | January | 2026 | 2026-01-26 12:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 68
202512-NM25-00569 | GDL17 | Residencial | 23 | Period | 2026-03-12 16:18 | March | 2026 | 2026-03-17 11:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 19
202512-NM25-00574 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:41 | February | 2026 | 2026-02-05 15:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202512-NM25-00576 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:54 | March | 2026 | 2026-03-11 08:12 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 29
202512-NM25-00578 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:44 | February | 2026 | 2026-02-24 14:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202512-NM25-00581 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 13:35 | March | 2026 | 2026-03-12 08:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 25
202512-NM25-00583 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:17 | March | 2026 | 2026-03-05 16:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 27
202512-NM25-00585 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 21:55 | February | 2026 | 2026-02-16 13:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202512-NM25-00587 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-02 15:07 | December | 2025 | 2026-02-25 16:03 | 85 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 2 | 11 | 74 | 2026-04-01 | 119
202512-NM25-00588 | GDL17 | Residencial | 11.5 | Period | 2026-02-28 08:21 | February | 2026 | 2026-03-05 14:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 32
202512-NM25-00589 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 14:54 | December | 2025 | 2026-03-13 13:01 | 86 | Study | Estudio (E) | Activated | Backlog |  | No | 86 |  | MAYAGUEZ | March |  | 86 | 0 | 2026-04-01 | 104
202512-NM25-00596 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:09 | March | 2026 | 2026-04-24 10:36 | 46 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | April |  | 46 | 43 | 2026-04-01 | 22
202512-NM25-00598 | GDL17 | Residencial | 4.608 | Period | 2026-03-03 12:38 | March | 2026 | 2026-03-11 08:04 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 28
202512-NM25-00600 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 17:17 | January | 2026 | 2026-01-20 14:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-00605 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 17:44 | March | 2026 | 2026-03-19 10:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 13
202512-NM25-00612 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:31 | December | 2025 | 2026-01-09 15:50 | 9 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 9 | 0 | 2026-04-01 | 91
202512-NM25-00637 | GDL17 | Residencial | 23 | Period | 2026-03-18 14:19 | March | 2026 | 2026-03-25 10:06 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 13
202512-NM25-00645 | GDL17 | Residencial | 10 | Period | 2026-02-20 15:12 | February | 2026 | 2026-02-26 08:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-00650 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:38 | February | 2026 | 2026-02-18 13:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202512-NM25-00652 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-02 17:02 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 121 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 119
202512-NM25-00654 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 08:32 | February | 2026 | 2026-02-27 09:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 36
202512-NM25-00656 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:49 | February | 2026 | 2026-02-26 08:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-00661 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:28 | February | 2026 | 2026-02-26 13:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-00664 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:59 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 61
202512-NM25-00665 | GDL17 | Comercial | 11.5 | Period | 2026-01-15 17:41 | January | 2026 | 2026-01-21 14:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 75
202512-NM25-00686 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:14 | February | 2026 | 2026-02-27 10:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-00688 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:38 | March | 2026 | 2026-04-08 09:38 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 15 | 0 | 2026-04-01 | 8
202512-NM25-00690 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:07 | March | 2026 | 2026-03-27 15:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 8
202512-NM25-00704 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:57 | March | 2026 | 2026-03-23 10:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 15
202512-NM25-00705 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:01 | March | 2026 | 2026-03-30 15:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 8
202512-NM25-00711 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 11:48 | February | 2026 | 2026-02-16 14:56 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 12 | 0 | 2026-04-01 | 56
202512-NM25-00722 | GDL17 | Residencial | 3.8 | Period | 2026-02-06 09:22 | February | 2026 | 2026-02-10 15:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-00724 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:30 | February | 2026 | 2026-02-13 16:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 47
202512-NM25-00725 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:39 | March | 2026 | 2026-03-18 16:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 15
202512-NM25-00726 | GDL17 | Residencial | 7.6 | Period | 2026-01-05 11:12 | January | 2026 | 2026-01-13 16:19 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 86
202512-NM25-00730 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-09 08:01 | December | 2025 | 2026-03-09 15:13 | 90 | Study | Estudio (E) | Activated | Backlog |  | No | 90 |  | BAYAMON | March |  | 90 | 0 | 2026-04-01 | 113
202512-NM25-00733 | GDL17 | Residencial | 7.68 | Period | 2026-01-08 10:25 | January | 2026 | 2026-01-13 16:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-00743 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 08:17 | January | 2026 | 2026-01-26 14:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-00744 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-09 08:44 | December | 2025 | 2026-02-03 10:01 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | ARECIBO | February |  | 56 | 0 | 2026-04-01 | 113
202512-NM25-00760 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-09 15:18 | December | 2025 | 2026-02-05 15:52 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | SAN JUAN | February |  | 58 | 0 | 2026-04-01 | 112
202512-NM25-00770 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-24 10:22 | December | 2025 | 2026-03-27 11:19 | 93 | Study | Estudio (E) | Activated | Backlog |  | No | 93 |  | CAGUAS | March |  | 93 | 0 | 2026-04-01 | 98
202512-NM25-00774 | GDL17 | Residencial | 3.84 | Out of period | 2025-12-30 10:00 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 92
202512-NM25-00781 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:59 | February | 2026 | 2026-02-25 08:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-00797 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-16 08:41 | December | 2025 | 2026-02-24 11:24 | 70 | Study | Estudio (E) | Activated | Backlog |  | No | 70 |  | ARECIBO | February |  | 70 | 0 | 2026-04-01 | 106
202512-NM25-00800 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:39 | March | 2026 | 2026-03-26 08:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-00802 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-09 07:57 | December | 2025 | 2026-02-05 11:16 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | PONCE | February |  | 58 | 0 | 2026-04-01 | 113
202512-NM25-00830 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:06 | January | 2026 | 2026-01-13 08:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-00836 | GDL17 | Residencial | 4.992 | Period | 2026-02-04 13:03 | February | 2026 | 2026-02-25 13:49 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 55
202512-NM25-00841 | GDL17 | Residencial | 5.76 | Period | 2026-02-24 11:26 | February | 2026 | 2026-02-27 13:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 36
202512-NM25-00844 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 02:03 | February | 2026 | 2026-03-05 10:56 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 14 | 0 | 2026-04-01 | 40
202512-NM25-00852 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 18:48 | January | 2026 | 2026-01-28 15:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-00853 | GDL17 | Comercial | 23 | Period | 2026-02-19 16:26 | February | 2026 | 2026-02-25 08:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-00858 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 14:55 | March | 2026 | 2026-03-23 14:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 15
202512-NM25-00876 | GDL17 | Comercial | 12 | Period | 2026-03-17 13:10 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 14
202512-NM25-00887 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 14:25 | January | 2026 | 2026-02-02 10:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-00896 | GDL17 | Residencial | 7.6 | Period | 2026-03-02 22:02 | March | 2026 | 2026-03-05 15:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202512-NM25-00913 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 18:33 | February | 2026 | 2026-02-18 10:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 46
202512-NM25-00918 | GDL17 | Residencial | 8 | Period | 2026-01-14 07:43 | January | 2026 | 2026-01-20 10:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 77
202512-NM25-00925 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 08:29 | February | 2026 | 2026-02-16 11:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 47
202512-NM25-00927 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:29 | February | 2026 | 2026-02-26 08:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-00935 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 12:16 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 45
202512-NM25-00936 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 16:31 | February | 2026 | 2026-02-12 09:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 49
202512-NM25-00937 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 12:36 | March | 2026 | 2026-03-10 16:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 26
202512-NM25-00938 | GDL17 | Residencial | 10 | Period | 2026-01-22 14:30 | January | 2026 | 2026-03-03 14:21 | 40 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March |  | 40 | 0 | 2026-04-01 | 68
202512-NM25-00948 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:47 | February | 2026 | 2026-03-03 14:33 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 13 | 0 | 2026-04-01 | 42
202512-NM25-00960 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:17 | January | 2026 | 2026-01-16 14:15 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 81
202512-NM25-00962 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:09 | January | 2026 | 2026-01-26 08:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 72
202512-NM25-00972 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:03 | January | 2026 | 2026-01-26 13:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 69
202512-NM25-00976 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 11:01 | February | 2026 | 2026-02-06 14:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 55
202512-NM25-00981 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-04 09:19 | December | 2025 | 2026-03-19 16:53 | 105 | Study | Estudio (E) | Activated | Backlog |  | No | 105 |  | BAYAMON | March |  | 105 | 0 | 2026-04-01 | 118
202512-NM25-00990 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-04 09:31 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 124 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 118
202512-NM25-00992 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-10 15:22 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 111
202512-NM25-01000 | GDL17 | Residencial | 3.84 | Period | 2026-02-27 13:54 | February | 2026 | 2026-03-04 13:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 32
202512-NM25-01002 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:46 | January | 2026 | 2026-02-03 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 61
202512-NM25-01003 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-04 10:50 | December | 2025 | 2026-02-13 08:40 | 71 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 6 | 65 | 2026-04-01 | 118
202512-NM25-01010 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:45 | January | 2026 | 2026-01-23 15:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 68
202512-NM25-01011 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 17:54 | February | 2026 | 2026-03-06 10:08 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 36
202512-NM25-01019 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:19 | February | 2026 | 2026-02-11 14:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 50
202512-NM25-01030 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:25 | February | 2026 | 2026-02-05 16:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 56
202512-NM25-01036 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 10:15 | February | 2026 | 2026-02-11 09:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 51
202512-NM25-01038 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:00 | March | 2026 | 2026-03-23 07:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 15
202512-NM25-01042 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:22 | January | 2026 | 2026-01-08 14:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 88
202512-NM25-01052 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:15 | March | 2026 | 2026-03-04 14:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 29
202512-NM25-01055 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:54 | February | 2026 | 2026-02-23 14:11 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 20 | 0 | 2026-04-01 | 56
202512-NM25-01056 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:57 | February | 2026 | 2026-02-26 14:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-01068 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:01 | January | 2026 | 2026-01-26 15:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-01069 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:46 | February | 2026 | 2026-03-02 09:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 35
202512-NM25-01070 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:52 | January | 2026 | 2026-03-27 10:53 | 63 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March |  | 63 | 0 | 2026-04-01 | 68
202512-NM25-01074 | GDL17 | Residencial | 6.912 | Out of period | 2025-12-05 11:00 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 126 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 117
202512-NM25-01076 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 09:26 | March | 2026 | 2026-03-18 11:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 16
202512-NM25-01078 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 08:50 | January | 2026 | 2026-01-13 14:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-01081 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:22 | March | 2026 | 2026-03-10 08:41 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 29
202512-NM25-01087 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:39 | January | 2026 | 2026-01-30 08:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 62
202512-NM25-01088 | GDL17 | Residencial | 10.752 | Period | 2026-02-25 15:25 | February | 2026 | 2026-03-03 11:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 3 | 3 | 2026-04-01 | 34
202512-NM25-01092 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:43 | March | 2026 | 2026-03-25 15:00 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 3 | 18 | 2026-04-01 | 27
202512-NM25-01094 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:51 | February | 2026 | 2026-02-09 10:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 57
202512-NM25-01098 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:53 | February | 2026 | 2026-02-12 14:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 54
202512-NM25-01101 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:03 | March | 2026 | 2026-03-06 07:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 30
202512-NM25-01107 | GDL17 | Comercial | 11.5 | Period | 2026-02-20 13:10 | February | 2026 | 2026-02-25 14:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-01111 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-12 15:02 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 109
202512-NM25-01114 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 21:19 | January | 2026 | 2026-02-04 09:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-01118 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 07:35 | March | 2026 | 2026-03-23 09:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 15
202512-NM25-01122 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:34 | January | 2026 | 2026-01-14 15:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-01127 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:20 | March | 2026 | 2026-03-27 10:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-01130 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:12 | January | 2026 | 2026-01-29 12:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-01146 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 13:21 | March | 2026 | 2026-03-18 15:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202512-NM25-01150 | GDL17 | Residencial | 11.5 | Period | 2026-01-12 07:45 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 79
202512-NM25-01159 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 18:37 | January | 2026 | 2026-02-03 11:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 61
202512-NM25-01164 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:39 | January | 2026 | 2026-01-13 09:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-01169 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 12:34 | January | 2026 | 2026-01-09 09:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 83
202512-NM25-01179 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 17:07 | February | 2026 | 2026-03-04 11:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 34
202512-NM25-01180 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:24 | March | 2026 | 2026-03-12 14:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202512-NM25-01188 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:04 | March | 2026 | 2026-03-05 10:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 29
202512-NM25-01191 | GDL17 | Residencial | 23 | Period | 2026-01-30 18:11 | January | 2026 | 2026-02-12 13:27 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 13 | 0 | 2026-04-01 | 60
202512-NM25-01192 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:07 | March | 2026 | 2026-04-14 14:50 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 35 | 34 | 2026-04-01 | 22
202512-NM25-01194 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 17:54 | January | 2026 | 2026-01-23 16:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202512-NM25-01196 | GDL17 | Residencial | 6.8 | Period | 2026-01-09 11:15 | January | 2026 | 2026-02-24 16:08 | 46 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | February | 1 | 10 | 36 | 2026-04-01 | 82
202512-NM25-01200 | GDL17 | Residencial | 9 | Period | 2026-01-08 11:44 | January | 2026 | 2026-01-13 08:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-01204 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 07:31 | January | 2026 | 2026-01-27 09:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-01205 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:25 | January | 2026 | 2026-01-21 11:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 72
202512-NM25-01209 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:51 | January | 2026 | 2026-01-12 13:51 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 10 | 0 | 2026-04-01 | 88
202512-NM25-01210 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:14 | January | 2026 | 2026-01-13 10:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-01211 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:09 | January | 2026 | 2026-03-06 13:48 | 63 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March | 2 | 6 | 57 | 2026-04-01 | 88
202512-NM25-01212 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:35 | January | 2026 | 2026-01-14 16:08 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 12 | 0 | 2026-04-01 | 88
202512-NM25-01214 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:58 | January | 2026 | 2026-01-14 14:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 84
202512-NM25-01217 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 08:49 | January | 2026 | 2026-01-13 15:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-01218 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:29 | January | 2026 | 2026-01-22 10:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 75
202512-NM25-01219 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:26 | January | 2026 | 2026-01-14 15:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-01239 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:40 | January | 2026 | 2026-01-29 10:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-01244 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 13:21 | March | 2026 | 2026-03-19 17:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 14
202512-NM25-01245 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-12 11:13 | December | 2025 | 2026-03-26 16:10 | 104 | Study | Estudio (E) | Activated | Backlog |  | No | 104 |  | PONCE | March |  | 104 | 0 | 2026-04-01 | 110
202512-NM25-01246 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-10 10:06 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 112
202512-NM25-01248 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:04 | February | 2026 | 2026-02-17 15:42 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 12 | 0 | 2026-04-01 | 54
202512-NM25-01250 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-10 13:30 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 118 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 111
202512-NM25-01251 | GDL17 | Residencial | 4.608 | Period | 2026-01-28 10:31 | January | 2026 | 2026-01-30 16:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-01254 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 09:59 | January | 2026 | 2026-01-09 09:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 89
202512-NM25-01257 | GDL17 | Residencial | 3.84 | Period | 2026-01-26 10:35 | January | 2026 | 2026-01-27 12:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-01260 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:10 | January | 2026 | 2026-01-13 08:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-01264 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:33 | January | 2026 | 2026-02-02 09:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 63
202512-NM25-01267 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:41 | January | 2026 | 2026-01-20 12:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-01270 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:50 | March | 2026 | 2026-03-26 10:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-01272 | GDL17 | Residencial | 3.84 | Period | 2026-01-26 11:25 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 65
202512-NM25-01273 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-05 11:25 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 117
202512-NM25-01276 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:18 | January | 2026 | 2026-01-20 15:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-01280 | GDL17 | Residencial | 6.912 | Period | 2026-02-25 17:53 | February | 2026 | 2026-03-02 10:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-01282 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:02 | January | 2026 | 2026-01-19 11:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-01284 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:29 | February | 2026 | 2026-02-12 14:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202512-NM25-01286 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 08:57 | March | 2026 | 2026-03-17 11:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 16
202512-NM25-01287 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:01 | February | 2026 | 2026-02-27 09:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-01298 | GDL17 | Residencial | 7.68 | Period | 2026-03-09 16:44 | March | 2026 | 2026-03-12 09:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 22
202512-NM25-01299 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:51 | March | 2026 | 2026-03-23 13:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 14
202512-NM25-01305 | GDL17 | Residencial | 14.592 | Period | 2026-02-11 11:34 | February | 2026 | 2026-02-17 16:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 49
202512-NM25-01309 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 09:43 | February | 2026 | 2026-02-11 09:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 51
202512-NM25-01313 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:40 | January | 2026 | 2026-01-28 10:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-01315 | GDL17 | Comercial | 11.5 | Period | 2026-03-17 07:38 | March | 2026 | 2026-03-19 16:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 15
202512-NM25-01319 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:29 | January | 2026 | 2026-01-14 14:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 84
202512-NM25-01331 | GDL17 | Residencial | 6 | Period | 2026-03-24 10:22 | March | 2026 | 2026-03-27 14:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-01335 | GDL17 | Residencial | 11.52 | Period | 2026-03-17 15:57 | March | 2026 | 2026-03-18 15:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 14
202512-NM25-01336 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:10 | March | 2026 | 2026-04-08 07:59 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 9 | 0 | 2026-04-01 | 2
202512-NM25-01338 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-22 13:07 | December | 2025 | 2026-03-23 10:49 | 91 | Study | Estudio (E) | Activated | Backlog |  | No | 91 |  | BAYAMON | March |  | 91 | 0 | 2026-04-01 | 99
202512-NM25-01344 | GDL17 | Residencial | 7.6 | Period | 2026-02-16 11:28 | February | 2026 | 2026-02-25 13:22 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 44
202512-NM25-01346 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 18:27 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 35
202512-NM25-01349 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:45 | January | 2026 | 2026-01-30 08:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 68
202512-NM25-01351 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 19:39 | February | 2026 | 2026-02-10 13:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 54
202512-NM25-01353 | GDL17 | Residencial | 23 | Period | 2026-02-26 15:15 | February | 2026 | 2026-03-03 14:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202512-NM25-01371 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:52 | January | 2026 | 2026-02-09 14:04 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 72
202512-NM25-01375 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 07:20 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 15
202512-NM25-01376 | GDL17 | Residencial | 7.6 | Period | 2026-02-06 07:58 | February | 2026 | 2026-02-10 10:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-01391 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:05 | January | 2026 | 2026-02-02 11:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-01396 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:55 | February | 2026 | 2026-02-18 08:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 46
202512-NM25-01401 | GDL17 | Residencial | 3.84 | Period | 2026-01-23 10:47 | January | 2026 | 2026-01-29 08:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 68
202512-NM25-01407 | GDL17 | Residencial | 23 | Period | 2026-01-08 16:21 | January | 2026 | 2026-01-20 09:46 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | January | 1 | 6 | 6 | 2026-04-01 | 82
202512-NM25-01415 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:32 | January | 2026 | 2026-01-30 09:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 64
202512-NM25-01417 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 19:00 | January | 2026 | 2026-01-16 14:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202512-NM25-01424 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 13:44 | March | 2026 | 2026-03-17 10:05 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 25
202512-NM25-01431 | GDL17 | Residencial | 19.1 | Out of period | 2025-12-15 13:43 | December | 2025 | 2026-02-19 10:11 | 66 | Study | Estudio (E) | Activated | Backlog |  | No | 66 |  | PONCE | February |  | 66 | 0 | 2026-04-01 | 106
202512-NM25-01436 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:37 | March | 2026 | 2026-03-12 14:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202512-NM25-01452 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 17:09 | March | 2026 | 2026-03-06 13:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202512-NM25-01453 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 22:56 | February | 2026 | 2026-02-26 08:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 38
202512-NM25-01455 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 01:55 | February | 2026 | 2026-02-23 09:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 42
202512-NM25-01465 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:29 | January | 2026 | 2026-01-15 15:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-01472 | GDL17 | Residencial | 7.6 | Period | 2026-01-05 12:24 | January | 2026 | 2026-01-21 13:50 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 16 | 0 | 2026-04-01 | 85
202512-NM25-01478 | GDL17 | Residencial | 15 | Period | 2026-01-28 15:35 | January | 2026 | 2026-01-30 09:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 62
202512-NM25-01487 | GDL17 | Residencial | 21.38 | Out of period | 2025-12-22 13:51 | December | 2025 | 2026-03-16 15:35 | 84 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 4 | 8 | 76 | 2026-04-01 | 99
202512-NM25-01490 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 10:58 | January | 2026 | 2026-01-28 17:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 68
202512-NM25-01496 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:05 | January | 2026 | 2026-01-21 14:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 74
202512-NM25-01497 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:37 | January | 2026 | 2026-01-15 07:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-01502 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:35 | February | 2026 | 2026-02-23 09:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 43
202512-NM25-01519 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 16:03 | February | 2026 | 2026-02-13 16:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 47
202512-NM25-01520 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:45 | January | 2026 | 2026-01-19 08:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 77
202512-NM25-01521 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 09:21 | February | 2026 | 2026-02-11 08:23 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 9 | 0 | 2026-04-01 | 58
202512-NM25-01525 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-12 09:30 | December | 2025 | 2026-02-03 09:22 | 53 | Study | Estudio (E) | Activated | Backlog |  | No | 53 |  | ARECIBO | February |  | 53 | 0 | 2026-04-01 | 110
202512-NM25-01530 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 10:31 | March | 2026 | 2026-03-11 08:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 23
202512-NM25-01535 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 08:58 | January | 2026 | 2026-02-03 13:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-01539 | GDL17 | Residencial | 5.76 | Period | 2026-01-05 09:47 | January | 2026 | 2026-01-09 08:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 86
202512-NM25-01554 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-08 09:13 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 114
202512-NM25-01556 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:17 | February | 2026 | 2026-02-18 11:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 47
202512-NM25-01565 | GDL17 | Residencial | 8 | Period | 2026-01-14 10:47 | January | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 77
202512-NM25-01591 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 09:55 | February | 2026 | 2026-02-13 12:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 49
202512-NM25-01597 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:02 | January | 2026 | 2026-01-13 12:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-01607 | GDL17 | Residencial | 8 | Period | 2026-01-14 10:29 | January | 2026 | 2026-03-06 08:23 | 51 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 51 | 0 | 2026-04-01 | 77
202512-NM25-01609 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 08:57 | January | 2026 | 2026-01-30 11:13 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 15 | 0 | 2026-04-01 | 76
202512-NM25-01611 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:10 | January | 2026 | 2026-01-09 08:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-01612 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:10 | January | 2026 | 2026-01-13 08:27 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 10 | 0 | 2026-04-01 | 89
202512-NM25-01615 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:24 | March | 2026 | 2026-03-27 11:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 8
202512-NM25-01617 | GDL17 | Residencial | 3.84 | Period | 2026-01-02 12:56 | January | 2026 | 2026-01-12 13:37 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 10 | 0 | 2026-04-01 | 88
202512-NM25-01618 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:25 | January | 2026 | 2026-01-12 16:26 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 10 | 0 | 2026-04-01 | 88
202512-NM25-01622 | GDL17 | Residencial | 3.84 | Period | 2026-01-22 11:27 | January | 2026 | 2026-01-28 15:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 69
202512-NM25-01624 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:14 | January | 2026 | 2026-01-21 16:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-01627 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:22 | January | 2026 | 2026-02-04 13:08 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 2 | 11 | 2026-04-01 | 69
202512-NM25-01639 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:43 | January | 2026 | 2026-02-04 11:11 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 77
202512-NM25-01644 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:38 | January | 2026 | 2026-01-16 11:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 81
202512-NM25-01645 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:05 | January | 2026 | 2026-01-21 13:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-01647 | GDL17 | Residencial | 23 | Period | 2026-01-15 09:40 | January | 2026 | 2026-01-16 15:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-01649 | GDL17 | Residencial | 8 | Period | 2026-01-05 10:46 | January | 2026 | 2026-01-09 09:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 86
202512-NM25-01654 | GDL17 | Residencial | 23 | Out of period | 2025-12-11 15:13 | December | 2025 | 2026-02-02 13:18 | 53 | Study | Estudio (E) | Activated | Backlog |  | No | 53 |  | BAYAMON | February |  | 53 | 0 | 2026-04-01 | 110
202512-NM25-01656 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:52 | February | 2026 | 2026-02-10 15:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 56
202512-NM25-01660 | GDL17 | Residencial | 8 | Period | 2026-02-02 11:43 | February | 2026 | 2026-02-04 09:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 58
202512-NM25-01669 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 16:15 | March | 2026 | 2026-03-30 10:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202512-NM25-01673 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:02 | January | 2026 | 2026-01-13 11:25 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 11 | 0 | 2026-04-01 | 89
202512-NM25-01675 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:01 | February | 2026 | 2026-02-06 12:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-01678 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:16 | December | 2025 | 2026-01-09 08:44 | 9 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 91
202512-NM25-01679 | GDL17 | Residencial | 3.84 | Period | 2026-02-03 09:11 | February | 2026 | 2026-02-05 12:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-01693 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:43 | January | 2026 | 2026-01-30 14:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 64
202512-NM25-01696 | GDL17 | Residencial | 3.84 | Period | 2026-01-15 12:18 | January | 2026 | 2026-01-20 14:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-01704 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:52 | January | 2026 | 2026-01-14 10:42 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 12 | 0 | 2026-04-01 | 88
202512-NM25-01716 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:51 | March | 2026 | 2026-03-06 16:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 26
202512-NM25-01728 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:21 | January | 2026 | 2026-01-28 09:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 65
202512-NM25-01730 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 15:43 | February | 2026 | 2026-02-10 12:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202512-NM25-01731 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 08:58 | January | 2026 | 2026-01-13 09:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-01733 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:47 | January | 2026 | 2026-01-19 13:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-01740 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:11 | February | 2026 | 2026-03-02 09:54 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 42
202512-NM25-01750 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 15:02 | February | 2026 | 2026-02-12 07:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 54
202512-NM25-01755 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:10 | January | 2026 | 2026-01-26 10:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 69
202512-NM25-01767 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:47 | February | 2026 | 2026-02-10 08:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 54
202512-NM25-01770 | GDL17 | Comercial | 7.6 | Period | 2026-01-13 22:07 | January | 2026 | 2026-01-15 09:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-01772 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 08:39 | January | 2026 | 2026-01-28 13:23 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 13 | 0 | 2026-04-01 | 76
202512-NM25-01774 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:33 | January | 2026 | 2026-02-09 10:24 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 20 | 0 | 2026-04-01 | 71
202512-NM25-01788 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:36 | January | 2026 | 2026-01-29 16:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 63
202512-NM25-01791 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:41 | January | 2026 | 2026-01-21 10:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-01792 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 08:36 | January | 2026 | 2026-01-29 10:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 65
202512-NM25-01794 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:03 | January | 2026 | 2026-01-29 17:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 65
202512-NM25-01798 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:37 | January | 2026 | 2026-01-26 14:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-01799 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 09:00 | January | 2026 | 2026-02-04 11:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 62
202512-NM25-01804 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 09:34 | March | 2026 | 2026-03-19 15:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 16
202512-NM25-01806 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:32 | December | 2025 | 2026-01-05 10:06 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-01810 | GDL17 | Residencial | 7.296 | Period | 2026-01-27 09:00 | January | 2026 | 2026-01-30 15:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 64
202512-NM25-01811 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 11:20 | January | 2026 | 2026-01-30 12:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-01814 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-22 10:09 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 100
202512-NM25-01816 | GDL17 | Residencial | 5.76 | Period | 2026-02-05 11:00 | February | 2026 | 2026-02-09 16:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-01817 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-08 15:58 | December | 2025 | 2026-02-10 12:53 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | ARECIBO | February |  | 64 | 0 | 2026-04-01 | 113
202512-NM25-01819 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-08 16:03 | December | 2025 | 2026-02-02 15:23 | 56 | Study | Estudio (E) | Activated | Backlog |  | No | 56 |  | SAN JUAN | February |  | 56 | 0 | 2026-04-01 | 113
202512-NM25-01823 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:26 | January | 2026 | 2026-03-03 13:00 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 35 | 0 | 2026-04-01 | 63
202512-NM25-01829 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:31 | February | 2026 | 2026-03-04 09:34 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 15 | 0 | 2026-04-01 | 42
202512-NM25-01832 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 08:14 | January | 2026 | 2026-02-02 14:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 61
202512-NM25-01837 | GDL17 | Residencial | 3.84 | Period | 2026-01-02 11:04 | January | 2026 | 2026-01-08 13:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 89
202512-NM25-01839 | GDL17 | Residencial | 11.4 | Period | 2026-02-20 12:54 | February | 2026 | 2026-02-25 15:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-01844 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 19:57 | February | 2026 | 2026-02-18 10:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 45
202512-NM25-01845 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 19:28 | January | 2026 | 2026-01-23 14:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202512-NM25-01847 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:52 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 43
202512-NM25-01856 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:25 | February | 2026 | 2026-03-05 11:19 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 37
202512-NM25-01857 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:48 | March | 2026 | 2026-03-20 13:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 14
202512-NM25-01862 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:38 | January | 2026 | 2026-01-22 08:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-01864 | GDL17 | Residencial | 6.8 | Period | 2026-02-25 10:32 | February | 2026 | 2026-03-02 11:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 35
202512-NM25-01866 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:46 | January | 2026 | 2026-02-02 14:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-01867 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:58 | February | 2026 | 2026-02-09 12:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-01871 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:23 | January | 2026 | 2026-01-27 13:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-01880 | GDL17 | Residencial | 23 | Period | 2026-01-23 11:11 | January | 2026 | 2026-02-10 15:29 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 18 | 0 | 2026-04-01 | 68
202512-NM25-01886 | GDL17 | Residencial | 3.84 | Period | 2026-01-07 11:33 | January | 2026 | 2026-01-12 15:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-01892 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:21 | January | 2026 | 2026-01-29 10:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-01897 | GDL17 | Residencial | 4.608 | Period | 2026-01-02 09:29 | January | 2026 | 2026-01-07 10:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 89
202512-NM25-01904 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:25 | February | 2026 | 2026-02-26 09:06 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 42
202512-NM25-01906 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:22 | February | 2026 | 2026-02-19 13:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 44
202512-NM25-01907 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:32 | January | 2026 | 2026-01-08 14:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 88
202512-NM25-01908 | GDL17 | Residencial | 3.84 | Period | 2026-01-02 14:20 | January | 2026 | 2026-01-08 09:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 88
202512-NM25-01909 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:13 | January | 2026 | 2026-01-08 08:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-01910 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:20 | January | 2026 | 2026-01-09 10:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 83
202512-NM25-01917 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:38 | January | 2026 | 2026-01-13 15:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-01920 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:03 | January | 2026 | 2026-01-12 15:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-01923 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:08 | January | 2026 | 2026-01-13 15:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-01929 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 08:36 | January | 2026 | 2026-01-19 09:52 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 11 | 0 | 2026-04-01 | 83
202512-NM25-01931 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:38 | January | 2026 | 2026-02-10 08:43 | 32 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 31 | 0 | 2026-04-01 | 82
202512-NM25-01947 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:43 | February | 2026 | 2026-02-12 08:29 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 55
202512-NM25-01949 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:15 | January | 2026 | 2026-01-16 13:34 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-01952 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:27 | January | 2026 | 2026-01-20 16:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-01956 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:20 | February | 2026 | 2026-02-16 14:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 47
202512-NM25-01964 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:42 | January | 2026 | 2026-01-20 15:24 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-01965 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:06 | January | 2026 | 2026-01-26 09:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 70
202512-NM25-01966 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-26 12:49 | December | 2025 | 2026-03-30 10:37 | 94 | Study | Estudio (E) | Activated | Backlog |  | No | 94 |  | CAGUAS | March |  | 94 | 0 | 2026-04-01 | 95
202512-NM25-01974 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:50 | January | 2026 | 2026-01-21 07:47 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 82
202512-NM25-01975 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 14:01 | January | 2026 | 2026-01-14 16:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-01981 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:39 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 34
202512-NM25-01982 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:49 | February | 2026 | 2026-03-12 09:43 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 22 | 0 | 2026-04-01 | 41
202512-NM25-01983 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:34 | January | 2026 | 2026-01-19 10:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-01984 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:53 | January | 2026 | 2026-02-04 13:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 62
202512-NM25-01989 | GDL17 | Residencial | 23 | Period | 2026-01-09 14:43 | January | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 81
202512-NM25-01991 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:41 | January | 2026 | 2026-01-30 10:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 64
202512-NM25-01992 | GDL17 | Residencial | 22.8 | Period | 2026-03-11 12:09 | March | 2026 | 2026-04-22 14:47 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 42 | 2 | 2026-04-01 | 20
202512-NM25-01997 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:07 | January | 2026 | 2026-01-16 08:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 81
202512-NM25-02006 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:37 | December | 2025 | 2026-01-15 15:28 | 15 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 15 | 0 | 2026-04-01 | 91
202512-NM25-02010 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-09 10:06 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 113
202512-NM25-02015 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:10 | December | 2025 | 2026-01-05 14:47 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-02017 | GDL17 | Residencial | 22.8 | Period | 2026-03-11 12:11 | March | 2026 | 2026-04-22 14:51 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 42 | 2 | 2026-04-01 | 20
202512-NM25-02018 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:14 | January | 2026 | 2026-02-10 14:53 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 14 | 0 | 2026-04-01 | 63
202512-NM25-02019 | GDL17 | Residencial | 8 | Period | 2026-02-18 12:17 | February | 2026 | 2026-02-23 14:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 41
202512-NM25-02020 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 11:00 | March | 2026 | 2026-03-27 11:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-02026 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:42 | March | 2026 | 2026-03-19 14:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 15
202512-NM25-02037 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:52 | January | 2026 | 2026-01-12 14:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-02039 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 19:13 | February | 2026 | 2026-02-10 11:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 54
202512-NM25-02041 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 20:43 | January | 2026 | 2026-01-13 08:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-02055 | GDL17 | Comercial | 23 | Out of period | 2025-12-31 10:44 | December | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 91
202512-NM25-02056 | GDL17 | Residencial | 8 | Period | 2026-01-05 12:05 | January | 2026 | 2026-01-09 15:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 85
202512-NM25-02059 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:22 | February | 2026 | 2026-03-06 08:00 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 34
202512-NM25-02064 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-09 16:05 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 112
202512-NM25-02065 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:22 | January | 2026 | 2026-02-04 13:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 61
202512-NM25-02069 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 13:14 | March | 2026 | 2026-03-20 14:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 13
202512-NM25-02076 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:26 | January | 2026 | 2026-01-15 08:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-02078 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:24 | January | 2026 | 2026-01-14 14:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-02079 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:54 | January | 2026 | 2026-01-20 14:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 77
202512-NM25-02080 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:21 | January | 2026 | 2026-02-03 08:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 62
202512-NM25-02084 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 12:17 | February | 2026 | 2026-03-03 11:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202512-NM25-02086 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:03 | January | 2026 | 2026-01-15 11:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-02092 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:31 | January | 2026 | 2026-01-19 12:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 74
202512-NM25-02094 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:01 | February | 2026 | 2026-02-16 09:43 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 54
202512-NM25-02097 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 07:33 | January | 2026 | 2026-01-19 15:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-02098 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 18:57 | January | 2026 | 2026-02-04 10:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 61
202512-NM25-02099 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 10:03 | February | 2026 | 2026-02-05 15:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 58
202512-NM25-02104 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 17:02 | January | 2026 | 2026-02-06 15:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 60
202512-NM25-02106 | GDL17 | Residencial | 7.259 | Period | 2026-01-15 15:19 | January | 2026 | 2026-01-21 16:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | January | 1 | 2 | 4 | 2026-04-01 | 75
202512-NM25-02107 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:28 | January | 2026 | 2026-02-05 09:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 61
202512-NM25-02113 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:23 | February | 2026 | 2026-02-23 09:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202512-NM25-02118 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-16 09:30 | December | 2025 | 2026-02-03 09:27 | 49 | Study | Estudio (E) | Activated | Backlog |  | No | 49 |  | ARECIBO | February |  | 49 | 0 | 2026-04-01 | 106
202512-NM25-02120 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:31 | February | 2026 | 2026-02-17 10:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202512-NM25-02121 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 17:24 | February | 2026 | 2026-02-17 14:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 47
202512-NM25-02122 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 17:45 | February | 2026 | 2026-02-20 15:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 43
202512-NM25-02125 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:09 | February | 2026 | 2026-02-18 10:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202512-NM25-02126 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 17:02 | February | 2026 | 2026-02-26 10:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 36
202512-NM25-02132 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 17:39 | February | 2026 | 2026-02-24 07:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202512-NM25-02134 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-19 09:25 | December | 2025 | 2026-03-13 16:26 | 84 | Study | Estudio (E) | Activated | Backlog |  | No | 84 |  | MAYAGUEZ | March |  | 84 | 0 | 2026-04-01 | 103
202512-NM25-02135 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:15 | March | 2026 | 2026-04-08 10:41 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 22 | 0 | 2026-04-01 | 15
202512-NM25-02138 | GDL17 | Residencial | 14.5 | Period | 2026-02-05 13:16 | February | 2026 | 2026-02-09 12:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-02141 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:00 | January | 2026 | 2026-01-12 15:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-02143 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:11 | February | 2026 | 2026-03-05 09:33 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 35
202512-NM25-02144 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:28 | February | 2026 | 2026-02-09 08:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-02147 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:51 | February | 2026 | 2026-03-04 10:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202512-NM25-02154 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 20:20 | March | 2026 | 2026-03-06 10:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 28
202512-NM25-02155 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:19 | February | 2026 | 2026-02-27 09:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-02157 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:57 | March | 2026 | 2026-03-09 10:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 29
202512-NM25-02159 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 12:57 | March | 2026 | 2026-04-07 13:42 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 7 | 0 | 2026-04-01 | 0
202512-NM25-02167 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:49 | March | 2026 | 2026-03-27 10:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 8
202512-NM25-02177 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:30 | December | 2025 | 2026-01-05 13:15 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-02179 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:50 | February | 2026 | 2026-02-25 09:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 40
202512-NM25-02181 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-11 13:33 | December | 2025 | 2026-02-02 09:12 | 53 | Study | Estudio (E) | Activated | Backlog |  | No | 53 |  | CAGUAS | February |  | 53 | 0 | 2026-04-01 | 110
202512-NM25-02186 | GDL17 | Residencial | 7.68 | Period | 2026-01-09 10:35 | January | 2026 | 2026-01-21 15:14 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 12 | 0 | 2026-04-01 | 82
202512-NM25-02187 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:08 | February | 2026 | 2026-02-25 12:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-02188 | GDL17 | Residencial | 7.68 | Period | 2026-01-16 13:45 | January | 2026 | 2026-01-20 10:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-02189 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:39 | December | 2025 | 2026-01-16 16:01 | 16 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 16 | 0 | 2026-04-01 | 91
202512-NM25-02191 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:22 | March | 2026 | 2026-04-06 10:05 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 27 | 0 | 2026-04-01 | 22
202512-NM25-02193 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 16:43 | February | 2026 | 2026-02-06 11:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-02195 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:44 | December | 2025 | 2026-01-07 09:10 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-02198 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:15 | December | 2025 | 2026-01-07 13:16 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-02201 | GDL17 | Residencial | 23 | Period | 2026-01-07 10:49 | January | 2026 | 2026-01-30 12:41 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 23 | 0 | 2026-04-01 | 84
202512-NM25-02202 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:07 | January | 2026 | 2026-01-19 16:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-02203 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:21 | March | 2026 | 2026-03-06 08:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202512-NM25-02223 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 08:40 | January | 2026 | 2026-02-02 10:53 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 10 | 0 | 2026-04-01 | 68
202512-NM25-02234 | GDL17 | Residencial | 6.144 | Period | 2026-01-07 10:46 | January | 2026 | 2026-01-12 15:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-02238 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 07:56 | March | 2026 | 2026-03-18 13:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202512-NM25-02239 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:50 | January | 2026 | 2026-01-21 15:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 75
202512-NM25-02241 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:32 | January | 2026 | 2026-01-20 14:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-02245 | GDL17 | Residencial | 10.812 | Period | 2026-02-03 14:18 | February | 2026 | 2026-02-06 11:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-02252 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:43 | December | 2025 | 2026-01-08 15:39 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-02255 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 09:09 | March | 2026 | 2026-03-30 07:40 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 11 | 0 | 2026-04-01 | 13
202512-NM25-02270 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:09 | February | 2026 | 2026-02-06 14:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-02273 | GDL17 | Residencial | 8 | Out of period | 2025-12-12 13:51 | December | 2025 | 2026-03-26 16:11 | 104 | Study | Estudio (E) | Activated | Backlog |  | No | 104 |  | ARECIBO | March |  | 104 | 0 | 2026-04-01 | 109
202512-NM25-02276 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:47 | January | 2026 | 2026-01-28 13:22 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 13 | 0 | 2026-04-01 | 76
202512-NM25-02278 | GDL17 | Residencial | 13.44 | Period | 2026-02-27 10:51 | February | 2026 | 2026-03-03 14:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 33
202512-NM25-02282 | GDL17 | Residencial | 6.818 | Period | 2026-01-26 15:46 | January | 2026 | 2026-01-28 10:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-02285 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-12 09:15 | December | 2025 | 2026-03-17 07:53 | 95 | Study | Estudio (E) | Activated | Backlog |  | No | 95 |  | BAYAMON | March |  | 95 | 0 | 2026-04-01 | 110
202512-NM25-02293 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:21 | February | 2026 | 2026-02-25 14:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-02296 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:34 | February | 2026 | 2026-02-05 13:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 56
202512-NM25-02297 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:22 | February | 2026 | 2026-02-25 11:06 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 41
202512-NM25-02302 | GDL17 | Residencial | 8 | Period | 2026-01-14 09:49 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 77
202512-NM25-02307 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-29 10:05 | December | 2025 | 2026-02-16 10:04 | 49 | Study | Estudio (E) | Activated | Backlog |  | No | 49 |  | BAYAMON | February |  | 49 | 0 | 2026-04-01 | 93
202512-NM25-02309 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 13:49 | March | 2026 | 2026-03-05 16:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 28
202512-NM25-02313 | GDL17 | Residencial | 6.732 | Out of period | 2025-12-10 11:20 | December | 2025 | 2026-03-26 16:09 | 106 | Study | Estudio (E) | Activated | Backlog |  | No | 106 |  | BAYAMON | March |  | 106 | 0 | 2026-04-01 | 112
202512-NM25-02315 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:15 | February | 2026 | 2026-03-03 15:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 33
202512-NM25-02316 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:11 | February | 2026 | 2026-02-10 16:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 56
202512-NM25-02318 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:11 | January | 2026 | 2026-01-26 11:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-02319 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:05 | January | 2026 | 2026-02-04 10:41 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 77
202512-NM25-02320 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:18 | January | 2026 | 2026-03-25 13:18 | 70 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 70 | 0 | 2026-04-01 | 77
202512-NM25-02327 | GDL17 | Residencial | 23 | Period | 2026-01-23 09:44 | January | 2026 | 2026-01-26 15:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-02328 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:55 | January | 2026 | 2026-02-02 08:55 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 17 | 0 | 2026-04-01 | 75
202512-NM25-02329 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:37 | January | 2026 | 2026-01-20 10:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-02330 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:03 | January | 2026 | 2026-01-14 11:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-02332 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 19:53 | January | 2026 | 2026-02-03 13:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 60
202512-NM25-02334 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-16 14:04 | December | 2025 | 2026-02-06 15:53 | 52 | Study | Estudio (E) | Activated | Backlog |  | No | 52 |  | BAYAMON | February |  | 52 | 0 | 2026-04-01 | 105
202512-NM25-02335 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:32 | February | 2026 | 2026-03-09 13:50 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 21 | 0 | 2026-04-01 | 49
202512-NM25-02336 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:29 | January | 2026 | 2026-01-09 08:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-02338 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:58 | January | 2026 | 2026-01-26 14:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-02341 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:41 | February | 2026 | 2026-02-12 13:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202512-NM25-02348 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:28 | February | 2026 | 2026-02-27 10:05 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 11 | 0 | 2026-04-01 | 43
202512-NM25-02354 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 18:58 | January | 2026 | 2026-02-04 14:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 61
202512-NM25-02355 | GDL17 | Comercial | 11.5 | Period | 2026-02-23 13:15 | February | 2026 | 2026-03-04 10:38 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 36
202512-NM25-02357 | GDL17 | Residencial | 8 | Period | 2026-01-28 08:50 | January | 2026 | 2026-02-04 08:30 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 63
202512-NM25-02366 | GDL17 | Residencial | 23 | Period | 2026-03-10 18:32 | March | 2026 | 2026-03-16 07:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 21
202512-NM25-02371 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-11 14:44 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 110
202512-NM25-02375 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 14:30 | February | 2026 | 2026-02-18 14:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 45
202512-NM25-02376 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:56 | February | 2026 | 2026-02-25 15:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-02388 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 15:13 | January | 2026 | 2026-01-26 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 68
202512-NM25-02391 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 19:27 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 34
202512-NM25-02397 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:58 | February | 2026 | 2026-03-06 15:04 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 23 | 0 | 2026-04-01 | 48
202512-NM25-02406 | GDL17 | Residencial | 12 | Out of period | 2025-12-31 09:53 | December | 2025 | 2026-01-07 13:24 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-02408 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:32 | February | 2026 | 2026-02-26 08:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 37
202512-NM25-02409 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 19:50 | February | 2026 | 2026-02-25 07:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 41
202512-NM25-02412 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 10:52 | February | 2026 | 2026-02-20 08:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202512-NM25-02414 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 14:52 | February | 2026 | 2026-02-27 09:49 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 40
202512-NM25-02415 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 17:22 | February | 2026 | 2026-02-23 09:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202512-NM25-02416 | GDL17 | Residencial | 17.722 | Period | 2026-03-02 11:00 | March | 2026 | 2026-03-04 09:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 30
202512-NM25-02423 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:20 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 57
202512-NM25-02427 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:30 | January | 2026 | 2026-01-07 14:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 89
202512-NM25-02430 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:23 | January | 2026 | 2026-01-19 11:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-02434 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:48 | January | 2026 | 2026-01-13 15:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-02436 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:02 | March | 2026 | 2026-03-05 08:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 28
202512-NM25-02447 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:03 | January | 2026 | 2026-01-29 16:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 62
202512-NM25-02448 | GDL17 | Residencial | 10.112 | Period | 2026-01-05 09:39 | January | 2026 | 2026-01-12 10:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 86
202512-NM25-02452 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:59 | February | 2026 | 2026-02-23 13:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 43
202512-NM25-02456 | GDL17 | Residencial | 7.68 | Period | 2026-01-15 14:19 | January | 2026 | 2026-01-19 11:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-02459 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:52 | March | 2026 | 2026-03-16 14:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 18
202512-NM25-02461 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-10 17:49 | December | 2025 | 2026-03-10 13:27 | 90 | Study | Estudio (E) | Activated | Backlog |  | No | 90 |  | MAYAGUEZ | March |  | 90 | 0 | 2026-04-01 | 111
202512-NM25-02466 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 08:38 | February | 2026 | 2026-03-02 16:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 34
202512-NM25-02469 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 12:45 | March | 2026 | 2026-03-06 15:54 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 25
202512-NM25-02472 | GDL17 | Residencial | 23 | Period | 2026-01-09 19:06 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 81
202512-NM25-02473 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 09:48 | March | 2026 | 2026-03-10 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 26
202512-NM25-02483 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 11:38 | February | 2026 | 2026-02-09 11:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-02485 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 11:11 | February | 2026 | 2026-02-09 16:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-02488 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:33 | February | 2026 | 2026-02-10 10:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202512-NM25-02500 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:02 | January | 2026 | 2026-01-14 15:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-02505 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:01 | January | 2026 | 2026-01-28 10:22 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 71
202512-NM25-02518 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:01 | February | 2026 | 2026-02-23 09:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202512-NM25-02519 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:00 | January | 2026 | 2026-01-19 13:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-02533 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 14:45 | March | 2026 | 2026-03-23 13:52 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 5 | 9 | 2026-04-01 | 22
202512-NM25-02539 | GDL17 | Residencial | 7.64 | Period | 2026-01-07 09:44 | January | 2026 | 2026-01-09 09:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-02540 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 09:45 | March | 2026 | 2026-03-04 14:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 30
202512-NM25-02543 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:53 | January | 2026 | 2026-01-19 11:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-02547 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:11 | January | 2026 | 2026-01-14 11:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 84
202512-NM25-02548 | GDL17 | Residencial | 23 | Period | 2026-01-15 09:32 | January | 2026 | 2026-01-16 15:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-02555 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 13:11 | February | 2026 | 2026-03-03 09:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202512-NM25-02560 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-18 14:38 | December | 2025 | 2026-03-27 10:35 | 99 | Study | Estudio (E) | Activated | Backlog |  | No | 99 |  | CAGUAS | March |  | 99 | 0 | 2026-04-01 | 103
202512-NM25-02562 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:44 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 64
202512-NM25-02563 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 17:32 | February | 2026 | 2026-03-03 09:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 33
202512-NM25-02571 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 07:23 | January | 2026 | 2026-01-14 14:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-02574 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:47 | February | 2026 | 2026-02-10 15:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-02576 | GDL17 | Residencial | 19.1 | Period | 2026-01-14 09:31 | January | 2026 | 2026-01-27 09:31 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 3 | 2 | 11 | 2026-04-01 | 77
202512-NM25-02577 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:44 | February | 2026 | 2026-02-12 15:57 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 57
202512-NM25-02582 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:21 | January | 2026 | 2026-01-26 14:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-02583 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:33 | February | 2026 | 2026-03-03 10:50 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 41
202512-NM25-02586 | GDL17 | Residencial | 8 | Period | 2026-01-15 10:30 | January | 2026 | 2026-01-16 16:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-02589 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:37 | January | 2026 | 2026-01-13 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-02592 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:46 | January | 2026 | 2026-01-16 13:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-02596 | GDL17 | Residencial | 24.96 | Period | 2026-03-18 10:27 | March | 2026 | 2026-03-19 16:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 14
202512-NM25-02606 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:03 | February | 2026 | 2026-02-05 12:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-02618 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 20:55 | January | 2026 | 2026-02-04 11:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-02621 | GDL17 | Residencial | 3.84 | Period | 2026-01-19 11:12 | January | 2026 | 2026-01-20 13:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 72
202512-NM25-02622 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:28 | January | 2026 | 2026-01-20 08:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-02623 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:03 | March | 2026 | 2026-04-01 10:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 2
202512-NM25-02624 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-19 08:23 | December | 2025 | 2026-02-24 12:55 | 67 | Study | Estudio (E) | Activated | Backlog |  | No | 67 |  | CAGUAS | February |  | 67 | 0 | 2026-04-01 | 103
202512-NM25-02627 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:49 | January | 2026 | 2026-01-28 11:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 68
202512-NM25-02629 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:48 | January | 2026 | 2026-01-19 16:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-02630 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:52 | January | 2026 | 2026-01-15 14:35 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-02631 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:04 | January | 2026 | 2026-01-15 11:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-02632 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:58 | January | 2026 | 2026-01-13 16:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-02634 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 09:53 | March | 2026 | 2026-03-05 15:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 29
202512-NM25-02636 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:17 | January | 2026 | 2026-01-19 08:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 76
202512-NM25-02639 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 08:16 | January | 2026 | 2026-01-14 15:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-02640 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:39 | March | 2026 | 2026-03-17 09:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 18
202512-NM25-02643 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:13 | December | 2025 | 2026-01-05 13:46 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-02644 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 14:28 | March | 2026 | 2026-03-17 11:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 19
202512-NM25-02646 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:18 | February | 2026 | 2026-02-23 14:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202512-NM25-02647 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 08:37 | January | 2026 | 2026-01-16 15:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-02648 | GDL17 | Residencial | 23.8 | Period | 2026-02-23 09:59 | February | 2026 | 2026-02-26 08:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 37
202512-NM25-02651 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 18:42 | February | 2026 | 2026-02-25 08:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-02652 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 10:00 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 110 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 105
202512-NM25-02658 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:53 | January | 2026 | 2026-01-14 14:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-02660 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:46 | January | 2026 | 2026-01-13 09:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-02666 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:36 | March | 2026 | 2026-03-05 15:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 28
202512-NM25-02669 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:30 | January | 2026 | 2026-02-03 08:52 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 24 | 0 | 2026-04-01 | 82
202512-NM25-02670 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:00 | January | 2026 | 2026-02-05 08:46 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 10 | 0 | 2026-04-01 | 64
202512-NM25-02675 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:10 | January | 2026 | 2026-01-14 09:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-02679 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:13 | January | 2026 | 2026-03-10 10:37 | 60 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 60 | 0 | 2026-04-01 | 82
202512-NM25-02681 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:24 | January | 2026 | 2026-01-28 08:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 69
202512-NM25-02682 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:11 | February | 2026 | 2026-02-04 17:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-02683 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:27 | January | 2026 | 2026-01-14 14:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-02684 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 12:48 | March | 2026 | 2026-03-06 16:29 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 25
202512-NM25-02685 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 14:58 | January | 2026 | 2026-01-14 13:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-02686 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:58 | March | 2026 | 2026-03-09 10:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 26
202512-NM25-02687 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:53 | January | 2026 | 2026-01-14 10:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-02688 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:54 | February | 2026 | 2026-02-25 11:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-02689 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 07:20 | February | 2026 | 2026-02-23 09:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202512-NM25-02695 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:24 | January | 2026 | 2026-02-18 13:46 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 33 | 0 | 2026-04-01 | 75
202512-NM25-02699 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:58 | February | 2026 | 2026-02-23 10:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 42
202512-NM25-02701 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:21 | February | 2026 | 2026-02-27 13:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 39
202512-NM25-02706 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 18:56 | February | 2026 | 2026-03-02 08:19 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 40
202512-NM25-02710 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-11 17:08 | December | 2025 | 2026-02-13 10:25 | 64 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 5 | 59 | 2026-04-01 | 110
202512-NM25-02711 | GDL17 | Residencial | 23 | Period | 2026-01-15 11:45 | January | 2026 | 2026-01-19 13:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-02713 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:48 | February | 2026 | 2026-03-02 09:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-02716 | GDL17 | Residencial | 8.448 | Period | 2026-02-24 15:50 | February | 2026 | 2026-03-09 10:48 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 35
202512-NM25-02717 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:49 | February | 2026 | 2026-02-10 09:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 56
202512-NM25-02719 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:05 | March | 2026 | 2026-03-16 16:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 18
202512-NM25-02720 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:36 | February | 2026 | 2026-02-26 10:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-02722 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:04 | February | 2026 | 2026-03-03 13:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-02723 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-17 18:08 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 104
202512-NM25-02724 | GDL17 | Residencial | 3.66 | Period | 2026-01-29 11:08 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 62
202512-NM25-02725 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 17:33 | January | 2026 | 2026-02-03 15:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202512-NM25-02729 | GDL17 | Residencial | 23 | Period | 2026-01-30 19:09 | January | 2026 | 2026-02-17 10:27 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 17 | 0 | 2026-04-01 | 60
202512-NM25-02732 | GDL17 | Residencial | 23 | Period | 2026-02-02 15:46 | February | 2026 | 2026-02-04 16:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-02733 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 10:38 | December | 2025 | 2026-02-10 13:52 | 55 | Study | Estudio (E) | Activated | Backlog |  | No | 55 |  | BAYAMON | February |  | 55 | 0 | 2026-04-01 | 105
202512-NM25-02734 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:34 | February | 2026 | 2026-03-06 15:50 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 40
202512-NM25-02742 | GDL17 | Comercial | 11.5 | Out of period | 2025-12-18 14:25 | December | 2025 | 2026-02-03 16:29 | 47 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | February | 1 | 6 | 41 | 2026-04-01 | 103
202512-NM25-02743 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:04 | January | 2026 | 2026-01-13 12:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-02747 | GDL17 | Residencial | 4.026 | Period | 2026-02-06 07:55 | February | 2026 | 2026-02-09 11:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 54
202512-NM25-02748 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:20 | March | 2026 | 2026-03-18 13:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202512-NM25-02758 | GDL17 | Residencial | 7.6 | Period | 2026-01-09 10:29 | January | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 82
202512-NM25-02760 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:12 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 39
202512-NM25-02763 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:54 | February | 2026 | 2026-03-10 08:06 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 34
202512-NM25-02766 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:43 | February | 2026 | 2026-02-25 15:55 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 8 | 1 | 2026-04-01 | 44
202512-NM25-02768 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:15 | February | 2026 | 2026-03-03 08:08 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 11 | 0 | 2026-04-01 | 39
202512-NM25-02773 | GDL17 | Residencial | 9.216 | Out of period | 2025-12-31 08:58 | December | 2025 | 2026-01-08 15:33 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-02784 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:31 | January | 2026 | 2026-01-16 16:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-02785 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:13 | January | 2026 | 2026-01-19 16:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-02786 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:48 | March | 2026 | 2026-03-09 08:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 29
202512-NM25-02787 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:03 | January | 2026 | 2026-01-19 09:24 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 83
202512-NM25-02790 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:10 | February | 2026 | 2026-03-02 09:01 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 39
202512-NM25-02792 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:50 | March | 2026 | 2026-03-04 09:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 30
202512-NM25-02793 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:56 | January | 2026 | 2026-01-12 13:05 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 10 | 0 | 2026-04-01 | 88
202512-NM25-02794 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:55 | January | 2026 | 2026-01-14 10:49 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 88
202512-NM25-02796 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:27 | January | 2026 | 2026-01-26 13:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-02797 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 11:11 | March | 2026 | 2026-03-23 10:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 14
202512-NM25-02799 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:33 | January | 2026 | 2026-01-21 14:35 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 13 | 0 | 2026-04-01 | 83
202512-NM25-02801 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:31 | January | 2026 | 2026-02-04 10:33 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 62
202512-NM25-02803 | GDL17 | Residencial | 24 | Period | 2026-01-16 11:21 | January | 2026 | 2026-01-19 11:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-02804 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:25 | January | 2026 | 2026-02-04 10:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-02805 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-12 10:34 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 110
202512-NM25-02806 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 08:59 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 82
202512-NM25-02807 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:25 | January | 2026 | 2026-01-13 15:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-02808 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:56 | January | 2026 | 2026-01-22 11:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-02809 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:52 | January | 2026 | 2026-01-09 15:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 89
202512-NM25-02811 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:04 | January | 2026 | 2026-01-30 14:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 68
202512-NM25-02812 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:52 | January | 2026 | 2026-01-12 12:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-02813 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:46 | January | 2026 | 2026-01-09 10:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-02814 | GDL17 | Residencial | 3.84 | Period | 2026-03-03 11:27 | March | 2026 | 2026-03-06 07:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202512-NM25-02815 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:30 | January | 2026 | 2026-01-13 08:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-02818 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:17 | January | 2026 | 2026-01-12 08:06 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 9 | 0 | 2026-04-01 | 88
202512-NM25-02819 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:04 | January | 2026 | 2026-01-20 13:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-02820 | GDL17 | Residencial | 3.84 | Period | 2026-02-02 08:36 | February | 2026 | 2026-02-04 15:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 58
202512-NM25-02825 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:44 | January | 2026 | 2026-01-16 10:54 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-02826 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:35 | January | 2026 | 2026-01-23 11:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202512-NM25-02828 | GDL17 | Residencial | 6.528 | Period | 2026-01-27 13:05 | January | 2026 | 2026-02-03 09:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 63
202512-NM25-02829 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:32 | January | 2026 | 2026-01-30 12:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 63
202512-NM25-02831 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:15 | February | 2026 | 2026-02-05 14:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-02832 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 08:45 | January | 2026 | 2026-03-10 13:46 | 67 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 67 | 0 | 2026-04-01 | 89
202512-NM25-02833 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:11 | January | 2026 | 2026-01-13 10:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-02838 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 14:56 | March | 2026 | 2026-03-19 15:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 13
202512-NM25-02840 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:19 | January | 2026 | 2026-01-28 11:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 65
202512-NM25-02846 | GDL17 | Residencial | 5.6 | Out of period | 2025-12-22 10:32 | December | 2025 |  |  | NM Document Resubmission | Validación (V) | Backlog | Backlog |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 100
202512-NM25-02847 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:52 | January | 2026 | 2026-02-03 10:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 60
202512-NM25-02848 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:33 | March | 2026 | 2026-03-06 13:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 26
202512-NM25-02853 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-22 13:48 | December | 2025 | 2026-02-12 15:28 | 52 | Study | Estudio (E) | Activated | Backlog |  | No | 52 |  | BAYAMON | February |  | 52 | 0 | 2026-04-01 | 99
202512-NM25-02855 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:06 | January | 2026 | 2026-01-14 09:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 84
202512-NM25-02861 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:03 | January | 2026 | 2026-01-12 15:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-02862 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:48 | January | 2026 | 2026-01-09 10:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-02864 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:12 | January | 2026 | 2026-01-09 10:31 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 88
202512-NM25-02865 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:38 | January | 2026 | 2026-01-29 09:35 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 13 | 0 | 2026-04-01 | 75
202512-NM25-02869 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:04 | January | 2026 | 2026-02-18 13:40 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 27 | 0 | 2026-04-01 | 68
202512-NM25-02870 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:41 | January | 2026 | 2026-02-09 13:38 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 12 | 0 | 2026-04-01 | 62
202512-NM25-02871 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 12:45 | January | 2026 | 2026-02-02 09:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-02873 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:16 | January | 2026 | 2026-01-30 09:19 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 10 | 0 | 2026-04-01 | 71
202512-NM25-02874 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:46 | January | 2026 | 2026-01-14 16:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-02875 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:46 | January | 2026 | 2026-01-07 13:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-02876 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:39 | January | 2026 | 2026-02-03 10:08 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-02877 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:54 | January | 2026 | 2026-01-16 15:14 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 83
202512-NM25-02881 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:37 | January | 2026 | 2026-01-07 10:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-02882 | GDL17 | Residencial | 3.84 | Period | 2026-01-29 10:33 | January | 2026 | 2026-02-02 15:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 62
202512-NM25-02883 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:09 | February | 2026 | 2026-03-30 13:02 | 31 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 31 | 0 | 2026-04-01 | 32
202512-NM25-02890 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 14:21 | January | 2026 | 2026-01-16 11:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 81
202512-NM25-02895 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:45 | January | 2026 | 2026-02-05 14:59 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 10 | 0 | 2026-04-01 | 65
202512-NM25-02896 | GDL17 | Residencial | 7.68 | Period | 2026-01-07 11:07 | January | 2026 | 2026-01-12 13:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-02901 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 08:02 | February | 2026 | 2026-02-04 14:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 58
202512-NM25-02902 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:27 | January | 2026 | 2026-01-13 13:22 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 11 | 0 | 2026-04-01 | 88
202512-NM25-02903 | GDL17 | Residencial | 7.68 | Period | 2026-02-10 07:49 | February | 2026 | 2026-02-26 16:17 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 16 | 0 | 2026-04-01 | 50
202512-NM25-02904 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:44 | January | 2026 | 2026-01-26 16:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-02906 | GDL17 | Residencial | 6.912 | Period | 2026-02-03 12:55 | February | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 56
202512-NM25-02908 | GDL17 | Residencial | 3.84 | Period | 2026-01-19 14:35 | January | 2026 | 2026-01-21 09:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-02910 | GDL17 | Residencial | 3.84 | Period | 2026-01-23 09:34 | January | 2026 | 2026-01-26 13:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-02919 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:25 | January | 2026 | 2026-01-08 14:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 88
202512-NM25-02922 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 18:34 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 35
202512-NM25-02923 | GDL17 | Residencial | 3.84 | Period | 2026-01-07 09:22 | January | 2026 | 2026-01-12 16:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-02924 | GDL17 | Residencial | 23 | Period | 2026-01-08 12:03 | January | 2026 | 2026-01-19 16:16 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 11 | 0 | 2026-04-01 | 82
202512-NM25-02925 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 12:12 | February | 2026 | 2026-02-16 08:47 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 54
202512-NM25-02929 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:43 | January | 2026 | 2026-01-15 09:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 83
202512-NM25-02936 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:10 | January | 2026 | 2026-01-19 11:11 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 10 | 0 | 2026-04-01 | 82
202512-NM25-02938 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:09 | January | 2026 | 2026-02-03 09:09 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 65
202512-NM25-02940 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:56 | January | 2026 | 2026-01-22 07:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 75
202512-NM25-02943 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:16 | January | 2026 | 2026-01-16 14:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-02949 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:01 | January | 2026 | 2026-01-29 10:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-02950 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 11:00 | January | 2026 | 2026-01-09 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-02951 | GDL17 | Residencial | 23 | Period | 2026-03-02 15:25 | March | 2026 | 2026-03-05 14:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 29
202512-NM25-02953 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:53 | January | 2026 | 2026-03-04 14:48 | 54 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 54 | 0 | 2026-04-01 | 82
202512-NM25-02954 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-23 09:07 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 108 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 99
202512-NM25-02955 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:03 | February | 2026 | 2026-02-25 15:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-02956 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 12:18 | February | 2026 | 2026-03-02 13:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-02958 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:38 | February | 2026 | 2026-02-25 15:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-02961 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:42 | January | 2026 | 2026-01-16 16:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-02963 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:12 | January | 2026 | 2026-01-13 10:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-02965 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:18 | January | 2026 | 2026-01-19 15:25 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 10 | 0 | 2026-04-01 | 81
202512-NM25-02969 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:29 | January | 2026 | 2026-01-26 10:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 71
202512-NM25-02971 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 17:48 | February | 2026 | 2026-03-02 10:33 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 35
202512-NM25-02972 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 11:06 | January | 2026 | 2026-02-03 12:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 63
202512-NM25-02973 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:45 | January | 2026 | 2026-01-13 15:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 81
202512-NM25-02974 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:12 | January | 2026 | 2026-01-29 09:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 65
202512-NM25-02975 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 08:33 | January | 2026 | 2026-01-28 14:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 65
202512-NM25-02976 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 12:59 | January | 2026 | 2026-02-03 09:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 61
202512-NM25-02978 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:05 | January | 2026 | 2026-01-20 15:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 77
202512-NM25-02979 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:56 | January | 2026 | 2026-01-30 07:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 63
202512-NM25-02980 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:37 | January | 2026 | 2026-01-19 09:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-02981 | GDL17 | Residencial | 3.84 | Period | 2026-02-05 13:57 | February | 2026 | 2026-02-09 12:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-02982 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 18:36 | February | 2026 | 2026-02-25 14:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-02986 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:09 | January | 2026 | 2026-01-13 15:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-02989 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:42 | March | 2026 | 2026-04-13 13:59 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 20 | 0 | 2026-04-01 | 7
202512-NM25-02991 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:57 | January | 2026 | 2026-01-19 08:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-02992 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 11:32 | March | 2026 | 2026-03-18 15:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202512-NM25-02993 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:26 | January | 2026 | 2026-01-28 09:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 71
202512-NM25-02995 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 19:05 | January | 2026 | 2026-02-04 17:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 61
202512-NM25-02998 | GDL17 | Residencial | 23 | Period | 2026-01-15 09:11 | January | 2026 | 2026-02-03 07:43 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 19 | 0 | 2026-04-01 | 76
202512-NM25-03000 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:33 | January | 2026 | 2026-01-26 13:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03001 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:14 | January | 2026 | 2026-01-15 14:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-03002 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:54 | January | 2026 | 2026-02-10 09:37 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 19 | 0 | 2026-04-01 | 68
202512-NM25-03003 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:55 | January | 2026 | 2026-01-13 08:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03005 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:47 | January | 2026 | 2026-01-29 13:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-03006 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:01 | January | 2026 | 2026-01-16 15:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03007 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:34 | February | 2026 | 2026-03-06 13:16 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 35
202512-NM25-03009 | GDL17 | Residencial | 3.84 | Period | 2026-01-07 13:37 | January | 2026 | 2026-03-17 08:31 | 69 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 68 | 0 | 2026-04-01 | 83
202512-NM25-03011 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:33 | January | 2026 | 2026-01-14 14:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-03012 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:47 | January | 2026 | 2026-01-30 13:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 65
202512-NM25-03013 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 09:39 | March | 2026 | 2026-03-09 14:51 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 23
202512-NM25-03014 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:06 | January | 2026 | 2026-01-23 15:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 69
202512-NM25-03015 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:28 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 63
202512-NM25-03018 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:03 | January | 2026 | 2026-01-26 08:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 70
202512-NM25-03019 | GDL17 | Residencial | 3.84 | Period | 2026-01-22 10:40 | January | 2026 | 2026-01-29 15:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 69
202512-NM25-03020 | GDL17 | Residencial | 8.832 | Period | 2026-01-19 10:03 | January | 2026 | 2026-01-28 10:56 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 72
202512-NM25-03023 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:17 | January | 2026 | 2026-01-22 10:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-03025 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:14 | January | 2026 | 2026-01-26 14:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 69
202512-NM25-03026 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:51 | January | 2026 | 2026-02-12 13:26 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 69
202512-NM25-03028 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:57 | January | 2026 | 2026-01-15 07:54 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-03029 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:25 | January | 2026 | 2026-01-13 15:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-03030 | GDL17 | Residencial | 4.992 | Period | 2026-01-02 14:29 | January | 2026 | 2026-01-13 07:50 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 88
202512-NM25-03031 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:04 | January | 2026 | 2026-01-19 13:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03032 | GDL17 | Residencial | 3.245 | Out of period | 2025-12-15 08:50 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 107
202512-NM25-03034 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:47 | January | 2026 | 2026-01-12 08:52 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 10 | 0 | 2026-04-01 | 88
202512-NM25-03036 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:22 | January | 2026 | 2026-01-12 12:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-03037 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:25 | January | 2026 | 2026-01-19 13:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-03039 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:03 | January | 2026 | 2026-01-14 10:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-03040 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:06 | January | 2026 | 2026-01-09 10:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 83
202512-NM25-03041 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 08:13 | January | 2026 | 2026-02-03 09:52 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 19 | 0 | 2026-04-01 | 76
202512-NM25-03045 | GDL17 | Residencial | 23 | Period | 2026-02-25 13:59 | February | 2026 | 2026-03-02 09:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-03046 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:29 | January | 2026 | 2026-01-19 08:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-03047 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:31 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 75
202512-NM25-03048 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:34 | January | 2026 | 2026-01-20 13:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03049 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:38 | January | 2026 | 2026-01-20 10:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03050 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 13:38 | March | 2026 | 2026-04-15 15:58 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | April |  | 28 | 24 | 2026-04-01 | 13
202512-NM25-03051 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:17 | January | 2026 | 2026-01-13 14:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03053 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:07 | January | 2026 | 2026-01-29 07:49 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 13 | 0 | 2026-04-01 | 74
202512-NM25-03054 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:38 | January | 2026 | 2026-01-28 15:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 68
202512-NM25-03056 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:34 | January | 2026 | 2026-01-20 09:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03057 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:05 | January | 2026 | 2026-01-08 14:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 89
202512-NM25-03059 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 12:48 | January | 2026 | 2026-01-14 13:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-03061 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:54 | January | 2026 | 2026-01-20 10:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03063 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 15:31 | January | 2026 | 2026-01-20 13:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03064 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:35 | January | 2026 | 2026-01-28 16:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 68
202512-NM25-03065 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:04 | January | 2026 | 2026-01-26 15:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03066 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:29 | January | 2026 | 2026-01-26 15:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03067 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:40 | January | 2026 | 2026-01-23 13:14 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 16 | 0 | 2026-04-01 | 83
202512-NM25-03069 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:57 | January | 2026 | 2026-01-14 10:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-03072 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:03 | January | 2026 | 2026-01-09 10:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 83
202512-NM25-03073 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:10 | January | 2026 | 2026-02-12 10:18 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 20 | 0 | 2026-04-01 | 68
202512-NM25-03074 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:40 | January | 2026 | 2026-01-14 14:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-03075 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:16 | February | 2026 | 2026-02-09 16:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-03081 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:52 | December | 2025 | 2026-01-07 10:38 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03082 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 17:19 | March | 2026 | 2026-03-20 15:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 12
202512-NM25-03083 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 11:28 | February | 2026 | 2026-02-13 15:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 54
202512-NM25-03084 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:29 | January | 2026 | 2026-01-23 09:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 68
202512-NM25-03087 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:24 | January | 2026 | 2026-02-11 13:48 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 19 | 0 | 2026-04-01 | 67
202512-NM25-03088 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:14 | February | 2026 | 2026-02-05 16:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-03090 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 14:43 | January | 2026 | 2026-01-14 16:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-03092 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:18 | January | 2026 | 2026-01-12 13:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 10 | 0 | 2026-04-01 | 88
202512-NM25-03094 | GDL17 | Residencial | 19.1 | Period | 2026-01-23 13:45 | January | 2026 | 2026-01-26 13:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-03095 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:37 | January | 2026 | 2026-01-09 10:23 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 88
202512-NM25-03096 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:06 | January | 2026 | 2026-01-26 15:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-03097 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:41 | January | 2026 | 2026-02-04 08:21 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 65
202512-NM25-03098 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:49 | February | 2026 | 2026-02-05 16:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-03100 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:25 | January | 2026 | 2026-01-29 10:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 67
202512-NM25-03102 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:24 | February | 2026 | 2026-02-09 12:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-03103 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:37 | December | 2025 | 2026-01-07 10:55 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03104 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 13:40 | January | 2026 | 2026-02-06 16:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 60
202512-NM25-03105 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:21 | February | 2026 | 2026-02-05 15:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-03106 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 11:19 | December | 2025 | 2026-01-05 16:14 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-03107 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:54 | January | 2026 | 2026-01-19 09:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-03108 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 07:27 | January | 2026 | 2026-01-15 12:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03109 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:44 | January | 2026 | 2026-01-26 14:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-03113 | GDL17 | Residencial | 7.68 | Period | 2026-02-25 12:58 | February | 2026 | 2026-03-03 15:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 34
202512-NM25-03118 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:06 | January | 2026 | 2026-01-26 14:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-03119 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 08:53 | January | 2026 | 2026-01-14 09:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-03120 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:30 | January | 2026 | 2026-01-30 14:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 67
202512-NM25-03121 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:56 | January | 2026 | 2026-01-22 14:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-03122 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:52 | January | 2026 | 2026-01-21 16:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-03123 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:45 | January | 2026 | 2026-01-30 11:19 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 67
202512-NM25-03125 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 08:00 | January | 2026 | 2026-01-16 10:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-03126 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:13 | January | 2026 | 2026-01-30 07:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 62
202512-NM25-03127 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:27 | January | 2026 | 2026-02-12 10:24 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 62
202512-NM25-03128 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:29 | January | 2026 | 2026-01-20 15:21 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 82
202512-NM25-03129 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 12:46 | January | 2026 | 2026-01-29 16:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 62
202512-NM25-03132 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:01 | January | 2026 | 2026-01-30 10:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 62
202512-NM25-03135 | GDL17 | Residencial | 4.2 | Period | 2026-01-07 11:30 | January | 2026 | 2026-01-09 15:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-03136 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:27 | December | 2025 | 2026-01-07 15:02 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03139 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 18:07 | January | 2026 | 2026-02-03 10:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 61
202512-NM25-03140 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 19:50 | February | 2026 | 2026-02-27 11:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 35
202512-NM25-03141 | GDL17 | Residencial | 23 | Period | 2026-02-19 19:33 | February | 2026 | 2026-02-25 08:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-03146 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 11:17 | December | 2025 | 2026-01-07 09:41 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03147 | GDL17 | Residencial | 6.8 | Period | 2026-02-02 15:46 | February | 2026 | 2026-02-04 16:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-03148 | GDL17 | Residencial | 9 | Period | 2026-02-16 20:50 | February | 2026 | 2026-02-20 15:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 43
202512-NM25-03149 | GDL17 | Residencial | 24 | Period | 2026-01-07 10:34 | January | 2026 | 2026-01-12 14:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-03157 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:14 | December | 2025 | 2026-01-07 14:49 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03166 | GDL17 | Residencial | 15.04 | Period | 2026-01-26 13:18 | January | 2026 | 2026-01-28 14:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03167 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 07:21 | February | 2026 | 2026-02-23 09:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202512-NM25-03169 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:47 | January | 2026 | 2026-01-21 13:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-03172 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:15 | January | 2026 | 2026-01-23 15:20 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 76
202512-NM25-03177 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:00 | January | 2026 | 2026-01-21 15:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-03181 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:10 | January | 2026 | 2026-02-02 09:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-03182 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:26 | January | 2026 | 2026-01-19 15:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03185 | GDL17 | Comercial | 23 | Period | 2026-02-10 13:13 | February | 2026 | 2026-02-11 15:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202512-NM25-03188 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 11:54 | February | 2026 | 2026-02-10 11:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 55
202512-NM25-03190 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:49 | January | 2026 | 2026-01-19 12:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03193 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:41 | January | 2026 | 2026-02-03 07:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 63
202512-NM25-03203 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:58 | January | 2026 | 2026-01-30 08:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 65
202512-NM25-03211 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:04 | January | 2026 | 2026-01-30 10:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 64
202512-NM25-03213 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:05 | January | 2026 | 2026-01-15 15:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-03214 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:19 | January | 2026 | 2026-01-15 10:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03215 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:18 | January | 2026 | 2026-01-16 09:58 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 83
202512-NM25-03219 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:14 | January | 2026 | 2026-01-20 08:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-03220 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 12:28 | January | 2026 | 2026-01-28 14:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 69
202512-NM25-03222 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:45 | January | 2026 | 2026-01-16 10:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 76
202512-NM25-03227 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:57 | January | 2026 | 2026-02-03 15:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-03228 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:25 | January | 2026 | 2026-02-04 16:11 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 16 | 0 | 2026-04-01 | 71
202512-NM25-03229 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:11 | January | 2026 | 2026-01-20 09:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-03232 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:35 | January | 2026 | 2026-01-15 10:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03235 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:02 | January | 2026 | 2026-01-15 14:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03236 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:21 | January | 2026 | 2026-01-19 11:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 77
202512-NM25-03237 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 10:30 | February | 2026 | 2026-02-11 14:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 50
202512-NM25-03238 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:10 | January | 2026 | 2026-01-20 14:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03244 | GDL17 | Residencial | 6.912 | Period | 2026-03-16 16:44 | March | 2026 | 2026-03-18 16:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 15
202512-NM25-03248 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 08:19 | February | 2026 | 2026-02-16 11:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 50
202512-NM25-03249 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:37 | January | 2026 | 2026-01-15 14:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03252 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 15:34 | February | 2026 | 2026-02-12 10:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202512-NM25-03254 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:36 | January | 2026 | 2026-01-19 07:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 77
202512-NM25-03257 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:32 | January | 2026 | 2026-01-28 10:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03258 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:48 | January | 2026 | 2026-01-15 14:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03259 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:13 | January | 2026 | 2026-01-14 14:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-03263 | GDL17 | Residencial | 8 | Period | 2026-02-05 09:08 | February | 2026 | 2026-02-09 16:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-03265 | GDL17 | Residencial | 3.84 | Period | 2026-02-03 07:54 | February | 2026 | 2026-02-24 15:24 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 21 | 0 | 2026-04-01 | 57
202512-NM25-03266 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:56 | January | 2026 | 2026-01-14 09:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-03267 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:53 | January | 2026 | 2026-01-15 15:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03270 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:32 | January | 2026 | 2026-01-23 09:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 69
202512-NM25-03272 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:27 | January | 2026 | 2026-02-06 10:49 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 17 | 0 | 2026-04-01 | 71
202512-NM25-03275 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:55 | January | 2026 | 2026-01-21 13:48 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 12 | 0 | 2026-04-01 | 82
202512-NM25-03276 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:58 | January | 2026 | 2026-01-09 10:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-03279 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:21 | January | 2026 | 2026-01-15 14:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03280 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:07 | January | 2026 | 2026-01-28 16:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 64
202512-NM25-03282 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:29 | February | 2026 | 2026-02-10 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-03283 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:33 | January | 2026 | 2026-01-14 14:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-03284 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 08:50 | January | 2026 | 2026-02-05 09:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 61
202512-NM25-03286 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:02 | January | 2026 | 2026-01-26 15:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03287 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:13 | January | 2026 | 2026-01-16 16:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-03288 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 08:55 | January | 2026 | 2026-01-07 09:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 89
202512-NM25-03289 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:58 | January | 2026 | 2026-01-16 10:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-03290 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 14:25 | January | 2026 | 2026-02-04 14:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 61
202512-NM25-03292 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:20 | January | 2026 | 2026-01-13 14:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-03293 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:52 | February | 2026 | 2026-02-06 15:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-03294 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:16 | January | 2026 | 2026-01-15 14:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03295 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 20:34 | March | 2026 | 2026-03-11 11:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202512-NM25-03296 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 08:11 | January | 2026 | 2026-01-14 14:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 84
202512-NM25-03297 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:36 | January | 2026 | 2026-02-03 09:19 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 20 | 0 | 2026-04-01 | 77
202512-NM25-03298 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 14:42 | March | 2026 | 2026-03-11 11:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 25
202512-NM25-03299 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 09:22 | January | 2026 | 2026-02-03 16:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-03300 | GDL17 | Residencial | 23 | Period | 2026-03-20 12:54 | March | 2026 | 2026-03-23 14:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 11
202512-NM25-03303 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:16 | January | 2026 | 2026-01-15 13:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03306 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:19 | January | 2026 | 2026-01-15 10:27 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03307 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 08:33 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 84
202512-NM25-03308 | GDL17 | Residencial | 5.76 | Period | 2026-01-21 19:51 | January | 2026 | 2026-03-02 08:29 | 40 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March |  | 40 | 0 | 2026-04-01 | 69
202512-NM25-03310 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:39 | January | 2026 | 2026-01-19 13:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 74
202512-NM25-03314 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:59 | February | 2026 | 2026-03-20 15:25 | 44 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 44 | 0 | 2026-04-01 | 55
202512-NM25-03316 | GDL17 | Residencial | 7.6 | Period | 2026-01-08 13:14 | January | 2026 | 2026-01-19 10:15 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 11 | 0 | 2026-04-01 | 82
202512-NM25-03317 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 07:34 | January | 2026 | 2026-01-26 14:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03321 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 11:07 | January | 2026 | 2026-01-15 12:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03322 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 08:01 | January | 2026 | 2026-01-26 14:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03324 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 07:55 | January | 2026 | 2026-01-21 12:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-03325 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:40 | January | 2026 | 2026-01-15 14:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03326 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:41 | January | 2026 | 2026-01-07 10:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-03327 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 08:37 | January | 2026 | 2026-01-26 11:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03329 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 07:27 | January | 2026 | 2026-01-09 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-03330 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:28 | January | 2026 | 2026-01-07 15:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-03332 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:36 | February | 2026 | 2026-02-12 13:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202512-NM25-03334 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:11 | January | 2026 | 2026-01-13 10:20 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 11 | 0 | 2026-04-01 | 88
202512-NM25-03335 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:58 | January | 2026 | 2026-01-07 10:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-03336 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:56 | January | 2026 | 2026-01-13 14:46 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 11 | 0 | 2026-04-01 | 88
202512-NM25-03337 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:59 | January | 2026 | 2026-01-15 15:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03339 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:52 | December | 2025 | 2026-01-05 13:23 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-03340 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:59 | January | 2026 | 2026-01-28 13:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 67
202512-NM25-03343 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-30 03:03 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 92
202512-NM25-03344 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-23 09:58 | December | 2025 | 2026-02-03 09:45 | 42 | Study | Estudio (E) | Activated | Backlog |  | No | 42 |  | ARECIBO | February |  | 42 | 0 | 2026-04-01 | 99
202512-NM25-03348 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:32 | January | 2026 | 2026-01-30 08:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 67
202512-NM25-03349 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:07 | January | 2026 | 2026-01-20 15:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 77
202512-NM25-03352 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:26 | January | 2026 | 2026-01-23 14:27 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 77
202512-NM25-03353 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:50 | January | 2026 | 2026-01-29 09:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-03354 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:39 | January | 2026 | 2026-01-22 09:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-03356 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:35 | January | 2026 | 2026-02-02 09:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 62
202512-NM25-03357 | GDL17 | Residencial | 8 | Out of period | 2025-12-22 13:00 | December | 2025 | 2026-03-27 11:14 | 95 | Study | Estudio (E) | Activated | Backlog |  | No | 95 |  | CAGUAS | March |  | 95 | 0 | 2026-04-01 | 99
202512-NM25-03362 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:12 | January | 2026 | 2026-01-22 13:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-03365 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:01 | February | 2026 | 2026-02-18 09:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 49
202512-NM25-03366 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:40 | January | 2026 | 2026-01-12 15:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03367 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:05 | January | 2026 | 2026-01-19 10:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03368 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:02 | January | 2026 | 2026-01-09 09:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 83
202512-NM25-03369 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 07:32 | January | 2026 | 2026-01-19 14:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 77
202512-NM25-03370 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:48 | January | 2026 | 2026-01-15 14:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03372 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:31 | January | 2026 | 2026-01-29 15:00 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 15 | 0 | 2026-04-01 | 77
202512-NM25-03374 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:26 | January | 2026 | 2026-01-13 14:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-03376 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:04 | January | 2026 | 2026-01-13 09:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03380 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:11 | February | 2026 | 2026-02-16 14:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202512-NM25-03381 | GDL17 | Residencial | 15 | Period | 2026-01-26 18:11 | January | 2026 | 2026-01-28 14:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03382 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:49 | January | 2026 | 2026-01-16 14:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-03383 | GDL17 | Residencial | 8 | Period | 2026-01-28 08:58 | January | 2026 | 2026-01-30 09:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-03385 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:31 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 75
202512-NM25-03386 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:00 | January | 2026 | 2026-01-22 13:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 69
202512-NM25-03388 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:53 | December | 2025 | 2026-01-07 14:38 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03391 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:55 | January | 2026 | 2026-01-26 08:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 69
202512-NM25-03392 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 08:39 | January | 2026 | 2026-02-16 15:12 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 26 | 0 | 2026-04-01 | 69
202512-NM25-03393 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:48 | January | 2026 | 2026-01-19 11:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-03400 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:15 | January | 2026 | 2026-02-04 08:23 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 70
202512-NM25-03401 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:50 | January | 2026 | 2026-02-02 07:46 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 10 | 0 | 2026-04-01 | 67
202512-NM25-03402 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:31 | January | 2026 | 2026-01-19 13:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-03403 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:13 | January | 2026 | 2026-02-02 11:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-03404 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:07 | January | 2026 | 2026-02-03 16:16 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 74
202512-NM25-03407 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:26 | December | 2025 | 2026-01-07 07:53 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03409 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:18 | January | 2026 | 2026-01-26 15:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03410 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 17:00 | February | 2026 | 2026-02-26 08:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-03411 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:59 | January | 2026 | 2026-01-08 08:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 88
202512-NM25-03412 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:07 | December | 2025 | 2026-01-05 14:10 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-03415 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:06 | February | 2026 | 2026-02-18 12:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 44
202512-NM25-03416 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:23 | January | 2026 | 2026-01-15 10:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03417 | GDL17 | Residencial | 8.448 | Period | 2026-02-26 17:47 | February | 2026 | 2026-03-03 16:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 33
202512-NM25-03419 | GDL17 | Residencial | 14.75 | Period | 2026-01-09 08:20 | January | 2026 | 2026-01-16 10:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-03422 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:30 | January | 2026 | 2026-01-08 10:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 88
202512-NM25-03424 | GDL17 | Residencial | 11.4 | Out of period | 2025-12-26 09:45 | December | 2025 | 2026-03-03 15:17 | 67 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 1 | 4 | 63 | 2026-04-01 | 96
202512-NM25-03425 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:19 | February | 2026 | 2026-02-05 14:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 57
202512-NM25-03426 | GDL17 | Residencial | 9.984 | Period | 2026-01-30 09:57 | January | 2026 | 2026-02-02 15:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 61
202512-NM25-03431 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:30 | January | 2026 | 2026-01-21 14:39 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 82
202512-NM25-03433 | GDL17 | Residencial | 8 | Period | 2026-01-20 10:45 | January | 2026 | 2026-01-29 09:13 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 71
202512-NM25-03434 | GDL17 | Residencial | 3.84 | Period | 2026-01-08 07:19 | January | 2026 | 2026-01-13 15:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03437 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 15:05 | January | 2026 | 2026-01-20 10:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03438 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:27 | January | 2026 | 2026-01-13 10:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03445 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:35 | January | 2026 | 2026-01-16 09:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-03446 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:26 | January | 2026 | 2026-01-16 09:31 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-03448 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:40 | February | 2026 | 2026-02-25 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 40
202512-NM25-03450 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:46 | January | 2026 | 2026-01-23 14:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 69
202512-NM25-03453 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:47 | January | 2026 | 2026-02-02 08:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 63
202512-NM25-03454 | GDL17 | Residencial | 3.84 | Period | 2026-01-15 13:20 | January | 2026 | 2026-02-10 10:29 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 26 | 0 | 2026-04-01 | 75
202512-NM25-03455 | GDL17 | Residencial | 24 | Period | 2026-01-02 17:25 | January | 2026 | 2026-02-24 15:40 | 53 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | February |  | 53 | 0 | 2026-04-01 | 88
202512-NM25-03457 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 12:18 | January | 2026 | 2026-02-02 13:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-03459 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 14:02 | January | 2026 | 2026-01-21 13:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-03463 | GDL17 | Residencial | 23 | Period | 2026-02-19 15:00 | February | 2026 | 2026-02-25 08:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-03464 | GDL17 | Residencial | 15.16 | Period | 2026-02-18 09:14 | February | 2026 | 2026-02-23 09:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 42
202512-NM25-03466 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 12:48 | February | 2026 | 2026-02-10 14:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 53
202512-NM25-03467 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 14:20 | January | 2026 | 2026-01-21 13:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-03468 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 12:47 | January | 2026 | 2026-01-13 08:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03473 | GDL17 | Comercial | 11.4 | Period | 2026-01-19 20:40 | January | 2026 | 2026-01-22 13:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | January | 1 | 3 | 0 | 2026-04-01 | 71
202512-NM25-03478 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:48 | February | 2026 | 2026-02-10 10:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 57
202512-NM25-03485 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:43 | February | 2026 | 2026-02-13 15:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 47
202512-NM25-03490 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:48 | February | 2026 | 2026-02-26 13:39 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 20 | 0 | 2026-04-01 | 54
202512-NM25-03492 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:56 | January | 2026 | 2026-01-27 14:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-03494 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:49 | February | 2026 | 2026-03-30 08:42 | 53 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 53 | 0 | 2026-04-01 | 55
202512-NM25-03498 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:03 | January | 2026 | 2026-01-13 15:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-03506 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:24 | January | 2026 | 2026-01-16 15:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03508 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:34 | January | 2026 | 2026-01-28 10:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03513 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 12:37 | February | 2026 | 2026-02-10 14:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 53
202512-NM25-03514 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:50 | February | 2026 | 2026-02-26 09:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 36
202512-NM25-03515 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:50 | January | 2026 | 2026-01-20 15:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03517 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:57 | January | 2026 | 2026-01-23 09:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 75
202512-NM25-03520 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:15 | March | 2026 | 2026-03-11 16:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 21
202512-NM25-03525 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 07:57 | February | 2026 | 2026-02-10 09:49 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 57
202512-NM25-03526 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-23 08:48 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 104 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 99
202512-NM25-03528 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:34 | February | 2026 | 2026-02-10 14:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 55
202512-NM25-03532 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:16 | January | 2026 | 2026-02-04 09:04 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 19 | 0 | 2026-04-01 | 74
202512-NM25-03534 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:04 | January | 2026 | 2026-01-15 10:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03537 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:35 | January | 2026 | 2026-01-19 08:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-03538 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:39 | January | 2026 | 2026-02-04 12:52 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 64
202512-NM25-03540 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:49 | February | 2026 | 2026-02-09 12:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 54
202512-NM25-03542 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:52 | January | 2026 | 2026-01-15 14:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03544 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:41 | February | 2026 | 2026-02-06 10:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-03547 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:36 | February | 2026 | 2026-02-25 13:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202512-NM25-03548 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:01 | January | 2026 | 2026-01-19 10:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-03552 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 11:43 | December | 2025 | 2026-01-07 14:40 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03554 | GDL17 | Residencial | 7.68 | Period | 2026-02-25 13:43 | February | 2026 | 2026-03-02 09:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-03556 | GDL17 | Residencial | 24.31 | Period | 2026-02-18 15:01 | February | 2026 | 2026-02-24 07:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202512-NM25-03557 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 17:59 | January | 2026 | 2026-01-19 11:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03558 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:56 | March | 2026 | 2026-03-31 10:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202512-NM25-03559 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:49 | January | 2026 | 2026-01-14 12:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-03560 | GDL17 | Residencial | 5.76 | Period | 2026-02-12 18:24 | February | 2026 | 2026-02-18 10:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 47
202512-NM25-03561 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:27 | January | 2026 | 2026-01-21 13:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 75
202512-NM25-03562 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 08:14 | March | 2026 | 2026-04-09 10:07 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 21 | 0 | 2026-04-01 | 13
202512-NM25-03567 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:02 | January | 2026 | 2026-01-19 07:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 76
202512-NM25-03570 | GDL17 | Residencial | 19.1 | Period | 2026-01-26 10:51 | January | 2026 | 2026-01-27 13:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-03573 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 10:03 | March | 2026 | 2026-04-01 14:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-03574 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:11 | March | 2026 | 2026-03-06 07:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 30
202512-NM25-03576 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:35 | January | 2026 | 2026-02-13 09:02 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 30 | 0 | 2026-04-01 | 77
202512-NM25-03577 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:51 | February | 2026 | 2026-02-26 08:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 37
202512-NM25-03579 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:28 | January | 2026 | 2026-01-16 12:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 76
202512-NM25-03585 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:08 | January | 2026 | 2026-01-26 13:33 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 10 | 0 | 2026-04-01 | 75
202512-NM25-03587 | GDL17 | Residencial | 7.68 | Period | 2026-02-12 09:47 | February | 2026 | 2026-02-16 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 3 | 1 | 2026-04-01 | 48
202512-NM25-03588 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:59 | January | 2026 | 2026-01-26 13:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03591 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:20 | January | 2026 | 2026-01-28 10:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 67
202512-NM25-03592 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:27 | January | 2026 | 2026-01-23 08:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 70
202512-NM25-03593 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 10:17 | February | 2026 | 2026-02-09 13:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 56
202512-NM25-03596 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:03 | January | 2026 | 2026-01-19 13:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 76
202512-NM25-03597 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 07:35 | January | 2026 | 2026-01-29 08:45 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 13 | 0 | 2026-04-01 | 75
202512-NM25-03598 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 08:01 | February | 2026 | 2026-02-11 11:24 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202512-NM25-03599 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:46 | January | 2026 | 2026-01-12 14:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-03601 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:45 | January | 2026 | 2026-01-19 15:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-03603 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:47 | January | 2026 | 2026-01-15 14:35 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03605 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:36 | January | 2026 | 2026-01-19 13:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03609 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:35 | January | 2026 | 2026-02-23 15:24 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 25 | 0 | 2026-04-01 | 61
202512-NM25-03610 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:16 | January | 2026 | 2026-01-19 11:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03612 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:15 | January | 2026 | 2026-01-14 09:32 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 12 | 0 | 2026-04-01 | 88
202512-NM25-03613 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 14:49 | February | 2026 | 2026-02-19 14:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 43
202512-NM25-03614 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 08:27 | February | 2026 | 2026-02-24 15:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202512-NM25-03616 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:20 | February | 2026 | 2026-02-09 14:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-03617 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 07:57 | January | 2026 | 2026-01-19 16:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-03618 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 09:53 | March | 2026 | 2026-03-06 14:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 29
202512-NM25-03619 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:00 | January | 2026 | 2026-02-02 12:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 63
202512-NM25-03620 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 08:26 | January | 2026 | 2026-02-09 09:31 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 17 | 0 | 2026-04-01 | 68
202512-NM25-03624 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:38 | January | 2026 | 2026-01-19 13:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03625 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:17 | January | 2026 | 2026-01-19 14:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-03627 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:11 | January | 2026 | 2026-02-04 09:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-03629 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:45 | February | 2026 | 2026-02-10 15:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202512-NM25-03630 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:38 | January | 2026 | 2026-01-29 15:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 67
202512-NM25-03631 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:53 | January | 2026 | 2026-03-20 15:10 | 56 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 56 | 0 | 2026-04-01 | 67
202512-NM25-03633 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:40 | January | 2026 | 2026-01-20 08:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03635 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 11:19 | January | 2026 | 2026-02-11 13:59 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 5 | 9 | 2026-04-01 | 63
202512-NM25-03636 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:48 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 61
202512-NM25-03637 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:50 | January | 2026 | 2026-02-04 14:27 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 63
202512-NM25-03639 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:03 | January | 2026 | 2026-01-29 15:13 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 13 | 0 | 2026-04-01 | 75
202512-NM25-03640 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:31 | January | 2026 | 2026-01-14 08:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-03642 | GDL17 | Residencial | 24 | Period | 2026-01-03 13:14 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 87
202512-NM25-03645 | GDL17 | Residencial | 3.84 | Period | 2026-01-16 08:12 | January | 2026 | 2026-01-20 14:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03647 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-15 18:15 | December | 2025 | 2026-02-13 14:42 | 60 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | MAYAGUEZ | February | 1 | 4 | 56 | 2026-04-01 | 106
202512-NM25-03651 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:39 | February | 2026 | 2026-02-26 08:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-03656 | GDL17 | Residencial | 19.2 | Out of period | 2025-12-20 16:03 | December | 2025 | 2026-02-19 16:13 | 61 | Study | Estudio (E) | Activated | Backlog |  | No | 61 |  | BAYAMON | February |  | 61 | 0 | 2026-04-01 | 101
202512-NM25-03661 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:24 | December | 2025 | 2026-01-07 14:49 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03664 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:47 | January | 2026 | 2026-01-13 16:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-03665 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:15 | January | 2026 | 2026-01-29 12:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-03668 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:59 | March | 2026 | 2026-03-27 07:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-03674 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:02 | January | 2026 | 2026-01-29 11:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03677 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:18 | January | 2026 | 2026-01-16 09:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 76
202512-NM25-03682 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:28 | January | 2026 | 2026-02-02 10:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 64
202512-NM25-03687 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 07:30 | January | 2026 | 2026-01-21 11:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-03688 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:39 | January | 2026 | 2026-01-07 10:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-03689 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:34 | January | 2026 | 2026-01-23 08:13 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 15 | 0 | 2026-04-01 | 83
202512-NM25-03691 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:47 | January | 2026 | 2026-01-20 10:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03693 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:12 | January | 2026 | 2026-01-28 09:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03696 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:05 | January | 2026 | 2026-01-30 08:55 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 15 | 0 | 2026-04-01 | 76
202512-NM25-03698 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:08 | March | 2026 | 2026-03-27 07:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-03702 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:21 | January | 2026 | 2026-01-12 08:53 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 89
202512-NM25-03704 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:16 | March | 2026 | 2026-03-06 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 29
202512-NM25-03707 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 12:47 | January | 2026 | 2026-01-13 10:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-03711 | GDL17 | Residencial | 8 | Period | 2026-01-13 19:48 | January | 2026 | 2026-01-20 08:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 77
202512-NM25-03714 | GDL17 | Residencial | 11.4 | Period | 2026-01-23 18:31 | January | 2026 | 2026-01-26 14:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-03721 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:51 | January | 2026 | 2026-01-09 08:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-03723 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 19:37 | February | 2026 | 2026-02-27 08:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-03727 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:21 | January | 2026 | 2026-01-20 11:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-03728 | GDL17 | Residencial | 3.84 | Period | 2026-02-16 09:58 | February | 2026 | 2026-02-23 07:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 44
202512-NM25-03729 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-16 09:46 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 127 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 106
202512-NM25-03731 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:33 | January | 2026 | 2026-01-23 08:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 74
202512-NM25-03735 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:38 | January | 2026 | 2026-01-26 14:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-03742 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 14:23 | January | 2026 | 2026-03-05 09:34 | 45 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 45 | 0 | 2026-04-01 | 71
202512-NM25-03743 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 10:39 | March | 2026 | 2026-03-13 08:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 23
202512-NM25-03744 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:35 | January | 2026 | 2026-02-09 09:32 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 12 | 0 | 2026-04-01 | 63
202512-NM25-03745 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-16 13:50 | December | 2025 | 2026-02-18 11:02 | 64 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February |  | 64 | 1 | 2026-04-01 | 105
202512-NM25-03747 | GDL17 | Residencial | 5.76 | Period | 2026-01-02 13:52 | January | 2026 | 2026-01-07 10:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-03748 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:24 | January | 2026 | 2026-02-03 16:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-03750 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:23 | March | 2026 | 2026-03-30 07:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 8
202512-NM25-03751 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:10 | January | 2026 | 2026-02-03 10:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 62
202512-NM25-03753 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:20 | January | 2026 | 2026-01-26 12:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 71
202512-NM25-03755 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:22 | January | 2026 | 2026-01-26 15:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03756 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:21 | February | 2026 | 2026-02-25 15:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202512-NM25-03757 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:17 | January | 2026 | 2026-02-02 09:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 64
202512-NM25-03760 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 07:32 | January | 2026 | 2026-01-15 14:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-03762 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 13:45 | January | 2026 | 2026-02-16 08:31 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 64
202512-NM25-03763 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:13 | January | 2026 | 2026-01-12 13:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03764 | GDL17 | Residencial | 3.84 | Out of period | 2025-12-31 11:08 | December | 2025 | 2026-01-13 16:14 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-03767 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:31 | January | 2026 | 2026-02-03 10:09 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 68
202512-NM25-03768 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:50 | January | 2026 | 2026-01-16 12:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 76
202512-NM25-03769 | GDL17 | Residencial | 7.6 | Period | 2026-01-12 14:43 | January | 2026 | 2026-01-21 13:50 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 1 | 6 | 3 | 2026-04-01 | 78
202512-NM25-03770 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:41 | January | 2026 | 2026-01-12 13:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03771 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:03 | January | 2026 | 2026-01-14 08:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 83
202512-NM25-03772 | GDL17 | Residencial | 14.976 | Period | 2026-01-26 13:32 | January | 2026 | 2026-02-16 08:29 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 64
202512-NM25-03773 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:18 | January | 2026 | 2026-02-17 13:41 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 26 | 0 | 2026-04-01 | 68
202512-NM25-03779 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:12 | January | 2026 | 2026-01-20 15:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-03783 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 07:51 | January | 2026 | 2026-01-21 15:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-03784 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 07:43 | January | 2026 | 2026-01-23 15:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 69
202512-NM25-03788 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:35 | January | 2026 | 2026-01-16 16:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03790 | GDL17 | Residencial | 4.224 | Period | 2026-03-24 09:28 | March | 2026 | 2026-03-27 10:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-03791 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 08:31 | February | 2026 | 2026-02-16 15:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 50
202512-NM25-03797 | GDL17 | Residencial | 7.6 | Period | 2026-03-10 14:37 | March | 2026 | 2026-03-12 10:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 21
202512-NM25-03799 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:22 | January | 2026 | 2026-01-21 07:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-03801 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:41 | January | 2026 | 2026-02-02 08:05 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 18 | 0 | 2026-04-01 | 76
202512-NM25-03803 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:45 | January | 2026 | 2026-01-26 13:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-03805 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:03 | January | 2026 | 2026-01-13 09:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-03813 | GDL17 | Residencial | 23 | Out of period | 2025-12-31 08:59 | December | 2025 | 2026-01-05 09:05 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-03814 | GDL17 | Residencial | 10 | Period | 2026-02-20 10:24 | February | 2026 | 2026-02-25 16:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-03824 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-16 15:40 | December | 2025 | 2026-02-06 15:25 | 52 | Study | Estudio (E) | Activated | Backlog |  | No | 52 |  | BAYAMON | February |  | 52 | 0 | 2026-04-01 | 105
202512-NM25-03825 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:15 | February | 2026 | 2026-02-16 11:27 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 54
202512-NM25-03827 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:22 | January | 2026 | 2026-01-22 13:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 71
202512-NM25-03829 | GDL17 | Residencial | 5.76 | Period | 2026-01-08 08:42 | January | 2026 | 2026-01-13 15:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03832 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:17 | January | 2026 | 2026-01-19 12:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 74
202512-NM25-03834 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:29 | March | 2026 | 2026-03-12 15:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 21
202512-NM25-03835 | GDL17 | Residencial | 3.84 | Period | 2026-01-30 11:13 | January | 2026 | 2026-02-10 10:48 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 11 | 0 | 2026-04-01 | 61
202512-NM25-03836 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:10 | January | 2026 | 2026-01-15 15:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-03840 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:07 | January | 2026 | 2026-02-04 09:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 63
202512-NM25-03843 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:40 | January | 2026 | 2026-01-26 13:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 70
202512-NM25-03844 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:31 | January | 2026 | 2026-02-18 12:52 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 30 | 0 | 2026-04-01 | 71
202512-NM25-03846 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:58 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 76
202512-NM25-03847 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:54 | January | 2026 | 2026-01-19 10:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-03849 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:55 | January | 2026 | 2026-02-02 12:54 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 68
202512-NM25-03851 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 08:52 | January | 2026 | 2026-02-03 15:37 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 65
202512-NM25-03852 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:26 | January | 2026 | 2026-02-09 09:22 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 14 | 0 | 2026-04-01 | 64
202512-NM25-03854 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:24 | January | 2026 | 2026-01-16 12:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 76
202512-NM25-03855 | GDL17 | Residencial | 7.68 | Period | 2026-03-24 09:36 | March | 2026 | 2026-03-27 09:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-03857 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:37 | January | 2026 | 2026-01-26 14:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 69
202512-NM25-03858 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:58 | January | 2026 | 2026-02-02 14:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-03859 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:10 | January | 2026 | 2026-01-27 13:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-03861 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:55 | January | 2026 | 2026-01-13 09:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03863 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:52 | January | 2026 | 2026-01-30 16:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-03868 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:31 | February | 2026 | 2026-02-09 09:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-03870 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:43 | January | 2026 | 2026-01-13 16:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-03872 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:49 | December | 2025 | 2026-01-07 10:15 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-03876 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:07 | January | 2026 | 2026-01-26 13:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 69
202512-NM25-03877 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 14:59 | March | 2026 | 2026-03-18 13:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 15
202512-NM25-03878 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:37 | January | 2026 | 2026-01-21 15:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 72
202512-NM25-03882 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:24 | January | 2026 | 2026-01-12 16:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-03884 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:57 | January | 2026 | 2026-01-29 16:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-03885 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 07:32 | January | 2026 | 2026-01-28 11:13 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 20 | 0 | 2026-04-01 | 83
202512-NM25-03888 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:08 | January | 2026 | 2026-02-02 13:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 64
202512-NM25-03889 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:56 | January | 2026 | 2026-01-29 10:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03893 | GDL17 | Residencial | 4.992 | Period | 2026-03-17 12:43 | March | 2026 | 2026-03-20 15:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 14
202512-NM25-03895 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:31 | February | 2026 | 2026-02-13 09:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 54
202512-NM25-03897 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:19 | January | 2026 | 2026-01-29 13:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03898 | GDL17 | Residencial | 24 | Period | 2026-01-13 21:25 | January | 2026 | 2026-01-15 09:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-03899 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:52 | January | 2026 | 2026-01-26 08:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 68
202512-NM25-03900 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:07 | January | 2026 | 2026-01-08 09:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 88
202512-NM25-03903 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:22 | January | 2026 | 2026-01-29 09:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 67
202512-NM25-03904 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:43 | January | 2026 | 2026-01-26 13:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03906 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 08:21 | January | 2026 | 2026-01-26 15:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-03910 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:34 | January | 2026 | 2026-01-29 09:16 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | January | 1 | 3 | 10 | 2026-04-01 | 75
202512-NM25-03911 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-19 16:24 | December | 2025 | 2026-03-20 08:09 | 91 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | PONCE | March | 1 | 6 | 85 | 2026-04-01 | 102
202512-NM25-03913 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:12 | January | 2026 | 2026-01-22 11:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 75
202512-NM25-03914 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:25 | January | 2026 | 2026-02-11 14:57 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 20 | 0 | 2026-04-01 | 68
202512-NM25-03920 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:18 | January | 2026 | 2026-01-13 09:00 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 89
202512-NM25-03922 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 15:58 | February | 2026 | 2026-02-18 10:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 45
202512-NM25-03923 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 20:28 | February | 2026 | 2026-02-20 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 43
202512-NM25-03927 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:29 | February | 2026 | 2026-03-02 12:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-03931 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:51 | January | 2026 | 2026-01-21 07:43 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 11 | 0 | 2026-04-01 | 82
202512-NM25-03936 | GDL17 | Residencial | 3.84 | Period | 2026-01-27 08:13 | January | 2026 | 2026-01-28 14:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 64
202512-NM25-03945 | GDL17 | Residencial | 3.8 | Period | 2026-02-21 19:22 | February | 2026 | 2026-03-03 07:49 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 38
202512-NM25-03946 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 17:59 | March | 2026 | 2026-03-05 15:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 29
202512-NM25-03950 | GDL17 | Residencial | 8 | Period | 2026-01-03 17:48 | January | 2026 | 2026-01-08 13:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 87
202512-NM25-03954 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 13:21 | March | 2026 | 2026-03-16 10:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 19
202512-NM25-03956 | GDL17 | Comercial | 11.5 | Period | 2026-02-17 18:42 | February | 2026 | 2026-02-24 08:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 42
202512-NM25-03957 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:11 | March | 2026 | 2026-04-07 09:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 7 | 0 | 2026-04-01 | 2
202512-NM25-03958 | GDL17 | Residencial | 15 | Period | 2026-01-08 18:04 | January | 2026 | 2026-01-13 15:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-03959 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:40 | February | 2026 | 2026-02-04 18:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-03960 | GDL17 | Residencial | 16 | Out of period | 2025-12-22 08:03 | December | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 100
202512-NM25-03961 | GDL17 | Residencial | 22.8 | Period | 2026-01-09 15:59 | January | 2026 | 2026-01-20 08:45 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 81
202512-NM25-03962 | GDL17 | Residencial | 18 | Period | 2026-02-23 10:31 | February | 2026 | 2026-03-16 07:48 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 21 | 0 | 2026-04-01 | 37
202512-NM25-03963 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:44 | January | 2026 | 2026-02-04 08:01 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-03965 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:04 | January | 2026 | 2026-01-20 12:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 74
202512-NM25-03967 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:18 | January | 2026 | 2026-01-20 08:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-03969 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 12:58 | January | 2026 | 2026-02-02 10:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-03970 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:10 | January | 2026 | 2026-01-16 09:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-03972 | GDL17 | Residencial | 23 | Period | 2026-01-09 10:52 | January | 2026 | 2026-02-27 15:53 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | February | 1 | 1 | 48 | 2026-04-01 | 82
202512-NM25-03973 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:23 | January | 2026 | 2026-01-28 09:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-03974 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:09 | December | 2025 | 2026-01-08 13:19 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-03981 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:05 | January | 2026 | 2026-01-21 16:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-03983 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:56 | January | 2026 | 2026-01-26 14:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-03988 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 20:13 | February | 2026 | 2026-02-26 08:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 38
202512-NM25-03992 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:39 | February | 2026 | 2026-02-23 09:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202512-NM25-03994 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 07:58 | February | 2026 | 2026-02-24 16:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202512-NM25-03996 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:17 | January | 2026 | 2026-02-03 13:01 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 71
202512-NM25-03998 | GDL17 | Residencial | 3.84 | Period | 2026-01-14 12:47 | January | 2026 | 2026-01-20 15:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-04001 | GDL17 | Residencial | 3.84 | Period | 2026-01-09 08:53 | January | 2026 | 2026-01-13 13:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-04002 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:03 | February | 2026 | 2026-02-06 15:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 55
202512-NM25-04003 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:08 | January | 2026 | 2026-02-09 07:56 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 60
202512-NM25-04006 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:01 | February | 2026 | 2026-02-25 08:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202512-NM25-04011 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:11 | January | 2026 | 2026-01-22 14:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 72
202512-NM25-04015 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:55 | January | 2026 | 2026-01-21 14:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-04019 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:33 | January | 2026 | 2026-01-16 15:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-04021 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 10:44 | January | 2026 | 2026-02-04 11:07 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 6 | 2 | 2026-04-01 | 64
202512-NM25-04022 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:30 | December | 2025 | 2026-01-08 15:26 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-04023 | GDL17 | Residencial | 23 | Period | 2026-01-08 08:26 | January | 2026 | 2026-01-16 13:52 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 83
202512-NM25-04026 | GDL17 | Residencial | 4.224 | Period | 2026-02-16 13:35 | February | 2026 | 2026-02-26 10:51 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 43
202512-NM25-04029 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 08:55 | January | 2026 | 2026-01-20 15:32 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 12 | 0 | 2026-04-01 | 83
202512-NM25-04033 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:38 | January | 2026 | 2026-02-04 17:47 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 19 | 0 | 2026-04-01 | 74
202512-NM25-04034 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:52 | February | 2026 | 2026-02-05 10:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 57
202512-NM25-04035 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:20 | January | 2026 | 2026-01-28 09:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-04039 | GDL17 | Residencial | 8.83 | Period | 2026-01-21 10:56 | January | 2026 | 2026-01-22 09:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-04043 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:53 | February | 2026 | 2026-02-24 14:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202512-NM25-04045 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:03 | January | 2026 | 2026-01-26 08:56 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 9 | 0 | 2026-04-01 | 74
202512-NM25-04047 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:33 | January | 2026 | 2026-02-06 09:35 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 64
202512-NM25-04050 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 14:49 | March | 2026 | 2026-03-13 14:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 20
202512-NM25-04057 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:50 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 74
202512-NM25-04061 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:47 | January | 2026 | 2026-01-26 14:34 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 74
202512-NM25-04065 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:55 | January | 2026 | 2026-01-23 09:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 69
202512-NM25-04066 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:06 | January | 2026 | 2026-01-23 08:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 71
202512-NM25-04067 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:44 | January | 2026 | 2026-01-19 09:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 76
202512-NM25-04069 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 09:52 | February | 2026 | 2026-02-16 14:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 49
202512-NM25-04070 | GDL17 | Residencial | 3.84 | Period | 2026-01-26 10:38 | January | 2026 | 2026-02-02 13:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 65
202512-NM25-04077 | GDL17 | Residencial | 3.84 | Period | 2026-01-20 08:07 | January | 2026 | 2026-01-22 09:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 71
202512-NM25-04078 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:38 | January | 2026 | 2026-01-26 11:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 71
202512-NM25-04080 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:35 | January | 2026 | 2026-02-02 14:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 62
202512-NM25-04081 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:50 | January | 2026 | 2026-01-30 15:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 65
202512-NM25-04082 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 20:16 | February | 2026 | 2026-03-03 11:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 33
202512-NM25-04083 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 09:11 | January | 2026 | 2026-01-29 11:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 68
202512-NM25-04086 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 09:28 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 13
202512-NM25-04087 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 14:51 | February | 2026 | 2026-02-19 08:58 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 48
202512-NM25-04090 | GDL17 | Residencial | 7.6 | Period | 2026-02-10 12:37 | February | 2026 | 2026-02-16 11:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 49
202512-NM25-04091 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:40 | January | 2026 | 2026-01-22 09:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-04095 | GDL17 | Residencial | 3.84 | Period | 2026-01-29 09:22 | January | 2026 | 2026-02-20 08:56 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 62
202512-NM25-04099 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:11 | February | 2026 | 2026-03-02 09:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 37
202512-NM25-04106 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 14:04 | February | 2026 | 2026-02-18 13:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 47
202512-NM25-04107 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 11:34 | December | 2025 | 2026-03-26 16:24 | 99 | Study | Estudio (E) | Activated | Backlog |  | No | 99 |  | BAYAMON | March |  | 99 | 0 | 2026-04-01 | 105
202512-NM25-04108 | GDL17 | Residencial | 3.8 | Period | 2026-01-08 13:00 | January | 2026 | 2026-01-13 08:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-04123 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:58 | January | 2026 | 2026-01-29 15:14 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 72
202512-NM25-04128 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 16:06 | January | 2026 | 2026-01-22 13:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-04130 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:10 | January | 2026 | 2026-01-29 11:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-04132 | GDL17 | Residencial | 3.84 | Period | 2026-01-22 15:23 | January | 2026 | 2026-01-27 10:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 68
202512-NM25-04133 | GDL17 | Residencial | 17.644 | Period | 2026-02-05 08:23 | February | 2026 | 2026-02-09 09:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-04134 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:20 | January | 2026 | 2026-01-21 15:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-04137 | GDL17 | Residencial | 9 | Period | 2026-02-21 11:01 | February | 2026 | 2026-02-26 15:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-04138 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:16 | January | 2026 | 2026-01-23 08:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 71
202512-NM25-04142 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:39 | February | 2026 | 2026-02-11 14:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202512-NM25-04145 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:05 | January | 2026 | 2026-02-03 13:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 60
202512-NM25-04146 | GDL17 | Residencial | 4.992 | Period | 2026-01-07 14:30 | January | 2026 | 2026-01-21 13:24 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | January | 1 | 3 | 11 | 2026-04-01 | 83
202512-NM25-04149 | GDL17 | Residencial | 3.84 | Period | 2026-01-30 10:08 | January | 2026 | 2026-02-17 08:34 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 61
202512-NM25-04150 | GDL17 | Residencial | 11.4 | Period | 2026-01-26 09:43 | January | 2026 | 2026-01-27 14:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-04151 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:14 | January | 2026 | 2026-02-02 10:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 64
202512-NM25-04153 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:58 | January | 2026 | 2026-01-14 16:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-04154 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 17:15 | February | 2026 | 2026-03-09 10:57 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 32
202512-NM25-04157 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:29 | February | 2026 | 2026-02-23 09:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202512-NM25-04158 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:04 | January | 2026 | 2026-01-13 09:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-04161 | GDL17 | Residencial | 4.992 | Period | 2026-01-23 10:27 | January | 2026 | 2026-01-26 14:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-04162 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:05 | February | 2026 | 2026-02-04 16:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-04163 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:10 | January | 2026 | 2026-02-09 11:10 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 20 | 0 | 2026-04-01 | 70
202512-NM25-04164 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:05 | March | 2026 | 2026-03-09 12:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 27
202512-NM25-04165 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 12:57 | March | 2026 | 2026-03-23 15:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 14
202512-NM25-04169 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:42 | January | 2026 | 2026-01-19 11:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-04173 | GDL17 | Residencial | 7.6 | Period | 2026-01-08 10:03 | January | 2026 | 2026-01-13 14:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04174 | GDL17 | Residencial | 3.84 | Period | 2026-01-02 10:18 | January | 2026 | 2026-01-08 08:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 89
202512-NM25-04175 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 10:45 | January | 2026 | 2026-02-02 09:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 62
202512-NM25-04179 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 09:20 | January | 2026 | 2026-01-21 15:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 72
202512-NM25-04180 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:25 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 83
202512-NM25-04182 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 12:13 | January | 2026 | 2026-01-26 10:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 68
202512-NM25-04184 | GDL17 | Residencial | 3.84 | Period | 2026-01-16 09:08 | January | 2026 | 2026-01-19 16:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-04189 | GDL17 | Residencial | 5.376 | Period | 2026-01-02 09:15 | January | 2026 | 2026-01-08 10:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 89
202512-NM25-04194 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:07 | February | 2026 | 2026-02-27 09:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-04200 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 14:07 | December | 2025 | 2026-03-26 16:28 | 99 | Study | Estudio (E) | Activated | Backlog |  | No | 99 |  | CAGUAS | March |  | 99 | 0 | 2026-04-01 | 104
202512-NM25-04208 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-29 10:13 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 93
202512-NM25-04211 | GDL17 | Residencial | 8 | Period | 2026-01-05 02:01 | January | 2026 | 2026-01-09 15:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 86
202512-NM25-04215 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:44 | February | 2026 | 2026-03-06 13:33 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 32
202512-NM25-04217 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:04 | January | 2026 | 2026-01-21 11:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-04220 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:35 | January | 2026 | 2026-01-22 09:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-04221 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:18 | January | 2026 | 2026-01-22 09:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-04223 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:07 | February | 2026 | 2026-02-13 14:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 47
202512-NM25-04224 | GDL17 | Residencial | 23 | Period | 2026-03-02 16:48 | March | 2026 | 2026-03-11 13:40 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 9 | 0 | 2026-04-01 | 29
202512-NM25-04225 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 14:45 | January | 2026 | 2026-01-20 15:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-04227 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:44 | February | 2026 | 2026-02-18 10:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202512-NM25-04229 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:30 | February | 2026 | 2026-03-12 14:46 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 34 | 0 | 2026-04-01 | 54
202512-NM25-04234 | GDL17 | Residencial | 8 | Period | 2026-01-07 15:58 | January | 2026 | 2026-01-21 14:35 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 2 | 6 | 8 | 2026-04-01 | 83
202512-NM25-04235 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:57 | January | 2026 | 2026-01-12 13:43 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 10 | 0 | 2026-04-01 | 88
202512-NM25-04244 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:17 | January | 2026 | 2026-01-21 16:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-04246 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 18:37 | March | 2026 | 2026-03-06 09:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202512-NM25-04247 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-17 16:09 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 104
202512-NM25-04264 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:09 | January | 2026 | 2026-01-29 10:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 65
202512-NM25-04268 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-17 17:07 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 110 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 104
202512-NM25-04270 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:16 | March | 2026 | 2026-03-10 13:33 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 29
202512-NM25-04275 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:47 | February | 2026 | 2026-02-04 15:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-04286 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 10:08 | February | 2026 | 2026-03-16 13:55 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 6 | 22 | 2026-04-01 | 44
202512-NM25-04287 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:49 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 12
202512-NM25-04290 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 14:45 | February | 2026 | 2026-02-16 08:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 48
202512-NM25-04294 | GDL17 | Residencial | 11.5 | Period | 2026-02-14 13:26 | February | 2026 | 2026-02-18 08:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 45
202512-NM25-04299 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 18:10 | February | 2026 | 2026-02-06 14:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-04305 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:43 | February | 2026 | 2026-03-05 13:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 33
202512-NM25-04310 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 15:30 | January | 2026 | 2026-01-21 09:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 74
202512-NM25-04312 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:56 | January | 2026 | 2026-01-14 13:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-04316 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:10 | January | 2026 | 2026-01-22 13:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-04317 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:56 | January | 2026 | 2026-01-16 13:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202512-NM25-04319 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:12 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 67
202512-NM25-04320 | GDL17 | Residencial | 9.984 | Period | 2026-01-07 10:14 | January | 2026 | 2026-01-09 08:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-04330 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:22 | January | 2026 | 2026-01-22 09:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-04331 | GDL17 | Residencial | 15.2 | Period | 2026-01-02 09:48 | January | 2026 | 2026-01-08 10:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 89
202512-NM25-04333 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:12 | December | 2025 | 2026-01-07 09:25 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-04339 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:58 | February | 2026 | 2026-02-25 15:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-04341 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 14:23 | January | 2026 | 2026-02-02 12:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-04342 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:20 | January | 2026 | 2026-01-19 14:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-04347 | GDL17 | Residencial | 5.76 | Period | 2026-01-07 14:08 | January | 2026 | 2026-01-09 08:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 83
202512-NM25-04354 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 08:40 | December | 2025 | 2026-01-14 13:39 | 14 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 14 | 0 | 2026-04-01 | 91
202512-NM25-04355 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:48 | January | 2026 | 2026-01-30 09:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-04364 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-18 10:21 | December | 2025 | 2026-03-02 12:56 | 74 | Study | Estudio (E) | Activated | Backlog |  | No | 74 |  | BAYAMON | March |  | 74 | 0 | 2026-04-01 | 104
202512-NM25-04371 | GDL17 | Residencial | 23 | Period | 2026-01-08 10:38 | January | 2026 | 2026-02-04 09:23 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 2 | 25 | 2026-04-01 | 83
202512-NM25-04374 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:39 | February | 2026 | 2026-03-02 10:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 35
202512-NM25-04375 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:30 | January | 2026 | 2026-01-13 14:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04376 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 09:48 | January | 2026 | 2026-01-22 13:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-04379 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:34 | January | 2026 | 2026-01-12 15:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04380 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:38 | January | 2026 | 2026-01-13 13:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04384 | GDL17 | Residencial | 3.84 | Period | 2026-01-02 09:45 | January | 2026 | 2026-01-09 10:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 89
202512-NM25-04385 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:13 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 64
202512-NM25-04387 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:31 | January | 2026 | 2026-01-13 08:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-04390 | GDL17 | Residencial | 8 | Period | 2026-02-19 10:05 | February | 2026 | 2026-02-24 08:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 41
202512-NM25-04393 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:17 | February | 2026 | 2026-02-13 16:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 47
202512-NM25-04395 | GDL17 | Residencial | 23 | Period | 2026-02-04 15:19 | February | 2026 | 2026-02-09 15:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202512-NM25-04397 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 07:31 | December | 2025 | 2026-01-21 13:10 | 21 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 21 | 0 | 2026-04-01 | 91
202512-NM25-04399 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:57 | February | 2026 | 2026-03-05 07:49 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 9 | 0 | 2026-04-01 | 36
202512-NM25-04400 | GDL17 | Residencial | 4.224 | Period | 2026-03-03 10:25 | March | 2026 | 2026-03-05 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 29
202512-NM25-04401 | GDL17 | Residencial | 24.78 | Period | 2026-01-07 19:38 | January | 2026 | 2026-01-14 09:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 83
202512-NM25-04404 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:57 | January | 2026 | 2026-01-30 10:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 63
202512-NM25-04406 | GDL17 | Residencial | 8 | Period | 2026-01-21 14:28 | January | 2026 | 2026-01-26 09:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 69
202512-NM25-04409 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 20:20 | January | 2026 | 2026-02-12 10:53 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 60
202512-NM25-04411 | GDL17 | Residencial | 7.6 | Period | 2026-02-23 11:40 | February | 2026 | 2026-03-05 08:21 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 9 | 0 | 2026-04-01 | 37
202512-NM25-04414 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:06 | December | 2025 | 2026-01-07 15:01 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-04417 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:29 | January | 2026 | 2026-01-21 15:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-04419 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:48 | February | 2026 | 2026-03-02 11:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-04420 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 09:54 | January | 2026 | 2026-01-09 10:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 89
202512-NM25-04421 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-18 11:01 | December | 2025 | 2026-02-05 18:01 | 49 | Study | Estudio (E) | Activated | Backlog |  | No | 49 |  | SAN JUAN | February |  | 49 | 0 | 2026-04-01 | 104
202512-NM25-04422 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:22 | January | 2026 | 2026-01-08 15:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 89
202512-NM25-04423 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:11 | January | 2026 | 2026-01-29 11:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-04424 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:44 | January | 2026 | 2026-01-12 12:38 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 10 | 0 | 2026-04-01 | 89
202512-NM25-04425 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 20:15 | March | 2026 | 2026-03-23 15:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 13
202512-NM25-04428 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:11 | January | 2026 | 2026-01-08 09:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 89
202512-NM25-04430 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:48 | February | 2026 | 2026-02-26 09:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202512-NM25-04432 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:55 | February | 2026 | 2026-03-02 13:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 35
202512-NM25-04433 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:49 | March | 2026 | 2026-03-27 10:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-04434 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:19 | January | 2026 | 2026-01-19 13:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-04435 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 17:31 | March | 2026 | 2026-04-21 14:17 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 33 | 0 | 2026-04-01 | 12
202512-NM25-04436 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:15 | February | 2026 | 2026-03-06 15:53 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 10 | 0 | 2026-04-01 | 36
202512-NM25-04438 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:19 | January | 2026 | 2026-01-22 07:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-04441 | GDL17 | Residencial | 23 | Period | 2026-02-23 11:03 | February | 2026 | 2026-02-27 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 37
202512-NM25-04443 | GDL17 | Residencial | 9.216 | Period | 2026-01-07 15:36 | January | 2026 | 2026-01-12 10:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04445 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:41 | January | 2026 | 2026-01-19 14:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-04447 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-29 08:08 | December | 2025 | 2026-03-03 09:58 | 64 | Study | Estudio (E) | Activated | Backlog |  | No | 64 |  | BAYAMON | March |  | 64 | 0 | 2026-04-01 | 93
202512-NM25-04449 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:10 | January | 2026 | 2026-01-19 13:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 74
202512-NM25-04450 | GDL17 | Residencial | 23 | Period | 2026-03-02 17:18 | March | 2026 | 2026-03-05 09:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202512-NM25-04451 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 16:40 | February | 2026 | 2026-02-12 15:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 49
202512-NM25-04453 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:40 | December | 2025 | 2026-01-08 15:21 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-04455 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:28 | February | 2026 | 2026-02-09 15:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-04456 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:23 | January | 2026 | 2026-01-19 10:12 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 10 | 0 | 2026-04-01 | 82
202512-NM25-04457 | GDL17 | Residencial | 5.76 | Out of period | 2025-12-31 11:28 | December | 2025 | 2026-01-19 15:45 | 19 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 19 | 0 | 2026-04-01 | 91
202512-NM25-04464 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:11 | December | 2025 | 2026-01-13 08:56 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-04467 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:15 | January | 2026 | 2026-01-19 11:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-04470 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 12:57 | March | 2026 | 2026-04-01 14:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 5 | 0 | 2026-04-01 | 4
202512-NM25-04472 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-18 11:58 | December | 2025 | 2026-02-19 15:52 | 63 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | BAYAMON | February | 1 | 63 | 0 | 2026-04-01 | 104
202512-NM25-04478 | GDL17 | Residencial | 3.84 | Period | 2026-01-07 10:48 | January | 2026 | 2026-01-12 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-04480 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 15:53 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 60
202512-NM25-04482 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:29 | January | 2026 | 2026-01-22 13:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-04484 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:48 | January | 2026 | 2026-01-14 14:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-04485 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 12:30 | January | 2026 | 2026-01-13 13:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-04486 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:17 | January | 2026 | 2026-01-15 08:08 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-04487 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:19 | March | 2026 | 2026-04-08 09:00 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 35 | 0 | 2026-04-01 | 27
202512-NM25-04490 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:39 | January | 2026 | 2026-01-13 09:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04491 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:00 | January | 2026 | 2026-01-21 08:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-04493 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:44 | December | 2025 | 2026-01-07 11:19 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-04495 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:06 | December | 2025 | 2026-01-14 13:33 | 14 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 14 | 0 | 2026-04-01 | 91
202512-NM25-04498 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-24 13:06 | December | 2025 | 2026-02-04 15:02 | 42 | Study | Estudio (E) | Activated | Backlog |  | No | 42 |  | CAGUAS | February |  | 42 | 0 | 2026-04-01 | 97
202512-NM25-04500 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:50 | December | 2025 | 2026-01-14 14:32 | 14 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 14 | 0 | 2026-04-01 | 91
202512-NM25-04506 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:33 | December | 2025 | 2026-01-13 13:46 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-04510 | GDL17 | Residencial | 8 | Period | 2026-01-15 12:05 | January | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 75
202512-NM25-04511 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:26 | January | 2026 | 2026-02-11 13:48 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 15 | 0 | 2026-04-01 | 63
202512-NM25-04513 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:16 | January | 2026 | 2026-01-20 14:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 76
202512-NM25-04514 | GDL17 | Residencial | 4.992 | Period | 2026-01-27 09:58 | January | 2026 | 2026-01-30 15:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | January | 1 | 2 | 1 | 2026-04-01 | 64
202512-NM25-04522 | GDL17 | Residencial | 10.752 | Period | 2026-01-14 13:22 | January | 2026 | 2026-01-20 16:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-04523 | GDL17 | Residencial | 7.6 | Period | 2026-03-09 10:03 | March | 2026 | 2026-03-09 14:41 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 23
202512-NM25-04527 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 10:44 | January | 2026 | 2026-01-29 09:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-04529 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:18 | January | 2026 | 2026-02-10 08:28 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 12 | 0 | 2026-04-01 | 61
202512-NM25-04531 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:51 | February | 2026 | 2026-02-04 14:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-04535 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-18 14:33 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 103
202512-NM25-04536 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 14:31 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 64
202512-NM25-04538 | GDL17 | Residencial | 23 | Period | 2026-02-24 15:38 | February | 2026 | 2026-03-03 15:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 35
202512-NM25-04539 | GDL17 | Residencial | 7.6 | Period | 2026-02-02 13:33 | February | 2026 | 2026-02-10 09:02 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 57
202512-NM25-04540 | GDL17 | Residencial | 3.8 | Period | 2026-02-16 12:23 | February | 2026 | 2026-02-23 14:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 43
202512-NM25-04541 | GDL17 | Residencial | 14.274 | Period | 2026-01-27 14:16 | January | 2026 | 2026-02-04 08:04 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 63
202512-NM25-04542 | GDL17 | Residencial | 5.376 | Period | 2026-01-07 09:50 | January | 2026 | 2026-01-12 11:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-04544 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 08:45 | January | 2026 | 2026-02-03 16:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-04545 | GDL17 | Residencial | 7.6 | Period | 2026-02-18 08:42 | February | 2026 | 2026-03-03 08:03 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 13 | 0 | 2026-04-01 | 42
202512-NM25-04548 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 18:58 | January | 2026 | 2026-02-16 09:38 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 16 | 0 | 2026-04-01 | 60
202512-NM25-04550 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 06:33 | February | 2026 | 2026-02-19 14:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 47
202512-NM25-04551 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:30 | January | 2026 | 2026-02-03 08:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-04553 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 18:57 | March | 2026 | 2026-04-10 09:58 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 15 | 0 | 2026-04-01 | 5
202512-NM25-04558 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:26 | January | 2026 | 2026-01-23 16:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 68
202512-NM25-04561 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 11:28 | January | 2026 | 2026-01-12 14:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-04562 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-18 15:20 | December | 2025 | 2026-03-04 10:23 | 76 | Study | Estudio (E) | Activated | Backlog |  | No | 76 |  | MAYAGUEZ | March |  | 76 | 0 | 2026-04-01 | 103
202512-NM25-04567 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 10:24 | January | 2026 | 2026-02-09 12:27 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 10 | 0 | 2026-04-01 | 61
202512-NM25-04574 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:57 | January | 2026 | 2026-01-29 09:38 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 12 | 0 | 2026-04-01 | 75
202512-NM25-04576 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 11:18 | January | 2026 | 2026-01-30 08:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-04577 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:04 | February | 2026 | 2026-02-18 10:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 46
202512-NM25-04578 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 14:44 | January | 2026 | 2026-02-03 15:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202512-NM25-04582 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-18 16:09 | December | 2025 | 2026-02-11 07:33 | 55 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 2 | 43 | 0 | 2026-04-01 | 103
202512-NM25-04590 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 09:45 | January | 2026 | 2026-02-10 13:57 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 13 | 2 | 2026-04-01 | 68
202512-NM25-04594 | GDL17 | Residencial | 11.904 | Period | 2026-03-02 12:11 | March | 2026 | 2026-03-11 08:55 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 29
202512-NM25-04596 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:47 | February | 2026 | 2026-03-03 13:21 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 39
202512-NM25-04597 | GDL17 | Residencial | 8 | Period | 2026-01-05 13:51 | January | 2026 | 2026-02-03 10:47 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 6 | 23 | 2026-04-01 | 85
202512-NM25-04598 | GDL17 | Residencial | 19.1 | Period | 2026-02-24 16:55 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 35
202512-NM25-04599 | GDL17 | Residencial | 23 | Period | 2026-02-24 16:54 | February | 2026 | 2026-03-02 10:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 35
202512-NM25-04600 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 19:01 | February | 2026 | 2026-02-20 08:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202512-NM25-04601 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 20:03 | February | 2026 | 2026-02-11 16:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 49
202512-NM25-04603 | GDL17 | Residencial | 8 | Period | 2026-01-05 02:24 | January | 2026 | 2026-01-12 09:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 86
202512-NM25-04606 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:14 | February | 2026 | 2026-02-27 10:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 35
202512-NM25-04607 | GDL17 | Residencial | 8 | Period | 2026-01-05 02:59 | January | 2026 | 2026-01-08 09:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 86
202512-NM25-04608 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:25 | February | 2026 | 2026-02-25 15:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-04609 | GDL17 | Residencial | 12 | Period | 2026-01-19 23:40 | January | 2026 | 2026-02-06 15:01 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 71
202512-NM25-04610 | GDL17 | Residencial | 13.6 | Period | 2026-02-25 10:38 | February | 2026 | 2026-02-27 14:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 35
202512-NM25-04621 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:17 | January | 2026 | 2026-01-19 13:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-04627 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 15:55 | January | 2026 | 2026-01-29 12:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 67
202512-NM25-04630 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 12:41 | January | 2026 | 2026-01-21 08:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-04636 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:26 | January | 2026 | 2026-01-28 09:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 67
202512-NM25-04638 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 07:33 | December | 2025 | 2026-01-05 08:08 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-04640 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:37 | January | 2026 | 2026-01-21 11:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-04641 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:25 | December | 2025 | 2026-01-07 13:31 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-04642 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 15:56 | February | 2026 | 2026-03-11 08:08 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 14 | 0 | 2026-04-01 | 34
202512-NM25-04643 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:48 | December | 2025 | 2026-01-15 08:13 | 15 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 15 | 0 | 2026-04-01 | 91
202512-NM25-04644 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:15 | January | 2026 | 2026-01-21 14:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-04647 | GDL17 | Residencial | 23 | Period | 2026-01-14 13:52 | January | 2026 | 2026-01-15 14:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-04653 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:18 | February | 2026 | 2026-02-17 08:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202512-NM25-04658 | GDL17 | Residencial | 20.716 | Period | 2026-01-15 09:41 | January | 2026 | 2026-01-16 15:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-04660 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 09:27 | January | 2026 | 2026-01-07 12:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 89
202512-NM25-04661 | GDL17 | Comercial | 11.5 | Period | 2026-01-19 13:18 | January | 2026 | 2026-01-20 15:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-04662 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:56 | January | 2026 | 2026-02-02 08:41 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 17 | 0 | 2026-04-01 | 75
202512-NM25-04664 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 11:24 | February | 2026 | 2026-02-24 15:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202512-NM25-04665 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 17:12 | March | 2026 | 2026-03-31 12:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-04667 | GDL17 | Residencial | 3.8 | Period | 2026-01-15 07:47 | January | 2026 | 2026-02-11 15:09 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 27 | 0 | 2026-04-01 | 76
202512-NM25-04668 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 08:56 | January | 2026 | 2026-01-26 13:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 69
202512-NM25-04669 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-22 13:06 | December | 2025 | 2026-02-11 12:42 | 51 | Study | Estudio (E) | Activated | Backlog |  | No | 51 |  | MAYAGUEZ | February |  | 51 | 0 | 2026-04-01 | 99
202512-NM25-04671 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:38 | January | 2026 | 2026-03-30 13:47 | 62 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March |  | 62 | 0 | 2026-04-01 | 64
202512-NM25-04674 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 09:13 | January | 2026 | 2026-01-15 08:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-04676 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 09:28 | February | 2026 | 2026-02-04 15:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 58
202512-NM25-04678 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:03 | February | 2026 | 2026-02-11 16:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 55
202512-NM25-04679 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:00 | February | 2026 | 2026-02-26 08:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202512-NM25-04681 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-29 08:21 | December | 2025 | 2026-03-11 15:32 | 72 | Study | Estudio (E) | Activated | Backlog |  | No | 72 |  | BAYAMON | March |  | 72 | 0 | 2026-04-01 | 93
202512-NM25-04683 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-19 11:02 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 103
202512-NM25-04684 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 07:16 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 8
202512-NM25-04685 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 19:57 | February | 2026 | 2026-02-25 14:57 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 15 | 0 | 2026-04-01 | 49
202512-NM25-04686 | GDL17 | Residencial | 23 | Period | 2026-01-14 10:00 | January | 2026 | 2026-01-23 15:00 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 9 | 0 | 2026-04-01 | 77
202512-NM25-04687 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:33 | January | 2026 | 2026-01-14 13:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 82
202512-NM25-04692 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:02 | January | 2026 | 2026-01-26 10:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 70
202512-NM25-04693 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:52 | January | 2026 | 2026-01-13 10:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04694 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:51 | January | 2026 | 2026-02-16 14:54 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 21 | 0 | 2026-04-01 | 64
202512-NM25-04697 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:11 | January | 2026 | 2026-01-12 15:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04698 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 12:16 | January | 2026 | 2026-01-14 13:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 83
202512-NM25-04701 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 15:04 | January | 2026 | 2026-01-12 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-04702 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 07:29 | January | 2026 | 2026-01-19 15:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 77
202512-NM25-04704 | GDL17 | Residencial | 6.912 | Period | 2026-01-02 11:30 | January | 2026 | 2026-01-14 14:52 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 12 | 0 | 2026-04-01 | 89
202512-NM25-04705 | GDL17 | Residencial | 7.6 | Period | 2026-02-19 10:09 | February | 2026 | 2026-02-26 08:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202512-NM25-04707 | GDL17 | Residencial | 7.6 | Period | 2026-01-05 13:52 | January | 2026 | 2026-01-13 11:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | January | 1 | 6 | 2 | 2026-04-01 | 85
202512-NM25-04708 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-19 11:52 | December | 2025 | 2026-03-13 14:59 | 84 | Study | Estudio (E) | Activated | Backlog |  | No | 84 |  | ARECIBO | March |  | 84 | 0 | 2026-04-01 | 103
202512-NM25-04710 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:55 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 70
202512-NM25-04711 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:25 | January | 2026 | 2026-01-15 09:25 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 83
202512-NM25-04714 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:55 | March | 2026 | 2026-03-27 07:59 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 14
202512-NM25-04715 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:45 | March | 2026 | 2026-03-05 14:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 29
202512-NM25-04718 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 15:32 | January | 2026 | 2026-01-26 08:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-04720 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 21:21 | February | 2026 | 2026-02-25 15:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 41
202512-NM25-04722 | GDL17 | Residencial | 11.4 | Period | 2026-02-12 09:32 | February | 2026 | 2026-02-13 10:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202512-NM25-04727 | GDL17 | Residencial | 3.8 | Out of period | 2025-12-31 12:07 | December | 2025 | 2026-01-12 13:36 | 12 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 90
202512-NM25-04729 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:36 | March | 2026 | 2026-03-05 15:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 28
202512-NM25-04732 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 07:35 | February | 2026 | 2026-02-17 13:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 48
202512-NM25-04734 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:42 | March | 2026 | 2026-04-01 14:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-04740 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 08:25 | January | 2026 | 2026-02-06 13:41 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 62
202512-NM25-04741 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 23:24 | February | 2026 | 2026-02-12 15:09 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 55
202512-NM25-04744 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 11:14 | February | 2026 | 2026-02-05 15:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-04745 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-19 13:21 | December | 2025 | 2026-02-10 09:26 | 53 | Study | Estudio (E) | Activated | Backlog |  | No | 53 |  | PONCE | February |  | 53 | 0 | 2026-04-01 | 102
202512-NM25-04749 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:56 | January | 2026 | 2026-02-03 10:07 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 14 | 0 | 2026-04-01 | 71
202512-NM25-04752 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:36 | March | 2026 | 2026-03-18 10:55 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 9 | 0 | 2026-04-01 | 23
202512-NM25-04753 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 08:52 | January | 2026 | 2026-01-28 14:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 69
202512-NM25-04758 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:16 | March | 2026 | 2026-03-16 09:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 22
202512-NM25-04761 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 08:36 | January | 2026 | 2026-02-04 15:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 62
202512-NM25-04763 | GDL17 | Residencial | 7.68 | Period | 2026-01-09 08:02 | January | 2026 | 2026-02-25 08:26 | 47 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | February |  | 47 | 0 | 2026-04-01 | 82
202512-NM25-04764 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 19:44 | February | 2026 | 2026-02-10 15:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 54
202512-NM25-04770 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 16:47 | February | 2026 | 2026-02-13 14:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 49
202512-NM25-04776 | GDL17 | Residencial | 3.8 | Period | 2026-01-19 09:03 | January | 2026 | 2026-01-21 08:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 72
202512-NM25-04781 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:49 | March | 2026 | 2026-04-01 14:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-04783 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:56 | March | 2026 | 2026-04-01 14:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 2
202512-NM25-04797 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 16:01 | March | 2026 | 2026-03-19 16:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 14
202512-NM25-04798 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:44 | February | 2026 | 2026-02-26 08:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-04801 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-19 15:39 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 104 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 102
202512-NM25-04803 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:50 | January | 2026 | 2026-02-03 16:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 60
202512-NM25-04806 | GDL17 | Residencial | 11.5 | Period | 2026-02-07 14:35 | February | 2026 | 2026-02-10 15:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 52
202512-NM25-04807 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:41 | January | 2026 | 2026-02-04 16:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-04811 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:07 | March | 2026 | 2026-04-01 14:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-04813 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:49 | February | 2026 | 2026-02-25 09:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 40
202512-NM25-04817 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 07:56 | December | 2025 | 2026-01-05 10:08 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-04822 | GDL17 | Residencial | 5.76 | Period | 2026-01-27 10:03 | January | 2026 | 2026-01-29 15:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-04828 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 18:50 | January | 2026 | 2026-02-03 13:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 60
202512-NM25-04831 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 07:23 | January | 2026 | 2026-02-09 13:29 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 24 | 0 | 2026-04-01 | 75
202512-NM25-04832 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:30 | January | 2026 | 2026-02-04 09:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-04834 | GDL17 | Residencial | 3.8 | Period | 2026-01-17 10:36 | January | 2026 | 2026-01-20 10:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 74
202512-NM25-04843 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:37 | February | 2026 | 2026-02-25 12:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-04845 | GDL17 | Residencial | 23 | Period | 2026-01-20 11:25 | January | 2026 | 2026-02-12 10:52 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 1 | 22 | 2026-04-01 | 71
202512-NM25-04846 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 19:03 | February | 2026 | 2026-03-18 08:51 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 26 | 0 | 2026-04-01 | 39
202512-NM25-04855 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:32 | January | 2026 | 2026-01-21 13:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-04856 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:34 | January | 2026 | 2026-01-28 13:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 69
202512-NM25-04857 | GDL17 | Residencial | 3.66 | Period | 2026-03-26 21:19 | March | 2026 | 2026-03-31 13:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-04858 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:14 | February | 2026 | 2026-02-11 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202512-NM25-04859 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:12 | December | 2025 | 2026-01-07 13:31 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-04860 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:11 | January | 2026 | 2026-01-20 15:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-04863 | GDL17 | Residencial | 15.2 | Period | 2026-01-27 13:51 | January | 2026 | 2026-02-02 09:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 63
202512-NM25-04865 | GDL17 | Residencial | 8.8 | Period | 2026-01-16 16:24 | January | 2026 | 2026-01-26 14:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 10 | 0 | 2026-04-01 | 74
202512-NM25-04868 | GDL17 | Comercial | 10 | Period | 2026-01-05 09:58 | January | 2026 | 2026-02-27 15:23 | 53 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | February | 1 | 52 | 1 | 2026-04-01 | 86
202512-NM25-04869 | GDL17 | Residencial | 12 | Period | 2026-01-14 08:44 | January | 2026 | 2026-01-15 10:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-04871 | GDL17 | Residencial | 4.608 | Period | 2026-01-14 15:20 | January | 2026 | 2026-01-28 15:07 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 14 | 0 | 2026-04-01 | 76
202512-NM25-04873 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 10:20 | January | 2026 | 2026-02-06 10:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 62
202512-NM25-04874 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:53 | January | 2026 | 2026-01-13 14:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-04877 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 09:09 | February | 2026 | 2026-02-11 16:08 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 0 | 0 | 2026-04-01 | 49
202512-NM25-04880 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 14:00 | January | 2026 | 2026-02-02 11:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-04883 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 09:57 | January | 2026 | 2026-02-05 17:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 61
202512-NM25-04887 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 10:09 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 62
202512-NM25-04893 | GDL17 | Residencial | 5.76 | Period | 2026-01-02 15:04 | January | 2026 | 2026-01-13 14:11 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 11 | 0 | 2026-04-01 | 88
202512-NM25-04896 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:57 | January | 2026 | 2026-01-20 09:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 76
202512-NM25-04897 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 07:49 | February | 2026 | 2026-02-18 07:58 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 51
202512-NM25-04900 | GDL17 | Residencial | 7.296 | Period | 2026-01-20 08:10 | January | 2026 | 2026-02-11 10:37 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 71
202512-NM25-04904 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:18 | January | 2026 | 2026-01-19 15:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 76
202512-NM25-04907 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:52 | January | 2026 | 2026-01-20 14:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-04908 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:09 | January | 2026 | 2026-02-02 07:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-04910 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:44 | February | 2026 | 2026-02-06 14:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-04913 | GDL17 | Residencial | 5.76 | Period | 2026-02-27 16:32 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 32
202512-NM25-04918 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:18 | March | 2026 | 2026-04-06 10:14 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 12 | 0 | 2026-04-01 | 7
202512-NM25-04924 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-24 13:22 | December | 2025 | 2026-03-26 16:15 | 92 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | March | 3 | 22 | 70 | 2026-04-01 | 97
202512-NM25-04926 | GDL17 | Residencial | 7.6 | Period | 2026-03-05 13:51 | March | 2026 | 2026-03-09 09:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 26
202512-NM25-04931 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 14:48 | February | 2026 | 2026-02-19 13:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 48
202512-NM25-04933 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-22 10:07 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 100
202512-NM25-04937 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 14:47 | February | 2026 | 2026-02-11 12:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 55
202512-NM25-04938 | GDL17 | Residencial | 9 | Period | 2026-02-27 19:22 | February | 2026 | 2026-03-04 08:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 32
202512-NM25-04942 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 19:32 | February | 2026 | 2026-03-03 11:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202512-NM25-04945 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:45 | January | 2026 | 2026-02-04 17:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-04948 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-22 10:59 | December | 2025 | 2026-03-27 11:06 | 95 | Study | Estudio (E) | Activated | Backlog |  | No | 95 |  | PONCE | March |  | 95 | 0 | 2026-04-01 | 100
202512-NM25-04949 | GDL17 | Residencial | 23 | Out of period | 2025-12-22 16:52 | December | 2025 | 2026-03-03 14:05 | 71 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | March | 1 | 5 | 66 | 2026-04-01 | 99
202512-NM25-04952 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 15:58 | January | 2026 | 2026-02-11 16:05 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 12 | 0 | 2026-04-01 | 60
202512-NM25-04957 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:21 | January | 2026 | 2026-02-04 10:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-04958 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 18:00 | January | 2026 | 2026-02-04 09:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-04959 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-22 11:49 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 100
202512-NM25-04960 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 07:24 | March | 2026 | 2026-03-27 09:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 8
202512-NM25-04961 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:01 | January | 2026 | 2026-02-04 07:45 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 63
202512-NM25-04963 | GDL17 | Residencial | 15 | Period | 2026-01-14 09:57 | January | 2026 | 2026-01-15 15:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-04964 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:21 | March | 2026 | 2026-04-01 14:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-04968 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 08:12 | February | 2026 | 2026-02-11 16:06 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 57
202512-NM25-04970 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:20 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 2
202512-NM25-04971 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 10:25 | January | 2026 | 2026-02-09 13:46 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 62
202512-NM25-04979 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 18:25 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 41
202512-NM25-04980 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 12:50 | February | 2026 | 2026-02-25 07:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-04981 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:32 | March | 2026 | 2026-03-17 09:33 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 21
202512-NM25-04987 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 10:12 | January | 2026 | 2026-02-12 11:06 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 14 | 0 | 2026-04-01 | 62
202512-NM25-04992 | GDL17 | Residencial | 15.3 | Period | 2026-02-26 11:20 | February | 2026 | 2026-03-02 15:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 34
202512-NM25-04993 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:24 | February | 2026 | 2026-03-09 10:45 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 34
202512-NM25-04994 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:23 | January | 2026 | 2026-01-21 14:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-04998 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:05 | February | 2026 | 2026-03-02 13:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 35
202512-NM25-04999 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:50 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 60
202512-NM25-05006 | GDL17 | Residencial | 10 | Period | 2026-02-23 11:07 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 37
202512-NM25-05009 | GDL17 | Residencial | 7.6 | Period | 2026-02-17 10:24 | February | 2026 | 2026-02-24 15:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 43
202512-NM25-05010 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:13 | February | 2026 | 2026-03-02 11:22 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 12 | 0 | 2026-04-01 | 42
202512-NM25-05017 | GDL17 | Comercial | 20 | Period | 2026-03-23 16:45 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 8
202512-NM25-05020 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:43 | February | 2026 | 2026-03-02 09:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-05022 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:44 | February | 2026 | 2026-03-02 10:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 35
202512-NM25-05024 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:23 | January | 2026 | 2026-01-14 11:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 84
202512-NM25-05031 | GDL17 | Residencial | 3.84 | Period | 2026-01-28 07:31 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 63
202512-NM25-05035 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:27 | February | 2026 | 2026-02-26 15:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 37
202512-NM25-05038 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:36 | March | 2026 | 2026-03-09 11:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 29
202512-NM25-05044 | GDL17 | Residencial | 23 | Period | 2026-02-20 13:47 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 39
202512-NM25-05047 | GDL17 | Residencial | 5.76 | Period | 2026-01-08 12:25 | January | 2026 | 2026-01-13 08:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-05048 | GDL17 | Residencial | 23 | Period | 2026-03-04 18:28 | March | 2026 | 2026-03-09 08:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 27
202512-NM25-05051 | GDL17 | Residencial | 5.76 | Period | 2026-01-15 14:53 | January | 2026 | 2026-01-19 11:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05052 | GDL17 | Residencial | 23 | Period | 2026-01-20 12:30 | January | 2026 | 2026-01-22 13:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-05054 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:59 | January | 2026 | 2026-01-19 11:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05056 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:26 | January | 2026 | 2026-02-02 11:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 64
202512-NM25-05057 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:52 | February | 2026 | 2026-02-16 10:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 48
202512-NM25-05059 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 10:44 | January | 2026 | 2026-02-04 10:29 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 64
202512-NM25-05064 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 19:40 | February | 2026 | 2026-03-04 08:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 32
202512-NM25-05069 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 09:51 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 21
202512-NM25-05071 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 15:07 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 48
202512-NM25-05085 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:25 | February | 2026 | 2026-03-02 10:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 35
202512-NM25-05088 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 11:15 | January | 2026 | 2026-01-29 15:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 68
202512-NM25-05090 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 08:42 | January | 2026 | 2026-01-16 15:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-05094 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:26 | February | 2026 | 2026-02-13 10:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202512-NM25-05100 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:37 | January | 2026 | 2026-01-26 11:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 69
202512-NM25-05109 | GDL17 | Residencial | 3.84 | Period | 2026-02-24 12:55 | February | 2026 | 2026-02-27 09:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-05121 | GDL17 | Residencial | 3.8 | Period | 2026-02-04 11:27 | February | 2026 | 2026-02-09 09:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 56
202512-NM25-05123 | GDL17 | Residencial | 7.68 | Period | 2026-01-20 14:51 | January | 2026 | 2026-01-22 09:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-05124 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 09:58 | January | 2026 | 2026-01-14 12:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 84
202512-NM25-05129 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 18:26 | March | 2026 | 2026-03-05 10:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 29
202512-NM25-05134 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-22 17:16 | December | 2025 | 2026-02-03 10:19 | 43 | Study | Estudio (E) | Activated | Backlog |  | No | 43 |  | ARECIBO | February |  | 43 | 0 | 2026-04-01 | 99
202512-NM25-05144 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:08 | January | 2026 | 2026-01-19 15:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 76
202512-NM25-05148 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:44 | January | 2026 | 2026-01-26 11:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 70
202512-NM25-05150 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 18:52 | March | 2026 | 2026-04-01 14:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 4
202512-NM25-05152 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 17:38 | February | 2026 | 2026-03-03 08:27 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 39
202512-NM25-05161 | GDL17 | Residencial | 0 | Period | 2026-02-11 14:07 | February | 2026 | 2026-02-17 14:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 48
202512-NM25-05163 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:16 | March | 2026 | 2026-04-02 13:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 6 | 0 | 2026-04-01 | 5
202512-NM25-05166 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:59 | March | 2026 | 2026-04-02 15:33 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 8 | 0 | 2026-04-01 | 7
202512-NM25-05172 | GDL17 | Residencial | 15 | Out of period | 2025-12-24 11:01 | December | 2025 | 2026-02-05 18:15 | 43 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | February | 2 | 8 | 35 | 2026-04-01 | 98
202512-NM25-05174 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:36 | January | 2026 | 2026-01-26 13:18 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 11 | 0 | 2026-04-01 | 75
202512-NM25-05175 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:16 | January | 2026 | 2026-02-03 11:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 61
202512-NM25-05178 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:19 | February | 2026 | 2026-02-11 07:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 55
202512-NM25-05179 | GDL17 | Residencial | 7.6 | Period | 2026-01-08 13:47 | January | 2026 | 2026-01-19 08:54 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 11 | 0 | 2026-04-01 | 82
202512-NM25-05182 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 14:54 | March | 2026 | 2026-03-24 14:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 1 | 5 | 2026-04-01 | 13
202512-NM25-05184 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:42 | February | 2026 | 2026-03-02 09:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 35
202512-NM25-05188 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 13:59 | January | 2026 | 2026-01-20 15:40 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 13 | 0 | 2026-04-01 | 83
202512-NM25-05189 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 13:32 | February | 2026 | 2026-02-11 15:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202512-NM25-05190 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:15 | January | 2026 | 2026-01-29 10:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 64
202512-NM25-05191 | GDL17 | Residencial | 9 | Out of period | 2025-12-29 09:05 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 93
202512-NM25-05193 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:06 | January | 2026 | 2026-01-13 15:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-05198 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 12:02 | December | 2025 | 2026-01-08 12:48 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 90
202512-NM25-05201 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:19 | February | 2026 | 2026-03-03 15:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-05207 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 20:16 | January | 2026 | 2026-01-13 13:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-05208 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:25 | January | 2026 | 2026-01-23 16:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 69
202512-NM25-05209 | GDL17 | Residencial | 8 | Period | 2026-02-18 13:06 | February | 2026 | 2026-02-23 14:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 41
202512-NM25-05213 | GDL17 | Residencial | 8 | Period | 2026-02-18 12:56 | February | 2026 | 2026-02-23 14:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 41
202512-NM25-05216 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:37 | January | 2026 | 2026-02-04 08:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 63
202512-NM25-05217 | GDL17 | Residencial | 3.84 | Period | 2026-02-20 15:42 | February | 2026 | 2026-02-26 12:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-05224 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:18 | January | 2026 | 2026-02-25 16:06 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 3 | 26 | 2026-04-01 | 64
202512-NM25-05229 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 15:38 | March | 2026 | 2026-03-26 08:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 8
202512-NM25-05232 | GDL17 | Residencial | 18 | Period | 2026-02-01 20:16 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 58
202512-NM25-05235 | GDL17 | Residencial | 17.2 | Period | 2026-02-14 17:01 | February | 2026 | 2026-03-06 13:09 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 20 | 0 | 2026-04-01 | 45
202512-NM25-05236 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 15:48 | December | 2025 | 2026-01-05 13:38 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 90
202512-NM25-05239 | GDL17 | Residencial | 5.76 | Period | 2026-03-01 10:39 | March | 2026 | 2026-03-06 13:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 31
202512-NM25-05241 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:20 | February | 2026 | 2026-02-23 09:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202512-NM25-05245 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 17:23 | February | 2026 | 2026-03-12 15:39 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 33
202512-NM25-05246 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-23 11:46 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 99
202512-NM25-05252 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:31 | February | 2026 | 2026-02-25 12:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-05253 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:32 | February | 2026 | 2026-02-16 14:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 49
202512-NM25-05257 | GDL17 | Residencial | 23 | Period | 2026-03-10 10:30 | March | 2026 | 2026-03-17 14:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 22
202512-NM25-05258 | GDL17 | Residencial | 8 | Period | 2026-02-05 07:34 | February | 2026 | 2026-02-13 11:18 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 55
202512-NM25-05261 | GDL17 | Residencial | 23 | Out of period | 2025-12-23 12:33 | December | 2025 | 2026-03-30 14:38 | 97 | Study | Estudio (E) | Activated | Backlog |  | No | 97 |  | CAGUAS | March |  | 97 | 0 | 2026-04-01 | 98
202512-NM25-05262 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-26 09:17 | December | 2025 | 2026-02-17 13:58 | 53 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | February | 1 | 42 | 0 | 2026-04-01 | 96
202512-NM25-05263 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-23 12:23 | December | 2025 | 2026-03-03 11:16 | 70 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | ARECIBO | March | 1 | 61 | 0 | 2026-04-01 | 98
202512-NM25-05264 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 20:27 | January | 2026 | 2026-02-04 12:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 61
202512-NM25-05269 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:12 | January | 2026 | 2026-01-09 10:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 84
202512-NM25-05271 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 14:47 | January | 2026 | 2026-01-22 09:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-05277 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 17:43 | February | 2026 | 2026-02-25 08:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-05280 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:11 | March | 2026 | 2026-03-24 08:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 5 | 1 | 2026-04-01 | 14
202512-NM25-05282 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:08 | February | 2026 | 2026-02-12 07:57 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 56
202512-NM25-05285 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:15 | January | 2026 | 2026-01-19 08:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-05286 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 12:47 | March | 2026 | 2026-03-10 11:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 22
202512-NM25-05291 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 08:50 | January | 2026 | 2026-01-20 15:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 72
202512-NM25-05293 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:54 | January | 2026 | 2026-02-03 13:40 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 11 | 0 | 2026-04-01 | 68
202512-NM25-05298 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:29 | January | 2026 | 2026-03-16 16:51 | 53 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 53 | 0 | 2026-04-01 | 69
202512-NM25-05299 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-23 14:32 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 98
202512-NM25-05302 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-23 14:42 | December | 2025 | 2026-02-19 08:08 | 58 | Study | Estudio (E) | Activated | Backlog |  | No | 58 |  | BAYAMON | February |  | 58 | 0 | 2026-04-01 | 98
202512-NM25-05303 | GDL17 | Residencial | 8 | Period | 2026-01-15 15:07 | January | 2026 | 2026-01-19 13:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05310 | GDL17 | Residencial | 7.68 | Period | 2026-01-09 15:03 | January | 2026 | 2026-01-19 12:44 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 81
202512-NM25-05316 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-23 15:23 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No | 127 | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 98
202512-NM25-05320 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-30 21:59 | December | 2025 | 2026-02-10 08:02 | 41 | Study | Estudio (E) | Activated | Backlog |  | No | 41 |  | BAYAMON | February |  | 42 | 0 | 2026-04-01 | 91
202512-NM25-05325 | GDL17 | Comercial | 11.5 | Period | 2026-01-02 12:49 | January | 2026 | 2026-01-07 10:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 88
202512-NM25-05343 | GDL17 | Residencial | 10 | Period | 2026-01-30 09:26 | January | 2026 | 2026-02-04 08:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 61
202512-NM25-05356 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:45 | February | 2026 | 2026-02-16 16:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 48
202512-NM25-05358 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:52 | February | 2026 | 2026-02-11 14:40 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 57
202512-NM25-05359 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 13:10 | March | 2026 | 2026-03-13 10:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 20
202512-NM25-05361 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:44 | March | 2026 | 2026-03-09 15:22 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 0 | 0 | 2026-04-01 | 22
202512-NM25-05363 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:56 | January | 2026 | 2026-02-03 12:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 60
202512-NM25-05364 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 12:07 | March | 2026 | 2026-03-20 15:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 12
202512-NM25-05366 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:08 | March | 2026 | 2026-03-04 10:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 29
202512-NM25-05367 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:31 | January | 2026 | 2026-01-28 16:02 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 14 | 0 | 2026-04-01 | 76
202512-NM25-05368 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:10 | January | 2026 | 2026-01-19 10:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-05372 | GDL17 | Residencial | 6.144 | Period | 2026-01-30 13:35 | January | 2026 | 2026-02-04 13:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-05375 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:20 | February | 2026 | 2026-02-06 15:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 55
202512-NM25-05376 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-24 08:33 | December | 2025 | 2026-03-31 09:54 | 97 | Study | Estudio (E) | Activated | Backlog |  | No | 97 |  | MAYAGUEZ | March |  | 97 | 0 | 2026-04-01 | 98
202512-NM25-05384 | GDL17 | Residencial | 8 | Period | 2026-01-28 08:42 | January | 2026 | 2026-01-29 15:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 63
202512-NM25-05386 | GDL17 | Residencial | 11.5 | Period | 2026-01-10 10:59 | January | 2026 | 2026-01-14 11:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 81
202512-NM25-05390 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 21:08 | January | 2026 | 2026-01-26 07:50 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 12 | 0 | 2026-04-01 | 76
202512-NM25-05392 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:08 | December | 2025 | 2026-01-05 15:04 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-05395 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:17 | January | 2026 | 2026-02-04 08:35 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 19 | 0 | 2026-04-01 | 75
202512-NM25-05396 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:27 | January | 2026 | 2026-01-21 13:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 74
202512-NM25-05397 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:44 | December | 2025 | 2026-01-07 13:21 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-05400 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:35 | January | 2026 | 2026-01-08 14:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 88
202512-NM25-05405 | GDL17 | Residencial | 23 | Period | 2026-02-25 17:23 | February | 2026 | 2026-03-02 10:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-05408 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:21 | March | 2026 | 2026-03-17 09:12 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 27
202512-NM25-05409 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 19:19 | February | 2026 | 2026-03-04 11:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 34
202512-NM25-05410 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 11:37 | January | 2026 | 2026-01-20 14:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05413 | GDL17 | Residencial | 23 | Period | 2026-01-02 14:31 | January | 2026 | 2026-01-14 13:33 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 88
202512-NM25-05414 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 10:41 | January | 2026 | 2026-01-20 16:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 77
202512-NM25-05415 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 15:27 | January | 2026 | 2026-03-05 13:01 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March |  | 41 | 0 | 2026-04-01 | 67
202512-NM25-05424 | GDL17 | Residencial | 8.784 | Period | 2026-01-16 09:42 | January | 2026 | 2026-01-29 13:55 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 13 | 0 | 2026-04-01 | 75
202512-NM25-05428 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:22 | March | 2026 | 2026-03-06 11:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 28
202512-NM25-05431 | GDL17 | Residencial | 3.8 | Period | 2026-01-16 11:16 | January | 2026 | 2026-01-19 12:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-05438 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 06:54 | January | 2026 | 2026-01-12 10:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202512-NM25-05439 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 14:56 | March | 2026 | 2026-03-09 15:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 25
202512-NM25-05440 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:11 | January | 2026 | 2026-01-27 13:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-05442 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:38 | February | 2026 | 2026-02-05 10:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-05445 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:03 | February | 2026 | 2026-02-11 14:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 50
202512-NM25-05446 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 17:56 | February | 2026 | 2026-02-26 13:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 40
202512-NM25-05451 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 14:29 | February | 2026 | 2026-02-16 11:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 47
202512-NM25-05456 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 13:25 | March | 2026 | 2026-03-26 10:04 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 22 | 0 | 2026-04-01 | 27
202512-NM25-05461 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 16:39 | February | 2026 | 2026-02-12 09:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202512-NM25-05463 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-24 15:22 | December | 2025 | 2026-02-05 13:31 | 43 | Study | Estudio (E) | Activated | Backlog |  | No | 43 |  | ARECIBO | February |  | 43 | 0 | 2026-04-01 | 97
202512-NM25-05473 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 17:41 | March | 2026 | 2026-03-13 15:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 21
202512-NM25-05479 | GDL17 | Residencial | 23 | Period | 2026-01-30 21:02 | January | 2026 | 2026-02-17 08:40 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 60
202512-NM25-05483 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:19 | February | 2026 | 2026-03-09 14:01 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 34
202512-NM25-05484 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 20:37 | January | 2026 | 2026-02-04 09:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-05485 | GDL17 | Residencial | 23 | Period | 2026-03-03 15:11 | March | 2026 | 2026-03-05 09:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 28
202512-NM25-05486 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 14:10 | March | 2026 | 2026-03-23 08:03 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 18
202512-NM25-05490 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 14:11 | March | 2026 | 2026-04-02 09:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 3 | 0 | 2026-04-01 | 1
202512-NM25-05492 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-26 08:13 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 110 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 96
202512-NM25-05500 | GDL17 | Residencial | 9 | Period | 2026-02-27 00:26 | February | 2026 | 2026-03-18 13:59 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 6 | 13 | 2026-04-01 | 33
202512-NM25-05511 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-26 09:45 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 96
202512-NM25-05515 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-26 09:46 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 102 | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 96
202512-NM25-05517 | GDL17 | Residencial | 10 | Period | 2026-01-20 21:34 | January | 2026 | 2026-01-23 09:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 70
202512-NM25-05519 | GDL17 | Residencial | 23 | Period | 2026-02-25 15:33 | February | 2026 | 2026-03-02 14:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-05520 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:55 | January | 2026 | 2026-01-27 14:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 65
202512-NM25-05528 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 07:35 | January | 2026 | 2026-02-02 13:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 63
202512-NM25-05533 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 19:57 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 56
202512-NM25-05534 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:03 | January | 2026 | 2026-01-15 13:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202512-NM25-05535 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:05 | March | 2026 | 2026-03-06 13:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 26
202512-NM25-05539 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:27 | January | 2026 | 2026-01-19 14:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05540 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:05 | January | 2026 | 2026-01-23 10:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-05541 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 08:37 | January | 2026 | 2026-01-14 08:38 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 12 | 0 | 2026-04-01 | 89
202512-NM25-05542 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 19:19 | January | 2026 | 2026-02-03 12:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 60
202512-NM25-05543 | GDL17 | Residencial | 3.966 | Period | 2026-01-16 10:34 | January | 2026 | 2026-01-20 09:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05545 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:34 | January | 2026 | 2026-01-20 15:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 71
202512-NM25-05549 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 16:09 | January | 2026 | 2026-02-11 13:39 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 20 | 0 | 2026-04-01 | 68
202512-NM25-05550 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 14:44 | January | 2026 | 2026-01-12 12:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 84
202512-NM25-05552 | GDL17 | Residencial | 7.68 | Period | 2026-01-09 20:25 | January | 2026 | 2026-01-19 13:21 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 81
202512-NM25-05553 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:34 | February | 2026 | 2026-02-12 13:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202512-NM25-05556 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 16:40 | January | 2026 | 2026-02-11 15:24 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 15 | 0 | 2026-04-01 | 63
202512-NM25-05561 | GDL17 | Residencial | 3.84 | Period | 2026-03-10 16:51 | March | 2026 | 2026-03-13 14:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 21
202512-NM25-05564 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:41 | March | 2026 | 2026-03-12 15:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 23
202512-NM25-05567 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:31 | February | 2026 | 2026-02-26 08:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-05571 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:52 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 29
202512-NM25-05573 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:59 | January | 2026 | 2026-01-20 13:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05575 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 11:38 | January | 2026 | 2026-01-22 12:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-05577 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:35 | January | 2026 | 2026-01-22 13:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-05578 | GDL17 | Residencial | 15 | Period | 2026-01-11 10:53 | January | 2026 | 2026-01-14 15:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 80
202512-NM25-05580 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 17:44 | March | 2026 | 2026-03-26 11:04 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 2 | 2 | 21 | 2026-04-01 | 28
202512-NM25-05582 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 17:07 | February | 2026 | 2026-02-12 14:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202512-NM25-05584 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 18:06 | March | 2026 | 2026-03-23 15:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202512-NM25-05585 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:44 | March | 2026 | 2026-03-04 13:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 29
202512-NM25-05587 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:13 | January | 2026 | 2026-03-09 13:49 | 38 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March | 1 | 31 | 0 | 2026-04-01 | 60
202512-NM25-05589 | GDL17 | Residencial | 11.5 | Period | 2026-03-07 14:46 | March | 2026 | 2026-03-18 16:29 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 24
202512-NM25-05591 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 13:54 | January | 2026 | 2026-01-14 15:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 83
202512-NM25-05593 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:18 | December | 2025 | 2026-01-08 16:12 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-05595 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 14:02 | January | 2026 | 2026-01-28 10:11 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 9 | 0 | 2026-04-01 | 71
202512-NM25-05600 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 19:16 | February | 2026 | 2026-02-25 09:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-05610 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:56 | March | 2026 | 2026-03-05 10:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 28
202512-NM25-05611 | GDL17 | Residencial | 23 | Period | 2026-03-03 13:57 | March | 2026 | 2026-04-14 15:19 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 42 | 38 | 2026-04-01 | 28
202512-NM25-05612 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:39 | January | 2026 | 2026-02-06 09:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 61
202512-NM25-05613 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:06 | January | 2026 | 2026-01-13 08:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-05623 | GDL17 | Residencial | 12 | Period | 2026-01-03 18:14 | January | 2026 | 2026-01-13 15:30 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 10 | 0 | 2026-04-01 | 87
202512-NM25-05625 | GDL17 | Residencial | 2.4 | Out of period | 2025-12-26 16:49 | December | 2025 | 2026-03-19 17:39 | 83 | Study | Estudio (E) | Activated | Backlog |  | No | 83 |  | CAGUAS | March |  | 83 | 0 | 2026-04-01 | 95
202512-NM25-05626 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:34 | February | 2026 | 2026-03-02 09:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-05636 | GDL17 | Residencial | 12 | Period | 2026-01-03 12:36 | January | 2026 | 2026-01-09 15:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 87
202512-NM25-05653 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 11:41 | January | 2026 | 2026-01-23 09:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-05657 | GDL17 | Residencial | 7.35 | Period | 2026-01-07 12:58 | January | 2026 | 2026-01-13 11:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 83
202512-NM25-05658 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:50 | December | 2025 | 2026-01-05 15:04 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-05659 | GDL17 | Residencial | 5.6 | Period | 2026-02-03 15:09 | February | 2026 | 2026-02-06 14:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-05664 | GDL17 | Residencial | 7.84 | Period | 2026-03-04 12:41 | March | 2026 | 2026-03-09 10:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 27
202512-NM25-05667 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:42 | February | 2026 | 2026-02-16 09:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 47
202512-NM25-05670 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:16 | February | 2026 | 2026-02-24 08:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 41
202512-NM25-05673 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:19 | February | 2026 | 2026-02-16 08:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202512-NM25-05685 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-29 08:47 | December | 2025 | 2026-03-27 11:21 | 88 | Study | Estudio (E) | Activated | Backlog |  | No | 88 |  | ARECIBO | March |  | 88 | 0 | 2026-04-01 | 93
202512-NM25-05691 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 14:08 | February | 2026 | 2026-02-19 14:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202512-NM25-05721 | GDL17 | Residencial | 3.8 | Period | 2026-01-15 11:45 | January | 2026 | 2026-01-19 09:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-05722 | GDL17 | Residencial | 5.76 | Period | 2026-01-08 11:37 | January | 2026 | 2026-01-13 13:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-05726 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:24 | January | 2026 | 2026-01-29 10:23 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 72
202512-NM25-05727 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:50 | February | 2026 | 2026-02-10 14:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 55
202512-NM25-05730 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:13 | February | 2026 | 2026-03-05 09:15 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 6 | 1 | 2026-04-01 | 34
202512-NM25-05731 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 14:04 | February | 2026 | 2026-02-18 13:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 47
202512-NM25-05733 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-29 10:49 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 93
202512-NM25-05735 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 12:06 | December | 2025 | 2026-01-09 16:28 | 9 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 90
202512-NM25-05736 | GDL17 | Residencial | 8 | Period | 2026-02-05 08:02 | February | 2026 | 2026-02-17 10:11 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 12 | 0 | 2026-04-01 | 55
202512-NM25-05741 | GDL17 | Residencial | 14.64 | Period | 2026-02-03 09:40 | February | 2026 | 2026-02-05 12:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-05742 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 17:44 | February | 2026 | 2026-03-06 08:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 32
202512-NM25-05747 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:10 | January | 2026 | 2026-01-26 13:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 70
202512-NM25-05750 | GDL17 | Residencial | 3.8 | Period | 2026-01-19 15:45 | January | 2026 | 2026-01-21 12:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202512-NM25-05752 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 07:24 | January | 2026 | 2026-02-02 10:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 64
202512-NM25-05758 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 08:44 | March | 2026 | 2026-03-16 09:51 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 26
202512-NM25-05760 | GDL17 | Residencial | 8.052 | Period | 2026-01-21 07:35 | January | 2026 | 2026-02-13 16:18 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 23 | 0 | 2026-04-01 | 70
202512-NM25-05761 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 07:22 | January | 2026 | 2026-01-21 09:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 75
202512-NM25-05763 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-29 11:40 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 101 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 93
202512-NM25-05769 | GDL17 | Residencial | 3.8 | Period | 2026-01-15 13:03 | January | 2026 | 2026-01-19 08:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05779 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:54 | December | 2025 | 2026-01-19 10:57 | 19 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 19 | 0 | 2026-04-01 | 91
202512-NM25-05782 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:31 | January | 2026 | 2026-02-06 14:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 62
202512-NM25-05784 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:48 | March | 2026 | 2026-03-06 13:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 27
202512-NM25-05785 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:34 | January | 2026 | 2026-01-22 14:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-05788 | GDL17 | Residencial | 5.6 | Period | 2026-01-07 11:52 | January | 2026 | 2026-01-15 15:36 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 8 | 0 | 2026-04-01 | 84
202512-NM25-05795 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:56 | February | 2026 | 2026-02-11 11:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 55
202512-NM25-05797 | GDL17 | Residencial | 5.76 | Period | 2026-01-23 16:41 | January | 2026 | 2026-01-28 13:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 67
202512-NM25-05799 | GDL17 | Comercial | 11.5 | Period | 2026-02-27 11:21 | February | 2026 | 2026-03-06 10:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 33
202512-NM25-05803 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:01 | February | 2026 | 2026-02-25 16:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202512-NM25-05804 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:36 | January | 2026 | 2026-01-29 09:02 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 69
202512-NM25-05805 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 13:49 | March | 2026 | 2026-03-12 14:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 25
202512-NM25-05810 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:07 | January | 2026 | 2026-01-20 14:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 72
202512-NM25-05812 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 22:26 | February | 2026 | 2026-02-24 08:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202512-NM25-05813 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:29 | January | 2026 | 2026-01-13 15:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 82
202512-NM25-05814 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 09:32 | February | 2026 | 2026-02-11 16:06 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 0 | 0 | 2026-04-01 | 49
202512-NM25-05815 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:28 | January | 2026 | 2026-01-22 10:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-05821 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:56 | February | 2026 | 2026-02-06 15:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 55
202512-NM25-05822 | GDL17 | Residencial | 4.608 | Period | 2026-02-02 07:41 | February | 2026 | 2026-03-04 10:10 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 30 | 0 | 2026-04-01 | 58
202512-NM25-05824 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:15 | February | 2026 | 2026-02-27 14:53 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 40
202512-NM25-05829 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:53 | February | 2026 | 2026-03-12 14:51 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 32
202512-NM25-05831 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 08:17 | January | 2026 | 2026-01-30 13:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 62
202512-NM25-05832 | GDL17 | Residencial | 15.2 | Period | 2026-01-15 16:24 | January | 2026 | 2026-01-19 09:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05834 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 16:59 | February | 2026 | 2026-02-11 13:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 53
202512-NM25-05840 | GDL17 | Residencial | 7.68 | Period | 2026-02-10 15:15 | February | 2026 | 2026-02-11 10:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 49
202512-NM25-05843 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:37 | March | 2026 | 2026-04-10 09:31 | 32 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 31 | 0 | 2026-04-01 | 22
202512-NM25-05845 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 17:57 | March | 2026 | 2026-03-26 10:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202512-NM25-05846 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 12:14 | January | 2026 | 2026-01-13 15:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-05847 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 17:00 | January | 2026 | 2026-01-13 10:57 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 11 | 0 | 2026-04-01 | 88
202512-NM25-05849 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:36 | January | 2026 | 2026-01-16 16:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-05851 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 15:59 | January | 2026 | 2026-01-30 13:43 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 14 | 0 | 2026-04-01 | 74
202512-NM25-05853 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-29 16:53 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 99 | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 92
202512-NM25-05863 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:41 | December | 2025 | 2026-01-20 09:29 | 20 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 20 | 0 | 2026-04-01 | 91
202512-NM25-05864 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:41 | January | 2026 | 2026-01-26 16:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 68
202512-NM25-05865 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:32 | February | 2026 | 2026-03-06 09:48 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 40
202512-NM25-05867 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:35 | February | 2026 | 2026-02-23 13:22 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 20 | 0 | 2026-04-01 | 57
202512-NM25-05868 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:24 | January | 2026 | 2026-01-12 10:33 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 85
202512-NM25-05869 | GDL17 | Residencial | 5.76 | Period | 2026-01-14 09:33 | January | 2026 | 2026-01-16 14:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 77
202512-NM25-05874 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 13:58 | February | 2026 | 2026-03-06 11:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 33
202512-NM25-05875 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 12:19 | March | 2026 | 2026-03-23 13:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 14
202512-NM25-05876 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 15:14 | January | 2026 | 2026-02-03 13:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 62
202512-NM25-05877 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 20:13 | February | 2026 | 2026-02-26 10:17 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 40
202512-NM25-05884 | GDL17 | Residencial | 11.99 | Period | 2026-01-20 12:00 | January | 2026 | 2026-01-22 13:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-05886 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:46 | December | 2025 | 2026-01-13 09:29 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-05894 | GDL17 | Residencial | 12.672 | Period | 2026-01-26 16:35 | January | 2026 | 2026-01-28 12:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-05895 | GDL17 | Residencial | 23 | Period | 2026-01-29 15:17 | January | 2026 | 2026-02-04 08:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 61
202512-NM25-05896 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:40 | January | 2026 | 2026-01-23 15:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202512-NM25-05898 | GDL17 | Residencial | 3.8 | Period | 2026-01-21 13:43 | January | 2026 | 2026-01-22 12:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 69
202512-NM25-05901 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 16:21 | January | 2026 | 2026-02-04 15:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 62
202512-NM25-05902 | GDL17 | Residencial | 23 | Period | 2026-01-23 14:41 | January | 2026 | 2026-01-26 14:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 67
202512-NM25-05904 | GDL17 | Residencial | 8 | Period | 2026-02-05 08:20 | February | 2026 | 2026-02-09 15:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 55
202512-NM25-05908 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:47 | February | 2026 | 2026-02-23 09:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202512-NM25-05912 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 19:02 | February | 2026 | 2026-02-27 10:58 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 41
202512-NM25-05914 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:40 | March | 2026 | 2026-03-12 09:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202512-NM25-05915 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:48 | February | 2026 | 2026-02-16 15:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 47
202512-NM25-05919 | GDL17 | Residencial | 3.8 | Period | 2026-02-01 16:14 | February | 2026 | 2026-02-06 09:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 58
202512-NM25-05922 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-29 16:27 | December | 2025 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 92
202512-NM25-05925 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-29 16:52 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 114 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 92
202512-NM25-05938 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:27 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 67
202512-NM25-05941 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 15:58 | March | 2026 | 2026-03-16 07:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 21
202512-NM25-05949 | GDL17 | Residencial | 3.84 | Period | 2026-03-05 13:45 | March | 2026 | 2026-03-17 13:40 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 26
202512-NM25-05960 | GDL17 | Residencial | 4.608 | Period | 2026-03-17 13:13 | March | 2026 | 2026-03-31 13:33 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 14
202512-NM25-05972 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:50 | February | 2026 | 2026-02-26 08:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-05974 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 13:13 | January | 2026 | 2026-01-19 14:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05975 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 12:10 | January | 2026 | 2026-01-19 14:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05976 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 18:36 | January | 2026 | 2026-01-22 14:41 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 76
202512-NM25-05977 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 11:43 | January | 2026 | 2026-01-19 13:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 76
202512-NM25-05978 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 16:31 | January | 2026 | 2026-01-21 13:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 74
202512-NM25-05979 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 08:31 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 57
202512-NM25-05980 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 16:16 | January | 2026 | 2026-01-19 15:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-05981 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 08:53 | January | 2026 | 2026-02-02 15:11 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 11 | 0 | 2026-04-01 | 69
202512-NM25-05982 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 18:45 | January | 2026 | 2026-01-16 14:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202512-NM25-05983 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 15:23 | January | 2026 | 2026-01-26 12:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 69
202512-NM25-05985 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 15:39 | January | 2026 | 2026-01-23 11:25 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 75
202512-NM25-05986 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 10:28 | January | 2026 | 2026-01-28 09:55 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 12 | 0 | 2026-04-01 | 75
202512-NM25-05987 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 16:34 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  | 1 | 20 | 1 | 2026-04-01 | 70
202512-NM25-05990 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 09:51 | March | 2026 | 2026-04-06 08:03 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 10 | 0 | 2026-04-01 | 5
202512-NM25-05991 | GDL17 | Residencial | 7.6 | Period | 2026-03-26 13:45 | March | 2026 | 2026-03-31 13:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-05994 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 12:47 | January | 2026 | 2026-02-09 14:44 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 18 | 0 | 2026-04-01 | 68
202512-NM25-05995 | GDL17 | Residencial | 4.224 | Period | 2026-02-20 14:01 | February | 2026 | 2026-02-26 13:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202512-NM25-05997 | GDL17 | Residencial | 5.376 | Out of period | 2025-12-30 07:55 | December | 2025 | 2026-03-10 08:32 | 70 | Study | Estudio (E) | Activated | Backlog |  | No | 70 |  | MAYAGUEZ | March |  | 70 | 0 | 2026-04-01 | 92
202512-NM25-05998 | GDL17 | Residencial | 4.608 | Period | 2026-02-03 12:45 | February | 2026 | 2026-02-13 08:52 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 56
202512-NM25-06006 | GDL17 | Residencial | 3.8 | Period | 2026-01-26 13:53 | January | 2026 | 2026-01-29 09:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 64
202512-NM25-06008 | GDL17 | Residencial | 23 | Period | 2026-01-14 08:18 | January | 2026 | 2026-03-12 09:57 | 57 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 57 | 0 | 2026-04-01 | 77
202512-NM25-06010 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:13 | February | 2026 | 2026-02-09 14:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 55
202512-NM25-06012 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:27 | January | 2026 | 2026-02-06 09:46 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 75
202512-NM25-06013 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:19 | January | 2026 | 2026-01-19 15:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 75
202512-NM25-06015 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:15 | February | 2026 | 2026-03-02 14:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 36
202512-NM25-06016 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 17:38 | January | 2026 | 2026-02-17 14:13 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February | 1 | 30 | 4 | 2026-04-01 | 83
202512-NM25-06017 | GDL17 | Residencial | 7.6 | Period | 2026-01-09 12:07 | January | 2026 | 2026-01-14 15:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-06018 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:10 | February | 2026 | 2026-02-09 10:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202512-NM25-06019 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:45 | January | 2026 | 2026-01-22 09:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 70
202512-NM25-06021 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 17:22 | January | 2026 | 2026-01-12 16:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-06022 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 16:01 | March | 2026 | 2026-04-02 15:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 0
202512-NM25-06023 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 17:49 | January | 2026 | 2026-01-19 14:02 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 12 | 0 | 2026-04-01 | 83
202512-NM25-06024 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-30 09:26 | December | 2025 |  |  | NM Representative Review General Info | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 92
202512-NM25-06026 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 11:26 | January | 2026 | 2026-01-21 14:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-06027 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 12:04 | January | 2026 | 2026-01-22 11:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 69
202512-NM25-06028 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:27 | January | 2026 | 2026-01-30 11:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 62
202512-NM25-06029 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 10:36 | January | 2026 | 2026-01-20 09:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202512-NM25-06030 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 11:53 | January | 2026 | 2026-03-26 09:05 | 70 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March |  | 70 | 0 | 2026-04-01 | 76
202512-NM25-06031 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:34 | January | 2026 | 2026-01-20 13:19 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 18 | 0 | 2026-04-01 | 88
202512-NM25-06033 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:35 | February | 2026 | 2026-02-09 15:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 56
202512-NM25-06034 | GDL17 | Residencial | 3.84 | Period | 2026-02-03 14:00 | February | 2026 | 2026-02-06 11:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202512-NM25-06038 | GDL17 | Residencial | 8 | Period | 2026-03-20 10:21 | March | 2026 | 2026-03-23 13:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 12
202512-NM25-06040 | GDL17 | Residencial | 10.368 | Period | 2026-03-03 17:06 | March | 2026 | 2026-03-05 09:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 28
202512-NM25-06043 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 12:41 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 96 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 90
202512-NM25-06045 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:14 | February | 2026 | 2026-03-04 14:31 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 34
202512-NM25-06051 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 13:27 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 11
202512-NM25-06052 | GDL17 | Residencial | 3.8 | Period | 2026-01-15 09:25 | January | 2026 | 2026-01-16 15:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202512-NM25-06053 | GDL17 | Residencial | 3.84 | Period | 2026-01-14 13:34 | January | 2026 | 2026-01-20 13:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 76
202512-NM25-06056 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 17:50 | March | 2026 | 2026-03-20 15:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 12
202512-NM25-06061 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:16 | February | 2026 | 2026-02-05 14:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202512-NM25-06062 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 14:58 | December | 2025 | 2026-01-12 07:53 | 12 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 90
202512-NM25-06063 | GDL17 | Residencial | 8 | Period | 2026-01-28 09:12 | January | 2026 | 2026-01-30 14:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-06065 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-30 11:46 | December | 2025 |  |  | Study | Estudio (E) | Backlog | Backlog |  | No | 105 | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 92
202512-NM25-06068 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:45 | February | 2026 | 2026-03-03 15:48 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 42
202512-NM25-06070 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 07:05 | January | 2026 | 2026-01-30 14:16 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 16 | 0 | 2026-04-01 | 77
202512-NM25-06072 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 07:53 | January | 2026 | 2026-01-26 09:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 70
202512-NM25-06073 | GDL17 | Residencial | 8 | Period | 2026-01-08 10:28 | January | 2026 | 2026-01-13 09:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202512-NM25-06074 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-30 12:11 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 91
202512-NM25-06076 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:14 | February | 2026 | 2026-03-03 09:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202512-NM25-06081 | GDL17 | Residencial | 7.6 | Period | 2026-01-09 09:24 | January | 2026 | 2026-01-14 11:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-06082 | GDL17 | Residencial | 6.144 | Period | 2026-01-15 09:57 | January | 2026 | 2026-02-03 11:05 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 19 | 0 | 2026-04-01 | 76
202512-NM25-06084 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:55 | February | 2026 | 2026-02-25 15:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 39
202512-NM25-06089 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 07:42 | January | 2026 | 2026-01-29 08:16 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 70
202512-NM25-06092 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 17:55 | February | 2026 | 2026-02-27 09:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-06093 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:34 | January | 2026 | 2026-01-09 09:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 88
202512-NM25-06094 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 11:46 | January | 2026 | 2026-01-22 13:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-06097 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:24 | February | 2026 | 2026-02-05 12:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202512-NM25-06098 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:47 | January | 2026 | 2026-01-13 14:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-06100 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 18:45 | February | 2026 | 2026-02-27 09:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 35
202512-NM25-06101 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:11 | February | 2026 | 2026-03-02 09:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-06102 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 17:56 | March | 2026 | 2026-03-13 08:08 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 9 | 1 | 2026-04-01 | 28
202512-NM25-06103 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 15:35 | December | 2025 | 2026-01-07 15:08 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 90
202512-NM25-06105 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:32 | January | 2026 | 2026-02-04 14:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-06106 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:23 | February | 2026 | 2026-02-27 15:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 35
202512-NM25-06111 | GDL17 | Residencial | 15.34 | Out of period | 2025-12-30 14:58 | December | 2025 | 2026-02-04 17:54 | 36 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | SAN JUAN | February | 3 | 11 | 25 | 2026-04-01 | 91
202512-NM25-06113 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 12:40 | February | 2026 | 2026-02-10 14:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 53
202512-NM25-06115 | GDL17 | Residencial | 9 | Period | 2026-01-05 14:35 | January | 2026 | 2026-01-09 09:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 85
202512-NM25-06125 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:18 | March | 2026 |  |  | Create NEM Agreement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 9
202512-NM25-06128 | GDL17 | Residencial | 9 | Period | 2026-01-04 09:52 | January | 2026 | 2026-01-20 10:27 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 16 | 0 | 2026-04-01 | 87
202512-NM25-06129 | GDL17 | Residencial | 3.8 | Period | 2026-01-06 16:54 | January | 2026 | 2026-03-13 14:07 | 66 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 66 | 0 | 2026-04-01 | 84
202512-NM25-06139 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 08:32 | January | 2026 | 2026-01-14 15:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-06142 | GDL17 | Comercial | 18 | Out of period | 2025-12-31 16:05 | December | 2025 | 2026-01-12 08:29 | 12 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 12 | 0 | 2026-04-01 | 90
202512-NM25-06143 | GDL17 | Residencial | 16 | Period | 2026-01-05 16:47 | January | 2026 | 2026-01-09 08:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 85
202512-NM25-06147 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 17:19 | February | 2026 | 2026-03-02 14:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202512-NM25-06149 | GDL17 | Residencial | 6.144 | Period | 2026-02-04 18:18 | February | 2026 | 2026-02-09 13:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 55
202512-NM25-06152 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 13:56 | March | 2026 | 2026-03-16 10:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 20
202512-NM25-06154 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 09:17 | March | 2026 | 2026-03-17 16:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 16
202512-NM25-06155 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 07:48 | December | 2025 | 2026-01-08 16:13 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-06156 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:22 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 91
202512-NM25-06157 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:21 | December | 2025 | 2026-01-05 07:52 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-06158 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 11:54 | March | 2026 | 2026-03-18 13:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 16
202512-NM25-06159 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 08:28 | December | 2025 | 2026-01-14 12:53 | 14 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 14 | 0 | 2026-04-01 | 91
202512-NM25-06161 | GDL17 | Residencial | 5.92 | Out of period | 2025-12-31 08:37 | December | 2025 | 2026-01-05 08:47 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-06162 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 08:40 | December | 2025 | 2026-01-05 12:56 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-06163 | GDL17 | Residencial | 6.17 | Period | 2026-01-27 15:51 | January | 2026 | 2026-01-29 16:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202512-NM25-06165 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 08:46 | December | 2025 | 2026-01-19 10:43 | 19 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 19 | 0 | 2026-04-01 | 91
202512-NM25-06166 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:18 | January | 2026 | 2026-01-22 13:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-06167 | GDL17 | Residencial | 23 | Period | 2026-01-21 08:38 | January | 2026 | 2026-01-22 14:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202512-NM25-06168 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 08:57 | December | 2025 | 2026-01-08 14:57 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-06169 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:44 | January | 2026 | 2026-01-28 10:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-06170 | GDL17 | Residencial | 6.322 | Out of period | 2025-12-31 09:01 | December | 2025 | 2026-01-08 14:50 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-06171 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 07:56 | February | 2026 | 2026-02-12 12:50 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 57
202512-NM25-06173 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:00 | December | 2025 | 2026-01-13 15:44 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-06174 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:20 | December | 2025 | 2026-01-07 14:08 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06176 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:53 | January | 2026 | 2026-01-29 09:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202512-NM25-06177 | GDL17 | Residencial | 7.68 | Period | 2026-03-02 12:42 | March | 2026 | 2026-03-04 09:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 29
202512-NM25-06178 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:42 | December | 2025 | 2026-01-14 10:20 | 14 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 14 | 0 | 2026-04-01 | 91
202512-NM25-06179 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:22 | December | 2025 | 2026-01-13 08:42 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-06180 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:40 | December | 2025 | 2026-01-07 14:02 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06181 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 09:19 | January | 2026 | 2026-02-04 13:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 62
202512-NM25-06182 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:48 | December | 2025 | 2026-01-14 14:31 | 14 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 14 | 0 | 2026-04-01 | 91
202512-NM25-06183 | GDL17 | Residencial | 23 | Period | 2026-03-10 13:48 | March | 2026 | 2026-03-13 14:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 21
202512-NM25-06184 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 09:52 | December | 2025 | 2026-01-07 13:38 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06185 | GDL17 | Residencial | 15.3 | Out of period | 2025-12-31 09:57 | December | 2025 | 2026-02-10 10:29 | 41 | Study | Estudio (E) | Activated | Backlog |  |  |  |  | CAGUAS | February | 2 | 9 | 32 | 2026-04-01 | 91
202512-NM25-06186 | GDL17 | Residencial | 3.84 | Out of period | 2025-12-31 10:00 | December | 2025 | 2026-01-13 14:22 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-06187 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 10:06 | December | 2025 | 2026-01-08 14:02 | 8 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 8 | 0 | 2026-04-01 | 91
202512-NM25-06188 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:49 | March | 2026 | 2026-03-18 08:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202512-NM25-06189 | GDL17 | Residencial | 10.34 | Out of period | 2025-12-31 10:22 | December | 2025 | 2026-01-07 15:06 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06190 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:35 | December | 2025 | 2026-01-05 16:19 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-06191 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:21 | December | 2025 | 2026-01-07 15:12 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06192 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:19 | December | 2025 | 2026-01-05 14:20 | 5 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 91
202512-NM25-06193 | GDL17 | Residencial | 10.672 | Out of period | 2025-12-31 10:31 | December | 2025 | 2026-01-07 13:41 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06194 | GDL17 | Residencial | 8.448 | Period | 2026-03-02 16:34 | March | 2026 | 2026-03-05 10:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202512-NM25-06196 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 07:23 | February | 2026 | 2026-02-05 14:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202512-NM25-06198 | GDL17 | Residencial | 8.418 | Out of period | 2025-12-31 10:51 | December | 2025 | 2026-01-07 14:34 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06200 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 10:47 | December | 2025 | 2026-02-18 13:49 | 49 | Study | Estudio (E) | Activated | Backlog |  | No | 49 |  | ARECIBO | February |  | 49 | 0 | 2026-04-01 | 91
202512-NM25-06201 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 18:37 | March | 2026 | 2026-03-11 15:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 27
202512-NM25-06203 | GDL17 | Residencial | 5.31 | Out of period | 2025-12-31 11:03 | December | 2025 | 2026-01-07 09:25 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06204 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 11:21 | December | 2025 | 2026-01-13 09:25 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-06205 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 20:32 | January | 2026 | 2026-01-15 13:08 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 82
202512-NM25-06207 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 11:02 | December | 2025 | 2026-01-13 10:27 | 13 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 13 | 0 | 2026-04-01 | 91
202512-NM25-06208 | GDL17 | Residencial | 9.406 | Out of period | 2025-12-31 11:04 | December | 2025 | 2026-01-07 14:56 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 91
202512-NM25-06209 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 10:59 | December | 2025 | 2026-01-15 09:06 | 15 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | SAN JUAN | January |  | 15 | 0 | 2026-04-01 | 91
202512-NM25-06212 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:14 | March | 2026 | 2026-03-23 10:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 15
202512-NM25-06213 | GDL17 | Residencial | 3.66 | Period | 2026-01-09 14:18 | January | 2026 | 2026-01-14 12:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 81
202512-NM25-06214 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 16:59 | March | 2026 | 2026-03-31 12:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 5
202512-NM25-06215 | GDL17 | Residencial | 8.418 | Out of period | 2025-12-31 11:56 | December | 2025 | 2026-01-12 09:55 | 12 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 91
202512-NM25-06216 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 11:27 | December | 2025 | 2026-01-12 09:21 | 12 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | CAGUAS | January |  | 12 | 0 | 2026-04-01 | 91
202512-NM25-06219 | GDL17 | Residencial | 7.6 | Out of period | 2025-12-31 11:56 | December | 2025 | 2026-01-12 09:48 | 12 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | ARECIBO | January |  | 12 | 0 | 2026-04-01 | 91
202512-NM25-06220 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 18:21 | January | 2026 | 2026-02-10 09:30 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 60
202512-NM25-06221 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 13:46 | March | 2026 | 2026-03-13 14:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202512-NM25-06222 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 11:53 | December | 2025 | 2026-02-02 11:12 | 33 | Study | Estudio (E) | Activated | Backlog |  | No | 33 |  | BAYAMON | February |  | 33 | 0 | 2026-04-01 | 91
202512-NM25-06225 | GDL17 | Residencial | 4.992 | Period | 2026-02-25 15:59 | February | 2026 | 2026-03-04 10:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 34
202512-NM25-06226 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 19:49 | January | 2026 | 2026-01-13 14:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202512-NM25-06227 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:41 | January | 2026 | 2026-02-05 14:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 60
202512-NM25-06229 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:53 | January | 2026 | 2026-02-03 07:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 5 | 2 | 2026-04-01 | 64
202512-NM25-06231 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:16 | March | 2026 | 2026-03-05 16:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202512-NM25-06232 | GDL17 | Residencial | 5.76 | Period | 2026-03-31 12:31 | March | 2026 |  |  | NM Enter Technical Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 0
202512-NM25-06233 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:25 | January | 2026 | 2026-02-03 12:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 60
202512-NM25-06234 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 13:13 | December | 2025 | 2026-01-07 13:34 | 7 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 90
202512-NM25-06237 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:39 | February | 2026 | 2026-02-20 11:23 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 10 | 0 | 2026-04-01 | 50
202512-NM25-06238 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 13:31 | December | 2025 |  |  | Net Metering | Estudio (E) | Backlog | Backlog |  | No |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 90
202512-NM25-06239 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:31 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 34
202512-NM25-06240 | GDL17 | Residencial | 3.8 | Period | 2026-01-29 13:07 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 61
202512-NM25-06241 | GDL17 | Residencial | 11.5 | Out of period | 2025-12-31 13:44 | December | 2025 | 2026-01-12 10:00 | 12 | Study | Estudio (E) | Activated | Backlog |  | No |  |  | PONCE | January |  | 12 | 0 | 2026-04-01 | 90
202512-NM25-06242 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:21 | March | 2026 | 2026-04-01 13:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 2
202512-NM25-06245 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:15 | January | 2026 | 2026-02-09 16:10 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 10 | 0 | 2026-04-01 | 60
202512-NM25-06246 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:07 | January | 2026 | 2026-02-04 14:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 60
202512-NM25-06247 | GDL17 | Residencial | 8 | Period | 2026-01-25 23:10 | January | 2026 | 2026-01-28 09:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 65
202512-NM25-06248 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 20:46 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 61
202512-NM25-06251 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:35 | February | 2026 | 2026-03-11 14:51 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 12 | 0 | 2026-04-01 | 32
202512-NM25-06252 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 13:02 | March | 2026 | 2026-03-20 10:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 13
202512-NM25-06253 | GDL17 | Residencial | 11.5 | Period | 2026-02-07 19:52 | February | 2026 | 2026-02-10 15:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 52
202512-NM25-06254 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 20:19 | January | 2026 | 2026-02-02 15:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202512-NM25-06255 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:53 | March | 2026 | 2026-04-01 15:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 2
202512-NM25-06256 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 18:19 | February | 2026 | 2026-02-27 14:41 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 41
2025-GD-00033 | GDL17 | Residencial | 5 | Out of period | 2025-01-17 | January | 2025 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 439
2025-GD-00151 | GDL17 | Residencial | 8 | Out of period | 2025-09-16 | September | 2025 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending LUMA action | CAROLINA |  |  |  |  | 2026-04-01 | 197
202601-NM25-00010 | GDL17 | Comercial | 11.5 | Period | 2026-01-22 12:20 | January | 2026 | 2026-01-29 18:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-00011 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:36 | January | 2026 | 2026-01-23 12:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-00017 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 18:29 | February | 2026 | 2026-02-23 09:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-00019 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:21 | January | 2026 | 2026-01-29 14:22 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 13 | 0 | 2026-04-01 | 75
202601-NM25-00021 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 08:20 | March | 2026 | 2026-03-27 15:55 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 14 | 0 | 2026-04-01 | 19
202601-NM25-00022 | GDL17 | Residencial | 12 | Period | 2026-01-08 00:21 | January | 2026 | 2026-01-19 14:21 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 3 | 4 | 7 | 2026-04-01 | 83
202601-NM25-00026 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:54 | January | 2026 | 2026-01-27 12:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-00030 | GDL17 | Residencial | 3.8 | Period | 2026-01-28 09:43 | January | 2026 | 2026-01-29 16:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-00034 | GDL17 | Residencial | 3.8 | Period | 2026-01-14 11:29 | January | 2026 | 2026-01-16 15:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-00040 | GDL17 | Residencial | 7.6 | Period | 2026-01-05 13:07 | January | 2026 | 2026-01-14 15:17 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00056 | GDL17 | Residencial | 9.562 | Period | 2026-01-02 08:47 | January | 2026 | 2026-01-07 09:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 89
202601-NM25-00057 | GDL17 | Residencial | 7.492 | Period | 2026-01-02 08:40 | January | 2026 | 2026-01-07 10:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 89
202601-NM25-00058 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 08:54 | January | 2026 | 2026-01-09 09:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 89
202601-NM25-00059 | GDL17 | Residencial | 8.448 | Period | 2026-01-05 07:24 | January | 2026 | 2026-01-09 09:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 86
202601-NM25-00060 | GDL17 | Residencial | 21.02 | Period | 2026-01-02 09:03 | January | 2026 | 2026-01-07 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 89
202601-NM25-00062 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 09:12 | January | 2026 | 2026-01-14 16:27 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 89
202601-NM25-00065 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:08 | January | 2026 | 2026-01-08 13:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 89
202601-NM25-00066 | GDL17 | Residencial | 10 | Period | 2026-01-19 10:59 | January | 2026 | 2026-01-26 13:31 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 72
202601-NM25-00067 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:19 | January | 2026 | 2026-03-09 13:49 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March | 1 | 21 | 0 | 2026-04-01 | 64
202601-NM25-00069 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:16 | January | 2026 | 2026-01-08 10:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 89
202601-NM25-00074 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:29 | January | 2026 | 2026-01-14 09:41 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 89
202601-NM25-00075 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 14:16 | March | 2026 | 2026-04-13 12:54 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 13 | 0 | 2026-04-01 | 0
202601-NM25-00077 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 10:35 | January | 2026 | 2026-01-14 08:19 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 89
202601-NM25-00078 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:26 | February | 2026 | 2026-02-26 08:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-00080 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 11:00 | January | 2026 | 2026-02-03 15:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-00082 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 16:22 | March | 2026 | 2026-03-10 07:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 25
202601-NM25-00083 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 07:58 | January | 2026 | 2026-01-12 09:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 86
202601-NM25-00084 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 11:23 | January | 2026 | 2026-01-12 10:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 86
202601-NM25-00086 | GDL17 | Residencial | 8.724 | Period | 2026-01-02 11:40 | January | 2026 | 2026-01-07 10:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 89
202601-NM25-00087 | GDL17 | Residencial | 23 | Period | 2026-02-03 17:44 | February | 2026 | 2026-02-10 13:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 56
202601-NM25-00088 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:22 | January | 2026 | 2026-01-12 13:09 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 10 | 0 | 2026-04-01 | 89
202601-NM25-00089 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:18 | January | 2026 | 2026-01-07 10:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00091 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:09 | January | 2026 | 2026-01-20 14:19 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 18 | 0 | 2026-04-01 | 88
202601-NM25-00093 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 11:44 | January | 2026 | 2026-01-13 11:04 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 11 | 0 | 2026-04-01 | 89
202601-NM25-00095 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:00 | January | 2026 | 2026-01-08 13:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 89
202601-NM25-00097 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:26 | January | 2026 | 2026-01-07 10:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00098 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:33 | January | 2026 | 2026-01-28 14:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 68
202601-NM25-00100 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:23 | January | 2026 | 2026-01-08 14:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 88
202601-NM25-00101 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 15:46 | March | 2026 | 2026-03-09 11:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 26
202601-NM25-00102 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:45 | January | 2026 | 2026-01-12 11:17 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00103 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 07:55 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 69
202601-NM25-00104 | GDL17 | Residencial | 3.84 | Period | 2026-01-16 09:33 | January | 2026 | 2026-01-21 15:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-00105 | GDL17 | Residencial | 5.536 | Period | 2026-01-02 12:39 | January | 2026 | 2026-01-09 16:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 88
202601-NM25-00106 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 12:45 | January | 2026 | 2026-01-08 10:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 88
202601-NM25-00107 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:08 | January | 2026 | 2026-01-14 08:26 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 88
202601-NM25-00109 | GDL17 | Residencial | 7.102 | Period | 2026-01-02 13:03 | January | 2026 | 2026-01-07 10:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00110 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:17 | January | 2026 | 2026-02-03 08:41 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 19 | 0 | 2026-04-01 | 76
202601-NM25-00111 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:37 | January | 2026 | 2026-01-19 10:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-00112 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 13:48 | January | 2026 | 2026-01-20 15:31 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 18 | 0 | 2026-04-01 | 88
202601-NM25-00113 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:07 | January | 2026 | 2026-01-12 14:22 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 10 | 0 | 2026-04-01 | 88
202601-NM25-00114 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:30 | January | 2026 | 2026-02-04 13:45 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 14 | 0 | 2026-04-01 | 70
202601-NM25-00115 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:37 | January | 2026 | 2026-03-04 14:51 | 48 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 48 | 0 | 2026-04-01 | 76
202601-NM25-00116 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:46 | March | 2026 | 2026-03-26 08:02 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 22 | 0 | 2026-04-01 | 27
202601-NM25-00117 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:31 | January | 2026 | 2026-01-09 07:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 88
202601-NM25-00118 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:56 | March | 2026 | 2026-03-23 08:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 14
202601-NM25-00120 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 14:45 | January | 2026 | 2026-01-08 08:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00122 | GDL17 | Residencial | 19.1 | Period | 2026-01-16 10:30 | January | 2026 | 2026-01-27 12:57 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | January | 1 | 5 | 6 | 2026-04-01 | 75
202601-NM25-00123 | GDL17 | Comercial | 9 | Period | 2026-03-25 22:18 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 6
202601-NM25-00124 | GDL17 | Residencial | 8 | Period | 2026-01-07 10:31 | January | 2026 | 2026-01-13 14:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 84
202601-NM25-00125 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:09 | January | 2026 | 2026-01-13 15:11 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 11 | 0 | 2026-04-01 | 88
202601-NM25-00127 | GDL17 | Residencial | 9.072 | Period | 2026-01-02 15:19 | January | 2026 | 2026-01-07 10:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00128 | GDL17 | Residencial | 4 | Period | 2026-01-02 15:32 | January | 2026 | 2026-01-07 10:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00129 | GDL17 | Residencial | 6.296 | Period | 2026-01-02 15:33 | January | 2026 | 2026-01-07 10:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00130 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:54 | January | 2026 | 2026-01-14 09:11 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 88
202601-NM25-00131 | GDL17 | Residencial | 7.6 | Period | 2026-01-02 15:44 | January | 2026 | 2026-01-12 10:46 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 10 | 0 | 2026-04-01 | 88
202601-NM25-00132 | GDL17 | Residencial | 6.872 | Period | 2026-01-02 15:48 | January | 2026 | 2026-01-08 13:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 88
202601-NM25-00133 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:57 | January | 2026 | 2026-01-08 12:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 88
202601-NM25-00134 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 15:59 | January | 2026 | 2026-01-14 09:42 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 88
202601-NM25-00135 | GDL17 | Residencial | 9 | Period | 2026-01-09 12:57 | January | 2026 | 2026-01-21 10:02 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 81
202601-NM25-00136 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 08:17 | January | 2026 | 2026-01-16 13:33 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 86
202601-NM25-00137 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 16:15 | January | 2026 | 2026-01-14 13:28 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 88
202601-NM25-00138 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 16:31 | January | 2026 | 2026-01-14 15:13 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 88
202601-NM25-00139 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 16:37 | January | 2026 | 2026-01-08 09:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 88
202601-NM25-00140 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:52 | March | 2026 | 2026-04-07 08:18 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 28 | 0 | 2026-04-01 | 22
202601-NM25-00141 | GDL17 | Residencial | 8.126 | Period | 2026-01-02 16:44 | January | 2026 | 2026-01-08 12:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 88
202601-NM25-00142 | GDL17 | Residencial | 11.5 | Period | 2026-01-02 16:57 | January | 2026 | 2026-01-14 09:18 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 88
202601-NM25-00143 | GDL17 | Residencial | 23 | Period | 2026-03-13 15:59 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 18
202601-NM25-00144 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 08:11 | January | 2026 | 2026-01-12 09:15 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 9 | 0 | 2026-04-01 | 88
202601-NM25-00145 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 08:28 | January | 2026 | 2026-01-13 08:55 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 10 | 0 | 2026-04-01 | 88
202601-NM25-00146 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 08:55 | January | 2026 | 2026-01-08 12:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00147 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 09:17 | January | 2026 | 2026-01-08 12:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00148 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 09:35 | January | 2026 | 2026-01-08 12:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00149 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 10:25 | January | 2026 | 2026-01-20 09:19 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 17 | 0 | 2026-04-01 | 88
202601-NM25-00150 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 10:46 | January | 2026 | 2026-01-08 12:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 88
202601-NM25-00151 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 11:42 | January | 2026 | 2026-01-07 15:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 88
202601-NM25-00152 | GDL17 | Residencial | 11.5 | Period | 2026-01-03 12:16 | January | 2026 | 2026-01-08 07:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 87
202601-NM25-00153 | GDL17 | Residencial | 11.4 | Period | 2026-01-03 17:05 | January | 2026 | 2026-01-16 11:28 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 13 | 0 | 2026-04-01 | 87
202601-NM25-00155 | GDL17 | Residencial | 10 | Period | 2026-01-03 16:39 | January | 2026 | 2026-01-19 10:18 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 16 | 0 | 2026-04-01 | 87
202601-NM25-00156 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:29 | February | 2026 | 2026-02-20 10:49 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 48
202601-NM25-00157 | GDL17 | Residencial | 11.4 | Period | 2026-01-05 07:44 | January | 2026 | 2026-01-09 10:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 86
202601-NM25-00159 | GDL17 | Residencial | 19.1 | Period | 2026-02-02 10:42 | February | 2026 | 2026-02-04 15:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-00160 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 08:47 | January | 2026 | 2026-01-14 09:36 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 86
202601-NM25-00161 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:19 | January | 2026 | 2026-01-21 10:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 74
202601-NM25-00163 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 08:36 | January | 2026 | 2026-01-09 10:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 86
202601-NM25-00165 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 08:54 | January | 2026 | 2026-01-09 15:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 86
202601-NM25-00166 | GDL17 | Residencial | 7.6 | Period | 2026-01-05 09:09 | January | 2026 | 2026-01-14 07:58 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 86
202601-NM25-00167 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 09:16 | January | 2026 | 2026-01-12 08:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 86
202601-NM25-00168 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 09:33 | January | 2026 | 2026-01-14 09:27 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 9 | 0 | 2026-04-01 | 86
202601-NM25-00169 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 09:49 | January | 2026 | 2026-01-15 13:42 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 10 | 0 | 2026-04-01 | 86
202601-NM25-00170 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 16:54 | March | 2026 | 2026-03-18 14:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 14
202601-NM25-00171 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 09:41 | January | 2026 | 2026-01-13 08:04 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 8 | 0 | 2026-04-01 | 86
202601-NM25-00172 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 09:50 | January | 2026 | 2026-01-12 10:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 86
202601-NM25-00173 | GDL17 | Residencial | 7.6 | Period | 2026-01-05 09:54 | January | 2026 | 2026-01-12 10:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 86
202601-NM25-00175 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 10:21 | January | 2026 | 2026-01-08 15:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 86
202601-NM25-00177 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 10:18 | January | 2026 | 2026-01-09 15:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 86
202601-NM25-00178 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 10:24 | January | 2026 | 2026-01-28 15:15 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 23 | 0 | 2026-04-01 | 86
202601-NM25-00179 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 10:18 | January | 2026 | 2026-01-12 09:39 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 86
202601-NM25-00180 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 10:42 | January | 2026 | 2026-01-13 14:25 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 86
202601-NM25-00181 | GDL17 | Residencial | 5.5 | Period | 2026-03-18 22:06 | March | 2026 | 2026-03-19 11:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 13
202601-NM25-00182 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 10:35 | January | 2026 | 2026-01-19 09:10 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 14 | 0 | 2026-04-01 | 86
202601-NM25-00183 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:27 | February | 2026 | 2026-02-27 07:45 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 40
202601-NM25-00184 | GDL17 | Residencial | 9.136 | Period | 2026-01-05 10:48 | January | 2026 | 2026-01-09 10:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 86
202601-NM25-00185 | GDL17 | Residencial | 8 | Period | 2026-02-10 13:37 | February | 2026 | 2026-02-12 08:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 49
202601-NM25-00186 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 17:15 | February | 2026 | 2026-02-26 09:33 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 43
202601-NM25-00187 | GDL17 | Comercial | 11.5 | Period | 2026-01-05 11:01 | January | 2026 | 2026-01-09 15:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 86
202601-NM25-00188 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:43 | February | 2026 | 2026-02-13 14:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 47
202601-NM25-00189 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:35 | February | 2026 | 2026-03-09 13:33 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 27 | 0 | 2026-04-01 | 49
202601-NM25-00190 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 16:47 | March | 2026 | 2026-03-13 13:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 20
202601-NM25-00191 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:51 | February | 2026 | 2026-02-26 08:31 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 43
202601-NM25-00193 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:58 | February | 2026 | 2026-02-25 09:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 41
202601-NM25-00195 | GDL17 | Residencial | 8 | Period | 2026-01-27 09:28 | January | 2026 | 2026-01-30 15:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-00197 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 11:42 | January | 2026 | 2026-02-09 14:21 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 35 | 0 | 2026-04-01 | 86
202601-NM25-00198 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 11:45 | January | 2026 | 2026-01-14 13:26 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 9 | 0 | 2026-04-01 | 86
202601-NM25-00199 | GDL17 | Residencial | 5.956 | Period | 2026-01-05 11:51 | January | 2026 | 2026-01-09 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 86
202601-NM25-00200 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:00 | January | 2026 | 2026-01-21 08:01 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 16 | 0 | 2026-04-01 | 86
202601-NM25-00201 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:11 | January | 2026 | 2026-01-09 08:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00203 | GDL17 | Residencial | 4.72 | Period | 2026-01-05 12:15 | January | 2026 | 2026-01-09 10:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00206 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:23 | January | 2026 | 2026-01-15 14:43 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 10 | 0 | 2026-04-01 | 85
202601-NM25-00207 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:26 | January | 2026 | 2026-01-20 13:41 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 15 | 0 | 2026-04-01 | 85
202601-NM25-00209 | GDL17 | Residencial | 9.216 | Period | 2026-01-07 10:38 | January | 2026 | 2026-01-09 10:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 84
202601-NM25-00210 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:36 | January | 2026 | 2026-01-28 13:51 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 23 | 0 | 2026-04-01 | 85
202601-NM25-00211 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:26 | January | 2026 | 2026-01-14 15:06 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00212 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:28 | January | 2026 | 2026-01-12 09:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00214 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:32 | January | 2026 | 2026-01-09 10:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00216 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:34 | January | 2026 | 2026-01-13 10:55 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 85
202601-NM25-00217 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:37 | January | 2026 | 2026-01-14 10:32 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00220 | GDL17 | Comercial | 11.5 | Period | 2026-01-05 12:41 | January | 2026 | 2026-01-16 10:25 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 11 | 0 | 2026-04-01 | 85
202601-NM25-00222 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:43 | January | 2026 | 2026-01-12 10:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00223 | GDL17 | Residencial | 15.8 | Period | 2026-01-05 12:43 | January | 2026 | 2026-01-09 10:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00224 | GDL17 | Residencial | 7.6 | Period | 2026-02-09 15:37 | February | 2026 | 2026-02-11 08:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-00225 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:57 | January | 2026 | 2026-01-09 09:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00226 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:55 | January | 2026 | 2026-01-09 15:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00227 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 18:06 | February | 2026 | 2026-02-23 09:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-00228 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:59 | January | 2026 | 2026-01-12 10:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00229 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:52 | January | 2026 | 2026-01-13 13:47 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 85
202601-NM25-00230 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:14 | January | 2026 | 2026-01-09 09:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00231 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 12:59 | January | 2026 | 2026-01-09 15:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00233 | GDL17 | Residencial | 16.5 | Period | 2026-02-13 16:44 | February | 2026 | 2026-02-18 10:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202601-NM25-00234 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:32 | February | 2026 | 2026-02-24 11:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202601-NM25-00235 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:02 | January | 2026 | 2026-01-12 07:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00236 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:05 | January | 2026 | 2026-02-11 11:25 | 37 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 37 | 0 | 2026-04-01 | 85
202601-NM25-00238 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:12 | January | 2026 | 2026-01-09 15:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00239 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:15 | January | 2026 | 2026-01-12 11:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00240 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:13 | January | 2026 | 2026-01-12 10:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00241 | GDL17 | Residencial | 5.76 | Period | 2026-02-10 14:29 | February | 2026 | 2026-02-16 08:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 49
202601-NM25-00242 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:47 | January | 2026 | 2026-01-12 11:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00243 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:00 | February | 2026 | 2026-03-23 15:30 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 33 | 0 | 2026-04-01 | 41
202601-NM25-00245 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:25 | January | 2026 | 2026-01-12 11:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00246 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:25 | January | 2026 | 2026-01-12 09:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00247 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:35 | January | 2026 | 2026-01-29 08:28 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-00248 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:26 | January | 2026 | 2026-01-12 11:19 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00250 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:09 | February | 2026 | 2026-02-23 09:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-00251 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:34 | January | 2026 | 2026-01-09 10:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00252 | GDL17 | Residencial | 19.1 | Period | 2026-01-29 11:14 | January | 2026 | 2026-02-02 09:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-00253 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:41 | January | 2026 | 2026-01-14 15:58 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00254 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 16:31 | January | 2026 | 2026-01-14 16:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00255 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 11:02 | January | 2026 | 2026-02-04 17:56 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 71
202601-NM25-00256 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:45 | January | 2026 | 2026-01-09 15:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00257 | GDL17 | Residencial | 8 | Period | 2026-02-05 08:32 | February | 2026 | 2026-02-12 08:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 55
202601-NM25-00258 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:00 | January | 2026 | 2026-01-14 08:27 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00261 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:56 | January | 2026 | 2026-01-20 13:26 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 15 | 0 | 2026-04-01 | 85
202601-NM25-00263 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 11:54 | February | 2026 | 2026-02-25 07:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202601-NM25-00264 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 13:56 | January | 2026 | 2026-01-14 12:58 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00266 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:07 | March | 2026 | 2026-04-23 15:01 | 45 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 45 | 42 | 2026-04-01 | 22
202601-NM25-00268 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:42 | February | 2026 | 2026-02-26 10:28 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 43
202601-NM25-00271 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:23 | January | 2026 | 2026-01-14 10:11 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00272 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:20 | January | 2026 | 2026-01-12 12:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00273 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:52 | January | 2026 | 2026-01-12 13:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00275 | GDL17 | Residencial | 3.8 | Period | 2026-01-21 16:41 | January | 2026 | 2026-01-23 15:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-00276 | GDL17 | Residencial | 15.34 | Period | 2026-01-07 17:10 | January | 2026 | 2026-01-13 13:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00277 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:33 | January | 2026 | 2026-01-12 13:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00278 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:33 | January | 2026 | 2026-01-28 08:36 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 23 | 0 | 2026-04-01 | 85
202601-NM25-00280 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:09 | January | 2026 | 2026-01-22 13:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-00281 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:37 | January | 2026 | 2026-01-09 15:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00285 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:50 | January | 2026 | 2026-01-09 09:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00287 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 14:51 | January | 2026 | 2026-01-14 14:20 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00290 | GDL17 | Residencial | 12 | Period | 2026-02-12 02:16 | February | 2026 | 2026-02-13 08:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-00292 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 13:57 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 4
202601-NM25-00295 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 15:32 | January | 2026 | 2026-01-12 13:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00297 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 11:34 | January | 2026 | 2026-02-24 14:25 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | February | 1 | 8 | 1 | 2026-04-01 | 70
202601-NM25-00299 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 15:17 | January | 2026 | 2026-01-14 11:01 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00300 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 15:27 | January | 2026 | 2026-01-14 13:52 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 9 | 0 | 2026-04-01 | 85
202601-NM25-00305 | GDL17 | Residencial | 6.25 | Period | 2026-01-05 15:32 | January | 2026 | 2026-01-09 09:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00309 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 15:47 | January | 2026 | 2026-01-09 15:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00310 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 15:52 | January | 2026 | 2026-01-14 08:26 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 8 | 0 | 2026-04-01 | 85
202601-NM25-00312 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 09:08 | January | 2026 | 2026-01-29 14:41 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 9 | 0 | 2026-04-01 | 71
202601-NM25-00316 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 16:07 | January | 2026 | 2026-01-09 10:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00317 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:32 | January | 2026 | 2026-01-16 10:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-00318 | GDL17 | Residencial | 7.296 | Period | 2026-03-18 16:36 | March | 2026 | 2026-03-19 17:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 13
202601-NM25-00319 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:35 | March | 2026 | 2026-03-11 08:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 28
202601-NM25-00321 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 16:19 | January | 2026 | 2026-01-13 09:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00322 | GDL17 | Residencial | 3.8 | Period | 2026-02-06 12:19 | February | 2026 | 2026-02-11 09:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 53
202601-NM25-00325 | GDL17 | Residencial | 6.296 | Period | 2026-01-05 16:45 | January | 2026 | 2026-01-09 15:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00326 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:08 | February | 2026 | 2026-02-27 12:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 36
202601-NM25-00327 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:42 | March | 2026 | 2026-03-27 13:46 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 11 | 0 | 2026-04-01 | 15
202601-NM25-00328 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 17:00 | January | 2026 | 2026-01-12 09:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 85
202601-NM25-00330 | GDL17 | Residencial | 5.015 | Period | 2026-01-05 17:06 | January | 2026 | 2026-01-09 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00332 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 17:12 | January | 2026 | 2026-01-09 16:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 85
202601-NM25-00335 | GDL17 | Residencial | 12 | Period | 2026-01-08 12:53 | January | 2026 | 2026-01-13 12:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00337 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 17:32 | January | 2026 | 2026-03-10 13:09 | 64 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 64 | 0 | 2026-04-01 | 85
202601-NM25-00340 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 17:39 | January | 2026 | 2026-01-19 10:42 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 14 | 0 | 2026-04-01 | 85
202601-NM25-00341 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:59 | March | 2026 | 2026-03-24 08:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 13
202601-NM25-00344 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:18 | January | 2026 | 2026-01-09 15:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 84
202601-NM25-00345 | GDL17 | Residencial | 11.5 | Period | 2026-01-05 17:50 | January | 2026 | 2026-01-12 13:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 85
202601-NM25-00346 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:26 | January | 2026 | 2026-01-13 15:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00347 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 20:30 | January | 2026 | 2026-01-16 16:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-00350 | GDL17 | Residencial | 11.5 | Period | 2026-01-06 08:31 | January | 2026 | 2026-01-09 08:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 85
202601-NM25-00351 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:37 | February | 2026 | 2026-02-19 14:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202601-NM25-00352 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 16:02 | March | 2026 | 2026-03-06 13:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 26
202601-NM25-00353 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 18:08 | March | 2026 | 2026-03-17 10:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 21
202601-NM25-00354 | GDL17 | Residencial | 18.17 | Period | 2026-01-06 12:27 | January | 2026 | 2026-01-12 11:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 84
202601-NM25-00356 | GDL17 | Residencial | 23 | Period | 2026-03-16 15:47 | March | 2026 | 2026-04-22 14:01 | 37 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 37 | 0 | 2026-04-01 | 15
202601-NM25-00357 | GDL17 | Residencial | 12 | Period | 2026-01-19 13:59 | January | 2026 | 2026-01-21 10:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-00359 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 14:03 | March | 2026 | 2026-04-13 09:19 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 18 | 0 | 2026-04-01 | 5
202601-NM25-00360 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 14:23 | February | 2026 | 2026-02-19 10:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 43
202601-NM25-00363 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:51 | January | 2026 | 2026-01-20 09:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-00364 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 09:35 | January | 2026 | 2026-02-03 13:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-00366 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:49 | January | 2026 | 2026-01-23 07:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 70
202601-NM25-00367 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:17 | January | 2026 | 2026-02-03 10:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 64
202601-NM25-00368 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:13 | January | 2026 | 2026-01-29 08:38 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 13 | 0 | 2026-04-01 | 75
202601-NM25-00369 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:48 | February | 2026 | 2026-02-04 13:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-00370 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:34 | January | 2026 | 2026-01-28 10:27 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 70
202601-NM25-00372 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:02 | January | 2026 | 2026-01-09 15:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 84
202601-NM25-00373 | GDL17 | Comercial | 15.36 | Period | 2026-01-22 01:50 | January | 2026 | 2026-02-03 10:54 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 2 | 10 | 2026-04-01 | 69
202601-NM25-00374 | GDL17 | Residencial | 6.528 | Period | 2026-01-26 10:57 | January | 2026 | 2026-01-30 10:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 65
202601-NM25-00375 | GDL17 | Residencial | 9 | Period | 2026-01-07 16:28 | January | 2026 | 2026-01-13 14:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00377 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:35 | January | 2026 | 2026-02-16 15:59 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 64
202601-NM25-00378 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 16:18 | January | 2026 | 2026-01-23 10:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-00380 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:14 | January | 2026 | 2026-01-30 13:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-00381 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:30 | January | 2026 | 2026-01-14 12:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 84
202601-NM25-00383 | GDL17 | Residencial | 16.576 | Period | 2026-01-07 10:10 | January | 2026 | 2026-01-09 14:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 84
202601-NM25-00384 | GDL17 | Residencial | 10 | Period | 2026-01-07 11:18 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 84
202601-NM25-00385 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 16:14 | March | 2026 | 2026-04-01 15:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 5 | 0 | 2026-04-01 | 4
202601-NM25-00386 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:41 | January | 2026 | 2026-01-14 11:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 84
202601-NM25-00387 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 17:44 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 83
202601-NM25-00388 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 09:45 | January | 2026 | 2026-01-09 10:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 84
202601-NM25-00389 | GDL17 | Residencial | 13.2 | Period | 2026-01-16 09:11 | January | 2026 | 2026-01-22 15:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 75
202601-NM25-00390 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:40 | January | 2026 | 2026-01-13 15:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00391 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 09:53 | January | 2026 | 2026-01-13 11:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 84
202601-NM25-00392 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:28 | January | 2026 | 2026-01-29 18:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 69
202601-NM25-00393 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:01 | January | 2026 | 2026-01-14 15:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 84
202601-NM25-00394 | GDL17 | Residencial | 7.68 | Period | 2026-02-05 15:05 | February | 2026 | 2026-02-12 10:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 54
202601-NM25-00395 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:03 | January | 2026 | 2026-01-12 13:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 84
202601-NM25-00396 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 20:18 | February | 2026 | 2026-02-23 09:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-00398 | GDL17 | Residencial | 23 | Period | 2026-02-23 16:53 | February | 2026 | 2026-02-26 08:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202601-NM25-00399 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:14 | January | 2026 | 2026-01-12 16:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202601-NM25-00400 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:12 | January | 2026 | 2026-01-13 11:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 84
202601-NM25-00402 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:26 | January | 2026 | 2026-01-13 13:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 84
202601-NM25-00403 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:25 | January | 2026 | 2026-01-14 11:28 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 84
202601-NM25-00405 | GDL17 | Residencial | 7.68 | Period | 2026-01-30 15:13 | January | 2026 | 2026-02-03 16:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-00406 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:30 | January | 2026 | 2026-01-12 13:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 84
202601-NM25-00407 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:05 | January | 2026 | 2026-01-23 08:44 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 15 | 0 | 2026-04-01 | 82
202601-NM25-00410 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:38 | January | 2026 | 2026-01-12 14:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 84
202601-NM25-00411 | GDL17 | Residencial | 5 | Period | 2026-01-21 08:32 | January | 2026 | 2026-01-22 10:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00412 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:03 | January | 2026 | 2026-01-29 08:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-00413 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:21 | February | 2026 | 2026-02-05 14:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-00414 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:49 | January | 2026 | 2026-01-09 08:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 84
202601-NM25-00416 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 10:44 | January | 2026 | 2026-01-12 14:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 84
202601-NM25-00418 | GDL17 | Residencial | 7.6 | Period | 2026-02-23 09:48 | February | 2026 | 2026-02-26 15:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 37
202601-NM25-00421 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:46 | January | 2026 | 2026-01-22 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-00422 | GDL17 | Residencial | 3.8 | Period | 2026-01-15 16:56 | January | 2026 | 2026-01-19 14:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-00425 | GDL17 | Residencial | 9.84 | Period | 2026-01-26 15:36 | January | 2026 | 2026-01-28 10:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00427 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 07:38 | January | 2026 | 2026-01-19 09:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-00428 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:08 | January | 2026 | 2026-01-22 13:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00429 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:01 | January | 2026 | 2026-01-12 14:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 84
202601-NM25-00431 | GDL17 | Residencial | 15 | Period | 2026-02-06 22:16 | February | 2026 | 2026-02-10 15:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 53
202601-NM25-00432 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:03 | January | 2026 | 2026-01-12 13:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 84
202601-NM25-00433 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 10:36 | January | 2026 | 2026-01-19 14:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-00434 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:04 | January | 2026 | 2026-01-21 14:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 77
202601-NM25-00435 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:33 | January | 2026 | 2026-01-22 14:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00436 | GDL17 | Residencial | 19.1 | Period | 2026-01-21 13:36 | January | 2026 | 2026-01-22 15:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-00438 | GDL17 | Residencial | 4.224 | Period | 2026-01-15 09:56 | January | 2026 | 2026-01-19 13:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-00439 | GDL17 | Residencial | 8 | Period | 2026-02-05 09:00 | February | 2026 | 2026-02-09 09:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-00440 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:55 | January | 2026 | 2026-01-23 14:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-00441 | GDL17 | Residencial | 17.5 | Period | 2026-01-09 14:22 | January | 2026 | 2026-01-27 12:59 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | January | 2 | 5 | 13 | 2026-04-01 | 81
202601-NM25-00442 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:58 | January | 2026 | 2026-01-29 13:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00444 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:31 | January | 2026 | 2026-01-09 15:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 84
202601-NM25-00445 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:03 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 75
202601-NM25-00446 | GDL17 | Residencial | 3.84 | Period | 2026-01-15 15:28 | January | 2026 | 2026-01-21 09:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 75
202601-NM25-00447 | GDL17 | Residencial | 11.5 | Period | 2026-01-13 20:56 | January | 2026 | 2026-01-15 16:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-00448 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:34 | January | 2026 | 2026-01-14 13:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 84
202601-NM25-00449 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 07:14 | January | 2026 | 2026-01-23 11:03 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 77
202601-NM25-00450 | GDL17 | Residencial | 15 | Period | 2026-01-14 12:10 | January | 2026 | 2026-01-15 16:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | January | 1 | 1 | 0 | 2026-04-01 | 76
202601-NM25-00451 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:39 | January | 2026 | 2026-01-26 08:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 71
202601-NM25-00452 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 15:29 | March | 2026 | 2026-04-02 15:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 0
202601-NM25-00453 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 11:52 | January | 2026 | 2026-01-14 08:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 84
202601-NM25-00454 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:53 | January | 2026 | 2026-02-03 15:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-00456 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:57 | January | 2026 | 2026-01-28 13:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00457 | GDL17 | Residencial | 10.044 | Period | 2026-01-07 12:26 | January | 2026 | 2026-01-09 10:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 83
202601-NM25-00458 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 07:54 | January | 2026 | 2026-01-29 14:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-00460 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 12:08 | January | 2026 | 2026-01-12 10:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00461 | GDL17 | Residencial | 23 | Period | 2026-03-12 14:48 | March | 2026 | 2026-03-30 14:52 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 18 | 0 | 2026-04-01 | 19
202601-NM25-00462 | GDL17 | Residencial | 23 | Period | 2026-01-19 09:20 | January | 2026 | 2026-01-20 14:27 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-00463 | GDL17 | Residencial | 11.824 | Period | 2026-01-15 08:46 | January | 2026 | 2026-01-16 15:27 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00465 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:07 | February | 2026 | 2026-03-04 11:14 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 36
202601-NM25-00466 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:26 | January | 2026 | 2026-01-22 10:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-00467 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:21 | January | 2026 | 2026-01-23 16:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-00468 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 17:02 | February | 2026 | 2026-02-27 14:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 35
202601-NM25-00469 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:23 | January | 2026 | 2026-01-29 15:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-00470 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:45 | January | 2026 | 2026-01-29 15:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-00471 | GDL17 | Residencial | 14 | Period | 2026-01-07 16:42 | January | 2026 | 2026-01-12 15:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00472 | GDL17 | Comercial | 23 | Period | 2026-01-27 09:11 | January | 2026 | 2026-01-29 09:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00473 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:06 | January | 2026 | 2026-01-26 12:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-00474 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:22 | February | 2026 | 2026-02-10 15:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-00475 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:28 | January | 2026 | 2026-01-26 13:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-00478 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:03 | January | 2026 | 2026-02-10 14:19 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 14 | 0 | 2026-04-01 | 64
202601-NM25-00479 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 13:12 | January | 2026 | 2026-01-13 15:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00480 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:28 | January | 2026 | 2026-01-22 10:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00481 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:32 | January | 2026 | 2026-01-29 10:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00482 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:52 | January | 2026 | 2026-01-29 10:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00483 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:51 | January | 2026 | 2026-01-20 10:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-00484 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:20 | January | 2026 | 2026-01-22 10:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-00485 | GDL17 | Residencial | 15 | Period | 2026-01-07 15:39 | January | 2026 | 2026-01-12 16:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00486 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:01 | January | 2026 | 2026-01-26 12:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 69
202601-NM25-00487 | GDL17 | Residencial | 3.84 | Period | 2026-01-21 09:29 | January | 2026 | 2026-01-22 10:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00488 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:57 | January | 2026 | 2026-01-22 11:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-00489 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 19:04 | February | 2026 | 2026-02-27 13:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 38
202601-NM25-00490 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:29 | January | 2026 | 2026-01-22 14:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00491 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 20:49 | February | 2026 | 2026-03-11 09:05 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 19 | 0 | 2026-04-01 | 39
202601-NM25-00494 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 07:45 | February | 2026 | 2026-02-11 15:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-00495 | GDL17 | Residencial | 15.2 | Period | 2026-02-11 11:51 | February | 2026 | 2026-02-24 13:00 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 13 | 0 | 2026-04-01 | 49
202601-NM25-00497 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:12 | January | 2026 | 2026-02-03 10:39 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 64
202601-NM25-00498 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:18 | January | 2026 | 2026-01-26 14:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-00499 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:09 | January | 2026 | 2026-01-12 14:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00500 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:37 | January | 2026 | 2026-01-21 13:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-00501 | GDL17 | Residencial | 5.376 | Period | 2026-02-02 14:30 | February | 2026 | 2026-02-04 09:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-00502 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 07:28 | January | 2026 | 2026-03-03 10:05 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 34 | 0 | 2026-04-01 | 63
202601-NM25-00503 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:56 | March | 2026 | 2026-03-19 14:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202601-NM25-00504 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:23 | January | 2026 | 2026-02-03 16:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-00505 | GDL17 | Residencial | 23 | Period | 2026-01-26 14:17 | January | 2026 | 2026-01-30 12:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 64
202601-NM25-00507 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:39 | January | 2026 | 2026-01-12 14:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00508 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:36 | February | 2026 | 2026-02-06 11:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 55
202601-NM25-00509 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 14:40 | January | 2026 | 2026-01-12 14:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00511 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:50 | January | 2026 | 2026-01-29 08:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-00512 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:35 | January | 2026 | 2026-01-13 14:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00513 | GDL17 | Residencial | 12 | Period | 2026-01-19 11:58 | January | 2026 | 2026-01-21 10:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 72
202601-NM25-00514 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:46 | January | 2026 | 2026-01-19 10:27 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 11 | 0 | 2026-04-01 | 83
202601-NM25-00515 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:06 | January | 2026 | 2026-01-12 15:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00516 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 17:31 | January | 2026 | 2026-02-17 14:02 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | February | 1 | 31 | 5 | 2026-04-01 | 83
202601-NM25-00517 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:08 | January | 2026 | 2026-01-16 15:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00518 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:42 | January | 2026 | 2026-01-14 15:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00519 | GDL17 | Residencial | 3.8 | Period | 2026-01-08 10:46 | January | 2026 | 2026-01-14 15:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00520 | GDL17 | Residencial | 10.672 | Period | 2026-01-07 15:22 | January | 2026 | 2026-01-12 16:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00522 | GDL17 | Residencial | 9.52 | Period | 2026-01-07 15:29 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 83
202601-NM25-00524 | GDL17 | Residencial | 11.44 | Period | 2026-01-07 15:33 | January | 2026 | 2026-01-12 15:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00526 | GDL17 | Residencial | 15 | Period | 2026-01-07 20:50 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 83
202601-NM25-00527 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:44 | January | 2026 | 2026-01-15 08:17 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 83
202601-NM25-00528 | GDL17 | Residencial | 11.5 | Period | 2026-01-07 15:55 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 83
202601-NM25-00529 | GDL17 | Comercial | 13.032 | Period | 2026-01-15 10:18 | January | 2026 | 2026-01-16 16:03 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00534 | GDL17 | Comercial | 7.6 | Period | 2026-01-07 16:10 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 83
202601-NM25-00535 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 10:32 | January | 2026 | 2026-02-17 13:47 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 12 | 1 | 2026-04-01 | 69
202601-NM25-00536 | GDL17 | Residencial | 7.424 | Period | 2026-01-07 16:21 | January | 2026 | 2026-01-13 13:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00537 | GDL17 | Residencial | 7.32 | Period | 2026-01-07 18:48 | January | 2026 | 2026-01-29 13:04 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | January | 3 | 6 | 16 | 2026-04-01 | 83
202601-NM25-00538 | GDL17 | Residencial | 7.6 | Period | 2026-01-07 16:16 | January | 2026 | 2026-01-21 09:42 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 14 | 0 | 2026-04-01 | 83
202601-NM25-00539 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 10:52 | January | 2026 | 2026-01-22 09:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00540 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 17:25 | March | 2026 | 2026-03-13 10:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-00541 | GDL17 | Residencial | 6.68 | Period | 2026-01-08 08:10 | January | 2026 | 2026-01-13 16:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00542 | GDL17 | Residencial | 23 | Period | 2026-01-07 16:53 | January | 2026 | 2026-01-13 14:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00543 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 12:33 | January | 2026 | 2026-01-20 11:06 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 82
202601-NM25-00544 | GDL17 | Residencial | 12 | Period | 2026-02-03 10:13 | February | 2026 | 2026-02-23 08:41 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 20 | 0 | 2026-04-01 | 57
202601-NM25-00545 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:01 | March | 2026 | 2026-03-12 13:40 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 29
202601-NM25-00546 | GDL17 | Residencial | 12.672 | Period | 2026-02-06 15:41 | February | 2026 | 2026-02-10 15:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202601-NM25-00547 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:18 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 83
202601-NM25-00548 | GDL17 | Residencial | 23 | Period | 2026-03-03 16:35 | March | 2026 | 2026-03-09 09:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 28
202601-NM25-00549 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:52 | March | 2026 | 2026-03-05 09:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202601-NM25-00550 | GDL17 | Residencial | 15.2 | Period | 2026-02-17 08:53 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 43
202601-NM25-00552 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 14:46 | February | 2026 | 2026-02-23 10:51 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 10 | 0 | 2026-04-01 | 46
202601-NM25-00553 | GDL17 | Residencial | 23 | Period | 2026-02-12 09:12 | February | 2026 | 2026-02-13 13:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 48
202601-NM25-00554 | GDL17 | Residencial | 5.76 | Period | 2026-03-02 12:27 | March | 2026 | 2026-03-05 12:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202601-NM25-00555 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:35 | February | 2026 | 2026-02-23 15:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 43
202601-NM25-00556 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:08 | March | 2026 | 2026-03-23 11:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 15
202601-NM25-00558 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 07:42 | January | 2026 | 2026-01-16 15:45 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 83
202601-NM25-00559 | GDL17 | Residencial | 7.6 | Period | 2026-01-08 13:17 | January | 2026 | 2026-01-13 08:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00560 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 10:14 | March | 2026 | 2026-03-09 14:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 28
202601-NM25-00561 | GDL17 | Residencial | 23 | Period | 2026-01-22 07:43 | January | 2026 | 2026-01-26 13:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-00562 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:46 | January | 2026 | 2026-01-16 15:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00564 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 07:33 | February | 2026 | 2026-02-11 13:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-00565 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 07:35 | January | 2026 | 2026-02-03 08:09 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 13 | 0 | 2026-04-01 | 70
202601-NM25-00566 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 08:49 | January | 2026 | 2026-01-16 16:06 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 83
202601-NM25-00569 | GDL17 | Residencial | 5.926 | Period | 2026-01-08 08:44 | January | 2026 | 2026-01-14 14:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00570 | GDL17 | Residencial | 7.822 | Period | 2026-01-08 08:44 | January | 2026 | 2026-01-13 15:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00571 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 08:20 | February | 2026 | 2026-02-12 09:46 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 56
202601-NM25-00573 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 08:50 | January | 2026 | 2026-01-12 16:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 83
202601-NM25-00574 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 10:58 | February | 2026 | 2026-02-27 10:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 35
202601-NM25-00575 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 07:24 | January | 2026 | 2026-02-04 13:20 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 64
202601-NM25-00576 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:38 | March | 2026 | 2026-03-05 11:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 29
202601-NM25-00577 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 10:08 | January | 2026 | 2026-01-16 16:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00578 | GDL17 | Residencial | 15.36 | Period | 2026-03-11 16:22 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 20
202601-NM25-00579 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:11 | January | 2026 | 2026-01-19 10:13 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 11 | 0 | 2026-04-01 | 83
202601-NM25-00580 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:35 | January | 2026 | 2026-01-22 14:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00581 | GDL17 | Residencial | 7.6 | Period | 2026-01-08 09:14 | January | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | ARECIBO | January |  |  |  | 2026-04-01 | 83
202601-NM25-00582 | GDL17 | Residencial | 16.3 | Period | 2026-02-06 12:35 | February | 2026 | 2026-02-11 15:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | February | 1 | 3 | 2 | 2026-04-01 | 53
202601-NM25-00583 | GDL17 | Residencial | 6.572 | Period | 2026-01-08 09:25 | January | 2026 | 2026-01-13 15:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00586 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:33 | January | 2026 | 2026-01-13 14:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00587 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:46 | January | 2026 | 2026-01-23 15:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-00588 | GDL17 | Residencial | 2.304 | Period | 2026-01-14 18:03 | January | 2026 | 2026-01-28 07:39 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 13 | 0 | 2026-04-01 | 76
202601-NM25-00589 | GDL17 | Residencial | 3.84 | Period | 2026-03-11 13:45 | March | 2026 | 2026-03-13 13:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 20
202601-NM25-00590 | GDL17 | Residencial | 23 | Period | 2026-03-02 16:12 | March | 2026 | 2026-03-04 14:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202601-NM25-00591 | GDL17 | Residencial | 7.6 | Period | 2026-01-08 09:45 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 83
202601-NM25-00592 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 17:53 | March | 2026 | 2026-03-16 13:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 21
202601-NM25-00593 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:29 | January | 2026 | 2026-01-20 08:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-00594 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 09:57 | January | 2026 | 2026-01-14 13:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00595 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:48 | January | 2026 | 2026-01-19 11:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-00596 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:25 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 64
202601-NM25-00597 | GDL17 | Residencial | 4.026 | Period | 2026-01-08 10:14 | January | 2026 | 2026-01-13 16:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00599 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:42 | January | 2026 | 2026-01-13 16:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00600 | GDL17 | Residencial | 5.562 | Period | 2026-01-08 10:47 | January | 2026 | 2026-01-14 14:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00601 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 10:24 | January | 2026 | 2026-01-14 13:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00602 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:43 | January | 2026 | 2026-01-14 09:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00603 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:54 | January | 2026 | 2026-01-14 16:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 83
202601-NM25-00604 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:01 | February | 2026 | 2026-02-20 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 42
202601-NM25-00605 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 14:45 | January | 2026 | 2026-01-19 09:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 10 | 0 | 2026-04-01 | 81
202601-NM25-00606 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:12 | January | 2026 | 2026-01-19 07:43 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 83
202601-NM25-00608 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:15 | March | 2026 | 2026-03-16 15:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 18
202601-NM25-00609 | GDL17 | Residencial | 23 | Period | 2026-03-05 16:52 | March | 2026 | 2026-03-12 09:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 26
202601-NM25-00610 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 08:10 | January | 2026 | 2026-01-20 14:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-00611 | GDL17 | Residencial | 7.6 | Period | 2026-01-09 13:31 | January | 2026 | 2026-01-14 15:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00612 | GDL17 | Residencial | 8.448 | Period | 2026-03-02 12:00 | March | 2026 | 2026-03-04 10:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 29
202601-NM25-00613 | GDL17 | Residencial | 18 | Period | 2026-01-15 16:31 | January | 2026 | 2026-01-21 11:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 75
202601-NM25-00614 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:25 | January | 2026 | 2026-01-28 14:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00615 | GDL17 | Residencial | 7.68 | Period | 2026-01-23 09:42 | January | 2026 | 2026-01-26 13:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-00616 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 14:58 | January | 2026 | 2026-01-15 09:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 81
202601-NM25-00617 | GDL17 | Comercial | 8 | Period | 2026-01-29 10:36 | January | 2026 | 2026-03-19 09:26 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March | 1 | 38 | 11 | 2026-04-01 | 62
202601-NM25-00618 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 10:46 | January | 2026 | 2026-01-14 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00619 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:41 | February | 2026 | 2026-02-27 11:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 35
202601-NM25-00621 | GDL17 | Residencial | 10.672 | Period | 2026-01-08 11:20 | January | 2026 | 2026-01-13 14:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00622 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 12:14 | January | 2026 | 2026-01-22 16:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-00623 | GDL17 | Comercial | 8 | Period | 2026-01-29 10:40 | January | 2026 | 2026-03-31 14:44 | 61 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March | 2 | 41 | 20 | 2026-04-01 | 62
202601-NM25-00624 | GDL17 | Residencial | 15.2 | Period | 2026-01-26 10:24 | January | 2026 | 2026-02-13 08:47 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 65
202601-NM25-00625 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 11:28 | January | 2026 | 2026-01-13 10:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 83
202601-NM25-00626 | GDL17 | Comercial | 8 | Period | 2026-01-29 10:27 | January | 2026 | 2026-03-19 09:54 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March | 1 | 38 | 11 | 2026-04-01 | 62
202601-NM25-00627 | GDL17 | Residencial | 9 | Period | 2026-01-19 12:37 | January | 2026 | 2026-02-04 08:10 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 15 | 0 | 2026-04-01 | 71
202601-NM25-00628 | GDL17 | Residencial | 11.5 | Period | 2026-01-13 20:47 | January | 2026 | 2026-01-15 09:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-00629 | GDL17 | Residencial | 8 | Period | 2026-02-19 09:55 | February | 2026 | 2026-02-24 08:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 41
202601-NM25-00630 | GDL17 | Comercial | 8 | Period | 2026-01-29 10:17 | January | 2026 | 2026-03-19 09:51 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March | 1 | 38 | 11 | 2026-04-01 | 62
202601-NM25-00631 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 11:59 | January | 2026 | 2026-01-14 14:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00632 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 17:38 | January | 2026 | 2026-01-16 15:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-00634 | GDL17 | Residencial | 23 | Period | 2026-03-16 16:04 | March | 2026 | 2026-03-17 13:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-00635 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:50 | January | 2026 | 2026-01-13 08:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00636 | GDL17 | Residencial | 19.1 | Period | 2026-01-08 13:17 | January | 2026 | 2026-02-02 12:48 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 2 | 7 | 18 | 2026-04-01 | 82
202601-NM25-00638 | GDL17 | Residencial | 3.84 | Period | 2026-03-02 16:16 | March | 2026 | 2026-03-16 08:05 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 14 | 0 | 2026-04-01 | 29
202601-NM25-00639 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 08:05 | January | 2026 | 2026-01-16 15:24 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00641 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:50 | January | 2026 | 2026-01-13 13:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00643 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:42 | January | 2026 | 2026-01-14 16:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 82
202601-NM25-00644 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 13:58 | January | 2026 | 2026-01-13 13:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00645 | GDL17 | Residencial | 9 | Period | 2026-01-23 09:02 | January | 2026 | 2026-02-03 15:49 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 68
202601-NM25-00646 | GDL17 | Residencial | 7.6 | Period | 2026-01-08 13:44 | January | 2026 | 2026-01-14 15:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 82
202601-NM25-00648 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:45 | January | 2026 | 2026-01-30 10:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-00649 | GDL17 | Residencial | 7.68 | Period | 2026-02-09 15:45 | February | 2026 | 2026-02-12 09:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 50
202601-NM25-00651 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:05 | January | 2026 | 2026-01-30 13:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-00652 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 13:02 | March | 2026 | 2026-03-13 14:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 20
202601-NM25-00653 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 11:28 | February | 2026 | 2026-02-24 13:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-00654 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:46 | February | 2026 | 2026-02-12 14:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-00656 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 10:31 | January | 2026 | 2026-02-05 11:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 2 | 5 | 2026-04-01 | 62
202601-NM25-00658 | GDL17 | Residencial | 6.144 | Period | 2026-01-08 15:35 | January | 2026 | 2026-01-15 14:08 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 82
202601-NM25-00659 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:13 | January | 2026 | 2026-01-20 16:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-00660 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 14:56 | January | 2026 | 2026-01-14 15:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 82
202601-NM25-00661 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:49 | January | 2026 | 2026-02-04 08:46 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 63
202601-NM25-00662 | GDL17 | Residencial | 15.36 | Period | 2026-01-14 08:30 | January | 2026 | 2026-01-15 13:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00663 | GDL17 | Residencial | 8.562 | Period | 2026-01-08 15:21 | January | 2026 | 2026-01-14 09:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 82
202601-NM25-00664 | GDL17 | Residencial | 5.076 | Period | 2026-01-08 15:22 | January | 2026 | 2026-01-13 15:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00665 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:29 | January | 2026 | 2026-01-15 16:00 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 82
202601-NM25-00666 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:45 | January | 2026 | 2026-01-14 15:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 82
202601-NM25-00667 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:35 | January | 2026 | 2026-01-13 09:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00668 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 15:31 | January | 2026 | 2026-01-13 08:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00669 | GDL17 | Residencial | 7.072 | Period | 2026-01-08 15:40 | January | 2026 | 2026-01-14 08:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 82
202601-NM25-00671 | GDL17 | Residencial | 9.52 | Period | 2026-01-08 15:58 | January | 2026 | 2026-01-13 15:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00672 | GDL17 | Residencial | 3.84 | Period | 2026-01-16 11:43 | January | 2026 | 2026-01-19 10:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-00674 | GDL17 | Residencial | 11.4 | Period | 2026-02-11 09:55 | February | 2026 | 2026-02-17 08:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 49
202601-NM25-00676 | GDL17 | Residencial | 23 | Period | 2026-03-06 16:00 | March | 2026 | 2026-03-12 13:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 25
202601-NM25-00678 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 16:39 | January | 2026 | 2026-01-13 14:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00679 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 16:49 | January | 2026 | 2026-01-20 13:58 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 82
202601-NM25-00680 | GDL17 | Residencial | 4.224 | Period | 2026-01-14 18:07 | January | 2026 | 2026-01-16 07:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-00681 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 17:35 | January | 2026 | 2026-01-28 16:12 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 20 | 0 | 2026-04-01 | 82
202601-NM25-00683 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 13:45 | March | 2026 | 2026-03-05 16:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 28
202601-NM25-00684 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 17:56 | January | 2026 | 2026-01-14 15:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 82
202601-NM25-00685 | GDL17 | Residencial | 5.76 | Period | 2026-03-10 18:03 | March | 2026 | 2026-03-17 09:34 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 21
202601-NM25-00686 | GDL17 | Residencial | 11.5 | Period | 2026-01-08 18:18 | January | 2026 | 2026-01-13 10:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00687 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 17:58 | February | 2026 | 2026-02-10 08:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-00688 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 14:11 | March | 2026 | 2026-03-09 16:19 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 0 | 0 | 2026-04-01 | 22
202601-NM25-00689 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:19 | March | 2026 | 2026-04-23 13:05 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 49 | 0 | 2026-04-01 | 26
202601-NM25-00690 | GDL17 | Residencial | 8 | Period | 2026-01-22 15:59 | January | 2026 | 2026-01-26 13:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-00697 | GDL17 | Residencial | 6.8 | Period | 2026-01-08 22:04 | January | 2026 | 2026-01-13 12:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00698 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:50 | January | 2026 | 2026-02-16 11:11 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 21 | 0 | 2026-04-01 | 65
202601-NM25-00699 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 08:13 | January | 2026 | 2026-01-29 16:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 69
202601-NM25-00700 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 15:41 | February | 2026 | 2026-02-10 12:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-00701 | GDL17 | Comercial | 22.8 | Period | 2026-02-25 10:30 | February | 2026 | 2026-03-26 10:35 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 3 | 26 | 2026-04-01 | 35
202601-NM25-00703 | GDL17 | Residencial | 23 | Period | 2026-01-26 09:37 | January | 2026 | 2026-01-27 13:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-00705 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:00 | January | 2026 | 2026-01-19 13:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-00707 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 09:41 | January | 2026 | 2026-01-20 14:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-00708 | GDL17 | Residencial | 5.76 | Period | 2026-01-20 12:17 | January | 2026 | 2026-01-26 07:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 70
202601-NM25-00709 | GDL17 | Residencial | 8 | Period | 2026-01-16 07:31 | January | 2026 | 2026-01-19 13:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-00710 | GDL17 | Residencial | 4.992 | Period | 2026-01-15 09:45 | January | 2026 | 2026-01-16 15:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00711 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 11:17 | January | 2026 | 2026-02-02 10:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-00714 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 08:44 | January | 2026 | 2026-02-10 10:30 | 32 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 32 | 0 | 2026-04-01 | 82
202601-NM25-00716 | GDL17 | Residencial | 9.6 | Period | 2026-01-09 08:47 | January | 2026 | 2026-01-15 09:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 82
202601-NM25-00720 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:19 | January | 2026 | 2026-01-29 10:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00723 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 17:17 | March | 2026 | 2026-03-13 11:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 20
202601-NM25-00724 | GDL17 | Comercial | 19.2 | Period | 2026-01-09 09:41 | January | 2026 | 2026-02-16 10:12 | 38 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | February |  | 38 | 0 | 2026-04-01 | 82
202601-NM25-00725 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:42 | January | 2026 | 2026-01-28 12:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00727 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 15:14 | January | 2026 | 2026-02-03 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-00728 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 17:28 | February | 2026 | 2026-02-18 11:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 46
202601-NM25-00729 | GDL17 | Residencial | 3.8 | Period | 2026-02-05 11:31 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 55
202601-NM25-00730 | GDL17 | Residencial | 9.59 | Period | 2026-01-09 09:12 | January | 2026 | 2026-01-14 14:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00733 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:09 | January | 2026 | 2026-01-28 08:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00741 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:18 | January | 2026 | 2026-01-23 08:50 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 75
202601-NM25-00743 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 14:48 | January | 2026 | 2026-01-16 16:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-00745 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 14:04 | February | 2026 | 2026-03-04 13:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 34
202601-NM25-00746 | GDL17 | Residencial | 3.8 | Period | 2026-01-19 11:21 | January | 2026 | 2026-01-23 14:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 72
202601-NM25-00747 | GDL17 | Residencial | 5.76 | Period | 2026-02-05 12:05 | February | 2026 | 2026-02-09 12:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-00749 | GDL17 | Residencial | 7.462 | Period | 2026-01-09 10:03 | January | 2026 | 2026-01-14 14:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00754 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:22 | January | 2026 | 2026-01-26 08:09 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 11 | 0 | 2026-04-01 | 75
202601-NM25-00756 | GDL17 | Residencial | 15.416 | Period | 2026-01-20 09:29 | January | 2026 | 2026-01-21 15:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-00757 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 12:04 | March | 2026 | 2026-03-18 10:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 19
202601-NM25-00758 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 16:23 | February | 2026 | 2026-02-12 10:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-00762 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:50 | January | 2026 | 2026-01-19 09:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-00763 | GDL17 | Residencial | 4.224 | Period | 2026-01-15 07:14 | January | 2026 | 2026-01-16 14:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00765 | GDL17 | Residencial | 9.6 | Period | 2026-01-09 11:25 | January | 2026 | 2026-01-14 09:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00766 | GDL17 | Residencial | 7.6 | Period | 2026-02-23 07:57 | February | 2026 | 2026-03-03 08:02 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 37
202601-NM25-00767 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 11:21 | January | 2026 | 2026-01-22 09:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00768 | GDL17 | Residencial | 7.6 | Period | 2026-02-06 08:15 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 54
202601-NM25-00769 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:00 | January | 2026 | 2026-01-21 16:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-00771 | GDL17 | Residencial | 11.44 | Period | 2026-01-29 10:10 | January | 2026 | 2026-02-03 13:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-00772 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:52 | February | 2026 | 2026-02-16 08:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 48
202601-NM25-00774 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:31 | February | 2026 | 2026-02-10 11:02 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 57
202601-NM25-00776 | GDL17 | Residencial | 7.6 | Period | 2026-02-02 11:21 | February | 2026 | 2026-02-04 13:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-00777 | GDL17 | Residencial | 8.064 | Period | 2026-01-27 12:20 | January | 2026 | 2026-01-29 18:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-00778 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 09:57 | February | 2026 | 2026-02-04 15:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-00779 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 12:51 | January | 2026 | 2026-01-29 15:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-00780 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:46 | January | 2026 | 2026-01-30 13:41 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 9 | 0 | 2026-04-01 | 70
202601-NM25-00781 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:02 | February | 2026 | 2026-02-05 13:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 57
202601-NM25-00783 | GDL17 | Residencial | 23 | Period | 2026-01-26 09:56 | January | 2026 | 2026-01-27 14:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-00784 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 12:00 | January | 2026 | 2026-01-14 08:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 82
202601-NM25-00785 | GDL17 | Residencial | 4.992 | Period | 2026-01-09 16:30 | January | 2026 | 2026-01-19 16:11 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 10 | 0 | 2026-04-01 | 81
202601-NM25-00786 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 12:17 | January | 2026 | 2026-01-14 14:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00787 | GDL17 | Residencial | 9.752 | Period | 2026-01-09 12:23 | January | 2026 | 2026-01-14 14:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00788 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 14:11 | February | 2026 | 2026-03-03 10:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202601-NM25-00789 | GDL17 | Residencial | 3.8 | Period | 2026-01-14 13:08 | January | 2026 | 2026-01-20 09:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-00790 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 12:29 | January | 2026 | 2026-01-14 14:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00792 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 12:43 | January | 2026 | 2026-01-14 14:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00793 | GDL17 | Residencial | 23 | Period | 2026-03-05 10:42 | March | 2026 | 2026-03-11 13:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 27
202601-NM25-00795 | GDL17 | Residencial | 4.992 | Period | 2026-01-09 13:27 | January | 2026 | 2026-01-14 14:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00796 | GDL17 | Residencial | 14.208 | Period | 2026-03-10 15:38 | March | 2026 | 2026-03-12 14:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-00797 | GDL17 | Residencial | 11.4 | Period | 2026-01-09 13:18 | January | 2026 | 2026-01-29 16:27 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 20 | 0 | 2026-04-01 | 81
202601-NM25-00798 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:04 | March | 2026 | 2026-03-05 13:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202601-NM25-00800 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:54 | March | 2026 | 2026-03-18 16:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 19
202601-NM25-00801 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 13:44 | January | 2026 | 2026-01-15 08:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 81
202601-NM25-00802 | GDL17 | Residencial | 11.4 | Period | 2026-01-09 15:49 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 81
202601-NM25-00804 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 18:09 | February | 2026 | 2026-02-10 14:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-00805 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:04 | January | 2026 | 2026-01-29 07:53 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 70
202601-NM25-00806 | GDL17 | Residencial | 7.6 | Period | 2026-03-05 10:08 | March | 2026 | 2026-03-17 13:44 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 13 | 0 | 2026-04-01 | 27
202601-NM25-00808 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:51 | February | 2026 | 2026-03-03 11:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202601-NM25-00809 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:42 | January | 2026 | 2026-02-11 12:59 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 28 | 0 | 2026-04-01 | 76
202601-NM25-00810 | GDL17 | Residencial | 9.6 | Period | 2026-01-21 08:24 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 70
202601-NM25-00811 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:18 | January | 2026 | 2026-01-14 15:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00812 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:06 | January | 2026 | 2026-01-14 16:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00813 | GDL17 | Residencial | 7.296 | Period | 2026-01-15 07:52 | January | 2026 | 2026-01-23 09:48 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 76
202601-NM25-00814 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:51 | January | 2026 | 2026-01-21 10:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-00815 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 10:32 | February | 2026 | 2026-03-27 07:41 | 44 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March | 1 | 36 | 3 | 2026-04-01 | 49
202601-NM25-00816 | GDL17 | Residencial | 7.6 | Period | 2026-02-23 10:49 | February | 2026 | 2026-03-03 11:08 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 37
202601-NM25-00818 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:01 | January | 2026 | 2026-01-16 10:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-00819 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:38 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 57
202601-NM25-00820 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:05 | January | 2026 | 2026-01-19 15:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-00821 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 10:41 | January | 2026 | 2026-02-02 15:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 61
202601-NM25-00822 | GDL17 | Residencial | 4.026 | Period | 2026-01-09 15:23 | January | 2026 | 2026-01-14 14:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00823 | GDL17 | Residencial | 1.92 | Period | 2026-01-09 15:25 | January | 2026 | 2026-01-14 15:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00824 | GDL17 | Residencial | 7.6 | Period | 2026-01-09 15:19 | January | 2026 | 2026-01-20 14:40 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 11 | 0 | 2026-04-01 | 81
202601-NM25-00825 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:37 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 81
202601-NM25-00826 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:45 | January | 2026 | 2026-01-14 16:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00827 | GDL17 | Residencial | 7.6 | Period | 2026-01-09 15:43 | January | 2026 | 2026-01-19 13:56 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 10 | 0 | 2026-04-01 | 81
202601-NM25-00828 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:26 | March | 2026 | 2026-03-17 09:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 18
202601-NM25-00829 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:46 | January | 2026 | 2026-01-13 16:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 81
202601-NM25-00830 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 15:49 | January | 2026 | 2026-03-12 14:17 | 62 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 62 | 0 | 2026-04-01 | 81
202601-NM25-00831 | GDL17 | Residencial | 7.6 | Period | 2026-02-17 11:15 | February | 2026 | 2026-02-24 08:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 43
202601-NM25-00832 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:43 | March | 2026 | 2026-03-05 08:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202601-NM25-00833 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 16:25 | January | 2026 | 2026-03-10 11:07 | 60 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 60 | 0 | 2026-04-01 | 81
202601-NM25-00835 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 16:25 | January | 2026 | 2026-01-14 08:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00836 | GDL17 | Residencial | 11.4 | Period | 2026-01-09 16:42 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 81
202601-NM25-00837 | GDL17 | Residencial | 11.5 | Period | 2026-01-09 16:45 | January | 2026 | 2026-01-14 09:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 81
202601-NM25-00839 | GDL17 | Residencial | 8.832 | Period | 2026-02-25 16:03 | February | 2026 | 2026-03-02 10:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202601-NM25-00840 | GDL17 | Residencial | 22.8 | Period | 2026-01-29 12:53 | January | 2026 | 2026-02-02 10:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-00841 | GDL17 | Residencial | 5.25 | Period | 2026-01-14 15:58 | January | 2026 | 2026-02-24 08:08 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February | 1 | 8 | 33 | 2026-04-01 | 76
202601-NM25-00842 | GDL17 | Residencial | 5.25 | Period | 2026-02-17 17:07 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 42
202601-NM25-00843 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:42 | March | 2026 | 2026-03-18 09:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 19
202601-NM25-00844 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 13:39 | March | 2026 | 2026-03-11 11:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 27
202601-NM25-00845 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 18:56 | January | 2026 | 2026-01-22 10:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-00846 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 05:40 | March | 2026 | 2026-03-26 10:25 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 14
202601-NM25-00847 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:33 | February | 2026 | 2026-02-19 13:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 46
202601-NM25-00852 | GDL17 | Residencial | 9 | Period | 2026-02-18 00:18 | February | 2026 | 2026-02-23 09:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-00853 | GDL17 | Comercial | 18 | Period | 2026-01-24 20:06 | January | 2026 | 2026-01-29 08:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 66
202601-NM25-00854 | GDL17 | Residencial | 18 | Period | 2026-01-26 09:52 | January | 2026 | 2026-01-29 08:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 65
202601-NM25-00855 | GDL17 | Residencial | 9 | Period | 2026-02-19 19:00 | February | 2026 | 2026-02-27 12:52 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 40
202601-NM25-00856 | GDL17 | Residencial | 15 | Period | 2026-01-11 22:45 | January | 2026 | 2026-01-14 15:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 79
202601-NM25-00860 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:27 | February | 2026 | 2026-02-06 14:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-00862 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 13:18 | January | 2026 | 2026-03-19 09:58 | 64 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March | 1 | 36 | 27 | 2026-04-01 | 76
202601-NM25-00863 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:22 | January | 2026 | 2026-01-16 13:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-00864 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 10:16 | January | 2026 | 2026-02-03 16:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-00865 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:27 | January | 2026 | 2026-01-20 08:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 77
202601-NM25-00866 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 14:04 | February | 2026 | 2026-02-11 14:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 54
202601-NM25-00867 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 10:12 | February | 2026 | 2026-03-30 12:42 | 46 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March | 2 | 37 | 6 | 2026-04-01 | 48
202601-NM25-00868 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:26 | January | 2026 | 2026-03-31 13:49 | 76 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 76 | 0 | 2026-04-01 | 77
202601-NM25-00869 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:21 | January | 2026 | 2026-01-19 14:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-00870 | GDL17 | Residencial | 8 | Period | 2026-02-19 08:39 | February | 2026 | 2026-02-24 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-00871 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 12:57 | January | 2026 | 2026-02-04 07:54 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 63
202601-NM25-00872 | GDL17 | Residencial | 19.1 | Period | 2026-01-26 13:52 | January | 2026 | 2026-01-28 14:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00874 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:10 | January | 2026 | 2026-01-28 15:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-00875 | GDL17 | Residencial | 16.22 | Period | 2026-01-16 10:08 | January | 2026 | 2026-01-27 09:36 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | January | 1 | 5 | 6 | 2026-04-01 | 75
202601-NM25-00877 | GDL17 | Residencial | 15 | Period | 2026-01-21 10:22 | January | 2026 | 2026-01-22 14:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00878 | GDL17 | Residencial | 9.15 | Period | 2026-01-14 09:27 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 77
202601-NM25-00881 | GDL17 | Residencial | 7.682 | Period | 2026-01-14 07:40 | January | 2026 | 2026-01-15 13:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00882 | GDL17 | Residencial | 16.81 | Period | 2026-01-26 11:20 | January | 2026 | 2026-02-24 16:07 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 5 | 24 | 2026-04-01 | 65
202601-NM25-00885 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 10:59 | February | 2026 | 2026-02-12 12:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-00886 | GDL17 | Residencial | 19 | Period | 2026-01-14 15:47 | January | 2026 | 2026-01-16 14:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-00888 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:16 | February | 2026 | 2026-02-24 16:13 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 12 | 1 | 2026-04-01 | 49
202601-NM25-00889 | GDL17 | Residencial | 13.908 | Period | 2026-01-14 14:45 | January | 2026 | 2026-02-18 15:02 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 35 | 0 | 2026-04-01 | 76
202601-NM25-00891 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:31 | January | 2026 | 2026-01-29 09:05 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 69
202601-NM25-00893 | GDL17 | Residencial | 7.6 | Period | 2026-02-27 10:39 | February | 2026 | 2026-03-05 10:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 33
202601-NM25-00894 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 11:06 | January | 2026 | 2026-01-15 12:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00895 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:36 | January | 2026 | 2026-02-16 15:39 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 33 | 0 | 2026-04-01 | 77
202601-NM25-00897 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:15 | February | 2026 | 2026-02-25 14:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202601-NM25-00898 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:57 | January | 2026 | 2026-01-20 09:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-00900 | GDL17 | Residencial | 7.6 | Period | 2026-02-06 09:47 | February | 2026 | 2026-02-10 14:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-00901 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:38 | January | 2026 | 2026-02-16 15:43 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 33 | 0 | 2026-04-01 | 77
202601-NM25-00902 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:30 | March | 2026 | 2026-03-31 14:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 7
202601-NM25-00903 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:40 | January | 2026 | 2026-02-16 15:45 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 33 | 0 | 2026-04-01 | 77
202601-NM25-00904 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 15:46 | January | 2026 | 2026-01-21 14:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-00905 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:42 | January | 2026 | 2026-02-25 10:55 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February | 1 | 40 | 2 | 2026-04-01 | 77
202601-NM25-00906 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:46 | January | 2026 | 2026-02-18 10:31 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 35 | 0 | 2026-04-01 | 77
202601-NM25-00907 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:40 | March | 2026 | 2026-03-18 14:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-00908 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:49 | January | 2026 | 2026-02-18 10:28 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 35 | 0 | 2026-04-01 | 77
202601-NM25-00909 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:53 | January | 2026 | 2026-02-18 10:25 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 35 | 0 | 2026-04-01 | 77
202601-NM25-00910 | GDL17 | Residencial | 13.44 | Period | 2026-03-04 11:16 | March | 2026 | 2026-03-06 13:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 28
202601-NM25-00911 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 09:59 | January | 2026 | 2026-02-17 16:27 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 34 | 0 | 2026-04-01 | 77
202601-NM25-00912 | GDL17 | Comercial | 5.3 | Period | 2026-01-14 10:05 | January | 2026 | 2026-02-17 16:26 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | February |  | 34 | 0 | 2026-04-01 | 77
202601-NM25-00914 | GDL17 | Residencial | 3.84 | Period | 2026-02-10 10:53 | February | 2026 | 2026-02-12 08:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 50
202601-NM25-00915 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:53 | March | 2026 | 2026-03-05 15:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 29
202601-NM25-00916 | GDL17 | Residencial | 23 | Period | 2026-01-26 13:54 | January | 2026 | 2026-01-28 15:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-00918 | GDL17 | Residencial | 11.4 | Period | 2026-01-13 20:42 | January | 2026 | 2026-01-14 16:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00920 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 12:52 | March | 2026 | 2026-03-10 14:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 25
202601-NM25-00921 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 23:04 | February | 2026 | 2026-02-25 08:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202601-NM25-00924 | GDL17 | Residencial | 23 | Period | 2026-02-19 18:22 | February | 2026 | 2026-02-25 08:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202601-NM25-00925 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:12 | January | 2026 | 2026-01-16 15:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00927 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 07:22 | January | 2026 | 2026-01-15 08:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00928 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 20:38 | February | 2026 | 2026-02-27 14:52 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 40
202601-NM25-00930 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:16 | February | 2026 | 2026-02-23 09:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-00931 | GDL17 | Residencial | 5.961 | Period | 2026-01-14 12:56 | January | 2026 | 2026-01-15 14:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00932 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:36 | January | 2026 | 2026-01-29 11:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 67
202601-NM25-00936 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:12 | March | 2026 | 2026-03-05 08:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202601-NM25-00937 | GDL17 | Residencial | 23 | Period | 2026-01-26 11:43 | January | 2026 | 2026-02-13 14:08 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 65
202601-NM25-00939 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 01:08 | February | 2026 | 2026-02-25 08:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202601-NM25-00940 | GDL17 | Residencial | 8 | Period | 2026-02-18 13:20 | February | 2026 | 2026-03-04 09:44 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 41
202601-NM25-00942 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:02 | February | 2026 | 2026-02-12 12:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-00943 | GDL17 | Residencial | 3.84 | Period | 2026-01-21 08:07 | January | 2026 | 2026-01-22 12:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-00945 | GDL17 | Residencial | 7.68 | Period | 2026-01-22 11:40 | January | 2026 | 2026-01-29 08:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 69
202601-NM25-00946 | GDL17 | Residencial | 6 | Period | 2026-03-23 12:32 | March | 2026 | 2026-03-25 15:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 8
202601-NM25-00947 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:31 | January | 2026 | 2026-01-27 12:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-00949 | GDL17 | Residencial | 5.376 | Period | 2026-01-14 08:20 | January | 2026 | 2026-01-15 13:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00950 | GDL17 | Residencial | 23 | Period | 2026-03-16 14:48 | March | 2026 | 2026-03-17 13:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-00953 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:03 | January | 2026 | 2026-01-15 12:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00955 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:51 | January | 2026 | 2026-01-26 10:27 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | January | 1 | 8 | 2 | 2026-04-01 | 74
202601-NM25-00956 | GDL17 | Residencial | 8 | Period | 2026-02-05 23:27 | February | 2026 | 2026-02-10 14:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-00957 | GDL17 | Residencial | 7.6 | Period | 2026-02-09 08:58 | February | 2026 | 2026-02-11 10:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 51
202601-NM25-00958 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:31 | January | 2026 | 2026-01-29 09:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-00960 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 18:42 | February | 2026 | 2026-02-25 08:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202601-NM25-00961 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:21 | January | 2026 | 2026-01-30 08:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 64
202601-NM25-00962 | GDL17 | Residencial | 11.5 | Period | 2026-02-28 13:07 | February | 2026 | 2026-03-04 15:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 31
202601-NM25-00964 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:35 | January | 2026 | 2026-01-20 10:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-00965 | GDL17 | Residencial | 12 | Period | 2026-01-15 11:12 | January | 2026 | 2026-01-19 10:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-00966 | GDL17 | Residencial | 24 | Period | 2026-01-14 17:17 | January | 2026 | 2026-01-16 13:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-00967 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 08:39 | January | 2026 | 2026-01-29 10:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 65
202601-NM25-00968 | GDL17 | Residencial | 17.2 | Period | 2026-01-15 09:38 | January | 2026 | 2026-01-16 15:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-00972 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:58 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 43
202601-NM25-00973 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 13:16 | March | 2026 | 2026-03-31 16:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 4
202601-NM25-00975 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:26 | March | 2026 | 2026-03-04 14:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202601-NM25-00976 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 18:43 | March | 2026 | 2026-03-16 13:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 19
202601-NM25-00977 | GDL17 | Residencial | 13.6 | Period | 2026-01-18 14:03 | January | 2026 | 2026-01-20 14:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 72
202601-NM25-00982 | GDL17 | Residencial | 9 | Period | 2026-01-19 22:14 | January | 2026 | 2026-01-21 14:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-00983 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 09:52 | March | 2026 | 2026-03-19 16:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 15
202601-NM25-00985 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 12:53 | January | 2026 | 2026-02-04 17:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 62
202601-NM25-00986 | GDL17 | Residencial | 7.6 | Period | 2026-03-02 09:28 | March | 2026 | 2026-03-04 15:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 30
202601-NM25-00987 | GDL17 | Residencial | 15.93 | Period | 2026-01-14 15:22 | January | 2026 | 2026-02-06 10:54 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 3 | 4 | 19 | 2026-04-01 | 76
202601-NM25-00988 | GDL17 | Residencial | 7.6 | Period | 2026-02-06 22:00 | February | 2026 | 2026-02-10 15:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 53
202601-NM25-00991 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 08:08 | January | 2026 | 2026-01-21 14:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 77
202601-NM25-00993 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 07:59 | January | 2026 | 2026-01-15 08:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00995 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:15 | January | 2026 | 2026-01-15 12:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-00996 | GDL17 | Residencial | 7.6 | Period | 2026-02-20 19:23 | February | 2026 | 2026-02-26 08:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-00997 | GDL17 | Residencial | 7.6 | Period | 2026-03-12 07:39 | March | 2026 | 2026-03-13 16:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 20
202601-NM25-00998 | GDL17 | Residencial | 18.09 | Period | 2026-01-29 09:38 | January | 2026 | 2026-03-13 13:24 | 43 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March | 3 | 34 | 9 | 2026-04-01 | 62
202601-NM25-01000 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:12 | February | 2026 | 2026-02-12 09:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 54
202601-NM25-01001 | GDL17 | Residencial | 11.5 | Period | 2026-01-25 12:44 | January | 2026 | 2026-01-26 16:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-01003 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 07:57 | March | 2026 | 2026-03-18 13:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 16
202601-NM25-01004 | GDL17 | Comercial | 11.5 | Period | 2026-01-27 15:15 | January | 2026 | 2026-01-30 09:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 63
202601-NM25-01006 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:39 | January | 2026 | 2026-01-28 15:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-01007 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:01 | February | 2026 | 2026-02-16 09:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 49
202601-NM25-01008 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 11:02 | March | 2026 | 2026-03-18 15:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-01009 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 08:38 | January | 2026 | 2026-02-10 10:19 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 72
202601-NM25-01010 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:28 | January | 2026 | 2026-02-04 11:25 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 64
202601-NM25-01012 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:36 | February | 2026 | 2026-02-19 08:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202601-NM25-01013 | GDL17 | Residencial | 8 | Period | 2026-02-19 09:39 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 41
202601-NM25-01014 | GDL17 | Residencial | 12 | Period | 2026-02-02 14:23 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 57
202601-NM25-01015 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 17:28 | March | 2026 | 2026-04-24 14:25 | 44 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 44 | 42 | 2026-04-01 | 20
202601-NM25-01016 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 11:42 | January | 2026 | 2026-02-05 10:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 61
202601-NM25-01017 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 07:16 | March | 2026 | 2026-04-13 11:24 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 21 | 0 | 2026-04-01 | 8
202601-NM25-01019 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:23 | January | 2026 | 2026-01-20 15:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01020 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:13 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 35
202601-NM25-01021 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:10 | January | 2026 | 2026-01-15 16:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01022 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 17:55 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 47
202601-NM25-01023 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 13:58 | January | 2026 | 2026-01-19 13:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01024 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:00 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 76
202601-NM25-01025 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:40 | January | 2026 | 2026-01-19 15:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01027 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:10 | January | 2026 | 2026-01-30 10:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 65
202601-NM25-01028 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:08 | March | 2026 | 2026-03-05 09:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 28
202601-NM25-01030 | GDL17 | Residencial | 3.8 | Period | 2026-01-19 14:37 | January | 2026 | 2026-01-21 12:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01031 | GDL17 | Residencial | 9.6 | Period | 2026-01-14 08:17 | January | 2026 | 2026-01-15 11:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01032 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:29 | February | 2026 | 2026-03-05 14:36 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 35
202601-NM25-01033 | GDL17 | Residencial | 3.84 | Period | 2026-01-16 10:54 | January | 2026 | 2026-02-06 15:31 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 75
202601-NM25-01034 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:49 | January | 2026 | 2026-01-19 12:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01035 | GDL17 | Residencial | 7.6 | Period | 2026-02-27 09:39 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 33
202601-NM25-01036 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:00 | January | 2026 | 2026-02-11 10:45 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 12 | 0 | 2026-04-01 | 60
202601-NM25-01040 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:14 | January | 2026 | 2026-01-16 16:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-01041 | GDL17 | Residencial | 23 | Period | 2026-03-10 12:46 | March | 2026 | 2026-03-11 16:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 21
202601-NM25-01042 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:32 | January | 2026 | 2026-01-19 08:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-01043 | GDL17 | Residencial | 12 | Period | 2026-01-22 09:10 | January | 2026 | 2026-01-23 16:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-01044 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 22:20 | February | 2026 | 2026-03-02 09:35 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 8 | 3 | 2026-04-01 | 40
202601-NM25-01045 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 15:03 | February | 2026 | 2026-02-11 13:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-01047 | GDL17 | Residencial | 8 | Period | 2026-01-14 11:56 | January | 2026 | 2026-01-23 10:34 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 77
202601-NM25-01048 | GDL17 | Residencial | 5.376 | Period | 2026-01-19 10:43 | January | 2026 | 2026-01-23 09:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 72
202601-NM25-01050 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:47 | February | 2026 | 2026-02-09 15:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 57
202601-NM25-01051 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:28 | February | 2026 | 2026-02-06 13:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-01054 | GDL17 | Residencial | 23 | Period | 2026-02-23 11:45 | February | 2026 | 2026-02-27 09:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 37
202601-NM25-01055 | GDL17 | Residencial | 4.224 | Period | 2026-01-22 13:51 | January | 2026 | 2026-01-28 15:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-01057 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:31 | February | 2026 | 2026-02-27 11:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 35
202601-NM25-01058 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 09:42 | March | 2026 | 2026-03-11 08:20 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 6 | 2 | 2026-04-01 | 29
202601-NM25-01059 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:53 | January | 2026 | 2026-01-30 08:08 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 14 | 0 | 2026-04-01 | 75
202601-NM25-01060 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:22 | January | 2026 | 2026-02-12 10:09 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 62
202601-NM25-01061 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:44 | January | 2026 | 2026-01-27 09:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | January | 1 | 1 | 3 | 2026-04-01 | 67
202601-NM25-01062 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 08:08 | January | 2026 | 2026-01-16 15:27 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01063 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 15:55 | January | 2026 | 2026-01-20 12:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01065 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 17:21 | February | 2026 | 2026-02-26 08:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-01067 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:30 | February | 2026 | 2026-02-17 14:23 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 54
202601-NM25-01068 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 08:18 | January | 2026 | 2026-01-21 10:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-01070 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:31 | January | 2026 | 2026-01-26 15:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-01071 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:09 | March | 2026 | 2026-03-16 17:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 20
202601-NM25-01072 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 17:37 | February | 2026 | 2026-03-04 08:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 32
202601-NM25-01073 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 18:04 | January | 2026 | 2026-01-19 15:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01074 | GDL17 | Residencial | 7.68 | Period | 2026-01-19 12:49 | January | 2026 | 2026-01-22 14:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 71
202601-NM25-01076 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 07:49 | January | 2026 | 2026-01-16 14:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01077 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:23 | March | 2026 | 2026-03-18 07:54 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 21
202601-NM25-01081 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:36 | January | 2026 | 2026-02-09 11:08 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 10 | 0 | 2026-04-01 | 61
202601-NM25-01082 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:55 | January | 2026 | 2026-02-03 09:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-01083 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:24 | January | 2026 | 2026-01-22 13:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 74
202601-NM25-01084 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 13:09 | February | 2026 | 2026-02-12 14:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-01086 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:27 | March | 2026 | 2026-03-04 09:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 29
202601-NM25-01087 | GDL17 | Residencial | 8 | Period | 2026-01-22 13:37 | January | 2026 | 2026-01-23 15:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-01089 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 20:11 | March | 2026 | 2026-03-06 07:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 28
202601-NM25-01092 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:33 | January | 2026 | 2026-02-04 08:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-01095 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 16:30 | March | 2026 | 2026-03-12 08:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 25
202601-NM25-01097 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 13:45 | January | 2026 | 2026-02-06 10:32 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 11 | 0 | 2026-04-01 | 64
202601-NM25-01098 | GDL17 | Residencial | 7.6 | Period | 2026-03-11 12:09 | March | 2026 | 2026-04-13 15:54 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 33 | 0 | 2026-04-01 | 20
202601-NM25-01100 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:38 | February | 2026 | 2026-02-10 16:18 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 57
202601-NM25-01104 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 14:21 | March | 2026 | 2026-03-09 09:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 25
202601-NM25-01106 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:49 | March | 2026 | 2026-03-12 16:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 22
202601-NM25-01108 | GDL17 | Residencial | 23 | Period | 2026-02-18 10:59 | February | 2026 | 2026-02-25 13:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 42
202601-NM25-01110 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 19:06 | March | 2026 | 2026-03-13 15:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 21
202601-NM25-01111 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:04 | February | 2026 | 2026-03-03 15:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 34
202601-NM25-01113 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:27 | March | 2026 | 2026-03-11 14:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202601-NM25-01114 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 14:12 | February | 2026 | 2026-02-12 13:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-01116 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:49 | January | 2026 | 2026-02-02 10:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-01117 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:35 | March | 2026 | 2026-03-13 12:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 20
202601-NM25-01120 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:17 | January | 2026 | 2026-01-16 11:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-01121 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:25 | January | 2026 | 2026-01-16 11:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-01122 | GDL17 | Residencial | 5.165 | Period | 2026-01-14 08:40 | January | 2026 | 2026-01-15 15:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01125 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 08:35 | January | 2026 | 2026-01-16 13:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-01126 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:21 | February | 2026 | 2026-02-27 11:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 35
202601-NM25-01128 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:39 | January | 2026 | 2026-02-02 08:42 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 19 | 0 | 2026-04-01 | 77
202601-NM25-01129 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 08:37 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 77
202601-NM25-01130 | GDL17 | Residencial | 11.136 | Period | 2026-02-02 09:20 | February | 2026 | 2026-02-04 15:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-01131 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:46 | January | 2026 | 2026-01-15 16:03 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01133 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:55 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 69
202601-NM25-01135 | GDL17 | Residencial | 10.672 | Period | 2026-01-14 08:50 | January | 2026 | 2026-01-15 16:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01136 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 08:54 | January | 2026 | 2026-02-18 08:34 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | February | 2 | 28 | 6 | 2026-04-01 | 77
202601-NM25-01138 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 08:54 | January | 2026 | 2026-01-20 10:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 77
202601-NM25-01139 | GDL17 | Residencial | 5.956 | Period | 2026-01-14 08:57 | January | 2026 | 2026-01-15 11:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01140 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 08:56 | January | 2026 | 2026-01-15 16:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01141 | GDL17 | Residencial | 6.612 | Period | 2026-01-14 09:01 | January | 2026 | 2026-01-15 12:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01142 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:09 | January | 2026 | 2026-01-16 11:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-01143 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:20 | January | 2026 | 2026-01-19 08:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-01144 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 09:21 | January | 2026 | 2026-01-23 08:24 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 9 | 0 | 2026-04-01 | 77
202601-NM25-01145 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 09:08 | January | 2026 | 2026-03-03 15:53 | 48 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March | 1 | 40 | 8 | 2026-04-01 | 77
202601-NM25-01146 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:25 | January | 2026 | 2026-01-15 16:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01147 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:15 | January | 2026 | 2026-02-09 07:47 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 26 | 0 | 2026-04-01 | 77
202601-NM25-01148 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:18 | January | 2026 | 2026-01-19 08:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-01150 | GDL17 | Residencial | 6.317 | Period | 2026-01-14 09:44 | January | 2026 | 2026-01-15 14:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01152 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 09:21 | January | 2026 | 2026-01-15 16:21 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01153 | GDL17 | Residencial | 6.322 | Period | 2026-01-14 09:30 | January | 2026 | 2026-01-15 12:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01154 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 09:29 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 77
202601-NM25-01155 | GDL17 | Residencial | 7.102 | Period | 2026-01-14 09:29 | January | 2026 | 2026-01-15 12:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01158 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 09:41 | January | 2026 | 2026-01-15 16:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01159 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:34 | January | 2026 | 2026-02-04 17:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 61
202601-NM25-01160 | GDL17 | Residencial | 9.368 | Period | 2026-01-14 09:45 | January | 2026 | 2026-01-15 16:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01161 | GDL17 | Residencial | 7.6 | Period | 2026-02-18 07:47 | February | 2026 | 2026-02-24 13:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-01162 | GDL17 | Residencial | 7.026 | Period | 2026-01-14 09:48 | January | 2026 | 2026-01-15 16:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01163 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:54 | January | 2026 | 2026-01-29 08:57 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 71
202601-NM25-01165 | GDL17 | Residencial | 10.482 | Period | 2026-01-14 09:50 | January | 2026 | 2026-01-15 10:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01166 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:00 | January | 2026 | 2026-01-19 14:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 77
202601-NM25-01167 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:55 | March | 2026 | 2026-03-13 16:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 21
202601-NM25-01168 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:39 | February | 2026 | 2026-02-06 13:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-01169 | GDL17 | Residencial | 5.566 | Period | 2026-01-14 10:05 | January | 2026 | 2026-01-16 13:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 77
202601-NM25-01170 | GDL17 | Residencial | 8.972 | Period | 2026-01-14 10:14 | January | 2026 | 2026-01-16 15:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 77
202601-NM25-01171 | GDL17 | Residencial | 12.954 | Period | 2026-01-14 10:05 | January | 2026 | 2026-01-16 15:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 77
202601-NM25-01172 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:07 | January | 2026 | 2026-01-16 13:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 77
202601-NM25-01173 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:15 | January | 2026 | 2026-02-04 07:41 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 77
202601-NM25-01174 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:56 | February | 2026 | 2026-02-25 15:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 39
202601-NM25-01175 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 08:38 | January | 2026 | 2026-01-29 09:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 69
202601-NM25-01176 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 11:05 | January | 2026 | 2026-01-21 15:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-01179 | GDL17 | Residencial | 9.904 | Period | 2026-01-14 10:19 | January | 2026 | 2026-01-15 16:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 1 | 0 | 1 | 2026-04-01 | 77
202601-NM25-01180 | GDL17 | Residencial | 5.772 | Period | 2026-01-14 10:42 | January | 2026 | 2026-01-16 15:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-01181 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 15:12 | February | 2026 | 2026-03-18 11:06 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 21 | 0 | 2026-04-01 | 34
202601-NM25-01182 | GDL17 | Residencial | 11.304 | Period | 2026-01-22 17:33 | January | 2026 | 2026-03-19 14:26 | 56 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March |  | 56 | 0 | 2026-04-01 | 68
202601-NM25-01183 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:29 | January | 2026 | 2026-01-15 11:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01184 | GDL17 | Residencial | 19.1 | Period | 2026-01-20 09:01 | January | 2026 | 2026-01-21 16:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-01185 | GDL17 | Comercial | 11.5 | Period | 2026-01-20 12:25 | January | 2026 | 2026-01-23 15:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 70
202601-NM25-01186 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:43 | January | 2026 | 2026-01-19 10:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-01189 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:51 | January | 2026 | 2026-01-19 14:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-01190 | GDL17 | Residencial | 7.072 | Period | 2026-01-14 11:21 | January | 2026 | 2026-01-15 12:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01191 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 10:56 | January | 2026 | 2026-01-20 15:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 77
202601-NM25-01192 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:54 | January | 2026 | 2026-02-02 15:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-01193 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:09 | January | 2026 | 2026-02-17 08:13 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 65
202601-NM25-01194 | GDL17 | Residencial | 9.662 | Period | 2026-01-14 11:02 | January | 2026 | 2026-01-15 11:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01195 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 11:00 | January | 2026 | 2026-01-23 08:29 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 9 | 0 | 2026-04-01 | 77
202601-NM25-01197 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:56 | January | 2026 | 2026-01-15 13:35 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01198 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:53 | February | 2026 | 2026-02-11 16:01 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 0 | 0 | 2026-04-01 | 49
202601-NM25-01199 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:44 | January | 2026 | 2026-02-17 08:54 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 34 | 0 | 2026-04-01 | 77
202601-NM25-01200 | GDL17 | Residencial | 5.015 | Period | 2026-01-14 11:20 | January | 2026 | 2026-01-15 12:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01201 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:21 | January | 2026 | 2026-01-20 14:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 77
202601-NM25-01202 | GDL17 | Residencial | 6.902 | Period | 2026-01-14 11:21 | January | 2026 | 2026-01-15 10:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 77
202601-NM25-01203 | GDL17 | Comercial | 24.75 | Period | 2026-01-14 11:27 | January | 2026 | 2026-01-19 09:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 77
202601-NM25-01205 | GDL17 | Residencial | 5.76 | Period | 2026-01-19 13:48 | January | 2026 | 2026-01-21 14:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | January | 1 | 1 | 1 | 2026-04-01 | 71
202601-NM25-01206 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:41 | March | 2026 | 2026-03-30 08:15 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 8
202601-NM25-01207 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:03 | January | 2026 | 2026-01-20 14:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01209 | GDL17 | Residencial | 11.492 | Period | 2026-01-14 11:48 | January | 2026 | 2026-01-21 13:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 77
202601-NM25-01210 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:11 | February | 2026 | 2026-03-03 16:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 34
202601-NM25-01211 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:38 | March | 2026 | 2026-03-16 12:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 22
202601-NM25-01212 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 16:50 | January | 2026 | 2026-01-23 14:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-01213 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:55 | January | 2026 | 2026-01-16 09:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 77
202601-NM25-01214 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 11:58 | January | 2026 | 2026-01-21 08:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 77
202601-NM25-01215 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 14:06 | March | 2026 | 2026-03-30 09:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 7
202601-NM25-01216 | GDL17 | Residencial | 3.84 | Period | 2026-01-23 08:27 | January | 2026 | 2026-02-02 15:59 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 10 | 0 | 2026-04-01 | 68
202601-NM25-01217 | GDL17 | Residencial | 4.608 | Period | 2026-01-29 13:39 | January | 2026 | 2026-02-04 13:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 3 | 3 | 2026-04-01 | 61
202601-NM25-01219 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:10 | January | 2026 | 2026-01-16 13:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01220 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 12:07 | January | 2026 | 2026-01-21 14:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 76
202601-NM25-01221 | GDL17 | Residencial | 5.566 | Period | 2026-01-14 12:21 | January | 2026 | 2026-01-15 10:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01222 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:12 | January | 2026 | 2026-01-26 10:53 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 12 | 0 | 2026-04-01 | 76
202601-NM25-01223 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:41 | February | 2026 | 2026-02-17 08:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-01224 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:48 | January | 2026 | 2026-01-16 08:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01225 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 12:22 | January | 2026 | 2026-01-15 13:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01227 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:27 | January | 2026 | 2026-01-16 09:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01228 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 12:26 | January | 2026 | 2026-01-15 14:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01229 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:56 | March | 2026 | 2026-03-17 08:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 22
202601-NM25-01230 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 12:38 | January | 2026 | 2026-01-20 09:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01231 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 15:37 | January | 2026 | 2026-01-30 10:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-01232 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:39 | January | 2026 | 2026-02-04 17:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-01234 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 12:58 | January | 2026 | 2026-01-19 10:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-01235 | GDL17 | Residencial | 23 | Period | 2026-03-04 18:43 | March | 2026 | 2026-03-06 14:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 27
202601-NM25-01236 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:06 | January | 2026 | 2026-01-16 14:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01237 | GDL17 | Residencial | 10.572 | Period | 2026-01-14 13:10 | January | 2026 | 2026-01-15 10:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01238 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 13:14 | January | 2026 | 2026-02-10 14:39 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 5 | 21 | 2026-04-01 | 76
202601-NM25-01239 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:19 | January | 2026 | 2026-01-21 10:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 76
202601-NM25-01240 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:23 | January | 2026 | 2026-01-23 15:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-01241 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:23 | January | 2026 | 2026-01-15 13:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01242 | GDL17 | Residencial | 12 | Period | 2026-01-14 16:13 | January | 2026 | 2026-01-16 16:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01243 | GDL17 | Comercial | 10.33 | Period | 2026-01-14 13:23 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 76
202601-NM25-01244 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:45 | January | 2026 | 2026-01-23 15:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-01247 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 13:31 | January | 2026 | 2026-01-15 14:03 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01248 | GDL17 | Residencial | 7.6 | Period | 2026-03-06 06:37 | March | 2026 | 2026-03-09 16:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 26
202601-NM25-01249 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 13:36 | January | 2026 | 2026-01-22 14:58 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 76
202601-NM25-01251 | GDL17 | Residencial | 8 | Period | 2026-02-19 10:11 | February | 2026 | 2026-02-24 08:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 41
202601-NM25-01252 | GDL17 | Residencial | 7.396 | Period | 2026-01-14 13:37 | January | 2026 | 2026-01-15 14:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01253 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 07:37 | January | 2026 | 2026-01-21 15:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 72
202601-NM25-01254 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:46 | February | 2026 | 2026-02-26 14:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 37
202601-NM25-01255 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:53 | February | 2026 | 2026-02-04 11:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-01256 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 13:46 | January | 2026 | 2026-01-15 14:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01257 | GDL17 | Residencial | 8 | Period | 2026-01-16 12:05 | January | 2026 | 2026-01-27 10:15 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | January | 1 | 6 | 5 | 2026-04-01 | 74
202601-NM25-01259 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:09 | January | 2026 | 2026-01-28 10:54 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 71
202601-NM25-01261 | GDL17 | Residencial | 5.076 | Period | 2026-01-14 13:55 | January | 2026 | 2026-01-15 11:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01262 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:04 | March | 2026 | 2026-03-11 13:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 27
202601-NM25-01263 | GDL17 | Residencial | 11.52 | Period | 2026-01-15 07:37 | January | 2026 | 2026-01-16 14:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01264 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 12:44 | March | 2026 | 2026-04-14 15:08 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | April |  | 25 | 21 | 2026-04-01 | 11
202601-NM25-01266 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 14:04 | January | 2026 | 2026-01-15 15:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01267 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 18:51 | March | 2026 | 2026-03-18 16:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 19
202601-NM25-01268 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:18 | January | 2026 | 2026-01-20 13:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01269 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 12:45 | March | 2026 | 2026-04-02 15:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 0
202601-NM25-01270 | GDL17 | Residencial | 6.912 | Period | 2026-01-14 14:24 | January | 2026 | 2026-01-15 16:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01272 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:45 | February | 2026 | 2026-03-02 09:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202601-NM25-01273 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 08:49 | January | 2026 | 2026-01-29 09:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-01274 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 12:46 | January | 2026 | 2026-01-29 09:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-01276 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:33 | January | 2026 | 2026-01-19 08:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-01278 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 05:51 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 34
202601-NM25-01280 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 08:18 | February | 2026 | 2026-02-11 16:14 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 0 | 0 | 2026-04-01 | 49
202601-NM25-01281 | GDL17 | Residencial | 5.58 | Period | 2026-01-14 14:36 | January | 2026 | 2026-01-16 09:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | January | 1 | 2 | 0 | 2026-04-01 | 76
202601-NM25-01282 | GDL17 | Residencial | 3.8 | Period | 2026-02-20 15:05 | February | 2026 | 2026-02-26 08:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-01283 | GDL17 | Residencial | 9.406 | Period | 2026-01-14 14:41 | January | 2026 | 2026-01-15 15:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01285 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:19 | March | 2026 | 2026-03-10 08:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 27
202601-NM25-01287 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 14:51 | January | 2026 | 2026-01-20 10:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01289 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 11:44 | January | 2026 | 2026-01-26 14:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 71
202601-NM25-01291 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 09:45 | January | 2026 | 2026-02-04 10:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-01294 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 15:19 | January | 2026 | 2026-01-16 13:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01295 | GDL17 | Residencial | 4.236 | Period | 2026-01-14 15:17 | January | 2026 | 2026-01-16 13:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01296 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:19 | January | 2026 | 2026-01-19 09:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-01297 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 17:11 | March | 2026 | 2026-03-16 09:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202601-NM25-01299 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:34 | January | 2026 | 2026-01-22 10:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01300 | GDL17 | Residencial | 10.672 | Period | 2026-01-14 15:22 | January | 2026 | 2026-01-16 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01301 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 09:17 | January | 2026 | 2026-02-04 10:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-01302 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:06 | January | 2026 | 2026-01-28 08:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 67
202601-NM25-01303 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:04 | February | 2026 | 2026-03-02 09:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202601-NM25-01304 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:31 | February | 2026 | 2026-03-03 14:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202601-NM25-01305 | GDL17 | Residencial | 7.68 | Period | 2026-01-14 15:30 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 76
202601-NM25-01306 | GDL17 | Residencial | 5.376 | Period | 2026-01-26 12:42 | January | 2026 | 2026-01-28 15:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-01307 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:45 | January | 2026 | 2026-02-03 13:26 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 20 | 0 | 2026-04-01 | 76
202601-NM25-01309 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 15:47 | January | 2026 | 2026-01-16 14:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01310 | GDL17 | Residencial | 7.87 | Period | 2026-01-14 15:48 | January | 2026 | 2026-01-16 08:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01311 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 15:33 | January | 2026 | 2026-02-27 14:37 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | February |  | 42 | 0 | 2026-04-01 | 74
202601-NM25-01312 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 14:11 | January | 2026 | 2026-01-19 13:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01314 | GDL17 | Residencial | 7.6 | Period | 2026-02-27 10:14 | February | 2026 | 2026-03-11 07:59 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 12 | 0 | 2026-04-01 | 33
202601-NM25-01315 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:51 | January | 2026 | 2026-01-19 10:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01316 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:01 | January | 2026 | 2026-01-16 15:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01317 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:10 | January | 2026 | 2026-01-21 12:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01318 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:15 | January | 2026 | 2026-02-18 14:48 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | February |  | 35 | 0 | 2026-04-01 | 76
202601-NM25-01319 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:13 | January | 2026 | 2026-01-20 14:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01320 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 16:21 | January | 2026 | 2026-01-16 16:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01321 | GDL17 | Residencial | 7.866 | Period | 2026-01-19 10:47 | January | 2026 | 2026-01-20 15:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01322 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:28 | January | 2026 | 2026-01-19 13:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-01323 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:31 | January | 2026 | 2026-01-16 10:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01324 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 16:34 | January | 2026 | 2026-01-21 16:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 76
202601-NM25-01325 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:45 | January | 2026 | 2026-01-20 10:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-01327 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 16:53 | January | 2026 | 2026-01-16 15:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01328 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 16:45 | January | 2026 | 2026-01-19 14:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-01329 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 17:08 | January | 2026 | 2026-01-19 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-01330 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 17:32 | January | 2026 | 2026-01-22 13:51 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 8 | 0 | 2026-04-01 | 76
202601-NM25-01331 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 17:14 | January | 2026 | 2026-01-23 09:30 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 8 | 0 | 2026-04-01 | 76
202601-NM25-01332 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 11:12 | March | 2026 | 2026-03-20 08:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 16
202601-NM25-01333 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 18:17 | January | 2026 | 2026-01-16 13:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 76
202601-NM25-01334 | GDL17 | Residencial | 11.5 | Period | 2026-01-14 17:43 | January | 2026 | 2026-01-20 13:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01336 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 17:35 | February | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 48
202601-NM25-01337 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 17:52 | January | 2026 | 2026-01-19 14:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-01339 | GDL17 | Residencial | 3.8 | Period | 2026-01-21 09:09 | January | 2026 | 2026-01-22 10:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-01340 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 12:59 | March | 2026 | 2026-03-25 13:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 12
202601-NM25-01341 | GDL17 | Residencial | 7.6 | Period | 2026-01-14 18:07 | January | 2026 | 2026-01-20 09:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 76
202601-NM25-01346 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:58 | January | 2026 | 2026-01-19 10:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-01347 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:50 | February | 2026 | 2026-02-10 16:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-01350 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 18:35 | February | 2026 | 2026-03-04 08:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202601-NM25-01352 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:02 | February | 2026 | 2026-03-12 16:22 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 35 | 0 | 2026-04-01 | 54
202601-NM25-01354 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:13 | March | 2026 | 2026-03-05 09:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 28
202601-NM25-01355 | GDL17 | Residencial | 8 | Period | 2026-02-03 12:14 | February | 2026 | 2026-02-05 12:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-01358 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:23 | January | 2026 | 2026-01-26 12:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-01359 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 08:10 | February | 2026 | 2026-03-04 16:24 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 22 | 0 | 2026-04-01 | 50
202601-NM25-01360 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:16 | January | 2026 | 2026-01-30 08:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-01361 | GDL17 | Residencial | 3.84 | Period | 2026-01-30 15:28 | January | 2026 | 2026-02-05 13:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 60
202601-NM25-01363 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:16 | February | 2026 | 2026-02-06 13:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-01366 | GDL17 | Residencial | 15.34 | Period | 2026-02-25 09:37 | February | 2026 | 2026-02-27 10:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 35
202601-NM25-01367 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:01 | January | 2026 | 2026-01-26 13:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-01370 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 08:46 | January | 2026 | 2026-01-16 14:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01371 | GDL17 | Residencial | 5.196 | Period | 2026-01-15 09:17 | January | 2026 | 2026-02-02 15:01 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 76
202601-NM25-01372 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 08:54 | January | 2026 | 2026-01-16 13:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01373 | GDL17 | Residencial | 7.6 | Period | 2026-03-11 07:46 | March | 2026 | 2026-03-16 13:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 21
202601-NM25-01375 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:57 | February | 2026 | 2026-02-16 14:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-01376 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:22 | January | 2026 | 2026-01-19 12:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-01377 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:08 | January | 2026 | 2026-01-19 12:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-01378 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:07 | January | 2026 | 2026-01-19 07:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-01379 | GDL17 | Residencial | 15.5 | Period | 2026-03-04 16:45 | March | 2026 | 2026-03-06 09:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 27
202601-NM25-01380 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:18 | January | 2026 | 2026-01-16 14:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01381 | GDL17 | Residencial | 7.6 | Period | 2026-03-10 07:28 | March | 2026 | 2026-03-12 14:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 22
202601-NM25-01382 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 06:32 | February | 2026 | 2026-02-25 13:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202601-NM25-01383 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:54 | February | 2026 | 2026-02-10 12:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 55
202601-NM25-01384 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:23 | March | 2026 | 2026-03-25 16:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 8
202601-NM25-01385 | GDL17 | Residencial | 6.33 | Period | 2026-01-15 09:34 | January | 2026 | 2026-01-20 13:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 76
202601-NM25-01386 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:50 | February | 2026 | 2026-02-05 11:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-01387 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:43 | January | 2026 | 2026-01-16 15:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01389 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 09:45 | January | 2026 | 2026-01-16 14:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01391 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:31 | January | 2026 | 2026-01-19 13:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-01393 | GDL17 | Residencial | 8 | Period | 2026-02-19 09:48 | February | 2026 | 2026-02-24 08:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 41
202601-NM25-01394 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:30 | February | 2026 | 2026-02-12 09:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-01397 | GDL17 | Residencial | 8 | Period | 2026-02-18 13:10 | February | 2026 | 2026-02-27 09:15 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 41
202601-NM25-01400 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:17 | January | 2026 | 2026-01-30 10:03 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 69
202601-NM25-01402 | GDL17 | Residencial | 18.67 | Period | 2026-02-06 08:36 | February | 2026 | 2026-02-10 14:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-01403 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:42 | January | 2026 | 2026-01-29 09:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-01404 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:46 | January | 2026 | 2026-01-22 07:39 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 76
202601-NM25-01405 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 10:02 | January | 2026 | 2026-01-16 15:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01406 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:37 | February | 2026 | 2026-02-11 09:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-01408 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 06:25 | March | 2026 | 2026-03-23 08:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 15
202601-NM25-01409 | GDL17 | Residencial | 7 | Period | 2026-02-17 11:04 | February | 2026 | 2026-02-24 10:17 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 43
202601-NM25-01410 | GDL17 | Comercial | 11.5 | Period | 2026-01-22 14:24 | January | 2026 | 2026-01-23 11:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-01411 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:34 | January | 2026 | 2026-01-16 15:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01412 | GDL17 | Residencial | 6 | Period | 2026-02-25 09:37 | February | 2026 | 2026-03-02 16:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 35
202601-NM25-01413 | GDL17 | Residencial | 13.44 | Period | 2026-01-28 10:08 | January | 2026 | 2026-01-30 16:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-01415 | GDL17 | Comercial | 7.6 | Period | 2026-01-28 11:39 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 63
202601-NM25-01416 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:11 | March | 2026 | 2026-03-06 13:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 26
202601-NM25-01417 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:33 | January | 2026 | 2026-02-03 15:22 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 68
202601-NM25-01418 | GDL17 | Residencial | 8 | Period | 2026-01-23 14:28 | January | 2026 | 2026-01-29 09:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 67
202601-NM25-01420 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 10:49 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 76
202601-NM25-01421 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:45 | January | 2026 | 2026-01-19 15:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01422 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:35 | February | 2026 | 2026-02-24 13:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 42
202601-NM25-01423 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:13 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 76
202601-NM25-01425 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:41 | March | 2026 | 2026-03-17 07:57 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 6 | 8 | 2026-04-01 | 28
202601-NM25-01426 | GDL17 | Residencial | 7.6 | Period | 2026-03-19 06:20 | March | 2026 | 2026-04-08 15:15 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | April |  | 20 | 0 | 2026-04-01 | 13
202601-NM25-01427 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 13:53 | January | 2026 | 2026-01-19 10:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01429 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:51 | January | 2026 | 2026-01-19 08:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 76
202601-NM25-01430 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:28 | February | 2026 | 2026-02-27 15:08 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 39
202601-NM25-01431 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:06 | January | 2026 | 2026-01-21 11:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-01433 | GDL17 | Residencial | 4.224 | Period | 2026-01-15 11:41 | January | 2026 | 2026-03-05 09:33 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 49 | 0 | 2026-04-01 | 76
202601-NM25-01434 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 19:31 | February | 2026 | 2026-02-25 09:19 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 43
202601-NM25-01435 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:45 | February | 2026 | 2026-02-27 07:46 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 41
202601-NM25-01436 | GDL17 | Residencial | 7.68 | Period | 2026-02-03 11:54 | February | 2026 | 2026-02-05 14:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-01437 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 09:27 | March | 2026 | 2026-03-18 09:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 19
202601-NM25-01438 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:00 | January | 2026 | 2026-01-19 12:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01439 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:27 | January | 2026 | 2026-02-10 12:51 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 71
202601-NM25-01440 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 11:58 | January | 2026 | 2026-01-16 15:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 76
202601-NM25-01441 | GDL17 | Comercial | 11.5 | Period | 2026-02-11 08:23 | February | 2026 | 2026-02-16 09:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 49
202601-NM25-01442 | GDL17 | Residencial | 12 | Period | 2026-01-16 08:43 | January | 2026 | 2026-01-19 13:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01443 | GDL17 | Residencial | 9 | Period | 2026-01-19 09:22 | January | 2026 | 2026-01-22 13:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 72
202601-NM25-01444 | GDL17 | Comercial | 11.5 | Period | 2026-03-17 12:36 | March | 2026 | 2026-03-18 15:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 14
202601-NM25-01445 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 18:03 | March | 2026 | 2026-03-18 15:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 14
202601-NM25-01446 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 16:57 | February | 2026 | 2026-03-02 07:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202601-NM25-01447 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:17 | January | 2026 | 2026-01-19 09:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01448 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:12 | January | 2026 | 2026-01-19 12:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01449 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:31 | January | 2026 | 2026-01-16 14:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 75
202601-NM25-01450 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 14:35 | January | 2026 | 2026-01-30 16:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 64
202601-NM25-01451 | GDL17 | Residencial | 8 | Period | 2026-01-23 12:55 | January | 2026 | 2026-01-26 11:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-01452 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 12:43 | January | 2026 | 2026-01-22 15:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 75
202601-NM25-01453 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 15:23 | February | 2026 | 2026-02-12 09:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 49
202601-NM25-01456 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:39 | January | 2026 | 2026-01-23 11:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-01457 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:46 | January | 2026 | 2026-01-19 10:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01458 | GDL17 | Residencial | 4.992 | Period | 2026-01-15 13:07 | January | 2026 | 2026-01-23 16:12 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 75
202601-NM25-01459 | GDL17 | Residencial | 8 | Period | 2026-01-23 11:11 | January | 2026 | 2026-01-26 11:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-01460 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:03 | January | 2026 | 2026-02-03 12:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-01461 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 14:49 | January | 2026 | 2026-02-10 08:26 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 12 | 0 | 2026-04-01 | 62
202601-NM25-01462 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:22 | January | 2026 | 2026-01-19 14:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01463 | GDL17 | Residencial | 24 | Period | 2026-01-15 14:13 | January | 2026 | 2026-01-19 14:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01464 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:24 | January | 2026 | 2026-01-23 12:55 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 75
202601-NM25-01465 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:21 | March | 2026 | 2026-03-06 09:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 27
202601-NM25-01466 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:38 | January | 2026 | 2026-02-16 13:40 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 19 | 0 | 2026-04-01 | 62
202601-NM25-01469 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:16 | January | 2026 | 2026-01-29 10:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-01470 | GDL17 | Residencial | 4.992 | Period | 2026-01-15 13:36 | January | 2026 | 2026-01-20 13:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-01472 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:34 | February | 2026 | 2026-02-05 10:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-01473 | GDL17 | Residencial | 23 | Period | 2026-01-23 09:05 | January | 2026 | 2026-01-26 11:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-01474 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 13:59 | January | 2026 | 2026-01-19 16:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01476 | GDL17 | Residencial | 2.688 | Period | 2026-01-16 08:05 | January | 2026 | 2026-02-03 16:28 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 75
202601-NM25-01477 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 07:54 | January | 2026 | 2026-01-19 12:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01478 | GDL17 | Residencial | 6.8 | Period | 2026-02-04 22:53 | February | 2026 | 2026-02-09 09:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-01479 | GDL17 | Residencial | 7.332 | Period | 2026-01-15 15:16 | January | 2026 | 2026-01-19 13:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01481 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 09:36 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 72
202601-NM25-01483 | GDL17 | Residencial | 6.912 | Period | 2026-02-18 09:24 | February | 2026 | 2026-02-26 15:53 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 42
202601-NM25-01484 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:23 | January | 2026 | 2026-01-29 08:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-01485 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:13 | January | 2026 | 2026-01-29 08:15 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 14 | 0 | 2026-04-01 | 75
202601-NM25-01486 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 16:37 | February | 2026 | 2026-02-12 13:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 53
202601-NM25-01487 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:37 | January | 2026 | 2026-01-19 14:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01488 | GDL17 | Residencial | 9 | Period | 2026-02-04 14:18 | February | 2026 | 2026-02-06 16:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 55
202601-NM25-01490 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 13:52 | February | 2026 | 2026-02-12 13:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-01491 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:17 | January | 2026 | 2026-01-20 10:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01492 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 14:19 | March | 2026 | 2026-03-11 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 22
202601-NM25-01493 | GDL17 | Residencial | 23 | Period | 2026-01-15 14:29 | January | 2026 | 2026-01-19 14:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01494 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:39 | January | 2026 | 2026-01-19 13:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01495 | GDL17 | Residencial | 7.6 | Period | 2026-03-11 09:22 | March | 2026 | 2026-03-16 16:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 21
202601-NM25-01496 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:48 | March | 2026 | 2026-04-06 13:29 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 35 | 0 | 2026-04-01 | 30
202601-NM25-01497 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 11:29 | January | 2026 | 2026-02-10 10:40 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 11 | 0 | 2026-04-01 | 61
202601-NM25-01498 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:33 | January | 2026 | 2026-02-02 13:07 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 17 | 0 | 2026-04-01 | 74
202601-NM25-01499 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:05 | January | 2026 | 2026-01-22 12:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 75
202601-NM25-01500 | GDL17 | Residencial | 3.456 | Period | 2026-01-15 15:19 | January | 2026 | 2026-01-21 15:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 75
202601-NM25-01501 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:45 | January | 2026 | 2026-01-19 12:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01502 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:46 | January | 2026 | 2026-01-20 09:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01503 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 00:06 | February | 2026 | 2026-03-03 11:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202601-NM25-01504 | GDL17 | Residencial | 6.49 | Period | 2026-01-15 14:45 | January | 2026 | 2026-01-19 09:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01505 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 14:43 | January | 2026 | 2026-01-19 12:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01506 | GDL17 | Residencial | 23 | Period | 2026-02-27 17:55 | February | 2026 | 2026-03-25 15:10 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 6 | 20 | 2026-04-01 | 32
202601-NM25-01507 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 10:29 | February | 2026 | 2026-02-04 13:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-01509 | GDL17 | Residencial | 2.5 | Period | 2026-01-15 15:51 | January | 2026 | 2026-01-20 07:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-01510 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:01 | January | 2026 | 2026-02-13 07:53 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 16 | 0 | 2026-04-01 | 63
202601-NM25-01511 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:06 | January | 2026 | 2026-02-23 14:46 | 39 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | February |  | 39 | 0 | 2026-04-01 | 75
202601-NM25-01512 | GDL17 | Residencial | 8.64 | Period | 2026-01-15 15:18 | January | 2026 | 2026-01-19 13:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01513 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:31 | February | 2026 | 2026-02-10 07:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202601-NM25-01515 | GDL17 | Residencial | 3.84 | Period | 2026-02-20 13:24 | February | 2026 | 2026-03-04 14:05 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 39
202601-NM25-01516 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:36 | January | 2026 | 2026-01-26 10:48 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 11 | 0 | 2026-04-01 | 75
202601-NM25-01517 | GDL17 | Residencial | 4.608 | Period | 2026-02-04 08:21 | February | 2026 | 2026-02-12 13:05 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 9 | 0 | 2026-04-01 | 56
202601-NM25-01518 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:29 | January | 2026 | 2026-02-03 08:18 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 19 | 0 | 2026-04-01 | 75
202601-NM25-01519 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:43 | January | 2026 | 2026-01-22 13:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 75
202601-NM25-01520 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:58 | January | 2026 | 2026-01-28 14:51 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 12 | 0 | 2026-04-01 | 74
202601-NM25-01521 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 12:30 | March | 2026 | 2026-03-23 14:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 4 | 2 | 2026-04-01 | 14
202601-NM25-01522 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 22:36 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 29
202601-NM25-01523 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:47 | January | 2026 | 2026-01-23 15:49 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 75
202601-NM25-01524 | GDL17 | Residencial | 12 | Period | 2026-01-15 16:56 | January | 2026 | 2026-01-19 15:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01525 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:03 | March | 2026 | 2026-03-12 15:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 22
202601-NM25-01526 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:48 | January | 2026 | 2026-01-19 11:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01527 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 15:44 | January | 2026 | 2026-01-19 09:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01528 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 16:22 | January | 2026 | 2026-02-10 10:43 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 26 | 0 | 2026-04-01 | 75
202601-NM25-01529 | GDL17 | Residencial | 5.926 | Period | 2026-01-15 15:50 | January | 2026 | 2026-01-19 09:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01530 | GDL17 | Comercial | 11.5 | Period | 2026-01-16 15:09 | January | 2026 | 2026-01-20 08:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01531 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 16:10 | January | 2026 | 2026-01-19 13:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01533 | GDL17 | Residencial | 5.566 | Period | 2026-01-15 16:04 | January | 2026 | 2026-01-19 10:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01534 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 16:36 | January | 2026 | 2026-01-19 08:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01535 | GDL17 | Comercial | 8 | Period | 2026-01-21 16:24 | January | 2026 | 2026-01-23 10:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-01536 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 16:08 | January | 2026 | 2026-01-19 15:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01537 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 16:21 | January | 2026 | 2026-01-23 10:59 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 75
202601-NM25-01538 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 16:38 | January | 2026 | 2026-01-28 12:56 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 13 | 0 | 2026-04-01 | 75
202601-NM25-01539 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 14:12 | February | 2026 | 2026-02-12 13:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-01540 | GDL17 | Residencial | 7.68 | Period | 2026-02-13 10:24 | February | 2026 | 2026-02-18 15:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 47
202601-NM25-01541 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 10:47 | January | 2026 | 2026-01-26 15:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-01542 | GDL17 | Residencial | 11.5 | Period | 2026-01-15 16:44 | January | 2026 | 2026-03-04 13:48 | 48 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 48 | 0 | 2026-04-01 | 75
202601-NM25-01543 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 11:18 | February | 2026 | 2026-02-09 16:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-01544 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 12:29 | January | 2026 | 2026-01-26 11:03 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 10 | 0 | 2026-04-01 | 74
202601-NM25-01545 | GDL17 | Residencial | 7.68 | Period | 2026-01-27 18:13 | January | 2026 | 2026-02-06 11:24 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 2 | 8 | 2026-04-01 | 63
202601-NM25-01546 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 14:31 | January | 2026 | 2026-01-26 13:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-01547 | GDL17 | Residencial | 7.68 | Period | 2026-03-05 07:47 | March | 2026 | 2026-03-12 12:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 27
202601-NM25-01548 | GDL17 | Residencial | 7.68 | Period | 2026-02-17 09:25 | February | 2026 | 2026-02-20 16:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 43
202601-NM25-01549 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 17:02 | January | 2026 | 2026-01-19 15:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01551 | GDL17 | Residencial | 7.6 | Period | 2026-01-15 18:32 | January | 2026 | 2026-01-19 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01552 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:49 | March | 2026 | 2026-03-25 15:34 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 4 | 19 | 2026-04-01 | 29
202601-NM25-01553 | GDL17 | Residencial | 10.752 | Period | 2026-03-05 16:12 | March | 2026 | 2026-03-17 07:58 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 11 | 0 | 2026-04-01 | 26
202601-NM25-01554 | GDL17 | Residencial | 23 | Period | 2026-02-27 18:22 | February | 2026 | 2026-03-04 08:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 32
202601-NM25-01556 | GDL17 | Residencial | 23 | Period | 2026-01-29 14:42 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 61
202601-NM25-01557 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:14 | March | 2026 | 2026-04-23 12:46 | 50 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 50 | 0 | 2026-04-01 | 27
202601-NM25-01560 | GDL17 | Residencial | 9 | Period | 2026-01-20 16:04 | January | 2026 | 2026-01-22 13:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-01561 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:11 | March | 2026 | 2026-03-16 14:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 19
202601-NM25-01565 | GDL17 | Comercial | 20 | Period | 2026-01-29 07:36 | January | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 62
202601-NM25-01569 | GDL17 | Residencial | 5.76 | Period | 2026-02-03 09:18 | February | 2026 | 2026-02-09 09:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 57
202601-NM25-01570 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:04 | January | 2026 | 2026-01-22 13:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-01572 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 07:59 | January | 2026 | 2026-01-19 15:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01575 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:21 | February | 2026 | 2026-02-19 10:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 43
202601-NM25-01577 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:01 | January | 2026 | 2026-01-28 10:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-01578 | GDL17 | Residencial | 5 | Period | 2026-01-25 20:29 | January | 2026 | 2026-01-26 15:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 0 | 0 | 2026-04-01 | 65
202601-NM25-01584 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 08:59 | January | 2026 | 2026-01-21 13:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-01585 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 21:34 | January | 2026 | 2026-02-04 15:21 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 69
202601-NM25-01590 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 09:08 | January | 2026 | 2026-01-19 15:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01591 | GDL17 | Residencial | 4.224 | Period | 2026-01-29 14:06 | January | 2026 | 2026-02-02 14:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-01593 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 13:15 | February | 2026 | 2026-02-09 08:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 56
202601-NM25-01595 | GDL17 | Residencial | 4.224 | Period | 2026-01-30 09:36 | January | 2026 | 2026-02-03 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-01596 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:36 | March | 2026 | 2026-03-13 15:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 21
202601-NM25-01597 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:31 | February | 2026 | 2026-02-09 10:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-01599 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:24 | February | 2026 | 2026-02-05 15:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-01600 | GDL17 | Residencial | 6.912 | Period | 2026-02-02 09:38 | February | 2026 | 2026-02-04 11:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-01603 | GDL17 | Residencial | 15 | Period | 2026-01-19 19:57 | January | 2026 | 2026-02-03 09:35 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 12 | 3 | 2026-04-01 | 71
202601-NM25-01604 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:59 | February | 2026 | 2026-02-10 14:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-01607 | GDL17 | Residencial | 5.76 | Period | 2026-01-30 14:11 | January | 2026 | 2026-02-05 10:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 60
202601-NM25-01608 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 10:38 | March | 2026 | 2026-03-17 13:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 16
202601-NM25-01609 | GDL17 | Residencial | 23 | Period | 2026-02-03 13:09 | February | 2026 | 2026-02-05 13:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-01610 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 08:31 | January | 2026 | 2026-02-11 09:03 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 13 | 0 | 2026-04-01 | 62
202601-NM25-01611 | GDL17 | Residencial | 3.8 | Period | 2026-01-19 10:26 | January | 2026 | 2026-03-10 14:05 | 50 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 50 | 0 | 2026-04-01 | 72
202601-NM25-01612 | GDL17 | Residencial | 15 | Period | 2026-01-27 17:10 | January | 2026 | 2026-02-16 14:33 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 20 | 0 | 2026-04-01 | 63
202601-NM25-01614 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:01 | February | 2026 | 2026-03-26 15:58 | 48 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 48 | 0 | 2026-04-01 | 53
202601-NM25-01615 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 15:52 | February | 2026 | 2026-02-10 09:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 53
202601-NM25-01616 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 09:53 | March | 2026 | 2026-03-18 14:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-01617 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:31 | February | 2026 | 2026-03-03 11:15 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 4 | 3 | 2026-04-01 | 35
202601-NM25-01618 | GDL17 | Residencial | 8.448 | Period | 2026-03-02 13:44 | March | 2026 | 2026-03-04 09:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 29
202601-NM25-01619 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:43 | January | 2026 | 2026-01-29 15:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-01620 | GDL17 | Residencial | 3.84 | Period | 2026-01-27 15:22 | January | 2026 | 2026-01-29 14:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-01621 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 15:46 | January | 2026 | 2026-02-04 17:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-01622 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:24 | January | 2026 | 2026-02-11 08:05 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 64
202601-NM25-01625 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:43 | March | 2026 | 2026-03-06 15:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 26
202601-NM25-01626 | GDL17 | Residencial | 23 | Period | 2026-03-02 14:01 | March | 2026 | 2026-03-04 15:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202601-NM25-01627 | GDL17 | Residencial | 7.68 | Period | 2026-02-03 13:37 | February | 2026 | 2026-02-05 14:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-01628 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:17 | February | 2026 | 2026-02-13 10:38 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 10 | 0 | 2026-04-01 | 57
202601-NM25-01630 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:51 | February | 2026 | 2026-02-06 10:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 57
202601-NM25-01631 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:44 | January | 2026 | 2026-01-20 14:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01632 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:10 | January | 2026 | 2026-01-22 14:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 75
202601-NM25-01634 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 10:58 | January | 2026 | 2026-01-20 16:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01635 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 11:57 | March | 2026 | 2026-03-19 07:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-01636 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:46 | January | 2026 | 2026-02-26 08:47 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 30 | 0 | 2026-04-01 | 63
202601-NM25-01637 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:25 | March | 2026 | 2026-03-13 13:39 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 29
202601-NM25-01638 | GDL17 | Residencial | 9 | Period | 2026-02-02 17:20 | February | 2026 | 2026-02-05 16:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202601-NM25-01639 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:23 | January | 2026 | 2026-01-20 07:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01640 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:22 | January | 2026 | 2026-01-19 15:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01641 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:54 | January | 2026 | 2026-02-03 10:41 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 67
202601-NM25-01642 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:19 | January | 2026 | 2026-01-22 10:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-01643 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:29 | January | 2026 | 2026-01-19 12:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01644 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:38 | January | 2026 | 2026-01-20 13:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 75
202601-NM25-01645 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:03 | March | 2026 | 2026-03-23 11:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 14
202601-NM25-01646 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:36 | January | 2026 | 2026-01-21 08:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 75
202601-NM25-01647 | GDL17 | Residencial | 5.196 | Period | 2026-01-16 11:38 | January | 2026 | 2026-01-19 10:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01648 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:41 | January | 2026 | 2026-01-26 13:32 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 10 | 0 | 2026-04-01 | 75
202601-NM25-01649 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 15:53 | February | 2026 | 2026-02-11 08:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-01651 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:44 | January | 2026 | 2026-01-19 15:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01652 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:26 | January | 2026 | 2026-01-22 13:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-01653 | GDL17 | Residencial | 5.494 | Period | 2026-01-16 12:07 | January | 2026 | 2026-01-19 10:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01656 | GDL17 | Residencial | 11.4 | Period | 2026-01-19 21:25 | January | 2026 | 2026-01-21 10:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01657 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:52 | January | 2026 | 2026-01-19 13:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 75
202601-NM25-01658 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:54 | January | 2026 | 2026-01-22 14:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-01659 | GDL17 | Residencial | 25 | Period | 2026-03-10 10:26 | March | 2026 | 2026-03-12 15:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 22
202601-NM25-01660 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:50 | January | 2026 | 2026-01-30 11:11 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 14 | 0 | 2026-04-01 | 75
202601-NM25-01661 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 11:54 | January | 2026 | 2026-01-26 14:42 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 75
202601-NM25-01662 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:03 | January | 2026 | 2026-01-20 08:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01663 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:44 | February | 2026 | 2026-02-12 13:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-01665 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 16:26 | January | 2026 | 2026-01-29 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-01666 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:03 | January | 2026 | 2026-01-26 11:05 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 10 | 0 | 2026-04-01 | 74
202601-NM25-01667 | GDL17 | Residencial | 15.2 | Period | 2026-01-29 08:02 | January | 2026 | 2026-02-06 15:19 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 62
202601-NM25-01668 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:20 | January | 2026 | 2026-01-19 12:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01669 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:07 | January | 2026 | 2026-01-26 09:38 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 9 | 0 | 2026-04-01 | 74
202601-NM25-01671 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:23 | March | 2026 | 2026-03-19 13:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 14
202601-NM25-01672 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:30 | January | 2026 | 2026-01-19 14:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01673 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 12:16 | January | 2026 | 2026-01-29 09:50 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 12 | 0 | 2026-04-01 | 74
202601-NM25-01674 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:15 | January | 2026 | 2026-01-19 15:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01675 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 17:14 | February | 2026 | 2026-03-02 10:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202601-NM25-01676 | GDL17 | Residencial | 10.04 | Period | 2026-01-16 13:17 | January | 2026 | 2026-01-20 09:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01678 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:28 | January | 2026 | 2026-01-21 12:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 74
202601-NM25-01679 | GDL17 | Residencial | 5 | Period | 2026-01-19 10:51 | January | 2026 | 2026-01-20 15:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01681 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:16 | March | 2026 | 2026-03-19 08:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 14
202601-NM25-01682 | GDL17 | Residencial | 5.76 | Period | 2026-03-05 13:36 | March | 2026 | 2026-03-06 14:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 26
202601-NM25-01683 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:36 | January | 2026 | 2026-01-23 13:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 7 | 0 | 2026-04-01 | 74
202601-NM25-01684 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:40 | January | 2026 | 2026-01-19 10:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01685 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:48 | January | 2026 | 2026-01-23 13:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 74
202601-NM25-01686 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:41 | January | 2026 | 2026-01-26 13:41 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 10 | 0 | 2026-04-01 | 74
202601-NM25-01687 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:49 | January | 2026 | 2026-01-19 14:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01688 | GDL17 | Residencial | 5.76 | Period | 2026-02-24 14:11 | February | 2026 | 2026-03-03 13:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 35
202601-NM25-01690 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 16:53 | January | 2026 | 2026-01-22 10:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-01691 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:46 | March | 2026 | 2026-03-23 14:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 15
202601-NM25-01692 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 12:55 | January | 2026 | 2026-01-19 11:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01694 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 11:40 | March | 2026 | 2026-03-18 15:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-01695 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 21:13 | January | 2026 | 2026-02-02 13:18 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 71
202601-NM25-01697 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 13:01 | January | 2026 | 2026-01-20 13:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01698 | GDL17 | Residencial | 8 | Period | 2026-01-16 14:07 | January | 2026 | 2026-01-21 15:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 74
202601-NM25-01699 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:07 | January | 2026 | 2026-01-22 10:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 74
202601-NM25-01700 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:08 | January | 2026 | 2026-01-30 11:26 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 14 | 0 | 2026-04-01 | 74
202601-NM25-01701 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:14 | January | 2026 | 2026-01-20 14:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01703 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 13:55 | January | 2026 | 2026-01-23 08:54 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 74
202601-NM25-01705 | GDL17 | Residencial | 3.84 | Period | 2026-01-16 13:41 | January | 2026 | 2026-01-20 14:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01706 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:34 | January | 2026 | 2026-01-26 16:13 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 10 | 0 | 2026-04-01 | 74
202601-NM25-01707 | GDL17 | Residencial | 7.832 | Period | 2026-01-16 13:36 | January | 2026 | 2026-01-20 10:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01708 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:58 | March | 2026 | 2026-03-12 07:47 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 27
202601-NM25-01709 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:44 | January | 2026 | 2026-02-03 13:33 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 63
202601-NM25-01710 | GDL17 | Residencial | 7.6 | Period | 2026-03-02 14:24 | March | 2026 | 2026-03-04 13:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 29
202601-NM25-01711 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:48 | February | 2026 | 2026-02-10 09:38 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 56
202601-NM25-01712 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:53 | January | 2026 | 2026-02-04 16:07 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 19 | 0 | 2026-04-01 | 74
202601-NM25-01713 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:52 | February | 2026 | 2026-02-10 08:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-01716 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 15:36 | March | 2026 | 2026-03-24 08:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 13
202601-NM25-01718 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 13:52 | January | 2026 | 2026-01-22 13:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 74
202601-NM25-01719 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 18:48 | February | 2026 | 2026-03-03 09:48 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 20 | 0 | 2026-04-01 | 49
202601-NM25-01720 | GDL17 | Residencial | 10 | Period | 2026-01-16 15:23 | January | 2026 | 2026-01-20 10:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01722 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:35 | January | 2026 | 2026-02-12 08:43 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 15 | 0 | 2026-04-01 | 63
202601-NM25-01723 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 13:37 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 20
202601-NM25-01724 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 07:25 | March | 2026 | 2026-03-06 13:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 27
202601-NM25-01725 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:47 | February | 2026 | 2026-02-10 14:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-01726 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:28 | January | 2026 | 2026-01-29 08:57 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 13 | 0 | 2026-04-01 | 74
202601-NM25-01727 | GDL17 | Residencial | 13.036 | Period | 2026-01-16 14:26 | January | 2026 | 2026-03-02 10:16 | 45 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March | 2 | 25 | 18 | 2026-04-01 | 74
202601-NM25-01729 | GDL17 | Residencial | 23 | Period | 2026-02-23 17:10 | February | 2026 | 2026-03-03 13:15 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 36
202601-NM25-01730 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 10:40 | March | 2026 | 2026-03-27 15:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 10 | 0 | 2026-04-01 | 15
202601-NM25-01731 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:41 | January | 2026 | 2026-01-19 14:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01733 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:49 | March | 2026 | 2026-03-06 14:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 27
202601-NM25-01734 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:51 | January | 2026 | 2026-01-20 09:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01735 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 14:55 | January | 2026 | 2026-01-29 08:45 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 13 | 0 | 2026-04-01 | 74
202601-NM25-01737 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 09:19 | March | 2026 | 2026-04-08 08:23 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 8 | 0 | 2026-04-01 | 1
202601-NM25-01738 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 15:15 | January | 2026 | 2026-03-05 15:29 | 48 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 48 | 0 | 2026-04-01 | 74
202601-NM25-01739 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 15:53 | January | 2026 | 2026-01-26 10:59 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 10 | 0 | 2026-04-01 | 74
202601-NM25-01740 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 15:19 | January | 2026 | 2026-01-20 10:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01741 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 15:33 | January | 2026 | 2026-02-03 16:12 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 74
202601-NM25-01743 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 15:49 | January | 2026 | 2026-01-20 13:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01744 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 15:52 | January | 2026 | 2026-01-19 15:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01745 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 16:10 | January | 2026 | 2026-01-21 14:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 74
202601-NM25-01746 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 16:08 | January | 2026 | 2026-01-20 14:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01747 | GDL17 | Residencial | 7.6 | Period | 2026-01-16 16:10 | January | 2026 | 2026-01-20 14:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01748 | GDL17 | Residencial | 4.536 | Period | 2026-01-16 16:23 | January | 2026 | 2026-01-20 10:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01749 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 16:22 | January | 2026 | 2026-01-20 11:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01750 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 16:39 | January | 2026 | 2026-01-20 10:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01751 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 16:35 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 74
202601-NM25-01752 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 16:49 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 74
202601-NM25-01753 | GDL17 | Residencial | 4.786 | Period | 2026-01-16 16:46 | January | 2026 | 2026-01-20 10:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01754 | GDL17 | Residencial | 12 | Period | 2026-01-21 16:18 | January | 2026 | 2026-01-23 10:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-01755 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 17:12 | January | 2026 | 2026-01-19 13:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 74
202601-NM25-01756 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 17:17 | January | 2026 | 2026-02-06 10:47 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 2 | 9 | 12 | 2026-04-01 | 74
202601-NM25-01758 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 17:48 | January | 2026 | 2026-01-20 08:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 74
202601-NM25-01761 | GDL17 | Residencial | 11.5 | Period | 2026-01-16 17:56 | January | 2026 | 2026-02-02 13:18 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 17 | 0 | 2026-04-01 | 74
202601-NM25-01768 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 12:21 | March | 2026 | 2026-03-13 14:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 22
202601-NM25-01778 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:52 | March | 2026 | 2026-03-05 09:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 28
202601-NM25-01781 | GDL17 | Residencial | 8.8 | Period | 2026-01-31 17:47 | January | 2026 | 2026-02-04 09:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 59
202601-NM25-01782 | GDL17 | Residencial | 8.8 | Period | 2026-02-01 09:59 | February | 2026 | 2026-02-04 13:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 59
202601-NM25-01783 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 07:46 | January | 2026 | 2026-01-20 14:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01784 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 10:25 | February | 2026 | 2026-02-06 15:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-01785 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:32 | February | 2026 | 2026-02-16 12:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-01787 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 08:29 | January | 2026 | 2026-01-30 09:30 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 11 | 0 | 2026-04-01 | 72
202601-NM25-01788 | GDL17 | Residencial | 8 | Period | 2026-01-19 09:07 | January | 2026 | 2026-01-23 08:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 72
202601-NM25-01789 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 08:29 | January | 2026 | 2026-01-29 09:11 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 10 | 0 | 2026-04-01 | 72
202601-NM25-01791 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 08:46 | January | 2026 | 2026-01-20 15:03 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01793 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:54 | February | 2026 | 2026-02-12 12:45 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 55
202601-NM25-01795 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 08:43 | January | 2026 | 2026-01-22 15:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 72
202601-NM25-01796 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:43 | February | 2026 | 2026-02-24 16:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-01797 | GDL17 | Residencial | 5.554 | Period | 2026-01-19 08:55 | January | 2026 | 2026-01-20 15:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01798 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:27 | February | 2026 | 2026-02-16 13:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-01799 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:34 | January | 2026 | 2026-02-10 13:15 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 67
202601-NM25-01800 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:13 | January | 2026 | 2026-01-23 07:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-01801 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:44 | February | 2026 | 2026-02-18 13:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 47
202601-NM25-01802 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:41 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 49
202601-NM25-01803 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 08:14 | February | 2026 | 2026-02-13 11:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 50
202601-NM25-01804 | GDL17 | Residencial | 14.99 | Period | 2026-02-13 10:26 | February | 2026 | 2026-02-16 15:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 47
202601-NM25-01805 | GDL17 | Residencial | 16.47 | Period | 2026-01-19 09:25 | January | 2026 | 2026-01-29 13:14 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 10 | 0 | 2026-04-01 | 72
202601-NM25-01806 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 12:45 | January | 2026 | 2026-01-29 16:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-01807 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 15:20 | January | 2026 | 2026-02-03 13:57 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 12 | 0 | 2026-04-01 | 68
202601-NM25-01808 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:51 | March | 2026 | 2026-04-01 09:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 2
202601-NM25-01809 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:34 | January | 2026 | 2026-01-28 14:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-01810 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:20 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 54
202601-NM25-01811 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:54 | February | 2026 | 2026-02-09 14:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-01812 | GDL17 | Residencial | 4.224 | Period | 2026-01-19 09:16 | January | 2026 | 2026-01-20 14:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01814 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 09:19 | January | 2026 | 2026-01-28 15:22 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 9 | 0 | 2026-04-01 | 72
202601-NM25-01815 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 09:13 | January | 2026 | 2026-01-23 07:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 72
202601-NM25-01816 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 07:41 | January | 2026 | 2026-02-03 12:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-01817 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:57 | January | 2026 | 2026-01-23 08:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-01818 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:24 | February | 2026 | 2026-02-16 14:27 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 57
202601-NM25-01820 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 12:34 | January | 2026 | 2026-01-27 12:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-01821 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:33 | January | 2026 | 2026-01-22 10:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-01822 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:14 | January | 2026 | 2026-02-17 08:01 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 26 | 0 | 2026-04-01 | 69
202601-NM25-01823 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:14 | January | 2026 | 2026-01-22 14:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-01824 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 09:25 | January | 2026 | 2026-01-20 13:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01826 | GDL17 | Residencial | 23 | Period | 2026-02-03 11:20 | February | 2026 | 2026-03-09 15:09 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | March | 1 | 5 | 29 | 2026-04-01 | 57
202601-NM25-01827 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:34 | January | 2026 | 2026-01-23 10:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-01828 | GDL17 | Residencial | 2.562 | Period | 2026-01-19 09:57 | January | 2026 | 2026-01-20 13:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01829 | GDL17 | Residencial | 7.6 | Period | 2026-03-12 11:11 | March | 2026 | 2026-03-31 11:29 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 1 | 18 | 2026-04-01 | 20
202601-NM25-01831 | GDL17 | Residencial | 2.5 | Period | 2026-01-19 10:21 | January | 2026 | 2026-01-23 15:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 72
202601-NM25-01832 | GDL17 | Residencial | 8 | Period | 2026-02-24 12:11 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 35
202601-NM25-01833 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:10 | January | 2026 | 2026-02-03 13:04 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 13 | 0 | 2026-04-01 | 70
202601-NM25-01834 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:31 | February | 2026 | 2026-02-17 10:22 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 57
202601-NM25-01835 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 09:57 | January | 2026 | 2026-01-28 11:24 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 9 | 0 | 2026-04-01 | 72
202601-NM25-01836 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 14:10 | March | 2026 | 2026-03-18 14:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 15
202601-NM25-01837 | GDL17 | Residencial | 7.68 | Period | 2026-01-22 15:55 | January | 2026 | 2026-01-23 15:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-01839 | GDL17 | Residencial | 7.6 | Period | 2026-02-19 09:24 | February | 2026 | 2026-02-24 08:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-01840 | GDL17 | Residencial | 6.572 | Period | 2026-01-19 10:05 | January | 2026 | 2026-01-20 12:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01842 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 10:12 | January | 2026 | 2026-01-23 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 72
202601-NM25-01843 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 10:19 | January | 2026 | 2026-01-20 12:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01846 | GDL17 | Residencial | 5.566 | Period | 2026-01-19 10:26 | January | 2026 | 2026-01-20 14:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01847 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:56 | January | 2026 | 2026-01-23 11:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-01848 | GDL17 | Residencial | 23 | Period | 2026-01-19 10:29 | January | 2026 | 2026-01-20 14:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01849 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 18:27 | February | 2026 | 2026-03-04 08:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202601-NM25-01850 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 11:31 | January | 2026 | 2026-02-04 09:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-01851 | GDL17 | Residencial | 3.8 | Period | 2026-01-20 08:29 | January | 2026 | 2026-01-29 09:10 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 9 | 0 | 2026-04-01 | 71
202601-NM25-01852 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:03 | February | 2026 | 2026-03-17 10:43 | 39 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March | 3 | 34 | 5 | 2026-04-01 | 53
202601-NM25-01853 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:52 | February | 2026 | 2026-02-18 10:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 46
202601-NM25-01854 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 10:42 | January | 2026 | 2026-01-20 14:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 72
202601-NM25-01856 | GDL17 | Residencial | 8 | Period | 2026-03-20 10:39 | March | 2026 | 2026-03-24 16:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 12
202601-NM25-01858 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 17:11 | March | 2026 | 2026-03-12 08:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 25
202601-NM25-01859 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 11:01 | January | 2026 | 2026-01-21 16:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 72
202601-NM25-01860 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 11:17 | January | 2026 | 2026-01-21 12:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 72
202601-NM25-01861 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 11:22 | January | 2026 | 2026-01-21 10:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 72
202601-NM25-01862 | GDL17 | Residencial | 9.15 | Period | 2026-01-19 11:02 | January | 2026 | 2026-02-03 09:25 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 72
202601-NM25-01863 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 11:25 | January | 2026 | 2026-01-26 12:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 72
202601-NM25-01864 | GDL17 | Residencial | 7.6 | Period | 2026-03-20 13:07 | March | 2026 | 2026-03-23 12:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 11
202601-NM25-01865 | GDL17 | Residencial | 15.2 | Period | 2026-01-26 10:27 | January | 2026 | 2026-01-29 14:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 65
202601-NM25-01866 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 11:56 | March | 2026 | 2026-03-18 10:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 2 | 0 | 2026-04-01 | 16
202601-NM25-01867 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 11:23 | January | 2026 | 2026-01-22 15:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 72
202601-NM25-01868 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:36 | February | 2026 | 2026-02-10 13:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-01869 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:46 | March | 2026 | 2026-03-12 11:01 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 29
202601-NM25-01870 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 13:38 | March | 2026 | 2026-03-31 14:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 4
202601-NM25-01871 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 07:49 | January | 2026 | 2026-01-26 09:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-01872 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 11:51 | January | 2026 | 2026-02-03 16:09 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 72
202601-NM25-01873 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 12:39 | February | 2026 | 2026-02-10 10:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202601-NM25-01874 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 11:57 | January | 2026 | 2026-01-21 13:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 72
202601-NM25-01876 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 11:59 | January | 2026 | 2026-01-23 10:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 72
202601-NM25-01877 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 17:48 | February | 2026 | 2026-02-19 12:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 46
202601-NM25-01878 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:38 | January | 2026 | 2026-01-26 11:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-01879 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 12:13 | January | 2026 | 2026-01-28 16:05 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 9 | 0 | 2026-04-01 | 71
202601-NM25-01880 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 12:18 | January | 2026 | 2026-01-26 14:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 71
202601-NM25-01881 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 12:22 | January | 2026 | 2026-01-21 11:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01882 | GDL17 | Residencial | 8 | Period | 2026-03-11 10:22 | March | 2026 | 2026-03-13 09:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-01883 | GDL17 | Residencial | 5.49 | Period | 2026-01-19 12:28 | January | 2026 | 2026-01-21 09:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01884 | GDL17 | Residencial | 4.608 | Period | 2026-01-20 18:46 | January | 2026 | 2026-01-26 14:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 70
202601-NM25-01885 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 12:38 | January | 2026 | 2026-01-21 11:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01887 | GDL17 | Residencial | 6.322 | Period | 2026-01-19 12:52 | January | 2026 | 2026-02-18 15:04 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 30 | 0 | 2026-04-01 | 71
202601-NM25-01888 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 12:49 | January | 2026 | 2026-02-04 07:45 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 15 | 0 | 2026-04-01 | 71
202601-NM25-01889 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 12:59 | February | 2026 | 2026-03-03 15:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 33
202601-NM25-01890 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:04 | January | 2026 | 2026-01-20 16:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-01891 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 13:11 | January | 2026 | 2026-01-26 09:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 71
202601-NM25-01892 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 07:13 | January | 2026 | 2026-01-23 08:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 71
202601-NM25-01893 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:39 | January | 2026 | 2026-01-26 14:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | January | 1 | 4 | 1 | 2026-04-01 | 70
202601-NM25-01894 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:20 | January | 2026 | 2026-01-20 15:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-01896 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 16:43 | January | 2026 | 2026-01-26 14:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-01897 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 12:57 | March | 2026 | 2026-03-18 11:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 15
202601-NM25-01898 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 13:29 | February | 2026 | 2026-02-11 14:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-01901 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:39 | January | 2026 | 2026-01-26 15:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 71
202601-NM25-01903 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 13:44 | February | 2026 | 2026-03-04 14:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 33
202601-NM25-01904 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:40 | January | 2026 | 2026-01-26 11:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 71
202601-NM25-01905 | GDL17 | Residencial | 5.76 | Period | 2026-03-25 09:51 | March | 2026 | 2026-03-30 10:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 7
202601-NM25-01906 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:54 | January | 2026 | 2026-01-28 12:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 69
202601-NM25-01908 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:29 | February | 2026 | 2026-02-23 14:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-01909 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 13:50 | January | 2026 | 2026-01-21 15:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01917 | GDL17 | Residencial | 19.1 | Period | 2026-02-11 15:30 | February | 2026 | 2026-02-24 08:09 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 12 | 1 | 2026-04-01 | 48
202601-NM25-01919 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 14:41 | January | 2026 | 2026-01-20 15:54 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-01920 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:02 | February | 2026 | 2026-03-05 09:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 33
202601-NM25-01922 | GDL17 | Residencial | 3.84 | Period | 2026-01-22 10:34 | January | 2026 | 2026-01-23 15:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-01923 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:53 | February | 2026 | 2026-03-05 16:12 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 39
202601-NM25-01924 | GDL17 | Residencial | 11.4 | Period | 2026-01-19 22:26 | January | 2026 | 2026-01-21 15:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01925 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:04 | January | 2026 | 2026-03-12 11:11 | 49 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 49 | 0 | 2026-04-01 | 68
202601-NM25-01927 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 08:11 | February | 2026 | 2026-02-20 09:18 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 10 | 0 | 2026-04-01 | 50
202601-NM25-01929 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:57 | March | 2026 | 2026-03-09 13:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 28
202601-NM25-01932 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:28 | January | 2026 | 2026-01-29 08:04 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 8 | 0 | 2026-04-01 | 70
202601-NM25-01933 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 08:26 | February | 2026 | 2026-02-25 08:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202601-NM25-01934 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:51 | January | 2026 | 2026-01-30 07:52 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | January | 1 | 4 | 6 | 2026-04-01 | 71
202601-NM25-01937 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 09:26 | March | 2026 | 2026-03-23 09:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 14
202601-NM25-01938 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 09:03 | January | 2026 | 2026-01-30 10:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-01940 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:19 | January | 2026 | 2026-01-20 16:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-01942 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:30 | January | 2026 | 2026-01-21 13:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01943 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:24 | January | 2026 | 2026-01-21 14:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01944 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:37 | January | 2026 | 2026-01-22 14:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 71
202601-NM25-01946 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:42 | January | 2026 | 2026-01-26 07:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 71
202601-NM25-01948 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:37 | January | 2026 | 2026-03-23 13:46 | 63 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 63 | 0 | 2026-04-01 | 71
202601-NM25-01949 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:45 | February | 2026 | 2026-02-13 11:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 48
202601-NM25-01951 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:12 | January | 2026 | 2026-01-29 12:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-01952 | GDL17 | Residencial | 9.216 | Period | 2026-01-19 15:48 | January | 2026 | 2026-01-28 15:50 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 9 | 0 | 2026-04-01 | 71
202601-NM25-01953 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:43 | January | 2026 | 2026-01-21 07:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01954 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 15:49 | January | 2026 | 2026-01-21 13:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01956 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:51 | January | 2026 | 2026-01-21 11:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01958 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:57 | January | 2026 | 2026-01-21 11:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01959 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 15:54 | January | 2026 | 2026-01-21 10:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01960 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:15 | January | 2026 | 2026-02-10 10:20 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 71
202601-NM25-01962 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:05 | January | 2026 | 2026-01-23 09:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 71
202601-NM25-01963 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:47 | January | 2026 | 2026-02-02 15:28 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 11 | 0 | 2026-04-01 | 69
202601-NM25-01964 | GDL17 | Residencial | 6.958 | Period | 2026-01-19 16:11 | January | 2026 | 2026-01-21 09:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01965 | GDL17 | Residencial | 3.8 | Period | 2026-01-29 08:32 | January | 2026 | 2026-01-30 15:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-01966 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:19 | January | 2026 | 2026-01-26 10:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 71
202601-NM25-01967 | GDL17 | Residencial | 7.68 | Period | 2026-02-04 12:07 | February | 2026 | 2026-02-17 16:30 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 13 | 0 | 2026-04-01 | 55
202601-NM25-01969 | GDL17 | Residencial | 12 | Period | 2026-01-28 19:02 | January | 2026 | 2026-02-17 08:22 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 2 | 16 | 4 | 2026-04-01 | 62
202601-NM25-01971 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:20 | January | 2026 | 2026-01-21 10:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01972 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 16:28 | January | 2026 | 2026-01-21 10:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01973 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:28 | January | 2026 | 2026-01-21 12:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01976 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:34 | January | 2026 | 2026-01-23 12:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 71
202601-NM25-01977 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:29 | January | 2026 | 2026-01-21 10:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01979 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:38 | January | 2026 | 2026-01-26 14:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 71
202601-NM25-01980 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:40 | January | 2026 | 2026-02-04 17:23 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 16 | 0 | 2026-04-01 | 71
202601-NM25-01981 | GDL17 | Residencial | 11.5 | Period | 2026-01-19 16:42 | January | 2026 | 2026-01-21 10:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01982 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 15:33 | March | 2026 | 2026-03-12 10:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-01983 | GDL17 | Residencial | 7.6 | Period | 2026-01-19 16:46 | January | 2026 | 2026-01-21 13:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01985 | GDL17 | Comercial | 11.5 | Period | 2026-02-04 14:42 | February | 2026 | 2026-02-10 13:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 55
202601-NM25-01986 | GDL17 | Residencial | 6.572 | Period | 2026-01-19 16:48 | January | 2026 | 2026-01-23 07:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 71
202601-NM25-01988 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 10:26 | February | 2026 | 2026-02-09 12:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-01990 | GDL17 | Residencial | 3.3 | Period | 2026-02-18 18:48 | February | 2026 | 2026-02-24 07:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202601-NM25-01991 | GDL17 | Residencial | 5.17 | Period | 2026-01-19 16:58 | January | 2026 | 2026-01-21 10:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-01994 | GDL17 | Comercial | 12 | Period | 2026-01-19 17:18 | January | 2026 | 2026-02-06 11:17 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 71
202601-NM25-01997 | GDL17 | Residencial | 8 | Period | 2026-01-21 15:18 | January | 2026 | 2026-01-23 14:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-01998 | GDL17 | Residencial | 12 | Period | 2026-01-19 18:30 | January | 2026 | 2026-02-04 09:12 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 16 | 0 | 2026-04-01 | 71
202601-NM25-02003 | GDL17 | Residencial | 8 | Period | 2026-01-22 16:17 | January | 2026 | 2026-01-29 16:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | January | 1 | 2 | 5 | 2026-04-01 | 68
202601-NM25-02004 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 07:34 | January | 2026 | 2026-01-21 13:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-02005 | GDL17 | Residencial | 10.614 | Period | 2026-03-23 08:41 | March | 2026 | 2026-03-27 09:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 1 | 3 | 2026-04-01 | 9
202601-NM25-02006 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 15:35 | January | 2026 | 2026-01-29 09:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-02007 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:54 | January | 2026 | 2026-02-04 14:49 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 67
202601-NM25-02008 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:15 | January | 2026 | 2026-01-26 15:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02009 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:38 | February | 2026 | 2026-02-06 16:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 55
202601-NM25-02010 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:55 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 71
202601-NM25-02011 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:47 | February | 2026 | 2026-02-09 16:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 54
202601-NM25-02012 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:16 | January | 2026 | 2026-01-26 10:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 6 | 0 | 2026-04-01 | 71
202601-NM25-02013 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:45 | January | 2026 | 2026-01-29 09:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 65
202601-NM25-02015 | GDL17 | Residencial | 3.072 | Period | 2026-01-20 08:26 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 71
202601-NM25-02016 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 12:40 | January | 2026 | 2026-01-27 13:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-02017 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:31 | January | 2026 | 2026-01-21 13:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-02018 | GDL17 | Residencial | 14.16 | Period | 2026-01-22 14:32 | January | 2026 | 2026-01-23 16:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-02019 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:53 | January | 2026 | 2026-01-29 12:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 69
202601-NM25-02020 | GDL17 | Residencial | 9.216 | Period | 2026-02-19 06:58 | February | 2026 | 2026-02-24 11:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-02021 | GDL17 | Residencial | 16.492 | Period | 2026-02-02 11:55 | February | 2026 | 2026-02-05 13:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 58
202601-NM25-02022 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 08:55 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 71
202601-NM25-02024 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 09:03 | January | 2026 | 2026-01-21 16:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-02025 | GDL17 | Residencial | 6.144 | Period | 2026-02-17 15:27 | February | 2026 | 2026-02-23 09:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-02026 | GDL17 | Residencial | 13 | Period | 2026-03-05 14:52 | March | 2026 | 2026-03-06 13:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 26
202601-NM25-02027 | GDL17 | Residencial | 5.964 | Period | 2026-01-20 09:17 | January | 2026 | 2026-01-21 15:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-02029 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:53 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 55
202601-NM25-02030 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:45 | March | 2026 | 2026-04-02 13:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 1
202601-NM25-02031 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:48 | January | 2026 | 2026-02-03 13:34 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 71
202601-NM25-02032 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:09 | February | 2026 | 2026-02-19 08:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 43
202601-NM25-02033 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 16:59 | March | 2026 | 2026-03-25 12:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 11
202601-NM25-02034 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 11:28 | February | 2026 | 2026-02-10 14:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 55
202601-NM25-02035 | GDL17 | Residencial | 8 | Period | 2026-01-22 17:17 | January | 2026 | 2026-02-04 09:07 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 68
202601-NM25-02037 | GDL17 | Residencial | 19.1 | Period | 2026-01-26 14:36 | January | 2026 | 2026-01-28 10:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02038 | GDL17 | Residencial | 7.6 | Period | 2026-03-12 09:26 | March | 2026 | 2026-03-26 09:21 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 14 | 0 | 2026-04-01 | 20
202601-NM25-02039 | GDL17 | Residencial | 8 | Period | 2026-01-27 15:52 | January | 2026 | 2026-01-29 11:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02041 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 10:43 | January | 2026 | 2026-01-28 10:59 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 8 | 0 | 2026-04-01 | 71
202601-NM25-02042 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 08:19 | January | 2026 | 2026-01-26 13:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02044 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 09:09 | February | 2026 | 2026-02-11 09:14 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 57
202601-NM25-02046 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:47 | January | 2026 | 2026-01-22 09:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-02047 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:15 | January | 2026 | 2026-01-22 11:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02048 | GDL17 | Residencial | 6.434 | Period | 2026-02-10 12:28 | February | 2026 | 2026-02-11 13:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-02049 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 10:58 | January | 2026 | 2026-01-22 13:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 71
202601-NM25-02050 | GDL17 | Residencial | 8 | Period | 2026-01-26 20:13 | January | 2026 | 2026-01-28 13:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02051 | GDL17 | Residencial | 20 | Period | 2026-02-03 08:18 | February | 2026 | 2026-02-09 14:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 57
202601-NM25-02052 | GDL17 | Residencial | 7.492 | Period | 2026-01-20 10:52 | January | 2026 | 2026-01-21 14:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-02053 | GDL17 | Residencial | 7.992 | Period | 2026-01-20 11:01 | January | 2026 | 2026-01-21 15:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-02054 | GDL17 | Residencial | 6.912 | Period | 2026-01-30 14:50 | January | 2026 | 2026-02-03 13:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-02055 | GDL17 | Residencial | 8 | Period | 2026-01-26 20:36 | January | 2026 | 2026-01-28 15:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02057 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 11:41 | January | 2026 | 2026-01-21 15:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 71
202601-NM25-02059 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 11:45 | January | 2026 | 2026-01-30 10:10 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 10 | 0 | 2026-04-01 | 71
202601-NM25-02060 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:48 | January | 2026 | 2026-01-22 10:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02061 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:11 | January | 2026 | 2026-01-23 15:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02062 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 10:44 | February | 2026 | 2026-02-12 16:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-02063 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:00 | January | 2026 | 2026-02-02 10:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-02064 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:39 | March | 2026 | 2026-03-06 10:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 29
202601-NM25-02066 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 11:37 | January | 2026 | 2026-01-29 10:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-02067 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 12:28 | January | 2026 | 2026-01-22 13:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02069 | GDL17 | Residencial | 23 | Period | 2026-03-20 18:44 | March | 2026 | 2026-03-25 13:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 11
202601-NM25-02072 | GDL17 | Residencial | 3.8 | Period | 2026-01-26 16:06 | January | 2026 | 2026-03-12 14:22 | 45 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 45 | 0 | 2026-04-01 | 64
202601-NM25-02073 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 17:09 | March | 2026 | 2026-03-09 08:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 27
202601-NM25-02074 | GDL17 | Residencial | 16 | Period | 2026-01-20 14:04 | January | 2026 | 2026-01-22 11:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02075 | GDL17 | Residencial | 3.84 | Period | 2026-02-11 11:00 | February | 2026 | 2026-02-12 12:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-02076 | GDL17 | Residencial | 10 | Period | 2026-01-30 11:17 | January | 2026 | 2026-02-03 11:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-02077 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 13:25 | March | 2026 | 2026-03-16 14:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 20
202601-NM25-02078 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:05 | February | 2026 | 2026-03-17 15:14 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 2 | 11 | 10 | 2026-04-01 | 35
202601-NM25-02080 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:34 | February | 2026 | 2026-02-05 13:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-02082 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:59 | February | 2026 | 2026-03-30 08:40 | 54 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March |  | 53 | 0 | 2026-04-01 | 55
202601-NM25-02083 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:48 | February | 2026 | 2026-02-09 15:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 56
202601-NM25-02084 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 15:28 | January | 2026 | 2026-02-25 15:38 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 28 | 0 | 2026-04-01 | 62
202601-NM25-02087 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:01 | January | 2026 | 2026-01-22 11:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02088 | GDL17 | Residencial | 3.84 | Period | 2026-02-17 14:01 | February | 2026 | 2026-02-23 09:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-02089 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:40 | January | 2026 | 2026-01-22 12:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02090 | GDL17 | Residencial | 5.376 | Period | 2026-03-10 14:19 | March | 2026 | 2026-03-12 15:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-02092 | GDL17 | Residencial | 8.54 | Period | 2026-01-20 13:38 | January | 2026 | 2026-01-22 12:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02093 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:08 | January | 2026 | 2026-02-26 13:51 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 1 | 28 | 2026-04-01 | 63
202601-NM25-02095 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 15:39 | February | 2026 | 2026-02-12 16:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 54
202601-NM25-02096 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 11:30 | January | 2026 | 2026-01-22 10:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02097 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 13:53 | January | 2026 | 2026-01-22 12:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02099 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 07:45 | February | 2026 | 2026-02-10 14:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-02100 | GDL17 | Residencial | 10.368 | Period | 2026-01-23 08:58 | January | 2026 | 2026-01-26 14:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02101 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:04 | February | 2026 | 2026-02-11 13:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-02103 | GDL17 | Comercial | 6 | Period | 2026-02-18 17:52 | February | 2026 | 2026-02-24 11:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202601-NM25-02104 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:17 | March | 2026 | 2026-03-09 14:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 29
202601-NM25-02105 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 14:29 | January | 2026 | 2026-01-23 12:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 70
202601-NM25-02106 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 12:21 | January | 2026 | 2026-02-12 10:04 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 17 | 5 | 2026-04-01 | 69
202601-NM25-02107 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:28 | January | 2026 | 2026-01-26 10:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 70
202601-NM25-02108 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:23 | February | 2026 | 2026-02-06 15:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 55
202601-NM25-02110 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 08:36 | January | 2026 | 2026-01-27 12:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-02111 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:35 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 55
202601-NM25-02113 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:19 | January | 2026 | 2026-01-22 10:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02115 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:36 | January | 2026 | 2026-01-22 14:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02116 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 17:21 | March | 2026 | 2026-03-09 14:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 27
202601-NM25-02117 | GDL17 | Residencial | 24 | Period | 2026-01-20 15:10 | January | 2026 | 2026-01-22 09:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02118 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 11:05 | January | 2026 | 2026-02-06 10:03 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 16 | 0 | 2026-04-01 | 70
202601-NM25-02119 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:40 | January | 2026 | 2026-01-29 10:10 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 9 | 0 | 2026-04-01 | 70
202601-NM25-02120 | GDL17 | Residencial | 2.688 | Period | 2026-02-19 14:35 | February | 2026 | 2026-02-24 14:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202601-NM25-02121 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:11 | February | 2026 | 2026-02-16 14:53 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 11 | 0 | 2026-04-01 | 54
202601-NM25-02123 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:45 | January | 2026 | 2026-01-22 09:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02125 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:42 | January | 2026 | 2026-01-22 09:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02126 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:50 | February | 2026 | 2026-02-27 09:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202601-NM25-02129 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 14:56 | January | 2026 | 2026-01-22 14:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02130 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:06 | January | 2026 | 2026-02-13 16:17 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 24 | 0 | 2026-04-01 | 70
202601-NM25-02132 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 15:20 | January | 2026 | 2026-01-22 09:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02133 | GDL17 | Residencial | 7.6 | Period | 2026-03-04 09:30 | March | 2026 | 2026-03-09 09:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 28
202601-NM25-02134 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 18:58 | March | 2026 | 2026-03-05 09:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 28
202601-NM25-02135 | GDL17 | Residencial | 3.84 | Period | 2026-01-23 09:59 | January | 2026 | 2026-01-26 15:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02136 | GDL17 | Residencial | 6.222 | Period | 2026-01-20 15:11 | January | 2026 | 2026-01-22 09:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02137 | GDL17 | Residencial | 23 | Period | 2026-01-20 15:40 | January | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 70
202601-NM25-02140 | GDL17 | Residencial | 4.026 | Period | 2026-01-20 15:30 | January | 2026 | 2026-01-22 09:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02141 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:26 | January | 2026 | 2026-02-20 12:51 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 30 | 0 | 2026-04-01 | 69
202601-NM25-02142 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:30 | January | 2026 | 2026-01-29 15:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02144 | GDL17 | Residencial | 7.6 | Period | 2026-01-20 15:43 | January | 2026 | 2026-01-22 08:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02145 | GDL17 | Residencial | 23 | Period | 2026-02-20 16:45 | February | 2026 | 2026-02-26 13:33 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-02146 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:44 | February | 2026 | 2026-02-19 15:04 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 54
202601-NM25-02147 | GDL17 | Residencial | 3.8 | Period | 2026-01-30 11:06 | January | 2026 | 2026-02-04 07:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-02148 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 16:07 | January | 2026 | 2026-01-22 10:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02149 | GDL17 | Residencial | 7.462 | Period | 2026-01-20 15:56 | January | 2026 | 2026-01-22 08:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02150 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 13:30 | February | 2026 | 2026-02-13 09:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-02151 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 16:00 | January | 2026 | 2026-01-22 08:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02153 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:10 | January | 2026 | 2026-02-05 11:29 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 69
202601-NM25-02154 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:46 | February | 2026 | 2026-02-26 15:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 37
202601-NM25-02155 | GDL17 | Residencial | 19.1 | Period | 2026-02-12 07:29 | February | 2026 | 2026-02-25 08:39 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 9 | 4 | 2026-04-01 | 48
202601-NM25-02156 | GDL17 | Residencial | 12 | Period | 2026-01-29 11:40 | January | 2026 | 2026-02-02 11:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-02157 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 16:54 | January | 2026 | 2026-01-26 10:32 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 70
202601-NM25-02158 | GDL17 | Residencial | 11.4 | Period | 2026-01-30 10:53 | January | 2026 | 2026-02-20 07:45 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 61
202601-NM25-02159 | GDL17 | Residencial | 11.4 | Period | 2026-02-09 05:46 | February | 2026 | 2026-02-10 15:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 51
202601-NM25-02161 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 17:48 | March | 2026 | 2026-03-05 15:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202601-NM25-02162 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 14:34 | March | 2026 | 2026-03-16 13:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202601-NM25-02163 | GDL17 | Residencial | 11.5 | Period | 2026-01-20 17:30 | January | 2026 | 2026-01-22 10:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02166 | GDL17 | Residencial | 5.376 | Period | 2026-01-21 13:18 | January | 2026 | 2026-02-09 11:16 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 19 | 0 | 2026-04-01 | 69
202601-NM25-02167 | GDL17 | Residencial | 12 | Period | 2026-01-21 10:34 | January | 2026 | 2026-01-22 14:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02168 | GDL17 | Residencial | 5 | Period | 2026-02-08 15:10 | February | 2026 | 2026-02-13 13:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 51
202601-NM25-02169 | GDL17 | Comercial | 15.51 | Period | 2026-01-20 20:25 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 70
202601-NM25-02170 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 18:01 | February | 2026 | 2026-03-13 10:15 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 33
202601-NM25-02171 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:47 | March | 2026 | 2026-03-05 10:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 29
202601-NM25-02172 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:28 | March | 2026 | 2026-03-09 16:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 28
202601-NM25-02173 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 19:00 | March | 2026 | 2026-03-11 13:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 22
202601-NM25-02174 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 12:50 | March | 2026 | 2026-04-01 14:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 5 | 0 | 2026-04-01 | 4
202601-NM25-02176 | GDL17 | Residencial | 16 | Period | 2026-01-28 00:45 | January | 2026 | 2026-01-30 08:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 63
202601-NM25-02184 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 15:42 | February | 2026 | 2026-02-17 10:33 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 49
202601-NM25-02186 | GDL17 | Residencial | 3.8 | Period | 2026-02-05 10:31 | February | 2026 | 2026-02-11 08:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 55
202601-NM25-02187 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:03 | January | 2026 | 2026-01-22 12:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02189 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:54 | January | 2026 | 2026-01-30 14:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02192 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:57 | February | 2026 | 2026-02-16 14:16 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 55
202601-NM25-02193 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:24 | February | 2026 | 2026-02-16 14:40 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 11 | 0 | 2026-04-01 | 54
202601-NM25-02194 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 12:43 | February | 2026 | 2026-02-10 13:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-02195 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 08:34 | January | 2026 | 2026-01-26 09:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 70
202601-NM25-02196 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 13:38 | January | 2026 | 2026-01-30 11:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02197 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:53 | February | 2026 | 2026-03-06 08:48 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 16 | 0 | 2026-04-01 | 42
202601-NM25-02198 | GDL17 | Residencial | 7.41 | Period | 2026-01-21 08:56 | January | 2026 | 2026-01-22 14:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02199 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 08:57 | January | 2026 | 2026-01-22 14:24 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02202 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:17 | January | 2026 | 2026-01-23 07:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02203 | GDL17 | Residencial | 7.572 | Period | 2026-01-21 09:03 | January | 2026 | 2026-01-21 14:31 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 0 | 0 | 2026-04-01 | 70
202601-NM25-02204 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 07:17 | January | 2026 | 2026-01-30 11:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-02205 | GDL17 | Residencial | 2.928 | Period | 2026-01-21 09:09 | January | 2026 | 2026-03-17 08:57 | 55 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March | 2 | 42 | 8 | 2026-04-01 | 70
202601-NM25-02206 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:36 | January | 2026 | 2026-01-26 16:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02207 | GDL17 | Residencial | 11.136 | Period | 2026-01-21 09:36 | January | 2026 | 2026-01-22 11:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02210 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:33 | January | 2026 | 2026-01-23 07:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02211 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:34 | January | 2026 | 2026-01-23 10:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02212 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:49 | January | 2026 | 2026-01-27 16:27 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-02213 | GDL17 | Residencial | 6.528 | Period | 2026-01-30 07:39 | January | 2026 | 2026-02-03 12:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-02214 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 09:56 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 70
202601-NM25-02215 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:52 | February | 2026 | 2026-02-16 13:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-02216 | GDL17 | Residencial | 8.064 | Period | 2026-01-30 07:56 | January | 2026 | 2026-02-04 08:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-02217 | GDL17 | Residencial | 18 | Period | 2026-01-22 12:38 | January | 2026 | 2026-01-30 12:51 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 8 | 0 | 2026-04-01 | 68
202601-NM25-02218 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 15:03 | January | 2026 | 2026-02-03 10:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-02219 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 10:06 | January | 2026 | 2026-01-22 13:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02220 | GDL17 | Residencial | 3 | Period | 2026-01-21 09:58 | January | 2026 | 2026-01-22 13:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02222 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 10:09 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 70
202601-NM25-02226 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:45 | February | 2026 | 2026-02-23 09:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-02227 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 10:39 | January | 2026 | 2026-01-30 16:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-02228 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 11:00 | January | 2026 | 2026-01-23 15:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | January | 1 | 1 | 1 | 2026-04-01 | 70
202601-NM25-02229 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:30 | January | 2026 | 2026-01-22 09:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02230 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:21 | February | 2026 | 2026-03-03 13:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 34
202601-NM25-02231 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:03 | January | 2026 | 2026-02-18 10:34 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 19 | 0 | 2026-04-01 | 61
202601-NM25-02232 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 10:58 | January | 2026 | 2026-01-26 14:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 70
202601-NM25-02233 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:56 | February | 2026 | 2026-02-05 11:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-02234 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 11:29 | January | 2026 | 2026-01-30 14:45 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 9 | 0 | 2026-04-01 | 70
202601-NM25-02235 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 11:13 | January | 2026 | 2026-01-22 09:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02236 | GDL17 | Residencial | 11.4 | Period | 2026-01-21 14:01 | January | 2026 | 2026-01-26 13:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-02237 | GDL17 | Residencial | 7 | Period | 2026-01-21 11:53 | January | 2026 | 2026-01-29 10:43 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 8 | 0 | 2026-04-01 | 70
202601-NM25-02238 | GDL17 | Residencial | 6.572 | Period | 2026-01-21 11:18 | January | 2026 | 2026-01-23 14:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | January | 1 | 1 | 1 | 2026-04-01 | 70
202601-NM25-02239 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 05:19 | March | 2026 | 2026-03-26 10:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202601-NM25-02240 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:33 | January | 2026 | 2026-01-29 16:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02242 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 11:28 | January | 2026 | 2026-01-23 09:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 70
202601-NM25-02243 | GDL17 | Residencial | 23 | Period | 2026-01-26 17:40 | January | 2026 | 2026-01-28 15:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02244 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:51 | February | 2026 | 2026-02-09 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-02245 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 11:19 | January | 2026 | 2026-01-22 09:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02246 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:18 | February | 2026 | 2026-02-19 08:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202601-NM25-02247 | GDL17 | Residencial | 10.368 | Period | 2026-01-22 15:00 | January | 2026 | 2026-02-10 09:15 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 19 | 0 | 2026-04-01 | 68
202601-NM25-02248 | GDL17 | Residencial | 8.644 | Period | 2026-01-21 11:27 | January | 2026 | 2026-01-22 09:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02249 | GDL17 | Residencial | 3.84 | Period | 2026-01-30 14:13 | January | 2026 | 2026-02-03 15:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-02250 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:02 | January | 2026 | 2026-03-17 15:12 | 47 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 3 | 8 | 39 | 2026-04-01 | 62
202601-NM25-02251 | GDL17 | Residencial | 11.44 | Period | 2026-01-21 11:30 | January | 2026 | 2026-01-22 09:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02252 | GDL17 | Residencial | 8 | Period | 2026-02-02 22:50 | February | 2026 | 2026-02-09 10:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 57
202601-NM25-02253 | GDL17 | Residencial | 10.04 | Period | 2026-01-21 11:40 | January | 2026 | 2026-01-22 10:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02254 | GDL17 | Residencial | 6.732 | Period | 2026-01-21 11:39 | January | 2026 | 2026-01-22 10:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 70
202601-NM25-02255 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 12:02 | January | 2026 | 2026-01-26 07:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-02256 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:41 | January | 2026 | 2026-01-26 10:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-02257 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 10:55 | March | 2026 | 2026-03-18 09:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 16
202601-NM25-02258 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 16:47 | January | 2026 | 2026-01-28 12:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 67
202601-NM25-02259 | GDL17 | Residencial | 7.68 | Period | 2026-01-26 15:32 | January | 2026 | 2026-01-28 10:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02260 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:50 | February | 2026 | 2026-02-23 09:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-02261 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:53 | February | 2026 | 2026-02-26 08:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-02262 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 14:09 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 25
202601-NM25-02265 | GDL17 | Residencial | 22.6 | Period | 2026-02-04 15:30 | February | 2026 | 2026-02-23 11:02 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 55
202601-NM25-02266 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 10:45 | February | 2026 | 2026-02-11 13:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 56
202601-NM25-02267 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 12:19 | January | 2026 | 2026-01-29 08:13 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 69
202601-NM25-02268 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 12:59 | January | 2026 | 2026-01-23 11:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02269 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:48 | March | 2026 | 2026-03-31 11:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202601-NM25-02271 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 09:20 | March | 2026 | 2026-03-31 07:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 8
202601-NM25-02273 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 17:40 | March | 2026 | 2026-03-26 11:05 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 15 | 0 | 2026-04-01 | 20
202601-NM25-02274 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 12:39 | January | 2026 | 2026-01-22 15:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02277 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 12:51 | January | 2026 | 2026-01-22 10:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02279 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 17:12 | January | 2026 | 2026-01-23 15:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02280 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:07 | January | 2026 | 2026-01-26 07:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 69
202601-NM25-02281 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 13:58 | March | 2026 | 2026-03-17 10:17 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 25
202601-NM25-02284 | GDL17 | Residencial | 5.196 | Period | 2026-01-21 13:24 | January | 2026 | 2026-01-26 14:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-02286 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 13:41 | January | 2026 | 2026-01-26 15:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-02287 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:06 | March | 2026 | 2026-03-04 13:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 29
202601-NM25-02288 | GDL17 | Residencial | 11.904 | Period | 2026-01-21 13:34 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 69
202601-NM25-02290 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 11:29 | March | 2026 | 2026-03-20 08:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 15
202601-NM25-02291 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:55 | January | 2026 | 2026-01-29 10:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02292 | GDL17 | Residencial | 15 | Period | 2026-03-27 13:16 | March | 2026 | 2026-04-01 14:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 5 | 0 | 2026-04-01 | 4
202601-NM25-02293 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 15:26 | January | 2026 | 2026-01-30 09:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02294 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 08:36 | January | 2026 | 2026-02-04 13:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 1 | 5 | 2026-04-01 | 62
202601-NM25-02295 | GDL17 | Residencial | 6.144 | Period | 2026-01-29 11:57 | January | 2026 | 2026-02-04 10:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-02296 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:10 | January | 2026 | 2026-02-18 10:14 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 27 | 0 | 2026-04-01 | 69
202601-NM25-02298 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:41 | January | 2026 | 2026-01-23 15:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02299 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 08:58 | February | 2026 | 2026-02-19 08:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 48
202601-NM25-02300 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:41 | January | 2026 | 2026-02-18 07:43 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 28 | 0 | 2026-04-01 | 69
202601-NM25-02301 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 14:44 | January | 2026 | 2026-01-23 10:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02303 | GDL17 | Residencial | 3.84 | Period | 2026-01-22 17:14 | January | 2026 | 2026-01-26 11:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02304 | GDL17 | Residencial | 15 | Period | 2026-01-22 14:53 | January | 2026 | 2026-01-29 08:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-02307 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:28 | February | 2026 | 2026-02-25 09:31 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 42
202601-NM25-02308 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:34 | March | 2026 | 2026-03-11 12:52 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 30
202601-NM25-02310 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 19:21 | January | 2026 | 2026-02-04 13:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 61
202601-NM25-02312 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:31 | January | 2026 | 2026-01-23 08:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02313 | GDL17 | Residencial | 5.76 | Period | 2026-02-20 14:54 | February | 2026 | 2026-02-26 08:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-02315 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 15:34 | January | 2026 | 2026-01-26 15:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-02316 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 15:35 | January | 2026 | 2026-01-23 15:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02317 | GDL17 | Residencial | 9.74 | Period | 2026-01-21 15:48 | January | 2026 | 2026-02-04 15:21 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 69
202601-NM25-02318 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 15:53 | January | 2026 | 2026-03-19 17:03 | 57 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 57 | 0 | 2026-04-01 | 69
202601-NM25-02319 | GDL17 | Residencial | 3.8 | Period | 2026-02-09 10:50 | February | 2026 | 2026-02-11 10:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 51
202601-NM25-02320 | GDL17 | Residencial | 3.54 | Period | 2026-02-04 14:18 | February | 2026 | 2026-02-06 16:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 55
202601-NM25-02321 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 18:54 | February | 2026 | 2026-02-23 09:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-02325 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:06 | January | 2026 | 2026-02-09 15:58 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 61
202601-NM25-02326 | GDL17 | Residencial | 15.2 | Period | 2026-01-21 16:01 | January | 2026 | 2026-01-23 15:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02328 | GDL17 | Residencial | 12.258 | Period | 2026-01-21 16:06 | January | 2026 | 2026-01-23 10:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02331 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 16:25 | January | 2026 | 2026-01-23 11:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02332 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 16:32 | January | 2026 | 2026-01-26 14:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 69
202601-NM25-02333 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 18:43 | March | 2026 | 2026-03-17 09:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 19
202601-NM25-02335 | GDL17 | Residencial | 5.076 | Period | 2026-01-21 16:34 | January | 2026 | 2026-01-23 15:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02336 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 11:59 | March | 2026 | 2026-04-02 10:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 7 | 0 | 2026-04-01 | 6
202601-NM25-02337 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 16:47 | January | 2026 | 2026-01-23 07:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02338 | GDL17 | Residencial | 7.134 | Period | 2026-01-21 16:54 | January | 2026 | 2026-01-23 13:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02339 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 16:56 | January | 2026 | 2026-01-23 16:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02341 | GDL17 | Residencial | 11.4 | Period | 2026-02-16 10:17 | February | 2026 | 2026-02-19 11:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202601-NM25-02343 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 17:18 | January | 2026 | 2026-01-23 16:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02344 | GDL17 | Residencial | 5.076 | Period | 2026-01-21 17:06 | January | 2026 | 2026-01-23 15:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02345 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 11:24 | February | 2026 | 2026-02-11 11:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 51
202601-NM25-02346 | GDL17 | Residencial | 13.862 | Period | 2026-01-21 17:25 | January | 2026 | 2026-01-23 15:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02348 | GDL17 | Residencial | 7.6 | Period | 2026-01-21 17:17 | January | 2026 | 2026-01-23 16:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02349 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 08:14 | March | 2026 | 2026-03-11 12:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 23
202601-NM25-02352 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 17:33 | January | 2026 | 2026-01-23 16:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02353 | GDL17 | Residencial | 10.564 | Period | 2026-01-21 17:38 | January | 2026 | 2026-01-23 16:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02354 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 15:07 | March | 2026 | 2026-03-30 13:07 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 4 | 20 | 2026-04-01 | 25
202601-NM25-02357 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 11:28 | January | 2026 | 2026-02-02 10:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-02358 | GDL17 | Residencial | 11.5 | Period | 2026-01-21 17:51 | January | 2026 | 2026-01-23 15:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02359 | GDL17 | Residencial | 7.756 | Period | 2026-01-21 17:52 | January | 2026 | 2026-01-23 15:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02360 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:59 | February | 2026 | 2026-02-16 11:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 48
202601-NM25-02363 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 12:40 | January | 2026 | 2026-01-28 11:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-02364 | GDL17 | Residencial | 9 | Period | 2026-01-24 16:27 | January | 2026 | 2026-01-26 13:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 66
202601-NM25-02366 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 19:48 | February | 2026 | 2026-02-26 10:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-02370 | GDL17 | Residencial | 10.98 | Period | 2026-01-21 18:43 | January | 2026 | 2026-01-23 16:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 69
202601-NM25-02373 | GDL17 | Residencial | 15 | Period | 2026-01-24 17:05 | January | 2026 | 2026-01-26 15:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 66
202601-NM25-02377 | GDL17 | Residencial | 9 | Period | 2026-01-22 10:36 | January | 2026 | 2026-01-26 15:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 69
202601-NM25-02378 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 07:59 | January | 2026 | 2026-02-09 13:07 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 19 | 0 | 2026-04-01 | 69
202601-NM25-02379 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:54 | March | 2026 | 2026-03-04 14:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 30
202601-NM25-02380 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 10:13 | February | 2026 | 2026-03-02 10:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 35
202601-NM25-02382 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 08:52 | January | 2026 | 2026-01-29 10:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 69
202601-NM25-02383 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:27 | January | 2026 | 2026-01-29 13:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02386 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:28 | January | 2026 | 2026-01-29 10:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02387 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:20 | January | 2026 | 2026-02-12 09:35 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 62
202601-NM25-02388 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:48 | January | 2026 | 2026-01-29 15:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02389 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 08:52 | January | 2026 | 2026-01-22 16:06 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 0 | 0 | 2026-04-01 | 69
202601-NM25-02390 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 08:36 | January | 2026 | 2026-01-29 07:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 7 | 0 | 2026-04-01 | 69
202601-NM25-02391 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 07:28 | January | 2026 | 2026-02-11 13:08 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 12 | 0 | 2026-04-01 | 61
202601-NM25-02392 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 12:36 | February | 2026 | 2026-03-03 11:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 33
202601-NM25-02395 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 07:55 | March | 2026 | 2026-03-19 10:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 14
202601-NM25-02396 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:24 | February | 2026 | 2026-02-06 12:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-02397 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:57 | February | 2026 | 2026-02-13 09:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 56
202601-NM25-02398 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:49 | February | 2026 | 2026-02-09 09:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 56
202601-NM25-02401 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 07:56 | January | 2026 | 2026-01-29 15:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-02402 | GDL17 | Residencial | 6.584 | Period | 2026-01-22 09:15 | January | 2026 | 2026-01-22 16:13 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 0 | 0 | 2026-04-01 | 69
202601-NM25-02403 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:36 | January | 2026 | 2026-02-02 09:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-02405 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:50 | January | 2026 | 2026-01-29 14:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02406 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:16 | January | 2026 | 2026-01-29 14:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-02407 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:56 | January | 2026 | 2026-01-30 10:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02408 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:31 | February | 2026 | 2026-02-06 14:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 57
202601-NM25-02409 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:15 | January | 2026 | 2026-01-30 12:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 63
202601-NM25-02410 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:21 | February | 2026 | 2026-03-11 13:08 | 36 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 36 | 0 | 2026-04-01 | 57
202601-NM25-02411 | GDL17 | Residencial | 8.23 | Period | 2026-01-22 09:27 | January | 2026 | 2026-01-23 14:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02412 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:39 | January | 2026 | 2026-01-23 14:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02413 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:34 | January | 2026 | 2026-02-02 13:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-02415 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:36 | January | 2026 | 2026-01-22 16:29 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 0 | 0 | 2026-04-01 | 69
202601-NM25-02416 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:31 | February | 2026 | 2026-02-23 10:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202601-NM25-02417 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 07:45 | January | 2026 | 2026-02-04 08:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-02418 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:03 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 64
202601-NM25-02419 | GDL17 | Residencial | 8 | Period | 2026-03-11 10:31 | March | 2026 | 2026-03-13 09:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-02420 | GDL17 | Residencial | 8.562 | Period | 2026-01-22 09:54 | January | 2026 | 2026-01-23 14:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02421 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 09:55 | January | 2026 | 2026-01-23 14:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02423 | GDL17 | Residencial | 7.492 | Period | 2026-01-22 09:59 | January | 2026 | 2026-01-23 14:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02424 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:31 | January | 2026 | 2026-02-02 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 63
202601-NM25-02426 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:54 | January | 2026 | 2026-02-26 08:24 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 28 | 0 | 2026-04-01 | 63
202601-NM25-02428 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:53 | February | 2026 | 2026-02-09 09:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-02429 | GDL17 | Residencial | 11.136 | Period | 2026-02-23 18:53 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 36
202601-NM25-02430 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:34 | January | 2026 | 2026-02-26 11:17 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 29 | 0 | 2026-04-01 | 63
202601-NM25-02431 | GDL17 | Residencial | 11.492 | Period | 2026-01-22 10:27 | January | 2026 | 2026-01-23 14:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02432 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:30 | January | 2026 | 2026-01-23 14:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02433 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:01 | January | 2026 | 2026-02-16 09:53 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 62
202601-NM25-02434 | GDL17 | Residencial | 7.6 | Period | 2026-03-13 14:56 | March | 2026 | 2026-03-20 12:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 18
202601-NM25-02437 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:30 | February | 2026 | 2026-03-03 16:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 32
202601-NM25-02438 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:34 | January | 2026 | 2026-02-09 15:06 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 61
202601-NM25-02439 | GDL17 | Residencial | 23 | Period | 2026-01-24 20:35 | January | 2026 | 2026-01-26 14:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 66
202601-NM25-02441 | GDL17 | Residencial | 15 | Period | 2026-02-24 08:57 | February | 2026 | 2026-02-27 09:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202601-NM25-02442 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 11:01 | January | 2026 | 2026-01-23 15:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 69
202601-NM25-02443 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 10:59 | January | 2026 | 2026-01-26 08:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 69
202601-NM25-02445 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 12:09 | January | 2026 | 2026-01-29 11:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-02446 | GDL17 | Residencial | 23 | Period | 2026-03-04 15:35 | March | 2026 | 2026-03-05 16:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 27
202601-NM25-02448 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:29 | January | 2026 | 2026-01-30 08:19 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 8 | 0 | 2026-04-01 | 69
202601-NM25-02449 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:25 | January | 2026 | 2026-01-26 12:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 69
202601-NM25-02450 | GDL17 | Residencial | 15 | Period | 2026-02-13 13:50 | February | 2026 | 2026-02-18 10:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202601-NM25-02451 | GDL17 | Residencial | 8 | Period | 2026-02-28 22:22 | February | 2026 | 2026-03-04 09:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 31
202601-NM25-02452 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:42 | January | 2026 | 2026-01-29 10:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 69
202601-NM25-02453 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:51 | February | 2026 | 2026-02-23 09:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 42
202601-NM25-02454 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:47 | January | 2026 | 2026-01-28 16:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 69
202601-NM25-02455 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:47 | February | 2026 | 2026-02-05 14:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-02458 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 17:24 | March | 2026 | 2026-03-17 08:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 19
202601-NM25-02459 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 11:58 | January | 2026 | 2026-02-11 10:26 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 20 | 0 | 2026-04-01 | 69
202601-NM25-02461 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 11:56 | March | 2026 | 2026-03-23 13:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 13
202601-NM25-02462 | GDL17 | Residencial | 8 | Period | 2026-01-26 17:19 | January | 2026 | 2026-01-28 13:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02463 | GDL17 | Residencial | 7.6 | Period | 2026-02-09 10:48 | February | 2026 | 2026-02-11 10:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 51
202601-NM25-02464 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:30 | March | 2026 | 2026-03-20 14:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 13
202601-NM25-02465 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 12:22 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 68
202601-NM25-02466 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 18:19 | March | 2026 | 2026-03-17 08:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 19
202601-NM25-02468 | GDL17 | Residencial | 7.5 | Period | 2026-02-17 16:02 | February | 2026 | 2026-02-25 08:03 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 5 | 3 | 2026-04-01 | 42
202601-NM25-02469 | GDL17 | Residencial | 8.214 | Period | 2026-01-22 12:41 | January | 2026 | 2026-01-23 15:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-02470 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 12:37 | January | 2026 | 2026-01-23 15:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-02471 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 10:12 | February | 2026 | 2026-03-30 16:13 | 45 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March | 2 | 7 | 17 | 2026-04-01 | 47
202601-NM25-02472 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:51 | March | 2026 | 2026-03-12 16:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-02473 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:15 | January | 2026 | 2026-01-28 18:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-02474 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 10:46 | March | 2026 | 2026-03-17 08:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 19
202601-NM25-02477 | GDL17 | Residencial | 15.2 | Period | 2026-02-05 07:54 | February | 2026 | 2026-02-09 14:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 55
202601-NM25-02478 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:27 | January | 2026 | 2026-02-13 08:36 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 60
202601-NM25-02479 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 14:12 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 46
202601-NM25-02480 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:31 | February | 2026 | 2026-03-04 15:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 34
202601-NM25-02481 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:47 | March | 2026 | 2026-03-25 11:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 12
202601-NM25-02482 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:49 | January | 2026 | 2026-01-26 12:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02484 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 13:59 | January | 2026 | 2026-01-29 07:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-02486 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 18:22 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 22
202601-NM25-02488 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:16 | January | 2026 | 2026-01-29 15:49 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 1 | 2 | 5 | 2026-04-01 | 68
202601-NM25-02489 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:22 | January | 2026 | 2026-01-26 10:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02490 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 16:09 | January | 2026 | 2026-01-29 12:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-02492 | GDL17 | Residencial | 16 | Period | 2026-02-22 14:45 | February | 2026 | 2026-02-27 16:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 37
202601-NM25-02493 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 07:53 | January | 2026 | 2026-01-30 12:39 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-02494 | GDL17 | Residencial | 3.8 | Period | 2026-01-23 07:32 | January | 2026 | 2026-01-26 15:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02495 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 14:49 | January | 2026 | 2026-01-23 15:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-02496 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 18:39 | January | 2026 | 2026-01-30 12:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02498 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:10 | March | 2026 | 2026-03-25 15:18 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 4 | 19 | 2026-04-01 | 29
202601-NM25-02499 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:11 | February | 2026 | 2026-02-18 10:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 46
202601-NM25-02500 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 17:25 | January | 2026 | 2026-01-26 11:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02501 | GDL17 | Residencial | 6 | Period | 2026-01-30 08:25 | January | 2026 | 2026-02-02 15:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 61
202601-NM25-02502 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:06 | February | 2026 | 2026-02-05 11:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202601-NM25-02503 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:46 | March | 2026 | 2026-03-09 15:41 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 0 | 0 | 2026-04-01 | 23
202601-NM25-02508 | GDL17 | Residencial | 7.6 | Period | 2026-01-22 15:16 | January | 2026 | 2026-01-26 15:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02509 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 10:26 | February | 2026 | 2026-02-16 16:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 49
202601-NM25-02510 | GDL17 | Residencial | 10.528 | Period | 2026-01-22 15:33 | January | 2026 | 2026-01-26 13:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02511 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 15:38 | January | 2026 | 2026-01-26 15:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02512 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 15:21 | January | 2026 | 2026-01-26 13:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02514 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 18:31 | February | 2026 | 2026-02-25 14:18 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 42
202601-NM25-02515 | GDL17 | Residencial | 8 | Period | 2026-01-23 12:02 | January | 2026 | 2026-01-28 18:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 5 | 0 | 2026-04-01 | 67
202601-NM25-02516 | GDL17 | Residencial | 10.672 | Period | 2026-01-22 15:50 | January | 2026 | 2026-01-26 14:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02517 | GDL17 | Residencial | 13.804 | Period | 2026-01-22 15:45 | January | 2026 | 2026-01-26 15:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02518 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 15:49 | January | 2026 | 2026-01-23 10:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 68
202601-NM25-02519 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 18:13 | March | 2026 | 2026-04-24 09:56 | 44 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | April |  | 44 | 41 | 2026-04-01 | 20
202601-NM25-02520 | GDL17 | Residencial | 9.136 | Period | 2026-01-22 15:56 | January | 2026 | 2026-01-26 14:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02521 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 16:08 | January | 2026 | 2026-02-03 10:17 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 68
202601-NM25-02522 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:36 | March | 2026 | 2026-03-23 10:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 13
202601-NM25-02523 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 16:15 | January | 2026 | 2026-02-05 15:36 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 14 | 0 | 2026-04-01 | 68
202601-NM25-02524 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 16:26 | January | 2026 | 2026-01-29 15:31 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-02525 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 16:33 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 68
202601-NM25-02526 | GDL17 | Residencial | 3.54 | Period | 2026-01-22 16:34 | January | 2026 | 2026-01-29 15:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 7 | 0 | 2026-04-01 | 68
202601-NM25-02527 | GDL17 | Residencial | 14.29 | Period | 2026-01-22 16:35 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 68
202601-NM25-02528 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 12:51 | March | 2026 | 2026-03-23 09:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 12
202601-NM25-02529 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:39 | February | 2026 | 2026-03-04 09:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202601-NM25-02530 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 16:50 | January | 2026 | 2026-01-26 10:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02531 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 17:10 | January | 2026 | 2026-01-26 11:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 68
202601-NM25-02532 | GDL17 | Residencial | 11.5 | Period | 2026-01-22 16:58 | January | 2026 | 2026-02-12 10:21 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 68
202601-NM25-02533 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:45 | February | 2026 | 2026-02-09 10:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 57
202601-NM25-02534 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:07 | February | 2026 | 2026-02-20 08:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202601-NM25-02535 | GDL17 | Residencial | 23 | Period | 2026-02-02 19:42 | February | 2026 | 2026-02-25 13:37 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 23 | 0 | 2026-04-01 | 57
202601-NM25-02538 | GDL17 | Residencial | 3.84 | Period | 2026-03-11 17:52 | March | 2026 | 2026-03-16 14:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 20
202601-NM25-02539 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:41 | March | 2026 | 2026-03-26 09:03 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 9 | 0 | 2026-04-01 | 15
202601-NM25-02543 | GDL17 | Residencial | 7.846 | Period | 2026-01-23 10:01 | January | 2026 | 2026-01-26 14:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02546 | GDL17 | Residencial | 12 | Period | 2026-02-23 09:54 | February | 2026 | 2026-02-27 08:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 37
202601-NM25-02547 | GDL17 | Residencial | 3.84 | Period | 2026-01-28 14:05 | January | 2026 | 2026-02-03 11:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-02548 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 08:35 | January | 2026 | 2026-01-26 15:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02549 | GDL17 | Residencial | 7.68 | Period | 2026-02-05 16:47 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 54
202601-NM25-02550 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 09:13 | January | 2026 | 2026-01-26 12:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02551 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 11:09 | February | 2026 | 2026-03-06 09:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 33
202601-NM25-02552 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:27 | January | 2026 | 2026-01-28 09:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 68
202601-NM25-02553 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:15 | January | 2026 | 2026-02-05 12:42 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 63
202601-NM25-02554 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:16 | January | 2026 | 2026-02-04 07:59 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 65
202601-NM25-02555 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 15:00 | January | 2026 | 2026-02-03 16:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-02556 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 09:33 | January | 2026 | 2026-01-28 14:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 68
202601-NM25-02559 | GDL17 | Comercial | 10 | Period | 2026-01-27 08:23 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 64
202601-NM25-02560 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:35 | March | 2026 | 2026-03-30 15:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202601-NM25-02562 | GDL17 | Residencial | 10.368 | Period | 2026-01-28 07:27 | January | 2026 | 2026-02-03 11:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 63
202601-NM25-02563 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:39 | January | 2026 | 2026-02-06 15:35 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 5 | 4 | 2026-04-01 | 62
202601-NM25-02564 | GDL17 | Residencial | 19.1 | Period | 2026-02-03 13:27 | February | 2026 | 2026-02-05 10:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-02565 | GDL17 | Residencial | 15.76 | Period | 2026-01-23 17:05 | January | 2026 | 2026-01-26 14:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02567 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 10:47 | January | 2026 | 2026-01-26 16:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02568 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 10:57 | January | 2026 | 2026-02-09 09:53 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 17 | 0 | 2026-04-01 | 68
202601-NM25-02569 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 11:02 | January | 2026 | 2026-01-26 11:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02570 | GDL17 | Residencial | 19.51 | Period | 2026-01-23 14:05 | January | 2026 | 2026-02-02 13:20 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 10 | 0 | 2026-04-01 | 67
202601-NM25-02571 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 18:48 | March | 2026 | 2026-03-10 09:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 27
202601-NM25-02572 | GDL17 | Comercial | 13.6 | Period | 2026-01-24 11:45 | January | 2026 | 2026-02-03 15:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 67
202601-NM25-02573 | GDL17 | Residencial | 11.4 | Period | 2026-02-15 14:47 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 44
202601-NM25-02574 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 14:05 | March | 2026 | 2026-03-16 10:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202601-NM25-02575 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:31 | January | 2026 | 2026-01-29 11:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 68
202601-NM25-02576 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 13:38 | March | 2026 | 2026-03-19 07:42 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 19
202601-NM25-02578 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:50 | January | 2026 | 2026-01-26 11:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02579 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 12:27 | January | 2026 | 2026-01-26 10:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02581 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 11:37 | January | 2026 | 2026-01-26 16:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02582 | GDL17 | Residencial | 11.4 | Period | 2026-02-12 08:25 | February | 2026 | 2026-02-13 11:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 48
202601-NM25-02583 | GDL17 | Residencial | 6.296 | Period | 2026-01-23 11:53 | January | 2026 | 2026-01-26 10:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 68
202601-NM25-02585 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 14:10 | March | 2026 | 2026-03-17 08:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 18
202601-NM25-02586 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:04 | February | 2026 | 2026-02-26 14:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202601-NM25-02587 | GDL17 | Residencial | 11.26 | Period | 2026-01-23 12:10 | January | 2026 | 2026-01-26 10:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02588 | GDL17 | Residencial | 7.536 | Period | 2026-01-23 12:20 | January | 2026 | 2026-01-26 10:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02589 | GDL17 | Residencial | 15 | Period | 2026-01-24 15:14 | January | 2026 | 2026-01-29 18:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 66
202601-NM25-02590 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 12:36 | January | 2026 | 2026-01-29 15:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 67
202601-NM25-02591 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 12:48 | January | 2026 | 2026-01-28 15:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 5 | 0 | 2026-04-01 | 67
202601-NM25-02592 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:35 | March | 2026 | 2026-04-01 14:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 5
202601-NM25-02593 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 12:40 | January | 2026 | 2026-01-26 10:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02594 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 13:35 | March | 2026 | 2026-03-13 14:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 20
202601-NM25-02595 | GDL17 | Residencial | 8 | Period | 2026-02-19 08:27 | February | 2026 | 2026-02-24 08:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-02596 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:43 | March | 2026 | 2026-03-05 09:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 28
202601-NM25-02597 | GDL17 | Residencial | 13.144 | Period | 2026-01-23 13:00 | January | 2026 | 2026-01-30 09:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | January | 1 | 1 | 6 | 2026-04-01 | 67
202601-NM25-02598 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 14:09 | January | 2026 | 2026-01-29 10:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 67
202601-NM25-02599 | GDL17 | Residencial | 9 | Period | 2026-01-23 13:48 | January | 2026 | 2026-01-28 14:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 5 | 0 | 2026-04-01 | 67
202601-NM25-02601 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:14 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 12
202601-NM25-02602 | GDL17 | Residencial | 15 | Period | 2026-01-24 18:02 | January | 2026 | 2026-01-26 15:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 66
202601-NM25-02603 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:31 | March | 2026 | 2026-03-12 15:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-02604 | GDL17 | Residencial | 23 | Period | 2026-01-23 13:02 | January | 2026 | 2026-01-29 17:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 6 | 0 | 2026-04-01 | 67
202601-NM25-02605 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:04 | January | 2026 | 2026-01-30 14:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 67
202601-NM25-02606 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:05 | March | 2026 | 2026-04-08 09:07 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | April |  | 35 | 0 | 2026-04-01 | 27
202601-NM25-02607 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:16 | January | 2026 | 2026-01-28 12:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 65
202601-NM25-02608 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 12:51 | March | 2026 | 2026-04-14 15:11 | 33 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 33 | 30 | 2026-04-01 | 19
202601-NM25-02609 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:28 | January | 2026 | 2026-01-26 15:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02611 | GDL17 | Residencial | 15 | Period | 2026-01-24 18:46 | January | 2026 | 2026-01-26 14:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 66
202601-NM25-02612 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:19 | January | 2026 | 2026-02-06 14:38 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 14 | 0 | 2026-04-01 | 67
202601-NM25-02613 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:57 | March | 2026 | 2026-03-04 10:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 30
202601-NM25-02614 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 13:31 | January | 2026 | 2026-01-26 14:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02615 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 12:01 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 63
202601-NM25-02617 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:44 | February | 2026 | 2026-03-30 16:27 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 34 | 0 | 2026-04-01 | 36
202601-NM25-02618 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:39 | March | 2026 | 2026-03-18 09:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 20
202601-NM25-02619 | GDL17 | Residencial | 5.376 | Period | 2026-01-30 08:12 | January | 2026 | 2026-02-12 15:18 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 61
202601-NM25-02621 | GDL17 | Residencial | 15 | Period | 2026-01-27 11:02 | January | 2026 | 2026-02-02 13:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 64
202601-NM25-02622 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 10:32 | February | 2026 | 2026-02-18 13:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 47
202601-NM25-02623 | GDL17 | Residencial | 8.064 | Period | 2026-01-28 10:16 | January | 2026 | 2026-01-29 12:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-02625 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:47 | March | 2026 | 2026-04-10 11:14 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 28 | 0 | 2026-04-01 | 18
202601-NM25-02626 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 18:07 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 4
202601-NM25-02627 | GDL17 | Residencial | 10 | Period | 2026-02-04 19:54 | February | 2026 | 2026-02-09 14:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202601-NM25-02629 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 08:38 | February | 2026 | 2026-02-11 10:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 51
202601-NM25-02630 | GDL17 | Residencial | 19.1 | Period | 2026-01-23 15:15 | January | 2026 | 2026-01-28 08:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 5 | 0 | 2026-04-01 | 67
202601-NM25-02632 | GDL17 | Residencial | 8 | Period | 2026-01-26 17:49 | January | 2026 | 2026-01-28 13:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02633 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:25 | January | 2026 | 2026-01-28 13:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 5 | 0 | 2026-04-01 | 67
202601-NM25-02634 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:22 | January | 2026 | 2026-03-04 15:18 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 31 | 4 | 2026-04-01 | 62
202601-NM25-02635 | GDL17 | Residencial | 7.6 | Period | 2026-01-23 15:29 | January | 2026 | 2026-01-26 15:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02636 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:22 | March | 2026 | 2026-03-17 10:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 19
202601-NM25-02637 | GDL17 | Residencial | 12 | Period | 2026-01-26 18:15 | January | 2026 | 2026-01-28 14:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02638 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 15:38 | January | 2026 | 2026-01-30 07:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 7 | 0 | 2026-04-01 | 67
202601-NM25-02640 | GDL17 | Residencial | 4.608 | Period | 2026-03-20 10:28 | March | 2026 | 2026-03-26 14:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 2 | 4 | 2026-04-01 | 12
202601-NM25-02642 | GDL17 | Residencial | 8.448 | Period | 2026-01-23 15:54 | January | 2026 | 2026-01-26 14:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02643 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 16:01 | January | 2026 | 2026-01-29 08:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 67
202601-NM25-02644 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:18 | January | 2026 | 2026-02-09 08:54 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 65
202601-NM25-02645 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 16:08 | January | 2026 | 2026-01-29 13:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 6 | 0 | 2026-04-01 | 67
202601-NM25-02646 | GDL17 | Residencial | 11.44 | Period | 2026-01-23 16:08 | January | 2026 | 2026-01-26 14:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02648 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 17:33 | March | 2026 | 2026-03-16 10:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202601-NM25-02649 | GDL17 | Residencial | 7.68 | Period | 2026-03-12 09:09 | March | 2026 | 2026-03-17 13:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 20
202601-NM25-02650 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 08:09 | January | 2026 | 2026-01-27 10:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-02651 | GDL17 | Residencial | 5.72 | Period | 2026-01-23 16:48 | January | 2026 | 2026-01-26 14:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02652 | GDL17 | Residencial | 12 | Period | 2026-02-05 00:58 | February | 2026 | 2026-02-09 12:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-02653 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:01 | March | 2026 | 2026-03-26 09:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202601-NM25-02654 | GDL17 | Residencial | 12 | Period | 2026-01-26 18:40 | January | 2026 | 2026-01-29 16:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02656 | GDL17 | Residencial | 8 | Period | 2026-01-27 18:39 | January | 2026 | 2026-02-04 10:01 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 63
202601-NM25-02657 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 17:22 | January | 2026 | 2026-01-30 07:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 6 | 0 | 2026-04-01 | 67
202601-NM25-02658 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 17:27 | January | 2026 | 2026-01-30 15:28 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 7 | 0 | 2026-04-01 | 67
202601-NM25-02659 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:31 | March | 2026 | 2026-03-16 16:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 18
202601-NM25-02660 | GDL17 | Residencial | 12 | Period | 2026-01-28 17:04 | January | 2026 | 2026-01-30 10:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02661 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 17:37 | January | 2026 | 2026-01-26 13:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 67
202601-NM25-02662 | GDL17 | Residencial | 11.5 | Period | 2026-01-23 17:53 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 67
202601-NM25-02663 | GDL17 | Residencial | 12 | Period | 2026-01-28 17:42 | January | 2026 | 2026-02-18 10:16 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 62
202601-NM25-02664 | GDL17 | Residencial | 9 | Period | 2026-01-28 18:32 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 62
202601-NM25-02665 | GDL17 | Residencial | 5.76 | Period | 2026-01-28 12:18 | January | 2026 | 2026-01-29 15:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-02666 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:12 | February | 2026 | 2026-02-23 09:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-02669 | GDL17 | Residencial | 23 | Period | 2026-03-04 19:10 | March | 2026 | 2026-03-06 09:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 27
202601-NM25-02670 | GDL17 | Residencial | 5.76 | Period | 2026-02-18 23:46 | February | 2026 | 2026-02-24 08:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-02674 | GDL17 | Residencial | 11.4 | Period | 2026-02-03 10:20 | February | 2026 | 2026-02-05 11:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-02675 | GDL17 | Residencial | 8 | Period | 2026-02-03 10:23 | February | 2026 | 2026-02-05 14:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-02677 | GDL17 | Residencial | 12 | Period | 2026-01-26 22:55 | January | 2026 | 2026-01-30 10:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 4 | 0 | 2026-04-01 | 64
202601-NM25-02678 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 15:11 | January | 2026 | 2026-01-30 11:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02679 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:51 | February | 2026 | 2026-02-11 09:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-02680 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 08:03 | January | 2026 | 2026-02-06 14:57 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 65
202601-NM25-02681 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 08:00 | January | 2026 | 2026-02-05 08:07 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 65
202601-NM25-02682 | GDL17 | Residencial | 12 | Period | 2026-01-27 09:29 | January | 2026 | 2026-02-02 15:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 64
202601-NM25-02683 | GDL17 | Comercial | 12 | Period | 2026-02-27 13:56 | February | 2026 | 2026-03-06 10:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 32
202601-NM25-02684 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:10 | February | 2026 | 2026-02-16 15:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 47
202601-NM25-02685 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 15:02 | February | 2026 | 2026-02-19 08:56 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 49
202601-NM25-02686 | GDL17 | Residencial | 5.376 | Period | 2026-01-27 07:32 | January | 2026 | 2026-02-02 11:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 64
202601-NM25-02687 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:59 | February | 2026 | 2026-02-06 15:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 55
202601-NM25-02690 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:14 | February | 2026 | 2026-02-06 10:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-02692 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:26 | February | 2026 | 2026-02-16 13:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-02693 | GDL17 | Residencial | 16 | Period | 2026-01-27 16:48 | January | 2026 | 2026-02-24 14:25 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 2 | 21 | 6 | 2026-04-01 | 63
202601-NM25-02694 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:06 | February | 2026 | 2026-02-23 07:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202601-NM25-02696 | GDL17 | Residencial | 7.68 | Period | 2026-03-02 17:57 | March | 2026 | 2026-03-16 09:38 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 29
202601-NM25-02697 | GDL17 | Residencial | 3.456 | Period | 2026-03-02 17:01 | March | 2026 | 2026-03-05 09:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 29
202601-NM25-02698 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 09:37 | January | 2026 | 2026-02-05 11:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 61
202601-NM25-02700 | GDL17 | Residencial | 4.608 | Period | 2026-02-17 08:59 | February | 2026 | 2026-02-20 08:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202601-NM25-02702 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:18 | February | 2026 | 2026-02-11 10:58 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 57
202601-NM25-02703 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 14:52 | February | 2026 | 2026-02-25 14:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202601-NM25-02705 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:49 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 56
202601-NM25-02706 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:08 | January | 2026 | 2026-01-30 10:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 4 | 0 | 2026-04-01 | 65
202601-NM25-02707 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:37 | January | 2026 | 2026-01-29 10:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 65
202601-NM25-02709 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:19 | February | 2026 | 2026-02-19 08:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 47
202601-NM25-02710 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:15 | February | 2026 | 2026-02-06 11:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-02711 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 15:27 | January | 2026 | 2026-01-30 09:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02712 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 09:59 | January | 2026 | 2026-01-27 14:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-02713 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:04 | January | 2026 | 2026-02-12 07:58 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 61
202601-NM25-02714 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:23 | February | 2026 | 2026-03-18 09:46 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 20 | 0 | 2026-04-01 | 34
202601-NM25-02716 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:46 | February | 2026 | 2026-02-06 12:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-02717 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:01 | January | 2026 | 2026-01-30 10:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 65
202601-NM25-02718 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 15:52 | January | 2026 | 2026-01-30 14:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02719 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 11:30 | January | 2026 | 2026-02-02 10:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-02720 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 10:10 | January | 2026 | 2026-02-04 09:01 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 65
202601-NM25-02721 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:51 | January | 2026 | 2026-02-04 11:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 62
202601-NM25-02722 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 10:47 | January | 2026 | 2026-01-29 17:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 65
202601-NM25-02723 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:04 | January | 2026 | 2026-01-27 14:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-02724 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:50 | January | 2026 | 2026-01-29 09:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02725 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 09:13 | January | 2026 | 2026-02-03 16:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-02726 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:20 | January | 2026 | 2026-01-28 16:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02727 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 18:51 | March | 2026 | 2026-03-18 13:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 15
202601-NM25-02728 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 11:31 | January | 2026 | 2026-01-30 07:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 65
202601-NM25-02729 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:45 | March | 2026 | 2026-03-05 13:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 28
202601-NM25-02730 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 13:41 | February | 2026 | 2026-02-11 10:31 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 56
202601-NM25-02732 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 07:28 | January | 2026 | 2026-01-29 15:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-02733 | GDL17 | Residencial | 7.322 | Period | 2026-01-26 11:43 | January | 2026 | 2026-01-27 12:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 65
202601-NM25-02734 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:06 | March | 2026 | 2026-03-09 14:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 29
202601-NM25-02736 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 13:27 | January | 2026 | 2026-01-29 10:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02737 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 12:13 | January | 2026 | 2026-01-27 12:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-02739 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 07:37 | January | 2026 | 2026-01-30 11:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02740 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:03 | January | 2026 | 2026-01-28 09:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02741 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 12:19 | January | 2026 | 2026-01-30 13:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 4 | 0 | 2026-04-01 | 64
202601-NM25-02742 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:45 | March | 2026 | 2026-03-05 15:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 28
202601-NM25-02744 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 12:37 | January | 2026 | 2026-02-10 09:01 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 15 | 0 | 2026-04-01 | 64
202601-NM25-02745 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:41 | January | 2026 | 2026-02-03 13:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-02747 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 07:37 | February | 2026 | 2026-02-06 16:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 55
202601-NM25-02748 | GDL17 | Residencial | 8 | Period | 2026-03-12 09:04 | March | 2026 | 2026-03-17 12:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 20
202601-NM25-02749 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:21 | January | 2026 | 2026-01-28 16:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02750 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:29 | January | 2026 | 2026-01-28 16:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02751 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:44 | February | 2026 | 2026-02-04 13:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-02752 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:00 | March | 2026 | 2026-03-18 15:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 15
202601-NM25-02753 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:37 | January | 2026 | 2026-01-28 15:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02754 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:48 | January | 2026 | 2026-01-27 16:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-02755 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:45 | January | 2026 | 2026-01-28 15:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02756 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:54 | January | 2026 | 2026-01-29 12:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02757 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:28 | February | 2026 | 2026-03-05 13:13 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 35
202601-NM25-02758 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 13:55 | January | 2026 | 2026-01-29 18:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02759 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:52 | March | 2026 | 2026-03-12 13:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 22
202601-NM25-02760 | GDL17 | Residencial | 23 | Period | 2026-03-24 13:44 | March | 2026 | 2026-03-30 09:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 7
202601-NM25-02761 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:16 | January | 2026 | 2026-01-27 16:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-02762 | GDL17 | Residencial | 4.224 | Period | 2026-01-27 10:12 | January | 2026 | 2026-02-25 07:45 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 28 | 0 | 2026-04-01 | 64
202601-NM25-02763 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:17 | February | 2026 | 2026-02-27 09:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202601-NM25-02765 | GDL17 | Comercial | 11.5 | Period | 2026-01-26 14:25 | January | 2026 | 2026-01-29 07:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02766 | GDL17 | Residencial | 6.528 | Period | 2026-01-26 15:03 | January | 2026 | 2026-01-30 08:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 4 | 0 | 2026-04-01 | 64
202601-NM25-02767 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:36 | January | 2026 | 2026-01-28 10:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02769 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:50 | January | 2026 | 2026-01-30 08:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 4 | 0 | 2026-04-01 | 64
202601-NM25-02770 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 13:47 | February | 2026 | 2026-02-16 15:06 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 12 | 0 | 2026-04-01 | 55
202601-NM25-02771 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:46 | January | 2026 | 2026-01-29 10:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02772 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 12:08 | January | 2026 | 2026-01-29 10:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02773 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 14:58 | January | 2026 | 2026-01-29 09:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02774 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:47 | January | 2026 | 2026-02-04 15:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 62
202601-NM25-02775 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:11 | January | 2026 | 2026-01-28 09:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02777 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:13 | January | 2026 | 2026-02-05 07:41 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 10 | 0 | 2026-04-01 | 64
202601-NM25-02779 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:12 | January | 2026 | 2026-01-28 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02780 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:11 | January | 2026 | 2026-01-28 09:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02783 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:06 | January | 2026 | 2026-01-29 15:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02784 | GDL17 | Residencial | 4.85 | Period | 2026-01-26 15:38 | January | 2026 | 2026-01-28 10:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02786 | GDL17 | Residencial | 5.95 | Period | 2026-01-26 15:21 | January | 2026 | 2026-01-28 09:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02787 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:23 | January | 2026 | 2026-01-28 09:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02788 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:28 | January | 2026 | 2026-01-28 10:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02791 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 15:38 | January | 2026 | 2026-02-04 08:47 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 64
202601-NM25-02792 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:33 | January | 2026 | 2026-01-28 10:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02794 | GDL17 | Residencial | 6.3 | Period | 2026-01-28 13:53 | January | 2026 | 2026-01-30 09:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-02795 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:56 | January | 2026 | 2026-01-28 11:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02796 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 15:53 | January | 2026 | 2026-01-28 10:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02797 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 08:15 | February | 2026 | 2026-02-06 10:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 58
202601-NM25-02798 | GDL17 | Residencial | 4.786 | Period | 2026-01-26 16:05 | January | 2026 | 2026-01-28 11:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02799 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:09 | January | 2026 | 2026-02-03 12:52 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 64
202601-NM25-02800 | GDL17 | Residencial | 8 | Period | 2026-02-04 16:15 | February | 2026 | 2026-02-09 13:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202601-NM25-02801 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:21 | January | 2026 | 2026-01-28 15:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02802 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:21 | January | 2026 | 2026-01-29 15:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02803 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:30 | January | 2026 | 2026-02-02 09:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 64
202601-NM25-02804 | GDL17 | Residencial | 3.072 | Period | 2026-01-26 16:29 | January | 2026 | 2026-01-28 12:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02805 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 16:35 | January | 2026 | 2026-02-09 08:23 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 14 | 0 | 2026-04-01 | 64
202601-NM25-02806 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:41 | January | 2026 | 2026-01-28 13:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02807 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:49 | January | 2026 | 2026-01-29 12:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02809 | GDL17 | Residencial | 7.6 | Period | 2026-01-26 16:48 | January | 2026 | 2026-02-09 11:28 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 14 | 0 | 2026-04-01 | 64
202601-NM25-02810 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:51 | January | 2026 | 2026-01-28 13:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02811 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 16:52 | January | 2026 | 2026-02-11 15:18 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 16 | 0 | 2026-04-01 | 64
202601-NM25-02812 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:00 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 64
202601-NM25-02813 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:16 | January | 2026 | 2026-01-28 13:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02814 | GDL17 | Residencial | 5.196 | Period | 2026-01-26 17:10 | January | 2026 | 2026-01-28 13:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02815 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:30 | January | 2026 | 2026-02-03 13:04 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 64
202601-NM25-02816 | GDL17 | Residencial | 8 | Period | 2026-01-28 13:28 | January | 2026 | 2026-02-02 11:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-02817 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:47 | January | 2026 | 2026-02-03 08:38 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 64
202601-NM25-02818 | GDL17 | Residencial | 11.5 | Period | 2026-01-26 17:52 | January | 2026 | 2026-02-02 07:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 64
202601-NM25-02819 | GDL17 | Residencial | 8 | Period | 2026-01-26 18:04 | January | 2026 | 2026-01-28 13:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02820 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 16:49 | February | 2026 | 2026-02-13 16:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 47
202601-NM25-02821 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:17 | February | 2026 | 2026-02-16 11:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-02822 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 07:21 | February | 2026 | 2026-03-03 14:28 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 15 | 0 | 2026-04-01 | 43
202601-NM25-02823 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:18 | February | 2026 | 2026-02-23 09:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-02824 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:47 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 12
202601-NM25-02825 | GDL17 | Residencial | 4.8 | Period | 2026-01-27 08:29 | January | 2026 | 2026-02-09 08:12 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 64
202601-NM25-02826 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 08:58 | February | 2026 | 2026-02-05 12:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-02827 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 11:34 | February | 2026 | 2026-02-16 12:58 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 55
202601-NM25-02828 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 14:03 | January | 2026 | 2026-02-03 12:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-02829 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 08:37 | January | 2026 | 2026-02-02 10:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 64
202601-NM25-02830 | GDL17 | Residencial | 6.732 | Period | 2026-01-27 08:19 | January | 2026 | 2026-01-29 11:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02831 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 08:21 | January | 2026 | 2026-02-05 13:46 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 9 | 0 | 2026-04-01 | 64
202601-NM25-02833 | GDL17 | Residencial | 13.81 | Period | 2026-01-27 08:34 | January | 2026 | 2026-01-28 14:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-02834 | GDL17 | Residencial | 9.506 | Period | 2026-01-27 08:32 | January | 2026 | 2026-01-29 11:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02835 | GDL17 | Residencial | 6.532 | Period | 2026-01-27 08:41 | January | 2026 | 2026-01-28 15:24 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 64
202601-NM25-02837 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:26 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 64
202601-NM25-02838 | GDL17 | Residencial | 23 | Period | 2026-01-27 10:54 | January | 2026 | 2026-01-29 10:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02839 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:36 | January | 2026 | 2026-02-04 13:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-02841 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 09:22 | March | 2026 | 2026-03-11 08:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 23
202601-NM25-02842 | GDL17 | Residencial | 7.68 | Period | 2026-02-02 14:50 | February | 2026 | 2026-02-04 13:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-02843 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 10:29 | February | 2026 | 2026-02-11 14:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-02844 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 07:14 | February | 2026 | 2026-02-06 08:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 55
202601-NM25-02846 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 09:50 | January | 2026 | 2026-02-03 10:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 64
202601-NM25-02847 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 10:27 | January | 2026 | 2026-02-04 08:29 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 64
202601-NM25-02849 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 17:12 | February | 2026 | 2026-03-02 14:52 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 40
202601-NM25-02850 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 17:41 | February | 2026 | 2026-02-16 14:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-02851 | GDL17 | Residencial | 11.5 | Period | 2026-02-15 13:35 | February | 2026 | 2026-02-19 11:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 44
202601-NM25-02853 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:41 | February | 2026 | 2026-03-03 08:37 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 37
202601-NM25-02854 | GDL17 | Residencial | 3.84 | Period | 2026-01-27 10:45 | January | 2026 | 2026-01-29 10:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02856 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:31 | January | 2026 | 2026-03-05 13:58 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 35 | 0 | 2026-04-01 | 61
202601-NM25-02857 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 10:15 | January | 2026 | 2026-01-29 14:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02858 | GDL17 | Comercial | 24.96 | Period | 2026-02-20 13:08 | February | 2026 | 2026-02-25 15:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202601-NM25-02860 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 13:25 | March | 2026 | 2026-04-01 14:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 5 | 0 | 2026-04-01 | 4
202601-NM25-02861 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:58 | January | 2026 | 2026-01-29 15:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02862 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:47 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 63
202601-NM25-02865 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:16 | March | 2026 | 2026-04-09 10:36 | 31 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | April |  | 31 | 30 | 2026-04-01 | 23
202601-NM25-02869 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:47 | January | 2026 | 2026-01-30 13:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02870 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 10:49 | January | 2026 | 2026-01-30 15:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02871 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 10:58 | January | 2026 | 2026-02-02 09:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 64
202601-NM25-02872 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:01 | January | 2026 | 2026-01-29 11:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02875 | GDL17 | Residencial | 24.43 | Period | 2026-01-27 13:55 | January | 2026 | 2026-01-29 15:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02877 | GDL17 | Residencial | 3.456 | Period | 2026-01-27 11:43 | January | 2026 | 2026-01-30 09:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 3 | 0 | 2026-04-01 | 64
202601-NM25-02878 | GDL17 | Residencial | 15.2 | Period | 2026-01-27 11:34 | January | 2026 | 2026-01-29 10:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02879 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 19:21 | March | 2026 | 2026-03-06 13:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 27
202601-NM25-02881 | GDL17 | Residencial | 5.58 | Period | 2026-01-27 14:47 | January | 2026 | 2026-01-29 15:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02882 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:29 | January | 2026 | 2026-01-29 09:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02883 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 18:50 | March | 2026 | 2026-03-18 07:53 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 21
202601-NM25-02884 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 11:55 | January | 2026 | 2026-02-02 10:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 64
202601-NM25-02885 | GDL17 | Residencial | 12 | Period | 2026-02-06 14:19 | February | 2026 | 2026-02-10 14:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 53
202601-NM25-02886 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 12:22 | March | 2026 | 2026-03-18 12:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 19
202601-NM25-02887 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 13:08 | January | 2026 | 2026-02-03 15:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 63
202601-NM25-02889 | GDL17 | Residencial | 3.072 | Period | 2026-01-27 11:50 | January | 2026 | 2026-01-29 13:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 64
202601-NM25-02890 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 12:38 | January | 2026 | 2026-02-10 11:07 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 60
202601-NM25-02891 | GDL17 | Residencial | 4.608 | Period | 2026-02-13 16:10 | February | 2026 | 2026-02-18 08:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 46
202601-NM25-02893 | GDL17 | Residencial | 17.26 | Period | 2026-01-27 12:03 | January | 2026 | 2026-01-29 11:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02894 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:35 | March | 2026 | 2026-03-31 12:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 6
202601-NM25-02895 | GDL17 | Residencial | 6.954 | Period | 2026-01-27 12:13 | January | 2026 | 2026-02-06 13:21 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 63
202601-NM25-02896 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:20 | March | 2026 | 2026-03-31 14:36 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 29 | 0 | 2026-04-01 | 29
202601-NM25-02897 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:41 | March | 2026 | 2026-04-13 08:33 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 34 | 9 | 2026-04-01 | 22
202601-NM25-02898 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 17:29 | March | 2026 | 2026-03-05 08:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202601-NM25-02899 | GDL17 | Residencial | 9 | Period | 2026-02-08 10:03 | February | 2026 | 2026-02-11 12:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 52
202601-NM25-02900 | GDL17 | Comercial | 11.5 | Period | 2026-01-27 12:33 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 63
202601-NM25-02901 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:50 | March | 2026 | 2026-03-23 15:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 12
202601-NM25-02902 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:01 | January | 2026 | 2026-02-02 11:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-02903 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:27 | March | 2026 | 2026-03-10 08:18 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 29
202601-NM25-02904 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 12:37 | January | 2026 | 2026-01-30 13:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 3 | 0 | 2026-04-01 | 63
202601-NM25-02905 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:34 | February | 2026 | 2026-02-10 10:26 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 5 | 3 | 2026-04-01 | 57
202601-NM25-02906 | GDL17 | Residencial | 4.72 | Period | 2026-01-27 16:20 | January | 2026 | 2026-01-29 15:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02907 | GDL17 | Residencial | 8.682 | Period | 2026-01-27 12:54 | January | 2026 | 2026-01-29 14:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02908 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 12:58 | January | 2026 | 2026-02-03 13:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 63
202601-NM25-02910 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:10 | January | 2026 | 2026-02-04 14:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-02911 | GDL17 | Residencial | 7.832 | Period | 2026-01-27 13:06 | January | 2026 | 2026-01-29 14:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02912 | GDL17 | Residencial | 6.902 | Period | 2026-01-27 13:11 | January | 2026 | 2026-01-29 15:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02913 | GDL17 | Residencial | 23 | Period | 2026-01-27 13:24 | January | 2026 | 2026-02-04 08:39 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 63
202601-NM25-02914 | GDL17 | Residencial | 6.846 | Period | 2026-01-27 13:22 | January | 2026 | 2026-01-29 15:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02915 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 14:27 | January | 2026 | 2026-02-10 10:03 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 61
202601-NM25-02916 | GDL17 | Residencial | 12 | Period | 2026-02-02 13:35 | February | 2026 | 2026-02-10 09:43 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 57
202601-NM25-02917 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 15:24 | January | 2026 | 2026-01-30 09:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-02918 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:51 | January | 2026 | 2026-02-10 15:20 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 12 | 0 | 2026-04-01 | 61
202601-NM25-02919 | GDL17 | Residencial | 12.644 | Period | 2026-01-27 13:35 | January | 2026 | 2026-01-29 10:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02921 | GDL17 | Residencial | 6.362 | Period | 2026-01-27 13:43 | January | 2026 | 2026-01-29 12:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02924 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:56 | January | 2026 | 2026-01-30 12:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 3 | 0 | 2026-04-01 | 63
202601-NM25-02926 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 08:22 | January | 2026 | 2026-02-03 13:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-02927 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:42 | January | 2026 | 2026-02-10 15:06 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 14 | 0 | 2026-04-01 | 63
202601-NM25-02929 | GDL17 | Residencial | 7.6 | Period | 2026-03-06 14:17 | March | 2026 | 2026-03-09 13:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 25
202601-NM25-02930 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 09:29 | January | 2026 | 2026-02-04 09:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 62
202601-NM25-02932 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 11:46 | March | 2026 | 2026-03-23 12:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 14
202601-NM25-02933 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 14:36 | January | 2026 | 2026-02-09 09:35 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 63
202601-NM25-02934 | GDL17 | Comercial | 9.586 | Period | 2026-01-27 14:41 | January | 2026 | 2026-01-29 15:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02935 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 12:49 | March | 2026 | 2026-03-17 13:27 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-02936 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:35 | February | 2026 | 2026-02-09 12:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 54
202601-NM25-02937 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:25 | January | 2026 | 2026-01-29 12:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02938 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 12:10 | March | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 13
202601-NM25-02940 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 11:16 | January | 2026 | 2026-02-04 15:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-02941 | GDL17 | Residencial | 7.6 | Period | 2026-02-27 15:37 | February | 2026 | 2026-03-03 16:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 32
202601-NM25-02942 | GDL17 | Residencial | 8 | Period | 2026-02-19 08:13 | February | 2026 | 2026-02-25 09:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202601-NM25-02943 | GDL17 | Residencial | 7.6 | Period | 2026-03-19 05:41 | March | 2026 | 2026-03-26 11:19 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 13
202601-NM25-02944 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 15:45 | January | 2026 | 2026-02-03 12:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 63
202601-NM25-02946 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:57 | January | 2026 | 2026-02-04 09:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | February | 1 | 5 | 2 | 2026-04-01 | 63
202601-NM25-02947 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 13:10 | March | 2026 | 2026-03-20 10:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 13
202601-NM25-02948 | GDL17 | Residencial | 11.346 | Period | 2026-02-25 14:28 | February | 2026 | 2026-03-02 10:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202601-NM25-02949 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 16:13 | January | 2026 | 2026-02-03 08:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 63
202601-NM25-02950 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 16:13 | January | 2026 | 2026-01-30 14:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 3 | 0 | 2026-04-01 | 63
202601-NM25-02951 | GDL17 | Residencial | 11.5 | Period | 2026-01-27 16:25 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 63
202601-NM25-02953 | GDL17 | Residencial | 5.804 | Period | 2026-01-27 16:17 | January | 2026 | 2026-01-29 11:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02954 | GDL17 | Residencial | 8.992 | Period | 2026-01-27 16:28 | January | 2026 | 2026-01-29 11:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02955 | GDL17 | Residencial | 13.036 | Period | 2026-01-27 16:41 | January | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 63
202601-NM25-02956 | GDL17 | Residencial | 7.6 | Period | 2026-01-27 16:40 | January | 2026 | 2026-01-29 11:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 63
202601-NM25-02958 | GDL17 | Residencial | 12 | Period | 2026-02-08 12:20 | February | 2026 | 2026-02-11 15:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 51
202601-NM25-02959 | GDL17 | Residencial | 9.136 | Period | 2026-01-28 10:39 | January | 2026 | 2026-02-04 09:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 2 | 5 | 2026-04-01 | 63
202601-NM25-02960 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:50 | March | 2026 | 2026-03-26 14:19 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 24 | 0 | 2026-04-01 | 29
202601-NM25-02961 | GDL17 | Residencial | 9 | Period | 2026-01-27 20:22 | January | 2026 | 2026-02-20 15:17 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 24 | 0 | 2026-04-01 | 63
202601-NM25-02964 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 17:19 | March | 2026 | 2026-03-18 15:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 18
202601-NM25-02966 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:21 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 33
202601-NM25-02967 | GDL17 | Residencial | 7.32 | Period | 2026-02-05 05:29 | February | 2026 | 2026-02-06 13:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 55
202601-NM25-02968 | GDL17 | Residencial | 6.72 | Period | 2026-02-06 22:09 | February | 2026 | 2026-02-10 14:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 53
202601-NM25-02970 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 07:50 | February | 2026 | 2026-02-18 11:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 48
202601-NM25-02971 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 09:46 | January | 2026 | 2026-02-04 10:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 62
202601-NM25-02972 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 07:52 | January | 2026 | 2026-02-06 08:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 61
202601-NM25-02974 | GDL17 | Residencial | 7.68 | Period | 2026-01-28 08:16 | January | 2026 | 2026-02-03 08:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 63
202601-NM25-02975 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:50 | February | 2026 | 2026-02-24 08:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202601-NM25-02976 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 08:47 | January | 2026 | 2026-01-29 16:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-02978 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:09 | March | 2026 | 2026-03-31 14:23 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 8
202601-NM25-02979 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:21 | January | 2026 | 2026-02-03 13:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-02981 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:40 | February | 2026 | 2026-02-06 13:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-02984 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:20 | February | 2026 | 2026-02-06 11:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-02985 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:02 | January | 2026 | 2026-02-17 14:48 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 20 | 0 | 2026-04-01 | 63
202601-NM25-02991 | GDL17 | Residencial | 3.8 | Period | 2026-03-30 15:11 | March | 2026 | 2026-04-02 09:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 3 | 0 | 2026-04-01 | 1
202601-NM25-02993 | GDL17 | Residencial | 7.68 | Period | 2026-02-19 09:05 | February | 2026 | 2026-02-27 08:23 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 41
202601-NM25-02995 | GDL17 | Residencial | 9.136 | Period | 2026-01-28 11:20 | January | 2026 | 2026-01-29 11:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-02996 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 09:59 | February | 2026 | 2026-02-16 09:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 49
202601-NM25-02998 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 07:36 | February | 2026 | 2026-02-06 09:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-03000 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 09:40 | January | 2026 | 2026-01-29 16:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-03001 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:15 | February | 2026 | 2026-02-06 10:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-03002 | GDL17 | Residencial | 12 | Period | 2026-01-28 18:44 | January | 2026 | 2026-01-30 12:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03003 | GDL17 | Comercial | 11.5 | Period | 2026-02-26 10:57 | February | 2026 | 2026-03-09 10:13 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 34
202601-NM25-03004 | GDL17 | Residencial | 9.394 | Period | 2026-01-28 09:53 | January | 2026 | 2026-02-24 08:01 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 7 | 20 | 2026-04-01 | 63
202601-NM25-03005 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:09 | March | 2026 | 2026-04-02 14:11 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 16 | 0 | 2026-04-01 | 15
202601-NM25-03006 | GDL17 | Residencial | 3.8 | Period | 2026-03-17 14:08 | March | 2026 | 2026-03-18 15:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 14
202601-NM25-03009 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:24 | February | 2026 | 2026-02-05 13:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 57
202601-NM25-03011 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 14:21 | March | 2026 | 2026-03-16 14:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202601-NM25-03016 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 11:40 | March | 2026 | 2026-03-18 11:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 16
202601-NM25-03019 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 14:51 | February | 2026 | 2026-02-27 10:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 35
202601-NM25-03020 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:33 | January | 2026 | 2026-02-03 13:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 63
202601-NM25-03023 | GDL17 | Residencial | 3.84 | Period | 2026-02-03 13:26 | February | 2026 | 2026-02-05 13:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-03024 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 10:20 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 63
202601-NM25-03025 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:45 | March | 2026 | 2026-03-18 13:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202601-NM25-03026 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:23 | February | 2026 | 2026-02-11 16:17 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 57
202601-NM25-03027 | GDL17 | Residencial | 7.6 | Period | 2026-02-09 08:37 | February | 2026 | 2026-02-10 15:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 51
202601-NM25-03028 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 15:11 | March | 2026 | 2026-03-13 07:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-03030 | GDL17 | Residencial | 3.8 | Period | 2026-01-28 14:12 | January | 2026 | 2026-01-30 13:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03031 | GDL17 | Residencial | 24.576 | Period | 2026-02-05 10:24 | February | 2026 | 2026-02-09 10:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-03032 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:29 | February | 2026 | 2026-02-16 15:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 47
202601-NM25-03033 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 14:10 | March | 2026 | 2026-03-20 08:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 13
202601-NM25-03034 | GDL17 | Residencial | 23 | Period | 2026-03-09 10:44 | March | 2026 | 2026-03-17 09:19 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 23
202601-NM25-03037 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:05 | February | 2026 | 2026-02-09 11:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 57
202601-NM25-03038 | GDL17 | Residencial | 3.84 | Period | 2026-01-30 13:15 | January | 2026 | 2026-02-03 09:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03039 | GDL17 | Residencial | 12 | Period | 2026-02-02 10:44 | February | 2026 | 2026-02-04 08:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-03041 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 11:26 | February | 2026 | 2026-02-16 08:57 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 58
202601-NM25-03042 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:10 | March | 2026 | 2026-04-07 14:49 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 14 | 0 | 2026-04-01 | 8
202601-NM25-03043 | GDL17 | Residencial | 7.68 | Period | 2026-02-09 16:07 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 50
202601-NM25-03045 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:19 | February | 2026 | 2026-02-05 10:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03046 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:26 | January | 2026 | 2026-02-03 13:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03047 | GDL17 | Residencial | 4.992 | Period | 2026-03-26 13:25 | March | 2026 | 2026-03-31 11:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 5
202601-NM25-03048 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 11:04 | February | 2026 | 2026-02-09 16:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-03050 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:49 | March | 2026 | 2026-04-01 14:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 5 | 0 | 2026-04-01 | 5
202601-NM25-03052 | GDL17 | Residencial | 7.102 | Period | 2026-01-28 11:40 | January | 2026 | 2026-01-29 10:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 63
202601-NM25-03053 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 11:47 | January | 2026 | 2026-02-02 13:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 63
202601-NM25-03056 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:20 | February | 2026 | 2026-03-30 08:55 | 54 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | March |  | 53 | 0 | 2026-04-01 | 55
202601-NM25-03058 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 13:02 | March | 2026 | 2026-03-20 14:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 14
202601-NM25-03060 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 10:05 | March | 2026 | 2026-03-17 15:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 16
202601-NM25-03061 | GDL17 | Residencial | 12.61 | Period | 2026-01-28 15:47 | January | 2026 | 2026-01-30 10:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03067 | GDL17 | Residencial | 3 | Period | 2026-01-28 12:04 | January | 2026 | 2026-01-29 13:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-03071 | GDL17 | Residencial | 13.6 | Period | 2026-02-06 13:49 | February | 2026 | 2026-02-10 14:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202601-NM25-03073 | GDL17 | Residencial | 22.026 | Period | 2026-03-17 13:36 | March | 2026 | 2026-03-18 15:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 14
202601-NM25-03074 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:14 | March | 2026 | 2026-03-18 07:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 20
202601-NM25-03075 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 17:57 | February | 2026 | 2026-02-10 13:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-03076 | GDL17 | Residencial | 4.026 | Period | 2026-01-28 12:44 | January | 2026 | 2026-01-30 08:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-03077 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 18:09 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 14
202601-NM25-03080 | GDL17 | Residencial | 3.84 | Period | 2026-02-03 10:42 | February | 2026 | 2026-02-05 14:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03081 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 14:01 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 13
202601-NM25-03082 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:43 | February | 2026 | 2026-02-24 13:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-03083 | GDL17 | Residencial | 4.425 | Period | 2026-01-28 13:12 | January | 2026 | 2026-01-30 11:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03086 | GDL17 | Residencial | 15.36 | Period | 2026-01-28 13:24 | January | 2026 | 2026-03-17 08:25 | 48 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March |  | 47 | 0 | 2026-04-01 | 62
202601-NM25-03089 | GDL17 | Residencial | 4.758 | Period | 2026-02-04 14:44 | February | 2026 | 2026-02-09 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-03090 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 18:23 | March | 2026 | 2026-03-19 11:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 13
202601-NM25-03094 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 13:56 | January | 2026 | 2026-01-30 11:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03095 | GDL17 | Residencial | 8.84 | Period | 2026-01-28 13:56 | January | 2026 | 2026-02-03 13:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-03097 | GDL17 | Residencial | 7.68 | Period | 2026-01-28 14:25 | January | 2026 | 2026-02-02 16:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 4 | 1 | 2026-04-01 | 62
202601-NM25-03101 | GDL17 | Residencial | 8.064 | Period | 2026-02-20 10:31 | February | 2026 | 2026-03-06 09:13 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 40
202601-NM25-03102 | GDL17 | Residencial | 17.6 | Period | 2026-01-28 14:13 | January | 2026 | 2026-01-30 10:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03103 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:00 | March | 2026 | 2026-03-30 11:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 7
202601-NM25-03104 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:11 | March | 2026 | 2026-04-02 09:35 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | April |  | 9 | 4 | 2026-04-01 | 7
202601-NM25-03105 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:44 | January | 2026 | 2026-02-03 13:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03106 | GDL17 | Residencial | 9.022 | Period | 2026-01-28 14:19 | January | 2026 | 2026-01-30 10:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03110 | GDL17 | Residencial | 7.6 | Period | 2026-02-10 15:31 | February | 2026 | 2026-02-11 14:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-03112 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:37 | March | 2026 | 2026-03-26 11:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202601-NM25-03115 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:39 | March | 2026 | 2026-03-30 09:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202601-NM25-03116 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:54 | March | 2026 | 2026-03-30 15:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 8
202601-NM25-03118 | GDL17 | Residencial | 18 | Period | 2026-02-24 16:32 | February | 2026 | 2026-03-23 10:49 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 2 | 7 | 20 | 2026-04-01 | 35
202601-NM25-03120 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:36 | March | 2026 | 2026-03-30 11:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 8
202601-NM25-03121 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 13:23 | March | 2026 | 2026-04-10 10:58 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 24 | 0 | 2026-04-01 | 14
202601-NM25-03125 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 18:15 | March | 2026 | 2026-03-23 09:25 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 18
202601-NM25-03126 | GDL17 | Residencial | 5.196 | Period | 2026-01-28 15:28 | January | 2026 | 2026-01-30 08:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-03128 | GDL17 | Residencial | 23 | Period | 2026-02-04 15:28 | February | 2026 | 2026-02-10 12:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 55
202601-NM25-03129 | GDL17 | Residencial | 19.1 | Period | 2026-01-29 10:43 | January | 2026 | 2026-01-30 16:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-03135 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:08 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 61
202601-NM25-03136 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 10:45 | January | 2026 | 2026-02-05 14:45 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 62
202601-NM25-03138 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 16:36 | January | 2026 | 2026-02-09 11:08 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 12 | 0 | 2026-04-01 | 62
202601-NM25-03139 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 16:44 | January | 2026 | 2026-01-30 10:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03140 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:41 | March | 2026 | 2026-03-06 09:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 27
202601-NM25-03141 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:04 | February | 2026 | 2026-02-25 13:20 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 1 | 11 | 2026-04-01 | 47
202601-NM25-03142 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:21 | March | 2026 | 2026-03-17 14:19 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 21
202601-NM25-03143 | GDL17 | Residencial | 7.6 | Period | 2026-01-28 16:59 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 62
202601-NM25-03145 | GDL17 | Comercial | 15 | Period | 2026-02-08 14:47 | February | 2026 | 2026-02-16 15:55 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 4 | 4 | 2026-04-01 | 51
202601-NM25-03146 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 14:07 | February | 2026 | 2026-02-12 13:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-03147 | GDL17 | Residencial | 11.5 | Period | 2026-02-22 10:31 | February | 2026 | 2026-02-26 08:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 38
202601-NM25-03148 | GDL17 | Residencial | 23 | Period | 2026-03-10 17:18 | March | 2026 | 2026-03-13 13:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 21
202601-NM25-03149 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:22 | February | 2026 | 2026-02-18 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 47
202601-NM25-03151 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 17:24 | February | 2026 | 2026-02-11 14:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-03156 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 16:37 | February | 2026 | 2026-02-12 11:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 53
202601-NM25-03158 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 18:32 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 54
202601-NM25-03159 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 17:59 | January | 2026 | 2026-02-04 09:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 62
202601-NM25-03163 | GDL17 | Residencial | 11.5 | Period | 2026-01-28 18:14 | January | 2026 | 2026-02-17 14:08 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 20 | 0 | 2026-04-01 | 62
202601-NM25-03165 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:46 | March | 2026 | 2026-03-12 07:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-03167 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 17:04 | February | 2026 | 2026-02-27 12:42 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 15 | 0 | 2026-04-01 | 47
202601-NM25-03168 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:35 | March | 2026 | 2026-03-18 15:37 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 21
202601-NM25-03174 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 10:43 | February | 2026 | 2026-03-04 11:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 34
202601-NM25-03175 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:23 | March | 2026 | 2026-03-11 15:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 21
202601-NM25-03178 | GDL17 | Residencial | 6 | Period | 2026-02-03 10:54 | February | 2026 | 2026-02-05 15:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03179 | GDL17 | Residencial | 10 | Period | 2026-03-25 10:39 | March | 2026 | 2026-03-30 11:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 7
202601-NM25-03180 | GDL17 | Residencial | 9 | Period | 2026-02-12 19:46 | February | 2026 | 2026-02-17 07:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202601-NM25-03185 | GDL17 | Residencial | 7.6 | Period | 2026-02-19 20:20 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 40
202601-NM25-03187 | GDL17 | Residencial | 3.8 | Period | 2026-02-23 09:34 | February | 2026 | 2026-03-03 11:12 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 9 | 0 | 2026-04-01 | 37
202601-NM25-03192 | GDL17 | Comercial | 11.5 | Period | 2026-02-14 14:57 | February | 2026 | 2026-02-24 13:12 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 45
202601-NM25-03194 | GDL17 | Residencial | 15 | Period | 2026-01-28 23:17 | January | 2026 | 2026-01-30 13:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03195 | GDL17 | Residencial | 9 | Period | 2026-01-28 23:47 | January | 2026 | 2026-01-30 08:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-03196 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:30 | February | 2026 | 2026-02-12 13:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-03197 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 14:44 | March | 2026 | 2026-03-18 14:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 15
202601-NM25-03200 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:07 | February | 2026 | 2026-02-06 13:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-03205 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 08:23 | January | 2026 | 2026-01-30 13:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | January |  | 2 | 0 | 2026-04-01 | 62
202601-NM25-03209 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:08 | March | 2026 | 2026-03-26 14:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202601-NM25-03212 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:15 | February | 2026 | 2026-02-12 14:07 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 56
202601-NM25-03215 | GDL17 | Residencial | 3.8 | Period | 2026-02-20 13:31 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 39
202601-NM25-03216 | GDL17 | Residencial | 11.346 | Period | 2026-02-19 09:22 | February | 2026 | 2026-02-24 08:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-03217 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 08:49 | January | 2026 | 2026-02-09 09:23 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 11 | 0 | 2026-04-01 | 62
202601-NM25-03220 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 09:18 | January | 2026 | 2026-02-04 10:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-03221 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:39 | February | 2026 | 2026-02-05 13:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03222 | GDL17 | Residencial | 11.5 | Period | 2026-02-28 19:47 | February | 2026 | 2026-03-04 09:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 31
202601-NM25-03224 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:41 | March | 2026 | 2026-03-17 12:41 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 22
202601-NM25-03227 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:19 | March | 2026 | 2026-03-12 08:29 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 30
202601-NM25-03228 | GDL17 | Residencial | 9 | Period | 2026-01-30 13:46 | January | 2026 | 2026-02-04 09:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-03230 | GDL17 | Residencial | 3.8 | Period | 2026-03-03 16:23 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 28
202601-NM25-03233 | GDL17 | Residencial | 4.992 | Period | 2026-01-29 10:22 | January | 2026 | 2026-02-04 10:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-03234 | GDL17 | Residencial | 7.67 | Period | 2026-01-29 10:51 | January | 2026 | 2026-02-02 09:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-03237 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 13:33 | January | 2026 | 2026-02-16 11:01 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 17 | 0 | 2026-04-01 | 60
202601-NM25-03238 | GDL17 | Comercial | 20 | Period | 2026-03-23 16:11 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 8
202601-NM25-03241 | GDL17 | Residencial | 10.62 | Period | 2026-01-29 10:57 | January | 2026 | 2026-02-04 10:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 62
202601-NM25-03242 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:42 | February | 2026 | 2026-03-05 08:44 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 35
202601-NM25-03244 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:39 | February | 2026 | 2026-02-25 11:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 40
202601-NM25-03245 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 09:46 | February | 2026 | 2026-02-11 11:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-03246 | GDL17 | Residencial | 11.52 | Period | 2026-01-29 11:19 | January | 2026 | 2026-01-30 15:27 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | January |  | 1 | 0 | 2026-04-01 | 62
202601-NM25-03247 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 13:17 | January | 2026 | 2026-02-04 10:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-03249 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:27 | February | 2026 | 2026-02-12 10:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 55
202601-NM25-03251 | GDL17 | Residencial | 12 | Period | 2026-02-04 08:31 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 56
202601-NM25-03252 | GDL17 | Residencial | 4.224 | Period | 2026-01-29 11:41 | January | 2026 | 2026-02-05 10:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 62
202601-NM25-03253 | GDL17 | Residencial | 7.6 | Period | 2026-02-10 08:29 | February | 2026 | 2026-02-11 14:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-03254 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 12:24 | March | 2026 | 2026-04-01 14:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 1
202601-NM25-03255 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:22 | February | 2026 | 2026-02-05 14:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03257 | GDL17 | Residencial | 4.425 | Period | 2026-01-29 11:41 | January | 2026 | 2026-02-02 11:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-03258 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 12:36 | January | 2026 | 2026-02-03 13:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03259 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 09:28 | March | 2026 | 2026-03-31 14:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 5
202601-NM25-03260 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:16 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 57
202601-NM25-03261 | GDL17 | Residencial | 11.4 | Period | 2026-02-04 05:48 | February | 2026 | 2026-03-04 15:37 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 3 | 14 | 14 | 2026-04-01 | 56
202601-NM25-03262 | GDL17 | Residencial | 5.566 | Period | 2026-01-29 11:29 | January | 2026 | 2026-02-02 10:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 62
202601-NM25-03263 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:22 | February | 2026 | 2026-02-06 10:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-03265 | GDL17 | Residencial | 7.5 | Period | 2026-02-11 10:09 | February | 2026 | 2026-02-12 10:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-03266 | GDL17 | Residencial | 7.6 | Period | 2026-02-09 08:50 | February | 2026 | 2026-02-17 07:43 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 51
202601-NM25-03267 | GDL17 | Residencial | 16.3 | Period | 2026-01-29 11:51 | January | 2026 | 2026-02-02 12:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 1 | 3 | 2026-04-01 | 62
202601-NM25-03269 | GDL17 | Residencial | 3.8 | Period | 2026-01-29 12:03 | January | 2026 | 2026-02-02 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03270 | GDL17 | Residencial | 10.98 | Period | 2026-01-29 15:13 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 61
202601-NM25-03271 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 12:26 | March | 2026 | 2026-04-01 14:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 2 | 0 | 2026-04-01 | 1
202601-NM25-03272 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 11:53 | January | 2026 | 2026-02-03 08:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 62
202601-NM25-03273 | GDL17 | Residencial | 13.2 | Period | 2026-01-30 12:11 | January | 2026 | 2026-02-09 13:16 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 10 | 0 | 2026-04-01 | 60
202601-NM25-03274 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 12:11 | January | 2026 | 2026-02-06 12:49 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 61
202601-NM25-03275 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:43 | February | 2026 | 2026-02-10 10:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202601-NM25-03276 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:14 | March | 2026 | 2026-03-27 12:52 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 4 | 13 | 2026-04-01 | 21
202601-NM25-03277 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:25 | January | 2026 | 2026-02-03 12:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03278 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 12:01 | March | 2026 | 2026-03-12 16:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 22
202601-NM25-03279 | GDL17 | Residencial | 15 | Period | 2026-02-02 16:13 | February | 2026 | 2026-02-04 15:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03280 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 12:38 | January | 2026 | 2026-02-09 10:10 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 11 | 0 | 2026-04-01 | 61
202601-NM25-03281 | GDL17 | Residencial | 19.1 | Period | 2026-02-02 15:06 | February | 2026 | 2026-02-04 13:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03282 | GDL17 | Comercial | 24 | Period | 2026-02-10 16:47 | February | 2026 | 2026-03-16 15:52 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March | 2 | 32 | 1 | 2026-04-01 | 49
202601-NM25-03284 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:21 | January | 2026 | 2026-02-10 08:23 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 12 | 0 | 2026-04-01 | 61
202601-NM25-03287 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:09 | February | 2026 | 2026-02-12 11:01 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 10 | 0 | 2026-04-01 | 57
202601-NM25-03288 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:13 | February | 2026 | 2026-02-09 10:00 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 57
202601-NM25-03289 | GDL17 | Residencial | 22.8 | Period | 2026-02-04 16:27 | February | 2026 | 2026-02-11 09:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 4 | 3 | 2026-04-01 | 55
202601-NM25-03291 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:43 | January | 2026 | 2026-02-02 13:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03292 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:47 | January | 2026 | 2026-02-02 14:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03293 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 13:54 | January | 2026 | 2026-02-03 10:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-03294 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:38 | February | 2026 | 2026-02-06 07:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 57
202601-NM25-03295 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:58 | February | 2026 | 2026-02-05 13:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-03296 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:17 | March | 2026 | 2026-03-12 15:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 21
202601-NM25-03297 | GDL17 | Residencial | 23 | Period | 2026-01-30 10:17 | January | 2026 | 2026-02-03 13:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03298 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 12:20 | March | 2026 | 2026-03-18 15:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 20
202601-NM25-03299 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 14:07 | January | 2026 | 2026-03-24 16:17 | 54 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 22 | 0 | 2026-04-01 | 61
202601-NM25-03300 | GDL17 | Residencial | 23 | Period | 2026-01-29 14:09 | January | 2026 | 2026-02-02 09:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03302 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:19 | January | 2026 | 2026-02-02 08:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 61
202601-NM25-03303 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 15:27 | January | 2026 | 2026-02-02 13:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03305 | GDL17 | Residencial | 15 | Period | 2026-02-27 15:30 | February | 2026 | 2026-03-05 08:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 32
202601-NM25-03306 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 07:50 | February | 2026 | 2026-02-12 11:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 1 | 1 | 2026-04-01 | 50
202601-NM25-03307 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 19:02 | March | 2026 | 2026-03-26 11:13 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 14
202601-NM25-03309 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 07:49 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 40
202601-NM25-03310 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 09:01 | March | 2026 | 2026-03-11 16:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 27
202601-NM25-03312 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 15:23 | January | 2026 | 2026-02-02 14:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03313 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:38 | February | 2026 | 2026-02-05 13:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-03314 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:10 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 54
202601-NM25-03315 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:07 | January | 2026 | 2026-02-04 10:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 61
202601-NM25-03316 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 15:40 | January | 2026 | 2026-02-06 11:08 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 61
202601-NM25-03317 | GDL17 | Comercial | 11.5 | Period | 2026-03-10 13:37 | March | 2026 | 2026-03-16 14:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 21
202601-NM25-03318 | GDL17 | Residencial | 7.6 | Period | 2026-01-29 15:56 | January | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 61
202601-NM25-03319 | GDL17 | Residencial | 11.5 | Period | 2026-01-29 16:34 | January | 2026 | 2026-02-03 10:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-03320 | GDL17 | Residencial | 8.85 | Period | 2026-02-06 16:56 | February | 2026 | 2026-02-10 15:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 53
202601-NM25-03321 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 17:06 | February | 2026 | 2026-02-18 10:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202601-NM25-03322 | GDL17 | Residencial | 22.8 | Period | 2026-01-30 15:12 | January | 2026 | 2026-02-05 17:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 5 | 1 | 2026-04-01 | 60
202601-NM25-03323 | GDL17 | Residencial | 12.592 | Period | 2026-01-29 16:54 | January | 2026 | 2026-02-02 13:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03324 | GDL17 | Residencial | 5.566 | Period | 2026-01-29 17:04 | January | 2026 | 2026-02-02 16:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03325 | GDL17 | Residencial | 4.425 | Period | 2026-02-15 22:23 | February | 2026 | 2026-02-20 15:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 44
202601-NM25-03326 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 13:31 | March | 2026 | 2026-03-11 10:17 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 28
202601-NM25-03327 | GDL17 | Residencial | 11.5 | Period | 2026-03-08 23:29 | March | 2026 | 2026-04-07 08:42 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 29 | 0 | 2026-04-01 | 23
202601-NM25-03328 | GDL17 | Residencial | 8 | Period | 2026-02-03 13:14 | February | 2026 | 2026-02-05 12:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-03329 | GDL17 | Residencial | 10.4 | Period | 2026-02-25 13:12 | February | 2026 | 2026-03-17 15:25 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 20 | 0 | 2026-04-01 | 34
202601-NM25-03330 | GDL17 | Residencial | 4.224 | Period | 2026-01-30 09:00 | January | 2026 | 2026-02-11 08:11 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 61
202601-NM25-03331 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 08:55 | January | 2026 | 2026-02-03 10:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03332 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 08:40 | January | 2026 | 2026-02-03 13:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03333 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 09:14 | January | 2026 | 2026-02-02 15:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 61
202601-NM25-03334 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:18 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 2
202601-NM25-03335 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 08:52 | January | 2026 | 2026-02-03 13:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03336 | GDL17 | Residencial | 12 | Period | 2026-01-30 10:48 | January | 2026 | 2026-02-04 09:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 61
202601-NM25-03338 | GDL17 | Residencial | 22.8 | Period | 2026-01-30 10:44 | January | 2026 | 2026-02-05 07:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 61
202601-NM25-03339 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 09:19 | January | 2026 | 2026-02-02 16:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 61
202601-NM25-03341 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 09:30 | January | 2026 | 2026-02-09 12:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 10 | 0 | 2026-04-01 | 61
202601-NM25-03343 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 10:35 | February | 2026 | 2026-03-03 14:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 35
202601-NM25-03344 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:27 | February | 2026 | 2026-02-11 11:20 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 56
202601-NM25-03345 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 11:49 | February | 2026 | 2026-02-20 10:13 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 48
202601-NM25-03347 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 09:55 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 61
202601-NM25-03349 | GDL17 | Residencial | 9.96 | Period | 2026-02-11 11:39 | February | 2026 | 2026-02-12 13:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202601-NM25-03350 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 10:22 | January | 2026 | 2026-02-03 12:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03355 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:48 | February | 2026 | 2026-02-26 08:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 37
202601-NM25-03356 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 11:11 | January | 2026 | 2026-02-03 11:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 61
202601-NM25-03357 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 08:46 | March | 2026 | 2026-04-02 09:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 1
202601-NM25-03358 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:20 | February | 2026 | 2026-02-06 16:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 55
202601-NM25-03359 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:20 | February | 2026 | 2026-02-10 11:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 56
202601-NM25-03360 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:36 | March | 2026 | 2026-03-18 10:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 20
202601-NM25-03361 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 10:51 | January | 2026 | 2026-02-12 14:17 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 13 | 0 | 2026-04-01 | 61
202601-NM25-03362 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 10:43 | January | 2026 | 2026-02-05 14:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 61
202601-NM25-03363 | GDL17 | Residencial | 5.856 | Period | 2026-02-12 07:34 | February | 2026 | 2026-02-18 09:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 48
202601-NM25-03366 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 09:59 | February | 2026 | 2026-02-04 15:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-03367 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:02 | February | 2026 | 2026-02-09 14:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-03368 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 10:56 | January | 2026 | 2026-02-05 17:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 61
202601-NM25-03369 | GDL17 | Residencial | 10.752 | Period | 2026-02-03 14:54 | February | 2026 | 2026-02-06 13:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-03370 | GDL17 | Residencial | 16.512 | Period | 2026-02-03 16:30 | February | 2026 | 2026-02-06 07:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-03371 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:13 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 28
202601-NM25-03373 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:53 | March | 2026 | 2026-03-12 15:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 26
202601-NM25-03374 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:45 | February | 2026 | 2026-02-09 16:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-03375 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:52 | February | 2026 | 2026-02-04 12:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03378 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:48 | March | 2026 | 2026-03-16 13:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202601-NM25-03380 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 12:21 | January | 2026 | 2026-02-04 09:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-03381 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 11:28 | February | 2026 | 2026-02-10 08:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-03383 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:40 | February | 2026 | 2026-03-03 10:23 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 40
202601-NM25-03384 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:56 | February | 2026 | 2026-02-11 10:33 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 57
202601-NM25-03385 | GDL17 | Residencial | 23 | Period | 2026-03-25 15:52 | March | 2026 | 2026-03-30 11:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202601-NM25-03386 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:58 | March | 2026 | 2026-03-25 15:12 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 4 | 19 | 2026-04-01 | 29
202601-NM25-03390 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:33 | February | 2026 | 2026-02-24 07:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202601-NM25-03391 | GDL17 | Residencial | 14.694 | Period | 2026-01-30 12:29 | January | 2026 | 2026-02-03 13:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03392 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:52 | February | 2026 | 2026-02-13 15:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202601-NM25-03396 | GDL17 | Residencial | 8 | Period | 2026-02-03 16:04 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 56
202601-NM25-03397 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:49 | February | 2026 | 2026-02-27 09:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202601-NM25-03399 | GDL17 | Residencial | 10.518 | Period | 2026-01-30 13:51 | January | 2026 | 2026-02-03 13:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03402 | GDL17 | Comercial | 11.5 | Period | 2026-01-30 15:06 | January | 2026 | 2026-02-05 14:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 5 | 1 | 2026-04-01 | 60
202601-NM25-03403 | GDL17 | Residencial | 5.376 | Period | 2026-01-30 13:35 | January | 2026 | 2026-02-03 13:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03404 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:39 | February | 2026 | 2026-02-11 13:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 55
202601-NM25-03407 | GDL17 | Residencial | 16 | Period | 2026-02-03 11:19 | February | 2026 | 2026-03-04 09:22 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 27 | 2 | 2026-04-01 | 57
202601-NM25-03408 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 07:31 | February | 2026 | 2026-02-04 13:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-03412 | GDL17 | Comercial | 12.208 | Period | 2026-02-10 17:13 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 49
202601-NM25-03413 | GDL17 | Residencial | 7.146 | Period | 2026-01-30 14:36 | January | 2026 | 2026-02-03 13:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03414 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 19:04 | March | 2026 | 2026-03-06 09:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202601-NM25-03415 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:49 | January | 2026 | 2026-02-06 08:42 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 60
202601-NM25-03416 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 14:44 | January | 2026 | 2026-02-03 12:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03418 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 14:56 | January | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 60
202601-NM25-03419 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:12 | January | 2026 | 2026-02-05 11:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 60
202601-NM25-03421 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 19:24 | March | 2026 | 2026-03-16 09:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 20
202601-NM25-03422 | GDL17 | Residencial | 6.902 | Period | 2026-01-30 15:21 | January | 2026 | 2026-02-03 12:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03423 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 08:49 | February | 2026 | 2026-02-06 13:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-03424 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:22 | February | 2026 | 2026-02-05 10:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202601-NM25-03425 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 10:29 | February | 2026 | 2026-02-23 10:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 44
202601-NM25-03426 | GDL17 | Residencial | 2.562 | Period | 2026-01-30 15:29 | January | 2026 | 2026-02-11 09:36 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 11 | 0 | 2026-04-01 | 60
202601-NM25-03427 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:27 | January | 2026 | 2026-02-05 10:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 6 | 0 | 2026-04-01 | 60
202601-NM25-03428 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 08:39 | February | 2026 | 2026-02-17 14:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 47
202601-NM25-03429 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 10:29 | February | 2026 | 2026-02-09 15:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 56
202601-NM25-03430 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 10:23 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 44
202601-NM25-03431 | GDL17 | Residencial | 7.102 | Period | 2026-01-30 15:37 | January | 2026 | 2026-02-04 10:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03433 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:11 | February | 2026 | 2026-02-23 14:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202601-NM25-03434 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:41 | January | 2026 | 2026-02-04 17:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-03435 | GDL17 | Residencial | 22.32 | Period | 2026-02-05 08:12 | February | 2026 | 2026-02-09 09:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-03436 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:57 | January | 2026 | 2026-02-03 15:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03437 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 10:22 | February | 2026 | 2026-02-11 13:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 50
202601-NM25-03438 | GDL17 | Residencial | 19.1 | Period | 2026-02-16 13:21 | February | 2026 | 2026-02-23 09:33 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 43
202601-NM25-03439 | GDL17 | Residencial | 9.752 | Period | 2026-01-30 15:54 | January | 2026 | 2026-02-04 08:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03440 | GDL17 | Residencial | 23 | Period | 2026-02-16 09:35 | February | 2026 | 2026-02-19 13:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 44
202601-NM25-03441 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 15:56 | January | 2026 | 2026-02-04 17:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 60
202601-NM25-03442 | GDL17 | Residencial | 7.6 | Period | 2026-01-30 16:04 | January | 2026 | 2026-02-06 12:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 60
202601-NM25-03443 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:06 | January | 2026 | 2026-02-25 16:20 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 13 | 13 | 2026-04-01 | 60
202601-NM25-03444 | GDL17 | Residencial | 11.5 | Period | 2026-01-30 16:15 | January | 2026 | 2026-02-04 10:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 60
202601-NM25-03445 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 07:15 | February | 2026 | 2026-02-12 08:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 50
202601-NM25-03446 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:24 | February | 2026 | 2026-02-13 15:35 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 55
202601-NM25-03447 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 09:29 | February | 2026 | 2026-02-04 10:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 58
202601-NM25-03448 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:59 | February | 2026 | 2026-02-09 10:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202601-NM25-03449 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:30 | February | 2026 | 2026-02-20 14:29 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 55
202601-NM25-03450 | GDL17 | Residencial | 23 | Period | 2026-02-03 13:21 | February | 2026 | 2026-02-05 12:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 56
202601-NM25-03451 | GDL17 | Residencial | 8 | Period | 2026-02-04 13:01 | February | 2026 | 2026-02-06 10:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 55
202601-NM25-03452 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:37 | February | 2026 | 2026-02-26 08:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202601-NM25-03453 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:14 | February | 2026 | 2026-02-16 07:52 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 10 | 0 | 2026-04-01 | 54
202601-NM25-03454 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:20 | February | 2026 | 2026-02-26 14:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 41
202601-NM25-03455 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:32 | February | 2026 | 2026-02-12 10:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 50
202601-NM25-03456 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:33 | February | 2026 | 2026-02-06 13:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 55
202601-NM25-03457 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:51 | February | 2026 | 2026-02-09 09:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202601-NM25-03458 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 07:57 | February | 2026 | 2026-02-10 10:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 56
202601-NM25-03460 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 09:33 | March | 2026 | 2026-03-04 14:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 30
202601-NM25-03462 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:17 | February | 2026 | 2026-02-06 10:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202601-NM25-03463 | GDL17 | Residencial | 8 | Period | 2026-02-12 09:01 | February | 2026 | 2026-02-13 14:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 48
202601-NM25-03465 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 17:32 | March | 2026 | 2026-04-09 08:45 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 13 | 0 | 2026-04-01 | 5
202601-NM25-03466 | GDL17 | Residencial | 15 | Period | 2026-01-30 19:42 | January | 2026 | 2026-02-06 08:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 60
202601-NM25-03467 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:03 | March | 2026 | 2026-03-18 11:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 20
202601-NM25-03470 | GDL17 | Residencial | 20 | Period | 2026-02-07 10:40 | February | 2026 | 2026-02-12 08:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 53
202601-NM25-03471 | GDL17 | Residencial | 11.4 | Period | 2026-02-09 14:02 | February | 2026 | 2026-02-12 11:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00001 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:35 | February | 2026 | 2026-02-23 09:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-00002 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 11:19 | February | 2026 | 2026-02-11 10:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 55
202602-NM25-00004 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:58 | February | 2026 | 2026-02-16 16:12 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 56
202602-NM25-00005 | GDL17 | Residencial | 4.992 | Period | 2026-02-02 08:13 | February | 2026 | 2026-02-04 14:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 58
202602-NM25-00006 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 08:09 | February | 2026 | 2026-02-05 13:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 58
202602-NM25-00007 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 08:24 | February | 2026 | 2026-02-04 14:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 58
202602-NM25-00009 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 08:26 | February | 2026 | 2026-02-04 15:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 58
202602-NM25-00011 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 08:38 | February | 2026 | 2026-02-04 15:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 58
202602-NM25-00012 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:24 | February | 2026 | 2026-02-19 07:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-00014 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:28 | February | 2026 | 2026-02-09 15:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00015 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:54 | February | 2026 | 2026-02-06 12:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00016 | GDL17 | Residencial | 7.6 | Period | 2026-02-17 07:58 | February | 2026 | 2026-02-20 08:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 43
202602-NM25-00017 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 10:05 | February | 2026 | 2026-02-09 12:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 58
202602-NM25-00018 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:30 | February | 2026 | 2026-02-10 13:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00020 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:21 | February | 2026 | 2026-02-04 15:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00021 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:23 | February | 2026 | 2026-02-25 12:40 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 22 | 0 | 2026-04-01 | 56
202602-NM25-00023 | GDL17 | Residencial | 8 | Period | 2026-02-02 15:09 | February | 2026 | 2026-02-05 12:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00024 | GDL17 | Residencial | 8 | Period | 2026-03-12 09:17 | March | 2026 | 2026-03-26 09:00 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 14 | 0 | 2026-04-01 | 20
202602-NM25-00025 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 10:34 | February | 2026 | 2026-02-04 15:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 58
202602-NM25-00026 | GDL17 | Residencial | 12.288 | Period | 2026-02-03 13:12 | February | 2026 | 2026-02-05 10:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00027 | GDL17 | Residencial | 8 | Period | 2026-03-10 08:11 | March | 2026 | 2026-03-12 13:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-00028 | GDL17 | Residencial | 7.6 | Period | 2026-02-02 13:44 | February | 2026 | 2026-02-06 12:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 57
202602-NM25-00030 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 11:17 | February | 2026 | 2026-02-05 15:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 58
202602-NM25-00031 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:44 | February | 2026 | 2026-02-09 14:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00033 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:09 | February | 2026 | 2026-02-04 15:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00034 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 07:54 | March | 2026 | 2026-03-12 14:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 1 | 5 | 2026-04-01 | 26
202602-NM25-00035 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:50 | February | 2026 | 2026-02-12 12:52 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 55
202602-NM25-00036 | GDL17 | Residencial | 7.68 | Period | 2026-02-12 14:36 | February | 2026 | 2026-02-16 11:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-00037 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 11:39 | February | 2026 | 2026-02-12 09:14 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 58
202602-NM25-00040 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 19:06 | February | 2026 | 2026-02-09 14:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00041 | GDL17 | Residencial | 8 | Period | 2026-02-03 17:01 | February | 2026 | 2026-02-06 13:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00042 | GDL17 | Residencial | 11.4 | Period | 2026-02-10 15:22 | February | 2026 | 2026-02-11 14:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00043 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 11:58 | February | 2026 | 2026-02-05 13:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 58
202602-NM25-00044 | GDL17 | Residencial | 7.68 | Period | 2026-02-06 14:16 | February | 2026 | 2026-02-11 15:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00045 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:13 | February | 2026 | 2026-02-04 12:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00046 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:11 | February | 2026 | 2026-02-04 11:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00047 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:19 | March | 2026 | 2026-03-30 13:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 6
202602-NM25-00048 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:30 | March | 2026 | 2026-03-30 12:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 7
202602-NM25-00049 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:17 | February | 2026 | 2026-02-09 08:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 57
202602-NM25-00051 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:59 | February | 2026 | 2026-02-11 11:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00052 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:21 | March | 2026 | 2026-03-09 14:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 29
202602-NM25-00054 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:30 | February | 2026 | 2026-02-05 09:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00055 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:39 | February | 2026 | 2026-02-04 14:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00056 | GDL17 | Residencial | 3.8 | Period | 2026-03-02 11:40 | March | 2026 | 2026-03-13 16:12 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 11 | 0 | 2026-04-01 | 30
202602-NM25-00058 | GDL17 | Residencial | 5 | Period | 2026-02-05 12:02 | February | 2026 | 2026-02-09 14:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00059 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:43 | February | 2026 | 2026-03-04 15:26 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 9 | 0 | 2026-04-01 | 37
202602-NM25-00061 | GDL17 | Residencial | 5.196 | Period | 2026-02-02 12:40 | February | 2026 | 2026-02-04 14:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00062 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:46 | February | 2026 | 2026-02-11 15:20 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 57
202602-NM25-00063 | GDL17 | Residencial | 22.8 | Period | 2026-02-06 16:42 | February | 2026 | 2026-03-19 10:50 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 41 | 0 | 2026-04-01 | 53
202602-NM25-00064 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:45 | February | 2026 | 2026-02-09 15:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 57
202602-NM25-00065 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:49 | February | 2026 | 2026-02-05 12:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00067 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:59 | February | 2026 | 2026-02-05 13:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00069 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:14 | March | 2026 | 2026-03-30 09:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202602-NM25-00070 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:01 | February | 2026 | 2026-02-05 13:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00071 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 12:59 | February | 2026 | 2026-02-17 14:43 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 57
202602-NM25-00072 | GDL17 | Residencial | 11.51 | Period | 2026-02-02 13:00 | February | 2026 | 2026-02-12 15:38 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 10 | 0 | 2026-04-01 | 57
202602-NM25-00073 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:54 | February | 2026 | 2026-02-13 08:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 54
202602-NM25-00076 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:12 | February | 2026 | 2026-02-05 09:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00077 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:52 | February | 2026 | 2026-02-20 08:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-00078 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:26 | February | 2026 | 2026-02-05 10:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00080 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:27 | February | 2026 | 2026-02-05 15:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00081 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:02 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 48
202602-NM25-00082 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 17:10 | March | 2026 | 2026-03-06 09:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 27
202602-NM25-00083 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:16 | February | 2026 | 2026-02-06 13:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00084 | GDL17 | Residencial | 3.456 | Period | 2026-02-02 13:40 | February | 2026 | 2026-02-06 10:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 57
202602-NM25-00085 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:51 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 54
202602-NM25-00086 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 09:18 | February | 2026 | 2026-02-16 14:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 50
202602-NM25-00087 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:49 | February | 2026 | 2026-02-09 14:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00088 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 09:39 | February | 2026 | 2026-02-24 07:46 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 11 | 0 | 2026-04-01 | 47
202602-NM25-00089 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:42 | February | 2026 | 2026-02-04 13:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00090 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:41 | February | 2026 | 2026-02-11 11:12 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 57
202602-NM25-00091 | GDL17 | Residencial | 6.8 | Period | 2026-02-27 11:32 | February | 2026 | 2026-03-03 13:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-00092 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:03 | February | 2026 | 2026-02-23 09:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00094 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:52 | February | 2026 | 2026-02-04 08:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00095 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:28 | February | 2026 | 2026-02-09 10:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00096 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 13:55 | February | 2026 | 2026-02-05 14:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00097 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 08:27 | February | 2026 | 2026-02-06 13:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00100 | GDL17 | Residencial | 12.672 | Period | 2026-02-02 14:29 | February | 2026 | 2026-02-12 09:32 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 57
202602-NM25-00103 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:19 | February | 2026 | 2026-02-05 08:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00104 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:26 | February | 2026 | 2026-02-04 15:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00105 | GDL17 | Residencial | 23 | Period | 2026-03-11 14:31 | March | 2026 | 2026-03-17 08:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-00106 | GDL17 | Residencial | 7.68 | Period | 2026-02-13 10:28 | February | 2026 | 2026-02-26 11:28 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 7 | 6 | 2026-04-01 | 47
202602-NM25-00107 | GDL17 | Residencial | 5.76 | Period | 2026-02-09 14:08 | February | 2026 | 2026-02-12 10:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00109 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:23 | February | 2026 | 2026-02-09 10:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 57
202602-NM25-00110 | GDL17 | Comercial | 6.348 | Period | 2026-02-02 14:28 | February | 2026 | 2026-02-04 15:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00111 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:25 | February | 2026 | 2026-02-06 10:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 57
202602-NM25-00112 | GDL17 | Residencial | 16.22 | Period | 2026-02-02 14:34 | February | 2026 | 2026-02-12 15:46 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 6 | 0 | 2026-04-01 | 57
202602-NM25-00115 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:31 | February | 2026 | 2026-02-04 10:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00118 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:41 | February | 2026 | 2026-02-05 13:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00119 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:40 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 57
202602-NM25-00121 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:45 | February | 2026 | 2026-02-04 10:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00124 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:00 | February | 2026 | 2026-03-06 09:11 | 32 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 32 | 0 | 2026-04-01 | 57
202602-NM25-00125 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:49 | February | 2026 | 2026-02-04 08:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00126 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:54 | February | 2026 | 2026-02-04 13:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00129 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:09 | February | 2026 | 2026-02-11 10:19 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 57
202602-NM25-00130 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 14:59 | February | 2026 | 2026-02-04 13:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00131 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:04 | February | 2026 | 2026-02-04 12:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00132 | GDL17 | Comercial | 11.5 | Period | 2026-02-02 15:08 | February | 2026 | 2026-02-04 13:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00133 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:08 | February | 2026 | 2026-02-06 09:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 57
202602-NM25-00134 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:12 | February | 2026 | 2026-02-04 10:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00136 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:17 | February | 2026 | 2026-02-05 10:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00137 | GDL17 | Residencial | 14.5 | Period | 2026-02-02 15:20 | February | 2026 | 2026-02-04 14:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00138 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:58 | February | 2026 | 2026-03-30 13:19 | 56 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 43 | 7 | 2026-04-01 | 57
202602-NM25-00139 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:19 | February | 2026 | 2026-02-04 11:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00141 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:25 | February | 2026 | 2026-02-11 12:45 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 9 | 0 | 2026-04-01 | 57
202602-NM25-00142 | GDL17 | Residencial | 9 | Period | 2026-02-05 11:35 | February | 2026 | 2026-02-11 15:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 55
202602-NM25-00143 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:14 | February | 2026 | 2026-02-05 12:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00144 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:26 | February | 2026 | 2026-02-04 14:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00145 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:28 | February | 2026 | 2026-02-04 14:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00146 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:37 | February | 2026 | 2026-02-06 08:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00147 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:31 | February | 2026 | 2026-02-04 14:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00148 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:40 | February | 2026 | 2026-02-13 16:09 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 57
202602-NM25-00149 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:33 | February | 2026 | 2026-02-09 09:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 57
202602-NM25-00150 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:34 | February | 2026 | 2026-02-09 15:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 57
202602-NM25-00152 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:35 | February | 2026 | 2026-02-25 13:17 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 23 | 0 | 2026-04-01 | 57
202602-NM25-00153 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:40 | February | 2026 | 2026-02-04 14:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00155 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 08:51 | February | 2026 | 2026-02-16 07:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 48
202602-NM25-00156 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:45 | February | 2026 | 2026-02-05 11:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00157 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:43 | February | 2026 | 2026-02-04 11:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00158 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:48 | February | 2026 | 2026-02-10 13:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 57
202602-NM25-00159 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:44 | February | 2026 | 2026-02-04 15:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00160 | GDL17 | Residencial | 7.68 | Period | 2026-02-05 09:34 | February | 2026 | 2026-02-09 14:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00161 | GDL17 | Residencial | 3.84 | Period | 2026-02-05 08:15 | February | 2026 | 2026-02-09 10:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00162 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:51 | February | 2026 | 2026-02-04 12:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00163 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 10:51 | March | 2026 | 2026-03-17 13:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 16
202602-NM25-00164 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:52 | February | 2026 | 2026-02-04 13:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00165 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:54 | February | 2026 | 2026-02-11 14:27 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 57
202602-NM25-00167 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:58 | February | 2026 | 2026-02-04 14:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00168 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 15:57 | February | 2026 | 2026-02-04 16:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00169 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:44 | February | 2026 | 2026-02-09 14:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00170 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:02 | February | 2026 | 2026-02-05 17:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00171 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:08 | February | 2026 | 2026-02-06 10:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 57
202602-NM25-00172 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:07 | February | 2026 | 2026-02-05 08:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00173 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:14 | February | 2026 | 2026-02-06 10:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 57
202602-NM25-00174 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:17 | February | 2026 | 2026-02-05 10:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00175 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:20 | February | 2026 | 2026-02-05 16:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00176 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:15 | February | 2026 | 2026-02-24 15:55 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 43
202602-NM25-00177 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:29 | February | 2026 | 2026-02-10 10:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 57
202602-NM25-00178 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:33 | February | 2026 | 2026-02-05 15:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00179 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:40 | February | 2026 | 2026-02-05 10:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 57
202602-NM25-00180 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 16:50 | February | 2026 | 2026-02-12 08:13 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 57
202602-NM25-00181 | GDL17 | Residencial | 8 | Period | 2026-02-11 10:52 | February | 2026 | 2026-02-12 14:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00182 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:03 | February | 2026 | 2026-02-17 09:20 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 15 | 0 | 2026-04-01 | 57
202602-NM25-00183 | GDL17 | Residencial | 12 | Period | 2026-02-05 17:02 | February | 2026 | 2026-02-11 11:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 54
202602-NM25-00185 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:25 | February | 2026 | 2026-02-12 16:14 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 57
202602-NM25-00186 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:31 | February | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 57
202602-NM25-00187 | GDL17 | Residencial | 11.5 | Period | 2026-02-02 17:46 | February | 2026 | 2026-02-04 18:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00189 | GDL17 | Residencial | 13.2 | Period | 2026-02-03 11:37 | February | 2026 | 2026-02-18 11:04 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 2 | 7 | 8 | 2026-04-01 | 57
202602-NM25-00191 | GDL17 | Residencial | 16 | Period | 2026-02-03 10:40 | February | 2026 | 2026-02-05 07:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00192 | GDL17 | Residencial | 16 | Period | 2026-02-04 12:04 | February | 2026 | 2026-02-13 13:23 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 55
202602-NM25-00193 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 18:40 | March | 2026 | 2026-03-16 09:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-00197 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:33 | March | 2026 | 2026-03-16 17:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 21
202602-NM25-00198 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 07:49 | February | 2026 | 2026-02-05 12:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00202 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 15:07 | February | 2026 | 2026-02-18 13:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 48
202602-NM25-00203 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:38 | February | 2026 | 2026-02-06 16:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00204 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:08 | March | 2026 | 2026-03-19 10:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 14
202602-NM25-00206 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:16 | February | 2026 | 2026-02-10 10:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 57
202602-NM25-00207 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 07:43 | February | 2026 | 2026-02-10 13:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 5 | 1 | 2026-04-01 | 56
202602-NM25-00208 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:22 | February | 2026 | 2026-02-04 17:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 57
202602-NM25-00210 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:29 | February | 2026 | 2026-02-24 09:54 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 21 | 0 | 2026-04-01 | 57
202602-NM25-00211 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:31 | February | 2026 | 2026-02-05 10:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00213 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:41 | February | 2026 | 2026-02-05 11:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00214 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:42 | February | 2026 | 2026-02-05 11:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00217 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:07 | February | 2026 | 2026-02-23 14:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-00218 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:56 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 57
202602-NM25-00219 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 08:55 | February | 2026 | 2026-02-09 16:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 57
202602-NM25-00221 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:00 | February | 2026 | 2026-02-05 11:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00222 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:08 | February | 2026 | 2026-02-05 12:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00225 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:13 | February | 2026 | 2026-02-05 12:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00227 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 13:27 | February | 2026 | 2026-02-26 08:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 38
202602-NM25-00228 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 17:15 | February | 2026 | 2026-02-09 13:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00232 | GDL17 | Residencial | 3.84 | Period | 2026-02-05 15:34 | February | 2026 | 2026-02-09 11:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00234 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:46 | February | 2026 | 2026-02-12 07:59 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 57
202602-NM25-00236 | GDL17 | Residencial | 3.8 | Period | 2026-02-04 15:20 | February | 2026 | 2026-02-11 10:28 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 55
202602-NM25-00238 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 09:59 | February | 2026 | 2026-02-05 13:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00240 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:36 | February | 2026 | 2026-02-10 10:00 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 56
202602-NM25-00241 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:17 | February | 2026 | 2026-02-11 11:04 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 57
202602-NM25-00242 | GDL17 | Residencial | 12.444 | Period | 2026-02-13 09:18 | February | 2026 | 2026-02-19 08:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 47
202602-NM25-00243 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 12:11 | March | 2026 | 2026-03-13 12:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202602-NM25-00244 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 08:48 | March | 2026 | 2026-04-16 16:15 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 22 | 0 | 2026-04-01 | 7
202602-NM25-00245 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:34 | February | 2026 | 2026-02-05 08:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00248 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:33 | March | 2026 | 2026-03-04 09:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 30
202602-NM25-00251 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:45 | February | 2026 | 2026-02-24 08:25 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 57
202602-NM25-00252 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:44 | February | 2026 | 2026-02-23 09:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-00253 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:48 | February | 2026 | 2026-02-05 10:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00254 | GDL17 | Residencial | 7.68 | Period | 2026-03-04 15:29 | March | 2026 | 2026-03-06 13:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 27
202602-NM25-00255 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 10:46 | February | 2026 | 2026-02-05 15:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00256 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:03 | March | 2026 | 2026-03-06 13:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-00258 | GDL17 | Comercial | 7.6 | Period | 2026-02-03 10:53 | February | 2026 | 2026-02-05 13:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00259 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:05 | February | 2026 | 2026-02-11 10:17 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 57
202602-NM25-00262 | GDL17 | Residencial | 9 | Period | 2026-02-15 12:37 | February | 2026 | 2026-03-02 09:19 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 14 | 0 | 2026-04-01 | 44
202602-NM25-00264 | GDL17 | Residencial | 6.526 | Period | 2026-02-03 13:56 | February | 2026 | 2026-02-06 10:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00267 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 10:23 | February | 2026 | 2026-02-19 16:15 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 49
202602-NM25-00270 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:28 | February | 2026 | 2026-02-09 13:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 54
202602-NM25-00271 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:18 | February | 2026 | 2026-02-11 08:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00272 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:21 | February | 2026 | 2026-02-19 08:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 44
202602-NM25-00273 | GDL17 | Residencial | 12 | Period | 2026-02-04 20:11 | February | 2026 | 2026-02-09 12:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00274 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 17:08 | March | 2026 | 2026-04-28 16:23 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 28 | 0 | 2026-04-01 | 0
202602-NM25-00275 | GDL17 | Residencial | 18 | Period | 2026-02-25 15:26 | February | 2026 | 2026-03-11 09:49 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 13 | 0 | 2026-04-01 | 34
202602-NM25-00277 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 12:03 | March | 2026 | 2026-03-16 11:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-00278 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 11:48 | February | 2026 | 2026-02-05 14:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 57
202602-NM25-00280 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:43 | March | 2026 | 2026-03-12 15:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 21
202602-NM25-00282 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:00 | February | 2026 | 2026-02-05 13:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00283 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:10 | February | 2026 | 2026-02-05 17:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00285 | GDL17 | Residencial | 9 | Period | 2026-02-06 11:43 | February | 2026 | 2026-02-09 16:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 54
202602-NM25-00287 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:21 | February | 2026 | 2026-02-05 13:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00290 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 12:32 | February | 2026 | 2026-02-16 10:35 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 56
202602-NM25-00294 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 18:48 | March | 2026 | 2026-03-13 15:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 20
202602-NM25-00295 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:42 | February | 2026 | 2026-02-27 14:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-00301 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:26 | February | 2026 | 2026-02-18 07:43 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 15 | 0 | 2026-04-01 | 56
202602-NM25-00302 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 13:44 | February | 2026 | 2026-02-06 07:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00306 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 18:25 | March | 2026 | 2026-03-13 15:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 20
202602-NM25-00307 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 08:39 | March | 2026 | 2026-03-18 14:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 15
202602-NM25-00308 | GDL17 | Residencial | 6 | Period | 2026-02-12 14:30 | February | 2026 | 2026-02-16 10:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-00310 | GDL17 | Residencial | 7.6 | Period | 2026-02-20 11:20 | February | 2026 | 2026-02-25 09:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-00311 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:08 | February | 2026 | 2026-02-06 10:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00315 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:08 | March | 2026 | 2026-03-27 14:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-00317 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:20 | February | 2026 | 2026-02-06 12:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00318 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:45 | February | 2026 | 2026-02-12 08:33 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 55
202602-NM25-00319 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 15:52 | March | 2026 | 2026-04-02 12:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 6 | 0 | 2026-04-01 | 4
202602-NM25-00320 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 14:23 | February | 2026 | 2026-02-12 10:00 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 56
202602-NM25-00322 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:28 | March | 2026 | 2026-03-06 08:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-00323 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 15:00 | February | 2026 | 2026-02-12 10:23 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 9 | 0 | 2026-04-01 | 56
202602-NM25-00324 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:22 | February | 2026 | 2026-03-03 12:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-00327 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:52 | February | 2026 | 2026-02-12 09:23 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 55
202602-NM25-00328 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 14:51 | February | 2026 | 2026-02-10 10:38 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 56
202602-NM25-00332 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:25 | February | 2026 | 2026-02-25 14:39 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 42
202602-NM25-00333 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 12:24 | February | 2026 | 2026-02-18 07:57 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 13 | 0 | 2026-04-01 | 54
202602-NM25-00335 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 13:14 | February | 2026 | 2026-02-16 10:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-00336 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 10:54 | February | 2026 | 2026-02-27 10:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-00338 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:38 | February | 2026 | 2026-02-12 07:50 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 56
202602-NM25-00339 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:46 | March | 2026 | 2026-03-17 11:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 18
202602-NM25-00341 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 15:02 | February | 2026 | 2026-02-16 14:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-00342 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:49 | February | 2026 | 2026-02-04 14:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00343 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:27 | February | 2026 | 2026-02-09 13:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 56
202602-NM25-00345 | GDL17 | Residencial | 8 | Period | 2026-02-03 16:43 | February | 2026 | 2026-02-05 09:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00347 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:51 | March | 2026 | 2026-03-16 17:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 21
202602-NM25-00348 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:57 | March | 2026 | 2026-03-18 09:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 18
202602-NM25-00350 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 15:32 | February | 2026 | 2026-02-04 14:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00351 | GDL17 | Residencial | 9.456 | Period | 2026-02-03 15:29 | February | 2026 | 2026-02-04 14:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00354 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:41 | February | 2026 | 2026-02-04 15:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00355 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:40 | February | 2026 | 2026-02-10 15:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 56
202602-NM25-00356 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:40 | February | 2026 | 2026-02-06 14:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00357 | GDL17 | Residencial | 7.6 | Period | 2026-02-10 14:16 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 49
202602-NM25-00359 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:50 | February | 2026 | 2026-02-09 16:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 56
202602-NM25-00360 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 08:43 | February | 2026 | 2026-02-27 09:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-00361 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 15:50 | February | 2026 | 2026-02-04 15:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00362 | GDL17 | Residencial | 23 | Period | 2026-02-06 16:59 | February | 2026 | 2026-02-16 12:47 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 53
202602-NM25-00363 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:50 | March | 2026 | 2026-03-16 13:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 20
202602-NM25-00364 | GDL17 | Residencial | 7.68 | Period | 2026-02-17 11:35 | February | 2026 | 2026-02-20 08:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-00365 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 16:00 | February | 2026 | 2026-02-04 16:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00367 | GDL17 | Residencial | 7.6 | Period | 2026-02-03 16:07 | February | 2026 | 2026-02-04 13:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00368 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 16:05 | February | 2026 | 2026-02-04 13:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00369 | GDL17 | Residencial | 8 | Period | 2026-02-04 13:14 | February | 2026 | 2026-02-06 15:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00372 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:38 | March | 2026 | 2026-04-01 15:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 2
202602-NM25-00373 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:02 | March | 2026 | 2026-03-04 09:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 30
202602-NM25-00374 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 17:01 | February | 2026 | 2026-02-16 09:37 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 13 | 0 | 2026-04-01 | 56
202602-NM25-00375 | GDL17 | Residencial | 11.5 | Period | 2026-02-03 17:26 | February | 2026 | 2026-02-04 12:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00376 | GDL17 | Residencial | 5.566 | Period | 2026-02-03 16:30 | February | 2026 | 2026-02-04 12:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00377 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 21:08 | February | 2026 | 2026-03-03 16:22 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 41
202602-NM25-00378 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 20:16 | February | 2026 | 2026-03-03 10:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-00379 | GDL17 | Residencial | 6.296 | Period | 2026-02-03 16:47 | February | 2026 | 2026-02-04 12:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00380 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 12:35 | March | 2026 | 2026-03-19 12:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 13
202602-NM25-00381 | GDL17 | Residencial | 9.882 | Period | 2026-02-03 17:08 | February | 2026 | 2026-02-04 11:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00382 | GDL17 | Residencial | 10.672 | Period | 2026-02-03 16:59 | February | 2026 | 2026-02-04 11:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00383 | GDL17 | Comercial | 12 | Period | 2026-02-03 18:11 | February | 2026 | 2026-03-10 09:21 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March |  | 35 | 0 | 2026-04-01 | 56
202602-NM25-00384 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:44 | February | 2026 | 2026-02-24 13:27 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 43
202602-NM25-00385 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:52 | March | 2026 | 2026-03-30 12:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 7
202602-NM25-00387 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 07:54 | February | 2026 | 2026-02-13 12:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 48
202602-NM25-00388 | GDL17 | Residencial | 5.605 | Period | 2026-02-03 17:45 | February | 2026 | 2026-02-04 11:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00389 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 11:08 | February | 2026 | 2026-02-09 08:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 56
202602-NM25-00390 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:44 | March | 2026 | 2026-04-24 09:41 | 30 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | April |  | 29 | 23 | 2026-04-01 | 6
202602-NM25-00391 | GDL17 | Residencial | 3.84 | Period | 2026-02-03 17:51 | February | 2026 | 2026-02-04 11:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 56
202602-NM25-00392 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:40 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 22
202602-NM25-00393 | GDL17 | Residencial | 15 | Period | 2026-02-03 21:10 | February | 2026 | 2026-02-06 13:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00394 | GDL17 | Residencial | 8 | Period | 2026-02-04 10:58 | February | 2026 | 2026-02-12 07:40 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 56
202602-NM25-00399 | GDL17 | Residencial | 5.28 | Period | 2026-02-04 08:51 | February | 2026 | 2026-02-12 15:03 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 2 | 2 | 6 | 2026-04-01 | 56
202602-NM25-00400 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 11:44 | February | 2026 | 2026-02-11 13:17 | 2 | Create NEM Agreement | Validación (V) | Activated | Applicant Registration | yes | yes |  |  | MAYAGUEZ | February | 1 | 1 | 1 | 2026-04-01 | 51
202602-NM25-00402 | GDL17 | Residencial | 7.68 | Period | 2026-02-10 18:47 | February | 2026 | 2026-02-11 15:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00403 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 08:42 | February | 2026 | 2026-02-06 12:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00404 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 08:42 | February | 2026 | 2026-02-06 13:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00406 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 15:33 | February | 2026 | 2026-03-10 13:49 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 34
202602-NM25-00407 | GDL17 | Residencial | 9.904 | Period | 2026-02-04 09:02 | February | 2026 | 2026-02-06 13:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00409 | GDL17 | Residencial | 7.68 | Period | 2026-02-17 16:17 | February | 2026 | 2026-02-25 14:49 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 42
202602-NM25-00410 | GDL17 | Residencial | 7.68 | Period | 2026-02-17 21:21 | February | 2026 | 2026-02-23 13:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00411 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 09:17 | February | 2026 | 2026-02-06 13:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00413 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 11:18 | February | 2026 | 2026-02-06 13:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00414 | GDL17 | Residencial | 7.68 | Period | 2026-02-12 22:12 | February | 2026 | 2026-02-24 08:38 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 11 | 0 | 2026-04-01 | 47
202602-NM25-00415 | GDL17 | Residencial | 5.076 | Period | 2026-02-04 09:29 | February | 2026 | 2026-02-06 13:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00422 | GDL17 | Residencial | 3.84 | Period | 2026-02-26 17:40 | February | 2026 | 2026-03-05 13:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 33
202602-NM25-00423 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:41 | February | 2026 | 2026-02-11 11:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00424 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 16:41 | March | 2026 | 2026-03-24 10:31 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 14
202602-NM25-00427 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:46 | February | 2026 | 2026-02-24 16:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-00429 | GDL17 | Residencial | 8 | Period | 2026-03-11 12:03 | March | 2026 | 2026-03-13 10:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 20
202602-NM25-00430 | GDL17 | Residencial | 3.5 | Period | 2026-02-04 10:13 | February | 2026 | 2026-02-06 15:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 56
202602-NM25-00431 | GDL17 | Residencial | 8 | Period | 2026-02-04 11:26 | February | 2026 | 2026-02-06 14:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00434 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 15:12 | February | 2026 | 2026-02-11 09:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 54
202602-NM25-00442 | GDL17 | Comercial | 16 | Period | 2026-02-04 12:26 | February | 2026 | 2026-02-12 11:07 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 55
202602-NM25-00443 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 10:48 | February | 2026 | 2026-02-10 09:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 56
202602-NM25-00447 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:41 | February | 2026 | 2026-02-16 15:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-00448 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 18:02 | March | 2026 | 2026-03-17 10:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 19
202602-NM25-00452 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:30 | February | 2026 | 2026-02-26 08:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-00457 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 07:32 | February | 2026 | 2026-02-25 09:27 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 42
202602-NM25-00458 | GDL17 | Residencial | 7.6 | Period | 2026-02-04 11:13 | February | 2026 | 2026-02-06 13:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00463 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 22:06 | February | 2026 | 2026-02-23 09:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00464 | GDL17 | Residencial | 4.224 | Period | 2026-02-04 11:15 | February | 2026 | 2026-03-05 11:06 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 29 | 0 | 2026-04-01 | 56
202602-NM25-00469 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 08:53 | February | 2026 | 2026-03-02 16:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-00472 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 11:49 | February | 2026 | 2026-02-06 15:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 56
202602-NM25-00473 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 07:57 | February | 2026 | 2026-02-10 14:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00475 | GDL17 | Residencial | 12 | Period | 2026-02-05 12:51 | February | 2026 | 2026-02-09 14:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00477 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:25 | February | 2026 | 2026-02-06 16:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00479 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:33 | February | 2026 | 2026-02-17 10:25 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 12 | 0 | 2026-04-01 | 55
202602-NM25-00480 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:15 | February | 2026 | 2026-02-11 15:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 55
202602-NM25-00482 | GDL17 | Residencial | 8 | Period | 2026-02-12 10:21 | February | 2026 | 2026-02-13 10:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-00483 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:33 | March | 2026 | 2026-03-11 14:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-00486 | GDL17 | Residencial | 13.176 | Period | 2026-02-06 10:37 | February | 2026 | 2026-02-11 10:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00487 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 11:22 | February | 2026 | 2026-02-09 16:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00488 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:34 | February | 2026 | 2026-02-10 08:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00490 | GDL17 | Residencial | 3.8 | Period | 2026-03-05 09:36 | March | 2026 | 2026-03-25 13:54 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 2 | 18 | 2026-04-01 | 27
202602-NM25-00491 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 11:00 | March | 2026 | 2026-03-19 11:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 14
202602-NM25-00492 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:53 | February | 2026 | 2026-02-25 10:50 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 55
202602-NM25-00493 | GDL17 | Residencial | 8.09 | Period | 2026-02-04 12:44 | February | 2026 | 2026-02-06 16:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00494 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:59 | March | 2026 | 2026-04-13 08:26 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 13 | 0 | 2026-04-01 | 2
202602-NM25-00495 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:47 | February | 2026 | 2026-02-06 14:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00498 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 12:55 | February | 2026 | 2026-02-06 14:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00499 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 14:05 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 46
202602-NM25-00500 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 19:48 | February | 2026 | 2026-02-23 15:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00501 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:05 | February | 2026 | 2026-02-10 10:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00506 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:19 | February | 2026 | 2026-02-13 14:34 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 55
202602-NM25-00508 | GDL17 | Residencial | 9.136 | Period | 2026-02-04 13:27 | February | 2026 | 2026-02-06 15:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00510 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:29 | February | 2026 | 2026-02-09 09:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00511 | GDL17 | Residencial | 6.222 | Period | 2026-02-04 13:36 | February | 2026 | 2026-02-11 12:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 55
202602-NM25-00512 | GDL17 | Residencial | 4.224 | Period | 2026-02-04 13:45 | February | 2026 | 2026-02-10 08:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00515 | GDL17 | Residencial | 11.098 | Period | 2026-02-04 13:39 | February | 2026 | 2026-02-06 15:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00518 | GDL17 | Residencial | 7.68 | Period | 2026-02-06 12:30 | February | 2026 | 2026-02-09 16:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 53
202602-NM25-00520 | GDL17 | Residencial | 5.566 | Period | 2026-02-04 13:49 | February | 2026 | 2026-02-09 09:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00523 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 13:59 | February | 2026 | 2026-02-06 15:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 55
202602-NM25-00525 | GDL17 | Residencial | 3.8 | Period | 2026-02-05 14:39 | February | 2026 | 2026-02-09 09:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00527 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 20:56 | February | 2026 | 2026-02-27 10:31 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 9 | 0 | 2026-04-01 | 41
202602-NM25-00528 | GDL17 | Residencial | 5.926 | Period | 2026-02-04 14:23 | February | 2026 | 2026-02-09 10:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00529 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 14:47 | February | 2026 | 2026-02-09 11:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00530 | GDL17 | Residencial | 7.68 | Period | 2026-02-19 15:03 | February | 2026 | 2026-03-02 10:23 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 40
202602-NM25-00533 | GDL17 | Residencial | 7.396 | Period | 2026-02-04 14:34 | February | 2026 | 2026-02-09 10:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00534 | GDL17 | Residencial | 3.8 | Period | 2026-02-10 09:31 | February | 2026 | 2026-02-12 08:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00536 | GDL17 | Residencial | 6.612 | Period | 2026-02-04 14:44 | February | 2026 | 2026-02-09 10:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00539 | GDL17 | Residencial | 5.956 | Period | 2026-02-04 14:54 | February | 2026 | 2026-02-09 14:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00542 | GDL17 | Residencial | 3.8 | Period | 2026-02-06 13:25 | February | 2026 | 2026-02-10 14:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00545 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:04 | February | 2026 | 2026-02-09 11:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00546 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:25 | February | 2026 | 2026-02-06 08:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 55
202602-NM25-00548 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:14 | February | 2026 | 2026-02-09 15:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00550 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 08:34 | February | 2026 | 2026-02-27 15:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-00551 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:22 | February | 2026 | 2026-02-09 13:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00552 | GDL17 | Residencial | 6.322 | Period | 2026-02-04 15:19 | February | 2026 | 2026-02-09 13:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00553 | GDL17 | Residencial | 5.76 | Period | 2026-03-09 09:32 | March | 2026 | 2026-03-12 14:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 23
202602-NM25-00555 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 08:00 | February | 2026 | 2026-02-13 11:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 48
202602-NM25-00556 | GDL17 | Residencial | 23 | Period | 2026-02-04 15:33 | February | 2026 | 2026-02-09 09:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00558 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 15:37 | February | 2026 | 2026-02-09 13:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00562 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 16:01 | February | 2026 | 2026-02-13 16:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 48
202602-NM25-00563 | GDL17 | Residencial | 17.568 | Period | 2026-02-16 09:22 | February | 2026 | 2026-02-19 13:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 44
202602-NM25-00564 | GDL17 | Residencial | 23 | Period | 2026-03-02 11:43 | March | 2026 | 2026-03-16 10:41 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 30
202602-NM25-00565 | GDL17 | Residencial | 22.8 | Period | 2026-02-20 14:19 | February | 2026 | 2026-02-25 15:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-00569 | GDL17 | Residencial | 12 | Period | 2026-02-05 15:31 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 54
202602-NM25-00570 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 17:29 | February | 2026 | 2026-03-27 14:33 | 51 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March |  | 51 | 0 | 2026-04-01 | 55
202602-NM25-00571 | GDL17 | Residencial | 7.68 | Period | 2026-02-25 13:23 | February | 2026 | 2026-03-02 10:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-00574 | GDL17 | Residencial | 11.5 | Period | 2026-02-04 17:27 | February | 2026 | 2026-02-09 11:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00577 | GDL17 | Residencial | 5.76 | Period | 2026-02-19 10:56 | February | 2026 | 2026-02-24 14:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-00579 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:29 | February | 2026 | 2026-02-13 10:49 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 53
202602-NM25-00582 | GDL17 | Residencial | 10.85 | Period | 2026-02-04 17:44 | February | 2026 | 2026-02-09 12:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00583 | GDL17 | Residencial | 7.6 | Period | 2026-03-05 09:29 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 27
202602-NM25-00585 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:10 | March | 2026 | 2026-03-25 15:31 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 2 | 13 | 2026-04-01 | 22
202602-NM25-00588 | GDL17 | Residencial | 12 | Period | 2026-02-06 11:42 | February | 2026 | 2026-02-24 08:09 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 2 | 14 | 4 | 2026-04-01 | 54
202602-NM25-00590 | GDL17 | Residencial | 12 | Period | 2026-02-04 21:47 | February | 2026 | 2026-02-09 14:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00593 | GDL17 | Residencial | 17.5 | Period | 2026-02-13 11:41 | February | 2026 | 2026-02-16 14:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-00594 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:17 | March | 2026 | 2026-03-16 13:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 20
202602-NM25-00597 | GDL17 | Comercial | 11.5 | Period | 2026-02-17 16:49 | February | 2026 | 2026-02-23 09:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00598 | GDL17 | Residencial | 12 | Period | 2026-02-10 11:56 | February | 2026 | 2026-02-12 09:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00599 | GDL17 | Residencial | 10 | Period | 2026-02-12 17:12 | February | 2026 | 2026-02-16 15:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-00604 | GDL17 | Residencial | 3.3 | Period | 2026-02-20 18:29 | February | 2026 | 2026-02-26 08:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-00606 | GDL17 | Residencial | 11.52 | Period | 2026-02-06 10:24 | February | 2026 | 2026-02-12 14:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 54
202602-NM25-00608 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:04 | February | 2026 | 2026-02-18 09:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-00609 | GDL17 | Residencial | 3.8 | Period | 2026-02-20 20:04 | February | 2026 | 2026-02-26 15:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-00610 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 13:15 | February | 2026 | 2026-02-18 08:48 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 49
202602-NM25-00611 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:42 | February | 2026 | 2026-03-06 12:48 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 16 | 0 | 2026-04-01 | 42
202602-NM25-00612 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:04 | February | 2026 | 2026-02-09 09:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00615 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:27 | February | 2026 | 2026-02-11 13:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00616 | GDL17 | Residencial | 8 | Period | 2026-02-06 15:47 | February | 2026 | 2026-02-11 11:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00617 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 08:49 | February | 2026 | 2026-02-09 13:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00618 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:28 | February | 2026 | 2026-02-09 15:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00619 | GDL17 | Residencial | 5.856 | Period | 2026-02-05 16:26 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 54
202602-NM25-00620 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:27 | February | 2026 | 2026-02-10 09:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00621 | GDL17 | Residencial | 4.826 | Period | 2026-02-05 09:05 | February | 2026 | 2026-02-09 12:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00622 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:05 | February | 2026 | 2026-02-09 13:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00623 | GDL17 | Residencial | 7.6 | Period | 2026-02-19 09:47 | February | 2026 | 2026-02-24 08:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-00624 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:37 | February | 2026 | 2026-02-10 11:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00626 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 09:43 | February | 2026 | 2026-02-09 10:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00627 | GDL17 | Residencial | 3.835 | Period | 2026-02-05 10:30 | February | 2026 | 2026-02-09 11:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00628 | GDL17 | Residencial | 7.6 | Period | 2026-03-10 14:56 | March | 2026 | 2026-03-11 14:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 21
202602-NM25-00629 | GDL17 | Residencial | 4.72 | Period | 2026-03-24 15:54 | March | 2026 | 2026-03-30 10:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202602-NM25-00631 | GDL17 | Residencial | 23 | Period | 2026-03-10 09:46 | March | 2026 | 2026-03-12 16:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-00632 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 11:31 | February | 2026 | 2026-03-02 08:10 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 24 | 0 | 2026-04-01 | 54
202602-NM25-00634 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 11:17 | February | 2026 | 2026-02-12 08:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 54
202602-NM25-00635 | GDL17 | Residencial | 6.14 | Period | 2026-02-05 12:49 | February | 2026 | 2026-02-09 14:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00636 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 10:14 | February | 2026 | 2026-02-13 09:23 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 55
202602-NM25-00637 | GDL17 | Residencial | 8.448 | Period | 2026-02-10 09:00 | February | 2026 | 2026-02-13 08:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 50
202602-NM25-00639 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 14:11 | March | 2026 | 2026-03-16 10:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202602-NM25-00640 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:37 | February | 2026 | 2026-02-25 12:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-00641 | GDL17 | Residencial | 6.296 | Period | 2026-02-05 10:44 | February | 2026 | 2026-02-09 10:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00643 | GDL17 | Residencial | 8 | Period | 2026-02-06 10:40 | February | 2026 | 2026-02-09 13:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 54
202602-NM25-00644 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 08:25 | March | 2026 | 2026-03-09 08:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 27
202602-NM25-00645 | GDL17 | Residencial | 7.6 | Period | 2026-02-20 14:19 | February | 2026 | 2026-02-25 15:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-00646 | GDL17 | Residencial | 6.656 | Period | 2026-02-05 11:22 | February | 2026 | 2026-02-09 16:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00647 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:46 | February | 2026 | 2026-02-20 09:08 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 54
202602-NM25-00648 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 11:58 | February | 2026 | 2026-02-25 07:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-00649 | GDL17 | Residencial | 7.6 | Period | 2026-03-04 09:15 | March | 2026 | 2026-03-06 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 28
202602-NM25-00650 | GDL17 | Residencial | 18 | Period | 2026-02-19 14:29 | February | 2026 | 2026-02-24 14:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-00651 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 11:37 | February | 2026 | 2026-02-10 10:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 55
202602-NM25-00652 | GDL17 | Residencial | 7.68 | Period | 2026-03-02 08:43 | March | 2026 | 2026-03-13 13:44 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 3 | 8 | 2026-04-01 | 30
202602-NM25-00653 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 15:08 | February | 2026 | 2026-02-26 08:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 38
202602-NM25-00655 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:56 | February | 2026 | 2026-02-16 13:54 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 54
202602-NM25-00656 | GDL17 | Residencial | 7.68 | Period | 2026-03-16 13:53 | March | 2026 | 2026-03-18 07:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202602-NM25-00657 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 11:50 | February | 2026 | 2026-02-09 13:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00658 | GDL17 | Residencial | 10.672 | Period | 2026-02-05 11:53 | February | 2026 | 2026-02-09 11:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 55
202602-NM25-00661 | GDL17 | Residencial | 7.6 | Period | 2026-02-19 14:04 | February | 2026 | 2026-02-25 10:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-00662 | GDL17 | Residencial | 9 | Period | 2026-03-06 16:54 | March | 2026 | 2026-03-09 14:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 25
202602-NM25-00664 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:10 | March | 2026 | 2026-03-27 09:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-00667 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 13:04 | February | 2026 | 2026-02-18 09:26 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 13 | 0 | 2026-04-01 | 54
202602-NM25-00668 | GDL17 | Residencial | 11.582 | Period | 2026-02-05 13:13 | February | 2026 | 2026-02-09 14:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00669 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 13:29 | February | 2026 | 2026-02-09 16:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00670 | GDL17 | Residencial | 7.68 | Period | 2026-03-03 09:40 | March | 2026 | 2026-03-05 13:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-00671 | GDL17 | Residencial | 3.294 | Period | 2026-02-05 13:38 | February | 2026 | 2026-02-09 16:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00672 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:19 | March | 2026 | 2026-03-04 09:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 30
202602-NM25-00674 | GDL17 | Comercial | 7.6 | Period | 2026-02-05 13:53 | February | 2026 | 2026-02-10 16:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00675 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:27 | March | 2026 | 2026-03-11 10:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-00676 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:09 | February | 2026 | 2026-02-11 14:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00678 | GDL17 | Residencial | 16.702 | Period | 2026-02-05 14:39 | February | 2026 | 2026-02-09 15:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00679 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 14:59 | February | 2026 | 2026-02-09 14:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00680 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 14:49 | February | 2026 | 2026-02-13 15:30 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 54
202602-NM25-00681 | GDL17 | Residencial | 15.2 | Period | 2026-02-05 15:03 | February | 2026 | 2026-02-10 12:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00683 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:14 | February | 2026 | 2026-02-10 13:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00684 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 14:46 | February | 2026 | 2026-02-18 08:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 48
202602-NM25-00686 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 15:41 | February | 2026 | 2026-02-09 08:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 54
202602-NM25-00688 | GDL17 | Residencial | 8.148 | Period | 2026-02-05 15:24 | February | 2026 | 2026-02-16 08:07 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 54
202602-NM25-00689 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:50 | February | 2026 | 2026-02-13 13:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 54
202602-NM25-00690 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 15:55 | February | 2026 | 2026-03-11 15:35 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March | 2 | 5 | 29 | 2026-04-01 | 54
202602-NM25-00692 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:49 | February | 2026 | 2026-02-11 15:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00693 | GDL17 | Residencial | 7.68 | Period | 2026-02-18 16:57 | February | 2026 | 2026-02-27 10:21 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 41
202602-NM25-00694 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 08:06 | February | 2026 | 2026-03-02 12:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-00695 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:35 | March | 2026 | 2026-03-12 08:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 26
202602-NM25-00696 | GDL17 | Residencial | 7.09 | Period | 2026-02-05 15:35 | February | 2026 | 2026-02-09 09:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00697 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:46 | March | 2026 | 2026-03-30 14:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-00698 | GDL17 | Residencial | 8 | Period | 2026-02-05 16:22 | February | 2026 | 2026-02-09 16:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00700 | GDL17 | Residencial | 8.856 | Period | 2026-02-05 15:53 | February | 2026 | 2026-02-09 16:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00701 | GDL17 | Residencial | 23 | Period | 2026-02-09 15:18 | February | 2026 | 2026-02-11 12:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00702 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 16:04 | February | 2026 | 2026-02-10 13:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00704 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 16:43 | February | 2026 | 2026-02-09 16:10 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00706 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:17 | February | 2026 | 2026-02-19 09:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 47
202602-NM25-00707 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:07 | March | 2026 | 2026-03-16 15:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202602-NM25-00708 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:00 | March | 2026 | 2026-03-11 14:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-00709 | GDL17 | Residencial | 9 | Period | 2026-02-06 12:37 | February | 2026 | 2026-02-12 10:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 53
202602-NM25-00710 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 17:02 | February | 2026 | 2026-02-10 13:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00711 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 07:44 | February | 2026 | 2026-02-19 08:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-00712 | GDL17 | Residencial | 12 | Period | 2026-02-05 18:10 | February | 2026 | 2026-02-10 10:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00713 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 17:40 | February | 2026 | 2026-02-10 13:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00714 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 11:11 | March | 2026 | 2026-03-11 15:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 26
202602-NM25-00718 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:42 | March | 2026 | 2026-03-20 13:31 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 19
202602-NM25-00720 | GDL17 | Residencial | 7.6 | Period | 2026-02-05 18:03 | February | 2026 | 2026-02-17 16:19 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 12 | 0 | 2026-04-01 | 54
202602-NM25-00721 | GDL17 | Residencial | 11.5 | Period | 2026-02-05 18:21 | February | 2026 | 2026-02-10 13:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00722 | GDL17 | Residencial | 18 | Period | 2026-02-10 06:31 | February | 2026 | 2026-02-11 11:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00724 | GDL17 | Residencial | 15 | Period | 2026-02-10 18:23 | February | 2026 | 2026-02-19 08:15 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 2 | 7 | 2026-04-01 | 49
202602-NM25-00725 | GDL17 | Residencial | 12 | Period | 2026-02-05 21:35 | February | 2026 | 2026-02-10 08:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00726 | GDL17 | Residencial | 12 | Period | 2026-02-05 22:39 | February | 2026 | 2026-02-10 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00727 | GDL17 | Residencial | 3.84 | Period | 2026-02-12 08:27 | February | 2026 | 2026-02-16 12:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202602-NM25-00728 | GDL17 | Comercial | 15.2 | Period | 2026-03-16 15:51 | March | 2026 | 2026-03-19 10:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 15
202602-NM25-00729 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:27 | March | 2026 | 2026-03-17 15:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-00731 | GDL17 | Residencial | 3.8 | Period | 2026-02-18 11:44 | February | 2026 | 2026-03-06 15:29 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 16 | 0 | 2026-04-01 | 42
202602-NM25-00732 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:47 | March | 2026 | 2026-03-13 08:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 23
202602-NM25-00733 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:09 | February | 2026 | 2026-02-11 13:54 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00735 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:36 | February | 2026 | 2026-02-10 13:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00736 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:05 | February | 2026 | 2026-02-16 15:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-00737 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 09:23 | February | 2026 | 2026-02-12 13:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00738 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 08:47 | February | 2026 | 2026-02-27 09:04 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 21 | 0 | 2026-04-01 | 54
202602-NM25-00739 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 11:12 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 50
202602-NM25-00742 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:15 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 29
202602-NM25-00744 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 11:55 | March | 2026 | 2026-03-05 16:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 28
202602-NM25-00745 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:31 | February | 2026 | 2026-02-10 12:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00746 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 09:49 | February | 2026 | 2026-02-11 15:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 54
202602-NM25-00747 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:29 | February | 2026 | 2026-03-03 10:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 32
202602-NM25-00749 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:05 | February | 2026 | 2026-03-03 13:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-00752 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 10:14 | February | 2026 | 2026-02-16 14:39 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 54
202602-NM25-00753 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 07:48 | March | 2026 | 2026-03-06 14:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 27
202602-NM25-00754 | GDL17 | Residencial | 19.1 | Period | 2026-02-06 10:23 | February | 2026 | 2026-02-11 15:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 4 | 1 | 2026-04-01 | 54
202602-NM25-00756 | GDL17 | Comercial | 22.656 | Period | 2026-02-06 10:27 | February | 2026 | 2026-02-09 12:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 54
202602-NM25-00757 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 13:24 | March | 2026 | 2026-04-07 10:00 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 20 | 0 | 2026-04-01 | 13
202602-NM25-00758 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 09:26 | February | 2026 | 2026-02-26 13:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 41
202602-NM25-00759 | GDL17 | Residencial | 23 | Period | 2026-02-10 11:36 | February | 2026 | 2026-02-11 13:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00760 | GDL17 | Comercial | 15 | Period | 2026-02-10 17:59 | February | 2026 | 2026-03-23 11:06 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | March | 1 | 39 | 2 | 2026-04-01 | 49
202602-NM25-00761 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 11:22 | February | 2026 | 2026-02-20 07:46 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 14 | 0 | 2026-04-01 | 54
202602-NM25-00762 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 11:16 | February | 2026 | 2026-02-10 08:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 54
202602-NM25-00763 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 12:42 | February | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 53
202602-NM25-00764 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 09:43 | February | 2026 | 2026-02-13 07:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 50
202602-NM25-00765 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 14:08 | February | 2026 | 2026-02-13 15:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 47
202602-NM25-00766 | GDL17 | Residencial | 4.608 | Period | 2026-02-11 10:06 | February | 2026 | 2026-02-12 10:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00768 | GDL17 | Residencial | 12.53 | Period | 2026-02-06 11:51 | February | 2026 | 2026-02-09 16:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 54
202602-NM25-00771 | GDL17 | Residencial | 7.6 | Period | 2026-02-23 14:07 | February | 2026 | 2026-02-26 08:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-00775 | GDL17 | Residencial | 3.8 | Period | 2026-02-27 15:34 | February | 2026 | 2026-03-03 14:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-00776 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:47 | March | 2026 | 2026-04-07 16:08 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 14 | 0 | 2026-04-01 | 7
202602-NM25-00779 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:12 | March | 2026 | 2026-03-06 11:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-00781 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:29 | February | 2026 | 2026-02-25 08:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-00784 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:16 | February | 2026 | 2026-02-26 13:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-00786 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 17:00 | February | 2026 | 2026-02-23 09:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00787 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:32 | March | 2026 | 2026-03-06 09:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 28
202602-NM25-00788 | GDL17 | Residencial | 7.6 | Period | 2026-02-14 18:38 | February | 2026 | 2026-03-11 10:31 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 24 | 0 | 2026-04-01 | 45
202602-NM25-00789 | GDL17 | Residencial | 16.96 | Period | 2026-02-19 13:08 | February | 2026 | 2026-03-03 13:23 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 40
202602-NM25-00790 | GDL17 | Residencial | 9.136 | Period | 2026-02-06 12:46 | February | 2026 | 2026-02-11 11:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00792 | GDL17 | Residencial | 9.7 | Period | 2026-02-06 12:50 | February | 2026 | 2026-02-11 15:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00793 | GDL17 | Residencial | 8 | Period | 2026-02-19 09:28 | February | 2026 | 2026-02-24 08:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-00794 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 13:01 | February | 2026 | 2026-02-11 15:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00795 | GDL17 | Residencial | 5.536 | Period | 2026-02-06 13:01 | February | 2026 | 2026-02-11 15:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00796 | GDL17 | Residencial | 3.8 | Period | 2026-02-09 09:26 | February | 2026 | 2026-02-12 10:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 51
202602-NM25-00797 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 15:25 | February | 2026 | 2026-02-17 12:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 48
202602-NM25-00798 | GDL17 | Residencial | 11.701 | Period | 2026-02-24 15:31 | February | 2026 | 2026-03-06 10:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 4 | 6 | 2026-04-01 | 35
202602-NM25-00799 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 13:43 | February | 2026 | 2026-02-11 14:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00801 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:52 | February | 2026 | 2026-03-03 15:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-00803 | GDL17 | Residencial | 12 | Period | 2026-02-10 17:30 | February | 2026 | 2026-02-11 14:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00804 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 10:34 | March | 2026 | 2026-03-18 17:38 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 9 | 0 | 2026-04-01 | 23
202602-NM25-00805 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 13:59 | February | 2026 | 2026-02-16 14:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 10 | 0 | 2026-04-01 | 53
202602-NM25-00806 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:36 | February | 2026 | 2026-02-26 08:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-00807 | GDL17 | Residencial | 0 | Period | 2026-02-06 14:55 | February | 2026 | 2026-02-18 09:00 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 11 | 0 | 2026-04-01 | 53
202602-NM25-00808 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 08:44 | February | 2026 | 2026-02-12 13:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00809 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:29 | March | 2026 | 2026-03-16 08:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 21
202602-NM25-00810 | GDL17 | Residencial | 15 | Period | 2026-02-06 17:03 | February | 2026 | 2026-02-10 11:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00811 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:09 | February | 2026 | 2026-02-11 15:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00813 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:45 | February | 2026 | 2026-02-12 13:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 53
202602-NM25-00814 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:26 | February | 2026 | 2026-02-17 09:49 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 53
202602-NM25-00815 | GDL17 | Residencial | 10.88 | Period | 2026-02-06 14:35 | February | 2026 | 2026-02-11 10:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00816 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:51 | February | 2026 | 2026-02-13 14:23 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 53
202602-NM25-00817 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 14:42 | February | 2026 | 2026-02-11 15:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00818 | GDL17 | Residencial | 7.6 | Period | 2026-02-06 15:06 | February | 2026 | 2026-02-11 16:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00819 | GDL17 | Residencial | 7.464 | Period | 2026-02-06 14:49 | February | 2026 | 2026-02-11 15:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00820 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 15:02 | February | 2026 | 2026-02-11 16:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00821 | GDL17 | Residencial | 4.826 | Period | 2026-02-06 15:18 | February | 2026 | 2026-02-11 16:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00823 | GDL17 | Residencial | 7.846 | Period | 2026-02-06 15:19 | February | 2026 | 2026-02-11 16:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00824 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 15:28 | February | 2026 | 2026-02-11 11:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00825 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 15:28 | February | 2026 | 2026-02-11 11:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00826 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:48 | March | 2026 | 2026-03-17 07:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 22
202602-NM25-00827 | GDL17 | Residencial | 9.33 | Period | 2026-02-06 15:42 | February | 2026 | 2026-02-11 11:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 53
202602-NM25-00829 | GDL17 | Residencial | 4.83 | Period | 2026-02-06 15:47 | February | 2026 | 2026-02-10 15:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00830 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 16:16 | February | 2026 | 2026-02-24 11:25 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 18 | 0 | 2026-04-01 | 53
202602-NM25-00831 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 15:53 | February | 2026 | 2026-02-16 12:39 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 10 | 0 | 2026-04-01 | 53
202602-NM25-00832 | GDL17 | Residencial | 7.202 | Period | 2026-02-06 16:19 | February | 2026 | 2026-02-10 13:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00834 | GDL17 | Residencial | 7.202 | Period | 2026-02-06 16:30 | February | 2026 | 2026-02-10 13:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00835 | GDL17 | Residencial | 11.5 | Period | 2026-02-06 16:34 | February | 2026 | 2026-02-10 14:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00836 | GDL17 | Residencial | 9.344 | Period | 2026-02-06 16:40 | February | 2026 | 2026-02-10 11:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00837 | GDL17 | Residencial | 8.932 | Period | 2026-02-06 16:40 | February | 2026 | 2026-02-10 12:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00838 | GDL17 | Residencial | 8 | Period | 2026-02-17 16:28 | February | 2026 | 2026-02-23 09:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00839 | GDL17 | Residencial | 8 | Period | 2026-02-09 14:12 | February | 2026 | 2026-03-02 07:55 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 20 | 0 | 2026-04-01 | 50
202602-NM25-00841 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:15 | March | 2026 | 2026-03-30 09:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 7
202602-NM25-00842 | GDL17 | Residencial | 3.8 | Period | 2026-02-17 15:26 | February | 2026 | 2026-02-23 09:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00843 | GDL17 | Residencial | 15 | Period | 2026-02-06 23:45 | February | 2026 | 2026-02-10 14:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 53
202602-NM25-00844 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 11:01 | February | 2026 | 2026-02-12 08:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 51
202602-NM25-00845 | GDL17 | Residencial | 11.5 | Period | 2026-02-07 11:41 | February | 2026 | 2026-02-10 11:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 53
202602-NM25-00846 | GDL17 | Comercial | 11.5 | Period | 2026-02-16 11:49 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 44
202602-NM25-00847 | GDL17 | Comercial | 18 | Period | 2026-02-24 09:36 | February | 2026 | 2026-03-31 14:38 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | March | 1 | 24 | 11 | 2026-04-01 | 36
202602-NM25-00848 | GDL17 | Residencial | 4 | Period | 2026-02-24 07:10 | February | 2026 | 2026-03-24 14:32 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 5 | 23 | 2026-04-01 | 36
202602-NM25-00849 | GDL17 | Residencial | 12 | Period | 2026-02-11 14:21 | February | 2026 | 2026-02-12 13:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-00852 | GDL17 | Residencial | 18 | Period | 2026-02-12 13:37 | February | 2026 | 2026-02-23 09:01 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 10 | 1 | 2026-04-01 | 47
202602-NM25-00853 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:37 | February | 2026 | 2026-02-23 09:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00857 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 10:25 | February | 2026 | 2026-02-12 13:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00861 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 14:43 | February | 2026 | 2026-02-18 14:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 47
202602-NM25-00862 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 09:03 | February | 2026 | 2026-02-11 11:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00863 | GDL17 | Residencial | 6 | Period | 2026-02-10 11:19 | February | 2026 | 2026-02-11 13:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00865 | GDL17 | Comercial | 10 | Period | 2026-02-26 13:13 | February | 2026 | 2026-03-05 10:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-00866 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:10 | February | 2026 | 2026-02-26 15:14 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 41
202602-NM25-00867 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 09:31 | February | 2026 | 2026-02-10 16:21 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 51
202602-NM25-00869 | GDL17 | Residencial | 7.68 | Period | 2026-02-12 14:15 | February | 2026 | 2026-02-23 14:37 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 11 | 0 | 2026-04-01 | 47
202602-NM25-00871 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 16:20 | February | 2026 | 2026-02-18 09:54 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 50
202602-NM25-00872 | GDL17 | Residencial | 6.02 | Period | 2026-02-09 10:44 | February | 2026 | 2026-02-11 10:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 51
202602-NM25-00874 | GDL17 | Residencial | 9 | Period | 2026-02-09 13:57 | February | 2026 | 2026-02-16 15:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 50
202602-NM25-00875 | GDL17 | Residencial | 12.644 | Period | 2026-02-09 10:41 | February | 2026 | 2026-02-11 10:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 51
202602-NM25-00877 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:36 | March | 2026 | 2026-04-09 15:22 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 16 | 0 | 2026-04-01 | 8
202602-NM25-00878 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 10:46 | February | 2026 | 2026-02-11 10:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 51
202602-NM25-00879 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 10:48 | February | 2026 | 2026-02-12 16:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 51
202602-NM25-00880 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 10:54 | February | 2026 | 2026-02-11 13:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 51
202602-NM25-00881 | GDL17 | Residencial | 3.84 | Period | 2026-02-09 14:32 | February | 2026 | 2026-02-11 10:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00882 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 11:22 | February | 2026 | 2026-02-24 10:10 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 15 | 0 | 2026-04-01 | 51
202602-NM25-00883 | GDL17 | Residencial | 7.6 | Period | 2026-02-09 11:23 | February | 2026 | 2026-02-11 11:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 51
202602-NM25-00884 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:54 | February | 2026 | 2026-02-23 09:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-00885 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:53 | February | 2026 | 2026-02-24 08:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00886 | GDL17 | Residencial | 7.6 | Period | 2026-02-09 11:38 | February | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 51
202602-NM25-00888 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:16 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 22
202602-NM25-00890 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:08 | March | 2026 | 2026-03-18 15:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 14
202602-NM25-00891 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 07:08 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 44
202602-NM25-00893 | GDL17 | Residencial | 6.036 | Period | 2026-02-09 12:16 | February | 2026 | 2026-02-11 12:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00895 | GDL17 | Residencial | 6.8 | Period | 2026-02-10 15:50 | February | 2026 | 2026-02-11 13:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00897 | GDL17 | Residencial | 12 | Period | 2026-02-17 21:46 | February | 2026 | 2026-02-24 10:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 42
202602-NM25-00898 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 12:49 | February | 2026 | 2026-02-11 13:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00900 | GDL17 | Residencial | 5.956 | Period | 2026-02-09 12:33 | February | 2026 | 2026-02-11 12:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00901 | GDL17 | Residencial | 7.6 | Period | 2026-03-06 07:57 | March | 2026 | 2026-03-13 10:33 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 26
202602-NM25-00902 | GDL17 | Residencial | 17.38 | Period | 2026-02-09 12:44 | February | 2026 | 2026-02-11 12:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00903 | GDL17 | Residencial | 6.8 | Period | 2026-02-09 16:48 | February | 2026 | 2026-02-10 13:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00905 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 13:07 | February | 2026 | 2026-02-12 14:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 50
202602-NM25-00906 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 14:53 | February | 2026 | 2026-02-27 09:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-00907 | GDL17 | Residencial | 5.76 | Period | 2026-02-16 16:06 | February | 2026 | 2026-02-20 13:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 43
202602-NM25-00909 | GDL17 | Residencial | 9.8 | Period | 2026-03-03 08:55 | March | 2026 | 2026-03-05 14:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 29
202602-NM25-00912 | GDL17 | Residencial | 8 | Period | 2026-03-12 11:44 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 20
202602-NM25-00918 | GDL17 | Residencial | 12 | Period | 2026-02-11 10:46 | February | 2026 | 2026-02-13 13:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 49
202602-NM25-00922 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 17:07 | February | 2026 | 2026-02-11 11:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00925 | GDL17 | Residencial | 12 | Period | 2026-02-11 16:40 | February | 2026 | 2026-02-13 12:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 48
202602-NM25-00926 | GDL17 | Residencial | 6.8 | Period | 2026-02-09 18:19 | February | 2026 | 2026-02-10 13:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00928 | GDL17 | Residencial | 8 | Period | 2026-02-11 13:02 | February | 2026 | 2026-02-18 11:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 48
202602-NM25-00929 | GDL17 | Residencial | 12 | Period | 2026-03-05 08:47 | March | 2026 | 2026-03-06 09:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 27
202602-NM25-00930 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 15:48 | February | 2026 | 2026-02-10 13:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00931 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 15:57 | February | 2026 | 2026-02-11 13:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00932 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 16:33 | February | 2026 | 2026-02-11 14:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00933 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 16:09 | February | 2026 | 2026-02-11 13:43 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00934 | GDL17 | Residencial | 7.68 | Period | 2026-02-13 10:30 | February | 2026 | 2026-02-24 13:56 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 7 | 4 | 2026-04-01 | 47
202602-NM25-00935 | GDL17 | Residencial | 10.752 | Period | 2026-02-09 16:16 | February | 2026 | 2026-02-10 15:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00937 | GDL17 | Residencial | 9.474 | Period | 2026-02-09 16:21 | February | 2026 | 2026-02-11 14:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00938 | GDL17 | Residencial | 6.546 | Period | 2026-02-09 16:28 | February | 2026 | 2026-02-11 11:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00939 | GDL17 | Comercial | 11.5 | Period | 2026-02-09 16:30 | February | 2026 | 2026-02-10 14:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00940 | GDL17 | Residencial | 8.472 | Period | 2026-02-09 16:37 | February | 2026 | 2026-02-11 14:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00941 | GDL17 | Residencial | 3.072 | Period | 2026-02-09 16:38 | February | 2026 | 2026-02-12 08:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00942 | GDL17 | Residencial | 8 | Period | 2026-02-11 16:16 | February | 2026 | 2026-02-16 10:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 48
202602-NM25-00943 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 17:50 | February | 2026 | 2026-03-11 16:06 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 15 | 0 | 2026-04-01 | 35
202602-NM25-00944 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 16:47 | February | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 50
202602-NM25-00945 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 16:49 | February | 2026 | 2026-02-18 13:12 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 50
202602-NM25-00946 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 17:15 | February | 2026 | 2026-02-10 14:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00948 | GDL17 | Residencial | 11.5 | Period | 2026-02-09 17:27 | February | 2026 | 2026-02-12 09:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00950 | GDL17 | Residencial | 8 | Period | 2026-02-11 18:37 | February | 2026 | 2026-02-16 10:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 48
202602-NM25-00951 | GDL17 | Residencial | 15.2 | Period | 2026-03-20 12:41 | March | 2026 | 2026-03-23 14:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 11
202602-NM25-00953 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:30 | February | 2026 | 2026-02-12 08:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 49
202602-NM25-00954 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:25 | March | 2026 | 2026-03-06 10:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 28
202602-NM25-00955 | GDL17 | Residencial | 16.26 | Period | 2026-02-11 14:28 | February | 2026 | 2026-02-12 10:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-00957 | GDL17 | Residencial | 10.5 | Period | 2026-03-20 14:41 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 11
202602-NM25-00958 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:02 | February | 2026 | 2026-02-18 11:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-00959 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 09:11 | February | 2026 | 2026-02-11 15:58 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 0 | 0 | 2026-04-01 | 49
202602-NM25-00960 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 08:43 | February | 2026 | 2026-02-12 09:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00962 | GDL17 | Residencial | 24 | Period | 2026-02-10 09:18 | February | 2026 | 2026-02-18 08:46 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | February | 1 | 7 | 1 | 2026-04-01 | 50
202602-NM25-00963 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 10:03 | February | 2026 | 2026-02-27 09:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-00964 | GDL17 | Residencial | 23 | Period | 2026-02-12 09:20 | February | 2026 | 2026-02-13 12:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-00965 | GDL17 | Residencial | 23 | Period | 2026-02-11 09:39 | February | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 49
202602-NM25-00967 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 14:18 | February | 2026 | 2026-02-19 14:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-00968 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:53 | February | 2026 | 2026-02-25 15:28 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 48
202602-NM25-00969 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 09:41 | February | 2026 | 2026-02-11 14:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00970 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 09:48 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 50
202602-NM25-00971 | GDL17 | Residencial | 3.84 | Period | 2026-02-11 09:20 | February | 2026 | 2026-02-11 15:53 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 0 | 0 | 2026-04-01 | 49
202602-NM25-00975 | GDL17 | Residencial | 6.256 | Period | 2026-02-10 10:18 | February | 2026 | 2026-02-11 15:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00976 | GDL17 | Residencial | 5.76 | Period | 2026-02-18 20:42 | February | 2026 | 2026-02-24 11:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-00978 | GDL17 | Residencial | 8 | Period | 2026-02-12 12:01 | February | 2026 | 2026-02-17 08:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-00979 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 14:00 | March | 2026 | 2026-04-06 15:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 7 | 0 | 2026-04-01 | 1
202602-NM25-00980 | GDL17 | Residencial | 5.376 | Period | 2026-02-10 10:55 | February | 2026 | 2026-02-12 16:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00981 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 16:18 | March | 2026 | 2026-03-25 13:43 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 5 | 9 | 2026-04-01 | 20
202602-NM25-00982 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:52 | February | 2026 | 2026-02-25 16:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-00983 | GDL17 | Residencial | 8.064 | Period | 2026-02-10 11:18 | February | 2026 | 2026-02-12 15:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 50
202602-NM25-00984 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 15:51 | February | 2026 | 2026-02-11 12:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00986 | GDL17 | Comercial | 15 | Period | 2026-02-11 16:59 | February | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 48
202602-NM25-00987 | GDL17 | Residencial | 8.304 | Period | 2026-02-10 11:54 | February | 2026 | 2026-02-11 13:24 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 50
202602-NM25-00990 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 12:10 | February | 2026 | 2026-02-11 13:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00991 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:09 | February | 2026 | 2026-03-02 14:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-00992 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:06 | March | 2026 | 2026-03-11 13:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 26
202602-NM25-00993 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 11:22 | February | 2026 | 2026-02-24 09:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-00994 | GDL17 | Residencial | 23 | Period | 2026-02-16 13:42 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 43
202602-NM25-00995 | GDL17 | Residencial | 14.976 | Period | 2026-02-10 12:36 | February | 2026 | 2026-02-11 13:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00996 | GDL17 | Residencial | 23 | Period | 2026-02-10 12:58 | February | 2026 | 2026-02-11 14:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00997 | GDL17 | Residencial | 8 | Period | 2026-03-12 09:55 | March | 2026 | 2026-03-17 12:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-00998 | GDL17 | Residencial | 7.6 | Period | 2026-02-10 12:53 | February | 2026 | 2026-02-11 14:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-00999 | GDL17 | Residencial | 7.6 | Period | 2026-03-10 13:28 | March | 2026 | 2026-03-12 13:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 21
202602-NM25-01000 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 09:00 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 48
202602-NM25-01001 | GDL17 | Residencial | 3.8 | Period | 2026-03-09 15:06 | March | 2026 | 2026-03-10 10:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-01002 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 07:06 | February | 2026 | 2026-02-17 09:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 48
202602-NM25-01003 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 13:37 | February | 2026 | 2026-02-16 07:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 49
202602-NM25-01004 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 07:13 | February | 2026 | 2026-02-17 14:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 48
202602-NM25-01005 | GDL17 | Residencial | 8 | Period | 2026-03-10 08:38 | March | 2026 | 2026-03-16 13:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 22
202602-NM25-01006 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 15:10 | March | 2026 | 2026-03-12 12:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202602-NM25-01008 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:16 | February | 2026 | 2026-02-13 10:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 49
202602-NM25-01009 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:26 | February | 2026 | 2026-02-11 14:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01011 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:40 | February | 2026 | 2026-02-11 14:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01014 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:56 | February | 2026 | 2026-02-12 14:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 49
202602-NM25-01015 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:18 | February | 2026 | 2026-02-13 10:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01017 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:33 | February | 2026 | 2026-02-13 09:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01018 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 14:57 | February | 2026 | 2026-02-16 12:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 49
202602-NM25-01021 | GDL17 | Residencial | 5 | Period | 2026-02-14 12:33 | February | 2026 | 2026-02-18 10:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 45
202602-NM25-01022 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 15:17 | February | 2026 | 2026-02-11 12:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01023 | GDL17 | Comercial | 7.6 | Period | 2026-03-26 14:27 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 5
202602-NM25-01024 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 15:21 | February | 2026 | 2026-02-12 13:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 49
202602-NM25-01025 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 15:24 | February | 2026 | 2026-02-12 11:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 49
202602-NM25-01027 | GDL17 | Residencial | 3.84 | Period | 2026-02-27 08:59 | February | 2026 | 2026-03-05 10:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-01028 | GDL17 | Residencial | 4.026 | Period | 2026-02-10 15:33 | February | 2026 | 2026-02-11 14:54 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01029 | GDL17 | Residencial | 9.136 | Period | 2026-02-10 15:34 | February | 2026 | 2026-02-11 14:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01030 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 16:02 | February | 2026 | 2026-02-16 13:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 49
202602-NM25-01031 | GDL17 | Residencial | 8 | Period | 2026-02-11 16:36 | February | 2026 | 2026-02-17 14:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 48
202602-NM25-01032 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:13 | March | 2026 | 2026-03-11 15:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-01033 | GDL17 | Residencial | 9.136 | Period | 2026-02-10 15:43 | February | 2026 | 2026-02-11 12:42 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01034 | GDL17 | Comercial | 7.6 | Period | 2026-02-13 15:04 | February | 2026 | 2026-03-27 10:11 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 42 | 0 | 2026-04-01 | 46
202602-NM25-01035 | GDL17 | Residencial | 5.566 | Period | 2026-02-10 15:53 | February | 2026 | 2026-02-11 12:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01036 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 16:07 | February | 2026 | 2026-02-11 14:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01037 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:09 | March | 2026 | 2026-03-11 14:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 21
202602-NM25-01038 | GDL17 | Residencial | 7.974 | Period | 2026-02-10 16:23 | February | 2026 | 2026-02-11 14:54 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01039 | GDL17 | Residencial | 23 | Period | 2026-03-10 14:54 | March | 2026 | 2026-03-13 09:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 21
202602-NM25-01041 | GDL17 | Residencial | 7.67 | Period | 2026-02-10 16:43 | February | 2026 | 2026-02-11 15:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01042 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:55 | February | 2026 | 2026-03-03 16:16 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 11 | 0 | 2026-04-01 | 39
202602-NM25-01043 | GDL17 | Residencial | 11.44 | Period | 2026-02-10 16:39 | February | 2026 | 2026-02-11 15:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01044 | GDL17 | Residencial | 9.6 | Period | 2026-02-10 17:31 | February | 2026 | 2026-02-18 09:34 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 49
202602-NM25-01045 | GDL17 | Residencial | 23 | Period | 2026-02-10 17:45 | February | 2026 | 2026-02-11 15:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01046 | GDL17 | Residencial | 6.8 | Period | 2026-02-10 21:32 | February | 2026 | 2026-02-11 15:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01047 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 18:03 | March | 2026 | 2026-03-23 08:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 14
202602-NM25-01048 | GDL17 | Residencial | 11.5 | Period | 2026-02-10 18:05 | February | 2026 | 2026-02-11 14:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01049 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 09:41 | February | 2026 | 2026-02-11 15:51 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 0 | 0 | 2026-04-01 | 49
202602-NM25-01050 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:23 | March | 2026 | 2026-03-25 15:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 9
202602-NM25-01051 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:39 | March | 2026 | 2026-03-24 11:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-01053 | GDL17 | Residencial | 16.104 | Period | 2026-03-26 07:08 | March | 2026 | 2026-03-30 13:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 6
202602-NM25-01054 | GDL17 | Residencial | 8 | Period | 2026-03-10 11:03 | March | 2026 | 2026-03-13 13:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 22
202602-NM25-01057 | GDL17 | Residencial | 16.896 | Period | 2026-03-17 09:01 | March | 2026 | 2026-03-18 14:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 15
202602-NM25-01058 | GDL17 | Residencial | 8 | Period | 2026-02-20 12:55 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 39
202602-NM25-01059 | GDL17 | Residencial | 6.612 | Period | 2026-02-11 08:14 | February | 2026 | 2026-02-19 15:34 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 49
202602-NM25-01060 | GDL17 | Residencial | 9.562 | Period | 2026-02-11 08:24 | February | 2026 | 2026-02-25 07:40 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 14 | 0 | 2026-04-01 | 49
202602-NM25-01062 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 08:37 | February | 2026 | 2026-02-19 08:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 47
202602-NM25-01063 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:38 | February | 2026 | 2026-02-12 11:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01066 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 08:43 | February | 2026 | 2026-02-17 14:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 49
202602-NM25-01067 | GDL17 | Residencial | 3.8 | Period | 2026-03-11 08:24 | March | 2026 | 2026-03-12 14:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 21
202602-NM25-01068 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 08:23 | March | 2026 | 2026-03-11 11:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 27
202602-NM25-01069 | GDL17 | Residencial | 9.136 | Period | 2026-02-11 09:09 | February | 2026 | 2026-02-11 15:43 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 0 | 0 | 2026-04-01 | 49
202602-NM25-01070 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 14:05 | March | 2026 | 2026-03-17 13:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202602-NM25-01071 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 12:52 | March | 2026 | 2026-03-23 12:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-01074 | GDL17 | Comercial | 23 | Period | 2026-02-23 11:29 | February | 2026 | 2026-03-09 09:55 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 13 | 1 | 2026-04-01 | 37
202602-NM25-01075 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:50 | February | 2026 | 2026-02-13 09:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01076 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 10:52 | February | 2026 | 2026-02-17 07:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 49
202602-NM25-01077 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 10:24 | February | 2026 | 2026-02-16 10:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 49
202602-NM25-01078 | GDL17 | Residencial | 4.992 | Period | 2026-02-16 14:33 | February | 2026 | 2026-03-03 16:09 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 15 | 0 | 2026-04-01 | 43
202602-NM25-01080 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 10:41 | February | 2026 | 2026-02-24 08:23 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 13 | 0 | 2026-04-01 | 49
202602-NM25-01081 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 10:53 | February | 2026 | 2026-02-12 12:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 49
202602-NM25-01082 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:55 | March | 2026 | 2026-03-11 16:18 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 28
202602-NM25-01083 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 11:34 | February | 2026 | 2026-02-13 13:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 49
202602-NM25-01085 | GDL17 | Residencial | 16 | Period | 2026-02-12 19:21 | February | 2026 | 2026-02-16 10:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01086 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:22 | February | 2026 | 2026-02-18 08:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 47
202602-NM25-01087 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 08:29 | March | 2026 | 2026-03-10 15:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 28
202602-NM25-01088 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:15 | February | 2026 | 2026-02-12 13:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01089 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 21:03 | March | 2026 | 2026-03-18 11:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 19
202602-NM25-01090 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:48 | February | 2026 | 2026-02-24 09:40 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01091 | GDL17 | Residencial | 5.196 | Period | 2026-02-11 12:08 | February | 2026 | 2026-02-12 12:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01092 | GDL17 | Residencial | 6.84 | Period | 2026-02-11 12:16 | February | 2026 | 2026-02-12 12:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01093 | GDL17 | Residencial | 7.462 | Period | 2026-02-11 12:20 | February | 2026 | 2026-02-12 12:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01095 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 11:54 | March | 2026 | 2026-03-06 09:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 28
202602-NM25-01096 | GDL17 | Residencial | 6.322 | Period | 2026-02-11 12:29 | February | 2026 | 2026-02-12 12:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01097 | GDL17 | Residencial | 6.672 | Period | 2026-02-11 12:30 | February | 2026 | 2026-02-12 12:54 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01099 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 12:40 | February | 2026 | 2026-02-12 13:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01100 | GDL17 | Residencial | 15 | Period | 2026-02-12 16:18 | February | 2026 | 2026-02-16 13:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01101 | GDL17 | Residencial | 7.102 | Period | 2026-02-11 12:50 | February | 2026 | 2026-02-12 13:24 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01102 | GDL17 | Residencial | 7.6 | Period | 2026-03-23 13:09 | March | 2026 | 2026-03-25 14:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 8
202602-NM25-01104 | GDL17 | Residencial | 9.216 | Period | 2026-02-11 15:07 | February | 2026 | 2026-02-12 10:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01105 | GDL17 | Residencial | 12.208 | Period | 2026-02-11 14:12 | February | 2026 | 2026-02-12 13:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01107 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:19 | March | 2026 | 2026-03-25 16:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 8
202602-NM25-01108 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 11:22 | March | 2026 | 2026-03-18 15:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202602-NM25-01109 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:09 | March | 2026 | 2026-03-13 15:00 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 10 | 0 | 2026-04-01 | 28
202602-NM25-01110 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:12 | February | 2026 | 2026-03-17 08:48 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 27 | 0 | 2026-04-01 | 41
202602-NM25-01111 | GDL17 | Residencial | 3.84 | Period | 2026-02-12 09:12 | February | 2026 | 2026-02-16 16:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202602-NM25-01112 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:39 | March | 2026 | 2026-03-04 14:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 30
202602-NM25-01113 | GDL17 | Residencial | 7.202 | Period | 2026-02-11 14:22 | February | 2026 | 2026-02-12 13:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01114 | GDL17 | Residencial | 13.036 | Period | 2026-02-11 14:32 | February | 2026 | 2026-02-12 10:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01115 | GDL17 | Comercial | 12.288 | Period | 2026-02-11 15:06 | February | 2026 | 2026-02-12 10:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01117 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:32 | February | 2026 | 2026-02-19 11:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 48
202602-NM25-01118 | GDL17 | Residencial | 3.84 | Period | 2026-02-16 10:44 | February | 2026 | 2026-03-02 10:17 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 44
202602-NM25-01120 | GDL17 | Residencial | 7.6 | Period | 2026-02-11 15:20 | February | 2026 | 2026-02-17 13:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 48
202602-NM25-01121 | GDL17 | Residencial | 5.76 | Period | 2026-02-19 13:17 | February | 2026 | 2026-02-27 13:12 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 40
202602-NM25-01122 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 16:15 | February | 2026 | 2026-02-13 15:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 48
202602-NM25-01123 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:36 | March | 2026 | 2026-04-07 16:24 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 14 | 0 | 2026-04-01 | 8
202602-NM25-01124 | GDL17 | Residencial | 23 | Period | 2026-03-10 10:48 | March | 2026 | 2026-03-30 13:09 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 4 | 16 | 2026-04-01 | 22
202602-NM25-01125 | GDL17 | Residencial | 10 | Period | 2026-02-19 16:23 | February | 2026 | 2026-02-27 08:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 40
202602-NM25-01127 | GDL17 | Residencial | 8 | Period | 2026-02-18 09:24 | February | 2026 | 2026-02-23 09:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01129 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:39 | February | 2026 | 2026-02-27 14:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-01130 | GDL17 | Residencial | 6.902 | Period | 2026-02-11 17:23 | February | 2026 | 2026-02-13 16:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 48
202602-NM25-01131 | GDL17 | Residencial | 8.26 | Period | 2026-02-11 17:15 | February | 2026 | 2026-02-12 10:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01132 | GDL17 | Residencial | 7.38 | Period | 2026-02-11 17:24 | February | 2026 | 2026-02-12 10:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01133 | GDL17 | Residencial | 6.546 | Period | 2026-02-11 17:38 | February | 2026 | 2026-02-12 10:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01134 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 17:37 | February | 2026 | 2026-02-16 09:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 48
202602-NM25-01135 | GDL17 | Residencial | 6.072 | Period | 2026-02-11 17:48 | February | 2026 | 2026-02-12 10:35 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01136 | GDL17 | Residencial | 11.5 | Period | 2026-02-11 18:13 | February | 2026 | 2026-02-13 09:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 48
202602-NM25-01137 | GDL17 | Residencial | 11.522 | Period | 2026-02-11 18:13 | February | 2026 | 2026-02-12 10:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01138 | GDL17 | Residencial | 4.026 | Period | 2026-02-11 18:56 | February | 2026 | 2026-02-16 14:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 3 | 2 | 2026-04-01 | 48
202602-NM25-01139 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:05 | March | 2026 | 2026-03-16 12:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 22
202602-NM25-01140 | GDL17 | Residencial | 11.44 | Period | 2026-02-11 18:58 | February | 2026 | 2026-02-12 10:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01141 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:41 | March | 2026 | 2026-03-24 08:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 11
202602-NM25-01142 | GDL17 | Residencial | 15 | Period | 2026-02-11 22:36 | February | 2026 | 2026-02-20 09:08 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 48
202602-NM25-01143 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:53 | March | 2026 | 2026-03-06 14:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 26
202602-NM25-01144 | GDL17 | Residencial | 8.126 | Period | 2026-02-12 08:32 | February | 2026 | 2026-02-13 12:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 48
202602-NM25-01145 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 19:15 | March | 2026 | 2026-03-30 10:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 7
202602-NM25-01146 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:08 | February | 2026 | 2026-02-26 10:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 40
202602-NM25-01147 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:46 | February | 2026 | 2026-02-16 14:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 48
202602-NM25-01148 | GDL17 | Residencial | 13.908 | Period | 2026-03-07 13:55 | March | 2026 | 2026-03-09 11:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 24
202602-NM25-01149 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 08:42 | February | 2026 | 2026-03-02 16:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-01150 | GDL17 | Residencial | 8 | Period | 2026-03-10 08:03 | March | 2026 | 2026-03-11 11:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-01151 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 09:48 | February | 2026 | 2026-02-23 10:34 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 11 | 0 | 2026-04-01 | 48
202602-NM25-01152 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:05 | February | 2026 | 2026-02-13 10:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01153 | GDL17 | Residencial | 18 | Period | 2026-02-12 11:18 | February | 2026 | 2026-03-02 14:30 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 18 | 0 | 2026-04-01 | 48
202602-NM25-01154 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 10:35 | February | 2026 | 2026-02-13 09:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 48
202602-NM25-01155 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:57 | February | 2026 | 2026-03-11 15:44 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 20 | 0 | 2026-04-01 | 40
202602-NM25-01157 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:36 | March | 2026 | 2026-03-17 14:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 15
202602-NM25-01158 | GDL17 | Residencial | 8 | Period | 2026-02-17 09:57 | February | 2026 | 2026-02-20 08:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01159 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:10 | March | 2026 | 2026-03-05 09:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202602-NM25-01161 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 08:28 | February | 2026 | 2026-02-26 08:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01163 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:18 | March | 2026 | 2026-03-16 15:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 18
202602-NM25-01164 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 16:24 | March | 2026 | 2026-03-16 12:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-01165 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 20:16 | February | 2026 | 2026-02-23 09:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01166 | GDL17 | Residencial | 6.296 | Period | 2026-02-12 12:03 | February | 2026 | 2026-02-13 12:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 47
202602-NM25-01167 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:53 | February | 2026 | 2026-03-04 08:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-01169 | GDL17 | Residencial | 7.68 | Period | 2026-02-22 14:52 | February | 2026 | 2026-02-26 08:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-01170 | GDL17 | Residencial | 23 | Period | 2026-02-18 16:42 | February | 2026 | 2026-02-24 13:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01172 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 12:32 | February | 2026 | 2026-02-23 14:47 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 11 | 0 | 2026-04-01 | 47
202602-NM25-01173 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:36 | February | 2026 | 2026-03-04 09:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-01174 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 14:01 | February | 2026 | 2026-03-04 09:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 5 | 1 | 2026-04-01 | 33
202602-NM25-01176 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 09:56 | February | 2026 | 2026-02-27 09:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-01177 | GDL17 | Residencial | 10.752 | Period | 2026-02-17 14:19 | February | 2026 | 2026-02-23 09:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01178 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:30 | February | 2026 | 2026-02-24 14:10 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 11 | 0 | 2026-04-01 | 47
202602-NM25-01181 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 08:35 | March | 2026 | 2026-03-30 10:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 7
202602-NM25-01189 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:17 | February | 2026 | 2026-03-03 11:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-01190 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:39 | March | 2026 | 2026-03-10 09:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-01192 | GDL17 | Residencial | 12.178 | Period | 2026-02-12 13:22 | February | 2026 | 2026-02-16 10:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-01193 | GDL17 | Residencial | 18 | Period | 2026-02-19 13:38 | February | 2026 | 2026-02-24 14:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01195 | GDL17 | Residencial | 9.7 | Period | 2026-02-12 13:32 | February | 2026 | 2026-02-16 10:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-01196 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 07:40 | February | 2026 | 2026-02-18 14:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01197 | GDL17 | Residencial | 12 | Period | 2026-02-19 21:59 | February | 2026 | 2026-02-25 13:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01198 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 14:25 | March | 2026 | 2026-03-18 08:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 18
202602-NM25-01199 | GDL17 | Residencial | 12 | Period | 2026-02-19 10:11 | February | 2026 | 2026-02-24 08:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 41
202602-NM25-01200 | GDL17 | Residencial | 5.666 | Period | 2026-02-12 13:54 | February | 2026 | 2026-02-16 10:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-01201 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:11 | February | 2026 | 2026-02-23 08:28 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 47
202602-NM25-01202 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:10 | February | 2026 | 2026-02-18 12:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01204 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:29 | March | 2026 | 2026-03-18 14:57 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 22
202602-NM25-01205 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 17:04 | March | 2026 |  |  | Customer Orientation | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 13
202602-NM25-01207 | GDL17 | Residencial | 14.976 | Period | 2026-02-17 07:39 | February | 2026 | 2026-03-02 07:59 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 43
202602-NM25-01209 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 07:17 | February | 2026 | 2026-02-20 08:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 44
202602-NM25-01210 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:24 | February | 2026 | 2026-02-23 09:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01211 | GDL17 | Residencial | 23 | Period | 2026-02-13 09:36 | February | 2026 | 2026-02-16 14:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-01212 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 14:35 | February | 2026 | 2026-02-16 10:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-01219 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 08:57 | February | 2026 | 2026-03-13 10:52 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 28 | 0 | 2026-04-01 | 47
202602-NM25-01220 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:50 | March | 2026 | 2026-03-06 09:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 30
202602-NM25-01225 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 13:34 | March | 2026 | 2026-03-19 08:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 19
202602-NM25-01226 | GDL17 | Comercial | 15.204 | Period | 2026-02-12 15:36 | February | 2026 | 2026-02-16 13:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01227 | GDL17 | Residencial | 9.516 | Period | 2026-03-16 08:32 | March | 2026 | 2026-03-17 13:35 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 1 | 0 | 2026-04-01 | 16
202602-NM25-01228 | GDL17 | Residencial | 7.6 | Period | 2026-03-23 14:07 | March | 2026 | 2026-03-30 07:53 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 8
202602-NM25-01229 | GDL17 | Residencial | 10.928 | Period | 2026-02-12 15:31 | February | 2026 | 2026-02-16 14:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01230 | GDL17 | Residencial | 14.18 | Period | 2026-02-12 15:32 | February | 2026 | 2026-02-16 15:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01231 | GDL17 | Residencial | 7.072 | Period | 2026-02-12 15:46 | February | 2026 | 2026-02-16 15:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01232 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 08:09 | March | 2026 | 2026-04-01 10:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 2
202602-NM25-01233 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 15:49 | February | 2026 | 2026-02-16 15:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01234 | GDL17 | Residencial | 12 | Period | 2026-02-12 18:07 | February | 2026 | 2026-02-17 15:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 47
202602-NM25-01235 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 15:58 | February | 2026 | 2026-02-16 15:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01236 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:12 | February | 2026 | 2026-03-04 16:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-01237 | GDL17 | Residencial | 9.136 | Period | 2026-02-12 16:10 | February | 2026 | 2026-02-16 15:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01238 | GDL17 | Residencial | 7.102 | Period | 2026-02-12 16:11 | February | 2026 | 2026-02-16 15:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01240 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 14:59 | February | 2026 | 2026-02-18 11:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01242 | GDL17 | Residencial | 11.5 | Period | 2026-02-12 16:27 | February | 2026 | 2026-02-16 15:45 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01243 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 17:30 | February | 2026 | 2026-02-26 08:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-01244 | GDL17 | Residencial | 7.6 | Period | 2026-02-12 16:34 | February | 2026 | 2026-02-16 15:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01245 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 14:14 | February | 2026 | 2026-02-27 10:57 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | February | 1 | 13 | 1 | 2026-04-01 | 46
202602-NM25-01246 | GDL17 | Residencial | 9 | Period | 2026-02-24 10:44 | February | 2026 | 2026-02-27 09:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-01247 | GDL17 | Residencial | 12 | Period | 2026-02-13 17:02 | February | 2026 | 2026-02-20 07:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 46
202602-NM25-01248 | GDL17 | Comercial | 6.8 | Period | 2026-03-16 12:50 | March | 2026 | 2026-03-17 15:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202602-NM25-01249 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:18 | March | 2026 | 2026-04-13 08:10 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 13 | 0 | 2026-04-01 | 2
202602-NM25-01250 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 07:38 | February | 2026 | 2026-02-16 10:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01251 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:04 | March | 2026 | 2026-03-04 09:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 30
202602-NM25-01252 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:06 | March | 2026 | 2026-03-16 13:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 20
202602-NM25-01255 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 08:25 | February | 2026 | 2026-02-17 09:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 47
202602-NM25-01256 | GDL17 | Residencial | 10.672 | Period | 2026-02-13 08:29 | February | 2026 | 2026-02-18 14:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 47
202602-NM25-01259 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:09 | February | 2026 | 2026-02-17 15:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01260 | GDL17 | Comercial | 11.5 | Period | 2026-03-10 11:15 | March | 2026 | 2026-03-11 15:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-01262 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:08 | February | 2026 | 2026-02-25 15:32 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 12 | 0 | 2026-04-01 | 47
202602-NM25-01263 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 09:22 | February | 2026 | 2026-02-16 14:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-01264 | GDL17 | Residencial | 5.076 | Period | 2026-02-13 09:17 | February | 2026 | 2026-02-16 13:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 47
202602-NM25-01265 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:05 | February | 2026 | 2026-02-26 10:03 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 10 | 0 | 2026-04-01 | 44
202602-NM25-01266 | GDL17 | Residencial | 4.992 | Period | 2026-02-16 10:05 | February | 2026 | 2026-02-19 11:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01267 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 10:25 | March | 2026 | 2026-03-16 13:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 7 | 0 | 2026-04-01 | 23
202602-NM25-01268 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 13:29 | March | 2026 | 2026-03-16 15:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 19
202602-NM25-01269 | GDL17 | Residencial | 10 | Period | 2026-02-20 17:19 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 39
202602-NM25-01270 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:58 | February | 2026 | 2026-02-16 15:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01271 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 09:47 | February | 2026 | 2026-03-09 11:06 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 19 | 0 | 2026-04-01 | 41
202602-NM25-01273 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 15:41 | February | 2026 | 2026-03-03 13:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-01276 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 13:27 | February | 2026 | 2026-03-03 09:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-01277 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:33 | February | 2026 | 2026-02-16 15:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01278 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 10:55 | February | 2026 | 2026-02-18 11:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 47
202602-NM25-01279 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 10:50 | February | 2026 | 2026-02-19 15:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 47
202602-NM25-01280 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:45 | March | 2026 | 2026-03-13 14:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 21
202602-NM25-01281 | GDL17 | Residencial | 23 | Period | 2026-02-13 11:09 | February | 2026 | 2026-03-31 07:39 | 46 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March | 1 | 39 | 6 | 2026-04-01 | 47
202602-NM25-01282 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 15:50 | February | 2026 | 2026-02-19 13:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | February | 1 | 5 | 1 | 2026-04-01 | 46
202602-NM25-01284 | GDL17 | Residencial | 3.8 | Period | 2026-02-27 11:56 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 33
202602-NM25-01285 | GDL17 | Comercial | 11.5 | Period | 2026-02-13 11:32 | February | 2026 | 2026-02-18 15:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 47
202602-NM25-01286 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:02 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 8
202602-NM25-01287 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:42 | February | 2026 | 2026-02-20 09:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 47
202602-NM25-01288 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 11:45 | February | 2026 | 2026-02-16 15:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 47
202602-NM25-01289 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:07 | February | 2026 | 2026-02-18 11:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01291 | GDL17 | Residencial | 12 | Period | 2026-02-18 14:24 | February | 2026 | 2026-02-23 14:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01292 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:03 | February | 2026 | 2026-02-19 13:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 46
202602-NM25-01293 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:14 | February | 2026 | 2026-02-18 10:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01295 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 12:25 | February | 2026 | 2026-02-20 08:39 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 46
202602-NM25-01296 | GDL17 | Residencial | 18.09 | Period | 2026-02-13 12:52 | February | 2026 | 2026-02-18 10:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01297 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:15 | March | 2026 | 2026-03-10 10:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-01298 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:04 | February | 2026 | 2026-03-03 15:51 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 18 | 0 | 2026-04-01 | 46
202602-NM25-01299 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 13:18 | February | 2026 | 2026-02-18 10:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01300 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 22:35 | February | 2026 | 2026-02-25 08:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01301 | GDL17 | Residencial | 4.608 | Period | 2026-02-26 12:17 | February | 2026 | 2026-03-03 13:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-01302 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 13:34 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 33
202602-NM25-01303 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:24 | March | 2026 | 2026-03-31 11:21 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 2 | 6 | 2026-04-01 | 9
202602-NM25-01304 | GDL17 | Residencial | 7.68 | Period | 2026-02-17 10:17 | February | 2026 | 2026-02-20 08:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01306 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:47 | February | 2026 | 2026-02-18 11:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01307 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:25 | March | 2026 | 2026-03-12 09:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 22
202602-NM25-01311 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:13 | March | 2026 | 2026-03-10 14:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 28
202602-NM25-01314 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:43 | March | 2026 | 2026-03-12 11:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 22
202602-NM25-01316 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:43 | February | 2026 | 2026-03-03 13:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-01317 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:09 | March | 2026 | 2026-03-13 08:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 20
202602-NM25-01318 | GDL17 | Residencial | 7.38 | Period | 2026-02-13 15:30 | February | 2026 | 2026-02-18 10:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01319 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 15:29 | February | 2026 | 2026-02-20 08:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 46
202602-NM25-01320 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 08:53 | March | 2026 | 2026-04-08 13:28 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 28 | 0 | 2026-04-01 | 21
202602-NM25-01321 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:39 | February | 2026 | 2026-02-19 14:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 46
202602-NM25-01322 | GDL17 | Residencial | 7.6 | Period | 2026-02-13 15:47 | February | 2026 | 2026-02-18 12:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01323 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 15:59 | February | 2026 | 2026-02-25 13:57 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 12 | 0 | 2026-04-01 | 46
202602-NM25-01324 | GDL17 | Residencial | 11.4 | Period | 2026-02-19 12:04 | February | 2026 | 2026-02-24 13:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01325 | GDL17 | Residencial | 7.6 | Period | 2026-02-16 08:06 | February | 2026 | 2026-02-19 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01326 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:13 | February | 2026 | 2026-02-18 12:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01327 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:12 | February | 2026 | 2026-02-18 09:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 46
202602-NM25-01328 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:25 | February | 2026 | 2026-02-18 10:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01329 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:28 | February | 2026 | 2026-02-19 13:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 46
202602-NM25-01330 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:42 | February | 2026 | 2026-02-18 15:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01331 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:36 | February | 2026 | 2026-02-23 08:09 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 9 | 0 | 2026-04-01 | 46
202602-NM25-01332 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:23 | February | 2026 | 2026-02-19 08:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01333 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 07:37 | March | 2026 | 2026-03-11 09:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 27
202602-NM25-01334 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:47 | February | 2026 | 2026-02-24 07:49 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 10 | 0 | 2026-04-01 | 46
202602-NM25-01335 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:53 | February | 2026 | 2026-02-18 10:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 46
202602-NM25-01336 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:06 | February | 2026 | 2026-02-19 10:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01337 | GDL17 | Residencial | 11.5 | Period | 2026-02-13 16:58 | February | 2026 | 2026-02-18 10:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 46
202602-NM25-01338 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:11 | March | 2026 | 2026-03-16 11:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 22
202602-NM25-01339 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 17:22 | March | 2026 | 2026-03-16 15:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-01340 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:16 | February | 2026 | 2026-02-19 11:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01341 | GDL17 | Residencial | 8 | Period | 2026-02-16 08:07 | February | 2026 | 2026-02-23 09:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | February | 1 | 4 | 3 | 2026-04-01 | 44
202602-NM25-01342 | GDL17 | Residencial | 4.224 | Period | 2026-02-16 07:56 | February | 2026 | 2026-03-03 14:40 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 16 | 0 | 2026-04-01 | 44
202602-NM25-01344 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:12 | February | 2026 | 2026-02-23 09:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01345 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 14:19 | February | 2026 | 2026-03-04 08:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-01346 | GDL17 | Residencial | 7.6 | Period | 2026-02-16 08:42 | February | 2026 | 2026-02-19 13:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 44
202602-NM25-01348 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:31 | February | 2026 | 2026-02-19 13:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 44
202602-NM25-01349 | GDL17 | Residencial | 13.44 | Period | 2026-02-18 13:48 | February | 2026 | 2026-02-23 14:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01351 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:41 | February | 2026 | 2026-02-19 13:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 44
202602-NM25-01354 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:56 | February | 2026 | 2026-03-12 08:48 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 15 | 0 | 2026-04-01 | 35
202602-NM25-01355 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 08:52 | February | 2026 | 2026-02-19 14:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 44
202602-NM25-01357 | GDL17 | Residencial | 12 | Period | 2026-02-17 17:41 | February | 2026 | 2026-02-23 09:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01358 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:01 | February | 2026 | 2026-02-19 10:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01361 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 07:42 | February | 2026 | 2026-02-26 08:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-01362 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:36 | February | 2026 | 2026-02-24 14:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01363 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:13 | February | 2026 | 2026-02-19 14:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 44
202602-NM25-01364 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:49 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 44
202602-NM25-01366 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:24 | February | 2026 | 2026-02-19 08:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01367 | GDL17 | Residencial | 7.6 | Period | 2026-02-16 10:07 | February | 2026 | 2026-02-23 15:19 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 44
202602-NM25-01369 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 09:51 | February | 2026 | 2026-02-19 08:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 44
202602-NM25-01370 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 11:23 | February | 2026 | 2026-02-20 08:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01373 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 10:08 | February | 2026 | 2026-02-24 15:30 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 44
202602-NM25-01376 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 10:18 | February | 2026 | 2026-02-19 11:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01377 | GDL17 | Residencial | 10.33 | Period | 2026-02-16 10:51 | February | 2026 | 2026-02-19 11:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01378 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:08 | February | 2026 | 2026-03-03 09:15 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 41
202602-NM25-01379 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 08:05 | February | 2026 | 2026-03-02 14:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-01380 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:02 | February | 2026 | 2026-02-19 10:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01381 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:40 | February | 2026 | 2026-02-25 08:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01383 | GDL17 | Residencial | 10.608 | Period | 2026-02-16 11:31 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 44
202602-NM25-01384 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:39 | February | 2026 | 2026-02-19 12:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01385 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:22 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 44
202602-NM25-01387 | GDL17 | Residencial | 3.84 | Period | 2026-02-20 08:24 | February | 2026 | 2026-02-26 08:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01388 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:47 | February | 2026 | 2026-02-19 08:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01390 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:45 | February | 2026 | 2026-02-19 12:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 44
202602-NM25-01391 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:42 | March | 2026 | 2026-03-27 07:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-01393 | GDL17 | Residencial | 3.8 | Period | 2026-02-25 10:18 | February | 2026 | 2026-03-11 11:25 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 15 | 0 | 2026-04-01 | 35
202602-NM25-01394 | GDL17 | Residencial | 3.84 | Period | 2026-02-19 15:36 | February | 2026 | 2026-02-25 08:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01395 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 11:57 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 44
202602-NM25-01397 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 14:39 | February | 2026 | 2026-03-03 11:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-01399 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:06 | February | 2026 | 2026-02-19 12:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01400 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:20 | February | 2026 | 2026-02-26 12:57 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 10 | 0 | 2026-04-01 | 43
202602-NM25-01401 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:24 | February | 2026 | 2026-02-23 09:41 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01402 | GDL17 | Residencial | 8 | Period | 2026-02-17 09:31 | February | 2026 | 2026-02-20 08:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01403 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:30 | February | 2026 | 2026-02-23 09:28 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01404 | GDL17 | Residencial | 7.87 | Period | 2026-02-16 12:39 | February | 2026 | 2026-02-23 15:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01405 | GDL17 | Residencial | 15.04 | Period | 2026-02-19 10:54 | February | 2026 | 2026-02-24 14:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01406 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:04 | February | 2026 | 2026-03-19 15:13 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 24 | 0 | 2026-04-01 | 36
202602-NM25-01407 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:44 | February | 2026 | 2026-02-24 07:53 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 43
202602-NM25-01408 | GDL17 | Residencial | 9.714 | Period | 2026-02-16 13:03 | February | 2026 | 2026-02-23 09:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01409 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 12:56 | February | 2026 | 2026-02-23 09:28 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01411 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:10 | February | 2026 | 2026-02-24 09:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 43
202602-NM25-01413 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:21 | March | 2026 | 2026-03-12 15:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-01415 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 13:29 | February | 2026 | 2026-02-23 09:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01416 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:30 | March | 2026 | 2026-04-08 14:23 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 15 | 0 | 2026-04-01 | 8
202602-NM25-01417 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 10:12 | March | 2026 | 2026-03-17 10:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 21
202602-NM25-01418 | GDL17 | Residencial | 7.6 | Period | 2026-02-16 13:52 | February | 2026 | 2026-02-19 09:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01419 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 17:29 | March | 2026 | 2026-03-13 13:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 21
202602-NM25-01421 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:23 | February | 2026 | 2026-02-27 10:58 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 10 | 0 | 2026-04-01 | 42
202602-NM25-01422 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 14:02 | February | 2026 | 2026-02-19 10:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01423 | GDL17 | Residencial | 3.84 | Period | 2026-02-19 10:37 | February | 2026 | 2026-02-27 15:47 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 41
202602-NM25-01424 | GDL17 | Residencial | 11.492 | Period | 2026-02-16 14:13 | February | 2026 | 2026-02-19 10:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01426 | GDL17 | Comercial | 11.5 | Period | 2026-03-11 15:36 | March | 2026 | 2026-03-16 09:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-01427 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:14 | February | 2026 | 2026-02-23 14:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01429 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:52 | February | 2026 | 2026-03-03 14:25 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 15 | 0 | 2026-04-01 | 43
202602-NM25-01431 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:54 | February | 2026 | 2026-02-23 09:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01432 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:13 | February | 2026 | 2026-02-20 13:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 43
202602-NM25-01433 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:25 | February | 2026 | 2026-02-19 10:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01434 | GDL17 | Residencial | 11.44 | Period | 2026-02-16 15:33 | February | 2026 | 2026-02-19 10:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01436 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:34 | February | 2026 | 2026-02-19 10:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01437 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:04 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 11
202602-NM25-01438 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:43 | February | 2026 | 2026-02-20 14:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 43
202602-NM25-01439 | GDL17 | Residencial | 4.02 | Period | 2026-02-16 15:42 | February | 2026 | 2026-02-19 10:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01441 | GDL17 | Residencial | 22.8 | Period | 2026-02-16 16:43 | February | 2026 | 2026-02-20 08:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01442 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:33 | March | 2026 | 2026-03-17 13:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 20
202602-NM25-01443 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:52 | February | 2026 | 2026-03-03 13:39 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 15 | 0 | 2026-04-01 | 43
202602-NM25-01444 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 15:53 | February | 2026 | 2026-02-19 10:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01445 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:34 | March | 2026 | 2026-04-16 08:53 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 20 | 0 | 2026-04-01 | 5
202602-NM25-01446 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:01 | February | 2026 | 2026-02-20 11:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01447 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:11 | February | 2026 | 2026-02-20 09:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01448 | GDL17 | Residencial | 4.286 | Period | 2026-02-16 16:09 | February | 2026 | 2026-02-19 10:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01449 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:10 | February | 2026 | 2026-02-19 10:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 43
202602-NM25-01450 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:19 | February | 2026 | 2026-02-19 15:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01451 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:19 | February | 2026 | 2026-02-20 08:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01452 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:19 | February | 2026 | 2026-03-04 15:56 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 16 | 0 | 2026-04-01 | 43
202602-NM25-01453 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 11:03 | March | 2026 | 2026-03-11 09:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 27
202602-NM25-01454 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:58 | March | 2026 | 2026-03-11 14:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 21
202602-NM25-01455 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:27 | February | 2026 | 2026-02-20 08:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01456 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:29 | February | 2026 | 2026-02-20 08:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01457 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:38 | February | 2026 | 2026-02-20 08:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01458 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:37 | February | 2026 | 2026-02-25 08:19 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 43
202602-NM25-01460 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 08:18 | February | 2026 | 2026-02-24 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01461 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:46 | February | 2026 | 2026-02-20 15:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 43
202602-NM25-01462 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:46 | February | 2026 | 2026-02-20 08:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01463 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:55 | February | 2026 | 2026-02-20 08:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01464 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 16:54 | February | 2026 | 2026-02-23 08:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 43
202602-NM25-01465 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 17:03 | February | 2026 | 2026-02-20 08:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01466 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 17:03 | February | 2026 | 2026-02-23 10:52 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 43
202602-NM25-01468 | GDL17 | Residencial | 11.5 | Period | 2026-02-16 17:13 | February | 2026 | 2026-02-20 08:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01469 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:30 | March | 2026 | 2026-04-10 14:36 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | April |  | 18 | 15 | 2026-04-01 | 9
202602-NM25-01471 | GDL17 | Residencial | 6.8 | Period | 2026-03-19 15:54 | March | 2026 | 2026-03-24 08:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 12
202602-NM25-01472 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 09:51 | March | 2026 | 2026-03-30 10:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 7
202602-NM25-01473 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:41 | March | 2026 | 2026-03-23 13:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-01474 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:46 | March | 2026 | 2026-03-13 14:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 22
202602-NM25-01476 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:16 | March | 2026 | 2026-03-26 10:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-01477 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 11:36 | March | 2026 | 2026-03-20 08:56 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 21
202602-NM25-01478 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:38 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 12
202602-NM25-01479 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 11:29 | March | 2026 | 2026-03-23 09:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 13
202602-NM25-01483 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:06 | February | 2026 | 2026-02-25 13:17 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 41
202602-NM25-01484 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 09:29 | March | 2026 | 2026-03-09 13:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 26
202602-NM25-01485 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 11:31 | February | 2026 | 2026-02-24 14:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01486 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:12 | February | 2026 | 2026-02-26 08:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-01487 | GDL17 | Residencial | 7.68 | Period | 2026-02-19 15:56 | February | 2026 | 2026-02-25 09:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01488 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:16 | February | 2026 | 2026-02-20 09:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01489 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 14:16 | February | 2026 | 2026-03-03 11:17 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 40
202602-NM25-01490 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:26 | February | 2026 | 2026-02-20 08:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01491 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:27 | February | 2026 | 2026-02-20 08:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01492 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:36 | February | 2026 | 2026-02-23 09:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 43
202602-NM25-01493 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:37 | February | 2026 | 2026-02-26 15:34 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 9 | 0 | 2026-04-01 | 43
202602-NM25-01494 | GDL17 | Residencial | 4.608 | Period | 2026-03-23 18:20 | March | 2026 | 2026-04-08 15:06 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 16 | 0 | 2026-04-01 | 8
202602-NM25-01496 | GDL17 | Residencial | 9.6 | Period | 2026-03-19 13:28 | March | 2026 | 2026-03-20 09:34 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 12
202602-NM25-01497 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:55 | March | 2026 | 2026-03-13 15:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 21
202602-NM25-01498 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:52 | February | 2026 | 2026-02-20 08:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01499 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:50 | February | 2026 | 2026-02-25 08:18 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 43
202602-NM25-01500 | GDL17 | Residencial | 4.992 | Period | 2026-02-19 07:41 | February | 2026 | 2026-03-12 15:05 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 21 | 0 | 2026-04-01 | 41
202602-NM25-01501 | GDL17 | Comercial | 7.6 | Period | 2026-02-17 09:12 | February | 2026 | 2026-02-20 08:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01502 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 08:59 | February | 2026 | 2026-03-23 12:55 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | March |  | 35 | 0 | 2026-04-01 | 43
202602-NM25-01503 | GDL17 | Residencial | 8 | Period | 2026-03-20 09:29 | March | 2026 | 2026-03-23 13:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-01504 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:02 | February | 2026 | 2026-02-20 08:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01505 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:58 | February | 2026 | 2026-03-02 10:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 35
202602-NM25-01506 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:13 | February | 2026 | 2026-02-20 08:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01508 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:03 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 34
202602-NM25-01510 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:23 | February | 2026 | 2026-02-20 08:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01511 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:05 | February | 2026 | 2026-03-03 13:54 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 36
202602-NM25-01513 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:33 | February | 2026 | 2026-02-20 08:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01514 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:37 | February | 2026 | 2026-02-24 15:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 43
202602-NM25-01515 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 09:45 | February | 2026 | 2026-02-24 15:06 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 43
202602-NM25-01516 | GDL17 | Residencial | 6 | Period | 2026-03-19 09:44 | March | 2026 | 2026-03-23 08:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 13
202602-NM25-01517 | GDL17 | Comercial | 11.5 | Period | 2026-02-23 12:18 | February | 2026 | 2026-02-26 14:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-01518 | GDL17 | Residencial | 3.84 | Period | 2026-02-23 09:47 | February | 2026 | 2026-03-05 12:49 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 37
202602-NM25-01520 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:17 | February | 2026 | 2026-03-06 13:27 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 36
202602-NM25-01521 | GDL17 | Residencial | 5.76 | Period | 2026-02-20 14:49 | February | 2026 | 2026-02-26 08:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-01522 | GDL17 | Residencial | 12.81 | Period | 2026-02-17 10:04 | February | 2026 | 2026-02-20 10:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01524 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 13:34 | March | 2026 | 2026-03-26 10:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 2 | 4 | 2 | 2026-04-01 | 11
202602-NM25-01526 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 07:36 | March | 2026 | 2026-03-20 08:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 15
202602-NM25-01527 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:54 | February | 2026 | 2026-03-12 15:13 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 32
202602-NM25-01528 | GDL17 | Residencial | 7.6 | Period | 2026-03-05 15:27 | March | 2026 | 2026-03-06 14:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 26
202602-NM25-01529 | GDL17 | Residencial | 23 | Period | 2026-02-20 14:43 | February | 2026 | 2026-02-26 08:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-01530 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 10:30 | February | 2026 | 2026-02-20 08:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01531 | GDL17 | Residencial | 8 | Period | 2026-03-20 09:35 | March | 2026 | 2026-03-24 10:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-01532 | GDL17 | Residencial | 5.76 | Period | 2026-02-17 10:29 | February | 2026 | 2026-02-20 08:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01533 | GDL17 | Residencial | 17.5 | Period | 2026-03-13 11:52 | March | 2026 | 2026-03-16 14:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 19
202602-NM25-01535 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 10:38 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 43
202602-NM25-01536 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 16:47 | February | 2026 | 2026-03-10 16:16 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 14 | 0 | 2026-04-01 | 35
202602-NM25-01541 | GDL17 | Residencial | 15.2 | Period | 2026-02-17 11:33 | February | 2026 | 2026-02-20 08:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01542 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:53 | February | 2026 | 2026-02-25 13:01 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 42
202602-NM25-01544 | GDL17 | Residencial | 7.6 | Period | 2026-02-17 11:31 | February | 2026 | 2026-02-20 08:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 43
202602-NM25-01549 | GDL17 | Residencial | 3.84 | Period | 2026-02-19 12:50 | February | 2026 | 2026-02-25 07:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01550 | GDL17 | Residencial | 3.84 | Period | 2026-02-23 13:27 | February | 2026 | 2026-03-02 15:49 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 36
202602-NM25-01552 | GDL17 | Residencial | 5.76 | Period | 2026-03-06 09:14 | March | 2026 | 2026-04-22 15:02 | 47 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 47 | 0 | 2026-04-01 | 26
202602-NM25-01553 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 14:21 | March | 2026 | 2026-03-13 08:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 20
202602-NM25-01554 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:31 | February | 2026 | 2026-03-12 13:03 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 14 | 0 | 2026-04-01 | 34
202602-NM25-01557 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:16 | February | 2026 | 2026-02-26 11:17 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 41
202602-NM25-01558 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 15:44 | February | 2026 | 2026-03-12 10:17 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 15 | 0 | 2026-04-01 | 34
202602-NM25-01560 | GDL17 | Residencial | 10.112 | Period | 2026-02-17 12:23 | February | 2026 | 2026-02-23 09:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01564 | GDL17 | Residencial | 8 | Period | 2026-03-20 09:40 | March | 2026 | 2026-03-26 09:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 12
202602-NM25-01567 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 12:48 | February | 2026 | 2026-02-23 09:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01569 | GDL17 | Residencial | 8 | Period | 2026-02-17 15:45 | February | 2026 | 2026-02-25 14:14 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 42
202602-NM25-01574 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:32 | February | 2026 | 2026-03-03 13:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-01575 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 15:46 | February | 2026 | 2026-02-25 13:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01576 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 14:23 | February | 2026 | 2026-02-27 09:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-01577 | GDL17 | Residencial | 8 | Period | 2026-02-17 15:08 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 42
202602-NM25-01580 | GDL17 | Residencial | 23 | Period | 2026-02-19 13:34 | February | 2026 | 2026-02-27 12:46 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 8 | 0 | 2026-04-01 | 40
202602-NM25-01581 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 08:12 | March | 2026 | 2026-03-13 10:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 22
202602-NM25-01582 | GDL17 | Residencial | 12 | Period | 2026-02-20 15:37 | February | 2026 | 2026-02-27 09:28 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 39
202602-NM25-01584 | GDL17 | Residencial | 6.79 | Period | 2026-02-17 13:29 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | No | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 42
202602-NM25-01585 | GDL17 | Residencial | 8 | Period | 2026-03-20 10:06 | March | 2026 | 2026-04-07 15:02 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 18 | 0 | 2026-04-01 | 12
202602-NM25-01586 | GDL17 | Residencial | 9.206 | Period | 2026-02-17 13:32 | February | 2026 | 2026-02-23 09:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01587 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:11 | March | 2026 | 2026-03-16 14:55 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 29
202602-NM25-01590 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 08:01 | February | 2026 | 2026-02-25 08:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01591 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 13:42 | February | 2026 | 2026-02-24 10:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 42
202602-NM25-01595 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 13:52 | March | 2026 | 2026-03-16 16:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 19
202602-NM25-01596 | GDL17 | Residencial | 7.072 | Period | 2026-02-17 13:51 | February | 2026 | 2026-02-23 09:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01598 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 15:52 | March | 2026 | 2026-03-31 16:03 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 14 | 0 | 2026-04-01 | 14
202602-NM25-01604 | GDL17 | Residencial | 7.87 | Period | 2026-02-17 13:59 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 42
202602-NM25-01607 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:16 | February | 2026 | 2026-02-23 13:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01611 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:12 | February | 2026 | 2026-02-27 08:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 40
202602-NM25-01612 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:36 | February | 2026 | 2026-02-23 14:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01613 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 13:38 | March | 2026 | 2026-03-05 16:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 27
202602-NM25-01614 | GDL17 | Residencial | 8.562 | Period | 2026-02-17 14:34 | February | 2026 | 2026-02-23 09:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01615 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:37 | February | 2026 | 2026-02-25 10:39 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 42
202602-NM25-01616 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:26 | February | 2026 | 2026-02-23 07:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01617 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:33 | February | 2026 | 2026-02-23 09:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01618 | GDL17 | Residencial | 11.4 | Period | 2026-02-23 15:05 | February | 2026 | 2026-02-27 10:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-01619 | GDL17 | Residencial | 15 | Period | 2026-02-17 17:38 | February | 2026 | 2026-02-23 09:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01621 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:32 | February | 2026 | 2026-02-23 09:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01622 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:29 | February | 2026 | 2026-02-23 09:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01623 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:03 | February | 2026 | 2026-02-24 08:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 41
202602-NM25-01624 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:49 | February | 2026 | 2026-02-23 09:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01625 | GDL17 | Residencial | 6.296 | Period | 2026-02-17 14:45 | February | 2026 | 2026-02-23 09:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01626 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 14:56 | February | 2026 | 2026-02-24 14:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 42
202602-NM25-01628 | GDL17 | Residencial | 3.456 | Period | 2026-02-19 16:08 | February | 2026 | 2026-02-27 09:37 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 8 | 0 | 2026-04-01 | 40
202602-NM25-01629 | GDL17 | Residencial | 12 | Period | 2026-02-19 12:33 | February | 2026 | 2026-02-25 07:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01630 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:43 | February | 2026 | 2026-02-23 10:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01631 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:45 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 2
202602-NM25-01632 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 01:43 | February | 2026 | 2026-02-25 08:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01634 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:15 | February | 2026 | 2026-03-05 12:41 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 16 | 0 | 2026-04-01 | 42
202602-NM25-01635 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 17:54 | March | 2026 | 2026-03-23 13:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 15
202602-NM25-01636 | GDL17 | Residencial | 15.28 | Period | 2026-02-17 15:17 | February | 2026 | 2026-02-23 09:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01637 | GDL17 | Comercial | 6.872 | Period | 2026-02-17 15:20 | February | 2026 | 2026-02-23 09:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01639 | GDL17 | Residencial | 9.136 | Period | 2026-02-17 15:30 | February | 2026 | 2026-02-23 09:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01640 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:37 | February | 2026 | 2026-02-26 07:50 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 42
202602-NM25-01641 | GDL17 | Residencial | 11.215 | Period | 2026-02-17 15:54 | February | 2026 | 2026-02-23 09:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01642 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:45 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 42
202602-NM25-01644 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:45 | February | 2026 | 2026-02-23 09:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01645 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:42 | February | 2026 | 2026-02-23 12:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01646 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:52 | February | 2026 | 2026-02-23 15:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01647 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 15:53 | February | 2026 | 2026-02-23 13:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01648 | GDL17 | Residencial | 11.4 | Period | 2026-02-23 10:19 | February | 2026 | 2026-02-26 08:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 37
202602-NM25-01649 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:00 | February | 2026 | 2026-02-23 12:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01650 | GDL17 | Residencial | 7.6 | Period | 2026-02-17 16:17 | February | 2026 | 2026-02-23 09:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01651 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:10 | February | 2026 | 2026-02-23 09:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01652 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:17 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 42
202602-NM25-01653 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:24 | February | 2026 | 2026-03-18 13:52 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 29 | 0 | 2026-04-01 | 42
202602-NM25-01655 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:33 | February | 2026 | 2026-02-25 13:47 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 42
202602-NM25-01656 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:34 | February | 2026 | 2026-02-23 09:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01657 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 11:29 | March | 2026 | 2026-03-17 13:22 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 26
202602-NM25-01658 | GDL17 | Residencial | 11.5 | Period | 2026-02-17 16:38 | February | 2026 | 2026-03-12 11:07 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 23 | 0 | 2026-04-01 | 42
202602-NM25-01660 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:22 | March | 2026 | 2026-03-25 08:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 14
202602-NM25-01661 | GDL17 | Residencial | 7 | Period | 2026-02-24 17:59 | February | 2026 | 2026-02-27 09:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-01662 | GDL17 | Residencial | 5.6 | Period | 2026-03-13 13:35 | March | 2026 | 2026-04-10 14:28 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | April |  | 28 | 27 | 2026-04-01 | 18
202602-NM25-01663 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 15:37 | March | 2026 | 2026-04-14 15:14 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 18 | 0 | 2026-04-01 | 4
202602-NM25-01664 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 08:56 | March | 2026 | 2026-03-24 12:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 9
202602-NM25-01665 | GDL17 | Residencial | 18 | Period | 2026-02-17 22:49 | February | 2026 | 2026-02-24 13:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 7 | 0 | 2026-04-01 | 42
202602-NM25-01666 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 11:23 | March | 2026 | 2026-03-16 09:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 21
202602-NM25-01669 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:56 | February | 2026 | 2026-02-24 14:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01670 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 09:16 | February | 2026 | 2026-02-27 12:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-01671 | GDL17 | Residencial | 4.224 | Period | 2026-02-20 08:45 | February | 2026 | 2026-02-25 08:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01672 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:00 | March | 2026 | 2026-03-09 15:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 26
202602-NM25-01673 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:09 | February | 2026 | 2026-02-24 12:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01674 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:39 | February | 2026 | 2026-02-23 09:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01675 | GDL17 | Comercial | 15.2 | Period | 2026-02-18 08:47 | February | 2026 | 2026-02-24 16:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 42
202602-NM25-01676 | GDL17 | Residencial | 16 | Period | 2026-03-09 11:15 | March | 2026 | 2026-03-11 12:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 23
202602-NM25-01677 | GDL17 | Residencial | 7.38 | Period | 2026-02-18 08:43 | February | 2026 | 2026-02-23 09:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01678 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:40 | February | 2026 | 2026-03-03 13:01 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 41
202602-NM25-01679 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 08:51 | February | 2026 | 2026-02-23 09:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01680 | GDL17 | Residencial | 7.736 | Period | 2026-02-18 08:56 | February | 2026 | 2026-02-23 09:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01681 | GDL17 | Residencial | 6.144 | Period | 2026-03-18 17:45 | March | 2026 | 2026-03-19 11:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 0 | 0 | 2026-04-01 | 13
202602-NM25-01683 | GDL17 | Residencial | 10 | Period | 2026-02-18 09:20 | February | 2026 | 2026-02-23 09:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01684 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 09:23 | February | 2026 | 2026-02-25 11:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 42
202602-NM25-01685 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:22 | March | 2026 | 2026-03-18 10:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 18
202602-NM25-01686 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 13:26 | February | 2026 | 2026-03-03 12:45 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 40
202602-NM25-01690 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:52 | March | 2026 | 2026-03-20 08:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 15
202602-NM25-01691 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 10:08 | February | 2026 | 2026-02-25 11:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 7 | 0 | 2026-04-01 | 42
202602-NM25-01692 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:51 | February | 2026 | 2026-02-24 07:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01695 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:34 | February | 2026 | 2026-03-03 13:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-01697 | GDL17 | Residencial | 12 | Period | 2026-03-12 10:17 | March | 2026 | 2026-04-07 14:41 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 26 | 0 | 2026-04-01 | 20
202602-NM25-01699 | GDL17 | Residencial | 13.036 | Period | 2026-02-18 11:49 | February | 2026 | 2026-02-23 14:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 42
202602-NM25-01700 | GDL17 | Residencial | 12 | Period | 2026-03-26 11:50 | March | 2026 | 2026-03-31 14:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-01701 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 13:34 | March | 2026 | 2026-03-11 14:05 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 6 | 2 | 2026-04-01 | 28
202602-NM25-01702 | GDL17 | Residencial | 8.35 | Period | 2026-03-13 13:33 | March | 2026 | 2026-03-16 16:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 18
202602-NM25-01703 | GDL17 | Residencial | 11.4 | Period | 2026-03-08 22:16 | March | 2026 | 2026-03-09 14:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 0 | 0 | 2026-04-01 | 23
202602-NM25-01704 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 12:04 | March | 2026 | 2026-03-23 15:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-01705 | GDL17 | Residencial | 23 | Period | 2026-02-19 07:15 | February | 2026 | 2026-02-25 11:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01706 | GDL17 | Residencial | 16.5 | Period | 2026-02-19 14:20 | February | 2026 | 2026-02-24 14:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01708 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 08:52 | February | 2026 | 2026-02-25 08:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01709 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:22 | February | 2026 | 2026-02-23 14:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01710 | GDL17 | Residencial | 3.8 | Period | 2026-02-19 12:52 | February | 2026 | 2026-02-25 07:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01711 | GDL17 | Residencial | 9.136 | Period | 2026-02-18 12:29 | February | 2026 | 2026-02-23 14:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01712 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:35 | February | 2026 | 2026-03-05 10:12 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 15 | 0 | 2026-04-01 | 41
202602-NM25-01713 | GDL17 | Residencial | 5.836 | Period | 2026-02-18 12:39 | February | 2026 | 2026-02-24 13:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01715 | GDL17 | Residencial | 8.598 | Period | 2026-02-18 12:45 | February | 2026 | 2026-02-24 08:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01716 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 16:14 | February | 2026 | 2026-03-02 09:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-01717 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 12:50 | February | 2026 | 2026-02-24 15:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01718 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 08:58 | February | 2026 | 2026-02-27 09:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-01719 | GDL17 | Residencial | 11.44 | Period | 2026-02-18 12:57 | February | 2026 | 2026-02-23 14:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01720 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 13:07 | February | 2026 | 2026-02-23 14:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01721 | GDL17 | Residencial | 3.84 | Period | 2026-02-20 07:44 | February | 2026 | 2026-03-04 13:39 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 13 | 0 | 2026-04-01 | 40
202602-NM25-01722 | GDL17 | Comercial | 7.6 | Period | 2026-02-20 08:12 | February | 2026 | 2026-03-03 12:50 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 40
202602-NM25-01724 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:09 | February | 2026 | 2026-03-04 15:58 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 35
202602-NM25-01725 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:34 | March | 2026 | 2026-03-16 12:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 20
202602-NM25-01726 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 07:18 | March | 2026 | 2026-03-06 08:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-01727 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:04 | March | 2026 | 2026-03-23 10:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-01728 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:44 | February | 2026 | 2026-02-25 14:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01730 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:41 | March | 2026 | 2026-03-16 11:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 21
202602-NM25-01733 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:09 | February | 2026 | 2026-02-26 14:38 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 8 | 0 | 2026-04-01 | 41
202602-NM25-01734 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:39 | March | 2026 | 2026-03-30 12:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 8
202602-NM25-01738 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 14:29 | February | 2026 | 2026-02-23 15:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01739 | GDL17 | Residencial | 8 | Period | 2026-02-19 21:00 | February | 2026 | 2026-02-25 08:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01740 | GDL17 | Residencial | 5.294 | Period | 2026-02-20 14:23 | February | 2026 | 2026-02-25 15:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-01742 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 14:44 | February | 2026 | 2026-02-25 08:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01744 | GDL17 | Residencial | 8.42 | Period | 2026-02-18 14:47 | February | 2026 | 2026-02-23 15:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01745 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 14:30 | March | 2026 | 2026-03-23 15:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-01746 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:54 | February | 2026 | 2026-02-24 13:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01747 | GDL17 | Comercial | 22.8 | Period | 2026-02-18 16:50 | February | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 41
202602-NM25-01748 | GDL17 | Residencial | 7.6 | Period | 2026-02-27 14:33 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 32
202602-NM25-01749 | GDL17 | Residencial | 4.608 | Period | 2026-02-18 15:17 | February | 2026 | 2026-02-24 07:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01751 | GDL17 | Residencial | 5.076 | Period | 2026-02-18 15:27 | February | 2026 | 2026-02-24 13:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01752 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:35 | February | 2026 | 2026-02-24 12:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01753 | GDL17 | Residencial | 5.222 | Period | 2026-02-18 15:35 | February | 2026 | 2026-02-24 07:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01754 | GDL17 | Residencial | 9.904 | Period | 2026-02-18 15:46 | February | 2026 | 2026-02-24 07:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01756 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 15:53 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 41
202602-NM25-01757 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:18 | February | 2026 | 2026-02-24 07:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01758 | GDL17 | Residencial | 6.612 | Period | 2026-02-18 16:01 | February | 2026 | 2026-02-24 07:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01759 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:32 | March | 2026 | 2026-03-10 10:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-01760 | GDL17 | Residencial | 10 | Period | 2026-02-20 19:45 | February | 2026 | 2026-02-26 08:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-01762 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 10:26 | March | 2026 | 2026-03-10 09:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 5 | 1 | 2026-04-01 | 28
202602-NM25-01763 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 16:46 | February | 2026 | 2026-02-24 07:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01765 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 17:00 | February | 2026 | 2026-02-24 07:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01766 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 17:09 | February | 2026 | 2026-02-24 07:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01769 | GDL17 | Residencial | 7.6 | Period | 2026-03-22 09:17 | March | 2026 | 2026-03-31 10:19 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 10
202602-NM25-01773 | GDL17 | Residencial | 11.112 | Period | 2026-02-18 18:26 | February | 2026 | 2026-02-24 15:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01775 | GDL17 | Residencial | 3.8 | Period | 2026-03-12 11:16 | March | 2026 | 2026-03-20 14:28 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 20
202602-NM25-01777 | GDL17 | Residencial | 14.274 | Period | 2026-02-18 18:47 | February | 2026 | 2026-02-24 07:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01778 | GDL17 | Gubernamental | 11.5 | Period | 2026-02-18 19:01 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 41
202602-NM25-01780 | GDL17 | Residencial | 11.5 | Period | 2026-02-18 18:57 | February | 2026 | 2026-02-24 15:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01784 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 15:05 | March | 2026 | 2026-04-08 08:39 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 0
202602-NM25-01786 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 13:36 | March | 2026 | 2026-03-16 16:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202602-NM25-01788 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 13:18 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 11
202602-NM25-01790 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 17:30 | March | 2026 | 2026-04-01 12:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 4
202602-NM25-01793 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 07:13 | March | 2026 | 2026-03-09 15:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 26
202602-NM25-01794 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 13:24 | February | 2026 | 2026-03-06 10:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 2 | 5 | 5 | 2026-04-01 | 35
202602-NM25-01796 | GDL17 | Residencial | 10 | Period | 2026-02-25 10:42 | February | 2026 | 2026-02-27 14:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-01804 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 07:39 | February | 2026 | 2026-02-24 08:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01805 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 08:02 | February | 2026 | 2026-02-25 09:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01807 | GDL17 | Residencial | 7.462 | Period | 2026-02-19 08:31 | February | 2026 | 2026-02-24 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01808 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 08:36 | February | 2026 | 2026-02-24 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01809 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 07:48 | February | 2026 | 2026-03-02 09:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 37
202602-NM25-01810 | GDL17 | Residencial | 5.95 | Period | 2026-02-19 08:42 | February | 2026 | 2026-02-25 09:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01811 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:30 | February | 2026 | 2026-02-25 10:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01812 | GDL17 | Residencial | 9.662 | Period | 2026-02-19 08:57 | February | 2026 | 2026-02-25 09:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01813 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 08:56 | February | 2026 | 2026-02-25 09:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01814 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:39 | February | 2026 | 2026-02-26 08:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-01815 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 11:51 | March | 2026 | 2026-03-17 16:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 21
202602-NM25-01816 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 09:03 | February | 2026 | 2026-02-24 14:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01819 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 09:18 | February | 2026 | 2026-02-24 10:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01820 | GDL17 | Residencial | 7.68 | Period | 2026-02-23 14:27 | February | 2026 | 2026-03-04 16:23 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 36
202602-NM25-01821 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 09:19 | February | 2026 | 2026-03-03 11:26 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 41
202602-NM25-01822 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 08:49 | February | 2026 | 2026-03-31 08:05 | 39 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | March |  | 39 | 0 | 2026-04-01 | 40
202602-NM25-01823 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:03 | March | 2026 | 2026-03-25 11:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 12
202602-NM25-01826 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 09:47 | February | 2026 | 2026-02-26 13:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 8 | 0 | 2026-04-01 | 41
202602-NM25-01830 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:14 | February | 2026 | 2026-02-24 08:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 41
202602-NM25-01832 | GDL17 | Residencial | 12.976 | Period | 2026-02-19 10:25 | February | 2026 | 2026-02-24 14:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01833 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:17 | February | 2026 | 2026-02-24 15:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01834 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:16 | March | 2026 | 2026-03-18 14:44 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 15 | 0 | 2026-04-01 | 28
202602-NM25-01835 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:41 | February | 2026 | 2026-02-25 09:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01836 | GDL17 | Residencial | 8 | Period | 2026-02-19 23:38 | February | 2026 | 2026-02-25 08:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01839 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:33 | March | 2026 | 2026-03-20 16:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 14
202602-NM25-01840 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:24 | March | 2026 | 2026-03-06 15:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 28
202602-NM25-01841 | GDL17 | Residencial | 7.68 | Period | 2026-03-17 14:58 | March | 2026 | 2026-03-20 11:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 14
202602-NM25-01842 | GDL17 | Residencial | 4.992 | Period | 2026-02-23 13:40 | February | 2026 | 2026-02-26 08:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-01843 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:41 | February | 2026 | 2026-03-02 10:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-01844 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:44 | February | 2026 | 2026-02-25 09:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01845 | GDL17 | Residencial | 6 | Period | 2026-02-23 14:41 | February | 2026 | 2026-02-26 08:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-01846 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:04 | February | 2026 | 2026-02-26 08:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-01847 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 10:54 | February | 2026 | 2026-02-24 14:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01851 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 13:40 | March | 2026 | 2026-03-16 14:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 18
202602-NM25-01852 | GDL17 | Residencial | 19.5 | Period | 2026-02-19 11:06 | February | 2026 | 2026-02-24 14:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 41
202602-NM25-01854 | GDL17 | Residencial | 7.6 | Period | 2026-02-19 11:17 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 41
202602-NM25-01855 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 13:07 | March | 2026 | 2026-03-11 10:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 27
202602-NM25-01856 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:08 | February | 2026 | 2026-02-25 15:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01857 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 11:22 | February | 2026 | 2026-02-25 10:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 41
202602-NM25-01858 | GDL17 | Residencial | 16.5 | Period | 2026-02-20 12:35 | February | 2026 | 2026-02-25 12:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-01859 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:09 | March | 2026 | 2026-03-13 16:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 20
202602-NM25-01862 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 08:28 | March | 2026 | 2026-03-11 16:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 28
202602-NM25-01865 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 14:01 | February | 2026 | 2026-03-02 12:41 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 40
202602-NM25-01867 | GDL17 | Residencial | 8 | Period | 2026-02-19 23:17 | February | 2026 | 2026-02-25 08:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01868 | GDL17 | Residencial | 11.362 | Period | 2026-02-19 16:44 | February | 2026 | 2026-02-25 08:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01869 | GDL17 | Residencial | 12 | Period | 2026-02-19 16:07 | February | 2026 | 2026-02-25 08:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01870 | GDL17 | Residencial | 8 | Period | 2026-03-18 23:01 | March | 2026 | 2026-03-20 08:27 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 13
202602-NM25-01871 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:46 | March | 2026 | 2026-03-05 09:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 28
202602-NM25-01872 | GDL17 | Residencial | 8 | Period | 2026-03-20 11:13 | March | 2026 | 2026-03-25 10:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 12
202602-NM25-01873 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:12 | March | 2026 | 2026-03-30 10:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 7
202602-NM25-01874 | GDL17 | Residencial | 8 | Period | 2026-02-20 09:55 | February | 2026 | 2026-03-12 08:48 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 20 | 0 | 2026-04-01 | 40
202602-NM25-01875 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:29 | March | 2026 | 2026-04-09 07:41 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 22 | 0 | 2026-04-01 | 14
202602-NM25-01876 | GDL17 | Residencial | 7.6 | Period | 2026-02-19 13:59 | February | 2026 | 2026-02-24 14:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01877 | GDL17 | Residencial | 16 | Period | 2026-02-25 10:01 | February | 2026 | 2026-03-12 09:56 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 15 | 0 | 2026-04-01 | 35
202602-NM25-01878 | GDL17 | Residencial | 4.392 | Period | 2026-02-25 10:23 | February | 2026 | 2026-02-27 11:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-01880 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 07:50 | February | 2026 | 2026-02-26 14:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-01881 | GDL17 | Residencial | 8 | Period | 2026-02-19 21:14 | February | 2026 | 2026-03-04 11:07 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 40
202602-NM25-01883 | GDL17 | Residencial | 6.902 | Period | 2026-02-19 14:05 | February | 2026 | 2026-02-24 14:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01887 | GDL17 | Residencial | 12 | Period | 2026-02-23 20:04 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 36
202602-NM25-01888 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:24 | February | 2026 | 2026-02-25 13:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01889 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 12:56 | March | 2026 | 2026-04-07 14:08 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 13 | 0 | 2026-04-01 | 6
202602-NM25-01890 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 14:09 | March | 2026 | 2026-03-31 14:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 5
202602-NM25-01891 | GDL17 | Residencial | 2.688 | Period | 2026-02-19 15:14 | February | 2026 | 2026-02-25 08:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01892 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:29 | March | 2026 | 2026-03-25 16:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 8
202602-NM25-01894 | GDL17 | Residencial | 4.392 | Period | 2026-02-19 15:22 | February | 2026 | 2026-02-25 13:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01895 | GDL17 | Residencial | 6.67 | Period | 2026-02-19 15:29 | February | 2026 | 2026-02-25 08:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01896 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:42 | February | 2026 | 2026-02-27 14:30 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 8 | 0 | 2026-04-01 | 40
202602-NM25-01897 | GDL17 | Residencial | 7.6 | Period | 2026-02-23 07:53 | February | 2026 | 2026-03-02 11:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 37
202602-NM25-01898 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:33 | March | 2026 | 2026-04-02 13:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 1
202602-NM25-01899 | GDL17 | Residencial | 7.68 | Period | 2026-03-03 11:58 | March | 2026 | 2026-03-11 13:00 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 29
202602-NM25-01900 | GDL17 | Residencial | 7.68 | Period | 2026-02-27 10:02 | February | 2026 | 2026-03-11 09:29 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 33
202602-NM25-01904 | GDL17 | Residencial | 7.6 | Period | 2026-02-19 16:52 | February | 2026 | 2026-02-25 08:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01905 | GDL17 | Residencial | 8 | Period | 2026-02-24 14:20 | February | 2026 | 2026-02-27 09:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-01906 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 10:56 | March | 2026 | 2026-03-25 15:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 9
202602-NM25-01907 | GDL17 | Residencial | 9.136 | Period | 2026-02-20 08:37 | February | 2026 | 2026-02-25 08:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01910 | GDL17 | Residencial | 11.5 | Period | 2026-02-19 16:48 | February | 2026 | 2026-02-25 13:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01912 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:37 | March | 2026 | 2026-03-26 08:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 12
202602-NM25-01914 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:14 | March | 2026 | 2026-03-27 14:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 11
202602-NM25-01915 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 11:58 | February | 2026 | 2026-02-27 08:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-01916 | GDL17 | Residencial | 6.142 | Period | 2026-02-19 17:31 | February | 2026 | 2026-02-25 08:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01918 | GDL17 | Residencial | 3.66 | Period | 2026-02-19 17:43 | February | 2026 | 2026-02-25 08:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01919 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:33 | March | 2026 | 2026-03-23 14:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-01920 | GDL17 | Residencial | 3.66 | Period | 2026-02-25 17:42 | February | 2026 | 2026-03-02 10:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-01922 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:31 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 11
202602-NM25-01923 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:33 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 11
202602-NM25-01925 | GDL17 | Residencial | 8 | Period | 2026-02-27 06:52 | February | 2026 | 2026-03-03 16:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-01926 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 12:06 | March | 2026 | 2026-03-24 15:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 11
202602-NM25-01928 | GDL17 | Residencial | 15.2 | Period | 2026-02-20 07:53 | February | 2026 | 2026-02-25 08:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01929 | GDL17 | Residencial | 6.144 | Period | 2026-03-10 10:07 | March | 2026 | 2026-03-12 16:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-01930 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:01 | March | 2026 | 2026-03-09 14:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 28
202602-NM25-01931 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 08:07 | February | 2026 | 2026-02-25 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01932 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 15:00 | March | 2026 | 2026-03-09 09:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 26
202602-NM25-01933 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 08:23 | February | 2026 | 2026-02-25 08:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01934 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:28 | February | 2026 | 2026-03-02 10:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-01935 | GDL17 | Residencial | 4.992 | Period | 2026-02-26 11:38 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 34
202602-NM25-01936 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 08:35 | February | 2026 | 2026-02-25 11:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01937 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:09 | March | 2026 | 2026-03-19 16:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 14
202602-NM25-01938 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 08:49 | February | 2026 | 2026-03-02 09:46 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 40
202602-NM25-01939 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:55 | February | 2026 | 2026-03-04 16:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 35
202602-NM25-01940 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 14:27 | March | 2026 | 2026-03-23 12:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 13
202602-NM25-01941 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 14:57 | February | 2026 | 2026-03-05 07:57 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 34
202602-NM25-01942 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:01 | February | 2026 | 2026-03-06 08:30 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 40
202602-NM25-01943 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:39 | February | 2026 | 2026-03-02 09:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-01944 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:14 | February | 2026 | 2026-02-26 13:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 40
202602-NM25-01945 | GDL17 | Residencial | 3.84 | Period | 2026-03-04 10:19 | March | 2026 | 2026-03-06 10:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 28
202602-NM25-01946 | GDL17 | Residencial | 3.8 | Period | 2026-02-24 15:30 | February | 2026 | 2026-03-03 11:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 4 | 3 | 2026-04-01 | 35
202602-NM25-01947 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:22 | February | 2026 | 2026-03-02 08:30 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 40
202602-NM25-01949 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:32 | February | 2026 | 2026-03-03 15:14 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 40
202602-NM25-01950 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:29 | February | 2026 | 2026-02-27 11:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 8 | 0 | 2026-04-01 | 40
202602-NM25-01951 | GDL17 | Residencial | 23 | Period | 2026-02-20 09:44 | February | 2026 | 2026-02-25 16:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01952 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 09:47 | February | 2026 | 2026-02-25 10:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01953 | GDL17 | Residencial | 8 | Period | 2026-02-20 12:39 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 39
202602-NM25-01955 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:18 | March | 2026 | 2026-03-26 10:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-01956 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:42 | February | 2026 | 2026-03-02 07:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 35
202602-NM25-01958 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:02 | February | 2026 | 2026-02-25 09:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01959 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:10 | February | 2026 | 2026-02-25 08:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01960 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:07 | February | 2026 | 2026-02-25 08:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01961 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:44 | February | 2026 | 2026-03-02 13:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-01962 | GDL17 | Residencial | 2.989 | Period | 2026-03-07 13:59 | March | 2026 | 2026-03-09 14:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 24
202602-NM25-01963 | GDL17 | Residencial | 3.84 | Period | 2026-02-26 10:23 | February | 2026 | 2026-03-05 11:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 34
202602-NM25-01964 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:33 | February | 2026 | 2026-02-25 08:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01965 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:17 | February | 2026 | 2026-03-02 11:10 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-01966 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:20 | February | 2026 | 2026-02-26 11:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 7 | 0 | 2026-04-01 | 40
202602-NM25-01967 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:22 | February | 2026 | 2026-02-25 12:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01968 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:08 | February | 2026 | 2026-02-25 09:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01969 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:33 | February | 2026 | 2026-02-25 08:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 40
202602-NM25-01970 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 10:16 | February | 2026 | 2026-03-02 10:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 35
202602-NM25-01972 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:13 | March | 2026 | 2026-03-23 13:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 14
202602-NM25-01973 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 16:39 | March | 2026 | 2026-03-11 10:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 25
202602-NM25-01974 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:33 | February | 2026 | 2026-02-27 07:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 7 | 0 | 2026-04-01 | 40
202602-NM25-01975 | GDL17 | Residencial | 5.25 | Period | 2026-03-10 10:31 | March | 2026 | 2026-03-16 13:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 22
202602-NM25-01976 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:48 | February | 2026 | 2026-03-03 14:36 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 12 | 0 | 2026-04-01 | 40
202602-NM25-01978 | GDL17 | Residencial | 3.245 | Period | 2026-02-23 15:06 | February | 2026 | 2026-02-26 08:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-01979 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:52 | February | 2026 | 2026-03-10 12:35 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 18 | 0 | 2026-04-01 | 39
202602-NM25-01980 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 10:52 | February | 2026 | 2026-02-26 07:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01981 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:00 | February | 2026 | 2026-03-02 10:15 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 40
202602-NM25-01982 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:03 | February | 2026 | 2026-03-02 08:53 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 40
202602-NM25-01983 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:05 | February | 2026 | 2026-02-25 13:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01985 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:08 | February | 2026 | 2026-02-26 10:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01986 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:31 | March | 2026 | 2026-03-05 09:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202602-NM25-01987 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:15 | February | 2026 | 2026-03-03 14:06 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 40
202602-NM25-01988 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 10:55 | March | 2026 | 2026-04-16 14:36 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 16 | 0 | 2026-04-01 | 1
202602-NM25-01989 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:51 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 40
202602-NM25-01990 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:35 | February | 2026 | 2026-02-26 15:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 40
202602-NM25-01991 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:27 | March | 2026 | 2026-03-24 07:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-01992 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:39 | February | 2026 | 2026-02-25 09:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 40
202602-NM25-01994 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 17:10 | February | 2026 | 2026-02-26 08:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-01995 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:46 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 40
202602-NM25-01996 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 11:57 | February | 2026 | 2026-02-25 09:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 40
202602-NM25-01998 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:07 | February | 2026 | 2026-03-06 08:14 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 39
202602-NM25-01999 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:02 | February | 2026 | 2026-02-25 09:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 39
202602-NM25-02000 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:02 | February | 2026 | 2026-02-26 08:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02001 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:05 | February | 2026 | 2026-02-25 10:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 39
202602-NM25-02002 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:58 | February | 2026 | 2026-03-05 09:47 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 35
202602-NM25-02003 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:05 | February | 2026 | 2026-03-04 14:38 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 39
202602-NM25-02004 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:12 | February | 2026 | 2026-02-25 14:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02005 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:13 | February | 2026 | 2026-02-25 12:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02006 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:14 | February | 2026 | 2026-02-26 15:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02007 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:22 | February | 2026 | 2026-02-26 12:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02008 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:25 | February | 2026 | 2026-03-04 11:04 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 39
202602-NM25-02009 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:26 | February | 2026 | 2026-02-25 12:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02010 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:36 | February | 2026 | 2026-02-25 12:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02013 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:29 | February | 2026 | 2026-02-25 12:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02014 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:37 | February | 2026 | 2026-03-04 11:19 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 39
202602-NM25-02015 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:35 | February | 2026 | 2026-02-26 09:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02018 | GDL17 | Residencial | 15.04 | Period | 2026-02-20 12:37 | February | 2026 | 2026-02-25 12:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02020 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:45 | February | 2026 | 2026-02-25 14:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02022 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:52 | February | 2026 | 2026-02-25 15:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02023 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:57 | February | 2026 | 2026-03-02 15:12 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02024 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:56 | February | 2026 | 2026-02-25 15:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02026 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 12:54 | February | 2026 | 2026-02-27 10:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 7 | 0 | 2026-04-01 | 39
202602-NM25-02027 | GDL17 | Residencial | 10.43 | Period | 2026-02-20 13:02 | February | 2026 | 2026-02-25 15:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02028 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:13 | February | 2026 | 2026-02-25 13:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02029 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:13 | February | 2026 | 2026-02-25 15:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02030 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:11 | February | 2026 | 2026-02-26 13:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02033 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:18 | February | 2026 | 2026-02-26 15:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02034 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:34 | February | 2026 | 2026-02-26 13:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02035 | GDL17 | Residencial | 3.8 | Period | 2026-03-18 08:48 | March | 2026 | 2026-03-20 10:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 14
202602-NM25-02036 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:27 | February | 2026 | 2026-02-26 14:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02037 | GDL17 | Residencial | 19.7 | Period | 2026-02-20 13:26 | February | 2026 | 2026-02-26 13:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02038 | GDL17 | Residencial | 6 | Period | 2026-03-03 11:37 | March | 2026 | 2026-03-06 14:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-02039 | GDL17 | Residencial | 5.76 | Period | 2026-03-13 12:22 | March | 2026 | 2026-03-18 17:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 18
202602-NM25-02040 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:34 | February | 2026 | 2026-02-25 15:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02042 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:43 | February | 2026 | 2026-03-03 10:55 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 39
202602-NM25-02043 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:51 | February | 2026 | 2026-02-25 15:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02045 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:49 | February | 2026 | 2026-02-26 12:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02046 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:09 | February | 2026 | 2026-03-02 08:36 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02048 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:51 | February | 2026 | 2026-02-27 13:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 39
202602-NM25-02050 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 13:59 | February | 2026 | 2026-03-03 15:36 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 39
202602-NM25-02052 | GDL17 | Residencial | 3.8 | Period | 2026-03-02 10:22 | March | 2026 | 2026-03-04 09:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 30
202602-NM25-02053 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:10 | February | 2026 | 2026-03-04 10:06 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 39
202602-NM25-02055 | GDL17 | Residencial | 6 | Period | 2026-03-10 09:35 | March | 2026 | 2026-03-12 11:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-02057 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:18 | February | 2026 | 2026-02-25 15:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02060 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 17:52 | February | 2026 | 2026-02-26 08:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02061 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:33 | February | 2026 | 2026-02-26 08:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02062 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:31 | February | 2026 | 2026-02-26 08:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02067 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:08 | February | 2026 | 2026-03-02 09:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02070 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:39 | February | 2026 | 2026-02-26 08:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02071 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:47 | February | 2026 | 2026-02-25 16:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02072 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:48 | February | 2026 | 2026-02-26 08:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02073 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 14:50 | February | 2026 | 2026-03-02 13:02 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02074 | GDL17 | Residencial | 7.6 | Period | 2026-02-20 14:58 | February | 2026 | 2026-03-02 12:51 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02078 | GDL17 | Residencial | 23 | Period | 2026-03-20 10:43 | March | 2026 | 2026-03-27 09:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 1 | 6 | 2026-04-01 | 12
202602-NM25-02079 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:04 | February | 2026 | 2026-02-26 08:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02080 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:01 | February | 2026 | 2026-03-02 13:40 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02081 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:05 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 39
202602-NM25-02082 | GDL17 | Residencial | 7.6 | Period | 2026-03-05 11:01 | March | 2026 | 2026-03-09 11:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 27
202602-NM25-02083 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:09 | February | 2026 | 2026-02-26 08:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02084 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:20 | February | 2026 | 2026-02-26 08:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02087 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:26 | February | 2026 | 2026-02-26 08:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02089 | GDL17 | Comercial | 11.5 | Period | 2026-02-20 15:28 | February | 2026 | 2026-03-04 14:50 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 12 | 0 | 2026-04-01 | 39
202602-NM25-02092 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:30 | February | 2026 | 2026-03-02 16:12 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02093 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:37 | February | 2026 | 2026-02-26 13:26 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02094 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:34 | February | 2026 | 2026-02-26 08:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02095 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:37 | February | 2026 | 2026-03-03 15:12 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 39
202602-NM25-02097 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:46 | February | 2026 | 2026-02-26 08:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02098 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:01 | March | 2026 | 2026-03-26 10:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-02099 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:46 | February | 2026 | 2026-02-27 13:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 7 | 0 | 2026-04-01 | 39
202602-NM25-02100 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:55 | February | 2026 | 2026-02-26 08:19 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02101 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 15:54 | February | 2026 | 2026-02-26 13:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02102 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:01 | February | 2026 | 2026-03-02 11:11 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02104 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:04 | February | 2026 | 2026-02-26 13:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02105 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:10 | February | 2026 | 2026-03-04 10:38 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 39
202602-NM25-02107 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:18 | February | 2026 | 2026-03-04 08:56 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 12 | 0 | 2026-04-01 | 39
202602-NM25-02108 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:28 | February | 2026 | 2026-02-26 08:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02109 | GDL17 | Residencial | 7.296 | Period | 2026-03-10 11:02 | March | 2026 | 2026-03-13 13:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 22
202602-NM25-02110 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:33 | February | 2026 | 2026-03-02 07:58 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02111 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:52 | February | 2026 | 2026-03-02 14:04 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 39
202602-NM25-02112 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:49 | February | 2026 | 2026-03-03 08:28 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 39
202602-NM25-02113 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:47 | February | 2026 | 2026-02-26 10:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02114 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:52 | February | 2026 | 2026-02-26 08:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02115 | GDL17 | Residencial | 11.5 | Period | 2026-02-20 16:59 | February | 2026 | 2026-02-26 08:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 6 | 0 | 2026-04-01 | 39
202602-NM25-02116 | GDL17 | Residencial | 8 | Period | 2026-02-23 20:39 | February | 2026 | 2026-02-27 09:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02120 | GDL17 | Residencial | 11.5 | Period | 2026-02-21 08:13 | February | 2026 | 2026-02-26 08:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 5 | 0 | 2026-04-01 | 39
202602-NM25-02121 | GDL17 | Residencial | 8 | Period | 2026-02-21 08:54 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 39
202602-NM25-02122 | GDL17 | Residencial | 9 | Period | 2026-03-08 18:08 | March | 2026 | 2026-03-09 11:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 23
202602-NM25-02123 | GDL17 | Residencial | 9 | Period | 2026-03-09 09:02 | March | 2026 | 2026-03-09 11:16 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 0 | 0 | 2026-04-01 | 23
202602-NM25-02124 | GDL17 | Residencial | 15 | Period | 2026-02-21 22:28 | February | 2026 | 2026-03-10 15:57 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 17 | 0 | 2026-04-01 | 38
202602-NM25-02125 | GDL17 | Residencial | 7.68 | Period | 2026-02-21 23:06 | February | 2026 | 2026-03-02 13:16 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 7 | 2 | 2026-04-01 | 38
202602-NM25-02126 | GDL17 | Residencial | 11.4 | Period | 2026-02-23 22:04 | February | 2026 | 2026-02-27 09:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02127 | GDL17 | Residencial | 13.6 | Period | 2026-02-25 20:10 | February | 2026 | 2026-03-02 10:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02128 | GDL17 | Comercial | 5 | Period | 2026-03-02 18:22 | March | 2026 | 2026-03-11 11:02 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 2 | 5 | 4 | 2026-04-01 | 29
202602-NM25-02129 | GDL17 | Residencial | 7.6 | Period | 2026-02-24 03:46 | February | 2026 | 2026-02-27 09:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02130 | GDL17 | Residencial | 18 | Period | 2026-02-23 07:05 | February | 2026 | 2026-02-27 09:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 3 | 1 | 2026-04-01 | 37
202602-NM25-02131 | GDL17 | Residencial | 12.288 | Period | 2026-02-23 15:11 | February | 2026 | 2026-03-02 13:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 36
202602-NM25-02133 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:44 | February | 2026 | 2026-02-26 14:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-02135 | GDL17 | Residencial | 3.84 | Period | 2026-02-23 10:34 | February | 2026 | 2026-02-26 09:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02139 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:50 | March | 2026 | 2026-03-30 09:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 8
202602-NM25-02141 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 10:24 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 35
202602-NM25-02142 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:10 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 34
202602-NM25-02143 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:10 | February | 2026 | 2026-03-03 15:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 37
202602-NM25-02144 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:26 | February | 2026 | 2026-03-02 14:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02145 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:19 | February | 2026 | 2026-02-26 16:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-02146 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:39 | February | 2026 | 2026-03-09 15:23 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 12 | 0 | 2026-04-01 | 34
202602-NM25-02147 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:27 | February | 2026 | 2026-02-27 13:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 37
202602-NM25-02148 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:03 | February | 2026 | 2026-02-26 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02149 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 09:37 | March | 2026 | 2026-03-16 11:02 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 27
202602-NM25-02150 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:44 | February | 2026 | 2026-02-26 08:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02151 | GDL17 | Residencial | 3.84 | Period | 2026-03-18 07:43 | March | 2026 | 2026-03-25 07:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 14
202602-NM25-02152 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:43 | February | 2026 | 2026-02-26 08:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02153 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:33 | March | 2026 | 2026-03-27 07:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-02154 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:48 | February | 2026 | 2026-02-26 08:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02155 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:51 | February | 2026 | 2026-02-27 10:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-02156 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:58 | February | 2026 | 2026-02-26 08:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02158 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 08:58 | February | 2026 | 2026-02-27 12:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 5 | 0 | 2026-04-01 | 37
202602-NM25-02159 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:09 | February | 2026 | 2026-02-26 08:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02160 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:14 | February | 2026 | 2026-03-05 10:23 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 37
202602-NM25-02161 | GDL17 | Residencial | 7.6 | Period | 2026-02-24 10:59 | February | 2026 | 2026-03-02 12:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 36
202602-NM25-02162 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:16 | February | 2026 | 2026-02-27 13:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 5 | 0 | 2026-04-01 | 37
202602-NM25-02163 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:06 | February | 2026 | 2026-03-04 13:13 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 10 | 0 | 2026-04-01 | 37
202602-NM25-02164 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:37 | February | 2026 | 2026-02-26 08:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02165 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:26 | February | 2026 | 2026-02-26 09:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02166 | GDL17 | Residencial | 11.4 | Period | 2026-02-25 10:04 | February | 2026 | 2026-03-10 07:39 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 12 | 1 | 2026-04-01 | 35
202602-NM25-02167 | GDL17 | Residencial | 4.992 | Period | 2026-02-23 09:42 | February | 2026 | 2026-03-05 08:36 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 37
202602-NM25-02168 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:34 | February | 2026 | 2026-02-26 09:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02169 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:36 | February | 2026 | 2026-03-05 13:10 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 37
202602-NM25-02170 | GDL17 | Residencial | 14.44 | Period | 2026-02-25 13:41 | February | 2026 | 2026-03-02 09:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02171 | GDL17 | Residencial | 7.68 | Period | 2026-03-16 16:04 | March | 2026 | 2026-03-20 13:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 15
202602-NM25-02172 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:46 | February | 2026 | 2026-02-26 09:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02173 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:46 | March | 2026 | 2026-03-11 13:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 21
202602-NM25-02174 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:21 | February | 2026 | 2026-03-06 13:13 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 9 | 0 | 2026-04-01 | 34
202602-NM25-02175 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:00 | February | 2026 | 2026-03-05 09:12 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 37
202602-NM25-02177 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 09:55 | February | 2026 | 2026-02-26 07:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02178 | GDL17 | Residencial | 7.68 | Period | 2026-02-25 15:09 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 34
202602-NM25-02179 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:07 | February | 2026 | 2026-02-26 09:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02182 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:12 | February | 2026 | 2026-02-27 14:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 5 | 0 | 2026-04-01 | 37
202602-NM25-02183 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:16 | February | 2026 | 2026-02-26 09:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02186 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:25 | February | 2026 | 2026-02-26 10:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02187 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 18:02 | March | 2026 | 2026-03-05 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 28
202602-NM25-02188 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:33 | February | 2026 | 2026-02-26 09:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02190 | GDL17 | Residencial | 9.216 | Period | 2026-02-25 13:29 | February | 2026 | 2026-03-03 09:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 4 | 2 | 2026-04-01 | 34
202602-NM25-02191 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:41 | February | 2026 | 2026-03-05 13:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 37
202602-NM25-02193 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:35 | February | 2026 | 2026-03-03 13:41 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 36
202602-NM25-02194 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 10:50 | February | 2026 | 2026-02-27 11:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-02195 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:21 | March | 2026 | 2026-03-23 14:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-02196 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:06 | February | 2026 | 2026-03-09 10:18 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 14 | 0 | 2026-04-01 | 37
202602-NM25-02197 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:00 | February | 2026 | 2026-02-26 08:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 37
202602-NM25-02198 | GDL17 | Residencial | 9 | Period | 2026-02-23 14:08 | February | 2026 | 2026-03-02 09:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02199 | GDL17 | Residencial | 4.224 | Period | 2026-02-23 15:19 | February | 2026 | 2026-03-02 08:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02202 | GDL17 | Residencial | 10.672 | Period | 2026-02-23 11:13 | February | 2026 | 2026-02-26 09:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 37
202602-NM25-02203 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:12 | February | 2026 | 2026-03-04 14:24 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 37
202602-NM25-02205 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:15 | February | 2026 | 2026-02-27 15:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-02206 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:30 | February | 2026 | 2026-03-03 14:00 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 37
202602-NM25-02207 | GDL17 | Residencial | 9.15 | Period | 2026-02-23 11:32 | February | 2026 | 2026-02-27 09:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02208 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:23 | February | 2026 | 2026-02-27 09:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02209 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:26 | February | 2026 | 2026-03-06 08:56 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 37
202602-NM25-02210 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:13 | March | 2026 | 2026-04-01 08:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 1 | 0 | 2026-04-01 | 2
202602-NM25-02211 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:30 | February | 2026 | 2026-02-27 09:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02212 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:08 | February | 2026 | 2026-03-04 15:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02213 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:54 | March | 2026 | 2026-03-09 08:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 28
202602-NM25-02214 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:32 | February | 2026 | 2026-02-27 09:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02215 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:34 | February | 2026 | 2026-03-02 09:20 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 37
202602-NM25-02216 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:27 | March | 2026 | 2026-03-11 09:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 23
202602-NM25-02217 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:39 | February | 2026 | 2026-03-17 09:26 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 21 | 0 | 2026-04-01 | 36
202602-NM25-02218 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:43 | February | 2026 | 2026-02-27 15:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-02219 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:46 | February | 2026 | 2026-03-02 11:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 37
202602-NM25-02220 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:07 | March | 2026 | 2026-03-30 10:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 8
202602-NM25-02221 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:50 | February | 2026 | 2026-02-27 15:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 37
202602-NM25-02222 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:46 | February | 2026 | 2026-03-18 10:39 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 23 | 0 | 2026-04-01 | 37
202602-NM25-02223 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:43 | February | 2026 | 2026-02-27 09:41 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02225 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:53 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 37
202602-NM25-02226 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:51 | February | 2026 | 2026-02-26 11:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 37
202602-NM25-02227 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:06 | February | 2026 | 2026-02-26 08:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02228 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:51 | February | 2026 | 2026-02-26 08:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 37
202602-NM25-02229 | GDL17 | Residencial | 14.208 | Period | 2026-02-23 11:56 | February | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 37
202602-NM25-02230 | GDL17 | Residencial | 9.58 | Period | 2026-02-23 12:05 | February | 2026 | 2026-02-26 08:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02231 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 11:58 | February | 2026 | 2026-02-26 08:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 37
202602-NM25-02232 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:00 | February | 2026 | 2026-03-06 13:19 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 37
202602-NM25-02233 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:02 | February | 2026 | 2026-02-26 14:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02234 | GDL17 | Residencial | 3.84 | Period | 2026-02-23 14:14 | February | 2026 | 2026-02-27 11:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02235 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 16:40 | March | 2026 | 2026-03-24 14:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 11
202602-NM25-02236 | GDL17 | Residencial | 7.072 | Period | 2026-02-23 12:09 | February | 2026 | 2026-02-26 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02237 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:13 | February | 2026 | 2026-03-03 13:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 36
202602-NM25-02238 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:18 | February | 2026 | 2026-02-26 08:39 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02240 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:24 | February | 2026 | 2026-02-26 08:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02241 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:22 | February | 2026 | 2026-03-05 09:58 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 36
202602-NM25-02244 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:28 | February | 2026 | 2026-02-26 09:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02245 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:31 | February | 2026 | 2026-02-26 13:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02246 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:30 | February | 2026 | 2026-03-06 09:04 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 36
202602-NM25-02247 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:34 | February | 2026 | 2026-02-26 15:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02248 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:37 | February | 2026 | 2026-02-26 08:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02249 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:37 | February | 2026 | 2026-03-02 09:09 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02250 | GDL17 | Residencial | 9 | Period | 2026-03-05 11:31 | March | 2026 | 2026-03-11 13:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 27
202602-NM25-02251 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:43 | February | 2026 | 2026-03-02 07:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02252 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:44 | February | 2026 | 2026-02-27 13:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02253 | GDL17 | Residencial | 23 | Period | 2026-02-24 12:38 | February | 2026 | 2026-02-27 09:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02254 | GDL17 | Residencial | 17.4 | Period | 2026-02-23 12:46 | February | 2026 | 2026-02-26 08:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02255 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:45 | February | 2026 | 2026-02-27 09:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02256 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:57 | February | 2026 | 2026-02-27 15:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02257 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 12:53 | February | 2026 | 2026-02-27 13:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02259 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:03 | February | 2026 | 2026-02-24 16:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02262 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:13 | February | 2026 | 2026-02-24 16:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02263 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:15 | February | 2026 | 2026-02-24 16:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02264 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:20 | February | 2026 | 2026-02-25 10:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02265 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:13 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 11
202602-NM25-02266 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:26 | February | 2026 | 2026-02-27 12:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02267 | GDL17 | Residencial | 10.672 | Period | 2026-02-23 13:25 | February | 2026 | 2026-02-25 10:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02268 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:07 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 29
202602-NM25-02269 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:34 | February | 2026 | 2026-02-25 15:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02270 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 13:58 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 11
202602-NM25-02271 | GDL17 | Residencial | 23 | Period | 2026-02-23 13:34 | February | 2026 | 2026-02-25 10:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02272 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:43 | February | 2026 | 2026-02-26 15:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02273 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:58 | February | 2026 | 2026-02-25 11:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02274 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:44 | February | 2026 | 2026-02-25 10:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02276 | GDL17 | Residencial | 7.87 | Period | 2026-02-23 13:49 | February | 2026 | 2026-02-25 10:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02277 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:52 | March | 2026 | 2026-03-05 15:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-02278 | GDL17 | Residencial | 4.608 | Period | 2026-02-23 14:22 | February | 2026 | 2026-03-09 15:48 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 36
202602-NM25-02279 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 13:58 | February | 2026 | 2026-02-25 10:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02280 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 13:39 | March | 2026 | 2026-03-05 08:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 28
202602-NM25-02281 | GDL17 | Residencial | 5.31 | Period | 2026-03-11 13:56 | March | 2026 | 2026-03-16 08:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 20
202602-NM25-02282 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:08 | February | 2026 | 2026-02-27 09:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02283 | GDL17 | Residencial | 15 | Period | 2026-02-23 15:05 | February | 2026 | 2026-02-27 15:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02284 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:13 | February | 2026 | 2026-02-26 15:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02286 | GDL17 | Residencial | 8 | Period | 2026-02-23 21:32 | February | 2026 | 2026-02-25 12:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02287 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:24 | February | 2026 | 2026-02-26 13:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02288 | GDL17 | Residencial | 7.68 | Period | 2026-03-02 13:59 | March | 2026 | 2026-03-11 10:17 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 29
202602-NM25-02289 | GDL17 | Residencial | 8 | Period | 2026-02-23 21:22 | February | 2026 | 2026-03-06 10:25 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 36
202602-NM25-02290 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:34 | February | 2026 | 2026-02-25 15:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02291 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:46 | February | 2026 | 2026-03-02 07:43 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02292 | GDL17 | Residencial | 3.84 | Period | 2026-03-10 07:30 | March | 2026 | 2026-03-12 15:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-02293 | GDL17 | Residencial | 8 | Period | 2026-02-24 15:42 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 35
202602-NM25-02294 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 13:33 | March | 2026 | 2026-03-16 13:12 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 25
202602-NM25-02295 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 14:58 | February | 2026 | 2026-02-25 11:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02296 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 13:20 | February | 2026 | 2026-03-09 09:44 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 34
202602-NM25-02298 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:11 | February | 2026 | 2026-02-24 15:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02300 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:12 | February | 2026 | 2026-02-24 16:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02301 | GDL17 | Comercial | 11.5 | Period | 2026-02-23 15:12 | February | 2026 | 2026-02-24 15:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02303 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:21 | February | 2026 | 2026-03-06 10:51 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 36
202602-NM25-02304 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:22 | February | 2026 | 2026-02-25 11:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02305 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:23 | February | 2026 | 2026-03-04 07:51 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 36
202602-NM25-02306 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:30 | February | 2026 | 2026-02-24 15:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02307 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:38 | February | 2026 | 2026-02-27 08:35 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02308 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:35 | February | 2026 | 2026-02-24 15:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02310 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:42 | February | 2026 | 2026-03-02 15:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 36
202602-NM25-02312 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 07:31 | March | 2026 | 2026-03-12 15:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 21
202602-NM25-02313 | GDL17 | Residencial | 15 | Period | 2026-02-26 11:53 | February | 2026 | 2026-03-03 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02314 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:49 | February | 2026 | 2026-02-24 15:16 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02315 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:50 | February | 2026 | 2026-03-18 17:50 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 23 | 0 | 2026-04-01 | 36
202602-NM25-02316 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:57 | February | 2026 | 2026-02-24 15:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02317 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:58 | February | 2026 | 2026-02-24 15:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02318 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 15:58 | February | 2026 | 2026-03-02 13:31 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 36
202602-NM25-02319 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:00 | February | 2026 | 2026-02-24 15:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02320 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:03 | February | 2026 | 2026-02-25 10:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02321 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:08 | February | 2026 | 2026-02-26 13:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02322 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:09 | February | 2026 | 2026-02-24 15:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02323 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:10 | February | 2026 | 2026-02-25 08:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02324 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:23 | February | 2026 | 2026-02-25 14:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02325 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:29 | February | 2026 | 2026-02-25 13:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02326 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:18 | February | 2026 | 2026-03-05 07:53 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 36
202602-NM25-02327 | GDL17 | Residencial | 7.87 | Period | 2026-02-23 16:18 | February | 2026 | 2026-02-24 16:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02328 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:19 | February | 2026 | 2026-02-25 16:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02330 | GDL17 | Residencial | 7.09 | Period | 2026-02-23 16:27 | February | 2026 | 2026-02-24 16:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02331 | GDL17 | Residencial | 8.644 | Period | 2026-02-23 16:42 | February | 2026 | 2026-02-24 15:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02332 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:34 | February | 2026 | 2026-03-03 14:00 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 36
202602-NM25-02333 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:33 | February | 2026 | 2026-02-25 11:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02334 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:45 | February | 2026 | 2026-02-26 07:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02335 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:46 | February | 2026 | 2026-02-27 09:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02337 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 17:06 | February | 2026 | 2026-02-27 07:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02338 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:52 | February | 2026 | 2026-02-24 15:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02339 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 17:01 | February | 2026 | 2026-02-24 15:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02340 | GDL17 | Residencial | 23 | Period | 2026-02-23 17:03 | February | 2026 | 2026-03-02 10:41 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02341 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 16:55 | February | 2026 | 2026-02-24 15:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02342 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 17:13 | February | 2026 | 2026-03-02 08:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02344 | GDL17 | Residencial | 7.87 | Period | 2026-02-23 17:10 | February | 2026 | 2026-02-25 08:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02345 | GDL17 | Residencial | 11.5 | Period | 2026-02-23 17:10 | February | 2026 | 2026-02-25 08:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02346 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 17:13 | March | 2026 | 2026-03-26 09:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-02347 | GDL17 | Residencial | 9.344 | Period | 2026-02-23 17:21 | February | 2026 | 2026-02-25 08:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02349 | GDL17 | Residencial | 8 | Period | 2026-02-23 21:12 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 36
202602-NM25-02350 | GDL17 | Residencial | 11.5 | Period | 2026-03-21 13:33 | March | 2026 | 2026-03-24 14:05 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 10
202602-NM25-02351 | GDL17 | Residencial | 2.36 | Period | 2026-02-23 20:09 | February | 2026 | 2026-02-25 08:42 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02352 | GDL17 | Residencial | 7.6 | Period | 2026-03-05 17:22 | March | 2026 | 2026-03-06 09:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 26
202602-NM25-02356 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 18:12 | March | 2026 | 2026-04-09 13:23 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | April |  | 20 | 16 | 2026-04-01 | 11
202602-NM25-02357 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:06 | March | 2026 | 2026-03-25 15:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 8
202602-NM25-02359 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 13:35 | March | 2026 | 2026-04-02 14:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 0
202602-NM25-02360 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 16:44 | March | 2026 | 2026-04-08 09:42 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 9 | 0 | 2026-04-01 | 1
202602-NM25-02361 | GDL17 | Residencial | 24 | Period | 2026-02-23 21:10 | February | 2026 | 2026-02-24 16:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02362 | GDL17 | Residencial | 22.8 | Period | 2026-02-24 07:34 | February | 2026 | 2026-03-18 09:57 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 22 | 0 | 2026-04-01 | 36
202602-NM25-02366 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 08:42 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 36
202602-NM25-02367 | GDL17 | Residencial | 7.6 | Period | 2026-02-24 08:34 | February | 2026 | 2026-02-27 14:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02369 | GDL17 | Residencial | 15.8 | Period | 2026-02-24 08:45 | February | 2026 | 2026-02-27 13:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02370 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 09:00 | February | 2026 | 2026-02-27 13:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 4 | 0 | 2026-04-01 | 36
202602-NM25-02371 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:01 | February | 2026 | 2026-02-27 09:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02372 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 09:08 | February | 2026 | 2026-03-02 13:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02374 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 09:15 | February | 2026 | 2026-02-27 09:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02375 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:29 | February | 2026 | 2026-03-06 09:31 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 9 | 0 | 2026-04-01 | 35
202602-NM25-02377 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 15:15 | March | 2026 | 2026-03-30 12:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-02378 | GDL17 | Residencial | 16.01 | Period | 2026-02-24 09:53 | February | 2026 | 2026-03-04 10:13 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 2 | 6 | 2 | 2026-04-01 | 36
202602-NM25-02381 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 09:54 | February | 2026 | 2026-03-04 08:02 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 36
202602-NM25-02387 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:49 | March | 2026 | 2026-03-23 14:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-02390 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:16 | March | 2026 | 2026-03-06 10:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 28
202602-NM25-02391 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:28 | February | 2026 | 2026-02-27 09:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02392 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:20 | March | 2026 | 2026-03-26 13:02 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 14
202602-NM25-02393 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:42 | February | 2026 | 2026-02-27 14:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02394 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 10:37 | February | 2026 | 2026-03-03 13:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 36
202602-NM25-02396 | GDL17 | Residencial | 9.552 | Period | 2026-02-24 10:53 | February | 2026 | 2026-03-02 08:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02397 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:57 | February | 2026 | 2026-03-03 15:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02398 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:28 | February | 2026 | 2026-03-13 09:51 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 17 | 0 | 2026-04-01 | 36
202602-NM25-02399 | GDL17 | Residencial | 6.528 | Period | 2026-02-24 11:19 | February | 2026 | 2026-03-02 07:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 36
202602-NM25-02400 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:16 | February | 2026 | 2026-02-27 09:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02401 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 07:33 | March | 2026 | 2026-03-05 09:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202602-NM25-02402 | GDL17 | Comercial | 11.5 | Period | 2026-02-24 11:15 | February | 2026 | 2026-02-27 09:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 36
202602-NM25-02404 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 13:34 | March | 2026 | 2026-03-11 16:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 27
202602-NM25-02405 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:24 | February | 2026 | 2026-02-26 15:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02407 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:31 | February | 2026 | 2026-03-04 13:20 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 36
202602-NM25-02408 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:39 | February | 2026 | 2026-02-25 13:24 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02409 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:36 | February | 2026 | 2026-02-26 13:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02410 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:55 | February | 2026 | 2026-02-25 13:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 36
202602-NM25-02411 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 08:48 | February | 2026 | 2026-03-04 11:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-02413 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:46 | February | 2026 | 2026-02-26 08:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 2 | 0 | 2026-04-01 | 36
202602-NM25-02414 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:49 | February | 2026 | 2026-03-05 13:31 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 36
202602-NM25-02415 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:24 | February | 2026 | 2026-02-26 10:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02416 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:06 | February | 2026 | 2026-03-05 14:18 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 35
202602-NM25-02417 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 11:54 | February | 2026 | 2026-03-04 14:26 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 36
202602-NM25-02418 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:08 | February | 2026 | 2026-03-05 14:46 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 35
202602-NM25-02419 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:31 | March | 2026 | 2026-03-05 15:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 27
202602-NM25-02420 | GDL17 | Residencial | 7.84 | Period | 2026-02-24 12:15 | February | 2026 | 2026-02-25 13:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02421 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:13 | February | 2026 | 2026-02-27 13:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02422 | GDL17 | Comercial | 23 | Period | 2026-03-20 18:09 | March | 2026 | 2026-03-27 08:33 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 4 | 3 | 2026-04-01 | 11
202602-NM25-02423 | GDL17 | Residencial | 7.6 | Period | 2026-02-24 13:04 | February | 2026 | 2026-02-25 13:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02425 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:20 | February | 2026 | 2026-02-27 13:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02427 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:21 | February | 2026 | 2026-02-25 13:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02428 | GDL17 | Residencial | 10.84 | Period | 2026-02-24 12:35 | February | 2026 | 2026-02-25 13:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02429 | GDL17 | Residencial | 8 | Period | 2026-03-20 11:19 | March | 2026 | 2026-03-23 16:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-02430 | GDL17 | Residencial | 23 | Period | 2026-02-24 12:29 | February | 2026 | 2026-02-25 13:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02431 | GDL17 | Comercial | 24 | Period | 2026-03-17 13:16 | March | 2026 | 2026-04-09 10:21 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 22 | 0 | 2026-04-01 | 14
202602-NM25-02432 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:36 | February | 2026 | 2026-03-04 11:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 35
202602-NM25-02433 | GDL17 | Residencial | 11.51 | Period | 2026-02-24 13:02 | February | 2026 | 2026-02-26 10:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | February | 1 | 1 | 1 | 2026-04-01 | 35
202602-NM25-02434 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:39 | February | 2026 | 2026-03-18 08:35 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 22 | 0 | 2026-04-01 | 35
202602-NM25-02435 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:42 | February | 2026 | 2026-03-05 13:50 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 35
202602-NM25-02436 | GDL17 | Residencial | 7.474 | Period | 2026-02-24 12:49 | February | 2026 | 2026-02-25 13:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02437 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:47 | February | 2026 | 2026-02-25 12:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02438 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:49 | February | 2026 | 2026-03-04 09:42 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 35
202602-NM25-02439 | GDL17 | Residencial | 7.6 | Period | 2026-02-27 09:46 | February | 2026 | 2026-03-04 09:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02440 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 12:59 | February | 2026 | 2026-02-25 12:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02441 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:01 | February | 2026 | 2026-02-26 13:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02442 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:01 | February | 2026 | 2026-03-16 17:07 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 20 | 0 | 2026-04-01 | 35
202602-NM25-02443 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 08:45 | February | 2026 | 2026-03-05 09:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-02444 | GDL17 | Residencial | 7.38 | Period | 2026-02-24 14:14 | February | 2026 | 2026-02-25 12:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02445 | GDL17 | Residencial | 16.26 | Period | 2026-02-24 13:10 | February | 2026 | 2026-02-25 12:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02446 | GDL17 | Residencial | 8.45 | Period | 2026-02-24 13:14 | February | 2026 | 2026-02-25 12:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02448 | GDL17 | Residencial | 19.1 | Period | 2026-02-26 09:47 | February | 2026 | 2026-03-03 15:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02450 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:28 | February | 2026 | 2026-03-02 11:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02452 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:39 | February | 2026 | 2026-03-03 09:34 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 35
202602-NM25-02454 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 13:53 | February | 2026 | 2026-03-09 14:44 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 35
202602-NM25-02455 | GDL17 | Residencial | 13.036 | Period | 2026-02-24 13:55 | February | 2026 | 2026-03-24 16:17 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 2 | 27 | 0 | 2026-04-01 | 35
202602-NM25-02456 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:09 | February | 2026 | 2026-02-27 14:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02458 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:41 | February | 2026 | 2026-03-03 13:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02459 | GDL17 | Residencial | 8 | Period | 2026-02-26 20:58 | February | 2026 | 2026-03-03 11:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02461 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:23 | February | 2026 | 2026-02-27 12:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02462 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 18:46 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 33
202602-NM25-02463 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:35 | February | 2026 | 2026-02-25 14:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 1 | 0 | 2026-04-01 | 35
202602-NM25-02464 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:29 | February | 2026 | 2026-02-27 08:31 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02465 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:37 | February | 2026 | 2026-03-03 13:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 35
202602-NM25-02466 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 11:31 | March | 2026 | 2026-03-10 07:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 28
202602-NM25-02467 | GDL17 | Residencial | 15 | Period | 2026-02-25 14:34 | February | 2026 | 2026-03-04 09:23 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-02469 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:42 | February | 2026 | 2026-02-26 15:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02470 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 14:54 | February | 2026 | 2026-03-02 10:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 35
202602-NM25-02471 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:00 | February | 2026 | 2026-03-02 10:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 35
202602-NM25-02473 | GDL17 | Residencial | 3.84 | Period | 2026-02-27 10:16 | February | 2026 | 2026-03-05 13:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 33
202602-NM25-02476 | GDL17 | Residencial | 7.87 | Period | 2026-02-24 15:11 | February | 2026 | 2026-03-02 13:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02477 | GDL17 | Residencial | 16.06 | Period | 2026-02-24 15:17 | February | 2026 | 2026-02-27 10:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02478 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 10:22 | February | 2026 | 2026-03-06 12:40 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 34
202602-NM25-02479 | GDL17 | Comercial | 11.4 | Period | 2026-03-03 14:27 | March | 2026 | 2026-03-27 08:27 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 2 | 22 | 2026-04-01 | 28
202602-NM25-02480 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:23 | February | 2026 | 2026-03-02 09:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02482 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:26 | February | 2026 | 2026-03-03 14:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 35
202602-NM25-02483 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:34 | February | 2026 | 2026-03-03 16:08 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 35
202602-NM25-02486 | GDL17 | Residencial | 7.97 | Period | 2026-02-24 15:35 | February | 2026 | 2026-03-05 09:33 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 4 | 5 | 2026-04-01 | 35
202602-NM25-02487 | GDL17 | Residencial | 16 | Period | 2026-02-24 20:03 | February | 2026 | 2026-02-27 09:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02488 | GDL17 | Comercial | 9 | Period | 2026-03-18 11:03 | March | 2026 | 2026-03-19 15:38 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 14
202602-NM25-02489 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 15:44 | February | 2026 | 2026-03-02 15:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02490 | GDL17 | Residencial | 7.87 | Period | 2026-02-24 15:59 | February | 2026 | 2026-03-06 10:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 4 | 6 | 2026-04-01 | 35
202602-NM25-02491 | GDL17 | Residencial | 7.6 | Period | 2026-03-09 09:00 | March | 2026 | 2026-03-09 13:53 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 0 | 0 | 2026-04-01 | 23
202602-NM25-02492 | GDL17 | Residencial | 12 | Period | 2026-03-24 15:39 | March | 2026 | 2026-03-30 09:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202602-NM25-02493 | GDL17 | Residencial | 23 | Period | 2026-02-24 15:57 | February | 2026 | 2026-03-02 09:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02494 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:09 | February | 2026 | 2026-03-11 12:37 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 15 | 0 | 2026-04-01 | 35
202602-NM25-02495 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:13 | February | 2026 | 2026-03-02 10:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 35
202602-NM25-02496 | GDL17 | Residencial | 10.814 | Period | 2026-02-24 16:14 | February | 2026 | 2026-03-02 10:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 35
202602-NM25-02497 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:39 | February | 2026 | 2026-03-06 12:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 33
202602-NM25-02498 | GDL17 | Residencial | 7.6 | Period | 2026-02-24 16:37 | February | 2026 | 2026-03-02 10:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02499 | GDL17 | Residencial | 12 | Period | 2026-02-25 08:55 | February | 2026 | 2026-03-02 11:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02500 | GDL17 | Residencial | 9.714 | Period | 2026-02-24 16:27 | February | 2026 | 2026-03-02 10:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 35
202602-NM25-02501 | GDL17 | Residencial | 9.724 | Period | 2026-02-24 16:30 | February | 2026 | 2026-03-02 10:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02502 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 17:48 | March | 2026 | 2026-03-26 08:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 8
202602-NM25-02504 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:41 | February | 2026 | 2026-03-04 09:30 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 35
202602-NM25-02505 | GDL17 | Residencial | 7.84 | Period | 2026-02-24 16:54 | February | 2026 | 2026-03-02 10:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02507 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 16:57 | February | 2026 | 2026-02-27 09:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02509 | GDL17 | Residencial | 11.5 | Period | 2026-02-24 17:05 | February | 2026 | 2026-02-27 14:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02511 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:33 | March | 2026 | 2026-03-10 10:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 22
202602-NM25-02512 | GDL17 | Residencial | 8 | Period | 2026-02-24 18:04 | February | 2026 | 2026-03-03 15:30 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 35
202602-NM25-02513 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 17:51 | March | 2026 | 2026-03-30 13:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-02516 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 18:47 | March | 2026 | 2026-03-27 16:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 11
202602-NM25-02517 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 17:12 | March | 2026 |  |  | Customer Orientation Acknowledgement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 11
202602-NM25-02518 | GDL17 | Comercial | 11.5 | Period | 2026-03-20 18:15 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 11
202602-NM25-02519 | GDL17 | Residencial | 11.52 | Period | 2026-02-25 10:53 | February | 2026 | 2026-02-27 10:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02521 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 13:56 | March | 2026 |  |  | Create NEM Agreement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 4
202602-NM25-02522 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 16:56 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 6
202602-NM25-02525 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:29 | March | 2026 | 2026-03-27 14:56 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-02528 | GDL17 | Residencial | 10 | Period | 2026-03-19 17:34 | March | 2026 | 2026-03-23 14:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-02529 | GDL17 | Residencial | 5 | Period | 2026-02-25 09:51 | February | 2026 | 2026-03-10 13:58 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 35
202602-NM25-02531 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:52 | February | 2026 | 2026-02-27 16:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | February |  | 2 | 0 | 2026-04-01 | 35
202602-NM25-02532 | GDL17 | Residencial | 8.26 | Period | 2026-03-12 12:54 | March | 2026 | 2026-03-17 09:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 4 | 1 | 2026-04-01 | 19
202602-NM25-02533 | GDL17 | Residencial | 8.254 | Period | 2026-02-25 08:33 | February | 2026 | 2026-02-27 11:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02535 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:06 | February | 2026 | 2026-03-03 09:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02536 | GDL17 | Residencial | 11.198 | Period | 2026-02-25 08:50 | February | 2026 | 2026-02-27 14:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02537 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:03 | March | 2026 | 2026-03-25 13:47 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 2 | 10 | 2026-04-01 | 18
202602-NM25-02538 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:04 | February | 2026 | 2026-03-06 09:15 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 35
202602-NM25-02539 | GDL17 | Residencial | 4.992 | Period | 2026-02-25 10:36 | February | 2026 | 2026-03-02 12:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 35
202602-NM25-02541 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:25 | February | 2026 | 2026-03-09 12:44 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 35
202602-NM25-02542 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:43 | February | 2026 | 2026-03-06 13:01 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 10 | 0 | 2026-04-01 | 35
202602-NM25-02543 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:32 | February | 2026 | 2026-03-05 15:07 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 9 | 0 | 2026-04-01 | 35
202602-NM25-02544 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:28 | February | 2026 | 2026-03-06 10:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 6 | 1 | 2026-04-01 | 32
202602-NM25-02545 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 15:55 | March | 2026 | 2026-04-07 12:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 7 | 0 | 2026-04-01 | 0
202602-NM25-02546 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:10 | March | 2026 | 2026-03-20 07:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 14
202602-NM25-02547 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:11 | February | 2026 | 2026-03-03 16:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02548 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:08 | March | 2026 | 2026-03-12 10:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 21
202602-NM25-02551 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 10:00 | February | 2026 | 2026-03-02 10:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 35
202602-NM25-02552 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 09:59 | February | 2026 | 2026-03-09 16:21 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 35
202602-NM25-02553 | GDL17 | Residencial | 3.456 | Period | 2026-03-04 09:03 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 28
202602-NM25-02556 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 19:56 | February | 2026 | 2026-03-02 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02557 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 13:10 | February | 2026 | 2026-03-19 08:36 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 2 | 19 | 2 | 2026-04-01 | 33
202602-NM25-02558 | GDL17 | Residencial | 8.832 | Period | 2026-03-25 11:35 | March | 2026 | 2026-04-02 13:22 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | April |  | 8 | 4 | 2026-04-01 | 7
202602-NM25-02559 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 10:16 | February | 2026 | 2026-02-27 15:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | February |  | 3 | 0 | 2026-04-01 | 35
202602-NM25-02560 | GDL17 | Residencial | 8 | Period | 2026-03-20 10:14 | March | 2026 | 2026-03-25 09:32 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 12
202602-NM25-02561 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:05 | March | 2026 | 2026-03-18 10:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 15
202602-NM25-02562 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:14 | March | 2026 | 2026-03-19 10:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 14
202602-NM25-02564 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 09:55 | February | 2026 | 2026-03-03 13:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02565 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 10:37 | March | 2026 | 2026-03-17 08:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202602-NM25-02567 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 11:17 | February | 2026 | 2026-03-12 09:10 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 15 | 0 | 2026-04-01 | 35
202602-NM25-02568 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:12 | February | 2026 | 2026-03-05 09:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-02570 | GDL17 | Residencial | 8 | Period | 2026-03-20 10:34 | March | 2026 | 2026-03-23 14:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-02571 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 11:39 | February | 2026 | 2026-03-02 09:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 35
202602-NM25-02572 | GDL17 | Residencial | 11.4 | Period | 2026-02-25 14:23 | February | 2026 | 2026-03-04 08:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-02575 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:42 | February | 2026 | 2026-03-03 16:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02576 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 13:45 | March | 2026 | 2026-03-05 09:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 28
202602-NM25-02577 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 13:53 | March | 2026 | 2026-03-18 15:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 14
202602-NM25-02581 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 12:42 | February | 2026 | 2026-03-02 14:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02582 | GDL17 | Residencial | 7.6 | Period | 2026-03-26 08:58 | March | 2026 | 2026-03-30 13:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 6
202602-NM25-02583 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 10:05 | March | 2026 | 2026-03-05 07:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 29
202602-NM25-02584 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 13:50 | March | 2026 | 2026-03-31 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 5
202602-NM25-02586 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:19 | March | 2026 | 2026-03-06 09:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 26
202602-NM25-02587 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:43 | March | 2026 | 2026-03-26 10:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-02589 | GDL17 | Residencial | 7.68 | Period | 2026-03-02 11:38 | March | 2026 | 2026-03-06 08:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 30
202602-NM25-02591 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:39 | February | 2026 | 2026-03-03 15:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-02593 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 13:15 | March | 2026 | 2026-04-02 09:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 3 | 0 | 2026-04-01 | 1
202602-NM25-02594 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 14:38 | February | 2026 | 2026-03-02 09:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02595 | GDL17 | Residencial | 15 | Period | 2026-03-12 10:03 | March | 2026 | 2026-03-16 08:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 20
202602-NM25-02597 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 08:19 | February | 2026 | 2026-03-03 16:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02598 | GDL17 | Residencial | 7.6 | Period | 2026-03-11 10:47 | March | 2026 | 2026-03-17 15:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 21
202602-NM25-02599 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 15:09 | February | 2026 | 2026-03-02 13:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02600 | GDL17 | Comercial | 11.5 | Period | 2026-02-25 15:23 | February | 2026 | 2026-03-02 10:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02601 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 08:30 | March | 2026 | 2026-03-17 15:38 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 22
202602-NM25-02602 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:00 | March | 2026 | 2026-03-12 13:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-02603 | GDL17 | Residencial | 10.672 | Period | 2026-02-25 16:14 | February | 2026 | 2026-03-04 09:38 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 7 | 0 | 2026-04-01 | 34
202602-NM25-02604 | GDL17 | Residencial | 12 | Period | 2026-02-28 14:25 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 31
202602-NM25-02605 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:10 | February | 2026 | 2026-03-03 16:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02607 | GDL17 | Gubernamental | 23 | Period | 2026-02-25 16:21 | February | 2026 | 2026-03-25 15:10 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 28 | 0 | 2026-04-01 | 34
202602-NM25-02608 | GDL17 | Residencial | 7.259 | Period | 2026-03-07 14:12 | March | 2026 | 2026-03-09 13:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 24
202602-NM25-02610 | GDL17 | Residencial | 7.832 | Period | 2026-02-25 16:35 | February | 2026 | 2026-03-02 16:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02611 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 16:55 | February | 2026 | 2026-03-03 15:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-02612 | GDL17 | Residencial | 7.6 | Period | 2026-02-25 17:04 | February | 2026 | 2026-03-06 08:11 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 34
202602-NM25-02613 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 17:04 | February | 2026 | 2026-03-02 12:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02614 | GDL17 | Residencial | 19.59 | Period | 2026-02-25 16:48 | February | 2026 | 2026-03-02 10:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02616 | GDL17 | Residencial | 11.5 | Period | 2026-02-25 17:08 | February | 2026 | 2026-03-02 14:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02617 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:05 | March | 2026 | 2026-03-13 14:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 22
202602-NM25-02619 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:51 | March | 2026 | 2026-03-25 15:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 9
202602-NM25-02620 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:41 | March | 2026 | 2026-04-27 14:43 | 38 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 38 | 0 | 2026-04-01 | 12
202602-NM25-02622 | GDL17 | Residencial | 6.954 | Period | 2026-02-26 08:37 | February | 2026 | 2026-03-02 15:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02624 | GDL17 | Residencial | 9.562 | Period | 2026-02-26 08:55 | February | 2026 | 2026-03-02 16:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02625 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 11:58 | February | 2026 | 2026-03-16 15:04 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 17 | 0 | 2026-04-01 | 33
202602-NM25-02626 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:10 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 34
202602-NM25-02627 | GDL17 | Residencial | 5.376 | Period | 2026-03-02 11:57 | March | 2026 | 2026-03-04 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 30
202602-NM25-02628 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:20 | February | 2026 | 2026-03-03 09:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02629 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:23 | February | 2026 | 2026-03-02 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02630 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:33 | March | 2026 | 2026-03-04 10:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 30
202602-NM25-02632 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:06 | March | 2026 | 2026-03-23 13:14 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 18
202602-NM25-02633 | GDL17 | Residencial | 8 | Period | 2026-03-20 11:26 | March | 2026 | 2026-04-01 07:50 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 11 | 0 | 2026-04-01 | 12
202602-NM25-02634 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 09:44 | February | 2026 | 2026-03-09 15:44 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 34
202602-NM25-02638 | GDL17 | Residencial | 9 | Period | 2026-03-02 17:53 | March | 2026 | 2026-03-05 09:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-02639 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:05 | February | 2026 | 2026-03-03 08:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02640 | GDL17 | Residencial | 11.98 | Period | 2026-02-26 10:24 | February | 2026 | 2026-03-03 11:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02641 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:30 | March | 2026 | 2026-03-23 14:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 12
202602-NM25-02642 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:53 | March | 2026 | 2026-03-30 12:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-02643 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 09:11 | March | 2026 | 2026-03-25 09:47 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 9 | 0 | 2026-04-01 | 16
202602-NM25-02644 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 10:41 | February | 2026 | 2026-03-03 13:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02646 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 12:24 | March | 2026 |  |  | Create NEM Agreement | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 7
202602-NM25-02647 | GDL17 | Residencial | 8 | Period | 2026-02-27 11:33 | February | 2026 | 2026-03-04 09:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02649 | GDL17 | Residencial | 5.58 | Period | 2026-02-26 10:50 | February | 2026 | 2026-03-03 14:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 34
202602-NM25-02650 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 14:26 | March | 2026 | 2026-04-08 10:07 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 9 | 0 | 2026-04-01 | 1
202602-NM25-02651 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:03 | February | 2026 | 2026-03-02 13:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02652 | GDL17 | Residencial | 3.84 | Period | 2026-02-27 13:40 | February | 2026 | 2026-03-11 13:47 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 32
202602-NM25-02653 | GDL17 | Residencial | 6.222 | Period | 2026-03-10 10:21 | March | 2026 | 2026-03-12 15:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 22
202602-NM25-02654 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:47 | March | 2026 | 2026-04-08 13:32 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 14 | 0 | 2026-04-01 | 7
202602-NM25-02655 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:47 | February | 2026 | 2026-03-03 09:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 34
202602-NM25-02656 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:12 | March | 2026 | 2026-03-06 13:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 27
202602-NM25-02657 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:34 | March | 2026 | 2026-03-31 11:13 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 8
202602-NM25-02660 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 17:08 | March | 2026 | 2026-03-23 14:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-02663 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 11:53 | February | 2026 | 2026-03-05 10:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 34
202602-NM25-02665 | GDL17 | Residencial | 12 | Period | 2026-02-27 18:00 | February | 2026 | 2026-03-04 13:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02667 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 12:10 | February | 2026 | 2026-03-03 09:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02669 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:48 | March | 2026 | 2026-03-25 16:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 8
202602-NM25-02670 | GDL17 | Residencial | 13.44 | Period | 2026-02-26 12:38 | February | 2026 | 2026-03-03 12:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02672 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:01 | March | 2026 | 2026-03-31 14:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 5
202602-NM25-02674 | GDL17 | Residencial | 5.856 | Period | 2026-02-26 12:49 | February | 2026 | 2026-03-03 13:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02675 | GDL17 | Residencial | 8.09 | Period | 2026-02-26 12:59 | February | 2026 | 2026-03-03 14:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02676 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 14:55 | February | 2026 | 2026-03-05 08:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-02678 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 09:18 | March | 2026 | 2026-03-11 13:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 1 | 1 | 2026-04-01 | 23
202602-NM25-02679 | GDL17 | Residencial | 19.808 | Period | 2026-02-26 13:01 | February | 2026 | 2026-03-03 14:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02681 | GDL17 | Residencial | 7.6 | Period | 2026-02-26 14:46 | February | 2026 | 2026-03-05 08:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-02682 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 13:11 | February | 2026 | 2026-03-03 16:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02683 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 10:14 | March | 2026 | 2026-03-16 07:54 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 10 | 0 | 2026-04-01 | 26
202602-NM25-02684 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 13:30 | February | 2026 | 2026-03-04 11:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-02686 | GDL17 | Residencial | 6.672 | Period | 2026-02-26 13:38 | February | 2026 | 2026-03-03 11:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02688 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 15:51 | March | 2026 | 2026-03-05 09:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 28
202602-NM25-02690 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 14:43 | February | 2026 | 2026-03-03 13:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02691 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:29 | February | 2026 | 2026-03-04 11:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-02692 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:20 | February | 2026 | 2026-03-04 08:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02694 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 18:29 | March | 2026 | 2026-04-09 13:23 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | April |  | 20 | 16 | 2026-04-01 | 11
202602-NM25-02695 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:28 | March | 2026 | 2026-03-18 17:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 15
202602-NM25-02696 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:21 | February | 2026 | 2026-03-03 13:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02697 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:25 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 33
202602-NM25-02701 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:38 | February | 2026 | 2026-03-05 14:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 33
202602-NM25-02702 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:40 | February | 2026 | 2026-03-03 11:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02703 | GDL17 | Residencial | 3.8 | Period | 2026-03-11 09:53 | March | 2026 | 2026-03-16 08:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 21
202602-NM25-02704 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 15:52 | February | 2026 | 2026-03-03 09:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02706 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:05 | February | 2026 | 2026-03-11 11:04 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 13 | 0 | 2026-04-01 | 33
202602-NM25-02707 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:26 | February | 2026 | 2026-03-03 09:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02708 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:19 | February | 2026 | 2026-03-03 12:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02709 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:11 | February | 2026 | 2026-03-05 10:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 5 | 1 | 2026-04-01 | 33
202602-NM25-02710 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:42 | February | 2026 | 2026-03-05 16:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 33
202602-NM25-02711 | GDL17 | Residencial | 8 | Period | 2026-02-27 14:38 | February | 2026 | 2026-03-03 13:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02712 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 08:29 | February | 2026 | 2026-03-03 14:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02713 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 16:57 | February | 2026 | 2026-03-06 11:19 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 33
202602-NM25-02714 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:41 | March | 2026 | 2026-03-16 17:11 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 18
202602-NM25-02715 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 15:32 | March | 2026 | 2026-03-18 17:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 19
202602-NM25-02716 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 18:55 | March | 2026 | 2026-03-30 13:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-02717 | GDL17 | Residencial | 11.5 | Period | 2026-02-26 17:31 | February | 2026 | 2026-03-03 10:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02718 | GDL17 | Residencial | 21.956 | Period | 2026-02-26 17:46 | February | 2026 | 2026-03-03 14:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02719 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 14:01 | March | 2026 | 2026-03-31 14:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 5
202602-NM25-02721 | GDL17 | Residencial | 16 | Period | 2026-02-27 10:10 | February | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 33
202602-NM25-02723 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:57 | March | 2026 | 2026-03-27 11:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 8
202602-NM25-02724 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:42 | February | 2026 | 2026-03-09 13:02 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 10 | 0 | 2026-04-01 | 32
202602-NM25-02725 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 07:55 | February | 2026 | 2026-03-03 16:11 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02726 | GDL17 | Residencial | 4.758 | Period | 2026-02-27 08:24 | February | 2026 | 2026-03-03 11:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02727 | GDL17 | Residencial | 8 | Period | 2026-03-02 07:16 | March | 2026 | 2026-03-10 08:14 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 30
202602-NM25-02728 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 08:40 | February | 2026 | 2026-03-03 11:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02729 | GDL17 | Residencial | 15.2 | Period | 2026-03-12 10:31 | March | 2026 | 2026-03-20 10:38 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 20
202602-NM25-02730 | GDL17 | Residencial | 13.42 | Period | 2026-02-27 08:49 | February | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 33
202602-NM25-02731 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:00 | February | 2026 | 2026-03-11 13:18 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 12 | 0 | 2026-04-01 | 33
202602-NM25-02733 | GDL17 | Residencial | 11.44 | Period | 2026-02-27 09:10 | February | 2026 | 2026-03-06 08:05 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 33
202602-NM25-02734 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:47 | March | 2026 | 2026-03-05 16:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 27
202602-NM25-02736 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:23 | February | 2026 | 2026-03-03 16:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02737 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:35 | February | 2026 | 2026-03-03 15:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02738 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:53 | March | 2026 | 2026-03-05 14:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 29
202602-NM25-02739 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:45 | February | 2026 | 2026-03-03 16:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02740 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 09:54 | February | 2026 | 2026-03-03 16:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02741 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:06 | March | 2026 | 2026-03-25 15:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 2 | 5 | 2026-04-01 | 14
202602-NM25-02743 | GDL17 | Residencial | 16.51 | Period | 2026-02-27 10:08 | February | 2026 | 2026-03-03 13:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02744 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:20 | February | 2026 | 2026-03-03 14:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02746 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:28 | February | 2026 | 2026-03-10 07:59 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 33
202602-NM25-02748 | GDL17 | Comercial | 24 | Period | 2026-03-08 11:03 | March | 2026 | 2026-03-09 13:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 24
202602-NM25-02749 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:35 | February | 2026 | 2026-03-03 14:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02750 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:52 | March | 2026 | 2026-03-26 10:04 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-02751 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 10:14 | March | 2026 | 2026-03-11 09:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 23
202602-NM25-02752 | GDL17 | Residencial | 4.224 | Period | 2026-03-03 09:21 | March | 2026 | 2026-03-05 13:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-02753 | GDL17 | Residencial | 14.512 | Period | 2026-02-27 10:46 | February | 2026 | 2026-03-03 14:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02754 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 10:55 | February | 2026 | 2026-03-03 14:31 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02755 | GDL17 | Residencial | 15.89 | Period | 2026-02-27 11:17 | February | 2026 | 2026-03-03 10:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 33
202602-NM25-02756 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 12:57 | March | 2026 | 2026-03-23 14:19 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 6 | 8 | 2026-04-01 | 22
202602-NM25-02757 | GDL17 | Comercial | 22.8 | Period | 2026-02-28 08:55 | February | 2026 | 2026-03-04 09:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02759 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 07:53 | March | 2026 | 2026-03-24 12:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 9
202602-NM25-02763 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 11:15 | February | 2026 | 2026-03-05 14:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 33
202602-NM25-02764 | GDL17 | Residencial | 13.056 | Period | 2026-02-27 11:30 | February | 2026 | 2026-03-04 16:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02766 | GDL17 | Residencial | 7.6 | Period | 2026-02-27 11:34 | February | 2026 | 2026-03-03 14:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02767 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 13:39 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 12
202602-NM25-02768 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:03 | March | 2026 | 2026-03-12 15:47 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 29
202602-NM25-02769 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:52 | March | 2026 | 2026-03-11 13:08 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 29
202602-NM25-02771 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 11:42 | February | 2026 | 2026-03-03 11:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 33
202602-NM25-02773 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 11:51 | February | 2026 | 2026-03-03 14:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02774 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 11:54 | February | 2026 | 2026-03-05 10:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 33
202602-NM25-02775 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 11:56 | February | 2026 | 2026-03-03 14:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 33
202602-NM25-02776 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:01 | February | 2026 | 2026-03-04 12:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02777 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:03 | February | 2026 | 2026-03-16 10:04 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 16 | 0 | 2026-04-01 | 32
202602-NM25-02778 | GDL17 | Residencial | 23 | Period | 2026-02-27 12:07 | February | 2026 | 2026-03-03 09:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 32
202602-NM25-02780 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:21 | February | 2026 | 2026-03-03 16:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02781 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:15 | February | 2026 | 2026-03-05 14:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 32
202602-NM25-02782 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:18 | February | 2026 | 2026-03-03 09:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 32
202602-NM25-02783 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:47 | February | 2026 | 2026-03-03 13:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02784 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:28 | February | 2026 | 2026-03-03 16:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02786 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:08 | March | 2026 | 2026-03-05 09:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 28
202602-NM25-02787 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:38 | February | 2026 | 2026-03-03 13:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02788 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:37 | February | 2026 | 2026-03-03 15:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02792 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:47 | February | 2026 | 2026-03-04 14:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02793 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:48 | February | 2026 | 2026-03-04 09:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02794 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 07:58 | March | 2026 | 2026-03-09 13:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 28
202602-NM25-02795 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:52 | February | 2026 | 2026-03-12 08:00 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 32
202602-NM25-02798 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:55 | February | 2026 | 2026-03-03 08:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 32
202602-NM25-02799 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 12:57 | February | 2026 | 2026-03-03 15:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02800 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 16:08 | March | 2026 | 2026-03-30 12:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-02803 | GDL17 | Residencial | 5.76 | Period | 2026-03-26 11:13 | March | 2026 | 2026-04-01 14:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | April |  | 6 | 1 | 2026-04-01 | 6
202602-NM25-02804 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:37 | February | 2026 | 2026-03-05 08:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02805 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:20 | February | 2026 | 2026-03-05 10:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02807 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 09:23 | March | 2026 | 2026-03-30 10:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 7
202602-NM25-02809 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:20 | February | 2026 | 2026-03-17 14:39 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 18 | 0 | 2026-04-01 | 32
202602-NM25-02811 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 08:28 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202602-NM25-02812 | GDL17 | Residencial | 4.992 | Period | 2026-03-05 11:53 | March | 2026 | 2026-03-11 16:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 27
202602-NM25-02814 | GDL17 | Residencial | 11.44 | Period | 2026-02-27 13:34 | February | 2026 | 2026-03-03 11:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 32
202602-NM25-02816 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 13:51 | February | 2026 | 2026-03-04 09:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02818 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:05 | February | 2026 | 2026-03-05 14:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 32
202602-NM25-02819 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 17:16 | March | 2026 | 2026-03-20 15:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 12
202602-NM25-02821 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:26 | February | 2026 | 2026-03-04 13:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02833 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:23 | February | 2026 | 2026-03-03 15:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02835 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 19:15 | March | 2026 | 2026-03-30 13:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-02836 | GDL17 | Residencial | 3.8 | Period | 2026-03-12 15:37 | March | 2026 | 2026-03-17 13:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 19
202602-NM25-02837 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 13:20 | March | 2026 | 2026-03-05 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 28
202602-NM25-02838 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:38 | February | 2026 | 2026-03-09 11:10 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 32
202602-NM25-02842 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:41 | February | 2026 | 2026-03-03 10:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 32
202602-NM25-02844 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:58 | February | 2026 | 2026-03-04 08:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02845 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 14:57 | February | 2026 | 2026-03-03 13:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02847 | GDL17 | Residencial | 14.2 | Period | 2026-02-27 15:07 | February | 2026 | 2026-03-11 15:48 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 12 | 0 | 2026-04-01 | 32
202602-NM25-02848 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:06 | March | 2026 | 2026-03-05 13:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 28
202602-NM25-02849 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:26 | February | 2026 | 2026-03-06 15:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 32
202602-NM25-02850 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:21 | February | 2026 | 2026-03-04 14:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02852 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:31 | February | 2026 | 2026-03-05 14:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 32
202602-NM25-02853 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:33 | February | 2026 | 2026-03-03 15:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02854 | GDL17 | Residencial | 7.462 | Period | 2026-02-27 15:32 | February | 2026 | 2026-03-03 14:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02855 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 14:41 | March | 2026 | 2026-03-17 08:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 18
202602-NM25-02856 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:36 | February | 2026 | 2026-03-05 15:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 32
202602-NM25-02857 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:51 | March | 2026 | 2026-03-18 14:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202602-NM25-02858 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:42 | February | 2026 | 2026-03-03 16:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02859 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:52 | February | 2026 | 2026-03-12 13:19 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 13 | 0 | 2026-04-01 | 32
202602-NM25-02860 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:46 | February | 2026 | 2026-03-03 16:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02863 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:52 | February | 2026 | 2026-03-06 14:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 32
202602-NM25-02864 | GDL17 | Residencial | 7.6 | Period | 2026-02-27 15:59 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 32
202602-NM25-02865 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 15:56 | February | 2026 | 2026-03-03 16:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02866 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:02 | February | 2026 | 2026-03-04 08:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02869 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:06 | February | 2026 | 2026-03-03 16:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 32
202602-NM25-02870 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:13 | February | 2026 |  |  | Study | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 32
202602-NM25-02871 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 16:20 | February | 2026 | 2026-03-04 08:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02873 | GDL17 | Residencial | 3.8 | Period | 2026-03-03 11:53 | March | 2026 | 2026-03-06 10:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-02874 | GDL17 | Residencial | 8.26 | Period | 2026-02-27 16:46 | February | 2026 | 2026-03-04 08:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02875 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:11 | March | 2026 | 2026-03-13 14:51 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 27
202602-NM25-02877 | GDL17 | Residencial | 8 | Period | 2026-03-19 15:42 | March | 2026 | 2026-03-23 09:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 12
202602-NM25-02878 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 17:00 | February | 2026 | 2026-03-04 10:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02879 | GDL17 | Residencial | 18 | Period | 2026-03-12 23:37 | March | 2026 | 2026-03-16 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 19
202602-NM25-02880 | GDL17 | Residencial | 11.5 | Period | 2026-02-27 17:19 | February | 2026 | 2026-03-04 09:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 32
202602-NM25-02881 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 16:32 | March | 2026 | 2026-03-30 13:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202602-NM25-02883 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:04 | March | 2026 | 2026-03-25 14:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 9
202602-NM25-02884 | GDL17 | Residencial | 25 | Period | 2026-03-13 11:18 | March | 2026 | 2026-03-16 14:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 19
202602-NM25-02885 | GDL17 | Residencial | 12 | Period | 2026-03-02 17:27 | March | 2026 | 2026-03-05 09:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 29
202602-NM25-02886 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 12:32 | March | 2026 | 2026-03-30 09:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 7
202602-NM25-02887 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 19:09 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 8
202602-NM25-02888 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 17:41 | March | 2026 | 2026-03-26 10:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 8
202602-NM25-02889 | GDL17 | Residencial | 12 | Period | 2026-03-03 11:37 | March | 2026 | 2026-03-09 08:35 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 29
202602-NM25-02892 | GDL17 | Residencial | 11.4 | Period | 2026-03-05 10:44 | March | 2026 | 2026-03-09 11:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 27
202602-NM25-02896 | GDL17 | Residencial | 3.66 | Period | 2026-03-12 11:34 | March | 2026 | 2026-03-16 09:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 20
202603-NM25-00001 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 11:27 | March | 2026 | 2026-03-11 14:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 2 | 4 | 2026-04-01 | 27
202603-NM25-00002 | GDL17 | Residencial | 5 | Period | 2026-03-02 19:53 | March | 2026 | 2026-03-05 09:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00003 | GDL17 | Residencial | 8 | Period | 2026-03-02 20:13 | March | 2026 | 2026-03-05 09:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00004 | GDL17 | Comercial | 5.3 | Period | 2026-03-09 08:55 | March | 2026 | 2026-03-17 09:46 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00005 | GDL17 | Comercial | 5.3 | Period | 2026-03-09 08:57 | March | 2026 | 2026-03-17 09:49 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00006 | GDL17 | Comercial | 21.8 | Period | 2026-03-09 08:59 | March | 2026 | 2026-03-17 09:55 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00007 | GDL17 | Comercial | 9.8 | Period | 2026-03-09 09:01 | March | 2026 | 2026-03-17 09:58 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00008 | GDL17 | Comercial | 5.3 | Period | 2026-03-09 09:03 | March | 2026 | 2026-03-17 09:58 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00009 | GDL17 | Comercial | 5.3 | Period | 2026-03-09 09:05 | March | 2026 | 2026-03-17 09:59 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00010 | GDL17 | Comercial | 21.8 | Period | 2026-03-09 09:06 | March | 2026 | 2026-03-26 09:40 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 9 | 8 | 2026-04-01 | 23
202603-NM25-00011 | GDL17 | Comercial | 5.3 | Period | 2026-03-09 09:08 | March | 2026 | 2026-03-17 10:00 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00012 | GDL17 | Comercial | 21.8 | Period | 2026-03-09 09:09 | March | 2026 | 2026-03-17 10:00 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00013 | GDL17 | Comercial | 5.3 | Period | 2026-03-09 14:30 | March | 2026 | 2026-03-17 10:00 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 22
202603-NM25-00014 | GDL17 | Comercial | 5.3 | Period | 2026-03-05 09:24 | March | 2026 | 2026-03-17 09:42 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 27
202603-NM25-00015 | GDL17 | Comercial | 5.3 | Period | 2026-03-05 09:28 | March | 2026 | 2026-03-17 09:39 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 27
202603-NM25-00016 | GDL17 | Comercial | 5.3 | Period | 2026-03-05 09:37 | March | 2026 | 2026-03-17 09:45 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 27
202603-NM25-00017 | GDL17 | Comercial | 5.3 | Period | 2026-03-05 09:47 | March | 2026 | 2026-03-17 09:54 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 27
202603-NM25-00018 | GDL17 | Comercial | 5.3 | Period | 2026-03-04 14:30 | March | 2026 | 2026-03-17 09:37 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 27
202603-NM25-00019 | GDL17 | Comercial | 5.3 | Period | 2026-03-04 13:19 | March | 2026 | 2026-03-17 09:36 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 27
202603-NM25-00020 | GDL17 | Comercial | 5.3 | Period | 2026-03-04 13:21 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 27
202603-NM25-00021 | GDL17 | Comercial | 5.3 | Period | 2026-03-04 13:23 | March | 2026 | 2026-03-17 09:37 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 27
202603-NM25-00022 | GDL17 | Comercial | 5.3 | Period | 2026-03-04 13:25 | March | 2026 | 2026-03-17 09:40 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 27
202603-NM25-00024 | GDL17 | Comercial | 5.3 | Period | 2026-03-04 10:35 | March | 2026 | 2026-03-30 09:22 | 26 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 26 | 0 | 2026-04-01 | 28
202603-NM25-00025 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 07:19 | March | 2026 | 2026-03-05 13:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 30
202603-NM25-00026 | GDL17 | Comercial | 5.3 | Period | 2026-03-04 09:14 | March | 2026 | 2026-03-17 09:36 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 28
202603-NM25-00027 | GDL17 | Comercial | 5.3 | Period | 2026-03-04 09:12 | March | 2026 | 2026-03-17 09:36 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 13 | 0 | 2026-04-01 | 28
202603-NM25-00029 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 13:38 | March | 2026 | 2026-03-20 11:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 1 | 1 | 2026-04-01 | 13
202603-NM25-00030 | GDL17 | Residencial | 3.8 | Period | 2026-03-09 11:42 | March | 2026 | 2026-03-11 14:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 23
202603-NM25-00033 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:19 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 8
202603-NM25-00039 | GDL17 | Residencial | 7.6 | Period | 2026-03-02 09:02 | March | 2026 | 2026-03-05 13:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 30
202603-NM25-00040 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 11:19 | March | 2026 | 2026-03-26 14:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 13
202603-NM25-00041 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 07:24 | March | 2026 | 2026-03-05 13:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00042 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:33 | March | 2026 | 2026-03-06 15:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 29
202603-NM25-00043 | GDL17 | Residencial | 3.84 | Period | 2026-03-03 09:21 | March | 2026 | 2026-03-11 14:57 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 29
202603-NM25-00044 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 08:53 | March | 2026 | 2026-03-09 15:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 28
202603-NM25-00045 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:45 | March | 2026 | 2026-03-26 13:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 14
202603-NM25-00046 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 11:35 | March | 2026 | 2026-04-08 16:03 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 13 | 0 | 2026-04-01 | 6
202603-NM25-00048 | GDL17 | Residencial | 3.84 | Period | 2026-03-03 13:49 | March | 2026 | 2026-03-11 07:50 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 28
202603-NM25-00049 | GDL17 | Residencial | 7.6 | Period | 2026-03-02 09:46 | March | 2026 | 2026-03-04 13:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 30
202603-NM25-00050 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 09:40 | March | 2026 | 2026-03-05 15:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 30
202603-NM25-00051 | GDL17 | Residencial | 3.8 | Period | 2026-03-02 09:44 | March | 2026 | 2026-03-04 12:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 30
202603-NM25-00052 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:19 | March | 2026 | 2026-03-11 13:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 1 | 1 | 2026-04-01 | 23
202603-NM25-00053 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:02 | March | 2026 | 2026-03-05 10:32 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 30
202603-NM25-00054 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:05 | March | 2026 | 2026-03-11 10:44 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 9 | 0 | 2026-04-01 | 30
202603-NM25-00056 | GDL17 | Residencial | 3.84 | Period | 2026-03-04 14:04 | March | 2026 | 2026-03-05 16:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00057 | GDL17 | Residencial | 7.6 | Period | 2026-03-09 09:39 | March | 2026 | 2026-03-09 14:06 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 0 | 0 | 2026-04-01 | 23
202603-NM25-00058 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:22 | March | 2026 | 2026-03-16 14:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00059 | GDL17 | Residencial | 12 | Period | 2026-03-04 11:47 | March | 2026 | 2026-03-09 09:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 4 | 1 | 2026-04-01 | 28
202603-NM25-00060 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:21 | March | 2026 | 2026-03-06 13:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00061 | GDL17 | Residencial | 9 | Period | 2026-03-16 14:23 | March | 2026 | 2026-03-17 15:11 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-00062 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 10:39 | March | 2026 | 2026-03-16 17:14 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 15 | 0 | 2026-04-01 | 30
202603-NM25-00063 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:06 | March | 2026 | 2026-03-18 15:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-00064 | GDL17 | Residencial | 8 | Period | 2026-03-19 13:10 | March | 2026 | 2026-03-20 15:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-00065 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 10:50 | March | 2026 | 2026-03-06 14:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00066 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 13:04 | March | 2026 | 2026-03-18 09:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-00067 | GDL17 | Residencial | 8.6 | Period | 2026-03-02 10:58 | March | 2026 | 2026-03-04 09:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 30
202603-NM25-00068 | GDL17 | Comercial | 2.304 | Period | 2026-03-07 14:16 | March | 2026 | 2026-03-09 13:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 24
202603-NM25-00070 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 08:27 | March | 2026 | 2026-03-05 09:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00071 | GDL17 | Residencial | 10.022 | Period | 2026-03-02 11:06 | March | 2026 | 2026-03-04 13:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 30
202603-NM25-00072 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:36 | March | 2026 | 2026-03-05 09:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 30
202603-NM25-00073 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:32 | March | 2026 | 2026-03-04 13:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 30
202603-NM25-00074 | GDL17 | Residencial | 14.208 | Period | 2026-03-02 11:42 | March | 2026 | 2026-04-22 11:19 | 51 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 50 | 0 | 2026-04-01 | 30
202603-NM25-00076 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 11:53 | March | 2026 | 2026-03-11 10:29 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 30
202603-NM25-00079 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 12:04 | March | 2026 | 2026-03-06 09:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00080 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:44 | March | 2026 | 2026-03-13 11:27 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 28
202603-NM25-00082 | GDL17 | Residencial | 3.8 | Period | 2026-03-17 08:08 | March | 2026 | 2026-03-18 16:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-00083 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:26 | March | 2026 | 2026-03-13 14:35 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 27
202603-NM25-00084 | GDL17 | Residencial | 8 | Period | 2026-03-04 17:34 | March | 2026 | 2026-03-09 08:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 27
202603-NM25-00085 | GDL17 | Residencial | 7.6 | Period | 2026-03-09 14:06 | March | 2026 | 2026-03-09 15:45 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 22
202603-NM25-00087 | GDL17 | Residencial | 15.2 | Period | 2026-03-09 08:41 | March | 2026 | 2026-03-09 11:00 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 0 | 0 | 2026-04-01 | 23
202603-NM25-00088 | GDL17 | Residencial | 3.84 | Period | 2026-03-04 07:53 | March | 2026 | 2026-03-09 10:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 28
202603-NM25-00089 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:07 | March | 2026 | 2026-03-11 07:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 26
202603-NM25-00090 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 08:49 | March | 2026 | 2026-03-06 10:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00091 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 11:49 | March | 2026 | 2026-03-04 15:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00092 | GDL17 | Comercial | 11.5 | Period | 2026-03-30 12:31 | March | 2026 | 2026-04-30 15:08 | 31 | Net Metering | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 31 | 0 | 2026-04-01 | 1
202603-NM25-00093 | GDL17 | Residencial | 3.8 | Period | 2026-03-09 13:17 | March | 2026 | 2026-03-10 10:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00094 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:42 | March | 2026 | 2026-03-04 09:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00095 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 08:08 | March | 2026 | 2026-03-11 09:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 28
202603-NM25-00096 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:44 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 29
202603-NM25-00097 | GDL17 | Residencial | 3.84 | Period | 2026-03-19 14:28 | March | 2026 | 2026-03-20 15:20 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-00098 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 13:53 | March | 2026 | 2026-03-04 14:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00099 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:26 | March | 2026 | 2026-03-04 14:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00100 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 10:23 | March | 2026 | 2026-03-25 14:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-00101 | GDL17 | Residencial | 19.2 | Period | 2026-03-04 14:44 | March | 2026 | 2026-03-05 15:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00102 | GDL17 | Residencial | 11.492 | Period | 2026-03-02 14:19 | March | 2026 | 2026-03-04 14:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00103 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:35 | March | 2026 | 2026-03-05 15:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00104 | GDL17 | Residencial | 9.292 | Period | 2026-03-02 14:30 | March | 2026 | 2026-03-04 14:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00106 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 14:40 | March | 2026 | 2026-04-06 08:44 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 35 | 0 | 2026-04-01 | 29
202603-NM25-00107 | GDL17 | Residencial | 16 | Period | 2026-03-02 18:50 | March | 2026 | 2026-03-05 09:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00108 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:02 | March | 2026 | 2026-03-04 13:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00111 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:17 | March | 2026 | 2026-03-04 14:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00112 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:10 | March | 2026 | 2026-03-09 15:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 27
202603-NM25-00113 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:36 | March | 2026 | 2026-03-06 08:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00114 | GDL17 | Residencial | 8.09 | Period | 2026-03-02 15:16 | March | 2026 | 2026-03-04 13:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00115 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 13:29 | March | 2026 | 2026-04-22 07:51 | 47 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 47 | 0 | 2026-04-01 | 25
202603-NM25-00116 | GDL17 | Residencial | 23 | Period | 2026-03-02 15:26 | March | 2026 | 2026-03-04 14:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00118 | GDL17 | Residencial | 5.076 | Period | 2026-03-02 15:45 | March | 2026 | 2026-03-04 14:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00119 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:46 | March | 2026 | 2026-03-05 16:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00120 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 17:20 | March | 2026 | 2026-03-30 09:53 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 26 | 0 | 2026-04-01 | 28
202603-NM25-00121 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 07:53 | March | 2026 | 2026-04-13 12:39 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | April |  | 14 | 2 | 2026-04-01 | 2
202603-NM25-00123 | GDL17 | Residencial | 5.076 | Period | 2026-03-02 15:56 | March | 2026 | 2026-03-04 14:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00124 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:05 | March | 2026 | 2026-03-04 13:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00125 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 15:58 | March | 2026 | 2026-03-09 08:37 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 29
202603-NM25-00126 | GDL17 | Residencial | 7.098 | Period | 2026-03-02 16:07 | March | 2026 | 2026-03-04 14:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00127 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:07 | March | 2026 | 2026-03-09 09:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 29
202603-NM25-00128 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:14 | March | 2026 | 2026-03-05 09:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00129 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:12 | March | 2026 | 2026-03-06 13:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 28
202603-NM25-00130 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:16 | March | 2026 | 2026-03-10 15:42 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 8 | 0 | 2026-04-01 | 29
202603-NM25-00131 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:26 | March | 2026 | 2026-03-06 10:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 29
202603-NM25-00132 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:26 | March | 2026 | 2026-03-10 08:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 29
202603-NM25-00133 | GDL17 | Residencial | 8 | Period | 2026-03-04 17:55 | March | 2026 | 2026-03-06 09:12 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00134 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:35 | March | 2026 | 2026-03-11 11:07 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 9 | 0 | 2026-04-01 | 29
202603-NM25-00135 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:48 | March | 2026 | 2026-03-20 13:57 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 18 | 0 | 2026-04-01 | 29
202603-NM25-00136 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:43 | March | 2026 | 2026-03-16 17:24 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 14 | 0 | 2026-04-01 | 29
202603-NM25-00137 | GDL17 | Residencial | 23 | Period | 2026-03-02 17:01 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | MAYAGUEZ | March |  |  |  | 2026-04-01 | 29
202603-NM25-00138 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 16:51 | March | 2026 | 2026-03-05 13:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00139 | GDL17 | Residencial | 23 | Period | 2026-03-02 17:01 | March | 2026 | 2026-04-22 15:15 | 51 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 51 | 0 | 2026-04-01 | 29
202603-NM25-00140 | GDL17 | Residencial | 14 | Period | 2026-03-02 17:08 | March | 2026 | 2026-03-05 15:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00141 | GDL17 | Residencial | 8 | Period | 2026-03-03 13:06 | March | 2026 | 2026-03-05 09:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00142 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 17:40 | March | 2026 | 2026-03-05 09:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00143 | GDL17 | Residencial | 15 | Period | 2026-03-02 20:13 | March | 2026 | 2026-03-11 15:55 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 9 | 0 | 2026-04-01 | 29
202603-NM25-00144 | GDL17 | Residencial | 11.5 | Period | 2026-03-02 18:00 | March | 2026 | 2026-03-05 09:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00146 | GDL17 | Residencial | 5.376 | Period | 2026-03-23 16:10 | March | 2026 | 2026-03-31 09:41 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 8
202603-NM25-00147 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:19 | March | 2026 | 2026-03-30 15:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-00148 | GDL17 | Residencial | 7.6 | Period | 2026-03-04 05:48 | March | 2026 | 2026-03-05 14:12 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00149 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:59 | March | 2026 | 2026-03-05 09:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00152 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:07 | March | 2026 | 2026-03-05 09:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00154 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:20 | March | 2026 | 2026-03-06 10:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00155 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:30 | March | 2026 | 2026-03-17 16:49 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 29
202603-NM25-00156 | GDL17 | Residencial | 12 | Period | 2026-03-03 22:14 | March | 2026 | 2026-04-30 08:10 | 57 | Net Metering | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 57 | 0 | 2026-04-01 | 28
202603-NM25-00157 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 08:41 | March | 2026 | 2026-03-05 16:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00158 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 09:05 | March | 2026 | 2026-03-05 09:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00159 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 12:44 | March | 2026 | 2026-03-12 09:01 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 28
202603-NM25-00160 | GDL17 | Residencial | 11.4 | Period | 2026-03-11 11:00 | March | 2026 | 2026-03-30 13:31 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 2 | 5 | 14 | 2026-04-01 | 21
202603-NM25-00162 | GDL17 | Residencial | 8.072 | Period | 2026-03-03 08:58 | March | 2026 | 2026-03-05 09:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00163 | GDL17 | Residencial | 5.366 | Period | 2026-03-03 08:59 | March | 2026 | 2026-03-05 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00164 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 08:43 | March | 2026 | 2026-03-09 08:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 27
202603-NM25-00165 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 08:10 | March | 2026 | 2026-03-17 13:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 16
202603-NM25-00166 | GDL17 | Residencial | 8.456 | Period | 2026-03-03 09:18 | March | 2026 | 2026-03-05 09:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00167 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 08:26 | March | 2026 | 2026-03-11 08:34 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 26
202603-NM25-00168 | GDL17 | Residencial | 4.608 | Period | 2026-03-05 11:32 | March | 2026 | 2026-03-06 13:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00169 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 09:26 | March | 2026 | 2026-03-05 09:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00171 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 09:42 | March | 2026 | 2026-03-10 14:42 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 29
202603-NM25-00174 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:45 | March | 2026 | 2026-03-05 13:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00175 | GDL17 | Residencial | 9.516 | Period | 2026-03-11 07:49 | March | 2026 | 2026-03-13 15:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 1 | 1 | 2026-04-01 | 21
202603-NM25-00177 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 07:20 | March | 2026 | 2026-03-10 15:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 27
202603-NM25-00179 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:07 | March | 2026 | 2026-03-06 13:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 29
202603-NM25-00180 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:09 | March | 2026 | 2026-03-05 08:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00181 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:18 | March | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 29
202603-NM25-00182 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:21 | March | 2026 | 2026-03-05 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00183 | GDL17 | Residencial | 11.529 | Period | 2026-03-07 14:42 | March | 2026 | 2026-03-09 11:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 24
202603-NM25-00184 | GDL17 | Residencial | 11.4 | Period | 2026-03-05 10:44 | March | 2026 | 2026-03-11 07:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 5 | 1 | 2026-04-01 | 27
202603-NM25-00186 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:58 | March | 2026 | 2026-03-06 09:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00187 | GDL17 | Residencial | 8 | Period | 2026-03-03 13:36 | March | 2026 | 2026-03-04 10:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00190 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:42 | March | 2026 | 2026-03-11 16:17 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 29
202603-NM25-00191 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:51 | March | 2026 | 2026-03-05 11:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00192 | GDL17 | Residencial | 6.588 | Period | 2026-03-03 13:45 | March | 2026 | 2026-04-22 15:11 | 50 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 50 | 2 | 2026-04-01 | 28
202603-NM25-00193 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:03 | March | 2026 | 2026-03-04 12:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00194 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 10:59 | March | 2026 | 2026-03-16 10:13 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 13 | 0 | 2026-04-01 | 29
202603-NM25-00195 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 10:27 | March | 2026 | 2026-03-17 08:58 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 12 | 0 | 2026-04-01 | 28
202603-NM25-00196 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:19 | March | 2026 | 2026-03-11 09:00 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 29
202603-NM25-00199 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:32 | March | 2026 | 2026-03-04 12:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00200 | GDL17 | Residencial | 7.68 | Period | 2026-03-17 09:56 | March | 2026 | 2026-03-23 13:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-00201 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:24 | March | 2026 | 2026-03-05 12:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 29
202603-NM25-00202 | GDL17 | Residencial | 5 | Period | 2026-03-04 21:05 | March | 2026 | 2026-03-06 09:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00203 | GDL17 | Residencial | 9 | Period | 2026-03-03 13:33 | March | 2026 | 2026-03-05 08:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00204 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:33 | March | 2026 | 2026-03-12 09:42 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 9 | 0 | 2026-04-01 | 29
202603-NM25-00205 | GDL17 | Residencial | 10.43 | Period | 2026-03-03 11:34 | March | 2026 | 2026-03-04 13:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00206 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 16:15 | March | 2026 | 2026-04-02 09:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-00207 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:45 | March | 2026 | 2026-03-04 13:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00208 | GDL17 | Residencial | 8.052 | Period | 2026-03-03 11:51 | March | 2026 | 2026-03-04 13:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00209 | GDL17 | Residencial | 4.992 | Period | 2026-03-03 11:45 | March | 2026 | 2026-03-11 10:56 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 29
202603-NM25-00210 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 11:54 | March | 2026 | 2026-03-04 13:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 29
202603-NM25-00211 | GDL17 | Residencial | 7.6 | Period | 2026-03-29 17:01 | March | 2026 | 2026-04-09 13:39 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 11 | 0 | 2026-04-01 | 2
202603-NM25-00212 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:38 | March | 2026 | 2026-03-06 14:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 26
202603-NM25-00213 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:03 | March | 2026 | 2026-03-04 13:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00214 | GDL17 | Residencial | 9.6 | Period | 2026-03-03 12:13 | March | 2026 | 2026-03-04 13:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00215 | GDL17 | Residencial | 11.51 | Period | 2026-03-03 12:15 | March | 2026 | 2026-03-04 13:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00216 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:18 | March | 2026 | 2026-03-12 09:52 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 9 | 0 | 2026-04-01 | 28
202603-NM25-00219 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 10:46 | March | 2026 | 2026-03-06 10:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00220 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:31 | March | 2026 | 2026-03-06 09:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 28
202603-NM25-00221 | GDL17 | Residencial | 15.2 | Period | 2026-03-03 12:27 | March | 2026 | 2026-03-05 13:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00222 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:29 | March | 2026 | 2026-03-05 12:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00223 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:34 | March | 2026 | 2026-03-06 09:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 28
202603-NM25-00225 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:12 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 14
202603-NM25-00226 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 12:57 | March | 2026 | 2026-03-05 08:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00227 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:32 | March | 2026 | 2026-03-30 12:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-00228 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 13:14 | March | 2026 | 2026-03-04 13:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00231 | GDL17 | Residencial | 7.6 | Period | 2026-03-13 15:11 | March | 2026 | 2026-03-17 09:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-00233 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:55 | March | 2026 | 2026-03-18 12:53 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 21
202603-NM25-00234 | GDL17 | Residencial | 7.6 | Period | 2026-03-04 10:02 | March | 2026 | 2026-04-02 13:20 | 29 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | April |  | 29 | 2 | 2026-04-01 | 28
202603-NM25-00236 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 13:32 | March | 2026 | 2026-03-09 10:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 27
202603-NM25-00238 | GDL17 | Residencial | 8.064 | Period | 2026-03-03 14:22 | March | 2026 | 2026-03-04 15:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00240 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 14:40 | March | 2026 | 2026-03-09 15:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 28
202603-NM25-00241 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:49 | March | 2026 | 2026-03-05 15:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00242 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 12:30 | March | 2026 | 2026-03-09 11:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 27
202603-NM25-00243 | GDL17 | Residencial | 23 | Period | 2026-03-09 15:11 | March | 2026 | 2026-03-16 17:36 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00244 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 07:44 | March | 2026 | 2026-03-09 15:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 28
202603-NM25-00246 | GDL17 | Residencial | 8 | Period | 2026-03-05 14:27 | March | 2026 | 2026-03-06 14:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 26
202603-NM25-00247 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 16:23 | March | 2026 | 2026-03-09 07:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 26
202603-NM25-00248 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:06 | March | 2026 | 2026-03-11 15:39 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 28
202603-NM25-00251 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:39 | March | 2026 | 2026-03-04 13:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00252 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 07:28 | March | 2026 | 2026-04-22 13:32 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 35 | 0 | 2026-04-01 | 14
202603-NM25-00253 | GDL17 | Residencial | 6.612 | Period | 2026-03-03 15:26 | March | 2026 | 2026-03-04 13:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 28
202603-NM25-00254 | GDL17 | Residencial | 13.44 | Period | 2026-03-03 16:02 | March | 2026 | 2026-03-11 15:43 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 28
202603-NM25-00255 | GDL17 | Residencial | 7.6 | Period | 2026-03-03 15:48 | March | 2026 | 2026-03-11 10:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 28
202603-NM25-00256 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:03 | March | 2026 | 2026-03-18 09:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 2 | 4 | 2 | 2026-04-01 | 20
202603-NM25-00258 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 15:40 | March | 2026 | 2026-03-05 10:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 28
202603-NM25-00259 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:47 | March | 2026 | 2026-03-09 14:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 26
202603-NM25-00263 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:07 | March | 2026 | 2026-03-13 07:48 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 9 | 0 | 2026-04-01 | 28
202603-NM25-00264 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:23 | March | 2026 | 2026-03-09 13:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 28
202603-NM25-00267 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:21 | March | 2026 | 2026-04-24 13:24 | 52 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | April |  | 52 | 0 | 2026-04-01 | 28
202603-NM25-00268 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:32 | March | 2026 | 2026-03-10 08:45 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 28
202603-NM25-00269 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 16:51 | March | 2026 | 2026-03-13 10:45 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 28
202603-NM25-00270 | GDL17 | Residencial | 8 | Period | 2026-03-04 17:07 | March | 2026 | 2026-03-06 09:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00272 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 17:10 | March | 2026 | 2026-03-05 15:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 1 | 1 | 2026-04-01 | 28
202603-NM25-00273 | GDL17 | Residencial | 12 | Period | 2026-03-04 21:10 | March | 2026 | 2026-03-10 15:41 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 27
202603-NM25-00274 | GDL17 | Residencial | 11.5 | Period | 2026-03-03 17:34 | March | 2026 | 2026-03-10 15:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 28
202603-NM25-00277 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:28 | March | 2026 | 2026-03-25 12:44 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 21 | 0 | 2026-04-01 | 27
202603-NM25-00279 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:40 | March | 2026 | 2026-04-02 07:48 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 8 | 0 | 2026-04-01 | 7
202603-NM25-00280 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 14:23 | March | 2026 | 2026-03-31 14:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-00282 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 14:53 | March | 2026 | 2026-03-18 17:39 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 14 | 0 | 2026-04-01 | 27
202603-NM25-00283 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:11 | March | 2026 | 2026-03-06 09:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00284 | GDL17 | Residencial | 8 | Period | 2026-03-04 01:11 | March | 2026 | 2026-03-10 09:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 28
202603-NM25-00286 | GDL17 | Residencial | 11.4 | Period | 2026-03-09 10:55 | March | 2026 | 2026-03-17 14:22 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 23
202603-NM25-00287 | GDL17 | Residencial | 8 | Period | 2026-03-04 08:31 | March | 2026 | 2026-03-09 08:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 28
202603-NM25-00289 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:40 | March | 2026 | 2026-03-06 13:35 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 26
202603-NM25-00292 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 08:35 | March | 2026 | 2026-03-11 12:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 28
202603-NM25-00294 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 09:42 | March | 2026 | 2026-03-06 13:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00295 | GDL17 | Residencial | 3.84 | Period | 2026-03-05 11:34 | March | 2026 | 2026-03-06 16:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00298 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:39 | March | 2026 | 2026-03-06 09:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 27
202603-NM25-00299 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 09:33 | March | 2026 | 2026-03-09 09:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 28
202603-NM25-00300 | GDL17 | Residencial | 6.528 | Period | 2026-03-04 10:06 | March | 2026 | 2026-03-12 14:54 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 28
202603-NM25-00302 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 08:56 | March | 2026 | 2026-03-10 15:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 26
202603-NM25-00304 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:26 | March | 2026 | 2026-03-09 12:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 27
202603-NM25-00305 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 09:05 | March | 2026 | 2026-03-11 10:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 27
202603-NM25-00306 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 10:08 | March | 2026 | 2026-03-09 13:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 28
202603-NM25-00307 | GDL17 | Residencial | 11.96 | Period | 2026-03-04 10:08 | March | 2026 | 2026-03-09 16:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 28
202603-NM25-00308 | GDL17 | Residencial | 7.6 | Period | 2026-03-09 15:59 | March | 2026 | 2026-03-11 13:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00309 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 10:08 | March | 2026 | 2026-03-09 13:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 28
202603-NM25-00310 | GDL17 | Residencial | 3.8 | Period | 2026-03-06 11:36 | March | 2026 | 2026-03-11 11:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 26
202603-NM25-00312 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 09:26 | March | 2026 | 2026-03-30 10:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-00315 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:46 | March | 2026 | 2026-03-30 12:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-00316 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 11:07 | March | 2026 | 2026-04-27 10:38 | 54 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 54 | 0 | 2026-04-01 | 28
202603-NM25-00317 | GDL17 | Residencial | 8.832 | Period | 2026-03-24 13:53 | March | 2026 | 2026-03-30 09:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-00318 | GDL17 | Residencial | 7.296 | Period | 2026-03-04 10:49 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 28
202603-NM25-00319 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:34 | March | 2026 | 2026-03-23 13:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-00320 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:55 | March | 2026 | 2026-03-27 09:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-00321 | GDL17 | Residencial | 7.6 | Period | 2026-03-11 07:56 | March | 2026 | 2026-03-17 16:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00322 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 07:37 | March | 2026 | 2026-03-06 15:14 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 26
202603-NM25-00323 | GDL17 | Residencial | 4.224 | Period | 2026-03-09 16:06 | March | 2026 | 2026-03-10 14:21 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00324 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 11:29 | March | 2026 | 2026-03-13 08:51 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 9 | 0 | 2026-04-01 | 28
202603-NM25-00325 | GDL17 | Residencial | 8.382 | Period | 2026-03-04 11:36 | March | 2026 | 2026-03-09 16:03 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 28
202603-NM25-00326 | GDL17 | Residencial | 8 | Period | 2026-03-17 19:21 | March | 2026 | 2026-03-18 14:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-00328 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 11:53 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 28
202603-NM25-00330 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 12:10 | March | 2026 | 2026-03-09 08:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 27
202603-NM25-00331 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 09:37 | March | 2026 | 2026-03-30 10:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-00332 | GDL17 | Residencial | 12 | Period | 2026-03-04 17:04 | March | 2026 | 2026-03-06 07:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00333 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 13:02 | March | 2026 | 2026-03-12 10:26 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 27
202603-NM25-00334 | GDL17 | Residencial | 5.6 | Period | 2026-03-17 14:10 | March | 2026 | 2026-03-20 10:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 14
202603-NM25-00335 | GDL17 | Residencial | 8.23 | Period | 2026-03-04 13:41 | March | 2026 | 2026-03-09 16:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 5 | 0 | 2026-04-01 | 27
202603-NM25-00337 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:53 | March | 2026 | 2026-03-16 13:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-00338 | GDL17 | Residencial | 9.216 | Period | 2026-03-07 14:44 | March | 2026 | 2026-03-17 07:40 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 24
202603-NM25-00339 | GDL17 | Residencial | 10.858 | Period | 2026-03-04 13:50 | March | 2026 | 2026-03-06 12:52 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00341 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:55 | March | 2026 | 2026-03-10 09:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00344 | GDL17 | Residencial | 11.4 | Period | 2026-03-10 17:09 | March | 2026 | 2026-03-19 15:14 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 21
202603-NM25-00348 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 08:50 | March | 2026 | 2026-03-13 11:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 22
202603-NM25-00349 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 07:47 | March | 2026 | 2026-04-20 10:45 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 41 | 0 | 2026-04-01 | 22
202603-NM25-00351 | GDL17 | Residencial | 14.572 | Period | 2026-03-04 15:01 | March | 2026 | 2026-03-05 16:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00353 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 17:19 | March | 2026 | 2026-03-09 13:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 25
202603-NM25-00354 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:11 | March | 2026 | 2026-03-06 13:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00355 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:31 | March | 2026 | 2026-03-27 07:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-00356 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 16:30 | March | 2026 | 2026-03-16 16:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-00357 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 15:22 | March | 2026 | 2026-03-09 11:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 27
202603-NM25-00358 | GDL17 | Residencial | 4.116 | Period | 2026-03-04 15:43 | March | 2026 | 2026-03-06 13:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00359 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:01 | March | 2026 | 2026-03-16 10:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-00360 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 09:54 | March | 2026 | 2026-03-17 08:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00361 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 16:18 | March | 2026 | 2026-03-06 13:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00363 | GDL17 | Residencial | 12 | Period | 2026-03-08 08:23 | March | 2026 | 2026-03-12 09:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 24
202603-NM25-00364 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:07 | March | 2026 | 2026-04-14 07:42 | 27 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | April |  | 27 | 0 | 2026-04-01 | 13
202603-NM25-00365 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:10 | March | 2026 | 2026-03-31 07:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-00367 | GDL17 | Residencial | 12.976 | Period | 2026-03-04 16:18 | March | 2026 | 2026-03-05 16:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00369 | GDL17 | Residencial | 6.954 | Period | 2026-03-04 16:36 | March | 2026 | 2026-03-06 09:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00371 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 15:57 | March | 2026 | 2026-03-20 16:14 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 21
202603-NM25-00372 | GDL17 | Residencial | 5.124 | Period | 2026-03-04 17:24 | March | 2026 | 2026-03-06 09:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00373 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 11:53 | March | 2026 | 2026-03-19 08:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 16
202603-NM25-00378 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 11:30 | March | 2026 | 2026-03-25 14:05 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 9 | 0 | 2026-04-01 | 16
202603-NM25-00379 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 17:30 | March | 2026 | 2026-04-16 09:06 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 23 | 0 | 2026-04-01 | 8
202603-NM25-00381 | GDL17 | Residencial | 11.5 | Period | 2026-03-04 18:50 | March | 2026 | 2026-03-06 10:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00382 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 16:28 | March | 2026 | 2026-04-16 16:20 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 22 | 0 | 2026-04-01 | 6
202603-NM25-00383 | GDL17 | Residencial | 8 | Period | 2026-03-25 15:05 | March | 2026 | 2026-04-01 14:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 6
202603-NM25-00384 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 12:57 | March | 2026 | 2026-04-17 09:33 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 18 | 0 | 2026-04-01 | 1
202603-NM25-00385 | GDL17 | Residencial | 8 | Period | 2026-03-05 17:57 | March | 2026 | 2026-03-09 11:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 26
202603-NM25-00386 | GDL17 | Residencial | 9.6 | Period | 2026-03-10 12:55 | March | 2026 | 2026-03-11 13:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00387 | GDL17 | Residencial | 8.448 | Period | 2026-03-05 08:15 | March | 2026 | 2026-03-06 15:03 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00388 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 10:50 | March | 2026 | 2026-03-27 13:43 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 13
202603-NM25-00389 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 10:50 | March | 2026 | 2026-04-06 09:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 6 | 0 | 2026-04-01 | 1
202603-NM25-00390 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 12:44 | March | 2026 | 2026-03-18 16:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-00391 | GDL17 | Residencial | 4.224 | Period | 2026-03-05 09:25 | March | 2026 | 2026-03-06 10:45 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00392 | GDL17 | Residencial | 4.992 | Period | 2026-03-17 13:21 | March | 2026 | 2026-03-25 09:27 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 2 | 6 | 2 | 2026-04-01 | 14
202603-NM25-00394 | GDL17 | Residencial | 8 | Period | 2026-03-05 18:58 | March | 2026 | 2026-03-09 15:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 26
202603-NM25-00395 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:03 | March | 2026 | 2026-03-17 15:15 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 5 | 3 | 2026-04-01 | 22
202603-NM25-00396 | GDL17 | Residencial | 6.612 | Period | 2026-03-05 09:51 | March | 2026 | 2026-03-06 13:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 27
202603-NM25-00398 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 12:31 | March | 2026 | 2026-03-12 07:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 22
202603-NM25-00401 | GDL17 | Residencial | 7.6 | Period | 2026-03-05 09:54 | March | 2026 | 2026-03-06 09:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 27
202603-NM25-00406 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 10:42 | March | 2026 | 2026-03-20 15:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-00407 | GDL17 | Residencial | 12 | Period | 2026-03-12 18:22 | March | 2026 | 2026-03-17 08:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-00411 | GDL17 | Residencial | 3.8 | Period | 2026-03-09 15:59 | March | 2026 | 2026-03-17 10:54 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 22
202603-NM25-00412 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 13:38 | March | 2026 | 2026-04-30 10:37 | 31 | Net Metering | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 31 | 0 | 2026-04-01 | 1
202603-NM25-00415 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:20 | March | 2026 | 2026-03-18 10:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-00418 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 10:48 | March | 2026 | 2026-03-09 07:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 27
202603-NM25-00420 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:11 | March | 2026 | 2026-03-23 12:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-00421 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 15:34 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 13
202603-NM25-00422 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 08:27 | March | 2026 | 2026-03-13 08:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 22
202603-NM25-00424 | GDL17 | Residencial | 7.6 | Period | 2026-03-05 13:20 | March | 2026 | 2026-03-09 12:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 26
202603-NM25-00425 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 08:10 | March | 2026 | 2026-03-19 16:24 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 19
202603-NM25-00426 | GDL17 | Residencial | 8 | Period | 2026-03-05 12:19 | March | 2026 | 2026-03-10 15:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 26
202603-NM25-00427 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 09:17 | March | 2026 | 2026-04-08 13:55 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 8 | 0 | 2026-04-01 | 1
202603-NM25-00428 | GDL17 | Residencial | 5 | Period | 2026-03-06 11:11 | March | 2026 | 2026-03-06 15:42 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 0 | 0 | 2026-04-01 | 26
202603-NM25-00430 | GDL17 | Residencial | 3.8 | Period | 2026-03-10 10:43 | March | 2026 | 2026-03-11 16:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00431 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 12:11 | March | 2026 | 2026-03-11 13:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 26
202603-NM25-00433 | GDL17 | Residencial | 9 | Period | 2026-03-10 13:28 | March | 2026 | 2026-03-16 09:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00435 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 13:07 | March | 2026 | 2026-03-12 08:07 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 26
202603-NM25-00437 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 15:33 | March | 2026 | 2026-04-02 15:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-00438 | GDL17 | Residencial | 22.8 | Period | 2026-03-23 12:42 | March | 2026 | 2026-03-26 10:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 2 | 1 | 2026-04-01 | 8
202603-NM25-00439 | GDL17 | Residencial | 22.8 | Period | 2026-03-23 13:11 | March | 2026 | 2026-03-26 10:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 2 | 1 | 2026-04-01 | 8
202603-NM25-00442 | GDL17 | Residencial | 5.956 | Period | 2026-03-05 13:57 | March | 2026 | 2026-03-11 13:56 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 5 | 1 | 2026-04-01 | 26
202603-NM25-00443 | GDL17 | Residencial | 15 | Period | 2026-03-10 15:10 | March | 2026 | 2026-03-12 13:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00445 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:22 | March | 2026 | 2026-03-11 10:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 26
202603-NM25-00446 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:15 | March | 2026 | 2026-03-13 07:59 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 26
202603-NM25-00447 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 10:10 | March | 2026 | 2026-03-06 16:26 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 0 | 0 | 2026-04-01 | 26
202603-NM25-00449 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:19 | March | 2026 | 2026-03-17 09:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-00450 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 14:58 | March | 2026 | 2026-03-06 12:58 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 26
202603-NM25-00451 | GDL17 | Residencial | 6.93 | Period | 2026-03-05 16:07 | March | 2026 | 2026-03-23 11:14 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 4 | 14 | 2026-04-01 | 26
202603-NM25-00452 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 15:16 | March | 2026 | 2026-03-10 09:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 26
202603-NM25-00453 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:37 | March | 2026 | 2026-03-23 09:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-00455 | GDL17 | Residencial | 8 | Period | 2026-03-10 11:05 | March | 2026 | 2026-03-17 12:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00456 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 15:48 | March | 2026 | 2026-03-06 10:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 0 | 0 | 2026-04-01 | 26
202603-NM25-00457 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 10:28 | March | 2026 | 2026-03-20 15:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-00458 | GDL17 | Residencial | 8 | Period | 2026-03-10 13:35 | March | 2026 | 2026-03-16 08:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 21
202603-NM25-00460 | GDL17 | Residencial | 8.56 | Period | 2026-03-05 16:48 | March | 2026 | 2026-03-11 09:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 26
202603-NM25-00461 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:09 | March | 2026 | 2026-03-06 10:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 26
202603-NM25-00462 | GDL17 | Residencial | 8 | Period | 2026-03-25 12:53 | March | 2026 | 2026-04-10 07:45 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 16 | 0 | 2026-04-01 | 6
202603-NM25-00463 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:05 | March | 2026 | 2026-03-09 14:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 26
202603-NM25-00464 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:12 | March | 2026 | 2026-03-09 09:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 26
202603-NM25-00465 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:41 | March | 2026 | 2026-03-30 11:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-00466 | GDL17 | Residencial | 8 | Period | 2026-03-10 13:54 | March | 2026 | 2026-03-17 13:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 21
202603-NM25-00469 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:48 | March | 2026 | 2026-03-12 13:28 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 26
202603-NM25-00470 | GDL17 | Residencial | 11.5 | Period | 2026-03-05 17:55 | March | 2026 | 2026-03-09 10:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 26
202603-NM25-00471 | GDL17 | Residencial | 24 | Period | 2026-03-10 13:58 | March | 2026 | 2026-04-23 15:03 | 44 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | April |  | 44 | 0 | 2026-04-01 | 21
202603-NM25-00474 | GDL17 | Residencial | 7.64 | Period | 2026-03-20 14:15 | March | 2026 | 2026-03-24 12:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 11
202603-NM25-00476 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:30 | March | 2026 | 2026-03-18 17:17 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 20
202603-NM25-00477 | GDL17 | Residencial | 8 | Period | 2026-03-06 15:12 | March | 2026 | 2026-03-09 15:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 25
202603-NM25-00478 | GDL17 | Residencial | 14.82 | Period | 2026-03-06 09:44 | March | 2026 | 2026-04-22 11:21 | 47 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | ARECIBO | April |  | 47 | 0 | 2026-04-01 | 26
202603-NM25-00480 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 10:19 | March | 2026 | 2026-03-06 16:27 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 26
202603-NM25-00481 | GDL17 | Residencial | 7.6 | Period | 2026-03-06 10:00 | March | 2026 | 2026-03-13 08:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 26
202603-NM25-00482 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 16:32 | March | 2026 | 2026-03-13 16:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 25
202603-NM25-00483 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 10:38 | March | 2026 | 2026-03-27 09:32 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 21 | 0 | 2026-04-01 | 26
202603-NM25-00486 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 11:20 | March | 2026 | 2026-03-11 13:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 26
202603-NM25-00489 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 10:51 | March | 2026 | 2026-03-11 16:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 26
202603-NM25-00490 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 14:43 | March | 2026 | 2026-03-09 14:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 25
202603-NM25-00491 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 11:04 | March | 2026 | 2026-03-10 16:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 26
202603-NM25-00492 | GDL17 | Residencial | 8 | Period | 2026-03-19 13:05 | March | 2026 | 2026-03-20 15:35 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-00496 | GDL17 | Residencial | 11.4 | Period | 2026-03-12 15:01 | March | 2026 | 2026-03-16 15:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00497 | GDL17 | Residencial | 6.612 | Period | 2026-03-06 11:58 | March | 2026 | 2026-03-06 16:28 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 26
202603-NM25-00500 | GDL17 | Residencial | 7.6 | Period | 2026-03-06 12:14 | March | 2026 | 2026-03-12 09:40 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 25
202603-NM25-00501 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 13:19 | March | 2026 | 2026-03-19 13:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 14
202603-NM25-00503 | GDL17 | Residencial | 9 | Period | 2026-03-07 11:54 | March | 2026 | 2026-03-09 12:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 25
202603-NM25-00518 | GDL17 | Residencial | 12 | Period | 2026-03-10 15:42 | March | 2026 | 2026-03-13 15:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 21
202603-NM25-00519 | GDL17 | Residencial | 6.8 | Period | 2026-03-06 16:19 | March | 2026 | 2026-03-10 14:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 25
202603-NM25-00521 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 07:29 | March | 2026 | 2026-03-17 13:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00531 | GDL17 | Residencial | 6 | Period | 2026-03-12 18:48 | March | 2026 | 2026-03-16 14:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00532 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 13:43 | March | 2026 | 2026-03-23 09:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-00533 | GDL17 | Residencial | 12 | Period | 2026-03-10 16:11 | March | 2026 | 2026-03-12 10:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00534 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:12 | March | 2026 | 2026-03-27 07:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-00540 | GDL17 | Comercial | 18 | Period | 2026-03-25 21:45 | March | 2026 | 2026-03-30 13:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-00541 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 15:18 | March | 2026 | 2026-03-11 16:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 25
202603-NM25-00542 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 15:29 | March | 2026 | 2026-03-17 13:05 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 11 | 0 | 2026-04-01 | 25
202603-NM25-00544 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 08:23 | March | 2026 | 2026-04-01 12:32 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | April |  | 12 | 1 | 2026-04-01 | 12
202603-NM25-00545 | GDL17 | Residencial | 11.5 | Period | 2026-03-06 15:29 | March | 2026 | 2026-03-18 09:14 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 12 | 0 | 2026-04-01 | 25
202603-NM25-00551 | GDL17 | Residencial | 9 | Period | 2026-03-19 10:04 | March | 2026 | 2026-03-25 11:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 13
202603-NM25-00556 | GDL17 | Residencial | 8 | Period | 2026-03-23 09:09 | March | 2026 | 2026-03-30 08:32 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 9
202603-NM25-00568 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:20 | March | 2026 | 2026-03-30 10:42 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-00569 | GDL17 | Residencial | 12 | Period | 2026-03-06 19:19 | March | 2026 | 2026-03-09 12:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 25
202603-NM25-00570 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:40 | March | 2026 | 2026-03-26 09:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 8
202603-NM25-00573 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:14 | March | 2026 | 2026-04-10 14:38 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | April |  | 18 | 15 | 2026-04-01 | 8
202603-NM25-00580 | GDL17 | Residencial | 4.5 | Period | 2026-03-19 15:47 | March | 2026 | 2026-03-23 13:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-00581 | GDL17 | Residencial | 12 | Period | 2026-03-19 16:27 | March | 2026 | 2026-03-27 15:56 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 12
202603-NM25-00583 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 10:35 | March | 2026 | 2026-03-13 09:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00592 | GDL17 | Residencial | 7.6 | Period | 2026-03-26 10:21 | March | 2026 | 2026-04-08 10:41 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 13 | 0 | 2026-04-01 | 6
202603-NM25-00593 | GDL17 | Residencial | 24 | Period | 2026-03-10 17:02 | March | 2026 | 2026-03-12 08:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00594 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:35 | March | 2026 | 2026-03-17 07:49 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00595 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:06 | March | 2026 | 2026-03-12 12:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00599 | GDL17 | Comercial | 11.5 | Period | 2026-03-10 10:02 | March | 2026 | 2026-03-17 14:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00601 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:46 | March | 2026 | 2026-03-17 16:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00604 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:20 | March | 2026 | 2026-03-27 14:26 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 10 | 0 | 2026-04-01 | 15
202603-NM25-00607 | GDL17 | Residencial | 3.84 | Period | 2026-03-19 14:49 | March | 2026 | 2026-03-23 13:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-00610 | GDL17 | Residencial | 10 | Period | 2026-03-20 18:23 | March | 2026 | 2026-03-27 09:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 11
202603-NM25-00612 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 07:18 | March | 2026 | 2026-03-30 13:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-00615 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 09:02 | March | 2026 | 2026-03-09 12:42 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 0 | 0 | 2026-04-01 | 23
202603-NM25-00617 | GDL17 | Residencial | 8 | Period | 2026-03-17 15:30 | March | 2026 | 2026-03-18 14:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-00620 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:28 | March | 2026 | 2026-03-25 07:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-00621 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:15 | March | 2026 | 2026-04-16 13:16 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | April |  | 23 | 20 | 2026-04-01 | 8
202603-NM25-00622 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 08:49 | March | 2026 | 2026-04-06 08:02 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 11 | 0 | 2026-04-01 | 6
202603-NM25-00623 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 10:15 | March | 2026 | 2026-03-09 13:52 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 23
202603-NM25-00624 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 07:17 | March | 2026 | 2026-03-30 09:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-00625 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 11:58 | March | 2026 | 2026-03-31 10:13 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 12 | 0 | 2026-04-01 | 14
202603-NM25-00626 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:17 | March | 2026 | 2026-04-09 10:52 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 17 | 0 | 2026-04-01 | 8
202603-NM25-00627 | GDL17 | Residencial | 7.68 | Period | 2026-03-16 10:01 | March | 2026 | 2026-03-30 07:44 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 14 | 0 | 2026-04-01 | 16
202603-NM25-00628 | GDL17 | Residencial | 3.54 | Period | 2026-03-09 10:08 | March | 2026 | 2026-03-09 13:48 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 0 | 0 | 2026-04-01 | 23
202603-NM25-00629 | GDL17 | Residencial | 7.6 | Period | 2026-03-09 10:16 | March | 2026 | 2026-03-11 15:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 23
202603-NM25-00630 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 13:51 | March | 2026 | 2026-03-18 16:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 19
202603-NM25-00631 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 10:56 | March | 2026 | 2026-03-11 09:23 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 23
202603-NM25-00635 | GDL17 | Residencial | 4.608 | Period | 2026-03-10 10:00 | March | 2026 | 2026-03-12 13:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00636 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:57 | March | 2026 | 2026-03-31 13:15 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 2 | 1 | 10 | 2026-04-01 | 12
202603-NM25-00637 | GDL17 | Residencial | 5.926 | Period | 2026-03-09 11:29 | March | 2026 | 2026-03-09 13:34 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 0 | 0 | 2026-04-01 | 23
202603-NM25-00638 | GDL17 | Residencial | 18 | Period | 2026-03-25 12:59 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 6
202603-NM25-00639 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:53 | March | 2026 | 2026-03-18 08:41 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 9 | 0 | 2026-04-01 | 23
202603-NM25-00640 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 11:51 | March | 2026 | 2026-03-10 15:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 23
202603-NM25-00642 | GDL17 | Residencial | 8.418 | Period | 2026-03-09 12:10 | March | 2026 | 2026-03-13 11:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 22
202603-NM25-00644 | GDL17 | Residencial | 10 | Period | 2026-03-10 08:52 | March | 2026 | 2026-03-12 10:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00645 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:00 | March | 2026 | 2026-03-11 08:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00646 | GDL17 | Residencial | 16.836 | Period | 2026-03-09 12:21 | March | 2026 | 2026-03-09 15:35 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 0 | 0 | 2026-04-01 | 22
202603-NM25-00648 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 12:33 | March | 2026 | 2026-03-11 13:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00650 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:54 | March | 2026 | 2026-03-13 12:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 22
202603-NM25-00651 | GDL17 | Residencial | 8.418 | Period | 2026-03-09 13:23 | March | 2026 | 2026-03-09 15:17 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 0 | 0 | 2026-04-01 | 22
202603-NM25-00652 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:22 | March | 2026 | 2026-03-19 08:42 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 2 | 8 | 2 | 2026-04-01 | 22
202603-NM25-00653 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:30 | March | 2026 | 2026-03-11 14:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00654 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:47 | March | 2026 | 2026-03-09 15:51 | 0 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 22
202603-NM25-00655 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:39 | March | 2026 | 2026-03-10 14:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00656 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 14:09 | March | 2026 | 2026-03-10 15:05 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00657 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:37 | March | 2026 | 2026-03-12 13:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00658 | GDL17 | Residencial | 7.68 | Period | 2026-03-24 14:40 | March | 2026 | 2026-04-02 14:49 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | April |  | 9 | 4 | 2026-04-01 | 7
202603-NM25-00659 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 13:59 | March | 2026 | 2026-03-18 07:48 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 22
202603-NM25-00662 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 07:30 | March | 2026 | 2026-03-13 15:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 20
202603-NM25-00663 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 14:41 | March | 2026 | 2026-03-19 08:42 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 2 | 8 | 2 | 2026-04-01 | 22
202603-NM25-00665 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:03 | March | 2026 | 2026-03-23 13:58 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 3 | 9 | 5 | 2026-04-01 | 22
202603-NM25-00666 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 14:35 | March | 2026 | 2026-03-23 13:56 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 2 | 10 | 4 | 2026-04-01 | 22
202603-NM25-00667 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 08:24 | March | 2026 | 2026-03-17 16:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00668 | GDL17 | Comercial | 5.3 | Period | 2026-03-10 09:03 | March | 2026 | 2026-03-17 10:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00669 | GDL17 | Comercial | 5.3 | Period | 2026-03-10 09:05 | March | 2026 |  |  | NM Enter Technical Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202603-NM25-00670 | GDL17 | Comercial | 5.3 | Period | 2026-03-10 09:07 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202603-NM25-00671 | GDL17 | Comercial | 5.3 | Period | 2026-03-10 09:08 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202603-NM25-00672 | GDL17 | Comercial | 5.3 | Period | 2026-03-10 09:10 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202603-NM25-00673 | GDL17 | Comercial | 5.3 | Period | 2026-03-10 09:12 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202603-NM25-00674 | GDL17 | Comercial | 5.3 | Period | 2026-03-10 09:17 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202603-NM25-00675 | GDL17 | Comercial | 5.3 | Period | 2026-03-10 09:25 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202603-NM25-00676 | GDL17 | Comercial | 21.8 | Period | 2026-03-10 09:47 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 22
202603-NM25-00677 | GDL17 | Comercial | 5.3 | Period | 2026-03-11 09:06 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 21
202603-NM25-00678 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:19 | March | 2026 | 2026-03-23 14:01 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 2 | 11 | 3 | 2026-04-01 | 22
202603-NM25-00679 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:07 | March | 2026 | 2026-03-19 08:25 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 2 | 8 | 2 | 2026-04-01 | 22
202603-NM25-00680 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:24 | March | 2026 | 2026-03-11 09:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00683 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:19 | March | 2026 | 2026-03-23 14:03 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 2 | 11 | 3 | 2026-04-01 | 22
202603-NM25-00684 | GDL17 | Residencial | 8 | Period | 2026-03-11 00:45 | March | 2026 | 2026-03-12 13:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00685 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:36 | March | 2026 | 2026-03-17 16:28 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 8 | 0 | 2026-04-01 | 22
202603-NM25-00686 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:35 | March | 2026 | 2026-03-10 13:32 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00688 | GDL17 | Residencial | 23 | Period | 2026-03-09 15:25 | March | 2026 | 2026-03-10 11:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00689 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:42 | March | 2026 | 2026-03-11 13:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00690 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:49 | March | 2026 | 2026-03-13 15:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 2 | 2 | 2026-04-01 | 22
202603-NM25-00691 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:56 | March | 2026 | 2026-03-31 08:53 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 21 | 0 | 2026-04-01 | 22
202603-NM25-00692 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:51 | March | 2026 | 2026-03-17 13:32 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 22
202603-NM25-00694 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 15:54 | March | 2026 | 2026-03-12 08:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00695 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:06 | March | 2026 | 2026-03-11 15:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00696 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:02 | March | 2026 | 2026-03-12 08:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00697 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:48 | March | 2026 | 2026-03-17 12:57 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00698 | GDL17 | Residencial | 12 | Period | 2026-03-10 17:30 | March | 2026 | 2026-03-12 10:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00699 | GDL17 | Residencial | 8.382 | Period | 2026-03-12 13:32 | March | 2026 | 2026-04-30 12:46 | 49 | NM Project Acceptance Special | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | CAGUAS | April |  | 49 | 45 | 2026-04-01 | 19
202603-NM25-00700 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 14:58 | March | 2026 | 2026-03-17 10:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-00701 | GDL17 | Residencial | 6 | Period | 2026-03-23 10:50 | March | 2026 | 2026-03-26 09:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 9
202603-NM25-00702 | GDL17 | Residencial | 23 | Period | 2026-03-09 16:12 | March | 2026 | 2026-03-10 13:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00706 | GDL17 | Residencial | 14.572 | Period | 2026-03-09 16:22 | March | 2026 | 2026-03-10 13:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00708 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:29 | March | 2026 | 2026-03-26 10:50 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 17 | 0 | 2026-04-01 | 22
202603-NM25-00709 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:17 | March | 2026 | 2026-03-10 10:41 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00710 | GDL17 | Residencial | 10 | Period | 2026-03-10 18:30 | March | 2026 | 2026-03-30 16:23 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 20 | 0 | 2026-04-01 | 21
202603-NM25-00711 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:39 | March | 2026 | 2026-03-12 07:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00712 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:41 | March | 2026 | 2026-03-10 12:53 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00713 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 16:52 | March | 2026 | 2026-03-10 11:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00714 | GDL17 | Residencial | 11.5 | Period | 2026-03-09 17:01 | March | 2026 | 2026-03-10 11:09 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00717 | GDL17 | Residencial | 18 | Period | 2026-03-11 11:39 | March | 2026 | 2026-03-16 14:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 21
202603-NM25-00718 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:41 | March | 2026 | 2026-03-11 15:51 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00719 | GDL17 | Residencial | 9.7 | Period | 2026-03-09 17:12 | March | 2026 | 2026-03-10 11:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00720 | GDL17 | Residencial | 8 | Period | 2026-03-10 15:52 | March | 2026 | 2026-03-13 15:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 21
202603-NM25-00721 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 15:19 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 6
202603-NM25-00722 | GDL17 | Residencial | 8 | Period | 2026-03-10 13:27 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 21
202603-NM25-00723 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:43 | March | 2026 | 2026-03-30 13:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-00724 | GDL17 | Residencial | 8 | Period | 2026-03-11 01:09 | March | 2026 | 2026-03-12 09:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00725 | GDL17 | Residencial | 8 | Period | 2026-03-11 13:32 | March | 2026 | 2026-03-13 13:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00726 | GDL17 | Residencial | 8 | Period | 2026-03-25 09:42 | March | 2026 | 2026-04-13 12:48 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 19 | 0 | 2026-04-01 | 7
202603-NM25-00727 | GDL17 | Residencial | 8 | Period | 2026-03-11 01:24 | March | 2026 | 2026-03-16 15:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 21
202603-NM25-00728 | GDL17 | Residencial | 8 | Period | 2026-03-11 14:05 | March | 2026 | 2026-03-16 14:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-00729 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:29 | March | 2026 | 2026-03-30 12:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-00733 | GDL17 | Comercial | 5.3 | Period | 2026-03-11 09:08 | March | 2026 | 2026-03-17 10:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00734 | GDL17 | Comercial | 5.3 | Period | 2026-03-11 09:10 | March | 2026 | 2026-03-17 10:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00736 | GDL17 | Comercial | 5.3 | Period | 2026-03-11 09:12 | March | 2026 | 2026-03-17 10:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00738 | GDL17 | Residencial | 7.6 | Period | 2026-03-11 08:25 | March | 2026 | 2026-03-12 13:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00739 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:20 | March | 2026 | 2026-03-30 13:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-00740 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 08:34 | March | 2026 | 2026-03-13 12:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 22
202603-NM25-00741 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 13:46 | March | 2026 | 2026-03-26 11:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 2 | 4 | 2 | 2026-04-01 | 11
202603-NM25-00742 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 08:52 | March | 2026 | 2026-03-11 11:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00743 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 14:17 | March | 2026 | 2026-03-17 13:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 20
202603-NM25-00745 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 08:54 | March | 2026 | 2026-03-11 11:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 22
202603-NM25-00747 | GDL17 | Residencial | 18 | Period | 2026-03-21 10:36 | March | 2026 | 2026-03-24 14:07 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 11
202603-NM25-00748 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:20 | March | 2026 | 2026-03-18 13:42 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 2 | 3 | 5 | 2026-04-01 | 22
202603-NM25-00750 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:24 | March | 2026 | 2026-03-13 15:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 22
202603-NM25-00751 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:26 | March | 2026 | 2026-03-13 07:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 22
202603-NM25-00757 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:30 | March | 2026 | 2026-03-12 15:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00759 | GDL17 | Residencial | 10.752 | Period | 2026-03-10 13:24 | March | 2026 | 2026-03-12 14:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00760 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 10:32 | March | 2026 | 2026-03-23 14:28 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-00762 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:49 | March | 2026 | 2026-03-18 10:06 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 22
202603-NM25-00763 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 09:44 | March | 2026 | 2026-03-16 09:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 22
202603-NM25-00764 | GDL17 | Residencial | 12 | Period | 2026-03-17 15:02 | March | 2026 | 2026-04-01 14:49 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 15 | 0 | 2026-04-01 | 14
202603-NM25-00767 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:37 | March | 2026 | 2026-03-31 14:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-00768 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:04 | March | 2026 | 2026-03-18 17:01 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 22
202603-NM25-00770 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:13 | March | 2026 | 2026-03-12 15:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00771 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:14 | March | 2026 | 2026-03-12 09:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00772 | GDL17 | Residencial | 9 | Period | 2026-03-13 09:07 | March | 2026 | 2026-03-17 09:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00773 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:21 | March | 2026 | 2026-03-12 13:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00775 | GDL17 | Residencial | 23 | Period | 2026-03-31 14:19 | March | 2026 | 2026-04-02 15:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-00776 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:23 | March | 2026 | 2026-03-16 12:59 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 22
202603-NM25-00777 | GDL17 | Residencial | 23 | Period | 2026-03-16 16:35 | March | 2026 | 2026-03-25 13:11 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 15
202603-NM25-00778 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:35 | March | 2026 | 2026-03-18 09:27 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 22
202603-NM25-00780 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 10:47 | March | 2026 | 2026-03-17 14:45 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 22
202603-NM25-00785 | GDL17 | Residencial | 3.84 | Period | 2026-03-11 11:14 | March | 2026 | 2026-03-18 16:55 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 21
202603-NM25-00787 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:22 | March | 2026 | 2026-03-12 14:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 22
202603-NM25-00789 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 07:33 | March | 2026 | 2026-03-18 16:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-00790 | GDL17 | Residencial | 15 | Period | 2026-03-10 12:55 | March | 2026 | 2026-03-11 13:28 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00792 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 11:35 | March | 2026 | 2026-03-23 08:25 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 22
202603-NM25-00793 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 09:31 | March | 2026 | 2026-03-18 08:41 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 16
202603-NM25-00794 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 08:57 | March | 2026 | 2026-03-31 11:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-00796 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:09 | March | 2026 | 2026-03-16 13:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00798 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 12:53 | March | 2026 | 2026-03-12 15:24 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00800 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:04 | March | 2026 | 2026-03-11 13:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00801 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:07 | March | 2026 | 2026-03-12 13:49 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00802 | GDL17 | Comercial | 6.91 | Period | 2026-03-10 13:20 | March | 2026 | 2026-03-12 15:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00803 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:21 | March | 2026 | 2026-03-12 15:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00805 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:29 | March | 2026 | 2026-03-17 09:58 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 21
202603-NM25-00806 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:33 | March | 2026 | 2026-03-12 14:06 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00807 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:52 | March | 2026 | 2026-03-16 15:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00808 | GDL17 | Residencial | 8.84 | Period | 2026-03-10 13:40 | March | 2026 | 2026-03-12 14:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00809 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:50 | March | 2026 | 2026-03-25 08:21 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 14 | 0 | 2026-04-01 | 21
202603-NM25-00810 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 13:47 | March | 2026 | 2026-03-12 15:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00813 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:16 | March | 2026 | 2026-03-11 13:54 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00814 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:16 | March | 2026 | 2026-03-23 13:14 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 21
202603-NM25-00815 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:45 | March | 2026 | 2026-03-25 09:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 14
202603-NM25-00816 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 14:53 | March | 2026 | 2026-03-13 13:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 21
202603-NM25-00817 | GDL17 | Residencial | 6 | Period | 2026-03-16 17:11 | March | 2026 | 2026-03-19 07:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-00818 | GDL17 | Residencial | 18 | Period | 2026-03-10 17:44 | March | 2026 | 2026-03-16 16:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00819 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:33 | March | 2026 | 2026-03-30 09:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-00820 | GDL17 | Residencial | 15.36 | Period | 2026-03-11 09:29 | March | 2026 | 2026-03-12 16:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00821 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 15:09 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 21
202603-NM25-00823 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 08:07 | March | 2026 | 2026-03-17 14:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00824 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 11:43 | March | 2026 | 2026-03-31 14:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-00825 | GDL17 | Residencial | 19.1 | Period | 2026-03-11 09:28 | March | 2026 | 2026-03-17 14:23 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 2 | 2 | 4 | 2026-04-01 | 21
202603-NM25-00826 | GDL17 | Residencial | 7.68 | Period | 2026-03-16 16:15 | March | 2026 | 2026-03-23 08:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-00829 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 15:40 | March | 2026 | 2026-03-17 09:40 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00831 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 15:53 | March | 2026 | 2026-03-13 08:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00832 | GDL17 | Residencial | 16.703 | Period | 2026-03-24 16:18 | March | 2026 | 2026-03-30 09:53 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-00833 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:08 | March | 2026 | 2026-03-11 13:01 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00834 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:32 | March | 2026 | 2026-03-23 14:35 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-00835 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:25 | March | 2026 | 2026-03-11 12:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00836 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:32 | March | 2026 | 2026-03-12 13:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00837 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:33 | March | 2026 | 2026-03-12 12:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00838 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:42 | March | 2026 | 2026-03-18 09:59 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 21
202603-NM25-00839 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:44 | March | 2026 | 2026-03-13 14:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 21
202603-NM25-00840 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:53 | March | 2026 | 2026-03-13 13:33 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 21
202603-NM25-00841 | GDL17 | Residencial | 11.5 | Period | 2026-03-10 16:58 | March | 2026 | 2026-03-16 11:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00844 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:31 | March | 2026 | 2026-03-26 12:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-00852 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:06 | March | 2026 | 2026-03-16 07:59 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-00864 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:20 | March | 2026 | 2026-03-16 13:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 19
202603-NM25-00865 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 09:35 | March | 2026 | 2026-03-13 09:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00866 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 12:53 | March | 2026 | 2026-03-19 16:03 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 19
202603-NM25-00870 | GDL17 | Residencial | 6.104 | Period | 2026-03-11 09:25 | March | 2026 | 2026-03-12 15:14 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 21
202603-NM25-00873 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:03 | March | 2026 | 2026-03-25 12:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 8
202603-NM25-00874 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 10:02 | March | 2026 | 2026-03-13 09:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00875 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 12:33 | March | 2026 | 2026-03-16 15:50 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00876 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 10:06 | March | 2026 | 2026-03-13 09:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00877 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 08:25 | March | 2026 | 2026-03-17 13:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-00878 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 08:10 | March | 2026 | 2026-03-16 17:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-00879 | GDL17 | Residencial | 4.608 | Period | 2026-03-17 13:11 | March | 2026 | 2026-03-19 14:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 14
202603-NM25-00881 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:19 | March | 2026 | 2026-03-30 12:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-00882 | GDL17 | Residencial | 7.6 | Period | 2026-03-11 10:48 | March | 2026 | 2026-03-13 09:46 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 21
202603-NM25-00883 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 10:38 | March | 2026 | 2026-03-16 14:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 5 | 0 | 2026-04-01 | 21
202603-NM25-00884 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 10:43 | March | 2026 | 2026-03-18 12:35 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 2 | 2 | 5 | 2026-04-01 | 21
202603-NM25-00885 | GDL17 | Residencial | 6.144 | Period | 2026-03-23 15:39 | March | 2026 | 2026-03-27 09:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 3 | 1 | 2026-04-01 | 8
202603-NM25-00887 | GDL17 | Residencial | 3.84 | Period | 2026-03-13 09:36 | March | 2026 | 2026-03-17 10:40 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00889 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 07:14 | March | 2026 | 2026-03-25 08:23 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 14
202603-NM25-00890 | GDL17 | Residencial | 9 | Period | 2026-03-19 10:24 | March | 2026 | 2026-03-20 15:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-00891 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:46 | March | 2026 | 2026-03-18 13:38 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-00892 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 12:10 | March | 2026 | 2026-03-24 09:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 12
202603-NM25-00893 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 14:45 | March | 2026 | 2026-03-13 13:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00894 | GDL17 | Residencial | 23 | Period | 2026-03-20 12:41 | March | 2026 | 2026-03-23 14:15 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 11
202603-NM25-00898 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 10:30 | March | 2026 | 2026-03-19 08:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 19
202603-NM25-00899 | GDL17 | Residencial | 15 | Period | 2026-03-11 12:53 | March | 2026 | 2026-03-13 12:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00901 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 11:50 | March | 2026 | 2026-03-17 09:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 21
202603-NM25-00902 | GDL17 | Comercial | 23 | Period | 2026-03-12 17:21 | March | 2026 | 2026-03-17 07:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-00904 | GDL17 | Residencial | 6 | Period | 2026-03-13 07:53 | March | 2026 | 2026-03-16 13:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 19
202603-NM25-00905 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 21:06 | March | 2026 | 2026-03-20 15:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-00906 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:20 | March | 2026 | 2026-04-10 15:57 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 11 | 0 | 2026-04-01 | 2
202603-NM25-00907 | GDL17 | Residencial | 3.8 | Period | 2026-03-27 16:44 | March | 2026 | 2026-04-01 15:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-00908 | GDL17 | Residencial | 3.8 | Period | 2026-03-13 08:37 | March | 2026 | 2026-03-20 15:10 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 19
202603-NM25-00910 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:44 | March | 2026 | 2026-04-01 15:44 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 7 | 0 | 2026-04-01 | 6
202603-NM25-00913 | GDL17 | Residencial | 5 | Period | 2026-03-31 19:15 | March | 2026 | 2026-04-02 08:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 1 | 0 | 2026-04-01 | 0
202603-NM25-00915 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:37 | March | 2026 | 2026-03-31 15:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-00916 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 18:06 | March | 2026 | 2026-03-23 14:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-00917 | GDL17 | Residencial | 8.984 | Period | 2026-03-11 12:59 | March | 2026 | 2026-03-13 13:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00918 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 14:23 | March | 2026 | 2026-03-24 08:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 13
202603-NM25-00920 | GDL17 | Residencial | 9 | Period | 2026-03-25 08:54 | March | 2026 | 2026-04-01 15:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 7 | 0 | 2026-04-01 | 7
202603-NM25-00922 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 12:24 | March | 2026 | 2026-03-30 10:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-00923 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:58 | March | 2026 | 2026-03-30 10:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-00925 | GDL17 | Residencial | 8.448 | Period | 2026-03-12 13:00 | March | 2026 | 2026-03-20 11:07 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 19
202603-NM25-00926 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 11:06 | March | 2026 | 2026-03-26 12:49 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 10 | 0 | 2026-04-01 | 16
202603-NM25-00927 | GDL17 | Residencial | 10.112 | Period | 2026-03-11 13:40 | March | 2026 | 2026-03-13 13:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00930 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 13:49 | March | 2026 | 2026-03-13 08:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 20
202603-NM25-00932 | GDL17 | Residencial | 9 | Period | 2026-03-21 09:29 | March | 2026 | 2026-03-25 13:26 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 11
202603-NM25-00934 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 17:16 | March | 2026 | 2026-03-27 12:57 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 10 | 0 | 2026-04-01 | 14
202603-NM25-00935 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 14:14 | March | 2026 | 2026-03-13 13:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00936 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:15 | March | 2026 | 2026-03-17 13:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-00937 | GDL17 | Comercial | 18 | Period | 2026-03-12 17:58 | March | 2026 | 2026-03-26 14:26 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 19
202603-NM25-00938 | GDL17 | Residencial | 7.68 | Period | 2026-03-23 13:49 | March | 2026 | 2026-04-08 10:54 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 16 | 0 | 2026-04-01 | 8
202603-NM25-00940 | GDL17 | Residencial | 7.68 | Period | 2026-03-17 16:26 | March | 2026 | 2026-03-19 09:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-00941 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 14:30 | March | 2026 | 2026-03-18 09:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 20
202603-NM25-00942 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 14:45 | March | 2026 | 2026-03-13 09:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 20
202603-NM25-00943 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 14:07 | March | 2026 | 2026-04-29 14:24 | 30 | Net Metering | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | April |  | 30 | 19 | 2026-04-01 | 1
202603-NM25-00945 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 14:57 | March | 2026 | 2026-03-13 12:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00946 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:00 | March | 2026 | 2026-03-25 14:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-00947 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:01 | March | 2026 | 2026-03-18 17:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-00948 | GDL17 | Residencial | 10 | Period | 2026-03-12 12:06 | March | 2026 | 2026-03-17 14:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-00950 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 08:09 | March | 2026 | 2026-03-30 13:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-00951 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:09 | March | 2026 | 2026-03-16 08:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-00952 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:17 | March | 2026 | 2026-03-18 10:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 20
202603-NM25-00953 | GDL17 | Residencial | 2.928 | Period | 2026-03-12 08:28 | March | 2026 | 2026-03-23 12:47 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 20
202603-NM25-00954 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:38 | March | 2026 | 2026-03-17 14:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 20
202603-NM25-00955 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:25 | March | 2026 | 2026-03-13 10:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 20
202603-NM25-00956 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:38 | March | 2026 | 2026-03-13 11:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00957 | GDL17 | Residencial | 4.392 | Period | 2026-03-11 15:45 | March | 2026 | 2026-03-17 11:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 1 | 5 | 2026-04-01 | 20
202603-NM25-00958 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 19:46 | March | 2026 | 2026-03-16 17:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-00959 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:34 | March | 2026 | 2026-03-12 16:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 20
202603-NM25-00960 | GDL17 | Residencial | 8.972 | Period | 2026-03-11 15:38 | March | 2026 | 2026-03-13 12:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00961 | GDL17 | Residencial | 7.6 | Period | 2026-03-11 16:16 | March | 2026 | 2026-03-19 07:48 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 20
202603-NM25-00962 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 15:54 | March | 2026 | 2026-03-17 11:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 20
202603-NM25-00963 | GDL17 | Residencial | 7.6 | Period | 2026-03-23 10:24 | March | 2026 | 2026-03-25 14:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-00965 | GDL17 | Residencial | 3.84 | Period | 2026-03-11 16:11 | March | 2026 | 2026-03-13 13:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00966 | GDL17 | Residencial | 9.714 | Period | 2026-03-11 16:11 | March | 2026 | 2026-03-13 12:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00967 | GDL17 | Residencial | 11.4 | Period | 2026-03-11 17:28 | March | 2026 | 2026-03-13 13:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00968 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 16:20 | March | 2026 | 2026-03-18 16:12 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 20
202603-NM25-00971 | GDL17 | Residencial | 11.5 | Period | 2026-03-11 16:58 | March | 2026 | 2026-03-16 08:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-00977 | GDL17 | Residencial | 11.5 | Period | 2026-03-28 10:26 | March | 2026 | 2026-04-01 14:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 4 | 0 | 2026-04-01 | 4
202603-NM25-00978 | GDL17 | Residencial | 15 | Period | 2026-03-11 20:44 | March | 2026 | 2026-03-13 15:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 20
202603-NM25-00980 | GDL17 | Residencial | 4.32 | Period | 2026-03-29 21:19 | March | 2026 | 2026-04-01 14:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 3 | 0 | 2026-04-01 | 2
202603-NM25-00981 | GDL17 | Residencial | 18 | Period | 2026-03-31 22:23 | March | 2026 | 2026-04-02 15:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-00982 | GDL17 | Residencial | 15 | Period | 2026-03-12 12:33 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 19
202603-NM25-00983 | GDL17 | Residencial | 7.68 | Period | 2026-03-17 21:12 | March | 2026 | 2026-03-23 10:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-00987 | GDL17 | Residencial | 7.6 | Period | 2026-03-12 13:02 | March | 2026 | 2026-03-17 10:23 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 4 | 1 | 2026-04-01 | 19
202603-NM25-00990 | GDL17 | Residencial | 7.6 | Period | 2026-03-12 10:40 | March | 2026 | 2026-03-17 13:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-00992 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 08:42 | March | 2026 | 2026-03-16 12:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-00993 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 08:46 | March | 2026 | 2026-03-17 13:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-00994 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:09 | March | 2026 | 2026-03-25 09:32 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 20
202603-NM25-00995 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 15:18 | March | 2026 | 2026-03-30 10:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-00996 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:15 | March | 2026 | 2026-03-17 14:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-00998 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:34 | March | 2026 | 2026-03-16 08:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-00999 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 10:00 | March | 2026 | 2026-03-17 11:29 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01000 | GDL17 | Comercial | 11.5 | Period | 2026-03-19 15:03 | March | 2026 | 2026-03-23 14:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01002 | GDL17 | Residencial | 5.76 | Period | 2026-03-12 09:57 | March | 2026 | 2026-03-16 13:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-01003 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 09:56 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 20
202603-NM25-01004 | GDL17 | Residencial | 7.6 | Period | 2026-03-12 10:43 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 20
202603-NM25-01005 | GDL17 | Residencial | 12 | Period | 2026-03-12 10:55 | March | 2026 | 2026-03-26 10:52 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 20
202603-NM25-01007 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:29 | March | 2026 | 2026-03-27 08:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 9
202603-NM25-01008 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 13:05 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 15
202603-NM25-01009 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:13 | March | 2026 | 2026-03-16 10:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-01010 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:17 | March | 2026 | 2026-03-18 08:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 20
202603-NM25-01011 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:11 | March | 2026 | 2026-03-17 10:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-01012 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:37 | March | 2026 | 2026-03-16 09:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-01013 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 13:05 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 5
202603-NM25-01014 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:34 | March | 2026 | 2026-03-16 10:39 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-01015 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 10:31 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 20
202603-NM25-01017 | GDL17 | Comercial | 9.15 | Period | 2026-03-12 14:42 | March | 2026 | 2026-03-16 14:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01018 | GDL17 | Comercial | 25 | Period | 2026-03-12 12:27 | March | 2026 | 2026-03-16 15:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01019 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:39 | March | 2026 | 2026-03-30 13:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-01020 | GDL17 | Residencial | 25 | Period | 2026-03-17 14:46 | March | 2026 | 2026-03-24 14:51 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 14
202603-NM25-01021 | GDL17 | Residencial | 3.8 | Period | 2026-03-27 11:31 | March | 2026 | 2026-04-01 14:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-01024 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:20 | March | 2026 | 2026-03-19 17:04 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 20
202603-NM25-01025 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:14 | March | 2026 | 2026-03-16 13:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 20
202603-NM25-01026 | GDL17 | Residencial | 7.6 | Period | 2026-03-13 13:33 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 18
202603-NM25-01027 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:41 | March | 2026 | 2026-03-16 14:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 19
202603-NM25-01028 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:23 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 20
202603-NM25-01029 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 11:36 | March | 2026 | 2026-03-17 14:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-01030 | GDL17 | Residencial | 7.6 | Period | 2026-03-12 11:40 | March | 2026 | 2026-04-27 10:42 | 46 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 46 | 0 | 2026-04-01 | 20
202603-NM25-01032 | GDL17 | Residencial | 8.254 | Period | 2026-03-12 11:47 | March | 2026 | 2026-03-17 13:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 20
202603-NM25-01033 | GDL17 | Residencial | 7.68 | Period | 2026-03-19 16:00 | March | 2026 | 2026-03-20 15:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-01035 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 12:07 | March | 2026 | 2026-03-23 09:49 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 19
202603-NM25-01036 | GDL17 | Residencial | 12 | Period | 2026-03-16 14:53 | March | 2026 | 2026-03-19 17:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 15
202603-NM25-01038 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 17:04 | March | 2026 | 2026-03-30 12:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01039 | GDL17 | Residencial | 4.992 | Period | 2026-03-13 13:43 | March | 2026 | 2026-03-16 17:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01040 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 18:00 | March | 2026 | 2026-03-17 10:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01041 | GDL17 | Residencial | 5.076 | Period | 2026-03-12 13:08 | March | 2026 | 2026-03-16 13:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01042 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 13:33 | March | 2026 | 2026-03-23 13:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-01043 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 09:53 | March | 2026 | 2026-03-20 08:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01044 | GDL17 | Residencial | 16.492 | Period | 2026-03-12 13:18 | March | 2026 | 2026-03-16 17:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01045 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 13:26 | March | 2026 | 2026-03-17 14:06 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-01047 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 15:19 | March | 2026 | 2026-03-17 13:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01049 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 10:45 | March | 2026 | 2026-04-06 14:06 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 24 | 0 | 2026-04-01 | 19
202603-NM25-01050 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 14:41 | March | 2026 | 2026-03-19 15:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 15
202603-NM25-01051 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 17:21 | March | 2026 | 2026-03-26 09:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01052 | GDL17 | Residencial | 7.6 | Period | 2026-03-25 14:54 | March | 2026 | 2026-03-30 12:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01053 | GDL17 | Residencial | 8 | Period | 2026-03-15 10:45 | March | 2026 | 2026-03-18 13:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 17
202603-NM25-01056 | GDL17 | Residencial | 10.924 | Period | 2026-03-12 15:00 | March | 2026 | 2026-03-17 14:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 2 | 3 | 2026-04-01 | 19
202603-NM25-01058 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 10:07 | March | 2026 | 2026-04-27 14:06 | 42 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 42 | 31 | 2026-04-01 | 16
202603-NM25-01063 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 15:18 | March | 2026 | 2026-03-17 08:20 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-01065 | GDL17 | Residencial | 19.1 | Period | 2026-03-25 09:53 | March | 2026 | 2026-03-30 10:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01067 | GDL17 | Residencial | 4.026 | Period | 2026-03-12 14:56 | March | 2026 | 2026-03-16 14:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01070 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 15:07 | March | 2026 | 2026-03-31 10:27 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 19 | 0 | 2026-04-01 | 19
202603-NM25-01072 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 15:16 | March | 2026 | 2026-03-17 12:55 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-01073 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 15:36 | March | 2026 | 2026-03-16 15:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01074 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 12:00 | March | 2026 | 2026-03-23 13:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01075 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 15:26 | March | 2026 | 2026-03-23 11:22 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 19
202603-NM25-01076 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:13 | March | 2026 | 2026-03-23 10:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-01078 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 15:43 | March | 2026 | 2026-03-17 14:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-01079 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 15:42 | March | 2026 | 2026-04-06 08:04 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 25 | 0 | 2026-04-01 | 19
202603-NM25-01080 | GDL17 | Residencial | 10.892 | Period | 2026-03-12 15:50 | March | 2026 | 2026-03-16 15:30 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01081 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:14 | March | 2026 | 2026-03-17 14:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 2 | 3 | 2026-04-01 | 19
202603-NM25-01082 | GDL17 | Residencial | 15.72 | Period | 2026-03-12 16:21 | March | 2026 | 2026-03-16 15:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01083 | GDL17 | Residencial | 6.312 | Period | 2026-03-12 16:25 | March | 2026 | 2026-03-25 12:56 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 4 | 6 | 7 | 2026-04-01 | 19
202603-NM25-01084 | GDL17 | Residencial | 8.254 | Period | 2026-03-12 16:03 | March | 2026 | 2026-03-30 13:21 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 18 | 0 | 2026-04-01 | 19
202603-NM25-01085 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:25 | March | 2026 | 2026-03-18 13:55 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 3 | 3 | 2026-04-01 | 19
202603-NM25-01086 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:30 | March | 2026 | 2026-03-20 08:00 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 19
202603-NM25-01087 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 17:08 | March | 2026 | 2026-03-19 15:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 19
202603-NM25-01088 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 12:44 | March | 2026 | 2026-04-07 10:18 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 11 | 0 | 2026-04-01 | 4
202603-NM25-01089 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 16:39 | March | 2026 | 2026-03-17 08:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 19
202603-NM25-01090 | GDL17 | Residencial | 7.6 | Period | 2026-03-19 08:26 | March | 2026 | 2026-03-23 14:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-01091 | GDL17 | Residencial | 16.99 | Period | 2026-03-13 10:34 | March | 2026 | 2026-03-17 13:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 1 | 3 | 2026-04-01 | 19
202603-NM25-01093 | GDL17 | Residencial | 7.6 | Period | 2026-03-19 10:56 | March | 2026 | 2026-03-25 13:47 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 13
202603-NM25-01094 | GDL17 | Residencial | 11.5 | Period | 2026-03-12 17:44 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 19
202603-NM25-01096 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:02 | March | 2026 | 2026-03-17 10:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01097 | GDL17 | Comercial | 11.4 | Period | 2026-03-13 07:38 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 19
202603-NM25-01098 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:06 | March | 2026 | 2026-03-25 14:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01099 | GDL17 | Residencial | 3.456 | Period | 2026-03-13 08:35 | March | 2026 | 2026-03-16 16:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 19
202603-NM25-01100 | GDL17 | Residencial | 11.4 | Period | 2026-03-13 09:46 | March | 2026 | 2026-03-17 08:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01101 | GDL17 | Residencial | 7.6 | Period | 2026-03-20 12:21 | March | 2026 | 2026-03-25 15:19 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 11
202603-NM25-01102 | GDL17 | Residencial | 7.6 | Period | 2026-03-13 08:47 | March | 2026 | 2026-03-17 08:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01103 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:49 | March | 2026 | 2026-04-07 09:40 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 11 | 0 | 2026-04-01 | 5
202603-NM25-01104 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 09:38 | March | 2026 | 2026-03-23 10:10 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 7 | 3 | 2026-04-01 | 19
202603-NM25-01105 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 09:38 | March | 2026 | 2026-03-23 15:24 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 7 | 0 | 2026-04-01 | 16
202603-NM25-01106 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 09:32 | March | 2026 | 2026-03-18 14:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 2 | 1 | 4 | 2026-04-01 | 19
202603-NM25-01110 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:04 | March | 2026 | 2026-03-23 07:49 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 10 | 0 | 2026-04-01 | 19
202603-NM25-01114 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 10:05 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 19
202603-NM25-01117 | GDL17 | Comercial | 12 | Period | 2026-03-17 11:24 | March | 2026 | 2026-03-18 15:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01118 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 10:17 | March | 2026 | 2026-03-18 14:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 1 | 4 | 2026-04-01 | 19
202603-NM25-01119 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 10:18 | March | 2026 | 2026-03-18 13:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 2 | 3 | 2026-04-01 | 19
202603-NM25-01122 | GDL17 | Residencial | 3.8 | Period | 2026-03-13 13:35 | March | 2026 | 2026-03-17 07:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-01123 | GDL17 | Comercial | 12 | Period | 2026-03-19 17:44 | March | 2026 | 2026-04-13 15:54 | 25 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | April |  | 25 | 3 | 2026-04-01 | 12
202603-NM25-01126 | GDL17 | Residencial | 12.672 | Period | 2026-03-16 09:06 | March | 2026 | 2026-03-18 09:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 16
202603-NM25-01127 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:03 | March | 2026 | 2026-03-17 13:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 19
202603-NM25-01128 | GDL17 | Residencial | 7.6 | Period | 2026-03-23 09:32 | March | 2026 | 2026-03-25 15:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01129 | GDL17 | Residencial | 5.76 | Period | 2026-03-19 08:31 | March | 2026 | 2026-04-24 08:23 | 36 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 36 | 0 | 2026-04-01 | 13
202603-NM25-01130 | GDL17 | Residencial | 3.456 | Period | 2026-03-13 14:59 | March | 2026 | 2026-03-18 08:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 2 | 3 | 2026-04-01 | 18
202603-NM25-01131 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:13 | March | 2026 | 2026-03-16 13:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 19
202603-NM25-01132 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:10 | March | 2026 | 2026-03-30 08:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01133 | GDL17 | Residencial | 16.5 | Period | 2026-03-17 09:27 | March | 2026 | 2026-03-18 14:37 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01134 | GDL17 | Residencial | 5.566 | Period | 2026-03-13 11:44 | March | 2026 | 2026-03-16 14:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 19
202603-NM25-01136 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 11:33 | March | 2026 | 2026-03-16 17:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 19
202603-NM25-01138 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:02 | March | 2026 | 2026-03-16 14:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01139 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:01 | March | 2026 | 2026-03-17 13:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-01140 | GDL17 | Residencial | 8.932 | Period | 2026-03-13 12:02 | March | 2026 | 2026-03-16 14:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01141 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 14:40 | March | 2026 | 2026-03-24 15:49 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 11 | 0 | 2026-04-01 | 18
202603-NM25-01142 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:07 | March | 2026 | 2026-03-19 16:11 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 18
202603-NM25-01143 | GDL17 | Residencial | 19.2 | Period | 2026-03-13 16:01 | March | 2026 | 2026-03-17 10:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01144 | GDL17 | Residencial | 9.292 | Period | 2026-03-13 12:31 | March | 2026 | 2026-03-16 15:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01145 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:39 | March | 2026 | 2026-03-31 16:08 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 18 | 0 | 2026-04-01 | 18
202603-NM25-01146 | GDL17 | Residencial | 8.664 | Period | 2026-03-13 13:39 | March | 2026 | 2026-03-17 08:08 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-01148 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:38 | March | 2026 | 2026-03-18 10:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 18
202603-NM25-01150 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 12:48 | March | 2026 | 2026-03-16 15:37 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01151 | GDL17 | Residencial | 8.192 | Period | 2026-03-13 13:02 | March | 2026 | 2026-03-16 15:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01152 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 13:10 | March | 2026 | 2026-03-16 15:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01154 | GDL17 | Residencial | 12 | Period | 2026-03-25 15:26 | March | 2026 | 2026-03-30 13:36 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01156 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 13:26 | March | 2026 | 2026-03-17 09:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-01161 | GDL17 | Residencial | 7.67 | Period | 2026-03-13 14:48 | March | 2026 | 2026-03-17 08:58 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-01162 | GDL17 | Residencial | 15.3 | Period | 2026-03-17 11:30 | March | 2026 | 2026-03-18 14:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01165 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:05 | March | 2026 | 2026-03-20 09:48 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 18
202603-NM25-01166 | GDL17 | Residencial | 8 | Period | 2026-03-20 11:43 | March | 2026 | 2026-03-23 14:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01167 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:20 | March | 2026 | 2026-03-18 08:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-01169 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 15:37 | March | 2026 | 2026-03-18 15:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 18
202603-NM25-01171 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:04 | March | 2026 | 2026-03-16 16:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01173 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:21 | March | 2026 | 2026-03-17 09:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-01174 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:05 | March | 2026 | 2026-04-23 13:59 | 41 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 41 | 0 | 2026-04-01 | 18
202603-NM25-01175 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 12:10 | March | 2026 | 2026-03-31 15:05 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 6
202603-NM25-01177 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:19 | March | 2026 | 2026-03-16 13:40 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 18
202603-NM25-01178 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 16:24 | March | 2026 | 2026-03-18 14:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 18
202603-NM25-01182 | GDL17 | Residencial | 11.5 | Period | 2026-03-13 17:51 | March | 2026 | 2026-03-18 14:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 4 | 1 | 2026-04-01 | 18
202603-NM25-01186 | GDL17 | Residencial | 12 | Period | 2026-03-13 21:11 | March | 2026 | 2026-03-17 10:55 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 18
202603-NM25-01189 | GDL17 | Residencial | 9 | Period | 2026-03-14 08:49 | March | 2026 | 2026-03-20 11:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 18
202603-NM25-01190 | GDL17 | Residencial | 5 | Period | 2026-03-14 10:36 | March | 2026 | 2026-03-19 11:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 18
202603-NM25-01193 | GDL17 | Residencial | 8 | Period | 2026-03-25 12:10 | March | 2026 | 2026-04-02 15:14 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 8 | 0 | 2026-04-01 | 6
202603-NM25-01197 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:28 | March | 2026 | 2026-03-23 08:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-01198 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:41 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 15
202603-NM25-01199 | GDL17 | Residencial | 5.076 | Period | 2026-03-16 08:47 | March | 2026 | 2026-03-17 11:06 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 16
2026-GD-00056 | GD1M | Comercial | 55.5 | Period | 2026-03-30 | March | 2026 |  |  | Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 2
2026-GD-00041 | GD1M | Comercial | 69.36 | Period | 2026-03-11 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 21
2026-GD-00038 | GD1M | Comercial | 30 | Period | 2026-03-10 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 22
2026-GD-00036 | GD1M | Comercial | 36 | Period | 2026-03-06 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 26
2026-GD-00033 | GD1M | Comercial | 530 | Period | 2026-03-05 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 27
2026-GD-00032 | GD1M | Comercial | 30 | Period | 2026-03-04 | March | 2026 |  |  | Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 28
2026-GD-00023 | GD1M | Residencial | 30.1 | Period | 2026-02-18 | February | 2026 |  |  | Determinar Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 42
2026-GD-00018 | GD1M | Comercial | 36 | Period | 2026-02-14 | February | 2026 |  |  | Finalizar estudio o indicar pago por mejora | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 46
2026-GD-00016 | GD1M | Residencial | 34.5 | Period | 2026-02-05 | February | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 55
2026-GD-00012 | GD1M | Comercial | 126 | Period | 2026-01-21 | January | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 70
2026-GD-00009 | GD1M | Comercial | 33.3 | Period | 2026-01-14 | January | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 77
2026-GD-00005 | GD1M | Comercial | 66.75 | Period | 2026-01-09 | January | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Arecibo |  |  |  |  | 2026-04-01 | 82
2026-GD-00058 | GD1M | Comercial | 30.68 | Period | 2026-03-31 | March | 2026 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 1
2026-GD-00027 | GD1M | Comercial | 30 | Period | 2026-02-20 | February | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 40
2026-GD-00014 | GD1M | Comercial | 33.02 | Period | 2026-01-29 | January | 2026 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 62
2026-GD-00013 | GD1M | Comercial | 102 | Period | 2026-01-27 | January | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 64
2026-GD-00007 | GD1M | Comercial | 106 | Period | 2026-01-14 | January | 2026 |  |  | Notificar Fecha de Pruebas y Construccion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 77
2026-GD-00051 | GD1M | Comercial | 32 | Period | 2026-03-25 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 7
2026-GD-00047 | GD1M | Comercial | 48 | Period | 2026-03-18 | March | 2026 |  |  | Evaluar y Certificar Cartografia | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 14
2026-GD-00046 | GD1M | Comercial | 34.2 | Period | 2026-03-17 | March | 2026 |  |  | Evaluar y Certificar Cartografia | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 15
2026-GD-00044 | GD1M | Comercial | 46.77 | Period | 2026-03-12 | March | 2026 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 20
2026-GD-00040 | GD1M | Comercial | 32.62 | Period | 2026-03-11 | March | 2026 |  |  | Evaluar y Certificar Cartografia, Planificación Estatus Medición | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 21
2026-GD-00024 | GD1M | Comercial | 625 | Period | 2026-02-20 | February | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 40
2026-GD-00015 | GD1M | Comercial | 97 | Period | 2026-02-05 | February | 2026 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 55
2026-GD-00010 | GD1M | Comercial | 34.5 | Period | 2026-01-16 | January | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 75
2026-GD-00053 | GD1M | Comercial | 36 | Period | 2026-03-26 | March | 2026 |  |  | Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 6
2026-GD-00052 | GD1M | Comercial | 62.4 | Period | 2026-03-26 | March | 2026 |  |  | Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 6
2026-GD-00043 | GD1M | Comercial | 32 | Period | 2026-03-12 | March | 2026 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 20
2026-GD-00039 | GD1M | Comercial | 30 | Period | 2026-03-11 | March | 2026 |  |  | Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 21
2026-GD-00030 | GD1M | Comercial | 34.5 | Period | 2026-03-03 | March | 2026 |  |  | Analisis Planificacion Central Distribucion, Evaluar y Certificar Cartografia | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 29
2026-GD-00020 | GD1M | Comercial | 48 | Period | 2026-02-17 | February | 2026 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 43
2026-GD-00055 | GD1M | Comercial | 99.9 | Period | 2026-03-30 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 2
2026-GD-00054 | GD1M | Comercial | 43.54 | Period | 2026-03-30 | March | 2026 |  |  | Estudio | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 2
2026-GD-00050 | GD1M | Comercial | 34.2 | Period | 2026-03-25 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 7
2026-GD-00037 | GD1M | Comercial | 90 | Period | 2026-03-08 | March | 2026 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 24
2026-GD-00035 | GD1M | Comercial | 30 | Period | 2026-03-05 | March | 2026 |  |  | Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 27
2026-GD-00034 | GD1M | Industrial | 71.529 | Period | 2026-03-05 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 27
2026-GD-00031 | GD1M | Comercial | 30 | Period | 2026-03-03 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 29
2026-GD-00029 | GD1M | Comercial | 60 | Period | 2026-03-03 | March | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 29
2026-GD-00028 | GD1M | Comercial | 34.5 | Period | 2026-02-26 | February | 2026 |  |  | Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 34
2026-GD-00011 | GD1M | Comercial | 30.2 | Period | 2026-01-19 | January | 2026 |  |  | Finalizar estudio o indicar pago por mejora | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 72
2026-GD-00057 | GD1M | Comercial | 60 | Period | 2026-03-30 | March | 2026 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 2
2026-GD-00042 | GD1M | Comercial | 56 | Period | 2026-03-12 | March | 2026 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 20
2026-GD-00022 | GD1M | Comercial | 33.3 | Period | 2026-02-18 | February | 2026 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 42
2026-GD-00021 | GD1M | Comercial | 42.63 | Period | 2026-02-17 | February | 2026 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 43
2026-GD-00008 | GD1M | Comercial | 238 | Period | 2026-01-14 | January | 2026 |  |  | Evaluacion | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 77
2026-GD-00006 | GD1M | Comercial | 924 | Period | 2026-01-09 | January | 2026 |  |  | Anejar Documentos | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 82
2026-GD-00004 | GD1M | Gubernamental | 1117 | Period | 2026-01-05 | January | 2026 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 86
2026-GD-00003 | GD1M | Gubernamental | 288.6 | Period | 2026-01-05 | January | 2026 |  |  | Pago Estudio Suplementario | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | San Juan |  |  |  |  | 2026-04-01 | 86
2026-GD-00019 | TRANSMISSION | Industrial | 996.6 | Period | 2026-02-16 | February | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 44
2026-GD-00026 | TRANSMISSION | Comercial | 792 | Period | 2026-02-20 | February | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 40
2026-GD-00017 | TRANSMISSION | Comercial | - | Period | 2026-02-11 | February | 2026 |  |  | Completar Información Adicional | Estudio (E) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 49
2026-GD-00045 | TRANSMISSION | Industrial | 942 | Period | 2026-03-17 | March | 2026 |  |  | Validación | Estudio (E) | Backlog | Backlog |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 15
202603-NM25-01200 | GDL17 | Residencial | 3.84 | Period | 2026-03-17 10:08 | March | 2026 | 2026-03-18 15:29 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01201 | GDL17 | Residencial | 12 | Period | 2026-03-19 10:04 | March | 2026 | 2026-03-25 14:16 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 13
202603-NM25-01202 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 11:35 | March | 2026 | 2026-03-18 15:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01203 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 09:18 | March | 2026 | 2026-03-18 09:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 16
202603-NM25-01207 | GDL17 | Residencial | 6.912 | Period | 2026-03-16 15:08 | March | 2026 | 2026-03-18 17:50 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01209 | GDL17 | Residencial | 8 | Period | 2026-03-16 11:41 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 16
202603-NM25-01210 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 09:50 | March | 2026 | 2026-03-17 14:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 16
202603-NM25-01212 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 10:04 | March | 2026 | 2026-03-17 16:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 16
202603-NM25-01213 | GDL17 | Residencial | 11.4 | Period | 2026-03-24 18:56 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 7
202603-NM25-01215 | GDL17 | Residencial | 10 | Period | 2026-03-23 03:10 | March | 2026 | 2026-03-24 13:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01218 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:02 | March | 2026 | 2026-03-19 17:48 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01219 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 10:20 | March | 2026 | 2026-03-17 14:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 16
202603-NM25-01221 | GDL17 | Residencial | 23 | Period | 2026-03-16 10:55 | March | 2026 | 2026-03-18 14:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 16
202603-NM25-01222 | GDL17 | Residencial | 9.136 | Period | 2026-03-16 10:35 | March | 2026 | 2026-03-17 13:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 16
202603-NM25-01223 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:23 | March | 2026 | 2026-04-22 13:09 | 36 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | BAYAMON | April |  | 36 | 0 | 2026-04-01 | 15
202603-NM25-01224 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 10:24 | March | 2026 | 2026-04-02 09:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-01225 | GDL17 | Residencial | 5 | Period | 2026-03-28 10:32 | March | 2026 | 2026-04-01 14:51 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 4 | 0 | 2026-04-01 | 4
202603-NM25-01226 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 10:55 | March | 2026 | 2026-03-18 09:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 16
202603-NM25-01230 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 14:09 | March | 2026 | 2026-04-02 14:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-01232 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 11:33 | March | 2026 | 2026-03-18 09:02 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 16
202603-NM25-01235 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 08:39 | March | 2026 | 2026-03-31 14:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-01238 | GDL17 | Residencial | 25 | Period | 2026-03-16 18:06 | March | 2026 | 2026-03-17 13:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01239 | GDL17 | Residencial | 15 | Period | 2026-03-24 15:14 | March | 2026 | 2026-04-02 09:39 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | April |  | 9 | 5 | 2026-04-01 | 7
202603-NM25-01240 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 11:07 | March | 2026 | 2026-03-23 16:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-01242 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:55 | March | 2026 | 2026-03-31 08:36 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 14 | 0 | 2026-04-01 | 15
202603-NM25-01243 | GDL17 | Residencial | 8.64 | Period | 2026-03-16 14:33 | March | 2026 | 2026-03-17 13:25 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01244 | GDL17 | Residencial | 7.6 | Period | 2026-03-16 14:36 | March | 2026 | 2026-03-30 12:52 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 3 | 11 | 2026-04-01 | 15
202603-NM25-01246 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 18:10 | March | 2026 | 2026-04-10 08:15 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 22 | 0 | 2026-04-01 | 13
202603-NM25-01247 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 14:44 | March | 2026 | 2026-03-18 09:09 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01248 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 12:01 | March | 2026 | 2026-03-24 15:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 11
202603-NM25-01249 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:21 | March | 2026 | 2026-03-27 07:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01250 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:05 | March | 2026 | 2026-03-25 15:00 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 8 | 1 | 2026-04-01 | 15
202603-NM25-01253 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:12 | March | 2026 | 2026-04-13 15:57 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | April |  | 28 | 0 | 2026-04-01 | 15
202603-NM25-01254 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:25 | March | 2026 | 2026-03-23 09:56 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-01255 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:19 | March | 2026 | 2026-03-17 16:08 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01256 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:27 | March | 2026 | 2026-03-17 13:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01257 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:52 | March | 2026 | 2026-03-17 13:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01258 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 15:51 | March | 2026 | 2026-03-17 12:50 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01260 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:01 | March | 2026 | 2026-03-23 12:42 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 15
202603-NM25-01261 | GDL17 | Residencial | 9 | Period | 2026-03-21 09:49 | March | 2026 | 2026-03-25 12:43 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 11
202603-NM25-01262 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:51 | March | 2026 | 2026-03-17 16:18 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01263 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:09 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 15
202603-NM25-01264 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:16 | March | 2026 | 2026-03-27 12:53 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 15
202603-NM25-01265 | GDL17 | Comercial | 11.5 | Period | 2026-03-16 16:25 | March | 2026 | 2026-03-18 16:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01267 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:26 | March | 2026 | 2026-03-19 14:26 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 15
202603-NM25-01268 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:33 | March | 2026 | 2026-03-18 15:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01269 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:14 | March | 2026 | 2026-03-27 07:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01270 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:48 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 15
202603-NM25-01271 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:40 | March | 2026 | 2026-03-17 15:47 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01272 | GDL17 | Comercial | 12 | Period | 2026-03-29 16:13 | March | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 2
202603-NM25-01273 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 16:49 | March | 2026 | 2026-03-18 15:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01274 | GDL17 | Residencial | 4.5 | Period | 2026-03-21 21:17 | March | 2026 | 2026-03-30 15:39 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 9 | 0 | 2026-04-01 | 10
202603-NM25-01277 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 16:38 | March | 2026 | 2026-03-27 10:30 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 12
202603-NM25-01278 | GDL17 | Residencial | 11.5 | Period | 2026-03-16 17:00 | March | 2026 | 2026-03-25 09:58 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 8 | 0 | 2026-04-01 | 15
202603-NM25-01279 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 14:35 | March | 2026 | 2026-04-02 09:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-01280 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:33 | March | 2026 | 2026-03-31 14:38 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-01282 | GDL17 | Residencial | 5.9 | Period | 2026-03-17 10:42 | March | 2026 | 2026-03-18 15:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01287 | GDL17 | Residencial | 8.54 | Period | 2026-03-17 07:19 | March | 2026 | 2026-03-20 15:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 15
202603-NM25-01290 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 13:17 | March | 2026 | 2026-04-10 11:00 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 23 | 0 | 2026-04-01 | 14
202603-NM25-01292 | GDL17 | Residencial | 9.344 | Period | 2026-03-17 08:26 | March | 2026 | 2026-03-18 13:43 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01293 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 13:20 | March | 2026 | 2026-03-18 15:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01294 | GDL17 | Residencial | 7.68 | Period | 2026-03-23 14:56 | March | 2026 | 2026-04-07 10:38 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 15 | 0 | 2026-04-01 | 8
202603-NM25-01295 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:36 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 15
202603-NM25-01296 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:36 | March | 2026 | 2026-03-18 13:46 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01297 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:43 | March | 2026 | 2026-03-23 08:31 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-01298 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:39 | March | 2026 | 2026-04-02 07:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 9 | 0 | 2026-04-01 | 8
202603-NM25-01299 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 08:53 | March | 2026 | 2026-03-19 15:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01300 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:02 | March | 2026 | 2026-03-30 13:19 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 13 | 0 | 2026-04-01 | 15
202603-NM25-01301 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:06 | March | 2026 | 2026-03-23 09:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-01302 | GDL17 | Residencial | 7.87 | Period | 2026-03-17 09:06 | March | 2026 | 2026-03-18 14:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01303 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 20:04 | March | 2026 | 2026-03-23 09:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01304 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:15 | March | 2026 | 2026-03-20 12:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 15
202603-NM25-01305 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:19 | March | 2026 | 2026-03-23 09:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-01306 | GDL17 | Residencial | 15.58 | Period | 2026-03-24 11:05 | March | 2026 | 2026-03-30 12:42 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-01307 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:26 | March | 2026 | 2026-03-18 17:30 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01308 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:25 | March | 2026 | 2026-03-27 11:10 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 10 | 0 | 2026-04-01 | 15
202603-NM25-01309 | GDL17 | Residencial | 7.68 | Period | 2026-03-27 09:56 | March | 2026 | 2026-04-09 16:20 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 13 | 0 | 2026-04-01 | 5
202603-NM25-01310 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:45 | March | 2026 | 2026-03-18 16:21 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01311 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 09:44 | March | 2026 | 2026-03-19 13:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01312 | GDL17 | Residencial | 7.296 | Period | 2026-03-20 09:22 | March | 2026 | 2026-03-23 09:06 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01313 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:56 | March | 2026 | 2026-03-18 14:44 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01314 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 09:59 | March | 2026 | 2026-03-23 08:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-01315 | GDL17 | Residencial | 7.6 | Period | 2026-03-17 10:00 | March | 2026 | 2026-03-20 10:13 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 15
202603-NM25-01317 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:11 | March | 2026 | 2026-03-20 08:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 15
202603-NM25-01318 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:39 | March | 2026 | 2026-04-06 14:31 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 20 | 0 | 2026-04-01 | 15
202603-NM25-01319 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 07:31 | March | 2026 | 2026-03-27 15:34 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 9
202603-NM25-01320 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:23 | March | 2026 | 2026-03-18 16:21 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01322 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 09:02 | March | 2026 | 2026-03-27 10:55 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 13
202603-NM25-01323 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:34 | March | 2026 | 2026-03-23 13:57 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 15
202603-NM25-01324 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:57 | March | 2026 | 2026-03-20 09:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 2 | 1 | 2026-04-01 | 15
202603-NM25-01326 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 13:22 | March | 2026 | 2026-03-31 07:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-01330 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:14 | March | 2026 | 2026-03-26 14:40 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 14
202603-NM25-01331 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 10:59 | March | 2026 | 2026-03-19 12:44 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01332 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 11:02 | March | 2026 | 2026-03-18 15:04 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 15
202603-NM25-01335 | GDL17 | Residencial | 3.8 | Period | 2026-03-23 13:02 | March | 2026 | 2026-04-14 11:18 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | April |  | 22 | 3 | 2026-04-01 | 8
202603-NM25-01336 | GDL17 | Residencial | 24.888 | Period | 2026-03-19 15:41 | March | 2026 | 2026-03-23 13:12 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01337 | GDL17 | Residencial | 23 | Period | 2026-03-17 11:14 | March | 2026 | 2026-03-19 07:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 15
202603-NM25-01339 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:19 | March | 2026 | 2026-03-24 13:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01340 | GDL17 | Residencial | 8.84 | Period | 2026-03-17 13:13 | March | 2026 | 2026-03-20 15:10 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 14
202603-NM25-01341 | GDL17 | Residencial | 12.81 | Period | 2026-03-18 13:02 | March | 2026 | 2026-03-27 09:16 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | March | 1 | 1 | 8 | 2026-04-01 | 13
202603-NM25-01342 | GDL17 | Residencial | 7.2 | Period | 2026-03-25 16:08 | March | 2026 | 2026-03-30 13:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01343 | GDL17 | Residencial | 10.848 | Period | 2026-03-17 12:20 | March | 2026 | 2026-03-18 15:23 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01346 | GDL17 | Residencial | 9.216 | Period | 2026-03-18 07:30 | March | 2026 | 2026-03-19 10:36 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01347 | GDL17 | Residencial | 3.8 | Period | 2026-03-18 14:54 | March | 2026 | 2026-04-22 13:19 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 35 | 0 | 2026-04-01 | 13
202603-NM25-01348 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 15:44 | March | 2026 | 2026-03-31 16:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 6
202603-NM25-01349 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 08:27 | March | 2026 | 2026-03-30 13:23 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-01350 | GDL17 | Residencial | 8 | Period | 2026-03-17 14:25 | March | 2026 | 2026-03-20 11:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 14
202603-NM25-01351 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:58 | March | 2026 | 2026-03-27 07:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01352 | GDL17 | Residencial | 3.84 | Period | 2026-03-17 15:30 | March | 2026 | 2026-03-25 11:10 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 8 | 0 | 2026-04-01 | 14
202603-NM25-01353 | GDL17 | Residencial | 9.33 | Period | 2026-03-17 13:04 | March | 2026 | 2026-03-23 10:49 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01355 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:13 | March | 2026 | 2026-03-23 12:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01356 | GDL17 | Residencial | 7.6 | Period | 2026-03-31 13:56 | March | 2026 | 2026-04-10 15:33 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 10 | 0 | 2026-04-01 | 0
202603-NM25-01357 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:15 | March | 2026 | 2026-03-31 13:25 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 14 | 0 | 2026-04-01 | 14
202603-NM25-01359 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:21 | March | 2026 | 2026-03-30 11:10 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 12
202603-NM25-01360 | GDL17 | Residencial | 11.4 | Period | 2026-03-25 14:13 | March | 2026 | 2026-04-08 14:37 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | April |  | 14 | 8 | 2026-04-01 | 6
202603-NM25-01361 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:22 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 14
202603-NM25-01362 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 20:54 | March | 2026 | 2026-03-20 15:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-01363 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 14:59 | March | 2026 | 2026-04-08 09:21 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 12 | 0 | 2026-04-01 | 4
202603-NM25-01364 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:41 | March | 2026 | 2026-03-20 08:39 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 14
202603-NM25-01366 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:31 | March | 2026 | 2026-03-23 14:52 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01367 | GDL17 | Residencial | 8 | Period | 2026-03-20 12:06 | March | 2026 | 2026-03-31 09:01 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 8 | 3 | 2026-04-01 | 11
202603-NM25-01368 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:57 | March | 2026 | 2026-03-20 12:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 14
202603-NM25-01369 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:13 | March | 2026 | 2026-04-07 12:58 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 15 | 0 | 2026-04-01 | 8
202603-NM25-01370 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:23 | March | 2026 | 2026-03-30 10:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01371 | GDL17 | Residencial | 5 | Period | 2026-03-18 14:24 | March | 2026 | 2026-03-23 09:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-01372 | GDL17 | Residencial | 11.4 | Period | 2026-03-26 07:00 | March | 2026 | 2026-03-30 13:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-01373 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 14:49 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 14
202603-NM25-01374 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:54 | March | 2026 | 2026-03-20 14:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 14
202603-NM25-01376 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:08 | March | 2026 | 2026-03-20 10:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 14
202603-NM25-01379 | GDL17 | Residencial | 23 | Period | 2026-03-19 15:24 | March | 2026 | 2026-03-20 15:26 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-01380 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 18:06 | March | 2026 | 2026-03-30 14:41 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01381 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 12:41 | March | 2026 | 2026-04-02 09:24 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-01383 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:22 | March | 2026 | 2026-03-23 15:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01384 | GDL17 | Residencial | 11.422 | Period | 2026-03-17 15:28 | March | 2026 | 2026-03-18 15:10 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01385 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 11:22 | March | 2026 | 2026-03-30 14:11 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 6 | 6 | 2026-04-01 | 14
202603-NM25-01387 | GDL17 | Residencial | 8 | Period | 2026-03-23 22:16 | March | 2026 | 2026-03-26 10:07 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01389 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:39 | March | 2026 | 2026-03-24 08:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01391 | GDL17 | Residencial | 11.346 | Period | 2026-03-19 17:26 | March | 2026 | 2026-03-20 15:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-01392 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:56 | March | 2026 | 2026-03-18 15:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01393 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 16:27 | March | 2026 | 2026-03-20 13:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 14
202603-NM25-01395 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 15:54 | March | 2026 | 2026-03-24 07:52 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01396 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 16:12 | March | 2026 | 2026-03-19 09:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01398 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:23 | March | 2026 | 2026-03-25 11:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 12
202603-NM25-01399 | GDL17 | Residencial | 23 | Period | 2026-03-17 16:37 | March | 2026 | 2026-03-23 10:02 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-01400 | GDL17 | Residencial | 8 | Period | 2026-03-23 22:45 | March | 2026 | 2026-03-26 10:08 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01401 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 16:32 | March | 2026 | 2026-03-23 10:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-01404 | GDL17 | Residencial | 7.6 | Period | 2026-03-20 16:38 | March | 2026 | 2026-03-25 12:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 11
202603-NM25-01406 | GDL17 | Comercial | 25 | Period | 2026-03-27 08:29 | March | 2026 | 2026-03-31 14:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-01407 | GDL17 | Residencial | 11.5 | Period | 2026-03-17 16:49 | March | 2026 | 2026-03-23 13:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01408 | GDL17 | Residencial | 8 | Period | 2026-03-23 02:20 | March | 2026 | 2026-03-24 13:15 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01409 | GDL17 | Residencial | 12 | Period | 2026-03-20 15:36 | March | 2026 | 2026-03-24 09:01 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 11
202603-NM25-01410 | GDL17 | Residencial | 8 | Period | 2026-03-24 12:54 | March | 2026 | 2026-03-30 10:18 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01411 | GDL17 | Residencial | 7.6 | Period | 2026-03-23 10:55 | March | 2026 | 2026-03-26 15:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 9
202603-NM25-01414 | GDL17 | Residencial | 8 | Period | 2026-03-23 00:49 | March | 2026 | 2026-03-27 09:49 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 9
202603-NM25-01416 | GDL17 | Residencial | 8 | Period | 2026-03-23 03:40 | March | 2026 | 2026-04-08 09:20 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 17 | 0 | 2026-04-01 | 9
202603-NM25-01417 | GDL17 | Residencial | 10 | Period | 2026-03-18 15:25 | March | 2026 | 2026-03-25 14:30 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 13
202603-NM25-01418 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:57 | March | 2026 | 2026-03-30 10:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01419 | GDL17 | Residencial | 8 | Period | 2026-03-23 03:22 | March | 2026 | 2026-03-27 10:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 9
202603-NM25-01420 | GDL17 | Residencial | 18 | Period | 2026-03-18 11:54 | March | 2026 | 2026-03-20 14:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 14
202603-NM25-01421 | GDL17 | Residencial | 5 | Period | 2026-03-21 16:14 | March | 2026 | 2026-04-02 14:09 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 12 | 0 | 2026-04-01 | 10
202603-NM25-01422 | GDL17 | Residencial | 23 | Period | 2026-03-17 22:08 | March | 2026 | 2026-03-18 15:13 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01424 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 15:47 | March | 2026 | 2026-03-27 12:49 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 9 | 0 | 2026-04-01 | 13
202603-NM25-01425 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 12:34 | March | 2026 | 2026-03-20 14:49 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-01426 | GDL17 | Residencial | 14.592 | Period | 2026-03-19 13:40 | March | 2026 | 2026-04-22 13:03 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 34 | 0 | 2026-04-01 | 12
202603-NM25-01427 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 08:53 | March | 2026 | 2026-03-24 08:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 14
202603-NM25-01428 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 08:49 | March | 2026 | 2026-04-10 09:11 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 23 | 0 | 2026-04-01 | 14
202603-NM25-01429 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:41 | March | 2026 | 2026-03-23 09:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-01431 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 14:44 | March | 2026 | 2026-03-30 09:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01434 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 09:34 | March | 2026 | 2026-03-19 10:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01435 | GDL17 | Residencial | 15.2 | Period | 2026-03-20 10:38 | March | 2026 | 2026-03-23 14:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01436 | GDL17 | Residencial | 3.8 | Period | 2026-03-31 10:56 | March | 2026 | 2026-04-02 09:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-01439 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 08:50 | March | 2026 | 2026-03-23 13:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-01440 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 10:17 | March | 2026 | 2026-03-23 08:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-01442 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:09 | March | 2026 | 2026-04-22 13:40 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 35 | 0 | 2026-04-01 | 14
202603-NM25-01445 | GDL17 | Comercial | 11.5 | Period | 2026-03-18 10:29 | March | 2026 | 2026-03-23 14:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 14
202603-NM25-01449 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 12:51 | March | 2026 | 2026-03-30 09:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01450 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 10:50 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | CAGUAS | March |  |  |  | 2026-04-01 | 14
202603-NM25-01452 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 15:24 | March | 2026 | 2026-03-31 14:44 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 4
202603-NM25-01453 | GDL17 | Residencial | 8 | Period | 2026-03-24 18:40 | March | 2026 | 2026-04-01 15:54 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 8 | 0 | 2026-04-01 | 7
202603-NM25-01454 | GDL17 | Residencial | 9 | Period | 2026-03-18 12:31 | March | 2026 | 2026-03-20 09:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 13
202603-NM25-01455 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 11:29 | March | 2026 | 2026-03-20 09:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 14
202603-NM25-01456 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 09:43 | March | 2026 | 2026-04-02 12:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 4 | 0 | 2026-04-01 | 2
202603-NM25-01459 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 11:10 | March | 2026 | 2026-03-20 08:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 14
202603-NM25-01460 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:05 | March | 2026 | 2026-03-27 15:46 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01463 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 11:26 | March | 2026 | 2026-03-20 09:21 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 14
202603-NM25-01464 | GDL17 | Residencial | 11.136 | Period | 2026-03-18 11:44 | March | 2026 | 2026-03-19 13:52 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01466 | GDL17 | Residencial | 10.04 | Period | 2026-03-18 11:38 | March | 2026 | 2026-03-19 13:40 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01467 | GDL17 | Residencial | 7.6 | Period | 2026-03-23 16:03 | March | 2026 | 2026-03-31 15:30 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 7 | 1 | 2026-04-01 | 8
202603-NM25-01468 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:25 | March | 2026 | 2026-04-01 15:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 3 | 0 | 2026-04-01 | 2
202603-NM25-01469 | GDL17 | Residencial | 15.34 | Period | 2026-03-18 11:48 | March | 2026 | 2026-03-19 12:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 14
202603-NM25-01473 | GDL17 | Residencial | 7.6 | Period | 2026-03-25 14:42 | March | 2026 | 2026-04-07 14:13 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 13 | 0 | 2026-04-01 | 6
202603-NM25-01477 | GDL17 | Residencial | 8 | Period | 2026-03-25 09:15 | March | 2026 | 2026-03-30 10:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01478 | GDL17 | Residencial | 10.224 | Period | 2026-03-18 12:53 | March | 2026 | 2026-03-23 09:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-01480 | GDL17 | Residencial | 10 | Period | 2026-03-19 10:36 | March | 2026 | 2026-03-20 14:56 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01485 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 14:06 | March | 2026 | 2026-03-23 13:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-01486 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 07:33 | March | 2026 | 2026-03-30 07:58 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-01491 | GDL17 | Residencial | 6.34 | Period | 2026-03-18 14:58 | March | 2026 | 2026-03-19 12:33 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01492 | GDL17 | Residencial | 8.66 | Period | 2026-03-18 14:36 | March | 2026 | 2026-03-19 11:21 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01493 | GDL17 | Residencial | 11.4 | Period | 2026-03-18 15:07 | March | 2026 | 2026-03-23 08:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-01495 | GDL17 | Residencial | 7.6 | Period | 2026-03-18 16:28 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 13
202603-NM25-01496 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 15:05 | March | 2026 | 2026-03-25 13:47 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 13
202603-NM25-01497 | GDL17 | Residencial | 9 | Period | 2026-03-20 16:32 | March | 2026 | 2026-03-26 14:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 11
202603-NM25-01498 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 15:20 | March | 2026 | 2026-03-23 14:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-01499 | GDL17 | Residencial | 9.752 | Period | 2026-03-18 15:21 | March | 2026 | 2026-03-19 11:19 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01500 | GDL17 | Residencial | 23 | Period | 2026-03-24 08:55 | March | 2026 | 2026-03-27 16:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01501 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 15:28 | March | 2026 | 2026-03-19 11:07 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 0 | 0 | 2026-04-01 | 13
202603-NM25-01502 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 15:42 | March | 2026 | 2026-03-20 12:47 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 13
202603-NM25-01506 | GDL17 | Residencial | 7.87 | Period | 2026-03-18 15:54 | March | 2026 | 2026-03-19 11:22 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01507 | GDL17 | Residencial | 11.4 | Period | 2026-03-19 09:32 | March | 2026 | 2026-03-23 10:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-01508 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:10 | March | 2026 | 2026-03-19 15:02 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01509 | GDL17 | Residencial | 5.926 | Period | 2026-03-18 16:07 | March | 2026 | 2026-03-20 07:54 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01510 | GDL17 | Residencial | 23 | Period | 2026-03-18 16:53 | March | 2026 | 2026-03-27 09:58 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 13
202603-NM25-01511 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:46 | March | 2026 | 2026-03-23 13:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-01512 | GDL17 | Residencial | 11.492 | Period | 2026-03-18 16:19 | March | 2026 | 2026-03-19 11:17 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 0 | 0 | 2026-04-01 | 13
202603-NM25-01513 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:35 | March | 2026 | 2026-03-20 16:04 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 13
202603-NM25-01515 | GDL17 | Residencial | 6.872 | Period | 2026-03-18 16:33 | March | 2026 | 2026-03-19 11:00 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 0 | 0 | 2026-04-01 | 13
202603-NM25-01518 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:47 | March | 2026 | 2026-03-19 13:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01519 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 16:53 | March | 2026 | 2026-03-23 11:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-01522 | GDL17 | Residencial | 11.5 | Period | 2026-03-18 17:16 | March | 2026 | 2026-03-23 13:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 13
202603-NM25-01523 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:30 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 8
202603-NM25-01531 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 07:18 | March | 2026 | 2026-03-27 09:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 9
202603-NM25-01535 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 09:19 | March | 2026 | 2026-03-23 08:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-01536 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 09:20 | March | 2026 | 2026-03-23 15:42 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-01537 | GDL17 | Residencial | 3.835 | Period | 2026-03-19 09:07 | March | 2026 | 2026-03-23 14:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 13
202603-NM25-01542 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:50 | March | 2026 | 2026-03-30 10:07 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01546 | GDL17 | Residencial | 7.6 | Period | 2026-03-23 09:27 | March | 2026 | 2026-03-25 15:34 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01547 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:52 | March | 2026 | 2026-03-30 15:02 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 11 | 0 | 2026-04-01 | 12
202603-NM25-01549 | GDL17 | Residencial | 7.6 | Period | 2026-03-19 10:07 | March | 2026 | 2026-03-20 15:39 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 1 | 0 | 2026-04-01 | 13
202603-NM25-01550 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:22 | March | 2026 | 2026-03-31 14:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-01553 | GDL17 | Residencial | 7.6 | Period | 2026-03-19 10:22 | March | 2026 | 2026-04-10 10:15 | 22 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 22 | 0 | 2026-04-01 | 13
202603-NM25-01555 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 13:33 | March | 2026 | 2026-03-27 08:46 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 2 | 6 | 0 | 2026-04-01 | 11
202603-NM25-01565 | GDL17 | Residencial | 6.24 | Period | 2026-03-25 18:21 | March | 2026 | 2026-03-30 13:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01568 | GDL17 | Residencial | 8 | Period | 2026-03-24 20:02 | March | 2026 | 2026-03-30 10:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01571 | GDL17 | Residencial | 7.6 | Period | 2026-03-19 12:06 | March | 2026 | 2026-03-31 07:32 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 1 | 0 | 2026-04-01 | 12
202603-NM25-01577 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 15:08 | March | 2026 | 2026-03-25 12:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | March | 1 | 4 | 1 | 2026-04-01 | 11
202603-NM25-01579 | GDL17 | Residencial | 8 | Period | 2026-03-25 09:21 | March | 2026 | 2026-03-30 10:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01580 | GDL17 | Residencial | 9 | Period | 2026-03-23 09:02 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 9
202603-NM25-01581 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 16:18 | March | 2026 | 2026-03-30 12:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01582 | GDL17 | Residencial | 7.6 | Period | 2026-03-19 14:03 | March | 2026 | 2026-03-23 12:46 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01583 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 16:54 | March | 2026 | 2026-03-30 12:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01585 | GDL17 | Residencial | 22.8 | Period | 2026-03-20 11:22 | March | 2026 | 2026-03-23 16:25 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01586 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:08 | March | 2026 | 2026-03-30 11:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01587 | GDL17 | Residencial | 5.176 | Period | 2026-03-19 16:40 | March | 2026 | 2026-03-23 10:05 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01588 | GDL17 | Residencial | 8 | Period | 2026-03-24 22:03 | March | 2026 | 2026-03-30 09:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01590 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 13:59 | March | 2026 | 2026-04-01 08:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-01594 | GDL17 | Residencial | 8 | Period | 2026-03-24 22:21 | March | 2026 | 2026-03-30 10:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01595 | GDL17 | Residencial | 8 | Period | 2026-03-19 14:22 | March | 2026 | 2026-03-20 09:31 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-01599 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 15:01 | March | 2026 | 2026-03-27 10:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 8
202603-NM25-01600 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 08:40 | March | 2026 | 2026-03-23 14:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01602 | GDL17 | Comercial | 24 | Period | 2026-03-19 16:10 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 12
202603-NM25-01604 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:35 | March | 2026 | 2026-03-25 12:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 12
202603-NM25-01606 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 09:05 | March | 2026 | 2026-04-08 11:12 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 14 | 0 | 2026-04-01 | 7
202603-NM25-01608 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 08:06 | March | 2026 | 2026-03-30 10:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01609 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 07:59 | March | 2026 | 2026-03-30 15:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 8
202603-NM25-01610 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:23 | March | 2026 | 2026-03-25 10:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 12
202603-NM25-01611 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 07:13 | March | 2026 | 2026-03-24 12:59 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01613 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:23 | March | 2026 | 2026-03-20 15:57 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 1 | 0 | 2026-04-01 | 12
202603-NM25-01614 | GDL17 | Residencial | 12 | Period | 2026-03-19 16:55 | March | 2026 | 2026-03-30 07:52 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 10 | 0 | 2026-04-01 | 12
202603-NM25-01616 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 16:45 | March | 2026 | 2026-03-23 12:36 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 3 | 1 | 2026-04-01 | 12
202603-NM25-01617 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 08:40 | March | 2026 | 2026-03-24 10:00 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01618 | GDL17 | Residencial | 3.84 | Period | 2026-03-24 07:47 | March | 2026 | 2026-04-08 09:06 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 15 | 0 | 2026-04-01 | 8
202603-NM25-01619 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:40 | March | 2026 | 2026-03-23 07:52 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01620 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:44 | March | 2026 | 2026-03-26 13:29 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 7 | 0 | 2026-04-01 | 12
202603-NM25-01621 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 15:54 | March | 2026 | 2026-03-26 11:30 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01622 | GDL17 | Residencial | 11.4 | Period | 2026-03-19 16:18 | March | 2026 | 2026-03-23 07:54 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 1 | 3 | 1 | 2026-04-01 | 12
202603-NM25-01623 | GDL17 | Residencial | 3.84 | Period | 2026-03-20 07:57 | March | 2026 | 2026-04-08 14:54 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | April |  | 19 | 3 | 2026-04-01 | 12
202603-NM25-01624 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:54 | March | 2026 | 2026-04-09 10:39 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 21 | 0 | 2026-04-01 | 12
202603-NM25-01625 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 15:54 | March | 2026 | 2026-03-23 12:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01626 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 16:23 | March | 2026 | 2026-03-31 12:35 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 3 | 2 | 10 | 2026-04-01 | 12
202603-NM25-01627 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 16:04 | March | 2026 | 2026-04-22 12:48 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 34 | 0 | 2026-04-01 | 12
202603-NM25-01630 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 16:29 | March | 2026 | 2026-03-23 14:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01631 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 07:22 | March | 2026 | 2026-04-08 10:33 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 10 | 0 | 2026-04-01 | 2
202603-NM25-01633 | GDL17 | Residencial | 11.5 | Period | 2026-03-19 16:42 | March | 2026 | 2026-03-23 14:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01634 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 14:59 | March | 2026 | 2026-04-08 15:05 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 8 | 0 | 2026-04-01 | 0
202603-NM25-01635 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 16:52 | March | 2026 | 2026-03-31 13:27 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | March | 1 | 4 | 3 | 2026-04-01 | 7
202603-NM25-01636 | GDL17 | Residencial | 8 | Period | 2026-03-24 23:19 | March | 2026 | 2026-04-09 08:57 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 16 | 0 | 2026-04-01 | 7
202603-NM25-01637 | GDL17 | Residencial | 12 | Period | 2026-03-26 10:18 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 6
202603-NM25-01638 | GDL17 | Residencial | 8 | Period | 2026-03-24 22:52 | March | 2026 | 2026-04-29 14:44 | 36 | Net Metering | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 36 | 0 | 2026-04-01 | 7
202603-NM25-01640 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 21:47 | March | 2026 | 2026-03-31 12:45 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 6
202603-NM25-01642 | GDL17 | Residencial | 6.8 | Period | 2026-03-22 20:21 | March | 2026 | 2026-03-25 09:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 9
202603-NM25-01645 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 08:33 | March | 2026 | 2026-03-26 10:33 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 12
202603-NM25-01647 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:43 | March | 2026 | 2026-03-27 16:22 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 9
202603-NM25-01649 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 08:46 | March | 2026 | 2026-03-23 11:28 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01650 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 08:52 | March | 2026 | 2026-03-25 14:51 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | March | 3 | 1 | 3 | 2026-04-01 | 12
202603-NM25-01652 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:06 | March | 2026 | 2026-03-23 14:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01653 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:15 | March | 2026 | 2026-03-25 14:31 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 12
202603-NM25-01655 | GDL17 | Residencial | 13.056 | Period | 2026-03-20 09:33 | March | 2026 | 2026-03-23 13:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01657 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:27 | March | 2026 | 2026-03-24 11:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01658 | GDL17 | Residencial | 13.6 | Period | 2026-03-20 14:52 | March | 2026 | 2026-03-23 16:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 11
202603-NM25-01659 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:39 | March | 2026 | 2026-04-23 15:06 | 34 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | SAN JUAN | April |  | 34 | 0 | 2026-04-01 | 12
202603-NM25-01661 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:08 | March | 2026 | 2026-03-25 08:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 12
202603-NM25-01662 | GDL17 | Residencial | 5.28 | Period | 2026-03-25 18:46 | March | 2026 | 2026-03-30 11:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01663 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:50 | March | 2026 | 2026-03-25 14:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 12
202603-NM25-01664 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 09:59 | March | 2026 | 2026-03-27 11:21 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 12
202603-NM25-01665 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:20 | March | 2026 | 2026-04-09 10:31 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 20 | 0 | 2026-04-01 | 12
202603-NM25-01666 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:10 | March | 2026 | 2026-03-30 16:15 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 10 | 0 | 2026-04-01 | 12
202603-NM25-01667 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:36 | March | 2026 | 2026-03-25 16:08 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 12
202603-NM25-01668 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:28 | March | 2026 | 2026-03-25 13:16 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 12
202603-NM25-01670 | GDL17 | Residencial | 11.4 | Period | 2026-03-20 10:54 | March | 2026 | 2026-03-31 10:14 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 11 | 0 | 2026-04-01 | 12
202603-NM25-01671 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 10:59 | March | 2026 | 2026-03-23 16:12 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01672 | GDL17 | Residencial | 7.566 | Period | 2026-03-20 11:38 | March | 2026 | 2026-03-23 14:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01673 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:18 | March | 2026 | 2026-04-06 07:53 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | MAYAGUEZ | April |  | 16 | 1 | 2026-04-01 | 12
202603-NM25-01674 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 10:07 | March | 2026 | 2026-04-13 08:57 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 21 | 0 | 2026-04-01 | 9
202603-NM25-01676 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:21 | March | 2026 | 2026-03-26 07:54 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 12
202603-NM25-01678 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 12:21 | March | 2026 | 2026-04-02 09:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-01679 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:00 | March | 2026 | 2026-03-27 07:48 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01680 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:36 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 12
202603-NM25-01682 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 12:17 | March | 2026 | 2026-03-25 15:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 11
202603-NM25-01683 | GDL17 | Residencial | 8.192 | Period | 2026-03-20 11:43 | March | 2026 | 2026-03-23 14:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01684 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 11:56 | March | 2026 | 2026-03-23 15:58 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 12
202603-NM25-01685 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 10:21 | March | 2026 | 2026-03-26 14:08 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 9
202603-NM25-01686 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 12:22 | March | 2026 | 2026-03-23 14:36 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 11
202603-NM25-01687 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 12:45 | March | 2026 | 2026-03-25 09:50 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 11
202603-NM25-01689 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 09:52 | March | 2026 | 2026-03-30 09:34 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-01691 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:33 | March | 2026 | 2026-03-25 13:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 11
202603-NM25-01692 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 15:10 | March | 2026 | 2026-04-02 13:55 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-01693 | GDL17 | Residencial | 7.8 | Period | 2026-03-20 13:45 | March | 2026 | 2026-03-24 08:32 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 11
202603-NM25-01694 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 13:44 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 11
202603-NM25-01695 | GDL17 | Residencial | 13.824 | Period | 2026-03-23 15:43 | March | 2026 | 2026-03-26 12:42 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01696 | GDL17 | Residencial | 3.84 | Period | 2026-03-24 11:47 | March | 2026 | 2026-03-31 08:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 8
202603-NM25-01697 | GDL17 | Residencial | 24 | Period | 2026-03-27 13:10 | March | 2026 | 2026-04-01 14:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-01698 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 14:41 | March | 2026 | 2026-03-25 08:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 11
202603-NM25-01700 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 15:45 | March | 2026 | 2026-03-26 08:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 11
202603-NM25-01701 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 09:33 | March | 2026 | 2026-04-07 14:39 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 9 | 0 | 2026-04-01 | 2
202603-NM25-01702 | GDL17 | Residencial | 5.76 | Period | 2026-03-25 18:58 | March | 2026 | 2026-03-30 13:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01703 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 14:08 | March | 2026 | 2026-04-06 09:26 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 1
202603-NM25-01704 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 15:34 | March | 2026 | 2026-03-25 10:28 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 11
202603-NM25-01705 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 16:47 | March | 2026 | 2026-03-31 12:37 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-01707 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 15:41 | March | 2026 | 2026-03-24 13:33 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 11
202603-NM25-01708 | GDL17 | Residencial | 9 | Period | 2026-03-23 09:53 | March | 2026 | 2026-03-25 15:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01710 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 14:11 | March | 2026 | 2026-03-31 14:48 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 4
202603-NM25-01714 | GDL17 | Residencial | 9.852 | Period | 2026-03-20 16:23 | March | 2026 | 2026-03-24 13:37 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 11
202603-NM25-01720 | GDL17 | Residencial | 3.072 | Period | 2026-03-20 16:35 | March | 2026 | 2026-03-26 09:33 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 11
202603-NM25-01725 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 16:57 | March | 2026 | 2026-04-08 15:40 | 15 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 15 | 0 | 2026-04-01 | 7
202603-NM25-01726 | GDL17 | Residencial | 11.5 | Period | 2026-03-20 17:49 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 11
202603-NM25-01733 | GDL17 | Residencial | 10 | Period | 2026-03-23 10:02 | March | 2026 | 2026-03-25 07:53 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01740 | GDL17 | Residencial | 12 | Period | 2026-03-23 11:38 | March | 2026 | 2026-03-27 16:02 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 9
202603-NM25-01746 | GDL17 | Residencial | 3.8 | Period | 2026-03-25 07:55 | March | 2026 | 2026-03-30 10:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01747 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 15:44 | March | 2026 | 2026-03-30 14:22 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | March | 1 | 5 | 2 | 2026-04-01 | 8
202603-NM25-01748 | GDL17 | Residencial | 12 | Period | 2026-03-21 12:58 | March | 2026 | 2026-03-25 10:07 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 10
202603-NM25-01749 | GDL17 | Residencial | 12 | Period | 2026-03-26 10:16 | March | 2026 | 2026-03-31 13:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01751 | GDL17 | Residencial | 15 | Period | 2026-03-27 17:10 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 4
202603-NM25-01752 | GDL17 | Residencial | 12 | Period | 2026-03-21 21:06 | March | 2026 | 2026-03-24 07:55 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 10
202603-NM25-01753 | GDL17 | Residencial | 12 | Period | 2026-03-23 17:29 | March | 2026 | 2026-03-26 09:38 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01754 | GDL17 | Residencial | 12 | Period | 2026-03-23 17:55 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 8
202603-NM25-01755 | GDL17 | Residencial | 24 | Period | 2026-03-25 09:51 | March | 2026 | 2026-03-31 13:14 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | March | 1 | 4 | 2 | 2026-04-01 | 7
202603-NM25-01757 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 08:28 | March | 2026 | 2026-03-24 12:55 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01759 | GDL17 | Residencial | 13.041 | Period | 2026-03-23 08:53 | March | 2026 | 2026-03-24 12:48 | 1 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 1 | 0 | 2026-04-01 | 9
202603-NM25-01764 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:05 | March | 2026 | 2026-03-27 07:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01766 | GDL17 | Residencial | 23 | Period | 2026-03-24 10:47 | March | 2026 | 2026-04-14 07:44 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 21 | 0 | 2026-04-01 | 8
202603-NM25-01769 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:20 | March | 2026 | 2026-03-25 14:01 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01770 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:22 | March | 2026 | 2026-03-25 13:59 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01771 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:39 | March | 2026 | 2026-03-25 15:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01773 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:41 | March | 2026 | 2026-03-31 14:07 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 8 | 0 | 2026-04-01 | 9
202603-NM25-01777 | GDL17 | Residencial | 7.6 | Period | 2026-03-23 10:02 | March | 2026 | 2026-03-25 16:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01779 | GDL17 | Residencial | 7.6 | Period | 2026-03-25 14:18 | March | 2026 | 2026-04-14 14:50 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | April |  | 20 | 15 | 2026-04-01 | 6
202603-NM25-01781 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 09:59 | March | 2026 | 2026-03-27 15:27 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 9
202603-NM25-01783 | GDL17 | Residencial | 3.66 | Period | 2026-03-23 10:08 | March | 2026 | 2026-03-25 16:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01785 | GDL17 | Residencial | 4.608 | Period | 2026-03-23 10:12 | March | 2026 | 2026-03-25 16:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01786 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 10:55 | March | 2026 | 2026-03-25 11:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 9
202603-NM25-01788 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 10:22 | March | 2026 | 2026-03-30 09:38 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 9
202603-NM25-01793 | GDL17 | Residencial | 23 | Period | 2026-03-23 11:16 | March | 2026 | 2026-03-25 15:57 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01800 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 10:49 | March | 2026 | 2026-03-25 16:03 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 9
202603-NM25-01805 | GDL17 | Comercial | 3.8 | Period | 2026-03-24 07:31 | March | 2026 | 2026-03-30 12:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 7 | 0 | 2026-04-01 | 8
202603-NM25-01809 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:11 | March | 2026 | 2026-03-30 10:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01813 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 11:50 | March | 2026 | 2026-03-25 15:51 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 9
202603-NM25-01814 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 16:09 | March | 2026 | 2026-04-06 09:33 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 10 | 0 | 2026-04-01 | 4
202603-NM25-01815 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:15 | March | 2026 | 2026-03-25 15:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 2 | 0 | 2026-04-01 | 8
202603-NM25-01819 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 07:15 | March | 2026 | 2026-03-31 14:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01820 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:50 | March | 2026 | 2026-03-26 10:17 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01822 | GDL17 | Residencial | 6.701 | Period | 2026-03-24 11:04 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 8
202603-NM25-01824 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:26 | March | 2026 | 2026-03-25 15:18 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 2 | 0 | 2026-04-01 | 8
202603-NM25-01830 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:37 | March | 2026 | 2026-03-26 10:14 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01831 | GDL17 | Residencial | 11.4 | Period | 2026-03-30 00:02 | March | 2026 | 2026-04-01 15:02 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 3 | 0 | 2026-04-01 | 2
202603-NM25-01833 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:48 | March | 2026 | 2026-03-25 15:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 2 | 0 | 2026-04-01 | 8
202603-NM25-01834 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:49 | March | 2026 | 2026-03-25 15:37 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 2 | 0 | 2026-04-01 | 8
202603-NM25-01837 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 12:58 | March | 2026 | 2026-04-06 14:10 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 14 | 0 | 2026-04-01 | 8
202603-NM25-01842 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 15:37 | March | 2026 | 2026-03-26 13:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01845 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:38 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 8
202603-NM25-01848 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:00 | March | 2026 | 2026-03-30 10:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 7 | 0 | 2026-04-01 | 8
202603-NM25-01850 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:45 | March | 2026 | 2026-03-30 08:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01851 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:57 | March | 2026 | 2026-04-08 16:21 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 16 | 0 | 2026-04-01 | 8
202603-NM25-01852 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 10:39 | March | 2026 | 2026-03-27 15:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01854 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 14:08 | March | 2026 | 2026-04-10 08:42 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 11 | 0 | 2026-04-01 | 1
202603-NM25-01855 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 13:59 | March | 2026 | 2026-03-30 08:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-01856 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 11:23 | March | 2026 | 2026-04-10 14:49 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | April |  | 17 | 12 | 2026-04-01 | 8
202603-NM25-01857 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 12:52 | March | 2026 | 2026-03-30 12:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01858 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:45 | March | 2026 | 2026-04-13 08:22 | 20 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 20 | 0 | 2026-04-01 | 7
202603-NM25-01860 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 14:45 | March | 2026 | 2026-03-26 10:27 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01861 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 08:13 | March | 2026 | 2026-03-31 14:17 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-01862 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 10:58 | March | 2026 | 2026-04-13 09:01 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 17 | 0 | 2026-04-01 | 5
202603-NM25-01863 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 15:01 | March | 2026 | 2026-03-30 15:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 8
202603-NM25-01866 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 10:23 | March | 2026 | 2026-04-09 08:33 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 13 | 0 | 2026-04-01 | 5
202603-NM25-01867 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 13:23 | March | 2026 | 2026-03-30 10:25 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01868 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 15:23 | March | 2026 | 2026-03-31 09:01 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 8 | 0 | 2026-04-01 | 8
202603-NM25-01869 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 14:04 | March | 2026 | 2026-03-30 09:44 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01872 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 15:35 | March | 2026 | 2026-03-26 13:03 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01873 | GDL17 | Residencial | 18.028 | Period | 2026-03-23 15:50 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 8
202603-NM25-01874 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 07:39 | March | 2026 | 2026-03-31 14:04 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-01875 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:01 | March | 2026 | 2026-03-26 11:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01876 | GDL17 | Residencial | 12.72 | Period | 2026-03-25 17:52 | March | 2026 | 2026-03-30 13:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01877 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:11 | March | 2026 | 2026-03-26 16:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01878 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:10 | March | 2026 | 2026-03-26 11:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01879 | GDL17 | Residencial | 11.4 | Period | 2026-03-23 16:37 | March | 2026 | 2026-03-27 08:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01880 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 17:55 | March | 2026 | 2026-04-07 14:24 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 8 | 0 | 2026-04-01 | 1
202603-NM25-01881 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:23 | March | 2026 | 2026-03-27 09:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 8
202603-NM25-01882 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:25 | March | 2026 | 2026-03-26 12:50 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01883 | GDL17 | Comercial | 24 | Period | 2026-03-26 15:09 | March | 2026 | 2026-04-08 10:53 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 13 | 0 | 2026-04-01 | 5
202603-NM25-01884 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:28 | March | 2026 | 2026-04-10 14:44 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 18 | 0 | 2026-04-01 | 8
202603-NM25-01885 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:33 | March | 2026 | 2026-03-27 11:03 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 8
202603-NM25-01886 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:39 | March | 2026 | 2026-03-26 12:59 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01887 | GDL17 | Residencial | 8.56 | Period | 2026-03-23 16:40 | March | 2026 | 2026-03-26 13:00 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01888 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:43 | March | 2026 | 2026-03-26 08:41 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 2 | 0 | 2026-04-01 | 8
202603-NM25-01890 | GDL17 | Residencial | 11.5 | Period | 2026-03-23 16:50 | March | 2026 | 2026-04-08 08:08 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 15 | 0 | 2026-04-01 | 8
202603-NM25-01891 | GDL17 | Residencial | 11.44 | Period | 2026-03-24 14:45 | March | 2026 | 2026-03-30 09:50 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01896 | GDL17 | Residencial | 12 | Period | 2026-03-24 20:07 | March | 2026 | 2026-03-30 10:22 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01897 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:00 | March | 2026 | 2026-03-31 10:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01898 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:19 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 8
202603-NM25-01900 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:31 | March | 2026 | 2026-03-27 07:53 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01901 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:31 | March | 2026 | 2026-03-27 07:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01902 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:43 | March | 2026 | 2026-03-27 07:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01903 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:58 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 8
202603-NM25-01904 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 08:57 | March | 2026 | 2026-03-27 07:49 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01906 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:15 | March | 2026 | 2026-03-27 07:47 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01908 | GDL17 | Residencial | 4.758 | Period | 2026-03-24 09:18 | March | 2026 | 2026-03-30 13:36 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-01909 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:28 | March | 2026 | 2026-04-06 14:34 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 13 | 0 | 2026-04-01 | 8
202603-NM25-01910 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:44 | March | 2026 | 2026-03-30 14:07 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01912 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:34 | March | 2026 | 2026-03-27 15:29 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01914 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:36 | March | 2026 | 2026-04-02 13:36 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-01915 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 09:54 | March | 2026 | 2026-03-27 07:44 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01926 | GDL17 | Residencial | 11.4 | Period | 2026-03-24 11:44 | March | 2026 | 2026-03-30 10:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-01927 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:18 | March | 2026 | 2026-03-27 15:51 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01928 | GDL17 | Comercial | 6.528 | Period | 2026-03-24 11:20 | March | 2026 | 2026-04-24 14:21 | 31 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | PONCE | April |  | 31 | 14 | 2026-04-01 | 8
202603-NM25-01931 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:22 | March | 2026 | 2026-03-27 15:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01932 | GDL17 | Residencial | 4.224 | Period | 2026-03-25 14:10 | March | 2026 | 2026-03-30 12:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01934 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:28 | March | 2026 | 2026-03-27 14:16 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01935 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 11:31 | March | 2026 | 2026-03-27 15:52 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 3 | 0 | 2026-04-01 | 8
202603-NM25-01936 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:46 | March | 2026 | 2026-03-30 10:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-01937 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:42 | March | 2026 | 2026-03-30 10:30 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 8
202603-NM25-01938 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 11:56 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 8
202603-NM25-01939 | GDL17 | Residencial | 24 | Period | 2026-03-28 13:20 | March | 2026 | 2026-04-01 15:13 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 4 | 0 | 2026-04-01 | 3
202603-NM25-01941 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:28 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 7
202603-NM25-01942 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:11 | March | 2026 | 2026-03-30 11:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-01943 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 10:43 | March | 2026 | 2026-04-01 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-01944 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 12:02 | March | 2026 | 2026-03-31 11:13 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 7 | 0 | 2026-04-01 | 7
202603-NM25-01947 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 12:40 | March | 2026 | 2026-03-30 08:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01952 | GDL17 | Residencial | 3.8 | Period | 2026-03-27 07:56 | March | 2026 | 2026-04-13 16:10 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 17 | 0 | 2026-04-01 | 5
202603-NM25-01953 | GDL17 | Residencial | 23 | Period | 2026-03-24 13:20 | March | 2026 | 2026-03-30 11:00 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01954 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 12:49 | March | 2026 | 2026-03-30 11:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01955 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:32 | March | 2026 | 2026-03-30 12:38 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01956 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 13:11 | March | 2026 | 2026-03-31 12:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-01957 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 13:02 | March | 2026 | 2026-03-30 11:27 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01958 | GDL17 | Gubernamental | 23 | Period | 2026-03-24 15:48 | March | 2026 | 2026-03-30 13:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01959 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 07:51 | March | 2026 | 2026-04-07 16:18 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 1
202603-NM25-01960 | GDL17 | Comercial | 11.5 | Period | 2026-03-26 15:34 | March | 2026 | 2026-04-09 09:36 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 14 | 0 | 2026-04-01 | 5
202603-NM25-01963 | GDL17 | Residencial | 11.4 | Period | 2026-03-24 15:56 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 7
202603-NM25-01964 | GDL17 | Residencial | 7.68 | Period | 2026-03-25 14:33 | March | 2026 | 2026-04-07 10:49 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 13 | 0 | 2026-04-01 | 6
202603-NM25-01965 | GDL17 | Residencial | 3.8 | Period | 2026-03-31 11:18 | March | 2026 | 2026-04-24 10:23 | 24 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 24 | 0 | 2026-04-01 | 1
202603-NM25-01967 | GDL17 | Residencial | 7.6 | Period | 2026-03-31 12:45 | March | 2026 | 2026-04-08 13:39 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 8 | 0 | 2026-04-01 | 0
202603-NM25-01968 | GDL17 | Residencial | 10.79 | Period | 2026-03-24 13:53 | March | 2026 | 2026-03-30 09:43 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01970 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 07:37 | March | 2026 | 2026-03-31 13:53 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-01972 | GDL17 | Residencial | 14.74 | Period | 2026-03-24 15:48 | March | 2026 | 2026-03-30 10:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01973 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 14:38 | March | 2026 | 2026-03-30 09:48 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01974 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:49 | March | 2026 | 2026-03-30 12:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01975 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:51 | March | 2026 | 2026-04-10 09:55 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 11 | 0 | 2026-04-01 | 2
202603-NM25-01978 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 14:54 | March | 2026 | 2026-03-30 09:51 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01979 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:03 | March | 2026 | 2026-03-27 15:45 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 3 | 0 | 2026-04-01 | 7
202603-NM25-01980 | GDL17 | Residencial | 15.16 | Period | 2026-03-25 09:02 | March | 2026 | 2026-03-31 15:13 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01982 | GDL17 | Residencial | 7.6 | Period | 2026-03-24 16:23 | March | 2026 | 2026-04-01 15:29 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 8 | 0 | 2026-04-01 | 7
202603-NM25-01983 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 08:51 | March | 2026 | 2026-04-07 15:44 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | April |  | 11 | 0 | 2026-04-01 | 5
202603-NM25-01985 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:14 | March | 2026 | 2026-03-31 11:25 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 7 | 0 | 2026-04-01 | 7
202603-NM25-01986 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:24 | March | 2026 | 2026-04-09 15:47 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 16 | 0 | 2026-04-01 | 7
202603-NM25-01987 | GDL17 | Residencial | 13.824 | Period | 2026-03-26 08:08 | March | 2026 | 2026-04-01 13:12 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | April |  | 6 | 0 | 2026-04-01 | 6
202603-NM25-01989 | GDL17 | Residencial | 3.84 | Period | 2026-03-24 15:19 | March | 2026 | 2026-03-27 15:01 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 3 | 0 | 2026-04-01 | 7
202603-NM25-01990 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:19 | March | 2026 | 2026-03-30 10:01 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01991 | GDL17 | Comercial | 24 | Period | 2026-03-27 14:45 | March | 2026 | 2026-04-01 15:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-01995 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 15:43 | March | 2026 | 2026-04-02 08:39 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 9 | 0 | 2026-04-01 | 7
202603-NM25-01996 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 15:32 | March | 2026 | 2026-03-30 12:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-01997 | GDL17 | Residencial | 9.74 | Period | 2026-03-24 15:51 | March | 2026 | 2026-03-30 10:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-01999 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 16:09 | March | 2026 | 2026-03-30 13:08 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-02001 | GDL17 | Residencial | 11.5 | Period | 2026-03-24 16:35 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 7
202603-NM25-02002 | GDL17 | Residencial | 8.23 | Period | 2026-03-24 16:08 | March | 2026 | 2026-03-30 10:10 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-02005 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:02 | March | 2026 | 2026-04-07 14:11 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | April |  | 13 | 3 | 2026-04-01 | 6
202603-NM25-02006 | GDL17 | Residencial | 23 | Period | 2026-03-24 16:23 | March | 2026 | 2026-04-07 13:32 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 14 | 0 | 2026-04-01 | 7
202603-NM25-02007 | GDL17 | Residencial | 12 | Period | 2026-03-31 19:01 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 0
202603-NM25-02011 | GDL17 | Residencial | 5.17 | Period | 2026-03-24 17:33 | March | 2026 | 2026-03-30 10:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-02013 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 13:55 | March | 2026 | 2026-04-01 14:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02014 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:26 | March | 2026 | 2026-03-30 13:57 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-02016 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:58 | March | 2026 | 2026-03-30 13:14 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-02017 | GDL17 | Residencial | 8.85 | Period | 2026-03-24 18:24 | March | 2026 | 2026-03-30 10:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-02018 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:15 | March | 2026 | 2026-03-30 13:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-02019 | GDL17 | Residencial | 8 | Period | 2026-03-25 09:00 | March | 2026 | 2026-03-31 08:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-02020 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:35 | March | 2026 | 2026-03-31 13:33 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02026 | GDL17 | Residencial | 8.064 | Period | 2026-03-25 08:52 | March | 2026 | 2026-03-30 10:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02028 | GDL17 | Residencial | 8 | Period | 2026-03-25 11:36 | March | 2026 | 2026-03-30 11:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02029 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 10:38 | March | 2026 | 2026-03-30 10:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02031 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:35 | March | 2026 | 2026-04-01 09:09 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 6 | 0 | 2026-04-01 | 6
202603-NM25-02032 | GDL17 | Residencial | 19.1 | Period | 2026-03-25 10:21 | March | 2026 | 2026-03-30 10:48 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02033 | GDL17 | Residencial | 4.224 | Period | 2026-03-26 14:01 | March | 2026 | 2026-03-31 14:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02034 | GDL17 | Residencial | 5.926 | Period | 2026-03-25 09:54 | March | 2026 | 2026-03-30 10:29 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02035 | GDL17 | Residencial | 6.912 | Period | 2026-03-26 13:33 | March | 2026 | 2026-03-31 13:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02042 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:03 | March | 2026 | 2026-03-30 15:47 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02047 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:20 | March | 2026 | 2026-03-30 11:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02048 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 10:42 | March | 2026 | 2026-04-08 16:28 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 9 | 0 | 2026-04-01 | 2
202603-NM25-02049 | GDL17 | Residencial | 13.072 | Period | 2026-03-25 11:34 | March | 2026 | 2026-03-31 13:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 6 | 0 | 2026-04-01 | 7
202603-NM25-02050 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:32 | March | 2026 | 2026-03-30 15:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02051 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 11:56 | March | 2026 | 2026-03-30 11:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 7
202603-NM25-02057 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 12:00 | March | 2026 | 2026-04-13 07:56 | 19 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 19 | 0 | 2026-04-01 | 7
202603-NM25-02058 | GDL17 | Residencial | 15.89 | Period | 2026-03-25 12:10 | March | 2026 | 2026-03-30 12:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02062 | GDL17 | Residencial | 5.076 | Period | 2026-03-25 12:41 | March | 2026 | 2026-03-30 12:40 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02063 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 15:33 | March | 2026 | 2026-04-29 10:06 | 35 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 34 | 0 | 2026-04-01 | 6
202603-NM25-02067 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:16 | March | 2026 | 2026-04-07 15:17 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 12 | 0 | 2026-04-01 | 6
202603-NM25-02070 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:24 | March | 2026 | 2026-03-30 12:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02071 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:30 | March | 2026 | 2026-03-30 12:45 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02074 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:31 | March | 2026 | 2026-03-30 12:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02075 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:48 | March | 2026 | 2026-03-31 13:52 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02076 | GDL17 | Residencial | 7.68 | Period | 2026-03-25 14:32 | March | 2026 | 2026-03-30 12:53 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02077 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 13:53 | March | 2026 |  |  | Cancelled | Estudio (E) | Backlog |  | No | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 6
202603-NM25-02080 | GDL17 | Residencial | 12 | Period | 2026-03-27 15:56 | March | 2026 | 2026-04-08 11:08 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 12 | 0 | 2026-04-01 | 4
202603-NM25-02082 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:20 | March | 2026 | 2026-03-30 12:54 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02084 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:56 | March | 2026 | 2026-04-01 14:04 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | April |  | 6 | 1 | 2026-04-01 | 6
202603-NM25-02086 | GDL17 | Residencial | 7.6 | Period | 2026-03-25 14:28 | March | 2026 | 2026-03-30 12:46 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02088 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 14:39 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 6
202603-NM25-02090 | GDL17 | Comercial | 20.256 | Period | 2026-03-25 15:22 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 6
202603-NM25-02092 | GDL17 | Residencial | 8 | Period | 2026-03-25 15:46 | March | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 6
202603-NM25-02095 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 15:24 | March | 2026 | 2026-03-30 12:56 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02096 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 15:27 | March | 2026 | 2026-04-08 14:21 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 14 | 0 | 2026-04-01 | 6
202603-NM25-02097 | GDL17 | Residencial | 7.08 | Period | 2026-03-25 15:42 | March | 2026 | 2026-03-30 12:57 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02099 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 09:57 | March | 2026 | 2026-04-02 09:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02102 | GDL17 | Comercial | 18 | Period | 2026-03-27 19:19 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 4
202603-NM25-02104 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 16:32 | March | 2026 | 2026-03-30 12:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02105 | GDL17 | Residencial | 15.16 | Period | 2026-03-25 16:48 | March | 2026 | 2026-03-30 12:59 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02109 | GDL17 | Residencial | 12 | Period | 2026-03-25 21:53 | March | 2026 | 2026-03-30 13:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02111 | GDL17 | Residencial | 11.5 | Period | 2026-03-25 17:15 | March | 2026 | 2026-04-01 07:50 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 6
202603-NM25-02113 | GDL17 | Residencial | 10.368 | Period | 2026-03-27 15:14 | March | 2026 | 2026-03-31 16:09 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 4
202603-NM25-02120 | GDL17 | Residencial | 16 | Period | 2026-03-28 13:50 | March | 2026 | 2026-04-01 15:16 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 4 | 0 | 2026-04-01 | 3
202603-NM25-02121 | GDL17 | Residencial | 11.4 | Period | 2026-03-26 22:47 | March | 2026 | 2026-04-02 09:37 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | SAN JUAN | April |  | 7 | 2 | 2026-04-01 | 5
202603-NM25-02126 | GDL17 | Residencial | 8.022 | Period | 2026-03-26 08:42 | March | 2026 | 2026-03-30 13:47 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-02127 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 08:41 | March | 2026 | 2026-03-30 13:24 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-02129 | GDL17 | Residencial | 6.822 | Period | 2026-03-26 09:07 | March | 2026 | 2026-04-07 16:13 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 12 | 0 | 2026-04-01 | 6
202603-NM25-02130 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 09:46 | March | 2026 | 2026-04-01 15:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 3 | 0 | 2026-04-01 | 2
202603-NM25-02131 | GDL17 | Residencial | 15.2 | Period | 2026-03-31 09:55 | March | 2026 | 2026-04-02 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02132 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 16:03 | March | 2026 | 2026-04-02 09:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02133 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:33 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 6
202603-NM25-02134 | GDL17 | Residencial | 12.99 | Period | 2026-03-26 09:28 | March | 2026 | 2026-03-30 13:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-02135 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:39 | March | 2026 | 2026-03-30 13:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-02136 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:31 | March | 2026 | 2026-04-02 11:11 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 7 | 0 | 2026-04-01 | 6
202603-NM25-02137 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 09:32 | March | 2026 | 2026-03-30 14:06 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 6
202603-NM25-02139 | GDL17 | Residencial | 4.392 | Period | 2026-03-31 12:48 | March | 2026 | 2026-04-02 15:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02140 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 14:17 | March | 2026 | 2026-03-31 14:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02143 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 06:37 | March | 2026 | 2026-04-02 09:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02144 | GDL17 | Residencial | 10.6 | Period | 2026-03-26 11:01 | March | 2026 | 2026-03-31 13:00 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02146 | GDL17 | Residencial | 7.6 | Period | 2026-03-26 12:30 | March | 2026 | 2026-03-31 13:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02147 | GDL17 | Residencial | 3.54 | Period | 2026-03-26 10:30 | March | 2026 | 2026-03-31 13:39 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02150 | GDL17 | Residencial | 16 | Period | 2026-03-26 12:15 | March | 2026 | 2026-04-01 08:29 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02151 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:54 | March | 2026 | 2026-03-31 13:10 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02152 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 10:41 | March | 2026 | 2026-03-31 13:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02153 | GDL17 | Residencial | 8 | Period | 2026-03-26 11:19 | March | 2026 | 2026-03-31 14:21 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02156 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:53 | March | 2026 | 2026-04-01 16:14 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02157 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 11:08 | March | 2026 | 2026-04-06 09:00 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 10 | 0 | 2026-04-01 | 6
202603-NM25-02159 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 11:22 | March | 2026 | 2026-03-31 14:17 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02161 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 11:11 | March | 2026 | 2026-03-31 12:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 6
202603-NM25-02165 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 13:33 | March | 2026 | 2026-04-02 09:19 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02168 | GDL17 | Residencial | 24 | Period | 2026-03-30 11:53 | March | 2026 | 2026-04-01 14:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 2
202603-NM25-02170 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 15:29 | March | 2026 | 2026-04-02 13:43 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02173 | GDL17 | Residencial | 3.072 | Period | 2026-03-26 12:42 | March | 2026 | 2026-04-27 14:50 | 32 | Study | Estudio (E) | Activated | Backlog | Yes | Yes | Yes |  | MAYAGUEZ | April |  | 32 | 0 | 2026-04-01 | 5
202603-NM25-02179 | GDL17 | Residencial | 6.195 | Period | 2026-03-26 13:52 | March | 2026 | 2026-03-31 11:15 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02182 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 13:31 | March | 2026 | 2026-03-31 15:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02184 | GDL17 | Residencial | 8.448 | Period | 2026-03-26 13:40 | March | 2026 | 2026-03-31 12:58 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02188 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:21 | March | 2026 | 2026-04-08 09:46 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 12 | 0 | 2026-04-01 | 5
202603-NM25-02189 | GDL17 | Residencial | 15 | Period | 2026-03-26 14:30 | March | 2026 | 2026-03-31 14:18 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02194 | GDL17 | Residencial | 7.6 | Period | 2026-03-31 13:05 | March | 2026 | 2026-04-08 15:56 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 8 | 0 | 2026-04-01 | 0
202603-NM25-02195 | GDL17 | Residencial | 4.546 | Period | 2026-03-26 15:01 | March | 2026 | 2026-03-31 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02196 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 15:18 | March | 2026 | 2026-03-31 14:22 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02198 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 15:20 | March | 2026 | 2026-03-31 14:24 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02200 | GDL17 | Residencial | 4.25 | Period | 2026-03-26 15:32 | March | 2026 | 2026-03-31 14:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02203 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 15:27 | March | 2026 | 2026-03-31 10:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02204 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 10:49 | March | 2026 | 2026-03-31 16:18 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-02205 | GDL17 | Residencial | 9.136 | Period | 2026-03-26 15:33 | March | 2026 | 2026-03-31 14:25 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02206 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 15:38 | March | 2026 | 2026-03-31 14:26 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02207 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:33 | March | 2026 | 2026-04-01 14:38 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02212 | GDL17 | Residencial | 23 | Period | 2026-03-26 15:45 | March | 2026 | 2026-03-31 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02213 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 15:48 | March | 2026 | 2026-03-31 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02216 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 16:01 | March | 2026 | 2026-03-31 14:27 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02218 | GDL17 | Residencial | 11.5 | Period | 2026-03-26 16:33 | March | 2026 | 2026-04-01 16:06 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 6 | 0 | 2026-04-01 | 5
202603-NM25-02219 | GDL17 | Residencial | 7.6 | Period | 2026-03-26 16:12 | March | 2026 | 2026-04-01 16:21 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 6 | 0 | 2026-04-01 | 5
202603-NM25-02224 | GDL17 | Residencial | 5.124 | Period | 2026-03-26 16:35 | March | 2026 | 2026-03-31 12:35 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02231 | GDL17 | Residencial | 9 | Period | 2026-03-26 21:07 | March | 2026 | 2026-03-31 12:43 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | March |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02232 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 08:40 | March | 2026 | 2026-03-31 14:19 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-02233 | GDL17 | Residencial | 5.49 | Period | 2026-03-27 08:41 | March | 2026 | 2026-03-31 14:20 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-02234 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 08:43 | March | 2026 | 2026-03-31 14:21 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-02237 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 09:12 | March | 2026 | 2026-03-31 14:25 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | March |  | 4 | 0 | 2026-04-01 | 5
202603-NM25-02238 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 12:28 | March | 2026 | 2026-04-01 14:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02241 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 10:38 | March | 2026 | 2026-04-01 14:09 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02245 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 10:54 | March | 2026 | 2026-04-06 16:07 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 10 | 0 | 2026-04-01 | 5
202603-NM25-02247 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 09:54 | March | 2026 | 2026-04-02 07:58 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02248 | GDL17 | Residencial | 7.6 | Period | 2026-03-27 14:44 | March | 2026 | 2026-04-14 13:29 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | ARECIBO | April |  | 18 | 0 | 2026-04-01 | 4
202603-NM25-02249 | GDL17 | Residencial | 8 | Period | 2026-03-27 11:05 | March | 2026 |  |  | NM Representative Review General Info | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 5
202603-NM25-02253 | GDL17 | Residencial | 3.456 | Period | 2026-03-27 11:33 | March | 2026 | 2026-04-01 14:30 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02254 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 11:50 | March | 2026 | 2026-04-01 14:44 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 5 | 0 | 2026-04-01 | 5
202603-NM25-02256 | GDL17 | Comercial | 18 | Period | 2026-03-28 15:36 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 3
202603-NM25-02261 | GDL17 | Residencial | 5.49 | Period | 2026-03-27 13:29 | March | 2026 | 2026-03-31 15:56 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | March |  | 4 | 0 | 2026-04-01 | 4
202603-NM25-02262 | GDL17 | Residencial | 9.136 | Period | 2026-03-27 13:38 | March | 2026 | 2026-04-01 14:49 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02264 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 13:52 | March | 2026 | 2026-04-02 16:20 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 6 | 0 | 2026-04-01 | 4
202603-NM25-02265 | GDL17 | Comercial | 11.5 | Period | 2026-03-27 14:47 | March | 2026 | 2026-04-01 15:02 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02266 | GDL17 | Residencial | 11.4 | Period | 2026-03-27 14:49 | March | 2026 | 2026-04-07 16:16 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | CAGUAS | April |  | 11 | 7 | 2026-04-01 | 4
202603-NM25-02267 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 14:40 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 4
202603-NM25-02268 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:17 | March | 2026 | 2026-04-07 08:29 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 2
202603-NM25-02269 | GDL17 | Residencial | 10.752 | Period | 2026-03-27 15:01 | March | 2026 | 2026-04-02 09:28 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 6 | 0 | 2026-04-01 | 4
202603-NM25-02271 | GDL17 | Residencial | 13.026 | Period | 2026-03-27 14:33 | March | 2026 | 2026-04-01 15:01 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02274 | GDL17 | Residencial | 23 | Period | 2026-03-31 10:28 | March | 2026 | 2026-04-08 16:19 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 8 | 0 | 2026-04-01 | 1
2024-GD-00060 | GD1M | Comercial | 396 | Out of period | 2024-01-27 | January | 2024 |  |  | Finalizar estudio o indicar pago por mejora | Estudio Suplementario (ES) | Backlog |  |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 795
2024-GD-00181 | GD1M | Residencial | 27.65 | Out of period | 2024-05-02 | May | 2024 |  |  | Finalizar estudio o indicar pago por mejora | Estudio Suplementario (ES) | Backlog |  |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 699
2023-GD-05043 | GD1M | Residencial | 30 | Out of period | 2023-09-11 | September | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 933
2022-GD-29558 | GD1M | Comercial | 35.72 | Out of period | 2022-12-01 | December | 2022 |  |  | Anejar Documentos | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1217
2023-GD-07137 | GD1M | Comercial | 30 | Out of period | 2023-03-11 | March | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1117
2023-GD-05969 | GD1M | Comercial | 81.35 | Out of period | 2023-02-28 | February | 2023 |  |  | Anejar Documentos | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1128
2023-GD-05552 | GD1M | Comercial | 36 | Out of period | 2023-02-23 | February | 2023 |  |  | Anejar Documentos | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1133
2023-GD-05417 | GD1M | Comercial | 26.55 | Out of period | 2023-02-21 | February | 2023 |  |  | Anejar Certificacion e Instalacion | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1135
2023-GD-04069 | GD1M | Comercial | 34.4 | Out of period | 2023-02-08 | February | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 1148
2023-GD-04020 | GD1M | Comercial | 56 | Out of period | 2023-10-16 | October | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 898
2023-GD-03410 | GD1M | Comercial | 28.61 | Out of period | 2023-09-07 | September | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 937
2023-GD-02296 | GD1M | Comercial | 27 | Out of period | 2023-01-23 | January | 2023 |  |  | Anejar Documentos | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1164
2023-GD-00918 | GD1M | Comercial | 33 | Out of period | 2023-01-11 | January | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1176
2023-GD-00887 | GD1M | Comercial | 49.5 | Out of period | 2023-01-11 | January | 2023 |  |  | Anejar Documentos | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1176
2022-GD-32491 | GD1M | Comercial | 32 | Out of period | 2022-12-27 | December | 2022 |  |  | Anejar Documentos | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1191
2022-GD-32451 | GD1M | Comercial | 38 | Out of period | 2022-12-23 | December | 2022 |  |  | Anejar Documentos | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | CAROLINA |  |  |  |  | 2026-04-01 | 1195
2022-GD-29266 | GD1M | Comercial | 160 | Out of period | 2023-09-08 | September | 2023 |  |  | Anejar Documentos | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 936
2022-GD-28170 | GD1M | Comercial | 45 | Out of period | 2022-11-18 | November | 2022 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1230
2022-GD-17887 | GD1M | Comercial | 72.1 | Out of period | 2023-08-30 | August | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 945
2023-GD-13181 | GD1M | Comercial | 33.04 | Out of period | 2023-08-10 | August | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 965
2023-GD-15502 | GD1M | Comercial | 30 | Out of period | 2023-04-17 | April | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 1080
2023-GD-19927 | GD1M | Comercial | 27.82 | Out of period | 2023-07-12 | July | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 994
2023-GD-20820 | GD1M | Comercial | 200 | Out of period | 2023-07-18 | July | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 988
2023-GD-24690 | GD1M | Comercial | 27.82 | Out of period | 2023-08-11 | August | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 964
2023-GD-25262 | GD1M | Residencial | 26.6 | Out of period | 2023-08-16 | August | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 959
2023-GD-31060 | GD1M | Residencial | 42 | Out of period | 2023-09-27 | September | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 917
2023-GD-39364 | GD1M | Comercial | 104.8 | Out of period | 2024-02-11 | February | 2023 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 780
2024-GD-00090 | GD1M | Residencial | 29.28 | Out of period | 2024-02-05 | February | 2024 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 786
2024-GD-00126 | GD1M | Comercial | 45 | Out of period | 2024-03-06 | March | 2024 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 756
2024-GD-00195 | GD1M | Comercial | 98 | Out of period | 2024-05-24 | May | 2024 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 677
2024-GD-00208 | GD1M | Comercial | 90 | Out of period | 2024-06-04 | June | 2024 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 666
2024-GD-00194 | GD1M | Residencial | 27.65 | Out of period | 2024-05-24 | May | 2024 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 677
2024-GD-00264 | GD1M | Comercial | 396 | Out of period | 2024-10-03 | October | 2024 |  |  | Analisis Planificacion Central Distribucion, Evaluar y Certificar Cartografia | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | Caguas |  |  |  |  | 2026-04-01 | 545
2024-GD-00300 | GD1M | Gubernamental | 31.48 | Out of period | 2024-12-30 | December | 2024 |  |  | Pago Estudio Suplementario | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 457
202603-NM25-02275 | GDL17 | Residencial | 17.6 | Period | 2026-03-27 15:47 | March | 2026 | 2026-04-01 15:05 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 5 | 0 | 2026-04-01 | 4
2025-GD-00198 | GD1M | Comercial | 746.3 | Out of period | 2025-11-06 | November | 2025 |  |  | Analisis Planificacion Central Distribucion, Evaluar y Certificar Cartografia | Gestión del Proponente | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 146
2025-GD-00163 | GD1M | Comercial | 185 | Out of period | 2025-09-23 | September | 2025 |  |  | Evaluar y Certificar Cartografia | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 190
2025-GD-00197 | GD1M | Comercial | 45 | Out of period | 2025-11-04 | November | 2025 |  |  | Evaluar y Certificar Cartografia | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 148
2022-GD-10159 | TRANSMISSION | Industrial | 0 | Out of period | 2022-06-01 | June | 2022 |  |  | parallelgateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 1400
2023-GD-08816 | TRANSMISSION | Industrial | 1811.3 | Out of period | 2023-03-27 | March | 2023 |  |  | parallelgateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 1101
2023-GD-08748 | TRANSMISSION | Comercial | 990 | Out of period | 2023-03-27 | March | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 1101
2023-GD-08345 | GD1M | Residencial | 45 | Out of period | 2023-03-22 | March | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1106
2023-GD-05194 | GD1M | Comercial | 56.05 | Out of period | 2023-02-20 | February | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1136
2023-GD-04128 | GD1M | Comercial | 30 | Out of period | 2023-02-08 | February | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1148
2023-GD-02395 | GD1M | Industrial | 264 | Out of period | 2023-01-24 | January | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1163
2022-GD-32127 | GD1M | Comercial | 528 | Out of period | 2022-12-22 | December | 2022 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1196
2022-GD-31477 | GD1M | Comercial | 106 | Out of period | 2022-12-15 | December | 2022 |  |  | Aprobar Certificacion Instalacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 1203
2022-GD-29119 | GD1M | Industrial | 55.63 | Out of period | 2023-10-16 | October | 2023 |  |  | Aprobar Certificacion Instalacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 898
2022-GD-28129 | GD1M | Comercial | 104.43 | Out of period | 2022-11-18 | November | 2022 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 1230
2022-GD-23648 | GD1M | Comercial | 726 | Out of period | 2023-10-10 | October | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 904
2022-GD-21380 | GD1M | Comercial | 45.75 | Out of period | 2022-09-13 | September | 2022 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 1296
2022-GD-18298 | GD1M | Comercial | 424 | Out of period | 2022-08-22 | August | 2022 |  |  | Verificar Poliza y Firmar Acuerdo | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1318
2022-GD-18295 | GD1M | Comercial | 424 | Out of period | 2022-08-22 | August | 2022 |  |  | Firmar Acuerdo, Verificar Poliza y Firmar Acuerdo | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1318
2022-GD-09431 | TRANSMISSION | Industrial | 0 | Out of period | 2023-08-15 | August | 2023 |  |  | parallelgateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 960
2022-GD-07641 | GD1M | Residencial | 27.45 | Out of period | 2022-05-04 | May | 2022 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 1428
2022-GD-07215 | GD1M | Comercial | 264 | Out of period | 2022-04-12 | April | 2022 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1450
2022-GD-05838 | GD1M | Comercial | 484.1 | Out of period | 2022-04-05 | April | 2022 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 1457
2022-GD-03313 | TRANSMISSION | Industrial | 0 | Out of period | 2022-02-23 | February | 2022 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 1498
2023-GD-11622 | GD1M | Comercial | 47.62 | Out of period | 2023-04-06 | April | 2023 |  |  | Aprobar Certificacion Instalacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 1091
2023-GD-19823 | TRANSMISSION | Comercial | 0 | Out of period | 2023-07-11 | July | 2023 |  |  | parallelgateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 995
2023-GD-20817 | GD1M | Comercial | 120 | Out of period | 2023-07-18 | July | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 988
2023-GD-29513 | GD1M | Residencial | 27.45 | Out of period | 2023-09-14 | September | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 930
2023-GD-30743 | GD1M | Comercial | 528 | Out of period | 2023-09-21 | September | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 923
2023-GD-31729 | GD1M | Comercial | 978.6 | Out of period | 2022-11-28 | November | 2023 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1220
2023-GD-38330 | GD1M | Residencial | 87.03 | Out of period | 2024-01-28 | January | 2023 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 794
2024-GD-00150 | GD1M | Comercial | 500 | Out of period | 2024-03-21 | March | 2024 |  |  | Estudio Coordinacion Proteccion UserTask, Inclusive Gateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 741
2024-GD-00048 | GD1M | Comercial | 119 | Out of period | 2024-01-27 | January | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 795
2024-GD-00063 | GD1M | Comercial | 449 | Out of period | 2024-01-27 | January | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 795
2024-GD-00062 | GD1M | Comercial | 297.3 | Out of period | 2024-01-27 | January | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 795
2024-GD-00057 | GD1M | Comercial | 363.3 | Out of period | 2024-01-27 | January | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 795
2024-GD-00055 | GD1M | Comercial | 231.3 | Out of period | 2024-01-27 | January | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 795
2024-GD-00022 | GD1M | Comercial | 26.72 | Out of period | 2024-01-17 | January | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 805
2024-GD-00064 | GD1M | Comercial | 363.3 | Out of period | 2024-01-27 | January | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 795
2024-GD-00094 | GD1M | Comercial | 26.72 | Out of period | 2024-02-07 | February | 2024 |  |  | Inspeccion de Campo | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 784
2024-GD-00084 | GD1M | Comercial | 52.7 | Out of period | 2024-02-01 | February | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 790
2024-GD-00053 | GD1M | Comercial | 351.3 | Out of period | 2024-01-27 | January | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 795
2024-GD-00054 | GD1M | Comercial | 383 | Out of period | 2024-01-27 | January | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 795
2024-GD-00179 | GD1M | Comercial | 275 | Out of period | 2024-05-01 | May | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | PONCE |  |  |  |  | 2026-04-01 | 700
2024-GD-00209 | GD1M | Comercial | 80 | Out of period | 2024-06-05 | June | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 665
2024-GD-00155 | GD1M | Comercial | 106 | Out of period | 2024-04-01 | April | 2024 |  |  | Inspeccion de Campo | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 730
2024-GD-00212 | GD1M | Comercial | 403.3 | Out of period | 2024-06-11 | June | 2024 |  |  | Inspeccion Documentos | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 659
2024-GD-00213 | GD1M | Comercial | 220.07 | Out of period | 2024-06-12 | June | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 658
2024-GD-00187 | GD1M | Comercial | 264 | Out of period | 2024-05-16 | May | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 685
2024-GD-00217 | GD1M | Comercial | 332 | Out of period | 2024-06-20 | June | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 650
2024-GD-00201 | GD1M | Comercial | 26.72 | Out of period | 2024-05-29 | May | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 672
2024-GD-00239 | GD1M | Comercial | 30 | Out of period | 2024-08-06 | August | 2024 |  |  | Inspeccion de Campo | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 603
2024-GD-00262 | GD1M | Comercial | 265 | Out of period | 2024-09-27 | September | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 551
2024-GD-00245 | GD1M | Comercial | 106 | Out of period | 2024-08-16 | August | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 593
2024-GD-00240 | GD1M | Comercial | 45 | Out of period | 2024-08-08 | August | 2024 |  |  | Inspeccion Documentos | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | SAN JUAN |  |  |  |  | 2026-04-01 | 601
2023-GD-39399 | TRANSMISSION | Comercial | 1800 | Out of period | 2024-04-01 | April | 2023 |  |  | parallelgateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 730
2024-GD-00215 | TRANSMISSION | Comercial | 139.9 | Out of period | 2024-06-19 | June | 2024 |  |  | parallelgateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 651
2024-GD-00225 | TRANSMISSION | Industrial | 1650 | Out of period | 2024-06-28 | June | 2024 |  |  | Inspeccion Documentos | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 642
2024-GD-00206 | TRANSMISSION | Comercial | 245.3 | Out of period | 2024-06-03 | June | 2024 |  |  | parallelgateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 667
2024-GD-00220 | TRANSMISSION | Residencial | 0 | Out of period | 2024-06-25 | June | 2024 |  |  | parallelgateway | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 645
2024-GD-00266 | GD1M | Comercial | 60 | Out of period | 2024-10-04 | October | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | Bayamon |  |  |  |  | 2026-04-01 | 544
2024-GD-00268 | GD1M | Comercial | 36 | Out of period | 2024-10-07 | October | 2024 |  |  | Evaluacion | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | Mayaguez |  |  |  |  | 2026-04-01 | 541
2024-GD-00267 | GD1M | Comercial | 26.72 | Out of period | 2024-10-07 | October | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 541
2024-GD-00276 | GD1M | Comercial | 116 | Out of period | 2024-10-22 | October | 2024 |  |  | Inspeccion de Campo | Inspección (I) | Backlog |  |  |  |  | Pending LUMA action | Arecibo |  |  |  |  | 2026-04-01 | 526
2024-GD-00280 | GD1M | Comercial | 103.5 | Out of period | 2024-10-30 | October | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 518
2024-GD-00287 | GD1M | Residencial | 31.2 | Out of period | 2024-11-26 | November | 2024 |  |  | Notificar Fecha de Pruebas y Construccion | Inspección (I) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 491
2023-GD-18244 | GD1M | Comercial | 30.4 | Out of period | 2023-08-09 | August | 2023 |  |  | Pago Aportacion | Transmisión | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 966
2023-GD-25042 | GD1M | Comercial | 27.82 | Out of period | 2023-08-08 | August | 2023 |  |  | Pago Aportacion | Transmisión | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 967
2024-GD-00292 | GD1M | Residencial | 30.74 | Out of period | 2024-12-10 | December | 2024 |  |  | Pago Aportacion | Transmisión | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 477
2023-GD-08864 | GD1M | Residencial | 26.88 | Out of period | 2023-03-28 | March | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1100
2023-GD-06536 | GD1M | Residencial | 86.38 | Out of period | 2023-03-06 | March | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1122
2023-GD-06396 | GD1M | Comercial | 40.32 | Out of period | 2023-03-03 | March | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1125
2023-GD-05733 | GD1M | Residencial | 26.11 | Out of period | 2023-02-24 | February | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1132
2023-GD-04039 | GD1M | Comercial | 151.63 | Out of period | 2023-02-07 | February | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1149
2023-GD-03474 | GD1M | Comercial | 46.5 | Out of period | 2023-09-08 | September | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 936
2023-GD-02583 | GD1M | Comercial | 46.5 | Out of period | 2023-09-14 | September | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 930
2023-GD-02384 | GD1M | Comercial | 0 | Out of period | 2023-01-24 | January | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1163
2023-GD-02209 | GD1M | Comercial | 132 | Out of period | 2023-01-20 | January | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1167
2023-GD-00827 | GD1M | Comercial | 61.44 | Out of period | 2023-01-10 | January | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1177
2023-GD-00366 | GD1M | Comercial | 36 | Out of period | 2023-01-02 | January | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 1185
2022-GD-32893 | GD1M | Comercial | 38 | Out of period | 2023-09-05 | September | 2023 |  |  | Validación | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 939
2022-GD-30830 | GD1M | Comercial | 58 | Out of period | 2022-12-12 | December | 2022 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1206
2022-GD-30559 | GD1M | Comercial | 609 | Out of period | 2023-11-22 | November | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 861
2022-GD-29752 | GD1M | Comercial | 489 | Out of period | 2023-09-12 | September | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 932
2022-GD-27142 | GD1M | Comercial | 69.12 | Out of period | 2023-09-06 | September | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 938
2022-GD-21093 | GD1M | Comercial | 57.5 | Out of period | 2022-09-09 | September | 2022 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1300
2022-GD-09177 | GD1M | Comercial | 42 | Out of period | 2022-05-12 | May | 2022 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 1420
2022-GD-06212 | TRANSMISSION | Industrial | 800 | Out of period | 2022-04-09 | April | 2022 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 1453
2022-GD-05808 | GD1M | Comercial | 57.6 | Out of period | 2022-04-04 | April | 2022 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1458
2023-GD-15237 | GD1M | Residencial | 86.4 | Out of period | 2023-08-09 | August | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 966
2023-GD-12795 | TRANSMISSION | Comercial | 489 | Out of period | 2023-04-06 | April | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 1091
2023-GD-13495 | GD1M | Residencial | 27.29 | Out of period | 2023-05-03 | May | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 1064
2023-GD-09648 | GD1M | Comercial | 198 | Out of period | 2023-08-16 | August | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 959
2023-GD-17930 | GD1M | Comercial | 30.7 | Out of period | 2023-10-11 | October | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 903
2023-GD-17985 | GD1M | Comercial | 54 | Out of period | 2023-10-11 | October | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 903
2023-GD-19001 | GD1M | Comercial | 60 | Out of period | 2023-07-06 | July | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1000
2023-GD-19994 | GD1M | Comercial | 656 | Out of period | 2023-07-12 | July | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 994
2023-GD-19995 | GD1M | Comercial | 500 | Out of period | 2023-08-03 | August | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 972
2023-GD-20475 | GD1M | Comercial | 744 | Out of period | 2023-07-14 | July | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-20478 | GD1M | Comercial | 384 | Out of period | 2023-07-14 | July | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-20479 | GD1M | Comercial | 552 | Out of period | 2023-07-10 | July | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 996
2023-GD-20485 | GD1M | Comercial | 986 | Out of period | 2023-07-14 | July | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 992
2023-GD-20706 | GD1M | Comercial | 744 | Out of period | 2023-07-17 | July | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 989
2023-GD-20819 | GD1M | Comercial | 37.5 | Out of period | 2023-07-18 | July | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 988
2023-GD-23978 | GD1M | Comercial | 750 | Out of period | 2023-09-06 | September | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 938
2023-GD-24186 | GD1M | Comercial | 48 | Out of period | 2023-08-09 | August | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 966
2023-GD-25920 | GD1M | Comercial | 450 | Out of period | 2023-08-14 | August | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 961
2023-GD-28827 | GD1M | Comercial | 33 | Out of period | 2023-05-03 | May | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1064
2023-GD-29391 | GD1M | Comercial | 944.3 | Out of period | 2023-05-16 | May | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 1051
202603-NM25-02276 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 15:23 | March | 2026 | 2026-04-01 15:04 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02277 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 16:08 | March | 2026 | 2026-04-22 07:57 | 23 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 23 | 0 | 2026-04-01 | 1
202603-NM25-02278 | GDL17 | Residencial | 11.5 | Period | 2026-03-28 13:02 | March | 2026 | 2026-04-13 10:45 | 16 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 16 | 0 | 2026-04-01 | 3
202603-NM25-02279 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 08:41 | March | 2026 | 2026-04-17 14:37 | 18 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 19 | 0 | 2026-04-01 | 2
202603-NM25-02280 | GDL17 | Residencial | 12 | Period | 2026-03-28 15:49 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 3
2023-GD-32779 | GD1M | Comercial | 26.72 | Out of period | 2023-10-28 | October | 2023 |  |  | Anejar Documentos, Asignar Inspector | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 886
2023-GD-33167 | GD1M | Comercial | 69.62 | Out of period | 2023-10-31 | October | 2023 |  |  | Aprobar Certificacion Instalacion | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | CAGUAS |  |  |  |  | 2026-04-01 | 883
2023-GD-33218 | GD1M | Residencial | 32.04 | Out of period | 2022-10-28 | October | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 1251
2023-GD-33463 | GD1M | Comercial | 31.57 | Out of period | 2023-11-02 | November | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 881
202603-NM25-02282 | GDL17 | Residencial | 9.15 | Period | 2026-03-30 09:12 | March | 2026 | 2026-04-01 13:22 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 2
2023-GD-36008 | GD1M | Residencial | 27.29 | Out of period | 2023-11-20 | November | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 863
2023-GD-36622 | GD1M | Comercial | 41.27 | Out of period | 2021-12-17 | December | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1566
2023-GD-37316 | GD1M | Comercial | 44.84 | Out of period | 2023-11-30 | November | 2023 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 853
2023-GD-37600 | GD1M | Comercial | 26.35 | Out of period | 2023-12-01 | December | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 852
2023-GD-38152 | GD1M | Comercial | 41.472 | Out of period | 2024-02-10 | February | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 781
2023-GD-38331 | GD1M | Comercial | 34.04 | Out of period | 2024-01-27 | January | 2023 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 795
2023-GD-38356 | GD1M | Comercial | 32 | Out of period | 2024-01-28 | January | 2023 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 794
2023-GD-38919 | GD1M | Comercial | 125.09 | Out of period | 2024-02-07 | February | 2023 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 784
2023-GD-39260 | GD1M | Comercial | 33.3 | Out of period | 2024-01-27 | January | 2023 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 795
2023-GD-39439 | GD1M | Comercial | 26.72 | Out of period | 2024-04-14 | April | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 717
2024-GD-00049 | GD1M | Comercial | 363.3 | Out of period | 2024-01-27 | January | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 795
2024-GD-00134 | GD1M | Comercial | 143 | Out of period | 2024-03-11 | March | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 751
2024-GD-00061 | GD1M | Comercial | 297.3 | Out of period | 2024-01-27 | January | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 795
2024-GD-00046 | GD1M | Comercial | 317 | Out of period | 2024-01-27 | January | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 795
2024-GD-00071 | GD1M | Comercial | 198 | Out of period | 2024-01-29 | January | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 793
2024-GD-00058 | GD1M | Comercial | 264 | Out of period | 2024-01-27 | January | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 795
2024-GD-00068 | GD1M | Comercial | 429.3 | Out of period | 2024-01-28 | January | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 794
2024-GD-00123 | GD1M | Comercial | 26.72 | Out of period | 2024-02-29 | February | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 762
2024-GD-00100 | GD1M | Residencial | 58.1 | Out of period | 2024-02-12 | February | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 779
2024-GD-00038 | GD1M | Comercial | 363.3 | Out of period | 2024-01-24 | January | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 798
2024-GD-00043 | GD1M | Comercial | 340 | Out of period | 2024-01-25 | January | 2024 |  |  | Anejar Certificacion e Instalacion | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 797
2024-GD-00021 | GD1M | Comercial | 27.08 | Out of period | 2024-01-17 | January | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 805
2024-GD-00065 | GD1M | Comercial | 165.3 | Out of period | 2024-01-27 | January | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 795
2024-GD-00056 | GD1M | Comercial | 264 | Out of period | 2024-01-27 | January | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 795
2024-GD-00127 | GD1M | Comercial | 38.35 | Out of period | 2024-03-06 | March | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 756
2024-GD-00101 | GD1M | Comercial | 32.94 | Out of period | 2024-02-15 | February | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 776
2024-GD-00052 | GD1M | Comercial | 383 | Out of period | 2024-01-27 | January | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 795
2024-GD-00131 | GD1M | Residencial | 45 | Out of period | 2024-03-07 | March | 2024 |  |  | Anejar Certificacion e Instalacion | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 755
2024-GD-00051 | GD1M | Comercial | 528 | Out of period | 2024-01-27 | January | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 795
2024-GD-00133 | GD1M | Comercial | 140 | Out of period | 2024-03-11 | March | 2024 |  |  | Anejar Certificacion e Instalacion | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 751
2024-GD-00142 | GD1M | Comercial | 806 | Out of period | 2024-03-15 | March | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 747
2024-GD-00096 | GD1M | Comercial | 784 | Out of period | 2024-02-09 | February | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 782
2024-GD-00072 | GD1M | Comercial | 515 | Out of period | 2024-01-29 | January | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 793
2024-GD-00163 | GD1M | Comercial | 26.72 | Out of period | 2024-04-09 | April | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 722
2024-GD-00169 | GD1M | Comercial | 45 | Out of period | 2024-04-14 | April | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 717
2024-GD-00218 | GD1M | Comercial | 38.76 | Out of period | 2024-06-20 | June | 2024 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 650
2024-GD-00216 | GD1M | Comercial | 56 | Out of period | 2024-06-20 | June | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 650
2024-GD-00192 | GD1M | Comercial | 600 | Out of period | 2024-05-23 | May | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 678
2024-GD-00200 | GD1M | Comercial | 330 | Out of period | 2024-05-29 | May | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 672
2024-GD-00205 | GD1M | Residencial | 28.03 | Out of period | 2024-05-31 | May | 2024 |  |  | Aprobar Certificacion Instalacion | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | BAYAMON |  |  |  |  | 2026-04-01 | 670
2024-GD-00191 | GD1M | Comercial | 265 | Out of period | 2024-05-23 | May | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 678
2024-GD-00162 | GD1M | Comercial | 26.72 | Out of period | 2024-04-08 | April | 2024 |  |  | Anejar Certificacion e Instalacion | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 723
2024-GD-00160 | GD1M | Comercial | 84.74 | Out of period | 2024-04-04 | April | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 727
2024-GD-00199 | GD1M | Comercial | 105 | Out of period | 2024-05-29 | May | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 672
2024-GD-00184 | GD1M | Comercial | 101 | Out of period | 2024-05-07 | May | 2024 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 694
2024-GD-00188 | GD1M | Comercial | 437 | Out of period | 2024-05-16 | May | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 685
2024-GD-00156 | GD1M | Comercial | 530 | Out of period | 2024-04-01 | April | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 730
2024-GD-00210 | GD1M | Comercial | 51.66 | Out of period | 2024-06-07 | June | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 663
2024-GD-00204 | GD1M | Comercial | 180 | Out of period | 2024-05-30 | May | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 671
2024-GD-00202 | GD1M | Comercial | 46.08 | Out of period | 2024-05-29 | May | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 672
2024-GD-00159 | GD1M | Comercial | 93.31 | Out of period | 2024-04-02 | April | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 729
2024-GD-00167 | GD1M | Comercial | 32.45 | Out of period | 2024-04-11 | April | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 720
2024-GD-00157 | GD1M | Comercial | 56 | Out of period | 2024-04-01 | April | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 730
2024-GD-00203 | GD1M | Comercial | 30.72 | Out of period | 2024-05-29 | May | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 672
2024-GD-00222 | GD1M | Comercial | 34.5 | Out of period | 2024-06-27 | June | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 643
202603-NM25-02286 | GDL17 | Residencial | 8.25 | Period | 2026-03-27 16:11 | March | 2026 | 2026-04-01 15:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02287 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 16:31 | March | 2026 | 2026-04-08 10:09 | 12 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 12 | 0 | 2026-04-01 | 4
202603-NM25-02288 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 16:26 | March | 2026 | 2026-04-01 15:11 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02289 | GDL17 | Residencial | 11.5 | Period | 2026-03-27 16:32 | March | 2026 | 2026-04-01 15:13 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02290 | GDL17 | Comercial | 23 | Period | 2026-03-27 16:30 | March | 2026 | 2026-04-01 15:12 | 5 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 5 | 0 | 2026-04-01 | 4
202603-NM25-02297 | GDL17 | Residencial | 22.8 | Period | 2026-03-28 21:32 | March | 2026 | 2026-04-01 15:15 | 4 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 4 | 0 | 2026-04-01 | 3
2024-GD-00253 | GD1M | Comercial | 212 | Out of period | 2024-08-29 | August | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 580
2024-GD-00249 | GD1M | Comercial | 46.74 | Out of period | 2024-08-26 | August | 2024 |  |  | Aprobar Certificacion Instalacion | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | ARECIBO |  |  |  |  | 2026-04-01 | 583
2024-GD-00256 | GD1M | Comercial | 106 | Out of period | 2024-09-04 | September | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 574
2024-GD-00237 | GD1M | Comercial | 1056 | Out of period | 2024-08-01 | August | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 608
2024-GD-00254 | GD1M | Comercial | 45 | Out of period | 2024-08-30 | August | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 579
2024-GD-00246 | GD1M | Comercial | 218 | Out of period | 2024-08-19 | August | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 590
2024-GD-00255 | GD1M | Comercial | 132 | Out of period | 2024-08-30 | August | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 579
2024-GD-00243 | GD1M | Comercial | 46.72 | Out of period | 2024-08-13 | August | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 596
2024-GD-00247 | GD1M | Comercial | 90 | Out of period | 2024-08-19 | August | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 590
2022-GD-09196 | GD1M | Residencial | 36 | Out of period | 2022-05-20 | May | 2022 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1412
2022-GD-03449 | GD1M | Residencial | 84 | Out of period | 2022-02-27 | February | 2022 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1494
2022-GD-03432 | GD1M | Residencial | 49.2 | Out of period | 2022-02-27 | February | 2022 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 1494
2023-GD-20717 | TRANSMISSION | Residencial | 253.6 | Out of period | 2023-07-18 | July | 2023 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | BAYAMON |  |  |  |  | 2026-04-01 | 988
2023-GD-38276 | TRANSMISSION | Comercial | 500 | Out of period | 2024-01-29 | January | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 793
2023-GD-38304 | TRANSMISSION | Comercial | 766.6 | Out of period | 2024-01-27 | January | 2023 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 795
2024-GD-00047 | TRANSMISSION | Comercial | 449 | Out of period | 2024-01-27 | January | 2024 |  |  | approveTransmissionEnd | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 795
2024-GD-00025 | TRANSMISSION | Industrial | 960 | Out of period | 2024-01-19 | January | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 803
2024-GD-00067 | TRANSMISSION | Comercial | 528 | Out of period | 2024-01-28 | January | 2024 |  |  | approveTransmissionEnd | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 794
2024-GD-00095 | TRANSMISSION | Residencial | 0 | Out of period | 2024-02-08 | February | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 783
2024-GD-00141 | TRANSMISSION | Comercial | 4928 | Out of period | 2024-03-13 | March | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 749
2024-GD-00059 | TRANSMISSION | Comercial | 515 | Out of period | 2024-01-27 | January | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 795
2024-GD-00066 | TRANSMISSION | Comercial | 528 | Out of period | 2024-01-28 | January | 2024 |  |  | Validación Monacillos | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 794
2024-GD-00092 | TRANSMISSION | Industrial | 960 | Out of period | 2024-02-05 | February | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 786
2024-GD-00083 | TRANSMISSION | Industrial | 960 | Out of period | 2024-02-01 | February | 2024 |  |  | approveTransmissionEnd | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 790
2024-GD-00074 | TRANSMISSION | Comercial | 1043 | Out of period | 2024-01-29 | January | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 793
2024-GD-00113 | TRANSMISSION | Comercial | 540 | Out of period | 2024-02-23 | February | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 768
2024-GD-00224 | TRANSMISSION | Comercial | 784 | Out of period | 2024-06-28 | June | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 642
2024-GD-00265 | GD1M | Comercial | 462 | Out of period | 2024-10-03 | October | 2024 |  |  | Aprobacion de Medicion Neta Oficina Comercial | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | San Juan |  |  |  |  | 2026-04-01 | 545
2024-GD-00270 | GD1M | Comercial | 2500 | Out of period | 2024-10-09 | October | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 539
202603-NM25-02301 | GDL17 | Residencial | 7.6 | Period | 2026-03-31 09:37 | March | 2026 | 2026-04-02 09:29 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 1
2024-GD-00271 | GD1M | Comercial | 38.4 | Out of period | 2024-10-14 | October | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 534
2024-GD-00272 | GD1M | Industrial | 537 | Out of period | 2024-10-16 | October | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 532
2024-GD-00273 | GD1M | Comercial | 780 | Out of period | 2024-10-17 | October | 2024 |  |  | Completar Información Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 531
2024-GD-00278 | GD1M | Comercial | 500 | Out of period | 2024-10-25 | October | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 523
2024-GD-00279 | GD1M | Comercial | 300 | Out of period | 2024-10-28 | October | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 520
2024-GD-00282 | GD1M | Comercial | 106 | Out of period | 2024-11-05 | November | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 512
2024-GD-00285 | GD1M | Gubernamental | 596 | Out of period | 2024-11-15 | November | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 502
2024-GD-00286 | GD1M | Residencial | 26.72 | Out of period | 2024-11-26 | November | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 491
2024-GD-00288 | GD1M | Comercial | 50.14 | Out of period | 2024-11-26 | November | 2024 |  |  | Anejar Documentos | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Ponce |  |  |  |  | 2026-04-01 | 491
2024-GD-00290 | GD1M | Comercial | 30.72 | Out of period | 2024-11-27 | November | 2024 |  |  | approvedDistributionEndEvent | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | Mayaguez |  |  |  |  | 2026-04-01 | 490
202603-NM25-02302 | GDL17 | Residencial | 7.6 | Period | 2026-03-29 10:16 | March | 2026 |  |  | NM Document Resubmission | Estudio (E) | Backlog |  | Yes | No |  | Pending Customer Action | CAGUAS |  |  |  |  | 2026-04-01 | 3
2024-GD-00294 | GD1M | Residencial | 278 | Out of period | 2024-12-12 | December | 2024 |  |  | Anejar Documentos, Asignar Inspector | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Bayamon |  |  |  |  | 2026-04-01 | 475
2024-GD-00298 | GD1M | Comercial | 998.2 | Out of period | 2024-12-26 | December | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | Mayaguez |  |  |  |  | 2026-04-01 | 461
2024-GD-00291 | TRANSMISSION | Gubernamental | 3074.4 | Out of period | 2024-12-04 | December | 2024 |  |  | approveTransmissionEnd | Validación (V) | Backlog |  |  |  |  | Pending LUMA action | MONACILLOS |  |  |  |  | 2026-04-01 | 483
2024-GD-00289 | TRANSMISSION | Comercial | 1500 | Out of period | 2024-11-08 | November | 2024 |  |  | Completar Informacion Adicional | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MONACILLOS |  |  |  |  | 2026-04-01 | 509
202603-NM25-02311 | GDL17 | Residencial | 10 | Period | 2026-03-31 09:51 | March | 2026 | 2026-04-02 09:30 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02315 | GDL17 | Comercial | 20 | Period | 2026-03-30 09:43 | March | 2026 |  |  | NM Project Acceptance Special | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | PONCE |  |  |  |  | 2026-04-01 | 2
202603-NM25-02322 | GDL17 | Residencial | 3.456 | Period | 2026-03-30 08:46 | March | 2026 | 2026-04-07 14:22 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 9 | 0 | 2026-04-01 | 2
202407-NM25-01086 | GD1M | Comercial | 30.4 | Out of period | 2025-01-03 08:54 | January | 2025 |  |  | NM Enter Technical Info | Validación (V) | Backlog |  |  |  |  | Pending Customer Action | MAYAGUEZ |  |  |  |  | 2026-04-01 | 453
202603-NM25-02332 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:01 | March | 2026 | 2026-04-07 11:22 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 8 | 0 | 2026-04-01 | 2
202603-NM25-02334 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:07 | March | 2026 | 2026-04-01 15:17 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 2
202603-NM25-02335 | GDL17 | Residencial | 12.91 | Period | 2026-03-30 09:27 | March | 2026 | 2026-04-08 14:47 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | BAYAMON | April |  | 10 | 1 | 2026-04-01 | 2
202603-NM25-02336 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 09:15 | March | 2026 | 2026-04-10 10:04 | 11 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 11 | 0 | 2026-04-01 | 2
202603-NM25-02338 | GDL17 | Residencial | 11.904 | Period | 2026-03-30 09:24 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | ARECIBO |  |  |  |  | 2026-04-01 | 2
202603-NM25-02339 | GDL17 | Residencial | 3.456 | Period | 2026-03-30 09:50 | March | 2026 | 2026-04-01 15:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 3 | 0 | 2026-04-01 | 2
202603-NM25-02352 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 10:42 | March | 2026 | 2026-04-07 08:33 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 7 | 0 | 2026-04-01 | 2
202603-NM25-02354 | GDL17 | Residencial | 9 | Period | 2026-03-30 14:01 | March | 2026 | 2026-04-09 13:50 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | No |  |  | PONCE | April |  | 10 | 6 | 2026-04-01 | 1
202603-NM25-02356 | GDL17 | Residencial | 8.562 | Period | 2026-03-30 10:36 | March | 2026 | 2026-04-01 15:13 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 2
202603-NM25-02358 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 11:14 | March | 2026 | 2026-04-02 14:57 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 3 | 0 | 2026-04-01 | 2
202603-NM25-02362 | GDL17 | Residencial | 8.304 | Period | 2026-03-30 11:14 | March | 2026 | 2026-04-01 15:10 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 2
202603-NM25-02365 | GDL17 | Residencial | 7.6 | Period | 2026-03-30 12:03 | March | 2026 | 2026-04-20 08:42 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 21 | 0 | 2026-04-01 | 1
202603-NM25-02367 | GDL17 | Residencial | 19.1 | Period | 2026-03-30 14:22 | March | 2026 | 2026-04-02 09:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02369 | GDL17 | Residencial | 4.992 | Period | 2026-03-30 12:05 | March | 2026 | 2026-04-06 08:14 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 7 | 0 | 2026-04-01 | 1
202603-NM25-02372 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 12:27 | March | 2026 | 2026-04-08 12:36 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 9 | 0 | 2026-04-01 | 1
202603-NM25-02379 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 12:59 | March | 2026 | 2026-04-02 09:18 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02380 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 15:08 | March | 2026 | 2026-04-09 11:16 | 10 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 10 | 0 | 2026-04-01 | 1
202603-NM25-02383 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 07:38 | March | 2026 | 2026-04-02 09:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02391 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 14:33 | March | 2026 | 2026-04-02 09:20 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02393 | GDL17 | Residencial | 3.84 | Period | 2026-03-31 08:24 | March | 2026 | 2026-04-06 16:15 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 6 | 0 | 2026-04-01 | 1
202603-NM25-02394 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 14:41 | March | 2026 | 2026-04-02 08:54 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02395 | GDL17 | Residencial | 3.835 | Period | 2026-03-30 14:57 | March | 2026 | 2026-04-02 09:21 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02398 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 15:14 | March | 2026 | 2026-04-02 14:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02399 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 15:29 | March | 2026 | 2026-04-02 09:22 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02401 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 15:23 | March | 2026 | 2026-04-16 09:53 | 17 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 17 | 0 | 2026-04-01 | 1
202603-NM25-02402 | GDL17 | Residencial | 4.224 | Period | 2026-03-30 15:27 | March | 2026 | 2026-04-27 12:41 | 28 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 28 | 0 | 2026-04-01 | 1
202603-NM25-02407 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 15:52 | March | 2026 | 2026-04-02 09:23 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02413 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 16:50 | March | 2026 | 2026-04-02 15:09 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02421 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 08:46 | March | 2026 | 2026-04-02 11:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02426 | GDL17 | Residencial | 11.5 | Period | 2026-03-30 22:28 | March | 2026 | 2026-04-02 14:34 | 3 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 3 | 0 | 2026-04-01 | 1
202603-NM25-02428 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 08:20 | March | 2026 | 2026-04-02 09:26 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02432 | GDL17 | Residencial | 19.1 | Period | 2026-03-31 08:40 | March | 2026 | 2026-04-02 09:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02433 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 08:36 | March | 2026 | 2026-04-13 09:24 | 13 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 13 | 0 | 2026-04-01 | 1
202603-NM25-02434 | GDL17 | Residencial | 3.54 | Period | 2026-03-31 08:52 | March | 2026 | 2026-04-02 12:56 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02436 | GDL17 | Residencial | 16.99 | Period | 2026-03-31 08:58 | March | 2026 | 2026-04-02 09:27 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02438 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 09:18 | March | 2026 | 2026-04-02 09:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02439 | GDL17 | Residencial | 11.626 | Period | 2026-03-31 09:28 | March | 2026 | 2026-04-02 09:28 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02440 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 09:39 | March | 2026 | 2026-04-21 09:12 | 21 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 21 | 0 | 2026-04-01 | 1
202603-NM25-02442 | GDL17 | Residencial | 9.6 | Period | 2026-03-31 09:26 | March | 2026 | 2026-04-08 09:11 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 8 | 0 | 2026-04-01 | 1
202603-NM25-02443 | GDL17 | Residencial | 3.54 | Period | 2026-03-31 09:29 | March | 2026 | 2026-04-02 07:45 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02445 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 13:42 | March | 2026 | 2026-04-07 15:01 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 0
202603-NM25-02453 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:22 | March | 2026 | 2026-04-02 09:33 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02454 | GDL17 | Residencial | 5.015 | Period | 2026-03-31 10:00 | March | 2026 | 2026-04-02 09:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02455 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 10:41 | March | 2026 | 2026-04-02 09:32 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02457 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 13:19 | March | 2026 | 2026-04-02 13:31 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02463 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:45 | March | 2026 | 2026-04-02 14:25 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02465 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:30 | March | 2026 | 2026-04-02 14:40 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02466 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 14:00 | March | 2026 | 2026-04-02 14:35 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02467 | GDL17 | Residencial | 7.6 | Period | 2026-03-31 10:54 | March | 2026 | 2026-04-08 08:05 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 8 | 0 | 2026-04-01 | 1
202603-NM25-02468 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 14:05 | March | 2026 | 2026-04-07 08:16 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 6 | 0 | 2026-04-01 | 0
202603-NM25-02472 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:03 | March | 2026 | 2026-04-08 11:05 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 8 | 0 | 2026-04-01 | 1
202603-NM25-02476 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:11 | March | 2026 | 2026-04-06 09:46 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 6 | 0 | 2026-04-01 | 1
202603-NM25-02477 | GDL17 | Residencial | 3.54 | Period | 2026-03-31 14:59 | March | 2026 | 2026-04-02 15:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02479 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:23 | March | 2026 | 2026-04-07 11:02 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 7 | 0 | 2026-04-01 | 1
202603-NM25-02482 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:34 | March | 2026 | 2026-04-07 14:59 | 7 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 7 | 0 | 2026-04-01 | 1
202603-NM25-02483 | GDL17 | Residencial | 7.324 | Period | 2026-03-31 11:39 | March | 2026 | 2026-04-02 15:00 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 2 | 0 | 2026-04-01 | 1
202603-NM25-02485 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 11:50 | March | 2026 |  |  | Net Metering | Estudio (E) | Backlog | Backlog | Yes | Yes | Yes | Pending Customer Action | SAN JUAN |  |  |  |  | 2026-04-01 | 1
202603-NM25-02486 | GDL17 | Residencial | 4.026 | Period | 2026-03-31 12:12 | March | 2026 | 2026-04-02 15:11 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | ARECIBO | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02488 | GDL17 | Residencial | 7.6 | Period | 2026-03-31 12:55 | March | 2026 | 2026-04-02 13:19 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | CAGUAS | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02489 | GDL17 | Residencial | 8.972 | Period | 2026-03-31 12:36 | March | 2026 | 2026-04-09 08:42 | 9 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 8 | 0 | 2026-04-01 | 0
202603-NM25-02490 | GDL17 | Residencial | 9.036 | Period | 2026-03-31 12:39 | March | 2026 | 2026-04-02 15:16 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02492 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 13:32 | March | 2026 | 2026-04-08 13:44 | 8 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | PONCE | April |  | 8 | 0 | 2026-04-01 | 0
202603-NM25-02505 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 15:21 | March | 2026 | 2026-04-06 09:03 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 5 | 0 | 2026-04-01 | 0
202603-NM25-02507 | GDL17 | Residencial | 11.5 | Period | 2026-03-31 15:00 | March | 2026 | 2026-04-06 09:39 | 6 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 5 | 0 | 2026-04-01 | 0
202603-NM25-02509 | GDL17 | Residencial | 7.6 | Period | 2026-03-31 15:31 | March | 2026 | 2026-04-02 15:14 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02520 | GDL17 | Residencial | 8.23 | Period | 2026-03-31 16:02 | March | 2026 | 2026-04-02 15:15 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02521 | GDL17 | Residencial | 9.52 | Period | 2026-03-31 16:13 | March | 2026 | 2026-04-02 15:05 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | MAYAGUEZ | April |  | 2 | 0 | 2026-04-01 | 0
202603-NM25-02534 | GDL17 | Residencial | 24 | Period | 2026-03-31 21:26 | March | 2026 | 2026-04-14 13:08 | 14 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | BAYAMON | April |  | 14 | 0 | 2026-04-01 | 0
202603-NM25-02539 | GDL17 | Residencial | 15 | Period | 2026-03-31 21:28 | March | 2026 | 2026-04-02 15:20 | 2 | Study | Estudio (E) | Activated | Application Complete | Yes | Yes |  |  | SAN JUAN | April |  | 2 | 0 | 2026-04-01 | 0

## vii - UPDATE
Energía de Sistemas Renovables (MWh)
Mes/Año | Fotovoltaica | Eólica | Landfill | Total
2019-04-01 | 21780493 | 18359447 | 1317893 | 41457833
2019-05-01 | 20299804 | 14862416 | 1519455 | 36681675
2019-06-01 | 22428510 | 18385951 | 1544595 | 42359056
2019-07-01 | 22300498 | 20054619 | 804926 | 43160043
2019-08-01 | 21086359 | 16228437 | 1671319 | 38986116
2019-09-01 | 18782441 | 7066199 | 897211 | 26745851
2019-10-01 | 20474446 | 6489073 | 759502 | 27723022
2019-11-01 | 20491090 | 6146555 | 1572344 | 28209989
2019-12-01 | 19407332 | 10193642 | 1599099 | 31200073
2020-01-01 | 16297055 | 5148737 | 678940 | 22124733
2020-02-01 | 20383708 | 13656138 | 737353 | 34777199
2020-03-01 | 22330480 | 11210737 | 1167144 | 34708361
2020-04-01 | 24283028 | 12928347 | 1039972 | 38251347
2020-05-01 | 24499279 | 15986079 | 1063828 | 41549186
2020-06-01 | 23922668 | 17668297 | 652434 | 42243399
2020-07-01 | 22753699 | 19455003 | 687712 | 42896414
2020-08-01 | 23587769 | 14886690 | 397024 | 38871483
2020-09-01 | 21752112 | 7652427 | 740384 | 30144923
2020-10-01 | 20818171 | 9328109 | 636115 | 30782395
2020-11-01 | 18068129 | 7753220 | 722753 | 26544102
2020-12-01 | 20620136 | 6886654 | 943887 | 28450677
2021-01-01 | 21177691 | 10125983 | 824627 | 32128301
2021-02-01 | 21482897 | 17185986 | 1071287 | 39740170
2021-03-01 | 26582517 | 15473156 | 1495194 | 43550867
2021-04-01 | 24413440 | 12483837 | 1381051 | 38278328
2021-05-01 | 25122178 | 17921778 | 1364888 | 44408844
2021-06-01 | 22092827 | 17297604 | 1188776 | 40579207
2021-07-01 | 23074472 | 22616938 | 1103551 | 46794961
2021-08-01 | 25206554 | 16324618 | 897527 | 42428699
2021-09-01 | 22994500 | 7394016 | 1097156 | 31485672
2021-10-01 | 20979518 | 8012816 | 979875 | 29972209
2021-11-01 | 20028972 | 9010205 | 948306 | 29987483
2021-12-01 | 19891158 | 11879892 | 1167770 | 32938820
2022-01-01 | 22691738 | 11582439 | 1525913 | 35800090
2022-02-01 | 20210706 | 12735868 | 1353583 | 34300157
2022-03-01 | 25262643 | 18481795 | 1454527 | 45198965
2022-04-01 | 21701103 | 17602813 | 1063516 | 40367432
2022-05-01 | 22819820 | 17672312 | 1569178 | 42061310
2022-06-01 | 23386641 | 17335838 | 1688924 | 42411403
2022-07-01 | 21029930 | 19393347 | 848383 | 41271660
2022-08-01 | 22150085 | 13676357 | 1548478 | 37374920
2022-09-01 | 15131882 | 4840105 | 806566 | 20778553
2022-10-01 | 19526587 | 7287282 | 749817 | 27563686
2022-11-01 | 18577311 | 7183192 | 608404 | 26368907
2022-12-01 | 20146691 | 7915278 | 688824 | 28750793
2023-01-01 | 20534547 | 10749019 | 639801 | 31923367
2023-02-01 | 20923274 | 12123323 | 842228 | 33888825
2023-03-01 | 22830037 | 10375342 | 874271 | 34079650
2023-04-01 | 23482791 | 9571457 | 815274 | 33869522
2023-05-01 | 23577626 | 8269883 | 926090 | 32773599
2023-06-01 | 22814212 | 7713762 | 1049802 | 31577776
2023-07-01 | 23344413 | 14795085 | 1358442 | 39497940
2023-08-01 | 21382075 | 10659546 | 918436 | 32960057
2023-09-01 | 22208598 | 4590983 | 1017270 | 27816851
2023-10-01 | 19503644 | 4270879 | 1396945 | 25171468
2023-11-01 | 18011241 | 11007642 | 1036042 | 30054925
2023-12-01 | 18753524 | 11788527 | 1227349 | 31769400
2024-01-01 | 19918636 | 17240781 | 921446 | 38080863
2024-02-01 | 17904607 | 9254894 | 716512 | 27876013
2024-03-01 | 22761800 | 13847627 | 739992 | 37349419
2024-04-01 | 21104479 | 13620814 | 897624 | 35622917
2024-05-01 | 21229995 | 11113465 | 722247 | 33065707
2024-06-01 | 19669171 | 15323442 | 584184 | 35576797
2024-07-01 | 19783023 | 22921435 | 929341 | 43633799
2024-08-01 | 21776306 | 17420089 | 405031 | 39601426
2024-09-01 | 19716536 | 11126563 | 341309 | 31184408
2024-10-01 | 17923773 | 5697463 | 610646 | 24231882
2024-11-01 | 15593885 | 6833691 | 702998 | 23130574
2024-12-01 | 16811404 | 10365809 | 864964 | 28042177
2025-01-01 | 18682609 | 15002448 | 1068107 | 34753164
2025-02-01 | 18912580 | 21648738 | 782738 | 41344056
2025-03-01 | 22959838 | 13447403 | 1112032 | 37519273
2025-04-01 | 21171172 | 15685806 | 1103661 | 37960639
2025-05-01 | 22289798 | 17358036 | 1076262 | 40724096
2025-06-01 | 21698600 | 26712731 | 1241301 | 49652632

## viii - UPDATE
Energía Adquirida de Clientes en Medición Neta (MWh)
Mes/año | Energía exportada | Energía Acreditada
2019-04-01 | 7971439 | 9413663
2019-05-01 | 8606364 | 9706537
2019-06-01 | 8281803 | 10733790
2019-07-01 | 7596425 | 11332102
2019-08-01 | 7427241 | 12649567
2019-09-01 | 7437773 | 14137773
2019-10-01 | 7131988 | 15316831
2019-11-01 | 7889118 | 14682753
2019-12-01 | 7217001 | 13398475
2020-01-01 | 6230150 | 12920971
2020-02-01 | 8480806 | 11581629
2020-03-01 | 8891825 | 10804937
2020-04-01 | 9116252 | 8064081
2020-05-01 | 10188082 | 12477021
2020-06-01 | 9541615 | 13261863
2020-07-01 | 9229138 | 15986364
2020-08-01 | 9189112 | 16423328
2020-09-01 | 12749749 | 17197050
2020-10-01 | 8815341 | 21686306
2020-11-01 | 9458581 | 15495915
2020-12-01 | 8537141 | 15433971
2021-01-01 | 9115420 | 15183420
2021-02-01 | 12636671 | 13499788
2021-03-01 | 17290325 | 12477020
2021-04-01 | 16365587 | 12449920
2021-05-01 | 13163856 | 11622306
2021-06-01 | 10357039 | 11235768
2021-07-01 | 12214517 | 19552257
2021-08-01 | 13234972 | 23387849
2021-09-01 | 14751810 | 27158083
2021-10-01 | 13815002 | 26084932
2021-11-01 | 14751659 | 24887269
2021-12-01 | 16082097 | 24581217
2022-01-01 | 16108673 | 22695288
2022-02-01 | 16386581 | 18847212
2022-03-01 | 18279129 | 17554117
2022-04-01 | 22594347 | 18271141
2022-05-01 | 22402246 | 17243731
2022-06-01 | 24636094 | 24414767
2022-07-01 | 22530114 | 26076432
2022-08-01 | 24286560 | 27616834
2022-09-01 | 23297722 | 29296788
2022-10-01 | 19444909 | 24188509
2022-11-01 | 24477151 | 29802353
2022-12-01 | 27913113 | 26955205
2023-01-01 | 28001668 | 25017349
2023-02-01 | 30456220 | 22540635
2023-03-01 | 38007070 | 21519943
2023-04-01 | 44714201 | 22131962
2023-05-01 | 46177497 | 25581660
2023-06-01 | 42416199 | 31591375
2023-07-01 | 41579539 | 41674552
2023-08-01 | 41141105 | 44447061
2023-09-01 | 38934286 | 47595717
2023-10-01 | 42904673 | 49694399
2023-11-01 | 38005692 | 48525085
Dic-2023 | 37900425 | 42729300
2024-01-01 | 38568518 | 36457312
2024-02-01 | 42458890 | 29995045
2024-03-01 | 53179599 | 25318640
2024-04-01 | 62010662 | 26826324
2024-05-01 | 51585718 | 32150342
2024-06-01 | 53301238 | 43622987
2024-07-24 | 50592696 | 52953739
2024-08-24 | 56100821 | 50927376
2024-09-24 | 60229683 | 50178396
2024-10-24 | 61549650 | 52489624
2024-11-24 | 48931250 | 57556603
2024-12-24 | 51995237 | 48814469
2025-01-24 | 47737024 | 43082069
2025-02-24 | 66372101 | 33992750
2025-03-24 | 76023267 | 28351193
2025-04-24 | 87325019.422 | 31778623
2025-05-24 | 70994287.701 | 32179032
2025-06-24 | 75430381.355 | 38750305

## ix - UPDATE
Energía distribuida (DG) como Porciento del Total de Energía Renovable
Mes/año | Energía exportada | PPOA | Total | % DG/ Total Renovable
2019-04-01 | 7971439 | 41457833 | 49429272 | 16.13
2019-05-01 | 8606364 | 36681675 | 45288039 | 19
2019-06-01 | 8281803 | 42359056 | 50640859 | 16.35
2019-07-01 | 7596425 | 43160043 | 50756468 | 14.97
2019-08-01 | 7427241 | 38986116 | 46413357 | 16
2019-09-01 | 7437773 | 26745851 | 34183624 | 21.76
2019-10-01 | 7131988 | 27723022 | 34855010 | 20.46
2019-11-01 | 7889118 | 28209989 | 36099107 | 21.85
2019-12-01 | 7217001 | 31200073 | 38417074 | 18.79
2020-01-01 | 6230150 | 22124733 | 28354883 | 21.97
2020-02-01 | 8480806 | 34777199 | 43258005 | 19.61
2020-03-01 | 8891825 | 34708361 | 43600186 | 20.39
2020-04-01 | 9116252 | 38251347 | 47367599 | 19.25
2020-05-01 | 10188082 | 41549186 | 51737268 | 19.69
2020-06-01 | 9541615 | 42243399 | 51785014 | 18.43
2020-07-01 | 9229138 | 42896414 | 52125552 | 17.71
2020-08-01 | 9189112 | 38871483 | 48060595 | 19.12
2020-09-01 | 12749749 | 30144923 | 42894672 | 29.72
2020-10-01 | 8815341 | 30782395 | 39597736 | 22.26
2020-11-01 | 9458581 | 26544102 | 36002683 | 26.27
2020-12-01 | 8537141 | 28450677 | 36987818 | 23.08
2021-01-01 | 9115420 | 32128301 | 41243721 | 22.1
2021-02-01 | 12636671 | 39740170 | 52376841 | 24.13
2021-03-01 | 17290325 | 43550867 | 60841192 | 28.42
2021-04-01 | 16365587 | 38278328 | 54643915 | 29.95
2021-05-01 | 13163856 | 44408844 | 57572700 | 22.86
2021-06-01 | 10357039 | 40579207 | 50936246 | 20.33
2021-07-01 | 12214517 | 46794961 | 59009478 | 20.7
2021-08-01 | 13234972 | 42428699 | 55663671 | 23.78
2021-09-01 | 14751810 | 31485672 | 46237482 | 31.9
2021-10-01 | 13815002 | 29972209 | 43787211 | 31.55
2021-11-01 | 14751659 | 29987483 | 44739142 | 32.97
2021-12-01 | 16082097 | 32938820 | 49020917 | 32.81
2022-01-01 | 16108673 | 35800090 | 51908763 | 31.03
2022-02-01 | 16386581 | 34300157 | 50686738 | 32.33
2022-03-01 | 18279129 | 45198965 | 63478094 | 28.8
2022-04-01 | 22594347 | 40367432 | 62961779 | 35.89
2022-05-01 | 22402246 | 42061310 | 64463556 | 34.75
2022-06-01 | 24636094 | 42411403 | 67047497 | 36.74
2022-07-01 | 22530114 | 41271660 | 63801774 | 35.31
2022-08-01 | 24286560 | 37374920 | 61661480 | 39.39
2022-09-01 | 23297722 | 20778553 | 44076275 | 52.86
2022-10-01 | 19444909 | 27563686 | 47008595 | 41.36
2022-11-01 | 24477151 | 26368907 | 50846058 | 48.14
2022-12-01 | 27913113 | 28750793 | 56663906 | 49.26
2023-01-01 | 28001668 | 31923367 | 59925035 | 46.73
2023-02-01 | 30456220 | 33888825 | 64345045 | 47.33
2023-03-01 | 38007070 | 34079650 | 72086720 | 52.72
2023-04-01 | 44714201 | 33869522 | 78583723 | 56.9
2023-05-01 | 46177497 | 32773599 | 78951096 | 58.49
2023-06-01 | 42416199 | 31577776 | 73993975 | 57.32
2023-07-01 | 41579539 | 39497940 | 81077479 | 51.28
2023-08-01 | 41141105 | 32960057 | 74101162 | 55.52
2023-09-01 | 38934286 | 27816851 | 66751137 | 58.33
2023-10-01 | 42904673 | 25171468 | 68076141 | 63.02
2023-11-01 | 38005692 | 30054925 | 68060617 | 55.84
Dic-2023 | 37900425 | 31769400 | 69669825 | 54.4
2024-01-01 | 38568518 | 38080863 | 76649381 | 50.32
2024-02-01 | 42458890 | 27876013 | 70334903 | 60.37
2024-03-01 | 53179599 | 37349419 | 90529018 | 58.74
Abr-2024 | 62010662 | 35622917 | 97633579 | 63.51
2024-05-01 | 51585718 | 33065707 | 84651425 | 60.94
2024-06-01 | 53301238 | 35576797 | 88878035 | 59.97
2024-07-24 | 50592696 | 43633799 | 94226495 | 53.69
2024-08-24 | 56100821 | 39601426 | 95702247 | 58.62
2024-09-24 | 60229683 | 31184408 | 91414091 | 65.89
2024-10-24 | 61549650 | 24231882 | 85781532 | 71.75
2024-11-24 | 48931250 | 23130574 | 72061824 | 67.9
2024-12-24 | 51995237 | 28042177 | 80037414 | 64.96
2025-01-24 | 47737024 | 34753164 | 82490188 | 57.87
2025-02-24 | 66372101 | 41344056 | 107716157 | 61.62
2025-03-24 | 76023267 | 37519273 | 113542540 | 66.96
2025-04-24 | 87325019.422 | 37960639 | 125285658.422 | 69.7
2025-05-24 | 70994287.701 | 40724096 | 111718383.701 | 63.54
2025-06-24 | 75430381.355 | 49652632 | 125083013.355 | 60.3

## xi - UPDATE
Energía Distribuida por la Autoridad a los Clientes (MWh)
Mes/año | Energía distribuida
2019-04-01 | 1304075.915
2019-05-01 | 1348935.629
2019-06-01 | 1423924.235
2019-07-01 | 1479995.566
2019-08-01 | 1480543.816
2019-09-01 | 1457784.59
2019-10-01 | 1488727.776
2019-11-01 | 1336583.718
2019-12-01 | 1322457.431
2020-01-01 | 1207184.222
2020-02-01 | 1026470.172
2020-03-01 | 1356291.624
2020-04-01 | 1115772.692
2020-05-01 | 1302945.91
2020-06-01 | 1429193.014
2020-07-01 | 1558002.399
2020-08-01 | 1458744.902
2020-09-01 | 1479873.965
2020-10-01 | 1485526.232
2020-11-01 | 1369752.332
2020-12-01 | 1245536.811
2021-01-01 | 1213392.085
2021-02-01 | 1093810.427
2021-03-01 | 1324216.499
2021-04-01 | 1303716.574
2021-05-01 | 1411436.496
2021-06-01 | 1336309.095
2021-07-01 | 1489644.406
2021-08-01 | 1504170.023
2021-09-01 | 1544352.428
2021-10-01 | 1225699.612
2021-11-01 | 1410063.753
2021-12-01 | 1412605.002
2022-01-01 | 1245269.112
2022-02-01 | 1148942.023
2022-03-01 | 1199864.385
2022-04-01 | 1172464.809
2022-05-01 | 1433524.4
2022-06-01 | 1495385.337
2022-07-01 | 1514557.001
2022-08-01 | 1413632.284
2022-09-01 | 1406665.965
2022-10-01 | 1038440.051
2022-11-01 | 1333021.203
2022-12-01 | 1256008.38
2023-01-01 | 1155362.326
2023-02-01 | 1142998.671
2023-03-01 | 1201145.905
2023-04-01 | 1243299.058
2023-05-01 | 1397041.715
2023-06-01 | 1490155.227
2023-07-01 | 1583975.759
2023-08-01 | 1580852.659
2023-09-01 | 1571265.596
2023-10-01 | 1616781.826
2023-11-01 | 1389705.238
2023-12-01 | 1358677.882
2024-01-01 | 1223336.571
2024-02-01 | 1210906.531
2024-03-01 | 1433193.393
Abr-2024 | 1397388.624
2024-05-01 | 1452814.117
2024-06-01 | 1539629.251
2024-07-01 | 1585516.009
2024-08-01 | 1562422.06
2024-09-01 | 1456338.235
2024-10-01 | 1603514.044
2024-11-01 | 1391164.77
2024-12-01 | 1373580.357
2025-01-01 | 1161667.135
2025-02-01 | 1169849.947
2025-03-01 | 1313234.831
2025-04-01 | 1294661.772
2025-05-01 | 1307475.129
2025-06-01 | 1462427.798

## x - UPDATE
Annual Compliance Report
Cartera de Energía Renovable - Año Natural 2024
Energía Renovable Adquirida (GWh) :
|  | PPOA's | 397
|  | DG | 640
|  | Total | 1037
Energía distribuida a los clientes (GWh)
|  | Energía Distribuida | 17230
|  | Hidro | 48
|  | Total | 17182
| % de Cumplimiento | 6.04%
|  | CER's Adquiridos | 397
Cartera de Energía Renovable - Año Natural 2023
Energía Renovable Adquirida (GWh) :
|  | PPOA's | 386
|  | DG | 453
|  | Total | 839
Energía distribuida a los clientes (GWh)
|  | Energía Distribuida | 16654
|  | Hidro | 38
|  | Total | 16616
| % de Cumplimiento | 5.05%
|  | CER's Adquiridos | 386
Cartera de Energía Renovable - Año Natural 2022
Energía Renovable Adquirida (GWh) :
|  | PPOA's | 422
|  | DG | 264
|  | Total | 686
Energía distribuida a los clientes (GWh)
|  | Energía Distribuida | 15683
|  | Hidro | 44
|  | Total | 15639
| % de Cumplimiento | 4.39%
|  | CER's Adquiridos | 422
Cartera de Energía Renovable - Año Natural 2021
Energía Renovable Adquirida (GWh) :
|  | PPOA's | 452
|  | DG | 162
|  | Total | 614
Energía distribuida a los clientes (GWh)
|  | Energía Distribuida | 16269
|  | Hidro | 40
|  | Total | 16230
| % de Cumplimiento | 3.78%
|  | CER's Adquiridos | 452
Cartera de Energía Renovable - Año Natural 2020
Energía Renovable Adquirida (GWh) :
|  | PPOA's | 411.12
|  | DG | 110.43
|  | Total | 521.55
Energía distribuida a los clientes (GWh)
|  | Energía Distribuida | 16035.29
|  | Hidro | 50.2
|  | Total | 15985.09
| % de Cumplimiento | 3.26%
|  | CER's Adquiridos | 411.12

## RO ii
Project Number | Nameplate Capacity (kW) | Customer Class | Metering Arrangement | Capacity Range | Generation Technology Used | Storage Available (kWh)
21-0-007 | 1430 | Industrial | No | 1.25MW-1.5MW | CHP | N/A
21-0-005 | 1430 | Industrial | No | 1.25MW-1.5MW | CHP | N/A
21-0-004 | 1430 | Industrial | No | 1.25MW-1.5MW | CHP | N/A
2024-GD-00289 | 1500 | Comercial | No | 1.25MW-1.5MW | Photovoltaic | N/A
21-0-006 | 1430 | Industrial | No | 1.25MW-1.5MW | CHP | N/A
2025-GD-00182 | 1476 | Comercial | Yes | 1.25MW-1.5MW | Photovoltaic | N/A
20-0-008 | 1354 | Industrial | No | 1.25MW-1.5MW | CHP | N/A
2024-GD-00225 | 1650 | Industrial | Yes | 1.5MW-1.75MW | Photovoltaic | N/A
2021-GD-09938 | 1608 | Comercial | Yes | 1.5MW-1.75MW | Photovoltaic | N/A
19-0-002 | 1748 | Industrial | No | 1.5MW-1.75MW | CHP | N/A
2025-GD-00156 | 1625 | Comercial | Yes | 1.5MW-1.75MW | Photovoltaic | N/A
2023-GD-39399 | 1800 | Comercial | No | 1.75MW-2MW | Photovoltaic | N/A
12-0-034 | 2000 | Comercial | Yes | 1.75MW-2MW | Photovoltaic | N/A
2026-GD-00012 | 126 | Comercial | No | 100-250kW | Photovoltaic | N/A
2026-GD-00013 | 102 | Comercial | No | 100-250kW | Photovoltaic | N/A
2026-GD-00008 | 238 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2021-GD-03549 | 132 | Comercial | No | 100-250kW | Photovoltaic | N/A
2024-GD-00155 | 106 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2018-GD-01051 | 176 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-22734 | 132 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00257 | 106 | Comercial | No | 100-250kW | Photovoltaic | N/A
13-4-0166GD | 116 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00282 | 106 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
09-2-307 | 147 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
15-3-1226 | 120 | Industrial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-02623 | 198 | Comercial | No | 100-250kW | Photovoltaic | N/A
2022-GD-18283 | 200 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-03232 | 144 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00100 | 139.3 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-01342 | 159 | Comercial | No | 100-250kW | Photovoltaic | N/A
11-2-581 | 144 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00134 | 143 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00280 | 103.5 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00149 | 212 | Comercial | No | 100-250kW | Photovoltaic | N/A
2018-GD-01175 | 150 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
12-2-346 | 186.08 | Gubernamental | No | 100-250kW | Photovoltaic | N/A
2024-GD-00226 | 153.9 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-07934 | 159 | Comercial | No | 100-250kW | Photovoltaic | N/A
2024-GD-00223 | 114 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00099 | 106 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
07-3-070A | 250 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00276 | 116 | Comercial | No | 100-250kW | Photovoltaic | N/A
2020-GD-00101 | 212 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00071 | 198 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2018-GD-02126 | 106 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-01709 | 159 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-00368 | 113.965 | Comercial | No | 100-250kW | Photovoltaic | N/A
2020-GD-00656 | 106 | Gubernamental | No | 100-250kW | Photovoltaic | N/A
2020-GD-00370 | 113.965 | Comercial | No | 100-250kW | Photovoltaic | N/A
14-6-0497 | 200 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00097 | 106 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2022-GD-17887 | 126.08 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-04039 | 151.63 | Comercial | No | 100-250kW | Photovoltaic | N/A
2019-GD-01996 | 159 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2018-GD-02160 | 196.2 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-00935 | 133 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00246 | 218 | Comercial | No | 100-250kW | Photovoltaic | N/A
2023-GD-03001 | 230.69 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
11-2-426 | 172 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00258 | 212 | Comercial | No | 100-250kW | Photovoltaic | N/A
12-1-475A | 168 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-01901 | 110.33 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2022-GD-07215 | 133.2 | Comercial | No | 100-250kW | Photovoltaic | 660
2025-GD-00192 | 225 | Comercial | No | 100-250kW | Photovoltaic | N/A
2018-GD-01146 | 105 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00048 | 119 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00055 | 231.3 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00065 | 165.3 | Comercial | No | 100-250kW | Photovoltaic | N/A
2019-GD-00988 | 198 | Comercial | No | 100-250kW | Photovoltaic | N/A
2024-GD-00206 | 245.3 | Comercial | No | 100-250kW | Photovoltaic | N/A
12-3-112A | 126 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-00971 | 732.6 | Industrial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00064 | 150 | Gubernamental | No | 100-250kW | Photovoltaic | N/A
99-3-234B | 168 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00213 | 196 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-01317 | 106 | Comercial | Yes | 100-250kW | Photovoltaic | 27
2024-GD-00152 | 106 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-24959 | 132 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
15-6-0303 | 240 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2018-GD-00260 | 115 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00163 | 185 | Comercial | No | 100-250kW | Photovoltaic | N/A
10-6-0104 | 180 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00118 | 150 | Comercial | No | 100-250kW | Photovoltaic | N/A
13-7-167 | 225 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
99-3-385B2 | 144 | Comercial | No | 100-250kW | Photovoltaic | N/A
2025-GD-00212 | 120 | Comercial | No | 100-250kW | Photovoltaic | N/A
90-0-163F1 | 191.02 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
15-1-315 | 150 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-02209 | 132 | Comercial | No | 100-250kW | Photovoltaic | N/A
2024-GD-00256 | 106 | Comercial | No | 100-250kW | Photovoltaic | N/A
14-2-560 | 170 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
10-1-115 | 110.4 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-00438 | 212 | Industrial | Yes | 100-250kW | Photovoltaic | N/A
11-3-134 | 185 | Industrial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00037 | 132 | Comercial | No | 100-250kW | Photovoltaic | N/A
15-4-0462GD | 150 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00255 | 132 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-01866 | 149.885 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
12-7-002 | 190 | Industrial | Yes | 100-250kW | Photovoltaic | N/A
16-2-0629 | 120 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00245 | 106 | Comercial | No | 100-250kW | Photovoltaic | N/A
2023-GD-16803 | 225 | Comercial | No | 100-250kW | Photovoltaic | N/A
2019-GD-00433 | 172.6 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-04541 | 106 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
16-2-1590 | 120 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-20820 | 200 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
13-4-0149GD | 180 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-39273 | 164.61 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
13-3-093A | 164 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2022-GD-20907 | 191 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00039 | 103.3 | Comercial | No | 100-250kW | Photovoltaic | N/A
2020-GD-04533 | 212 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00190 | 240 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00135 | 132 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00215 | 139.9 | Comercial | No | 100-250kW | Photovoltaic | N/A
2024-GD-00154 | 132 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00040 | 180 | Comercial | No | 100-250kW | Photovoltaic | N/A
2024-GD-00133 | 140 | Comercial | No | 100-250kW | Photovoltaic | N/A
2020-GD-03525 | 121.6 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2018-GD-00305 | 175 | Comercial | No | 100-250kW | Photovoltaic | N/A
2021-GD-02895 | 111.81 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
13-2-564 | 150 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-39364 | 104.8 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00253 | 212 | Comercial | No | 100-250kW | Photovoltaic | N/A
2018-GD-00110 | 165 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
16-7-0916 | 109.9 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-20817 | 120 | Comercial | No | 100-250kW | Photovoltaic | N/A
2025-GD-00201 | 132 | Comercial | No | 100-250kW | Photovoltaic | N/A
2019-GD-02718 | 159 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-01784 | 132 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2024-GD-00259 | 240 | Comercial | No | 100-250kW | Photovoltaic | N/A
2023-GD-22432 | 112 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-08653 | 116.82 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
99-3-235B1 | 192 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00102 | 159 | Comercial | No | 100-250kW | Photovoltaic | N/A
12-6-0208 | 192 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-00372 | 121.54 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-04678 | 146 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-01888 | 126 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00114 | 133.2 | Comercial | No | 100-250kW | Photovoltaic | N/A
2022-GD-31477 | 106 | Comercial | No | 100-250kW | Photovoltaic | N/A
12-3-166 | 140 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
09-2-071 | 150 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
12-2-287 | 225 | Industrial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00093 | 132 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2021-GD-02430 | 115.05 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
12-6-0085 | 200 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
16-4-0713GD | 113.52 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-01976 | 150 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00045 | 189 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
11-5-0190A | 144 | Comercial | No | 100-250kW | Photovoltaic | N/A
2021-GD-00252 | 199.42 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
11-2-427 | 172 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
14-6-0068 | 120 | Industrial | Yes | 100-250kW | Photovoltaic | N/A
2023-GD-09648 | 198 | Comercial | No | 100-250kW | Photovoltaic | N/A
14-2-996 | 184 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-09346 | 198 | Gubernamental | Yes | 100-250kW | Photovoltaic | N/A
2019-GD-02625 | 106 | Comercial | No | 100-250kW | Photovoltaic | N/A
2023-GD-10890 | 106.1 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2017-GD-00636 | 176 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2020-GD-04530 | 172 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2018-GD-00374 | 156 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
15-7-247 | 200 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2025-GD-00219 | 132 | Comercial | No | 100-250kW | Photovoltaic | N/A
2020-GD-02122 | 132 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
89-0-416D | 216 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2022-GD-11810 | 150 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2018-GD-00158 | 150 | Comercial | No | 100-250kW | Photovoltaic | N/A
2025-GD-00140 | 240 | Industrial | No | 100-250kW | Photovoltaic | N/A
11-6-0106 | 168 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2021-GD-06124 | 216 | Industrial | No | 100-250kW | Photovoltaic | N/A
2026-GD-00004 | 1117 | Gubernamental | No | 1MW-1.25MW | Photovoltaic | N/A
20-0-013 | 1018 | Industrial | No | 1MW-1.25MW | CHP | N/A
2024-GD-00237 | 1056 | Comercial | No | 1MW-1.25MW | Photovoltaic | N/A
2024-GD-00074 | 1043 | Comercial | No | 1MW-1.25MW | Hybrid | N/A
2024-GD-00251 | 1219 | Comercial | No | 1MW-1.25MW | CHP | N/A
2026-GD-00003 | 288.6 | Gubernamental | No | 250-500kW | Photovoltaic | N/A
2023-GD-25920 | 450 | Comercial | No | 250-500kW | Photovoltaic | N/A
15-9-423 | 360 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2025-GD-00101 | 396 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
13-0-010 | 500 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
13-0-058 | 500 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
14-3-070 | 300 | Industrial | No | 250-500kW | Photovoltaic | N/A
2025-GD-00098 | 264 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00061 | 297.3 | Comercial | No | 250-500kW | Photovoltaic | N/A
2021-GD-05805 | 300 | Comercial | No | 250-500kW | Photovoltaic | N/A
98-3-401A | 345 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
13-2-694 | 405 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2023-GD-19995 | 500 | Comercial | No | 250-500kW | Photovoltaic | N/A
2018-GD-01328 | 340 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00200 | 330 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2025-GD-00133 | 495.3 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00050 | 462 | Comercial | No | 250-500kW | Photovoltaic | N/A
2025-GD-00096 | 383 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2019-GD-03280 | 298.3 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2025-GD-00104 | 375 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
88-9-288D1 | 355 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00278 | 500 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00217 | 332 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00049 | 363.3 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00058 | 264 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00053 | 351.3 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00063 | 449 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00056 | 264 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00054 | 383 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00057 | 363.3 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00038 | 363.3 | Comercial | No | 250-500kW | Photovoltaic | N/A
2021-GD-13138 | 297.3 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
12-0-033 | 500 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00064 | 363.3 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2022-GD-26841 | 340 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00187 | 264 | Comercial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00068 | 429.3 | Comercial | No | 250-500kW | Photovoltaic | N/A
2021-GD-05808 | 400 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
13-1-330 | 400 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
13-6-0291 | 307 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
14-4-0142 | 324 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2025-GD-00116 | 264 | Comercial | No | 250-500kW | Photovoltaic | N/A
2018-GD-01324 | 496 | Industrial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00264 | 396 | Comercial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00046 | 317 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00265 | 462 | Comercial | No | 250-500kW | Photovoltaic | N/A
14-6-0271 | 408 | Industrial | Yes | 250-500kW | Photovoltaic | N/A
12-5-0117A | 276.5 | Comercial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00279 | 300 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
13-7-065 | 270 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
15-4-0461GD_RE(2) | 295.68 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2025-GD-00082 | 384 | Gubernamental | No | 250-500kW | Photovoltaic | N/A
2023-GD-20717 | 253.6 | Comercial | No | 250-500kW | Photovoltaic | N/A
2020-GD-02098 | 477 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2020-GD-03254 | 264 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00188 | 437 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
14-7-782 | 300.04 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
11-7-210-A | 333 | Industrial | Yes | 250-500kW | Photovoltaic | N/A
2019-GD-02624 | 264 | Comercial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00052 | 383 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2022-GD-07734 | 396 | Comercial | No | 250-500kW | Photovoltaic | N/A
2017-GD-02047 | 499 | Industrial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00191 | 265 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
12-6-0007 | 288 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2025-GD-00208 | 298.3 | Comercial | No | 250-500kW | Photovoltaic | N/A
2019-GD-00737 | 284 | Comercial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00262 | 265 | Comercial | No | 250-500kW | Photovoltaic | N/A
2022-GD-32127 | 489 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
12-1-041 | 500 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
13-0-046 | 500 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2023-GD-13295 | 424 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2023-GD-26563 | 393.6 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
13-1-339 | 439.03 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00164 | 311.52 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00211 | 482.3 | Comercial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00062 | 297.3 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00212 | 403.3 | Comercial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00294 | 278 | Comercial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00047 | 449 | Comercial | No | 250-500kW | Photovoltaic | N/A
13-7-202 | 500 | Comercial | Yes | 250-500kW | Photovoltaic | N/A
2024-GD-00179 | 275 | Comercial | No | 250-500kW | Photovoltaic | N/A
2025-GD-00206 | 375 | Comercial | No | 250-500kW | Photovoltaic | N/A
2022-GD-29752 | 495 | Comercial | No | 250-500kW | Photovoltaic | N/A
2023-GD-20478 | 384 | Comercial | No | 250-500kW | Photovoltaic | N/A
2025-GD-00214 | 427.9 | Comercial | No | 250-500kW | Photovoltaic | #N/A
2019-GD-01853 | 264 | Industrial | No | 250-500kW | Photovoltaic | N/A
2024-GD-00060 | 396 | Comercial | No | 250-500kW | Photovoltaic | N/A
2021-GD-09012 | 3000 | Industrial | No | 2MW+ | CHP | N/A
2021-GD-10145 | 2855 | Industrial | No | 2MW+ | CHP | N/A
2021-GD-05177 | 3423 | Industrial | No | 2MW+ | CHP | N/A
2024-GD-00220 | 5004 | Comercial | No | 2MW+ | CHP | N/A
16-0-014 | 2720 | Comercial | Yes | 2MW+ | Photovoltaic | N/A
2023-GD-37692 | 2875 | Industrial | No | 2MW+ | Photovoltaic | N/A
16-0-015 | 2228 | Industrial | No | 2MW+ | CHP | N/A
2024-GD-00095 | 9999 | Comercial | No | 2MW+ | CHP | N/A
18-0-007 | 9370 | Industrial | No | 2MW+ | CHP | N/A
2025-GD-00142 | 2492 | Industrial | No | 2MW+ | CHP | N/A
16-0-009 | 7000 | Industrial | No | 2MW+ | CHP | N/A
2024-GD-00141 | 4928 | Comercial | No | 2MW+ | Photovoltaic | N/A
10-0-039 | 5000 | Comercial | Yes | 2MW+ | Photovoltaic | N/A
2025-GD-00165 | 3132 | Comercial | No | 2MW+ | Hybrid | N/A
2022-GD-09431 | 10420 | Industrial | No | 2MW+ | CHP | N/A
17-0-008 | 4600 | Industrial | No | 2MW+ | CHP | N/A
2025-GD-00034 | 2044.3 | Comercial | Yes | 2MW+ | Photovoltaic | N/A
20-0-004 | 2282 | Industrial | No | 2MW+ | CHP | N/A
2023-GD-17075 | 3114 | Industrial | No | 2MW+ | CHP | N/A
2025-GD-00170 | 3750 | Gubernamental | No | 2MW+ | Photovoltaic | #N/A
2025-GD-00218 | 2500 | Gubernamental | No | 2MW+ | Photovoltaic | #N/A
19-0-004 | 2396 | Industrial | No | 2MW+ | CHP | N/A
2024-GD-00291 | 3074.4 | Gubernamental | No | 2MW+ | Hybrid | N/A
2026-GD-00033 | 530 | Comercial | No | 500-750kW | Photovoltaic | N/A
2026-GD-00024 | 625 | Comercial | No | 500-750kW | Photovoltaic | N/A
2024-GD-00051 | 528 | Comercial | No | 500-750kW | Photovoltaic | N/A
2022-GD-23648 | 726 | Comercial | No | 500-750kW | Photovoltaic | N/A
2025-GD-00155 | 660 | Comercial | Yes | 500-750kW | Photovoltaic | N/A
2023-GD-38276 | 575 | Comercial | No | 500-750kW | Photovoltaic | N/A
2023-GD-20479 | 516 | Comercial | No | 500-750kW | Photovoltaic | N/A
14-0-022 | 723 | Industrial | Yes | 500-750kW | Photovoltaic | N/A
15-7-339 | 614 | Comercial | Yes | 500-750kW | Photovoltaic | N/A
2023-GD-23978 | 750 | Comercial | No | 500-750kW | Photovoltaic | N/A
2025-GD-00198 | 746.3 | Comercial | No | 500-750kW | Photovoltaic | N/A
88-9-086B | 538.24 | Comercial | Yes | 500-750kW | Photovoltaic | N/A
2018-GD-02101 | 999 | Industrial | No | 500-750kW | Photovoltaic | N/A
2021-GD-05809 | 600 | Comercial | No | 500-750kW | Photovoltaic | N/A
2024-GD-00072 | 515 | Comercial | Yes | 500-750kW | Photovoltaic | N/A
2024-GD-00272 | 537 | Industrial | Yes | 500-750kW | Photovoltaic | N/A
2024-GD-00156 | 530 | Comercial | No | 500-750kW | Photovoltaic | N/A
14-0-007 | 942 | Industrial | Yes | 500-750kW | Photovoltaic | N/A
2024-GD-00067 | 528 | Comercial | No | 500-750kW | Photovoltaic | N/A
2023-GD-30743 | 528 | Comercial | No | 500-750kW | Photovoltaic | N/A
16-7-0647 | 545 | Comercial | No | 500-750kW | Photovoltaic | N/A
2024-GD-00192 | 600 | Comercial | Yes | 500-750kW | Photovoltaic | N/A
2024-GD-00113 | 540 | Comercial | No | 500-750kW | Photovoltaic | N/A
2025-GD-00089 | 720 | Comercial | No | 500-750kW | Photovoltaic | N/A
14-0-023 | 594 | Industrial | Yes | 500-750kW | Photovoltaic | N/A
2024-GD-00066 | 528 | Comercial | No | 500-750kW | Photovoltaic | N/A
2024-GD-00059 | 515 | Comercial | No | 500-750kW | Photovoltaic | N/A
2023-GD-20475 | 732 | Comercial | No | 500-750kW | Photovoltaic | N/A
2023-GD-19994 | 656 | Comercial | No | 500-750kW | Photovoltaic | N/A
2023-GD-20706 | 744 | Comercial | No | 500-750kW | Photovoltaic | N/A
2025-GD-00199 | 746.3 | Comercial | No | 500-750kW | Photovoltaic | N/A
2026-GD-00019 | 792 | Industrial | No | 750kW-1MW | Photovoltaic | N/A
2026-GD-00006 | 924 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
2026-GD-00026 | 792 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
2023-GD-38304 | 766.6 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
2018-GD-00350 | 801 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
2023-GD-29391 | 944.3 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
2019-GD-02741 | 864 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2024-GD-00238 | 1000 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
13-0-032 | 1000 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2020-GD-08445 | 800 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2018-GD-01683 | 987 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2024-GD-00096 | 784 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
2018-GD-01792 | 998 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
13-2-177 | 893 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2019-GD-03201 | 900 | Industrial | No | 750kW-1MW | Photovoltaic | N/A
20-0-002 | 794 | Industrial | No | 750kW-1MW | CHP | N/A
2023-GD-35465 | 800 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2024-GD-00273 | 780 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
16-0-006 | 993 | Industrial | Yes | 750kW-1MW | Photovoltaic | N/A
14-0-020 | 1000 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2022-GD-06212 | 800 | Industrial | No | 750kW-1MW | Photovoltaic | N/A
17-0-007 | 870 | Industrial | No | 750kW-1MW | CHP | N/A
2023-GD-20485 | 986 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
13-0-045 | 993.6 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2024-GD-00092 | 960 | Industrial | No | 750kW-1MW | Photovoltaic | N/A
12-6-203 | 1000 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2023-GD-08748 | 990 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
15-0-009 | 960 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2025-GD-00088 | 1000 | Comercial | Yes | 750kW-1MW | Photovoltaic | N/A
2024-GD-00298 | 998.2 | Comercial | No | 750kW-1MW | Photovoltaic | N/A
2025-GD-00136 | 1857 | Industrial | Yes | 1.75MW-2MW | CHP | N/A
2019-GD-00901 | 140 | Comercial | Yes | 100-250kW | PV | #N/A
2017-GD-00701 | 100 | Comercial | Yes | 0-100kW | Photovoltaic | N/A
13-1-221 | 100 | Comercial | Yes | 0-100kW | Photovoltaic | N/A
14-0-009 | 100 | Industrial | Yes | 0-100kW | Photovoltaic | N/A
2025-GD-00121 | 120 | Comercial | Yes | 100-250kW | Photovoltaic | N/A
2022-GD-20834 | 172.24 | Comercial | Yes | 100-250kW | PV | #N/A
2023-GD-08827 | 105 | Comercial | Yes | 100-250kW | PV | #N/A
13-3-150 | 100 | Comercial | Yes | 0-100kW | Photovoltaic | N/A

## RO iii
Project Number | Nameplate Capacity (kW) | Customer Class | Metering Arrangement | Capacity Range
2026-GD-00007 | 86.3 | Comercial | No | 0-100kW
2026-GD-00037 | 90 | Comercial | Yes | 0-100kW
202603-NM25-02311 | 10 | Residencial | Yes
202603-NM25-02434 | 3.54 | Residencial | Yes | 0-100kW
202603-NM25-01235 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02582 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01704 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00916 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-01196 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01017 | 9.15 | Comercial | Yes | 0-100kW
202601-NM25-02941 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01446 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02498 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01772 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02129 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02148 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02074 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02175 | 6.588 | Residencial | Yes | 0-100kW
202601-NM25-02103 | 6 | Comercial | Yes | 0-100kW
202602-NM25-01402 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01949 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01088 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02301 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02629 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00768 | 7.6 | Residencial | No | 0-100kW
202602-NM25-00679 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00381 | 9.882 | Residencial | Yes | 0-100kW
202601-NM25-01711 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03178 | 6 | Residencial | Yes | 0-100kW
202602-NM25-00005 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-03443 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02496 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02732 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00967 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02153 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01997 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02004 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01611 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-05431 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-03723 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00949 | 5.376 | Residencial | Yes | 0-100kW
202512-NM25-01770 | 7.6 | Comercial | Yes | 0-100kW
202601-NM25-00658 | 6.144 | Residencial | Yes | 0-100kW
202510-NM25-04189 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00599 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00526 | 15 | Residencial | Yes | 0-100kW
202601-NM25-00388 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02864 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02195 | 4.546 | Residencial | Yes | 0-100kW
202602-NM25-02624 | 9.562 | Residencial | Yes | 0-100kW
202602-NM25-01883 | 6.902 | Residencial | Yes | 0-100kW
202602-NM25-01852 | 19.5 | Residencial | Yes | 0-100kW
202511-NM25-00827 | 15.2 | Residencial | No | 0-100kW
202601-NM25-02630 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-02248 | 8.644 | Residencial | Yes | 0-100kW
2026-GD-00056 | 55.5 | Comercial | No | 0-100kW
2026-GD-00038 | 30 | Comercial | No | 0-100kW
2026-GD-00032 | 30 | Comercial | No | 0-100kW
2026-GD-00023 | 30.1 | Residencial | No | 0-100kW
2026-GD-00018 | 36 | Comercial | No | 0-100kW
2026-GD-00016 | 34.5 | Residencial | No | 0-100kW
2026-GD-00009 | 33.3 | Comercial | No | 0-100kW
2026-GD-00058 | 30.68 | Comercial | No | 0-100kW
2026-GD-00027 | 30 | Comercial | No | 0-100kW
2026-GD-00014 | 33.02 | Comercial | No | 0-100kW
2026-GD-00051 | 32 | Comercial | No | 0-100kW
2026-GD-00047 | 48 | Comercial | No | 0-100kW
2026-GD-00046 | 34.2 | Comercial | No | 0-100kW
2026-GD-00044 | 46.77 | Comercial | No | 0-100kW
2026-GD-00040 | 32.62 | Comercial | No | 0-100kW
2026-GD-00010 | 34.5 | Comercial | No | 0-100kW
2026-GD-00053 | 36 | Comercial | No | 0-100kW
2026-GD-00043 | 32 | Comercial | No | 0-100kW
2026-GD-00039 | 30 | Comercial | No | 0-100kW
2026-GD-00030 | 34.5 | Comercial | No | 0-100kW
2026-GD-00020 | 48 | Comercial | No | 0-100kW
2026-GD-00055 | 99.9 | Comercial | No | 0-100kW
2026-GD-00050 | 34.2 | Comercial | No | 0-100kW
2026-GD-00035 | 30 | Comercial | No | 0-100kW
2026-GD-00029 | 60 | Comercial | No | 0-100kW
2026-GD-00011 | 30.2 | Comercial | No | 0-100kW
2026-GD-00057 | 60 | Comercial | No | 0-100kW
2026-GD-00042 | 56 | Comercial | No | 0-100kW
2026-GD-00022 | 33.3 | Comercial | No | 0-100kW
202603-NM25-00981 | 18 | Residencial | Yes | 0-100kW
202603-NM25-02539 | 15 | Residencial | Yes | 0-100kW
202603-NM25-02534 | 24 | Residencial | Yes | 0-100kW
202603-NM25-00913 | 5 | Residencial | Yes | 0-100kW
202602-NM25-00274 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-02964 | 3.456 | Residencial | Yes | 0-100kW
202603-NM25-02007 | 12 | Residencial | No | 0-100kW
202512-NM25-06022 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02545 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02509 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00452 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02505 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01784 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02507 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01634 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05158 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00775 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00075 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02468 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02466 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01356 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02445 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02492 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02457 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02194 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02159 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02488 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01269 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01967 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02030 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02463 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06232 | 5.76 | Residencial | No | 0-100kW
202603-NM25-02485 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01914 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02482 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01898 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02479 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02453 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01965 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-02476 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02472 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01988 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02467 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00389 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02455 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02274 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01224 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02099 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02274 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02247 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02440 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02443 | 3.54 | Residencial | Yes | 0-100kW
202603-NM25-02442 | 9.6 | Residencial | Yes | 0-100kW
202601-NM25-01737 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00427 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-04204 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03357 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02421 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02433 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02393 | 3.84 | Residencial | Yes | 0-100kW
202508-NM25-03543 | 11.5 | Residencial | No | 0-100kW
202603-NM25-02428 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05177 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01959 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02383 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02143 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02426 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02317 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01880 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02413 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02360 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00206 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03815 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00171 | 11.5 | Residencial | No | 0-100kW
202510-NM25-01048 | 15 | Residencial | No | 0-100kW
202603-NM25-02277 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02132 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02407 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00437 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02399 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02170 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02402 | 4.224 | Residencial | Yes | 0-100kW
202603-NM25-02401 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02398 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02991 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-01692 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04354 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02394 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01279 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02391 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02650 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05490 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00943 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02354 | 9 | Residencial | Yes | 0-100kW
202602-NM25-00979 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03327 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00412 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02165 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02593 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-03584 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02379 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01381 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00148 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00092 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-02372 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03254 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01678 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02369 | 4.992 | Residencial | Yes | 0-100kW
202603-NM25-02365 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00494 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04783 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01808 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01012 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-04239 | 6.912 | Residencial | Yes | 0-100kW
202602-NM25-01631 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01249 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02358 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02210 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03957 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02773 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06255 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01975 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02352 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02048 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00372 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00053 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00906 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02268 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04970 | 11.5 | Residencial | No | 0-100kW
202507-NM25-03899 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-03334 | 11.5 | Residencial | No | 0-100kW
202603-NM25-02339 | 3.456 | Residencial | Yes | 0-100kW
202511-NM25-01465 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01456 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01701 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02315 | 20 | Comercial | No | 0-100kW
202603-NM25-01468 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06242 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02336 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02338 | 11.904 | Residencial | No | 0-100kW
202509-NM25-06014 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02282 | 9.15 | Residencial | Yes | 0-100kW
202512-NM25-01336 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02334 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02623 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02332 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02322 | 3.456 | Residencial | Yes | 0-100kW
202603-NM25-02279 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00121 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01631 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01831 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-00211 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02297 | 22.8 | Residencial | Yes | 0-100kW
202603-NM25-02120 | 16 | Residencial | Yes | 0-100kW
202603-NM25-01272 | 12 | Comercial | No | 0-100kW
202603-NM25-02302 | 7.6 | Residencial | No | 0-100kW
202603-NM25-02278 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02280 | 12 | Residencial | No | 0-100kW
202603-NM25-02256 | 18 | Comercial | No | 0-100kW
202603-NM25-01225 | 5 | Residencial | Yes | 0-100kW
202603-NM25-00977 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05150 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01790 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02102 | 18 | Comercial | No | 0-100kW
202603-NM25-02289 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02626 | 11.5 | Residencial | No | 0-100kW
202603-NM25-02287 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01751 | 15 | Residencial | No | 0-100kW
202603-NM25-02290 | 23 | Comercial | Yes | 0-100kW
202603-NM25-02288 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00385 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01814 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02080 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00319 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02275 | 17.6 | Residencial | Yes | 0-100kW
202602-NM25-01663 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01452 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02276 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02113 | 10.368 | Residencial | Yes | 0-100kW
202603-NM25-01363 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02266 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-02265 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-01991 | 24 | Comercial | Yes | 0-100kW
202603-NM25-02248 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01710 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02264 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02267 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01870 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00292 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02521 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02860 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03603 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02292 | 15 | Residencial | Yes | 0-100kW
202601-NM25-00973 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01697 | 24 | Residencial | Yes | 0-100kW
202512-NM25-04470 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02174 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01088 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02238 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03050 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04781 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00646 | 11.5 | Residencial | No | 0-100kW
202512-NM25-04734 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02592 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01445 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02207 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02253 | 3.456 | Residencial | Yes | 0-100kW
202603-NM25-01021 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-02384 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04811 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01862 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02245 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02249 | 8 | Residencial | No | 0-100kW
202603-NM25-02204 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01943 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02241 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01866 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03573 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01309 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-02156 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05990 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01103 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00767 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01280 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03259 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01550 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02188 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05163 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02237 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02672 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01983 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02234 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02232 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01406 | 25 | Comercial | Yes | 0-100kW
202603-NM25-01861 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00935 | 9.6 | Residencial | Yes | 0-100kW
202603-NM25-01952 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-04470 | 3.072 | Residencial | Yes | 0-100kW
202603-NM25-01970 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-00478 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02121 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-02231 | 9 | Residencial | Yes | 0-100kW
202512-NM25-04553 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00993 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03465 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04665 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06214 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01705 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02224 | 5.124 | Residencial | Yes | 0-100kW
202603-NM25-02218 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02219 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02216 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02213 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02212 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01960 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-02200 | 4.25 | Residencial | Yes | 0-100kW
202603-NM25-02198 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02196 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02203 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01883 | 24 | Comercial | Yes | 0-100kW
202509-NM25-04946 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02189 | 15 | Residencial | Yes | 0-100kW
202603-NM25-00280 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02140 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01023 | 7.6 | Comercial | No | 0-100kW
202509-NM25-02231 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01890 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00359 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02719 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02033 | 4.224 | Residencial | Yes | 0-100kW
202603-NM25-01590 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02584 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02184 | 8.448 | Residencial | Yes | 0-100kW
202603-NM25-02182 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05991 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01326 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02035 | 6.912 | Residencial | Yes | 0-100kW
202603-NM25-01956 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02173 | 3.072 | Residencial | Yes | 0-100kW
202603-NM25-02146 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02150 | 16 | Residencial | Yes | 0-100kW
202601-NM25-02336 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05360 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00046 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00824 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02159 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02153 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02803 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-02161 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02157 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02084 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02269 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02075 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02152 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02311 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00592 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00122 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-00798 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-01749 | 12 | Residencial | Yes | 0-100kW
202603-NM25-01637 | 12 | Residencial | No | 0-100kW
202603-NM25-02018 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05530 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01897 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02016 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03558 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00723 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02135 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02031 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02137 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02136 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02133 | 11.5 | Residencial | No | 0-100kW
202603-NM25-02014 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00739 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02067 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00794 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00047 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00233 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00622 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02127 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01349 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00950 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01987 | 13.824 | Residencial | Yes | 0-100kW
202603-NM25-00612 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01053 | 16.104 | Residencial | Yes | 0-100kW
202603-NM25-01372 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-01819 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02109 | 12 | Residencial | Yes | 0-100kW
202603-NM25-00540 | 18 | Comercial | Yes | 0-100kW
202601-NM25-00123 | 9 | Comercial | No | 0-100kW
202602-NM25-02835 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01702 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-02716 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01662 | 5.28 | Residencial | Yes | 0-100kW
202603-NM25-01565 | 6.24 | Residencial | Yes | 0-100kW
202603-NM25-02111 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01038 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01380 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02513 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01583 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02104 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02522 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02881 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00382 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01581 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01342 | 7.2 | Residencial | Yes | 0-100kW
202601-NM25-03385 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01348 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02063 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02092 | 8 | Residencial | No | 0-100kW
202603-NM25-01996 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02096 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01154 | 12 | Residencial | Yes | 0-100kW
202603-NM25-02095 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00995 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02377 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03112 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-02090 | 20.256 | Comercial | No | 0-100kW
202603-NM25-00721 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00383 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02642 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01473 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02894 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01964 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-02088 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00729 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01370 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02076 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01779 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01360 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-02082 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01132 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01932 | 4.224 | Residencial | Yes | 0-100kW
202603-NM25-02005 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00315 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00697 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00390 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01910 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00910 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00227 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02071 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02070 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00881 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01889 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00462 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00638 | 18 | Residencial | No | 0-100kW
202603-NM25-01857 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01449 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04613 | 9 | Residencial | Yes | 0-100kW
202603-NM25-01175 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01193 | 8 | Residencial | Yes | 0-100kW
202603-NM25-02057 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05166 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01418 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02051 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00385 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00915 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02558 | 8.832 | Residencial | Yes | 0-100kW
202603-NM25-02050 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02028 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00048 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02047 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00568 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01942 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02042 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03103 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-02053 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02654 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01850 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00465 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00279 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03179 | 10 | Residencial | Yes | 0-100kW
202510-NM25-00158 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04918 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02029 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01873 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00365 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03240 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01472 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01755 | 24 | Residencial | Yes | 0-100kW
202601-NM25-01905 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-00726 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00312 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02807 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01477 | 8 | Residencial | Yes | 0-100kW
202509-NM25-06032 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01579 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01606 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00920 | 9 | Residencial | Yes | 0-100kW
202602-NM25-00244 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02019 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01181 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02026 | 8.064 | Residencial | Yes | 0-100kW
202603-NM25-01608 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01746 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00624 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01636 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01638 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01594 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01568 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01453 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01588 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01896 | 12 | Residencial | Yes | 0-100kW
202603-NM25-01725 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01213 | 11.4 | Residencial | No | 0-100kW
202603-NM25-01635 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02006 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01982 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02001 | 11.5 | Residencial | No | 0-100kW
202512-NM25-01669 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01999 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00923 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01958 | 23 | Gubernamental | Yes | 0-100kW
202602-NM25-00776 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01963 | 11.4 | Residencial | No | 0-100kW
202603-NM25-01542 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01995 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02492 | 12 | Residencial | Yes | 0-100kW
202603-NM25-01986 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01989 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00069 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01990 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01239 | 15 | Residencial | Yes | 0-100kW
202603-NM25-01985 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01979 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01431 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00658 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01973 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-02394 | 6.528 | Residencial | Yes | 0-100kW
202601-NM25-01215 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01869 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00317 | 8.832 | Residencial | Yes | 0-100kW
202603-NM25-01858 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02760 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02989 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03115 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00819 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00902 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02560 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00230 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01867 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03025 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01941 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01953 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01809 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03104 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00196 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01957 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01410 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01954 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01947 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02886 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00922 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01944 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02646 | 11.5 | Residencial | No | 0-100kW
202511-NM25-00822 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01696 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-01936 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01938 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01926 | 11.4 | Residencial | Yes | 0-100kW
202512-NM25-00688 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00877 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01937 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01123 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01845 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01934 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01856 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01931 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01928 | 6.528 | Comercial | Yes | 0-100kW
202603-NM25-01927 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00315 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00033 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01460 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02020 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01766 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01734 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03120 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02525 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01852 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01127 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01523 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00621 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01331 | 6 | Residencial | Yes | 0-100kW
202601-NM25-03042 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01764 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03668 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01915 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01286 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02139 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03855 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01689 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01912 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01391 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01909 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03790 | 4.224 | Residencial | Yes | 0-100kW
202603-NM25-01249 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02271 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00147 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01906 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01269 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00534 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00664 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03698 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02220 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01679 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01904 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01500 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01903 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00320 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04433 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01902 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00355 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01901 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01900 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01416 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03097 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03789 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01369 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01898 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02978 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00690 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02098 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01609 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01618 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-04286 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-01486 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01805 | 3.8 | Comercial | Yes | 0-100kW
202512-NM25-04960 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01017 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02239 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01400 | 8 | Residencial | Yes | 0-100kW
202512-NM25-04684 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01387 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01494 | 4.608 | Residencial | Yes | 0-100kW
202602-NM25-02502 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02887 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00379 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01754 | 12 | Residencial | No | 0-100kW
202603-NM25-01753 | 12 | Residencial | Yes | 0-100kW
202602-NM25-02888 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01051 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02346 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01890 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01888 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01206 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05017 | 20 | Comercial | No | 0-100kW
202603-NM25-01886 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01879 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-01884 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01881 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01885 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00844 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00626 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01882 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01877 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01955 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00146 | 5.376 | Residencial | Yes | 0-100kW
202603-NM25-01878 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03238 | 20 | Comercial | Yes | 0-100kW
202603-NM25-01467 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01875 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01621 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01747 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01695 | 13.824 | Residencial | Yes | 0-100kW
202603-NM25-01873 | 18.028 | Residencial | No | 0-100kW
202603-NM25-00885 | 6.144 | Residencial | Yes | 0-100kW
202512-NM25-05229 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01842 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01872 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01868 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01599 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01863 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01294 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-01270 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02845 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01860 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02750 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02587 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02167 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01298 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02993 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00570 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03112 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02959 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03227 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03750 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01476 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02988 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00705 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01848 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01228 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01855 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01851 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03116 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00938 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-02669 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01820 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01364 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00800 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02657 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01892 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01615 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01384 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01107 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00573 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00439 | 22.8 | Residencial | Yes | 0-100kW
202602-NM25-01102 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03209 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01335 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-01837 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02723 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00404 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01834 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00438 | 22.8 | Residencial | Yes | 0-100kW
202603-NM25-01830 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01833 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00946 | 6 | Residencial | Yes | 0-100kW
202603-NM25-01824 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01815 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02357 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01813 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01740 | 12 | Residencial | Yes | 0-100kW
202602-NM25-02619 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03644 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01469 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01007 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01303 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03133 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01793 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02883 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06125 | 11.5 | Residencial | No | 0-100kW
202510-NM25-03942 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01411 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01800 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01906 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00963 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01786 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00100 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01685 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01785 | 4.608 | Residencial | Yes | 0-100kW
202603-NM25-01788 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01674 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01733 | 10 | Residencial | Yes | 0-100kW
202603-NM25-01708 | 9 | Residencial | Yes | 0-100kW
202603-NM25-01647 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01777 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01781 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01773 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01771 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01128 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01050 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01770 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01769 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00556 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01664 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01757 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01580 | 9 | Residencial | No | 0-100kW
202602-NM25-02759 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01319 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01531 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01611 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01416 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01419 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01215 | 10 | Residencial | Yes | 0-100kW
202603-NM25-01642 | 6.8 | Residencial | Yes | 0-100kW
202602-NM25-01769 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01408 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01414 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01274 | 4.5 | Residencial | Yes | 0-100kW
202603-NM25-01421 | 5 | Residencial | Yes | 0-100kW
202602-NM25-02350 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01752 | 12 | Residencial | Yes | 0-100kW
202603-NM25-01748 | 12 | Residencial | Yes | 0-100kW
202603-NM25-00747 | 18 | Residencial | Yes | 0-100kW
202603-NM25-01261 | 9 | Residencial | Yes | 0-100kW
202603-NM25-00610 | 10 | Residencial | Yes | 0-100kW
202602-NM25-02356 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00932 | 9 | Residencial | Yes | 0-100kW
202602-NM25-02516 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02069 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02694 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02235 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02518 | 11.5 | Comercial | No | 0-100kW
202603-NM25-01720 | 3.072 | Residencial | Yes | 0-100kW
202602-NM25-02422 | 23 | Comercial | Yes | 0-100kW
202603-NM25-01726 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02517 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02033 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01497 | 9 | Residencial | Yes | 0-100kW
202603-NM25-01404 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03366 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01700 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01577 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01658 | 13.6 | Residencial | Yes | 0-100kW
202603-NM25-01409 | 12 | Residencial | Yes | 0-100kW
202506-NM25-02323 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01141 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01698 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01691 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01914 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00957 | 10.5 | Residencial | No | 0-100kW
202602-NM25-01923 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01555 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01922 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01687 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02265 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01437 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02270 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00741 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01694 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01264 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06051 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01788 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00894 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00951 | 15.2 | Residencial | Yes | 0-100kW
202603-NM25-01686 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01101 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01926 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01367 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01682 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01248 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01684 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02620 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01051 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01166 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01912 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00834 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00620 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01680 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01919 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02633 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02641 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01585 | 22.8 | Residencial | Yes | 0-100kW
202603-NM25-01676 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01673 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01872 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02429 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00636 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02601 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01670 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-02078 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01856 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02901 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04287 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01667 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02570 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01478 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02640 | 4.608 | Residencial | Yes | 0-100kW
202603-NM25-01668 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06038 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01665 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01991 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02560 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01666 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01661 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01585 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01664 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01663 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01727 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02387 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01659 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01604 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02481 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01564 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01531 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01503 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01657 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01655 | 13.056 | Residencial | Yes | 0-100kW
202603-NM25-01312 | 7.296 | Residencial | Yes | 0-100kW
202603-NM25-00420 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01652 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01653 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01823 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01617 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01600 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01650 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01649 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00544 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01623 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-01645 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01362 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01303 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05584 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06056 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01123 | 12 | Comercial | Yes | 0-100kW
202602-NM25-02528 | 10 | Residencial | Yes | 0-100kW
202512-NM25-04435 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03082 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02819 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02660 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01614 | 12 | Residencial | Yes | 0-100kW
202603-NM25-01633 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01277 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01616 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00581 | 12 | Residencial | Yes | 0-100kW
202603-NM25-01626 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01630 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01622 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-01627 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01471 | 6.8 | Residencial | Yes | 0-100kW
202603-NM25-01602 | 24 | Comercial | No | 0-100kW
202603-NM25-01625 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01033 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01624 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01547 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01620 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01473 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00580 | 4.5 | Residencial | Yes | 0-100kW
202603-NM25-01613 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02877 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01398 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01619 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01379 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01359 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01355 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01000 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-00607 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00097 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-01595 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01745 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01426 | 14.592 | Residencial | Yes | 0-100kW
202509-NM25-01410 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01496 | 9.6 | Residencial | Yes | 0-100kW
202603-NM25-01582 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00064 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02767 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00492 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01340 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01071 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02528 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01425 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02461 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00040 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00892 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05364 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01571 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01704 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01240 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01479 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01093 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03770 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00388 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01480 | 10 | Residencial | Yes | 0-100kW
202603-NM25-00760 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00406 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00457 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01553 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00875 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-00890 | 9 | Residencial | Yes | 0-100kW
202603-NM25-01201 | 12 | Residencial | Yes | 0-100kW
202603-NM25-01507 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-01549 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02255 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00551 | 9 | Residencial | Yes | 0-100kW
202603-NM25-01043 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01516 | 6 | Residencial | Yes | 0-100kW
202603-NM25-01439 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04086 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01536 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01535 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01129 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-01322 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03562 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00865 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01090 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01426 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02943 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00181 | 5.5 | Residencial | Yes | 0-100kW
202512-NM25-04425 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01870 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01246 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01522 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03090 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01510 | 23 | Residencial | Yes | 0-100kW
202508-NM25-05042 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00605 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01518 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01205 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00341 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01519 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01511 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00318 | 7.296 | Residencial | Yes | 0-100kW
202601-NM25-02464 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01508 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02522 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01513 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01424 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01495 | 7.6 | Residencial | No | 0-100kW
202603-NM25-01502 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00364 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01501 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01417 | 10 | Residencial | Yes | 0-100kW
202601-NM25-01716 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00421 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01498 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03912 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01493 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-01496 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01347 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-05182 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02838 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01371 | 5 | Residencial | Yes | 0-100kW
202603-NM25-00918 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01940 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02656 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00637 | 23 | Residencial | Yes | 0-100kW
202601-NM25-03033 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03050 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00757 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01485 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03081 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00532 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02069 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00029 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01042 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00380 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01454 | 9 | Residencial | Yes | 0-100kW
202601-NM25-02947 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06252 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00625 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01464 | 11.136 | Residencial | Yes | 0-100kW
202601-NM25-02938 | 7.6 | Residencial | No | 0-100kW
202508-NM25-01461 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01455 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01420 | 18 | Residencial | Yes | 0-100kW
202601-NM25-02932 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01459 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02488 | 9 | Comercial | Yes | 0-100kW
202603-NM25-01463 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02797 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00491 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01299 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00815 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01197 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02596 | 24.96 | Residencial | Yes | 0-100kW
202603-NM25-01364 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01445 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-01440 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01442 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02392 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00204 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00225 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02741 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03825 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04714 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01645 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00045 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02747 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00319 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01937 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01429 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01330 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01434 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03058 | 23 | Residencial | Yes | 0-100kW
202512-NM25-05280 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02522 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01427 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01076 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01428 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02035 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-02307 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03669 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-00720 | 5.856 | Residencial | Yes | 0-100kW
202602-NM25-02151 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-01346 | 9.216 | Residencial | Yes | 0-100kW
202603-NM25-00252 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00846 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01422 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00889 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03307 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01047 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00983 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01407 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03077 | 11.5 | Residencial | No | 0-100kW
202512-NM25-04797 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01445 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00934 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01953 | 16.104 | Residencial | Yes | 0-100kW
202603-NM25-01395 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00424 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01399 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01401 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01393 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00940 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01396 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01857 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01335 | 11.52 | Residencial | Yes | 0-100kW
202601-NM25-00118 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01392 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01352 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-01374 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01598 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01671 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01389 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00617 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01681 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01357 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01383 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00890 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00764 | 12 | Residencial | Yes | 0-100kW
202602-NM25-01937 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01376 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01841 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01368 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01020 | 25 | Residencial | Yes | 0-100kW
202602-NM25-01839 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01373 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01366 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01875 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-01926 | 6 | Residencial | Yes | 0-100kW
202602-NM25-01972 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02546 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01350 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01361 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02562 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02220 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02577 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00334 | 5.6 | Residencial | Yes | 0-100kW
202601-NM25-03006 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-03121 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01244 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00392 | 4.992 | Residencial | Yes | 0-100kW
202603-NM25-01290 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02431 | 24 | Comercial | Yes | 0-100kW
202512-NM25-05960 | 4.608 | Residencial | Yes | 0-100kW
202603-NM25-00879 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-03058 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04165 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00876 | 12 | Comercial | No | 0-100kW
202603-NM25-00390 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03893 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-01521 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01074 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01444 | 11.5 | Comercial | Yes | 0-100kW
202511-NM25-04122 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-01202 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00503 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01635 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01694 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01691 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02992 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02290 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01117 | 12 | Comercial | Yes | 0-100kW
202602-NM25-01108 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01337 | 23 | Residencial | Yes | 0-100kW
202506-NM25-00790 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01008 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01332 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01331 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01730 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01242 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01318 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03025 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01323 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02695 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01320 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02135 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01317 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00604 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01200 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-01218 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00556 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00947 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00063 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01315 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01314 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00983 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01690 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01313 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00200 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-01616 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01310 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01311 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00907 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01307 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01308 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00453 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01223 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05982 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06212 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01301 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01305 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01304 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01297 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02026 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01300 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01057 | 16.896 | Residencial | Yes | 0-100kW
202512-NM25-00704 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01299 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02857 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03005 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00082 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-01198 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00307 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01295 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01296 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02748 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01448 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01038 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02238 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00300 | 6.144 | Residencial | Yes | 0-100kW
202511-NM25-00950 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01315 | 11.5 | Comercial | Yes | 0-100kW
202511-NM25-03249 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02727 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01526 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01118 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00789 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01238 | 25 | Residencial | Yes | 0-100kW
202512-NM25-01375 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01287 | 8.54 | Residencial | Yes | 0-100kW
202601-NM25-01408 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01635 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01278 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00208 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00817 | 6 | Residencial | Yes | 0-100kW
202603-NM25-01273 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06188 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01262 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02539 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01271 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01270 | 11.5 | Residencial | No | 0-100kW
202512-NM25-03244 | 6.912 | Residencial | Yes | 0-100kW
202603-NM25-00777 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01268 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02752 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01257 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01267 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01265 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-01264 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00826 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01263 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00634 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02171 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01260 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00356 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00891 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01258 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00327 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01157 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01256 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00725 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01254 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01255 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01047 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01253 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01207 | 6.912 | Residencial | Yes | 0-100kW
202603-NM25-01250 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00858 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01036 | 12 | Residencial | Yes | 0-100kW
202602-NM25-02561 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05733 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03877 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00950 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01070 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00656 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-03197 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01247 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01050 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01244 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01243 | 8.64 | Residencial | Yes | 0-100kW
202603-NM25-00061 | 9 | Residencial | Yes | 0-100kW
202601-NM25-01836 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01146 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00066 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01897 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01008 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01866 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06158 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01248 | 6.8 | Comercial | Yes | 0-100kW
202601-NM25-03016 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00378 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00373 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01209 | 8 | Residencial | No | 0-100kW
202603-NM25-00926 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01232 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02257 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02971 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01332 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00151 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01226 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01058 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01221 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00163 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02406 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01608 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00627 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-01219 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01210 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03060 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01212 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01105 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01804 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00793 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06154 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03235 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-01076 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01203 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00165 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02643 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01053 | 8 | Residencial | Yes | 0-100kW
202603-NM25-01126 | 12.672 | Residencial | Yes | 0-100kW
202508-NM25-03262 | 10 | Residencial | Yes | 0-100kW
202601-NM25-01003 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01189 | 9 | Residencial | Yes | 0-100kW
202601-NM25-03125 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01190 | 5 | Residencial | Yes | 0-100kW
202603-NM25-01182 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01186 | 12 | Residencial | Yes | 0-100kW
202509-NM25-03393 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01040 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02625 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02640 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00348 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01173 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01177 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02659 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01178 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00608 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01174 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01163 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02719 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01165 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01171 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01143 | 19.2 | Residencial | Yes | 0-100kW
202601-NM25-00143 | 23 | Residencial | No | 0-100kW
202602-NM25-02714 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01169 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00801 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00828 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01167 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01096 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00231 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02632 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01130 | 3.456 | Residencial | Yes | 0-100kW
202602-NM25-02537 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02855 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01198 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00700 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02434 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00398 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-05486 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01141 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02585 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01662 | 5.6 | Residencial | Yes | 0-100kW
202603-NM25-01156 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01039 | 4.992 | Residencial | Yes | 0-100kW
202602-NM25-01851 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01152 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01026 | 7.6 | Residencial | No | 0-100kW
202603-NM25-01150 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01145 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02459 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01148 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00339 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01139 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01027 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02039 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-01685 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00426 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01142 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01138 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00415 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00864 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01136 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01110 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01445 | 7.6 | Comercial | Yes | 0-100kW
202602-NM25-02884 | 25 | Residencial | Yes | 0-100kW
202603-NM25-01131 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01397 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01561 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01049 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01127 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-05251 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01118 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02565 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00898 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-01040 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-01119 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00360 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01114 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00999 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01100 | 11.4 | Residencial | Yes | 0-100kW
202510-NM25-02082 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-01106 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01104 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00887 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01437 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01129 | 5.3 | Comercial | Yes | 0-100kW
202510-NM25-00837 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00772 | 9 | Residencial | Yes | 0-100kW
202511-NM25-02175 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01102 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00908 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-01099 | 3.456 | Residencial | Yes | 0-100kW
202603-NM25-00667 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00021 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00521 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03776 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00425 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04562 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00904 | 6 | Residencial | Yes | 0-100kW
202603-NM25-01097 | 11.4 | Comercial | No | 0-100kW
202602-NM25-00448 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01089 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00958 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01297 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01267 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00531 | 6 | Residencial | Yes | 0-100kW
202601-NM25-02333 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00976 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00407 | 12 | Residencial | Yes | 0-100kW
202601-NM25-02466 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01087 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00937 | 18 | Comercial | Yes | 0-100kW
202603-NM25-01094 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02648 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02458 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00902 | 23 | Comercial | Yes | 0-100kW
202601-NM25-00800 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02648 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00569 | 23 | Residencial | Yes | 0-100kW
202509-NM25-01326 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01081 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00843 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00718 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01089 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01086 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01085 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04335 | 9.216 | Residencial | Yes | 0-100kW
202601-NM25-02636 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01078 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01079 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00707 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02715 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00461 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01073 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05679 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01075 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01063 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01072 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01070 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00496 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-00630 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02162 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02644 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02576 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02972 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00639 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02574 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01595 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01786 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01045 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00987 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01225 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01268 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02608 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03954 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-01508 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00925 | 8.448 | Residencial | Yes | 0-100kW
202603-NM25-00866 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02886 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03354 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00875 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00982 | 15 | Residencial | No | 0-100kW
202603-NM25-01035 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01018 | 25 | Comercial | Yes | 0-100kW
202603-NM25-00948 | 10 | Residencial | Yes | 0-100kW
202603-NM25-01030 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03074 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00757 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00912 | 8 | Residencial | No | 0-100kW
202603-NM25-00256 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02618 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01029 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02896 | 3.66 | Residencial | Yes | 0-100kW
202603-NM25-00476 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01028 | 11.5 | Residencial | No | 0-100kW
202603-NM25-01024 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01775 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-01010 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01025 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01829 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01071 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01697 | 12 | Residencial | Yes | 0-100kW
202603-NM25-01005 | 12 | Residencial | Yes | 0-100kW
202603-NM25-00337 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01004 | 7.6 | Residencial | No | 0-100kW
202603-NM25-01012 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01014 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01442 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05170 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-01015 | 11.5 | Residencial | No | 0-100kW
202510-NM25-00137 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00729 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01009 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01011 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00594 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00951 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01859 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01252 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03467 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03360 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02595 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02038 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01003 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00997 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00363 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00024 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00998 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00996 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02748 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00936 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03024 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02649 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-00994 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00852 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00877 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00993 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00992 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00997 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00953 | 2.928 | Residencial | Yes | 0-100kW
202602-NM25-00294 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00193 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00662 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-00728 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00978 | 15 | Residencial | Yes | 0-100kW
202601-NM25-03421 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02519 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02538 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00306 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01015 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03938 | 15.36 | Residencial | Yes | 0-100kW
202602-NM25-01339 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02273 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00723 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00967 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-00971 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00190 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00356 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00968 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00956 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01164 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00578 | 15.36 | Residencial | No | 0-100kW
202601-NM25-01117 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00981 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00961 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03248 | 6.912 | Residencial | Yes | 0-100kW
202603-NM25-00962 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00954 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00959 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01426 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-00955 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00952 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01553 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00743 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01317 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00359 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00945 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03262 | 12.288 | Residencial | Yes | 0-100kW
202512-NM25-04050 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00942 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00105 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00941 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00935 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06152 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02281 | 5.31 | Residencial | Yes | 0-100kW
202603-NM25-00728 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02077 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05359 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00930 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06221 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00589 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01723 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02594 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00725 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00243 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01815 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00652 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00899 | 15 | Residencial | Yes | 0-100kW
202509-NM25-02268 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03298 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02017 | 22.8 | Residencial | Yes | 0-100kW
202603-NM25-00901 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01992 | 22.8 | Residencial | Yes | 0-100kW
202601-NM25-01098 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00429 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00277 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02871 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00785 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00160 | 11.4 | Residencial | Yes | 0-100kW
202603-NM25-00717 | 18 | Residencial | Yes | 0-100kW
202602-NM25-01477 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01666 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00883 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02419 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00884 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-00764 | 23 | Residencial | No | 0-100kW
202602-NM25-01417 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00583 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00876 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01882 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00874 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00820 | 15.36 | Residencial | Yes | 0-100kW
202510-NM25-01136 | 5.3 | Comercial | Yes | 0-100kW
202602-NM25-02703 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-05069 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00865 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-04015 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00736 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-01495 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00734 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00733 | 5.3 | Comercial | Yes | 0-100kW
202602-NM25-01320 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00727 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00724 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01067 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00823 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00321 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00175 | 9.516 | Residencial | Yes | 0-100kW
202601-NM25-01373 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02312 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01728 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00353 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00684 | 8 | Residencial | Yes | 0-100kW
202511-NM25-04406 | 23 | Residencial | Yes | 0-100kW
202507-NM25-01300 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01110 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02883 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02366 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00710 | 10 | Residencial | Yes | 0-100kW
202603-NM25-00818 | 18 | Residencial | Yes | 0-100kW
202601-NM25-00685 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-00592 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02191 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00593 | 24 | Residencial | Yes | 0-100kW
202512-NM25-05473 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00698 | 12 | Residencial | Yes | 0-100kW
202602-NM25-01419 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00540 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03542 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-00838 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00344 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-01077 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00841 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00840 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05561 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00839 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00720 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00718 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00837 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04981 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00836 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05505 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00835 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00518 | 12 | Residencial | Yes | 0-100kW
202511-NM25-03570 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03520 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00533 | 12 | Residencial | Yes | 0-100kW
202603-NM25-00833 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05941 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00371 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00831 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00443 | 15 | Residencial | Yes | 0-100kW
202602-NM25-01006 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00829 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00796 | 14.208 | Residencial | Yes | 0-100kW
202601-NM25-01982 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03028 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03797 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01037 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00821 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00628 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01039 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00816 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00466 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01596 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03168 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00653 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03834 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02090 | 5.376 | Residencial | Yes | 0-100kW
202603-NM25-00813 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00814 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00531 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00807 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00471 | 24 | Residencial | Yes | 0-100kW
202603-NM25-00233 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03972 | 8.448 | Residencial | No | 0-100kW
202512-NM25-06183 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00197 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00809 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00805 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00810 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00280 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00657 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03317 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-00458 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00806 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01180 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00809 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00798 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00433 | 9 | Residencial | Yes | 0-100kW
202603-NM25-00722 | 8 | Residencial | No | 0-100kW
202601-NM25-02472 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00759 | 10.752 | Residencial | Yes | 0-100kW
202511-NM25-04184 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03142 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00803 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02548 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00801 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03834 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00800 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01454 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00790 | 15 | Residencial | Yes | 0-100kW
202603-NM25-00386 | 9.6 | Residencial | Yes | 0-100kW
202601-NM25-01167 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01497 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03165 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01730 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00347 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02173 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01041 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00796 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01280 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-00936 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02897 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02603 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03175 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03600 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03276 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00787 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01229 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01474 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00585 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00792 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01054 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00888 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01260 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-02109 | 7.296 | Residencial | Yes | 0-100kW
202603-NM25-00595 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00455 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00708 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00697 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01124 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01106 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00601 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03224 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00780 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01204 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00430 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01659 | 25 | Residencial | Yes | 0-100kW
202512-NM25-05914 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00778 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00594 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01975 | 5.25 | Residencial | Yes | 0-100kW
202512-NM25-05257 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00770 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01929 | 6.144 | Residencial | Yes | 0-100kW
202603-NM25-00776 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00773 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00771 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01139 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01032 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02617 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00599 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-00762 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00768 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00826 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00483 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02829 | 14.592 | Residencial | Yes | 0-100kW
202602-NM25-01413 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00631 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00763 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02055 | 6 | Residencial | Yes | 0-100kW
202602-NM25-01338 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00757 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00751 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00750 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00668 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00748 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01005 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00669 | 5.3 | Comercial | No | 0-100kW
202602-NM25-00027 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01525 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02602 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00745 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00644 | 10 | Residencial | Yes | 0-100kW
202603-NM25-00742 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00348 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00349 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00740 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02601 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02811 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00422 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01581 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04123 | 8.064 | Residencial | Yes | 0-100kW
202602-NM25-01150 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03295 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00709 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02292 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01381 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00266 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02173 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02486 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00341 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00392 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01190 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02511 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04607 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01307 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00538 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02759 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02571 | 23 | Residencial | Yes | 0-100kW
202512-NM25-01298 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-00714 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00713 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05843 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02191 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00712 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00711 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01211 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00702 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00708 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00675 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00596 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00308 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00140 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00323 | 4.224 | Residencial | Yes | 0-100kW
202603-NM25-00695 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00696 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00411 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01759 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00691 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00694 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04342 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00678 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00692 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00690 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01314 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00689 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00685 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00243 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00688 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00680 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00683 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00679 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00013 | 5.3 | Comercial | Yes | 0-100kW
202509-NM25-03668 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01001 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00395 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00665 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02533 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00663 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00666 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01492 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00688 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04758 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02865 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00656 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00659 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00650 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00654 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05361 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00655 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01113 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00058 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00652 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03743 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02931 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00645 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02756 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05286 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00648 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00398 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01768 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04367 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03278 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00639 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00640 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00732 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02503 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00030 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-05564 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04752 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02216 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00134 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00052 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01530 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01676 | 16 | Residencial | Yes | 0-100kW
202603-NM25-00631 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00286 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-03034 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02751 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00804 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00012 | 21.8 | Comercial | Yes | 0-100kW
202602-NM25-01267 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00629 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00623 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00011 | 5.3 | Comercial | Yes | 0-100kW
202511-NM25-04235 | 7.686 | Residencial | No | 0-100kW
202512-NM25-04523 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03013 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04382 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00553 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02841 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02678 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00010 | 21.8 | Comercial | Yes | 0-100kW
202603-NM25-00009 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00008 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00007 | 9.8 | Comercial | Yes | 0-100kW
202509-NM25-05364 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00006 | 21.8 | Comercial | Yes | 0-100kW
202602-NM25-02123 | 9 | Residencial | Yes | 0-100kW
202603-NM25-00615 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00005 | 5.3 | Comercial | Yes | 0-100kW
202602-NM25-02491 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00004 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-03327 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01357 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02349 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00338 | 9.216 | Residencial | Yes | 0-100kW
202602-NM25-01703 | 11.4 | Residencial | Yes | 0-100kW
202510-NM25-03009 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02122 | 9 | Residencial | Yes | 0-100kW
202508-NM25-03322 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02158 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02748 | 24 | Comercial | Yes | 0-100kW
202603-NM25-00363 | 12 | Residencial | Yes | 0-100kW
202512-NM25-05589 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05404 | 17.28 | Residencial | Yes | 0-100kW
202603-NM25-00183 | 11.529 | Residencial | Yes | 0-100kW
202603-NM25-00068 | 2.304 | Comercial | Yes | 0-100kW
202602-NM25-02608 | 7.259 | Residencial | Yes | 0-100kW
202602-NM25-01962 | 2.989 | Residencial | Yes | 0-100kW
202602-NM25-01148 | 13.908 | Residencial | Yes | 0-100kW
202603-NM25-00503 | 9 | Residencial | Yes | 0-100kW
202510-NM25-02614 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00569 | 12 | Residencial | Yes | 0-100kW
202509-NM25-01952 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00034 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00353 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01858 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00662 | 9 | Residencial | Yes | 0-100kW
202602-NM25-01973 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00482 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01095 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00082 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00519 | 6.8 | Residencial | Yes | 0-100kW
202601-NM25-00676 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00541 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00477 | 8 | Residencial | Yes | 0-100kW
202508-NM25-04542 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00545 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00542 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02354 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02281 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01424 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05439 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00490 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03298 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01104 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02929 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02262 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02294 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05805 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00115 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00581 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00310 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00491 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04629 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00920 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02684 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02469 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01398 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00500 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02404 | 10 | Comercial | Yes | 0-100kW
202512-NM25-05758 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01657 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00486 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00714 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01974 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-00609 | 23 | Residencial | Yes | 0-100kW
202511-NM25-00324 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-00489 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00483 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00480 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02683 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00481 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02473 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03270 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01484 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01552 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-00302 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03257 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00167 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02472 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00901 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00034 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00322 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01793 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01248 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03407 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00394 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00385 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00470 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00469 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00259 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02848 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02924 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03654 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-00154 | 15 | Residencial | No | 0-100kW
202603-NM25-00464 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00463 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05535 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00452 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00450 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00247 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01553 | 10.752 | Residencial | Yes | 0-100kW
202601-NM25-00352 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00456 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00101 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04448 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01740 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01932 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00689 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03373 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02026 | 13 | Residencial | Yes | 0-100kW
202509-NM25-03979 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00212 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00695 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00246 | 8 | Residencial | Yes | 0-100kW
202512-NM25-05949 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00445 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01625 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00446 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00089 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00992 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02686 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00818 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01143 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04926 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01716 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00882 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-00662 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00289 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01682 | 5.76 | Residencial | Yes | 0-100kW
202510-NM25-01828 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00937 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00424 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02586 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01416 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00435 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01672 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00298 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02875 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00426 | 8 | Residencial | Yes | 0-100kW
202511-NM25-00637 | 11.5 | Comercial | Yes | 0-100kW
202603-NM25-00431 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02812 | 4.992 | Residencial | Yes | 0-100kW
202603-NM25-00295 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00168 | 4.608 | Residencial | Yes | 0-100kW
202602-NM25-02250 | 9 | Residencial | Yes | 0-100kW
202603-NM25-00001 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05577 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01453 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02082 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00418 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00184 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-02892 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-00793 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00017 | 5.3 | Comercial | Yes | 0-100kW
202508-NM25-04621 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00304 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00083 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05408 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01285 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00294 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00806 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04164 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00401 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04295 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00016 | 5.3 | Comercial | Yes | 0-100kW
202602-NM25-02149 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00015 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00014 | 5.3 | Comercial | Yes | 0-100kW
202602-NM25-00490 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-00282 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00583 | 7.6 | Residencial | No | 0-100kW
202509-NM25-02111 | 4.392 | Residencial | Yes | 0-100kW
202512-NM25-04487 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00391 | 4.224 | Residencial | Yes | 0-100kW
202601-NM25-00116 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00980 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00305 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03310 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00263 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00090 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00929 | 12 | Residencial | Yes | 0-100kW
202603-NM25-00164 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00644 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01068 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00387 | 8.448 | Residencial | Yes | 0-100kW
202602-NM25-00753 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01547 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-01333 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01724 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00177 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00273 | 12 | Residencial | Yes | 0-100kW
202603-NM25-00202 | 5 | Residencial | Yes | 0-100kW
202601-NM25-02879 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02669 | 23 | Residencial | Yes | 0-100kW
202601-NM25-03414 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00381 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02571 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01235 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04246 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06201 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05048 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00133 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00084 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02116 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01262 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-00082 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02073 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01452 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00270 | 8 | Residencial | Yes | 0-100kW
202509-NM25-00240 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00332 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01708 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01092 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03140 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00998 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03860 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01465 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01557 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00361 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00583 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05784 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02734 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01262 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00254 | 7.68 | Residencial | Yes | 0-100kW
202508-NM25-02125 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00357 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00060 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-03198 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-00872 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02656 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00283 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02606 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00282 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03740 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00241 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00101 | 19.2 | Residencial | Yes | 0-100kW
202509-NM25-05627 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02419 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00018 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00277 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02429 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02203 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00316 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00112 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00123 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00560 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03320 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02404 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00236 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05456 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00022 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00021 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00019 | 5.3 | Comercial | Yes | 0-100kW
202602-NM25-01855 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00333 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00242 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02715 | 3.3 | Residencial | Yes | 0-100kW
202603-NM25-00330 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00744 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01095 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00059 | 12 | Residencial | Yes | 0-100kW
202509-NM25-01558 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02466 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00324 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00910 | 13.44 | Residencial | Yes | 0-100kW
202603-NM25-00234 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00065 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00318 | 7.296 | Residencial | No | 0-100kW
202603-NM25-00219 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00024 | 5.3 | Comercial | Yes | 0-100kW
202603-NM25-00195 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01762 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01945 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-01846 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00306 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00309 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00300 | 6.528 | Residencial | Yes | 0-100kW
202602-NM25-02794 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05649 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00186 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01929 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02213 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02726 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00319 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00299 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00787 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02133 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00264 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00011 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00649 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00026 | 5.3 | Comercial | Yes | 0-100kW
202602-NM25-01311 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00027 | 5.3 | Comercial | Yes | 0-100kW
202602-NM25-02553 | 3.456 | Residencial | No | 0-100kW
202603-NM25-00044 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00156 | 12 | Residencial | Yes | 0-100kW
202603-NM25-00292 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00287 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01087 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01862 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00070 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00095 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06102 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00088 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00244 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00041 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00284 | 8 | Residencial | Yes | 0-100kW
202511-NM25-03614 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02154 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01089 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02418 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02134 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00550 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02187 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00267 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05580 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00274 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00120 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00272 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06040 | 10.368 | Residencial | Yes | 0-100kW
202512-NM25-05610 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01778 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00269 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00174 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00548 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00263 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03230 | 3.8 | Residencial | No | 0-100kW
202512-NM25-05611 | 23 | Residencial | Yes | 0-100kW
202510-NM25-04281 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03371 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00223 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01672 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00254 | 13.44 | Residencial | Yes | 0-100kW
202603-NM25-00255 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02596 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01425 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00258 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00251 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01237 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02666 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02172 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00954 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02390 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01354 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00685 | 10 | Residencial | Yes | 0-100kW
202512-NM25-05485 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00248 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02436 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01082 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00252 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01871 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02729 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00240 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04729 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02479 | 11.4 | Comercial | Yes | 0-100kW
202512-NM25-05428 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00238 | 8.064 | Residencial | Yes | 0-100kW
202603-NM25-00129 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02786 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01028 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01195 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02848 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01109 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00048 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-02309 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00683 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02576 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02280 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00187 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01701 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00203 | 9 | Residencial | Yes | 0-100kW
202601-NM25-03326 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02837 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00228 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00141 | 8 | Residencial | Yes | 0-100kW
202509-NM25-03406 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00226 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01827 | 12 | Comercial | Yes | 0-100kW
202601-NM25-02742 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00159 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00080 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00598 | 4.608 | Residencial | Yes | 0-100kW
202512-NM25-05038 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00220 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00222 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01840 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00216 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01834 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02752 | 4.224 | Residencial | Yes | 0-100kW
202603-NM25-00213 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01899 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-02157 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00210 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02769 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01822 | 12 | Comercial | Yes | 0-100kW
202603-NM25-00209 | 4.992 | Residencial | Yes | 0-100kW
202603-NM25-00207 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02889 | 12 | Residencial | Yes | 0-100kW
202602-NM25-02038 | 6 | Residencial | Yes | 0-100kW
202603-NM25-00113 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00204 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00199 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02814 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00201 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00196 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00193 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00194 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00915 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00191 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02914 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03654 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00190 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02697 | 3.456 | Residencial | Yes | 0-100kW
202512-NM25-04400 | 4.224 | Residencial | Yes | 0-100kW
202512-NM25-01081 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00182 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00181 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-01146 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00180 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00179 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02583 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02634 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03618 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00577 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-00171 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01058 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00670 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-00169 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01869 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00043 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00158 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00149 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02738 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00157 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00103 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01986 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00155 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00154 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00779 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01159 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00152 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02768 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00256 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02877 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02401 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01726 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01522 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00896 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00003 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00143 | 15 | Residencial | Yes | 0-100kW
202603-NM25-00002 | 5 | Residencial | Yes | 0-100kW
202603-NM25-00107 | 16 | Residencial | Yes | 0-100kW
202512-NM25-05129 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02128 | 5 | Comercial | Yes | 0-100kW
202603-NM25-00144 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03946 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02696 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-00142 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02898 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02885 | 12 | Residencial | Yes | 0-100kW
202512-NM25-04450 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00139 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00132 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00576 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00549 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00138 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04224 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00135 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00106 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05038 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00136 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00134 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06194 | 8.448 | Residencial | Yes | 0-100kW
202603-NM25-00131 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00576 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03837 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00130 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04270 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00638 | 3.84 | Residencial | Yes | 0-100kW
202603-NM25-00128 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00590 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00127 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00124 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00125 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02786 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00119 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04715 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05585 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00832 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00042 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00116 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00975 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02951 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00111 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00936 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02498 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02268 | 11.5 | Residencial | No | 0-100kW
202603-NM25-00108 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04004 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-03386 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02960 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01552 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00554 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02064 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02903 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00099 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01710 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02104 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04324 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00545 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02288 | 7.68 | Residencial | Yes | 0-100kW
202603-NM25-00098 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02277 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00096 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01618 | 8.448 | Residencial | Yes | 0-100kW
202603-NM25-00094 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02287 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01637 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02734 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01188 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03709 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05571 | 11.5 | Residencial | No | 0-100kW
202510-NM25-01558 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02171 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06177 | 7.68 | Residencial | Yes | 0-100kW
202511-NM25-03857 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00322 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00612 | 8.448 | Residencial | Yes | 0-100kW
202509-NM25-05999 | 11.5 | Residencial | No | 0-100kW
202511-NM25-01464 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00052 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02896 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03704 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01052 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04594 | 11.904 | Residencial | Yes | 0-100kW
202602-NM25-01587 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05366 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01496 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00079 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00798 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00564 | 23 | Residencial | Yes | 0-100kW
202601-NM25-02613 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02627 | 5.376 | Residencial | Yes | 0-100kW
202603-NM25-00076 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00074 | 14.208 | Residencial | Yes | 0-100kW
202602-NM25-00056 | 3.8 | Residencial | Yes | 0-100kW
202502-NM25-02404 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02604 | 12 | Residencial | Yes | 0-100kW
202602-NM25-01112 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02589 | 7.68 | Residencial | Yes | 0-100kW
202508-NM25-03356 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00072 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00073 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03410 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00672 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03574 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00373 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02379 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01220 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00062 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02308 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02630 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02052 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-03227 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03050 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00054 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01312 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01251 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01101 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03810 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00053 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00919 | 11.5 | Residencial | No | 0-100kW
202512-NM25-02540 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00051 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00050 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-03701 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03460 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00986 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-05222 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00652 | 7.68 | Residencial | Yes | 0-100kW
202510-NM25-03517 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03886 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04913 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-00025 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02727 | 8 | Residencial | Yes | 0-100kW
202510-NM25-01750 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00302 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01891 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00079 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01512 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05239 | 5.76 | Residencial | Yes | 0-100kW
202509-NM25-01688 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02451 | 8 | Residencial | Yes | 0-100kW
202601-NM25-03222 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00814 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02870 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00962 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04024 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03361 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01176 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05785 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02757 | 22.8 | Comercial | Yes | 0-100kW
202512-NM25-00588 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05064 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04938 | 9 | Residencial | Yes | 0-100kW
202509-NM25-01389 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02086 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01350 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01849 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02665 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01506 | 23 | Residencial | Yes | 0-100kW
202512-NM25-05742 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01072 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03818 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02880 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04154 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02878 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05829 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04215 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02529 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01173 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06251 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02864 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02544 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02871 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01748 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02883 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02212 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02869 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-01621 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-02866 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02793 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02865 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02859 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02863 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02147 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02860 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02858 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02856 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00775 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02853 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02852 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03305 | 15 | Residencial | Yes | 0-100kW
202602-NM25-02849 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02850 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04341 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02844 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02845 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02724 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02842 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02711 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02838 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01035 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01117 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02821 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02833 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02805 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02818 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02683 | 12 | Comercial | Yes | 0-100kW
202602-NM25-01527 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01000 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02816 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02783 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02458 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02652 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02804 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02437 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00747 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02809 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02916 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02605 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04612 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03647 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02799 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02798 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02795 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04082 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02792 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02787 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02788 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02784 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02780 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02782 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03073 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02781 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02778 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02777 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02776 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02625 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02775 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02774 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02773 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02771 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02766 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02647 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02764 | 13.056 | Residencial | Yes | 0-100kW
202512-NM25-05799 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-02763 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02551 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03073 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02754 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02278 | 13.44 | Residencial | Yes | 0-100kW
202601-NM25-00893 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01069 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02749 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02746 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02128 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02744 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02628 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02473 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01314 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02568 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02721 | 16 | Residencial | No | 0-100kW
202602-NM25-02535 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01900 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-02740 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02439 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02739 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04305 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02575 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02704 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02497 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02737 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00710 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02736 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03221 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02547 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02709 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03405 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-02731 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01027 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02730 | 13.42 | Residencial | Yes | 0-100kW
202508-NM25-00747 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-02443 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02728 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02712 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02597 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02725 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01925 | 8 | Residencial | Yes | 0-100kW
202512-NM25-05500 | 9 | Residencial | Yes | 0-100kW
202601-NM25-01503 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02639 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00378 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03940 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04942 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02462 | 11.5 | Residencial | No | 0-100kW
202511-NM25-00428 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02170 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03417 | 8.448 | Residencial | Yes | 0-100kW
202508-NM25-03657 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00422 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-02563 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02717 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05245 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01045 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02713 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02710 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02707 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02966 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02708 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02315 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06076 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02706 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01920 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02391 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04193 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03617 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04426 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02702 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02701 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01304 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02691 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02697 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02696 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02692 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05470 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01353 | 23 | Residencial | Yes | 0-100kW
202510-NM25-00087 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01373 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02676 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02681 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02690 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01397 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-00993 | 10.368 | Comercial | Yes | 0-100kW
202602-NM25-01345 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00479 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00788 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03150 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01174 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05874 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01903 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01302 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02684 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01276 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00991 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00865 | 10 | Comercial | Yes | 0-100kW
202512-NM25-02555 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02682 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02557 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01889 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04070 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02670 | 13.44 | Residencial | Yes | 0-100kW
202601-NM25-02392 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04307 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01301 | 4.608 | Residencial | Yes | 0-100kW
202512-NM25-02084 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05901 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02667 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02663 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02313 | 15 | Residencial | Yes | 0-100kW
202602-NM25-02655 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05420 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01316 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01935 | 4.992 | Residencial | No | 0-100kW
202511-NM25-00439 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02480 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00899 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05028 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00991 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02651 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02397 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03003 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-00808 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03174 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02644 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01574 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01963 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02478 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00324 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05201 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03850 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01236 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00468 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00749 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02611 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02722 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01167 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00801 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02634 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01695 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01554 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02629 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02230 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04416 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02626 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00469 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02411 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01149 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02466 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04278 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05031 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00694 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01379 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01278 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03432 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03335 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02556 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01956 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05409 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00791 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00331 | 11.52 | Residencial | Yes | 0-100kW
202512-NM25-01280 | 6.912 | Residencial | Yes | 0-100kW
202507-NM25-02426 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-05405 | 23 | Residencial | Yes | 0-100kW
202512-NM25-06147 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01675 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03589 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02616 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01179 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02613 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02612 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01135 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01446 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03094 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02141 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02607 | 23 | Gubernamental | Yes | 0-100kW
202602-NM25-01716 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01150 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00839 | 8.832 | Residencial | Yes | 0-100kW
202512-NM25-06225 | 4.992 | Residencial | Yes | 0-100kW
202512-NM25-04642 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04419 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01961 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01558 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01843 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02488 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05519 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00406 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03927 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00275 | 18 | Residencial | Yes | 0-100kW
202512-NM25-01088 | 10.752 | Residencial | Yes | 0-100kW
202507-NM25-04683 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-02600 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-01189 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01181 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02178 | 7.68 | Residencial | No | 0-100kW
202602-NM25-02599 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01508 | 11.5 | Residencial | No | 0-100kW
202509-NM25-05345 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01941 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02763 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03777 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01981 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02591 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02594 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03153 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02467 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02714 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02572 | 11.4 | Residencial | Yes | 0-100kW
202511-NM25-01775 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05483 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06045 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05730 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06101 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02067 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00745 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01111 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01303 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03045 | 23 | Residencial | Yes | 0-100kW
202510-NM25-04358 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-02450 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02713 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01272 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03554 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-05020 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02146 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01943 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05626 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06239 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02190 | 9.216 | Residencial | Yes | 0-100kW
202512-NM25-04993 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00571 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-02059 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02174 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02296 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03368 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03329 | 10.4 | Residencial | Yes | 0-100kW
202601-NM25-01210 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02142 | 11.5 | Residencial | No | 0-100kW
202509-NM25-03366 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03113 | 7.68 | Residencial | Yes | 0-100kW
202511-NM25-04424 | 8.448 | Residencial | Yes | 0-100kW
202511-NM25-03267 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02581 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02956 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05533 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02002 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02531 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02922 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02571 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01057 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02144 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01265 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00042 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03641 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01126 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02567 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02435 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01925 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00574 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00336 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02519 | 11.52 | Residencial | Yes | 0-100kW
202602-NM25-01796 | 10 | Residencial | Yes | 0-100kW
202512-NM25-04610 | 13.6 | Residencial | Yes | 0-100kW
202602-NM25-02539 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-03343 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01864 | 6.8 | Residencial | Yes | 0-100kW
202601-NM25-00701 | 22.8 | Comercial | Yes | 0-100kW
202509-NM25-03923 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01878 | 4.392 | Residencial | Yes | 0-100kW
202602-NM25-01393 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02559 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01970 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02380 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02166 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-01877 | 16 | Residencial | Yes | 0-100kW
202602-NM25-02552 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01354 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01939 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02529 | 5 | Residencial | Yes | 0-100kW
202511-NM25-02266 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02542 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01129 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01412 | 6 | Residencial | Yes | 0-100kW
202512-NM25-03007 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02543 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02375 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02541 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05168 | 3.3 | Residencial | Yes | 0-100kW
202602-NM25-02538 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02499 | 12 | Residencial | Yes | 0-100kW
202511-NM25-00041 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02902 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00014 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02487 | 16 | Residencial | Yes | 0-100kW
202509-NM25-05876 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03140 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03723 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02268 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06100 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02155 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01346 | 11.5 | Residencial | No | 0-100kW
202509-NM25-03965 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04353 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02512 | 8 | Residencial | Yes | 0-100kW
202512-NM25-06092 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00943 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02971 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01755 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02509 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00468 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02507 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04599 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01536 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-03242 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02504 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04374 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03118 | 18 | Residencial | Yes | 0-100kW
202601-NM25-01032 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01745 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04088 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01735 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02495 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01740 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02494 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02816 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04432 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02716 | 8.448 | Residencial | Yes | 0-100kW
202512-NM25-01069 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05022 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02489 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05184 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02293 | 8 | Residencial | No | 0-100kW
202512-NM25-04538 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02434 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02483 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01617 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03774 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01946 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02757 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02482 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02480 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01749 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03074 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04259 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02456 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04998 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02078 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02663 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01287 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02471 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00493 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02470 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00906 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-03019 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-00351 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00804 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05302 | 23 | Residencial | Yes | 0-100kW
202511-NM25-02857 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00147 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02469 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02465 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00884 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02464 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04359 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01576 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02461 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01905 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02763 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01688 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-02143 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02282 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04194 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02455 | 13.036 | Residencial | Yes | 0-100kW
202602-NM25-02454 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01286 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02126 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00619 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02452 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02450 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01794 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-06106 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00059 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01020 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01724 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02442 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02441 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02440 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01505 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05109 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02438 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02437 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02435 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01887 | 12 | Residencial | Yes | 0-100kW
202602-NM25-02253 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02432 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02430 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02415 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02427 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02425 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02421 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01832 | 8 | Residencial | No | 0-100kW
202602-NM25-02418 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02416 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02410 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02417 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02414 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02413 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01398 | 11.5 | Residencial | No | 0-100kW
202509-NM25-03357 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02408 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00440 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02409 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02407 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00968 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02398 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00841 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-02405 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02399 | 6.528 | Residencial | Yes | 0-100kW
202602-NM25-02400 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04436 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02402 | 11.5 | Comercial | Yes | 0-100kW
202511-NM25-01743 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01801 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03540 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01511 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02161 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00127 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03274 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01246 | 9 | Residencial | Yes | 0-100kW
202601-NM25-02617 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02393 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02394 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02391 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03409 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00805 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05892 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02315 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00963 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02371 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02909 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01176 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02381 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00847 | 18 | Comercial | Yes | 0-100kW
202509-NM25-00804 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02374 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02372 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02370 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01718 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02441 | 15 | Residencial | Yes | 0-100kW
202602-NM25-00360 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02366 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02367 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00654 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02362 | 22.8 | Residencial | Yes | 0-100kW
202602-NM25-00848 | 4 | Residencial | Yes | 0-100kW
202602-NM25-02126 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-02286 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02289 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02349 | 8 | Residencial | No | 0-100kW
202602-NM25-02361 | 24 | Residencial | Yes | 0-100kW
202602-NM25-02116 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02351 | 2.36 | Residencial | Yes | 0-100kW
202509-NM25-05465 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05006 | 10 | Residencial | Yes | 0-100kW
202509-NM25-02605 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02429 | 11.136 | Residencial | No | 0-100kW
202509-NM25-05685 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03904 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02796 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01011 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02342 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01729 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02345 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02337 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02340 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02126 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03640 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02339 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03234 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04399 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02131 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02341 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00398 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02338 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04430 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02335 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02334 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03610 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02217 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02332 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02333 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02325 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02324 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02328 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02326 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06015 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03106 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02323 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02322 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00326 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02321 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02320 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02319 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02318 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02317 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02316 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04290 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01915 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04072 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02310 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02102 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02307 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02308 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02306 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02305 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02304 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02303 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02199 | 4.224 | Residencial | Yes | 0-100kW
202602-NM25-02301 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-02300 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02298 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02131 | 12.288 | Residencial | Yes | 0-100kW
202602-NM25-02283 | 15 | Residencial | Yes | 0-100kW
202602-NM25-01406 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02000 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02273 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02295 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02291 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03452 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02269 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02290 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01820 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-02287 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02278 | 4.608 | Residencial | Yes | 0-100kW
202509-NM25-01273 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01520 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00784 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02234 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02284 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02198 | 9 | Residencial | Yes | 0-100kW
202602-NM25-02279 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-01364 | 5.76 | Residencial | Yes | 0-100kW
202511-NM25-03967 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03523 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03803 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02274 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02272 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01842 | 4.992 | Residencial | Yes | 0-100kW
202510-NM25-01967 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02271 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00452 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02248 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01550 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02266 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02264 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02263 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02355 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-02262 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00465 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02259 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01496 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04679 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02256 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02257 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03673 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01745 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03397 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02255 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00993 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02252 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02251 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00295 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02249 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02248 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02888 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02193 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02247 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02245 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02246 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02244 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02240 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02241 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02238 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01517 | 11.5 | Comercial | Yes | 0-100kW
202509-NM25-06058 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02237 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02227 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02233 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02232 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02231 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02225 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02228 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02226 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02221 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03355 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02490 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02219 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02222 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00059 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02223 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04411 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02215 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02214 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02206 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02211 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01247 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02209 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02208 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02238 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02205 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02203 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04099 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01269 | 10 | Residencial | Yes | 0-100kW
202602-NM25-02196 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04441 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02197 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00816 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01254 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02853 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02191 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01639 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02135 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02188 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03962 | 18 | Residencial | Yes | 0-100kW
202509-NM25-01747 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02186 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01648 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-02183 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02182 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01841 | 10 | Residencial | Yes | 0-100kW
202602-NM25-02179 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02163 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03713 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02175 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02177 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02546 | 12 | Residencial | Yes | 0-100kW
202512-NM25-03577 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00418 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01518 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02172 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02133 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02167 | 4.992 | Residencial | Yes | 0-100kW
202602-NM25-02164 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02169 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03187 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-00640 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02168 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00359 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02165 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01856 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02162 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02160 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05162 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02159 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02933 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02156 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02158 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02155 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02154 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02154 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02150 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02152 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02408 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05035 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02147 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02145 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01486 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02143 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00766 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01897 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01880 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01809 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01361 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02130 | 18 | Residencial | Yes | 0-100kW
202509-NM25-05101 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02261 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01909 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-06043 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01169 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-02492 | 16 | Residencial | Yes | 0-100kW
202511-NM25-03021 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02347 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03147 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02631 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02125 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-02124 | 15 | Residencial | Yes | 0-100kW
202510-NM25-02904 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05878 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-03988 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03945 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-00489 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03408 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01831 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-03587 | 23 | Residencial | Yes | 0-100kW
202509-NM25-00496 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03260 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00653 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03262 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00227 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01317 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04320 | 3.3 | Residencial | Yes | 0-100kW
202512-NM25-04137 | 9 | Residencial | Yes | 0-100kW
202509-NM25-04385 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04051 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04531 | 24 | Residencial | Yes | 0-100kW
202508-NM25-04062 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02121 | 8 | Residencial | No | 0-100kW
202602-NM25-02120 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00491 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02366 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01480 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03862 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04846 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00800 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00604 | 3.3 | Residencial | Yes | 0-100kW
202512-NM25-00213 | 10.752 | Residencial | Yes | 0-100kW
202510-NM25-03180 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02060 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05152 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03291 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02897 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01065 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03215 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01994 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02115 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00504 | 9.6 | Residencial | Yes | 0-100kW
202511-NM25-02615 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01923 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02111 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01979 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02114 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02112 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02113 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03860 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01635 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02720 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02110 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01934 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02108 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00078 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02701 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02107 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02768 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02105 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02104 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02102 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02560 | 12.288 | Residencial | Yes | 0-100kW
202602-NM25-02100 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02101 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03243 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04054 | 23 | Residencial | Yes | 0-100kW
202512-NM25-00656 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02099 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02097 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05217 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02093 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01582 | 12 | Residencial | Yes | 0-100kW
202602-NM25-02095 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00806 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02094 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02092 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00927 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02089 | 11.5 | Comercial | Yes | 0-100kW
202508-NM25-05165 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02087 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01058 | 8 | Residencial | Yes | 0-100kW
202602-NM25-02084 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01965 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02760 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00645 | 10 | Residencial | Yes | 0-100kW
202512-NM25-02790 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02083 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01282 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-02081 | 11.5 | Residencial | No | 0-100kW
202602-NM25-02079 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01846 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00128 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02080 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02313 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02261 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00144 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05972 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02073 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01521 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-02072 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02071 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04596 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04798 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01529 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03651 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02070 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01814 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04020 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02061 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02062 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-05936 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-00661 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04608 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00565 | 22.8 | Residencial | Yes | 0-100kW
202602-NM25-00645 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02057 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02053 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02172 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02046 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03261 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02586 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05995 | 4.224 | Residencial | Yes | 0-100kW
202602-NM25-02050 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01249 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01056 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01174 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02376 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01731 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06084 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02043 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02048 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02045 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05044 | 23 | Residencial | No | 0-100kW
202509-NM25-01152 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02042 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03842 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02958 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02040 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02034 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01339 | 6.144 | Residencial | Yes | 0-100kW
202511-NM25-01954 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01980 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04096 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03162 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02036 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02298 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01515 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-01936 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02033 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02028 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02029 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00632 | 12.288 | Residencial | Yes | 0-100kW
202602-NM25-02030 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00947 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01107 | 11.5 | Comercial | Yes | 0-100kW
202509-NM25-04655 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02858 | 24.96 | Comercial | Yes | 0-100kW
202512-NM25-02955 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04339 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02023 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02024 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03278 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00928 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01042 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02026 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01839 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-02022 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00092 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02020 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02199 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01953 | 8 | Residencial | No | 0-100kW
202602-NM25-00640 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02014 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04843 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02010 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02015 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05252 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02013 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01430 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02009 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02008 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02007 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00193 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02006 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02005 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02004 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02187 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02877 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01998 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04402 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02003 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02001 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01999 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04060 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01996 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00622 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01989 | 11.5 | Residencial | No | 0-100kW
202512-NM25-02179 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04813 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01995 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01728 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03448 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01992 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03244 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03547 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01990 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02734 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05865 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04166 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05286 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00310 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04886 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01987 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01611 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01985 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01968 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01983 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01982 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01981 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01454 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01155 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02688 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01705 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01976 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01835 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01969 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01974 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01964 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03914 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03101 | 8.064 | Residencial | Yes | 0-100kW
202602-NM25-01811 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00781 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03814 | 10 | Residencial | Yes | 0-100kW
202602-NM25-01967 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01966 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01959 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01856 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01960 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01958 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05803 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04006 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01874 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00982 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00647 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01952 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01951 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01381 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01949 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00388 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01950 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01888 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01947 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00900 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01944 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03496 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01942 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-04575 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01708 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01938 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01822 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01671 | 4.224 | Residencial | Yes | 0-100kW
202602-NM25-01936 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01161 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01387 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-01933 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01722 | 7.6 | Comercial | Yes | 0-100kW
202602-NM25-01931 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01590 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03309 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01721 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01382 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00844 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01632 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00939 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01770 | 3.3 | Residencial | Yes | 0-100kW
202602-NM25-01836 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01867 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00921 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01300 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01044 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01197 | 12 | Residencial | Yes | 0-100kW
202510-NM25-01203 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02020 | 11.5 | Comercial | Yes | 0-100kW
202511-NM25-03500 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01881 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01739 | 8 | Residencial | Yes | 0-100kW
202510-NM25-02993 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00201 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03185 | 7.6 | Residencial | No | 0-100kW
202512-NM25-05877 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04132 | 20 | Residencial | Yes | 0-100kW
202509-NM25-03633 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00085 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04020 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-03141 | 23 | Residencial | Yes | 0-100kW
202512-NM25-05600 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00855 | 9 | Residencial | Yes | 0-100kW
202509-NM25-05463 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02706 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00960 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02651 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03494 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02982 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00924 | 23 | Residencial | Yes | 0-100kW
202511-NM25-02055 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02611 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05446 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03270 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01675 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05277 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03761 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02849 | 3.3 | Residencial | Yes | 0-100kW
202511-NM25-02839 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02849 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00781 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03151 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01904 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05991 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01910 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01493 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01896 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03383 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04027 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01665 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00853 | 23 | Comercial | Yes | 0-100kW
202602-NM25-01125 | 10 | Residencial | Yes | 0-100kW
202509-NM25-01277 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02293 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04072 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01430 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01628 | 3.456 | Residencial | Yes | 0-100kW
202602-NM25-01869 | 12 | Residencial | Yes | 0-100kW
202510-NM25-00549 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04239 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02393 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03272 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01487 | 7.68 | Residencial | Yes | 0-100kW
202510-NM25-01664 | 23 | Residencial | Yes | 0-100kW
202511-NM25-02900 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01575 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02427 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01394 | 3.84 | Residencial | Yes | 0-100kW
202508-NM25-04313 | 11.5 | Comercial | Yes | 0-100kW
202511-NM25-03099 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01894 | 4.392 | Residencial | Yes | 0-100kW
202512-NM25-05824 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00897 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00080 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01146 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02097 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03757 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00530 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-03463 | 23 | Residencial | Yes | 0-100kW
202601-NM25-02703 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02414 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01742 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02120 | 2.688 | Residencial | Yes | 0-100kW
202602-NM25-00650 | 18 | Residencial | Yes | 0-100kW
202511-NM25-01938 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01489 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00661 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00242 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01865 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01876 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00404 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01669 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05106 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04043 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01193 | 18 | Residencial | Yes | 0-100kW
202602-NM25-01362 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01580 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00183 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03461 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01686 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01121 | 5.76 | Residencial | Yes | 0-100kW
202511-NM25-03772 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02257 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-03616 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03335 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04980 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01549 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-03725 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03281 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00806 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01629 | 12 | Residencial | Yes | 0-100kW
202511-NM25-04068 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00805 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03734 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00396 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01324 | 11.4 | Residencial | Yes | 0-100kW
202510-NM25-01796 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00882 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00648 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01518 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00263 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02378 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03949 | 5.76 | Residencial | Yes | 0-100kW
202509-NM25-00038 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01485 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00653 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02123 | 23 | Comercial | Yes | 0-100kW
202602-NM25-01857 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00217 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01854 | 7.6 | Residencial | No | 0-100kW
202602-NM25-00577 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-01847 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01139 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01844 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03082 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01423 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-02301 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03982 | 7.68 | Residencial | Yes | 0-100kW
202508-NM25-04017 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03756 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01833 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01557 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05670 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01830 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01199 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01251 | 8 | Residencial | Yes | 0-100kW
202512-NM25-04705 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04390 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01623 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00629 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01393 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01271 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01826 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00623 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01013 | 8 | Residencial | No | 0-100kW
202602-NM25-00793 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00758 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01839 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03216 | 11.346 | Residencial | Yes | 0-100kW
202602-NM25-01821 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01819 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02993 | 7.68 | Residencial | Yes | 0-100kW
202509-NM25-04434 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01816 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-03923 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01813 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04161 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00870 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01808 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03614 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02595 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01933 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01460 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02942 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01805 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03994 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01500 | 4.992 | Residencial | Yes | 0-100kW
202602-NM25-01804 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01845 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02020 | 9.216 | Residencial | Yes | 0-100kW
202509-NM25-01851 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02201 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00336 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02670 | 5.76 | Residencial | Yes | 0-100kW
202510-NM25-01267 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02763 | 3.3 | Residencial | Yes | 0-100kW
202512-NM25-05812 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03304 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01756 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00075 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00377 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00813 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00527 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00976 | 5.76 | Residencial | Yes | 0-100kW
202511-NM25-04070 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04284 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04271 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03550 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02896 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05160 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02409 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01776 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04140 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02133 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05912 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01778 | 11.5 | Gubernamental | Yes | 0-100kW
202602-NM25-01780 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01990 | 3.3 | Residencial | Yes | 0-100kW
202509-NM25-03338 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04979 | 11.5 | Residencial | No | 0-100kW
202512-NM25-06256 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03154 | 23 | Residencial | Yes | 0-100kW
202511-NM25-00886 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03735 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02132 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02288 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03912 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03633 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01766 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00918 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03692 | 11.52 | Residencial | Yes | 0-100kW
202602-NM25-00693 | 7.68 | Residencial | Yes | 0-100kW
202510-NM25-01435 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01692 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05181 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01747 | 22.8 | Comercial | No | 0-100kW
202510-NM25-04219 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01763 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01435 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01170 | 23 | Residencial | Yes | 0-100kW
202511-NM25-00966 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04446 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01434 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03390 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01757 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00410 | 23 | Residencial | Yes | 0-100kW
202510-NM25-03887 | 3.456 | Residencial | Yes | 0-100kW
202511-NM25-00383 | 23 | Residencial | Yes | 0-100kW
202511-NM25-01539 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00605 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02980 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01746 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01944 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01642 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00427 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02493 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00444 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05061 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01752 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00323 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00825 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01241 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01749 | 4.608 | Residencial | Yes | 0-100kW
202511-NM25-00354 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00283 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-00243 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01678 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00234 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01738 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00747 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01291 | 12 | Residencial | Yes | 0-100kW
202601-NM25-03433 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01733 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01378 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01483 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00604 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02269 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00204 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00578 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02583 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00846 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04188 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00522 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03854 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01908 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03454 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00940 | 8 | Residencial | Yes | 0-100kW
202510-NM25-01686 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01397 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00866 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01720 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00113 | 23 | Residencial | Yes | 0-100kW
202511-NM25-00780 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05209 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00193 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03145 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05213 | 8 | Residencial | Yes | 0-100kW
202510-NM25-00972 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00876 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01717 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01982 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01753 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01873 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01712 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02516 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02297 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02019 | 8 | Residencial | Yes | 0-100kW
202511-NM25-01071 | 13.44 | Residencial | Yes | 0-100kW
202602-NM25-01110 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03029 | 8 | Residencial | Yes | 0-100kW
202510-NM25-01183 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04028 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04103 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00731 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-04664 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00993 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02378 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01108 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02699 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02453 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00611 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01615 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02416 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01904 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05031 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04420 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01481 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01740 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01691 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00217 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00884 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00885 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00948 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06068 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02507 | 7.6 | Comercial | Yes | 0-100kW
202510-NM25-04323 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04142 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-01726 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01984 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01127 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01483 | 6.912 | Residencial | Yes | 0-100kW
202602-NM25-01684 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-00793 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01683 | 10 | Residencial | Yes | 0-100kW
202512-NM25-05010 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01673 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01758 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00036 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02855 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02197 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01679 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02975 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01675 | 15.2 | Comercial | Yes | 0-100kW
202602-NM25-00252 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01796 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04545 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01674 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02307 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05241 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02694 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03254 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01161 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00457 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03167 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02689 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00430 | 7.68 | Comercial | Yes | 0-100kW
202512-NM25-01455 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01279 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02437 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00852 | 9 | Residencial | Yes | 0-100kW
202509-NM25-04743 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03075 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01665 | 18 | Residencial | Yes | 0-100kW
202511-NM25-01130 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05561 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03471 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00463 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02235 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00897 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00410 | 7.68 | Residencial | Yes | 0-100kW
202510-NM25-02019 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02149 | 6.8 | Residencial | Yes | 0-100kW
202602-NM25-01165 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00500 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03551 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00261 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00555 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02321 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03834 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03956 | 11.5 | Comercial | Yes | 0-100kW
202510-NM25-01525 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02514 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00017 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03953 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00218 | 8.448 | Residencial | Yes | 0-100kW
202601-NM25-00227 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01357 | 12 | Residencial | Yes | 0-100kW
202602-NM25-01619 | 15 | Residencial | Yes | 0-100kW
202510-NM25-03102 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00759 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02012 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02415 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01145 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00842 | 5.25 | Residencial | Yes | 0-100kW
202510-NM25-01354 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00786 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01282 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00597 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-05908 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04224 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03257 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01658 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02884 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01656 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01655 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04280 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00838 | 8 | Residencial | Yes | 0-100kW
202511-NM25-02922 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01653 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04118 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02646 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01936 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01650 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01652 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00409 | 7.68 | Residencial | Yes | 0-100kW
202510-NM25-01499 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01651 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01685 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01649 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05137 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01647 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01646 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01535 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01644 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01569 | 8 | Residencial | Yes | 0-100kW
202511-NM25-01789 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01630 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01645 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-01119 | 7.7 | Residencial | Yes | 0-100kW
202508-NM25-05238 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00853 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01640 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01502 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03354 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02025 | 6.144 | Residencial | Yes | 0-100kW
202509-NM25-02912 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00842 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01210 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02068 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01634 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02666 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01577 | 8 | Residencial | No | 0-100kW
202602-NM25-00092 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03404 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01626 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01431 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01624 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00449 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00643 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01617 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02139 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01621 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01622 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01721 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01616 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00332 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01421 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04186 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01177 | 10.752 | Residencial | Yes | 0-100kW
202510-NM25-03276 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02823 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01607 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03930 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01344 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00250 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02518 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02088 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-01935 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00017 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01591 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03992 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03659 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01423 | 23 | Residencial | Yes | 0-100kW
202512-NM25-01829 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04157 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02051 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03466 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00930 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00539 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04101 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03929 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05173 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04904 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00636 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02260 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01567 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04013 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02226 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03798 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02300 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03996 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01422 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04045 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03766 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02284 | 11.5 | Comercial | Yes | 0-100kW
202510-NM25-00205 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03385 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-00604 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04015 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00012 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04430 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04376 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03405 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00364 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-01541 | 15.2 | Residencial | Yes | 0-100kW
202602-NM25-01544 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00480 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01370 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00831 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00088 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02534 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01409 | 7 | Residencial | Yes | 0-100kW
202511-NM25-01742 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02412 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00972 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01849 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01530 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04453 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05009 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00994 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01304 | 7.68 | Residencial | Yes | 0-100kW
202509-NM25-01342 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01158 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00077 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03142 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01515 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01514 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01513 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01548 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-01510 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00560 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00339 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02238 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01506 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01432 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02100 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01504 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01656 | 24 | Gubernamental | Yes | 0-100kW
202601-NM25-02700 | 4.608 | Residencial | Yes | 0-100kW
202602-NM25-01385 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03593 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01118 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00550 | 15.2 | Residencial | No | 0-100kW
202602-NM25-01498 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01499 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02956 | 5.376 | Residencial | No | 0-100kW
202602-NM25-01493 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01492 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01491 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01490 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01488 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00016 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01207 | 14.976 | Residencial | Yes | 0-100kW
202601-NM25-02822 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01186 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02430 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03148 | 9 | Residencial | Yes | 0-100kW
202512-NM25-03923 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01767 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01434 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03049 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-04600 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02446 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02122 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01153 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03695 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01182 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00186 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01468 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01466 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01465 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01463 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01464 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00191 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02350 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01461 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01462 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01441 | 22.8 | Residencial | Yes | 0-100kW
202509-NM25-04631 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01457 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01458 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00555 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05220 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01456 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01455 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01451 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01452 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01450 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01340 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01427 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01447 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00434 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01449 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00907 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-01446 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04644 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01929 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02452 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01444 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01443 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01429 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00384 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01438 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00268 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01436 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01433 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01575 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03974 | 11.5 | Comercial | Yes | 0-100kW
202509-NM25-00616 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05135 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00004 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-03613 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01078 | 4.992 | Residencial | Yes | 0-100kW
202509-NM25-03648 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00360 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00967 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05691 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01422 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01847 | 11.5 | Residencial | No | 0-100kW
202509-NM25-03110 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01090 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03168 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01407 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-06027 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00994 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04026 | 4.224 | Residencial | Yes | 0-100kW
202602-NM25-00001 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01502 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01415 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02348 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01411 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01409 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00803 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03933 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01403 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01401 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03343 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04540 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01400 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02114 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03286 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00176 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00780 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03268 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00304 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01399 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01395 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00846 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-01364 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01388 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01390 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01384 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00584 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01344 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-02459 | 12.288 | Residencial | Yes | 0-100kW
202502-NM25-02575 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03430 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00272 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00800 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01977 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01336 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01380 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-06036 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00891 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02760 | 11.5 | Comercial | Yes | 0-100kW
202510-NM25-02149 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03425 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02573 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-01376 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02341 | 11.4 | Residencial | Yes | 0-100kW
202512-NM25-04286 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01373 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01367 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01266 | 4.992 | Residencial | Yes | 0-100kW
202512-NM25-03728 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-02762 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01369 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03440 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01366 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00563 | 17.568 | Residencial | Yes | 0-100kW
202510-NM25-04019 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03746 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02246 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01363 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04037 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01265 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01358 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01355 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-00089 | 5 | Residencial | Yes | 0-100kW
202510-NM25-03691 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02766 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01351 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01012 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01348 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00071 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03606 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00012 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01332 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01906 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01202 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01341 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01325 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03415 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01772 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00958 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01342 | 4.224 | Residencial | Yes | 0-100kW
202510-NM25-00691 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00711 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01196 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01685 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01209 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00393 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03325 | 4.425 | Residencial | Yes | 0-100kW
202601-NM25-02479 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02851 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02360 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00262 | 9 | Residencial | Yes | 0-100kW
202512-NM25-01844 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00788 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01148 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02214 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03922 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04497 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-03192 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-02375 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04294 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01021 | 5 | Residencial | Yes | 0-100kW
202512-NM25-00935 | 11.5 | Residencial | No | 0-100kW
202508-NM25-04010 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02629 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04078 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01982 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03156 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04212 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03085 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02421 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03537 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00206 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02226 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03294 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00307 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00913 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01877 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02765 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01843 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-00728 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03321 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01247 | 12 | Residencial | Yes | 0-100kW
202602-NM25-01337 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01335 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01334 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01330 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00650 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01331 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00847 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01329 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01760 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03365 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01326 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01327 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02891 | 4.608 | Residencial | Yes | 0-100kW
202602-NM25-01323 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01396 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01282 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00104 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01416 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01306 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01322 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04019 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04227 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01321 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01319 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04404 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00024 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01034 | 7.6 | Comercial | Yes | 0-100kW
202602-NM25-01240 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03206 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00552 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02240 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01245 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01022 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00499 | 7.6 | Residencial | No | 0-100kW
202510-NM25-01202 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02450 | 15 | Residencial | Yes | 0-100kW
202509-NM25-03402 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00277 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01458 | 23 | Comercial | Yes | 0-100kW
202511-NM25-01084 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01950 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01299 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02499 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01298 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04577 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01853 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03765 | 15.2 | Residencial | Yes | 0-100kW
202507-NM25-03995 | 4.224 | Comercial | Yes | 0-100kW
202511-NM25-01762 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01790 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01295 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04018 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02648 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01293 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02125 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01289 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00608 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01292 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05462 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02610 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01206 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05915 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01288 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01287 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01285 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-01178 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03032 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01956 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00706 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02684 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01281 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01270 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01375 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01278 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01279 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01223 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01277 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02966 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02622 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00934 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-00106 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-01540 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-01086 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02471 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03380 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03141 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03476 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02665 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01801 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00447 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00088 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01211 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01263 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03149 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02709 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00242 | 12.444 | Residencial | Yes | 0-100kW
202602-NM25-01201 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01259 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01262 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01219 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03137 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03428 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05154 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01062 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00925 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01255 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05033 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-04014 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04640 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02956 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01250 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04550 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03957 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00414 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-00585 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03867 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01726 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03139 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05443 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03180 | 9 | Residencial | Yes | 0-100kW
202509-NM25-00079 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01085 | 16 | Residencial | Yes | 0-100kW
202511-NM25-01155 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03560 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-01234 | 12 | Residencial | Yes | 0-100kW
202511-NM25-03193 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00867 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02079 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02121 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00599 | 10 | Residencial | Yes | 0-100kW
202601-NM25-03167 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02316 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02820 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01244 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01242 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00918 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01100 | 15 | Residencial | Yes | 0-100kW
202508-NM25-03837 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01519 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01782 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02646 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01235 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02215 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01233 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00388 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01785 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00724 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01798 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02692 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05673 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04393 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05219 | 10.368 | Residencial | Yes | 0-100kW
202602-NM25-00736 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00341 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01000 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00074 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02428 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00861 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00036 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-01212 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00308 | 6 | Residencial | Yes | 0-100kW
202512-NM25-05451 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00869 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-00765 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05731 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01613 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04106 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00611 | 23 | Residencial | Yes | 0-100kW
202510-NM25-00736 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05667 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00852 | 18 | Residencial | Yes | 0-100kW
202509-NM25-00006 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01754 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03717 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02821 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01556 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00335 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03509 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-04101 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05041 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04239 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00188 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03485 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01658 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01172 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04226 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00790 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00554 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04223 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00129 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-00978 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02360 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05632 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03693 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03345 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-03959 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00661 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03766 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02120 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01855 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01153 | 18 | Residencial | Yes | 0-100kW
202509-NM25-04745 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00754 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01075 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05902 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01154 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01017 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05094 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03203 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00482 | 8 | Residencial | Yes | 0-100kW
202511-NM25-01979 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01015 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04084 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01152 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03534 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00968 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03013 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00772 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05057 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03392 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01151 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03587 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-01147 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04722 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-01117 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00156 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00964 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04653 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00415 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01111 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00553 | 23 | Residencial | Yes | 0-100kW
202509-NM25-02497 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03463 | 8 | Residencial | Yes | 0-100kW
202512-NM25-05071 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02299 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01155 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00155 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01780 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01872 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00727 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02582 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-00555 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00387 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02970 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04732 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03363 | 5.856 | Residencial | Yes | 0-100kW
202602-NM25-01004 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02303 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01002 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00437 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00290 | 12 | Residencial | Yes | 0-100kW
202602-NM25-01142 | 15 | Residencial | Yes | 0-100kW
202508-NM25-04018 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-00950 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01136 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01134 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01336 | 11.5 | Residencial | No | 0-100kW
202511-NM25-00879 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01947 | 10 | Residencial | No | 0-100kW
202509-NM25-01693 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03744 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05582 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03375 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01549 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-00986 | 15 | Comercial | No | 0-100kW
202509-NM25-01244 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03441 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-00925 | 12 | Residencial | Yes | 0-100kW
202602-NM25-01031 | 8 | Residencial | Yes | 0-100kW
202508-NM25-04685 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-00942 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01122 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05436 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00081 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00562 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01776 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03252 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00797 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00510 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01120 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-04363 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03685 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00202 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01104 | 9.216 | Residencial | Yes | 0-100kW
202512-NM25-04087 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04931 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00684 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04290 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00849 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01539 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05161 | 0 | Residencial | Yes | 0-100kW
202601-NM25-03146 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04016 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00530 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01490 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02244 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02210 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03690 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01663 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05553 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02150 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01284 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01365 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00124 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01084 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00928 | 8 | Residencial | Yes | 0-100kW
202512-NM25-02397 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04021 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02138 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05356 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02341 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01099 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05142 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02278 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03412 | 12.208 | Comercial | Yes | 0-100kW
202511-NM25-02468 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00495 | 15.2 | Residencial | Yes | 0-100kW
202601-NM25-00654 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-02727 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-01361 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01802 | 11.5 | Residencial | No | 0-100kW
202602-NM25-01083 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01305 | 14.592 | Residencial | Yes | 0-100kW
202512-NM25-05253 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03196 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03612 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03258 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03389 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00942 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04953 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03365 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02075 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-01081 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00181 | 8 | Residencial | Yes | 0-100kW
202602-NM25-01076 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00918 | 12 | Residencial | Yes | 0-100kW
202601-NM25-02062 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00357 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01080 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00815 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02509 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01077 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00267 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03265 | 7.5 | Residencial | Yes | 0-100kW
202602-NM25-00766 | 4.608 | Residencial | Yes | 0-100kW
202508-NM25-03618 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02996 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00674 | 11.4 | Residencial | Yes | 0-100kW
202512-NM25-01591 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04069 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01049 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05814 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00971 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-00366 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00959 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04877 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01198 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03066 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03070 | 13.056 | Residencial | Yes | 0-100kW
202602-NM25-01066 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01258 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04254 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-00405 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01063 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03043 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01441 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-00888 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05578 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03357 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-03534 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01046 | 6.8 | Residencial | Yes | 0-100kW
202512-NM25-04601 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04685 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01719 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00402 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-00724 | 15 | Residencial | Yes | 0-100kW
202511-NM25-00401 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01048 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00760 | 15 | Comercial | Yes | 0-100kW
202602-NM25-01045 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01044 | 9.6 | Residencial | Yes | 0-100kW
202602-NM25-00803 | 12 | Residencial | Yes | 0-100kW
202601-NM25-03151 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00615 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03282 | 24 | Comercial | Yes | 0-100kW
202512-NM25-04770 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04451 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05461 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03628 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00936 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01036 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01030 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00984 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00895 | 6.8 | Residencial | Yes | 0-100kW
202601-NM25-02184 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03110 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01025 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01453 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01024 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01022 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05840 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-01045 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02685 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01018 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01014 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01011 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04142 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00189 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02335 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00953 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00241 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-01009 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01008 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03043 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-00676 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01007 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01003 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00185 | 8 | Residencial | Yes | 0-100kW
202512-NM25-05189 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01898 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00610 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03185 | 23 | Comercial | Yes | 0-100kW
202602-NM25-00996 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00998 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04090 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00995 | 14.976 | Residencial | Yes | 0-100kW
202602-NM25-00990 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00051 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00598 | 12 | Residencial | Yes | 0-100kW
202509-NM25-05689 | 16 | Residencial | Yes | 0-100kW
202512-NM25-06237 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00759 | 23 | Residencial | Yes | 0-100kW
202601-NM25-03455 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03490 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-00085 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01019 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00983 | 8.064 | Residencial | Yes | 0-100kW
202602-NM25-00739 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00733 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01289 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02101 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05445 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00980 | 5.376 | Residencial | Yes | 0-100kW
202601-NM25-00914 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-03237 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02843 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00857 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03437 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00970 | 11.5 | Residencial | No | 0-100kW
202601-NM25-03245 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00764 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00969 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00534 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-00737 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00962 | 24 | Residencial | Yes | 0-100kW
202602-NM25-00086 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00862 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00637 | 8.448 | Residencial | Yes | 0-100kW
202602-NM25-00808 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00960 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03791 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03253 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03248 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01803 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01927 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01359 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03598 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03306 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02903 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-00494 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00564 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03210 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03445 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00722 | 18 | Residencial | Yes | 0-100kW
202401-NM25-02992 | 10 | Residencial | Yes | 0-100kW
202511-NM25-01007 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00926 | 6.8 | Residencial | Yes | 0-100kW
202602-NM25-00948 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03939 | 24.5 | Residencial | Yes | 0-100kW
202602-NM25-00922 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00945 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00903 | 6.8 | Residencial | Yes | 0-100kW
202602-NM25-00944 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00941 | 3.072 | Residencial | Yes | 0-100kW
202602-NM25-00932 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00939 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-00871 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00935 | 10.752 | Residencial | Yes | 0-100kW
202602-NM25-00933 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00619 | 5.856 | Residencial | Yes | 0-100kW
202602-NM25-00931 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00930 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03987 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00649 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-00224 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00881 | 3.84 | Residencial | Yes | 0-100kW
202406-NM25-00557 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-00342 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00839 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00107 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-03471 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-00874 | 9 | Residencial | Yes | 0-100kW
202602-NM25-00905 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00898 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00400 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00886 | 7.6 | Residencial | No | 0-100kW
202601-NM25-02345 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00883 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00882 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00844 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00880 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02319 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02463 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00879 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00878 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01036 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01309 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00867 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00796 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-02576 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00957 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03266 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03027 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-02920 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-04897 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02159 | 11.4 | Residencial | Yes | 0-100kW
202507-NM25-02078 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02168 | 5 | Residencial | Yes | 0-100kW
202601-NM25-03145 | 15 | Comercial | Yes | 0-100kW
202601-NM25-02958 | 12 | Residencial | Yes | 0-100kW
202601-NM25-02899 | 9 | Residencial | Yes | 0-100kW
202512-NM25-06253 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04806 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00845 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03470 | 20 | Residencial | Yes | 0-100kW
202602-NM25-00843 | 15 | Residencial | Yes | 0-100kW
202601-NM25-00431 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02968 | 6.72 | Residencial | Yes | 0-100kW
202511-NM25-00954 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01611 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00810 | 15 | Residencial | Yes | 0-100kW
202602-NM25-00362 | 23 | Residencial | Yes | 0-100kW
202512-NM25-05834 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00063 | 22.8 | Residencial | Yes | 0-100kW
202601-NM25-01486 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03156 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00835 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00830 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01961 | 13.8 | Residencial | Yes | 0-100kW
202602-NM25-00831 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01615 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00616 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00546 | 12.672 | Residencial | Yes | 0-100kW
202602-NM25-00824 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00825 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00818 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02609 | 2.304 | Residencial | Yes | 0-100kW
202602-NM25-00820 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00807 | 0 | Residencial | Yes | 0-100kW
202602-NM25-00816 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00813 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00817 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00579 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00814 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02885 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00271 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00044 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-00811 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01852 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01614 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00805 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00799 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-04811 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00542 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-00794 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03466 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06113 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01873 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03513 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00709 | 9 | Residencial | Yes | 0-100kW
202602-NM25-00518 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-00322 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-01449 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02428 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00285 | 9 | Residencial | Yes | 0-100kW
202602-NM25-00588 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00632 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03083 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03381 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00761 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00634 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00762 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00655 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00073 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02011 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00423 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00643 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00486 | 13.176 | Residencial | Yes | 0-100kW
202512-NM25-03895 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04229 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00270 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00756 | 22.656 | Comercial | Yes | 0-100kW
202602-NM25-00606 | 11.52 | Residencial | Yes | 0-100kW
202601-NM25-01810 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00752 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04858 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01000 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01156 | 15.93 | Residencial | Yes | 0-100kW
202512-NM25-02094 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-02444 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-01098 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00746 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00692 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00569 | 12 | Residencial | Yes | 0-100kW
202601-NM25-00900 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00647 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01406 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02936 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00745 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03282 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00722 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-03825 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03453 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00683 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01604 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01713 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02679 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00689 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03540 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02574 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00738 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03629 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01868 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00735 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01220 | 12.288 | Residencial | Yes | 0-100kW
202512-NM25-01376 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00473 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02099 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00263 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00956 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00726 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00725 | 12 | Residencial | Yes | 0-100kW
202512-NM25-04764 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01351 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02039 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03158 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00026 | 11.4 | Residencial | Yes | 0-100kW
202602-NM25-00721 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00712 | 12 | Residencial | Yes | 0-100kW
202601-NM25-00804 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00720 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00687 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03075 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00713 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-02784 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00183 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00710 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02549 | 7.68 | Residencial | No | 0-100kW
202602-NM25-00704 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03102 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00698 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00702 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00690 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01730 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00700 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00686 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02095 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03046 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00232 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-03314 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00434 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00394 | 7.68 | Residencial | Yes | 0-100kW
202506-NM25-02201 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00681 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-01750 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03448 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00680 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02146 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03275 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00525 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-02488 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01067 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02193 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00142 | 9 | Residencial | Yes | 0-100kW
202512-NM25-03075 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02121 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00511 | 6.222 | Residencial | Yes | 0-100kW
202601-NM25-00866 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01867 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02981 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00674 | 7.6 | Comercial | Yes | 0-100kW
202602-NM25-00085 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01347 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01767 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03374 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00669 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00474 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03616 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00667 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01248 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01352 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-02615 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-00475 | 12 | Residencial | Yes | 0-100kW
202601-NM25-02194 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00333 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02925 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00747 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-03188 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00657 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00651 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05121 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02827 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00729 | 3.8 | Residencial | No | 0-100kW
202601-NM25-02034 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00487 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00002 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01543 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03048 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00976 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01816 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-03457 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00035 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02186 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-03449 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04455 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00014 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00618 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01988 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03031 | 24.576 | Residencial | Yes | 0-100kW
202602-NM25-00636 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00548 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03367 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01811 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01383 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03494 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00087 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00626 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00624 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00160 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-00620 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03249 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01596 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03263 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00622 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00439 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01793 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02029 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00617 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02111 | 11.5 | Residencial | No | 0-100kW
202512-NM25-03528 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03456 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00257 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00018 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04133 | 17.644 | Residencial | Yes | 0-100kW
202512-NM25-05904 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00161 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-04077 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00612 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05736 | 8 | Residencial | Yes | 0-100kW
202509-NM25-01224 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02747 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05258 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02844 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02967 | 7.32 | Residencial | Yes | 0-100kW
202601-NM25-02652 | 12 | Residencial | Yes | 0-100kW
202512-NM25-04741 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01478 | 6.8 | Residencial | Yes | 0-100kW
202602-NM25-00590 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00273 | 12 | Residencial | Yes | 0-100kW
202601-NM25-02627 | 10 | Residencial | Yes | 0-100kW
202602-NM25-00040 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06149 | 6.144 | Residencial | Yes | 0-100kW
202508-NM25-04083 | 6.912 | Residencial | Yes | 0-100kW
202602-NM25-00574 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00228 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03289 | 22.8 | Residencial | Yes | 0-100kW
202509-NM25-00194 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02800 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02192 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00327 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00502 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00558 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00556 | 23 | Residencial | Yes | 0-100kW
202601-NM25-02265 | 22.6 | Residencial | Yes | 0-100kW
202601-NM25-03128 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00546 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03446 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00551 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03056 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00236 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-04395 | 23 | Residencial | Yes | 0-100kW
202512-NM25-00167 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03480 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00545 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03314 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02082 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00529 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04937 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03273 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03089 | 4.758 | Residencial | Yes | 0-100kW
202512-NM25-01947 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01985 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-00111 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00477 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03358 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01488 | 9 | Residencial | Yes | 0-100kW
202602-NM25-00083 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04678 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00523 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03648 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02244 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02770 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00318 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00512 | 4.224 | Residencial | Yes | 0-100kW
202602-NM25-00031 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03404 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00203 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00087 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00508 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00479 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00510 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02144 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04272 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02108 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05375 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00506 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00369 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00501 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00836 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-03451 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02687 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05821 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05795 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00498 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00015 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02428 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00492 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05727 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00495 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02009 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00257 | 9 | Comercial | Yes | 0-100kW
202602-NM25-00488 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03868 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01513 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00442 | 16 | Comercial | Yes | 0-100kW
202511-NM25-02763 | 16 | Residencial | Yes | 0-100kW
202512-NM25-05178 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00480 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06010 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06018 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01967 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-04002 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00472 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00711 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00328 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00431 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00413 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00464 | 4.224 | Residencial | Yes | 0-100kW
202602-NM25-00458 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00389 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00394 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00443 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02266 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03429 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01784 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03593 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01055 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03293 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02398 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04910 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02066 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01051 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00860 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00021 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03359 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00411 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04277 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05282 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03200 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-01269 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00399 | 5.28 | Residencial | Yes | 0-100kW
202601-NM25-03423 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-02824 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-05490 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00404 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00403 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03251 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00097 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01517 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-00571 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01595 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03458 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02998 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00222 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03261 | 11.4 | Residencial | Yes | 0-100kW
202506-NM25-02226 | 13 | Residencial | Yes | 0-100kW
202512-NM25-05533 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00383 | 12 | Comercial | Yes | 0-100kW
202512-NM25-04299 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03924 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03915 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-00280 | 6 | Residencial | Yes | 0-100kW
202601-NM25-02705 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00375 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00374 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00041 | 8 | Residencial | Yes | 0-100kW
202509-NM25-04672 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00345 | 8 | Residencial | Yes | 0-100kW
202512-NM25-02193 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00954 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03370 | 16.512 | Residencial | Yes | 0-100kW
202602-NM25-00367 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00222 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00368 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03396 | 8 | Residencial | No | 0-100kW
202602-NM25-00365 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03223 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00018 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00359 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00361 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00342 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02717 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03544 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00354 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-00254 | 8.448 | Residencial | Yes | 0-100kW
202602-NM25-00356 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00355 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00338 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00350 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00343 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02690 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02306 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02316 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02270 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05659 | 5.6 | Residencial | Yes | 0-100kW
202602-NM25-00323 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02397 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04419 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01656 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01386 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02083 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02981 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01168 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00240 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06033 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00301 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02396 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00320 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03263 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00317 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02984 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03212 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02710 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03001 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00311 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03717 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-01899 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01675 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06034 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00004 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00218 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02716 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00302 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02730 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01627 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-01472 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02296 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03344 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03023 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-04019 | 23 | Residencial | Yes | 0-100kW
202601-NM25-03450 | 23 | Residencial | Yes | 0-100kW
202511-NM25-00283 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00153 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01593 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03328 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00026 | 12.288 | Residencial | Yes | 0-100kW
202601-NM25-01609 | 23 | Residencial | Yes | 0-100kW
202601-NM25-03295 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03698 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05998 | 4.608 | Residencial | Yes | 0-100kW
202511-NM25-02728 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03313 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01213 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00290 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03325 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01030 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00287 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03462 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01355 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00283 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00282 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01436 | 7.68 | Residencial | Yes | 0-100kW
202506-NM25-01546 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00600 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02122 | 10.752 | Residencial | Yes | 0-100kW
202512-NM25-03098 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00689 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00278 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01413 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02455 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05786 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00189 | 13.2 | Residencial | Yes | 0-100kW
202509-NM25-01353 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04276 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01599 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03105 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02410 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04176 | 23 | Comercial | No | 0-100kW
202601-NM25-03407 | 16 | Residencial | Yes | 0-100kW
202512-NM25-04744 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00259 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00258 | 7.6 | Comercial | Yes | 0-100kW
202602-NM25-00253 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01050 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00255 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00251 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03080 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00191 | 16 | Residencial | Yes | 0-100kW
202601-NM25-00819 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00245 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02408 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02429 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02675 | 8 | Residencial | Yes | 0-100kW
202601-NM25-03026 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03255 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00413 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02674 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-02702 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01622 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00241 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00544 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00238 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02233 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02831 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05979 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00234 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05741 | 14.64 | Residencial | Yes | 0-100kW
202601-NM25-03221 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03294 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05867 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02080 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01834 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01818 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-01744 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03045 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01569 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-01628 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00225 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01679 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02044 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00222 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02606 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00221 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02826 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01014 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00219 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03478 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-04806 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02533 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00214 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00213 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05442 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04312 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00211 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00210 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00208 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02051 | 20 | Residencial | Yes | 0-100kW
202602-NM25-00206 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02831 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03088 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04968 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03525 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06171 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03265 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00198 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06196 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02252 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02535 | 23 | Residencial | Yes | 0-100kW
202510-NM25-03306 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03827 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04073 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00187 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03959 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02117 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00185 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01638 | 9 | Residencial | Yes | 0-100kW
202512-NM25-02682 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04162 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00182 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03337 | 23 | Residencial | No | 0-100kW
202511-NM25-02558 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-05358 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04531 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00180 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01658 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04275 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02577 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03620 | 23 | Residencial | Yes | 0-100kW
202509-NM25-04365 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04092 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00574 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00179 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01100 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00146 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00178 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01191 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00177 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03424 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04012 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00175 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05324 | 16 | Residencial | Yes | 0-100kW
202602-NM25-00174 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00143 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00173 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03279 | 15 | Residencial | Yes | 0-100kW
202602-NM25-00171 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00172 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04727 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00170 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05424 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02993 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00124 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00167 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00138 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00168 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00165 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02875 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00164 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04034 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01630 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00162 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00158 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03346 | 16 | Residencial | Yes | 0-100kW
202508-NM25-02339 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-02732 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03147 | 6.8 | Residencial | Yes | 0-100kW
202602-NM25-00156 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00159 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00157 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00153 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00148 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00152 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00150 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00149 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00147 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02479 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00145 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00144 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00141 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06097 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04195 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01060 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00139 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00136 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00134 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00023 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00129 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00133 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00132 | 11.5 | Comercial | Yes | 0-100kW
202602-NM25-00131 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00130 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03312 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00126 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01255 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01361 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01094 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02842 | 7.68 | Residencial | Yes | 0-100kW
202602-NM25-00125 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00121 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02751 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00118 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00119 | 11.5 | Residencial | No | 0-100kW
202409-NM25-00804 | 9.15 | Residencial | Yes | 0-100kW
202602-NM25-00115 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00774 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00501 | 5.376 | Residencial | Yes | 0-100kW
202602-NM25-00100 | 12.672 | Residencial | Yes | 0-100kW
202602-NM25-00104 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00111 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00109 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03260 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00020 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00103 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00033 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02502 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03037 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00096 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00094 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03375 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00369 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00028 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00089 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00090 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00084 | 3.456 | Residencial | Yes | 0-100kW
202601-NM25-02916 | 12 | Residencial | Yes | 0-100kW
202512-NM25-04539 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01424 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05460 | 14.976 | Residencial | No | 0-100kW
202602-NM25-00080 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00078 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04387 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00043 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03425 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06061 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00431 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00076 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02165 | 13.6 | Residencial | Yes | 0-100kW
202601-NM25-00781 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00070 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00071 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00067 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03384 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00065 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00062 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05232 | 18 | Residencial | Yes | 0-100kW
202602-NM25-00064 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03684 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00055 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02905 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00054 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04351 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00049 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03418 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03288 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01922 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00046 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03287 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01935 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04121 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00043 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02021 | 16.492 | Residencial | Yes | 0-100kW
202511-NM25-02141 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-02651 | 12 | Residencial | Yes | 0-100kW
202512-NM25-01660 | 8 | Residencial | Yes | 0-100kW
202511-NM25-00816 | 11.346 | Residencial | Yes | 0-100kW
202602-NM25-00037 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04098 | 11.5 | Residencial | No | 0-100kW
202601-NM25-03041 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00776 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00030 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03039 | 12 | Residencial | Yes | 0-100kW
202602-NM25-00025 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01507 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-03334 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00017 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02099 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03366 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00778 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01600 | 6.912 | Residencial | Yes | 0-100kW
202601-NM25-03447 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04676 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01521 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01130 | 11.136 | Residencial | Yes | 0-100kW
202511-NM25-00334 | 3.5 | Residencial | Yes | 0-100kW
202602-NM25-00011 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02820 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00009 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00007 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02797 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00006 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02901 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05822 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-03408 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03415 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05919 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-03711 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01782 | 8.8 | Residencial | Yes | 0-100kW
202601-NM25-01781 | 8.8 | Residencial | Yes | 0-100kW
202508-NM25-03350 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02399 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01114 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03066 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05479 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02618 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05484 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04409 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03852 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02332 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03466 | 15 | Residencial | Yes | 0-100kW
202512-NM25-05542 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02729 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04548 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04828 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06220 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01191 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04958 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02725 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02104 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03436 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01253 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04803 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03201 | 8.064 | Residencial | Yes | 0-100kW
202512-NM25-04807 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05318 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00505 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-04832 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04957 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03444 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05587 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03442 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04952 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03441 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04480 | 7.6 | Residencial | No | 0-100kW
202512-NM25-02847 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04999 | 11.5 | Residencial | No | 0-100kW
202509-NM25-05517 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01621 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04945 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03434 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04069 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01232 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03426 | 2.562 | Residencial | Yes | 0-100kW
202601-NM25-01361 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02478 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03427 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03046 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03902 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00405 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-03419 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03322 | 22.8 | Residencial | Yes | 0-100kW
202509-NM25-01778 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03627 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03402 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-02555 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-05846 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00765 | 4.992 | Residencial | Yes | 0-100kW
202512-NM25-05363 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02054 | 6.912 | Residencial | Yes | 0-100kW
202511-NM25-03168 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03213 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04578 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03416 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06227 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02839 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01092 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06105 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03571 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01546 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03277 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02804 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06233 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06245 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02249 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01607 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02910 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04003 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06246 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04145 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01036 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03228 | 9 | Residencial | Yes | 0-100kW
202512-NM25-03104 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03403 | 5.376 | Residencial | Yes | 0-100kW
202512-NM25-05372 | 6.144 | Residencial | Yes | 0-100kW
202601-NM25-03237 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01671 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02312 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-03867 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03247 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03038 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-03239 | 23 | Residencial | Yes | 0-100kW
202511-NM25-00579 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03843 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02890 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03258 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03380 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03273 | 13.2 | Residencial | Yes | 0-100kW
202601-NM25-01016 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01497 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02076 | 10 | Residencial | Yes | 0-100kW
202601-NM25-02940 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03835 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-03356 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02147 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-00080 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03368 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00454 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02158 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-03361 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03336 | 12 | Residencial | Yes | 0-100kW
202601-NM25-03338 | 22.8 | Residencial | Yes | 0-100kW
202601-NM25-03105 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03362 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00821 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05612 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01081 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02107 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04567 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02065 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03350 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03135 | 11.5 | Residencial | No | 0-100kW
202512-NM25-04149 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02231 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03963 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04883 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03426 | 9.984 | Residencial | Yes | 0-100kW
202601-NM25-03347 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01291 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02698 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01595 | 4.224 | Residencial | Yes | 0-100kW
202404-NM25-00308 | 6 | Residencial | Yes | 0-100kW
202601-NM25-03341 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05122 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-05343 | 10 | Residencial | Yes | 0-100kW
202512-NM25-03299 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03339 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03333 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03330 | 4.224 | Residencial | Yes | 0-100kW
202512-NM25-01535 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03331 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03335 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03284 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03332 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00495 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02501 | 6 | Residencial | Yes | 0-100kW
202601-NM25-02926 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01832 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02619 | 5.376 | Residencial | Yes | 0-100kW
202512-NM25-00445 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02216 | 8.064 | Residencial | Yes | 0-100kW
202601-NM25-02972 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00664 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02417 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01816 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02213 | 6.528 | Residencial | Yes | 0-100kW
202503-NM25-04904 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02391 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06248 | 11.5 | Residencial | No | 0-100kW
202512-NM25-05264 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06254 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02310 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02995 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02354 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02098 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02137 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04742 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05895 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03139 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01961 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02986 | 5.76 | Residencial | Yes | 0-100kW
202511-NM25-03079 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03928 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04476 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01002 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03776 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03947 | 3.456 | Residencial | Yes | 0-100kW
202511-NM25-00562 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04604 | 5.76 | Residencial | Yes | 0-100kW
202508-NM25-04530 | 5.76 | Residencial | Yes | 0-100kW
202509-NM25-04878 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01396 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03315 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02642 | 23 | Residencial | Yes | 0-100kW
202510-NM25-03851 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-03318 | 7.6 | Residencial | No | 0-100kW
202511-NM25-03069 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03646 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02918 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04352 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03316 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01159 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02856 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04551 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02421 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03303 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00530 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03312 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01415 | 7.6 | Comercial | Yes | 0-100kW
202601-NM25-00727 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00558 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00933 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01391 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03299 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01905 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01116 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03636 | 11.5 | Residencial | No | 0-100kW
202512-NM25-03015 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01866 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01556 | 23 | Residencial | No | 0-100kW
202512-NM25-03609 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02889 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00789 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02915 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03290 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00887 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03903 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03357 | 11.5 | Residencial | No | 0-100kW
202512-NM25-05175 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03299 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02325 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01591 | 4.224 | Residencial | Yes | 0-100kW
202601-NM25-02713 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04880 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03858 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00078 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01575 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-04295 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01192 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03293 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00151 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03292 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00040 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01223 | 10 | Residencial | No | 0-100kW
202601-NM25-03291 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01217 | 4.608 | Residencial | Yes | 0-100kW
202510-NM25-02660 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02736 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-04058 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02413 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02438 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02885 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04172 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03284 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04529 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03403 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06240 | 3.8 | Residencial | No | 0-100kW
202508-NM25-01583 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02063 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01558 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02387 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02976 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03969 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00840 | 22.8 | Residencial | Yes | 0-100kW
202512-NM25-02871 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03280 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03266 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-04112 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03457 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03274 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03269 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02295 | 6.144 | Residencial | Yes | 0-100kW
202601-NM25-03272 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03252 | 4.224 | Residencial | Yes | 0-100kW
202601-NM25-02156 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01850 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02719 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02357 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03246 | 11.52 | Residencial | Yes | 0-100kW
202601-NM25-00711 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04353 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02724 | 3.66 | Residencial | No | 0-100kW
202601-NM25-03241 | 10.62 | Residencial | Yes | 0-100kW
202601-NM25-01082 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03674 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-04175 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03136 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02745 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00623 | 8 | Comercial | Yes | 0-100kW
202601-NM25-02227 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00617 | 8 | Comercial | Yes | 0-100kW
202512-NM25-04080 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02882 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00656 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05782 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00626 | 8 | Comercial | Yes | 0-100kW
202512-NM25-04971 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00504 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03233 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-02979 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04873 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00630 | 8 | Comercial | Yes | 0-100kW
202601-NM25-00864 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04987 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03751 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04887 | 7.6 | Residencial | No | 0-100kW
202601-NM25-01460 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02250 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00364 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02930 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04095 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-06181 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03220 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01301 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02725 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01938 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01799 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02189 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01984 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03217 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02870 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01466 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04761 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02294 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03356 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01965 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01610 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04740 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03205 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02080 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02387 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05831 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00380 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00424 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01667 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-00224 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03195 | 9 | Residencial | Yes | 0-100kW
202601-NM25-03194 | 15 | Residencial | Yes | 0-100kW
202601-NM25-01969 | 12 | Residencial | Yes | 0-100kW
202601-NM25-03002 | 12 | Residencial | Yes | 0-100kW
202601-NM25-02664 | 9 | Residencial | No | 0-100kW
202601-NM25-03163 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03159 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02663 | 12 | Residencial | Yes | 0-100kW
202601-NM25-02660 | 12 | Residencial | Yes | 0-100kW
202601-NM25-03143 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03139 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03138 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05901 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02718 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01231 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01478 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02084 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02711 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02293 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02917 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05876 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02678 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02218 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02407 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02721 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01461 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01087 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02403 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03127 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03097 | 7.68 | Residencial | Yes | 0-100kW
202508-NM25-00612 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-03030 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-02987 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02547 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-02587 | 14.08 | Residencial | Yes | 0-100kW
202601-NM25-00651 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02828 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03132 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02433 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03094 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02794 | 6.3 | Residencial | Yes | 0-100kW
202601-NM25-02774 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00648 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02563 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02196 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02801 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02816 | 8 | Residencial | Yes | 0-100kW
202510-NM25-00863 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06028 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03086 | 15.36 | Residencial | Yes | 0-100kW
202601-NM25-02634 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01060 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03126 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02447 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00985 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03129 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01524 | 23 | Residencial | Yes | 0-100kW
202601-NM25-03053 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-04046 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03024 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01811 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03635 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04576 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02972 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01905 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04355 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03193 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01788 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03744 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02430 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03020 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01251 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-02951 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02861 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02900 | 11.5 | Comercial | Yes | 0-100kW
202509-NM25-01465 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02093 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01413 | 13.44 | Residencial | Yes | 0-100kW
202512-NM25-02979 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00005 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02426 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03863 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03005 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01709 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00030 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-00391 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03000 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00285 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05216 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02553 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06063 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03840 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02985 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01510 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03383 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02946 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03637 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02357 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02976 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00470 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01619 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05384 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01722 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02424 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00469 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02974 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-02406 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04961 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02401 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00458 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05528 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05031 | 3.84 | Residencial | No | 0-100kW
202601-NM25-00502 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02562 | 10.368 | Residencial | Yes | 0-100kW
202601-NM25-02176 | 16 | Residencial | Yes | 0-100kW
202601-NM25-02961 | 9 | Residencial | Yes | 0-100kW
202601-NM25-02656 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01545 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-01612 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02693 | 16 | Residencial | Yes | 0-100kW
202601-NM25-02955 | 13.036 | Residencial | No | 0-100kW
202601-NM25-02956 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05556 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01665 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02418 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02950 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02949 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02039 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02388 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02862 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02944 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01264 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02142 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02937 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-06044 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01620 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-04156 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01004 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-02783 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04404 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03884 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00470 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02924 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00661 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00035 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02927 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01239 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02933 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02829 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02656 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00368 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04541 | 14.274 | Residencial | Yes | 0-100kW
202512-NM25-03665 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03089 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02841 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04423 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03619 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02861 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01677 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02405 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03353 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00155 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03453 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01636 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00138 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-03698 | 4.224 | Residencial | Yes | 0-100kW
202601-NM25-02386 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-01387 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-04511 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01823 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02913 | 23 | Residencial | Yes | 0-100kW
202509-NM25-00212 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-02018 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02887 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02828 | 6.528 | Residencial | Yes | 0-100kW
202601-NM25-02908 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00871 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01806 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02904 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02559 | 10 | Comercial | Yes | 0-100kW
202601-NM25-00777 | 8.064 | Residencial | Yes | 0-100kW
202601-NM25-02895 | 6.954 | Residencial | Yes | 0-100kW
202511-NM25-02821 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02772 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02893 | 17.26 | Residencial | Yes | 0-100kW
202601-NM25-02615 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02884 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00945 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02889 | 3.072 | Residencial | Yes | 0-100kW
202601-NM25-02877 | 3.456 | Residencial | Yes | 0-100kW
202509-NM25-00162 | 23 | Residencial | Yes | 0-100kW
202601-NM25-02878 | 15.2 | Residencial | Yes | 0-100kW
202601-NM25-02882 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01010 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02383 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01263 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01951 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04130 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03135 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02812 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02621 | 15 | Residencial | Yes | 0-100kW
202512-NM25-03674 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02872 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02949 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01312 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02871 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03889 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02838 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00482 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02870 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02869 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02854 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-05059 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04527 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03963 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04021 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01593 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03538 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04047 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02240 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00481 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03682 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02847 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03897 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05224 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03757 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02857 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04151 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01130 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02762 | 4.224 | Residencial | Yes | 0-100kW
202512-NM25-03888 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03211 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04822 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-00478 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00442 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04514 | 4.992 | Residencial | Yes | 0-100kW
202512-NM25-06176 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06229 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02846 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02724 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01991 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02876 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04671 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01809 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01138 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03840 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02682 | 12 | Residencial | Yes | 0-100kW
202601-NM25-00195 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02837 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03748 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01892 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00720 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00367 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01360 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00472 | 23 | Comercial | Yes | 0-100kW
202510-NM25-01618 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03280 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01810 | 7.296 | Residencial | Yes | 0-100kW
202512-NM25-03227 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01646 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-04544 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01403 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02404 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01006 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02829 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01415 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02825 | 4.8 | Residencial | Yes | 0-100kW
202601-NM25-01622 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02562 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02831 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03936 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-04385 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00497 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01607 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02739 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02686 | 5.376 | Residencial | Yes | 0-100kW
202512-NM25-00526 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05752 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00575 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02677 | 12 | Residencial | Yes | 0-100kW
202601-NM25-02055 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02050 | 8 | Residencial | Yes | 0-100kW
202511-NM25-03800 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03121 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03880 | 23 | Residencial | Yes | 0-100kW
202512-NM25-00852 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02654 | 12 | Residencial | Yes | 0-100kW
202509-NM25-01305 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02637 | 12 | Residencial | Yes | 0-100kW
202511-NM25-02623 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01732 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-03381 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02819 | 8 | Residencial | Yes | 0-100kW
202507-NM25-04178 | 10 | Residencial | Yes | 0-100kW
202507-NM25-03199 | 9.984 | Residencial | Yes | 0-100kW
202510-NM25-00068 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02818 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02632 | 8 | Residencial | Yes | 0-100kW
202510-NM25-03907 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02817 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02243 | 23 | Residencial | Yes | 0-100kW
202507-NM25-01841 | 15.2 | Residencial | Yes | 0-100kW
202601-NM25-02815 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04042 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03319 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02462 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02813 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02179 | 23 | Residencial | Yes | 0-100kW
202509-NM25-03332 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-00412 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-02318 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-04536 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02811 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03392 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02810 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01316 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02807 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02809 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03251 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05894 | 12.672 | Residencial | Yes | 0-100kW
202601-NM25-02805 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02803 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02804 | 3.072 | Residencial | Yes | 0-100kW
202509-NM25-01387 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04267 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04899 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-02802 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02801 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02799 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02072 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02795 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00191 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04694 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03068 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00725 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01313 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02791 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03508 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02792 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03257 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02259 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-00958 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02788 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03973 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02787 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02849 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00067 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02777 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03693 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02779 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02780 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03365 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03181 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00733 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01914 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02766 | 6.528 | Residencial | Yes | 0-100kW
202601-NM25-02740 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02670 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02773 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00456 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02769 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00511 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02212 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02754 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02771 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06169 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04908 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02767 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01450 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00377 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02974 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03852 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05056 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02765 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-04341 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04035 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00505 | 23 | Residencial | Yes | 0-100kW
202601-NM25-02761 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05190 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05797 | 5.76 | Residencial | Yes | 0-100kW
202506-NM25-03254 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02758 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02756 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00916 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03762 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01097 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02755 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01693 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02753 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00278 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03772 | 14.976 | Residencial | Yes | 0-100kW
202601-NM25-02750 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00614 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00596 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00961 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02749 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02726 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01577 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01368 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02117 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01437 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00779 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03453 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05799 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01306 | 5.376 | Residencial | Yes | 0-100kW
202601-NM25-02016 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04961 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02744 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01820 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01392 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02741 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02737 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03216 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03012 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00937 | 23 | Residencial | Yes | 0-100kW
202510-NM25-03267 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00947 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02728 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01272 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-02840 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01027 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04264 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01193 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02706 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03307 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02723 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00753 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00374 | 6.528 | Residencial | Yes | 0-100kW
202512-NM25-05520 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00698 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04081 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02722 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04077 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04070 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-02723 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01865 | 15.2 | Residencial | Yes | 0-100kW
202601-NM25-00624 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-01728 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02554 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00060 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03286 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02720 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02938 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02717 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02712 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03203 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03627 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03492 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00783 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00854 | 18 | Residencial | Yes | 0-100kW
202512-NM25-02895 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02013 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04150 | 11.4 | Residencial | Yes | 0-100kW
202512-NM25-03097 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02707 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00703 | 23 | Residencial | Yes | 0-100kW
202512-NM25-01871 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02644 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02607 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05440 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03859 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01794 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03851 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02110 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01792 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02975 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02650 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02680 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02681 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01204 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06247 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01001 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04094 | 6 | Residencial | Yes | 0-100kW
202601-NM25-02439 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00853 | 18 | Comercial | Yes | 0-100kW
202601-NM25-02611 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02602 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02373 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02364 | 9 | Residencial | Yes | 0-100kW
202601-NM25-02589 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02572 | 13.6 | Comercial | Yes | 0-100kW
202512-NM25-03714 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-02662 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02661 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02658 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02657 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02258 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01896 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02222 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02645 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02643 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04627 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02642 | 8.448 | Residencial | Yes | 0-100kW
202512-NM25-03123 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02638 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02206 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03348 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03120 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02635 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05415 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02633 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03903 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00498 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02008 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03118 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03340 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03983 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02007 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02482 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01061 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05902 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03735 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01799 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01546 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00475 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01418 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03100 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04319 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02598 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01302 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00473 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03096 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01641 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03631 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03401 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04015 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02599 | 9 | Residencial | Yes | 0-100kW
202512-NM25-03803 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03630 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00932 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02614 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02609 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05938 | 11.5 | Residencial | No | 0-100kW
202512-NM25-02796 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04636 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03756 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-03087 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03591 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02612 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02605 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02604 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01451 | 8 | Residencial | Yes | 0-100kW
202511-NM25-01839 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02591 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03667 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02593 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02590 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02579 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02515 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03588 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05293 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02578 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01349 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01878 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02581 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02066 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03000 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02575 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01816 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02552 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01484 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05088 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01459 | 8 | Residencial | Yes | 0-100kW
202512-NM25-01880 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03073 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02569 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01367 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01490 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02568 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01070 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02627 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01401 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01541 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02567 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02904 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05864 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-04048 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01417 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00098 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01070 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03066 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04161 | 4.992 | Residencial | Yes | 0-100kW
202512-NM25-03755 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02582 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03409 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03065 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03286 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01068 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02135 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-02338 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00026 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04590 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02327 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03904 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00615 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-01798 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03064 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02910 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02556 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03767 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02207 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-01358 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01469 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02550 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02318 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04083 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01473 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02811 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00645 | 9 | Residencial | Yes | 0-100kW
202601-NM25-01273 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02223 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03327 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02548 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01216 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-03620 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03906 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02042 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00743 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03322 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02493 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04249 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03317 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04214 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02204 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01182 | 11.304 | Residencial | Yes | 0-100kW
202601-NM25-02500 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02035 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02531 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02532 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02530 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02525 | 11.5 | Residencial | No | 0-100kW
202601-NM25-02524 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02003 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02523 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05549 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02490 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02521 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00690 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01837 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-02518 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02511 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02006 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04718 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04132 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-03652 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01807 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02508 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02388 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02247 | 10.368 | Residencial | Yes | 0-100kW
202501-NM25-04397 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03002 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02304 | 15 | Residencial | Yes | 0-100kW
202601-NM25-02495 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03093 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00938 | 10 | Residencial | Yes | 0-100kW
202511-NM25-03543 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00137 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04558 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01410 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-02489 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03084 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03773 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02488 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02473 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00874 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01925 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02484 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03849 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03899 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01055 | 4.224 | Residencial | Yes | 0-100kW
202511-NM25-02885 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00587 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01010 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03054 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01087 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00247 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03084 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03914 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00566 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02869 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05994 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01274 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02363 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02217 | 18 | Residencial | Yes | 0-100kW
202601-NM25-02470 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02465 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00010 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-04182 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02445 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02459 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02454 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02452 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00945 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-02448 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01622 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-05208 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02449 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02681 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03861 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02061 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00972 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02442 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02443 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03933 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01133 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02019 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02298 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03019 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-00023 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02377 | 9 | Residencial | Yes | 0-100kW
202601-NM25-01922 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00535 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02432 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05298 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-03347 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01240 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02963 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01755 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03876 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02421 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00200 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01963 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-02119 | 15.2 | Residencial | Yes | 0-100kW
202511-NM25-00534 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02412 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03857 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02415 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04856 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00551 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04938 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-01947 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01627 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00467 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01043 | 12 | Residencial | Yes | 0-100kW
202601-NM25-00486 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04668 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05981 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02389 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04753 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02382 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03392 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01175 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02479 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02390 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00699 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02378 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00103 | 7.6 | Residencial | No | 0-100kW
202601-NM25-01871 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03784 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00373 | 15.36 | Comercial | Yes | 0-100kW
202601-NM25-01585 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03308 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-01845 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05600 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01194 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02358 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-02808 | 6.528 | Residencial | Yes | 0-100kW
202601-NM25-02352 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02343 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02348 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02279 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01187 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02339 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01212 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02337 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00275 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02332 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02331 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01535 | 8 | Comercial | Yes | 0-100kW
202507-NM25-05130 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00378 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01754 | 12 | Residencial | Yes | 0-100kW
202508-NM25-02217 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-03526 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02318 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00231 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01244 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05896 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02316 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02315 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02312 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00891 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01665 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00392 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05983 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01128 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01800 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03014 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02942 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-03946 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03450 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02301 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02300 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01456 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02826 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01348 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03270 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04406 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02141 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01400 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02202 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01363 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03025 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01822 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02296 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02236 | 11.4 | Residencial | Yes | 0-100kW
202512-NM25-03391 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04065 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01906 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02707 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03026 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05898 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02286 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02256 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05100 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05804 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02288 | 11.904 | Residencial | No | 0-100kW
202508-NM25-00510 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02166 | 5.376 | Residencial | Yes | 0-100kW
202601-NM25-02280 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03386 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02268 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02277 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03223 | 16 | Comercial | Yes | 0-100kW
202601-NM25-02274 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03220 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02106 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02267 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00622 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06027 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02255 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02237 | 7 | Residencial | Yes | 0-100kW
202512-NM25-06094 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02680 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05653 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00297 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02096 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02234 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02242 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02334 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00767 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02245 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02235 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02118 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02318 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02228 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02232 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01817 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01658 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00539 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05148 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03354 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00011 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00580 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05785 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02167 | 12 | Residencial | Yes | 0-100kW
202601-NM25-00435 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01662 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02229 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00490 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01652 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00877 | 15 | Residencial | Yes | 0-100kW
202601-NM25-01823 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03362 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02169 | 15.51 | Comercial | Yes | 0-100kW
202512-NM25-04710 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00428 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02219 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05540 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01570 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02214 | 11.5 | Residencial | No | 0-100kW
202512-NM25-04376 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00780 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01702 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03843 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02207 | 11.136 | Residencial | Yes | 0-100kW
202601-NM25-02211 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01821 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02210 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00114 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00487 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00480 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01642 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03023 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03400 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01833 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01339 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02205 | 2.928 | Residencial | Yes | 0-100kW
202511-NM25-02492 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01965 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00805 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03018 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03289 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02199 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03121 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01847 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02058 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02447 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01893 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06167 | 23 | Residencial | Yes | 0-100kW
202511-NM25-03284 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01827 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02195 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00370 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03538 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00411 | 5 | Residencial | Yes | 0-100kW
202510-NM25-02933 | 6.912 | Residencial | Yes | 0-100kW
202601-NM25-01932 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03088 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00810 | 9.6 | Residencial | No | 0-100kW
202511-NM25-03101 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06166 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04316 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00943 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-02187 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06072 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06089 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00565 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05760 | 8.052 | Residencial | Yes | 0-100kW
202512-NM25-05517 | 10 | Residencial | Yes | 0-100kW
202601-NM25-02097 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-02315 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-01884 | 4.608 | Residencial | Yes | 0-100kW
202510-NM25-01684 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02163 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02157 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01690 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05987 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02148 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04128 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01560 | 9 | Residencial | Yes | 0-100kW
202601-NM25-02151 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00366 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02144 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01862 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03418 | 15 | Comercial | Yes | 0-100kW
202512-NM25-04220 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03592 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04330 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02132 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04221 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02117 | 24 | Residencial | Yes | 0-100kW
202601-NM25-02130 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04692 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02129 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05123 | 7.68 | Residencial | Yes | 0-100kW
202511-NM25-02584 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05271 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06019 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02123 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02125 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04091 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02119 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02115 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01938 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-02105 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01992 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05815 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02107 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00484 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02113 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04438 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02047 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05747 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02074 | 16 | Residencial | Yes | 0-100kW
202601-NM25-02087 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00488 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05052 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03753 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02060 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02089 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05577 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04482 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04163 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00280 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05496 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-02067 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01185 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-00708 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02059 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01289 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02057 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05575 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04845 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01176 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00255 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02049 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03082 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04749 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02010 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04015 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01163 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02031 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02046 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03433 | 8 | Residencial | Yes | 0-100kW
202601-NM25-02041 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01299 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03272 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00466 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02993 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03996 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01259 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03981 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01927 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03122 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01934 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00451 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04417 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02969 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01485 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05493 | 5.3 | Comercial | Yes | 0-100kW
202510-NM25-01133 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-04138 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02873 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01624 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00833 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-01946 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00312 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02024 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00769 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00008 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-02808 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02022 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00421 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04078 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01774 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02017 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01851 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01439 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02015 | 3.072 | Residencial | No | 0-100kW
202510-NM25-02060 | 6.912 | Residencial | Yes | 0-100kW
202601-NM25-02012 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04900 | 7.296 | Residencial | Yes | 0-100kW
202512-NM25-04077 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-01645 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02505 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04609 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01924 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-00982 | 9 | Residencial | Yes | 0-100kW
202601-NM25-01656 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-01695 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03473 | 11.4 | Comercial | Yes | 0-100kW
202601-NM25-01603 | 15 | Residencial | Yes | 0-100kW
202510-NM25-01576 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01998 | 12 | Residencial | Yes | 0-100kW
202510-NM25-01574 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01994 | 12 | Comercial | Yes | 0-100kW
202509-NM25-01185 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01983 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01981 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01980 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01979 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01976 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01977 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01972 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01973 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01971 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01966 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01960 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01962 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01958 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01959 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01956 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01954 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01952 | 9.216 | Residencial | Yes | 0-100kW
202601-NM25-00904 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05750 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01953 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-05051 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01948 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01944 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01191 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01942 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01943 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-03607 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03827 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01940 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00659 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04860 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04225 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01919 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01030 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-02908 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-03742 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03467 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03459 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05595 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00357 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01751 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00814 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01909 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01205 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-01964 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01904 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01901 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05545 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04855 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03844 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03228 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01894 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01276 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04661 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-03779 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01891 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04066 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04217 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01890 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-02460 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01888 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01074 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-00221 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04630 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01885 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00627 | 9 | Residencial | Yes | 0-100kW
202601-NM25-01881 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01880 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01879 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01876 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00513 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01874 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01872 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01863 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01867 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00746 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01860 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02621 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-00027 | 6.8 | Residencial | Yes | 0-100kW
202601-NM25-01862 | 9.15 | Residencial | Yes | 0-100kW
202601-NM25-01859 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00066 | 10 | Residencial | Yes | 0-100kW
202512-NM25-04123 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01371 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01679 | 5 | Residencial | Yes | 0-100kW
202601-NM25-01048 | 5.376 | Residencial | Yes | 0-100kW
202601-NM25-01854 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03878 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01848 | 23 | Residencial | Yes | 0-100kW
202512-NM25-01205 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05726 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00445 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01831 | 2.5 | Residencial | Yes | 0-100kW
202510-NM25-02211 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01843 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01842 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04011 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00962 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05810 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03020 | 8.832 | Residencial | Yes | 0-100kW
202601-NM25-01828 | 2.562 | Residencial | Yes | 0-100kW
202601-NM25-01835 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-04378 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00707 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01481 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01805 | 16.47 | Residencial | Yes | 0-100kW
202601-NM25-01824 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01443 | 9 | Residencial | Yes | 0-100kW
202601-NM25-00462 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04179 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01814 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00111 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01812 | 4.224 | Residencial | Yes | 0-100kW
202601-NM25-01815 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01788 | 8 | Residencial | Yes | 0-100kW
202512-NM25-04776 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-03551 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05291 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01791 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01795 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01009 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01935 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01789 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01787 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00610 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01783 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01253 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00977 | 13.6 | Residencial | Yes | 0-100kW
202512-NM25-04834 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-02309 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01761 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01758 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01755 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01752 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01750 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01942 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05978 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01749 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01745 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01747 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01746 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05851 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01739 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01744 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01743 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01311 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01741 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03063 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04310 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01740 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01738 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01530 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-01520 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01735 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03061 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04452 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01734 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04061 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01502 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01267 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01731 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03056 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02092 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01726 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05396 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01727 | 13.036 | Residencial | Yes | 0-100kW
202601-NM25-01491 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04449 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01698 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03053 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03404 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03965 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01703 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01712 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01718 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00955 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04057 | 11.5 | Residencial | No | 0-100kW
202512-NM25-03691 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02188 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-01705 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-04033 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03049 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01706 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03731 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01952 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01083 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01668 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03832 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03532 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01701 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01700 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01699 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04045 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01697 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01692 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00483 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01687 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01685 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01686 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01684 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01683 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03048 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01672 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01544 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01678 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00161 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01673 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01674 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03238 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01669 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01257 | 8 | Residencial | Yes | 0-100kW
202512-NM25-01496 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01666 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01662 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03517 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04574 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01661 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01657 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01660 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01034 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01651 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00672 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01648 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01644 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00500 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05410 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02329 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01646 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01643 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03037 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01639 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01640 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02803 | 24 | Residencial | Yes | 0-100kW
202512-NM25-06013 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00368 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01632 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03152 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01572 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01634 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02328 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01033 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00363 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03515 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03601 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01631 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02865 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02127 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-06029 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02241 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05986 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03561 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01431 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03367 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05573 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02940 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02239 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05424 | 8.784 | Residencial | Yes | 0-100kW
202512-NM25-03633 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03910 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00104 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-01218 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04994 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04134 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04244 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05395 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03610 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03913 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00389 | 13.2 | Residencial | Yes | 0-100kW
202512-NM25-05368 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-03400 | 9 | Residencial | Yes | 0-100kW
202601-NM25-01590 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03585 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04184 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-02202 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03639 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01584 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04662 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01059 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05769 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-02629 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03393 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01442 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01025 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00111 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04640 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06012 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02695 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01019 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02430 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00019 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01068 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04621 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02785 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03645 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01476 | 2.688 | Residencial | Yes | 0-100kW
202512-NM25-03548 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01420 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03617 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03324 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01477 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03783 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03597 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02097 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00709 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03687 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04831 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05761 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02704 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01219 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04432 | 5.76 | Residencial | No | 0-100kW
202601-NM25-01551 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03475 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03668 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01073 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03557 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00665 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-00095 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00249 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00600 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02803 | 10 | Residencial | Yes | 0-100kW
202601-NM25-01549 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01524 | 12 | Residencial | Yes | 0-100kW
202601-NM25-00422 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01542 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01538 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01534 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00613 | 18 | Residencial | Yes | 0-100kW
202512-NM25-05832 | 15.2 | Residencial | Yes | 0-100kW
202601-NM25-01528 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01537 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05980 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01531 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01536 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01509 | 2.5 | Residencial | Yes | 0-100kW
202601-NM25-01315 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01526 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01523 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01527 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01519 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05985 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02980 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01516 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03605 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05174 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03385 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01518 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00446 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01464 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-04196 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02106 | 7.259 | Residencial | Yes | 0-100kW
202601-NM25-01500 | 3.456 | Residencial | Yes | 0-100kW
202512-NM25-03229 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05303 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01511 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01499 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03031 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05054 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05051 | 5.76 | Residencial | Yes | 0-100kW
202508-NM25-02787 | 8.832 | Residencial | Yes | 0-100kW
202601-NM25-01501 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01505 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04445 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01162 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01494 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00358 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01487 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03047 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01493 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01462 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02456 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-04434 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03219 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01463 | 24 | Residencial | Yes | 0-100kW
202601-NM25-01485 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01312 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04117 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01474 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01023 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02991 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03847 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00762 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03190 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01457 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03624 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01470 | 4.992 | Residencial | Yes | 0-100kW
202512-NM25-03182 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04690 | 9 | Residencial | Yes | 0-100kW
202601-NM25-00754 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03454 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00741 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01447 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03672 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-05974 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01458 | 4.992 | Residencial | Yes | 0-100kW
202512-NM25-02819 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01372 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00705 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00467 | 22.8 | Residencial | Yes | 0-100kW
202601-NM25-00898 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04907 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01421 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01452 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03926 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01449 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05539 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01696 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01448 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05975 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03738 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04510 | 8 | Residencial | No | 0-100kW
202511-NM25-01724 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01438 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01440 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06030 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01429 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02711 | 23 | Residencial | Yes | 0-100kW
202512-NM25-05721 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-01633 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-05977 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01433 | 4.224 | Residencial | Yes | 0-100kW
202509-NM25-00019 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00713 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01391 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00593 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06026 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04342 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03625 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01423 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00965 | 12 | Residencial | Yes | 0-100kW
202510-NM25-04012 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-03696 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01282 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04491 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03177 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02543 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02302 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00595 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01404 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02961 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00433 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05849 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03788 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01983 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01411 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03402 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02784 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02586 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00110 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04513 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03172 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00925 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04635 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01405 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03006 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03846 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01346 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06082 | 6.144 | Residencial | Yes | 0-100kW
202512-NM25-04896 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00438 | 4.224 | Residencial | Yes | 0-100kW
202512-NM25-01733 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03169 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00562 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00710 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-01389 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01387 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04658 | 20.716 | Residencial | Yes | 0-100kW
202601-NM25-00115 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04019 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06052 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01376 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01380 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04467 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02998 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01317 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00517 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01377 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01378 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01609 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05369 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-01370 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05090 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01772 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00686 | 9.984 | Residencial | Yes | 0-100kW
202512-NM25-03041 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01062 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00639 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03107 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00813 | 7.296 | Residencial | Yes | 0-100kW
202601-NM25-01076 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04667 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-02276 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03801 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01791 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01263 | 11.52 | Residencial | Yes | 0-100kW
202601-NM25-00964 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03537 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03046 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03506 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03799 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05285 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00763 | 4.224 | Residencial | Yes | 0-100kW
202512-NM25-05390 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00347 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01417 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05982 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05976 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01333 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00680 | 4.224 | Residencial | Yes | 0-100kW
202601-NM25-01341 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02332 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00588 | 2.304 | Residencial | Yes | 0-100kW
202601-NM25-01337 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01334 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00632 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01330 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00966 | 24 | Residencial | Yes | 0-100kW
202601-NM25-01331 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01329 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01327 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01328 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01325 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02741 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01324 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01276 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01323 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01322 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01320 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01318 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01319 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01242 | 12 | Residencial | Yes | 0-100kW
202510-NM25-03367 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03308 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01316 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01024 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00841 | 5.25 | Residencial | Yes | 0-100kW
202601-NM25-01063 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01309 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00886 | 19 | Residencial | Yes | 0-100kW
202601-NM25-01307 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04067 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01563 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-05367 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01305 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-01465 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00863 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04871 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-01294 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01296 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03677 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03596 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00818 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04317 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01287 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03768 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00743 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00889 | 13.908 | Residencial | Yes | 0-100kW
202601-NM25-00809 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03579 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02622 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03854 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04904 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01268 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02298 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02636 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01515 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03836 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01266 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03534 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02631 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03567 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03235 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01120 | 5.3 | Comercial | Yes | 0-100kW
202510-NM25-01119 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-03542 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01117 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-04647 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03258 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03603 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01256 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03325 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03249 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01249 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06053 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-01247 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01241 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04522 | 10.752 | Residencial | Yes | 0-100kW
202601-NM25-01239 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03967 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00862 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03303 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01238 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00789 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01236 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01234 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01224 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03998 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-03222 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01230 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01227 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01228 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01225 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03727 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01222 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01219 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00450 | 15 | Residencial | Yes | 0-100kW
202512-NM25-05144 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01220 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01207 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01214 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01047 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01213 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01199 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03297 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01042 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00034 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01203 | 24.75 | Comercial | Yes | 0-100kW
202512-NM25-03352 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01201 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01040 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03349 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03321 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00894 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01195 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01589 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-01191 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02079 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01189 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03382 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01565 | 8 | Residencial | Yes | 0-100kW
202511-NM25-03098 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01186 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05414 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03372 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01607 | 8 | Residencial | Yes | 0-100kW
202601-NM25-01183 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00455 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03416 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03214 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01173 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03001 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03287 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01021 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01172 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00321 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00820 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00912 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-03213 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02978 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01166 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04686 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03337 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00911 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-04963 | 15 | Residencial | Yes | 0-100kW
202601-NM25-00909 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-03267 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00908 | 5.3 | Comercial | Yes | 0-100kW
202508-NM25-05365 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-03370 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00906 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-02592 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01639 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00905 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-01158 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00903 | 5.3 | Comercial | Yes | 0-100kW
202511-NM25-02750 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00901 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-00895 | 5.3 | Comercial | Yes | 0-100kW
202512-NM25-03254 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05869 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-00317 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01154 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00878 | 9.15 | Residencial | No | 0-100kW
202601-NM25-01146 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03236 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01144 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00869 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01143 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03306 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01148 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02320 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01147 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01136 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01142 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05367 | 5.3 | Comercial | Yes | 0-100kW
202601-NM25-01145 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01150 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02319 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03064 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01140 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02643 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01138 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01131 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01520 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04869 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01128 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01497 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01129 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03232 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01125 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03576 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00662 | 15.36 | Residencial | Yes | 0-100kW
202601-NM25-00865 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00868 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00158 | 4.392 | Residencial | Yes | 0-100kW
202601-NM25-01121 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03279 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06008 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01120 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01031 | 9.6 | Residencial | Yes | 0-100kW
202512-NM25-03294 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00995 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00991 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00434 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04074 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00953 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02086 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05534 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00993 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01658 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00918 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00427 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03760 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03369 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04702 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03108 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00927 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00449 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-03901 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06070 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-05514 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00639 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02133 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00527 | 12 | Residencial | Yes | 0-100kW
202512-NM25-03898 | 24 | Residencial | Yes | 0-100kW
202601-NM25-00447 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00628 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00918 | 11.4 | Residencial | Yes | 0-100kW
202511-NM25-03631 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03711 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03769 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00446 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00856 | 15 | Residencial | Yes | 0-100kW
202512-NM25-05578 | 15 | Residencial | Yes | 0-100kW
202512-NM25-00508 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-05386 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05552 | 7.68 | Residencial | Yes | 0-100kW
202508-NM25-04414 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02472 | 23 | Residencial | No | 0-100kW
202601-NM25-00836 | 11.4 | Residencial | Yes | 0-100kW
202509-NM25-04576 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03937 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01780 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03362 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02992 | 6.912 | Residencial | Yes | 0-100kW
202601-NM25-00837 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00802 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-00825 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01799 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-00254 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00785 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-00833 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00835 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03961 | 22.8 | Residencial | Yes | 0-100kW
202601-NM25-00795 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-00830 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00829 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00826 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00827 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00792 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01122 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00823 | 1.92 | Residencial | Yes | 0-100kW
202512-NM25-02078 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00824 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00811 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00960 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01997 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00812 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05310 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-00616 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00605 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03090 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02890 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02804 | 10.368 | Residencial | Yes | 0-100kW
202512-NM25-01975 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00468 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04153 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02874 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04095 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02973 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00801 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03074 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01644 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00611 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-05360 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00797 | 11.4 | Residencial | Yes | 0-100kW
202512-NM25-02965 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04981 | 5.376 | Residencial | Yes | 0-100kW
202508-NM25-02793 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01938 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00135 | 9 | Residencial | Yes | 0-100kW
202601-NM25-00534 | 7.6 | Comercial | Yes | 0-100kW
202601-NM25-00790 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00786 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06017 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00784 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00631 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01974 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05256 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02825 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00518 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03431 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04294 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02683 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00765 | 9.6 | Residencial | Yes | 0-100kW
202512-NM25-04456 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01196 | 6.8 | Residencial | Yes | 0-100kW
202512-NM25-01949 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02679 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02963 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03970 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02330 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03289 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02687 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02953 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00602 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03870 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01931 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03445 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02186 | 7.68 | Residencial | Yes | 0-100kW
202510-NM25-01978 | 8 | Residencial | Yes | 0-100kW
202512-NM25-04687 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02669 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05813 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02758 | 7.6 | Residencial | No | 0-100kW
202512-NM25-03446 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03259 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02936 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02675 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03498 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02632 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03275 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02658 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03931 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03559 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00724 | 19.2 | Comercial | Yes | 0-100kW
202512-NM25-02589 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03640 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03128 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02076 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06081 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03814 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02943 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02258 | 5 | Residencial | Yes | 0-100kW
202512-NM25-04674 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01597 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02806 | 11.5 | Residencial | No | 0-100kW
202512-NM25-03119 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04001 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00716 | 9.6 | Residencial | Yes | 0-100kW
202601-NM25-00714 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02647 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06139 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02639 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04763 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-03125 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02571 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00697 | 6.8 | Residencial | Yes | 0-100kW
202511-NM25-01008 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06205 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06226 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02234 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00686 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03958 | 15 | Residencial | Yes | 0-100kW
202507-NM25-04993 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00684 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03232 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03660 | 6.912 | Residencial | Yes | 0-100kW
202509-NM25-02467 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00681 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03374 | 4.608 | Residencial | Yes | 0-100kW
202601-NM25-00679 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00678 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04921 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01407 | 23 | Residencial | Yes | 0-100kW
202509-NM25-04968 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00092 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-05157 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00666 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00390 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01164 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00667 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00668 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00665 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00083 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03049 | 8 | Residencial | Yes | 0-100kW
202510-NM25-03699 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00830 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03039 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03069 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00660 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03110 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00635 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01632 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-02403 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03029 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03036 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02812 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02986 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05613 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00407 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01489 | 23 | Residencial | Yes | 0-100kW
202508-NM25-04322 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-00644 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03028 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04874 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00641 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05179 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02069 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00646 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00643 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03011 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03869 | 4.82 | Residencial | Yes | 0-100kW
202511-NM25-00176 | 7.68 | Residencial | Yes | 0-100kW
202508-NM25-04315 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02744 | 4.224 | Residencial | Yes | 0-100kW
202512-NM25-01219 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03374 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-02780 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01728 | 5.376 | Residencial | Yes | 0-100kW
202510-NM25-04132 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04486 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00559 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03316 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02006 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04158 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04108 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-03913 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00437 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00335 | 12 | Residencial | Yes | 0-100kW
202512-NM25-03059 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00543 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04281 | 9.216 | Residencial | Yes | 0-100kW
202512-NM25-04485 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05047 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-05846 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02924 | 23 | Residencial | Yes | 0-100kW
202508-NM25-01650 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02233 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00603 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03678 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01637 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02434 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03504 | 23 | Residencial | Yes | 0-100kW
202508-NM25-02714 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01200 | 9 | Residencial | Yes | 0-100kW
202509-NM25-03971 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05722 | 5.76 | Residencial | Yes | 0-100kW
202511-NM25-01628 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02799 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00625 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00756 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02573 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01210 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00606 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01260 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02743 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03266 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03861 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00515 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04484 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00519 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-04260 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-04848 | 9.6 | Residencial | Yes | 0-100kW
202512-NM25-03283 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06073 | 8 | Residencial | Yes | 0-100kW
202512-NM25-00733 | 7.68 | Residencial | Yes | 0-100kW
202601-NM25-00601 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02663 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03215 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00547 | 11.5 | Residencial | No | 0-100kW
202512-NM25-03051 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05925 | 5.376 | Residencial | Yes | 0-100kW
202512-NM25-05193 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03376 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02500 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04312 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03003 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02877 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00591 | 7.6 | Residencial | No | 0-100kW
202512-NM25-02929 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04490 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04380 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03394 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00515 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00579 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01923 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03326 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04029 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00573 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01078 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00566 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03829 | 5.76 | Residencial | Yes | 0-100kW
202510-NM25-03315 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01929 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04023 | 23 | Residencial | Yes | 0-100kW
202510-NM25-03677 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01774 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00558 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03885 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03434 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00022 | 12 | Residencial | Yes | 0-100kW
202512-NM25-02041 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05207 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04401 | 24.78 | Residencial | Yes | 0-100kW
202601-NM25-00537 | 7.32 | Residencial | Yes | 0-100kW
202509-NM25-03318 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06023 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-05318 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-06016 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00516 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06021 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02340 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03280 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00542 | 23 | Residencial | Yes | 0-100kW
202508-NM25-01298 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00375 | 9 | Residencial | Yes | 0-100kW
202508-NM25-03566 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00538 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-00274 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02483 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02755 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00384 | 10 | Residencial | Yes | 0-100kW
202512-NM25-04234 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00528 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00514 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05644 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00527 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00485 | 15 | Residencial | Yes | 0-100kW
202512-NM25-04443 | 9.216 | Residencial | Yes | 0-100kW
202509-NM25-00185 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00512 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04379 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03680 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04180 | 11.5 | Residencial | No | 0-100kW
202512-NM25-03882 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02408 | 15 | Residencial | Yes | 0-100kW
202508-NM25-04391 | 11.4 | Residencial | Yes | 0-100kW
202512-NM25-04697 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03860 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04449 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-04701 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01920 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03771 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02861 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05884 | 4.608 | Residencial | Yes | 0-100kW
202510-NM25-02040 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03770 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03366 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00507 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01917 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01985 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04387 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04146 | 4.992 | Residencial | Yes | 0-100kW
202601-NM25-00346 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03812 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01910 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00486 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03763 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02371 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00499 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04347 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-03040 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02787 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03072 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03368 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05188 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-00763 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02084 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05591 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04693 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03912 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03067 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03009 | 3.84 | Residencial | Yes | 0-100kW
202508-NM25-02383 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03689 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01697 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03438 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04711 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02807 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03900 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00479 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-03435 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00051 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05657 | 7.35 | Residencial | Yes | 0-100kW
202508-NM25-03615 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03468 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04039 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01169 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04698 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00460 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03544 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-02617 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00453 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05788 | 5.6 | Residencial | Yes | 0-100kW
202512-NM25-02862 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03664 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01330 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00448 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01946 | 12 | Residencial | Yes | 0-100kW
202601-NM25-00444 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03135 | 4.2 | Residencial | Yes | 0-100kW
202512-NM25-04561 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02000 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05024 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03292 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01089 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02637 | 19.2 | Residencial | Yes | 0-100kW
202510-NM25-01994 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04040 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-02896 | 7.68 | Residencial | Yes | 0-100kW
202405-NM25-00837 | 6.588 | Residencial | Yes | 0-100kW
202601-NM25-00432 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00429 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02950 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02141 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03276 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02812 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00414 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02201 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04478 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-02234 | 6.144 | Residencial | Yes | 0-100kW
202512-NM25-03599 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00416 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00410 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03149 | 24 | Residencial | Yes | 0-100kW
202601-NM25-00124 | 8 | Residencial | Yes | 0-100kW
202512-NM25-02815 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00406 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01319 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-03622 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00402 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00403 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01209 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-01081 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00399 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04320 | 9.984 | Residencial | Yes | 0-100kW
202601-NM25-00400 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05269 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02833 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01611 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00367 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00395 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03805 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00393 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01214 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00391 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02037 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03721 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04542 | 5.376 | Residencial | Yes | 0-100kW
202510-NM25-00372 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02660 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02813 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00386 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00381 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02923 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00344 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02547 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02855 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00372 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01731 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01217 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03307 | 11.5 | Residencial | No | 0-100kW
202512-NM25-03296 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03329 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05438 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-04091 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05467 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06129 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-00711 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01999 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05550 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03194 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04052 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02238 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00042 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01612 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01936 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02812 | 23 | Residencial | Yes | 0-100kW
202509-NM25-03094 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05048 | 15.36 | Residencial | Yes | 0-100kW
202508-NM25-05658 | 23 | Residencial | Yes | 0-100kW
202508-NM25-03724 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02247 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00023 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00065 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05611 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00345 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02774 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00340 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00305 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00332 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00328 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06143 | 16 | Residencial | Yes | 0-100kW
202509-NM25-00743 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00321 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04130 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00316 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00310 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00309 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00702 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05743 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03919 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00295 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00300 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00299 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00273 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00287 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00285 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00281 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06115 | 9 | Residencial | Yes | 0-100kW
202601-NM25-00277 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00278 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00271 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00272 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01837 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00258 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00528 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00264 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00261 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04707 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03891 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00242 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00256 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00253 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00251 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00248 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00246 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00245 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00239 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00230 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00240 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00238 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00040 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00236 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00235 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04935 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00228 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00231 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00225 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00226 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00229 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00554 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00102 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01243 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00222 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00220 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-00217 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00210 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00216 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00214 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00212 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00207 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00211 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01472 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05868 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00206 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00657 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00201 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02056 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00200 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00198 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00197 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00084 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00084 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00726 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00187 | 11.5 | Comercial | Yes | 0-100kW
202512-NM25-01649 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00180 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00182 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00178 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00175 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00177 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00179 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04868 | 10 | Comercial | Yes | 0-100kW
202601-NM25-00173 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00172 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00169 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01539 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-00171 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00168 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00167 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00166 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00165 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00160 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00163 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00136 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00083 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00157 | 11.4 | Residencial | Yes | 0-100kW
202512-NM25-04607 | 8 | Residencial | Yes | 0-100kW
202512-NM25-04603 | 8 | Residencial | Yes | 0-100kW
202512-NM25-04211 | 8 | Residencial | Yes | 0-100kW
202512-NM25-06128 | 9 | Residencial | Yes | 0-100kW
202512-NM25-05623 | 12 | Residencial | Yes | 0-100kW
202512-NM25-03950 | 8 | Residencial | Yes | 0-100kW
202601-NM25-00153 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-00155 | 10 | Residencial | Yes | 0-100kW
202512-NM25-03642 | 24 | Residencial | No | 0-100kW
202512-NM25-05636 | 12 | Residencial | Yes | 0-100kW
202601-NM25-00152 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00151 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00150 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00149 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00148 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00147 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00146 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00145 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00144 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03455 | 24 | Residencial | Yes | 0-100kW
202512-NM25-05847 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00142 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04111 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00139 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00138 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00137 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00134 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00133 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00130 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01209 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02875 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00131 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-00204 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03688 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05400 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06031 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00647 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00097 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02919 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00089 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01909 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03334 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00125 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00113 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04893 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-03336 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02794 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00120 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03326 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02822 | 11.5 | Residencial | No | 0-100kW
202512-NM25-02881 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00117 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05413 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03030 | 4.992 | Residencial | Yes | 0-100kW
202512-NM25-03330 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01042 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01908 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-02818 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03612 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03900 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03411 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03747 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-01704 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00112 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03034 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00231 | 12.288 | Residencial | Yes | 0-100kW
202512-NM25-03095 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06093 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01907 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03422 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02902 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00107 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01419 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03335 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04235 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01617 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-02793 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05363 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05325 | 11.5 | Comercial | Yes | 0-100kW
202601-NM25-00106 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01212 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01618 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00100 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03092 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00091 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01211 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00095 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05455 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02809 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04006 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00093 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00709 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04704 | 6.912 | Residencial | Yes | 0-100kW
202411-NM25-01892 | 6.588 | Residencial | Yes | 0-100kW
202601-NM25-00088 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04428 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01044 | 16.492 | Residencial | Yes | 0-100kW
202512-NM25-03057 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01837 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-01673 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04424 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00077 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02427 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00074 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04422 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03702 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04174 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-03920 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00069 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00870 | 6.104 | Residencial | Yes | 0-100kW
202512-NM25-01254 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04420 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04331 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-04384 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-01897 | 4.608 | Residencial | Yes | 0-100kW
202512-NM25-04660 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04189 | 5.376 | Residencial | Yes | 0-100kW
202601-NM25-00062 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03288 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00058 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02832 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05541 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00250 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00924 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03883 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01243 | 10.33 | Comercial | Yes | 0-100kW
202603-NM25-01341 | 12.81 | Residencial | Yes | 0-100kW
202601-NM25-01379 | 15.5 | Residencial | Yes | 0-100kW
202603-NM25-00268 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04992 | 15.3 | Residencial | Yes | 0-100kW
202511-NM25-02907 | 13.62 | Residencial | Yes | 0-100kW
202509-NM25-03378 | 15.3 | Residencial | Yes | 0-100kW
202509-NM25-02522 | 17.5 | Residencial | Yes | 0-100kW
202602-NM25-02037 | 19.7 | Residencial | Yes | 0-100kW
202602-NM25-01706 | 16.5 | Residencial | Yes | 0-100kW
202602-NM25-00789 | 16.96 | Residencial | Yes | 0-100kW
202509-NM25-05899 | 15.3 | Residencial | Yes | 0-100kW
202510-NM25-02963 | 15.3 | Residencial | Yes | 0-100kW
202510-NM25-02143 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00815 | 10.88 | Residencial | Yes | 0-100kW
202601-NM25-00582 | 16.3 | Residencial | Yes | 0-100kW
202601-NM25-03439 | 9.752 | Residencial | Yes | 0-100kW
202601-NM25-02875 | 24.43 | Residencial | Yes | 0-100kW
202601-NM25-02037 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-02527 | 14.29 | Residencial | Yes | 0-100kW
202601-NM25-02137 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01955 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01221 | 5.566 | Residencial | Yes | 0-100kW
202601-NM25-01141 | 6.612 | Residencial | Yes | 0-100kW
202601-NM25-00570 | 7.822 | Residencial | Yes | 0-100kW
202603-NM25-02271 | 13.026 | Residencial | Yes | 0-100kW
202603-NM25-02097 | 7.08 | Residencial | Yes | 0-100kW
202603-NM25-01509 | 5.926 | Residencial | Yes | 0-100kW
202602-NM25-00909 | 9.8 | Residencial | Yes | 0-100kW
202601-NM25-02092 | 8.54 | Residencial | Yes | 0-100kW
202601-NM25-00122 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-02048 | 6.434 | Residencial | Yes | 0-100kW
202603-NM25-00966 | 9.714 | Residencial | Yes | 0-100kW
202601-NM25-02431 | 11.492 | Residencial | Yes | 0-100kW
202601-NM25-02253 | 10.04 | Residencial | Yes | 0-100kW
202602-NM25-02378 | 16.01 | Residencial | Yes | 0-100kW
202601-NM25-01162 | 7.026 | Residencial | Yes | 0-100kW
202603-NM25-01032 | 8.254 | Residencial | Yes | 0-100kW
202603-NM25-00067 | 8.6 | Residencial | Yes | 0-100kW
202602-NM25-00407 | 9.904 | Residencial | Yes | 0-100kW
202601-NM25-02203 | 7.572 | Residencial | Yes | 0-100kW
202602-NM25-01096 | 6.322 | Residencial | Yes | 0-100kW
202601-NM25-00223 | 15.8 | Residencial | Yes | 0-100kW
202602-NM25-00072 | 11.51 | Residencial | Yes | 0-100kW
202603-NM25-00832 | 16.703 | Residencial | Yes | 0-100kW
202601-NM25-02881 | 5.58 | Residencial | Yes | 0-100kW
202601-NM25-00881 | 7.682 | Residencial | Yes | 0-100kW
202602-NM25-00700 | 8.856 | Residencial | Yes | 0-100kW
202602-NM25-00938 | 6.546 | Residencial | Yes | 0-100kW
202603-NM25-01282 | 5.9 | Residencial | Yes | 0-100kW
202512-NM25-02576 | 19.1 | Residencial | Yes | 0-100kW
202602-NM25-00798 | 11.701 | Residencial | Yes | 0-100kW
202601-NM25-03435 | 22.32 | Residencial | Yes | 0-100kW
202601-NM25-03126 | 5.196 | Residencial | Yes | 0-100kW
202602-NM25-01612 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00102 | 11.492 | Residencial | Yes | 0-100kW
202603-NM25-01759 | 13.041 | Residencial | Yes | 0-100kW
202601-NM25-01512 | 8.64 | Residencial | Yes | 0-100kW
202602-NM25-01097 | 6.672 | Residencial | Yes | 0-100kW
202512-NM25-02648 | 23.8 | Residencial | Yes | 0-100kW
202601-NM25-02468 | 7.5 | Residencial | Yes | 0-100kW
202512-NM25-03556 | 24.31 | Residencial | Yes | 0-100kW
202601-NM25-01917 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-02526 | 3.54 | Residencial | Yes | 0-100kW
202601-NM25-01964 | 6.958 | Residencial | Yes | 0-100kW
202512-NM25-05845 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03300 | 23 | Residencial | Yes | 0-100kW
202510-NM25-00450 | 17.2 | Residencial | Yes | 0-100kW
202601-NM25-00252 | 19.1 | Residencial | Yes | 0-100kW
202603-NM25-01343 | 10.848 | Residencial | Yes | 0-100kW
202601-NM25-02651 | 5.72 | Residencial | Yes | 0-100kW
202602-NM25-01092 | 6.84 | Residencial | Yes | 0-100kW
202602-NM25-02622 | 6.954 | Residencial | Yes | 0-100kW
202602-NM25-02610 | 7.832 | Residencial | Yes | 0-100kW
202601-NM25-02032 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02170 | 14.44 | Residencial | Yes | 0-100kW
202601-NM25-02469 | 8.214 | Residencial | Yes | 0-100kW
202602-NM25-01237 | 9.136 | Residencial | Yes | 0-100kW
202603-NM25-01144 | 9.292 | Residencial | Yes | 0-100kW
202512-NM25-00295 | 13.542 | Residencial | Yes | 0-100kW
202601-NM25-02136 | 6.222 | Residencial | Yes | 0-100kW
202602-NM25-01035 | 5.566 | Residencial | Yes | 0-100kW
202602-NM25-02688 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01083 | 6.312 | Residencial | Yes | 0-100kW
202602-NM25-00520 | 5.566 | Residencial | Yes | 0-100kW
202602-NM25-02459 | 8 | Residencial | Yes | 0-100kW
202512-NM25-06163 | 6.17 | Residencial | Yes | 0-100kW
202603-NM25-01546 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02269 | 10.752 | Residencial | Yes | 0-100kW
202602-NM25-02649 | 5.58 | Residencial | Yes | 0-100kW
202603-NM25-00205 | 10.43 | Residencial | Yes | 0-100kW
202601-NM25-02583 | 6.296 | Residencial | Yes | 0-100kW
202603-NM25-00960 | 8.972 | Residencial | Yes | 0-100kW
202602-NM25-00671 | 3.294 | Residencial | Yes | 0-100kW
202601-NM25-03257 | 4.425 | Residencial | Yes | 0-100kW
202601-NM25-02100 | 10.368 | Residencial | Yes | 0-100kW
202602-NM25-00095 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01151 | 8.192 | Residencial | Yes | 0-100kW
202601-NM25-01498 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01165 | 10.482 | Residencial | Yes | 0-100kW
202509-NM25-00022 | 9.56 | Residencial | Yes | 0-100kW
202602-NM25-00823 | 7.846 | Residencial | Yes | 0-100kW
202601-NM25-02238 | 6.572 | Residencial | Yes | 0-100kW
202601-NM25-02317 | 9.74 | Residencial | Yes | 0-100kW
202603-NM25-02134 | 12.99 | Residencial | Yes | 0-100kW
202602-NM25-00550 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-01159 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02902 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01339 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03083 | 4.425 | Residencial | Yes | 0-100kW
202510-NM25-02192 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01080 | 10.892 | Residencial | Yes | 0-100kW
202602-NM25-00382 | 10.672 | Residencial | Yes | 0-100kW
202603-NM25-02486 | 4.026 | Residencial | Yes | 0-100kW
202512-NM25-05664 | 7.84 | Residencial | Yes | 0-100kW
202511-NM25-01908 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02564 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-00129 | 6.296 | Residencial | Yes | 0-100kW
202511-NM25-03077 | 15.3 | Residencial | Yes | 0-100kW
202603-NM25-02454 | 5.015 | Residencial | Yes | 0-100kW
202602-NM25-00841 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00045 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02588 | 7.536 | Residencial | Yes | 0-100kW
202601-NM25-01991 | 5.17 | Residencial | Yes | 0-100kW
202602-NM25-02653 | 6.222 | Residencial | Yes | 0-100kW
202603-NM25-01222 | 9.136 | Residencial | Yes | 0-100kW
202512-NM25-05085 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01478 | 10.224 | Residencial | Yes | 0-100kW
202602-NM25-00539 | 5.956 | Residencial | Yes | 0-100kW
202512-NM25-01989 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00105 | 5.536 | Residencial | Yes | 0-100kW
202602-NM25-01641 | 11.215 | Residencial | Yes | 0-100kW
202603-NM25-01997 | 9.74 | Residencial | Yes | 0-100kW
202602-NM25-01418 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00354 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02380 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00570 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03073 | 22.026 | Residencial | Yes | 0-100kW
202512-NM25-02747 | 4.026 | Residencial | Yes | 0-100kW
202603-NM25-01140 | 8.932 | Residencial | Yes | 0-100kW
202602-NM25-01719 | 11.44 | Residencial | Yes | 0-100kW
202603-NM25-02436 | 16.99 | Residencial | Yes | 0-100kW
202512-NM25-06098 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00276 | 15.34 | Residencial | Yes | 0-100kW
202603-NM25-02139 | 4.392 | Residencial | Yes | 0-100kW
202510-NM25-02325 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03970 | 17.26 | Residencial | Yes | 0-100kW
202601-NM25-01086 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00980 | 4.32 | Residencial | Yes | 0-100kW
202601-NM25-01533 | 5.566 | Residencial | Yes | 0-100kW
202509-NM25-02979 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00628 | 3.54 | Residencial | Yes | 0-100kW
202510-NM25-04316 | 21.5 | Residencial | Yes | 0-100kW
202601-NM25-00436 | 19.1 | Residencial | Yes | 0-100kW
202603-NM25-01822 | 6.701 | Residencial | No | 0-100kW
202512-NM25-04720 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05678 | 17.5 | Residencial | Yes | 0-100kW
202509-NM25-04221 | 17.2 | Residencial | Yes | 0-100kW
202602-NM25-01725 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05543 | 3.966 | Residencial | Yes | 0-100kW
202602-NM25-01618 | 11.4 | Residencial | Yes | 0-100kW
202601-NM25-03422 | 6.902 | Residencial | Yes | 0-100kW
202602-NM25-02194 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01318 | 7.38 | Residencial | Yes | 0-100kW
202603-NM25-00957 | 4.392 | Residencial | Yes | 0-100kW
202602-NM25-01754 | 9.904 | Residencial | Yes | 0-100kW
202601-NM25-00522 | 9.52 | Residencial | Yes | 0-100kW
202602-NM25-01868 | 11.362 | Residencial | Yes | 0-100kW
202601-NM25-03399 | 10.518 | Residencial | Yes | 0-100kW
202601-NM25-00621 | 10.672 | Residencial | Yes | 0-100kW
202512-NM25-02685 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01767 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02505 | 7.84 | Residencial | Yes | 0-100kW
202601-NM25-01676 | 10.04 | Residencial | Yes | 0-100kW
202602-NM25-00508 | 9.136 | Residencial | Yes | 0-100kW
202603-NM25-01640 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02149 | 7.462 | Residencial | Yes | 0-100kW
202601-NM25-01861 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02543 | 7.846 | Residencial | Yes | 0-100kW
202602-NM25-00893 | 6.036 | Residencial | Yes | 0-100kW
202602-NM25-00379 | 6.296 | Residencial | Yes | 0-100kW
202602-NM25-02444 | 7.38 | Residencial | Yes | 0-100kW
202603-NM25-00905 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04375 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01693 | 7.8 | Residencial | Yes | 0-100kW
202601-NM25-01281 | 5.58 | Residencial | Yes | 0-100kW
202601-NM25-01160 | 9.368 | Residencial | Yes | 0-100kW
202602-NM25-02195 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00873 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02539 | 7.64 | Residencial | Yes | 0-100kW
202603-NM25-01671 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00802 | 6.91 | Comercial | Yes | 0-100kW
202602-NM25-01105 | 12.208 | Residencial | Yes | 0-100kW
202601-NM25-01122 | 5.165 | Residencial | Yes | 0-100kW
202603-NM25-00686 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01439 | 4.02 | Residencial | Yes | 0-100kW
202602-NM25-01114 | 13.036 | Residencial | Yes | 0-100kW
202603-NM25-01978 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01054 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02352 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02423 | 7.492 | Residencial | Yes | 0-100kW
202601-NM25-02919 | 12.644 | Residencial | Yes | 0-100kW
202602-NM25-02675 | 8.09 | Residencial | Yes | 0-100kW
202602-NM25-00192 | 16 | Residencial | Yes | 0-100kW
202603-NM25-01939 | 24 | Residencial | Yes | 0-100kW
202512-NM25-06231 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01366 | 15.34 | Residencial | Yes | 0-100kW
202603-NM25-00642 | 8.418 | Residencial | Yes | 0-100kW
202601-NM25-02911 | 7.832 | Residencial | Yes | 0-100kW
202602-NM25-01604 | 7.87 | Residencial | Yes | 0-100kW
202603-NM25-00497 | 6.612 | Residencial | Yes | 0-100kW
202508-NM25-03966 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00583 | 6.572 | Residencial | Yes | 0-100kW
202602-NM25-00900 | 5.956 | Residencial | Yes | 0-100kW
202603-NM25-01683 | 8.192 | Residencial | Yes | 0-100kW
202512-NM25-03707 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04049 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01542 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00749 | 7.462 | Residencial | Yes | 0-100kW
2026-GD-00028 | 34.5 | Comercial | Yes | 0-100kW
202601-NM25-00844 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00039 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01069 | 9.136 | Residencial | Yes | 0-100kW
202603-NM25-00326 | 8 | Residencial | Yes | 0-100kW
202511-NM25-04425 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02254 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02053 | 7.992 | Residencial | Yes | 0-100kW
202602-NM25-02436 | 7.474 | Residencial | Yes | 0-100kW
202512-NM25-05235 | 17.2 | Residencial | Yes | 0-100kW
202601-NM25-01237 | 10.572 | Residencial | Yes | 0-100kW
202602-NM25-00678 | 16.702 | Residencial | Yes | 0-100kW
202602-NM25-00872 | 6.02 | Residencial | Yes | 0-100kW
202601-NM25-02733 | 7.322 | Residencial | Yes | 0-100kW
202603-NM25-00325 | 8.382 | Residencial | Yes | 0-100kW
202601-NM25-03369 | 10.752 | Residencial | Yes | 0-100kW
202601-NM25-02446 | 23 | Residencial | Yes | 0-100kW
202601-NM25-02912 | 6.902 | Residencial | Yes | 0-100kW
202601-NM25-00520 | 10.672 | Residencial | Yes | 0-100kW
202603-NM25-00965 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00988 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01448 | 4.286 | Residencial | Yes | 0-100kW
202602-NM25-02536 | 11.198 | Residencial | Yes | 0-100kW
202601-NM25-03270 | 10.98 | Residencial | Yes | 0-100kW
202602-NM25-01028 | 4.026 | Residencial | Yes | 0-100kW
202512-NM25-03109 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01353 | 9.33 | Residencial | Yes | 0-100kW
202602-NM25-02420 | 7.84 | Residencial | Yes | 0-100kW
202510-NM25-03927 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00428 | 5 | Residencial | Yes | 0-100kW
202601-NM25-02395 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02284 | 5.196 | Residencial | Yes | 0-100kW
202602-NM25-01424 | 11.492 | Residencial | Yes | 0-100kW
202601-NM25-01887 | 6.322 | Residencial | Yes | 0-100kW
202603-NM25-00396 | 6.612 | Residencial | Yes | 0-100kW
202602-NM25-02446 | 8.45 | Residencial | Yes | 0-100kW
202601-NM25-02027 | 5.964 | Residencial | Yes | 0-100kW
202602-NM25-00137 | 14.5 | Residencial | Yes | 0-100kW
202602-NM25-01093 | 7.462 | Residencial | Yes | 0-100kW
202602-NM25-00629 | 4.72 | Residencial | Yes | 0-100kW
202512-NM25-02483 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01286 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01529 | 5.926 | Residencial | Yes | 0-100kW
202602-NM25-01226 | 15.204 | Comercial | Yes | 0-100kW
202603-NM25-02017 | 8.85 | Residencial | Yes | 0-100kW
202602-NM25-01744 | 8.42 | Residencial | Yes | 0-100kW
202602-NM25-00430 | 3.5 | Residencial | Yes | 0-100kW
202511-NM25-03601 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00056 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-04371 | 23 | Residencial | Yes | 0-100kW
202601-NM25-00109 | 7.102 | Residencial | Yes | 0-100kW
202603-NM25-02002 | 8.23 | Residencial | Yes | 0-100kW
202601-NM25-01300 | 10.672 | Residencial | Yes | 0-100kW
202603-NM25-01515 | 6.872 | Residencial | Yes | 0-100kW
202602-NM25-01760 | 10 | Residencial | Yes | 0-100kW
202602-NM25-02230 | 9.58 | Residencial | Yes | 0-100kW
202601-NM25-01883 | 5.49 | Residencial | Yes | 0-100kW
202602-NM25-00792 | 9.7 | Residencial | Yes | 0-100kW
202601-NM25-00170 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00566 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04061 | 8 | Residencial | Yes | 0-100kW
202602-NM25-00999 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00114 | 8.09 | Residencial | Yes | 0-100kW
202601-NM25-03323 | 12.592 | Residencial | Yes | 0-100kW
202603-NM25-02262 | 9.136 | Residencial | Yes | 0-100kW
202602-NM25-00955 | 16.26 | Residencial | Yes | 0-100kW
202602-NM25-02814 | 11.44 | Residencial | Yes | 0-100kW
202512-NM25-04964 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01385 | 6.33 | Residencial | Yes | 0-100kW
202602-NM25-01709 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02151 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02173 | 19.294 | Residencial | Yes | 0-100kW
202602-NM25-01765 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02179 | 6.195 | Residencial | Yes | 0-100kW
202601-NM25-02653 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01134 | 5.566 | Residencial | Yes | 0-100kW
202601-NM25-00351 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00754 | 19.1 | Residencial | Yes | 0-100kW
202602-NM25-00658 | 10.672 | Residencial | Yes | 0-100kW
202602-NM25-02847 | 14.2 | Residencial | Yes | 0-100kW
202603-NM25-00946 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00264 | 6.526 | Residencial | Yes | 0-100kW
202512-NM25-02138 | 14.5 | Residencial | Yes | 0-100kW
202603-NM25-00990 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01135 | 10.672 | Residencial | Yes | 0-100kW
202602-NM25-01920 | 3.66 | Residencial | Yes | 0-100kW
202601-NM25-00141 | 8.126 | Residencial | Yes | 0-100kW
202601-NM25-01194 | 9.662 | Residencial | Yes | 0-100kW
202602-NM25-01135 | 6.072 | Residencial | Yes | 0-100kW
202603-NM25-01324 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01132 | 7.38 | Residencial | Yes | 0-100kW
202602-NM25-01807 | 7.462 | Residencial | Yes | 0-100kW
202511-NM25-03307 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02907 | 8.682 | Residencial | Yes | 0-100kW
202603-NM25-02233 | 5.49 | Residencial | Yes | 0-100kW
202601-NM25-02954 | 8.992 | Residencial | Yes | 0-100kW
202601-NM25-03391 | 14.694 | Residencial | Yes | 0-100kW
202601-NM25-02570 | 19.51 | Residencial | Yes | 0-100kW
202602-NM25-00110 | 6.348 | Comercial | Yes | 0-100kW
202504-NM25-03351 | 23 | Comercial | Yes | 0-100kW
202601-NM25-00057 | 7.492 | Residencial | Yes | 0-100kW
202512-NM25-03094 | 19.1 | Residencial | Yes | 0-100kW
202602-NM25-02564 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00686 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04857 | 3.66 | Residencial | Yes | 0-100kW
202602-NM25-02202 | 10.672 | Residencial | Yes | 0-100kW
202602-NM25-01810 | 5.95 | Residencial | Yes | 0-100kW
202603-NM25-01935 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01067 | 4.026 | Residencial | Yes | 0-100kW
202603-NM25-00927 | 10.112 | Residencial | Yes | 0-100kW
202603-NM25-01065 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-03378 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01544 | 15.3 | Residencial | Yes | 0-100kW
202512-NM25-05875 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02144 | 10.6 | Residencial | Yes | 0-100kW
202603-NM25-01013 | 11.5 | Residencial | No | 0-100kW
202602-NM25-00415 | 5.076 | Residencial | Yes | 0-100kW
202602-NM25-00728 | 15.2 | Comercial | Yes | 0-100kW
202602-NM25-02218 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02433 | 11.51 | Residencial | Yes | 0-100kW
202603-NM25-01230 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00159 | 19.1 | Residencial | Yes | 0-100kW
202603-NM25-00057 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00250 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01720 | 10 | Residencial | Yes | 0-100kW
202509-NM25-03853 | 6 | Residencial | Yes | 0-100kW
202602-NM25-01377 | 10.33 | Residencial | Yes | 0-100kW
202601-NM25-01197 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00123 | 5.076 | Residencial | Yes | 0-100kW
202601-NM25-00440 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00509 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00827 | 9.33 | Residencial | Yes | 0-100kW
202602-NM25-02533 | 8.254 | Residencial | Yes | 0-100kW
202602-NM25-00515 | 11.098 | Residencial | Yes | 0-100kW
202602-NM25-01845 | 6 | Residencial | Yes | 0-100kW
202512-NM25-02792 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01002 | 5.76 | Residencial | Yes | 0-100kW
202603-NM25-01703 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00768 | 12.53 | Residencial | Yes | 0-100kW
202603-NM25-01091 | 16.99 | Residencial | Yes | 0-100kW
202602-NM25-02496 | 10.814 | Residencial | Yes | 0-100kW
202603-NM25-01436 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00351 | 14.572 | Residencial | Yes | 0-100kW
202601-NM25-03067 | 3 | Residencial | Yes | 0-100kW
202601-NM25-01626 | 23 | Residencial | Yes | 0-100kW
202509-NM25-00221 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02729 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-04865 | 8.8 | Residencial | Yes | 0-100kW
202510-NM25-03945 | 18.285 | Residencial | Yes | 0-100kW
202603-NM25-00907 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-00354 | 18.17 | Residencial | Yes | 0-100kW
202602-NM25-01091 | 5.196 | Residencial | Yes | 0-100kW
202601-NM25-01184 | 19.1 | Residencial | Yes | 0-100kW
202602-NM25-01328 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01252 | 7.396 | Residencial | Yes | 0-100kW
202601-NM25-02953 | 5.804 | Residencial | Yes | 0-100kW
202601-NM25-00618 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00056 | 9.562 | Residencial | Yes | 0-100kW
202601-NM25-01578 | 5 | Residencial | Yes | 0-100kW
202601-NM25-03281 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-00209 | 9.216 | Residencial | Yes | 0-100kW
202603-NM25-01122 | 3.8 | Residencial | Yes | 0-100kW
202602-NM25-01029 | 9.136 | Residencial | Yes | 0-100kW
202601-NM25-01725 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02850 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02236 | 7.072 | Residencial | Yes | 0-100kW
202603-NM25-01162 | 15.3 | Residencial | Yes | 0-100kW
202603-NM25-02058 | 15.89 | Residencial | Yes | 0-100kW
202512-NM25-00544 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01145 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01137 | 11.522 | Residencial | Yes | 0-100kW
202602-NM25-02347 | 9.344 | Residencial | Yes | 0-100kW
202602-NM25-00701 | 23 | Residencial | Yes | 0-100kW
202603-NM25-01714 | 9.852 | Residencial | Yes | 0-100kW
202601-NM25-02806 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01681 | 6.144 | Residencial | Yes | 0-100kW
202512-NM25-04039 | 8.83 | Residencial | Yes | 0-100kW
202602-NM25-00965 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03419 | 14.75 | Residencial | Yes | 0-100kW
202602-NM25-01192 | 12.178 | Residencial | Yes | 0-100kW
202603-NM25-01293 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01560 | 10.112 | Residencial | Yes | 0-100kW
202603-NM25-01385 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00350 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02959 | 9.136 | Residencial | Yes | 0-100kW
202603-NM25-02034 | 5.926 | Residencial | Yes | 0-100kW
202601-NM25-02833 | 13.81 | Residencial | Yes | 0-100kW
202601-NM25-00524 | 11.44 | Residencial | Yes | 0-100kW
202602-NM25-01928 | 15.2 | Residencial | Yes | 0-100kW
202602-NM25-02330 | 7.09 | Residencial | Yes | 0-100kW
202601-NM25-02474 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00706 | 14.572 | Residencial | Yes | 0-100kW
202603-NM25-02130 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06213 | 3.66 | Residencial | Yes | 0-100kW
202601-NM25-03095 | 8.84 | Residencial | Yes | 0-100kW
202601-NM25-03047 | 4.992 | Residencial | Yes | 0-100kW
202602-NM25-01661 | 7 | Residencial | Yes | 0-100kW
202601-NM25-01733 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02465 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02784 | 4.85 | Residencial | Yes | 0-100kW
202602-NM25-01700 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01153 | 6.322 | Residencial | Yes | 0-100kW
202601-NM25-00663 | 8.562 | Residencial | Yes | 0-100kW
202602-NM25-02879 | 18 | Residencial | Yes | 0-100kW
202602-NM25-00832 | 7.202 | Residencial | Yes | 0-100kW
202603-NM25-02477 | 3.54 | Residencial | Yes | 0-100kW
202601-NM25-00758 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01524 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01512 | 11.492 | Residencial | Yes | 0-100kW
202602-NM25-02369 | 15.8 | Residencial | Yes | 0-100kW
202603-NM25-02362 | 8.304 | Residencial | Yes | 0-100kW
202512-NM25-02630 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02830 | 6.732 | Residencial | Yes | 0-100kW
202602-NM25-02686 | 6.672 | Residencial | Yes | 0-100kW
202603-NM25-02438 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00184 | 9.136 | Residencial | Yes | 0-100kW
202510-NM25-01643 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01854 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00091 | 6.8 | Residencial | Yes | 0-100kW
202601-NM25-02964 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01647 | 23 | Residencial | Yes | 0-100kW
202601-NM25-02005 | 10.614 | Residencial | Yes | 0-100kW
202603-NM25-01199 | 5.076 | Residencial | Yes | 0-100kW
202603-NM25-00637 | 5.926 | Residencial | Yes | 0-100kW
202601-NM25-02346 | 13.862 | Residencial | Yes | 0-100kW
202601-NM25-00463 | 11.824 | Residencial | Yes | 0-100kW
202601-NM25-01597 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02439 | 11.626 | Residencial | Yes | 0-100kW
202601-NM25-01283 | 9.406 | Residencial | Yes | 0-100kW
202601-NM25-02834 | 9.506 | Residencial | Yes | 0-100kW
202512-NM25-01886 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00529 | 13.032 | Comercial | Yes | 0-100kW
202602-NM25-01232 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00337 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00358 | 4.116 | Residencial | Yes | 0-100kW
202603-NM25-02126 | 8.022 | Residencial | Yes | 0-100kW
202601-NM25-00671 | 9.52 | Residencial | Yes | 0-100kW
202602-NM25-01166 | 6.296 | Residencial | Yes | 0-100kW
202601-NM25-03271 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02679 | 19.808 | Residencial | Yes | 0-100kW
202603-NM25-02335 | 12.91 | Residencial | Yes | 0-100kW
202512-NM25-02336 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01059 | 6.612 | Residencial | Yes | 0-100kW
202602-NM25-00863 | 6 | Residencial | Yes | 0-100kW
202603-NM25-00140 | 14 | Residencial | Yes | 0-100kW
202509-NM25-04845 | 23 | Residencial | Yes | 0-100kW
202512-NM25-03300 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01180 | 5.772 | Residencial | Yes | 0-100kW
202512-NM25-06006 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-01436 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00215 | 11.51 | Residencial | Yes | 0-100kW
202601-NM25-01479 | 7.332 | Residencial | Yes | 0-100kW
202602-NM25-01297 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00128 | 4 | Residencial | Yes | 0-100kW
202601-NM25-01310 | 7.87 | Residencial | Yes | 0-100kW
202601-NM25-00987 | 15.93 | Residencial | Yes | 0-100kW
202510-NM25-02036 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01146 | 8.664 | Residencial | Yes | 0-100kW
202603-NM25-02395 | 3.835 | Residencial | Yes | 0-100kW
202601-NM25-01114 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02914 | 6.846 | Residencial | Yes | 0-100kW
202602-NM25-00042 | 11.4 | Residencial | Yes | 0-100kW
202509-NM25-01225 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01756 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01895 | 6.67 | Residencial | Yes | 0-100kW
202601-NM25-01152 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00536 | 6.612 | Residencial | Yes | 0-100kW
202602-NM25-02448 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-02291 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00387 | 11.5 | Residencial | No | 0-100kW
202601-NM25-01846 | 5.566 | Residencial | Yes | 0-100kW
202602-NM25-01596 | 7.072 | Residencial | Yes | 0-100kW
202603-NM25-01874 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02516 | 10.672 | Residencial | Yes | 0-100kW
202512-NM25-01192 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-04085 | 15.892 | Residencial | Yes | 0-100kW
202603-NM25-00367 | 12.976 | Residencial | Yes | 0-100kW
202602-NM25-02501 | 9.724 | Residencial | Yes | 0-100kW
202603-NM25-01537 | 3.835 | Residencial | Yes | 0-100kW
202602-NM25-00946 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01144 | 8.126 | Residencial | Yes | 0-100kW
202601-NM25-01647 | 5.196 | Residencial | Yes | 0-100kW
202512-NM25-05124 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01230 | 14.18 | Residencial | Yes | 0-100kW
202509-NM25-05896 | 17.2 | Residencial | Yes | 0-100kW
202603-NM25-01876 | 12.72 | Residencial | Yes | 0-100kW
202603-NM25-01491 | 6.34 | Residencial | Yes | 0-100kW
202603-NM25-00118 | 5.076 | Residencial | Yes | 0-100kW
202512-NM25-03166 | 15.04 | Residencial | Yes | 0-100kW
202603-NM25-00162 | 8.072 | Residencial | Yes | 0-100kW
202602-NM25-01133 | 6.546 | Residencial | Yes | 0-100kW
202603-NM25-02020 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00451 | 6.93 | Residencial | Yes | 0-100kW
202601-NM25-02565 | 15.76 | Residencial | Yes | 0-100kW
202512-NM25-02448 | 10.112 | Residencial | Yes | 0-100kW
202602-NM25-01533 | 17.5 | Residencial | Yes | 0-100kW
202601-NM25-00330 | 5.015 | Residencial | Yes | 0-100kW
202602-NM25-01243 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00738 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02251 | 11.44 | Residencial | Yes | 0-100kW
202601-NM25-02510 | 10.528 | Residencial | Yes | 0-100kW
202601-NM25-03011 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01887 | 8.56 | Residencial | Yes | 0-100kW
202601-NM25-02145 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01677 | 7.38 | Residencial | Yes | 0-100kW
202603-NM25-01499 | 9.752 | Residencial | Yes | 0-100kW
202602-NM25-01273 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02301 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04597 | 8 | Residencial | Yes | 0-100kW
202603-NM25-00166 | 8.456 | Residencial | Yes | 0-100kW
202602-NM25-00819 | 7.464 | Residencial | Yes | 0-100kW
202601-NM25-00086 | 8.724 | Residencial | Yes | 0-100kW
202603-NM25-02206 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00996 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-05163 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01733 | 15.3 | Residencial | Yes | 0-100kW
202601-NM25-01753 | 4.786 | Residencial | Yes | 0-100kW
202603-NM25-00646 | 16.836 | Residencial | Yes | 0-100kW
202603-NM25-01133 | 16.5 | Residencial | Yes | 0-100kW
202602-NM25-02327 | 7.87 | Residencial | Yes | 0-100kW
202601-NM25-00872 | 19.1 | Residencial | Yes | 0-100kW
202602-NM25-02428 | 10.84 | Residencial | Yes | 0-100kW
202601-NM25-01504 | 6.49 | Residencial | Yes | 0-100kW
202602-NM25-01751 | 5.076 | Residencial | Yes | 0-100kW
202603-NM25-01019 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02320 | 3.54 | Residencial | Yes | 0-100kW
202602-NM25-01832 | 12.976 | Residencial | Yes | 0-100kW
202602-NM25-02532 | 8.26 | Residencial | Yes | 0-100kW
202603-NM25-02074 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03710 | 16.5 | Residencial | Yes | 0-100kW
202603-NM25-00214 | 9.6 | Residencial | Yes | 0-100kW
202601-NM25-03076 | 4.026 | Residencial | Yes | 0-100kW
202602-NM25-02018 | 15.04 | Residencial | Yes | 0-100kW
202601-NM25-03102 | 17.6 | Residencial | Yes | 0-100kW
202601-NM25-01363 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03438 | 19.1 | Residencial | Yes | 0-100kW
202509-NM25-06038 | 17.5 | Residencial | Yes | 0-100kW
202602-NM25-00388 | 5.605 | Residencial | Yes | 0-100kW
202601-NM25-00457 | 10.044 | Residencial | Yes | 0-100kW
202602-NM25-02314 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01586 | 9.206 | Residencial | Yes | 0-100kW
202601-NM25-02623 | 8.064 | Residencial | Yes | 0-100kW
202601-NM25-00730 | 9.59 | Residencial | Yes | 0-100kW
202603-NM25-01161 | 7.67 | Residencial | Yes | 0-100kW
202602-NM25-00061 | 5.196 | Residencial | Yes | 0-100kW
202602-NM25-00112 | 16.22 | Residencial | Yes | 0-100kW
202602-NM25-02500 | 9.714 | Residencial | Yes | 0-100kW
202601-NM25-01840 | 6.572 | Residencial | Yes | 0-100kW
202601-NM25-00597 | 4.026 | Residencial | Yes | 0-100kW
202603-NM25-01336 | 24.888 | Residencial | Yes | 0-100kW
202602-NM25-01777 | 14.274 | Residencial | Yes | 0-100kW
202602-NM25-01434 | 11.44 | Residencial | Yes | 0-100kW
202602-NM25-00621 | 4.826 | Residencial | Yes | 0-100kW
202602-NM25-02598 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01139 | 5.956 | Residencial | Yes | 0-100kW
202601-NM25-00383 | 16.576 | Residencial | Yes | 0-100kW
202603-NM25-00331 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01522 | 12.81 | Residencial | Yes | 0-100kW
202601-NM25-02052 | 7.492 | Residencial | Yes | 0-100kW
202603-NM25-00126 | 7.098 | Residencial | Yes | 0-100kW
202601-NM25-01371 | 5.196 | Residencial | Yes | 0-100kW
202602-NM25-00937 | 9.474 | Residencial | Yes | 0-100kW
202602-NM25-02153 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02726 | 4.758 | Residencial | Yes | 0-100kW
202602-NM25-01041 | 7.67 | Residencial | Yes | 0-100kW
202602-NM25-00688 | 8.148 | Residencial | Yes | 0-100kW
202601-NM25-00669 | 7.072 | Residencial | Yes | 0-100kW
202602-NM25-00248 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02874 | 8.26 | Residencial | Yes | 0-100kW
202603-NM25-01586 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01171 | 12.954 | Residencial | Yes | 0-100kW
202602-NM25-02800 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01238 | 7.102 | Residencial | Yes | 0-100kW
202602-NM25-01637 | 6.872 | Comercial | Yes | 0-100kW
202601-NM25-02335 | 5.076 | Residencial | Yes | 0-100kW
202603-NM25-01707 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-02476 | 7.87 | Residencial | Yes | 0-100kW
202602-NM25-01346 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03267 | 16.3 | Residencial | Yes | 0-100kW
202601-NM25-01150 | 6.317 | Residencial | Yes | 0-100kW
202601-NM25-01707 | 7.832 | Residencial | Yes | 0-100kW
202602-NM25-01978 | 3.245 | Residencial | Yes | 0-100kW
202602-NM25-01680 | 7.736 | Residencial | Yes | 0-100kW
202601-NM25-03319 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00998 | 18.09 | Residencial | Yes | 0-100kW
202603-NM25-01672 | 7.566 | Residencial | Yes | 0-100kW
202603-NM25-02489 | 8.972 | Residencial | Yes | 0-100kW
202602-NM25-01284 | 3.8 | Residencial | Yes | 0-100kW
202603-NM25-00104 | 9.292 | Residencial | Yes | 0-100kW
202512-NM25-03332 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01740 | 5.294 | Residencial | Yes | 0-100kW
202603-NM25-00635 | 4.608 | Residencial | Yes | 0-100kW
202603-NM25-02483 | 7.324 | Residencial | Yes | 0-100kW
202603-NM25-01891 | 11.44 | Residencial | Yes | 0-100kW
202602-NM25-00393 | 15 | Residencial | Yes | 0-100kW
202602-NM25-00987 | 8.304 | Residencial | Yes | 0-100kW
202603-NM25-01972 | 14.74 | Residencial | Yes | 0-100kW
202603-NM25-01980 | 15.16 | Residencial | Yes | 0-100kW
202602-NM25-00593 | 17.5 | Residencial | Yes | 0-100kW
202603-NM25-01391 | 11.346 | Residencial | Yes | 0-100kW
202601-NM25-02353 | 10.564 | Residencial | Yes | 0-100kW
202602-NM25-01138 | 4.026 | Residencial | Yes | 0-100kW
202601-NM25-00471 | 14 | Residencial | Yes | 0-100kW
202602-NM25-00821 | 4.826 | Residencial | Yes | 0-100kW
202602-NM25-00940 | 8.472 | Residencial | Yes | 0-100kW
202602-NM25-02493 | 23 | Residencial | Yes | 0-100kW
202509-NM25-05468 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04169 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-01597 | 6 | Residencial | Yes | 0-100kW
202512-NM25-02282 | 6.818 | Residencial | Yes | 0-100kW
202601-NM25-00203 | 4.72 | Residencial | Yes | 0-100kW
202603-NM25-02520 | 8.23 | Residencial | Yes | 0-100kW
202601-NM25-03297 | 23 | Residencial | Yes | 0-100kW
202512-NM25-02416 | 17.722 | Residencial | Yes | 0-100kW
202603-NM25-00447 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01783 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-02882 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02736 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02155 | 19.1 | Residencial | Yes | 0-100kW
202602-NM25-01753 | 5.222 | Residencial | Yes | 0-100kW
202510-NM25-02317 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01098 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01891 | 2.688 | Residencial | Yes | 0-100kW
202602-NM25-00391 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-02743 | 16.51 | Residencial | Yes | 0-100kW
202603-NM25-00384 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02936 | 16.5 | Residencial | Yes | 0-100kW
202603-NM25-00893 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01826 | 23 | Residencial | Yes | 0-100kW
202602-NM25-00837 | 8.932 | Residencial | Yes | 0-100kW
202510-NM25-01516 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00822 | 4.026 | Residencial | Yes | 0-100kW
202603-NM25-02490 | 9.036 | Residencial | Yes | 0-100kW
202602-NM25-02344 | 7.87 | Residencial | Yes | 0-100kW
202602-NM25-02254 | 17.4 | Residencial | Yes | 0-100kW
202601-NM25-02254 | 6.732 | Residencial | Yes | 0-100kW
202601-NM25-00441 | 17.5 | Residencial | Yes | 0-100kW
202511-NM25-00977 | 17.2 | Residencial | Yes | 0-100kW
202510-NM25-00202 | 15.3 | Residencial | Yes | 0-100kW
202601-NM25-02786 | 5.95 | Residencial | Yes | 0-100kW
202602-NM25-01907 | 9.136 | Residencial | Yes | 0-100kW
202602-NM25-00058 | 5 | Residencial | Yes | 0-100kW
202601-NM25-01261 | 5.076 | Residencial | Yes | 0-100kW
202601-NM25-01427 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00577 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01435 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-02245 | 10.812 | Residencial | Yes | 0-100kW
202601-NM25-00305 | 6.25 | Residencial | Yes | 0-100kW
202602-NM25-01715 | 8.598 | Residencial | Yes | 0-100kW
202601-NM25-00636 | 19.1 | Residencial | Yes | 0-100kW
202602-NM25-01231 | 7.072 | Residencial | Yes | 0-100kW
202603-NM25-02129 | 6.822 | Residencial | Yes | 0-100kW
202601-NM25-03302 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05567 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03514 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00208 | 8.052 | Residencial | Yes | 0-100kW
202603-NM25-01302 | 7.87 | Residencial | Yes | 0-100kW
202602-NM25-01060 | 9.562 | Residencial | Yes | 0-100kW
202601-NM25-03262 | 5.566 | Residencial | Yes | 0-100kW
202603-NM25-00093 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-01797 | 5.554 | Residencial | Yes | 0-100kW
202602-NM25-02207 | 9.15 | Residencial | Yes | 0-100kW
202603-NM25-01384 | 11.422 | Residencial | Yes | 0-100kW
202601-NM25-00882 | 16.81 | Residencial | Yes | 0-100kW
202601-NM25-02198 | 7.41 | Residencial | Yes | 0-100kW
202601-NM25-01155 | 7.102 | Residencial | Yes | 0-100kW
202602-NM25-01812 | 9.662 | Residencial | Yes | 0-100kW
202602-NM25-02396 | 9.552 | Residencial | Yes | 0-100kW
202603-NM25-00148 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00790 | 9.136 | Residencial | Yes | 0-100kW
202603-NM25-00461 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00069 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00049 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01986 | 6.572 | Residencial | Yes | 0-100kW
202601-NM25-01270 | 6.912 | Residencial | Yes | 0-100kW
202603-NM25-01466 | 10.04 | Residencial | Yes | 0-100kW
202603-NM25-00369 | 6.954 | Residencial | Yes | 0-100kW
202601-NM25-03071 | 13.6 | Residencial | Yes | 0-100kW
202601-NM25-00536 | 7.424 | Residencial | Yes | 0-100kW
202602-NM25-01532 | 5.76 | Residencial | Yes | 0-100kW
202601-NM25-02140 | 4.026 | Residencial | Yes | 0-100kW
202602-NM25-02836 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-05266 | 11.5 | Residencial | No | 0-100kW
202603-NM25-02131 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-03570 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-00569 | 5.926 | Residencial | Yes | 0-100kW
202602-NM25-00552 | 6.322 | Residencial | Yes | 0-100kW
202512-NM25-05884 | 11.99 | Residencial | Yes | 0-100kW
202602-NM25-02267 | 10.672 | Residencial | Yes | 0-100kW
202603-NM25-01506 | 7.87 | Residencial | Yes | 0-100kW
202602-NM25-01702 | 8.35 | Residencial | Yes | 0-100kW
202602-NM25-02423 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03615 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01916 | 6.142 | Residencial | Yes | 0-100kW
202601-NM25-03061 | 12.61 | Residencial | Yes | 0-100kW
202602-NM25-00795 | 5.536 | Residencial | Yes | 0-100kW
202602-NM25-02614 | 19.59 | Residencial | Yes | 0-100kW
202601-NM25-00396 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01280 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01140 | 11.44 | Residencial | Yes | 0-100kW
202602-NM25-00875 | 12.644 | Residencial | Yes | 0-100kW
202601-NM25-01202 | 6.902 | Residencial | Yes | 0-100kW
202603-NM25-02356 | 8.562 | Residencial | Yes | 0-100kW
202602-NM25-01195 | 9.7 | Residencial | Yes | 0-100kW
202602-NM25-02486 | 7.97 | Residencial | Yes | 0-100kW
202602-NM25-00493 | 8.09 | Residencial | Yes | 0-100kW
202603-NM25-01292 | 9.344 | Residencial | Yes | 0-100kW
202602-NM25-02603 | 10.672 | Residencial | Yes | 0-100kW
202601-NM25-03106 | 9.022 | Residencial | Yes | 0-100kW
202601-NM25-02934 | 9.586 | Comercial | Yes | 0-100kW
202601-NM25-02303 | 3.84 | Residencial | Yes | 0-100kW
202601-NM25-00127 | 9.072 | Residencial | Yes | 0-100kW
202601-NM25-01554 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00808 | 8.84 | Residencial | Yes | 0-100kW
202603-NM25-02086 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-01492 | 8.66 | Residencial | Yes | 0-100kW
202603-NM25-00501 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02013 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-02238 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02326 | 15.2 | Residencial | Yes | 0-100kW
202601-NM25-00756 | 15.416 | Residencial | Yes | 0-100kW
202603-NM25-00478 | 14.82 | Residencial | Yes | 0-100kW
202601-NM25-02597 | 13.144 | Residencial | Yes | 0-100kW
202506-NM25-03013 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00995 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04863 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-02113 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01453 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00696 | 7.09 | Residencial | Yes | 0-100kW
202602-NM25-01227 | 9.516 | Residencial | Yes | 0-100kW
202602-NM25-02359 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01501 | 7.6 | Comercial | Yes | 0-100kW
202602-NM25-02733 | 11.44 | Residencial | Yes | 0-100kW
202603-NM25-02432 | 19.1 | Residencial | Yes | 0-100kW
202603-NM25-00719 | 9.7 | Residencial | Yes | 0-100kW
202603-NM25-00372 | 5.124 | Residencial | Yes | 0-100kW
202601-NM25-03349 | 9.96 | Residencial | Yes | 0-100kW
202601-NM25-02512 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01713 | 5.836 | Residencial | Yes | 0-100kW
202602-NM25-00902 | 17.38 | Residencial | Yes | 0-100kW
202601-NM25-02477 | 15.2 | Residencial | Yes | 0-100kW
202603-NM25-01306 | 15.58 | Residencial | Yes | 0-100kW
202603-NM25-01082 | 15.72 | Residencial | Yes | 0-100kW
202603-NM25-00221 | 15.2 | Residencial | Yes | 0-100kW
202602-NM25-01405 | 15.04 | Residencial | Yes | 0-100kW
202602-NM25-01711 | 9.136 | Residencial | Yes | 0-100kW
202601-NM25-02520 | 9.136 | Residencial | Yes | 0-100kW
202511-NM25-03831 | 17.26 | Residencial | Yes | 0-100kW
202602-NM25-01404 | 7.87 | Residencial | Yes | 0-100kW
202601-NM25-03320 | 8.85 | Residencial | Yes | 0-100kW
202601-NM25-02402 | 6.584 | Residencial | Yes | 0-100kW
202603-NM25-02261 | 5.49 | Residencial | Yes | 0-100kW
202602-NM25-00207 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-00425 | 9.84 | Residencial | Yes | 0-100kW
202601-NM25-02948 | 11.346 | Residencial | Yes | 0-100kW
202602-NM25-01101 | 7.102 | Residencial | Yes | 0-100kW
202603-NM25-01610 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01257 | 3.84 | Residencial | Yes | 0-100kW
202602-NM25-00169 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00917 | 8.984 | Residencial | Yes | 0-100kW
202601-NM25-03009 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02105 | 15.16 | Residencial | Yes | 0-100kW
202602-NM25-02331 | 8.644 | Residencial | Yes | 0-100kW
202603-NM25-00449 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04644 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00968 | 17.2 | Residencial | Yes | 0-100kW
202602-NM25-01131 | 8.26 | Residencial | Yes | 0-100kW
202603-NM25-01974 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01041 | 5.076 | Residencial | Yes | 0-100kW
202601-NM25-00060 | 21.02 | Residencial | Yes | 0-100kW
202601-NM25-02018 | 14.16 | Residencial | Yes | 0-100kW
202602-NM25-00528 | 5.926 | Residencial | Yes | 0-100kW
202602-NM25-01264 | 5.076 | Residencial | Yes | 0-100kW
202602-NM25-01613 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00829 | 4.83 | Residencial | Yes | 0-100kW
202602-NM25-01758 | 6.612 | Residencial | Yes | 0-100kW
202602-NM25-01296 | 18.09 | Residencial | Yes | 0-100kW
202601-NM25-01295 | 4.236 | Residencial | Yes | 0-100kW
202602-NM25-02127 | 13.6 | Residencial | Yes | 0-100kW
202602-NM25-00836 | 9.344 | Residencial | Yes | 0-100kW
202603-NM25-00651 | 8.418 | Residencial | Yes | 0-100kW
202511-NM25-00788 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00630 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02168 | 24 | Residencial | Yes | 0-100kW
202602-NM25-00533 | 7.396 | Residencial | Yes | 0-100kW
202511-NM25-02783 | 15.8 | Residencial | Yes | 0-100kW
202602-NM25-01773 | 11.112 | Residencial | Yes | 0-100kW
202603-NM25-01908 | 4.758 | Residencial | Yes | 0-100kW
202512-NM25-02519 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01670 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-01636 | 15.28 | Residencial | Yes | 0-100kW
202601-NM25-02161 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02409 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-01748 | 4.536 | Residencial | Yes | 0-100kW
202602-NM25-02445 | 16.26 | Residencial | Yes | 0-100kW
202505-NM25-01396 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01383 | 10.608 | Residencial | Yes | 0-100kW
202601-NM25-01864 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03437 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-01056 | 10.924 | Residencial | Yes | 0-100kW
202512-NM25-00215 | 17.5 | Residencial | Yes | 0-100kW
202601-NM25-03129 | 19.1 | Residencial | Yes | 0-100kW
202602-NM25-02490 | 7.87 | Residencial | Yes | 0-100kW
202601-NM25-00664 | 5.076 | Residencial | Yes | 0-100kW
202602-NM25-01033 | 9.136 | Residencial | Yes | 0-100kW
202602-NM25-00646 | 6.656 | Residencial | Yes | 0-100kW
202603-NM25-01469 | 15.34 | Residencial | Yes | 0-100kW
202603-NM25-00878 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02521 | 9.52 | Residencial | Yes | 0-100kW
202603-NM25-00163 | 5.366 | Residencial | Yes | 0-100kW
202602-NM25-02873 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-02587 | 11.26 | Residencial | Yes | 0-100kW
202601-NM25-02344 | 5.076 | Residencial | Yes | 0-100kW
202602-NM25-02027 | 10.43 | Residencial | Yes | 0-100kW
202602-NM25-01256 | 10.672 | Residencial | Yes | 0-100kW
202601-NM25-02995 | 9.136 | Residencial | Yes | 0-100kW
202602-NM25-01625 | 6.296 | Residencial | Yes | 0-100kW
202602-NM25-02854 | 7.462 | Residencial | Yes | 0-100kW
202601-NM25-00132 | 6.872 | Residencial | Yes | 0-100kW
202602-NM25-01614 | 8.562 | Residencial | Yes | 0-100kW
202602-NM25-01130 | 6.902 | Residencial | Yes | 0-100kW
202601-NM25-01169 | 5.566 | Residencial | Yes | 0-100kW
202602-NM25-02463 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02921 | 6.362 | Residencial | Yes | 0-100kW
202511-NM25-02785 | 13.824 | Residencial | Yes | 0-100kW
202602-NM25-00635 | 6.14 | Residencial | Yes | 0-100kW
202602-NM25-01858 | 16.5 | Residencial | Yes | 0-100kW
202601-NM25-00845 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-03234 | 7.67 | Residencial | Yes | 0-100kW
202601-NM25-03431 | 7.102 | Residencial | Yes | 0-100kW
202603-NM25-00339 | 10.858 | Residencial | Yes | 0-100kW
202601-NM25-02359 | 7.756 | Residencial | Yes | 0-100kW
202601-NM25-01649 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00586 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-00825 | 19.1 | Residencial | Yes | 0-100kW
202601-NM25-03324 | 5.566 | Residencial | Yes | 0-100kW
202603-NM25-02205 | 9.136 | Residencial | Yes | 0-100kW
202603-NM25-02147 | 3.54 | Residencial | Yes | 0-100kW
202603-NM25-00442 | 5.956 | Residencial | Yes | 0-100kW
202602-NM25-02276 | 7.87 | Residencial | Yes | 0-100kW
202603-NM25-00071 | 10.022 | Residencial | Yes | 0-100kW
202601-NM25-02824 | 11.5 | Residencial | No | 0-100kW
202601-NM25-00600 | 5.562 | Residencial | Yes | 0-100kW
202601-NM25-02798 | 4.786 | Residencial | Yes | 0-100kW
202602-NM25-02477 | 16.06 | Residencial | Yes | 0-100kW
202603-NM25-01587 | 5.176 | Residencial | Yes | 0-100kW
202602-NM25-00975 | 6.256 | Residencial | Yes | 0-100kW
202601-NM25-03004 | 9.394 | Residencial | Yes | 0-100kW
202603-NM25-00307 | 11.96 | Residencial | Yes | 0-100kW
202512-NM25-02548 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01170 | 8.972 | Residencial | Yes | 0-100kW
202512-NM25-04173 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-02011 | 5.17 | Residencial | Yes | 0-100kW
202512-NM25-03464 | 15.16 | Residencial | Yes | 0-100kW
202601-NM25-02665 | 5.76 | Residencial | Yes | 0-100kW
202602-NM25-01038 | 7.974 | Residencial | Yes | 0-100kW
202601-NM25-02971 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-01804 | 14.99 | Residencial | Yes | 0-100kW
202602-NM25-02753 | 14.512 | Residencial | Yes | 0-100kW
202602-NM25-01115 | 12.288 | Comercial | Yes | 0-100kW
202603-NM25-00882 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-00641 | 6.296 | Residencial | Yes | 0-100kW
202506-NM25-00763 | 23 | Comercial | Yes | 0-100kW
202602-NM25-00376 | 5.566 | Residencial | Yes | 0-100kW
202601-NM25-00541 | 6.68 | Residencial | Yes | 0-100kW
202603-NM25-01084 | 8.254 | Residencial | Yes | 0-100kW
202603-NM25-01052 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00335 | 8.23 | Residencial | Yes | 0-100kW
202602-NM25-01113 | 7.202 | Residencial | Yes | 0-100kW
202603-NM25-01340 | 8.84 | Residencial | Yes | 0-100kW
202602-NM25-01408 | 9.714 | Residencial | Yes | 0-100kW
202601-NM25-02220 | 3 | Residencial | Yes | 0-100kW
202603-NM25-02062 | 5.076 | Residencial | Yes | 0-100kW
202601-NM25-00233 | 16.5 | Residencial | Yes | 0-100kW
202602-NM25-01918 | 3.66 | Residencial | Yes | 0-100kW
202601-NM25-02370 | 10.98 | Residencial | Yes | 0-100kW
202602-NM25-02755 | 15.89 | Residencial | Yes | 0-100kW
202509-NM25-02840 | 23 | Residencial | Yes | 0-100kW
202603-NM25-00087 | 15.2 | Residencial | Yes | 0-100kW
202601-NM25-00561 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02718 | 21.956 | Residencial | Yes | 0-100kW
202601-NM25-00059 | 8.448 | Residencial | Yes | 0-100kW
202601-NM25-03052 | 7.102 | Residencial | Yes | 0-100kW
202601-NM25-00199 | 5.956 | Residencial | Yes | 0-100kW
202601-NM25-01394 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02367 | 19.1 | Residencial | Yes | 0-100kW
202603-NM25-01351 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01200 | 5.666 | Residencial | Yes | 0-100kW
202601-NM25-01209 | 11.492 | Residencial | Yes | 0-100kW
202601-NM25-02517 | 13.804 | Residencial | Yes | 0-100kW
202602-NM25-02640 | 11.98 | Residencial | Yes | 0-100kW
202511-NM25-00667 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02032 | 19.1 | Residencial | Yes | 0-100kW
202603-NM25-00253 | 6.612 | Residencial | Yes | 0-100kW
202601-NM25-01402 | 18.67 | Residencial | Yes | 0-100kW
202510-NM25-04017 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-02974 | 19.1 | Residencial | Yes | 0-100kW
202506-NM25-04303 | 5 | Residencial | Yes | 0-100kW
202601-NM25-01653 | 5.494 | Residencial | Yes | 0-100kW
202601-NM25-01200 | 5.015 | Residencial | Yes | 0-100kW
202603-NM25-00091 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00360 | 23 | Residencial | Yes | 0-100kW
202601-NM25-01190 | 7.072 | Residencial | Yes | 0-100kW
202601-NM25-02338 | 7.134 | Residencial | Yes | 0-100kW
202603-NM25-00192 | 6.588 | Residencial | Yes | 0-100kW
202602-NM25-01043 | 11.44 | Residencial | Yes | 0-100kW
202603-NM25-01968 | 10.79 | Residencial | Yes | 0-100kW
202508-NM25-05010 | 7.6 | Residencial | Yes | 0-100kW
202602-NM25-02638 | 9 | Residencial | Yes | 0-100kW
202601-NM25-02646 | 11.44 | Residencial | Yes | 0-100kW
202601-NM25-02411 | 8.23 | Residencial | Yes | 0-100kW
202510-NM25-02646 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-03148 | 23 | Residencial | Yes | 0-100kW
202602-NM25-01349 | 13.44 | Residencial | Yes | 0-100kW
202603-NM25-00085 | 7.6 | Residencial | Yes | 0-100kW
2026-GD-00021 | 42.63 | Comercial | Yes | 0-100kW
202601-NM25-00885 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-04130 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02465 | 15.2 | Residencial | Yes | 0-100kW
202601-NM25-01321 | 7.866 | Residencial | Yes | 0-100kW
202602-NM25-00834 | 7.202 | Residencial | Yes | 0-100kW
202512-NM25-02485 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-00931 | 5.961 | Residencial | Yes | 0-100kW
202507-NM25-03949 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05175 | 12 | Residencial | Yes | 0-100kW
202601-NM25-01892 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00701 | 6 | Residencial | Yes | 0-100kW
202603-NM25-00474 | 7.64 | Residencial | Yes | 0-100kW
202603-NM25-02286 | 8.25 | Residencial | Yes | 0-100kW
202602-NM25-01639 | 9.136 | Residencial | Yes | 0-100kW
202601-NM25-00875 | 16.22 | Residencial | Yes | 0-100kW
202603-NM25-00699 | 8.382 | Residencial | Yes | 0-100kW
202602-NM25-00627 | 3.835 | Residencial | Yes | 0-100kW
202601-NM25-00325 | 6.296 | Residencial | Yes | 0-100kW
202602-NM25-01584 | 6.79 | Residencial | Yes | 0-100kW
202601-NM25-02835 | 6.532 | Residencial | Yes | 0-100kW
202602-NM25-01710 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-04598 | 19.1 | Residencial | Yes | 0-100kW
202512-NM25-03310 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01229 | 10.928 | Residencial | Yes | 0-100kW
202601-NM25-02420 | 8.562 | Residencial | Yes | 0-100kW
202601-NM25-00594 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02494 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-05512 | 15.3 | Residencial | Yes | 0-100kW
202602-NM25-00351 | 9.456 | Residencial | Yes | 0-100kW
202601-NM25-01179 | 9.904 | Residencial | Yes | 0-100kW
202601-NM25-02935 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-01528 | 7.6 | Residencial | Yes | 0-100kW
202603-NM25-00460 | 8.56 | Residencial | Yes | 0-100kW
202602-NM25-01660 | 11.5 | Residencial | Yes | 0-100kW
202603-NM25-02049 | 13.072 | Residencial | Yes | 0-100kW
202602-NM25-01930 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00668 | 11.582 | Residencial | Yes | 0-100kW
202511-NM25-03083 | 23 | Residencial | Yes | 0-100kW
202512-NM25-04606 | 11.5 | Residencial | Yes | 0-100kW
202601-NM25-02906 | 4.72 | Residencial | Yes | 0-100kW
202601-NM25-02814 | 5.196 | Residencial | Yes | 0-100kW
202602-NM25-01699 | 13.036 | Residencial | Yes | 0-100kW
202601-NM25-02775 | 11.5 | Residencial | Yes | 0-100kW
202602-NM25-00582 | 10.85 | Residencial | Yes | 0-100kW
202601-NM25-00787 | 9.752 | Residencial | Yes | 0-100kW
202602-NM25-00609 | 3.8 | Residencial | Yes | 0-100kW
202601-NM25-00771 | 11.44 | Residencial | Yes | 0-100kW
202602-NM25-00771 | 7.6 | Residencial | Yes | 0-100kW
202601-NM25-02796 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02968 | 17.2 | Residencial | Yes | 0-100kW
202510-NM25-02175 | 6 | Residencial | Yes | 0-100kW
202601-NM25-03413 | 7.146 | Residencial | Yes | 0-100kW
202601-NM25-02328 | 12.258 | Residencial | Yes | 0-100kW
202602-NM25-02674 | 5.856 | Residencial | Yes | 0-100kW
202601-NM25-03296 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03972 | 23 | Residencial | Yes | 0-100kW
202602-NM25-02551 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-02054 | 5 | Residencial | No | 0-100kW
2019-GD-01829 | 3 | Residencial | Yes | 0-100kW
202512-NM25-05700 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00456 | 8 | Residencial | Yes | 0-100kW
2022-GD-24411 | 7.08 | Residencial | Yes | 0-100kW
16-2-0426 | 4.51 | Residencial | Yes | 0-100kW
202502-NM25-02065 | 8 | Residencial | Yes | 0-100kW
202505-NM25-04476 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-12419 | 5.76 | Residencial | Yes | 0-100kW
202504-NM25-06082 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-11706 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-15960 | 4.03 | Residencial | Yes | 0-100kW
202503-NM25-00446 | 7.6 | Residencial | Yes | 0-100kW
202309-NM25-00157 | 9.25 | Residencial | Yes | 0-100kW
2023-GD-31438 | 3.8 | Residencial | Yes | 0-100kW
15-7-812 | 3.22 | Residencial | Yes | 0-100kW
202504-NM25-05375 | 4.608 | Residencial | Yes | 0-100kW
16-5-0265A | 3.01 | Residencial | Yes | 0-100kW
202504-NM25-05679 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-39420 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28238 | 10 | Residencial | Yes | 0-100kW
2023-GD-25746 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-01737 | 8 | Residencial | Yes | 0-100kW
2022-GD-14620 | 2.07 | Residencial | Yes | 0-100kW
202403-NM25-01078 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-30080 | 5 | Residencial | Yes | 0-100kW
2022-GD-25641 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-03517 | 15 | Residencial | Yes | 0-100kW
2023-GD-32250 | 6 | Residencial | Yes | 0-100kW
202508-NM25-03423 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-06520 | 4.76 | Residencial | Yes | 0-100kW
202502-NM25-05481 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-00541 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-35696 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03947 | 8 | Residencial | Yes | 0-100kW
202402-NM25-03236 | 2.304 | Residencial | Yes | 0-100kW
202511-NM25-04369 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34535 | 2.93 | Residencial | Yes | 0-100kW
202502-NM25-02794 | 11.5 | Residencial | Yes | 0-100kW
202311-NM25-00920 | 3.66 | Residencial | Yes | 0-100kW
202407-NM25-02389 | 4.224 | Residencial | Yes | 0-100kW
2023-GD-24866 | 3.8 | Residencial | Yes | 0-100kW
202405-NM25-00703 | 11.26 | Residencial | Yes | 0-100kW
2023-GD-11497 | 3.3 | Residencial | Yes | 0-100kW
2022-GD-24538 | 8.85 | Comercial | Yes | 0-100kW
2023-GD-14562 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-04425 | 4.43 | Residencial | Yes | 0-100kW
2021-GD-03943 | 3.54 | Residencial | Yes | 0-100kW
202501-NM25-02738 | 7.6 | Residencial | Yes | 0-100kW
16-2-0625 | 5.8 | Residencial | Yes | 0-100kW
202409-NM25-00423 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02003 | 6.8 | Residencial | Yes | 0-100kW
202510-NM25-00467 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-07407 | 3.8 | Residencial | Yes | 0-100kW
202501-NM25-03273 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-04272 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-05153 | 2.928 | Residencial | Yes | 0-100kW
2023-GD-23424 | 9.6 | Residencial | Yes | 0-100kW
2022-GD-25044 | 3.6 | Residencial | Yes | 0-100kW
202503-NM25-02212 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-11246 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04327 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02458 | 8 | Residencial | Yes | 0-100kW
202507-NM25-02429 | 3.456 | Residencial | Yes | 0-100kW
2021-GD-11667 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-00737 | 15.2 | Residencial | Yes | 0-100kW
202505-NM25-02891 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-03928 | 10 | Residencial | Yes | 0-100kW
2021-GD-06955 | 3.24 | Residencial | Yes | 0-100kW
202502-NM25-05774 | 11.26 | Residencial | Yes | 0-100kW
202505-NM25-00010 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-35338 | 8.45 | Residencial | Yes | 0-100kW
202411-NM25-02647 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05980 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-32222 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-00361 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-01824 | 4 | Residencial | Yes | 0-100kW
202404-NM25-01586 | 6.954 | Residencial | Yes | 0-100kW
202508-NM25-01429 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-13869 | 3.54 | Residencial | Yes | 0-100kW
202508-NM25-03530 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-04010 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-03191 | 46.08 | Comercial | No | 0-100kW
202411-NM25-01365 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22561 | 15 | Residencial | Yes | 0-100kW
2021-GD-02676 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-02739 | 6 | Residencial | Yes | 0-100kW
2020-GD-02217 | 7.15 | Residencial | Yes | 0-100kW
202406-NM25-02560 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-08438 | 7.67 | Residencial | Yes | 0-100kW
202312-NM25-03181 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01804 | 8 | Residencial | Yes | 0-100kW
2022-GD-10500 | 4.03 | Residencial | Yes | 0-100kW
202510-NM25-00405 | 24 | Residencial | Yes | 0-100kW
2023-GD-20824 | 7.6 | Residencial | No | 0-100kW
202509-NM25-05977 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-22867 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-02995 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-19992 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06262 | 7.67 | Residencial | Yes | 0-100kW
2022-GD-10384 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-07439 | 2.95 | Residencial | Yes | 0-100kW
2023-GD-29819 | 13.6 | Comercial | Yes | 0-100kW
08-3-231 | 4 | Residencial | Yes | 0-100kW
2023-GD-03251 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-05366 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-32610 | 6.95 | Residencial | Yes | 0-100kW
2022-GD-11278 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-06765 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-22048 | 4.03 | Residencial | Yes | 0-100kW
202508-NM25-01927 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-02413 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-03485 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21096 | 5 | Residencial | Yes | 0-100kW
202412-NM25-03832 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-05433 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-28568 | 4.15 | Residencial | Yes | 0-100kW
2022-GD-28363 | 12.29 | Residencial | Yes | 0-100kW
202401-NM25-01004 | 5.376 | Residencial | Yes | 0-100kW
2023-GD-39185 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02349 | 5 | Residencial | Yes | 0-100kW
202504-NM25-00692 | 8.052 | Residencial | Yes | 0-100kW
2023-GD-30738 | 4.29 | Residencial | Yes | 0-100kW
202505-NM25-04053 | 13.36 | Residencial | Yes | 0-100kW
16-5-0594A | 4.73 | Residencial | Yes | 0-100kW
202403-NM25-03304 | 3.66 | Residencial | Yes | 0-100kW
202512-NM25-01697 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02672 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-32398 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-00485 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-04671 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04980 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-05018 | 7.7 | Residencial | Yes | 0-100kW
2022-GD-17832 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-26632 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-03626 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-26090 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-13916 | 3.84 | Residencial | Yes | 0-100kW
16-2-0843 | 6.45 | Residencial | Yes | 0-100kW
2021-GD-04516 | 12.1 | Residencial | Yes | 0-100kW
202512-NM25-01884 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-05319 | 4.39 | Residencial | Yes | 0-100kW
202403-NM25-01567 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01080 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-13507 | 6.8 | Residencial | Yes | 0-100kW
202504-NM25-02019 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14454 | 9.15 | Residencial | Yes | 0-100kW
202509-NM25-01634 | 7.68 | Residencial | Yes | 0-100kW
202501-NM25-03495 | 8.418 | Residencial | Yes | 0-100kW
2020-GD-05960 | 6.8 | Residencial | Yes | 0-100kW
202505-NM25-05312 | 3.8 | Residencial | Yes | 0-100kW
202506-NM25-01842 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00022 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00708 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-11941 | 3.8 | Residencial | No | 0-100kW
202407-NM25-03189 | 5.28 | Residencial | Yes | 0-100kW
2023-GD-22788 | 8 | Residencial | Yes | 0-100kW
202412-NM25-02487 | 6.588 | Residencial | Yes | 0-100kW
202401-NM25-03433 | 5 | Residencial | Yes | 0-100kW
202407-NM25-00502 | 7.32 | Residencial | Yes | 0-100kW
202509-NM25-04237 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-09186 | 6.59 | Residencial | Yes | 0-100kW
202403-NM25-01005 | 15.2 | Residencial | Yes | 0-100kW
2020-GD-08225 | 6.78 | Residencial | Yes | 0-100kW
202511-NM25-00138 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-00400 | 4.39 | Residencial | Yes | 0-100kW
202312-NM25-03486 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-30912 | 5 | Residencial | Yes | 0-100kW
202409-NM25-02081 | 10 | Residencial | Yes | 0-100kW
202505-NM25-00135 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00045 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-00158 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25359 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-01016 | 3.84 | Residencial | Yes | 0-100kW
202503-NM25-03519 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-01488 | 10.248 | Residencial | Yes | 0-100kW
202501-NM25-02284 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-17659 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04245 | 10 | Residencial | Yes | 0-100kW
2023-GD-01557 | 5 | Residencial | Yes | 0-100kW
2022-GD-09932 | 5.12 | Residencial | Yes | 0-100kW
202406-NM25-00825 | 6 | Residencial | Yes | 0-100kW
202505-NM25-02084 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-00219 | 11.136 | Residencial | Yes | 0-100kW
202506-NM25-03533 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10421 | 9.6 | Residencial | Yes | 0-100kW
2021-GD-02164 | 4 | Residencial | Yes | 0-100kW
2023-GD-14918 | 5 | Residencial | Yes | 0-100kW
202411-NM25-02554 | 2.304 | Residencial | Yes | 0-100kW
2023-GD-11114 | 6 | Residencial | Yes | 0-100kW
2020-GD-03069 | 3.245 | Residencial | Yes | 0-100kW
2023-GD-17613 | 8 | Residencial | Yes | 0-100kW
2022-GD-30202 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-11807 | 3.54 | Residencial | Yes | 0-100kW
202507-NM25-02767 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14491 | 5.49 | Residencial | Yes | 0-100kW
202404-NM25-02554 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01171 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00085 | 5.76 | Residencial | Yes | 0-100kW
202505-NM25-00657 | 7.562 | Residencial | Yes | 0-100kW
202507-NM25-01924 | 4.224 | Residencial | Yes | 0-100kW
2020-GD-05765 | 6.91 | Residencial | Yes | 0-100kW
202504-NM25-00473 | 8.832 | Residencial | Yes | 0-100kW
2023-GD-06206 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-20960 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22297 | 6.22 | Residencial | Yes | 0-100kW
2023-GD-37485 | 3.66 | Residencial | Yes | 0-100kW
202404-NM25-04521 | 2.562 | Residencial | Yes | 0-100kW
202310-NM25-00450 | 3.66 | Residencial | Yes | 0-100kW
14-7-243 | 7.2 | Residencial | Yes | 0-100kW
202503-NM25-02454 | 6.912 | Residencial | Yes | 0-100kW
2019-GD-00490 | 5.31 | Residencial | Yes | 0-100kW
2020-GD-01826 | 13.6 | Residencial | Yes | 0-100kW
202512-NM25-03930 | 11.4 | Residencial | Yes | 0-100kW
202501-NM25-01835 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-00497 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-03448 | 6.588 | Residencial | Yes | 0-100kW
2020-GD-08013 | 5 | Residencial | Yes | 0-100kW
2023-GD-00182 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-02885 | 15 | Comercial | Yes | 0-100kW
202408-NM25-05042 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29191 | 6 | Residencial | Yes | 0-100kW
2023-GD-08394 | 3.84 | Residencial | Yes | 0-100kW
202502-NM25-02982 | 12.078 | Residencial | Yes | 0-100kW
2022-GD-00243 | 8.42 | Residencial | Yes | 0-100kW
202505-NM25-02855 | 10.368 | Residencial | Yes | 0-100kW
202410-NM25-02892 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-04663 | 6.588 | Residencial | No | 0-100kW
202410-NM25-03578 | 15 | Residencial | Yes | 0-100kW
202505-NM25-03050 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-28248 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-27949 | 11.35 | Residencial | Yes | 0-100kW
2023-GD-10740 | 4.61 | Residencial | Yes | 0-100kW
2023-GD-34418 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-06165 | 8 | Residencial | Yes | 0-100kW
202401-NM25-01229 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08398 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-29940 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04302 | 7.32 | Residencial | Yes | 0-100kW
202506-NM25-02413 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20007 | 8.78 | Residencial | Yes | 0-100kW
202405-NM25-03504 | 12.6 | Residencial | Yes | 0-100kW
202410-NM25-01082 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-10085 | 9.6 | Residencial | Yes | 0-100kW
202503-NM25-04719 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03552 | 8 | Residencial | Yes | 0-100kW
2019-GD-02262 | 8.78 | Residencial | Yes | 0-100kW
2021-GD-08097 | 3 | Residencial | Yes | 0-100kW
202511-NM25-00938 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-19348 | 9.6 | Residencial | Yes | 0-100kW
202401-NM25-03013 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03270 | 4.5 | Residencial | Yes | 0-100kW
2022-GD-11075 | 6 | Residencial | Yes | 0-100kW
2021-GD-10703 | 5.9 | Residencial | Yes | 0-100kW
202406-NM25-00041 | 7.6 | Residencial | Yes | 0-100kW
16-3-211 | 3.87 | Residencial | Yes | 0-100kW
202405-NM25-02172 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-08354 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-06082 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-04817 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-26923 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-03338 | 6.195 | Residencial | Yes | 0-100kW
202407-NM25-01185 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21683 | 5.49 | Residencial | Yes | 0-100kW
202504-NM25-06173 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-09117 | 2.93 | Residencial | Yes | 0-100kW
2022-GD-01021 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-01907 | 4.76 | Residencial | Yes | 0-100kW
2020-GD-02436 | 12 | Residencial | Yes | 0-100kW
2021-GD-02791 | 6.49 | Residencial | Yes | 0-100kW
14-6-0436 | 2.79 | Residencial | Yes | 0-100kW
2023-GD-04099 | 8.42 | Residencial | Yes | 0-100kW
2021-GD-05553 | 3.75 | Residencial | Yes | 0-100kW
2020-GD-08704 | 10 | Residencial | Yes | 0-100kW
2022-GD-07290 | 6.8 | Residencial | Yes | 0-100kW
2019-GD-02826 | 8.35 | Residencial | Yes | 0-100kW
202402-NM25-03504 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-25913 | 13.6 | Comercial | Yes | 0-100kW
2022-GD-10725 | 3.66 | Residencial | Yes | 0-100kW
202401-NM25-03203 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-00521 | 8 | Residencial | Yes | 0-100kW
2023-GD-20446 | 5 | Residencial | Yes | 0-100kW
202404-NM25-02096 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-02166 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03803 | 7.6 | Comercial | Yes | 0-100kW
2022-GD-10871 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-13150 | 5 | Residencial | Yes | 0-100kW
202509-NM25-04951 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-37393 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-03255 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-10209 | 4.39 | Residencial | Yes | 0-100kW
202406-NM25-01874 | 4.608 | Residencial | Yes | 0-100kW
2022-GD-22246 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-30342 | 9.15 | Residencial | Yes | 0-100kW
202402-NM25-04069 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-02160 | 10.614 | Residencial | Yes | 0-100kW
2022-GD-10572 | 8.78 | Residencial | Yes | 0-100kW
202501-NM25-02681 | 23 | Residencial | Yes | 0-100kW
202406-NM25-01733 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-03866 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-03254 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07936 | 5.01 | Residencial | Yes | 0-100kW
14-7-470 | 5 | Residencial | Yes | 0-100kW
202403-NM25-03899 | 9 | Residencial | Yes | 0-100kW
2021-GD-04229 | 6.8 | Residencial | Yes | 0-100kW
202406-NM25-00339 | 9.064 | Residencial | Yes | 0-100kW
2023-GD-01308 | 4.03 | Residencial | Yes | 0-100kW
202502-NM25-03229 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28815 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-37235 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-00805 | 20 | Residencial | Yes | 0-100kW
2022-GD-12681 | 4.76 | Residencial | Yes | 0-100kW
15-7-1042 | 6 | Comercial | Yes | 0-100kW
2022-GD-13868 | 4.03 | Residencial | Yes | 0-100kW
16-3-078 | 6.88 | Residencial | Yes | 0-100kW
202511-NM25-03282 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03407 | 14.64 | Residencial | Yes | 0-100kW
16-7-1152 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11644 | 4.03 | Residencial | Yes | 0-100kW
202409-NM25-01287 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-05824 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27220 | 8.78 | Residencial | Yes | 0-100kW
2022-GD-09659 | 6.95 | Residencial | Yes | 0-100kW
202511-NM25-00172 | 3.84 | Residencial | Yes | 0-100kW
2017-GD-03777 | 3.655 | Residencial | Yes | 0-100kW
2022-GD-04203 | 6 | Residencial | Yes | 0-100kW
202507-NM25-02138 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03960 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12244 | 2.95 | Residencial | Yes | 0-100kW
202506-NM25-02462 | 6.912 | Residencial | Yes | 0-100kW
2022-GD-05527 | 5.49 | Residencial | Yes | 0-100kW
202509-NM25-00734 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-31925 | 7.6 | Residencial | No | 0-100kW
202407-NM25-03635 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-27268 | 3.6 | Residencial | Yes | 0-100kW
2023-GD-12209 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-03448 | 6.588 | Residencial | Yes | 0-100kW
2023-GD-19650 | 3.8 | Residencial | Yes | 0-100kW
202402-NM25-02199 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04733 | 5.9 | Comercial | Yes | 0-100kW
2022-GD-24866 | 4.03 | Residencial | Yes | 0-100kW
202512-NM25-06032 | 4.466 | Residencial | Yes | 0-100kW
2022-GD-32036 | 16.13 | Residencial | Yes | 0-100kW
13-5-0071A | 15 | Agricultural | Yes | 0-100kW
2023-GD-04256 | 8.45 | Residencial | Yes | 0-100kW
202501-NM25-05607 | 5.76 | Residencial | Yes | 0-100kW
202410-NM25-01793 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-01269 | 5 | Residencial | Yes | 0-100kW
2021-GD-12568 | 3.54 | Residencial | Yes | 0-100kW
2020-GD-04572 | 5.86 | Residencial | Yes | 0-100kW
14-6-0187 | 6.5 | Residencial | Yes | 0-100kW
202406-NM25-01044 | 7.6 | Residencial | No | 0-100kW
202505-NM25-04639 | 3.072 | Residencial | Yes | 0-100kW
2023-GD-30577 | 8 | Residencial | Yes | 0-100kW
2023-GD-09094 | 15.2 | Residencial | Yes | 0-100kW
2019-GD-00521 | 3.835 | Residencial | Yes | 0-100kW
202503-NM25-01627 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-04280 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01769 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-00922 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04430 | 9 | Residencial | Yes | 0-100kW
2023-GD-30560 | 8 | Residencial | Yes | 0-100kW
2020-GD-03339 | 7.375 | Residencial | Yes | 0-100kW
2022-GD-29632 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-01673 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-00870 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04098 | 8 | Residencial | Yes | 0-100kW
202410-NM25-00156 | 6.912 | Residencial | Yes | 0-100kW
16-3-513 | 4.09 | Residencial | Yes | 0-100kW
2023-GD-17954 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06865 | 16.47 | Residencial | Yes | 0-100kW
2023-GD-33880 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-17681 | 3.29 | Residencial | Yes | 0-100kW
2022-GD-29221 | 6.59 | Residencial | Yes | 0-100kW
2022-GD-00693 | 3.54 | Residencial | Yes | 0-100kW
202507-NM25-02362 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-00483 | 7.7 | Residencial | Yes | 0-100kW
202507-NM25-04052 | 15 | Residencial | Yes | 0-100kW
2022-GD-31835 | 4.75 | Residencial | Yes | 0-100kW
2022-GD-10610 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-03457 | 5.86 | Residencial | Yes | 0-100kW
202501-NM25-01603 | 2.928 | Residencial | Yes | 0-100kW
202311-NM25-00172 | 4.026 | Residencial | Yes | 0-100kW
2021-GD-01360 | 4.13 | Residencial | Yes | 0-100kW
2022-GD-12415 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-10767 | 9.6 | Residencial | Yes | 0-100kW
202406-NM25-03531 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18422 | 4.03 | Residencial | Yes | 0-100kW
202404-NM25-01780 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-12002 | 5 | Residencial | Yes | 0-100kW
16-3-775 | 3.23 | Residencial | Yes | 0-100kW
2022-GD-24566 | 3.54 | Comercial | Yes | 0-100kW
202406-NM25-01172 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-10432 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01725 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-25734 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31555 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-24590 | 8 | Residencial | Yes | 0-100kW
202402-NM25-02572 | 3.8 | Residencial | Yes | 0-100kW
202402-NM25-03249 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-07297 | 3.24 | Residencial | Yes | 0-100kW
202401-NM25-03204 | 8.448 | Residencial | Yes | 0-100kW
202312-NM25-00012 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19651 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-31612 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-30101 | 5.49 | Residencial | Yes | 0-100kW
202505-NM25-05323 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-16510 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02233 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-34687 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04093 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36211 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04502 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04941 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-37308 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-13067 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-01986 | 5.31 | Residencial | Yes | 0-100kW
202406-NM25-00451 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-03121 | 3.072 | Residencial | Yes | 0-100kW
202408-NM25-00582 | 4.608 | Residencial | Yes | 0-100kW
202509-NM25-00503 | 7.68 | Residencial | Yes | 0-100kW
202401-NM25-03351 | 8.418 | Residencial | Yes | 0-100kW
202504-NM25-04320 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-18638 | 2.66 | Residencial | Yes | 0-100kW
2023-GD-06540 | 15.2 | Residencial | Yes | 0-100kW
202404-NM25-03402 | 5.49 | Residencial | Yes | 0-100kW
2021-GD-08858 | 5.5 | Comercial | Yes | 0-100kW
202409-NM25-03405 | 15.2 | Residencial | Yes | 0-100kW
202408-NM25-03291 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01303 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-05156 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00591 | 8 | Residencial | Yes | 0-100kW
202503-NM25-04683 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-22961 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-13863 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-02314 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-01629 | 5.376 | Residencial | Yes | 0-100kW
2022-GD-32799 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-23826 | 5.9 | Residencial | Yes | 0-100kW
2022-GD-30029 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-00506 | 3.54 | Residencial | Yes | 0-100kW
202503-NM25-00765 | 7.6 | Residencial | Yes | 0-100kW
202311-NM25-00036 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-24161 | 5 | Residencial | Yes | 0-100kW
202412-NM25-01632 | 3.66 | Residencial | Yes | 0-100kW
16-3-428 | 2.58 | Residencial | Yes | 0-100kW
2022-GD-32605 | 15 | Residencial | Yes | 0-100kW
2021-GD-03928 | 7.67 | Residencial | Yes | 0-100kW
2023-GD-17647 | 3.8 | Residencial | No | 0-100kW
2021-GD-06950 | 3.24 | Residencial | Yes | 0-100kW
202509-NM25-05398 | 8.784 | Residencial | Yes | 0-100kW
2022-GD-29631 | 4.39 | Residencial | Yes | 0-100kW
202504-NM25-02271 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-05976 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-33134 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-00312 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-13740 | 18 | Residencial | Yes | 0-100kW
2020-GD-02784 | 4.72 | Residencial | Yes | 0-100kW
202506-NM25-04483 | 8 | Residencial | Yes | 0-100kW
202509-NM25-01862 | 4.224 | Residencial | Yes | 0-100kW
2022-GD-28323 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-03752 | 3.5 | Residencial | Yes | 0-100kW
2022-GD-24811 | 5.01 | Residencial | Yes | 0-100kW
2022-GD-20341 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-08392 | 6.95 | Residencial | Yes | 0-100kW
202501-NM25-02085 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04936 | 8.56 | Residencial | Yes | 0-100kW
2022-GD-05874 | 7.67 | Residencial | Yes | 0-100kW
2022-GD-01002 | 4.72 | Residencial | Yes | 0-100kW
202407-NM25-04489 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-02695 | 2.928 | Residencial | Yes | 0-100kW
2023-GD-12219 | 7.26 | Residencial | Yes | 0-100kW
202407-NM25-01752 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00774 | 6.528 | Residencial | Yes | 0-100kW
2022-GD-24210 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-01809 | 9.6 | Residencial | Yes | 0-100kW
202405-NM25-02230 | 8 | Residencial | Yes | 0-100kW
2023-GD-09154 | 6.9 | Residencial | Yes | 0-100kW
2020-GD-01498 | 3.54 | Residencial | Yes | 0-100kW
202406-NM25-00439 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03517 | 15 | Residencial | Yes | 0-100kW
2021-GD-13976 | 20.4 | Comercial | Yes | 0-100kW
2021-GD-00444 | 3.84 | Residencial | Yes | 0-100kW
202503-NM25-00266 | 15.1 | Residencial | Yes | 0-100kW
202409-NM25-03634 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14369 | 10 | Residencial | Yes | 0-100kW
202403-NM25-00605 | 9 | Residencial | Yes | 0-100kW
2022-GD-22801 | 7.32 | Residencial | Yes | 0-100kW
2022-GD-11081 | 6.19 | Residencial | Yes | 0-100kW
2022-GD-06010 | 5 | Residencial | Yes | 0-100kW
2022-GD-20454 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-23403 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-05713 | 6.8 | Residencial | Yes | 0-100kW
202501-NM25-01522 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-21755 | 4.03 | Residencial | Yes | 0-100kW
202506-NM25-02901 | 3.456 | Residencial | Yes | 0-100kW
2023-GD-03241 | 4.76 | Residencial | Yes | 0-100kW
202408-NM25-00342 | 6.588 | Residencial | Yes | 0-100kW
202512-NM25-06174 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25240 | 5 | Residencial | Yes | 0-100kW
202411-NM25-02567 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26120 | 4.03 | Residencial | Yes | 0-100kW
2018-GD-00143 | 3.77 | Residencial | Yes | 0-100kW
2021-GD-05092 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-15340 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-01147 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-06227 | 3.84 | Residencial | Yes | 0-100kW
202311-NM25-00783 | 14.64 | Residencial | Yes | 0-100kW
202412-NM25-01811 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17264 | 8 | Residencial | Yes | 0-100kW
202312-NM25-01658 | 5.856 | Residencial | Yes | 0-100kW
202412-NM25-01155 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-06110 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-32239 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-37231 | 8.83 | Residencial | Yes | 0-100kW
2019-GD-02367 | 8.35 | Residencial | Yes | 0-100kW
2022-GD-00928 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-26119 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04849 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07014 | 4.03 | Residencial | Yes | 0-100kW
202506-NM25-04152 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-01087 | 8 | Residencial | Yes | 0-100kW
15-7-874 | 7 | Residencial | Yes | 0-100kW
16-3-140 | 4.73 | Residencial | Yes | 0-100kW
202407-NM25-03530 | 6.954 | Residencial | Yes | 0-100kW
2023-GD-19294 | 5 | Residencial | Yes | 0-100kW
2022-GD-10230 | 2.95 | Residencial | Yes | 0-100kW
2019-GD-00477 | 4.5 | Residencial | Yes | 0-100kW
202511-NM25-00482 | 12.078 | Residencial | Yes | 0-100kW
202409-NM25-01492 | 4.026 | Residencial | Yes | 0-100kW
202410-NM25-02867 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12125 | 5.9 | Residencial | Yes | 0-100kW
202405-NM25-00641 | 3.66 | Residencial | Yes | 0-100kW
202408-NM25-03762 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00319 | 7 | Residencial | Yes | 0-100kW
2022-GD-14801 | 3.66 | Residencial | Yes | 0-100kW
202501-NM25-02141 | 7.6 | Comercial | Yes | 0-100kW
202412-NM25-04208 | 5 | Residencial | Yes | 0-100kW
202501-NM25-04141 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-00372 | 4.2 | Residencial | Yes | 0-100kW
2022-GD-09889 | 5 | Residencial | Yes | 0-100kW
2023-GD-15972 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02082 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36591 | 12 | Residencial | Yes | 0-100kW
2021-GD-01540 | 3.24 | Residencial | Yes | 0-100kW
202409-NM25-03781 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00913 | 4.5 | Residencial | Yes | 0-100kW
202412-NM25-00656 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02931 | 3.245 | Residencial | Yes | 0-100kW
2020-GD-06256 | 4 | Residencial | Yes | 0-100kW
2022-GD-01634 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-17266 | 4.03 | Residencial | Yes | 0-100kW
14-7-690 | 5.6 | Residencial | Yes | 0-100kW
2021-GD-00980 | 5.9 | Residencial | Yes | 0-100kW
202504-NM25-05751 | 7.68 | Residencial | Yes | 0-100kW
202401-NM25-02952 | 8 | Residencial | Yes | 0-100kW
202506-NM25-01621 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-06033 | 5.9 | Residencial | Yes | 0-100kW
202406-NM25-02870 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19861 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-03271 | 3.24 | Residencial | Yes | 0-100kW
202507-NM25-05010 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-01025 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-02501 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-01207 | 4.75 | Residencial | Yes | 0-100kW
2019-GD-03374 | 3.54 | Residencial | Yes | 0-100kW
202504-NM25-01568 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-01441 | 5.376 | Residencial | Yes | 0-100kW
2022-GD-11716 | 4.39 | Residencial | Yes | 0-100kW
202507-NM25-02410 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-36208 | 9 | Residencial | Yes | 0-100kW
15-4-0346GD | 10 | Residencial | Yes | 0-100kW
202409-NM25-02484 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00061 | 8 | Residencial | Yes | 0-100kW
202507-NM25-03269 | 12 | Residencial | Yes | 0-100kW
2023-GD-36568 | 7.6 | Residencial | Yes | 0-100kW
16-3-828 | 3.75 | Residencial | Yes | 0-100kW
202506-NM25-03342 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-01946 | 6.8 | Residencial | Yes | 0-100kW
202503-NM25-00017 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-20444 | 8 | Residencial | Yes | 0-100kW
2022-GD-06747 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-03736 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-15349 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04765 | 5.9 | Comercial | Yes | 0-100kW
202407-NM25-00331 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-04310 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24864 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-35396 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10476 | 7.67 | Residencial | Yes | 0-100kW
2020-GD-01046 | 5.31 | Residencial | Yes | 0-100kW
202503-NM25-00321 | 11.5 | Residencial | Yes | 0-100kW
14-2-751 | 6 | Residencial | Yes | 0-100kW
202411-NM25-03320 | 12.81 | Residencial | Yes | 0-100kW
2022-GD-19188 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-24803 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22831 | 4.03 | Residencial | Yes | 0-100kW
202403-NM25-03701 | 8.1 | Residencial | Yes | 0-100kW
202504-NM25-01511 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03008 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-16836 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03462 | 5 | Residencial | Yes | 0-100kW
202505-NM25-00741 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-32754 | 3.29 | Residencial | Yes | 0-100kW
202409-NM25-01251 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-05115 | 3.07 | Residencial | Yes | 0-100kW
2021-GD-08194 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-26088 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-26647 | 5.86 | Residencial | Yes | 0-100kW
202511-NM25-03866 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-14317 | 4.43 | Residencial | Yes | 0-100kW
2021-GD-08467 | 2.66 | Residencial | Yes | 0-100kW
202501-NM25-04472 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04458 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02534 | 6.588 | Residencial | Yes | 0-100kW
202511-NM25-00003 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-00118 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-20593 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-21039 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-02040 | 4.425 | Residencial | Yes | 0-100kW
2023-GD-16039 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03001 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05366 | 1.77 | Residencial | Yes | 0-100kW
2023-GD-38770 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-05458 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-02964 | 5 | Residencial | Yes | 0-100kW
202404-NM25-02296 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-00441 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-01093 | 4.5 | Residencial | Yes | 0-100kW
202403-NM25-00566 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-25023 | 7.68 | Residencial | Yes | 0-100kW
202311-NM25-00670 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-35032 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-04883 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-01409 | 5.605 | Residencial | Yes | 0-100kW
2020-GD-03044 | 4.5 | Residencial | Yes | 0-100kW
2023-GD-20102 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-08488 | 9 | Residencial | Yes | 0-100kW
2022-GD-25267 | 4.03 | Residencial | Yes | 0-100kW
202512-NM25-03503 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-01303 | 6.67 | Residencial | Yes | 0-100kW
202408-NM25-00115 | 10.614 | Residencial | Yes | 0-100kW
202505-NM25-03361 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-02994 | 3.66 | Residencial | Yes | 0-100kW
14-2-121 | 3.5 | Residencial | Yes | 0-100kW
2021-GD-14087 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-29000 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-03523 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-02230 | 3.84 | Residencial | Yes | 0-100kW
202505-NM25-01606 | 3.8 | Residencial | Yes | 0-100kW
202404-NM25-04295 | 6.588 | Residencial | Yes | 0-100kW
2022-GD-01380 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-32752 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-04194 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-05196 | 15.2 | Residencial | Yes | 0-100kW
202404-NM25-00662 | 15.2 | Residencial | Yes | 0-100kW
202405-NM25-00194 | 8 | Residencial | Yes | 0-100kW
202503-NM25-03449 | 3.8 | Residencial | Yes | 0-100kW
202501-NM25-01069 | 12 | Residencial | Yes | 0-100kW
2020-GD-09506 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-08109 | 2.66 | Residencial | Yes | 0-100kW
2021-GD-12939 | 7.38 | Residencial | Yes | 0-100kW
202410-NM25-01709 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04605 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18726 | 8.42 | Residencial | Yes | 0-100kW
2021-GD-03115 | 6.19 | Residencial | Yes | 0-100kW
2022-GD-01488 | 3.54 | Residencial | Yes | 0-100kW
202409-NM25-01666 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05254 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25996 | 3.84 | Residencial | Yes | 0-100kW
202412-NM25-02790 | 2.928 | Residencial | Yes | 0-100kW
202404-NM25-02011 | 4.992 | Residencial | Yes | 0-100kW
202406-NM25-03520 | 3.84 | Residencial | Yes | 0-100kW
202311-NM25-00115 | 4.758 | Residencial | Yes | 0-100kW
202405-NM25-01902 | 5.856 | Residencial | Yes | 0-100kW
2020-GD-08198 | 3.84 | Residencial | Yes | 0-100kW
16-3-179 | 2.15 | Residencial | Yes | 0-100kW
2022-GD-32344 | 8.06 | Residencial | Yes | 0-100kW
202402-NM25-02480 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23763 | 4.72 | Residencial | Yes | 0-100kW
202502-NM25-03732 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04251 | 3.8 | Comercial | Yes | 0-100kW
2023-GD-01917 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33638 | 4.03 | Residencial | Yes | 0-100kW
202511-NM25-04037 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16627 | 9 | Residencial | Yes | 0-100kW
2023-GD-38618 | 9 | Residencial | Yes | 0-100kW
202505-NM25-03779 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03159 | 11.4 | Residencial | Yes | 0-100kW
2021-GD-13965 | 5.61 | Residencial | Yes | 0-100kW
202507-NM25-04360 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-02852 | 5.9 | Residencial | Yes | 0-100kW
202409-NM25-03463 | 5.124 | Residencial | Yes | 0-100kW
2023-GD-27035 | 6.49 | Comercial | Yes | 0-100kW
2023-GD-15113 | 5.12 | Residencial | Yes | 0-100kW
202409-NM25-02444 | 9 | Residencial | Yes | 0-100kW
2021-GD-12272 | 8.78 | Residencial | Yes | 0-100kW
202503-NM25-01770 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-01457 | 19 | Residencial | Yes | 0-100kW
202411-NM25-00540 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21542 | 8 | Residencial | Yes | 0-100kW
2023-GD-33905 | 6.91 | Residencial | Yes | 0-100kW
2018-GD-00073 | 12 | Residencial | Yes | 0-100kW
2021-GD-03900 | 9.15 | Residencial | No | 0-100kW
2022-GD-19948 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-20895 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-05199 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04370 | 7.6 | Comercial | Yes | 0-100kW
2020-GD-01828 | 3.245 | Residencial | Yes | 0-100kW
2023-GD-18945 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01674 | 5.124 | Residencial | Yes | 0-100kW
202406-NM25-03635 | 5.76 | Residencial | Yes | 0-100kW
202402-NM25-04171 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-03316 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-05399 | 6.49 | Residencial | Yes | 0-100kW
2022-GD-09454 | 4.03 | Residencial | Yes | 0-100kW
202506-NM25-04468 | 8 | Residencial | Yes | 0-100kW
202502-NM25-02951 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-00906 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04590 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14904 | 3.84 | Residencial | Yes | 0-100kW
202412-NM25-01727 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11700 | 3.8 | Residencial | Yes | 0-100kW
2019-GD-02595 | 3.245 | Residencial | Yes | 0-100kW
2023-GD-31064 | 5 | Residencial | Yes | 0-100kW
2022-GD-00105 | 3.54 | Residencial | Yes | 0-100kW
202410-NM25-02100 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01227 | 3.66 | Residencial | Yes | 0-100kW
2018-GD-01167 | 6 | Residencial | Yes | 0-100kW
202410-NM25-04814 | 8 | Residencial | Yes | 0-100kW
202504-NM25-05672 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01356 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-24786 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-05873 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-00147 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-20677 | 4.03 | Comercial | Yes | 0-100kW
2023-GD-24950 | 8.78 | Residencial | No | 0-100kW
202312-NM25-03601 | 5.49 | Residencial | Yes | 0-100kW
15-5-0340A | 3.87 | Residencial | Yes | 0-100kW
2023-GD-14016 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-17913 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02344 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-09041 | 7.08 | Residencial | Yes | 0-100kW
202508-NM25-02448 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16073 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18910 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-04081 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-12475 | 3.46 | Residencial | Yes | 0-100kW
2022-GD-28088 | 3.8 | Residencial | Yes | 0-100kW
2017-GD-00819 | 12.85 | Residencial | Yes | 0-100kW
202506-NM25-01651 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25709 | 4.76 | Residencial | Yes | 0-100kW
202507-NM25-03701 | 11.5 | Residencial | Yes | 0-100kW
2024-GD-00110 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03883 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-13768 | 3.8 | Residencial | Yes | 0-100kW
202406-NM25-01716 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09953 | 4.43 | Residencial | Yes | 0-100kW
202410-NM25-01789 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12607 | 3.24 | Residencial | Yes | 0-100kW
202407-NM25-02707 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-05079 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34557 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-02122 | 8.56 | Residencial | Yes | 0-100kW
2022-GD-12685 | 5.86 | Residencial | Yes | 0-100kW
202409-NM25-00757 | 6.8 | Residencial | Yes | 0-100kW
2021-GD-13474 | 5.61 | Residencial | Yes | 0-100kW
2021-GD-09948 | 3.66 | Residencial | Yes | 0-100kW
202505-NM25-01184 | 4.992 | Residencial | Yes | 0-100kW
202511-NM25-03697 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-04388 | 7.84 | Residencial | Yes | 0-100kW
202411-NM25-00921 | 8 | Residencial | Yes | 0-100kW
2023-GD-22733 | 4.39 | Residencial | Yes | 0-100kW
202503-NM25-04752 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00258 | 3 | Residencial | Yes | 0-100kW
202503-NM25-02128 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-00207 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-00529 | 7.6 | Residencial | Yes | 0-100kW
16-3-151 | 6 | Residencial | Yes | 0-100kW
2021-GD-08264 | 10.03 | Residencial | Yes | 0-100kW
2022-GD-06702 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-03970 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05112 | 9 | Residencial | Yes | 0-100kW
2020-GD-09532 | 4.43 | Residencial | Yes | 0-100kW
202411-NM25-01467 | 8 | Residencial | Yes | 0-100kW
202312-NM25-02969 | 5.124 | Residencial | Yes | 0-100kW
202405-NM25-03945 | 4.758 | Residencial | Yes | 0-100kW
202412-NM25-02083 | 8.448 | Residencial | Yes | 0-100kW
202510-NM25-00255 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02693 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32568 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-02010 | 6.49 | Residencial | Yes | 0-100kW
2022-GD-25067 | 9.75 | Residencial | Yes | 0-100kW
2020-GD-08119 | 9.52 | Residencial | Yes | 0-100kW
202510-NM25-03068 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-00770 | 9.882 | Residencial | Yes | 0-100kW
2023-GD-12126 | 5 | Residencial | Yes | 0-100kW
202509-NM25-03058 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16384 | 16 | Residencial | Yes | 0-100kW
202401-NM25-01723 | 12.444 | Residencial | Yes | 0-100kW
202501-NM25-01510 | 7.6 | Residencial | No | 0-100kW
202408-NM25-02932 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02300 | 10 | Residencial | Yes | 0-100kW
2021-GD-10387 | 8.78 | Residencial | Yes | 0-100kW
202511-NM25-01332 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-10534 | 7.6 | Residencial | No | 0-100kW
202512-NM25-04528 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-17379 | 5.12 | Residencial | Yes | 0-100kW
2021-GD-01162 | 15.04 | Residencial | Yes | 0-100kW
2022-GD-06700 | 6.8 | Residencial | Yes | 0-100kW
202503-NM25-04674 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-00410 | 3.54 | Residencial | Yes | 0-100kW
202507-NM25-02503 | 8 | Residencial | Yes | 0-100kW
202510-NM25-04120 | 9.984 | Residencial | Yes | 0-100kW
202503-NM25-00817 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-02042 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03740 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-12156 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-00091 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-01577 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-10485 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-10487 | 21.23 | Comercial | Yes | 0-100kW
202503-NM25-02932 | 6.144 | Residencial | Yes | 0-100kW
2023-GD-07520 | 4.03 | Residencial | Yes | 0-100kW
202512-NM25-01936 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-00050 | 9.8 | Residencial | Yes | 0-100kW
2021-GD-10144 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-27244 | 4.76 | Comercial | Yes | 0-100kW
2021-GD-06338 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-35164 | 5.49 | Residencial | Yes | 0-100kW
2020-GD-02392 | 12 | Residencial | Yes | 0-100kW
202511-NM25-01732 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-08152 | 10 | Residencial | Yes | 0-100kW
202402-NM25-03602 | 4.026 | Residencial | Yes | 0-100kW
202410-NM25-02191 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-00025 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-23182 | 10.98 | Residencial | Yes | 0-100kW
202509-NM25-04260 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00887 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32719 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-00939 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00199 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-16374 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-03467 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-16359 | 4.03 | Residencial | Yes | 0-100kW
202508-NM25-03896 | 4.224 | Residencial | Yes | 0-100kW
2023-GD-15324 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11028 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04176 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-18886 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-15361 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-12189 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01145 | 3.8 | Residencial | Yes | 0-100kW
2019-GD-02320 | 16.7 | Residencial | Yes | 0-100kW
202506-NM25-03348 | 11.5 | Residencial | Yes | 0-100kW
14-1-538 | 6.02 | Residencial | Yes | 0-100kW
202404-NM25-00983 | 3.66 | Residencial | Yes | 0-100kW
202503-NM25-03090 | 2.688 | Residencial | Yes | 0-100kW
2023-GD-31231 | 3.8 | Residencial | Yes | 0-100kW
202401-NM25-01803 | 8 | Residencial | Yes | 0-100kW
2023-GD-08167 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-07773 | 4.75 | Comercial | Yes | 0-100kW
2023-GD-11338 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-14687 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-05038 | 5.01 | Residencial | Yes | 0-100kW
2020-GD-01161 | 5.015 | Residencial | Yes | 0-100kW
202508-NM25-00686 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-06023 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-21892 | 6.95 | Residencial | No | 0-100kW
2022-GD-19513 | 4.03 | Residencial | Yes | 0-100kW
202403-NM25-00465 | 6.144 | Residencial | Yes | 0-100kW
2023-GD-03056 | 5.76 | Residencial | Yes | 0-100kW
202401-NM25-03811 | 9.15 | Residencial | Yes | 0-100kW
202503-NM25-01179 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-06991 | 10 | Residencial | Yes | 0-100kW
2022-GD-29686 | 4.76 | Residencial | Yes | 0-100kW
202512-NM25-05125 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02593 | 8.052 | Residencial | Yes | 0-100kW
2021-GD-06139 | 3.54 | Residencial | Yes | 0-100kW
202504-NM25-02386 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-03463 | 7.6 | Comercial | Yes | 0-100kW
2023-GD-24647 | 3.84 | Residencial | Yes | 0-100kW
202409-NM25-00188 | 8 | Residencial | Yes | 0-100kW
2023-GD-08839 | 8.42 | Residencial | Yes | 0-100kW
202404-NM25-01689 | 5.49 | Residencial | Yes | 0-100kW
202411-NM25-01773 | 7.6 | Residencial | No | 0-100kW
2021-GD-02372 | 7.08 | Residencial | Yes | 0-100kW
2022-GD-05038 | 6.49 | Residencial | Yes | 0-100kW
202502-NM25-04435 | 18.21 | Residencial | Yes | 0-100kW
202403-NM25-02428 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-02274 | 3.54 | Residencial | Yes | 0-100kW
2020-GD-02407 | 4 | Residencial | Yes | 0-100kW
14-2-816 | 6 | Residencial | No | 0-100kW
2022-GD-07376 | 5.12 | Residencial | Yes | 0-100kW
202403-NM25-03272 | 3.66 | Residencial | Yes | 0-100kW
202412-NM25-00524 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02918 | 4 | Residencial | Yes | 0-100kW
2019-GD-02420 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-30089 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-07691 | 9.44 | Residencial | Yes | 0-100kW
202407-NM25-03914 | 15 | Residencial | Yes | 0-100kW
202408-NM25-03386 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-32115 | 11.9 | Comercial | Yes | 0-100kW
2022-GD-01791 | 3.84 | Residencial | Yes | 0-100kW
202503-NM25-03015 | 8.448 | Residencial | Yes | 0-100kW
2023-GD-33396 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-37525 | 6 | Residencial | Yes | 0-100kW
2023-GD-33875 | 4.03 | Residencial | Yes | 0-100kW
202504-NM25-01514 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18249 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-02422 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-29970 | 9.6 | Residencial | Yes | 0-100kW
202312-NM25-00626 | 16 | Residencial | Yes | 0-100kW
2022-GD-03914 | 3.84 | Residencial | Yes | 0-100kW
202508-NM25-03603 | 10 | Residencial | Yes | 0-100kW
2020-GD-05845 | 3 | Residencial | Yes | 0-100kW
202503-NM25-03201 | 10 | Residencial | Yes | 0-100kW
2022-GD-28459 | 10.03 | Residencial | Yes | 0-100kW
2021-GD-06891 | 7.38 | Residencial | Yes | 0-100kW
2019-GD-01374 | 8.35 | Residencial | Yes | 0-100kW
2021-GD-02955 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-12745 | 5.01 | Residencial | Yes | 0-100kW
202503-NM25-03871 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-39013 | 3.66 | Residencial | Yes | 0-100kW
202402-NM25-02067 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-22719 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-00574 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-00878 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-14822 | 19.2 | Residencial | Yes | 0-100kW
2023-GD-26868 | 7.59 | Residencial | Yes | 0-100kW
2023-GD-26837 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01271 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-06159 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07457 | 5 | Residencial | Yes | 0-100kW
2020-GD-05122 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-07577 | 10 | Residencial | Yes | 0-100kW
202404-NM25-04559 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-01543 | 7.32 | Residencial | Yes | 0-100kW
2022-GD-15075 | 9.52 | Residencial | Yes | 0-100kW
202405-NM25-04075 | 6 | Residencial | Yes | 0-100kW
202409-NM25-01097 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01541 | 6.528 | Residencial | Yes | 0-100kW
202404-NM25-00967 | 4.026 | Residencial | Yes | 0-100kW
202407-NM25-03478 | 3.8 | Residencial | Yes | 0-100kW
202408-NM25-01523 | 8 | Residencial | Yes | 0-100kW
202511-NM25-04171 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04000 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-21840 | 6.95 | Residencial | Yes | 0-100kW
2021-GD-03457 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-19111 | 6.59 | Residencial | Yes | 0-100kW
202404-NM25-04550 | 4.392 | Residencial | Yes | 0-100kW
2022-GD-25072 | 5.86 | Residencial | Yes | 0-100kW
202407-NM25-04503 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-02426 | 8 | Residencial | Yes | 0-100kW
202403-NM25-02838 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01783 | 6.144 | Residencial | Yes | 0-100kW
202409-NM25-00529 | 5.49 | Residencial | Yes | 0-100kW
202412-NM25-00148 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-23046 | 3.66 | Residencial | Yes | 0-100kW
202405-NM25-00049 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-02091 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-28031 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-20127 | 8.45 | Residencial | Yes | 0-100kW
202408-NM25-04678 | 4.992 | Residencial | Yes | 0-100kW
2021-GD-07383 | 9.49 | Residencial | Yes | 0-100kW
202507-NM25-02573 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-08293 | 5.12 | Residencial | Yes | 0-100kW
2020-GD-02563 | 3.77 | Residencial | Yes | 0-100kW
2022-GD-01194 | 4.76 | Residencial | Yes | 0-100kW
2020-GD-01284 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-01571 | 2.95 | Comercial | Yes | 0-100kW
202409-NM25-00051 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-05002 | 12 | Residencial | Yes | 0-100kW
2023-GD-21224 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24657 | 5.86 | Residencial | Yes | 0-100kW
13-3-206 | 3.36 | Residencial | Yes | 0-100kW
202502-NM25-04044 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-23435 | 4.03 | Residencial | Yes | 0-100kW
202508-NM25-02200 | 3.456 | Residencial | Yes | 0-100kW
2019-GD-01343 | 9.44 | Residencial | Yes | 0-100kW
202506-NM25-02946 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-09859 | 5 | Residencial | Yes | 0-100kW
202404-NM25-00985 | 3.8 | Residencial | Yes | 0-100kW
202407-NM25-00205 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19475 | 6.19 | Residencial | Yes | 0-100kW
202311-NM25-00913 | 8.052 | Residencial | Yes | 0-100kW
2021-GD-08959 | 4.72 | Residencial | Yes | 0-100kW
202508-NM25-03864 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-07167 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-09137 | 6.79 | Residencial | Yes | 0-100kW
2023-GD-37346 | 8 | Residencial | Yes | 0-100kW
202509-NM25-04034 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-31462 | 9 | Residencial | Yes | 0-100kW
202409-NM25-01611 | 8 | Residencial | Yes | 0-100kW
2022-GD-30162 | 4.76 | Residencial | Yes | 0-100kW
202512-NM25-00747 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-02953 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-30082 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-08659 | 8.78 | Residencial | Yes | 0-100kW
2023-GD-19128 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05559 | 8.26 | Residencial | Yes | 0-100kW
202502-NM25-03680 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-04856 | 8 | Residencial | Yes | 0-100kW
202401-NM25-01115 | 6 | Residencial | Yes | 0-100kW
202507-NM25-02037 | 3.835 | Residencial | Yes | 0-100kW
202504-NM25-00081 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-01329 | 8.35 | Residencial | Yes | 0-100kW
2022-GD-03798 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-14174 | 6.8 | Residencial | Yes | 0-100kW
202512-NM25-05697 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-15184 | 3.54 | Residencial | Yes | 0-100kW
202410-NM25-00993 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02197 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-05133 | 1.8 | Residencial | Yes | 0-100kW
2021-GD-01077 | 3.54 | Residencial | Yes | 0-100kW
202502-NM25-04165 | 8 | Residencial | Yes | 0-100kW
2023-GD-36860 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21037 | 3.3 | Residencial | Yes | 0-100kW
2021-GD-05389 | 5 | Residencial | Yes | 0-100kW
202409-NM25-03670 | 15.2 | Residencial | Yes | 0-100kW
202411-NM25-00828 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04187 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-10914 | 4.39 | Residencial | Yes | 0-100kW
202409-NM25-01608 | 10.368 | Residencial | Yes | 0-100kW
2023-GD-08355 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08829 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-03354 | 11.5 | Residencial | Yes | 0-100kW
14-9-105 | 6 | Residencial | Yes | 0-100kW
202501-NM25-05643 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-07644 | 6 | Residencial | Yes | 0-100kW
202411-NM25-02500 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03758 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00202 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-21731 | 3.66 | Residencial | Yes | 0-100kW
202502-NM25-06922 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-13202 | 4 | Residencial | Yes | 0-100kW
2022-GD-06486 | 5.61 | Residencial | Yes | 0-100kW
202509-NM25-03956 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-09289 | 5 | Residencial | Yes | 0-100kW
2020-GD-03209 | 4.5 | Residencial | Yes | 0-100kW
2023-GD-21682 | 7.6 | Residencial | No | 0-100kW
2022-GD-01219 | 4.43 | Residencial | Yes | 0-100kW
2020-GD-06307 | 4.5 | Residencial | Yes | 0-100kW
2023-GD-09419 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03248 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-02823 | 7.6 | Residencial | No | 0-100kW
202405-NM25-00061 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-00720 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-13106 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-05209 | 6.59 | Residencial | Yes | 0-100kW
202402-NM25-01932 | 2.1 | Residencial | Yes | 0-100kW
202407-NM25-00226 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-02865 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-13075 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-02682 | 6.22 | Residencial | Yes | 0-100kW
2023-GD-02620 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-11430 | 5.61 | Residencial | Yes | 0-100kW
2023-GD-13687 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-04198 | 8 | Residencial | Yes | 0-100kW
2021-GD-13021 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-09582 | 8 | Residencial | Yes | 0-100kW
202510-NM25-00039 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-12985 | 7.38 | Residencial | Yes | 0-100kW
202503-NM25-03980 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-12062 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-29707 | 8.4 | Residencial | Yes | 0-100kW
2023-GD-11022 | 2.93 | Residencial | Yes | 0-100kW
2017-GD-00668 | 12 | Residencial | No | 0-100kW
2023-GD-01760 | 8.42 | Residencial | Yes | 0-100kW
2017-GD-01132 | 4.3 | Residencial | Yes | 0-100kW
202503-NM25-01542 | 15.2 | Residencial | Yes | 0-100kW
202409-NM25-03060 | 10.98 | Residencial | Yes | 0-100kW
14-3-414 | 5 | Residencial | Yes | 0-100kW
2023-GD-26444 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-08928 | 5 | Residencial | Yes | 0-100kW
14-7-665 | 7 | Residencial | Yes | 0-100kW
202412-NM25-03865 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14506 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-36652 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-35640 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02520 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-22665 | 4.03 | Residencial | Yes | 0-100kW
2017-GD-03696 | 3.36 | Residencial | Yes | 0-100kW
2021-GD-15506 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-09100 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-08222 | 9.15 | Comercial | No | 0-100kW
202510-NM25-00385 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-12367 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-31771 | 15.2 | Residencial | Yes | 0-100kW
202402-NM25-01948 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05649 | 6.59 | Residencial | No | 0-100kW
202502-NM25-00447 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-31768 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-03130 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03827 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-20061 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13731 | 9.52 | Residencial | Yes | 0-100kW
2022-GD-24488 | 5.86 | Residencial | Yes | 0-100kW
202411-NM25-03011 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-03473 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15268 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-24072 | 5 | Residencial | Yes | 0-100kW
202508-NM25-02241 | 15.925 | Residencial | Yes | 0-100kW
202501-NM25-03940 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-06186 | 2.95 | Residencial | Yes | 0-100kW
2020-GD-05360 | 4.72 | Residencial | Yes | 0-100kW
202512-NM25-02853 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-01375 | 6 | Residencial | Yes | 0-100kW
202408-NM25-04474 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00320 | 13.6 | Residencial | Yes | 0-100kW
202412-NM25-02788 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04270 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-12782 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00611 | 11.5 | Residencial | Yes | 0-100kW
13-5-0087A | 6 | Residencial | Yes | 0-100kW
202502-NM25-05925 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-02881 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-02244 | 5.9 | Residencial | Yes | 0-100kW
2021-GD-08910 | 9.44 | Residencial | Yes | 0-100kW
2023-GD-01852 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-25123 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-11863 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-17931 | 4.39 | Residencial | No | 0-100kW
202410-NM25-00499 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35021 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-03050 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-31384 | 4.03 | Residencial | Yes | 0-100kW
202501-NM25-03673 | 2.928 | Residencial | Yes | 0-100kW
2022-GD-31087 | 3.84 | Residencial | Yes | 0-100kW
202504-NM25-04342 | 5 | Residencial | Yes | 0-100kW
2021-GD-09976 | 12.11 | Residencial | Yes | 0-100kW
2023-GD-27042 | 7.59 | Residencial | Yes | 0-100kW
2021-GD-12042 | 6.59 | Residencial | Yes | 0-100kW
2022-GD-32604 | 3.84 | Residencial | Yes | 0-100kW
12-6-0019 | 31.8 | Agricultural | Yes | 0-100kW
2021-GD-08508 | 5.61 | Residencial | Yes | 0-100kW
202501-NM25-03711 | 5.76 | Residencial | Yes | 0-100kW
202511-NM25-03668 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-13235 | 8.42 | Residencial | Yes | 0-100kW
2018-GD-01516 | 2.88 | Residencial | Yes | 0-100kW
2020-GD-04773 | 7 | Residencial | Yes | 0-100kW
202407-NM25-00385 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-03137 | 4.56 | Residencial | No | 0-100kW
2023-GD-26299 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06088 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-13987 | 9 | Residencial | Yes | 0-100kW
202404-NM25-03239 | 6.8 | Residencial | Yes | 0-100kW
202411-NM25-03601 | 2.928 | Residencial | Yes | 0-100kW
2022-GD-17108 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-04288 | 8 | Residencial | Yes | 0-100kW
2020-GD-03022 | 8.555 | Residencial | Yes | 0-100kW
17-2-0033 | 6.75 | Residencial | Yes | 0-100kW
2020-GD-07139 | 11.71 | Residencial | Yes | 0-100kW
202410-NM25-04106 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01327 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-15004 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-08411 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-13387 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-02506 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06940 | 3.25 | Comercial | Yes | 0-100kW
2022-GD-28218 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-03181 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-02435 | 3.24 | Residencial | Yes | 0-100kW
202512-NM25-03205 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-00009 | 7.6 | Residencial | No | 0-100kW
2021-GD-08116 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-22511 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-15502 | 30 | Comercial | No | 0-100kW
202403-NM25-03782 | 2.36 | Residencial | Yes | 0-100kW
2023-GD-00852 | 5.4 | Residencial | Yes | 0-100kW
202509-NM25-04367 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-04243 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-16594 | 3.84 | Residencial | Yes | 0-100kW
202412-NM25-03426 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04391 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-14671 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07658 | 5.31 | Residencial | Yes | 0-100kW
202410-NM25-02761 | 7.6 | Residencial | Yes | 0-100kW
16-7-0290 | 5 | Residencial | Yes | 0-100kW
202508-NM25-00965 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-02061 | 7.586 | Residencial | Yes | 0-100kW
202410-NM25-04679 | 5.1 | Residencial | Yes | 0-100kW
2023-GD-18510 | 8 | Residencial | Yes | 0-100kW
2022-GD-03823 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-11965 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-01450 | 8 | Residencial | Yes | 0-100kW
202412-NM25-03676 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02082 | 8.448 | Residencial | Yes | 0-100kW
2018-GD-01882 | 8.35 | Residencial | Yes | 0-100kW
2022-GD-07068 | 2.36 | Residencial | Yes | 0-100kW
2023-GD-29686 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-03405 | 4.42 | Residencial | Yes | 0-100kW
2021-GD-14831 | 7.67 | Residencial | Yes | 0-100kW
202403-NM25-01183 | 6.588 | Residencial | Yes | 0-100kW
202410-NM25-03765 | 4.026 | Residencial | Yes | 0-100kW
202512-NM25-00334 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04585 | 7.6 | Residencial | Yes | 0-100kW
14-6-0418 | 4.8 | Residencial | Yes | 0-100kW
2023-GD-13154 | 8.42 | Residencial | Yes | 0-100kW
2017-GD-00622 | 3.225 | Residencial | Yes | 0-100kW
15-6-0201 | 5.16 | Residencial | Yes | 0-100kW
2023-GD-14038 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-00566 | 10.61 | Residencial | Yes | 0-100kW
202508-NM25-03032 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-13971 | 5 | Residencial | Yes | 0-100kW
202502-NM25-04574 | 3.66 | Residencial | Yes | 0-100kW
202506-NM25-01617 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23816 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-12359 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-03234 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-00403 | 16.68 | Residencial | Yes | 0-100kW
2021-GD-06637 | 3.24 | Residencial | Yes | 0-100kW
2019-GD-01422 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-00684 | 6.78 | Residencial | Yes | 0-100kW
202412-NM25-00010 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11100 | 4.43 | Residencial | Yes | 0-100kW
202509-NM25-00915 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-02941 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-01805 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-04006 | 8.74 | Residencial | Yes | 0-100kW
2019-GD-00048 | 8 | Residencial | Yes | 0-100kW
2021-GD-11375 | 3.54 | Residencial | Yes | 0-100kW
202510-NM25-01286 | 3.072 | Residencial | Yes | 0-100kW
202508-NM25-02953 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-04320 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03052 | 10.248 | Comercial | Yes | 0-100kW
2022-GD-32310 | 4.03 | Residencial | Yes | 0-100kW
202407-NM25-01472 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04987 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-06652 | 5 | Residencial | Yes | 0-100kW
202510-NM25-01144 | 11.5 | Residencial | Yes | 0-100kW
202311-NM25-00751 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18783 | 4.39 | Residencial | Yes | 0-100kW
202502-NM25-07014 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-01685 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-04254 | 12 | Residencial | Yes | 0-100kW
202508-NM25-00101 | 9.216 | Residencial | Yes | 0-100kW
202502-NM25-02129 | 13.542 | Residencial | Yes | 0-100kW
2022-GD-00644 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-06670 | 4.03 | Residencial | Yes | 0-100kW
202411-NM25-02426 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-24201 | 6.95 | Residencial | Yes | 0-100kW
202409-NM25-00294 | 15.2 | Residencial | Yes | 0-100kW
202402-NM25-03779 | 6.588 | Residencial | Yes | 0-100kW
202502-NM25-01025 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-00965 | 2.7 | Residencial | Yes | 0-100kW
202409-NM25-03340 | 15.2 | Residencial | Yes | 0-100kW
202408-NM25-01579 | 9.15 | Residencial | Yes | 0-100kW
202405-NM25-00947 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18196 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-03841 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-00322 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00693 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-32557 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04131 | 13.19 | Residencial | Yes | 0-100kW
202507-NM25-00412 | 8 | Residencial | Yes | 0-100kW
202408-NM25-04469 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36876 | 10.61 | Residencial | Yes | 0-100kW
2023-GD-14796 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01881 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-16622 | 5 | Residencial | Yes | 0-100kW
2021-GD-10601 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-09465 | 8.42 | Comercial | Yes | 0-100kW
2023-GD-38646 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-03748 | 4.026 | Residencial | Yes | 0-100kW
2020-GD-07300 | 7.97 | Residencial | Yes | 0-100kW
202504-NM25-00410 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18103 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-18416 | 4.76 | Residencial | Yes | 0-100kW
2020-GD-05279 | 4.25 | Residencial | Yes | 0-100kW
202509-NM25-04083 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-03126 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-01892 | 3.29 | Residencial | Yes | 0-100kW
2022-GD-14297 | 3.54 | Residencial | Yes | 0-100kW
202410-NM25-03893 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05604 | 10.62 | Residencial | Yes | 0-100kW
2022-GD-14148 | 19.76 | Residencial | Yes | 0-100kW
2023-GD-30984 | 6 | Residencial | Yes | 0-100kW
202408-NM25-00678 | 8 | Residencial | Yes | 0-100kW
2021-GD-02376 | 9.2 | Residencial | Yes | 0-100kW
202404-NM25-02360 | 4.758 | Residencial | Yes | 0-100kW
2022-GD-29398 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-03006 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-22014 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-20530 | 3.29 | Residencial | Yes | 0-100kW
202405-NM25-00444 | 5.124 | Residencial | Yes | 0-100kW
2021-GD-11681 | 5 | Residencial | Yes | 0-100kW
202403-NM25-01630 | 5.124 | Residencial | Yes | 0-100kW
202407-NM25-01718 | 7.68 | Residencial | Yes | 0-100kW
202410-NM25-04550 | 4.758 | Residencial | Yes | 0-100kW
2021-GD-04627 | 9.6 | Residencial | Yes | 0-100kW
2022-GD-06272 | 7.08 | Residencial | Yes | 0-100kW
2023-GD-33021 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-00289 | 4.25 | Residencial | Yes | 0-100kW
202505-NM25-03493 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-00894 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32153 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-26375 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-05252 | 6.8 | Residencial | Yes | 0-100kW
202508-NM25-01210 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-01468 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02768 | 6 | Residencial | Yes | 0-100kW
2023-GD-28929 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-03248 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02117 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-00405 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-20058 | 8 | Residencial | Yes | 0-100kW
2023-GD-37349 | 4.03 | Residencial | Yes | 0-100kW
202503-NM25-03048 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-01182 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-14102 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-11370 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-09788 | 5 | Residencial | Yes | 0-100kW
202405-NM25-02920 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24780 | 6.8 | Residencial | Yes | 0-100kW
202511-NM25-01723 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00082 | 3.84 | Residencial | Yes | 0-100kW
202405-NM25-02514 | 8.052 | Residencial | Yes | 0-100kW
2023-GD-15106 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00592 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19626 | 8.78 | Residencial | Yes | 0-100kW
2022-GD-02742 | 6.22 | Residencial | Yes | 0-100kW
2020-GD-00806 | 5.015 | Residencial | Yes | 0-100kW
2023-GD-09206 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-26692 | 2.66 | Residencial | Yes | 0-100kW
202410-NM25-00488 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-11512 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-23728 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00859 | 4.43 | Residencial | Yes | 0-100kW
202503-NM25-04564 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-05732 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-03442 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-00844 | 4.608 | Residencial | Yes | 0-100kW
202501-NM25-04790 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-08534 | 2.95 | Residencial | Yes | 0-100kW
2023-GD-30466 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-00617 | 4.224 | Residencial | Yes | 0-100kW
202509-NM25-02315 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02573 | 4.25 | Residencial | Yes | 0-100kW
2022-GD-32220 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-34110 | 8.05 | Residencial | Yes | 0-100kW
2021-GD-04919 | 3.25 | Residencial | Yes | 0-100kW
202505-NM25-02993 | 5.76 | Residencial | Yes | 0-100kW
202503-NM25-05515 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-10776 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-30024 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32871 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-37649 | 3.66 | Residencial | No | 0-100kW
202504-NM25-04110 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-03379 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05000 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-29180 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-04484 | 4.13 | Residencial | Yes | 0-100kW
202408-NM25-04201 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22001 | 8.78 | Residencial | No | 0-100kW
2023-GD-05288 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-27702 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-26909 | 9.24 | Comercial | Yes | 0-100kW
202404-NM25-03785 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-02752 | 3.24 | Residencial | Yes | 0-100kW
202506-NM25-00496 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-18640 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01614 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-02913 | 6.954 | Residencial | Yes | 0-100kW
202410-NM25-02572 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-00852 | 15 | Residencial | Yes | 0-100kW
2020-GD-05003 | 3.24 | Residencial | Yes | 0-100kW
202506-NM25-03906 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-02375 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-04962 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-01527 | 3.66 | Residencial | Yes | 0-100kW
202408-NM25-00518 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-27142 | 3.3 | Residencial | Yes | 0-100kW
2022-GD-12115 | 8.42 | Residencial | Yes | 0-100kW
2021-GD-07660 | 4.03 | Residencial | Yes | 0-100kW
202403-NM25-00212 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01921 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-02002 | 5.5 | Residencial | Yes | 0-100kW
202401-NM25-01306 | 8.052 | Residencial | Yes | 0-100kW
2022-GD-19589 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-39181 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19244 | 6.9 | Residencial | Yes | 0-100kW
202506-NM25-04320 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-11419 | 14.75 | Residencial | Yes | 0-100kW
2022-GD-31935 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-13158 | 3.3 | Residencial | Yes | 0-100kW
202501-NM25-02949 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04068 | 8 | Residencial | Yes | 0-100kW
202502-NM25-04981 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-06088 | 14.64 | Residencial | No | 0-100kW
202404-NM25-00182 | 7.6 | Residencial | No | 0-100kW
202406-NM25-00512 | 6.222 | Residencial | Yes | 0-100kW
202503-NM25-00603 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06203 | 5.31 | Residencial | Yes | 0-100kW
202407-NM25-03975 | 2.928 | Residencial | Yes | 0-100kW
2022-GD-14552 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-20714 | 7.6 | Residencial | Yes | 0-100kW
15-3-632 | 9.75 | Residencial | Yes | 0-100kW
2023-GD-12841 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32470 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-08822 | 3.96 | Residencial | Yes | 0-100kW
2023-GD-12331 | 5 | Residencial | Yes | 0-100kW
202312-NM25-02875 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-18985 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33916 | 8 | Residencial | Yes | 0-100kW
202412-NM25-00563 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03785 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03862 | 7.68 | Residencial | Yes | 0-100kW
202507-NM25-00767 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-09538 | 15.2 | Residencial | Yes | 0-100kW
2020-GD-08366 | 5.5 | Residencial | Yes | 0-100kW
2023-GD-18392 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-22097 | 8.05 | Residencial | Yes | 0-100kW
202406-NM25-03224 | 15.2 | Comercial | Yes | 0-100kW
202503-NM25-01144 | 8.418 | Residencial | Yes | 0-100kW
2022-GD-01921 | 14.75 | Residencial | Yes | 0-100kW
2021-GD-01279 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-01423 | 3.24 | Residencial | Yes | 0-100kW
202407-NM25-03455 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35552 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-02429 | 4.76 | Residencial | Yes | 0-100kW
202402-NM25-03999 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-32272 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-18707 | 9.88 | Residencial | Yes | 0-100kW
15-3-428 | 5.38 | Residencial | Yes | 0-100kW
202410-NM25-03132 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23300 | 8.78 | Residencial | Yes | 0-100kW
2023-GD-18563 | 15.2 | Residencial | Yes | 0-100kW
202508-NM25-00122 | 11.5 | Residencial | Yes | 0-100kW
14-2-775 | 3.01 | Residencial | Yes | 0-100kW
2018-GD-00454 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-29714 | 9.22 | Residencial | Yes | 0-100kW
202411-NM25-00717 | 7.6 | Residencial | Yes | 0-100kW
14-3-629 | 5 | Residencial | Yes | 0-100kW
2022-GD-12345 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-00121 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03165 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26170 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-32124 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19746 | 4.03 | Residencial | Yes | 0-100kW
202509-NM25-01484 | 12 | Residencial | Yes | 0-100kW
202501-NM25-03901 | 6.8 | Residencial | Yes | 0-100kW
202503-NM25-05550 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03278 | 4.99 | Residencial | Yes | 0-100kW
202401-NM25-02499 | 8.052 | Residencial | No | 0-100kW
2022-GD-20672 | 5.86 | Residencial | Yes | 0-100kW
202505-NM25-03875 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-06676 | 4.39 | Residencial | Yes | 0-100kW
202508-NM25-02998 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-04171 | 2.928 | Residencial | Yes | 0-100kW
2022-GD-27008 | 6.59 | Residencial | Yes | 0-100kW
202407-NM25-02833 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13950 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36441 | 11.63 | Residencial | Yes | 0-100kW
2018-GD-01922 | 5.9 | Residencial | Yes | 0-100kW
202510-NM25-01329 | 8 | Residencial | Yes | 0-100kW
2020-GD-09224 | 3.24 | Residencial | Yes | 0-100kW
202408-NM25-04853 | 2.304 | Residencial | Yes | 0-100kW
2022-GD-02386 | 6.49 | Residencial | Yes | 0-100kW
202508-NM25-02209 | 11.136 | Residencial | Yes | 0-100kW
2023-GD-31816 | 3.8 | Residencial | Yes | 0-100kW
202409-NM25-02907 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03003 | 11.8 | Residencial | Yes | 0-100kW
2023-GD-35094 | 4.76 | Residencial | Yes | 0-100kW
2017-GD-01354 | 3.75 | Residencial | Yes | 0-100kW
202407-NM25-03634 | 9 | Residencial | Yes | 0-100kW
202509-NM25-04768 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-06771 | 5.12 | Residencial | Yes | 0-100kW
2022-GD-26017 | 6.22 | Residencial | Yes | 0-100kW
202411-NM25-01749 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01782 | 6.8 | Residencial | Yes | 0-100kW
202512-NM25-01979 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-02627 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-00847 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-17241 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26164 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-10094 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-12397 | 13.54 | Residencial | Yes | 0-100kW
2021-GD-03098 | 6.49 | Residencial | Yes | 0-100kW
16-3-973 | 5.16 | Residencial | Yes | 0-100kW
202410-NM25-01335 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12893 | 7.69 | Residencial | Yes | 0-100kW
2018-GD-00293 | 2.4 | Residencial | Yes | 0-100kW
202509-NM25-04403 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-00338 | 3.25 | Residencial | Yes | 0-100kW
202407-NM25-01837 | 7.6 | Residencial | Yes | 0-100kW
15-1-139 | 3.8 | Residencial | Yes | 0-100kW
202502-NM25-00311 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-02110 | 23 | Residencial | Yes | 0-100kW
202409-NM25-03545 | 5.21 | Residencial | Yes | 0-100kW
202510-NM25-00293 | 7.68 | Residencial | Yes | 0-100kW
202404-NM25-02114 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01157 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-01796 | 8 | Residencial | Yes | 0-100kW
2023-GD-29394 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-27919 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04008 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-03124 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-17668 | 5 | Residencial | Yes | 0-100kW
2023-GD-11341 | 6.5 | Residencial | Yes | 0-100kW
202407-NM25-04091 | 9 | Residencial | Yes | 0-100kW
2018-GD-00699 | 6.8 | Residencial | Yes | 0-100kW
202505-NM25-00436 | 8.784 | Residencial | Yes | 0-100kW
14-2-244 | 7.7 | Residencial | Yes | 0-100kW
2019-GD-01015 | 8.35 | Residencial | Yes | 0-100kW
2023-GD-10906 | 13.06 | Residencial | Yes | 0-100kW
2023-GD-19439 | 5 | Residencial | Yes | 0-100kW
202405-NM25-01833 | 3 | Residencial | Yes | 0-100kW
202402-NM25-00794 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-03112 | 8.56 | Residencial | Yes | 0-100kW
202509-NM25-04338 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-18099 | 9.15 | Residencial | No | 0-100kW
202409-NM25-04002 | 15.2 | Residencial | Yes | 0-100kW
202403-NM25-02382 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00522 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26003 | 6.59 | Residencial | Yes | 0-100kW
202403-NM25-02986 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06316 | 6.8 | Residencial | Yes | 0-100kW
202506-NM25-02443 | 15 | Residencial | Yes | 0-100kW
202312-NM25-01430 | 10.98 | Residencial | Yes | 0-100kW
2023-GD-19378 | 3.84 | Residencial | Yes | 0-100kW
202406-NM25-02029 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06420 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-12001 | 3.24 | Residencial | Yes | 0-100kW
202409-NM25-03271 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02109 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-15790 | 3.66 | Residencial | Yes | 0-100kW
202312-NM25-02895 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-24296 | 6.22 | Residencial | Yes | 0-100kW
2021-GD-01966 | 6.49 | Residencial | Yes | 0-100kW
2022-GD-19852 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-20414 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18582 | 4.76 | Residencial | Yes | 0-100kW
2017-GD-01668 | 3.75 | Residencial | Yes | 0-100kW
2022-GD-29458 | 8.35 | Residencial | Yes | 0-100kW
13-4-0218GD | 8 | Comercial | Yes | 0-100kW
2022-GD-26237 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-25055 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-26397 | 5.38 | Residencial | Yes | 0-100kW
2023-GD-12671 | 8 | Residencial | Yes | 0-100kW
202510-NM25-04169 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-01070 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15912 | 9.52 | Residencial | No | 0-100kW
202403-NM25-01023 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04301 | 4.992 | Residencial | Yes | 0-100kW
2023-GD-06243 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-02516 | 4.61 | Residencial | Yes | 0-100kW
202504-NM25-01331 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-01755 | 6 | Residencial | Yes | 0-100kW
2022-GD-06858 | 10.98 | Residencial | Yes | 0-100kW
202312-NM25-01770 | 5.856 | Residencial | Yes | 0-100kW
2023-GD-15751 | 4.39 | Residencial | Yes | 0-100kW
202504-NM25-04886 | 7.68 | Residencial | Yes | 0-100kW
202503-NM25-02954 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12910 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02594 | 9.516 | Residencial | Yes | 0-100kW
202406-NM25-03547 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04587 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04717 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07354 | 6.19 | Residencial | Yes | 0-100kW
202508-NM25-02690 | 23 | Residencial | Yes | 0-100kW
2018-GD-01969 | 4.72 | Residencial | Yes | 0-100kW
2021-GD-05623 | 9.88 | Residencial | Yes | 0-100kW
202410-NM25-02904 | 12 | Residencial | Yes | 0-100kW
202511-NM25-02027 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-14467 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03226 | 3.072 | Residencial | Yes | 0-100kW
202402-NM25-03835 | 8 | Residencial | Yes | 0-100kW
202503-NM25-05694 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-02617 | 4 | Residencial | Yes | 0-100kW
202502-NM25-04198 | 7.6 | Residencial | Yes | 0-100kW
202310-NM25-00295 | 6.222 | Residencial | Yes | 0-100kW
202504-NM25-03026 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-09404 | 6.19 | Residencial | Yes | 0-100kW
202407-NM25-03523 | 4.026 | Residencial | Yes | 0-100kW
2021-GD-13198 | 8 | Residencial | Yes | 0-100kW
202512-NM25-05642 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09167 | 5.86 | Residencial | Yes | 0-100kW
202503-NM25-03091 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-01281 | 6 | Residencial | Yes | 0-100kW
2022-GD-03471 | 3.66 | Residencial | Yes | 0-100kW
202502-NM25-02801 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-03890 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-33927 | 6 | Residencial | Yes | 0-100kW
2022-GD-18994 | 3.54 | Residencial | No | 0-100kW
2023-GD-07344 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-31898 | 8 | Residencial | Yes | 0-100kW
202310-NM25-00134 | 8.14 | Residencial | Yes | 0-100kW
202404-NM25-01408 | 5.49 | Residencial | Yes | 0-100kW
202501-NM25-04300 | 10.98 | Comercial | Yes | 0-100kW
202311-NM25-00220 | 4.758 | Residencial | Yes | 0-100kW
15-6-0043 | 4.51 | Comercial | Yes | 0-100kW
202411-NM25-01102 | 3.8 | Residencial | Yes | 0-100kW
202403-NM25-01064 | 5.856 | Residencial | Yes | 0-100kW
202312-NM25-01303 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13911 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-10071 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-37956 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-02982 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00102 | 3.25 | Residencial | Yes | 0-100kW
2022-GD-12607 | 5.12 | Residencial | Yes | 0-100kW
202410-NM25-04614 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-12217 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-03199 | 4.72 | Residencial | Yes | 0-100kW
202410-NM25-04885 | 6 | Residencial | Yes | 0-100kW
202512-NM25-01119 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-22038 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-04573 | 7.88 | Residencial | Yes | 0-100kW
2023-GD-03581 | 5.12 | Residencial | Yes | 0-100kW
202509-NM25-02109 | 8.448 | Residencial | Yes | 0-100kW
202404-NM25-02684 | 4.758 | Residencial | Yes | 0-100kW
2022-GD-11629 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-06529 | 5 | Residencial | Yes | 0-100kW
2023-GD-00467 | 5 | Residencial | Yes | 0-100kW
2019-GD-00680 | 8.35 | Residencial | Yes | 0-100kW
2021-GD-12453 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-01637 | 15 | Residencial | Yes | 0-100kW
202504-NM25-00893 | 5 | Residencial | Yes | 0-100kW
202410-NM25-04588 | 5.856 | Residencial | Yes | 0-100kW
202412-NM25-00412 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01522 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20297 | 4.03 | Residencial | Yes | 0-100kW
202412-NM25-03535 | 15.2 | Residencial | Yes | 0-100kW
202504-NM25-05367 | 7.6 | Residencial | Yes | 0-100kW
15-2-995 | 3.01 | Residencial | Yes | 0-100kW
202410-NM25-00648 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10918 | 6.75 | Residencial | Yes | 0-100kW
2017-GD-03482 | 5.16 | Residencial | Yes | 0-100kW
2022-GD-18360 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-05518 | 5 | Residencial | Yes | 0-100kW
202509-NM25-05027 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-00649 | 4.43 | Residencial | Yes | 0-100kW
2021-GD-00979 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-04389 | 4.13 | Residencial | Yes | 0-100kW
202512-NM25-00983 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-07567 | 4.03 | Residencial | Yes | 0-100kW
202507-NM25-02550 | 9.516 | Residencial | Yes | 0-100kW
2021-GD-03300 | 4.43 | Residencial | Yes | 0-100kW
2019-GD-02496 | 7.375 | Residencial | Yes | 0-100kW
202412-NM25-02119 | 12 | Residencial | Yes | 0-100kW
202502-NM25-02376 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03444 | 3.54 | Residencial | Yes | 0-100kW
202503-NM25-01696 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-06760 | 3.25 | Residencial | Yes | 0-100kW
2022-GD-26178 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-04236 | 3.29 | Residencial | Yes | 0-100kW
2022-GD-25095 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-28591 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-31082 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-23889 | 3.29 | Residencial | Yes | 0-100kW
2021-GD-14619 | 3.8 | Residencial | Yes | 0-100kW
202311-NM25-00372 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-21238 | 5 | Residencial | Yes | 0-100kW
202410-NM25-02020 | 3.84 | Comercial | Yes | 0-100kW
202410-NM25-04002 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04172 | 4.992 | Residencial | Yes | 0-100kW
202502-NM25-03603 | 7.6 | Residencial | Yes | 0-100kW
16-7-0589 | 4.73 | Residencial | Yes | 0-100kW
2022-GD-11637 | 8.42 | Residencial | Yes | 0-100kW
202311-NM25-00799 | 8.052 | Residencial | Yes | 0-100kW
2023-GD-28687 | 3.8 | Residencial | Yes | 0-100kW
202502-NM25-01098 | 11.712 | Residencial | Yes | 0-100kW
202502-NM25-00194 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-10897 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-09776 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-31632 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-10329 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-10788 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-05302 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-18718 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-03264 | 7.68 | Residencial | Yes | 0-100kW
2020-GD-07492 | 3.25 | Residencial | Yes | 0-100kW
2020-GD-04717 | 9.74 | Residencial | Yes | 0-100kW
2020-GD-02651 | 3.25 | Residencial | Yes | 0-100kW
2023-GD-25583 | 3.8 | Residencial | Yes | 0-100kW
202404-NM25-00154 | 4.29 | Residencial | Yes | 0-100kW
2021-GD-11892 | 5 | Residencial | Yes | 0-100kW
202404-NM25-00360 | 8 | Residencial | Yes | 0-100kW
202509-NM25-00516 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-13660 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00930 | 12.6 | Residencial | Yes | 0-100kW
202505-NM25-02190 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-04411 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-21189 | 3.8 | Residencial | Yes | 0-100kW
202505-NM25-04525 | 7.688 | Residencial | Yes | 0-100kW
2022-GD-01163 | 3.24 | Residencial | Yes | 0-100kW
202409-NM25-00965 | 2.928 | Residencial | Yes | 0-100kW
202511-NM25-02065 | 8 | Residencial | Yes | 0-100kW
202412-NM25-03921 | 2.928 | Residencial | Yes | 0-100kW
202407-NM25-02863 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-34601 | 4.03 | Residencial | Yes | 0-100kW
202311-NM25-00626 | 3.66 | Residencial | Yes | 0-100kW
202509-NM25-02270 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-00485 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-11924 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-32848 | 2.66 | Residencial | Yes | 0-100kW
2023-GD-04326 | 6 | Residencial | Yes | 0-100kW
202509-NM25-03296 | 8 | Residencial | Yes | 0-100kW
2017-GD-02639 | 7.5 | Residencial | Yes | 0-100kW
2022-GD-15677 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-16056 | 6.8 | Residencial | Yes | 0-100kW
2017-GD-01970 | 6.5 | Residencial | Yes | 0-100kW
202502-NM25-05929 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-03738 | 5.31 | Residencial | Yes | 0-100kW
2019-GD-01468 | 5.605 | Residencial | Yes | 0-100kW
202504-NM25-00485 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-03666 | 6.912 | Residencial | Yes | 0-100kW
2023-GD-14144 | 5 | Residencial | Yes | 0-100kW
202506-NM25-00299 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-04463 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01530 | 3.54 | Residencial | Yes | 0-100kW
202409-NM25-00816 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-09333 | 4.25 | Residencial | Yes | 0-100kW
2023-GD-38663 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09865 | 4.13 | Residencial | Yes | 0-100kW
202511-NM25-02251 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-01987 | 4.026 | Residencial | Yes | 0-100kW
202509-NM25-01303 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-32394 | 4.03 | Residencial | Yes | 0-100kW
16-4-0889GD | 9.03 | Residencial | Yes | 0-100kW
2021-GD-14267 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-30525 | 6 | Residencial | Yes | 0-100kW
2023-GD-24170 | 4.22 | Residencial | Yes | 0-100kW
202508-NM25-01536 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-30272 | 5 | Residencial | Yes | 0-100kW
2021-GD-12965 | 3.24 | Residencial | Yes | 0-100kW
202412-NM25-01231 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-26007 | 9.15 | Residencial | Yes | 0-100kW
2019-GD-00932 | 7.25 | Residencial | Yes | 0-100kW
2018-GD-01874 | 6.67 | Residencial | No | 0-100kW
202505-NM25-03778 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-03687 | 1.29 | Residencial | Yes | 0-100kW
2023-GD-29027 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-08215 | 3.25 | Residencial | Yes | 0-100kW
2023-GD-04600 | 13.25 | Residencial | Yes | 0-100kW
15-3-977 | 2.58 | Residencial | Yes | 0-100kW
2023-GD-35495 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-00678 | 6.588 | Residencial | Yes | 0-100kW
2022-GD-21038 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-07357 | 9 | Residencial | Yes | 0-100kW
202504-NM25-04719 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-03232 | 5.9 | Residencial | Yes | 0-100kW
202410-NM25-02711 | 15.2 | Residencial | Yes | 0-100kW
202411-NM25-02549 | 10 | Residencial | Yes | 0-100kW
2021-GD-05317 | 3.84 | Residencial | Yes | 0-100kW
202409-NM25-03826 | 21.83 | Residencial | Yes | 0-100kW
2023-GD-16351 | 3.66 | Residencial | Yes | 0-100kW
202408-NM25-02996 | 7.6 | Residencial | Yes | 0-100kW
16-7-1166 | 10 | Residencial | Yes | 0-100kW
2022-GD-27253 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-24644 | 5.12 | Residencial | Yes | 0-100kW
2019-GD-03393 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-17650 | 4.22 | Residencial | Yes | 0-100kW
202403-NM25-02334 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02099 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-05764 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04133 | 8 | Residencial | Yes | 0-100kW
2021-GD-12671 | 6.78 | Residencial | Yes | 0-100kW
202401-NM25-00511 | 4.392 | Residencial | Yes | 0-100kW
202409-NM25-04065 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03964 | 12.5 | Residencial | Yes | 0-100kW
202407-NM25-01290 | 4.992 | Residencial | Yes | 0-100kW
2021-GD-04254 | 9.15 | Residencial | Yes | 0-100kW
202407-NM25-00220 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-00165 | 16 | Residencial | Yes | 0-100kW
2020-GD-05890 | 3.25 | Residencial | Yes | 0-100kW
2022-GD-09283 | 5.12 | Residencial | Yes | 0-100kW
202404-NM25-00953 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-20676 | 9.15 | Residencial | Yes | 0-100kW
202403-NM25-03510 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32835 | 3.54 | Residencial | Yes | 0-100kW
202401-NM25-01038 | 2.928 | Residencial | Yes | 0-100kW
2022-GD-09020 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-16397 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-29097 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-07604 | 3.77 | Residencial | Yes | 0-100kW
2023-GD-15373 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07121 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-22975 | 4.03 | Residencial | Yes | 0-100kW
202401-NM25-01513 | 2.4 | Residencial | Yes | 0-100kW
2021-GD-05612 | 3.8 | Residencial | Yes | 0-100kW
202501-NM25-03010 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31285 | 9.6 | Residencial | Yes | 0-100kW
202312-NM25-00745 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36096 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-29436 | 5.12 | Residencial | Yes | 0-100kW
202408-NM25-01330 | 22.5 | Comercial | Yes | 0-100kW
17-4-0048GD | 3.7 | Residencial | Yes | 0-100kW
202409-NM25-00782 | 12 | Residencial | Yes | 0-100kW
2023-GD-10152 | 9.22 | Residencial | Yes | 0-100kW
2022-GD-17773 | 6.95 | Residencial | Yes | 0-100kW
202406-NM25-03432 | 7.32 | Residencial | Yes | 0-100kW
202502-NM25-04662 | 2.928 | Residencial | Yes | 0-100kW
202408-NM25-00361 | 15.2 | Residencial | Yes | 0-100kW
202502-NM25-02304 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-06782 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-13636 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00462 | 4.43 | Residencial | Yes | 0-100kW
202405-NM25-00362 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03998 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-25795 | 15 | Residencial | Yes | 0-100kW
202509-NM25-03444 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01500 | 2.928 | Residencial | Yes | 0-100kW
2020-GD-08340 | 5 | Residencial | Yes | 0-100kW
2023-GD-07846 | 7.26 | Residencial | Yes | 0-100kW
2022-GD-15351 | 5 | Residencial | Yes | 0-100kW
202410-NM25-02172 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-09110 | 8.45 | Residencial | Yes | 0-100kW
2022-GD-25487 | 4.03 | Residencial | Yes | 0-100kW
202403-NM25-01656 | 4.392 | Residencial | Yes | 0-100kW
202505-NM25-02652 | 11.4 | Residencial | Yes | 0-100kW
2020-GD-07744 | 5 | Comercial | Yes | 0-100kW
202312-NM25-00821 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-03387 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-10735 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-32514 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-12404 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-13089 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-04649 | 7.75 | Residencial | Yes | 0-100kW
202404-NM25-03044 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-22066 | 4.03 | Residencial | Yes | 0-100kW
202411-NM25-01138 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-26196 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-01236 | 5 | Residencial | Yes | 0-100kW
202404-NM25-02555 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06813 | 9.6 | Residencial | Yes | 0-100kW
2021-GD-04679 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-38409 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-36347 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22861 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03102 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-10023 | 3.66 | Residencial | Yes | 0-100kW
202410-NM25-00382 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03472 | 3.24 | Residencial | Yes | 0-100kW
202506-NM25-03309 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-28777 | 9 | Residencial | Yes | 0-100kW
2022-GD-03640 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-31852 | 5.12 | Residencial | Yes | 0-100kW
202508-NM25-00111 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-13446 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14640 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11824 | 4.43 | Residencial | Yes | 0-100kW
202410-NM25-03129 | 6 | Residencial | Yes | 0-100kW
202507-NM25-00391 | 13.908 | Residencial | Yes | 0-100kW
2023-GD-19137 | 5.12 | Residencial | Yes | 0-100kW
202512-NM25-00365 | 4.224 | Residencial | Yes | 0-100kW
2022-GD-17008 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-09177 | 7.6 | Residencial | Yes | 0-100kW
16-2-0280 | 11 | Residencial | Yes | 0-100kW
2023-GD-32535 | 8 | Residencial | Yes | 0-100kW
2017-GD-01413 | 7.095 | Residencial | Yes | 0-100kW
202409-NM25-02463 | 6 | Residencial | Yes | 0-100kW
2023-GD-38283 | 7.6 | Residencial | Yes | 0-100kW
202310-NM25-00481 | 8.784 | Residencial | Yes | 0-100kW
2023-GD-12917 | 5 | Residencial | Yes | 0-100kW
202402-NM25-03695 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03359 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02261 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-38996 | 3.84 | Residencial | Yes | 0-100kW
202409-NM25-00911 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-02562 | 9.516 | Residencial | Yes | 0-100kW
202407-NM25-03972 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06911 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-00968 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-01664 | 10 | Residencial | Yes | 0-100kW
2023-GD-32843 | 8.05 | Residencial | Yes | 0-100kW
202408-NM25-04525 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-04016 | 6 | Residencial | Yes | 0-100kW
14-2-946GD | 5.2 | Residencial | Yes | 0-100kW
2023-GD-25268 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02423 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05121 | 9.6 | Residencial | Yes | 0-100kW
202403-NM25-03671 | 19.032 | Residencial | Yes | 0-100kW
2022-GD-16264 | 8.85 | Residencial | Yes | 0-100kW
202511-NM25-01337 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-34259 | 6 | Residencial | Yes | 0-100kW
202401-NM25-01671 | 8.7 | Residencial | Yes | 0-100kW
2023-GD-19390 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02820 | 9 | Comercial | Yes | 0-100kW
16-3-409 | 6.24 | Residencial | Yes | 0-100kW
2022-GD-06898 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-01962 | 6.8 | Residencial | Yes | 0-100kW
202412-NM25-01669 | 8.448 | Residencial | Yes | 0-100kW
202401-NM25-00069 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01688 | 10 | Residencial | Yes | 0-100kW
202511-NM25-01018 | 12 | Residencial | Yes | 0-100kW
202507-NM25-00046 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03922 | 6.144 | Residencial | Yes | 0-100kW
2022-GD-20399 | 5.12 | Residencial | Yes | 0-100kW
2021-GD-09533 | 5.01 | Residencial | Yes | 0-100kW
202403-NM25-01068 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-22586 | 5 | Residencial | Yes | 0-100kW
202405-NM25-00249 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-34828 | 8 | Residencial | Yes | 0-100kW
2021-GD-09627 | 6.8 | Residencial | Yes | 0-100kW
2021-GD-11432 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-07170 | 5 | Residencial | Yes | 0-100kW
2020-GD-02472 | 9 | Residencial | Yes | 0-100kW
2023-GD-28700 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-03461 | 10.98 | Residencial | Yes | 0-100kW
2020-GD-03117 | 3.25 | Residencial | Yes | 0-100kW
202507-NM25-03988 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-13389 | 3.54 | Residencial | Yes | 0-100kW
202408-NM25-01037 | 4.026 | Residencial | Yes | 0-100kW
202407-NM25-01253 | 4.026 | Residencial | Yes | 0-100kW
202407-NM25-04250 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21104 | 8 | Residencial | Yes | 0-100kW
202503-NM25-05384 | 2.4 | Residencial | Yes | 0-100kW
202505-NM25-03112 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-13231 | 8.26 | Residencial | Yes | 0-100kW
2021-GD-11500 | 5.01 | Residencial | Yes | 0-100kW
15-3-831 | 2.79 | Residencial | Yes | 0-100kW
202509-NM25-04175 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-07333 | 7.67 | Residencial | Yes | 0-100kW
11-4-0097 | 2.16 | Residencial | Yes | 0-100kW
2021-GD-00318 | 6.8 | Residencial | Yes | 0-100kW
202506-NM25-04675 | 4.608 | Residencial | Yes | 0-100kW
202505-NM25-03214 | 9 | Residencial | Yes | 0-100kW
202402-NM25-03520 | 6.528 | Comercial | Yes | 0-100kW
2021-GD-06654 | 3.24 | Residencial | Yes | 0-100kW
202511-NM25-01259 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02402 | 5.376 | Comercial | Yes | 0-100kW
2023-GD-25696 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05409 | 5.01 | Residencial | Yes | 0-100kW
202312-NM25-03672 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-00035 | 8.8 | Residencial | Yes | 0-100kW
2020-GD-06745 | 6 | Residencial | Yes | 0-100kW
202410-NM25-03257 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02419 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-04133 | 6 | Residencial | Yes | 0-100kW
2022-GD-23760 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-29214 | 6 | Residencial | Yes | 0-100kW
202411-NM25-02622 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-04078 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-00170 | 3.655 | Residencial | Yes | 0-100kW
16-4-0534GD | 3.12 | Residencial | No | 0-100kW
202412-NM25-03226 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-04289 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-07818 | 2.95 | Residencial | Yes | 0-100kW
202402-NM25-02074 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01972 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-03581 | 4.026 | Residencial | Yes | 0-100kW
2020-GD-05966 | 6.8 | Residencial | Yes | 0-100kW
2021-GD-05620 | 5.01 | Residencial | Yes | 0-100kW
202412-NM25-00432 | 2.928 | Residencial | Yes | 0-100kW
202512-NM25-06140 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-05641 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-10362 | 5.12 | Residencial | No | 0-100kW
202508-NM25-02064 | 5.376 | Residencial | Yes | 0-100kW
202403-NM25-00315 | 6 | Residencial | Yes | 0-100kW
2021-GD-00013 | 9.88 | Residencial | Yes | 0-100kW
2023-GD-25904 | 8 | Residencial | Yes | 0-100kW
202403-NM25-00500 | 7.6 | Comercial | Yes | 0-100kW
202502-NM25-03138 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-01257 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13738 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-13768 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-12963 | 3.24 | Residencial | Yes | 0-100kW
202503-NM25-00826 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36549 | 5.38 | Residencial | No | 0-100kW
202501-NM25-02248 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15172 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01347 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13000 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00015 | 5.75 | Residencial | Yes | 0-100kW
202504-NM25-00976 | 5.494 | Residencial | Yes | 0-100kW
202411-NM25-03159 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02557 | 4.758 | Residencial | Yes | 0-100kW
2023-GD-05715 | 3.66 | Residencial | No | 0-100kW
202403-NM25-00302 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08703 | 6.19 | Residencial | Yes | 0-100kW
2023-GD-38533 | 5.76 | Comercial | Yes | 0-100kW
2023-GD-11274 | 2.5 | Residencial | Yes | 0-100kW
2022-GD-05214 | 6.19 | Residencial | Yes | 0-100kW
202407-NM25-00138 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02960 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-03232 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-17543 | 5 | Residencial | Yes | 0-100kW
2022-GD-17778 | 15 | Residencial | Yes | 0-100kW
202406-NM25-00695 | 4.758 | Residencial | Yes | 0-100kW
202401-NM25-01468 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00135 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02699 | 3.8 | Residencial | Yes | 0-100kW
202409-NM25-01891 | 3.294 | Residencial | Yes | 0-100kW
2023-GD-28340 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-04250 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-00035 | 9.145 | Residencial | Yes | 0-100kW
202509-NM25-02566 | 11.5 | Residencial | Yes | 0-100kW
16-3-061 | 2.58 | Residencial | Yes | 0-100kW
2022-GD-04315 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-28952 | 5.12 | Residencial | Yes | 0-100kW
202501-NM25-03908 | 4.992 | Residencial | Yes | 0-100kW
202410-NM25-01660 | 8 | Residencial | Yes | 0-100kW
202507-NM25-04090 | 7.68 | Residencial | Yes | 0-100kW
2020-GD-01174 | 5.25 | Residencial | Yes | 0-100kW
202502-NM25-06988 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-29033 | 4.22 | Residencial | Yes | 0-100kW
2020-GD-05961 | 5.9 | Residencial | Yes | 0-100kW
202407-NM25-00512 | 3.8 | Residencial | Yes | 0-100kW
15-3-740 | 7 | Residencial | Yes | 0-100kW
2022-GD-08491 | 5.49 | Residencial | Yes | 0-100kW
202402-NM25-02029 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01643 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00455 | 3.01 | Residencial | Yes | 0-100kW
202411-NM25-00901 | 8.832 | Residencial | Yes | 0-100kW
202402-NM25-03530 | 8.784 | Residencial | Yes | 0-100kW
202502-NM25-01385 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-00889 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-04167 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-03042 | 4.61 | Residencial | Yes | 0-100kW
202508-NM25-05053 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-15862 | 8 | Residencial | Yes | 0-100kW
2023-GD-17892 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14277 | 7.75 | Residencial | Yes | 0-100kW
2022-GD-31553 | 6.95 | Residencial | Yes | 0-100kW
202406-NM25-01976 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-14354 | 5 | Residencial | Yes | 0-100kW
2022-GD-30557 | 5 | Residencial | Yes | 0-100kW
202511-NM25-02779 | 11.5 | Residencial | Yes | 0-100kW
11-3-011 | 6 | Residencial | Yes | 0-100kW
2023-GD-30218 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-26521 | 15 | Residencial | Yes | 0-100kW
202309-NM25-00012 | 5.18 | Residencial | Yes | 0-100kW
202412-NM25-02137 | 8.298 | Residencial | Yes | 0-100kW
202501-NM25-04916 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-01764 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-01234 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-01393 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02484 | 4.392 | Residencial | Yes | 0-100kW
202509-NM25-04272 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-00825 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-03273 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-05393 | 6 | Residencial | Yes | 0-100kW
2025-GD-00193 | 33.3 | Comercial | No | 0-100kW
202405-NM25-01452 | 5.76 | Residencial | No | 0-100kW
202312-NM25-02337 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11805 | 4.03 | Residencial | Yes | 0-100kW
202511-NM25-03189 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-02664 | 9.516 | Residencial | Yes | 0-100kW
2022-GD-12313 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-21614 | 8 | Residencial | Yes | 0-100kW
2023-GD-06014 | 6.95 | Residencial | Yes | 0-100kW
202408-NM25-05004 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01516 | 8.26 | Comercial | Yes | 0-100kW
202508-NM25-01297 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-01881 | 6.8 | Residencial | Yes | 0-100kW
202406-NM25-00115 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-07773 | 4.03 | Residencial | Yes | 0-100kW
202510-NM25-00713 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-18058 | 4.03 | Residencial | Yes | 0-100kW
2017-GD-01039 | 8.5 | Residencial | Yes | 0-100kW
202403-NM25-00914 | 2.928 | Residencial | Yes | 0-100kW
16-3-277 | 2.58 | Residencial | Yes | 0-100kW
2022-GD-32494 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32519 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05152 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-04591 | 5 | Residencial | Yes | 0-100kW
2021-GD-11580 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14866 | 9.15 | Residencial | Yes | 0-100kW
2020-GD-07580 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-17404 | 5.12 | Residencial | Yes | 0-100kW
202410-NM25-03027 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28699 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14900 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-22115 | 5.12 | Residencial | Yes | 0-100kW
2022-GD-06397 | 5 | Residencial | Yes | 0-100kW
2022-GD-14973 | 8.42 | Residencial | Yes | 0-100kW
202512-NM25-01049 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-02989 | 7.296 | Residencial | Yes | 0-100kW
2023-GD-05701 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-12839 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-03582 | 8 | Residencial | Yes | 0-100kW
2021-GD-00564 | 7.08 | Residencial | No | 0-100kW
202409-NM25-02007 | 6 | Residencial | Yes | 0-100kW
2023-GD-34405 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-02481 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-02275 | 8 | Residencial | Yes | 0-100kW
2023-GD-35994 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02860 | 6 | Residencial | Yes | 0-100kW
2022-GD-09941 | 6.22 | Residencial | Yes | 0-100kW
202507-NM25-02893 | 9.6 | Residencial | Yes | 0-100kW
202506-NM25-01578 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-02026 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-02608 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-13264 | 11.63 | Residencial | Yes | 0-100kW
202411-NM25-03606 | 6.222 | Residencial | Yes | 0-100kW
202502-NM25-06804 | 11.63 | Residencial | Yes | 0-100kW
2022-GD-14344 | 6.22 | Residencial | Yes | 0-100kW
2019-GD-02630 | 2.95 | Residencial | Yes | 0-100kW
202511-NM25-00514 | 3.84 | Residencial | Yes | 0-100kW
202407-NM25-01591 | 5.49 | Residencial | Yes | 0-100kW
2021-GD-14649 | 4.43 | Residencial | Yes | 0-100kW
16-2-0066 | 5.59 | Residencial | Yes | 0-100kW
202406-NM25-02845 | 4.758 | Residencial | Yes | 0-100kW
202410-NM25-03097 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13906 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-02412 | 5.86 | Residencial | Yes | 0-100kW
202410-NM25-00733 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02234 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-09053 | 21.83 | Comercial | Yes | 0-100kW
202409-NM25-01254 | 5.856 | Residencial | Yes | 0-100kW
202509-NM25-01429 | 3.84 | Residencial | Yes | 0-100kW
2019-GD-02614 | 7.08 | Residencial | Yes | 0-100kW
202512-NM25-00885 | 12 | Residencial | Yes | 0-100kW
2023-GD-28574 | 10.25 | Residencial | No | 0-100kW
202401-NM25-02968 | 4.392 | Residencial | Yes | 0-100kW
202406-NM25-02088 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-39414 | 3.63 | Residencial | Yes | 0-100kW
202409-NM25-04096 | 3.3 | Residencial | Yes | 0-100kW
202407-NM25-02357 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-23259 | 12 | Residencial | Yes | 0-100kW
202507-NM25-02242 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-01828 | 12 | Residencial | Yes | 0-100kW
2017-GD-02121 | 4.25 | Residencial | Yes | 0-100kW
202312-NM25-01081 | 3.66 | Residencial | Yes | 0-100kW
202405-NM25-04146 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03881 | 8 | Residencial | Yes | 0-100kW
2022-GD-25760 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35478 | 4.22 | Residencial | Yes | 0-100kW
2022-GD-09673 | 5 | Residencial | Yes | 0-100kW
202509-NM25-04639 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-16384 | 6.6 | Residencial | Yes | 0-100kW
2017-GD-00098 | 3.25 | Residencial | Yes | 0-100kW
2021-GD-03557 | 3.54 | Residencial | Yes | 0-100kW
15-6-0061 | 9 | Residencial | Yes | 0-100kW
2022-GD-18191 | 4.39 | Residencial | Yes | 0-100kW
2024-GD-00082 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-01385 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-01783 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-00843 | 12.1 | Residencial | Yes | 0-100kW
202412-NM25-03534 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-01118 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-00934 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-01560 | 4.03 | Residencial | Yes | 0-100kW
202512-NM25-05043 | 17.64 | Residencial | Yes | 0-100kW
16-2-0297 | 5.37 | Residencial | Yes | 0-100kW
2021-GD-12347 | 5.9 | Residencial | Yes | 0-100kW
202505-NM25-01681 | 6.912 | Residencial | Yes | 0-100kW
2021-GD-15076 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-30067 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03513 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-11030 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-13167 | 5.86 | Residencial | Yes | 0-100kW
202501-NM25-00137 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-02215 | 5.76 | Residencial | Yes | 0-100kW
202408-NM25-04677 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-03393 | 8 | Residencial | Yes | 0-100kW
202511-NM25-00896 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-01508 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01523 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03560 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01750 | 8 | Residencial | Yes | 0-100kW
202506-NM25-04531 | 6.954 | Residencial | Yes | 0-100kW
2022-GD-09489 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-32804 | 4.76 | Residencial | Yes | 0-100kW
202404-NM25-01468 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-05322 | 3.54 | Residencial | Yes | 0-100kW
202411-NM25-01363 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03676 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-09498 | 2.95 | Residencial | Yes | 0-100kW
2022-GD-13832 | 10 | Residencial | Yes | 0-100kW
202403-NM25-00602 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-02931 | 3.8 | Residencial | Yes | 0-100kW
202408-NM25-01760 | 4.758 | Residencial | Yes | 0-100kW
202408-NM25-03023 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-08278 | 2.95 | Residencial | Yes | 0-100kW
2022-GD-23235 | 5.12 | Residencial | Yes | 0-100kW
202409-NM25-04416 | 10.614 | Residencial | Yes | 0-100kW
202508-NM25-02686 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05613 | 4.72 | Residencial | Yes | 0-100kW
202507-NM25-01564 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-03496 | 3.072 | Residencial | Yes | 0-100kW
202505-NM25-00591 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32602 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-02711 | 5 | Residencial | Yes | 0-100kW
2021-GD-03447 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-05984 | 6.59 | Residencial | Yes | 0-100kW
2017-GD-01664 | 6.45 | Residencial | Yes | 0-100kW
2022-GD-16909 | 4.39 | Residencial | Yes | 0-100kW
202410-NM25-01280 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-35070 | 8 | Residencial | No | 0-100kW
2023-GD-37947 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-03171 | 4.392 | Residencial | Yes | 0-100kW
202503-NM25-00297 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32480 | 6.22 | Residencial | Yes | 0-100kW
202503-NM25-00602 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-05669 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-03526 | 10 | Residencial | Yes | 0-100kW
2022-GD-18234 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-01158 | 5.9 | Residencial | Yes | 0-100kW
2021-GD-09070 | 4.72 | Residencial | Yes | 0-100kW
16-3-152 | 3 | Residencial | Yes | 0-100kW
202404-NM25-03860 | 12.074 | Residencial | Yes | 0-100kW
2022-GD-15167 | 5 | Residencial | Yes | 0-100kW
2022-GD-13337 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-15213 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-06676 | 4.72 | Residencial | Yes | 0-100kW
202510-NM25-03414 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22813 | 4.61 | Residencial | Yes | 0-100kW
2022-GD-28426 | 9.6 | Residencial | Yes | 0-100kW
202510-NM25-03252 | 15 | Residencial | Yes | 0-100kW
202503-NM25-05117 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-00713 | 4.43 | Residencial | Yes | 0-100kW
2021-GD-10160 | 10.61 | Residencial | Yes | 0-100kW
2021-GD-12541 | 2.66 | Residencial | Yes | 0-100kW
202502-NM25-00977 | 8 | Residencial | No | 0-100kW
202504-NM25-05883 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-00030 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07340 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-25807 | 4.03 | Residencial | Yes | 0-100kW
202510-NM25-01787 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-02523 | 3.25 | Residencial | Yes | 0-100kW
202408-NM25-00938 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-05543 | 3.54 | Residencial | Yes | 0-100kW
202504-NM25-00312 | 7.6 | Residencial | Yes | 0-100kW
16-7-0030 | 2.79 | Residencial | Yes | 0-100kW
202403-NM25-01375 | 4.026 | Residencial | Yes | 0-100kW
15-5-0116A | 2.5 | Residencial | Yes | 0-100kW
202502-NM25-04259 | 9.15 | Residencial | Yes | 0-100kW
202410-NM25-02141 | 8 | Residencial | Yes | 0-100kW
202511-NM25-01232 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11170 | 3.54 | Residencial | Yes | 0-100kW
2017-GD-00400 | 5.5 | Residencial | Yes | 0-100kW
202501-NM25-05590 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02686 | 5.76 | Residencial | Yes | 0-100kW
202406-NM25-00707 | 8 | Residencial | Yes | 0-100kW
2022-GD-30007 | 9.6 | Residencial | Yes | 0-100kW
202403-NM25-01040 | 8 | Residencial | Yes | 0-100kW
202511-NM25-00164 | 4.992 | Residencial | No | 0-100kW
2020-GD-00075 | 3.245 | Residencial | Yes | 0-100kW
202411-NM25-03469 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03800 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02943 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-04663 | 20.44 | Comercial | Yes | 0-100kW
202403-NM25-00377 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01163 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-28038 | 7.38 | Residencial | Yes | 0-100kW
202406-NM25-00122 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-00291 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-08149 | 7.08 | Residencial | Yes | 0-100kW
2022-GD-09618 | 5 | Residencial | Yes | 0-100kW
202409-NM25-04088 | 9 | Residencial | Yes | 0-100kW
2022-GD-24100 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-27957 | 8 | Residencial | Yes | 0-100kW
202404-NM25-01939 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02213 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-13694 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-24574 | 7.8 | Residencial | Yes | 0-100kW
2020-GD-05747 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00967 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32639 | 5 | Residencial | Yes | 0-100kW
202502-NM25-03238 | 10.98 | Residencial | Yes | 0-100kW
202508-NM25-02757 | 8 | Residencial | Yes | 0-100kW
16-3-144 | 3.87 | Residencial | Yes | 0-100kW
202404-NM25-02715 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01519 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01013 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-11680 | 3.84 | Residencial | Yes | 0-100kW
202402-NM25-03006 | 2.304 | Residencial | Yes | 0-100kW
2023-GD-31505 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02959 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03088 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-17250 | 5.12 | Residencial | Yes | 0-100kW
202408-NM25-04745 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24671 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-05189 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-32864 | 4.03 | Residencial | Yes | 0-100kW
202506-NM25-04091 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-00573 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02616 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03224 | 11.4 | Residencial | Yes | 0-100kW
2023-GD-34997 | 6.59 | Residencial | Yes | 0-100kW
202504-NM25-01646 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-03865 | 7.85 | Residencial | Yes | 0-100kW
2017-GD-03384 | 5 | Residencial | Yes | 0-100kW
202404-NM25-02499 | 5.376 | Residencial | Yes | 0-100kW
202404-NM25-03470 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-12774 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00628 | 7.79 | Residencial | Yes | 0-100kW
2020-GD-01110 | 3.245 | Residencial | Yes | 0-100kW
2020-GD-07168 | 4.75 | Residencial | Yes | 0-100kW
2017-GD-00483 | 5 | Residencial | Yes | 0-100kW
2023-GD-34510 | 10.98 | Residencial | Yes | 0-100kW
2022-GD-14901 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-07852 | 5 | Residencial | Yes | 0-100kW
202503-NM25-03217 | 9 | Residencial | Yes | 0-100kW
202406-NM25-01114 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-05150 | 4.392 | Residencial | Yes | 0-100kW
202501-NM25-01045 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14670 | 4.22 | Residencial | Yes | 0-100kW
202411-NM25-00581 | 7.2 | Residencial | Yes | 0-100kW
2022-GD-19402 | 8.78 | Residencial | No | 0-100kW
2022-GD-16373 | 5.5 | Residencial | Yes | 0-100kW
202409-NM25-01443 | 6.144 | Residencial | Yes | 0-100kW
2023-GD-12408 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-02205 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-03077 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01274 | 5 | Residencial | Yes | 0-100kW
2023-GD-33857 | 18.3 | Residencial | Yes | 0-100kW
202511-NM25-03007 | 11.5 | Residencial | Yes | 0-100kW
15-3-1241 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-06195 | 5.49 | Residencial | Yes | 0-100kW
202409-NM25-01088 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-00289 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03682 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11139 | 3.07 | Residencial | Yes | 0-100kW
202402-NM25-01297 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-16286 | 7.69 | Residencial | Yes | 0-100kW
202505-NM25-03217 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24237 | 6.22 | Residencial | Yes | 0-100kW
202503-NM25-05067 | 2.928 | Residencial | Yes | 0-100kW
202410-NM25-02916 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27997 | 5.86 | Residencial | Yes | 0-100kW
202407-NM25-00441 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02476 | 4.758 | Residencial | Yes | 0-100kW
2019-GD-35009 | 5 | Residencial | Yes | 0-100kW
202507-NM25-00948 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-20968 | 4.03 | Residencial | Yes | 0-100kW
202403-NM25-00329 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05615 | 3.25 | Residencial | Yes | 0-100kW
202502-NM25-04052 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04095 | 8.35 | Residencial | Yes | 0-100kW
202405-NM25-00119 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-03856 | 4.99 | Residencial | Yes | 0-100kW
2021-GD-07118 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-11398 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-28002 | 7.32 | Residencial | Yes | 0-100kW
202402-NM25-02105 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-02999 | 4.72 | Residencial | Yes | 0-100kW
202403-NM25-02043 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02684 | 6 | Residencial | Yes | 0-100kW
202503-NM25-00986 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-06917 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03605 | 7.67 | Residencial | Yes | 0-100kW
2022-GD-12757 | 11.43 | Residencial | Yes | 0-100kW
202504-NM25-00384 | 2.688 | Residencial | Yes | 0-100kW
2017-GD-03115 | 3.75 | Residencial | Yes | 0-100kW
2022-GD-21343 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-10327 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-00343 | 5.5 | Residencial | Yes | 0-100kW
202511-NM25-01161 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03449 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14175 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-04258 | 3.84 | Residencial | Yes | 0-100kW
202406-NM25-02337 | 10.248 | Residencial | Yes | 0-100kW
2022-GD-20041 | 4.39 | Residencial | Yes | 0-100kW
202510-NM25-03790 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01444 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-01073 | 4.026 | Residencial | Yes | 0-100kW
202505-NM25-00834 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-00462 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04211 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36221 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-25015 | 4.03 | Residencial | Yes | 0-100kW
202402-NM25-03066 | 8 | Residencial | Yes | 0-100kW
202506-NM25-03395 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-06671 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-08997 | 5 | Residencial | Yes | 0-100kW
202409-NM25-01226 | 8 | Residencial | Yes | 0-100kW
2023-GD-10593 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-00454 | 10 | Residencial | Yes | 0-100kW
2022-GD-26182 | 7.32 | Residencial | Yes | 0-100kW
202311-NM25-00383 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-02536 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02814 | 10.98 | Comercial | Yes | 0-100kW
GD-16-1-430 | 6.45 | Residencial | Yes | 0-100kW
202407-NM25-01992 | 10 | Residencial | Yes | 0-100kW
202402-NM25-01840 | 4.608 | Residencial | Yes | 0-100kW
202506-NM25-00308 | 15.2 | Residencial | Yes | 0-100kW
2020-GD-03416 | 6.8 | Residencial | Yes | 0-100kW
202508-NM25-02406 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-18059 | 10.98 | Comercial | Yes | 0-100kW
2023-GD-22380 | 8 | Residencial | Yes | 0-100kW
2017-GD-01692 | 2.25 | Residencial | Yes | 0-100kW
202409-NM25-01884 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03439 | 7.38 | Residencial | Yes | 0-100kW
202512-NM25-01544 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-33416 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18756 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-03943 | 9 | Residencial | Yes | 0-100kW
202502-NM25-03272 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04138 | 9.15 | Residencial | Yes | 0-100kW
202501-NM25-00684 | 12 | Residencial | Yes | 0-100kW
2022-GD-15389 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-36043 | 6.8 | Residencial | Yes | 0-100kW
202408-NM25-02575 | 8 | Residencial | Yes | 0-100kW
2021-GD-06543 | 11.63 | Residencial | Yes | 0-100kW
2022-GD-29498 | 5.86 | Residencial | Yes | 0-100kW
202502-NM25-02523 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-28526 | 4.03 | Residencial | Yes | 0-100kW
14-6-0283 | 6 | Residencial | Yes | 0-100kW
2022-GD-28634 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-02227 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-00191 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02562 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05378 | 3.5 | Residencial | Yes | 0-100kW
202508-NM25-05378 | 5.3 | Comercial | Yes | 0-100kW
2022-GD-19715 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-08279 | 5 | Residencial | Yes | 0-100kW
202503-NM25-00988 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20737 | 5.86 | Residencial | Yes | 0-100kW
202401-NM25-04033 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03399 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21036 | 4.03 | Residencial | Yes | 0-100kW
202407-NM25-03731 | 7.08 | Residencial | Yes | 0-100kW
2022-GD-23926 | 4.43 | Residencial | Yes | 0-100kW
2020-GD-01718 | 5.5 | Residencial | Yes | 0-100kW
202409-NM25-01933 | 5.124 | Residencial | Yes | 0-100kW
2022-GD-09509 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-25981 | 2.66 | Residencial | Yes | 0-100kW
202401-NM25-04586 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-01417 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-33037 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16602 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-26501 | 3.8 | Residencial | Yes | 0-100kW
202403-NM25-00392 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05292 | 2.562 | Residencial | Yes | 0-100kW
202505-NM25-05277 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-16828 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-04380 | 5.9 | Residencial | Yes | 0-100kW
202411-NM25-02791 | 9.036 | Residencial | Yes | 0-100kW
2019-GD-00757 | 8.35 | Residencial | Yes | 0-100kW
202502-NM25-06285 | 6.528 | Residencial | Yes | 0-100kW
2020-GD-08021 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-01052 | 5.61 | Residencial | No | 0-100kW
202507-NM25-02789 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00284 | 7 | Residencial | Yes | 0-100kW
15-6-0441 | 6.67 | Residencial | Yes | 0-100kW
2022-GD-18170 | 8.42 | Residencial | Yes | 0-100kW
202312-NM25-03056 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-04187 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-23171 | 7.32 | Residencial | Yes | 0-100kW
202401-NM25-01278 | 3.294 | Residencial | Yes | 0-100kW
2022-GD-01551 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-04706 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-04349 | 5 | Residencial | Yes | 0-100kW
202402-NM25-00989 | 8.418 | Residencial | Yes | 0-100kW
202405-NM25-04050 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-11557 | 5 | Residencial | Yes | 0-100kW
202501-NM25-00506 | 3.8 | Residencial | Yes | 0-100kW
202501-NM25-01618 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-20601 | 16 | Comercial | Yes | 0-100kW
2023-GD-14499 | 4.72 | Residencial | Yes | 0-100kW
202407-NM25-04192 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-03791 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28051 | 3.66 | Residencial | Yes | 0-100kW
2019-GD-00980 | 3 | Residencial | Yes | 0-100kW
202509-NM25-04972 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-00439 | 3.84 | Residencial | Yes | 0-100kW
202401-NM25-03821 | 9 | Residencial | Yes | 0-100kW
202506-NM25-04208 | 6.912 | Residencial | Yes | 0-100kW
202511-NM25-02528 | 11.5 | Residencial | No | 0-100kW
2021-GD-01006 | 4.72 | Residencial | Yes | 0-100kW
2023-GD-00109 | 5.49 | Residencial | Yes | 0-100kW
16-7-0350 | 6.67 | Residencial | Yes | 0-100kW
2023-GD-03989 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-14298 | 4.03 | Residencial | Yes | 0-100kW
202409-NM25-02725 | 15.2 | Residencial | Yes | 0-100kW
202312-NM25-03169 | 8.784 | Residencial | Yes | 0-100kW
202508-NM25-04667 | 3.84 | Residencial | Yes | 0-100kW
202405-NM25-01984 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-36950 | 13.18 | Residencial | Yes | 0-100kW
202410-NM25-03232 | 11.4 | Residencial | Yes | 0-100kW
2021-GD-02654 | 6.49 | Residencial | Yes | 0-100kW
202401-NM25-02354 | 12 | Comercial | Yes | 0-100kW
2023-GD-01585 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06649 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-04396 | 4.76 | Residencial | Yes | 0-100kW
08-7-316 | 6.25 | Residencial | Yes | 0-100kW
2023-GD-08797 | 5.12 | Residencial | Yes | 0-100kW
202404-NM25-00602 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03991 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-26470 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-04290 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-14266 | 15.2 | Residencial | Yes | 0-100kW
202511-NM25-01389 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12330 | 8 | Residencial | Yes | 0-100kW
2022-GD-12890 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-00614 | 5.76 | Residencial | Yes | 0-100kW
202312-NM25-03384 | 6.954 | Residencial | Yes | 0-100kW
202507-NM25-01199 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00399 | 4.758 | Residencial | Yes | 0-100kW
202507-NM25-00254 | 5.376 | Residencial | Yes | 0-100kW
202409-NM25-01846 | 7.686 | Residencial | No | 0-100kW
2022-GD-22575 | 6.22 | Residencial | Yes | 0-100kW
2021-GD-10532 | 8.364 | Residencial | Yes | 0-100kW
202412-NM25-01408 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12818 | 5.9 | Residencial | Yes | 0-100kW
202402-NM25-02209 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00947 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-02605 | 1.83 | Residencial | Yes | 0-100kW
2019-GD-00670 | 10.325 | Residencial | Yes | 0-100kW
2018-GD-00720 | 6.24 | Residencial | Yes | 0-100kW
202412-NM25-01587 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00163 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-32692 | 5.86 | Residencial | Yes | 0-100kW
2020-GD-06575 | 5.5 | Residencial | Yes | 0-100kW
2023-GD-12969 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-24347 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02172 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32716 | 4.76 | Residencial | Yes | 0-100kW
202410-NM25-01821 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35673 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-01064 | 4.72 | Residencial | Yes | 0-100kW
2023-GD-29463 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03816 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-04758 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-03878 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-18221 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03089 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-04251 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-28535 | 9.6 | Residencial | Yes | 0-100kW
2020-GD-00484 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-22569 | 2.25 | Residencial | Yes | 0-100kW
2023-GD-30055 | 6.59 | Residencial | Yes | 0-100kW
2018-GD-01819 | 10 | Residencial | Yes | 0-100kW
202406-NM25-02158 | 6 | Residencial | Yes | 0-100kW
2023-GD-06383 | 2.93 | Residencial | Yes | 0-100kW
2023-GD-17553 | 10.98 | Residencial | Yes | 0-100kW
2021-GD-06209 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06722 | 6.49 | Residencial | Yes | 0-100kW
2022-GD-31988 | 10.05 | Comercial | Yes | 0-100kW
202509-NM25-01363 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-00567 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32151 | 7.6 | Residencial | Yes | 0-100kW
16-2-0543 | 7.7 | Residencial | Yes | 0-100kW
2022-GD-09503 | 10 | Residencial | Yes | 0-100kW
2023-GD-31200 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15142 | 4.03 | Residencial | Yes | 0-100kW
2017-GD-03297 | 6 | Residencial | Yes | 0-100kW
2021-GD-05362 | 5.01 | Residencial | Yes | 0-100kW
202401-NM25-03565 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-03371 | 4 | Residencial | Yes | 0-100kW
2023-GD-15658 | 3.3 | Residencial | Yes | 0-100kW
202501-NM25-02318 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-01496 | 9.516 | Residencial | No | 0-100kW
2023-GD-39238 | 15 | Comercial | Yes | 0-100kW
202312-NM25-03190 | 6.222 | Residencial | Yes | 0-100kW
2023-GD-02393 | 24 | Comercial | Yes | 0-100kW
2022-GD-14854 | 4.03 | Residencial | Yes | 0-100kW
202506-NM25-02624 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02987 | 14.48 | Residencial | Yes | 0-100kW
2023-GD-13991 | 9 | Residencial | Yes | 0-100kW
202406-NM25-02136 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-04025 | 3.8 | Residencial | Yes | 0-100kW
16-4-1084GD | 3.65 | Residencial | Yes | 0-100kW
2022-GD-10937 | 4.03 | Residencial | Yes | 0-100kW
202503-NM25-02187 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-00573 | 8 | Residencial | Yes | 0-100kW
202408-NM25-01076 | 3.9 | Residencial | Yes | 0-100kW
2021-GD-11040 | 7.38 | Residencial | Yes | 0-100kW
202501-NM25-02999 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01363 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-02326 | 10.244 | Residencial | Yes | 0-100kW
202504-NM25-04585 | 8.448 | Residencial | Yes | 0-100kW
202404-NM25-02733 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-29734 | 5 | Residencial | Yes | 0-100kW
202501-NM25-02494 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04102 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-00718 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17693 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-16285 | 10 | Residencial | Yes | 0-100kW
2022-GD-08063 | 4.03 | Residencial | Yes | 0-100kW
202412-NM25-03507 | 9 | Residencial | Yes | 0-100kW
202508-NM25-03296 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-07205 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-23518 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-05665 | 2.95 | Residencial | Yes | 0-100kW
2023-GD-33168 | 6 | Residencial | Yes | 0-100kW
14-3-1048 | 5 | Residencial | Yes | 0-100kW
2017-GD-02219 | 6.75 | Residencial | Yes | 0-100kW
2020-GD-06412 | 3.25 | Residencial | Yes | 0-100kW
2023-GD-11168 | 17.7 | Comercial | Yes | 0-100kW
2022-GD-14518 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-33156 | 7.6 | Residencial | No | 0-100kW
2023-GD-05762 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-26617 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-03258 | 15.2 | Residencial | Yes | 0-100kW
202510-NM25-00843 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-01823 | 12.672 | Residencial | Yes | 0-100kW
202501-NM25-02743 | 12 | Residencial | Yes | 0-100kW
2020-GD-04689 | 7.67 | Residencial | Yes | 0-100kW
202507-NM25-00383 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10162 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-03501 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-22692 | 8.85 | Residencial | No | 0-100kW
2022-GD-06044 | 9.73 | Residencial | Yes | 0-100kW
2021-GD-01295 | 4.13 | Residencial | Yes | 0-100kW
202407-NM25-03392 | 4.758 | Residencial | No | 0-100kW
202505-NM25-00838 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-05782 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03495 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-35235 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24060 | 6 | Residencial | Yes | 0-100kW
202511-NM25-00925 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02860 | 14.64 | Residencial | Yes | 0-100kW
202409-NM25-02589 | 6.588 | Residencial | Yes | 0-100kW
202407-NM25-04189 | 7.6 | Residencial | No | 0-100kW
2021-GD-03324 | 8.85 | Residencial | Yes | 0-100kW
202502-NM25-03393 | 8 | Residencial | Yes | 0-100kW
202501-NM25-02776 | 2.36 | Residencial | Yes | 0-100kW
202507-NM25-02420 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-00521 | 7.75 | Residencial | Yes | 0-100kW
202505-NM25-03882 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03826 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-03149 | 7.68 | Residencial | Yes | 0-100kW
202409-NM25-00502 | 4.392 | Residencial | Yes | 0-100kW
16-2-1130 | 3.65 | Residencial | Yes | 0-100kW
2017-GD-02443 | 3.66 | Residencial | Yes | 0-100kW
202409-NM25-02243 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-03692 | 24 | Comercial | Yes | 0-100kW
2022-GD-15497 | 5.86 | Residencial | Yes | 0-100kW
202405-NM25-00353 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-31244 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06750 | 4.75 | Residencial | Yes | 0-100kW
202409-NM25-03086 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00214 | 3.225 | Residencial | Yes | 0-100kW
202509-NM25-01364 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03064 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01793 | 4.72 | Residencial | Yes | 0-100kW
202402-NM25-00152 | 8 | Residencial | Yes | 0-100kW
202505-NM25-02715 | 10 | Residencial | Yes | 0-100kW
202312-NM25-01603 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24601 | 4.39 | Residencial | Yes | 0-100kW
202508-NM25-05488 | 5.3 | Comercial | Yes | 0-100kW
2023-GD-03459 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-11060 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-04051 | 5.31 | Residencial | Yes | 0-100kW
202503-NM25-04244 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-06251 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-15435 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06162 | 11.5 | Residencial | No | 0-100kW
202505-NM25-01903 | 15.2 | Residencial | Yes | 0-100kW
202402-NM25-00977 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-04701 | 24.3 | Comercial | Yes | 0-100kW
202408-NM25-04904 | 4.608 | Residencial | Yes | 0-100kW
2023-GD-02804 | 4.39 | Residencial | Yes | 0-100kW
202404-NM25-03152 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-02014 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-20202 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-08535 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-32828 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-32686 | 15.2 | Residencial | No | 0-100kW
2018-GD-01816 | 4.34 | Residencial | Yes | 0-100kW
202506-NM25-00172 | 5.76 | Residencial | Yes | 0-100kW
202505-NM25-04885 | 5.76 | Residencial | Yes | 0-100kW
202511-NM25-01019 | 9 | Residencial | Yes | 0-100kW
202504-NM25-01706 | 8 | Residencial | Yes | 0-100kW
2022-GD-12976 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-30053 | 5.28 | Residencial | Yes | 0-100kW
202412-NM25-03831 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19317 | 2.93 | Residencial | Yes | 0-100kW
2022-GD-11608 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-00342 | 9 | Residencial | Yes | 0-100kW
2023-GD-09968 | 5 | Residencial | Yes | 0-100kW
2018-GD-00115 | 9.86 | Residencial | Yes | 0-100kW
202506-NM25-03578 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00933 | 6.912 | Residencial | Yes | 0-100kW
202509-NM25-05083 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-32831 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-21154 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13155 | 3.54 | Residencial | Yes | 0-100kW
2018-GD-00210 | 4.06 | Residencial | Yes | 0-100kW
2023-GD-17355 | 8 | Residencial | Yes | 0-100kW
202409-NM25-01320 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-04976 | 8.83 | Residencial | Yes | 0-100kW
2023-GD-23240 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20358 | 4.13 | Residencial | Yes | 0-100kW
202508-NM25-02198 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-06901 | 6.19 | Residencial | Yes | 0-100kW
2022-GD-32618 | 4.03 | Residencial | Yes | 0-100kW
202404-NM25-02024 | 8.418 | Residencial | Yes | 0-100kW
2023-GD-01951 | 5 | Residencial | Yes | 0-100kW
202507-NM25-04346 | 6.528 | Residencial | Yes | 0-100kW
2022-GD-31376 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-02690 | 11.5 | Residencial | No | 0-100kW
202312-NM25-01209 | 7.6 | Residencial | No | 0-100kW
202512-NM25-05099 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05415 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-05945 | 15 | Residencial | Yes | 0-100kW
2023-GD-36762 | 8 | Residencial | Yes | 0-100kW
202501-NM25-03238 | 4.026 | Residencial | Yes | 0-100kW
14-7-090 | 4 | Residencial | Yes | 0-100kW
202412-NM25-01798 | 15.2 | Residencial | Yes | 0-100kW
202401-NM25-01429 | 6.588 | Residencial | Yes | 0-100kW
2022-GD-13317 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01985 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01345 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05734 | 2.95 | Residencial | Yes | 0-100kW
2021-GD-14836 | 3.66 | Residencial | Yes | 0-100kW
202309-NM25-00029 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01658 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01759 | 9.216 | Residencial | Yes | 0-100kW
202403-NM25-01614 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-02714 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-03654 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-04061 | 3.24 | Residencial | Yes | 0-100kW
202404-NM25-03669 | 15.2 | Residencial | Yes | 0-100kW
202506-NM25-04591 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-02691 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-03616 | 6.49 | Residencial | Yes | 0-100kW
202512-NM25-02641 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-19313 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07565 | 5.86 | Residencial | Yes | 0-100kW
202401-NM25-04236 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-37253 | 15.2 | Residencial | Yes | 0-100kW
202404-NM25-00369 | 7.6 | Residencial | Yes | 0-100kW
15-2-980 | 1.72 | Residencial | Yes | 0-100kW
202510-NM25-04152 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00118 | 15 | Residencial | Yes | 0-100kW
202402-NM25-04399 | 3.66 | Residencial | Yes | 0-100kW
16-6-0364 | 2.58 | Residencial | Yes | 0-100kW
202406-NM25-00616 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02664 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-00819 | 4.392 | Residencial | Yes | 0-100kW
16-5-0522A | 6.88 | Residencial | Yes | 0-100kW
202502-NM25-01661 | 6.222 | Residencial | Yes | 0-100kW
2023-GD-32197 | 7.6 | Comercial | Yes | 0-100kW
202412-NM25-01338 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-36975 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-00473 | 4.43 | Residencial | Yes | 0-100kW
202505-NM25-03781 | 6.588 | Residencial | Yes | 0-100kW
202409-NM25-03889 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01444 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21392 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-02503 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-20468 | 5 | Residencial | Yes | 0-100kW
202311-NM25-00056 | 8.784 | Residencial | Yes | 0-100kW
202506-NM25-02067 | 5.76 | Residencial | Yes | 0-100kW
202405-NM25-02390 | 3.66 | Residencial | Yes | 0-100kW
202505-NM25-00956 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-03363 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-02794 | 4.25 | Residencial | Yes | 0-100kW
202504-NM25-00953 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-28227 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-08510 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-11562 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-01767 | 4.03 | Residencial | Yes | 0-100kW
16-2-0285 | 2.58 | Residencial | Yes | 0-100kW
2023-GD-38582 | 7.5 | Residencial | Yes | 0-100kW
15-5-0634A | 5.59 | Residencial | Yes | 0-100kW
2022-GD-22876 | 4.03 | Residencial | Yes | 0-100kW
202411-NM25-02805 | 8 | Residencial | Yes | 0-100kW
202502-NM25-03276 | 4.608 | Residencial | Yes | 0-100kW
2022-GD-19372 | 3.29 | Residencial | Yes | 0-100kW
2022-GD-24248 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-14103 | 9.52 | Residencial | Yes | 0-100kW
202503-NM25-01371 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-19922 | 4.39 | Residencial | Yes | 0-100kW
2020-GD-00180 | 3 | Residencial | Yes | 0-100kW
2021-GD-12861 | 5.9 | Residencial | Yes | 0-100kW
2022-GD-22802 | 4.76 | Residencial | Yes | 0-100kW
202408-NM25-01456 | 5 | Residencial | Yes | 0-100kW
202411-NM25-00151 | 18.128 | Residencial | Yes | 0-100kW
202406-NM25-02926 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-35429 | 6.59 | Residencial | Yes | 0-100kW
202412-NM25-03967 | 12.444 | Residencial | Yes | 0-100kW
2022-GD-21799 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-02032 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33026 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32900 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03160 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00940 | 5.9 | Residencial | Yes | 0-100kW
202507-NM25-02650 | 9 | Residencial | Yes | 0-100kW
202404-NM25-00959 | 8.416 | Residencial | Yes | 0-100kW
2022-GD-20535 | 7.32 | Residencial | No | 0-100kW
2022-GD-26472 | 3.8 | Residencial | Yes | 0-100kW
202410-NM25-03645 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01650 | 8 | Residencial | Yes | 0-100kW
2017-GD-01501 | 4.3 | Residencial | Yes | 0-100kW
2019-GD-02531 | 4 | Residencial | Yes | 0-100kW
202402-NM25-00109 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-17463 | 5 | Residencial | Yes | 0-100kW
2023-GD-14756 | 4 | Residencial | Yes | 0-100kW
202502-NM25-01037 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-09815 | 2.93 | Residencial | Yes | 0-100kW
2020-GD-04982 | 4.43 | Residencial | Yes | 0-100kW
202511-NM25-01309 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04010 | 5.31 | Residencial | Yes | 0-100kW
202404-NM25-00378 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00238 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-03335 | 8 | Residencial | Yes | 0-100kW
2020-GD-04471 | 6.62 | Residencial | Yes | 0-100kW
202503-NM25-05275 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-09271 | 7.38 | Residencial | Yes | 0-100kW
202504-NM25-00819 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-03304 | 24.9 | Residencial | Yes | 0-100kW
2021-GD-12100 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03525 | 4.026 | Residencial | Yes | 0-100kW
202407-NM25-02159 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18190 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04132 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28832 | 4.61 | Residencial | Yes | 0-100kW
202311-NM25-00446 | 5.4 | Residencial | Yes | 0-100kW
202501-NM25-01403 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04200 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-19140 | 8.42 | Residencial | Yes | 0-100kW
202402-NM25-01308 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-22064 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33159 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-00075 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-05434 | 10 | Residencial | Yes | 0-100kW
202512-NM25-02570 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-02705 | 6.195 | Residencial | Yes | 0-100kW
2023-GD-22781 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02724 | 3.245 | Residencial | Yes | 0-100kW
202501-NM25-01176 | 11.14 | Residencial | Yes | 0-100kW
2023-GD-15925 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31192 | 7.59 | Residencial | Yes | 0-100kW
202512-NM25-00745 | 11.5 | Residencial | Yes | 0-100kW
16-7-0004 | 5.59 | Residencial | Yes | 0-100kW
2023-GD-11527 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06530 | 5 | Residencial | Yes | 0-100kW
2023-GD-32286 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-02021 | 5 | Residencial | Yes | 0-100kW
202503-NM25-00194 | 4.224 | Residencial | Yes | 0-100kW
202312-NM25-00502 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-01632 | 10.03 | Residencial | Yes | 0-100kW
15-5-0001A | 5 | Residencial | Yes | 0-100kW
2023-GD-09294 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-14478 | 3.54 | Residencial | Yes | 0-100kW
202410-NM25-02403 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23503 | 4.39 | Residencial | Yes | 0-100kW
202412-NM25-02711 | 7.6 | Residencial | No | 0-100kW
2022-GD-00426 | 3.84 | Residencial | Yes | 0-100kW
202403-NM25-03572 | 9.882 | Residencial | Yes | 0-100kW
202505-NM25-03846 | 11.5 | Residencial | No | 0-100kW
202504-NM25-01670 | 6.954 | Comercial | Yes | 0-100kW
2021-GD-09040 | 4.76 | Residencial | Yes | 0-100kW
202406-NM25-02329 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-00760 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-09246 | 9.6 | Residencial | Yes | 0-100kW
202512-NM25-02764 | 11.5 | Residencial | Yes | 0-100kW
202312-NM25-02199 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33147 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-17036 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-04862 | 4.43 | Residencial | Yes | 0-100kW
202501-NM25-04671 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-22670 | 4.39 | Residencial | Yes | 0-100kW
202502-NM25-04997 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-01972 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-03320 | 7.6 | Comercial | Yes | 0-100kW
202405-NM25-01924 | 4.29 | Residencial | Yes | 0-100kW
202502-NM25-00365 | 10.752 | Residencial | Yes | 0-100kW
202505-NM25-01186 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-03082 | 6 | Residencial | Yes | 0-100kW
202409-NM25-00217 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07144 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-02557 | 5.49 | Residencial | Yes | 0-100kW
202506-NM25-03784 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-07100 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-19207 | 7.6 | Residencial | Yes | 0-100kW
16-3-733 | 2.75 | Residencial | Yes | 0-100kW
2023-GD-36047 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-38607 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-13335 | 6.8 | Residencial | Yes | 0-100kW
202408-NM25-02185 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01363 | 9.15 | Residencial | Yes | 0-100kW
2019-GD-00378 | 13.68 | Residencial | Yes | 0-100kW
202405-NM25-03564 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03097 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-20168 | 4.03 | Residencial | Yes | 0-100kW
202506-NM25-02326 | 4.758 | Residencial | Yes | 0-100kW
202504-NM25-05468 | 21.228 | Residencial | Yes | 0-100kW
2023-GD-22582 | 8 | Residencial | Yes | 0-100kW
202504-NM25-04645 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04450 | 9.216 | Residencial | Yes | 0-100kW
2022-GD-19361 | 2.93 | Residencial | Yes | 0-100kW
2021-GD-06374 | 4.43 | Residencial | Yes | 0-100kW
202509-NM25-00962 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-00307 | 3.66 | Residencial | Yes | 0-100kW
202312-NM25-03433 | 9 | Residencial | Yes | 0-100kW
202408-NM25-02414 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15009 | 5.49 | Residencial | Yes | 0-100kW
202508-NM25-02858 | 8 | Residencial | Yes | 0-100kW
2023-GD-25298 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06857 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-03737 | 6.59 | Residencial | Yes | 0-100kW
202501-NM25-03403 | 8.418 | Residencial | Yes | 0-100kW
202405-NM25-02710 | 6.588 | Residencial | Yes | 0-100kW
2022-GD-22639 | 4.03 | Residencial | Yes | 0-100kW
202504-NM25-04549 | 4.224 | Residencial | Yes | 0-100kW
2022-GD-16222 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-23306 | 4.95 | Residencial | Yes | 0-100kW
202401-NM25-03730 | 5.124 | Residencial | Yes | 0-100kW
202509-NM25-00488 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-06095 | 5 | Residencial | Yes | 0-100kW
2023-GD-09588 | 4.76 | Residencial | Yes | 0-100kW
202402-NM25-03201 | 8.784 | Residencial | Yes | 0-100kW
202312-NM25-00333 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-02533 | 5.605 | Residencial | Yes | 0-100kW
202512-NM25-01314 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-03352 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-23374 | 4.76 | Residencial | Yes | 0-100kW
202403-NM25-01166 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-03083 | 8 | Residencial | Yes | 0-100kW
2022-GD-17585 | 4.03 | Residencial | Yes | 0-100kW
202406-NM25-00288 | 4.95 | Residencial | Yes | 0-100kW
2020-GD-02205 | 4.425 | Residencial | Yes | 0-100kW
2022-GD-17505 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-01652 | 6.14 | Residencial | Yes | 0-100kW
2022-GD-22821 | 10.75 | Residencial | Yes | 0-100kW
202412-NM25-01550 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-01233 | 4.39 | Residencial | Yes | 0-100kW
2018-GD-00370 | 6 | Residencial | Yes | 0-100kW
202504-NM25-02369 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-05173 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-00161 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-31084 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32707 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-23557 | 4.03 | Residencial | Yes | 0-100kW
202501-NM25-01700 | 10.98 | Residencial | Yes | 0-100kW
202401-NM25-00416 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23083 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-25712 | 4.39 | Residencial | Yes | 0-100kW
202409-NM25-00222 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-23575 | 8 | Residencial | Yes | 0-100kW
2022-GD-24141 | 3.24 | Residencial | Yes | 0-100kW
202501-NM25-00181 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-02305 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24395 | 7.6 | Residencial | No | 0-100kW
2022-GD-16873 | 24.96 | Comercial | Yes | 0-100kW
2022-GD-02965 | 4.76 | Residencial | Yes | 0-100kW
202401-NM25-04060 | 4.026 | Residencial | Yes | 0-100kW
202410-NM25-03987 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04923 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-10933 | 4.76 | Residencial | Yes | 0-100kW
202504-NM25-02294 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-00766 | 7.2 | Residencial | Yes | 0-100kW
202407-NM25-01018 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14839 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17321 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-21674 | 4.61 | Comercial | Yes | 0-100kW
202503-NM25-04466 | 5.76 | Residencial | Yes | 0-100kW
15-1-484 | 0 | Comercial | No | 0-100kW
2022-GD-14496 | 7.5 | Residencial | Yes | 0-100kW
202401-NM25-02824 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-37012 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-02272 | 5.165 | Residencial | Yes | 0-100kW
2022-GD-16652 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-14708 | 5.5 | Residencial | Yes | 0-100kW
2023-GD-15767 | 15 | Residencial | Yes | 0-100kW
202506-NM25-00532 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-28635 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01057 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-04500 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-02685 | 10.98 | Residencial | Yes | 0-100kW
2023-GD-33967 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07741 | 5.9 | Residencial | Yes | 0-100kW
2021-GD-03399 | 4.43 | Residencial | Yes | 0-100kW
2019-GD-00539 | 22.6 | Comercial | No | 0-100kW
2023-GD-15474 | 12.44 | Residencial | Yes | 0-100kW
2023-GD-34622 | 4.03 | Residencial | Yes | 0-100kW
2019-GD-02346 | 7.5 | Residencial | Yes | 0-100kW
202411-NM25-01851 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-00637 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02127 | 9.44 | Comercial | Yes | 0-100kW
202411-NM25-00462 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-18706 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-13090 | 9.15 | Residencial | Yes | 0-100kW
2022-GD-06499 | 5 | Residencial | Yes | 0-100kW
2022-GD-15130 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-27295 | 6.59 | Residencial | Yes | 0-100kW
2018-GD-02103 | 10.82 | Residencial | Yes | 0-100kW
202502-NM25-04106 | 2.928 | Residencial | Yes | 0-100kW
202503-NM25-02166 | 7.6 | Residencial | No | 0-100kW
202407-NM25-02604 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-03770 | 3.5 | Residencial | Yes | 0-100kW
2022-GD-03292 | 3.24 | Residencial | Yes | 0-100kW
2020-GD-07595 | 10 | Residencial | Yes | 0-100kW
202402-NM25-03493 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-09342 | 2.95 | Residencial | Yes | 0-100kW
2021-GD-08668 | 5 | Residencial | Yes | 0-100kW
2017-GD-02558 | 2.365 | Residencial | Yes | 0-100kW
202512-NM25-00507 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-01536 | 8 | Residencial | Yes | 0-100kW
2023-GD-01492 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-03732 | 5 | Residencial | Yes | 0-100kW
2023-GD-35697 | 8.83 | Residencial | Yes | 0-100kW
202505-NM25-00211 | 5.938 | Residencial | Yes | 0-100kW
2022-GD-04728 | 5.9 | Comercial | Yes | 0-100kW
2022-GD-14125 | 6.59 | Residencial | Yes | 0-100kW
202504-NM25-04511 | 8.064 | Residencial | Yes | 0-100kW
202502-NM25-00663 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30293 | 3.29 | Residencial | Yes | 0-100kW
202511-NM25-01595 | 6.528 | Residencial | Yes | 0-100kW
202408-NM25-04208 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-14843 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-15038 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12886 | 4.43 | Residencial | Yes | 0-100kW
2019-GD-00799 | 24 | Comercial | Yes | 0-100kW
2022-GD-17563 | 5.86 | Residencial | Yes | 0-100kW
202409-NM25-04117 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-04364 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-19000 | 7.6 | Residencial | Yes | 0-100kW
202311-NM25-00084 | 10.98 | Residencial | Yes | 0-100kW
2022-GD-06555 | 5.61 | Residencial | Yes | 0-100kW
2022-GD-28026 | 10.98 | Residencial | Yes | 0-100kW
2023-GD-13873 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-17053 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-04657 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-04287 | 5 | Residencial | Yes | 0-100kW
2022-GD-22572 | 3.655 | Residencial | Yes | 0-100kW
2023-GD-10539 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-04954 | 4.43 | Residencial | Yes | 0-100kW
202409-NM25-03327 | 10 | Residencial | Yes | 0-100kW
202509-NM25-04092 | 11.5 | Residencial | Yes | 0-100kW
15-3-478 | 6.45 | Residencial | Yes | 0-100kW
202505-NM25-02642 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-02587 | 3.225 | Residencial | Yes | 0-100kW
202401-NM25-02642 | 5.856 | Residencial | Yes | 0-100kW
202509-NM25-02769 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05145 | 11.5 | Comercial | Yes | 0-100kW
2023-GD-24798 | 10 | Residencial | Yes | 0-100kW
2022-GD-30879 | 10.25 | Residencial | Yes | 0-100kW
202501-NM25-01535 | 3.54 | Residencial | Yes | 0-100kW
202506-NM25-00802 | 4.608 | Residencial | Yes | 0-100kW
202503-NM25-02884 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-04339 | 11.4 | Residencial | Yes | 0-100kW
202404-NM25-01079 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06854 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-10700 | 5.12 | Residencial | Yes | 0-100kW
202504-NM25-04398 | 11.5 | Residencial | No | 0-100kW
202505-NM25-04200 | 3.8 | Residencial | Yes | 0-100kW
202410-NM25-04664 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04720 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04960 | 7.67 | Residencial | Yes | 0-100kW
202505-NM25-00764 | 8 | Residencial | Yes | 0-100kW
202401-NM25-04478 | 4.392 | Residencial | Yes | 0-100kW
202505-NM25-01582 | 12 | Comercial | Yes | 0-100kW
2022-GD-22615 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-30133 | 5.86 | Residencial | Yes | 0-100kW
202404-NM25-03371 | 5.856 | Residencial | No | 0-100kW
2020-GD-07553 | 4 | Residencial | Yes | 0-100kW
202403-NM25-01011 | 4.392 | Residencial | Yes | 0-100kW
2020-GD-01729 | 5.25 | Residencial | Yes | 0-100kW
202409-NM25-04331 | 6.89 | Residencial | Yes | 0-100kW
202507-NM25-04727 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04920 | 9 | Residencial | Yes | 0-100kW
202505-NM25-03693 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00217 | 3.66 | Residencial | Yes | 0-100kW
2017-GD-00599 | 3.225 | Residencial | Yes | 0-100kW
202402-NM25-03160 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00902 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-02167 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-01963 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22267 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-16441 | 4.03 | Residencial | Yes | 0-100kW
202412-NM25-01017 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-05038 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01444 | 5.124 | Residencial | Yes | 0-100kW
2022-GD-17125 | 5.12 | Residencial | Yes | 0-100kW
202312-NM25-03422 | 4.758 | Residencial | Yes | 0-100kW
2022-GD-13454 | 3.54 | Residencial | Yes | 0-100kW
202402-NM25-01031 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27685 | 4.03 | Residencial | Yes | 0-100kW
202402-NM25-00367 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07844 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-25207 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-29267 | 6.59 | Residencial | No | 0-100kW
202409-NM25-00990 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-02258 | 15.2 | Residencial | Yes | 0-100kW
202406-NM25-03729 | 9 | Residencial | Yes | 0-100kW
2023-GD-12456 | 4.61 | Residencial | Yes | 0-100kW
2022-GD-23919 | 4.03 | Residencial | Yes | 0-100kW
15-5-0445A | 3 | Residencial | Yes | 0-100kW
2022-GD-30275 | 6.91 | Residencial | No | 0-100kW
202403-NM25-00623 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19501 | 10.25 | Residencial | Yes | 0-100kW
202509-NM25-03884 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02677 | 3.66 | Residencial | No | 0-100kW
2022-GD-27689 | 8.46 | Residencial | Yes | 0-100kW
2022-GD-10352 | 3.66 | Residencial | Yes | 0-100kW
202312-NM25-00963 | 3.84 | Residencial | Yes | 0-100kW
2020-GD-09063 | 3.24 | Residencial | Yes | 0-100kW
202402-NM25-03267 | 6.954 | Residencial | Yes | 0-100kW
202409-NM25-01422 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32079 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-04397 | 5.31 | Residencial | Yes | 0-100kW
2021-GD-07675 | 8.76 | Residencial | Yes | 0-100kW
2023-GD-27880 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-15756 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03272 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-01388 | 8 | Residencial | Yes | 0-100kW
15-6-0555 | 8.17 | Residencial | Yes | 0-100kW
2018-GD-01087 | 2.15 | Residencial | Yes | 0-100kW
202412-NM25-02133 | 9.15 | Residencial | Yes | 0-100kW
202410-NM25-02037 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-01869 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-04121 | 6.19 | Residencial | Yes | 0-100kW
202403-NM25-03286 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-00116 | 5.81 | Residencial | Yes | 0-100kW
2021-GD-05971 | 3.24 | Residencial | Yes | 0-100kW
202509-NM25-00928 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10757 | 10.4 | Residencial | Yes | 0-100kW
202411-NM25-02341 | 4.392 | Residencial | Yes | 0-100kW
202412-NM25-02833 | 3.66 | Residencial | Yes | 0-100kW
202509-NM25-06003 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-02133 | 11.712 | Residencial | Yes | 0-100kW
2023-GD-09416 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-02538 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-01460 | 4 | Residencial | Yes | 0-100kW
2023-GD-11883 | 10.58 | Residencial | Yes | 0-100kW
202405-NM25-03053 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-03137 | 5 | Residencial | Yes | 0-100kW
202509-NM25-00282 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11167 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-11052 | 4.13 | Residencial | Yes | 0-100kW
202509-NM25-05769 | 4.224 | Residencial | Yes | 0-100kW
2022-GD-29117 | 8.3 | Residencial | Yes | 0-100kW
2021-GD-05644 | 5.31 | Residencial | Yes | 0-100kW
2019-GD-02794 | 15.93 | Comercial | Yes | 0-100kW
202501-NM25-01159 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-02897 | 5 | Residencial | Yes | 0-100kW
202312-NM25-03058 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-01182 | 5.124 | Residencial | Yes | 0-100kW
2021-GD-00937 | 3.54 | Residencial | Yes | 0-100kW
202312-NM25-02615 | 4.392 | Residencial | No | 0-100kW
2019-GD-03190 | 9.92 | Residencial | Yes | 0-100kW
2022-GD-16813 | 12.81 | Residencial | Yes | 0-100kW
2023-GD-18282 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04364 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-23690 | 12.44 | Residencial | Yes | 0-100kW
14-1-527 | 5.87 | Residencial | Yes | 0-100kW
202510-NM25-03989 | 15 | Residencial | Yes | 0-100kW
202501-NM25-03916 | 14.208 | Residencial | Yes | 0-100kW
2023-GD-21530 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11704 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-02033 | 4.72 | Residencial | Yes | 0-100kW
202501-NM25-03468 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-10437 | 13.91 | Residencial | Yes | 0-100kW
202506-NM25-02273 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-03231 | 15 | Residencial | Yes | 0-100kW
2022-GD-06849 | 16 | Residencial | Yes | 0-100kW
2023-GD-20785 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-02854 | 4.03 | Residencial | Yes | 0-100kW
2019-GD-01084 | 12 | Comercial | Yes | 0-100kW
2019-GD-00883 | 9.44 | Residencial | Yes | 0-100kW
2022-GD-16917 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-19456 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-03906 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32477 | 15 | Residencial | Yes | 0-100kW
202501-NM25-01071 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-00743 | 4.608 | Residencial | Yes | 0-100kW
2022-GD-07921 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-28116 | 5 | Residencial | Yes | 0-100kW
202502-NM25-05723 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-02326 | 3.8 | Residencial | Yes | 0-100kW
202505-NM25-05217 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03171 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-07278 | 5.01 | Residencial | Yes | 0-100kW
2020-GD-02293 | 12.11 | Residencial | Yes | 0-100kW
2023-GD-22727 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01325 | 11.712 | Residencial | Yes | 0-100kW
2023-GD-15946 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11785 | 5.1 | Residencial | Yes | 0-100kW
202509-NM25-03380 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00835 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-00340 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02670 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-02004 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-21917 | 9.15 | Residencial | Yes | 0-100kW
2022-GD-27613 | 4.03 | Residencial | Yes | 0-100kW
202407-NM25-00944 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-01621 | 3.8 | Residencial | Yes | 0-100kW
202404-NM25-03075 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-03331 | 6.8 | Residencial | Yes | 0-100kW
202408-NM25-00534 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05913 | 8.42 | Residencial | Yes | 0-100kW
202505-NM25-01336 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-01649 | 9.882 | Residencial | Yes | 0-100kW
2023-GD-29439 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-01201 | 5.76 | Residencial | Yes | 0-100kW
202409-NM25-00153 | 8 | Residencial | Yes | 0-100kW
2020-GD-05000 | 7.57 | Residencial | Yes | 0-100kW
202512-NM25-00987 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-02050 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-26425 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13091 | 3.84 | Residencial | Yes | 0-100kW
202503-NM25-01969 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-03161 | 15 | Residencial | Yes | 0-100kW
15-3-093 | 4 | Residencial | Yes | 0-100kW
2023-GD-20941 | 5 | Comercial | Yes | 0-100kW
2022-GD-02447 | 7.67 | Residencial | Yes | 0-100kW
2023-GD-34348 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-18234 | 13.91 | Residencial | Yes | 0-100kW
2022-GD-11293 | 6.22 | Residencial | Yes | 0-100kW
202311-NM25-00607 | 5.49 | Residencial | Yes | 0-100kW
2020-GD-00435 | 3.25 | Residencial | Yes | 0-100kW
2022-GD-02135 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-23681 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31725 | 6.22 | Residencial | Yes | 0-100kW
202410-NM25-01476 | 6.588 | Residencial | Yes | 0-100kW
202311-NM25-00077 | 8.052 | Residencial | Yes | 0-100kW
15-1-104 | 5 | Residencial | Yes | 0-100kW
202503-NM25-01700 | 15.2 | Residencial | Yes | 0-100kW
15-4-0250GD | 1.4 | Residencial | Yes | 0-100kW
2023-GD-31171 | 8 | Residencial | Yes | 0-100kW
202505-NM25-02100 | 6.49 | Residencial | Yes | 0-100kW
2021-GD-09396 | 5.86 | Residencial | Yes | 0-100kW
202511-NM25-00112 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-11036 | 5.49 | Residencial | Yes | 0-100kW
202404-NM25-02053 | 3.294 | Residencial | Yes | 0-100kW
2022-GD-32723 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-30125 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-02549 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-01920 | 9.15 | Residencial | No | 0-100kW
15-3-1117 | 2.58 | Residencial | Yes | 0-100kW
15-7-157 | 7 | Residencial | Yes | 0-100kW
202407-NM25-01349 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13070 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01592 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-00130 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-31501 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11719 | 7.69 | Residencial | Yes | 0-100kW
202503-NM25-01159 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00763 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-00692 | 4.72 | Residencial | Yes | 0-100kW
2021-GD-12485 | 5.9 | Residencial | Yes | 0-100kW
2022-GD-31923 | 5 | Residencial | Yes | 0-100kW
202410-NM25-03136 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-01968 | 10 | Residencial | Yes | 0-100kW
2020-GD-01021 | 4.5 | Residencial | Yes | 0-100kW
14-6-0375 | 7.5 | Residencial | Yes | 0-100kW
202409-NM25-02066 | 15.2 | Comercial | Yes | 0-100kW
202412-NM25-04122 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04787 | 15.2 | Residencial | Yes | 0-100kW
202505-NM25-02733 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-02930 | 3.75 | Residencial | Yes | 0-100kW
2022-GD-31802 | 6 | Residencial | Yes | 0-100kW
2022-GD-05804 | 15.74 | Residencial | Yes | 0-100kW
202502-NM25-00248 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03748 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-20899 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-37806 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-31580 | 12.6 | Residencial | Yes | 0-100kW
16-4-1159GD | 3.44 | Residencial | Yes | 0-100kW
202407-NM25-00625 | 6 | Residencial | Yes | 0-100kW
2023-GD-12537 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05636 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-02047 | 9 | Residencial | Yes | 0-100kW
2023-GD-36899 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-16657 | 6.8 | Residencial | Yes | 0-100kW
202503-NM25-01170 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-03232 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-02007 | 4.13 | Residencial | Yes | 0-100kW
202407-NM25-01714 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17126 | 5 | Residencial | Yes | 0-100kW
2023-GD-07654 | 5.49 | Residencial | Yes | 0-100kW
202503-NM25-04068 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-01215 | 12.59 | Residencial | Yes | 0-100kW
2021-GD-07189 | 4.72 | Residencial | Yes | 0-100kW
202504-NM25-02847 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-13341 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-01360 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-02392 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-13807 | 10 | Residencial | Yes | 0-100kW
202403-NM25-01367 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01641 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-04954 | 2.562 | Residencial | Yes | 0-100kW
2017-GD-03551 | 6.25 | Residencial | Yes | 0-100kW
202412-NM25-03104 | 24.576 | Residencial | Yes | 0-100kW
202506-NM25-03127 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-00180 | 4.43 | Residencial | Yes | 0-100kW
2021-GD-05123 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-28626 | 6 | Residencial | Yes | 0-100kW
202502-NM25-04126 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-13140 | 8.26 | Residencial | Yes | 0-100kW
202405-NM25-00791 | 7.6 | Residencial | Yes | 0-100kW
202309-NM25-00071 | 8.14 | Residencial | Yes | 0-100kW
202405-NM25-00776 | 8 | Residencial | Yes | 0-100kW
2022-GD-28727 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-18331 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-27038 | 19.76 | Comercial | Yes | 0-100kW
202411-NM25-01426 | 10.98 | Residencial | Yes | 0-100kW
202401-NM25-01589 | 4.392 | Residencial | Yes | 0-100kW
202503-NM25-00742 | 8 | Residencial | Yes | 0-100kW
202403-NM25-03221 | 4.392 | Residencial | Yes | 0-100kW
202505-NM25-01359 | 8.052 | Residencial | Yes | 0-100kW
202402-NM25-03183 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06023 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-29928 | 9.88 | Residencial | Yes | 0-100kW
202406-NM25-00280 | 6 | Residencial | Yes | 0-100kW
202407-NM25-00391 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-27354 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03000 | 5 | Residencial | Yes | 0-100kW
202508-NM25-03918 | 3.84 | Residencial | Yes | 0-100kW
2018-GD-00703 | 5.04 | Residencial | Yes | 0-100kW
2023-GD-08640 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-25157 | 4.76 | Residencial | Yes | 0-100kW
2020-GD-01531 | 24.6 | Comercial | Yes | 0-100kW
2021-GD-12544 | 5.31 | Residencial | Yes | 0-100kW
202510-NM25-04167 | 8.448 | Residencial | Yes | 0-100kW
202507-NM25-00655 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-03056 | 7.6 | Residencial | Yes | 0-100kW
202310-NM25-00060 | 2.96 | Residencial | Yes | 0-100kW
2022-GD-09163 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-37565 | 8.42 | Residencial | Yes | 0-100kW
202410-NM25-02887 | 7.7 | Residencial | Yes | 0-100kW
2023-GD-38983 | 7.59 | Residencial | Yes | 0-100kW
202402-NM25-03842 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01289 | 3.66 | Residencial | Yes | 0-100kW
202509-NM25-05011 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-03328 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03942 | 5 | Residencial | Yes | 0-100kW
202512-NM25-04012 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-33915 | 60 | Comercial | Yes | 0-100kW
2022-GD-07479 | 6.95 | Residencial | Yes | 0-100kW
2022-GD-15310 | 5 | Residencial | Yes | 0-100kW
2022-GD-00149 | 4.03 | Residencial | Yes | 0-100kW
202408-NM25-05060 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-30886 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-13932 | 4.76 | Residencial | Yes | 0-100kW
202507-NM25-01585 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-02853 | 5.5 | Residencial | Yes | 0-100kW
14-3-609 | 4.2 | Residencial | Yes | 0-100kW
202509-NM25-05417 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-01136 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-02124 | 6.01 | Residencial | Yes | 0-100kW
2022-GD-26492 | 10.25 | Residencial | Yes | 0-100kW
2018-GD-01991 | 6 | Residencial | Yes | 0-100kW
202504-NM25-06070 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-14543 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11778 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-03047 | 8.064 | Residencial | Yes | 0-100kW
202411-NM25-01380 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00120 | 8 | Residencial | Yes | 0-100kW
2019-GD-01556 | 6.41 | Residencial | Yes | 0-100kW
2023-GD-18597 | 10.25 | Residencial | Yes | 0-100kW
2022-GD-07779 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-20258 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-00883 | 4.62 | Residencial | Yes | 0-100kW
202312-NM25-02685 | 4.608 | Residencial | Yes | 0-100kW
2019-GD-03401 | 9.145 | Residencial | Yes | 0-100kW
202312-NM25-01512 | 8.052 | Residencial | Yes | 0-100kW
2022-GD-25219 | 4.76 | Residencial | Yes | 0-100kW
202503-NM25-01028 | 6.178 | Residencial | Yes | 0-100kW
2023-GD-25598 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02959 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-02371 | 3.8 | Residencial | Yes | 0-100kW
16-3-805 | 4.3 | Residencial | Yes | 0-100kW
202410-NM25-02424 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01920 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-05532 | 4.13 | Residencial | Yes | 0-100kW
2022-GD-19130 | 6.22 | Residencial | Yes | 0-100kW
2020-GD-09625 | 8.26 | Residencial | Yes | 0-100kW
202408-NM25-04757 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-12803 | 8 | Residencial | Yes | 0-100kW
202502-NM25-04137 | 5 | Residencial | Yes | 0-100kW
2022-GD-23588 | 8.91 | Residencial | Yes | 0-100kW
2022-GD-13601 | 8.42 | Residencial | Yes | 0-100kW
202411-NM25-03106 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00783 | 8 | Residencial | Yes | 0-100kW
202401-NM25-00569 | 8 | Residencial | Yes | 0-100kW
202510-NM25-03338 | 8.64 | Residencial | Yes | 0-100kW
2023-GD-03105 | 5 | Residencial | Yes | 0-100kW
2023-GD-20651 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04067 | 6 | Residencial | Yes | 0-100kW
202411-NM25-03156 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03572 | 4.72 | Residencial | Yes | 0-100kW
2023-GD-13344 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02993 | 3.24 | Residencial | Yes | 0-100kW
2020-GD-06411 | 5 | Residencial | Yes | 0-100kW
2023-GD-23680 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31338 | 3.8 | Residencial | Yes | 0-100kW
202505-NM25-00152 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-03561 | 8.052 | Residencial | Yes | 0-100kW
2022-GD-31781 | 7.69 | Residencial | Yes | 0-100kW
202505-NM25-03581 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02574 | 6.912 | Residencial | Yes | 0-100kW
2022-GD-00728 | 3.66 | Residencial | Yes | 0-100kW
2019-GD-00579 | 6.785 | Residencial | Yes | 0-100kW
202404-NM25-01258 | 5.856 | Residencial | Yes | 0-100kW
2023-GD-20030 | 9.66 | Residencial | Yes | 0-100kW
202509-NM25-05638 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-03543 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-20212 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-00623 | 11.71 | Residencial | Yes | 0-100kW
2023-GD-14073 | 5 | Residencial | Yes | 0-100kW
202401-NM25-01875 | 8 | Residencial | Yes | 0-100kW
202407-NM25-03596 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22248 | 5.49 | Residencial | Yes | 0-100kW
202402-NM25-02954 | 8.418 | Comercial | Yes | 0-100kW
2023-GD-04814 | 7.3 | Residencial | Yes | 0-100kW
202502-NM25-03141 | 4.224 | Residencial | Yes | 0-100kW
2023-GD-34584 | 3.66 | Residencial | Yes | 0-100kW
202501-NM25-03374 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-03575 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27568 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-01407 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-12097 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-01436 | 5.12 | Residencial | Yes | 0-100kW
202506-NM25-01094 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-37488 | 6 | Residencial | Yes | 0-100kW
202402-NM25-02957 | 5 | Residencial | Yes | 0-100kW
202404-NM25-02430 | 10 | Residencial | Yes | 0-100kW
202401-NM25-00524 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03984 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-28705 | 5 | Residencial | Yes | 0-100kW
202502-NM25-01948 | 8 | Residencial | Yes | 0-100kW
202412-NM25-03212 | 11.44 | Residencial | Yes | 0-100kW
202508-NM25-00685 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04636 | 3.8 | Residencial | Yes | 0-100kW
202407-NM25-02494 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13860 | 8 | Residencial | Yes | 0-100kW
2023-GD-22701 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01825 | 21.96 | Residencial | Yes | 0-100kW
2023-GD-24215 | 4.76 | Residencial | Yes | 0-100kW
202409-NM25-03070 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26604 | 9.6 | Residencial | Yes | 0-100kW
2021-GD-09735 | 4.43 | Residencial | Yes | 0-100kW
202311-NM25-00506 | 5.124 | Residencial | Yes | 0-100kW
2022-GD-10824 | 7.97 | Residencial | Yes | 0-100kW
2021-GD-05412 | 5.61 | Residencial | Yes | 0-100kW
2017-GD-01384 | 5 | Residencial | No | 0-100kW
202506-NM25-00834 | 12 | Residencial | Yes | 0-100kW
2023-GD-18601 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16706 | 10 | Residencial | Yes | 0-100kW
2022-GD-27486 | 8.05 | Residencial | Yes | 0-100kW
202408-NM25-01915 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07868 | 4.03 | Residencial | Yes | 0-100kW
2018-GD-01995 | 6.8 | Residencial | Yes | 0-100kW
202411-NM25-03298 | 9 | Residencial | Yes | 0-100kW
2021-GD-05513 | 3.54 | Residencial | Yes | 0-100kW
202410-NM25-04858 | 4.758 | Residencial | Yes | 0-100kW
2022-GD-02420 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00881 | 2.66 | Residencial | Yes | 0-100kW
202506-NM25-04430 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-02762 | 4.75 | Residencial | Yes | 0-100kW
202505-NM25-00294 | 13.176 | Residencial | Yes | 0-100kW
202505-NM25-04663 | 17.644 | Residencial | Yes | 0-100kW
202502-NM25-05191 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-08685 | 5.49 | Residencial | Yes | 0-100kW
202503-NM25-04705 | 8 | Residencial | No | 0-100kW
2023-GD-08796 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-37159 | 3.66 | Residencial | Yes | 0-100kW
202505-NM25-04447 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01104 | 10 | Residencial | Yes | 0-100kW
202411-NM25-00019 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-00085 | 4.43 | Residencial | No | 0-100kW
2018-GD-01939 | 6.5 | Residencial | Yes | 0-100kW
202503-NM25-00162 | 5.376 | Residencial | Yes | 0-100kW
2023-GD-20427 | 5 | Residencial | Yes | 0-100kW
202402-NM25-02737 | 10 | Residencial | Yes | 0-100kW
202510-NM25-02697 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-00189 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-33028 | 3.6 | Residencial | Yes | 0-100kW
202501-NM25-03153 | 12 | Residencial | Yes | 0-100kW
2020-GD-05045 | 5 | Residencial | Yes | 0-100kW
2022-GD-12209 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-23286 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03770 | 8 | Residencial | Yes | 0-100kW
15-7-512 | 6 | Residencial | Yes | 0-100kW
202408-NM25-00124 | 12 | Residencial | Yes | 0-100kW
2023-GD-11470 | 7.6 | Residencial | No | 0-100kW
2022-GD-21456 | 5.49 | Residencial | Yes | 0-100kW
202502-NM25-00594 | 9.882 | Residencial | Yes | 0-100kW
202412-NM25-04210 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30483 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-27168 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00700 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-04610 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-03168 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-00109 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-39075 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-02643 | 5 | Residencial | Yes | 0-100kW
2022-GD-27592 | 5 | Residencial | Yes | 0-100kW
2022-GD-01522 | 5.01 | Residencial | Yes | 0-100kW
202505-NM25-02633 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-14579 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-06100 | 3.24 | Residencial | Yes | 0-100kW
202405-NM25-01228 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-10134 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01139 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02705 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-03940 | 8 | Residencial | Yes | 0-100kW
2018-GD-00571 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-35043 | 4 | Residencial | Yes | 0-100kW
202408-NM25-00645 | 4.392 | Residencial | Yes | 0-100kW
202402-NM25-02760 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16808 | 4.39 | Residencial | Yes | 0-100kW
202403-NM25-01960 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28527 | 7.6 | Comercial | Yes | 0-100kW
2023-GD-17040 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21658 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19616 | 6.95 | Residencial | Yes | 0-100kW
202411-NM25-01050 | 8.226 | Residencial | Yes | 0-100kW
2023-GD-16656 | 9.6 | Residencial | Yes | 0-100kW
2021-GD-05143 | 5.31 | Residencial | Yes | 0-100kW
2023-GD-37403 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-02913 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02914 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-01357 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-14089 | 5 | Residencial | Yes | 0-100kW
202509-NM25-06009 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07187 | 4.43 | Residencial | Yes | 0-100kW
2021-GD-07199 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-16269 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-29378 | 8 | Residencial | Yes | 0-100kW
2023-GD-30530 | 12 | Residencial | Yes | 0-100kW
2022-GD-24543 | 9.6 | Residencial | Yes | 0-100kW
202511-NM25-01189 | 3.456 | Residencial | Yes | 0-100kW
202509-NM25-01917 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03955 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-04104 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-02036 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-25928 | 8 | Residencial | Yes | 0-100kW
202504-NM25-00860 | 7.6 | Residencial | Yes | 0-100kW
2024-GD-00031 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02037 | 8.052 | Residencial | Yes | 0-100kW
2020-GD-06275 | 5.31 | Residencial | Yes | 0-100kW
202504-NM25-01354 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-02073 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-02074 | 7.525 | Residencial | Yes | 0-100kW
2022-GD-30989 | 6.8 | Residencial | Yes | 0-100kW
202502-NM25-04704 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-04016 | 4.026 | Residencial | Yes | 0-100kW
202409-NM25-02551 | 7.6 | Residencial | Yes | 0-100kW
14-7-345 | 14 | Residencial | Yes | 0-100kW
202405-NM25-00852 | 3.8 | Residencial | No | 0-100kW
202512-NM25-03738 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-02237 | 4.608 | Residencial | Yes | 0-100kW
202512-NM25-00076 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-11661 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28784 | 5 | Residencial | Yes | 0-100kW
2023-GD-34613 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06127 | 2.928 | Residencial | Yes | 0-100kW
202411-NM25-02498 | 3.8 | Residencial | Yes | 0-100kW
202312-NM25-00412 | 6 | Residencial | Yes | 0-100kW
202509-NM25-02229 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-12873 | 8.78 | Residencial | Yes | 0-100kW
2023-GD-03477 | 8.42 | Residencial | Yes | 0-100kW
202508-NM25-02066 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-01553 | 11.346 | Residencial | No | 0-100kW
15-1-690 | 8.4 | Residencial | Yes | 0-100kW
2020-GD-06048 | 3.84 | Residencial | Yes | 0-100kW
2020-GD-01435 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-31821 | 7.32 | Residencial | Yes | 0-100kW
202412-NM25-00706 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06598 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-28444 | 6.95 | Residencial | Yes | 0-100kW
2020-GD-01506 | 4.425 | Residencial | Yes | 0-100kW
202502-NM25-02398 | 3.84 | Residencial | Yes | 0-100kW
202402-NM25-01782 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-00777 | 6.8 | Residencial | Yes | 0-100kW
2018-GD-00708 | 8.35 | Residencial | Yes | 0-100kW
2021-GD-03569 | 6.8 | Residencial | Yes | 0-100kW
2020-GD-08661 | 9.85 | Residencial | Yes | 0-100kW
2021-GD-01232 | 4.72 | Residencial | Yes | 0-100kW
202403-NM25-00240 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-19945 | 7.69 | Residencial | Yes | 0-100kW
15-2-090 | 6 | Residencial | Yes | 0-100kW
202503-NM25-00233 | 5.76 | Residencial | Yes | 0-100kW
202402-NM25-01862 | 6 | Residencial | Yes | 0-100kW
202405-NM25-02712 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02583 | 3.66 | Residencial | Yes | 0-100kW
202505-NM25-03230 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-24169 | 3.66 | Residencial | Yes | 0-100kW
202403-NM25-01332 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-01230 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-03585 | 11.056 | Residencial | Yes | 0-100kW
202410-NM25-01587 | 5.49 | Residencial | Yes | 0-100kW
202402-NM25-01479 | 5 | Residencial | Yes | 0-100kW
2022-GD-25108 | 4.29 | Residencial | Yes | 0-100kW
2023-GD-27187 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14533 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-01728 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-27392 | 5 | Residencial | Yes | 0-100kW
202311-NM25-00790 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01457 | 4.992 | Residencial | Yes | 0-100kW
2022-GD-28410 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-33740 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05716 | 5.5 | Residencial | Yes | 0-100kW
2019-GD-02992 | 7.965 | Residencial | Yes | 0-100kW
202403-NM25-01821 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07090 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-17664 | 9.15 | Residencial | Yes | 0-100kW
2021-GD-13680 | 6.19 | Residencial | Yes | 0-100kW
202312-NM25-03315 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03120 | 10 | Residencial | Yes | 0-100kW
202512-NM25-01252 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24453 | 5.49 | Residencial | Yes | 0-100kW
2017-GD-03514 | 8.35 | Residencial | Yes | 0-100kW
2023-GD-28347 | 3.66 | Residencial | Yes | 0-100kW
202406-NM25-03355 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00830 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-04963 | 8.538 | Residencial | Yes | 0-100kW
202411-NM25-03120 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01776 | 9 | Residencial | Yes | 0-100kW
202402-NM25-03215 | 4.026 | Residencial | Yes | 0-100kW
202511-NM25-01236 | 23 | Residencial | Yes | 0-100kW
202503-NM25-05149 | 6.588 | Residencial | Yes | 0-100kW
2022-GD-09450 | 7.69 | Residencial | Yes | 0-100kW
202408-NM25-04535 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-01746 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-08884 | 2.95 | Residencial | Yes | 0-100kW
2022-GD-17435 | 8.75 | Residencial | Yes | 0-100kW
2021-GD-08445 | 3.54 | Residencial | Yes | 0-100kW
202502-NM25-01503 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04520 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-04355 | 6.6 | Residencial | Yes | 0-100kW
202502-NM25-06244 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-02619 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-31490 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06984 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-14952 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-20971 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-17193 | 8 | Residencial | Yes | 0-100kW
202501-NM25-02461 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02664 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03916 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-04277 | 5.76 | Residencial | Yes | 0-100kW
202507-NM25-02603 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-12040 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-32006 | 4.39 | Residencial | Yes | 0-100kW
2018-GD-00981 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02084 | 15.2 | Residencial | Yes | 0-100kW
202402-NM25-01556 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-00863 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02409 | 5.124 | Residencial | Yes | 0-100kW
202403-NM25-03973 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-32805 | 4.61 | Residencial | Yes | 0-100kW
2021-GD-05867 | 7.67 | Residencial | Yes | 0-100kW
2023-GD-35514 | 8 | Residencial | Yes | 0-100kW
2023-GD-00875 | 4.03 | Residencial | Yes | 0-100kW
202407-NM25-02760 | 12 | Residencial | Yes | 0-100kW
202409-NM25-00372 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00887 | 4.08 | Residencial | Yes | 0-100kW
202402-NM25-01044 | 7.6 | Residencial | Yes | 0-100kW
16-2-0164 | 2.79 | Residencial | Yes | 0-100kW
202402-NM25-03795 | 8.418 | Residencial | Yes | 0-100kW
2022-GD-26528 | 3.29 | Residencial | Yes | 0-100kW
202507-NM25-00616 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-00323 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-04567 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-10981 | 5 | Residencial | Yes | 0-100kW
2023-GD-24110 | 22.33 | Comercial | Yes | 0-100kW
202406-NM25-01614 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02512 | 3.245 | Residencial | No | 0-100kW
202408-NM25-00461 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05684 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10589 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-00811 | 3.66 | Residencial | Yes | 0-100kW
16-1-824 | 2.8 | Residencial | Yes | 0-100kW
2023-GD-28473 | 8 | Residencial | Yes | 0-100kW
2022-GD-07085 | 4.03 | Residencial | Yes | 0-100kW
202404-NM25-01696 | 6.588 | Residencial | Yes | 0-100kW
2023-GD-08760 | 5.49 | Residencial | Yes | 0-100kW
2021-GD-04695 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-13216 | 5.12 | Residencial | Yes | 0-100kW
2017-GD-00641 | 3.835 | Residencial | Yes | 0-100kW
202404-NM25-01160 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-30792 | 8.7 | Residencial | Yes | 0-100kW
2023-GD-32111 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03653 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-01915 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32240 | 4.99 | Residencial | Yes | 0-100kW
202407-NM25-03084 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14412 | 9.52 | Residencial | Yes | 0-100kW
2023-GD-14145 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-25596 | 6 | Residencial | Yes | 0-100kW
2022-GD-19540 | 4.03 | Residencial | Yes | 0-100kW
202501-NM25-04310 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-15094 | 3.54 | Residencial | Yes | 0-100kW
202512-NM25-05331 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00457 | 12.07 | Residencial | Yes | 0-100kW
2023-GD-39174 | 3.66 | Residencial | No | 0-100kW
2022-GD-27354 | 9.52 | Residencial | Yes | 0-100kW
202411-NM25-00038 | 4.392 | Residencial | Yes | 0-100kW
202506-NM25-02840 | 3.8 | Residencial | Yes | 0-100kW
202505-NM25-04106 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-21651 | 6.66 | Residencial | Yes | 0-100kW
2023-GD-22822 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04107 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01510 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20301 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-07606 | 6.95 | Residencial | Yes | 0-100kW
202512-NM25-03643 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02022 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-00185 | 3.24 | Residencial | Yes | 0-100kW
202506-NM25-02241 | 6 | Residencial | Yes | 0-100kW
202501-NM25-00427 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-02248 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-00014 | 7.87 | Residencial | Yes | 0-100kW
202501-NM25-04968 | 7.6 | Residencial | No | 0-100kW
202411-NM25-03305 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-05858 | 9.874 | Residencial | Yes | 0-100kW
2023-GD-23910 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00617 | 6 | Residencial | Yes | 0-100kW
15-9-318 | 4.3 | Residencial | Yes | 0-100kW
202506-NM25-00789 | 24 | Residencial | Yes | 0-100kW
2022-GD-02519 | 3.75 | Residencial | Yes | 0-100kW
2022-GD-01006 | 6.8 | Residencial | Yes | 0-100kW
202509-NM25-03695 | 13.824 | Comercial | Yes | 0-100kW
2022-GD-13716 | 4.39 | Residencial | Yes | 0-100kW
202406-NM25-02280 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-30430 | 3 | Residencial | Yes | 0-100kW
2023-GD-20731 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04717 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05336 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-27883 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04693 | 11.5 | Residencial | No | 0-100kW
202507-NM25-05049 | 24 | Residencial | Yes | 0-100kW
2023-GD-36025 | 3.8 | Residencial | Yes | 0-100kW
202312-NM25-00949 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-00202 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-04628 | 9.15 | Residencial | Yes | 0-100kW
2019-GD-00609 | 3.84 | Residencial | Yes | 0-100kW
202408-NM25-02922 | 3.8 | Residencial | Yes | 0-100kW
202410-NM25-02783 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-02615 | 9.882 | Residencial | Yes | 0-100kW
202412-NM25-00628 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00888 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-02056 | 5 | Residencial | Yes | 0-100kW
2023-GD-22592 | 4.76 | Residencial | Yes | 0-100kW
202411-NM25-00687 | 5.76 | Residencial | Yes | 0-100kW
202409-NM25-02451 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-35677 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01277 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-06286 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11795 | 3 | Residencial | Yes | 0-100kW
202403-NM25-04016 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-10309 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-06523 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-03656 | 12.98 | Residencial | Yes | 0-100kW
202502-NM25-03739 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18538 | 4.03 | Residencial | Yes | 0-100kW
16-2-0321 | 18 | Residencial | Yes | 0-100kW
202406-NM25-02236 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04152 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-01895 | 5.9 | Residencial | Yes | 0-100kW
202509-NM25-04143 | 11.5 | Residencial | No | 0-100kW
202504-NM25-03360 | 7.954 | Residencial | Yes | 0-100kW
202404-NM25-00495 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31883 | 19.2 | Residencial | Yes | 0-100kW
2023-GD-08688 | 5 | Residencial | Yes | 0-100kW
2020-GD-07356 | 7.5 | Residencial | Yes | 0-100kW
202312-NM25-02742 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-25553 | 4.99 | Residencial | Yes | 0-100kW
202408-NM25-04922 | 3.84 | Residencial | Yes | 0-100kW
17-3-125 | 4.25 | Residencial | Yes | 0-100kW
2020-GD-06968 | 4.48 | Residencial | Yes | 0-100kW
202410-NM25-04082 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26491 | 5 | Residencial | Yes | 0-100kW
2021-GD-00530 | 4.85 | Residencial | Yes | 0-100kW
2023-GD-32145 | 8.05 | Residencial | Yes | 0-100kW
2023-GD-04932 | 9.15 | Residencial | Yes | 0-100kW
2019-GD-03109 | 9 | Residencial | Yes | 0-100kW
202507-NM25-04587 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-13845 | 5 | Residencial | Yes | 0-100kW
202407-NM25-00961 | 4.758 | Residencial | Yes | 0-100kW
2023-GD-10579 | 4.2 | Residencial | Yes | 0-100kW
14-6-0083 | 7 | Residencial | Yes | 0-100kW
2023-GD-24149 | 6.8 | Residencial | Yes | 0-100kW
202505-NM25-03107 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-09657 | 3.66 | Residencial | Yes | 0-100kW
202408-NM25-03589 | 6 | Residencial | Yes | 0-100kW
2017-GD-02699 | 6.37 | Residencial | Yes | 0-100kW
2023-GD-02252 | 3.84 | Residencial | Yes | 0-100kW
16-2-1037 | 2.37 | Residencial | Yes | 0-100kW
202411-NM25-03172 | 7.26 | Residencial | Yes | 0-100kW
2023-GD-30881 | 3.8 | Residencial | No | 0-100kW
202411-NM25-01284 | 11.14 | Residencial | Yes | 0-100kW
202405-NM25-03025 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04521 | 3.8 | Residencial | Yes | 0-100kW
202409-NM25-02266 | 2.928 | Residencial | Yes | 0-100kW
2021-GD-01698 | 4.5 | Residencial | Yes | 0-100kW
2022-GD-08267 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-21642 | 13.172 | Residencial | Yes | 0-100kW
202410-NM25-02590 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33543 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-12537 | 4.76 | Residencial | Yes | 0-100kW
202405-NM25-00082 | 6.588 | Residencial | Yes | 0-100kW
202505-NM25-00307 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-01300 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14574 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-29899 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-07237 | 3.66 | Residencial | Yes | 0-100kW
202510-NM25-03402 | 8 | Residencial | Yes | 0-100kW
202411-NM25-01389 | 7.32 | Residencial | Yes | 0-100kW
202402-NM25-04473 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07320 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06143 | 3.5 | Residencial | Yes | 0-100kW
202407-NM25-02485 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01787 | 15.3 | Residencial | Yes | 0-100kW
202508-NM25-01307 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-00720 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-01344 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-39288 | 8.42 | Residencial | Yes | 0-100kW
202502-NM25-05640 | 10 | Residencial | Yes | 0-100kW
202507-NM25-03806 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-25546 | 9 | Residencial | Yes | 0-100kW
2020-GD-06817 | 7.31 | Residencial | Yes | 0-100kW
202506-NM25-00295 | 8 | Residencial | Yes | 0-100kW
2022-GD-28827 | 4.39 | Residencial | Yes | 0-100kW
202405-NM25-02606 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01837 | 6 | Residencial | Yes | 0-100kW
16-4-0055GD | 5 | Residencial | Yes | 0-100kW
202409-NM25-02289 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-03520 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09366 | 11.35 | Residencial | Yes | 0-100kW
202408-NM25-04699 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-13576 | 3.84 | Residencial | Yes | 0-100kW
2018-GD-00066 | 5.8 | Residencial | Yes | 0-100kW
2023-GD-01093 | 5.86 | Residencial | Yes | 0-100kW
2017-GD-02887 | 3.25 | Residencial | Yes | 0-100kW
202510-NM25-02204 | 11.46 | Residencial | No | 0-100kW
2018-GD-01157 | 4 | Residencial | Yes | 0-100kW
202507-NM25-04181 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-29674 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06721 | 4.72 | Residencial | Yes | 0-100kW
202405-NM25-02288 | 3.66 | Residencial | Yes | 0-100kW
202403-NM25-01874 | 8.052 | Residencial | Yes | 0-100kW
202511-NM25-00270 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-20117 | 4.61 | Residencial | Yes | 0-100kW
202508-NM25-04501 | 6.288 | Residencial | Yes | 0-100kW
2023-GD-01292 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-17520 | 14.64 | Residencial | Yes | 0-100kW
202510-NM25-03803 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04323 | 5.12 | Residencial | Yes | 0-100kW
2022-GD-07438 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-08524 | 7.6 | Residencial | Yes | 0-100kW
202310-NM25-00408 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03604 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14106 | 2.69 | Residencial | Yes | 0-100kW
2017-GD-02130 | 5.16 | Residencial | Yes | 0-100kW
202508-NM25-04985 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-04062 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01065 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-02531 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04434 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02568 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04955 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-02346 | 7.566 | Residencial | Yes | 0-100kW
2022-GD-09195 | 8 | Residencial | Yes | 0-100kW
202311-NM25-00429 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-25751 | 5 | Residencial | Yes | 0-100kW
202411-NM25-01256 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-00740 | 6 | Residencial | Yes | 0-100kW
202504-NM25-02860 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-00836 | 4 | Residencial | Yes | 0-100kW
2023-GD-27834 | 10.37 | Residencial | Yes | 0-100kW
2022-GD-08782 | 5 | Residencial | Yes | 0-100kW
2023-GD-18276 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-00848 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35651 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04366 | 8 | Residencial | Yes | 0-100kW
202504-NM25-02591 | 5.124 | Residencial | Yes | 0-100kW
2023-GD-13627 | 15.2 | Residencial | Yes | 0-100kW
202505-NM25-04886 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-28187 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-00871 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-09058 | 5 | Residencial | Yes | 0-100kW
202507-NM25-03511 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-21173 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02216 | 5 | Residencial | Yes | 0-100kW
2022-GD-26160 | 6.95 | Residencial | Yes | 0-100kW
2020-GD-07845 | 5.75 | Residencial | Yes | 0-100kW
202404-NM25-03485 | 11.712 | Comercial | Yes | 0-100kW
202508-NM25-02497 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-17239 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-39157 | 8 | Residencial | Yes | 0-100kW
202403-NM25-04079 | 8 | Residencial | Yes | 0-100kW
2022-GD-23494 | 6 | Residencial | Yes | 0-100kW
202501-NM25-02009 | 7.318 | Residencial | Yes | 0-100kW
2023-GD-20792 | 7.6 | Comercial | Yes | 0-100kW
2023-GD-25727 | 4.03 | Residencial | Yes | 0-100kW
202503-NM25-00939 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-03996 | 3.8 | Residencial | Yes | 0-100kW
202501-NM25-04808 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01068 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-03849 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-02721 | 5 | Residencial | Yes | 0-100kW
2023-GD-30209 | 2.95 | Residencial | Yes | 0-100kW
2019-GD-03315 | 6.49 | Residencial | Yes | 0-100kW
202403-NM25-00735 | 5 | Residencial | Yes | 0-100kW
202502-NM25-01854 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02993 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-22594 | 4.03 | Residencial | Yes | 0-100kW
202406-NM25-00739 | 15.2 | Residencial | Yes | 0-100kW
2017-GD-01727 | 9.75 | Residencial | Yes | 0-100kW
2022-GD-05459 | 5 | Residencial | Yes | 0-100kW
2023-GD-28539 | 4.76 | Residencial | Yes | 0-100kW
2020-GD-00232 | 4 | Residencial | Yes | 0-100kW
202508-NM25-01416 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03712 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-03106 | 3.8 | Residencial | Yes | 0-100kW
202404-NM25-00910 | 6 | Residencial | Yes | 0-100kW
2022-GD-19230 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-31591 | 5 | Residencial | Yes | 0-100kW
202407-NM25-02708 | 15.2 | Residencial | Yes | 0-100kW
202501-NM25-02047 | 15.2 | Residencial | Yes | 0-100kW
202503-NM25-05626 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-10568 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-10391 | 5 | Residencial | Yes | 0-100kW
2020-GD-07701 | 5 | Residencial | Yes | 0-100kW
2021-GD-07872 | 6 | Residencial | Yes | 0-100kW
2020-GD-04755 | 4 | Residencial | Yes | 0-100kW
2022-GD-18635 | 12.08 | Residencial | Yes | 0-100kW
2020-GD-01686 | 4.72 | Residencial | Yes | 0-100kW
2021-GD-04711 | 7.08 | Residencial | Yes | 0-100kW
14-2-190 | 15 | Residencial | Yes | 0-100kW
2022-GD-12628 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-01186 | 3.84 | Residencial | Yes | 0-100kW
16-4-0377GD | 1.7 | Residencial | Yes | 0-100kW
2022-GD-07797 | 5.49 | Residencial | Yes | 0-100kW
2021-GD-00791 | 4.5 | Residencial | Yes | 0-100kW
2023-GD-29156 | 7.59 | Residencial | Yes | 0-100kW
202511-NM25-00455 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-03680 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-09130 | 2.93 | Residencial | Yes | 0-100kW
202405-NM25-02186 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02689 | 6 | Comercial | Yes | 0-100kW
202407-NM25-01407 | 7.6 | Residencial | Yes | 0-100kW
15-3-859 | 6.25 | Residencial | Yes | 0-100kW
2023-GD-00927 | 4.76 | Residencial | Yes | 0-100kW
202401-NM25-00151 | 3.8 | Residencial | Yes | 0-100kW
202409-NM25-04302 | 9 | Residencial | Yes | 0-100kW
202512-NM25-01724 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-04064 | 8 | Residencial | Yes | 0-100kW
202410-NM25-02624 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-08428 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-01663 | 6.8 | Residencial | Yes | 0-100kW
202504-NM25-03231 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-13460 | 5.01 | Residencial | Yes | 0-100kW
202509-NM25-02020 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-02952 | 5.124 | Residencial | Yes | 0-100kW
202409-NM25-03822 | 7.2 | Residencial | Yes | 0-100kW
2022-GD-10582 | 9.6 | Residencial | Yes | 0-100kW
2020-GD-04029 | 3.25 | Residencial | Yes | 0-100kW
2023-GD-19524 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05484 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-19728 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03234 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-02699 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02310 | 7.6 | Residencial | No | 0-100kW
2022-GD-03167 | 7 | Residencial | Yes | 0-100kW
202411-NM25-02583 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-25167 | 4.03 | Residencial | Yes | 0-100kW
202510-NM25-01804 | 7.296 | Residencial | Yes | 0-100kW
202410-NM25-02725 | 6.222 | Residencial | Yes | 0-100kW
2023-GD-30195 | 5 | Residencial | Yes | 0-100kW
2022-GD-08075 | 5.12 | Residencial | Yes | 0-100kW
2022-GD-20109 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-30964 | 7.3 | Residencial | Yes | 0-100kW
2022-GD-20563 | 3.29 | Residencial | Yes | 0-100kW
202504-NM25-00379 | 7.38 | Residencial | Yes | 0-100kW
2020-GD-02694 | 6.75 | Residencial | Yes | 0-100kW
2022-GD-24778 | 8.78 | Residencial | Yes | 0-100kW
202408-NM25-03763 | 5 | Residencial | Yes | 0-100kW
202503-NM25-05484 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-00444 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-08416 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-03290 | 7.67 | Residencial | Yes | 0-100kW
2018-GD-00261 | 6.6 | Residencial | Yes | 0-100kW
2022-GD-28330 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-09562 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-24832 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-38520 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-17843 | 8.45 | Residencial | Yes | 0-100kW
2022-GD-10041 | 6 | Residencial | Yes | 0-100kW
202412-NM25-00090 | 5.124 | Residencial | Yes | 0-100kW
2023-GD-04723 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-19701 | 7.6 | Residencial | Yes | 0-100kW
15-9-173GD | 6 | Residencial | Yes | 0-100kW
2022-GD-01704 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-08081 | 5.12 | Residencial | Yes | 0-100kW
202401-NM25-04380 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-24983 | 7 | Residencial | Yes | 0-100kW
2022-GD-17607 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-01093 | 5 | Residencial | Yes | 0-100kW
2021-GD-12348 | 7.79 | Residencial | Yes | 0-100kW
2022-GD-26563 | 5 | Residencial | Yes | 0-100kW
2023-GD-31283 | 2.93 | Residencial | Yes | 0-100kW
202412-NM25-01385 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-12047 | 10 | Residencial | Yes | 0-100kW
2021-GD-08318 | 3.54 | Residencial | Yes | 0-100kW
202505-NM25-05194 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-20411 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-15202 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-17818 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05140 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33190 | 2.66 | Residencial | Yes | 0-100kW
202501-NM25-01446 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11240 | 8.78 | Residencial | Yes | 0-100kW
16-1-116 | 4.3 | Residencial | Yes | 0-100kW
2023-GD-22279 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-05597 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-07218 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-03004 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05074 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-01395 | 7.35 | Residencial | Yes | 0-100kW
2020-GD-03251 | 6 | Residencial | Yes | 0-100kW
202408-NM25-03931 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04698 | 8.784 | Residencial | Yes | 0-100kW
2023-GD-01414 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-04790 | 7.6 | Residencial | No | 0-100kW
15-7-245 | 25 | Comercial | Yes | 0-100kW
202502-NM25-03940 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01003 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18056 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02575 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-10096 | 3.54 | Residencial | Yes | 0-100kW
202506-NM25-00815 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06274 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-01944 | 3.66 | Residencial | Yes | 0-100kW
202409-NM25-02173 | 7.6 | Residencial | Yes | 0-100kW
202311-NM25-00331 | 8.052 | Residencial | Yes | 0-100kW
2021-GD-07767 | 6.8 | Residencial | Yes | 0-100kW
15-2-341 | 5.75 | Residencial | Yes | 0-100kW
202407-NM25-01957 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-01259 | 5.12 | Residencial | Yes | 0-100kW
2022-GD-22300 | 4.03 | Residencial | Yes | 0-100kW
202509-NM25-02547 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20256 | 8.42 | Residencial | Yes | 0-100kW
202410-NM25-01279 | 3.8 | Residencial | Yes | 0-100kW
2019-GD-02459 | 4.425 | Residencial | Yes | 0-100kW
2022-GD-31816 | 5 | Residencial | Yes | 0-100kW
2023-GD-38407 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-00138 | 3.54 | Residencial | Yes | 0-100kW
202503-NM25-04154 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-01767 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-03248 | 3.072 | Residencial | Yes | 0-100kW
202411-NM25-03359 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-03867 | 9.516 | Residencial | Yes | 0-100kW
202404-NM25-02730 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-01276 | 7.38 | Residencial | Yes | 0-100kW
2022-GD-27438 | 5.12 | Residencial | Yes | 0-100kW
202505-NM25-01901 | 5.76 | Residencial | Yes | 0-100kW
2020-GD-07159 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04286 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01390 | 5.605 | Residencial | Yes | 0-100kW
2022-GD-18367 | 8.42 | Residencial | Yes | 0-100kW
202504-NM25-03958 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14063 | 6 | Residencial | Yes | 0-100kW
2022-GD-01823 | 5.9 | Residencial | Yes | 0-100kW
202405-NM25-04092 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-34396 | 7.6 | Residencial | Yes | 0-100kW
15-7-374 | 14 | Residencial | Yes | 0-100kW
202504-NM25-01652 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02440 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-23897 | 8.05 | Residencial | Yes | 0-100kW
202402-NM25-01980 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04977 | 3.456 | Residencial | Yes | 0-100kW
202504-NM25-01217 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00874 | 4.09 | Residencial | Yes | 0-100kW
2022-GD-11759 | 8 | Residencial | Yes | 0-100kW
2022-GD-11661 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-17965 | 5.49 | Residencial | Yes | 0-100kW
202508-NM25-04285 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-04127 | 8 | Residencial | Yes | 0-100kW
2023-GD-31657 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14710 | 6.14 | Residencial | Yes | 0-100kW
202409-NM25-03917 | 3.8 | Residencial | Yes | 0-100kW
202412-NM25-03700 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-02062 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-13145 | 6.22 | Residencial | Yes | 0-100kW
2021-GD-04531 | 4.43 | Residencial | Yes | 0-100kW
202406-NM25-00658 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-04943 | 6 | Residencial | Yes | 0-100kW
2023-GD-27733 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-02812 | 7.67 | Residencial | Yes | 0-100kW
2022-GD-29796 | 5.38 | Residencial | Yes | 0-100kW
2020-GD-07487 | 5.5 | Residencial | Yes | 0-100kW
2019-GD-01116 | 5.9 | Residencial | Yes | 0-100kW
2022-GD-28954 | 6.14 | Residencial | Yes | 0-100kW
2020-GD-03239 | 3.25 | Residencial | Yes | 0-100kW
2023-GD-16125 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09496 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01992 | 8 | Residencial | Yes | 0-100kW
2023-GD-05153 | 5.49 | Residencial | Yes | 0-100kW
202511-NM25-00280 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-02262 | 3.54 | Residencial | Yes | 0-100kW
202512-NM25-05070 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-01916 | 3.24 | Residencial | Yes | 0-100kW
202505-NM25-00386 | 7.68 | Residencial | Yes | 0-100kW
2021-GD-09397 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-02971 | 5.86 | Residencial | Yes | 0-100kW
202501-NM25-02145 | 15 | Residencial | Yes | 0-100kW
202412-NM25-02513 | 3.072 | Residencial | Yes | 0-100kW
202501-NM25-03240 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01646 | 8.35 | Residencial | Yes | 0-100kW
202512-NM25-02676 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-02447 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-05542 | 11.5 | Residencial | Yes | 0-100kW
15-2-140 | 4.2 | Residencial | Yes | 0-100kW
2017-GD-03060 | 2.58 | Residencial | Yes | 0-100kW
2022-GD-05840 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-32266 | 4.03 | Residencial | Yes | 0-100kW
202409-NM25-02146 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04243 | 8 | Residencial | Yes | 0-100kW
202403-NM25-03152 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-29406 | 5 | Residencial | Yes | 0-100kW
2019-GD-01612 | 3.245 | Residencial | Yes | 0-100kW
2023-GD-23490 | 15.36 | Residencial | Yes | 0-100kW
2023-GD-11481 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04508 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03752 | 3.25 | Residencial | Yes | 0-100kW
202510-NM25-00888 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-01181 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-13143 | 3.54 | Residencial | No | 0-100kW
202410-NM25-01678 | 8 | Residencial | Yes | 0-100kW
2022-GD-15842 | 5.01 | Residencial | Yes | 0-100kW
202501-NM25-00882 | 4.026 | Residencial | Yes | 0-100kW
202412-NM25-03613 | 4.026 | Residencial | Yes | 0-100kW
202410-NM25-00336 | 6 | Residencial | Yes | 0-100kW
2022-GD-00958 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-10811 | 5.12 | Residencial | Yes | 0-100kW
202504-NM25-05102 | 5.5 | Residencial | Yes | 0-100kW
2022-GD-29519 | 3.8 | Residencial | Yes | 0-100kW
14-3-896 | 8 | Residencial | Yes | 0-100kW
2023-GD-33106 | 3.8 | Residencial | Yes | 0-100kW
202410-NM25-03284 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09863 | 4.03 | Residencial | Yes | 0-100kW
202502-NM25-01016 | 5.76 | Residencial | Yes | 0-100kW
202504-NM25-05147 | 8 | Residencial | Yes | 0-100kW
2022-GD-23856 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-06012 | 8 | Residencial | Yes | 0-100kW
202509-NM25-04694 | 8.418 | Residencial | Yes | 0-100kW
2023-GD-09501 | 20.76 | Residencial | Yes | 0-100kW
2022-GD-15765 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-02186 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-04841 | 6.8 | Residencial | Yes | 0-100kW
202405-NM25-02272 | 8 | Residencial | Yes | 0-100kW
2023-GD-05257 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-13106 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22484 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-19726 | 5.86 | Residencial | Yes | 0-100kW
16-7-0146 | 4.52 | Residencial | Yes | 0-100kW
202410-NM25-01958 | 11.024 | Residencial | Yes | 0-100kW
2023-GD-04699 | 5.2 | Comercial | Yes | 0-100kW
2023-GD-31531 | 4.39 | Residencial | No | 0-100kW
202503-NM25-02826 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-02124 | 7.764 | Residencial | Yes | 0-100kW
2023-GD-12799 | 15.2 | Residencial | Yes | 0-100kW
2017-GD-01603 | 4.515 | Residencial | Yes | 0-100kW
202504-NM25-00071 | 7.6 | Residencial | Yes | 0-100kW
15-9-273 | 2.58 | Residencial | Yes | 0-100kW
202406-NM25-01167 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-25359 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-20696 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-16098 | 20.13 | Residencial | Yes | 0-100kW
202404-NM25-03708 | 8.418 | Residencial | Yes | 0-100kW
202503-NM25-01950 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-01771 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00500 | 9 | Residencial | Yes | 0-100kW
2022-GD-00835 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02303 | 13.6 | Residencial | Yes | 0-100kW
2022-GD-03957 | 7.97 | Residencial | Yes | 0-100kW
202404-NM25-02080 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01768 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-04865 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-08912 | 16 | Residencial | Yes | 0-100kW
202402-NM25-01554 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24976 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-24649 | 24.89 | Residencial | Yes | 0-100kW
2020-GD-03060 | 3.5 | Residencial | Yes | 0-100kW
202409-NM25-02072 | 8 | Residencial | Yes | 0-100kW
2023-GD-20604 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03779 | 5 | Residencial | Yes | 0-100kW
2023-GD-29829 | 15.2 | Comercial | Yes | 0-100kW
2022-GD-03514 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-01121 | 10 | Residencial | Yes | 0-100kW
202510-NM25-03105 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-06034 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-16403 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00581 | 5.52 | Residencial | Yes | 0-100kW
202407-NM25-00439 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-01552 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-13508 | 7.6 | Residencial | Yes | 0-100kW
15-2-728 | 2.58 | Residencial | Yes | 0-100kW
202312-NM25-03572 | 8.052 | Residencial | Yes | 0-100kW
202402-NM25-02961 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02078 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02785 | 3.8 | Residencial | Yes | 0-100kW
202406-NM25-03064 | 3.8 | Residencial | Yes | 0-100kW
202409-NM25-02588 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00852 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14056 | 7.97 | Residencial | No | 0-100kW
2023-GD-18165 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-29852 | 4.39 | Residencial | Yes | 0-100kW
202504-NM25-02698 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-17882 | 6.22 | Residencial | Yes | 0-100kW
2021-GD-04326 | 7.38 | Residencial | Yes | 0-100kW
2023-GD-25976 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-09394 | 5 | Residencial | Yes | 0-100kW
202511-NM25-01710 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-02528 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-03046 | 15.2 | Residencial | Yes | 0-100kW
202409-NM25-00940 | 8 | Residencial | Yes | 0-100kW
2021-GD-04404 | 3.54 | Residencial | Yes | 0-100kW
16-1-338 | 4 | Residencial | Yes | 0-100kW
202504-NM25-05214 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11235 | 5 | Residencial | Yes | 0-100kW
2022-GD-26935 | 8.78 | Residencial | Yes | 0-100kW
202409-NM25-03088 | 6 | Residencial | Yes | 0-100kW
202406-NM25-02612 | 2.928 | Residencial | Yes | 0-100kW
2021-GD-08622 | 8.85 | Residencial | Yes | 0-100kW
202511-NM25-04378 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-28055 | 4.03 | Residencial | Yes | 0-100kW
202511-NM25-02930 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-02905 | 15.2 | Residencial | Yes | 0-100kW
202503-NM25-03614 | 8 | Residencial | Yes | 0-100kW
2023-GD-16011 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11789 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-01153 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-02104 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-00470 | 6.8 | Residencial | Yes | 0-100kW
202405-NM25-00619 | 18.3 | Residencial | Yes | 0-100kW
202408-NM25-01344 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12784 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-03779 | 8 | Residencial | Yes | 0-100kW
202407-NM25-01897 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-29132 | 5.7 | Residencial | Yes | 0-100kW
202508-NM25-00402 | 15.3 | Residencial | Yes | 0-100kW
202502-NM25-00007 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05260 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-01733 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-06445 | 3.66 | Residencial | Yes | 0-100kW
15-9-550 | 6 | Residencial | Yes | 0-100kW
2023-GD-35088 | 3.84 | Residencial | Yes | 0-100kW
202407-NM25-03947 | 3.294 | Residencial | Yes | 0-100kW
2022-GD-20786 | 3.66 | Residencial | Yes | 0-100kW
2019-GD-02912 | 3.245 | Residencial | Yes | 0-100kW
2022-GD-09070 | 3.24 | Residencial | Yes | 0-100kW
202502-NM25-03389 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01320 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-04579 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19448 | 4.03 | Residencial | Yes | 0-100kW
202409-NM25-02552 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-03211 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-04103 | 6.8 | Residencial | Yes | 0-100kW
15-7-1043 | 6 | Residencial | Yes | 0-100kW
202410-NM25-01919 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-09020 | 3.24 | Residencial | Yes | 0-100kW
202511-NM25-02142 | 23 | Residencial | Yes | 0-100kW
2018-GD-01953 | 3 | Residencial | Yes | 0-100kW
2023-GD-12358 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-16711 | 4.03 | Residencial | Yes | 0-100kW
202405-NM25-02176 | 12 | Residencial | Yes | 0-100kW
202411-NM25-00158 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-29917 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-37149 | 5 | Residencial | Yes | 0-100kW
202502-NM25-05053 | 7.6 | Residencial | Yes | 0-100kW
15-2-459 | 8.67 | Residencial | No | 0-100kW
2022-GD-07593 | 4.03 | Residencial | Yes | 0-100kW
2019-GD-02244 | 5 | Residencial | Yes | 0-100kW
2023-GD-29293 | 9.52 | Residencial | Yes | 0-100kW
2022-GD-18724 | 4.39 | Residencial | Yes | 0-100kW
13-3-014 | 8 | Residencial | Yes | 0-100kW
202503-NM25-01335 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09326 | 4.43 | Residencial | Yes | 0-100kW
202310-NM25-00015 | 8.14 | Residencial | No | 0-100kW
2017-GD-01410 | 3.225 | Residencial | Yes | 0-100kW
2022-GD-21173 | 6.95 | Residencial | Yes | 0-100kW
202409-NM25-00919 | 3.5 | Residencial | Yes | 0-100kW
2021-GD-07254 | 5.9 | Residencial | Yes | 0-100kW
2022-GD-09001 | 5 | Residencial | No | 0-100kW
202410-NM25-02470 | 11.22 | Residencial | Yes | 0-100kW
2022-GD-28787 | 5.38 | Residencial | Yes | 0-100kW
202402-NM25-04328 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02300 | 5.76 | Residencial | Yes | 0-100kW
202411-NM25-03669 | 3.8 | Residencial | Yes | 0-100kW
202506-NM25-02119 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-07902 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01201 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-02017 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-09610 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-04228 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-05753 | 4.25 | Residencial | Yes | 0-100kW
202410-NM25-04782 | 6 | Residencial | Yes | 0-100kW
2022-GD-30544 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-00057 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-29060 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-08586 | 3.54 | Residencial | Yes | 0-100kW
202406-NM25-01720 | 5.49 | Comercial | Yes | 0-100kW
2022-GD-19179 | 5.12 | Residencial | Yes | 0-100kW
202512-NM25-02664 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-01324 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-05196 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-03013 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-07343 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04230 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-29354 | 8.42 | Residencial | Yes | 0-100kW
202401-NM25-00314 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22278 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-00010 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-06653 | 8.78 | Residencial | Yes | 0-100kW
202412-NM25-01642 | 6 | Residencial | Yes | 0-100kW
2023-GD-31479 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-09231 | 8.78 | Residencial | Yes | 0-100kW
202412-NM25-02188 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11028 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-00594 | 8.42 | Residencial | Yes | 0-100kW
2019-GD-01518 | 5.5 | Comercial | Yes | 0-100kW
2019-GD-02664 | 3.54 | Residencial | Yes | 0-100kW
10-1-481 | 8.3 | Residencial | Yes | 0-100kW
2023-GD-36396 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-11533 | 6.19 | Residencial | Yes | 0-100kW
202407-NM25-00810 | 2.928 | Residencial | Yes | 0-100kW
202407-NM25-00780 | 3.294 | Residencial | Yes | 0-100kW
2021-GD-12127 | 5.61 | Residencial | Yes | 0-100kW
2023-GD-01169 | 3.84 | Residencial | Yes | 0-100kW
202502-NM25-02747 | 6.912 | Residencial | Yes | 0-100kW
2021-GD-04182 | 2.95 | Residencial | Yes | 0-100kW
202412-NM25-00068 | 7.08 | Residencial | Yes | 0-100kW
202403-NM25-01969 | 4.392 | Residencial | Yes | 0-100kW
16-5-0423A | 4.95 | Residencial | Yes | 0-100kW
202402-NM25-03568 | 7.26 | Residencial | Yes | 0-100kW
2023-GD-12007 | 5 | Residencial | Yes | 0-100kW
2022-GD-17776 | 6.59 | Residencial | Yes | 0-100kW
202506-NM25-03926 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-00486 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02895 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-00281 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-15514 | 4.43 | Residencial | Yes | 0-100kW
202506-NM25-03517 | 10 | Residencial | Yes | 0-100kW
202401-NM25-02834 | 6 | Residencial | Yes | 0-100kW
202401-NM25-00933 | 8.052 | Residencial | Yes | 0-100kW
16-6-0144 | 9 | Residencial | Yes | 0-100kW
202403-NM25-01173 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-22286 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-12781 | 5 | Residencial | Yes | 0-100kW
2020-GD-06595 | 4.43 | Residencial | Yes | 0-100kW
202401-NM25-03775 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-00298 | 4.224 | Residencial | Yes | 0-100kW
2020-GD-02571 | 6 | Residencial | Yes | 0-100kW
2021-GD-09703 | 3.8 | Residencial | Yes | 0-100kW
202407-NM25-02449 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-03671 | 3.3 | Comercial | Yes | 0-100kW
2020-GD-07873 | 5 | Residencial | Yes | 0-100kW
2022-GD-11652 | 3.66 | Residencial | Yes | 0-100kW
202412-NM25-01598 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01020 | 5.376 | Residencial | Yes | 0-100kW
2023-GD-37388 | 8 | Residencial | No | 0-100kW
2023-GD-21568 | 8 | Residencial | Yes | 0-100kW
2022-GD-14961 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-36349 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-02799 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-22865 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-15724 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01316 | 3.66 | Residencial | Yes | 0-100kW
202509-NM25-01537 | 6.912 | Residencial | Yes | 0-100kW
202502-NM25-04905 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-31643 | 5.49 | Residencial | Yes | 0-100kW
202501-NM25-05592 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-12907 | 5.5 | Residencial | Yes | 0-100kW
202502-NM25-05820 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-09183 | 6.8 | Residencial | Yes | 0-100kW
202507-NM25-03301 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-18716 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-00316 | 4.13 | Residencial | Yes | 0-100kW
2021-GD-09820 | 7.38 | Residencial | Yes | 0-100kW
2023-GD-08258 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01387 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-21670 | 6.95 | Residencial | Yes | 0-100kW
202512-NM25-00198 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-01534 | 3.66 | Residencial | Yes | 0-100kW
202311-NM25-00948 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02981 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-30086 | 8 | Residencial | Yes | 0-100kW
202511-NM25-01667 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-06968 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04163 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-13259 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03016 | 6.59 | Residencial | Yes | 0-100kW
2022-GD-15280 | 5 | Residencial | Yes | 0-100kW
202407-NM25-01521 | 15.2 | Residencial | Yes | 0-100kW
202405-NM25-00462 | 2.1 | Residencial | Yes | 0-100kW
15-1-362 | 7.68 | Residencial | No | 0-100kW
2022-GD-27838 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-01011 | 4.224 | Residencial | Yes | 0-100kW
2023-GD-30528 | 4.76 | Residencial | Yes | 0-100kW
2020-GD-08407 | 6.49 | Residencial | Yes | 0-100kW
2020-GD-04027 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-15456 | 10.98 | Residencial | Yes | 0-100kW
202509-NM25-03027 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14093 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-03007 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00274 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-23505 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13741 | 4.39 | Residencial | No | 0-100kW
202506-NM25-03081 | 23 | Residencial | Yes | 0-100kW
202407-NM25-01119 | 4.608 | Residencial | Yes | 0-100kW
202503-NM25-05708 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01421 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-05755 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-03211 | 5.76 | Residencial | Yes | 0-100kW
202403-NM25-03337 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17925 | 5.61 | Residencial | Yes | 0-100kW
2022-GD-19761 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-38299 | 4.76 | Residencial | Yes | 0-100kW
202405-NM25-00899 | 3.66 | Residencial | Yes | 0-100kW
202509-NM25-05770 | 4.608 | Residencial | Yes | 0-100kW
202404-NM25-01259 | 10.98 | Residencial | Yes | 0-100kW
202509-NM25-03850 | 11.5 | Residencial | No | 0-100kW
2022-GD-32637 | 4.03 | Residencial | Yes | 0-100kW
202503-NM25-03045 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14415 | 7.32 | Residencial | Yes | 0-100kW
202312-NM25-02947 | 15.2 | Residencial | Yes | 0-100kW
2017-GD-03322 | 7.5 | Residencial | Yes | 0-100kW
202409-NM25-01777 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01173 | 6 | Residencial | Yes | 0-100kW
2023-GD-15921 | 3 | Residencial | Yes | 0-100kW
2020-GD-00799 | 6.785 | Residencial | Yes | 0-100kW
2021-GD-15065 | 8.26 | Residencial | Yes | 0-100kW
2023-GD-20464 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-00050 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15657 | 6.22 | Residencial | Yes | 0-100kW
2019-GD-01622 | 5.5 | Residencial | Yes | 0-100kW
202504-NM25-01474 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14485 | 3.54 | Residencial | Yes | 0-100kW
202504-NM25-01115 | 9 | Residencial | Yes | 0-100kW
2022-GD-19260 | 4.39 | Residencial | Yes | 0-100kW
202408-NM25-03187 | 15.2 | Residencial | Yes | 0-100kW
202411-NM25-00233 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03302 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-18584 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-38458 | 5 | Residencial | Yes | 0-100kW
2020-GD-06186 | 5.61 | Residencial | Yes | 0-100kW
202505-NM25-03484 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-01105 | 3.12 | Residencial | Yes | 0-100kW
2020-GD-08268 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-33608 | 5.86 | Residencial | Yes | 0-100kW
202501-NM25-02092 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06161 | 4.13 | Residencial | Yes | 0-100kW
202312-NM25-01269 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02449 | 10 | Residencial | Yes | 0-100kW
202512-NM25-05551 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10643 | 6.22 | Residencial | Yes | 0-100kW
2023-GD-32964 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-01767 | 9.6 | Residencial | Yes | 0-100kW
202509-NM25-03200 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05037 | 5.86 | Residencial | Yes | 0-100kW
202401-NM25-00986 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-03874 | 9 | Residencial | Yes | 0-100kW
202502-NM25-06306 | 15.2 | Residencial | No | 0-100kW
12-1-326 | 6 | Residencial | Yes | 0-100kW
2021-GD-09650 | 4.03 | Residencial | Yes | 0-100kW
202407-NM25-02502 | 3.66 | Residencial | Yes | 0-100kW
2017-GD-00569 | 2.365 | Residencial | Yes | 0-100kW
2022-GD-28941 | 6 | Residencial | Yes | 0-100kW
2020-GD-08869 | 3.25 | Residencial | Yes | 0-100kW
202402-NM25-03694 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05051 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-22428 | 6 | Residencial | Yes | 0-100kW
202505-NM25-03146 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04126 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07455 | 3.25 | Residencial | Yes | 0-100kW
202501-NM25-03025 | 8 | Residencial | Yes | 0-100kW
202509-NM25-05737 | 6.528 | Residencial | Yes | 0-100kW
13-2-679 | 6.8 | Residencial | Yes | 0-100kW
202511-NM25-00931 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-03707 | 9 | Residencial | Yes | 0-100kW
202405-NM25-01464 | 6.144 | Residencial | Yes | 0-100kW
2023-GD-38632 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01715 | 4.392 | Residencial | Yes | 0-100kW
202501-NM25-01469 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-00938 | 3.5 | Residencial | Yes | 0-100kW
202501-NM25-03773 | 3.66 | Residencial | Yes | 0-100kW
202408-NM25-03347 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02972 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22078 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-00142 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-01571 | 5.124 | Residencial | Yes | 0-100kW
2023-GD-39325 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-38834 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-29725 | 8.42 | Residencial | Yes | 0-100kW
202506-NM25-03019 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19802 | 6.95 | Residencial | Yes | 0-100kW
15-2-453 | 4 | Residencial | Yes | 0-100kW
2020-GD-04654 | 3.84 | Residencial | Yes | 0-100kW
202504-NM25-05308 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-01101 | 3.8 | Residencial | Yes | 0-100kW
202412-NM25-03666 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-01283 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04285 | 3.66 | Residencial | Yes | 0-100kW
202503-NM25-02458 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04390 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-07113 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-23093 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19562 | 5.49 | Residencial | Yes | 0-100kW
202510-NM25-00081 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-13339 | 5 | Comercial | Yes | 0-100kW
2023-GD-18096 | 8 | Residencial | Yes | 0-100kW
202409-NM25-03072 | 22.8 | Residencial | Yes | 0-100kW
2023-GD-02816 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-01559 | 9.15 | Residencial | Yes | 0-100kW
2022-GD-02964 | 4.76 | Residencial | Yes | 0-100kW
202503-NM25-03473 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04416 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-27075 | 8.45 | Residencial | Yes | 0-100kW
202408-NM25-02779 | 15.2 | Residencial | Yes | 0-100kW
202402-NM25-04459 | 7.5 | Residencial | Yes | 0-100kW
202404-NM25-00562 | 19.398 | Residencial | Yes | 0-100kW
202506-NM25-00821 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-02088 | 14.274 | Residencial | Yes | 0-100kW
2023-GD-37052 | 4.61 | Residencial | Yes | 0-100kW
2022-GD-18126 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-03258 | 9.216 | Residencial | Yes | 0-100kW
202401-NM25-02246 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-00453 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-07038 | 6 | Residencial | Yes | 0-100kW
202312-NM25-03075 | 8.052 | Residencial | Yes | 0-100kW
2023-GD-17769 | 6.59 | Residencial | Yes | 0-100kW
2022-GD-31244 | 9.6 | Residencial | Yes | 0-100kW
2022-GD-29059 | 5 | Residencial | Yes | 0-100kW
19-7-159GD | 8.4 | Residencial | Yes | 0-100kW
2022-GD-07992 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-01653 | 3.54 | Residencial | Yes | 0-100kW
202512-NM25-01501 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-11231 | 5 | Residencial | Yes | 0-100kW
2022-GD-17597 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-19543 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03939 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-00210 | 4.608 | Residencial | Yes | 0-100kW
2022-GD-08125 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-15741 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-15169 | 3.54 | Residencial | Yes | 0-100kW
202502-NM25-03963 | 5.76 | Residencial | Yes | 0-100kW
202509-NM25-05076 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16724 | 3.84 | Residencial | Yes | 0-100kW
202407-NM25-00081 | 5.124 | Residencial | Yes | 0-100kW
2021-GD-12391 | 8 | Residencial | Yes | 0-100kW
202404-NM25-02537 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-27655 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-03543 | 5 | Residencial | Yes | 0-100kW
2023-GD-38413 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-29303 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03781 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-03745 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-01940 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02264 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24624 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-04058 | 3.5 | Residencial | Yes | 0-100kW
202406-NM25-03293 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-03226 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-02662 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-03482 | 5.76 | Residencial | Yes | 0-100kW
2017-GD-02647 | 2.5 | Residencial | Yes | 0-100kW
202312-NM25-02593 | 4.758 | Residencial | Yes | 0-100kW
2022-GD-19610 | 3.66 | Residencial | Yes | 0-100kW
202502-NM25-03053 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-02421 | 3 | Residencial | Yes | 0-100kW
2021-GD-12105 | 3.24 | Residencial | Yes | 0-100kW
202501-NM25-04823 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01499 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-02702 | 11.5 | Residencial | No | 0-100kW
202410-NM25-03906 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-02560 | 5.16 | Residencial | Yes | 0-100kW
2023-GD-00219 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-24252 | 5 | Residencial | Yes | 0-100kW
202502-NM25-04666 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-06018 | 6.47 | Residencial | Yes | 0-100kW
202502-NM25-05732 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-01156 | 11.5 | Residencial | Yes | 0-100kW
202309-NM25-00008 | 8.14 | Residencial | Yes | 0-100kW
202408-NM25-04693 | 10.248 | Residencial | Yes | 0-100kW
202510-NM25-01000 | 11.5 | Residencial | Yes | 0-100kW
202312-NM25-00264 | 4.992 | Residencial | No | 0-100kW
202404-NM25-00704 | 8 | Residencial | Yes | 0-100kW
2020-GD-08115 | 3.25 | Residencial | Yes | 0-100kW
202406-NM25-02119 | 15.2 | Residencial | Yes | 0-100kW
202408-NM25-04184 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-25812 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02951 | 7.8 | Residencial | No | 0-100kW
202404-NM25-02987 | 6.588 | Residencial | Yes | 0-100kW
202505-NM25-00708 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-01556 | 5.49 | Residencial | Yes | 0-100kW
2017-GD-00384 | 6.5 | Residencial | Yes | 0-100kW
202510-NM25-02195 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-01960 | 8.35 | Residencial | Yes | 0-100kW
15-4-0233GD | 3.87 | Residencial | Yes | 0-100kW
2022-GD-06260 | 4.39 | Residencial | Yes | 0-100kW
202412-NM25-00466 | 15.2 | Residencial | Yes | 0-100kW
2017-GD-03312 | 5.16 | Residencial | Yes | 0-100kW
2021-GD-02952 | 4 | Residencial | Yes | 0-100kW
2021-GD-04002 | 4.43 | Residencial | Yes | 0-100kW
2017-GD-00744 | 5.75 | Residencial | Yes | 0-100kW
202311-NM25-01025 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-21868 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26593 | 8 | Residencial | Yes | 0-100kW
2022-GD-15385 | 5 | Residencial | Yes | 0-100kW
202502-NM25-02280 | 8 | Residencial | Yes | 0-100kW
202407-NM25-04106 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02522 | 3.66 | Residencial | Yes | 0-100kW
202503-NM25-02375 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03506 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-00049 | 5.5 | Residencial | Yes | 0-100kW
2022-GD-25770 | 9.15 | Residencial | Yes | 0-100kW
2021-GD-15191 | 2.95 | Residencial | Yes | 0-100kW
2022-GD-05673 | 4.39 | Residencial | Yes | 0-100kW
14-7-214 | 5 | Residencial | Yes | 0-100kW
2023-GD-11714 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-00330 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09200 | 6.95 | Residencial | Yes | 0-100kW
2021-GD-06753 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-18688 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26082 | 5 | Residencial | Yes | 0-100kW
202404-NM25-00964 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-24438 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-01709 | 7.3 | Residencial | Yes | 0-100kW
16-7-0006 | 2.58 | Residencial | Yes | 0-100kW
2023-GD-33175 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-00623 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18175 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01084 | 3.84 | Residencial | Yes | 0-100kW
202504-NM25-04413 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-00226 | 6 | Residencial | Yes | 0-100kW
202507-NM25-03723 | 15 | Residencial | Yes | 0-100kW
2019-GD-00602 | 4.3 | Residencial | Yes | 0-100kW
202405-NM25-00800 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-06605 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-14699 | 8.26 | Residencial | Yes | 0-100kW
202406-NM25-03204 | 15.2 | Residencial | Yes | 0-100kW
202502-NM25-01290 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-02586 | 3.8 | Residencial | Yes | 0-100kW
202506-NM25-00940 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-01674 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21458 | 6 | Residencial | Yes | 0-100kW
202406-NM25-02869 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-12408 | 5.9 | Residencial | Yes | 0-100kW
202511-NM25-00599 | 3.84 | Residencial | No | 0-100kW
2023-GD-19874 | 4.76 | Comercial | Yes | 0-100kW
2021-GD-14695 | 5.9 | Residencial | Yes | 0-100kW
2022-GD-24672 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-09907 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19180 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-04816 | 6 | Residencial | Yes | 0-100kW
2021-GD-00266 | 3.84 | Residencial | Yes | 0-100kW
202411-NM25-00187 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02002 | 8 | Residencial | Yes | 0-100kW
2023-GD-05675 | 5 | Residencial | Yes | 0-100kW
202505-NM25-03235 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-32471 | 5.86 | Residencial | Yes | 0-100kW
202505-NM25-00583 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29536 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02858 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-05466 | 5 | Residencial | Yes | 0-100kW
202506-NM25-01944 | 5.376 | Residencial | Yes | 0-100kW
2017-GD-01257 | 8.5 | Residencial | Yes | 0-100kW
202408-NM25-01669 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36405 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-30670 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01627 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05194 | 4.224 | Residencial | Yes | 0-100kW
202409-NM25-00863 | 8 | Residencial | Yes | 0-100kW
202504-NM25-01940 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03003 | 10.368 | Residencial | Yes | 0-100kW
202505-NM25-05115 | 12 | Residencial | Yes | 0-100kW
202504-NM25-01811 | 2.928 | Residencial | Yes | 0-100kW
2022-GD-10929 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-32952 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03029 | 6.912 | Residencial | Yes | 0-100kW
2023-GD-03359 | 4.22 | Residencial | Yes | 0-100kW
202504-NM25-00409 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-08444 | 10 | Residencial | Yes | 0-100kW
202502-NM25-02319 | 10.248 | Residencial | Yes | 0-100kW
202402-NM25-00201 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11007 | 5.31 | Residencial | Yes | 0-100kW
202401-NM25-01291 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-00700 | 3.85 | Residencial | Yes | 0-100kW
2021-GD-11191 | 6.49 | Residencial | Yes | 0-100kW
202411-NM25-02040 | 3.8 | Residencial | Yes | 0-100kW
202402-NM25-03012 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-04643 | 4.224 | Residencial | Yes | 0-100kW
202509-NM25-06066 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00992 | 15.2 | Residencial | Yes | 0-100kW
202408-NM25-04607 | 3.8 | Residencial | Yes | 0-100kW
202402-NM25-01071 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24074 | 3.66 | Residencial | Yes | 0-100kW
15-7-290 | 5 | Residencial | Yes | 0-100kW
2018-GD-01217 | 5.28 | Residencial | Yes | 0-100kW
202502-NM25-01550 | 12 | Residencial | Yes | 0-100kW
2021-GD-15385 | 7.67 | Residencial | Yes | 0-100kW
2021-GD-11153 | 8.26 | Residencial | Yes | 0-100kW
202409-NM25-02582 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02152 | 4.026 | Residencial | Yes | 0-100kW
2019-GD-01444 | 4.15 | Residencial | Yes | 0-100kW
202505-NM25-02170 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14327 | 5 | Residencial | Yes | 0-100kW
202504-NM25-03708 | 3.8 | Residencial | Yes | 0-100kW
202401-NM25-02812 | 9.882 | Residencial | Yes | 0-100kW
2022-GD-00987 | 4.43 | Residencial | Yes | 0-100kW
14-5-0264A | 14 | Residencial | Yes | 0-100kW
202401-NM25-03574 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-01513 | 6 | Residencial | Yes | 0-100kW
2022-GD-02976 | 6.8 | Residencial | Yes | 0-100kW
202503-NM25-03731 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-01857 | 3.456 | Residencial | Yes | 0-100kW
2023-GD-36064 | 10.98 | Residencial | Yes | 0-100kW
2023-GD-27826 | 13.91 | Residencial | Yes | 0-100kW
15-9-314 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04330 | 6 | Residencial | Yes | 0-100kW
2023-GD-19385 | 5 | Residencial | Yes | 0-100kW
2023-GD-26745 | 12.08 | Residencial | Yes | 0-100kW
2023-GD-26652 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04072 | 15.2 | Residencial | Yes | 0-100kW
2020-GD-02903 | 7.97 | Residencial | Yes | 0-100kW
2019-GD-02954 | 5 | Residencial | Yes | 0-100kW
2023-GD-06494 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-25056 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04803 | 5.76 | Residencial | Yes | 0-100kW
2020-GD-01129 | 3 | Residencial | Yes | 0-100kW
2023-GD-23237 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01150 | 5.31 | Residencial | Yes | 0-100kW
202403-NM25-01906 | 13.542 | Residencial | Yes | 0-100kW
2022-GD-12106 | 3.29 | Residencial | Yes | 0-100kW
2023-GD-07488 | 6 | Residencial | Yes | 0-100kW
2022-GD-07439 | 6.49 | Residencial | Yes | 0-100kW
2021-GD-06544 | 4.43 | Residencial | Yes | 0-100kW
15-5-0205A | 8.17 | Residencial | No | 0-100kW
2023-GD-29847 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03266 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-01156 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31353 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-00927 | 8.4 | Residencial | Yes | 0-100kW
2022-GD-29657 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-17344 | 5.49 | Residencial | Yes | 0-100kW
2020-GD-03894 | 6.78 | Residencial | Yes | 0-100kW
2022-GD-06712 | 2.93 | Residencial | Yes | 0-100kW
202406-NM25-02238 | 7.6 | Residencial | No | 0-100kW
2023-GD-09019 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-13475 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-24121 | 2.66 | Comercial | Yes | 0-100kW
2023-GD-31352 | 7.6 | Residencial | No | 0-100kW
2023-GD-19612 | 7.6 | Residencial | Yes | 0-100kW
14-2-846 | 6 | Residencial | Yes | 0-100kW
202510-NM25-00227 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-06891 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-11069 | 6.95 | Residencial | Yes | 0-100kW
202510-NM25-04347 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04712 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03833 | 8 | Residencial | Yes | 0-100kW
202411-NM25-03473 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-03841 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21632 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-00024 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-01490 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02790 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-02245 | 7.6 | Residencial | Yes | 0-100kW
202309-NM25-00003 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00871 | 15 | Residencial | Yes | 0-100kW
202312-NM25-03025 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23683 | 8 | Residencial | Yes | 0-100kW
202405-NM25-00677 | 5.124 | Residencial | Yes | 0-100kW
2021-GD-00393 | 8.26 | Residencial | Yes | 0-100kW
2020-GD-05858 | 4.75 | Residencial | Yes | 0-100kW
202510-NM25-04183 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-00178 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-31776 | 4.22 | Residencial | No | 0-100kW
2022-GD-02121 | 3.54 | Residencial | Yes | 0-100kW
2019-GD-00344 | 5.5 | Residencial | Yes | 0-100kW
202405-NM25-03611 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02063 | 9.516 | Residencial | Yes | 0-100kW
202412-NM25-03961 | 13.6 | Residencial | Yes | 0-100kW
2023-GD-19430 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00793 | 8 | Residencial | Yes | 0-100kW
202509-NM25-04104 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-10170 | 10 | Residencial | Yes | 0-100kW
2023-GD-16160 | 3.8 | Comercial | Yes | 0-100kW
2022-GD-20092 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-14981 | 3.24 | Residencial | Yes | 0-100kW
16-3-849 | 4.5 | Residencial | Yes | 0-100kW
2023-GD-30292 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16728 | 7.6 | Residencial | No | 0-100kW
2020-GD-00750 | 13.6 | Residencial | Yes | 0-100kW
2023-GD-17116 | 5.49 | Residencial | Yes | 0-100kW
202503-NM25-02172 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-01803 | 4.026 | Residencial | No | 0-100kW
2023-GD-38700 | 7.6 | Residencial | Yes | 0-100kW
15-6-0548 | 6.8 | Residencial | Yes | 0-100kW
202407-NM25-03236 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-38483 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-01358 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06064 | 4.75 | Residencial | Yes | 0-100kW
2017-GD-03835 | 10 | Residencial | Yes | 0-100kW
2023-GD-16876 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-05792 | 13.176 | Residencial | Yes | 0-100kW
2023-GD-30361 | 4.99 | Residencial | Yes | 0-100kW
2025-GD-00065 | 38 | Comercial | Yes | 0-100kW
2022-GD-14432 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-08819 | 4.72 | Residencial | Yes | 0-100kW
2018-GD-01530 | 5.605 | Residencial | Yes | 0-100kW
2023-GD-37650 | 5.7 | Residencial | Yes | 0-100kW
2023-GD-06580 | 6.22 | Residencial | Yes | 0-100kW
2023-GD-31841 | 8.42 | Residencial | Yes | 0-100kW
202505-NM25-04166 | 15 | Residencial | No | 0-100kW
2023-GD-03444 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03306 | 3.072 | Residencial | Yes | 0-100kW
202403-NM25-03546 | 6 | Residencial | Yes | 0-100kW
2022-GD-23049 | 9.52 | Residencial | Yes | 0-100kW
2021-GD-07080 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-24636 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00892 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-06404 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00770 | 3.6 | Residencial | Yes | 0-100kW
202508-NM25-01208 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-10819 | 5 | Comercial | Yes | 0-100kW
2023-GD-38176 | 6.95 | Residencial | Yes | 0-100kW
202505-NM25-05030 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34067 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-14117 | 4.15 | Residencial | Yes | 0-100kW
202504-NM25-04027 | 3.8 | Residencial | Yes | 0-100kW
14-7-601 | 14 | Residencial | Yes | 0-100kW
2020-GD-06594 | 4 | Residencial | Yes | 0-100kW
2021-GD-09168 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-09508 | 4.13 | Residencial | Yes | 0-100kW
16-5-0452A | 7.09 | Residencial | Yes | 0-100kW
15-6-0101 | 3.44 | Residencial | Yes | 0-100kW
202403-NM25-02774 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03446 | 3.54 | Residencial | Yes | 0-100kW
202509-NM25-02023 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14348 | 3.29 | Residencial | Yes | 0-100kW
202508-NM25-01923 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-00692 | 4.608 | Residencial | Yes | 0-100kW
202405-NM25-02031 | 4.608 | Residencial | Yes | 0-100kW
202512-NM25-02274 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16448 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12014 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-02165 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-14952 | 8 | Residencial | Yes | 0-100kW
2021-GD-14314 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-00966 | 5 | Residencial | Yes | 0-100kW
202410-NM25-00544 | 5.6 | Residencial | Yes | 0-100kW
2021-GD-02116 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-08250 | 4.43 | Residencial | Yes | 0-100kW
202310-NM25-00555 | 4.758 | Residencial | Yes | 0-100kW
2023-GD-02571 | 8 | Comercial | No | 0-100kW
202411-NM25-02279 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04227 | 10 | Residencial | Yes | 0-100kW
15-1-676 | 10 | Residencial | Yes | 0-100kW
2021-GD-01989 | 5.31 | Residencial | Yes | 0-100kW
202507-NM25-01047 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-00093 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-06408 | 6.19 | Residencial | No | 0-100kW
2023-GD-12510 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-07290 | 4.39 | Residencial | Yes | 0-100kW
14-7-567 | 5.16 | Residencial | Yes | 0-100kW
202312-NM25-02046 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02085 | 6.8 | Residencial | Yes | 0-100kW
2020-GD-03870 | 6.25 | Residencial | Yes | 0-100kW
2022-GD-13698 | 4.39 | Residencial | Yes | 0-100kW
202404-NM25-00682 | 4.224 | Residencial | Yes | 0-100kW
202410-NM25-00111 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05660 | 10.61 | Residencial | Yes | 0-100kW
2020-GD-08605 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-22630 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-25844 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22086 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-17732 | 6.14 | Residencial | Yes | 0-100kW
2022-GD-15714 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-21451 | 3.29 | Residencial | Yes | 0-100kW
2020-GD-06936 | 4.72 | Residencial | Yes | 0-100kW
202509-NM25-04311 | 11.5 | Residencial | Yes | 0-100kW
202312-NM25-03004 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-08089 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-30556 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-11472 | 10.8 | Comercial | Yes | 0-100kW
2022-GD-05062 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-05824 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31368 | 5.38 | Residencial | Yes | 0-100kW
2022-GD-21998 | 3.66 | Residencial | Yes | 0-100kW
202402-NM25-00815 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02656 | 3 | Residencial | Yes | 0-100kW
202410-NM25-04906 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-12033 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-00497 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-31711 | 5 | Residencial | Yes | 0-100kW
202411-NM25-00535 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-00023 | 15.2 | Residencial | Yes | 0-100kW
202411-NM25-03325 | 15.2 | Residencial | No | 0-100kW
2022-GD-05627 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-13282 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-04546 | 4.75 | Residencial | Yes | 0-100kW
2023-GD-07362 | 4.03 | Residencial | Yes | 0-100kW
202409-NM25-00180 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-17765 | 5 | Residencial | Yes | 0-100kW
2021-GD-03738 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-39233 | 6 | Residencial | Yes | 0-100kW
202311-NM25-00605 | 3.66 | Residencial | Yes | 0-100kW
17-7-0018 | 4 | Residencial | Yes | 0-100kW
202401-NM25-03764 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18240 | 4.39 | Residencial | Yes | 0-100kW
202409-NM25-02501 | 15.738 | Residencial | Yes | 0-100kW
16-3-324 | 3.44 | Residencial | No | 0-100kW
202501-NM25-00929 | 3.8 | Residencial | Yes | 0-100kW
202501-NM25-03972 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-25190 | 7.32 | Residencial | Yes | 0-100kW
202409-NM25-02068 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-01762 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-01916 | 17.7 | Comercial | Yes | 0-100kW
202403-NM25-02916 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-04047 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15673 | 8.05 | Residencial | Yes | 0-100kW
202511-NM25-04344 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03344 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04049 | 14.75 | Residencial | Yes | 0-100kW
202411-NM25-01776 | 3.8 | Residencial | Yes | 0-100kW
202404-NM25-01130 | 9.56 | Residencial | Yes | 0-100kW
202501-NM25-04180 | 5.76 | Residencial | Yes | 0-100kW
202312-NM25-01160 | 7.6 | Residencial | No | 0-100kW
202403-NM25-02186 | 8 | Residencial | Yes | 0-100kW
2019-GD-03240 | 8.555 | Residencial | Yes | 0-100kW
202405-NM25-02209 | 15.2 | Residencial | Yes | 0-100kW
202504-NM25-02402 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06617 | 6.8 | Residencial | Yes | 0-100kW
16-5-0121A | 3 | Residencial | Yes | 0-100kW
2023-GD-14520 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-03369 | 5.605 | Residencial | Yes | 0-100kW
202410-NM25-02222 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03998 | 7.6 | Residencial | Yes | 0-100kW
15-1-024 | 5.5 | Residencial | Yes | 0-100kW
202409-NM25-00862 | 8 | Residencial | Yes | 0-100kW
202412-NM25-03436 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-03396 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11412 | 5 | Residencial | Yes | 0-100kW
2023-GD-19646 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03500 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14225 | 4.03 | Residencial | Yes | 0-100kW
202409-NM25-00389 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01801 | 7.6 | Residencial | Yes | 0-100kW
16-6-0473 | 3.65 | Residencial | Yes | 0-100kW
2021-GD-08130 | 7.75 | Residencial | Yes | 0-100kW
202402-NM25-00880 | 12 | Residencial | Yes | 0-100kW
2020-GD-07231 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-02860 | 8.35 | Residencial | Yes | 0-100kW
202312-NM25-03156 | 4.392 | Residencial | Yes | 0-100kW
202410-NM25-03431 | 12 | Residencial | Yes | 0-100kW
202502-NM25-03043 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-31266 | 4.03 | Residencial | Yes | 0-100kW
202407-NM25-01086 | 30.4 | Comercial | No | 0-100kW
2022-GD-11440 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-31663 | 6 | Residencial | Yes | 0-100kW
2022-GD-09435 | 9.15 | Residencial | Yes | 0-100kW
202505-NM25-01628 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32179 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-11652 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-12809 | 5.86 | Residencial | Yes | 0-100kW
202505-NM25-02542 | 8 | Residencial | Yes | 0-100kW
202501-NM25-02385 | 8 | Residencial | Yes | 0-100kW
2021-GD-11684 | 5 | Residencial | Yes | 0-100kW
2022-GD-05052 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-00721 | 4.72 | Residencial | Yes | 0-100kW
2023-GD-32131 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-17211 | 3.84 | Residencial | Yes | 0-100kW
15-1-453 | 6.45 | Residencial | Yes | 0-100kW
2021-GD-10775 | 7.38 | Residencial | Yes | 0-100kW
202512-NM25-02072 | 15.3 | Residencial | Yes | 0-100kW
202407-NM25-04406 | 15.2 | Residencial | Yes | 0-100kW
202509-NM25-03117 | 8 | Residencial | Yes | 0-100kW
2023-GD-30964 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-13636 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-10247 | 6.8 | Residencial | Yes | 0-100kW
202510-NM25-02461 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-10778 | 8 | Residencial | Yes | 0-100kW
202504-NM25-01681 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-12267 | 8.42 | Residencial | Yes | 0-100kW
202411-NM25-01018 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00319 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04233 | 2.928 | Residencial | Yes | 0-100kW
202510-NM25-02264 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04890 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02888 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-01326 | 21.228 | Residencial | Yes | 0-100kW
2023-GD-38566 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03103 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-25594 | 15.2 | Comercial | Yes | 0-100kW
202401-NM25-02417 | 5 | Residencial | Yes | 0-100kW
202407-NM25-04372 | 3.66 | Residencial | Yes | 0-100kW
202512-NM25-03197 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04253 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-07432 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-07382 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-03983 | 6.8 | Residencial | Yes | 0-100kW
2017-GD-01653 | 2.795 | Residencial | Yes | 0-100kW
2022-GD-00048 | 6.49 | Residencial | Yes | 0-100kW
202410-NM25-03261 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-28877 | 6.8 | Residencial | Yes | 0-100kW
2018-GD-00299 | 2.9 | Residencial | Yes | 0-100kW
2023-GD-01697 | 8.05 | Residencial | Yes | 0-100kW
202401-NM25-04302 | 8.052 | Residencial | No | 0-100kW
202504-NM25-00599 | 13.44 | Residencial | Yes | 0-100kW
16-4-0561GD | 3 | Residencial | Yes | 0-100kW
2022-GD-09923 | 5 | Residencial | Yes | 0-100kW
202410-NM25-01808 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-02636 | 12.685 | Residencial | Yes | 0-100kW
2022-GD-27727 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05482 | 3.84 | Residencial | Yes | 0-100kW
202409-NM25-03353 | 4.224 | Residencial | Yes | 0-100kW
202412-NM25-03134 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14931 | 5 | Residencial | Yes | 0-100kW
2021-GD-10936 | 6.8 | Residencial | Yes | 0-100kW
202505-NM25-04557 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-02857 | 11.4 | Residencial | Yes | 0-100kW
202511-NM25-00294 | 10.368 | Residencial | Yes | 0-100kW
2022-GD-16611 | 3.8 | Residencial | Yes | 0-100kW
202406-NM25-02666 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23656 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-05918 | 5 | Residencial | Yes | 0-100kW
2021-GD-03819 | 10.62 | Residencial | Yes | 0-100kW
2022-GD-19289 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-16601 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-27666 | 15 | Residencial | Yes | 0-100kW
2023-GD-27285 | 5 | Residencial | Yes | 0-100kW
202405-NM25-01042 | 7.6 | Comercial | Yes | 0-100kW
2018-GD-00580 | 3.36 | Residencial | Yes | 0-100kW
202506-NM25-01775 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-01039 | 8 | Residencial | Yes | 0-100kW
16-6-0691 | 3.87 | Residencial | Yes | 0-100kW
2022-GD-01712 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-15375 | 7.6 | Residencial | Yes | 0-100kW
15-3-063 | 3 | Residencial | Yes | 0-100kW
202504-NM25-01436 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-30431 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-04743 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-25811 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-30452 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02866 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07728 | 4.39 | Comercial | Yes | 0-100kW
14-7-721 | 5 | Residencial | Yes | 0-100kW
2022-GD-06523 | 5.12 | Residencial | Yes | 0-100kW
202503-NM25-05340 | 5.49 | Residencial | Yes | 0-100kW
202403-NM25-01684 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00735 | 2.928 | Residencial | Yes | 0-100kW
2023-GD-11125 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-34434 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10321 | 6.59 | Residencial | Yes | 0-100kW
2022-GD-10181 | 3.66 | Residencial | Yes | 0-100kW
202508-NM25-00889 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-19944 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24346 | 3.8 | Residencial | Yes | 0-100kW
202402-NM25-00138 | 8.052 | Residencial | Yes | 0-100kW
202510-NM25-04300 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-01087 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-00022 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-00094 | 4.758 | Residencial | Yes | 0-100kW
16-4-0727GD | 4.1 | Residencial | Yes | 0-100kW
202408-NM25-02852 | 6 | Residencial | Yes | 0-100kW
202502-NM25-00055 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-06868 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31462 | 8.42 | Residencial | Yes | 0-100kW
2019-GD-02648 | 3.54 | Residencial | Yes | 0-100kW
202402-NM25-02462 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04247 | 23 | Residencial | Yes | 0-100kW
2020-GD-04510 | 12.5 | Residencial | Yes | 0-100kW
202407-NM25-02347 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00413 | 6.178 | Residencial | Yes | 0-100kW
202512-NM25-05262 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03705 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00037 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-00749 | 8.418 | Residencial | Yes | 0-100kW
202402-NM25-02076 | 8.052 | Residencial | Yes | 0-100kW
2021-GD-05011 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-08774 | 5.12 | Residencial | Yes | 0-100kW
16-7-0899 | 6.66 | Residencial | Yes | 0-100kW
2022-GD-22548 | 4.76 | Residencial | Yes | 0-100kW
202504-NM25-01259 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26627 | 6 | Residencial | Yes | 0-100kW
2023-GD-01470 | 4.03 | Residencial | Yes | 0-100kW
202309-NM25-00117 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03289 | 8 | Residencial | Yes | 0-100kW
2022-GD-19270 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-22506 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-02098 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-03580 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35190 | 6.22 | Residencial | Yes | 0-100kW
2023-GD-35794 | 3.8 | Residencial | Yes | 0-100kW
202312-NM25-00387 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-14332 | 5 | Residencial | Yes | 0-100kW
202406-NM25-01736 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-05351 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14290 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-08014 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20392 | 9.88 | Residencial | Yes | 0-100kW
202406-NM25-01444 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-21352 | 6 | Residencial | Yes | 0-100kW
2023-GD-06011 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-17951 | 8 | Residencial | Yes | 0-100kW
202508-NM25-02911 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-01587 | 3.8 | Comercial | Yes | 0-100kW
202507-NM25-02355 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-02332 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-04032 | 6.95 | Residencial | Yes | 0-100kW
2021-GD-07282 | 5.9 | Residencial | Yes | 0-100kW
202405-NM25-02649 | 8 | Residencial | Yes | 0-100kW
2022-GD-01221 | 3.54 | Residencial | Yes | 0-100kW
202502-NM25-05497 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-01866 | 5.124 | Residencial | Yes | 0-100kW
2023-GD-03391 | 6.22 | Residencial | Yes | 0-100kW
202401-NM25-00362 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03146 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-37439 | 4.76 | Residencial | Yes | 0-100kW
202404-NM25-02960 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-00245 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-03566 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-01799 | 3.84 | Residencial | Yes | 0-100kW
202402-NM25-00437 | 3.84 | Residencial | Yes | 0-100kW
202312-NM25-02466 | 8.052 | Residencial | Yes | 0-100kW
2019-GD-02836 | 5 | Residencial | Yes | 0-100kW
2023-GD-37475 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31175 | 4.03 | Residencial | Yes | 0-100kW
16-4-1093GD | 2.58 | Residencial | Yes | 0-100kW
202404-NM25-03120 | 8 | Residencial | Yes | 0-100kW
2019-GD-00032 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01470 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-26438 | 4.39 | Residencial | Yes | 0-100kW
202411-NM25-02291 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-03842 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-30437 | 9.15 | Residencial | Yes | 0-100kW
2022-GD-15017 | 5.9 | Residencial | Yes | 0-100kW
202508-NM25-02124 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-01310 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-01737 | 9.52 | Residencial | Yes | 0-100kW
202509-NM25-01965 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-15014 | 5.31 | Residencial | Yes | 0-100kW
202507-NM25-03856 | 6.144 | Residencial | Yes | 0-100kW
2022-GD-16181 | 4.76 | Residencial | Yes | 0-100kW
202411-NM25-03070 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-09211 | 5.49 | Residencial | No | 0-100kW
2023-GD-35568 | 8.35 | Residencial | Yes | 0-100kW
2021-GD-04584 | 3.25 | Residencial | Yes | 0-100kW
2022-GD-29036 | 7.38 | Residencial | Yes | 0-100kW
2022-GD-23005 | 5.12 | Residencial | Yes | 0-100kW
2020-GD-03541 | 4.5 | Residencial | Yes | 0-100kW
202504-NM25-03541 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25541 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-17715 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-17277 | 8.42 | Residencial | No | 0-100kW
2020-GD-01383 | 14.16 | Residencial | Yes | 0-100kW
202412-NM25-00440 | 2.928 | Residencial | Yes | 0-100kW
202411-NM25-01409 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07225 | 3.54 | Residencial | Yes | 0-100kW
202503-NM25-00199 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-02013 | 16 | Comercial | Yes | 0-100kW
2020-GD-04303 | 6.49 | Residencial | Yes | 0-100kW
202512-NM25-00228 | 11.5 | Residencial | No | 0-100kW
2023-GD-01574 | 3.96 | Residencial | Yes | 0-100kW
2020-GD-03096 | 5.31 | Residencial | Yes | 0-100kW
2023-GD-37967 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03793 | 5.76 | Residencial | Yes | 0-100kW
2020-GD-05185 | 9.6 | Residencial | Yes | 0-100kW
202312-NM25-01536 | 8 | Residencial | Yes | 0-100kW
2023-GD-14223 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02646 | 3.835 | Residencial | Yes | 0-100kW
202511-NM25-00180 | 3.072 | Residencial | No | 0-100kW
2020-GD-07753 | 6 | Residencial | Yes | 0-100kW
2022-GD-26919 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-01153 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-23941 | 8.05 | Residencial | Yes | 0-100kW
2020-GD-02120 | 4.5 | Residencial | Yes | 0-100kW
2023-GD-09170 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01040 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-30869 | 4.99 | Residencial | Yes | 0-100kW
13-7-250 | 4.5 | Residencial | Yes | 0-100kW
2021-GD-02524 | 5.9 | Residencial | Yes | 0-100kW
2018-GD-00358 | 5.015 | Residencial | Yes | 0-100kW
2020-GD-07456 | 4.72 | Residencial | Yes | 0-100kW
2021-GD-13895 | 5.01 | Residencial | Yes | 0-100kW
14-2-881 | 5 | Residencial | Yes | 0-100kW
2023-GD-33869 | 15.2 | Residencial | No | 0-100kW
202504-NM25-03473 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-01734 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-20005 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03412 | 7.6 | Residencial | Yes | 0-100kW
15-1-519 | 8.25 | Residencial | Yes | 0-100kW
2021-GD-10052 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-01688 | 15.37 | Residencial | Yes | 0-100kW
202404-NM25-00675 | 7.6 | Residencial | No | 0-100kW
202501-NM25-01595 | 4.758 | Residencial | Yes | 0-100kW
2023-GD-29888 | 3.84 | Residencial | Yes | 0-100kW
202403-NM25-00266 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-05006 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-34735 | 8 | Residencial | Yes | 0-100kW
202510-NM25-01810 | 11.4 | Residencial | Yes | 0-100kW
2020-GD-08942 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-31053 | 3.8 | Residencial | Yes | 0-100kW
15-4-1025GD | 7 | Residencial | Yes | 0-100kW
202412-NM25-01465 | 2.928 | Residencial | Yes | 0-100kW
202402-NM25-01291 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-00836 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-00326 | 7.68 | Residencial | Yes | 0-100kW
202503-NM25-03432 | 3.072 | Residencial | Yes | 0-100kW
202508-NM25-03377 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-04619 | 8.26 | Residencial | Yes | 0-100kW
202505-NM25-01948 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-01080 | 12 | Residencial | Yes | 0-100kW
202505-NM25-02608 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01818 | 8 | Residencial | Yes | 0-100kW
202510-NM25-02484 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-04446 | 6.588 | Residencial | Yes | 0-100kW
202505-NM25-02957 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-04762 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-27175 | 7.3 | Residencial | Yes | 0-100kW
202502-NM25-03086 | 8 | Residencial | Yes | 0-100kW
202408-NM25-04507 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00865 | 11.712 | Residencial | Yes | 0-100kW
202504-NM25-04947 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-02758 | 5 | Residencial | Yes | 0-100kW
2021-GD-10255 | 5 | Residencial | No | 0-100kW
2022-GD-06055 | 9.88 | Residencial | Yes | 0-100kW
2021-GD-09739 | 5.9 | Residencial | No | 0-100kW
202502-NM25-01270 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11533 | 8 | Residencial | Yes | 0-100kW
2022-GD-02690 | 8 | Residencial | Yes | 0-100kW
202409-NM25-00554 | 5.376 | Residencial | Yes | 0-100kW
202412-NM25-02646 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-04014 | 4.758 | Residencial | Yes | 0-100kW
202508-NM25-00702 | 3.294 | Residencial | Yes | 0-100kW
2021-GD-06254 | 2.95 | Residencial | Yes | 0-100kW
202403-NM25-03926 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-00718 | 7.57 | Residencial | Yes | 0-100kW
202409-NM25-03420 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00308 | 2.95 | Comercial | Yes | 0-100kW
202406-NM25-02368 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-01015 | 11.51 | Residencial | Yes | 0-100kW
202404-NM25-03230 | 3.294 | Residencial | Yes | 0-100kW
202407-NM25-03501 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-04007 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04483 | 9.516 | Residencial | Yes | 0-100kW
2023-GD-15530 | 10.61 | Residencial | Yes | 0-100kW
202508-NM25-02942 | 14.1 | Residencial | Yes | 0-100kW
202411-NM25-02305 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06396 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-03741 | 8 | Residencial | Yes | 0-100kW
202411-NM25-03562 | 8.67 | Residencial | Yes | 0-100kW
202508-NM25-01939 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02831 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-00807 | 4.224 | Residencial | Yes | 0-100kW
202408-NM25-00305 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04051 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-04288 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-02910 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-23064 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-01138 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-17928 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-11737 | 5 | Residencial | Yes | 0-100kW
2022-GD-14842 | 4.03 | Residencial | Yes | 0-100kW
202412-NM25-00095 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-03641 | 5.9 | Residencial | Yes | 0-100kW
202502-NM25-06663 | 11.4 | Residencial | Yes | 0-100kW
202404-NM25-04490 | 4.758 | Residencial | Yes | 0-100kW
2023-GD-02999 | 5.12 | Residencial | Yes | 0-100kW
202309-NM25-00080 | 4.07 | Residencial | Yes | 0-100kW
202509-NM25-03803 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-03023 | 4.026 | Residencial | Yes | 0-100kW
202406-NM25-00856 | 6 | Residencial | Yes | 0-100kW
2023-GD-26822 | 3.66 | Residencial | Yes | 0-100kW
202501-NM25-01691 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19582 | 9 | Residencial | Yes | 0-100kW
2023-GD-01039 | 7.68 | Residencial | Yes | 0-100kW
202409-NM25-00418 | 15.2 | Residencial | Yes | 0-100kW
202409-NM25-01559 | 3.072 | Residencial | Yes | 0-100kW
202404-NM25-02057 | 3.294 | Residencial | Yes | 0-100kW
202511-NM25-00496 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-19810 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-05316 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-32638 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00149 | 4.75 | Residencial | Yes | 0-100kW
2022-GD-17670 | 4.76 | Residencial | Yes | 0-100kW
202404-NM25-00246 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15853 | 7.6 | Residencial | Yes | 0-100kW
14-2-528 | 4.8 | Residencial | Yes | 0-100kW
202506-NM25-02277 | 5.376 | Residencial | Yes | 0-100kW
2022-GD-02325 | 7.38 | Residencial | Yes | 0-100kW
202404-NM25-00423 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30292 | 6.59 | Residencial | Yes | 0-100kW
2021-GD-07114 | 8.85 | Residencial | No | 0-100kW
2023-GD-02021 | 4.39 | Residencial | No | 0-100kW
202310-NM25-00071 | 8.14 | Residencial | Yes | 0-100kW
2021-GD-07112 | 4.43 | Residencial | Yes | 0-100kW
2020-GD-00217 | 5.31 | Residencial | Yes | 0-100kW
202502-NM25-06082 | 4.392 | Residencial | Yes | 0-100kW
2022-GD-25378 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-06282 | 7.32 | Residencial | Yes | 0-100kW
202509-NM25-04817 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-32083 | 4.39 | Residencial | Yes | 0-100kW
202501-NM25-05618 | 7.6 | Residencial | No | 0-100kW
202508-NM25-05653 | 11.5 | Residencial | Yes | 0-100kW
2025-GD-00216 | 48 | Comercial | Yes | 0-100kW
202509-NM25-03129 | 8 | Residencial | Yes | 0-100kW
2023-GD-06867 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00136 | 3.84 | Residencial | Yes | 0-100kW
202403-NM25-00354 | 8 | Residencial | Yes | 0-100kW
202502-NM25-06340 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-00344 | 6.912 | Residencial | Yes | 0-100kW
2021-GD-05392 | 7.38 | Residencial | Yes | 0-100kW
202507-NM25-01425 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-06095 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-09585 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-11221 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-35450 | 12.08 | Residencial | Yes | 0-100kW
2018-GD-01563 | 13.68 | Residencial | Yes | 0-100kW
2023-GD-00356 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-14724 | 15.37 | Residencial | Yes | 0-100kW
202502-NM25-06390 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03007 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-01147 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-06781 | 6 | Residencial | Yes | 0-100kW
202408-NM25-04955 | 5.124 | Residencial | Yes | 0-100kW
15-6-0050 | 6 | Residencial | Yes | 0-100kW
2022-GD-21745 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-30848 | 7.6 | Residencial | No | 0-100kW
202512-NM25-06112 | 9 | Residencial | Yes | 0-100kW
202505-NM25-00774 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-08261 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-20930 | 8.42 | Residencial | Yes | 0-100kW
202409-NM25-00365 | 3.072 | Residencial | Yes | 0-100kW
2022-GD-26312 | 9.8 | Residencial | Yes | 0-100kW
202409-NM25-00598 | 23.424 | Comercial | Yes | 0-100kW
202408-NM25-02278 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06096 | 7.08 | Residencial | Yes | 0-100kW
202501-NM25-01650 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-10105 | 5.61 | Residencial | Yes | 0-100kW
2021-GD-11413 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-08714 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-02284 | 5 | Residencial | Yes | 0-100kW
202512-NM25-04055 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31300 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-32421 | 4.39 | Residencial | Yes | 0-100kW
202505-NM25-03320 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-00241 | 10 | Residencial | Yes | 0-100kW
2020-GD-08179 | 5.75 | Residencial | Yes | 0-100kW
2023-GD-30257 | 6 | Residencial | Yes | 0-100kW
2023-GD-28067 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-04927 | 6 | Residencial | Yes | 0-100kW
202312-NM25-00324 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-03081 | 15.2 | Residencial | Yes | 0-100kW
202402-NM25-00358 | 8 | Residencial | Yes | 0-100kW
202412-NM25-01722 | 6.222 | Residencial | Yes | 0-100kW
202507-NM25-03879 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00101 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-11234 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-27051 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35432 | 15.2 | Residencial | Yes | 0-100kW
2020-GD-00142 | 3.245 | Residencial | Yes | 0-100kW
202407-NM25-00485 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-07938 | 5.49 | Residencial | Yes | 0-100kW
202403-NM25-01079 | 5.856 | Residencial | Yes | 0-100kW
2022-GD-16679 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-14279 | 7.6 | Residencial | Yes | 0-100kW
202311-NM25-00549 | 2.1 | Residencial | Yes | 0-100kW
2022-GD-29151 | 6.6 | Residencial | Yes | 0-100kW
202312-NM25-01569 | 4.026 | Residencial | Yes | 0-100kW
202502-NM25-02064 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-34503 | 5.12 | Residencial | Yes | 0-100kW
2022-GD-11980 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-14022 | 4.72 | Residencial | Yes | 0-100kW
14-7-071 | 7.5 | Residencial | Yes | 0-100kW
202406-NM25-02716 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-20377 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01660 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-00647 | 8 | Residencial | Yes | 0-100kW
2023-GD-13685 | 6.49 | Residencial | Yes | 0-100kW
202510-NM25-02025 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-01993 | 5.01 | Residencial | Yes | 0-100kW
202411-NM25-00225 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-00783 | 7.6 | Comercial | Yes | 0-100kW
2023-GD-01617 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-04611 | 12 | Residencial | Yes | 0-100kW
202412-NM25-03204 | 15 | Residencial | Yes | 0-100kW
2022-GD-15735 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-38577 | 6 | Residencial | Yes | 0-100kW
2020-GD-07945 | 7.08 | Residencial | Yes | 0-100kW
202312-NM25-03596 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18054 | 5 | Residencial | Yes | 0-100kW
202408-NM25-01671 | 4.392 | Residencial | Yes | 0-100kW
2022-GD-24193 | 4.5 | Residencial | Yes | 0-100kW
2019-GD-00050 | 3 | Residencial | Yes | 0-100kW
202507-NM25-03968 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-06652 | 2.95 | Residencial | Yes | 0-100kW
202509-NM25-00415 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24933 | 10.25 | Residencial | Yes | 0-100kW
2021-GD-10069 | 7.97 | Residencial | Yes | 0-100kW
202511-NM25-02280 | 11.5 | Residencial | Yes | 0-100kW
202312-NM25-02982 | 9.882 | Residencial | Yes | 0-100kW
202504-NM25-03371 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-01010 | 15.372 | Residencial | Yes | 0-100kW
202408-NM25-04516 | 9.984 | Residencial | Yes | 0-100kW
2023-GD-04622 | 5.12 | Residencial | Yes | 0-100kW
202510-NM25-01938 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-03241 | 8 | Residencial | Yes | 0-100kW
2023-GD-07919 | 3.8 | Residencial | No | 0-100kW
202506-NM25-00305 | 4.992 | Residencial | Yes | 0-100kW
2021-GD-11328 | 3.54 | Residencial | Yes | 0-100kW
2018-GD-01437 | 87.025 | Comercial | Yes | 0-100kW
202409-NM25-01379 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31961 | 5.12 | Residencial | Yes | 0-100kW
202510-NM25-03233 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-09000 | 6.59 | Residencial | Yes | 0-100kW
202510-NM25-03575 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-05651 | 8.448 | Residencial | Yes | 0-100kW
2020-GD-03902 | 1.77 | Residencial | Yes | 0-100kW
2019-GD-03179 | 16.225 | Residencial | Yes | 0-100kW
202507-NM25-00459 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-15117 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-21387 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-06705 | 5.61 | Comercial | No | 0-100kW
2022-GD-10367 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15177 | 4.43 | Residencial | Yes | 0-100kW
202312-NM25-02227 | 7.5 | Residencial | Yes | 0-100kW
202410-NM25-04257 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-00709 | 5.31 | Residencial | Yes | 0-100kW
202411-NM25-02753 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-00823 | 3.66 | Residencial | Yes | 0-100kW
13-2-338 | 6 | Residencial | Yes | 0-100kW
202503-NM25-02167 | 3.8 | Residencial | Yes | 0-100kW
202404-NM25-03959 | 3.63 | Comercial | Yes | 0-100kW
2023-GD-23516 | 6 | Residencial | Yes | 0-100kW
202411-NM25-03321 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09223 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-22312 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06229 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-09827 | 7.32 | Residencial | Yes | 0-100kW
202502-NM25-00814 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06107 | 6.222 | Residencial | Yes | 0-100kW
2023-GD-12233 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-03451 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22752 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-03898 | 5.9 | Residencial | Yes | 0-100kW
202408-NM25-00460 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13040 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-01288 | 4.76 | Residencial | No | 0-100kW
202405-NM25-00527 | 5 | Residencial | Yes | 0-100kW
202503-NM25-05743 | 5 | Residencial | Yes | 0-100kW
2017-GD-00396 | 4.25 | Residencial | Yes | 0-100kW
202502-NM25-04541 | 11.5 | Residencial | Yes | 0-100kW
15-2-993 | 6.12 | Residencial | Yes | 0-100kW
202509-NM25-01661 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-03267 | 4.72 | Residencial | Yes | 0-100kW
16-1-906 | 4.3 | Residencial | Yes | 0-100kW
202412-NM25-00509 | 2.688 | Residencial | Yes | 0-100kW
2021-GD-06747 | 10.03 | Residencial | Yes | 0-100kW
2022-GD-21737 | 9.15 | Residencial | Yes | 0-100kW
2022-GD-24058 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-04739 | 3.54 | Residencial | Yes | 0-100kW
202506-NM25-01176 | 3.84 | Residencial | Yes | 0-100kW
202412-NM25-01915 | 13.1 | Residencial | Yes | 0-100kW
202512-NM25-03817 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-23356 | 9.6 | Residencial | Yes | 0-100kW
202511-NM25-04204 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-07594 | 3.84 | Residencial | Yes | 0-100kW
202407-NM25-00641 | 15 | Residencial | Yes | 0-100kW
2023-GD-24630 | 3.84 | Residencial | Yes | 0-100kW
202512-NM25-00487 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-02573 | 2.928 | Residencial | Yes | 0-100kW
202403-NM25-02554 | 2.7 | Residencial | Yes | 0-100kW
202510-NM25-02121 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-30550 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-00503 | 4.43 | Residencial | Yes | 0-100kW
202504-NM25-04403 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-01962 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-04428 | 8.052 | Residencial | Yes | 0-100kW
202410-NM25-01455 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-02383 | 4.608 | Residencial | Yes | 0-100kW
2020-GD-02164 | 4.3 | Residencial | Yes | 0-100kW
202411-NM25-03611 | 2.928 | Residencial | Yes | 0-100kW
202502-NM25-04204 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00165 | 4 | Residencial | Yes | 0-100kW
202507-NM25-00754 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-02820 | 3.8 | Residencial | Yes | 0-100kW
16-7-1043 | 6.24 | Residencial | Yes | 0-100kW
202511-NM25-00545 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05184 | 9.15 | Residencial | Yes | 0-100kW
202408-NM25-02736 | 4.392 | Residencial | Yes | 0-100kW
202507-NM25-03770 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-04915 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-03276 | 3.24 | Residencial | Yes | 0-100kW
202409-NM25-03607 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18571 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01933 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-03771 | 8.05 | Residencial | Yes | 0-100kW
202405-NM25-03555 | 6.8 | Residencial | Yes | 0-100kW
202506-NM25-00897 | 3.8 | Residencial | Yes | 0-100kW
202401-NM25-03458 | 5 | Residencial | Yes | 0-100kW
202405-NM25-01853 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-00576 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21290 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31788 | 9.88 | Residencial | Yes | 0-100kW
202502-NM25-06452 | 8 | Residencial | Yes | 0-100kW
202312-NM25-03616 | 6.222 | Residencial | Yes | 0-100kW
2023-GD-02599 | 8.42 | Residencial | Yes | 0-100kW
2019-GD-00620 | 8.35 | Residencial | Yes | 0-100kW
2023-GD-09992 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-03330 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11780 | 4.13 | Residencial | Yes | 0-100kW
2021-GD-12721 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-05220 | 8 | Residencial | Yes | 0-100kW
2023-GD-21805 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04059 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-01551 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-01294 | 4 | Residencial | Yes | 0-100kW
202508-NM25-02114 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-06133 | 7.32 | Residencial | Yes | 0-100kW
202503-NM25-04485 | 13.056 | Residencial | Yes | 0-100kW
2023-GD-38976 | 2.66 | Residencial | Yes | 0-100kW
202501-NM25-03161 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-03026 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-02929 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12797 | 5.49 | Residencial | Yes | 0-100kW
202407-NM25-01109 | 3.66 | Residencial | Yes | 0-100kW
202408-NM25-04185 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03265 | 11.73 | Residencial | Yes | 0-100kW
2023-GD-29620 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-02683 | 3.835 | Residencial | Yes | 0-100kW
202502-NM25-05530 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28182 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-08743 | 5.86 | Residencial | Yes | 0-100kW
202409-NM25-03033 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00735 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-15244 | 5.31 | Residencial | Yes | 0-100kW
2023-GD-19552 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01945 | 12 | Residencial | Yes | 0-100kW
2023-GD-06154 | 6.95 | Residencial | Yes | 0-100kW
202408-NM25-03687 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02143 | 6.954 | Residencial | Yes | 0-100kW
202507-NM25-00768 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-38090 | 8.42 | Residencial | Yes | 0-100kW
202501-NM25-04459 | 4.026 | Residencial | Yes | 0-100kW
2018-GD-00488 | 20 | Residencial | Yes | 0-100kW
2023-GD-20015 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01394 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-04968 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-00793 | 7.32 | Residencial | Yes | 0-100kW
2021-GD-14679 | 5.01 | Residencial | Yes | 0-100kW
202406-NM25-01815 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-02715 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-09236 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05296 | 8 | Residencial | Yes | 0-100kW
202404-NM25-01981 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-02405 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-04508 | 3.84 | Residencial | Yes | 0-100kW
15-4-0964GD | 4.2 | Residencial | Yes | 0-100kW
2021-GD-01328 | 2.95 | Residencial | Yes | 0-100kW
16-1-648 | 4 | Residencial | Yes | 0-100kW
202407-NM25-01611 | 3.66 | Residencial | Yes | 0-100kW
202401-NM25-00219 | 7.6 | Residencial | Yes | 0-100kW
14-4-0102GD | 3.5 | Residencial | Yes | 0-100kW
202407-NM25-00346 | 8 | Residencial | Yes | 0-100kW
2022-GD-13899 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-29333 | 3.84 | Residencial | Yes | 0-100kW
202406-NM25-02992 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-03723 | 2.07 | Residencial | Yes | 0-100kW
2022-GD-04421 | 8 | Residencial | Yes | 0-100kW
202507-NM25-04760 | 5.376 | Residencial | No | 0-100kW
2020-GD-08442 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-07424 | 12.08 | Residencial | No | 0-100kW
202412-NM25-02374 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00600 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-01355 | 7.08 | Residencial | Yes | 0-100kW
202405-NM25-03754 | 8 | Residencial | No | 0-100kW
2020-GD-01437 | 3.54 | Residencial | Yes | 0-100kW
16-5-0177A | 4.51 | Residencial | Yes | 0-100kW
2022-GD-10759 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-29311 | 8 | Residencial | Yes | 0-100kW
2021-GD-07808 | 3.48 | Residencial | Yes | 0-100kW
2023-GD-31128 | 8 | Residencial | Yes | 0-100kW
202510-NM25-03420 | 8 | Residencial | Yes | 0-100kW
202502-NM25-06305 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02313 | 3.8 | Residencial | Yes | 0-100kW
202410-NM25-01690 | 9.15 | Residencial | Yes | 0-100kW
202501-NM25-00194 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04866 | 6.95 | Residencial | Yes | 0-100kW
202407-NM25-02303 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-01949 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-02285 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26079 | 4.03 | Residencial | Yes | 0-100kW
202501-NM25-04307 | 2.928 | Residencial | Yes | 0-100kW
15-5-0078A | 5.04 | Residencial | Yes | 0-100kW
2022-GD-08530 | 5 | Residencial | Yes | 0-100kW
202404-NM25-02850 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02437 | 5.28 | Residencial | Yes | 0-100kW
2022-GD-03050 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-28626 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-29316 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02196 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-04058 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-10763 | 5.12 | Residencial | Yes | 0-100kW
202412-NM25-02471 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04230 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-05284 | 9.6 | Residencial | Yes | 0-100kW
202507-NM25-05148 | 4.608 | Residencial | Yes | 0-100kW
2023-GD-31259 | 5.12 | Residencial | Yes | 0-100kW
202402-NM25-00772 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13196 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-19920 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-20445 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12355 | 5.86 | Residencial | Yes | 0-100kW
202408-NM25-02495 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27271 | 6 | Residencial | Yes | 0-100kW
202410-NM25-03610 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-03082 | 4.13 | Residencial | Yes | 0-100kW
202508-NM25-04469 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-00269 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02353 | 24 | Residencial | Yes | 0-100kW
2023-GD-30782 | 8.05 | Residencial | Yes | 0-100kW
202406-NM25-01762 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02164 | 13.2 | Residencial | Yes | 0-100kW
202402-NM25-01585 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11682 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-29002 | 6.59 | Residencial | Yes | 0-100kW
15-1-609 | 6 | Residencial | Yes | 0-100kW
202412-NM25-03844 | 4.392 | Residencial | Yes | 0-100kW
202406-NM25-02924 | 10.248 | Residencial | Yes | 0-100kW
2018-GD-00105 | 2.9 | Residencial | Yes | 0-100kW
2023-GD-06275 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-00382 | 3.5 | Residencial | Yes | 0-100kW
2018-GD-00353 | 4.56 | Residencial | Yes | 0-100kW
202502-NM25-04508 | 8 | Residencial | Yes | 0-100kW
2022-GD-27626 | 4.72 | Residencial | Yes | 0-100kW
202406-NM25-02466 | 5.61 | Residencial | Yes | 0-100kW
2021-GD-10358 | 5.31 | Residencial | Yes | 0-100kW
17-4-066GD | 2.28 | Residencial | Yes | 0-100kW
202502-NM25-06766 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-02423 | 5.76 | Residencial | Yes | 0-100kW
2021-GD-02226 | 16 | Residencial | No | 0-100kW
202501-NM25-02792 | 9.216 | Residencial | Yes | 0-100kW
2021-GD-05302 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-10372 | 3.24 | Residencial | Yes | 0-100kW
202501-NM25-04089 | 10.5 | Residencial | Yes | 0-100kW
2022-GD-11200 | 5 | Residencial | Yes | 0-100kW
202401-NM25-03650 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-18483 | 5.49 | Residencial | Yes | 0-100kW
202504-NM25-03938 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-00226 | 2.928 | Residencial | Yes | 0-100kW
202509-NM25-02581 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-13662 | 4.39 | Residencial | No | 0-100kW
2020-GD-04841 | 5.31 | Residencial | Yes | 0-100kW
2021-GD-00545 | 4.72 | Residencial | Yes | 0-100kW
2023-GD-34980 | 3.66 | Residencial | Yes | 0-100kW
202509-NM25-05882 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-13655 | 3.84 | Residencial | Yes | 0-100kW
202507-NM25-02606 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-08469 | 4.61 | Residencial | Yes | 0-100kW
202504-NM25-00504 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-19840 | 6.8 | Comercial | Yes | 0-100kW
202402-NM25-00042 | 8 | Residencial | Yes | 0-100kW
202501-NM25-04799 | 19.398 | Residencial | Yes | 0-100kW
202508-NM25-00088 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-02806 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-00445 | 8.052 | Residencial | Yes | 0-100kW
2022-GD-16996 | 8.42 | Residencial | Yes | 0-100kW
202311-NM25-00588 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06586 | 6.14 | Residencial | Yes | 0-100kW
2023-GD-02352 | 4.03 | Residencial | Yes | 0-100kW
202410-NM25-01501 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-03212 | 9.516 | Residencial | Yes | 0-100kW
202407-NM25-01553 | 7.32 | Residencial | Yes | 0-100kW
2021-GD-14905 | 4.72 | Residencial | Yes | 0-100kW
202503-NM25-00570 | 2.688 | Residencial | Yes | 0-100kW
2022-GD-14256 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-22900 | 5.49 | Residencial | Yes | 0-100kW
202408-NM25-01573 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-01370 | 4.25 | Residencial | Yes | 0-100kW
2023-GD-01416 | 4.99 | Residencial | Yes | 0-100kW
2020-GD-00074 | 3.245 | Residencial | Yes | 0-100kW
2021-GD-04688 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-02832 | 5.12 | Residencial | Yes | 0-100kW
202410-NM25-01220 | 6 | Residencial | Yes | 0-100kW
202404-NM25-04582 | 6 | Residencial | Yes | 0-100kW
2020-GD-07343 | 5.01 | Residencial | Yes | 0-100kW
15-3-1192 | 4.3 | Residencial | Yes | 0-100kW
15-7-400 | 6 | Residencial | Yes | 0-100kW
2023-GD-13840 | 2.7 | Residencial | Yes | 0-100kW
2022-GD-26533 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-23730 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22100 | 6.22 | Residencial | Yes | 0-100kW
202403-NM25-03069 | 4.392 | Residencial | Yes | 0-100kW
202312-NM25-00760 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-03964 | 9.216 | Residencial | Yes | 0-100kW
2023-GD-01788 | 5.49 | Residencial | Yes | 0-100kW
202410-NM25-01959 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-12602 | 11.51 | Residencial | Yes | 0-100kW
16-4-0579GD | 3 | Residencial | Yes | 0-100kW
2023-GD-13084 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02571 | 5 | Residencial | Yes | 0-100kW
2020-GD-08767 | 5.5 | Residencial | Yes | 0-100kW
202412-NM25-00877 | 7.6 | Residencial | No | 0-100kW
2020-GD-03671 | 4.72 | Residencial | Yes | 0-100kW
2023-GD-33735 | 7.69 | Residencial | Yes | 0-100kW
202501-NM25-02393 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15501 | 6.59 | Residencial | Yes | 0-100kW
2021-GD-13879 | 5.61 | Residencial | Yes | 0-100kW
2023-GD-13095 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-02687 | 9 | Residencial | Yes | 0-100kW
202502-NM25-06287 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-01110 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01850 | 3.66 | Residencial | Yes | 0-100kW
202512-NM25-01484 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-09920 | 7.32 | Residencial | Yes | 0-100kW
2018-GD-00530 | 8 | Residencial | Yes | 0-100kW
2023-GD-19151 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24721 | 15.74 | Residencial | Yes | 0-100kW
202408-NM25-02193 | 6.946 | Residencial | Yes | 0-100kW
202509-NM25-02669 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-01232 | 10 | Residencial | Yes | 0-100kW
202510-NM25-00002 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-02067 | 4 | Residencial | Yes | 0-100kW
202504-NM25-06003 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-35404 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21003 | 6.88 | Residencial | Yes | 0-100kW
202411-NM25-01655 | 7.6 | Residencial | Yes | 0-100kW
09-6-0073 | 11 | Residencial | Yes | 0-100kW
202501-NM25-02489 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07312 | 6.8 | Residencial | Yes | 0-100kW
2021-GD-07013 | 3.24 | Residencial | Yes | 0-100kW
202410-NM25-01453 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14134 | 9.6 | Comercial | Yes | 0-100kW
202406-NM25-01726 | 8 | Residencial | Yes | 0-100kW
202407-NM25-01561 | 3.8 | Residencial | No | 0-100kW
202503-NM25-03133 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-02397 | 8 | Residencial | Yes | 0-100kW
2023-GD-32561 | 3.84 | Residencial | Yes | 0-100kW
2019-GD-00618 | 9 | Residencial | Yes | 0-100kW
202511-NM25-03304 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-05265 | 5 | Residencial | Yes | 0-100kW
2023-GD-09363 | 4.76 | Residencial | Yes | 0-100kW
202410-NM25-00022 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-01586 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-15328 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-30448 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01455 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-03980 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-00132 | 7.968 | Residencial | Yes | 0-100kW
2021-GD-07280 | 5.31 | Residencial | Yes | 0-100kW
202412-NM25-00529 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-01334 | 5.124 | Residencial | Yes | 0-100kW
2022-GD-24565 | 3.84 | Residencial | Yes | 0-100kW
202412-NM25-04229 | 4.992 | Residencial | Yes | 0-100kW
202502-NM25-06763 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03226 | 11.5 | Residencial | Yes | 0-100kW
2018-GD-01297 | 4.56 | Residencial | Yes | 0-100kW
202501-NM25-00264 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-00632 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04651 | 15.2 | Residencial | Yes | 0-100kW
2019-GD-00168 | 6.785 | Residencial | Yes | 0-100kW
202506-NM25-00326 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-01763 | 4.3 | Residencial | Yes | 0-100kW
2023-GD-31722 | 12 | Residencial | Yes | 0-100kW
202503-NM25-02953 | 8 | Residencial | Yes | 0-100kW
2021-GD-00027 | 3.25 | Residencial | Yes | 0-100kW
202404-NM25-01513 | 3.8 | Residencial | Yes | 0-100kW
202406-NM25-01715 | 2.928 | Residencial | Yes | 0-100kW
2023-GD-24657 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-02385 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-12285 | 4.03 | Residencial | Yes | 0-100kW
202310-NM25-00492 | 8.052 | Residencial | Yes | 0-100kW
202406-NM25-01128 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01844 | 23.424 | Comercial | Yes | 0-100kW
15-5-0720A | 2.58 | Residencial | No | 0-100kW
2023-GD-00818 | 4.99 | Residencial | Yes | 0-100kW
2023-GD-09708 | 5 | Residencial | Yes | 0-100kW
2021-GD-01787 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-30470 | 5.9 | Residencial | Yes | 0-100kW
2021-GD-02490 | 6.49 | Residencial | Yes | 0-100kW
2022-GD-19607 | 4.76 | Residencial | Yes | 0-100kW
202412-NM25-02442 | 8 | Residencial | Yes | 0-100kW
202501-NM25-04794 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01391 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03473 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00314 | 8 | Residencial | Yes | 0-100kW
202504-NM25-03690 | 18.048 | Comercial | Yes | 0-100kW
15-1-1016 | 4.95 | Residencial | Yes | 0-100kW
2020-GD-07119 | 6 | Residencial | Yes | 0-100kW
202407-NM25-00213 | 6 | Residencial | Yes | 0-100kW
2020-GD-00922 | 4.5 | Residencial | Yes | 0-100kW
202504-NM25-05639 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02018 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19108 | 7.6 | Comercial | Yes | 0-100kW
202412-NM25-02990 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-15611 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-09527 | 5 | Residencial | Yes | 0-100kW
202401-NM25-03062 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01560 | 8 | Residencial | Yes | 0-100kW
2022-GD-17487 | 8 | Residencial | Yes | 0-100kW
202510-NM25-02854 | 11.5 | Residencial | Yes | 0-100kW
15-9-559 | 3.01 | Residencial | Yes | 0-100kW
202511-NM25-01142 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-10448 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-17504 | 4.03 | Residencial | Yes | 0-100kW
2019-GD-02391 | 15.36 | Residencial | Yes | 0-100kW
2022-GD-13637 | 5.31 | Residencial | Yes | 0-100kW
2023-GD-06573 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-05380 | 2.66 | Residencial | Yes | 0-100kW
2022-GD-20793 | 9.52 | Residencial | Yes | 0-100kW
202504-NM25-02833 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-02671 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-10660 | 3.84 | Residencial | Yes | 0-100kW
202403-NM25-00216 | 9.15 | Residencial | Yes | 0-100kW
202502-NM25-06011 | 15 | Residencial | Yes | 0-100kW
2023-GD-03786 | 8.42 | Residencial | Yes | 0-100kW
202501-NM25-00595 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-01217 | 19.2 | Residencial | Yes | 0-100kW
202405-NM25-02541 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-11560 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01717 | 2.928 | Residencial | Yes | 0-100kW
202501-NM25-03859 | 8 | Comercial | Yes | 0-100kW
202412-NM25-02988 | 15.2 | Residencial | Yes | 0-100kW
202501-NM25-03757 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-03025 | 12 | Residencial | Yes | 0-100kW
202310-NM25-00455 | 8.052 | Residencial | Yes | 0-100kW
2022-GD-21009 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-31933 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-00593 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03096 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-04984 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-09029 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-04823 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-02477 | 5.9 | Residencial | Yes | 0-100kW
2021-GD-09708 | 5 | Residencial | Yes | 0-100kW
202503-NM25-03275 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01592 | 4.425 | Residencial | Yes | 0-100kW
2021-GD-10476 | 7.38 | Residencial | Yes | 0-100kW
2022-GD-30023 | 6 | Residencial | Yes | 0-100kW
2021-GD-09998 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-01008 | 5.31 | Residencial | Yes | 0-100kW
15-3-1170 | 4.52 | Residencial | Yes | 0-100kW
16-2-0018 | 3.65 | Residencial | Yes | 0-100kW
2021-GD-01314 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-14137 | 6 | Residencial | Yes | 0-100kW
202501-NM25-03448 | 11.5 | Residencial | Yes | 0-100kW
14-9-053 | 6.45 | Residencial | Yes | 0-100kW
202505-NM25-02393 | 11.346 | Residencial | Yes | 0-100kW
2023-GD-18811 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-28142 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05671 | 5 | Residencial | Yes | 0-100kW
202403-NM25-01097 | 5.124 | Residencial | Yes | 0-100kW
2022-GD-15028 | 4.03 | Residencial | Yes | 0-100kW
202412-NM25-01235 | 3.8 | Residencial | Yes | 0-100kW
202506-NM25-02142 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-06421 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08969 | 8 | Residencial | Yes | 0-100kW
2021-GD-01296 | 7.38 | Residencial | Yes | 0-100kW
2020-GD-00589 | 7.08 | Comercial | Yes | 0-100kW
2020-GD-04433 | 7.68 | Residencial | Yes | 0-100kW
2018-GD-00308 | 4 | Residencial | Yes | 0-100kW
2017-GD-03292 | 5.605 | Residencial | Yes | 0-100kW
202407-NM25-00635 | 3.66 | Residencial | Yes | 0-100kW
202407-NM25-02770 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00054 | 8.75 | Residencial | Yes | 0-100kW
202402-NM25-02410 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-04557 | 9 | Residencial | Yes | 0-100kW
202401-NM25-02683 | 6.222 | Residencial | Yes | 0-100kW
2023-GD-10135 | 5 | Residencial | Yes | 0-100kW
202408-NM25-01049 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02731 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06812 | 5 | Residencial | Yes | 0-100kW
2022-GD-18978 | 5 | Residencial | Yes | 0-100kW
202512-NM25-02262 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-12224 | 6.19 | Residencial | Yes | 0-100kW
202412-NM25-03992 | 6.222 | Residencial | Yes | 0-100kW
202405-NM25-00144 | 3.072 | Residencial | Yes | 0-100kW
202503-NM25-03184 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-02824 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-03276 | 7.6 | Residencial | Yes | 0-100kW
16-3-815 | 4.3 | Residencial | Yes | 0-100kW
2020-GD-06128 | 10.33 | Residencial | Yes | 0-100kW
2022-GD-30409 | 4.76 | Residencial | Yes | 0-100kW
202409-NM25-01161 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24836 | 9.75 | Residencial | Yes | 0-100kW
2023-GD-26961 | 5 | Residencial | Yes | 0-100kW
2020-GD-09381 | 6.8 | Residencial | Yes | 0-100kW
202505-NM25-02143 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-25137 | 8.42 | Residencial | Yes | 0-100kW
202405-NM25-03020 | 4.758 | Residencial | Yes | 0-100kW
202407-NM25-04334 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-05562 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-00489 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07215 | 7.67 | Residencial | Yes | 0-100kW
202411-NM25-01296 | 6.588 | Residencial | Yes | 0-100kW
202409-NM25-00235 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15755 | 6.95 | Residencial | Yes | 0-100kW
202510-NM25-03049 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04058 | 3.54 | Residencial | Yes | 0-100kW
202404-NM25-02468 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-23124 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-23913 | 5 | Residencial | Yes | 0-100kW
202411-NM25-02690 | 3.8 | Residencial | Yes | 0-100kW
15-4-0742GD | 4.08 | Residencial | Yes | 0-100kW
202409-NM25-01499 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15375 | 7.32 | Residencial | Yes | 0-100kW
202504-NM25-01979 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-03480 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30998 | 4.03 | Residencial | Yes | 0-100kW
202412-NM25-00657 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03092 | 4.39 | Residencial | Yes | 0-100kW
202506-NM25-03365 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36363 | 6.59 | Residencial | Yes | 0-100kW
2021-GD-08430 | 2.75 | Residencial | Yes | 0-100kW
202502-NM25-01647 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14220 | 6 | Residencial | Yes | 0-100kW
202507-NM25-03942 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-08209 | 5 | Residencial | Yes | 0-100kW
2022-GD-04464 | 4.39 | Residencial | Yes | 0-100kW
202411-NM25-02009 | 2.928 | Residencial | Yes | 0-100kW
202504-NM25-05011 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23110 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-02954 | 23 | Residencial | Yes | 0-100kW
202412-NM25-00542 | 14.7 | Residencial | Yes | 0-100kW
202510-NM25-03419 | 11.5 | Residencial | No | 0-100kW
2022-GD-03011 | 8.85 | Residencial | Yes | 0-100kW
2020-GD-03149 | 11.21 | Residencial | Yes | 0-100kW
2021-GD-06451 | 8.45 | Residencial | Yes | 0-100kW
202401-NM25-01292 | 2.36 | Residencial | Yes | 0-100kW
2018-GD-01661 | 8.35 | Residencial | Yes | 0-100kW
202401-NM25-00063 | 4.026 | Residencial | Yes | 0-100kW
202507-NM25-03458 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01801 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-00611 | 7.286 | Residencial | Yes | 0-100kW
202312-NM25-00300 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13601 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-12193 | 3.54 | Residencial | Yes | 0-100kW
202404-NM25-02543 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-13491 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-01535 | 2.3 | Residencial | Yes | 0-100kW
2019-GD-00466 | 8.12 | Residencial | Yes | 0-100kW
2023-GD-10651 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02711 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-21064 | 8 | Residencial | Yes | 0-100kW
202404-NM25-02817 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-09701 | 3.8 | Residencial | Yes | 0-100kW
2017-GD-02326 | 5.75 | Residencial | Yes | 0-100kW
202503-NM25-04554 | 6.528 | Residencial | Yes | 0-100kW
202403-NM25-01039 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06867 | 8.85 | Residencial | Yes | 0-100kW
202412-NM25-00764 | 8 | Residencial | Yes | 0-100kW
202406-NM25-00148 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01560 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19251 | 5 | Residencial | Yes | 0-100kW
202405-NM25-03332 | 2.928 | Residencial | Yes | 0-100kW
2022-GD-31158 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-02397 | 5.01 | Residencial | Yes | 0-100kW
202407-NM25-01740 | 3 | Residencial | Yes | 0-100kW
2022-GD-04349 | 4.72 | Residencial | Yes | 0-100kW
202505-NM25-00642 | 11.5 | Residencial | Yes | 0-100kW
14-7-650 | 5 | Residencial | Yes | 0-100kW
202403-NM25-00029 | 22.692 | Residencial | Yes | 0-100kW
2023-GD-10334 | 8 | Residencial | Yes | 0-100kW
202504-NM25-02063 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-02146 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-05789 | 5.49 | Residencial | Yes | 0-100kW
202502-NM25-04524 | 4.224 | Residencial | Yes | 0-100kW
2019-GD-00603 | 6 | Residencial | Yes | 0-100kW
202507-NM25-00470 | 3.84 | Residencial | Yes | 0-100kW
202507-NM25-04442 | 3.8 | Residencial | Yes | 0-100kW
202408-NM25-04180 | 4.224 | Residencial | Yes | 0-100kW
2023-GD-03130 | 6 | Residencial | Yes | 0-100kW
2022-GD-28188 | 4.3 | Residencial | Yes | 0-100kW
202412-NM25-02216 | 8 | Residencial | Yes | 0-100kW
2022-GD-23267 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-29870 | 3.8 | Residencial | Yes | 0-100kW
202405-NM25-03297 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01305 | 11.346 | Residencial | Yes | 0-100kW
2022-GD-30062 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01745 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-03991 | 6.588 | Residencial | Yes | 0-100kW
2022-GD-32771 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-32048 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-25159 | 5 | Residencial | Yes | 0-100kW
2022-GD-19413 | 7.32 | Residencial | Yes | 0-100kW
09-3-095 | 6 | Residencial | Yes | 0-100kW
202310-NM25-00454 | 3.66 | Residencial | Yes | 0-100kW
202409-NM25-04424 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00423 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-03024 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12135 | 4.43 | Residencial | Yes | 0-100kW
202501-NM25-04453 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-04064 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-06091 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-31474 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-07714 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-05777 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-07235 | 3.75 | Residencial | Yes | 0-100kW
2021-GD-08964 | 3.54 | Residencial | Yes | 0-100kW
202408-NM25-04473 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16649 | 4.5 | Residencial | Yes | 0-100kW
202411-NM25-03598 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-26086 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30196 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-28383 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-26886 | 4.03 | Residencial | Yes | 0-100kW
202410-NM25-02027 | 8.784 | Residencial | Yes | 0-100kW
202508-NM25-04371 | 8 | Residencial | Yes | 0-100kW
202403-NM25-03642 | 15.2 | Residencial | Yes | 0-100kW
202507-NM25-04912 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-03111 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-03041 | 6.8 | Residencial | Yes | 0-100kW
202407-NM25-00255 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-05806 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11790 | 6.3 | Residencial | Yes | 0-100kW
202509-NM25-02653 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-12536 | 8.05 | Residencial | Yes | 0-100kW
202512-NM25-04190 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-09648 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-28742 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-03533 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-27987 | 9.15 | Residencial | Yes | 0-100kW
202501-NM25-02344 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07826 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-02045 | 5.76 | Residencial | Yes | 0-100kW
2021-GD-04363 | 12.98 | Residencial | Yes | 0-100kW
2023-GD-10762 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-13107 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-04423 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-29268 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01900 | 7.6 | Residencial | No | 0-100kW
2022-GD-10988 | 5.12 | Residencial | Yes | 0-100kW
202404-NM25-02524 | 6.528 | Residencial | Yes | 0-100kW
202506-NM25-00086 | 7.296 | Residencial | Yes | 0-100kW
202407-NM25-00370 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-38053 | 6.14 | Residencial | Yes | 0-100kW
202408-NM25-01395 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-02098 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24700 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-03848 | 8.42 | Residencial | Yes | 0-100kW
202405-NM25-02918 | 4.758 | Residencial | Yes | 0-100kW
2021-GD-10135 | 6.8 | Residencial | Yes | 0-100kW
202512-NM25-03405 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-04483 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-02221 | 3.54 | Residencial | Yes | 0-100kW
202512-NM25-00593 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-07476 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-37735 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28549 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03192 | 3.84 | Residencial | Yes | 0-100kW
202505-NM25-03770 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05712 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-04428 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-00210 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-31576 | 6.95 | Residencial | Yes | 0-100kW
202406-NM25-02251 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-03772 | 6.49 | Residencial | Yes | 0-100kW
202502-NM25-03016 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-23752 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07292 | 5.5 | Residencial | Yes | 0-100kW
2023-GD-02736 | 5 | Residencial | Yes | 0-100kW
202406-NM25-02229 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-15941 | 5 | Residencial | Yes | 0-100kW
202409-NM25-01255 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00029 | 2.95 | Residencial | Yes | 0-100kW
2023-GD-37148 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04423 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-00850 | 8 | Residencial | Yes | 0-100kW
202408-NM25-02510 | 4.992 | Residencial | Yes | 0-100kW
2022-GD-10684 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-00497 | 5 | Residencial | Yes | 0-100kW
2022-GD-16350 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-30931 | 7.5 | Residencial | Yes | 0-100kW
2022-GD-14601 | 4.03 | Residencial | Yes | 0-100kW
202506-NM25-03921 | 7.464 | Residencial | Yes | 0-100kW
202501-NM25-03134 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-04250 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03324 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03732 | 3.8 | Residencial | Yes | 0-100kW
16-5-0361A | 6.44 | Residencial | Yes | 0-100kW
14-2-296 | 13 | Residencial | Yes | 0-100kW
2021-GD-01420 | 8.85 | Residencial | Yes | 0-100kW
2023-GD-16719 | 15 | Residencial | Yes | 0-100kW
202409-NM25-03048 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-18140 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-02483 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01865 | 6 | Residencial | Yes | 0-100kW
2023-GD-22161 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-03059 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14348 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-02307 | 8.418 | Residencial | Yes | 0-100kW
202409-NM25-01539 | 8.418 | Residencial | Yes | 0-100kW
2022-GD-31564 | 7.68 | Residencial | Yes | 0-100kW
202312-NM25-00184 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-03545 | 5 | Residencial | Yes | 0-100kW
2023-GD-01526 | 8.06 | Residencial | No | 0-100kW
202408-NM25-02832 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-01315 | 8.26 | Residencial | Yes | 0-100kW
2022-GD-18369 | 5.31 | Residencial | Yes | 0-100kW
202509-NM25-03470 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-02214 | 10 | Residencial | Yes | 0-100kW
202504-NM25-00368 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-04276 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-03515 | 15.2 | Comercial | Yes | 0-100kW
202410-NM25-03566 | 9.516 | Residencial | Yes | 0-100kW
2022-GD-16580 | 5 | Residencial | Yes | 0-100kW
2021-GD-13224 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-19819 | 14.4 | Residencial | Yes | 0-100kW
202404-NM25-03760 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02359 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-00012 | 12.6 | Residencial | Yes | 0-100kW
202502-NM25-03254 | 10.98 | Residencial | No | 0-100kW
2023-GD-26509 | 3.8 | Residencial | Yes | 0-100kW
202412-NM25-00988 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-00944 | 5.856 | Residencial | Yes | 0-100kW
202401-NM25-01154 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23942 | 22.36 | Residencial | Yes | 0-100kW
202409-NM25-03860 | 4.8 | Residencial | Yes | 0-100kW
202509-NM25-03848 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-21161 | 8.7 | Residencial | Yes | 0-100kW
202505-NM25-02061 | 11.5 | Residencial | No | 0-100kW
202509-NM25-04673 | 3.8 | Residencial | Yes | 0-100kW
202402-NM25-00563 | 5.124 | Residencial | Yes | 0-100kW
202402-NM25-02265 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00021 | 5.31 | Residencial | Yes | 0-100kW
202408-NM25-02900 | 3 | Residencial | Yes | 0-100kW
2023-GD-38822 | 4.03 | Residencial | Yes | 0-100kW
202409-NM25-03969 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-01357 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-00605 | 4.43 | Residencial | Yes | 0-100kW
202406-NM25-00899 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00255 | 5 | Residencial | Yes | 0-100kW
2022-GD-30405 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-12605 | 9.44 | Residencial | Yes | 0-100kW
2023-GD-07836 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01815 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-03581 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22473 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-04601 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-08974 | 5.31 | Residencial | Yes | 0-100kW
202410-NM25-02616 | 5.376 | Residencial | Yes | 0-100kW
2022-GD-14204 | 6 | Residencial | Yes | 0-100kW
2023-GD-20092 | 8 | Residencial | Yes | 0-100kW
2023-GD-12678 | 6.8 | Residencial | Yes | 0-100kW
202401-NM25-03646 | 8.052 | Residencial | Yes | 0-100kW
2023-GD-34188 | 3.3 | Residencial | Yes | 0-100kW
2022-GD-19939 | 4.03 | Residencial | Yes | 0-100kW
202510-NM25-01820 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-01850 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-37422 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-01792 | 2.95 | Residencial | Yes | 0-100kW
2021-GD-12900 | 6.49 | Residencial | Yes | 0-100kW
2022-GD-05621 | 6.95 | Residencial | Yes | 0-100kW
2017-GD-03380 | 6.665 | Residencial | Yes | 0-100kW
202510-NM25-02537 | 11.5 | Residencial | No | 0-100kW
202312-NM25-01250 | 5 | Comercial | Yes | 0-100kW
202512-NM25-00186 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-00051 | 8.418 | Residencial | Yes | 0-100kW
2023-GD-24507 | 8 | Residencial | Yes | 0-100kW
202407-NM25-00817 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04153 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17084 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-01601 | 3.8 | Residencial | Yes | 0-100kW
15-7-742 | 2.58 | Residencial | Yes | 0-100kW
202512-NM25-05204 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-31516 | 20.86 | Residencial | Yes | 0-100kW
2022-GD-08203 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-34772 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-05022 | 3.54 | Residencial | Yes | 0-100kW
202411-NM25-01027 | 15.2 | Residencial | Yes | 0-100kW
202411-NM25-03006 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05742 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25904 | 8.06 | Residencial | Yes | 0-100kW
202406-NM25-02282 | 2.36 | Residencial | Yes | 0-100kW
202502-NM25-00475 | 7.6 | Residencial | Yes | 0-100kW
202311-NM25-01040 | 6.588 | Residencial | Yes | 0-100kW
202311-NM25-00415 | 10.98 | Residencial | Yes | 0-100kW
2023-GD-15569 | 7.08 | Residencial | Yes | 0-100kW
2020-GD-08381 | 3.54 | Residencial | Yes | 0-100kW
2019-GD-01128 | 3.54 | Residencial | Yes | 0-100kW
202510-NM25-02106 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-19625 | 3.84 | Residencial | Yes | 0-100kW
202505-NM25-03166 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-01275 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30685 | 9.15 | Residencial | Yes | 0-100kW
202502-NM25-06934 | 3.8 | Residencial | Yes | 0-100kW
2017-GD-03173 | 4.515 | Residencial | Yes | 0-100kW
2023-GD-01447 | 3.8 | Residencial | Yes | 0-100kW
2017-GD-03596 | 6.96 | Residencial | Yes | 0-100kW
202502-NM25-05613 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13564 | 5.49 | Residencial | Yes | 0-100kW
2018-GD-00346 | 8 | Residencial | Yes | 0-100kW
2023-GD-09908 | 3.8 | Residencial | No | 0-100kW
202507-NM25-05021 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-03213 | 5.76 | Residencial | Yes | 0-100kW
202407-NM25-01877 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03785 | 7.68 | Residencial | Yes | 0-100kW
2021-GD-14129 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02478 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01469 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-04943 | 4.03 | Residencial | Yes | 0-100kW
202503-NM25-02508 | 8.448 | Residencial | Yes | 0-100kW
2018-GD-02096 | 24 | Comercial | Yes | 0-100kW
202408-NM25-00786 | 13.908 | Residencial | Yes | 0-100kW
2023-GD-00562 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-02408 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-22094 | 6.8 | Residencial | Yes | 0-100kW
16-2-1644 | 9 | Residencial | Yes | 0-100kW
2022-GD-06258 | 3.84 | Residencial | Yes | 0-100kW
202312-NM25-00021 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-00882 | 11.348 | Residencial | Yes | 0-100kW
202408-NM25-00711 | 6 | Residencial | Yes | 0-100kW
2017-GD-02855 | 8.16 | Residencial | Yes | 0-100kW
202403-NM25-02026 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01916 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33997 | 6 | Residencial | Yes | 0-100kW
202411-NM25-01444 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-01839 | 3.66 | Residencial | Yes | 0-100kW
202503-NM25-03343 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03553 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-01703 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01084 | 10.56 | Residencial | Yes | 0-100kW
2021-GD-00244 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-38219 | 5 | Residencial | Yes | 0-100kW
2021-GD-13692 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-13668 | 3.54 | Residencial | Yes | 0-100kW
202511-NM25-04389 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25918 | 4.43 | Comercial | Yes | 0-100kW
202507-NM25-02211 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18626 | 6.8 | Residencial | Yes | 0-100kW
202507-NM25-02419 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-01112 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-09337 | 6.8 | Residencial | Yes | 0-100kW
202501-NM25-01215 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-01759 | 15.55 | Residencial | Yes | 0-100kW
202509-NM25-06007 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-00576 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-01708 | 8 | Residencial | Yes | 0-100kW
202410-NM25-04857 | 4.992 | Residencial | Yes | 0-100kW
2019-GD-01324 | 8.64 | Residencial | Yes | 0-100kW
202405-NM25-04188 | 5 | Residencial | Yes | 0-100kW
2023-GD-22063 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02630 | 8.78 | Residencial | Yes | 0-100kW
202506-NM25-03665 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-31974 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00735 | 11.44 | Residencial | Yes | 0-100kW
202505-NM25-04540 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-01465 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-08390 | 3.84 | Residencial | Yes | 0-100kW
202507-NM25-03207 | 11.5 | Residencial | Yes | 0-100kW
15-3-342 | 4.2 | Residencial | Yes | 0-100kW
202407-NM25-03506 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31282 | 5.49 | Residencial | Yes | 0-100kW
202501-NM25-03155 | 15 | Residencial | Yes | 0-100kW
202511-NM25-00261 | 11.4 | Comercial | Yes | 0-100kW
2022-GD-32280 | 4.39 | Residencial | Yes | 0-100kW
202501-NM25-05754 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-04090 | 5 | Residencial | Yes | 0-100kW
202510-NM25-01894 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-36365 | 10.61 | Residencial | Yes | 0-100kW
2022-GD-01100 | 19.2 | Residencial | Yes | 0-100kW
2022-GD-25401 | 6 | Residencial | No | 0-100kW
2023-GD-06971 | 9.84 | Residencial | Yes | 0-100kW
202406-NM25-03495 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00612 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01775 | 2.928 | Residencial | Yes | 0-100kW
202408-NM25-02778 | 5.856 | Residencial | Yes | 0-100kW
202508-NM25-01462 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34126 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-02346 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02705 | 9 | Residencial | Yes | 0-100kW
202402-NM25-01911 | 5 | Residencial | Yes | 0-100kW
202412-NM25-03402 | 8 | Residencial | Yes | 0-100kW
202407-NM25-02798 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-00178 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-03889 | 2.688 | Residencial | Yes | 0-100kW
202409-NM25-02080 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-03669 | 4.392 | Residencial | Yes | 0-100kW
2021-GD-02320 | 9.25 | Residencial | Yes | 0-100kW
202409-NM25-03744 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00329 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-00472 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05198 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-00993 | 17.28 | Comercial | Yes | 0-100kW
2022-GD-12719 | 3.29 | Residencial | Yes | 0-100kW
2020-GD-04954 | 6.59 | Residencial | Yes | 0-100kW
202506-NM25-02955 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04768 | 10 | Residencial | Yes | 0-100kW
202506-NM25-01853 | 8 | Residencial | Yes | 0-100kW
2022-GD-29656 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31408 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02360 | 7.5 | Residencial | Yes | 0-100kW
202508-NM25-00921 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26751 | 3.8 | Residencial | Yes | 0-100kW
2018-GD-01573 | 5.31 | Comercial | Yes | 0-100kW
202402-NM25-01205 | 19.032 | Residencial | Yes | 0-100kW
2021-GD-06601 | 3.25 | Residencial | Yes | 0-100kW
2021-GD-10996 | 5.12 | Residencial | Yes | 0-100kW
202511-NM25-01750 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00626 | 8.16 | Residencial | Yes | 0-100kW
202411-NM25-00523 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11536 | 6 | Residencial | Yes | 0-100kW
202405-NM25-00112 | 15 | Residencial | Yes | 0-100kW
202504-NM25-00587 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-02886 | 3.5 | Residencial | Yes | 0-100kW
15-3-729 | 3.23 | Residencial | Yes | 0-100kW
202408-NM25-04118 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04382 | 10.98 | Residencial | Yes | 0-100kW
202506-NM25-04283 | 8 | Residencial | Yes | 0-100kW
2022-GD-04898 | 5.9 | Comercial | Yes | 0-100kW
2022-GD-16807 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-26777 | 5 | Residencial | Yes | 0-100kW
202412-NM25-00444 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-04001 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-00399 | 5 | Residencial | Yes | 0-100kW
202503-NM25-02427 | 8 | Residencial | Yes | 0-100kW
2023-GD-18968 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-04463 | 11.5 | Residencial | Yes | 0-100kW
15-2-629 | 3 | Residencial | Yes | 0-100kW
202402-NM25-00781 | 10.98 | Residencial | Yes | 0-100kW
2023-GD-02934 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14667 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-26432 | 7.69 | Residencial | No | 0-100kW
202412-NM25-01627 | 3.072 | Residencial | Yes | 0-100kW
2023-GD-32230 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-16948 | 4.03 | Residencial | Yes | 0-100kW
202406-NM25-00849 | 4.224 | Residencial | Yes | 0-100kW
2017-GD-02057 | 4.5 | Residencial | Yes | 0-100kW
202504-NM25-03593 | 6.8 | Residencial | Yes | 0-100kW
202412-NM25-03810 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-03216 | 8.052 | Residencial | Yes | 0-100kW
202411-NM25-01793 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-03813 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-35028 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-26297 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12104 | 8.26 | Residencial | Yes | 0-100kW
2022-GD-08978 | 4.03 | Residencial | Yes | 0-100kW
15-7-824 | 5.37 | Residencial | Yes | 0-100kW
202506-NM25-00381 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06029 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-22305 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-19971 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-04327 | 8.052 | Residencial | Yes | 0-100kW
202507-NM25-01412 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-02546 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07059 | 4.72 | Residencial | Yes | 0-100kW
202505-NM25-01651 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-32635 | 16.1 | Residencial | Yes | 0-100kW
2023-GD-27112 | 2.93 | Residencial | Yes | 0-100kW
2021-GD-06845 | 3.84 | Residencial | Yes | 0-100kW
202502-NM25-03616 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-13195 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-38071 | 15 | Residencial | Yes | 0-100kW
202409-NM25-02365 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-00505 | 3.24 | Residencial | Yes | 0-100kW
202401-NM25-03405 | 4.758 | Residencial | Yes | 0-100kW
15-3-452 | 4.3 | Residencial | Yes | 0-100kW
202501-NM25-05289 | 5.376 | Residencial | Yes | 0-100kW
2023-GD-34393 | 4.76 | Residencial | Yes | 0-100kW
202409-NM25-01651 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-05766 | 3.54 | Residencial | Yes | 0-100kW
202506-NM25-01523 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-20244 | 5.38 | Residencial | Yes | 0-100kW
2022-GD-01242 | 3.24 | Residencial | Yes | 0-100kW
2020-GD-02600 | 2.655 | Residencial | Yes | 0-100kW
202508-NM25-02224 | 5.4 | Residencial | Yes | 0-100kW
2021-GD-13933 | 4.72 | Residencial | Yes | 0-100kW
202401-NM25-02609 | 4.392 | Residencial | Yes | 0-100kW
202404-NM25-00800 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-29968 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-04034 | 8 | Residencial | Yes | 0-100kW
2020-GD-03365 | 6.8 | Residencial | Yes | 0-100kW
2021-GD-05016 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-37894 | 5 | Residencial | Yes | 0-100kW
2020-GD-00977 | 4.13 | Residencial | Yes | 0-100kW
202412-NM25-02086 | 3.294 | Residencial | Yes | 0-100kW
2017-GD-02988 | 23 | Comercial | Yes | 0-100kW
2022-GD-26532 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-14487 | 5 | Residencial | Yes | 0-100kW
2022-GD-24153 | 8 | Residencial | Yes | 0-100kW
2023-GD-22226 | 5.12 | Residencial | Yes | 0-100kW
202503-NM25-00717 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-01836 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02229 | 8 | Residencial | Yes | 0-100kW
2022-GD-23133 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-10079 | 8.26 | Residencial | Yes | 0-100kW
202509-NM25-04741 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-08936 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-03870 | 15 | Residencial | Yes | 0-100kW
202403-NM25-02873 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-12307 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-01263 | 6.49 | Residencial | Yes | 0-100kW
202507-NM25-00521 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-22605 | 3.66 | Residencial | Yes | 0-100kW
202406-NM25-01865 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-01687 | 12 | Residencial | Yes | 0-100kW
2023-GD-31298 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02386 | 8.784 | Residencial | Yes | 0-100kW
2022-GD-16042 | 6.53 | Residencial | Yes | 0-100kW
2023-GD-25741 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00848 | 8 | Residencial | Yes | 0-100kW
2019-GD-01071 | 13.75 | Residencial | Yes | 0-100kW
15-6-0776 | 4.3 | Residencial | Yes | 0-100kW
2022-GD-05571 | 5.12 | Residencial | Yes | 0-100kW
2020-GD-07569 | 3.25 | Residencial | Yes | 0-100kW
2021-GD-09619 | 4.43 | Residencial | Yes | 0-100kW
202404-NM25-00338 | 7.6 | Residencial | No | 0-100kW
202405-NM25-03654 | 5 | Residencial | Yes | 0-100kW
202503-NM25-01207 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14487 | 3.54 | Residencial | Yes | 0-100kW
202506-NM25-00630 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-03554 | 5 | Residencial | Yes | 0-100kW
2020-GD-05133 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-04500 | 8 | Residencial | Yes | 0-100kW
2022-GD-31904 | 6.91 | Residencial | Yes | 0-100kW
2019-GD-02749 | 3.245 | Residencial | Yes | 0-100kW
2023-GD-13219 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02038 | 8 | Residencial | Yes | 0-100kW
2022-GD-01997 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-10033 | 4.39 | Residencial | Yes | 0-100kW
202406-NM25-03328 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20625 | 5 | Residencial | Yes | 0-100kW
202511-NM25-00674 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02502 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-03845 | 10 | Comercial | No | 0-100kW
2022-GD-19445 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-00774 | 5 | Comercial | Yes | 0-100kW
2023-GD-15763 | 3 | Residencial | Yes | 0-100kW
202404-NM25-00784 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-15880 | 6.8 | Residencial | Yes | 0-100kW
2020-GD-07282 | 4 | Residencial | Yes | 0-100kW
2022-GD-27634 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-30613 | 10 | Residencial | Yes | 0-100kW
202410-NM25-01568 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01218 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-04826 | 4.03 | Residencial | Yes | 0-100kW
16-5-0751A | 3.66 | Residencial | Yes | 0-100kW
202503-NM25-01525 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-27176 | 5.86 | Residencial | No | 0-100kW
2021-GD-05007 | 8.26 | Residencial | Yes | 0-100kW
2023-GD-29292 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-01995 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06944 | 5.49 | Residencial | Yes | 0-100kW
14-6-0307 | 8.4 | Comercial | Yes | 0-100kW
2022-GD-23804 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-34615 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01686 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-04023 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-32713 | 5.86 | Residencial | Yes | 0-100kW
202512-NM25-00238 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-01847 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-02539 | 4.758 | Residencial | Yes | 0-100kW
202509-NM25-00895 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01930 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26372 | 4.03 | Residencial | Yes | 0-100kW
202410-NM25-03715 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-00385 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-13213 | 9.15 | Residencial | Yes | 0-100kW
202410-NM25-02978 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01835 | 2.304 | Residencial | Yes | 0-100kW
202505-NM25-02144 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-09913 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-30037 | 4.03 | Residencial | Yes | 0-100kW
202511-NM25-02880 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-19963 | 8 | Residencial | Yes | 0-100kW
202402-NM25-00525 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-02415 | 23.04 | Residencial | Yes | 0-100kW
2023-GD-33728 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-04006 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-03996 | 6.49 | Residencial | Yes | 0-100kW
16-7-0363 | 4.73 | Residencial | Yes | 0-100kW
202502-NM25-06125 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-06147 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-06461 | 8.03 | Residencial | Yes | 0-100kW
2022-GD-24631 | 5 | Residencial | Yes | 0-100kW
2023-GD-22990 | 10.98 | Residencial | Yes | 0-100kW
202508-NM25-03949 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07916 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-05633 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-00199 | 4 | Residencial | Yes | 0-100kW
202406-NM25-01098 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-02793 | 6.49 | Residencial | Yes | 0-100kW
2020-GD-04604 | 8.56 | Residencial | Yes | 0-100kW
202502-NM25-04381 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-38812 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04545 | 8 | Residencial | Yes | 0-100kW
2023-GD-24299 | 6.14 | Residencial | Yes | 0-100kW
202510-NM25-01629 | 11.5 | Residencial | Yes | 0-100kW
16-3-987 | 5 | Residencial | Yes | 0-100kW
2022-GD-07156 | 5.01 | Residencial | Yes | 0-100kW
16-1-198 | 8 | Residencial | Yes | 0-100kW
202411-NM25-01819 | 5.124 | Residencial | Yes | 0-100kW
2023-GD-28969 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23293 | 4.03 | Residencial | Yes | 0-100kW
202508-NM25-00859 | 8 | Residencial | Yes | 0-100kW
2022-GD-19443 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-13977 | 8.42 | Residencial | Yes | 0-100kW
202407-NM25-03803 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02916 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-01912 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-08337 | 5.31 | Residencial | No | 0-100kW
2023-GD-01225 | 8 | Residencial | Yes | 0-100kW
2022-GD-04355 | 5.9 | Residencial | Yes | 0-100kW
2020-GD-07923 | 7.97 | Residencial | Yes | 0-100kW
2022-GD-27840 | 4.39 | Residencial | Yes | 0-100kW
2017-GD-02595 | 8 | Residencial | Yes | 0-100kW
202310-NM25-00108 | 4.07 | Residencial | Yes | 0-100kW
2022-GD-09048 | 5.12 | Residencial | Yes | 0-100kW
202505-NM25-04642 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-12169 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-02976 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-39143 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-21798 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-02773 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-00144 | 3.8 | Residencial | Yes | 0-100kW
202412-NM25-03057 | 15.2 | Residencial | Yes | 0-100kW
202502-NM25-03524 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27648 | 5 | Residencial | Yes | 0-100kW
2020-GD-05699 | 8.85 | Residencial | Yes | 0-100kW
2017-GD-01012 | 3 | Residencial | Yes | 0-100kW
2022-GD-31270 | 5 | Residencial | Yes | 0-100kW
2023-GD-28339 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06700 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-03269 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-20534 | 5 | Residencial | Yes | 0-100kW
2019-GD-01939 | 5 | Residencial | Yes | 0-100kW
202312-NM25-03602 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-13963 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12075 | 9.15 | Comercial | Yes | 0-100kW
202505-NM25-00869 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-00936 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06936 | 3.24 | Residencial | Yes | 0-100kW
2020-GD-01672 | 3.5 | Residencial | Yes | 0-100kW
2023-GD-06987 | 5 | Residencial | Yes | 0-100kW
202401-NM25-00086 | 8.052 | Residencial | Yes | 0-100kW
2021-GD-05711 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-25410 | 3.84 | Residencial | Yes | 0-100kW
202402-NM25-01551 | 3.8 | Residencial | Yes | 0-100kW
2018-GD-00619 | 5.76 | Residencial | Yes | 0-100kW
2021-GD-02440 | 15.74 | Residencial | No | 0-100kW
202508-NM25-05381 | 5.3 | Comercial | Yes | 0-100kW
202502-NM25-05103 | 6.588 | Residencial | Yes | 0-100kW
202509-NM25-03367 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-03081 | 4.35 | Residencial | Yes | 0-100kW
202508-NM25-02988 | 12 | Residencial | No | 0-100kW
2019-GD-01929 | 10.4 | Residencial | Yes | 0-100kW
202508-NM25-03325 | 11.5 | Residencial | Yes | 0-100kW
17-4-0006GD | 3 | Residencial | Yes | 0-100kW
202509-NM25-05771 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-08931 | 4 | Residencial | Yes | 0-100kW
2021-GD-09013 | 2.93 | Residencial | Yes | 0-100kW
202404-NM25-04079 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02965 | 7.686 | Residencial | Yes | 0-100kW
2023-GD-12984 | 7.32 | Residencial | Yes | 0-100kW
202502-NM25-03345 | 6.912 | Residencial | Yes | 0-100kW
2021-GD-05463 | 8 | Residencial | Yes | 0-100kW
2023-GD-21642 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01812 | 6 | Residencial | Yes | 0-100kW
2022-GD-11832 | 4.39 | Residencial | Yes | 0-100kW
202412-NM25-02220 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01229 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-00983 | 11.5 | Residencial | Yes | 0-100kW
15-6-0248 | 7.2 | Residencial | Yes | 0-100kW
202503-NM25-04426 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-32632 | 3.8 | Residencial | Yes | 0-100kW
09-6-0432 | 7.38 | Comercial | No | 0-100kW
202504-NM25-04189 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-03161 | 6 | Residencial | Yes | 0-100kW
202406-NM25-00321 | 8 | Residencial | Yes | 0-100kW
2020-GD-02002 | 4.5 | Residencial | Yes | 0-100kW
2022-GD-29195 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-13788 | 4.25 | Residencial | Yes | 0-100kW
202408-NM25-01911 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-20112 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-22176 | 4.75 | Residencial | Yes | 0-100kW
202403-NM25-02941 | 9.15 | Residencial | Yes | 0-100kW
202409-NM25-01556 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04390 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20295 | 7.32 | Residencial | Yes | 0-100kW
202505-NM25-00064 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-08094 | 6 | Residencial | Yes | 0-100kW
2022-GD-25416 | 3.29 | Residencial | Yes | 0-100kW
2022-GD-23604 | 8 | Residencial | Yes | 0-100kW
2022-GD-27706 | 5.86 | Residencial | Yes | 0-100kW
202509-NM25-00814 | 7.296 | Residencial | Yes | 0-100kW
202503-NM25-05454 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-01848 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-28773 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-12735 | 6.53 | Residencial | Yes | 0-100kW
202502-NM25-02727 | 4.758 | Residencial | Yes | 0-100kW
2021-GD-03511 | 5.25 | Residencial | Yes | 0-100kW
2023-GD-29371 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-02742 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16533 | 11.35 | Comercial | Yes | 0-100kW
202507-NM25-01713 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02617 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-00061 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-08920 | 4.03 | Residencial | Yes | 0-100kW
2018-GD-00562 | 4.08 | Residencial | Yes | 0-100kW
15-5-0488A | 2.8 | Residencial | Yes | 0-100kW
202412-NM25-02534 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-00353 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-10026 | 5.31 | Residencial | Yes | 0-100kW
202501-NM25-03349 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36903 | 5.38 | Residencial | Yes | 0-100kW
2022-GD-12501 | 5 | Residencial | Yes | 0-100kW
202509-NM25-04190 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-00503 | 6.588 | Residencial | Yes | 0-100kW
202511-NM25-03200 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-09785 | 3.66 | Residencial | Yes | 0-100kW
14-5-0078A | 3 | Residencial | Yes | 0-100kW
2023-GD-17569 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-05722 | 3.54 | Residencial | Yes | 0-100kW
202504-NM25-04899 | 12 | Residencial | Yes | 0-100kW
202509-NM25-03829 | 23 | Residencial | Yes | 0-100kW
202506-NM25-02653 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27187 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-04042 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01578 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-05139 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-36801 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-25761 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32645 | 5.12 | Residencial | Yes | 0-100kW
202409-NM25-03240 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-13695 | 6 | Residencial | Yes | 0-100kW
202510-NM25-03460 | 23 | Residencial | Yes | 0-100kW
202509-NM25-05133 | 3.8 | Residencial | Yes | 0-100kW
202401-NM25-01763 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00696 | 6.22 | Residencial | Yes | 0-100kW
2023-GD-23555 | 5 | Residencial | Yes | 0-100kW
2023-GD-04989 | 5 | Residencial | Yes | 0-100kW
2023-GD-15285 | 4.76 | Residencial | Yes | 0-100kW
202409-NM25-00856 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11677 | 5.12 | Residencial | No | 0-100kW
2021-GD-00557 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-22595 | 7.3 | Residencial | Yes | 0-100kW
2023-GD-28396 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-03850 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12227 | 3 | Residencial | Yes | 0-100kW
2023-GD-17629 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-00644 | 10 | Residencial | Yes | 0-100kW
2020-GD-06073 | 5.9 | Residencial | Yes | 0-100kW
202402-NM25-03057 | 14.64 | Comercial | No | 0-100kW
202502-NM25-03100 | 5.76 | Residencial | Yes | 0-100kW
202507-NM25-01949 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19611 | 7.6 | Residencial | No | 0-100kW
2021-GD-01790 | 6.19 | Residencial | Yes | 0-100kW
2019-GD-00348 | 4.15 | Residencial | Yes | 0-100kW
2023-GD-14889 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19607 | 2.97 | Residencial | Yes | 0-100kW
2021-GD-10098 | 4.72 | Residencial | Yes | 0-100kW
2018-GD-00789 | 6.72 | Residencial | Yes | 0-100kW
202407-NM25-00901 | 8 | Residencial | Yes | 0-100kW
2023-GD-28928 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14475 | 4.03 | Residencial | Yes | 0-100kW
202403-NM25-02041 | 5 | Residencial | Yes | 0-100kW
2023-GD-30184 | 11.35 | Residencial | Yes | 0-100kW
16-7-0067 | 6 | Residencial | Yes | 0-100kW
202410-NM25-02548 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03556 | 4.224 | Residencial | Yes | 0-100kW
202406-NM25-02695 | 8 | Residencial | Yes | 0-100kW
202401-NM25-03918 | 8.052 | Residencial | Yes | 0-100kW
202403-NM25-03875 | 12.444 | Residencial | Yes | 0-100kW
202408-NM25-02979 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-03259 | 3.8 | Residencial | Yes | 0-100kW
202403-NM25-02845 | 4.224 | Residencial | Yes | 0-100kW
2019-GD-01765 | 3.25 | Residencial | Yes | 0-100kW
2023-GD-26429 | 8.05 | Residencial | Yes | 0-100kW
202407-NM25-01587 | 8.414 | Residencial | Yes | 0-100kW
202407-NM25-00868 | 7.6 | Residencial | Yes | 0-100kW
16-1-951 | 3.4 | Residencial | Yes | 0-100kW
2022-GD-32658 | 4.76 | Residencial | Yes | 0-100kW
202404-NM25-02496 | 5.124 | Residencial | Yes | 0-100kW
2023-GD-31147 | 5 | Residencial | Yes | 0-100kW
202504-NM25-05886 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36452 | 3.96 | Residencial | Yes | 0-100kW
14-5-0019A | 11 | Residencial | Yes | 0-100kW
202408-NM25-03146 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02690 | 6.53 | Residencial | Yes | 0-100kW
2020-GD-07202 | 16.6 | Residencial | Yes | 0-100kW
202409-NM25-00373 | 7.375 | Comercial | Yes | 0-100kW
202409-NM25-03746 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-00365 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-05272 | 5.9 | Residencial | Yes | 0-100kW
202410-NM25-04741 | 8 | Residencial | Yes | 0-100kW
202408-NM25-00290 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07833 | 7.32 | Residencial | Yes | 0-100kW
2020-GD-00686 | 3.245 | Residencial | Yes | 0-100kW
202412-NM25-03185 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-01594 | 5.856 | Residencial | Yes | 0-100kW
202406-NM25-00454 | 8 | Residencial | Yes | 0-100kW
2023-GD-00478 | 4.39 | Residencial | Yes | 0-100kW
2020-GD-00085 | 10 | Residencial | Yes | 0-100kW
2022-GD-05329 | 3.8 | Residencial | Yes | 0-100kW
202407-NM25-03150 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03737 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04794 | 11.5 | Residencial | Yes | 0-100kW
13-3-152 | 13.12 | Residencial | Yes | 0-100kW
2017-GD-00350 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-03169 | 21.228 | Residencial | Yes | 0-100kW
14-4-0149 | 18 | Residencial | Yes | 0-100kW
2020-GD-00557 | 3.5 | Residencial | Yes | 0-100kW
202408-NM25-02715 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04271 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-10815 | 4.39 | Residencial | Yes | 0-100kW
202405-NM25-00840 | 12 | Residencial | Yes | 0-100kW
2022-GD-22904 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-27682 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-06770 | 4.03 | Residencial | Yes | 0-100kW
202311-NM25-00945 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04409 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-19743 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12981 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01751 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03164 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34437 | 7.6 | Comercial | Yes | 0-100kW
2023-GD-30861 | 6 | Residencial | No | 0-100kW
2018-GD-00315 | 2.4 | Residencial | Yes | 0-100kW
202508-NM25-02033 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-00520 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05054 | 3.24 | Residencial | Yes | 0-100kW
202402-NM25-00484 | 10 | Residencial | Yes | 0-100kW
2023-GD-06350 | 9.22 | Residencial | Yes | 0-100kW
2020-GD-05884 | 7.08 | Residencial | Yes | 0-100kW
2022-GD-30100 | 5.49 | Residencial | Yes | 0-100kW
2021-GD-00189 | 4.5 | Residencial | Yes | 0-100kW
2022-GD-24692 | 7.32 | Residencial | Yes | 0-100kW
202502-NM25-02917 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15777 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01352 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14922 | 12.44 | Residencial | Yes | 0-100kW
202503-NM25-02880 | 3.072 | Residencial | Yes | 0-100kW
2018-GD-02056 | 19.85 | Residencial | Yes | 0-100kW
202501-NM25-02711 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-35667 | 9.52 | Residencial | Yes | 0-100kW
202412-NM25-01463 | 3.66 | Residencial | Yes | 0-100kW
202407-NM25-01984 | 8 | Residencial | Yes | 0-100kW
202405-NM25-04163 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-24177 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-37046 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-03509 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-19498 | 12.1 | Residencial | Yes | 0-100kW
202409-NM25-03497 | 10.61 | Residencial | Yes | 0-100kW
2021-GD-01029 | 8.85 | Residencial | Yes | 0-100kW
2019-GD-00846 | 4.15 | Residencial | Yes | 0-100kW
2021-GD-06843 | 3.54 | Residencial | Yes | 0-100kW
202412-NM25-00379 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03138 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-12768 | 3.8 | Residencial | No | 0-100kW
2022-GD-00831 | 4.72 | Residencial | Yes | 0-100kW
202412-NM25-03801 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02045 | 15.744 | Residencial | Yes | 0-100kW
202502-NM25-05639 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-10474 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11589 | 6 | Residencial | Yes | 0-100kW
11-7-014 | 4.15 | Residencial | Yes | 0-100kW
202501-NM25-01811 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-11999 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-01662 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08129 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-23720 | 4.76 | Residencial | Yes | 0-100kW
202402-NM25-02126 | 2.304 | Residencial | Yes | 0-100kW
2023-GD-36841 | 8.05 | Residencial | Yes | 0-100kW
2017-GD-01809 | 3.25 | Residencial | Yes | 0-100kW
202504-NM25-04939 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00520 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02129 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-00279 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-04155 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07848 | 19.03 | Comercial | Yes | 0-100kW
2023-GD-02754 | 8 | Residencial | Yes | 0-100kW
2023-GD-09918 | 15.2 | Residencial | Yes | 0-100kW
11-5-0162A | 7 | Residencial | Yes | 0-100kW
202309-NM25-00202 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-04607 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-20588 | 9 | Residencial | Yes | 0-100kW
2023-GD-11961 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-01004 | 6 | Residencial | Yes | 0-100kW
202410-NM25-04518 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15983 | 5.61 | Residencial | Yes | 0-100kW
2022-GD-26595 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-34058 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07457 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-36427 | 3.36 | Residencial | Yes | 0-100kW
202402-NM25-01049 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02822 | 9.216 | Residencial | Yes | 0-100kW
202412-NM25-00294 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12859 | 5 | Residencial | Yes | 0-100kW
2023-GD-38367 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-03365 | 2.88 | Residencial | Yes | 0-100kW
2022-GD-05708 | 8.78 | Residencial | Yes | 0-100kW
202407-NM25-00177 | 3.84 | Residencial | Yes | 0-100kW
202406-NM25-01111 | 18.662 | Residencial | Yes | 0-100kW
2023-GD-13726 | 4.39 | Residencial | Yes | 0-100kW
2020-GD-00190 | 6.79 | Residencial | Yes | 0-100kW
2022-GD-24591 | 8.42 | Residencial | Yes | 0-100kW
14-5-0265A | 8 | Residencial | Yes | 0-100kW
2022-GD-08304 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-03662 | 4.13 | Residencial | Yes | 0-100kW
2021-GD-08753 | 9.44 | Residencial | Yes | 0-100kW
2022-GD-31869 | 5.12 | Residencial | Yes | 0-100kW
202409-NM25-02724 | 3.456 | Residencial | Yes | 0-100kW
202409-NM25-00405 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-04271 | 8 | Residencial | Yes | 0-100kW
2022-GD-27761 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-12249 | 4.39 | Residencial | Yes | 0-100kW
2017-GD-01183 | 4 | Residencial | Yes | 0-100kW
2020-GD-03642 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-24390 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-16929 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-12936 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00270 | 6.95 | Residencial | Yes | 0-100kW
2022-GD-25953 | 4.99 | Residencial | Yes | 0-100kW
2021-GD-14585 | 8.26 | Residencial | Yes | 0-100kW
2022-GD-20661 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-04521 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35515 | 3.9 | Residencial | Yes | 0-100kW
202510-NM25-01393 | 6.958 | Residencial | Yes | 0-100kW
13-4-0154 | 6.16 | Residencial | Yes | 0-100kW
202502-NM25-04973 | 15 | Residencial | Yes | 0-100kW
202411-NM25-00986 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01576 | 11.5 | Residencial | Yes | 0-100kW
202311-NM25-00363 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-04946 | 4.76 | Residencial | Yes | 0-100kW
202412-NM25-01812 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02529 | 6.3 | Residencial | Yes | 0-100kW
2023-GD-11120 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08265 | 9.88 | Residencial | Yes | 0-100kW
202509-NM25-05667 | 11.5 | Residencial | No | 0-100kW
202507-NM25-04791 | 6 | Residencial | Yes | 0-100kW
202404-NM25-03890 | 10 | Residencial | Yes | 0-100kW
202405-NM25-02533 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03547 | 3.9 | Residencial | Yes | 0-100kW
2021-GD-02210 | 6.8 | Residencial | Yes | 0-100kW
15-3-654 | 2.58 | Residencial | Yes | 0-100kW
2023-GD-02700 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-01602 | 3.84 | Residencial | Yes | 0-100kW
202412-NM25-03482 | 3.66 | Residencial | Yes | 0-100kW
202502-NM25-00709 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07094 | 4.5 | Residencial | Yes | 0-100kW
15-3-417 | 3 | Residencial | Yes | 0-100kW
2021-GD-01986 | 6.49 | Residencial | Yes | 0-100kW
202407-NM25-00786 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01768 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-01567 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-10193 | 6.95 | Residencial | Yes | 0-100kW
202505-NM25-01766 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-02819 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-02959 | 10.98 | Residencial | Yes | 0-100kW
2022-GD-12038 | 2.93 | Residencial | Yes | 0-100kW
2021-GD-10005 | 4.76 | Residencial | Yes | 0-100kW
15-1-150 | 42 | Comercial | Yes | 0-100kW
2022-GD-23419 | 6.8 | Comercial | Yes | 0-100kW
202408-NM25-04590 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-05131 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-03959 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05377 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-09047 | 6.22 | Residencial | Yes | 0-100kW
202407-NM25-03687 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-10644 | 5 | Residencial | Yes | 0-100kW
202509-NM25-01104 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-35292 | 4.29 | Residencial | Yes | 0-100kW
2023-GD-03798 | 4.39 | Residencial | Yes | 0-100kW
202312-NM25-00746 | 8.784 | Residencial | Yes | 0-100kW
202510-NM25-03391 | 7.68 | Residencial | Yes | 0-100kW
202509-NM25-02683 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-03091 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-00629 | 3.456 | Residencial | Yes | 0-100kW
202511-NM25-03165 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02579 | 10.752 | Residencial | Yes | 0-100kW
2022-GD-05608 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-04408 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-19663 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05648 | 3.54 | Residencial | Yes | 0-100kW
202508-NM25-01763 | 11.5 | Comercial | Yes | 0-100kW
202407-NM25-01213 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02979 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-09890 | 5.12 | Residencial | Yes | 0-100kW
2017-GD-01831 | 2.58 | Residencial | Yes | 0-100kW
202511-NM25-02448 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-10570 | 5.01 | Residencial | Yes | 0-100kW
202409-NM25-00792 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-11372 | 8 | Residencial | Yes | 0-100kW
2022-GD-11587 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-33182 | 8 | Residencial | Yes | 0-100kW
2023-GD-31905 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03208 | 6.195 | Residencial | Yes | 0-100kW
202506-NM25-02813 | 8 | Residencial | Yes | 0-100kW
2023-GD-11610 | 3.96 | Residencial | Yes | 0-100kW
202504-NM25-04708 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-19810 | 7.38 | Residencial | Yes | 0-100kW
202403-NM25-01161 | 6.588 | Residencial | Yes | 0-100kW
2020-GD-04808 | 3.54 | Residencial | Yes | 0-100kW
202406-NM25-00485 | 24 | Comercial | Yes | 0-100kW
2023-GD-32941 | 15 | Residencial | Yes | 0-100kW
16-7-1131 | 5.81 | Residencial | Yes | 0-100kW
2023-GD-35739 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26241 | 3.29 | Residencial | Yes | 0-100kW
2022-GD-02463 | 4.72 | Residencial | Yes | 0-100kW
2020-GD-05106 | 7 | Residencial | Yes | 0-100kW
202404-NM25-02558 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-00910 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-04902 | 7.6 | Residencial | Yes | 0-100kW
17-4-0147GD | 4.5 | Residencial | Yes | 0-100kW
2022-GD-27547 | 9.6 | Comercial | Yes | 0-100kW
202411-NM25-01395 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05343 | 10.03 | Comercial | Yes | 0-100kW
2022-GD-23479 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-03125 | 3.54 | Residencial | Yes | 0-100kW
2020-GD-04675 | 3.24 | Residencial | Yes | 0-100kW
202402-NM25-02506 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-31413 | 5 | Residencial | Yes | 0-100kW
2022-GD-13128 | 5 | Residencial | Yes | 0-100kW
2023-GD-34887 | 2.2 | Residencial | Yes | 0-100kW
202411-NM25-00879 | 4.026 | Residencial | Yes | 0-100kW
202406-NM25-02248 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-08327 | 4.5 | Residencial | Yes | 0-100kW
2020-GD-00470 | 5 | Residencial | Yes | 0-100kW
2023-GD-38173 | 4.03 | Residencial | Yes | 0-100kW
202502-NM25-05135 | 2.928 | Residencial | Yes | 0-100kW
2023-GD-23191 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05385 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-38279 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-14696 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-00501 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-15800 | 8.05 | Residencial | Yes | 0-100kW
2022-GD-32626 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-08220 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-32405 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-12485 | 11.71 | Residencial | Yes | 0-100kW
202505-NM25-01516 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-02961 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03490 | 6.59 | Residencial | Yes | 0-100kW
17-2-0264 | 6.45 | Residencial | Yes | 0-100kW
202311-NM25-00789 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-02805 | 3.8 | Residencial | Yes | 0-100kW
202403-NM25-04077 | 11.4 | Residencial | Yes | 0-100kW
2021-GD-07989 | 3.24 | Residencial | Yes | 0-100kW
202502-NM25-04321 | 15.2 | Comercial | Yes | 0-100kW
202406-NM25-00443 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07970 | 5 | Residencial | Yes | 0-100kW
2020-GD-09412 | 4.13 | Residencial | Yes | 0-100kW
202412-NM25-03099 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18080 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00226 | 3.84 | Residencial | Yes | 0-100kW
2020-GD-06712 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-04307 | 7.6 | Residencial | Yes | 0-100kW
16-2-0769 | 3.44 | Residencial | Yes | 0-100kW
2019-GD-02332 | 16.7 | Residencial | Yes | 0-100kW
202407-NM25-03273 | 6 | Residencial | Yes | 0-100kW
2020-GD-02747 | 4.13 | Residencial | Yes | 0-100kW
202405-NM25-01649 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01921 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27248 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-19299 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05356 | 3.54 | Residencial | Yes | 0-100kW
202407-NM25-01818 | 8.784 | Residencial | Yes | 0-100kW
202506-NM25-00705 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-16840 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-02850 | 3.25 | Residencial | Yes | 0-100kW
202406-NM25-01312 | 8 | Residencial | Yes | 0-100kW
2022-GD-15447 | 2.56 | Residencial | Yes | 0-100kW
2023-GD-32277 | 4.03 | Residencial | Yes | 0-100kW
202411-NM25-01486 | 7.6 | Residencial | Yes | 0-100kW
15-3-1023 | 4.94 | Residencial | Yes | 0-100kW
202502-NM25-04341 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-08118 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-22436 | 4.76 | Residencial | Yes | 0-100kW
202511-NM25-03305 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-37173 | 1.83 | Residencial | Yes | 0-100kW
2023-GD-21545 | 3.66 | Residencial | Yes | 0-100kW
202505-NM25-05354 | 15 | Residencial | Yes | 0-100kW
09-6-0326 | 4.7 | Residencial | Yes | 0-100kW
202402-NM25-00234 | 5.856 | Residencial | Yes | 0-100kW
2023-GD-25039 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-00644 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-02572 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-32335 | 4.61 | Residencial | Yes | 0-100kW
2023-GD-21612 | 7.6 | Residencial | No | 0-100kW
202403-NM25-01559 | 9 | Residencial | Yes | 0-100kW
202409-NM25-01207 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00838 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-03358 | 8 | Residencial | Yes | 0-100kW
202506-NM25-04442 | 15 | Residencial | Yes | 0-100kW
2022-GD-05715 | 5.12 | Residencial | Yes | 0-100kW
202512-NM25-02551 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31291 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-16237 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-07685 | 3.54 | Residencial | Yes | 0-100kW
202507-NM25-01065 | 1.83 | Residencial | Yes | 0-100kW
202509-NM25-01501 | 9.6 | Residencial | Yes | 0-100kW
2020-GD-01829 | 4.75 | Residencial | Yes | 0-100kW
202505-NM25-05203 | 10.248 | Residencial | Yes | 0-100kW
2021-GD-11923 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-15294 | 6.22 | Residencial | Yes | 0-100kW
202508-NM25-02105 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-28215 | 3.84 | Residencial | Yes | 0-100kW
202506-NM25-03813 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-00346 | 3.8 | Residencial | No | 0-100kW
16-3-187 | 5.59 | Residencial | Yes | 0-100kW
2021-GD-11025 | 4.72 | Residencial | Yes | 0-100kW
2023-GD-00054 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-12445 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-01023 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06595 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06897 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-26390 | 6.95 | Residencial | Yes | 0-100kW
16-5-0497A | 3.23 | Residencial | Yes | 0-100kW
202409-NM25-04177 | 11.4 | Residencial | Yes | 0-100kW
202504-NM25-05696 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-02788 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-07147 | 3.54 | Residencial | Yes | 0-100kW
202412-NM25-01744 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05252 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-10590 | 9.22 | Residencial | Yes | 0-100kW
2023-GD-36464 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18496 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-01621 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-14319 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-18725 | 8 | Comercial | Yes | 0-100kW
202411-NM25-03528 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14768 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-28780 | 9.22 | Residencial | Yes | 0-100kW
202404-NM25-01111 | 7.26 | Residencial | Yes | 0-100kW
2019-GD-02830 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-12258 | 8.78 | Residencial | Yes | 0-100kW
16-6-0283 | 3.23 | Residencial | Yes | 0-100kW
2023-GD-37395 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09909 | 5 | Residencial | Yes | 0-100kW
202401-NM25-00214 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00735 | 7.68 | Residencial | Yes | 0-100kW
202504-NM25-01913 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-07324 | 3.54 | Residencial | Yes | 0-100kW
202502-NM25-05519 | 11.5 | Residencial | Yes | 0-100kW
16-7-0827 | 4.52 | Residencial | Yes | 0-100kW
202505-NM25-01470 | 6.588 | Residencial | Yes | 0-100kW
202412-NM25-03415 | 8.784 | Comercial | Yes | 0-100kW
2023-GD-14854 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-25044 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-05805 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06539 | 7.296 | Residencial | Yes | 0-100kW
202412-NM25-03858 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-07974 | 4.39 | Residencial | Yes | 0-100kW
2020-GD-01164 | 6.8 | Residencial | Yes | 0-100kW
2020-GD-07962 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09206 | 9.15 | Residencial | Yes | 0-100kW
2021-GD-13737 | 3.24 | Residencial | Yes | 0-100kW
202501-NM25-03932 | 6.588 | Residencial | Yes | 0-100kW
2022-GD-15164 | 5.49 | Residencial | Yes | 0-100kW
2019-GD-00261 | 8.35 | Residencial | Yes | 0-100kW
202406-NM25-03630 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-25281 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-01698 | 5.25 | Residencial | Yes | 0-100kW
2023-GD-29654 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07853 | 5 | Residencial | Yes | 0-100kW
202504-NM25-05719 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-01747 | 6.785 | Residencial | Yes | 0-100kW
2023-GD-32940 | 9 | Residencial | Yes | 0-100kW
2021-GD-08078 | 4.43 | Residencial | Yes | 0-100kW
202310-NM25-00225 | 4.81 | Residencial | Yes | 0-100kW
2022-GD-13953 | 3.66 | Residencial | Yes | 0-100kW
202506-NM25-00145 | 23 | Residencial | Yes | 0-100kW
202401-NM25-04295 | 6 | Residencial | Yes | 0-100kW
202508-NM25-01306 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-00818 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01197 | 5.9 | Residencial | Yes | 0-100kW
202406-NM25-03107 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02242 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-00870 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35195 | 4.22 | Residencial | Yes | 0-100kW
202506-NM25-00149 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08742 | 5 | Residencial | Yes | 0-100kW
2023-GD-11396 | 5 | Residencial | Yes | 0-100kW
202501-NM25-04949 | 5.76 | Residencial | Yes | 0-100kW
202510-NM25-03525 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-03017 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-01768 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-02330 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-09537 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-03194 | 6 | Residencial | Yes | 0-100kW
2023-GD-08318 | 3.8 | Residencial | No | 0-100kW
16-2-0753 | 4.94 | Residencial | Yes | 0-100kW
2023-GD-31945 | 8 | Residencial | Yes | 0-100kW
202509-NM25-01546 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-00065 | 8 | Residencial | Yes | 0-100kW
2025-GD-00103 | 90 | Comercial | Yes | 0-100kW
2022-GD-23872 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18892 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12313 | 3 | Residencial | Yes | 0-100kW
202508-NM25-01069 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-22717 | 4.03 | Residencial | Yes | 0-100kW
202404-NM25-03777 | 4.392 | Residencial | Yes | 0-100kW
202501-NM25-02314 | 5.124 | Residencial | Yes | 0-100kW
2021-GD-10236 | 4.43 | Residencial | Yes | 0-100kW
2018-GD-00255 | 3.36 | Residencial | Yes | 0-100kW
202311-NM25-00117 | 4.026 | Residencial | Yes | 0-100kW
202403-NM25-02068 | 6 | Residencial | Yes | 0-100kW
2020-GD-01214 | 3 | Residencial | Yes | 0-100kW
202502-NM25-06057 | 7.6 | Residencial | Yes | 0-100kW
19-3-079 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-14879 | 5 | Residencial | Yes | 0-100kW
202404-NM25-02303 | 9.882 | Residencial | Yes | 0-100kW
202411-NM25-00505 | 4.026 | Residencial | Yes | 0-100kW
202407-NM25-02867 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-01822 | 10.672 | Residencial | Yes | 0-100kW
202508-NM25-03153 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-06972 | 3.84 | Residencial | Yes | 0-100kW
2020-GD-04169 | 6.19 | Residencial | Yes | 0-100kW
2022-GD-00945 | 5 | Residencial | Yes | 0-100kW
2023-GD-29874 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21757 | 5.86 | Residencial | Yes | 0-100kW
202408-NM25-00722 | 11.4 | Residencial | Yes | 0-100kW
202312-NM25-02175 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03593 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-02217 | 4.43 | Residencial | Yes | 0-100kW
202405-NM25-03676 | 1.83 | Residencial | Yes | 0-100kW
202510-NM25-02151 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-06518 | 6.91 | Residencial | Yes | 0-100kW
202411-NM25-03573 | 6.222 | Residencial | Yes | 0-100kW
2023-GD-08086 | 4.03 | Residencial | No | 0-100kW
202510-NM25-03644 | 11.4 | Residencial | Yes | 0-100kW
202504-NM25-05634 | 7.68 | Residencial | Yes | 0-100kW
202510-NM25-03343 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-01309 | 8.784 | Residencial | No | 0-100kW
2022-GD-21708 | 8.78 | Comercial | Yes | 0-100kW
16-2-1220 | 5.16 | Residencial | Yes | 0-100kW
202508-NM25-02374 | 12.68 | Residencial | Yes | 0-100kW
2021-GD-13446 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-32209 | 6.22 | Residencial | Yes | 0-100kW
202508-NM25-04544 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04410 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03472 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-11680 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-15344 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01590 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-38208 | 6.14 | Residencial | Yes | 0-100kW
202502-NM25-02228 | 9.216 | Residencial | Yes | 0-100kW
2022-GD-31849 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-38402 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-02922 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02380 | 7.6 | Residencial | Yes | 0-100kW
16-4-0517GD | 4.5 | Residencial | Yes | 0-100kW
2022-GD-21897 | 4.76 | Residencial | Yes | 0-100kW
202507-NM25-00022 | 8 | Residencial | Yes | 0-100kW
202503-NM25-01026 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-00284 | 8.35 | Residencial | Yes | 0-100kW
2023-GD-03244 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05693 | 12 | Residencial | Yes | 0-100kW
2022-GD-28625 | 6.59 | Residencial | Yes | 0-100kW
202509-NM25-05134 | 8 | Residencial | Yes | 0-100kW
202512-NM25-05638 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-00627 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13523 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-28237 | 14.27 | Residencial | Yes | 0-100kW
202402-NM25-00259 | 8.052 | Residencial | Yes | 0-100kW
202509-NM25-03059 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02148 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10635 | 9 | Residencial | Yes | 0-100kW
2018-GD-00753 | 5.76 | Residencial | Yes | 0-100kW
202511-NM25-02846 | 11.4 | Residencial | Yes | 0-100kW
202509-NM25-00776 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-20986 | 5.4 | Residencial | Yes | 0-100kW
202411-NM25-02397 | 9.15 | Residencial | Yes | 0-100kW
202512-NM25-05503 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-30461 | 4.99 | Residencial | Yes | 0-100kW
202406-NM25-03388 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-17536 | 8 | Residencial | Yes | 0-100kW
2022-GD-18558 | 6.95 | Residencial | Yes | 0-100kW
202412-NM25-03647 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21476 | 8.26 | Residencial | Yes | 0-100kW
2018-GD-00446 | 2.9 | Residencial | Yes | 0-100kW
2020-GD-00478 | 3.245 | Residencial | Yes | 0-100kW
14-9-074 | 9.9 | Residencial | Yes | 0-100kW
202402-NM25-01740 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05141 | 5 | Residencial | Yes | 0-100kW
2021-GD-09651 | 10.03 | Residencial | Yes | 0-100kW
2021-GD-06521 | 6.49 | Residencial | Yes | 0-100kW
202411-NM25-00794 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-22387 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-12906 | 5 | Residencial | Yes | 0-100kW
2022-GD-21273 | 3.29 | Residencial | Yes | 0-100kW
2023-GD-19882 | 3.84 | Residencial | Yes | 0-100kW
202401-NM25-00981 | 4.026 | Residencial | Yes | 0-100kW
14-5-0039A | 40 | Comercial | Yes | 0-100kW
202501-NM25-02349 | 17.49 | Comercial | Yes | 0-100kW
202312-NM25-03049 | 4.758 | Residencial | Yes | 0-100kW
2023-GD-32987 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-20419 | 8.42 | Residencial | Yes | 0-100kW
202404-NM25-03314 | 8.196 | Residencial | Yes | 0-100kW
2021-GD-13310 | 6.19 | Residencial | Yes | 0-100kW
202512-NM25-03602 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20357 | 7.69 | Residencial | Yes | 0-100kW
2022-GD-13071 | 4.39 | Residencial | Yes | 0-100kW
202505-NM25-02548 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-03073 | 15.2 | Residencial | Yes | 0-100kW
202504-NM25-04152 | 6.588 | Residencial | Yes | 0-100kW
202408-NM25-04064 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31750 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-01475 | 5 | Residencial | Yes | 0-100kW
2022-GD-04908 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-24367 | 4.03 | Residencial | Yes | 0-100kW
202509-NM25-00191 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-03867 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-04338 | 7.6 | Comercial | Yes | 0-100kW
202409-NM25-04248 | 9.6 | Residencial | Yes | 0-100kW
2022-GD-03410 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-09142 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-32090 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-03635 | 2.928 | Residencial | Yes | 0-100kW
202509-NM25-04504 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-01419 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07943 | 3.54 | Residencial | Yes | 0-100kW
2020-GD-02586 | 3.245 | Residencial | Yes | 0-100kW
11-1-514 | 7.92 | Residencial | Yes | 0-100kW
202508-NM25-05387 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-22823 | 4.39 | Residencial | Yes | 0-100kW
2018-GD-00876 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-00781 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-01656 | 4.13 | Residencial | Yes | 0-100kW
202407-NM25-01627 | 4.026 | Residencial | Yes | 0-100kW
202408-NM25-03970 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-02658 | 3.456 | Residencial | Yes | 0-100kW
2023-GD-22620 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05965 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-01793 | 9 | Residencial | Yes | 0-100kW
2023-GD-13200 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01925 | 9.216 | Residencial | Yes | 0-100kW
202401-NM25-00120 | 6.588 | Residencial | Yes | 0-100kW
202412-NM25-02153 | 24.09 | Residencial | Yes | 0-100kW
16-5-0690A | 4.3 | Residencial | Yes | 0-100kW
202410-NM25-04123 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-03198 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-00914 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02271 | 4.392 | Residencial | Yes | 0-100kW
2022-GD-05984 | 5.31 | Residencial | Yes | 0-100kW
202502-NM25-04453 | 20.862 | Residencial | No | 0-100kW
202408-NM25-03994 | 3.8 | Residencial | Yes | 0-100kW
202502-NM25-06228 | 11.4 | Residencial | Yes | 0-100kW
202505-NM25-03762 | 7.6 | Residencial | Yes | 0-100kW
13-1-108 | 96 | Comercial | Yes | 0-100kW
2023-GD-26408 | 12.08 | Residencial | Yes | 0-100kW
2022-GD-19670 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-04110 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-23298 | 6.9 | Residencial | Yes | 0-100kW
202407-NM25-03042 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14462 | 5 | Residencial | Yes | 0-100kW
2022-GD-16023 | 4.03 | Residencial | Yes | 0-100kW
202502-NM25-01651 | 13.176 | Residencial | Yes | 0-100kW
2023-GD-00470 | 5.12 | Residencial | Yes | 0-100kW
2022-GD-26396 | 4.99 | Residencial | Yes | 0-100kW
2022-GD-23819 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-26200 | 3.6 | Residencial | Yes | 0-100kW
2023-GD-27980 | 7.6 | Residencial | Yes | 0-100kW
16-2-0607 | 5.16 | Residencial | Yes | 0-100kW
2021-GD-09692 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-36916 | 8.05 | Residencial | Yes | 0-100kW
2021-GD-14639 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-16104 | 4.026 | Residencial | Yes | 0-100kW
2017-GD-03695 | 3.48 | Residencial | Yes | 0-100kW
2023-GD-29222 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-11912 | 5.01 | Residencial | Yes | 0-100kW
202503-NM25-04591 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-00672 | 8 | Residencial | Yes | 0-100kW
202401-NM25-03782 | 8 | Residencial | Yes | 0-100kW
202508-NM25-04228 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-22463 | 5 | Residencial | Yes | 0-100kW
2022-GD-18973 | 2.5 | Residencial | Yes | 0-100kW
2023-GD-31410 | 5 | Residencial | Yes | 0-100kW
2022-GD-12130 | 5 | Residencial | Yes | 0-100kW
2023-GD-08102 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15450 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-11183 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-29844 | 12 | Residencial | Yes | 0-100kW
2020-GD-04565 | 2.36 | Residencial | Yes | 0-100kW
2022-GD-17262 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-06713 | 5.76 | Residencial | Yes | 0-100kW
202506-NM25-01718 | 11.5 | Residencial | Yes | 0-100kW
202310-NM25-00138 | 5.18 | Residencial | Yes | 0-100kW
202502-NM25-06569 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05116 | 3.25 | Residencial | Yes | 0-100kW
202512-NM25-06011 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-04544 | 4.026 | Residencial | Yes | 0-100kW
202404-NM25-02680 | 4.758 | Industrial | Yes | 0-100kW
202508-NM25-05266 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-01940 | 6 | Residencial | Yes | 0-100kW
202512-NM25-04817 | 11.5 | Residencial | Yes | 0-100kW
14-7-300 | 3.6 | Residencial | Yes | 0-100kW
202401-NM25-03864 | 3.6 | Residencial | Yes | 0-100kW
202410-NM25-03282 | 7.6 | Residencial | Yes | 0-100kW
15-9-300 | 11.18 | Residencial | Yes | 0-100kW
202408-NM25-04776 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-02769 | 6.588 | Residencial | Yes | 0-100kW
202410-NM25-00223 | 3.072 | Residencial | Yes | 0-100kW
2022-GD-19927 | 5 | Residencial | Yes | 0-100kW
10-6-0220 | 2.4 | Residencial | Yes | 0-100kW
202401-NM25-00841 | 3.8 | Residencial | Yes | 0-100kW
202405-NM25-04055 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01552 | 5.54 | Residencial | Yes | 0-100kW
202510-NM25-00073 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-03225 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00099 | 8 | Residencial | Yes | 0-100kW
202508-NM25-03616 | 8.052 | Residencial | Yes | 0-100kW
202504-NM25-00879 | 5 | Residencial | Yes | 0-100kW
202501-NM25-02222 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-35662 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09218 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-30419 | 8 | Residencial | Yes | 0-100kW
202404-NM25-01588 | 12 | Residencial | Yes | 0-100kW
202510-NM25-02362 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00579 | 7.08 | Residencial | Yes | 0-100kW
2023-GD-01986 | 4.03 | Residencial | Yes | 0-100kW
202412-NM25-02843 | 12 | Residencial | Yes | 0-100kW
2022-GD-19096 | 6.95 | Residencial | Yes | 0-100kW
202505-NM25-05318 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-08261 | 5.61 | Residencial | Yes | 0-100kW
2022-GD-21280 | 5.49 | Residencial | Yes | 0-100kW
202502-NM25-04006 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-06237 | 11.5 | Comercial | Yes | 0-100kW
202412-NM25-04037 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01397 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04426 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-33428 | 5.49 | Residencial | Yes | 0-100kW
14-2-686 | 7 | Residencial | Yes | 0-100kW
202403-NM25-00013 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03352 | 9.62 | Residencial | Yes | 0-100kW
2022-GD-10262 | 3.66 | Residencial | Yes | 0-100kW
202409-NM25-03968 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05137 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-32262 | 15 | Residencial | Yes | 0-100kW
202411-NM25-01979 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06547 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-36804 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-00221 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-02441 | 2.36 | Residencial | Yes | 0-100kW
202410-NM25-00650 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22430 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-22313 | 5 | Residencial | Yes | 0-100kW
202506-NM25-01063 | 3.456 | Residencial | Yes | 0-100kW
2020-GD-05346 | 3.5 | Residencial | Yes | 0-100kW
202404-NM25-03590 | 7.6 | Residencial | Yes | 0-100kW
16-6-0236 | 5 | Residencial | Yes | 0-100kW
2021-GD-10792 | 6.14 | Residencial | Yes | 0-100kW
202406-NM25-00667 | 5 | Residencial | Yes | 0-100kW
202501-NM25-01999 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00141 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-02110 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-01959 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03210 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-17879 | 3.66 | Residencial | Yes | 0-100kW
202403-NM25-01839 | 10.614 | Residencial | Yes | 0-100kW
2023-GD-07641 | 4.03 | Residencial | Yes | 0-100kW
202511-NM25-03185 | 18.5 | Residencial | Yes | 0-100kW
202411-NM25-01208 | 5.856 | Residencial | Yes | 0-100kW
2018-GD-01090 | 12 | Residencial | Yes | 0-100kW
2022-GD-29911 | 3.8 | Residencial | Yes | 0-100kW
202406-NM25-02452 | 6.912 | Residencial | Yes | 0-100kW
2019-GD-00697 | 4.15 | Residencial | Yes | 0-100kW
2022-GD-25376 | 10.25 | Residencial | Yes | 0-100kW
2023-GD-36205 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11717 | 4.03 | Residencial | Yes | 0-100kW
2019-GD-02053 | 9.44 | Residencial | Yes | 0-100kW
2023-GD-09018 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-18972 | 8.45 | Residencial | Yes | 0-100kW
202401-NM25-04499 | 6.912 | Residencial | Yes | 0-100kW
2021-GD-13667 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-28822 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-02690 | 3.8 | Residencial | Yes | 0-100kW
2019-GD-02574 | 6.49 | Residencial | Yes | 0-100kW
15-1-274 | 4 | Residencial | Yes | 0-100kW
2021-GD-07586 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-10351 | 5 | Residencial | No | 0-100kW
202401-NM25-03110 | 6 | Residencial | Yes | 0-100kW
2022-GD-04913 | 9.88 | Residencial | Yes | 0-100kW
2023-GD-32877 | 6.8 | Residencial | Yes | 0-100kW
202412-NM25-02151 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-15536 | 5.12 | Residencial | Yes | 0-100kW
202511-NM25-02556 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-14866 | 3.66 | Residencial | Yes | 0-100kW
202408-NM25-02392 | 4.2 | Residencial | Yes | 0-100kW
202410-NM25-00049 | 4.608 | Residencial | Yes | 0-100kW
2023-GD-07869 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-00087 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-25481 | 7.38 | Residencial | Yes | 0-100kW
2023-GD-11222 | 5 | Residencial | No | 0-100kW
202502-NM25-03380 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-28070 | 5 | Residencial | Yes | 0-100kW
2023-GD-02314 | 4.39 | Residencial | Yes | 0-100kW
202502-NM25-04180 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21149 | 6.78 | Residencial | Yes | 0-100kW
15-2-676 | 3 | Residencial | Yes | 0-100kW
2022-GD-04220 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-17460 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-24187 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-02456 | 2.304 | Residencial | Yes | 0-100kW
2023-GD-19317 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03313 | 5.86 | Residencial | No | 0-100kW
2022-GD-13978 | 3.84 | Residencial | Yes | 0-100kW
2020-GD-06733 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-24415 | 8.42 | Residencial | Yes | 0-100kW
202403-NM25-00227 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01467 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-01179 | 7.6 | Residencial | Yes | 0-100kW
15-6-0200 | 4.3 | Residencial | Yes | 0-100kW
202505-NM25-04118 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02634 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-30845 | 7.6 | Residencial | No | 0-100kW
2022-GD-10530 | 5 | Residencial | Yes | 0-100kW
202408-NM25-04402 | 8 | Residencial | Yes | 0-100kW
202512-NM25-01274 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-01529 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-00270 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01356 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-04198 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-01828 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-29435 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-00594 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-25846 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-15843 | 2.66 | Residencial | Yes | 0-100kW
2022-GD-18481 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-02495 | 12.08 | Residencial | Yes | 0-100kW
2020-GD-09341 | 3.54 | Residencial | Yes | 0-100kW
202412-NM25-03932 | 9 | Residencial | Yes | 0-100kW
202510-NM25-00229 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-03869 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-20787 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-28232 | 4.61 | Residencial | Yes | 0-100kW
2023-GD-01715 | 5 | Residencial | Yes | 0-100kW
202501-NM25-03767 | 3.072 | Residencial | Yes | 0-100kW
2023-GD-09352 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-01260 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-18685 | 4.03 | Residencial | Yes | 0-100kW
202404-NM25-01889 | 3.84 | Residencial | Yes | 0-100kW
202504-NM25-03827 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-01090 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-06118 | 3 | Residencial | Yes | 0-100kW
202512-NM25-01182 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-03701 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-02676 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-02389 | 4.43 | Residencial | Yes | 0-100kW
202503-NM25-05549 | 6.144 | Residencial | Yes | 0-100kW
2023-GD-01534 | 6.59 | Residencial | Yes | 0-100kW
202507-NM25-00352 | 8 | Residencial | Yes | 0-100kW
2022-GD-01074 | 5.9 | Residencial | Yes | 0-100kW
202406-NM25-02041 | 2.928 | Residencial | Yes | 0-100kW
202404-NM25-00739 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-00798 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-32759 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-28265 | 6 | Residencial | Yes | 0-100kW
202406-NM25-00681 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02483 | 4.392 | Residencial | Yes | 0-100kW
2019-GD-01316 | 7.375 | Residencial | Yes | 0-100kW
2022-GD-28069 | 4.03 | Residencial | Yes | 0-100kW
202404-NM25-00596 | 10 | Residencial | Yes | 0-100kW
202507-NM25-05066 | 7.6 | Residencial | No | 0-100kW
202509-NM25-00906 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01716 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-05355 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-05200 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-05818 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-03654 | 5.76 | Residencial | Yes | 0-100kW
16-4-1154GD | 4 | Residencial | Yes | 0-100kW
2020-GD-06614 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-07553 | 5 | Residencial | Yes | 0-100kW
202404-NM25-03867 | 5.49 | Residencial | Yes | 0-100kW
2020-GD-00307 | 5.76 | Residencial | Yes | 0-100kW
202502-NM25-03015 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15254 | 12 | Residencial | Yes | 0-100kW
2023-GD-11214 | 9.57 | Residencial | Yes | 0-100kW
202511-NM25-00322 | 7.296 | Residencial | Yes | 0-100kW
2019-GD-02847 | 3.245 | Residencial | Yes | 0-100kW
202403-NM25-03017 | 6.588 | Residencial | Yes | 0-100kW
2023-GD-38445 | 3.8 | Residencial | Yes | 0-100kW
202410-NM25-02132 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04505 | 9 | Residencial | Yes | 0-100kW
2022-GD-22755 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-07490 | 5.31 | Residencial | Yes | 0-100kW
202405-NM25-02185 | 8.784 | Residencial | Yes | 0-100kW
202510-NM25-02329 | 12 | Residencial | Yes | 0-100kW
2023-GD-18431 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-28971 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01027 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-03655 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-27113 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-07684 | 11.35 | Comercial | Yes | 0-100kW
202507-NM25-04126 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34084 | 5.124 | Residencial | Yes | 0-100kW
202509-NM25-00817 | 8.448 | Residencial | Yes | 0-100kW
2017-GD-02596 | 4.945 | Residencial | Yes | 0-100kW
2022-GD-19492 | 5.49 | Residencial | Yes | 0-100kW
202404-NM25-01153 | 8.052 | Residencial | Yes | 0-100kW
2023-GD-01113 | 6.8 | Residencial | Yes | 0-100kW
202312-NM25-03431 | 8 | Residencial | Yes | 0-100kW
202510-NM25-01185 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02729 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13055 | 3.66 | Residencial | Yes | 0-100kW
202411-NM25-00138 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01279 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04689 | 4.992 | Residencial | Yes | 0-100kW
202409-NM25-03886 | 21.228 | Residencial | Yes | 0-100kW
202405-NM25-01521 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-04328 | 5.9 | Residencial | Yes | 0-100kW
2022-GD-18434 | 10.25 | Residencial | No | 0-100kW
202511-NM25-03528 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-26040 | 4.03 | Residencial | Yes | 0-100kW
14-3-829 | 5 | Residencial | Yes | 0-100kW
2023-GD-31227 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15874 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-07590 | 4.99 | Residencial | Yes | 0-100kW
2023-GD-32850 | 8.05 | Residencial | Yes | 0-100kW
2023-GD-07534 | 6.59 | Residencial | Yes | 0-100kW
2022-GD-27117 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-07624 | 5 | Residencial | Yes | 0-100kW
202406-NM25-03131 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04494 | 8 | Residencial | Yes | 0-100kW
15-6-0534 | 6.75 | Residencial | Yes | 0-100kW
202402-NM25-00824 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-01601 | 8 | Residencial | Yes | 0-100kW
2019-GD-01805 | 6.8 | Residencial | Yes | 0-100kW
202410-NM25-04864 | 8 | Residencial | Yes | 0-100kW
202503-NM25-01932 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-01780 | 7.68 | Residencial | Yes | 0-100kW
202412-NM25-00753 | 7.6 | Residencial | Yes | 0-100kW
16-7-0395 | 6.45 | Residencial | Yes | 0-100kW
2022-GD-23990 | 5.49 | Residencial | Yes | 0-100kW
202405-NM25-00643 | 13.6 | Residencial | Yes | 0-100kW
202501-NM25-05402 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17865 | 5.12 | Residencial | Yes | 0-100kW
202411-NM25-02695 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04271 | 11.71 | Residencial | Yes | 0-100kW
2023-GD-15046 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06333 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-13550 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-17682 | 6.59 | Residencial | Yes | 0-100kW
2022-GD-28578 | 5.86 | Residencial | Yes | 0-100kW
2021-GD-10426 | 5.9 | Residencial | Yes | 0-100kW
2020-GD-00108 | 18 | Residencial | Yes | 0-100kW
2023-GD-06507 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-04844 | 9.6 | Residencial | Yes | 0-100kW
2022-GD-01716 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-32468 | 3.5 | Residencial | Yes | 0-100kW
202502-NM25-01764 | 10 | Residencial | Yes | 0-100kW
202404-NM25-00843 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-25277 | 4.39 | Residencial | Yes | 0-100kW
2017-GD-01334 | 4.73 | Residencial | Yes | 0-100kW
202505-NM25-04224 | 3.8 | Residencial | Yes | 0-100kW
202410-NM25-02125 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22187 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-27332 | 3.8 | Residencial | Yes | 0-100kW
202401-NM25-03231 | 4.608 | Residencial | Yes | 0-100kW
10-6-0088 | 4.02 | Residencial | Yes | 0-100kW
2024-GD-00269 | 23.99 | Comercial | No | 0-100kW
2023-GD-03979 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-01562 | 9.6 | Residencial | Yes | 0-100kW
2021-GD-04588 | 4.43 | Residencial | Yes | 0-100kW
2020-GD-01096 | 3 | Residencial | Yes | 0-100kW
202407-NM25-03283 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03590 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-39178 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07817 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01863 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03242 | 4.992 | Residencial | Yes | 0-100kW
2022-GD-23130 | 4.03 | Residencial | Yes | 0-100kW
15-3-398 | 5.5 | Residencial | Yes | 0-100kW
2021-GD-13799 | 4.43 | Residencial | Yes | 0-100kW
202508-NM25-03887 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-03197 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-15150 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-28655 | 3.84 | Residencial | Yes | 0-100kW
202506-NM25-01867 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-08570 | 9.88 | Residencial | Yes | 0-100kW
2022-GD-18631 | 4.13 | Residencial | Yes | 0-100kW
202405-NM25-02158 | 8 | Residencial | Yes | 0-100kW
2022-GD-02957 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-39415 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-08124 | 3.24 | Residencial | Yes | 0-100kW
202501-NM25-01644 | 7.6 | Residencial | Yes | 0-100kW
202310-NM25-00333 | 8.052 | Residencial | Yes | 0-100kW
202402-NM25-01758 | 4.224 | Residencial | Yes | 0-100kW
2022-GD-01822 | 5.61 | Residencial | Yes | 0-100kW
2017-GD-01213 | 7.44 | Residencial | Yes | 0-100kW
202503-NM25-02761 | 9.15 | Residencial | Yes | 0-100kW
2020-GD-08712 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-00348 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-07383 | 5.12 | Residencial | Yes | 0-100kW
202511-NM25-03596 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-03890 | 6 | Residencial | Yes | 0-100kW
2020-GD-07870 | 5 | Residencial | Yes | 0-100kW
2023-GD-30126 | 5.86 | Residencial | Yes | 0-100kW
13-7-188 | 5 | Residencial | Yes | 0-100kW
202402-NM25-03467 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00512 | 3.84 | Residencial | Yes | 0-100kW
202501-NM25-04222 | 3.8 | Residencial | No | 0-100kW
202406-NM25-01694 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29515 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26163 | 7.32 | Residencial | Yes | 0-100kW
202510-NM25-03959 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-11790 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-38639 | 8 | Residencial | Yes | 0-100kW
2020-GD-02481 | 5.25 | Residencial | Yes | 0-100kW
202409-NM25-03034 | 15.2 | Residencial | Yes | 0-100kW
202409-NM25-01112 | 6.84 | Residencial | Yes | 0-100kW
2022-GD-28745 | 5.86 | Residencial | Yes | 0-100kW
2021-GD-08572 | 2.95 | Residencial | Yes | 0-100kW
202408-NM25-00184 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-35857 | 6 | Residencial | Yes | 0-100kW
2023-GD-16117 | 6.78 | Residencial | Yes | 0-100kW
202407-NM25-01335 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01049 | 23 | Residencial | Yes | 0-100kW
202502-NM25-03932 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21522 | 4.03 | Residencial | Yes | 0-100kW
202508-NM25-03011 | 11.056 | Residencial | Yes | 0-100kW
2023-GD-17519 | 6.95 | Residencial | Yes | 0-100kW
2020-GD-03979 | 6.75 | Residencial | Yes | 0-100kW
2023-GD-24818 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-09574 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-03711 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-28249 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-19043 | 5 | Residencial | Yes | 0-100kW
2023-GD-38867 | 3.66 | Residencial | Yes | 0-100kW
202405-NM25-01160 | 3 | Residencial | Yes | 0-100kW
2017-GD-00711 | 3 | Residencial | Yes | 0-100kW
202504-NM25-02427 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-04554 | 4.76 | Residencial | Yes | 0-100kW
202508-NM25-04361 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-33014 | 6 | Residencial | Yes | 0-100kW
2022-GD-15169 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-12888 | 7.67 | Residencial | Yes | 0-100kW
2021-GD-03488 | 4.72 | Residencial | Yes | 0-100kW
2021-GD-05319 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-09947 | 16.02 | Residencial | Yes | 0-100kW
202501-NM25-02806 | 8 | Residencial | Yes | 0-100kW
202507-NM25-03951 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-03415 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12192 | 4.03 | Residencial | No | 0-100kW
2023-GD-36693 | 7.6 | Comercial | No | 0-100kW
2020-GD-07472 | 4 | Residencial | Yes | 0-100kW
202505-NM25-04384 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-22957 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02585 | 5.124 | Residencial | Yes | 0-100kW
2023-GD-06896 | 8 | Residencial | Yes | 0-100kW
2023-GD-29074 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-03653 | 3.84 | Residencial | Yes | 0-100kW
202406-NM25-00598 | 8.784 | Residencial | Yes | 0-100kW
202511-NM25-00980 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-02140 | 3.072 | Residencial | Yes | 0-100kW
2019-GD-00461 | 11 | Comercial | Yes | 0-100kW
2021-GD-01287 | 6.8 | Residencial | Yes | 0-100kW
202412-NM25-01531 | 16.104 | Residencial | No | 0-100kW
202407-NM25-04439 | 15.2 | Residencial | Yes | 0-100kW
202412-NM25-01361 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-03285 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-01633 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-20497 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01127 | 4.72 | Residencial | Yes | 0-100kW
2020-GD-03936 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-22767 | 5.61 | Residencial | Yes | 0-100kW
202403-NM25-02864 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-28435 | 10.98 | Residencial | Yes | 0-100kW
2022-GD-07022 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-21820 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-22773 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-02360 | 6.8 | Residencial | Yes | 0-100kW
202510-NM25-00240 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-23048 | 4.39 | Residencial | Yes | 0-100kW
202404-NM25-04532 | 8.4 | Residencial | Yes | 0-100kW
2023-GD-23294 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11361 | 5.31 | Residencial | Yes | 0-100kW
2017-GD-02893 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-03770 | 4.43 | Residencial | Yes | 0-100kW
202410-NM25-02297 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-05831 | 8 | Residencial | Yes | 0-100kW
2023-GD-27489 | 5 | Residencial | Yes | 0-100kW
2023-GD-24204 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-30138 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20417 | 5.49 | Residencial | Yes | 0-100kW
202512-NM25-00253 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-02330 | 6.144 | Residencial | Yes | 0-100kW
2022-GD-16615 | 6.8 | Residencial | Yes | 0-100kW
202507-NM25-04210 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-05395 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-13344 | 6 | Residencial | Yes | 0-100kW
202505-NM25-02148 | 23 | Residencial | Yes | 0-100kW
2023-GD-04908 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-27867 | 6.59 | Residencial | Yes | 0-100kW
202510-NM25-01339 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03831 | 8 | Residencial | Yes | 0-100kW
2021-GD-14310 | 3.24 | Residencial | Yes | 0-100kW
202312-NM25-00595 | 4.758 | Residencial | Yes | 0-100kW
202412-NM25-02205 | 9 | Residencial | Yes | 0-100kW
2022-GD-24856 | 4.39 | Residencial | Yes | 0-100kW
202501-NM25-04061 | 6.588 | Residencial | Yes | 0-100kW
2023-GD-20533 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07373 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-21164 | 10.25 | Residencial | Yes | 0-100kW
202510-NM25-00342 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-01667 | 5.376 | Residencial | Yes | 0-100kW
2023-GD-12946 | 5 | Residencial | Yes | 0-100kW
2021-GD-03875 | 5.01 | Residencial | Yes | 0-100kW
202510-NM25-04136 | 11.5 | Residencial | Yes | 0-100kW
15-3-169 | 5 | Residencial | Yes | 0-100kW
202406-NM25-01676 | 9.855 | Residencial | Yes | 0-100kW
2022-GD-19928 | 8.42 | Residencial | Yes | 0-100kW
2017-GD-01527 | 6.88 | Residencial | Yes | 0-100kW
2022-GD-27602 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-02894 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00959 | 7.68 | Residencial | Yes | 0-100kW
2020-GD-01962 | 8.35 | Residencial | Yes | 0-100kW
202510-NM25-03682 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-02918 | 2.928 | Residencial | Yes | 0-100kW
202507-NM25-04551 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-06682 | 7.08 | Residencial | Yes | 0-100kW
202503-NM25-04938 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-00780 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-26835 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-18485 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02635 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-31746 | 5.76 | Residencial | Yes | 0-100kW
202312-NM25-03352 | 6 | Residencial | Yes | 0-100kW
202412-NM25-02326 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-02916 | 5.124 | Residencial | Yes | 0-100kW
202407-NM25-02532 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29898 | 7.6 | Residencial | Yes | 0-100kW
15-3-908 | 3.22 | Residencial | Yes | 0-100kW
202504-NM25-01776 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-34466 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-21199 | 7 | Residencial | Yes | 0-100kW
2021-GD-04727 | 3.84 | Residencial | Yes | 0-100kW
202507-NM25-00554 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-25295 | 8.78 | Residencial | Yes | 0-100kW
202405-NM25-01895 | 8 | Residencial | Yes | 0-100kW
2023-GD-22572 | 5 | Residencial | Yes | 0-100kW
2022-GD-08217 | 9.52 | Residencial | Yes | 0-100kW
2023-GD-04093 | 4.76 | Residencial | Yes | 0-100kW
202407-NM25-03745 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-00402 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-00450 | 11.5 | Residencial | No | 0-100kW
202502-NM25-06518 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07444 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-07801 | 5.76 | Residencial | Yes | 0-100kW
202512-NM25-04748 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-04663 | 8.8 | Residencial | Yes | 0-100kW
2022-GD-10791 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06105 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-08575 | 2.95 | Residencial | Yes | 0-100kW
2023-GD-17796 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36303 | 7.69 | Residencial | Yes | 0-100kW
2022-GD-16008 | 6.49 | Residencial | Yes | 0-100kW
202407-NM25-00601 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01600 | 3.8 | Residencial | Yes | 0-100kW
202502-NM25-02473 | 7.6 | Comercial | Yes | 0-100kW
202408-NM25-03299 | 3.8 | Residencial | Yes | 0-100kW
202404-NM25-01965 | 8 | Residencial | Yes | 0-100kW
2020-GD-02677 | 7 | Residencial | Yes | 0-100kW
202402-NM25-02716 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-04125 | 5.31 | Residencial | Yes | 0-100kW
2020-GD-07199 | 10 | Residencial | Yes | 0-100kW
202512-NM25-05169 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-00757 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-01846 | 6.222 | Residencial | Yes | 0-100kW
202408-NM25-00015 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02919 | 3.5 | Residencial | Yes | 0-100kW
202407-NM25-00285 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00803 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-22229 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-25814 | 5 | Residencial | Yes | 0-100kW
202504-NM25-04237 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-05926 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-08121 | 5 | Residencial | Yes | 0-100kW
202506-NM25-02834 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-05153 | 15 | Residencial | Yes | 0-100kW
202511-NM25-01433 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01532 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00481 | 7.38 | Residencial | Yes | 0-100kW
2023-GD-12302 | 4.03 | Residencial | Yes | 0-100kW
202411-NM25-00654 | 3.456 | Residencial | Yes | 0-100kW
2022-GD-22846 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-02183 | 7.97 | Residencial | Yes | 0-100kW
202512-NM25-04652 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-10440 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-09345 | 6.47 | Residencial | Yes | 0-100kW
202508-NM25-03497 | 3.84 | Residencial | Yes | 0-100kW
202501-NM25-05221 | 16.47 | Residencial | Yes | 0-100kW
202401-NM25-01088 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16233 | 3.54 | Residencial | Yes | 0-100kW
202504-NM25-05836 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-24481 | 9.6 | Residencial | Yes | 0-100kW
202505-NM25-00214 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04040 | 3.8 | Residencial | Yes | 0-100kW
202401-NM25-00293 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01949 | 5.124 | Residencial | Yes | 0-100kW
202407-NM25-04110 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02494 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-25005 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-17284 | 8.91 | Residencial | Yes | 0-100kW
202509-NM25-04095 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-03674 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-03218 | 11.21 | Residencial | Yes | 0-100kW
202502-NM25-05192 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-32136 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-00312 | 4.25 | Residencial | Yes | 0-100kW
2022-GD-23151 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-11439 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-00037 | 7.79 | Residencial | Yes | 0-100kW
2022-GD-15406 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-38634 | 20 | Comercial | Yes | 0-100kW
202410-NM25-00741 | 3.456 | Residencial | Yes | 0-100kW
202501-NM25-01629 | 5.856 | Residencial | Yes | 0-100kW
202410-NM25-04556 | 3 | Residencial | Yes | 0-100kW
2018-GD-01717 | 24 | Residencial | Yes | 0-100kW
2022-GD-22877 | 3.66 | Residencial | Yes | 0-100kW
2019-GD-01415 | 5.9 | Residencial | Yes | 0-100kW
202508-NM25-00070 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-01995 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18526 | 8.42 | Residencial | Yes | 0-100kW
202510-NM25-01468 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-00795 | 6.8 | Residencial | Yes | 0-100kW
202507-NM25-01478 | 4.608 | Residencial | Yes | 0-100kW
202412-NM25-01363 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-03149 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-01727 | 5.5 | Residencial | Yes | 0-100kW
202404-NM25-01080 | 4.026 | Residencial | Yes | 0-100kW
202404-NM25-03453 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02647 | 4.392 | Residencial | Yes | 0-100kW
2020-GD-06571 | 3.25 | Residencial | Yes | 0-100kW
202509-NM25-03066 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03121 | 6.528 | Residencial | Yes | 0-100kW
202503-NM25-04650 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-03744 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-16791 | 4.03 | Residencial | Yes | 0-100kW
15-4-0201GD | 4.25 | Residencial | Yes | 0-100kW
2022-GD-17932 | 5.12 | Residencial | Yes | 0-100kW
202507-NM25-04982 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-13700 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09605 | 5.49 | Residencial | Yes | 0-100kW
2017-GD-00484 | 3.44 | Residencial | Yes | 0-100kW
2023-GD-17691 | 8 | Residencial | Yes | 0-100kW
15-2-023 | 8.5 | Residencial | Yes | 0-100kW
202501-NM25-01402 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-19935 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-28059 | 6.95 | Comercial | Yes | 0-100kW
2023-GD-06388 | 4.39 | Residencial | Yes | 0-100kW
2017-GD-03454 | 11.31 | Residencial | Yes | 0-100kW
14-2-801 | 7.5 | Residencial | Yes | 0-100kW
202512-NM25-05294 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14966 | 4.8 | Residencial | Yes | 0-100kW
202408-NM25-04252 | 8 | Residencial | No | 0-100kW
202502-NM25-04499 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-15327 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-34788 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-25459 | 6.91 | Residencial | Yes | 0-100kW
202502-NM25-01137 | 24.7 | Residencial | Yes | 0-100kW
202404-NM25-00402 | 12 | Residencial | Yes | 0-100kW
16-3-147 | 4.52 | Residencial | Yes | 0-100kW
202501-NM25-01993 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06138 | 2.93 | Residencial | Yes | 0-100kW
2022-GD-25728 | 12.08 | Residencial | Yes | 0-100kW
202312-NM25-01714 | 8 | Residencial | Yes | 0-100kW
202506-NM25-04094 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-02207 | 6.3 | Residencial | Yes | 0-100kW
2017-GD-03467 | 5.375 | Residencial | Yes | 0-100kW
2023-GD-36241 | 3.8 | Residencial | Yes | 0-100kW
202505-NM25-01887 | 8 | Residencial | Yes | 0-100kW
2021-GD-08880 | 3.54 | Residencial | Yes | 0-100kW
202411-NM25-01691 | 10 | Residencial | Yes | 0-100kW
202510-NM25-01276 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-30745 | 3.84 | Residencial | Yes | 0-100kW
202406-NM25-02267 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-27342 | 7.6 | Comercial | Yes | 0-100kW
2023-GD-17655 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-13815 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-00354 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-21600 | 11.35 | Residencial | Yes | 0-100kW
202402-NM25-03382 | 5 | Residencial | Yes | 0-100kW
202310-NM25-00332 | 8.052 | Residencial | Yes | 0-100kW
202408-NM25-02705 | 3.8 | Residencial | Yes | 0-100kW
202409-NM25-01864 | 3.84 | Residencial | Yes | 0-100kW
202502-NM25-05050 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-00813 | 5.49 | Residencial | Yes | 0-100kW
202502-NM25-01162 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02932 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01578 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00835 | 5.3 | Comercial | Yes | 0-100kW
202504-NM25-03266 | 2.928 | Residencial | Yes | 0-100kW
202408-NM25-00939 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-09454 | 15.2 | Residencial | Yes | 0-100kW
2020-GD-01399 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-01152 | 5.76 | Residencial | Yes | 0-100kW
2020-GD-02883 | 3.5 | Residencial | Yes | 0-100kW
2022-GD-04216 | 5 | Residencial | Yes | 0-100kW
2018-GD-01173 | 6.24 | Residencial | Yes | 0-100kW
2022-GD-25049 | 5.49 | Comercial | Yes | 0-100kW
2022-GD-09886 | 5 | Residencial | Yes | 0-100kW
2022-GD-13531 | 6 | Residencial | Yes | 0-100kW
202503-NM25-05172 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-32679 | 5.12 | Residencial | Yes | 0-100kW
14-1-300 | 5 | Residencial | Yes | 0-100kW
2017-GD-02362 | 3.75 | Residencial | Yes | 0-100kW
2023-GD-25846 | 20.86 | Residencial | No | 0-100kW
2017-GD-00918 | 3 | Residencial | Yes | 0-100kW
2022-GD-00782 | 5.9 | Residencial | Yes | 0-100kW
202405-NM25-02751 | 8 | Residencial | Yes | 0-100kW
2022-GD-03337 | 6.22 | Residencial | Yes | 0-100kW
202505-NM25-00151 | 5.76 | Residencial | Yes | 0-100kW
2021-GD-02878 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-03961 | 4.76 | Residencial | Yes | 0-100kW
202402-NM25-02112 | 9.882 | Residencial | No | 0-100kW
2017-GD-02161 | 3.01 | Residencial | Yes | 0-100kW
202502-NM25-04566 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-03969 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-07752 | 5.61 | Residencial | Yes | 0-100kW
15-7-1020 | 4.25 | Residencial | Yes | 0-100kW
202509-NM25-02038 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36148 | 12.81 | Residencial | Yes | 0-100kW
2022-GD-04817 | 9.6 | Residencial | Yes | 0-100kW
202508-NM25-00178 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-03095 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-15278 | 6.49 | Residencial | Yes | 0-100kW
202406-NM25-02750 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-22903 | 15.37 | Residencial | Yes | 0-100kW
202509-NM25-03945 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-00747 | 3.245 | Residencial | Yes | 0-100kW
202501-NM25-02993 | 6.6 | Residencial | Yes | 0-100kW
2023-GD-10196 | 8.26 | Residencial | Yes | 0-100kW
202508-NM25-04608 | 6.912 | Residencial | Yes | 0-100kW
2022-GD-25464 | 4.03 | Residencial | Yes | 0-100kW
202507-NM25-02025 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-03080 | 4.026 | Residencial | Yes | 0-100kW
202401-NM25-04666 | 13.6 | Residencial | Yes | 0-100kW
202504-NM25-02499 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-01557 | 2.15 | Residencial | Yes | 0-100kW
2023-GD-38798 | 9.52 | Residencial | Yes | 0-100kW
2022-GD-09616 | 6 | Residencial | Yes | 0-100kW
2022-GD-26481 | 6.95 | Residencial | Yes | 0-100kW
2019-GD-00369 | 7 | Residencial | Yes | 0-100kW
2020-GD-05409 | 10.03 | Residencial | Yes | 0-100kW
2021-GD-01852 | 5.01 | Residencial | Yes | 0-100kW
2020-GD-03249 | 4 | Residencial | Yes | 0-100kW
202501-NM25-02151 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-20992 | 7.32 | Residencial | Yes | 0-100kW
2019-GD-00657 | 5 | Residencial | Yes | 0-100kW
202503-NM25-02067 | 3.8 | Residencial | No | 0-100kW
2023-GD-38165 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-00781 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02087 | 4.22 | Residencial | Yes | 0-100kW
202403-NM25-01587 | 5.124 | Residencial | Yes | 0-100kW
202408-NM25-04542 | 6.8 | Residencial | Yes | 0-100kW
202501-NM25-01542 | 15.75 | Residencial | Yes | 0-100kW
202509-NM25-01147 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-03718 | 3 | Residencial | Yes | 0-100kW
202502-NM25-00348 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14614 | 36.58 | Comercial | Yes | 0-100kW
202411-NM25-01417 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02615 | 2.928 | Residencial | Yes | 0-100kW
2019-GD-03065 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-05036 | 8.05 | Residencial | Yes | 0-100kW
2017-GD-03280 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01553 | 6.8 | Residencial | Yes | 0-100kW
202501-NM25-01084 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-00244 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-00953 | 8.418 | Residencial | Yes | 0-100kW
202409-NM25-02071 | 11.4 | Residencial | Yes | 0-100kW
2022-GD-03546 | 7.38 | Residencial | Yes | 0-100kW
202506-NM25-04232 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-17878 | 2.66 | Residencial | Yes | 0-100kW
2023-GD-07502 | 5.86 | Residencial | Yes | 0-100kW
2021-GD-14241 | 5.01 | Residencial | Yes | 0-100kW
202508-NM25-05364 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-32303 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03692 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-05153 | 7.38 | Residencial | Yes | 0-100kW
202403-NM25-03448 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-09462 | 7.38 | Residencial | Yes | 0-100kW
2023-GD-27866 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00804 | 8.052 | Residencial | Yes | 0-100kW
202505-NM25-00323 | 12 | Residencial | Yes | 0-100kW
2022-GD-23879 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-04134 | 12 | Residencial | Yes | 0-100kW
2023-GD-34139 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-10310 | 5 | Residencial | Yes | 0-100kW
202507-NM25-03011 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-00671 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32933 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04913 | 5.76 | Residencial | Yes | 0-100kW
202412-NM25-00514 | 24.888 | Comercial | Yes | 0-100kW
202507-NM25-02528 | 3.84 | Residencial | Yes | 0-100kW
202511-NM25-00839 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-07243 | 6.6 | Residencial | Yes | 0-100kW
2023-GD-22291 | 8 | Residencial | Yes | 0-100kW
202403-NM25-02101 | 12 | Residencial | Yes | 0-100kW
2023-GD-20123 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15650 | 5 | Residencial | Yes | 0-100kW
202405-NM25-03157 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-24501 | 5.12 | Residencial | Yes | 0-100kW
202409-NM25-03231 | 13.176 | Residencial | Yes | 0-100kW
2022-GD-04438 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-07686 | 2.93 | Residencial | Yes | 0-100kW
2017-GD-00354 | 4.515 | Residencial | Yes | 0-100kW
202508-NM25-03561 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-03837 | 8.784 | Residencial | Yes | 0-100kW
2022-GD-12943 | 3.24 | Residencial | Yes | 0-100kW
2023-GD-35001 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-04080 | 6.8 | Residencial | Yes | 0-100kW
2023-GD-27316 | 4.61 | Residencial | Yes | 0-100kW
2021-GD-01604 | 5.5 | Residencial | Yes | 0-100kW
2023-GD-03803 | 10.03 | Residencial | Yes | 0-100kW
202404-NM25-01025 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12369 | 8.56 | Residencial | Yes | 0-100kW
202405-NM25-02669 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-05257 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22894 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-07950 | 3.29 | Residencial | Yes | 0-100kW
202312-NM25-02257 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-03397 | 5.52 | Residencial | Yes | 0-100kW
202504-NM25-03460 | 11.5 | Residencial | Yes | 0-100kW
202401-NM25-00019 | 8 | Residencial | Yes | 0-100kW
202410-NM25-02881 | 15.2 | Residencial | Yes | 0-100kW
202510-NM25-01768 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-01051 | 4.224 | Residencial | Yes | 0-100kW
2020-GD-03998 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-23304 | 8 | Residencial | Yes | 0-100kW
2020-GD-06718 | 4.5 | Residencial | Yes | 0-100kW
2023-GD-32781 | 15.2 | Residencial | Yes | 0-100kW
202408-NM25-02313 | 9.15 | Residencial | Yes | 0-100kW
202505-NM25-02234 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03826 | 15 | Residencial | Yes | 0-100kW
202508-NM25-00592 | 4.224 | Residencial | Yes | 0-100kW
2020-GD-04239 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-31422 | 4.61 | Residencial | Yes | 0-100kW
202507-NM25-01284 | 7.296 | Residencial | Yes | 0-100kW
2022-GD-08347 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-13778 | 5.01 | Residencial | Yes | 0-100kW
202503-NM25-03620 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34778 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-00604 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-18214 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-04496 | 3.54 | Residencial | Yes | 0-100kW
202508-NM25-01363 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-05767 | 5.31 | Residencial | Yes | 0-100kW
202510-NM25-02111 | 12.672 | Residencial | Yes | 0-100kW
2021-GD-13903 | 6.49 | Residencial | Yes | 0-100kW
202311-NM25-00181 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-15410 | 6.8 | Residencial | Yes | 0-100kW
16-3-873 | 3 | Residencial | Yes | 0-100kW
2021-GD-08337 | 8.35 | Residencial | Yes | 0-100kW
202504-NM25-03740 | 4.992 | Comercial | Yes | 0-100kW
2020-GD-07886 | 4.13 | Residencial | Yes | 0-100kW
2022-GD-26526 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24101 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-34044 | 8 | Residencial | Yes | 0-100kW
2021-GD-14968 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-04816 | 8.85 | Residencial | Yes | 0-100kW
2022-GD-08962 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-13164 | 4.03 | Residencial | Yes | 0-100kW
202510-NM25-03604 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-05193 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16526 | 8 | Residencial | No | 0-100kW
2019-GD-02814 | 5.605 | Residencial | Yes | 0-100kW
202402-NM25-00859 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-24791 | 15 | Residencial | Yes | 0-100kW
202410-NM25-02031 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-27088 | 7.97 | Residencial | Yes | 0-100kW
2021-GD-09579 | 3.84 | Residencial | Yes | 0-100kW
202501-NM25-03854 | 15 | Residencial | Yes | 0-100kW
202407-NM25-00861 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06728 | 4.13 | Residencial | Yes | 0-100kW
202507-NM25-04918 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-03461 | 5 | Residencial | Yes | 0-100kW
202507-NM25-00585 | 7.6 | Residencial | No | 0-100kW
202405-NM25-00831 | 5 | Residencial | Yes | 0-100kW
202401-NM25-03332 | 8 | Residencial | Yes | 0-100kW
202511-NM25-01781 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-00813 | 3.66 | Residencial | Yes | 0-100kW
202411-NM25-03228 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-05640 | 6.95 | Residencial | Yes | 0-100kW
202501-NM25-03133 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-03435 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-01236 | 3.66 | Residencial | Yes | 0-100kW
202403-NM25-01590 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33944 | 4.99 | Residencial | Yes | 0-100kW
202410-NM25-01832 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00988 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19009 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02613 | 13.66 | Residencial | Yes | 0-100kW
202504-NM25-00180 | 0 | Residencial | Yes | 0-100kW
2023-GD-15266 | 8.42 | Residencial | Yes | 0-100kW
2019-GD-02924 | 8.35 | Residencial | Yes | 0-100kW
202410-NM25-00166 | 2.688 | Residencial | Yes | 0-100kW
2022-GD-09311 | 6 | Residencial | Yes | 0-100kW
202409-NM25-04020 | 11.14 | Residencial | Yes | 0-100kW
2017-GD-03004 | 4 | Residencial | Yes | 0-100kW
2017-GD-01472 | 6.02 | Residencial | Yes | 0-100kW
2022-GD-19694 | 6.8 | Comercial | Yes | 0-100kW
2023-GD-09809 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-30476 | 3.84 | Residencial | Yes | 0-100kW
202503-NM25-05877 | 8 | Residencial | Yes | 0-100kW
2023-GD-25679 | 7.69 | Residencial | Yes | 0-100kW
202407-NM25-02582 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07222 | 4.76 | Residencial | Yes | 0-100kW
202309-NM25-00063 | 3.7 | Residencial | Yes | 0-100kW
202508-NM25-04520 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-00941 | 5.76 | Residencial | Yes | 0-100kW
202408-NM25-02374 | 8 | Residencial | Yes | 0-100kW
202502-NM25-04527 | 11.43 | Residencial | Yes | 0-100kW
2022-GD-16952 | 10.25 | Residencial | Yes | 0-100kW
2020-GD-09614 | 4.43 | Residencial | Yes | 0-100kW
202403-NM25-00508 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-02957 | 6.59 | Residencial | Yes | 0-100kW
2021-GD-05375 | 4.72 | Residencial | Yes | 0-100kW
202504-NM25-02930 | 5.76 | Residencial | Yes | 0-100kW
202409-NM25-00200 | 15 | Residencial | Yes | 0-100kW
202406-NM25-00618 | 8 | Residencial | Yes | 0-100kW
202407-NM25-04203 | 4.026 | Residencial | Yes | 0-100kW
2021-GD-06454 | 5.31 | Residencial | Yes | 0-100kW
202406-NM25-01861 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-00174 | 2.75 | Residencial | Yes | 0-100kW
2023-GD-35533 | 8 | Residencial | Yes | 0-100kW
2022-GD-19917 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-35422 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01991 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-01442 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-01140 | 4.392 | Residencial | Yes | 0-100kW
2017-GD-02299 | 5.375 | Residencial | Yes | 0-100kW
202401-NM25-00488 | 2.1 | Residencial | No | 0-100kW
202405-NM25-02370 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19751 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-00817 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-07018 | 3.29 | Residencial | Yes | 0-100kW
2021-GD-07967 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-00007 | 24 | Residencial | Yes | 0-100kW
202509-NM25-04788 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-03320 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-05914 | 7.08 | Residencial | Yes | 0-100kW
202403-NM25-03442 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29703 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06574 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-09178 | 9 | Residencial | Yes | 0-100kW
17-3-018 | 3 | Residencial | Yes | 0-100kW
202409-NM25-03345 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13427 | 48 | Comercial | Yes | 0-100kW
202507-NM25-03230 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-01238 | 7.6 | Residencial | Yes | 0-100kW
15-2-668 | 6 | Residencial | Yes | 0-100kW
202403-NM25-01309 | 9.516 | Residencial | Yes | 0-100kW
2018-GD-01828 | 7.03 | Residencial | Yes | 0-100kW
2021-GD-03359 | 6.49 | Residencial | Yes | 0-100kW
202503-NM25-05473 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-02533 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-03588 | 8 | Residencial | Yes | 0-100kW
202410-NM25-03456 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13623 | 7.32 | Residencial | Yes | 0-100kW
2021-GD-07447 | 4.25 | Residencial | Yes | 0-100kW
2020-GD-04289 | 9 | Residencial | Yes | 0-100kW
202506-NM25-01042 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-04681 | 5.816 | Residencial | Yes | 0-100kW
2023-GD-24676 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-32029 | 9.88 | Residencial | Yes | 0-100kW
202501-NM25-03714 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-06763 | 4.43 | Residencial | No | 0-100kW
2022-GD-10078 | 2.5 | Residencial | Yes | 0-100kW
202509-NM25-05162 | 10.752 | Residencial | Yes | 0-100kW
202506-NM25-03537 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06905 | 3.24 | Residencial | Yes | 0-100kW
202402-NM25-03198 | 7.6 | Residencial | No | 0-100kW
202402-NM25-03709 | 4.392 | Residencial | Yes | 0-100kW
202505-NM25-01654 | 8 | Residencial | Yes | 0-100kW
202512-NM25-03594 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-03041 | 11.5 | Residencial | Yes | 0-100kW
14-3-374 | 5.16 | Residencial | Yes | 0-100kW
2023-GD-08526 | 9.15 | Residencial | Yes | 0-100kW
2021-GD-09480 | 4.43 | Residencial | Yes | 0-100kW
2019-GD-02038 | 9 | Residencial | Yes | 0-100kW
202402-NM25-01942 | 8 | Residencial | Yes | 0-100kW
2021-GD-08978 | 5.01 | Residencial | Yes | 0-100kW
202403-NM25-00322 | 3.84 | Residencial | Yes | 0-100kW
202404-NM25-00735 | 8 | Residencial | Yes | 0-100kW
202504-NM25-00758 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-00473 | 5 | Residencial | No | 0-100kW
2022-GD-26502 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-00892 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-06654 | 5.86 | Residencial | Yes | 0-100kW
202502-NM25-06687 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19246 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-06240 | 10.98 | Residencial | Yes | 0-100kW
2018-GD-01170 | 4 | Residencial | Yes | 0-100kW
202401-NM25-01226 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-01011 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03064 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01665 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-02167 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-03151 | 15 | Residencial | Yes | 0-100kW
2023-GD-01510 | 4.61 | Residencial | Yes | 0-100kW
202405-NM25-00789 | 15.2 | Residencial | Yes | 0-100kW
202412-NM25-03349 | 12.444 | Residencial | Yes | 0-100kW
2022-GD-21984 | 5 | Residencial | Yes | 0-100kW
202512-NM25-00168 | 11.5 | Residencial | Yes | 0-100kW
15-2-811 | 3.87 | Residencial | Yes | 0-100kW
202510-NM25-01509 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02292 | 9 | Residencial | Yes | 0-100kW
2023-GD-28405 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-02329 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-02515 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-19689 | 6.59 | Residencial | Yes | 0-100kW
2022-GD-12071 | 6.91 | Residencial | Yes | 0-100kW
202504-NM25-02400 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20529 | 4.76 | Comercial | Yes | 0-100kW
202503-NM25-05375 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-37194 | 9 | Residencial | Yes | 0-100kW
202407-NM25-00504 | 7.16 | Residencial | Yes | 0-100kW
202408-NM25-03760 | 15.2 | Residencial | Yes | 0-100kW
202401-NM25-03965 | 5 | Residencial | Yes | 0-100kW
15-1-1035 | 5 | Residencial | No | 0-100kW
2022-GD-11214 | 4.03 | Residencial | No | 0-100kW
2018-GD-01021 | 6.8 | Residencial | Yes | 0-100kW
2019-GD-01565 | 7.06 | Residencial | Yes | 0-100kW
202509-NM25-03342 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-01061 | 7.6 | Comercial | Yes | 0-100kW
2022-GD-00303 | 3.54 | Residencial | Yes | 0-100kW
202501-NM25-02074 | 7.49 | Residencial | Yes | 0-100kW
202508-NM25-01005 | 6.912 | Residencial | Yes | 0-100kW
202506-NM25-02449 | 8 | Residencial | Yes | 0-100kW
2022-GD-00423 | 25.2 | Comercial | Yes | 0-100kW
2022-GD-32575 | 4.03 | Residencial | Yes | 0-100kW
202312-NM25-01543 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-05962 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02782 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14558 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-07264 | 5.01 | Residencial | Yes | 0-100kW
14-1-404 | 14 | Residencial | Yes | 0-100kW
202406-NM25-01804 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-00128 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-00190 | 8 | Residencial | Yes | 0-100kW
202408-NM25-01978 | 11.992 | Residencial | Yes | 0-100kW
2020-GD-03520 | 5 | Residencial | Yes | 0-100kW
2022-GD-32767 | 4.03 | Residencial | Yes | 0-100kW
14-4-0342GD | 8.17 | Comercial | No | 0-100kW
16-2-0435 | 4.3 | Residencial | Yes | 0-100kW
202407-NM25-03012 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-33145 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-05495 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-02521 | 6.6 | Residencial | Yes | 0-100kW
202410-NM25-02909 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04517 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-02499 | 4.392 | Residencial | Yes | 0-100kW
202506-NM25-04120 | 11.5 | Residencial | Yes | 0-100kW
16-6-0226 | 6.75 | Residencial | Yes | 0-100kW
202508-NM25-05608 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-30644 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-00149 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-01003 | 15.2 | Residencial | Yes | 0-100kW
202506-NM25-02093 | 11.5 | Residencial | Yes | 0-100kW
16-4-0813GD | 5 | Residencial | Yes | 0-100kW
202508-NM25-00202 | 23 | Residencial | Yes | 0-100kW
2023-GD-33036 | 3.8 | Residencial | Yes | 0-100kW
202402-NM25-02606 | 6 | Residencial | Yes | 0-100kW
2021-GD-10676 | 3.54 | Residencial | Yes | 0-100kW
202311-NM25-00435 | 8.052 | Residencial | Yes | 0-100kW
2023-GD-04695 | 4.3 | Residencial | Yes | 0-100kW
2020-GD-05385 | 4.25 | Residencial | Yes | 0-100kW
202509-NM25-02994 | 15.3 | Residencial | Yes | 0-100kW
2022-GD-09297 | 7.67 | Residencial | No | 0-100kW
2019-GD-01208 | 4.72 | Residencial | Yes | 0-100kW
202411-NM25-03488 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01794 | 15 | Residencial | Yes | 0-100kW
202507-NM25-05198 | 4.224 | Residencial | No | 0-100kW
202503-NM25-01428 | 10.614 | Residencial | Yes | 0-100kW
2022-GD-05832 | 14.64 | Residencial | Yes | 0-100kW
2023-GD-02018 | 9.6 | Residencial | Yes | 0-100kW
2022-GD-02297 | 3.54 | Residencial | Yes | 0-100kW
202511-NM25-00329 | 11.5 | Residencial | Yes | 0-100kW
202508-NM25-04148 | 9.984 | Residencial | Yes | 0-100kW
202403-NM25-02532 | 10.248 | Residencial | Yes | 0-100kW
2022-GD-24246 | 6 | Residencial | Yes | 0-100kW
202412-NM25-00918 | 15.2 | Residencial | Yes | 0-100kW
202511-NM25-03829 | 7.6 | Residencial | Yes | 0-100kW
2025-GD-00132 | 42 | Comercial | No | 0-100kW
2022-GD-16725 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-27499 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-15830 | 4.13 | Comercial | Yes | 0-100kW
202506-NM25-01078 | 7.6 | Residencial | Yes | 0-100kW
2024-GD-00014 | 23.76 | Residencial | Yes | 0-100kW
202404-NM25-01884 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05034 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-22358 | 5.86 | Residencial | Yes | 0-100kW
202405-NM25-02963 | 3.8 | Residencial | Yes | 0-100kW
202412-NM25-00954 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21240 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22382 | 6.59 | Residencial | Yes | 0-100kW
202507-NM25-00373 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-19506 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-00642 | 6.6 | Residencial | Yes | 0-100kW
202406-NM25-03436 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-38916 | 9.22 | Residencial | Yes | 0-100kW
202410-NM25-01391 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-39081 | 3.29 | Residencial | Yes | 0-100kW
202505-NM25-02130 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-01229 | 3 | Residencial | Yes | 0-100kW
202312-NM25-01206 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-02751 | 6 | Residencial | Yes | 0-100kW
2022-GD-32313 | 4.76 | Residencial | Yes | 0-100kW
202502-NM25-02657 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-01995 | 4.03 | Residencial | Yes | 0-100kW
202506-NM25-03463 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29570 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-08057 | 4.43 | Residencial | Yes | 0-100kW
202404-NM25-03674 | 3.66 | Residencial | Yes | 0-100kW
202406-NM25-02364 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00573 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20641 | 6.95 | Residencial | Yes | 0-100kW
202503-NM25-01830 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-03971 | 5.76 | Residencial | Yes | 0-100kW
202402-NM25-02443 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-02497 | 15.36 | Residencial | Yes | 0-100kW
202412-NM25-01311 | 6 | Residencial | Yes | 0-100kW
202502-NM25-05969 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-02134 | 6.25 | Residencial | Yes | 0-100kW
2022-GD-24135 | 3.24 | Residencial | Yes | 0-100kW
2020-GD-03689 | 6.8 | Residencial | Yes | 0-100kW
2021-GD-03298 | 3.24 | Residencial | Yes | 0-100kW
202509-NM25-04222 | 7.6 | Residencial | Yes | 0-100kW
202310-NM25-00246 | 15.2 | Residencial | Yes | 0-100kW
202404-NM25-00071 | 7.6 | Residencial | Yes | 0-100kW
15-9-459 | 2.58 | Residencial | Yes | 0-100kW
2021-GD-02738 | 8.26 | Residencial | Yes | 0-100kW
202505-NM25-04126 | 11.5 | Residencial | No | 0-100kW
2023-GD-05376 | 6.8 | Comercial | Yes | 0-100kW
202411-NM25-03445 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04517 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-03014 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01459 | 8 | Residencial | Yes | 0-100kW
202404-NM25-00004 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-02155 | 4.392 | Residencial | Yes | 0-100kW
2022-GD-17867 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-07154 | 4.03 | Residencial | Yes | 0-100kW
202507-NM25-00210 | 10 | Residencial | Yes | 0-100kW
2021-GD-13299 | 8.26 | Residencial | Yes | 0-100kW
202509-NM25-02404 | 3.8 | Residencial | Yes | 0-100kW
202502-NM25-04196 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01639 | 5.01 | Residencial | Yes | 0-100kW
202409-NM25-00396 | 6.588 | Residencial | Yes | 0-100kW
202505-NM25-03947 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-06863 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-00465 | 8 | Residencial | Yes | 0-100kW
2022-GD-20766 | 4.03 | Residencial | Yes | 0-100kW
202508-NM25-03869 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-00452 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30475 | 6 | Comercial | Yes | 0-100kW
202312-NM25-03350 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-31412 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-00911 | 3.75 | Residencial | Yes | 0-100kW
2020-GD-02194 | 10.03 | Residencial | Yes | 0-100kW
2020-GD-06764 | 13.54 | Residencial | Yes | 0-100kW
2023-GD-22956 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-00175 | 10.03 | Residencial | Yes | 0-100kW
202410-NM25-00491 | 2.928 | Residencial | Yes | 0-100kW
2022-GD-17319 | 5.12 | Residencial | Yes | 0-100kW
202410-NM25-01534 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00038 | 9 | Residencial | Yes | 0-100kW
202502-NM25-04569 | 15.372 | Residencial | Yes | 0-100kW
202505-NM25-03338 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34924 | 6 | Residencial | Yes | 0-100kW
2021-GD-10940 | 10.91 | Residencial | Yes | 0-100kW
202502-NM25-01201 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-15719 | 6 | Residencial | Yes | 0-100kW
2023-GD-10523 | 3 | Residencial | Yes | 0-100kW
2017-GD-01607 | 4.945 | Residencial | Yes | 0-100kW
2022-GD-03272 | 3.24 | Residencial | Yes | 0-100kW
2019-GD-00340 | 8.53 | Residencial | Yes | 0-100kW
202402-NM25-03193 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32223 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-01591 | 18 | Residencial | Yes | 0-100kW
2022-GD-12432 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-14524 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-09254 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-21472 | 5.49 | Residencial | Yes | 0-100kW
202408-NM25-00779 | 5 | Residencial | Yes | 0-100kW
2024-GD-00091 | 6.8 | Residencial | Yes | 0-100kW
2021-GD-09620 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-16433 | 6.49 | Residencial | Yes | 0-100kW
202504-NM25-02720 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03635 | 11.5 | Residencial | Yes | 0-100kW
15-6-0507 | 11.44 | Residencial | Yes | 0-100kW
2022-GD-00888 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-11931 | 5 | Residencial | No | 0-100kW
202404-NM25-03678 | 8 | Residencial | Yes | 0-100kW
2022-GD-05898 | 3.8 | Residencial | Yes | 0-100kW
14-5-0190A | 3 | Residencial | Yes | 0-100kW
202412-NM25-01188 | 13.6 | Residencial | Yes | 0-100kW
202409-NM25-01380 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-04058 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-30246 | 3.8 | Residencial | Yes | 0-100kW
202412-NM25-02829 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05434 | 16.84 | Residencial | No | 0-100kW
2021-GD-07344 | 5.01 | Residencial | Yes | 0-100kW
2023-GD-24674 | 9 | Residencial | Yes | 0-100kW
2023-GD-35017 | 4.61 | Residencial | Yes | 0-100kW
202507-NM25-01871 | 23 | Residencial | Yes | 0-100kW
202506-NM25-03681 | 15.16 | Residencial | Yes | 0-100kW
2020-GD-06195 | 4.75 | Residencial | Yes | 0-100kW
202502-NM25-06387 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-01568 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-18488 | 4.03 | Residencial | Yes | 0-100kW
2017-GD-02525 | 4 | Residencial | Yes | 0-100kW
2022-GD-29038 | 9.98 | Residencial | Yes | 0-100kW
2022-GD-11012 | 10.25 | Residencial | Yes | 0-100kW
202507-NM25-01778 | 5.76 | Residencial | Yes | 0-100kW
2021-GD-13201 | 5.9 | Residencial | Yes | 0-100kW
2021-GD-10503 | 5 | Residencial | Yes | 0-100kW
202505-NM25-01553 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16232 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-22407 | 13.18 | Residencial | Yes | 0-100kW
2018-GD-01982 | 6.8 | Residencial | Yes | 0-100kW
202402-NM25-02142 | 3.66 | Residencial | Yes | 0-100kW
202406-NM25-02204 | 3.66 | Residencial | Yes | 0-100kW
202502-NM25-04025 | 4.224 | Residencial | Yes | 0-100kW
202507-NM25-00981 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04648 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16922 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29791 | 15 | Residencial | Yes | 0-100kW
202408-NM25-00583 | 9.516 | Comercial | Yes | 0-100kW
202409-NM25-00258 | 4.224 | Residencial | Yes | 0-100kW
202509-NM25-03969 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-14828 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-24023 | 5 | Residencial | Yes | 0-100kW
202501-NM25-01441 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14768 | 4.76 | Residencial | Yes | 0-100kW
202506-NM25-00185 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16272 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30563 | 8.05 | Residencial | Yes | 0-100kW
202504-NM25-02979 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03625 | 11.5 | Residencial | Yes | 0-100kW
14-3-587 | 2.58 | Residencial | Yes | 0-100kW
202312-NM25-01389 | 8.784 | Residencial | Yes | 0-100kW
2022-GD-21459 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-03823 | 6 | Residencial | Yes | 0-100kW
202401-NM25-01688 | 10.8 | Residencial | Yes | 0-100kW
202401-NM25-02322 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-12056 | 8 | Residencial | Yes | 0-100kW
202505-NM25-02217 | 3.8 | Residencial | Yes | 0-100kW
2018-GD-01183 | 8.35 | Residencial | Yes | 0-100kW
202508-NM25-02755 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-06243 | 15.2 | Comercial | Yes | 0-100kW
202406-NM25-01347 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-23203 | 4.03 | Residencial | Yes | 0-100kW
202410-NM25-02885 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-07054 | 3.24 | Residencial | Yes | 0-100kW
202508-NM25-00205 | 4.992 | Residencial | No | 0-100kW
202406-NM25-02122 | 8 | Residencial | Yes | 0-100kW
202506-NM25-00047 | 6.912 | Residencial | Yes | 0-100kW
2019-GD-01568 | 7.97 | Residencial | Yes | 0-100kW
202505-NM25-01836 | 3.8 | Residencial | Yes | 0-100kW
202405-NM25-00365 | 6.8 | Residencial | Yes | 0-100kW
202511-NM25-01173 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00412 | 3.84 | Residencial | Yes | 0-100kW
2017-GD-03812 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-01690 | 4.43 | Residencial | Yes | 0-100kW
202505-NM25-00109 | 5.76 | Residencial | Yes | 0-100kW
2023-GD-11741 | 3.8 | Residencial | Yes | 0-100kW
202502-NM25-02746 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03463 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03852 | 4.03 | Residencial | Yes | 0-100kW
10-2-768 | 2.09 | Residencial | Yes | 0-100kW
202506-NM25-03907 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-10048 | 3.66 | Residencial | Yes | 0-100kW
202404-NM25-01523 | 7.5 | Residencial | Yes | 0-100kW
2023-GD-14690 | 8.42 | Residencial | Yes | 0-100kW
2021-GD-04244 | 5.5 | Residencial | Yes | 0-100kW
2022-GD-02753 | 8.56 | Residencial | Yes | 0-100kW
2023-GD-28368 | 8 | Residencial | Yes | 0-100kW
2020-GD-04894 | 5.9 | Residencial | Yes | 0-100kW
202508-NM25-04171 | 3.84 | Residencial | Yes | 0-100kW
202501-NM25-01694 | 8 | Residencial | Yes | 0-100kW
202511-NM25-03586 | 15.33 | Residencial | Yes | 0-100kW
2023-GD-29641 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01882 | 8 | Residencial | No | 0-100kW
2023-GD-26954 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-02594 | 6.954 | Residencial | Yes | 0-100kW
2023-GD-29138 | 8 | Residencial | Yes | 0-100kW
2023-GD-26300 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28601 | 10.98 | Residencial | Yes | 0-100kW
202411-NM25-02491 | 16.104 | Comercial | Yes | 0-100kW
2021-GD-13757 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-35206 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-19218 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-00114 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-31553 | 7.6 | Residencial | Yes | 0-100kW
16-7-0017 | 5.16 | Residencial | Yes | 0-100kW
2023-GD-08944 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-13310 | 5 | Residencial | Yes | 0-100kW
15-7-737 | 5 | Residencial | Yes | 0-100kW
2022-GD-28913 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-17827 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01173 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-02456 | 8.83 | Residencial | Yes | 0-100kW
202510-NM25-03899 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02356 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-01018 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04227 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-01237 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-05923 | 3.29 | Residencial | Yes | 0-100kW
2022-GD-24398 | 5.49 | Residencial | Yes | 0-100kW
202410-NM25-03548 | 8.064 | Residencial | Yes | 0-100kW
202508-NM25-04896 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-31126 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-21457 | 5.49 | Residencial | Yes | 0-100kW
202408-NM25-04726 | 6 | Residencial | Yes | 0-100kW
202409-NM25-03037 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03444 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-01004 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04789 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-31822 | 6 | Residencial | No | 0-100kW
202502-NM25-06120 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19183 | 6 | Residencial | Yes | 0-100kW
2021-GD-11498 | 7.67 | Residencial | Yes | 0-100kW
202405-NM25-00032 | 5.49 | Residencial | Yes | 0-100kW
202507-NM25-01992 | 5.76 | Residencial | Yes | 0-100kW
202408-NM25-02351 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-00827 | 14.5 | Residencial | Yes | 0-100kW
2020-GD-05973 | 8.35 | Residencial | Yes | 0-100kW
2022-GD-10064 | 4.39 | Residencial | Yes | 0-100kW
202411-NM25-02822 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-01802 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29284 | 6.95 | Residencial | Yes | 0-100kW
202311-NM25-00644 | 4.026 | Residencial | Yes | 0-100kW
2021-GD-13618 | 3.24 | Residencial | Yes | 0-100kW
202408-NM25-00239 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-38682 | 8 | Residencial | Yes | 0-100kW
202407-NM25-01121 | 8 | Residencial | Yes | 0-100kW
202510-NM25-03201 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-17565 | 9.15 | Residencial | Yes | 0-100kW
2022-GD-12445 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-11144 | 5.12 | Residencial | Yes | 0-100kW
202505-NM25-01180 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-15001 | 2.93 | Residencial | Yes | 0-100kW
2022-GD-26063 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-35187 | 8.45 | Residencial | Yes | 0-100kW
202501-NM25-04909 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09174 | 9.52 | Residencial | Yes | 0-100kW
2023-GD-00038 | 6.95 | Residencial | Yes | 0-100kW
2023-GD-19539 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01085 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-17536 | 6.22 | Residencial | Yes | 0-100kW
2023-GD-14575 | 9.2 | Residencial | Yes | 0-100kW
202404-NM25-02801 | 4.026 | Residencial | Yes | 0-100kW
202401-NM25-04011 | 8.052 | Residencial | Yes | 0-100kW
2021-GD-06619 | 6 | Residencial | Yes | 0-100kW
2023-GD-00170 | 4.03 | Residencial | Yes | 0-100kW
202409-NM25-04330 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-04498 | 7.25 | Comercial | Yes | 0-100kW
202507-NM25-01316 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-00243 | 17.934 | Residencial | Yes | 0-100kW
202509-NM25-00562 | 15 | Residencial | Yes | 0-100kW
202502-NM25-02819 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-30814 | 5.86 | Residencial | Yes | 0-100kW
2020-GD-09364 | 6.78 | Residencial | Yes | 0-100kW
202511-NM25-03463 | 4.608 | Residencial | Yes | 0-100kW
2021-GD-00842 | 3.54 | Residencial | Yes | 0-100kW
15-1-1227 | 4.2 | Residencial | Yes | 0-100kW
202409-NM25-01004 | 2.36 | Residencial | Yes | 0-100kW
202506-NM25-00645 | 5.76 | Residencial | Yes | 0-100kW
202503-NM25-01509 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-02532 | 3.84 | Residencial | Yes | 0-100kW
202502-NM25-00049 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-02945 | 7.08 | Residencial | Yes | 0-100kW
202511-NM25-03061 | 6.912 | Residencial | Yes | 0-100kW
2023-GD-13953 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-01238 | 3.25 | Residencial | Yes | 0-100kW
202508-NM25-02165 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-05750 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-09967 | 4.03 | Residencial | Yes | 0-100kW
2021-GD-14857 | 5.12 | Residencial | Yes | 0-100kW
2021-GD-09634 | 3.84 | Residencial | Yes | 0-100kW
202407-NM25-03550 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-25045 | 3.84 | Residencial | Yes | 0-100kW
202502-NM25-04518 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-29167 | 4.39 | Residencial | Yes | 0-100kW
202505-NM25-03865 | 6.912 | Residencial | Yes | 0-100kW
202512-NM25-04699 | 11.5 | Residencial | Yes | 0-100kW
14-3-182 | 5 | Residencial | Yes | 0-100kW
16-1-680 | 10.25 | Residencial | No | 0-100kW
2023-GD-01584 | 5.76 | Residencial | Yes | 0-100kW
202404-NM25-02642 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-05626 | 5.9 | Residencial | Yes | 0-100kW
202408-NM25-04765 | 2.928 | Residencial | Yes | 0-100kW
202506-NM25-03696 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03866 | 11.5 | Residencial | Yes | 0-100kW
13-4-0295GD | 5 | Comercial | Yes | 0-100kW
202405-NM25-03983 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-02797 | 10 | Residencial | Yes | 0-100kW
2023-GD-01148 | 9.22 | Residencial | Yes | 0-100kW
2023-GD-19508 | 4.03 | Residencial | No | 0-100kW
2022-GD-13124 | 3.8 | Residencial | Yes | 0-100kW
2018-GD-00389 | 3.5 | Residencial | Yes | 0-100kW
2017-GD-02440 | 6.665 | Residencial | Yes | 0-100kW
2023-GD-10471 | 9.88 | Residencial | Yes | 0-100kW
16-2-0406 | 11.25 | Residencial | Yes | 0-100kW
2023-GD-11288 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-03755 | 5.856 | Residencial | Yes | 0-100kW
2022-GD-24388 | 5.49 | Residencial | Yes | 0-100kW
13-7-028 | 11 | Residencial | Yes | 0-100kW
202504-NM25-04009 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-15557 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-07019 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-06281 | 4.72 | Residencial | Yes | 0-100kW
13-7-015 | 5 | Residencial | Yes | 0-100kW
202504-NM25-00422 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-03126 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-16085 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28226 | 15.2 | Residencial | Yes | 0-100kW
2019-GD-01789 | 5.75 | Residencial | Yes | 0-100kW
2023-GD-31042 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20610 | 5.49 | Residencial | Yes | 0-100kW
2017-GD-00931 | 3 | Residencial | Yes | 0-100kW
202504-NM25-02667 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-00289 | 6.8 | Residencial | Yes | 0-100kW
202505-NM25-01247 | 2.36 | Residencial | Yes | 0-100kW
2023-GD-09310 | 3.3 | Residencial | Yes | 0-100kW
2023-GD-35459 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-23174 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02940 | 2.928 | Residencial | Yes | 0-100kW
14-9-014 | 11.16 | Residencial | Yes | 0-100kW
202410-NM25-04635 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33511 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-03515 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-11749 | 7.08 | Residencial | Yes | 0-100kW
2023-GD-28837 | 8.45 | Residencial | Yes | 0-100kW
2022-GD-16808 | 9.88 | Residencial | Yes | 0-100kW
202505-NM25-03555 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-05013 | 11.5 | Residencial | Yes | 0-100kW
202312-NM25-00715 | 8.052 | Residencial | No | 0-100kW
202407-NM25-02368 | 7.6 | Residencial | Yes | 0-100kW
15-3-102 | 5 | Residencial | Yes | 0-100kW
202506-NM25-01847 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-35430 | 8.25 | Residencial | Yes | 0-100kW
202403-NM25-00432 | 2.304 | Residencial | Yes | 0-100kW
202509-NM25-05830 | 5.96 | Residencial | Yes | 0-100kW
2023-GD-12602 | 7.6 | Comercial | Yes | 0-100kW
2022-GD-05926 | 4.03 | Residencial | Yes | 0-100kW
202502-NM25-03087 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-32060 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-03885 | 3.84 | Residencial | Yes | 0-100kW
202501-NM25-01340 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-00687 | 9.145 | Residencial | Yes | 0-100kW
2021-GD-02784 | 6.17 | Residencial | Yes | 0-100kW
2020-GD-02986 | 5 | Residencial | Yes | 0-100kW
202512-NM25-05969 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-33895 | 4.39 | Residencial | Yes | 0-100kW
2025-GD-00189 | 34.5 | Comercial | Yes | 0-100kW
2022-GD-16197 | 5.49 | Residencial | Yes | 0-100kW
202407-NM25-00863 | 5.49 | Residencial | Yes | 0-100kW
202402-NM25-03983 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03735 | 3.96 | Residencial | Yes | 0-100kW
2023-GD-31143 | 8.05 | Residencial | Yes | 0-100kW
2023-GD-25646 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-27113 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-28434 | 6.59 | Residencial | Yes | 0-100kW
2020-GD-03908 | 6.49 | Residencial | Yes | 0-100kW
202403-NM25-00734 | 5 | Residencial | Yes | 0-100kW
2022-GD-23321 | 6.49 | Residencial | Yes | 0-100kW
202409-NM25-01102 | 6 | Residencial | Yes | 0-100kW
2022-GD-25227 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13832 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-10482 | 4.03 | Residencial | Yes | 0-100kW
202512-NM25-03130 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04041 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-01043 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05693 | 5.01 | Residencial | Yes | 0-100kW
202507-NM25-00260 | 15.2 | Residencial | Yes | 0-100kW
2020-GD-05108 | 4 | Residencial | Yes | 0-100kW
2018-GD-01188 | 4.08 | Residencial | Yes | 0-100kW
2017-GD-00076 | 6.02 | Residencial | Yes | 0-100kW
15-3-229 | 5.8 | Residencial | Yes | 0-100kW
202410-NM25-01125 | 8 | Residencial | Yes | 0-100kW
2022-GD-09744 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-26217 | 7.32 | Residencial | Yes | 0-100kW
2022-GD-20267 | 4.03 | Residencial | Yes | 0-100kW
202402-NM25-03945 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-14457 | 7.32 | Residencial | Yes | 0-100kW
2022-GD-13783 | 4.03 | Residencial | Yes | 0-100kW
202509-NM25-00615 | 4.224 | Residencial | Yes | 0-100kW
2023-GD-37813 | 8.05 | Residencial | Yes | 0-100kW
2023-GD-06322 | 12.72 | Residencial | Yes | 0-100kW
2021-GD-05443 | 7.67 | Residencial | Yes | 0-100kW
202409-NM25-01484 | 10 | Residencial | Yes | 0-100kW
202310-NM25-00167 | 12.21 | Residencial | Yes | 0-100kW
202508-NM25-01175 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-01819 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00395 | 5.376 | Residencial | Yes | 0-100kW
2023-GD-01046 | 8.42 | Residencial | Yes | 0-100kW
2021-GD-01245 | 5.31 | Residencial | Yes | 0-100kW
202406-NM25-03342 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-28607 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00552 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-01859 | 10.368 | Comercial | Yes | 0-100kW
202505-NM25-02618 | 11.5 | Residencial | No | 0-100kW
202503-NM25-02966 | 6.912 | Residencial | Yes | 0-100kW
2023-GD-01847 | 6.22 | Residencial | Yes | 0-100kW
202401-NM25-03711 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02125 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-01091 | 4.085 | Residencial | Yes | 0-100kW
2022-GD-21138 | 6.9 | Residencial | Yes | 0-100kW
2022-GD-19680 | 6.22 | Residencial | Yes | 0-100kW
202402-NM25-02839 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-35307 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01048 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-05064 | 3.54 | Residencial | Yes | 0-100kW
202412-NM25-00189 | 4.392 | Residencial | Yes | 0-100kW
202409-NM25-00810 | 2.928 | Residencial | Yes | 0-100kW
202506-NM25-00862 | 7.408 | Residencial | Yes | 0-100kW
202505-NM25-04144 | 7.688 | Residencial | Yes | 0-100kW
2019-GD-02733 | 4 | Residencial | Yes | 0-100kW
202501-NM25-04028 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-20887 | 10.25 | Residencial | Yes | 0-100kW
202406-NM25-00997 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03567 | 15.2 | Residencial | Yes | 0-100kW
16-6-0765 | 2.58 | Residencial | Yes | 0-100kW
202408-NM25-02554 | 8 | Residencial | Yes | 0-100kW
202405-NM25-00644 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05074 | 11.5 | Residencial | Yes | 0-100kW
15-9-026 | 4.09 | Residencial | Yes | 0-100kW
15-3-1047 | 4 | Residencial | Yes | 0-100kW
2022-GD-30507 | 9 | Residencial | Yes | 0-100kW
2021-GD-13800 | 4.72 | Residencial | Yes | 0-100kW
15-1-966 | 5 | Residencial | Yes | 0-100kW
2021-GD-14210 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-26146 | 3.29 | Residencial | Yes | 0-100kW
202406-NM25-02883 | 6 | Residencial | Yes | 0-100kW
2023-GD-26735 | 6.8 | Residencial | Yes | 0-100kW
2017-GD-00506 | 8.35 | Residencial | Yes | 0-100kW
202403-NM25-00208 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-37902 | 6 | Residencial | Yes | 0-100kW
202503-NM25-01793 | 6.912 | Residencial | Yes | 0-100kW
2023-GD-07513 | 6.3 | Residencial | Yes | 0-100kW
202411-NM25-00102 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-04693 | 4.72 | Residencial | Yes | 0-100kW
202509-NM25-04208 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-03579 | 8.052 | Residencial | Yes | 0-100kW
202409-NM25-03422 | 7.6 | Residencial | Yes | 0-100kW
14-3-314 | 5 | Residencial | Yes | 0-100kW
2019-GD-02057 | 5.9 | Residencial | Yes | 0-100kW
202312-NM25-00832 | 5.4 | Residencial | Yes | 0-100kW
2022-GD-23689 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-05454 | 4.76 | Residencial | Yes | 0-100kW
202504-NM25-02222 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04025 | 7.36 | Residencial | Yes | 0-100kW
202407-NM25-00947 | 8 | Residencial | Yes | 0-100kW
2022-GD-17247 | 6.95 | Residencial | Yes | 0-100kW
202403-NM25-00059 | 4.758 | Residencial | Yes | 0-100kW
202404-NM25-03436 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02855 | 4.608 | Residencial | Yes | 0-100kW
2023-GD-28655 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29195 | 5 | Residencial | No | 0-100kW
13-4-0249GD | 6 | Residencial | Yes | 0-100kW
2020-GD-09524 | 2.95 | Residencial | Yes | 0-100kW
2017-GD-01749 | 2.5 | Residencial | Yes | 0-100kW
202404-NM25-02351 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03797 | 3.5 | Residencial | Yes | 0-100kW
202404-NM25-02652 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02182 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04759 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-03816 | 7.68 | Residencial | Yes | 0-100kW
202503-NM25-01415 | 5 | Residencial | Yes | 0-100kW
202410-NM25-02899 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01321 | 4.8 | Residencial | Yes | 0-100kW
2022-GD-08335 | 9.52 | Residencial | Yes | 0-100kW
202501-NM25-03135 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-03927 | 8 | Residencial | Yes | 0-100kW
2023-GD-25570 | 8 | Residencial | Yes | 0-100kW
202410-NM25-00261 | 15.2 | Comercial | Yes | 0-100kW
15-3-459 | 12 | Residencial | Yes | 0-100kW
2022-GD-21957 | 4.03 | Residencial | Yes | 0-100kW
202508-NM25-05113 | 9 | Residencial | Yes | 0-100kW
202408-NM25-02095 | 3.84 | Residencial | Yes | 0-100kW
202408-NM25-02424 | 7.6 | Residencial | Yes | 0-100kW
16-6-0262 | 5 | Residencial | Yes | 0-100kW
2022-GD-26619 | 4.39 | Residencial | Yes | 0-100kW
16-4-0703GD | 4.52 | Residencial | Yes | 0-100kW
202503-NM25-04933 | 6.912 | Residencial | Yes | 0-100kW
2021-GD-10627 | 5.12 | Residencial | Yes | 0-100kW
202507-NM25-04207 | 11.5 | Residencial | Yes | 0-100kW
202311-NM25-00991 | 12.81 | Residencial | Yes | 0-100kW
202501-NM25-02550 | 11.712 | Residencial | Yes | 0-100kW
202406-NM25-01523 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-00015 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-09279 | 6.59 | Residencial | Yes | 0-100kW
202311-NM25-00821 | 8.052 | Residencial | Yes | 0-100kW
2022-GD-22840 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02825 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02461 | 8 | Residencial | Yes | 0-100kW
2022-GD-18443 | 6.04 | Residencial | Yes | 0-100kW
202504-NM25-00957 | 8 | Residencial | Yes | 0-100kW
2020-GD-01649 | 5 | Residencial | Yes | 0-100kW
2023-GD-36923 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-04492 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-13989 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-00141 | 6.19 | Residencial | Yes | 0-100kW
202405-NM25-02451 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-22722 | 5 | Residencial | Yes | 0-100kW
2022-GD-24529 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-31237 | 4.61 | Residencial | Yes | 0-100kW
202407-NM25-00079 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-37675 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07681 | 3.24 | Residencial | Yes | 0-100kW
202404-NM25-01879 | 5 | Residencial | Yes | 0-100kW
2022-GD-28472 | 10.98 | Residencial | Yes | 0-100kW
2018-GD-02127 | 8 | Residencial | Yes | 0-100kW
2021-GD-13546 | 4.72 | Residencial | Yes | 0-100kW
202312-NM25-01233 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06316 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-01748 | 6.22 | Residencial | Yes | 0-100kW
202411-NM25-02085 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-14193 | 8 | Residencial | Yes | 0-100kW
2021-GD-08440 | 4.13 | Residencial | Yes | 0-100kW
202508-NM25-02826 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-09852 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-15358 | 8.42 | Residencial | Yes | 0-100kW
202509-NM25-01003 | 3.456 | Residencial | Yes | 0-100kW
2023-GD-12762 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04420 | 10.248 | Residencial | Yes | 0-100kW
2022-GD-14787 | 3.66 | Residencial | Yes | 0-100kW
202401-NM25-03413 | 8.052 | Residencial | No | 0-100kW
202502-NM25-06537 | 8 | Residencial | Yes | 0-100kW
202406-NM25-02294 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-18361 | 10.37 | Residencial | Yes | 0-100kW
202505-NM25-04377 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-04477 | 8 | Residencial | Yes | 0-100kW
2023-GD-26372 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31943 | 3.8 | Residencial | Yes | 0-100kW
202509-NM25-03647 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-03843 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-04106 | 4 | Residencial | Yes | 0-100kW
202410-NM25-03321 | 3.072 | Residencial | Yes | 0-100kW
2023-GD-24138 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-25221 | 11.49 | Residencial | Yes | 0-100kW
202405-NM25-01801 | 6 | Residencial | Yes | 0-100kW
2023-GD-17931 | 15.36 | Residencial | Yes | 0-100kW
202506-NM25-03881 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-03879 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06689 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-20081 | 5.49 | Residencial | No | 0-100kW
2022-GD-20704 | 6.22 | Residencial | Yes | 0-100kW
2020-GD-00807 | 3.54 | Residencial | Yes | 0-100kW
202404-NM25-03766 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-04294 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-08503 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-27303 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00331 | 4 | Residencial | Yes | 0-100kW
2021-GD-00231 | 5.01 | Residencial | Yes | 0-100kW
2022-GD-27206 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-16037 | 9.88 | Residencial | Yes | 0-100kW
2023-GD-36895 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01586 | 11.5 | Residencial | Yes | 0-100kW
16-2-0842 | 4.95 | Residencial | Yes | 0-100kW
2023-GD-20213 | 3.8 | Residencial | Yes | 0-100kW
202501-NM25-00053 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04698 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-03423 | 6.195 | Residencial | Yes | 0-100kW
2024-GD-00045 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06091 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-13276 | 3 | Residencial | Yes | 0-100kW
2023-GD-13189 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-13828 | 4.76 | Residencial | Yes | 0-100kW
202508-NM25-05178 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-21459 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05603 | 4.72 | Residencial | Yes | 0-100kW
202507-NM25-00604 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-06054 | 24 | Comercial | Yes | 0-100kW
2023-GD-12765 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13326 | 3.8 | Residencial | Yes | 0-100kW
202504-NM25-04609 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-02577 | 15 | Comercial | Yes | 0-100kW
202508-NM25-03352 | 11.5 | Residencial | Yes | 0-100kW
202312-NM25-02530 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03354 | 7.6 | Residencial | Yes | 0-100kW
15-3-027 | 3.6 | Residencial | Yes | 0-100kW
14-5-0321A | 9.03 | Comercial | Yes | 0-100kW
2022-GD-14500 | 5 | Residencial | Yes | 0-100kW
202501-NM25-00087 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33911 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-05285 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-05051 | 8.05 | Residencial | Yes | 0-100kW
202312-NM25-03159 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-07842 | 7.26 | Residencial | Yes | 0-100kW
202507-NM25-02712 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09725 | 4.43 | Residencial | Yes | 0-100kW
202503-NM25-00616 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19716 | 6.53 | Residencial | No | 0-100kW
202410-NM25-00276 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-15147 | 8.26 | Residencial | Yes | 0-100kW
202510-NM25-00032 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-17748 | 6.95 | Residencial | Yes | 0-100kW
202408-NM25-02827 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-04674 | 6 | Residencial | Yes | 0-100kW
202402-NM25-01991 | 4.026 | Residencial | Yes | 0-100kW
202407-NM25-03132 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-13461 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02021 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24418 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-04940 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-14752 | 6.78 | Residencial | Yes | 0-100kW
202406-NM25-01841 | 7.6 | Residencial | No | 0-100kW
202505-NM25-03820 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-01810 | 3.84 | Residencial | Yes | 0-100kW
16-4-0750 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-04344 | 5.376 | Residencial | Yes | 0-100kW
202402-NM25-01446 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-02461 | 7.67 | Residencial | Yes | 0-100kW
2022-GD-11307 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-08037 | 2.69 | Residencial | Yes | 0-100kW
202501-NM25-01123 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-02645 | 3.54 | Residencial | Yes | 0-100kW
202403-NM25-00896 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-10835 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-04431 | 7.6 | Residencial | Yes | 0-100kW
202309-NM25-00064 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05774 | 10.98 | Residencial | Yes | 0-100kW
2021-GD-03642 | 3.24 | Residencial | Yes | 0-100kW
202501-NM25-00124 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04411 | 11.4 | Residencial | Yes | 0-100kW
202506-NM25-02646 | 6.468 | Residencial | Yes | 0-100kW
202405-NM25-04155 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-25964 | 5 | Residencial | Yes | 0-100kW
2022-GD-08956 | 5 | Residencial | Yes | 0-100kW
202506-NM25-00727 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-04071 | 7.68 | Residencial | Yes | 0-100kW
202512-NM25-01916 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-03350 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-09471 | 5.38 | Residencial | Yes | 0-100kW
2022-GD-15785 | 15 | Residencial | Yes | 0-100kW
202311-NM25-00444 | 8 | Residencial | No | 0-100kW
2022-GD-18691 | 4.76 | Residencial | Yes | 0-100kW
202409-NM25-01438 | 4.026 | Residencial | Yes | 0-100kW
202502-NM25-00040 | 6.76 | Residencial | Yes | 0-100kW
2023-GD-02226 | 4.76 | Residencial | Yes | 0-100kW
202505-NM25-03586 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-03804 | 11.5 | Residencial | Yes | 0-100kW
15-3-686 | 4.52 | Residencial | Yes | 0-100kW
202503-NM25-01672 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-22749 | 10.25 | Residencial | Yes | 0-100kW
202506-NM25-02399 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-12950 | 9.6 | Comercial | Yes | 0-100kW
2021-GD-11224 | 5.31 | Residencial | Yes | 0-100kW
202403-NM25-02215 | 9 | Residencial | Yes | 0-100kW
2023-GD-33942 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02057 | 5.12 | Residencial | Yes | 0-100kW
202411-NM25-00679 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36575 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-01136 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-08972 | 6.59 | Residencial | Yes | 0-100kW
202501-NM25-03456 | 6.912 | Residencial | Yes | 0-100kW
2022-GD-05660 | 21.54 | Residencial | Yes | 0-100kW
202410-NM25-04197 | 6.588 | Residencial | Yes | 0-100kW
2023-GD-18289 | 15.2 | Residencial | Yes | 0-100kW
202507-NM25-02377 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-04599 | 8.052 | Residencial | Yes | 0-100kW
202512-NM25-05614 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-00479 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-07870 | 3.24 | Residencial | Yes | 0-100kW
202403-NM25-01646 | 10.614 | Residencial | Yes | 0-100kW
2022-GD-10976 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-12336 | 6.22 | Residencial | Yes | 0-100kW
2023-GD-17972 | 24.58 | Residencial | Yes | 0-100kW
202501-NM25-03699 | 12 | Residencial | Yes | 0-100kW
202501-NM25-00887 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07807 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07772 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02198 | 9.516 | Residencial | Yes | 0-100kW
2022-GD-19905 | 6.59 | Residencial | Yes | 0-100kW
2017-GD-01104 | 3.01 | Residencial | Yes | 0-100kW
2022-GD-27207 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-03405 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-00397 | 5.49 | Residencial | Yes | 0-100kW
202508-NM25-00165 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-09916 | 15.2 | Residencial | Yes | 0-100kW
202410-NM25-01842 | 2.928 | Residencial | Yes | 0-100kW
2017-GD-00952 | 11.2 | Comercial | Yes | 0-100kW
202404-NM25-01859 | 5 | Residencial | Yes | 0-100kW
2022-GD-26564 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-16787 | 5.4 | Residencial | Yes | 0-100kW
202505-NM25-03289 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-06299 | 5.12 | Residencial | Yes | 0-100kW
2022-GD-24776 | 5.86 | Residencial | Yes | 0-100kW
2022-GD-04703 | 5.01 | Residencial | Yes | 0-100kW
2022-GD-25791 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-05309 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14174 | 8 | Residencial | Yes | 0-100kW
202508-NM25-03008 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-01794 | 7.97 | Residencial | Yes | 0-100kW
202407-NM25-00519 | 10.614 | Residencial | Yes | 0-100kW
2021-GD-01394 | 6 | Residencial | Yes | 0-100kW
2022-GD-20840 | 6.95 | Residencial | Yes | 0-100kW
202501-NM25-02265 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-01687 | 3.84 | Residencial | Yes | 0-100kW
202403-NM25-00851 | 9.882 | Residencial | Yes | 0-100kW
2022-GD-12232 | 7.32 | Residencial | Yes | 0-100kW
14-7-714 | 4.2 | Residencial | Yes | 0-100kW
202504-NM25-01623 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-05177 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-11452 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-39193 | 9.88 | Residencial | Yes | 0-100kW
2023-GD-11706 | 3.3 | Residencial | Yes | 0-100kW
202501-NM25-03433 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04078 | 9.52 | Residencial | Yes | 0-100kW
202501-NM25-00302 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00965 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-04420 | 6.588 | Residencial | Yes | 0-100kW
2022-GD-11779 | 4.15 | Residencial | Yes | 0-100kW
2023-GD-20671 | 7.6 | Residencial | No | 0-100kW
2020-GD-02173 | 13.908 | Residencial | Yes | 0-100kW
2022-GD-03258 | 8.05 | Residencial | Yes | 0-100kW
202511-NM25-02114 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-00862 | 10 | Residencial | Yes | 0-100kW
202511-NM25-04109 | 10 | Residencial | Yes | 0-100kW
2023-GD-09930 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-03917 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-23697 | 5 | Residencial | Yes | 0-100kW
2023-GD-14536 | 3.8 | Residencial | Yes | 0-100kW
2019-GD-00219 | 6.5 | Residencial | Yes | 0-100kW
202312-NM25-02844 | 8 | Residencial | Yes | 0-100kW
202502-NM25-01659 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02937 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-04945 | 5 | Residencial | Yes | 0-100kW
2023-GD-11895 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06531 | 7.38 | Residencial | Yes | 0-100kW
2022-GD-19488 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-17830 | 3 | Residencial | Yes | 0-100kW
2023-GD-05887 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-26294 | 3.07 | Residencial | Yes | 0-100kW
202511-NM25-00578 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-00071 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-01684 | 3.54 | Residencial | Yes | 0-100kW
202411-NM25-02809 | 15.2 | Residencial | Yes | 0-100kW
202501-NM25-01399 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-01263 | 5.31 | Residencial | Yes | 0-100kW
202505-NM25-03879 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02971 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06765 | 4.13 | Residencial | Yes | 0-100kW
202412-NM25-03731 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04654 | 9.984 | Residencial | Yes | 0-100kW
202408-NM25-04403 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04706 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21390 | 3.66 | Residencial | Yes | 0-100kW
202502-NM25-05883 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03775 | 3.456 | Residencial | Yes | 0-100kW
202405-NM25-00162 | 6.66 | Residencial | Yes | 0-100kW
202404-NM25-00290 | 10.614 | Residencial | Yes | 0-100kW
2021-GD-10984 | 12.24 | Residencial | Yes | 0-100kW
202404-NM25-00868 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-18940 | 15 | Residencial | Yes | 0-100kW
2022-GD-13463 | 5.25 | Residencial | Yes | 0-100kW
2023-GD-28256 | 12.21 | Residencial | Yes | 0-100kW
202511-NM25-01371 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29199 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00760 | 3.54 | Residencial | Yes | 0-100kW
202511-NM25-03663 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-15518 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03500 | 4 | Residencial | Yes | 0-100kW
202509-NM25-05368 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-26263 | 10.18 | Residencial | Yes | 0-100kW
202501-NM25-03949 | 7.296 | Residencial | Yes | 0-100kW
202506-NM25-04540 | 9 | Residencial | Yes | 0-100kW
2023-GD-09308 | 6.18 | Residencial | Yes | 0-100kW
2022-GD-03634 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-28061 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-18114 | 12.8 | Residencial | Yes | 0-100kW
2022-GD-16215 | 2.95 | Residencial | Yes | 0-100kW
202407-NM25-02305 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01294 | 3.54 | Residencial | Yes | 0-100kW
202502-NM25-01366 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28171 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07299 | 5.9 | Residencial | Yes | 0-100kW
2017-GD-01424 | 3.25 | Residencial | Yes | 0-100kW
202501-NM25-01243 | 10.752 | Residencial | Yes | 0-100kW
202503-NM25-02304 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03400 | 4.39 | Residencial | Yes | 0-100kW
202502-NM25-04681 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-01706 | 6.19 | Residencial | Yes | 0-100kW
2021-GD-06207 | 16 | Residencial | Yes | 0-100kW
202401-NM25-03533 | 4.392 | Residencial | Yes | 0-100kW
2022-GD-20816 | 5 | Residencial | Yes | 0-100kW
2022-GD-28195 | 6.22 | Residencial | Yes | 0-100kW
202408-NM25-03708 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-08434 | 4.13 | Residencial | Yes | 0-100kW
202310-NM25-00523 | 8.052 | Residencial | Yes | 0-100kW
14-3-252 | 6 | Residencial | Yes | 0-100kW
202405-NM25-03343 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-05730 | 5.9 | Residencial | Yes | 0-100kW
202402-NM25-04439 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-02217 | 13.542 | Residencial | Yes | 0-100kW
2020-GD-06094 | 5 | Residencial | Yes | 0-100kW
2022-GD-27743 | 3.5 | Residencial | Yes | 0-100kW
2022-GD-10912 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-05196 | 9 | Residencial | Yes | 0-100kW
2022-GD-04763 | 5.9 | Comercial | Yes | 0-100kW
2023-GD-03596 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-01969 | 3.8 | Residencial | Yes | 0-100kW
15-2-736 | 8.75 | Residencial | Yes | 0-100kW
2023-GD-27019 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-01126 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-03686 | 3.75 | Residencial | Yes | 0-100kW
202412-NM25-01911 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-24295 | 4.76 | Residencial | Yes | 0-100kW
202405-NM25-03989 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01044 | 2.36 | Residencial | Yes | 0-100kW
202501-NM25-01322 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-01738 | 4 | Residencial | Yes | 0-100kW
2021-GD-11479 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12832 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-03567 | 4.39 | Residencial | Yes | 0-100kW
15-7-752 | 6.6 | Residencial | Yes | 0-100kW
2022-GD-21183 | 12.08 | Residencial | Yes | 0-100kW
202401-NM25-03256 | 3.66 | Residencial | Yes | 0-100kW
202412-NM25-01807 | 11.4 | Residencial | Yes | 0-100kW
202508-NM25-05430 | 13.09 | Residencial | Yes | 0-100kW
202505-NM25-02527 | 19.22 | Residencial | Yes | 0-100kW
202505-NM25-02765 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16896 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-38124 | 2.93 | Residencial | Yes | 0-100kW
2023-GD-04046 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-11170 | 5 | Residencial | Yes | 0-100kW
202511-NM25-02035 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-01955 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03807 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-29033 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06184 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35550 | 3.84 | Residencial | Yes | 0-100kW
2021-GD-01870 | 8.85 | Residencial | Yes | 0-100kW
2020-GD-04872 | 7.25 | Residencial | Yes | 0-100kW
2023-GD-33650 | 6 | Residencial | Yes | 0-100kW
202410-NM25-03781 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-00678 | 4.608 | Residencial | Yes | 0-100kW
2023-GD-20781 | 15.2 | Residencial | Yes | 0-100kW
202502-NM25-06757 | 7.6 | Residencial | Yes | 0-100kW
14-5-0268A | 4.25 | Residencial | Yes | 0-100kW
202503-NM25-00625 | 3.84 | Residencial | Yes | 0-100kW
202503-NM25-03459 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-16719 | 9.15 | Residencial | Yes | 0-100kW
14-3-922 | 4 | Residencial | Yes | 0-100kW
2019-GD-01114 | 6.8 | Residencial | Yes | 0-100kW
202501-NM25-00211 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-09236 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02489 | 7.6 | Residencial | No | 0-100kW
2021-GD-14058 | 3.8 | Residencial | Yes | 0-100kW
202404-NM25-00698 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15891 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-02681 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-00105 | 20.166 | Residencial | Yes | 0-100kW
202509-NM25-05351 | 21.96 | Residencial | Yes | 0-100kW
2022-GD-05443 | 20.16 | Residencial | Yes | 0-100kW
2023-GD-15163 | 4.39 | Residencial | Yes | 0-100kW
202402-NM25-04413 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-02264 | 7.6 | Residencial | No | 0-100kW
202310-NM25-00376 | 8.052 | Residencial | Yes | 0-100kW
2023-GD-37851 | 3.8 | Residencial | Yes | 0-100kW
202510-NM25-00774 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-11373 | 13.54 | Residencial | Yes | 0-100kW
202506-NM25-01280 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-08751 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-18674 | 3.8 | Residencial | Yes | 0-100kW
2017-GD-00894 | 6 | Residencial | Yes | 0-100kW
202407-NM25-00158 | 6 | Residencial | Yes | 0-100kW
2023-GD-07604 | 6.95 | Residencial | Yes | 0-100kW
2022-GD-02860 | 5.49 | Residencial | Yes | 0-100kW
202312-NM25-00254 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09492 | 5.12 | Residencial | Yes | 0-100kW
202411-NM25-00112 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05186 | 5.9 | Residencial | Yes | 0-100kW
202408-NM25-02774 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-10870 | 3.24 | Residencial | Yes | 0-100kW
202502-NM25-03667 | 15 | Residencial | Yes | 0-100kW
2022-GD-21037 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-05074 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00171 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27367 | 8.06 | Residencial | Yes | 0-100kW
2020-GD-02192 | 4.425 | Residencial | Yes | 0-100kW
202509-NM25-01606 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-10442 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-04572 | 4.13 | Residencial | Yes | 0-100kW
2022-GD-26667 | 7.3 | Residencial | Yes | 0-100kW
202401-NM25-02452 | 5 | Residencial | Yes | 0-100kW
2022-GD-02787 | 5.86 | Residencial | Yes | 0-100kW
202401-NM25-01872 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06184 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02262 | 10 | Residencial | Yes | 0-100kW
202508-NM25-04965 | 8 | Residencial | Yes | 0-100kW
202410-NM25-04546 | 15.2 | Residencial | Yes | 0-100kW
16-4-1125GD | 3.65 | Residencial | No | 0-100kW
202510-NM25-01620 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-05828 | 6.95 | Residencial | Yes | 0-100kW
202402-NM25-00415 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-12424 | 4.03 | Residencial | Yes | 0-100kW
202405-NM25-03579 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03248 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-04939 | 5.01 | Residencial | Yes | 0-100kW
2022-GD-10190 | 3.66 | Residencial | Yes | 0-100kW
202511-NM25-02925 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-00600 | 2.97 | Residencial | Yes | 0-100kW
2021-GD-00976 | 10 | Residencial | Yes | 0-100kW
202507-NM25-02942 | 8 | Residencial | Yes | 0-100kW
2022-GD-16530 | 10.98 | Residencial | Yes | 0-100kW
2023-GD-08337 | 18.3 | Residencial | No | 0-100kW
202511-NM25-04282 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-19103 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01069 | 7.6 | Residencial | No | 0-100kW
202504-NM25-02429 | 4.392 | Residencial | Yes | 0-100kW
202406-NM25-00582 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30095 | 14.64 | Residencial | Yes | 0-100kW
202507-NM25-00533 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-00190 | 4.392 | Residencial | Yes | 0-100kW
202312-NM25-01155 | 7.6 | Residencial | No | 0-100kW
16-6-0295 | 3.01 | Residencial | Yes | 0-100kW
202510-NM25-02918 | 8 | Residencial | Yes | 0-100kW
2023-GD-27983 | 8.78 | Residencial | Yes | 0-100kW
2017-GD-01675 | 3.25 | Residencial | Yes | 0-100kW
2023-GD-01435 | 9.22 | Residencial | Yes | 0-100kW
202512-NM25-05646 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-11761 | 4.03 | Residencial | Yes | 0-100kW
202501-NM25-03549 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-02456 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-27671 | 9.6 | Residencial | Yes | 0-100kW
2020-GD-03509 | 13.6 | Residencial | Yes | 0-100kW
2022-GD-17730 | 7.08 | Residencial | No | 0-100kW
202412-NM25-02058 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00554 | 9.15 | Comercial | Yes | 0-100kW
2022-GD-06194 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-04792 | 4.8 | Residencial | No | 0-100kW
13-6-0035 | 5.38 | Comercial | Yes | 0-100kW
2023-GD-22319 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01411 | 8 | Residencial | Yes | 0-100kW
202509-NM25-02040 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-04677 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-07981 | 5.55 | Residencial | Yes | 0-100kW
2020-GD-03004 | 4.72 | Residencial | Yes | 0-100kW
2019-GD-03074 | 5.015 | Residencial | Yes | 0-100kW
2021-GD-04602 | 3.54 | Residencial | Yes | 0-100kW
202508-NM25-04146 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-01702 | 4.25 | Residencial | Yes | 0-100kW
2022-GD-04007 | 2.95 | Residencial | Yes | 0-100kW
202401-NM25-01418 | 4.392 | Residencial | Yes | 0-100kW
2020-GD-03331 | 10.325 | Residencial | Yes | 0-100kW
202510-NM25-02367 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03313 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13411 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-31847 | 6.59 | Residencial | Yes | 0-100kW
2023-GD-25467 | 5 | Residencial | Yes | 0-100kW
202507-NM25-02898 | 8 | Residencial | Yes | 0-100kW
2019-GD-01744 | 3.75 | Residencial | Yes | 0-100kW
2021-GD-12214 | 6.49 | Residencial | Yes | 0-100kW
2020-GD-02401 | 8.5 | Residencial | Yes | 0-100kW
2023-GD-23197 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31333 | 8.42 | Residencial | Yes | 0-100kW
2022-GD-14598 | 12.98 | Residencial | Yes | 0-100kW
202406-NM25-01550 | 3.84 | Residencial | Yes | 0-100kW
202411-NM25-02815 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-00444 | 3.66 | Residencial | Yes | 0-100kW
202404-NM25-04174 | 11.26 | Residencial | Yes | 0-100kW
2022-GD-28669 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19866 | 3.66 | Residencial | Yes | 0-100kW
202410-NM25-01133 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-23000 | 4.03 | Residencial | Yes | 0-100kW
202501-NM25-01302 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01621 | 7.6 | Comercial | Yes | 0-100kW
202502-NM25-03384 | 6.954 | Residencial | Yes | 0-100kW
202411-NM25-03607 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00817 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-00449 | 9.15 | Residencial | Yes | 0-100kW
202408-NM25-03802 | 5 | Residencial | Yes | 0-100kW
2022-GD-32769 | 4.76 | Residencial | Yes | 0-100kW
202504-NM25-02302 | 12 | Residencial | Yes | 0-100kW
2022-GD-10611 | 6 | Residencial | Yes | 0-100kW
202509-NM25-02451 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-01321 | 4.3 | Residencial | Yes | 0-100kW
202312-NM25-02060 | 6 | Residencial | Yes | 0-100kW
202410-NM25-03225 | 4.224 | Residencial | Yes | 0-100kW
2022-GD-04818 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-24561 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-22942 | 5 | Residencial | Yes | 0-100kW
2023-GD-02959 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02293 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-07321 | 12 | Comercial | Yes | 0-100kW
2022-GD-19709 | 11.71 | Residencial | Yes | 0-100kW
202410-NM25-03840 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-00912 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36810 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-09511 | 4.43 | Residencial | Yes | 0-100kW
2023-GD-35637 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-26741 | 8.45 | Residencial | Yes | 0-100kW
2021-GD-01311 | 6.25 | Residencial | Yes | 0-100kW
202511-NM25-00504 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-14574 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06181 | 5 | Residencial | Yes | 0-100kW
202406-NM25-00185 | 5.124 | Residencial | Yes | 0-100kW
202405-NM25-00233 | 9.15 | Residencial | Yes | 0-100kW
202408-NM25-03730 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01552 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-28055 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-10784 | 10.4 | Residencial | No | 0-100kW
202510-NM25-01155 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-20290 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-03912 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-00565 | 3.8 | Residencial | Yes | 0-100kW
202407-NM25-01865 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-05100 | 9 | Residencial | Yes | 0-100kW
202511-NM25-00835 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-00480 | 15 | Residencial | Yes | 0-100kW
2022-GD-21370 | 6.95 | Residencial | Yes | 0-100kW
202511-NM25-03838 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-01633 | 3.8 | Residencial | Yes | 0-100kW
202401-NM25-04392 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-38869 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-26403 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-35626 | 5.76 | Residencial | Yes | 0-100kW
2019-GD-00052 | 8.35 | Residencial | Yes | 0-100kW
2023-GD-31885 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-03222 | 4.25 | Residencial | Yes | 0-100kW
202402-NM25-04415 | 15.2 | Residencial | Yes | 0-100kW
2022-GD-03921 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-06213 | 8.85 | Residencial | Yes | 0-100kW
2023-GD-21421 | 8.45 | Residencial | No | 0-100kW
2022-GD-18003 | 4.2 | Residencial | Yes | 0-100kW
202410-NM25-03728 | 3.9 | Residencial | Yes | 0-100kW
202407-NM25-02236 | 5 | Residencial | Yes | 0-100kW
2022-GD-25269 | 3.29 | Residencial | No | 0-100kW
2019-GD-02235 | 6.195 | Residencial | Yes | 0-100kW
202411-NM25-01756 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-06779 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00780 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06424 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-02474 | 2.95 | Residencial | Yes | 0-100kW
202511-NM25-02858 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-11412 | 2.93 | Residencial | Yes | 0-100kW
202310-NM25-00449 | 8.052 | Residencial | Yes | 0-100kW
202411-NM25-03403 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-00742 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15736 | 5.31 | Residencial | Yes | 0-100kW
202411-NM25-00474 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-27482 | 5.12 | Residencial | Yes | 0-100kW
202509-NM25-01049 | 23 | Residencial | Yes | 0-100kW
2019-GD-02602 | 9 | Residencial | Yes | 0-100kW
2021-GD-00767 | 7.08 | Residencial | Yes | 0-100kW
202406-NM25-02825 | 6.24 | Residencial | Yes | 0-100kW
202409-NM25-02622 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-04758 | 5.9 | Comercial | Yes | 0-100kW
2023-GD-39073 | 8.78 | Residencial | Yes | 0-100kW
202511-NM25-00712 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-38999 | 12.44 | Residencial | Yes | 0-100kW
202412-NM25-02538 | 10 | Residencial | Yes | 0-100kW
2022-GD-30403 | 5 | Residencial | Yes | 0-100kW
2023-GD-36709 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-36633 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08060 | 6.59 | Residencial | Yes | 0-100kW
19-3-099 | 3.25 | Residencial | Yes | 0-100kW
2022-GD-22624 | 5 | Residencial | Yes | 0-100kW
15-5-0633A | 3 | Residencial | Yes | 0-100kW
2023-GD-15984 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-05538 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-12863 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-24222 | 12.08 | Residencial | Yes | 0-100kW
202406-NM25-01236 | 8 | Residencial | Yes | 0-100kW
2021-GD-08825 | 9.6 | Residencial | Yes | 0-100kW
202403-NM25-03146 | 4.026 | Residencial | Yes | 0-100kW
202505-NM25-01645 | 8 | Residencial | Yes | 0-100kW
202405-NM25-01095 | 3.66 | Residencial | Yes | 0-100kW
15-5-0687A | 4 | Residencial | Yes | 0-100kW
202402-NM25-00454 | 3.8 | Residencial | Yes | 0-100kW
202401-NM25-01149 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-33565 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13765 | 5.86 | Residencial | Yes | 0-100kW
202511-NM25-01141 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-04950 | 6.8 | Residencial | Yes | 0-100kW
202403-NM25-01047 | 9 | Residencial | Yes | 0-100kW
2022-GD-17222 | 4.03 | Residencial | Yes | 0-100kW
2022-GD-06536 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-31654 | 3.66 | Residencial | Yes | 0-100kW
202404-NM25-03376 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00993 | 8.35 | Residencial | Yes | 0-100kW
2019-GD-02710 | 6.195 | Residencial | Yes | 0-100kW
2022-GD-16408 | 4.03 | Residencial | Yes | 0-100kW
202501-NM25-02950 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-01525 | 4.992 | Residencial | Yes | 0-100kW
202403-NM25-00919 | 7.6 | Residencial | Yes | 0-100kW
16-7-0182 | 60 | Comercial | Yes | 0-100kW
2022-GD-30156 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-13777 | 7.6 | Residencial | Yes | 0-100kW
202511-NM25-01162 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-03073 | 19.62 | Residencial | Yes | 0-100kW
2022-GD-14254 | 5 | Residencial | Yes | 0-100kW
202408-NM25-00791 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-07090 | 6.84 | Residencial | Yes | 0-100kW
202410-NM25-00287 | 10.614 | Residencial | Yes | 0-100kW
202407-NM25-04256 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00638 | 9.6 | Residencial | Yes | 0-100kW
2022-GD-01182 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-05328 | 6.95 | Residencial | Yes | 0-100kW
202508-NM25-01216 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-13779 | 9.6 | Residencial | Yes | 0-100kW
202404-NM25-01271 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06874 | 4.76 | Residencial | Yes | 0-100kW
2022-GD-21043 | 5.31 | Residencial | Yes | 0-100kW
2020-GD-02441 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-07345 | 4.5 | Residencial | Yes | 0-100kW
2020-GD-00857 | 5.015 | Residencial | Yes | 0-100kW
2022-GD-29823 | 8 | Residencial | Yes | 0-100kW
202504-NM25-00387 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-02548 | 4.224 | Residencial | Yes | 0-100kW
2023-GD-06703 | 9 | Residencial | Yes | 0-100kW
202502-NM25-05474 | 13.36 | Residencial | Yes | 0-100kW
202502-NM25-02634 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09444 | 9.88 | Residencial | Yes | 0-100kW
2020-GD-05874 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-17378 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03180 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-31759 | 9 | Residencial | Yes | 0-100kW
202503-NM25-00110 | 11.5 | Residencial | Yes | 0-100kW
202405-NM25-03085 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-05778 | 15.36 | Residencial | Yes | 0-100kW
202405-NM25-01391 | 3.66 | Residencial | Yes | 0-100kW
202505-NM25-02018 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-06019 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-00058 | 10.248 | Residencial | Yes | 0-100kW
2020-GD-00731 | 10.56 | Residencial | Yes | 0-100kW
2022-GD-20298 | 5.49 | Residencial | Yes | 0-100kW
2018-GD-01804 | 5.28 | Residencial | Yes | 0-100kW
202311-NM25-00542 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19237 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-05143 | 8.5 | Residencial | Yes | 0-100kW
202408-NM25-03621 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-05388 | 5.76 | Residencial | Yes | 0-100kW
2021-GD-06112 | 7.68 | Residencial | Yes | 0-100kW
2022-GD-18918 | 6.95 | Residencial | Yes | 0-100kW
2022-GD-20936 | 7.68 | Residencial | Yes | 0-100kW
202410-NM25-01898 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31945 | 5.76 | Residencial | Yes | 0-100kW
2022-GD-20677 | 3.54 | Residencial | Yes | 0-100kW
202412-NM25-00634 | 16.47 | Residencial | Yes | 0-100kW
202411-NM25-01408 | 7.056 | Residencial | Yes | 0-100kW
2022-GD-18063 | 8.25 | Residencial | Yes | 0-100kW
2021-GD-11770 | 6.59 | Residencial | Yes | 0-100kW
202411-NM25-03487 | 15.2 | Residencial | Yes | 0-100kW
202312-NM25-01917 | 6.8 | Residencial | Yes | 0-100kW
202312-NM25-01532 | 3.66 | Residencial | Yes | 0-100kW
202412-NM25-02819 | 8 | Residencial | Yes | 0-100kW
202407-NM25-01982 | 11.52 | Residencial | Yes | 0-100kW
202403-NM25-03714 | 8 | Residencial | Yes | 0-100kW
202411-NM25-00175 | 2.928 | Residencial | Yes | 0-100kW
202401-NM25-04580 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-02016 | 7.68 | Residencial | Yes | 0-100kW
202410-NM25-02731 | 12 | Residencial | Yes | 0-100kW
202509-NM25-01345 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-01762 | 5.12 | Residencial | Yes | 0-100kW
2018-GD-00804 | 6 | Residencial | Yes | 0-100kW
2023-GD-13735 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02393 | 6 | Residencial | Yes | 0-100kW
2023-GD-26442 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-14617 | 4.03 | Residencial | Yes | 0-100kW
202403-NM25-00611 | 7.6 | Residencial | No | 0-100kW
202501-NM25-05687 | 15.2 | Residencial | Yes | 0-100kW
202507-NM25-03596 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-01428 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-25000 | 5.12 | Residencial | Yes | 0-100kW
202411-NM25-01122 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-26139 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31464 | 7.59 | Residencial | Yes | 0-100kW
202504-NM25-03035 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-00243 | 5.76 | Residencial | Yes | 0-100kW
15-9-308 | 2.58 | Residencial | Yes | 0-100kW
16-4-0773GD | 7.74 | Residencial | Yes | 0-100kW
2023-GD-30253 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-03201 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-29671 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-09388 | 7 | Residencial | Yes | 0-100kW
2021-GD-05825 | 7.932 | Residencial | Yes | 0-100kW
2020-GD-01269 | 3.25 | Residencial | Yes | 0-100kW
202502-NM25-02867 | 12 | Residencial | Yes | 0-100kW
2022-GD-08549 | 6.8 | Residencial | Yes | 0-100kW
202504-NM25-03235 | 9 | Residencial | Yes | 0-100kW
2023-GD-33306 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02882 | 7.67 | Residencial | Yes | 0-100kW
202403-NM25-00724 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-00283 | 7.6 | Residencial | Yes | 0-100kW
15-3-482 | 3.66 | Residencial | Yes | 0-100kW
2017-GD-00502 | 3.25 | Residencial | Yes | 0-100kW
2023-GD-15920 | 7.6 | Comercial | Yes | 0-100kW
202512-NM25-02286 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-08614 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-35891 | 2.7 | Residencial | Yes | 0-100kW
202401-NM25-01264 | 5.856 | Residencial | Yes | 0-100kW
2017-GD-01068 | 4 | Residencial | Yes | 0-100kW
202403-NM25-03149 | 8 | Residencial | Yes | 0-100kW
2019-GD-01864 | 18 | Residencial | Yes | 0-100kW
2022-GD-17984 | 8.05 | Residencial | Yes | 0-100kW
2021-GD-14468 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-07607 | 2.75 | Residencial | Yes | 0-100kW
202504-NM25-01353 | 5.124 | Residencial | Yes | 0-100kW
2022-GD-23501 | 5.49 | Residencial | Yes | 0-100kW
202409-NM25-00050 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-28327 | 9.22 | Residencial | Yes | 0-100kW
2023-GD-09514 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-01957 | 7.6 | Residencial | Yes | 0-100kW
14-6-0510 | 6 | Residencial | Yes | 0-100kW
202507-NM25-00509 | 11.5 | Residencial | Yes | 0-100kW
202312-NM25-01276 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02320 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-29768 | 7.32 | Residencial | Yes | 0-100kW
202501-NM25-01431 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-26981 | 5 | Residencial | Yes | 0-100kW
2023-GD-15367 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-23848 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07659 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-34597 | 7.6 | Residencial | No | 0-100kW
2021-GD-06584 | 3.54 | Residencial | Yes | 0-100kW
202406-NM25-03668 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06414 | 8.56 | Residencial | Yes | 0-100kW
2022-GD-25677 | 4.39 | Residencial | Yes | 0-100kW
202406-NM25-03046 | 4.392 | Residencial | Yes | 0-100kW
202504-NM25-04183 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-00362 | 7.6 | Residencial | Yes | 0-100kW
15-9-325 | 4.95 | Residencial | Yes | 0-100kW
2023-GD-22475 | 7.6 | Residencial | No | 0-100kW
2023-GD-09781 | 3.3 | Residencial | Yes | 0-100kW
202406-NM25-00455 | 6.954 | Residencial | Yes | 0-100kW
2023-GD-13227 | 3.8 | Residencial | Yes | 0-100kW
2020-GD-09281 | 5.9 | Residencial | Yes | 0-100kW
202410-NM25-00721 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-26895 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00010 | 8 | Residencial | Yes | 0-100kW
2022-GD-11752 | 3.8 | Residencial | Yes | 0-100kW
202410-NM25-03886 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-33297 | 20.4 | Residencial | Yes | 0-100kW
202508-NM25-00104 | 8 | Residencial | Yes | 0-100kW
2022-GD-25726 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-01364 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-28290 | 5 | Residencial | Yes | 0-100kW
2022-GD-19231 | 4.5 | Residencial | Yes | 0-100kW
2021-GD-10841 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-24606 | 7 | Residencial | Yes | 0-100kW
2021-GD-01668 | 3.5 | Residencial | Yes | 0-100kW
202503-NM25-01908 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-26268 | 7.6 | Residencial | Yes | 0-100kW
15-7-271 | 7 | Residencial | Yes | 0-100kW
202409-NM25-04193 | 4.758 | Residencial | Yes | 0-100kW
2017-GD-01509 | 4.5 | Residencial | Yes | 0-100kW
2020-GD-05853 | 9 | Residencial | Yes | 0-100kW
2022-GD-20503 | 2.97 | Residencial | Yes | 0-100kW
202412-NM25-01743 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-00358 | 3.24 | Residencial | Yes | 0-100kW
202510-NM25-00792 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-00741 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-27684 | 3.84 | Residencial | Yes | 0-100kW
202408-NM25-03671 | 3.8 | Residencial | Yes | 0-100kW
16-2-0391G | 4.3 | Residencial | Yes | 0-100kW
202401-NM25-03385 | 5.124 | Residencial | Yes | 0-100kW
2022-GD-26119 | 5.12 | Residencial | Yes | 0-100kW
2021-GD-11670 | 4.13 | Residencial | Yes | 0-100kW
2022-GD-06188 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-10960 | 4.03 | Residencial | Yes | 0-100kW
202505-NM25-01931 | 8 | Residencial | Yes | 0-100kW
14-5-0356A | 5 | Residencial | Yes | 0-100kW
2023-GD-13523 | 3 | Residencial | Yes | 0-100kW
202501-NM25-03915 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-00179 | 5.5 | Residencial | Yes | 0-100kW
202411-NM25-00926 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-30295 | 3.84 | Residencial | Yes | 0-100kW
2019-GD-02514 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-24930 | 5 | Residencial | Yes | 0-100kW
202403-NM25-01570 | 2.7 | Residencial | Yes | 0-100kW
202412-NM25-03289 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03745 | 3.072 | Residencial | Yes | 0-100kW
15-7-104 | 7.74 | Residencial | Yes | 0-100kW
202508-NM25-03234 | 11.5 | Comercial | Yes | 0-100kW
202505-NM25-00716 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-04867 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-04815 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15037 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-04590 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-16998 | 5.49 | Residencial | Yes | 0-100kW
202507-NM25-01025 | 9.6 | Residencial | Yes | 0-100kW
2020-GD-04064 | 5 | Residencial | Yes | 0-100kW
15-1-101 | 6.8 | Residencial | Yes | 0-100kW
202501-NM25-01825 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-01774 | 7.2 | Residencial | Yes | 0-100kW
202405-NM25-03163 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03799 | 11.5 | Residencial | Yes | 0-100kW
202410-NM25-00545 | 9.15 | Residencial | Yes | 0-100kW
202507-NM25-00163 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-05704 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00790 | 4.224 | Residencial | Yes | 0-100kW
14-3-412 | 9.03 | Residencial | Yes | 0-100kW
202408-NM25-02391 | 6 | Residencial | Yes | 0-100kW
202311-NM25-00600 | 8.052 | Residencial | Yes | 0-100kW
2022-GD-22315 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-10720 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-00230 | 11.5 | Residencial | Yes | 0-100kW
202309-NM25-00191 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-00633 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-12527 | 8.05 | Residencial | Yes | 0-100kW
202506-NM25-01070 | 9 | Residencial | Yes | 0-100kW
2022-GD-22543 | 5.12 | Residencial | Yes | 0-100kW
202512-NM25-04738 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-01756 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-20374 | 6.22 | Residencial | Yes | 0-100kW
202409-NM25-02759 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-04956 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-04627 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-32228 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24468 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-03490 | 5.76 | Residencial | Yes | 0-100kW
202502-NM25-04322 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-10255 | 6.8 | Residencial | Yes | 0-100kW
202504-NM25-02428 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-03871 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-20684 | 9.88 | Residencial | Yes | 0-100kW
2023-GD-04471 | 3.29 | Residencial | Yes | 0-100kW
2019-GD-01953 | 3 | Residencial | Yes | 0-100kW
14-3-245 | 4.8 | Residencial | Yes | 0-100kW
2020-GD-04753 | 7.28 | Residencial | Yes | 0-100kW
2023-GD-20555 | 4.76 | Residencial | Yes | 0-100kW
202412-NM25-03075 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03296 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-07744 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00475 | 8 | Residencial | Yes | 0-100kW
202410-NM25-00502 | 14.4 | Residencial | Yes | 0-100kW
14-7-546 | 99 | Comercial | Yes | 0-100kW
2022-GD-27164 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-30535 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-04927 | 6.95 | Residencial | Yes | 0-100kW
2021-GD-12374 | 3.54 | Residencial | Yes | 0-100kW
2022-GD-09130 | 4.13 | Residencial | Yes | 0-100kW
202504-NM25-05293 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-03765 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03843 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-22056 | 15.2 | Residencial | Yes | 0-100kW
2021-GD-14794 | 5.31 | Residencial | Yes | 0-100kW
2023-GD-15632 | 8.42 | Residencial | Yes | 0-100kW
202408-NM25-04613 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-04175 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-03959 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06127 | 5.61 | Residencial | Yes | 0-100kW
2018-GD-01200 | 15.8 | Residencial | Yes | 0-100kW
202411-NM25-00605 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-36574 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-03541 | 2.688 | Residencial | Yes | 0-100kW
2022-GD-29943 | 9.6 | Residencial | Yes | 0-100kW
202502-NM25-03885 | 3.84 | Residencial | Yes | 0-100kW
202509-NM25-00520 | 5.76 | Residencial | Yes | 0-100kW
14-3-906 | 4.2 | Residencial | Yes | 0-100kW
202408-NM25-01516 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-02038 | 2.562 | Residencial | Yes | 0-100kW
2020-GD-03633 | 8.8 | Residencial | Yes | 0-100kW
2020-GD-04599 | 3 | Residencial | Yes | 0-100kW
202404-NM25-01551 | 10.614 | Residencial | No | 0-100kW
2022-GD-08241 | 3.66 | Residencial | Yes | 0-100kW
202504-NM25-01796 | 11.5 | Residencial | Yes | 0-100kW
202310-NM25-00232 | 15.2 | Residencial | Yes | 0-100kW
2023-GD-09782 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-01228 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-01816 | 5 | Residencial | Yes | 0-100kW
202409-NM25-01818 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-14559 | 4.39 | Residencial | Yes | 0-100kW
2023-GD-02799 | 8.05 | Residencial | Yes | 0-100kW
202411-NM25-02535 | 19.764 | Residencial | Yes | 0-100kW
2023-GD-03778 | 3.66 | Residencial | Yes | 0-100kW
202401-NM25-01624 | 3.66 | Residencial | Yes | 0-100kW
202503-NM25-04103 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17745 | 9.6 | Residencial | Yes | 0-100kW
202401-NM25-03077 | 10 | Residencial | Yes | 0-100kW
202503-NM25-05887 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-01210 | 5.9 | Residencial | Yes | 0-100kW
2020-GD-01949 | 3 | Residencial | Yes | 0-100kW
202505-NM25-00139 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-02288 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-06423 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-27045 | 5 | Residencial | Yes | 0-100kW
2023-GD-12701 | 5 | Residencial | Yes | 0-100kW
202509-NM25-03486 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-08556 | 4.39 | Residencial | Yes | 0-100kW
2017-GD-00188 | 6.235 | Residencial | Yes | 0-100kW
2021-GD-01114 | 8.35 | Residencial | Yes | 0-100kW
202406-NM25-01391 | 8 | Residencial | Yes | 0-100kW
202407-NM25-01067 | 7.6 | Residencial | Yes | 0-100kW
14-4-0154GD | 5.25 | Residencial | Yes | 0-100kW
202410-NM25-01972 | 8 | Residencial | Yes | 0-100kW
202510-NM25-03768 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-01306 | 4.43 | Residencial | Yes | 0-100kW
202508-NM25-00386 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-01992 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-23822 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06955 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-07972 | 4.03 | Comercial | No | 0-100kW
2020-GD-04110 | 5 | Residencial | Yes | 0-100kW
202403-NM25-03064 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-14468 | 8.42 | Residencial | Yes | 0-100kW
202501-NM25-01569 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-04792 | 7.32 | Residencial | Yes | 0-100kW
2023-GD-12657 | 3 | Residencial | Yes | 0-100kW
202506-NM25-02309 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-02370 | 7.6 | Residencial | Yes | 0-100kW
202405-NM25-02193 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-27800 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-21706 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-09559 | 3.8 | Residencial | Yes | 0-100kW
202506-NM25-03893 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-04637 | 6.588 | Residencial | Yes | 0-100kW
2023-GD-38597 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-06765 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-05045 | 3.84 | Residencial | Yes | 0-100kW
202504-NM25-02567 | 15 | Residencial | Yes | 0-100kW
2023-GD-28076 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-03824 | 3.29 | Residencial | Yes | 0-100kW
2021-GD-02979 | 7.32 | Residencial | Yes | 0-100kW
202505-NM25-02915 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-00708 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19673 | 6.95 | Residencial | Yes | 0-100kW
202405-NM25-01237 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-04196 | 5 | Residencial | Yes | 0-100kW
2022-GD-13354 | 5.12 | Residencial | Yes | 0-100kW
2023-GD-02139 | 5.49 | Residencial | Yes | 0-100kW
202512-NM25-04777 | 11.5 | Residencial | Yes | 0-100kW
202408-NM25-02889 | 6 | Residencial | Yes | 0-100kW
202405-NM25-01141 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-31742 | 5.86 | Residencial | Yes | 0-100kW
202507-NM25-03363 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-02119 | 17.934 | Comercial | Yes | 0-100kW
2023-GD-03445 | 5 | Residencial | Yes | 0-100kW
202509-NM25-02560 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-38228 | 8.05 | Residencial | Yes | 0-100kW
202501-NM25-00946 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-03923 | 3.84 | Residencial | Yes | 0-100kW
202504-NM25-03778 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03547 | 4.608 | Residencial | Yes | 0-100kW
2020-GD-08532 | 4 | Residencial | Yes | 0-100kW
202407-NM25-00691 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08916 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-25985 | 3.8 | Residencial | Yes | 0-100kW
202411-NM25-02959 | 4.758 | Residencial | Yes | 0-100kW
2023-GD-01084 | 11.52 | Comercial | Yes | 0-100kW
202404-NM25-00027 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-00633 | 4.224 | Residencial | Yes | 0-100kW
2022-GD-20638 | 5.49 | Residencial | Yes | 0-100kW
202407-NM25-00762 | 9 | Residencial | Yes | 0-100kW
2021-GD-03759 | 6.19 | Residencial | Yes | 0-100kW
202502-NM25-00156 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-06526 | 5 | Residencial | Yes | 0-100kW
2021-GD-02782 | 4.13 | Residencial | Yes | 0-100kW
2022-GD-19216 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02864 | 7.6 | Residencial | Yes | 0-100kW
2017-GD-00370 | 12 | Residencial | Yes | 0-100kW
2022-GD-14082 | 4.03 | Residencial | Yes | 0-100kW
202401-NM25-02374 | 5.49 | Residencial | Yes | 0-100kW
2020-GD-01105 | 3.54 | Residencial | Yes | 0-100kW
202505-NM25-02235 | 11.5 | Residencial | Yes | 0-100kW
2019-GD-35015 | 5 | Residencial | Yes | 0-100kW
2023-GD-01035 | 6.22 | Residencial | Yes | 0-100kW
202512-NM25-04097 | 3.84 | Residencial | Yes | 0-100kW
202510-NM25-01662 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-05274 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-19191 | 5.12 | Residencial | Yes | 0-100kW
15-4-0429GD | 3 | Residencial | Yes | 0-100kW
202403-NM25-00444 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-03018 | 8.052 | Residencial | Yes | 0-100kW
202505-NM25-04754 | 4.224 | Residencial | Yes | 0-100kW
202512-NM25-04796 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20557 | 2.93 | Residencial | Yes | 0-100kW
2020-GD-02665 | 4.75 | Residencial | Yes | 0-100kW
2022-GD-04884 | 5.9 | Comercial | Yes | 0-100kW
202312-NM25-00275 | 15.2 | Residencial | Yes | 0-100kW
202402-NM25-01587 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-00776 | 4.76 | Residencial | Yes | 0-100kW
2021-GD-11228 | 6.49 | Residencial | Yes | 0-100kW
2023-GD-36902 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-30244 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-16255 | 4.39 | Residencial | Yes | 0-100kW
2022-GD-23495 | 4.03 | Residencial | Yes | 0-100kW
202504-NM25-00767 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01612 | 3.8 | Residencial | Yes | 0-100kW
202503-NM25-02739 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-09721 | 7.69 | Residencial | Yes | 0-100kW
202504-NM25-05015 | 11.5 | Residencial | No | 0-100kW
202312-NM25-03215 | 7.6 | Residencial | Yes | 0-100kW
15-3-957 | 3.66 | Residencial | Yes | 0-100kW
202507-NM25-04926 | 11.5 | Residencial | Yes | 0-100kW
202407-NM25-02520 | 5.124 | Residencial | Yes | 0-100kW
202412-NM25-01356 | 8 | Residencial | Yes | 0-100kW
202503-NM25-02164 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01109 | 4.026 | Residencial | Yes | 0-100kW
2022-GD-19608 | 12.81 | Residencial | Yes | 0-100kW
2022-GD-12820 | 9.6 | Residencial | Yes | 0-100kW
2023-GD-31521 | 5 | Residencial | Yes | 0-100kW
202405-NM25-01595 | 10 | Residencial | Yes | 0-100kW
202402-NM25-03740 | 6 | Residencial | Yes | 0-100kW
202406-NM25-03298 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-08399 | 7 | Residencial | Yes | 0-100kW
202409-NM25-01702 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-25092 | 8.78 | Residencial | Yes | 0-100kW
2022-GD-18769 | 9.15 | Residencial | Yes | 0-100kW
202504-NM25-05589 | 11.5 | Residencial | Yes | 0-100kW
202403-NM25-01607 | 2.562 | Residencial | Yes | 0-100kW
2022-GD-32375 | 4.03 | Residencial | Yes | 0-100kW
2017-GD-02654 | 4.5 | Residencial | Yes | 0-100kW
2021-GD-12175 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-30702 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-25026 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-32322 | 15.2 | Residencial | Yes | 0-100kW
202502-NM25-04434 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-03396 | 6.59 | Residencial | Yes | 0-100kW
16-3-131 | 2.8 | Residencial | Yes | 0-100kW
2022-GD-18699 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-18558 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-02336 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-00593 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-01327 | 5.5 | Residencial | Yes | 0-100kW
2023-GD-02951 | 6 | Residencial | Yes | 0-100kW
2021-GD-04997 | 7.67 | Residencial | Yes | 0-100kW
202508-NM25-03925 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-01206 | 4.61 | Residencial | Yes | 0-100kW
202312-NM25-01370 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-07077 | 4.39 | Residencial | Yes | 0-100kW
2019-GD-01418 | 12.5 | Residencial | Yes | 0-100kW
202401-NM25-02909 | 7.6 | Residencial | Yes | 0-100kW
2018-GD-02179 | 7 | Residencial | Yes | 0-100kW
2023-GD-26625 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-01461 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-03892 | 5.9 | Residencial | Yes | 0-100kW
2023-GD-36123 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-16642 | 7.6 | Residencial | No | 0-100kW
2023-GD-33465 | 3.66 | Residencial | Yes | 0-100kW
2021-GD-02001 | 5 | Residencial | Yes | 0-100kW
202411-NM25-00450 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-03832 | 7.68 | Residencial | Yes | 0-100kW
202509-NM25-04589 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-07903 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-29434 | 8.45 | Residencial | Yes | 0-100kW
202406-NM25-02433 | 4.992 | Residencial | Yes | 0-100kW
202410-NM25-01257 | 8 | Residencial | Yes | 0-100kW
202310-NM25-00262 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-13032 | 4.03 | Residencial | Yes | 0-100kW
202312-NM25-00433 | 6 | Residencial | Yes | 0-100kW
2023-GD-29784 | 7.6 | Residencial | Yes | 0-100kW
202311-NM25-00834 | 5.124 | Residencial | Yes | 0-100kW
2021-GD-05379 | 7.67 | Residencial | Yes | 0-100kW
2022-GD-23623 | 5.31 | Residencial | Yes | 0-100kW
2023-GD-12711 | 24 | Comercial | Yes | 0-100kW
202512-NM25-04102 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-03917 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-03366 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-07109 | 3.8 | Residencial | Yes | 0-100kW
202409-NM25-03495 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-35699 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-03562 | 11.5 | Residencial | Yes | 0-100kW
2025-GD-00117 | 66 | Comercial | No | 0-100kW
202404-NM25-03585 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19832 | 6.22 | Residencial | Yes | 0-100kW
2022-GD-32882 | 8.83 | Residencial | Yes | 0-100kW
2023-GD-37864 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-06162 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-02044 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-00206 | 3.25 | Residencial | Yes | 0-100kW
202504-NM25-05573 | 3.072 | Residencial | Yes | 0-100kW
2022-GD-31739 | 5.38 | Residencial | Yes | 0-100kW
2021-GD-08381 | 8.85 | Residencial | Yes | 0-100kW
2021-GD-10539 | 5.31 | Residencial | Yes | 0-100kW
202509-NM25-03247 | 11.5 | Residencial | Yes | 0-100kW
202409-NM25-02549 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-03647 | 7.6 | Residencial | Yes | 0-100kW
202412-NM25-02750 | 3 | Residencial | Yes | 0-100kW
2022-GD-10741 | 8.42 | Residencial | No | 0-100kW
2022-GD-27506 | 21.12 | Residencial | Yes | 0-100kW
2023-GD-22724 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-14316 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-12220 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-34975 | 7.6 | Residencial | Yes | 0-100kW
15-6-0569 | 4.2 | Residencial | Yes | 0-100kW
2023-GD-01198 | 5.38 | Residencial | Yes | 0-100kW
2023-GD-21531 | 7.6 | Residencial | Yes | 0-100kW
202402-NM25-04049 | 7.6 | Residencial | Yes | 0-100kW
202503-NM25-01838 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-06589 | 3.66 | Residencial | Yes | 0-100kW
202510-NM25-00897 | 11.5 | Residencial | Yes | 0-100kW
202505-NM25-05364 | 3.5 | Residencial | Yes | 0-100kW
2022-GD-09268 | 5 | Residencial | Yes | 0-100kW
2023-GD-19692 | 3.66 | Residencial | Yes | 0-100kW
14-5-0023A | 4 | Residencial | Yes | 0-100kW
202401-NM25-02027 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-19404 | 3.84 | Residencial | Yes | 0-100kW
16-2-0683 | 10.64 | Residencial | Yes | 0-100kW
202505-NM25-03152 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-07730 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07057 | 4.43 | Residencial | Yes | 0-100kW
202401-NM25-02907 | 4.026 | Residencial | Yes | 0-100kW
202311-NM25-00255 | 8.052 | Residencial | Yes | 0-100kW
2022-GD-26133 | 4.61 | Residencial | Yes | 0-100kW
2021-GD-08997 | 4.43 | Residencial | Yes | 0-100kW
2020-GD-03598 | 4.72 | Residencial | Yes | 0-100kW
2021-GD-14263 | 5 | Residencial | Yes | 0-100kW
2023-GD-22163 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30408 | 4.2 | Residencial | Yes | 0-100kW
2022-GD-31573 | 4.76 | Residencial | Yes | 0-100kW
2023-GD-04374 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-26619 | 3.84 | Residencial | Yes | 0-100kW
202410-NM25-04153 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-08857 | 5.86 | Residencial | Yes | 0-100kW
2023-GD-04606 | 6.8 | Residencial | Yes | 0-100kW
202505-NM25-04562 | 15 | Residencial | Yes | 0-100kW
202405-NM25-00679 | 6.91 | Residencial | Yes | 0-100kW
202509-NM25-02120 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-07347 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-28853 | 6 | Residencial | Yes | 0-100kW
17-7-0048 | 3.25 | Residencial | Yes | 0-100kW
2022-GD-12266 | 3.8 | Residencial | Yes | 0-100kW
202505-NM25-01907 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-02951 | 5.76 | Residencial | Yes | 0-100kW
202404-NM25-00858 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-03320 | 4.224 | Residencial | Yes | 0-100kW
15-3-777 | 4.51 | Residencial | Yes | 0-100kW
202403-NM25-02604 | 2.196 | Residencial | Yes | 0-100kW
2021-GD-09450 | 3.54 | Residencial | Yes | 0-100kW
202406-NM25-02893 | 9.516 | Residencial | Yes | 0-100kW
202311-NM25-00223 | 4.026 | Residencial | Yes | 0-100kW
202504-NM25-01816 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-34143 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-01681 | 6.8 | Residencial | Yes | 0-100kW
2021-GD-02051 | 4.13 | Residencial | Yes | 0-100kW
2023-GD-25605 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-01289 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02201 | 10.248 | Residencial | Yes | 0-100kW
2022-GD-11224 | 4.76 | Residencial | Yes | 0-100kW
202507-NM25-01964 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-24593 | 6.22 | Residencial | Yes | 0-100kW
202508-NM25-01864 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20036 | 9.15 | Residencial | Yes | 0-100kW
2021-GD-05329 | 2.95 | Residencial | Yes | 0-100kW
202504-NM25-02069 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-15769 | 5 | Residencial | Yes | 0-100kW
202407-NM25-01084 | 15 | Residencial | Yes | 0-100kW
2021-GD-15018 | 3.54 | Residencial | Yes | 0-100kW
2021-GD-03592 | 7.08 | Residencial | Yes | 0-100kW
2022-GD-21723 | 8.42 | Residencial | Yes | 0-100kW
202505-NM25-03299 | 14.208 | Residencial | Yes | 0-100kW
2020-GD-02233 | 5 | Residencial | Yes | 0-100kW
2020-GD-03953 | 7.6 | Residencial | Yes | 0-100kW
202512-NM25-00758 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16419 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26600 | 13.27 | Residencial | Yes | 0-100kW
2020-GD-09445 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-11252 | 9.6 | Comercial | Yes | 0-100kW
202511-NM25-00606 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34733 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-03463 | 4.026 | Residencial | Yes | 0-100kW
202312-NM25-02555 | 15.2 | Residencial | Yes | 0-100kW
202509-NM25-02872 | 3.84 | Residencial | Yes | 0-100kW
202411-NM25-03400 | 15 | Residencial | Yes | 0-100kW
202510-NM25-00852 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-04129 | 3.84 | Residencial | Yes | 0-100kW
202502-NM25-03845 | 7.6 | Residencial | Yes | 0-100kW
202403-NM25-01146 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-04355 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-02619 | 4.608 | Residencial | Yes | 0-100kW
2020-GD-06086 | 3 | Residencial | Yes | 0-100kW
202412-NM25-00099 | 7.6 | Residencial | Yes | 0-100kW
202507-NM25-01343 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31120 | 4.61 | Residencial | Yes | 0-100kW
202501-NM25-03310 | 8 | Residencial | Yes | 0-100kW
2023-GD-31806 | 7.6 | Residencial | Yes | 0-100kW
202410-NM25-04042 | 3.5 | Residencial | Yes | 0-100kW
2023-GD-33116 | 8.2 | Residencial | Yes | 0-100kW
202509-NM25-02608 | 4.608 | Residencial | Yes | 0-100kW
202504-NM25-02327 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-04931 | 11.5 | Residencial | Yes | 0-100kW
202503-NM25-02834 | 8 | Residencial | No | 0-100kW
2021-GD-04265 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-26934 | 10.61 | Residencial | Yes | 0-100kW
202406-NM25-03564 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-07060 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-25251 | 5 | Residencial | Yes | 0-100kW
202502-NM25-01010 | 7.6 | Residencial | Yes | 0-100kW
2019-GD-03206 | 4.425 | Residencial | Yes | 0-100kW
2023-GD-35341 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-03040 | 9.516 | Residencial | Yes | 0-100kW
202404-NM25-02327 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-31656 | 3.8 | Residencial | Yes | 0-100kW
202508-NM25-02051 | 11.5 | Residencial | Yes | 0-100kW
202501-NM25-01373 | 4.425 | Residencial | Yes | 0-100kW
2022-GD-05324 | 4.43 | Residencial | Yes | 0-100kW
202401-NM25-01823 | 3.66 | Residencial | Yes | 0-100kW
202509-NM25-05913 | 7.296 | Residencial | No | 0-100kW
2022-GD-25368 | 5.86 | Residencial | Yes | 0-100kW
202402-NM25-04304 | 6.222 | Residencial | Yes | 0-100kW
2022-GD-10816 | 4.39 | Residencial | Yes | 0-100kW
2019-GD-02358 | 2.36 | Residencial | Yes | 0-100kW
2021-GD-00424 | 4.72 | Residencial | Yes | 0-100kW
15-7-524 | 6.67 | Residencial | Yes | 0-100kW
2022-GD-12745 | 5.12 | Residencial | Yes | 0-100kW
202409-NM25-01296 | 2.196 | Residencial | Yes | 0-100kW
2022-GD-26522 | 4.39 | Residencial | Yes | 0-100kW
14-7-245 | 7.2 | Residencial | Yes | 0-100kW
2017-GD-01785 | 3.5 | Residencial | Yes | 0-100kW
202408-NM25-00339 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-31207 | 8.05 | Residencial | No | 0-100kW
15-1-798 | 4.73 | Residencial | Yes | 0-100kW
2022-GD-22370 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-03113 | 3.25 | Residencial | Yes | 0-100kW
2022-GD-10994 | 5.31 | Residencial | Yes | 0-100kW
2023-GD-07066 | 4.22 | Residencial | Yes | 0-100kW
2023-GD-19302 | 8.42 | Residencial | Yes | 0-100kW
202505-NM25-01579 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-05125 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25543 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-01103 | 3.12 | Residencial | Yes | 0-100kW
2022-GD-19353 | 4 | Residencial | Yes | 0-100kW
14-1-190 | 5 | Residencial | Yes | 0-100kW
2020-GD-02654 | 3.25 | Residencial | Yes | 0-100kW
202405-NM25-02057 | 3.294 | Residencial | Yes | 0-100kW
2023-GD-08415 | 10 | Residencial | Yes | 0-100kW
202310-NM25-00244 | 5.55 | Residencial | Yes | 0-100kW
2023-GD-07907 | 7.6 | Residencial | Yes | 0-100kW
202504-NM25-05674 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-02428 | 4.608 | Residencial | Yes | 0-100kW
2022-GD-21239 | 6.5 | Residencial | Yes | 0-100kW
13-4-0294GD | 3 | Residencial | Yes | 0-100kW
15-3-1073 | 6.02 | Residencial | Yes | 0-100kW
202505-NM25-00305 | 11.5 | Residencial | Yes | 0-100kW
202404-NM25-00552 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21282 | 3.66 | Residencial | Yes | 0-100kW
202401-NM25-01299 | 6.588 | Residencial | Yes | 0-100kW
2023-GD-17488 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02828 | 8.42 | Residencial | Yes | 0-100kW
202508-NM25-03231 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16661 | 6.8 | Residencial | Yes | 0-100kW
202505-NM25-02851 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-04537 | 12 | Residencial | Yes | 0-100kW
2022-GD-14870 | 3.8 | Residencial | Yes | 0-100kW
202310-NM25-00145 | 8.14 | Residencial | Yes | 0-100kW
2021-GD-07554 | 3.54 | Residencial | Yes | 0-100kW
2023-GD-12871 | 3.8 | Residencial | No | 0-100kW
2022-GD-11225 | 4.03 | Residencial | Yes | 0-100kW
202509-NM25-01419 | 9 | Residencial | Yes | 0-100kW
2022-GD-32026 | 9.15 | Residencial | Yes | 0-100kW
202510-NM25-03202 | 11.5 | Residencial | Yes | 0-100kW
202507-NM25-03803 | 9.984 | Residencial | Yes | 0-100kW
2021-GD-08685 | 8.26 | Residencial | Yes | 0-100kW
202504-NM25-01690 | 9.8 | Residencial | Yes | 0-100kW
202410-NM25-02654 | 2.7 | Residencial | No | 0-100kW
2021-GD-12689 | 5.31 | Residencial | Yes | 0-100kW
2023-GD-04760 | 4.61 | Residencial | Yes | 0-100kW
2022-GD-11945 | 9.6 | Residencial | Yes | 0-100kW
202510-NM25-01306 | 7.68 | Residencial | Yes | 0-100kW
2023-GD-29135 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00626 | 4.392 | Residencial | Yes | 0-100kW
2023-GD-15893 | 4.39 | Residencial | Yes | 0-100kW
16-6-0286 | 3.87 | Residencial | Yes | 0-100kW
202501-NM25-05106 | 6.785 | Residencial | Yes | 0-100kW
202410-NM25-03534 | 4.392 | Residencial | Yes | 0-100kW
202509-NM25-02716 | 4.992 | Residencial | Yes | 0-100kW
2022-GD-26824 | 9.6 | Residencial | Yes | 0-100kW
2021-GD-05283 | 3.84 | Residencial | Yes | 0-100kW
202409-NM25-00859 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17686 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-09512 | 4 | Residencial | Yes | 0-100kW
19-7-134GD | 7.08 | Residencial | Yes | 0-100kW
202503-NM25-04915 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-00677 | 9.6 | Comercial | Yes | 0-100kW
2023-GD-31181 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-13517 | 5.86 | Residencial | Yes | 0-100kW
2021-GD-05340 | 4.43 | Residencial | Yes | 0-100kW
202507-NM25-01657 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-10620 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-03170 | 6.49 | Residencial | Yes | 0-100kW
202509-NM25-01971 | 7.6 | Residencial | Yes | 0-100kW
202406-NM25-03301 | 2.562 | Residencial | Yes | 0-100kW
202503-NM25-01591 | 11.5 | Residencial | Yes | 0-100kW
202411-NM25-02331 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-06260 | 3.24 | Residencial | Yes | 0-100kW
202404-NM25-00709 | 4.608 | Residencial | Yes | 0-100kW
202411-NM25-01315 | 5.58 | Residencial | Yes | 0-100kW
202505-NM25-00860 | 11.5 | Residencial | Yes | 0-100kW
202512-NM25-04773 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-27178 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-10731 | 11.4 | Residencial | Yes | 0-100kW
2020-GD-03704 | 5.31 | Residencial | Yes | 0-100kW
2022-GD-11130 | 5 | Residencial | Yes | 0-100kW
202407-NM25-00023 | 12.36 | Residencial | Yes | 0-100kW
202409-NM25-04041 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06754 | 3.24 | Residencial | Yes | 0-100kW
202408-NM25-01695 | 4.608 | Residencial | Yes | 0-100kW
202511-NM25-04269 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-25647 | 5 | Residencial | Yes | 0-100kW
2020-GD-09540 | 4.72 | Residencial | Yes | 0-100kW
2021-GD-00293 | 3.24 | Residencial | Yes | 0-100kW
202407-NM25-01691 | 3.8 | Residencial | Yes | 0-100kW
2021-GD-03510 | 4.15 | Residencial | Yes | 0-100kW
2023-GD-19617 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00590 | 11.5 | Residencial | Yes | 0-100kW
202412-NM25-02446 | 15.2 | Residencial | No | 0-100kW
2020-GD-02318 | 3.25 | Residencial | Yes | 0-100kW
2020-GD-04900 | 6.19 | Residencial | Yes | 0-100kW
202405-NM25-01667 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-22025 | 5.12 | Residencial | Yes | 0-100kW
202511-NM25-03592 | 18 | Residencial | Yes | 0-100kW
2023-GD-01521 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-28413 | 17.7 | Comercial | Yes | 0-100kW
202503-NM25-02926 | 7.6 | Residencial | Yes | 0-100kW
202408-NM25-01282 | 10 | Residencial | Yes | 0-100kW
2017-GD-02854 | 7.86 | Residencial | Yes | 0-100kW
202409-NM25-04268 | 4.608 | Residencial | Yes | 0-100kW
202512-NM25-02204 | 7.6 | Residencial | Yes | 0-100kW
16-7-1183 | 7.74 | Residencial | Yes | 0-100kW
2023-GD-21769 | 3.66 | Residencial | Yes | 0-100kW
202402-NM25-00678 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-00260 | 5.124 | Residencial | Yes | 0-100kW
202412-NM25-03619 | 3.072 | Residencial | Yes | 0-100kW
202408-NM25-03415 | 3.8 | Residencial | Yes | 0-100kW
202408-NM25-03578 | 15.2 | Residencial | Yes | 0-100kW
202401-NM25-04263 | 4.026 | Residencial | Yes | 0-100kW
2021-GD-01676 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-19414 | 4.03 | Residencial | Yes | 0-100kW
202508-NM25-04354 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-17704 | 6.95 | Residencial | Yes | 0-100kW
2022-GD-05270 | 4.13 | Residencial | Yes | 0-100kW
202510-NM25-03738 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05009 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20449 | 6.95 | Residencial | Yes | 0-100kW
202510-NM25-00573 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-12953 | 5.12 | Residencial | Yes | 0-100kW
202507-NM25-00553 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-35532 | 7.6 | Residencial | No | 0-100kW
202411-NM25-00103 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-15704 | 5.01 | Residencial | Yes | 0-100kW
202510-NM25-01595 | 23.76 | Residencial | Yes | 0-100kW
14-7-092 | 8.4 | Residencial | No | 0-100kW
08-1-724 | 9.99 | Residencial | No | 0-100kW
202503-NM25-02219 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-02552 | 4.39 | Residencial | Yes | 0-100kW
2025-GD-00141 | 42 | Comercial | Yes | 0-100kW
2023-GD-02708 | 6.14 | Residencial | Yes | 0-100kW
2023-GD-21329 | 4.76 | Residencial | No | 0-100kW
202312-NM25-01641 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-15456 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-01421 | 4.75 | Residencial | Yes | 0-100kW
202312-NM25-00036 | 4.392 | Residencial | Yes | 0-100kW
202502-NM25-06499 | 7.6 | Residencial | Yes | 0-100kW
10-2-610 | 4 | Residencial | Yes | 0-100kW
2023-GD-25426 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-25182 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-06192 | 6.49 | Residencial | Yes | 0-100kW
2022-GD-02672 | 4.72 | Residencial | Yes | 0-100kW
202411-NM25-00227 | 8 | Residencial | Yes | 0-100kW
14-1-193 | 11 | Residencial | Yes | 0-100kW
202506-NM25-02385 | 8.448 | Residencial | Yes | 0-100kW
2023-GD-23929 | 7.6 | Residencial | Yes | 0-100kW
16-3-847 | 4.25 | Residencial | Yes | 0-100kW
202408-NM25-03516 | 10.98 | Residencial | Yes | 0-100kW
2022-GD-21303 | 4.72 | Residencial | Yes | 0-100kW
202403-NM25-04004 | 3.66 | Residencial | Yes | 0-100kW
2022-GD-14732 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-30174 | 5 | Residencial | Yes | 0-100kW
202409-NM25-03210 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-02265 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-19250 | 3.8 | Residencial | Yes | 0-100kW
2022-GD-04566 | 4.72 | Residencial | Yes | 0-100kW
202505-NM25-04256 | 11.5 | Residencial | Yes | 0-100kW
202504-NM25-04071 | 7.68 | Comercial | Yes | 0-100kW
2023-GD-10702 | 3.84 | Residencial | Yes | 0-100kW
202502-NM25-04918 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-39057 | 9.52 | Residencial | Yes | 0-100kW
202409-NM25-04240 | 5 | Comercial | Yes | 0-100kW
2022-GD-32229 | 4.03 | Residencial | Yes | 0-100kW
202312-NM25-00969 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-02659 | 5.31 | Residencial | Yes | 0-100kW
202408-NM25-01749 | 5 | Residencial | Yes | 0-100kW
202402-NM25-03172 | 7.6 | Residencial | Yes | 0-100kW
202508-NM25-04364 | 16.25 | Residencial | Yes | 0-100kW
2022-GD-08111 | 4.03 | Residencial | Yes | 0-100kW
2020-GD-07656 | 13.91 | Residencial | Yes | 0-100kW
2022-GD-03651 | 4.43 | Residencial | Yes | 0-100kW
2021-GD-11290 | 5.49 | Residencial | Yes | 0-100kW
2023-GD-01897 | 4.22 | Residencial | Yes | 0-100kW
2021-GD-15498 | 5.9 | Residencial | Yes | 0-100kW
202406-NM25-01079 | 8 | Residencial | No | 0-100kW
2022-GD-02833 | 3.84 | Residencial | Yes | 0-100kW
2023-GD-30705 | 3.66 | Residencial | Yes | 0-100kW
2018-GD-00717 | 3.84 | Residencial | Yes | 0-100kW
2022-GD-03669 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00255 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05385 | 11.5 | Residencial | Yes | 0-100kW
202509-NM25-00580 | 11.5 | Residencial | Yes | 0-100kW
202511-NM25-03065 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-33612 | 9.88 | Residencial | Yes | 0-100kW
202505-NM25-01715 | 11.5 | Residencial | Yes | 0-100kW
202502-NM25-04031 | 5.856 | Residencial | Yes | 0-100kW
202509-NM25-05484 | 7.6 | Comercial | Yes | 0-100kW
2023-GD-03273 | 6.95 | Residencial | Yes | 0-100kW
202502-NM25-02120 | 19.2 | Residencial | Yes | 0-100kW
202410-NM25-00389 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-01026 | 9 | Residencial | Yes | 0-100kW
2019-GD-02166 | 4.15 | Residencial | Yes | 0-100kW
15-2-693 | 2.79 | Residencial | Yes | 0-100kW
202508-NM25-01120 | 11.5 | Residencial | Yes | 0-100kW
2017-GD-00788 | 2.58 | Residencial | No | 0-100kW
202312-NM25-01258 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-02890 | 2.304 | Residencial | Yes | 0-100kW
2021-GD-07566 | 6.49 | Residencial | Yes | 0-100kW
2017-GD-03373 | 3.87 | Residencial | Yes | 0-100kW
2023-GD-18118 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-32518 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-01288 | 7.69 | Residencial | No | 0-100kW
2023-GD-24136 | 15 | Residencial | Yes | 0-100kW
202506-NM25-01846 | 6 | Residencial | Yes | 0-100kW
2022-GD-19799 | 6.95 | Residencial | Yes | 0-100kW
202504-NM25-05006 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-01858 | 8.418 | Residencial | Yes | 0-100kW
202504-NM25-05318 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31451 | 5.86 | Residencial | Yes | 0-100kW
202507-NM25-03072 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-04952 | 4.72 | Residencial | Yes | 0-100kW
202503-NM25-02919 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-00140 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-03632 | 7.6 | Residencial | Yes | 0-100kW
202505-NM25-03520 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-06652 | 3.24 | Residencial | Yes | 0-100kW
2021-GD-05616 | 5.9 | Residencial | Yes | 0-100kW
202407-NM25-01512 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05894 | 4.72 | Residencial | Yes | 0-100kW
202512-NM25-00902 | 11.5 | Residencial | Yes | 0-100kW
16-3-482 | 4.5 | Residencial | Yes | 0-100kW
202502-NM25-05117 | 8 | Residencial | Yes | 0-100kW
2022-GD-24468 | 5.76 | Residencial | Yes | 0-100kW
202504-NM25-05401 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-07818 | 6.84 | Residencial | Yes | 0-100kW
202501-NM25-00992 | 10.368 | Residencial | Yes | 0-100kW
202507-NM25-03871 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-21247 | 5 | Residencial | Yes | 0-100kW
202407-NM25-03301 | 7.6 | Residencial | Yes | 0-100kW
202311-NM25-00903 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-02620 | 6.222 | Residencial | Yes | 0-100kW
202403-NM25-01260 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-06743 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-04701 | 9.6 | Residencial | Yes | 0-100kW
202509-NM25-00139 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-20884 | 5.12 | Residencial | Yes | 0-100kW
2018-GD-01444 | 4.3 | Residencial | Yes | 0-100kW
202508-NM25-04807 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-00328 | 7.6 | Residencial | Yes | 0-100kW
202502-NM25-04004 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-34478 | 4.03 | Residencial | Yes | 0-100kW
05-3-278A | 27 | Comercial | Yes | 0-100kW
202506-NM25-03110 | 3.84 | Residencial | Yes | 0-100kW
202401-NM25-03375 | 4.026 | Residencial | Yes | 0-100kW
2023-GD-01331 | 9.6 | Residencial | Yes | 0-100kW
2022-GD-13447 | 4.76 | Residencial | Yes | 0-100kW
202404-NM25-02452 | 19.032 | Comercial | Yes | 0-100kW
2022-GD-30904 | 6.8 | Residencial | Yes | 0-100kW
202501-NM25-05147 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-01719 | 16 | Residencial | Yes | 0-100kW
202403-NM25-00655 | 5 | Residencial | Yes | 0-100kW
2022-GD-12722 | 7.97 | Residencial | Yes | 0-100kW
202503-NM25-01898 | 7.7 | Residencial | Yes | 0-100kW
202406-NM25-02093 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-00486 | 7.03 | Residencial | Yes | 0-100kW
15-7-281 | 4.3 | Residencial | Yes | 0-100kW
202408-NM25-03639 | 8 | Residencial | Yes | 0-100kW
202408-NM25-01426 | 7.6 | Residencial | Yes | 0-100kW
202506-NM25-00101 | 15.2 | Residencial | Yes | 0-100kW
202505-NM25-00043 | 11.5 | Residencial | Yes | 0-100kW
2021-GD-00575 | 4.43 | Residencial | Yes | 0-100kW
2022-GD-30357 | 5 | Residencial | Yes | 0-100kW
202503-NM25-00822 | 11.5 | Residencial | Yes | 0-100kW
2022-GD-08287 | 3.8 | Residencial | Yes | 0-100kW
202511-NM25-01180 | 3.84 | Residencial | Yes | 0-100kW
202311-NM25-00023 | 4.758 | Residencial | Yes | 0-100kW
202402-NM25-04239 | 3.294 | Residencial | Yes | 0-100kW
13-3-015 | 5.8 | Residencial | Yes | 0-100kW
2019-GD-00196 | 14 | Residencial | Yes | 0-100kW
202403-NM25-01563 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-03195 | 3.294 | Residencial | Yes | 0-100kW
2021-GD-08324 | 3.54 | Residencial | Yes | 0-100kW
2020-GD-05744 | 3.75 | Residencial | Yes | 0-100kW
2021-GD-04407 | 5.12 | Residencial | Yes | 0-100kW
202411-NM25-02846 | 3.66 | Residencial | Yes | 0-100kW
2020-GD-07011 | 4.72 | Residencial | Yes | 0-100kW
2022-GD-14604 | 6.59 | Residencial | Yes | 0-100kW
202509-NM25-04797 | 7.6 | Residencial | Yes | 0-100kW
202401-NM25-00747 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-07555 | 7.67 | Residencial | Yes | 0-100kW
202504-NM25-01308 | 12 | Residencial | Yes | 0-100kW
202512-NM25-04249 | 15.5 | Residencial | Yes | 0-100kW
202503-NM25-02594 | 7.6 | Residencial | Yes | 0-100kW
202407-NM25-04298 | 3.84 | Residencial | Yes | 0-100kW
202408-NM25-03340 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-01740 | 9 | Residencial | Yes | 0-100kW
202506-NM25-01789 | 5 | Residencial | Yes | 0-100kW
2021-GD-02377 | 3.84 | Residencial | Yes | 0-100kW
11-1-398 | 4.05 | Residencial | Yes | 0-100kW
202412-NM25-03996 | 0.366 | Residencial | Yes | 0-100kW
2021-GD-09413 | 7.67 | Residencial | Yes | 0-100kW
2022-GD-32039 | 4.03 | Residencial | Yes | 0-100kW
202510-NM25-02591 | 7.6 | Residencial | Yes | 0-100kW
202409-NM25-01125 | 5.61 | Residencial | Yes | 0-100kW
2023-GD-22284 | 5.86 | Residencial | Yes | 0-100kW
2021-GD-07429 | 5.9 | Residencial | Yes | 0-100kW
202407-NM25-03831 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-02053 | 4.41 | Residencial | Yes | 0-100kW
2021-GD-12567 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-26216 | 5.49 | Residencial | Yes | 0-100kW
2022-GD-17140 | 5.12 | Residencial | Yes | 0-100kW
15-5-0009A | 2.5 | Residencial | Yes | 0-100kW
202404-NM25-03097 | 9.882 | Residencial | Yes | 0-100kW
2022-GD-11250 | 2.66 | Residencial | Yes | 0-100kW
202404-NM25-04231 | 16.5 | Comercial | Yes | 0-100kW
2023-GD-02825 | 7.32 | Residencial | No | 0-100kW
2022-GD-01567 | 8.85 | Comercial | Yes | 0-100kW
202503-NM25-00074 | 7.66 | Residencial | Yes | 0-100kW
2023-GD-32988 | 7.6 | Residencial | Yes | 0-100kW
2021-GD-05677 | 6.8 | Residencial | Yes | 0-100kW
2022-GD-10260 | 3.84 | Residencial | No | 0-100kW
2021-GD-13754 | 6.8 | Residencial | Yes | 0-100kW
202504-NM25-06016 | 11.5 | Residencial | Yes | 0-100kW
2020-GD-01151 | 7.08 | Residencial | Yes | 0-100kW
202409-NM25-03679 | 7.6 | Residencial | Yes | 0-100kW
202510-NM25-02047 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-03161 | 4.03 | Residencial | Yes | 0-100kW
2023-GD-14147 | 3.8 | Residencial | Yes | 0-100kW
202512-NM25-02192 | 11.5 | Residencial | Yes | 0-100kW
202510-NM25-00779 | 4.608 | Residencial | Yes | 0-100kW
202501-NM25-05743 | 7.6 | Residencial | Yes | 0-100kW
202501-NM25-05484 | 11.4 | Residencial | Yes | 0-100kW
202502-NM25-04832 | 7.7 | Residencial | Yes | 0-100kW
2023-GD-12669 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-32693 | 6.59 | Residencial | Yes | 0-100kW
202511-NM25-03919 | 3.072 | Residencial | Yes | 0-100kW
202410-NM25-00210 | 3.456 | Residencial | Yes | 0-100kW
202503-NM25-04536 | 11.5 | Residencial | Yes | 0-100kW
16-1-642 | 10 | Residencial | Yes | 0-100kW
2020-GD-07024 | 4 | Residencial | Yes | 0-100kW
2021-GD-09175 | 3.54 | Residencial | Yes | 0-100kW
202407-NM25-04470 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-31519 | 3.84 | Residencial | Yes | 0-100kW
202407-NM25-00064 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-24967 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-08485 | 9.15 | Residencial | Yes | 0-100kW
202408-NM25-03805 | 9.6 | Residencial | Yes | 0-100kW
202510-NM25-00370 | 11.5 | Residencial | Yes | 0-100kW
202406-NM25-01092 | 3.8 | Residencial | Yes | 0-100kW
2023-GD-31096 | 4.39 | Residencial | Yes | 0-100kW
2021-GD-02237 | 4.43 | Residencial | Yes | 0-100kW
202510-NM25-00502 | 11.5 | Residencial | Yes | 0-100kW
202506-NM25-00915 | 16 | Residencial | Yes | 0-100kW
2022-GD-05465 | 7.6 | Residencial | Yes | 0-100kW
202312-NM25-00187 | 8.784 | Residencial | Yes | 0-100kW
2023-GD-20418 | 4.62 | Residencial | Yes | 0-100kW
2023-GD-05553 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-03683 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-16298 | 6.8 | Residencial | Yes | 0-100kW
202405-NM25-00894 | 3.84 | Residencial | Yes | 0-100kW
202505-NM25-02589 | 15 | Residencial | Yes | 0-100kW
202411-NM25-02310 | 3.8 | Residencial | Yes | 0-100kW
202507-NM25-00199 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-32440 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-12423 | 7.6 | Residencial | Yes | 0-100kW
202411-NM25-00518 | 4.392 | Residencial | Yes | 0-100kW
202504-NM25-01220 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-02665 | 3.54 | Residencial | Yes | 0-100kW
202508-NM25-00480 | 11.5 | Residencial | Yes | 0-100kW
2023-GD-09991 | 7.32 | Residencial | Yes | 0-100kW
2022-GD-28115 | 8.42 | Residencial | Yes | 0-100kW
2023-GD-03796 | 3.84 | Residencial | Yes | 0-100kW
15-6-0278 | 53.1 | Comercial | Yes | 0-100kW
2022-GD-31281 | 5.86 | Residencial | Yes | 0-100kW
2021-GD-01924 | 5.9 | Residencial | Yes | 0-100kW
16-5-0723A | 2.37 | Residencial | Yes | 0-100kW
15-7-210 | 6.25 | Residencial | Yes | 0-100kW
2023-GD-18122 | 7.6 | Residencial | Yes | 0-100kW
2023-GD-25634 | 7.6 | Residencial | Yes | 0-100kW
2022-GD-21121 | 9.15 | Residencial | Yes | 0-100kW
2023-GD-35659 | 3.66 | Residencial | Yes | 0-100kW
2023-GD-19046 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01087 | 4.758 | Residencial | Yes | 0-100kW
202411-NM25-00585 | 7.6 | Residencial | Yes | 0-100kW
202509-NM25-05683 | 12 | Residencial | Yes | 0-100kW
2021-GD-01260 | 3.24 | Residencial | Yes | 0-100kW
2022-GD-32546 | 3.29 | Residencial | Yes | 0-100kW
202507-NM25-01201 | 15.2 | Residencial | Yes | 0-100kW
202512-NM25-04903 | 11.5 | Residencial | Yes | 0-100kW
202402-NM25-03718 | 3.84 | Residencial | Yes | 0-100kW
202506-NM25-01659 | 7.6 | Residencial | Yes | 0-100kW
202404-NM25-01809 | 7.6 | Residencial | Yes | 0-100kW
2020-GD-02631 | 4.25 | Residencial | Yes | 0-100kW
2022-GD-13154 | 19.4 | Residencial | Yes | 0-100kW